## List of issued work order (Rs.
List of issued work order (Rs. in Lakh)
Sl No. | District | Division | Scheme | Scheme Category | Work Name | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Nadia Division | Providing Functional House Tap Connection from Elangi Zone-II Water Supply Scheme (Phase-I) of Retrofitting under Jal Swapno Programme in Nadia District , SM/08128 | Retrofitting | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Fulia Township W/S Scheme in Santipur Block of Nadia District under Nadia Division, P.H.E. Dte. | 1057/RSD | 02/12/2021 | 30 | HORIZEN | 3.31 | 3.18 | 96.03 | 0
2 | NADIA | Nadia Division | Providing Functional House Tap Connection from Elangi Zone-II Water Supply Scheme (Phase-I) of Retrofitting under Jal Swapno Programme in Nadia District , SM/08128 | Retrofitting | Material Requisition To Resource Division | 1034/ND | 03/03/2022 | 0 | Resource Division | 1.94 | 0 | 0 | 0
3 | NADIA | Nadia Division | Providing Functional House Tap Connection from Elangi Zone-II Water Supply Scheme (Phase-I) of Retrofitting under Jal Swapno Programme in Nadia District , SM/08128 | Retrofitting | Material Requisition To Resource Division | 432/ND | 31/01/2022 | 0 | Resource Division | 0.6 | 0 | 0 | 0
4 | NADIA | Nadia Division | Providing Functional House Tap Connection from Elangi Zone-II Water Supply Scheme (Phase-I) of Retrofitting under Jal Swapno Programme in Nadia District , SM/08128 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 0.18 | 100 | 81
5 | NADIA | Nadia Division | Providing Functional House Tap Connection from Elangi Zone-II Water Supply Scheme (Phase-I) of Retrofitting under Jal Swapno Programme in Nadia District , SM/08128 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Elangi Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | 2910/ND | 23/07/2021 | 60 | CHOWDHURY CONSTRUCTION | 36.18 | 30.83 | 85.22 | 100
6 | NADIA | Nadia Division | Providing Functional House Tap Connection from Elangi Zone-II Water Supply Scheme (Phase-I) of Retrofitting under Jal Swapno Programme in Nadia District , SM/08128 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Elangi Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | 2911/ND | 23/07/2021 | 60 | CHOWDHURY CONSTRUCTION | 36.15 | 30.8 | 85.21 | 100
7 | NADIA | Nadia Division | Providing Functional House Tap Connection from Elangi Zone-II Water Supply Scheme (Phase-I) of Retrofitting under Jal Swapno Programme in Nadia District , SM/08128 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Elangi Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | 2392/ND | 10/06/2021 | 45 | A.K.ADHIKARY | 8.44 | 16.46 | 195.13 | 100
8 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-II within Krishnagar-II, Nabadwip (Part) Block (Phase-B) , SM/07433 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-II, within Krishnagar-II & Nabadwip Block (Phase-B, Retrofitting)" | 773/ND | 10/02/2021 | 90 | M/S S.S ENTERPRISE | 96.42 | 136.86 | 141.93 | 0
9 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IV, (Uttar Duttapara), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07444 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IV, (Uttar Duttapara), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl No.- 02) Tender No.- 211/NAD-I/2020-2021. | 282/NAD-I | 03/02/2021 | 90 | MONDAL ENTERPRISE | 93.33 | 184.52 | 115.35 | 100
10 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-II Part-II, at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme , SM/08020 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur-Krishnapur, Zone-II, Part-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Halalpur-Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 768/NAD-I | 04/05/2021 | 60 | MALI CONSTRUCTION | 34.25 | 67.61 | 100 | 100
11 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- A) , SM/07419 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME NORTHERN SECTOR PART-I,ZONE-VI,WITHIN KALIGANJ BLOCK PHASE-A | 82/PPMS | 15/07/2021 | 0 | M/S ASOKE GHOSH & BROTHER | 30.57 | 0 | 0 | 0
12 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- A) , SM/07419 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- A) |  | 12/04/2021 | 0 | M/S ASOKE GHOSH & BROTHER | 30.57 | 0 | 0 | 0
13 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- A) , SM/07419 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- A) | 08/PFMS | 26/04/2022 | 0 | M/S ASOKE GHOSH & BROTHER | 49.45 | 0 | 0 | 0
14 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- A) , SM/07419 | Retrofitting | Laying of pipeline at Kaliganj Bazar under Kaliganj G.P under Zone -VI of Surface Water Based Water Supply Scheme, Nadia District Northern Sector (Part-I) under Debagram Sub Division P.H.E Dte.(S.I. No - 04.) | 586/DSD | 31/12/2021 | 30 | AVINABA ENGINEERING CONCERN | 0.49 | 0.47 | 96.5 | 0
15 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- A) , SM/07419 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block ( Phase -A) | 4088/ND | 31/12/2020 | 90 | M/S ASOKE GHOSH & BROTHER | 96.89 | 5.18 | 100 | 100
16 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- A) , SM/07419 | Retrofitting | Material Requisition To Resource Division | 308/ND | 15/01/2024 | 0 | Resource Division | 2.02 | 0 | 0 | 0
17 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- A) , SM/07419 | Retrofitting | Material Requisition To Resource Division | 309/ND | 15/01/2024 | 0 | Resource Division | 1.52 | 0 | 0 | 0
18 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- A) , SM/07419 | Retrofitting | Material Requisition To Resource Division | 310/ND | 15/01/2024 | 0 | Resource Division | 5.69 | 0 | 0 | 0
19 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-A) , SM/07459 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-A) | 276/PFMS | 08/10/2021 | 0 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 47.85 | 0 | 0 | 0
20 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-A) , SM/07459 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-A) | 566/PFMS | 25/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.46 | 0 | 0 | 0
21 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-A) , SM/07459 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block ( Phase -A) | 240/ND | 15/01/2021 | 90 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 97 | 92.19 | 95.04 | 0
22 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, (Subarnapur), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07448 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, (Subarnapur), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl No.- 4) tender No. - 215/NAD-I/2020-2021. | 284/NAD-I | 03/02/2021 | 90 | SINGHA ROY & CO. | 97.07 | 191.72 | 113.05 | 100
23 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-A) , SM/08135 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-IX within Nakashipara Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte.(SL.1) | 354/PFMS | 08/12/2021 | 0 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 87.39 | 0 | 0 | 0
24 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-A) , SM/08135 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-IX within Nakashipara Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte.(SL.1) | 865/ND | 18/02/2021 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 96.79 | 0 | 0 | 0
25 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-A) , SM/08135 | Retrofitting | Material Requisition To Resource Division | 4304/ND | 29/09/2022 | 0 | Resource Division | 12.27 | 0 | 0 | 0
26 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) , SM/08136 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) |  | 04/10/2021 | 0 | ORIENT CONSTRUCTION | 62.5 | 0 | 0 | 0
27 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) , SM/08136 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) | 291/PFMS | 08/10/2021 | 0 | ORIENT CONSTRUCTION | 62.5 | 0 | 0 | 0
28 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) , SM/08136 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) | 491/PFMS | 03/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.71 | 0 | 0 | 0
29 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) , SM/08136 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) | 489PFMS | 03/02/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 0.43 | 0 | 0 | 0
30 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) , SM/08136 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block ( Phase -B) in Nadia District under Nadia Division P.H.E. Dte. SL.No.2 | 890/ND | 19/02/2021 | 90 | ORIENT CONSTRICTION | 96.79 | 26.67 | 100 | 0
31 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) , SM/08136 | Retrofitting | Material Requisition To Resource Division | 4274/ND | 29/09/2022 | 0 | Resource Division | 12.5 | 0 | 0 | 0
32 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) , SM/08136 | Retrofitting | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4588/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 0 | 0 | 19
33 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshin Jhikipota Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08055 | Retrofitting | Providing Functional House Tap Connection from Dakshin Jhikipota Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | 284/PFMS | 08/10/2021 | 0 | SREEMA ENTERPRISE | 6.5 | 0 | 0 | 0
34 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshin Jhikipota Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08055 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Dakshin Jhitkipota Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | 2909/ND | 23/07/2021 | 75 | AMARENDRANATH PANDEY | 40.18 | 28.87 | 100 | 0
35 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshin Jhikipota Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08055 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Dakshin Jhitkipota Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | 2053/ND | 13/05/2021 | 45 | SREEMA ENTERPRISE | 9.72 | 2.82 | 100 | 0
36 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshin Jhikipota Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08055 | Retrofitting | Material Requisition To Resource Division | 1028/ND | 03/03/2022 | 0 | Resource Division | 10.98 | 0 | 0 | 0
37 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshin Jhikipota Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08055 | Retrofitting | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.10.2023 to 30.11.2023 | 1034/KLYSD-I | 29/09/2023 | 30 | SUMAN CHAKRABORTY | 4.89 | 4.2 | 100 | 100
38 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshin Jhikipota Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08055 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Dakshin Jhitkipota Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | 2052/ND | 13/05/2021 | 60 | H I ENTERPRISE | 42.6 | 65.58 | 153.97 | 100
39 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VII, (Kumarpur), Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07898 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VII, (Kumarpur), Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. Tender No.- 202/NAD-I/2020-2021. | 156/NAD-I | 25/01/2021 | 60 | TAPU SAHA | 84.28 | 165.46 | 144.4 | 100
40 | NADIA | Nadia Division | Providing Functional House Tap Connection from Sonda (Zone-II) Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07487 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT SONDA Z-1 | 459/DW | 30/03/2021 | 0 | BIDYUT KUMAR | 17.23 | 0 | 0 | 0
41 | NADIA | Nadia Division | Providing Functional House Tap Connection from Sonda (Zone-II) Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07487 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Sonda (Zone-II) W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Phase-I, Retrofitting) | 4041/ND | 30/12/2020 | 60 | BIDYUT KUMAR | 20.48 | 0 | 0 | 0
42 | NADIA | Nadia Division | Providing Functional House Tap Connection from Sonda (Zone-II) Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07487 | Retrofitting | Material Requisition To Resource Division | 790/ND | 18/02/2022 | 0 | Resource Division | 0.3 | 0 | 0 | 0
43 | NADIA | Nadia Division | Providing Functional House Tap Connection from Sonda (Zone-I) Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07488 | Retrofitting | Material Requisition To Resource Division | 811/ND | 18/02/2022 | 0 | Resource Division | 1.19 | 0 | 0 | 0
44 | NADIA | Nadia Division | Providing Functional House Tap Connection from Sonda (Zone-I) Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07488 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Sonda (Zone-I) W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Phase-I, Retrofitting). | 47/ND | 06/01/2021 | 90 | TARUN KUMAR BHATTACHARYA | 93.83 | 65.53 | 85.61 | 0
45 | NADIA | Nadia Division | Providing Functional House Tap Connection from Sonda (Zone-I) Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07488 | Retrofitting | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.10.2023 to 30.11.2023 | 1034/KLYSD-I | 29/09/2023 | 30 | SUMAN CHAKRABORTY | 4.89 | 0.49 | 100 | 100
46 | NADIA | Nadia Division | Providing Functional House Tap Connection from Sonda (Zone-I) Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07488 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 18.98 | 100 | 81
47 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-VII within Nakashipara Block (Phase-A). , SM/07496 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VII within Nakashipara Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte.(SL.6) | 869/ND | 18/02/2021 | 90 | ALOKE ENTERPRISE | 97.09 | 81.15 | 83.57 | 0
48 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-VII within Nakashipara Block (Phase-A). , SM/07496 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 1.12 | 100 | 81
49 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (PURBA BISHNUPUR), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme , SM/07903 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Dhara/Jal Swapna for Zone-V, (Purba Bishnupur) Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte (Sl. NO. 04) Tender No. 218/NAD-I/2020-2021. | 311/NAD-I | 08/02/2021 | 90 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 97.1 | 165.71 | 115.63 | 100
50 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (PURBA BISHNUPUR), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme , SM/07903 | Retrofitting | Retrofitting work for Purba Bishnupur Zone -V of Surface Water Based PWSS for Chakdah Part Water Supply Scheme under Office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte.( Sl.no. 06) | 1473/NAD-I | 22/08/2022 | 60 | APURBA MANDAL | 1.77 | 1.55 | 87.75 | 0
51 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Betbaria water supply scheme under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07940 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Betberia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1065/NACD-II | 25/09/2020 | 15 | NAMDAR ALI | 4.99 | 0 | 0 | 0
52 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I , SM/09090 | Retrofitting | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I | 617/PFMS | 14/03/2022 | 0 | UMWELT ENGINEERS PVT LTD | 3.94 | 0 | 0 | 0
53 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I , SM/09090 | Retrofitting | Providing (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Paschim Bhatjangla Zone -I water supply scheme in Nadia District under Nadia Division PHE Dte. | 336/ND | 25/01/2022 | 90 | PUSPA ENTERPRISE | 314.25 | 274.73 | 100 | 95
54 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I , SM/09090 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | 2152/ND | 21/05/2021 | 60 | ORIENT CONSTRUCTION | 42.68 | 12.75 | 200 | 100
55 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I , SM/09090 | Retrofitting | laying of distribution pipe line75mm dia and 63 mm dia UPVC pipe etc. for Providing functional household tap connection at Paschim Bhatjangla zone- I W/S scheme (Part - A) under Nadia Division P.H.E. Dte. | 1070/PH | 04/10/2021 | 15 | ORIENT CONSTRUCTION | 4.79 | 4.79 | 100 | 100
56 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I , SM/09090 | Retrofitting | Construction Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 31.00 cum/hr at Paschim Bhatjangla water supply scheme including 3 Months Trial Run & 3 Years O&M within Krishnagar-I block under RWS Nadia Sub-division under Nadia Division, P.H.E. Dte | 1251/ND | 22/02/2024 | 180 | APURBA MANDAL | 163.44 | 0 | 0 | 45
57 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I , SM/09090 | Retrofitting | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Paschim Bhatjangla Zone-I PWSS within Krishnagar-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 4073/ND | 26/07/2024 | 445 | SANDIP BISWAS | 148.49 | 0 | 0 | 70
58 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I , SM/09090 | Retrofitting | Repair and renovation works of R.C.C. Elevated Reservoir, Pump House, Boundary Wall and Construction of Service Road for Paschim Bhatjangla Zone-I Water Supply Scheme under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 543/ND | 24/01/2024 | 611 | G.S. CONSTRUCTION & CO | 39.9 | 4.67 | 11.7 | 60
59 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I , SM/09090 | Retrofitting | Sinking of 1 No. Big Dia Tubewell 300mm. x 200mm & 200 mtr deep by Direct Rotary Rig Method using PVC pipe & UPVC deep well screen (RDS) pipes with Ribs etc. including inter connection of Rising Main System for Paschim Bhatjangla Zone-II Water Supply Scheme at Head Work Site under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 5035/ND | 13/09/2024 | 45 | ZEST INFRACON | 16.29 | 0 | 0 | 60
60 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Tarapur, Part-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Tarapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08816 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Tarapur, Part-II, at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Tarapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1421/NAD-I | 08/11/2021 | 60 | M/S ASHA CONSTRUCTION | 77.3 | 73.4 | 100 | 100
61 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Muragachha Zone-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08818 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara/Jal Swapna for Muragachha Zone-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) | 497/NAD-I | 22/03/2022 | 60 | DIVINE | 144.2 | 144.13 | 100 | 100
62 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Garapota, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Hanskhali Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08824 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Garapota, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Garapota Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1410/NAD-I | 08/11/2021 | 60 | B.M. ENGINEERING & CONSTRUCTION | 86.04 | 84.75 | 100 | 100
63 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Garapota, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Hanskhali Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08824 | Retrofitting | Material Requisition To Resource Division | 140/NAD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0 | 0
64 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Garapota, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Hanskhali Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08824 | Retrofitting | Laying of additional pipelines at Node Point 27 to 32 at Garapota W/S Scheme under JJM within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte | 185/AE-II/NAD-I | 09/08/2024 | 7 | M/S ADIL CONSTRUCTION | 0.92 | 0.91 | 100 | 100
65 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Garapota, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Hanskhali Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08824 | Retrofitting | Interconnection between Common Manifold and distribution main at Bhayna Zone-I W/S Scheme under JJM in connection with Garapota and Bhayna W/S Scheme within Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (Sl. no. 03) | 1501/NAD-I | 18/09/2024 | 45 | B.S. ENTERPRISE | 19.54 | 8.1 | 100 | 100
66 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Garapota, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Hanskhali Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08824 | Retrofitting | Laying of additional pipelines and reconnection of damages FHTC at Garapota W/S Scheme under JJM within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. | 184/AE-II/NAD-I | 09/08/2024 | 7 | M/S ADIL CONSTRUCTION | 0.93 | 0.93 | 100 | 100
67 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Garapota, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Hanskhali Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08824 | Retrofitting | Laying of additional; pipelines at Garapota W/S Scheme under JJM within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. | 183/AE-II/NAD-I | 09/08/2024 | 7 | M/S ADIL CONSTRUCTION | 0.92 | 0.92 | 100 | 100
68 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IV, (Uttar Duttapara), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arseni , SM/08837 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IV, (Uttar Duttapara), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 49/NAD-I | 11/01/2022 | 90 | KINGS AND CO | 223.23 | 223.17 | 100 | 100
69 | NADIA | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/09041 | Retrofitting | Providing Functional House Tap Connection from Naserkuli Zone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | 42/PFMS | 27/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 0.49 | 0 | 0 | 0
70 | NADIA | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/09041 | Retrofitting | Providing Functional House Tap Connection from Naserkuli Zone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | 57/PFMS | 22/06/2022 | 0 | S.S. ENTERPRISE | 12.54 | 0 | 0 | 0
71 | NADIA | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/09041 | Retrofitting | Providing Functional House Tap Connection from Naserkuli Zone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | 41/PFMS | 27/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.2 | 0 | 0 | 0
72 | NADIA | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/09041 | Retrofitting | Material Requisition To Resource Division | 439/ND | 31/01/2022 | 0 | Resource Division | 1.19 | 0 | 0 | 0
73 | NADIA | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/09041 | Retrofitting | Material Requisition To Resource Division | 430/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0 | 0
74 | NADIA | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/09041 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Naserkuli Zone-II W/S scheme in Nadia District under Nadia Division P.H.E. Dte. | 5689/ND | 03/11/2021 | 90 | S.S. ENTERPRISE | 87.5 | 61.9 | 70.74 | 100
75 | NADIA | Nadia Division | Providing Functional House Tap Connection from Murutia WaterSupply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/09045 | Retrofitting | Providing Functional House Tap Connection from Murutia WaterSupply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | 606/PFMS | 11/03/2022 | 0 | OTHERS | 3.05 | 0 | 0 | 0
76 | NADIA | Nadia Division | Providing Functional House Tap Connection from Murutia WaterSupply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/09045 | Retrofitting | Material Requisition To Resource Division | 437/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0 | 0
77 | NADIA | Nadia Division | Providing Functional House Tap Connection from Murutia WaterSupply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/09045 | Retrofitting | Material Requisition To Resource Division | 780/ND | 18/02/2022 | 0 | Resource Division | 3.29 | 0 | 0 | 0
78 | NADIA | Nadia Division | Providing Functional House Tap Connection from Murutia WaterSupply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/09045 | Retrofitting | Material Requisition To Resource Division | 1025/ND | 03/03/2022 | 0 | Resource Division | 24.31 | 0 | 0 | 0
79 | NADIA | Nadia Division | Providing Functional House Tap Connection from Murutia WaterSupply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/09045 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Murutia W/S scheme in Nadia District under Nadia Division P.H.E. Dte. | 5686/ND | 03/11/2021 | 90 | SANJIB DEY | 88.14 | 65 | 73.75 | 100
80 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Bagakhali Zone-I water supply scheme underTehatta-I Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08307 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Bagakhali Zone-I W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 1064/NACD-II | 25/09/2020 | 15 | DEBASISH DEY | 5 | 0 | 0 | 0
81 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XI, (Chanduria) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08842 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-XI,(Chanduria) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 15/NAD-I | 05/01/2022 | 90 | MADE AND TRADE CO. | 441.26 | 379.43 | 100 | 100
82 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XI, (Chanduria) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08842 | Retrofitting | Interconnection from node point 105 to node point 16 for augmentation work at Koutakpur, Jibannagar and Kajibagan under Zone-XI, Chanduria W/S Scheme under Jal Jeevan Mission under Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte (sl.7) | 457/ NAD-I | 06/03/2023 | 21 | ABDUL ALIM MONDAL | 32.03 | 32.03 | 100 | 0
83 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XI, (Chanduria) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08842 | Retrofitting | Retrofitting work under Jal Jeevan Mission (JJM) for Brambhapara, Manasapota (Nirmalpally, Sahapara) Brambhapara, Chanduria (Sahapara) area under Chakdah Block by Augmentation of Surface Water Based W/S Scheme for Arsenic affected areas of Chakdah (Part Block) of Nadia District Zone-XI (Chanduria) under Nadia Arsenic Division-I, PHE Dte. (Sl.no.20) | 2190/NAD-I | 13/09/2023 | 15 | PRADIP KUMAR BANIK | 14.14 | 12.23 | 100 | 100
84 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District , SM/09570 | Retrofitting | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District | 642/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.49 | 0 | 0 | 0
85 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District , SM/09570 | Retrofitting | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District | 37/PFMS | 27/05/2022 | 0 | M/S TARAK CHANDRA PAUL | 144.73 | 0 | 0 | 0
86 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District , SM/09570 | Retrofitting | Providing functional household tap connection (part) including supply of 15mm dia PVC pipe of average length of 15 mtr along with laying of different dia UPVC pipe line and other allied works etc all complete for MAHISHNENGRA ZONE I W/S scheme (for Mahisnengra, Beraberia, Tegharia, Jatrapur Mouza) under Ranaghat Sub Division of Nadia Division P.H.Engineering Dte. | 963/ND | 28/02/2022 | 90 | M/S TARAK CHANDRA PAUL | 208.33 | 62.39 | 100 | 98
87 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District , SM/09570 | Retrofitting | Material Requisition To Resource Division | 1861/ND | 26/04/2023 | 0 | Resource Division | 26.26 | 0 | 0 | 0
88 | NADIA | Eastern Mechanical | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District , SM/09570 | Retrofitting | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at MAHISNENGRA ZONE - I W/S Scheme Block- Krishnagar-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/09570 | 1132/EMD | 04/06/2025 | 270 | JAL PRAVAHIKA PVT. LTD. | 36.52 | 0 | 0 | 0
89 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District , SM/09570 | Retrofitting | Construction and installation of MANIFOLD and allied works at Head Works site under Mahishnengra Zone-I Ground Based Water Supply Scheme under Krishnagar-I Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM). | 2400/ND | 23/05/2025 | 90 | MAA SARADA CONSTRUCTION | 12.28 | 0 | 0 | 0
90 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District , SM/09570 | Retrofitting | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
91 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. , SM/09571 | Retrofitting | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | 725/PFMS | 30/03/2022 | 0 | HORIZEN | 2.78 | 0 | 0 | 0
92 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. , SM/09571 | Retrofitting | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | 708/PFMS | 30/03/2022 | 0 | SANDIP BISWAS | 60 | 0 | 0 | 0
93 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. , SM/09571 | Retrofitting | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | 01/PFMS | 26/04/2022 | 0 | SANDIP BISWAS | 30.08 | 0 | 0 | 0
94 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. , SM/09571 | Retrofitting | Special repair & renovation & repair of AIRP pump house & allide works of Gazna W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | 476/A/RSD | 27/07/2022 | 30 | M/S DEBANANDA CONSTRUCTION | 1.99 | 1.97 | 98.82 | 50
95 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. , SM/09571 | Retrofitting | Providing functional household tap connection (part) including supply of 15mm dia PVC pipe of average length of 15 mtr, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Gazna Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.Engineering Dte. | 895/ND | 23/02/2022 | 90 | SANDIP BISWAS | 143.12 | 52.49 | 100 | 100
96 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. , SM/09571 | Retrofitting | Special repair & renovation of head work site pump house & allied works of Gazna W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | 556/RSD | 30/08/2022 | 30 | RUBI ENTERPRISE | 2.28 | 1.76 | 100 | 90
97 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. , SM/09571 | Retrofitting | Material Requisition To Resource Division | 6909/ND | 24/11/2021 | 0 | Resource Division | 0.68 | 0 | 0 | 0
98 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. , SM/09571 | Retrofitting | Material Requisition To Resource Division | 1873/ND | 26/04/2023 | 0 | Resource Division | 17.01 | 0 | 0 | 0
99 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. , SM/09571 | Retrofitting | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Gazna under Ranaghat Sub-Division under Nadia Division PHE Dte. | 1415/RSD | 19/11/2024 | 45 | M/S KM ENTERPRISE | 2.15 | 0 | 0 | 0
100 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. , SM/09571 | Retrofitting | Laying 160 mm dia UPVC pipe line inplace of damaged 160 mm dia from gazna Madhya Para to Gazna Para for smooth running of augmentation of Ground Water Supply Scheme for Gazna in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | 5333/ND | 21/12/2022 | 868 | SANDIP BISWAS | 17.06 | 13.69 | 80.26 | 95
101 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. , SM/09571 | Retrofitting | Replacemt of damaged & typically choked UPVC pipe line for augmentation of Ground Water Based Water Supply Scheme for Gazna PWSS of Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. (Balance) A- Part. | 4802/ND | 17/10/2023 | 90 | SANDIP BISWAS | 99.5 | 70.33 | 98.61 | 96
102 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. , SM/09571 | Retrofitting | Renovation of Semi-Gravity & Semi-Pressure Type AIRP at Gazna Water Supply Scheme of capacity 58.5 Cu.m/hr. | 783/ND | 05/02/2024 | 90 | APURBA MANDAL | 44.96 | 5.8 | 25.82 | 84
103 | NADIA | Eastern Mechanical | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. , SM/09571 | Retrofitting | Supply, & Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for Mini Piped Water Supply Scheme[Gazna(part) Block-Hanskhali, Uttar Bishnupur Block-Ranaghat-II, Augmentation to Accomodate FHTC , Dist. - Nadia. under EMD, PHE Dte. | 1307/EMD | 09/05/2024 | 388 | ORIENTAL ENGINEERING CO. | 12.61 | 0 | 0 | 45
104 | NADIA | Eastern Mechanical | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. , SM/09571 | Retrofitting | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at GAZNA W/S Scheme Block- HANSKHALI under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/09571 | 1150/EMD | 04/06/2025 | 90 | KARTICK BAL | 36.98 | 0 | 0 | 0
105 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. , SM/09571 | Retrofitting | Construction and installation of MANIFOLD and allied works at Head Works site under Gazna Ground Based Water Supply Scheme under Hanskhali Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM). | 3639/ND | 04/08/2025 | 90 | K.K. MARKETING | 11.85 | 0 | 0 | 0
106 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) , SM/08951 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) | 698/PFMS | 28/03/2022 | 0 | CALCON CONSTRUCTIONS | 83.66 | 0 | 0 | 0
107 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) , SM/08951 | Retrofitting | Providing Functional Household Tap connection(FHTC)at Surface Water Based Water Supply Scheme(Northern Sector) Part-II,Zone-VII within Nakashipara Block(Phase-C) | 7205/ND | 15/12/2021 | 90 | CALCON CONSTRUCTION | 179.4 | 63.59 | 100 | 100
108 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) , SM/08951 | Retrofitting | Schedule for Laying additional distribution pipeline for providing FHTC at Dhnanajoypur, Dhaparia and Radhanagar villages under zone-VII , Part- II Phase C, Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | 175/B/DSD | 18/04/2022 | 30 | CALCON CONSTRUCTIONS | 4.97 | 4.68 | 100 | 100
109 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) , SM/08951 | Retrofitting | Laying additional distribution pipeline for providing FHTC at Dhnanajoypur and Radhanagar villages under zone-VII , Part- II Phase C, Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | 50/DSD | 07/02/2022 | 15 | CALCON CONSTRUCTIONS | 4.75 | 4.71 | 100 | 100
110 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) , SM/08951 | Retrofitting | Laying additional distribution pipeline for providing FHTC at Dhaparia, Dhananjoypur & Shibpur zone-VII , Part- II Phase C, Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | 49/DSD | 07/02/2022 | 15 | CALCON CONSTRUCTIONS | 4.79 | 4.76 | 100 | 100
111 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) , SM/08951 | Retrofitting | Material Requisition To Resource Division | 795/ND | 18/02/2022 | 0 | Resource Division | 7.22 | 0 | 0 | 0
112 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) , SM/08951 | Retrofitting | Material Requisition To Resource Division | 797/ND | 18/02/2022 | 0 | Resource Division | 11 | 0 | 0 | 0
113 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) , SM/08951 | Retrofitting | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- VII/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4282/ND | 21/09/2023 | 534 | SATYABRATA CHAKRABORTY | 397.18 | 0 | 0 | 14
114 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) , SM/08956 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | 653/PFMS | 21/03/2022 | 0 | JAL PRAVAHIKA PRIVATE LIMITED | 55 | 0 | 0 | 0
115 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) , SM/08956 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | 664/PFMS | 23/03/2022 | 0 | JAL PRAVAHIKA PRIVATE LIMITED | 42.43 | 0 | 0 | 0
116 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) , SM/08956 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | 33/PFMS | 23/05/2022 | 0 | JAL PRAVAHIKA PRIVATE LIMITED | 50.46 | 0 | 0 | 0
117 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) , SM/08956 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-I,II & IV within KALIGANJ BLOCK(Phase-C) | 7050/ND | 06/12/2021 | 90 | JAL PRAVAHIKA PRIVATE LIMITED | 180.28 | 26.9 | 100 | 100
118 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) , SM/08956 | Retrofitting | Laying additional distribution pipeline for providing FHTC at Ballavpara, Basatpur, Kanua, Juranpur Bhagyabantapur, Gobra zone-I & II , Part- I Phase C, Surface water based Water Supply Scheme, Nadia Northern Sector , Kaliganj Block. | 175/C/DSD | 18/04/2022 | 30 | JAL PRAVAHIKA PRIVATE LIMITED | 4.85 | 4.8 | 100 | 100
119 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) , SM/08956 | Retrofitting | Material Requisition To Resource Division | 428/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0 | 0
120 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) , SM/08956 | Retrofitting | Material Requisition To Resource Division | 817/ND | 18/02/2022 | 0 | Resource Division | 10.98 | 0 | 0 | 0
121 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) , SM/08956 | Retrofitting | Material Requisition To Resource Division | 447/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0 | 0
122 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) , SM/08956 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 5.03 | 100 | 81
123 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) , SM/08956 | Retrofitting | Material Requisition To Resource Division | 307/ND | 15/01/2024 | 0 | Resource Division | 12.39 | 0 | 0 | 0
124 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) , SM/08956 | Retrofitting | Material Requisition To Resource Division | 304/ND | 15/01/2024 | 0 | Resource Division | 23.27 | 0 | 0 | 0
125 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) , SM/08956 | Retrofitting | Material Requisition To Resource Division | 303/ND | 15/01/2024 | 0 | Resource Division | 10.96 | 0 | 0 | 0
126 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) , SM/08956 | Retrofitting | Material Requisition To Resource Division | 305/ND | 15/01/2024 | 0 | Resource Division | 3.81 | 0 | 0 | 0
127 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) , SM/08956 | Retrofitting | Material Requisition To Resource Division | 306/ND | 15/01/2024 | 0 | Resource Division | 8.98 | 0 | 0 | 0
128 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) , SM/08956 | Retrofitting | Material Requisition To Resource Division | 318/ND | 15/01/2024 | 0 | Resource Division | 3.27 | 0 | 0 | 0
129 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshinpara Zone-II Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-A) , SM/08671 | Retrofitting | Providing Functional House Tap Connection from Dakshinpara Zone-II Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-A) | 606/PFMS | 11/03/2022 | 0 | OTHERS | 8.27 | 0 | 0 | 0
130 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshinpara Zone-II Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-A) , SM/08671 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Dakshinpara Z-II Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.E. Dte.(Phase-A) | 5178/ND | 20/09/2021 | 90 | JOY HIND TUBEWELL'S | 88.3 | 87.92 | 99.58 | 0
131 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshinpara Zone-II Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-A) , SM/08671 | Retrofitting | Material Requisition To Resource Division | 794/ND | 18/02/2022 | 0 | Resource Division | 8.92 | 0 | 0 | 0
132 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshinpara Zone-II Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-A) , SM/08671 | Retrofitting | Material Requisition To Resource Division | 101/ND | 06/01/2022 | 0 | Resource Division | 0.88 | 0 | 0 | 0
133 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR DAKSHIN JHITKIPOTA ZONE-I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte. , SM/09527 | Retrofitting | RETROFITTING UNDER JAL SWAPNA FOR DAKSHIN JHITKIPOTA ZONE-I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte. | 609/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.92 | 0 | 0 | 0
134 | NADIA | Eastern Mechanical | RETROFITTING UNDER JAL SWAPNA FOR DAKSHIN JHITKIPOTA ZONE-I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte. , SM/09527 | Retrofitting | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accommodate FHTC under DAKSHIN JHITKIPOTA(Z-1) W/S Scheme, Block-Krishnagar-I, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 09) | 1176/EMD | 21/03/2023 | 30 | SRI KRISHNA NIRMAN | 14.96 | 0 | 0 | 99
135 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR DAKSHIN JHITKIPOTA ZONE-I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte. , SM/09527 | Retrofitting | LAYING OF PIPELINE UNDER PALASHIPARA PWSS FROM PALASHIPARA BAZAR TO BURNIA BUS STAND. | 241/1/PFMS | 18/08/2023 | 0 | OTHERS | 49.99 | 0 | 0 | 0
136 | NADIA | Eastern Mechanical | RETROFITTING UNDER JAL SWAPNA FOR DAKSHIN JHITKIPOTA ZONE-I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte. , SM/09527 | Retrofitting | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at DAKSHIN JHITKIPOTA ZONE-II W/S Scheme Block- Krishnagar-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/09451] | 1145/EMD | 04/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 38.68 | 0 | 0 | 0
137 | NADIA | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR DAKSHIN JHITKIPOTA ZONE-I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte. , SM/09527 | Retrofitting | LAYING OF DISTRIBUTION SYSTEM INCLUDING SPECIALS & VALVES, PIPE SUPPORTING STRUCTURE ALL COMPLETE BASED ON ACTUAL ESTIMATE & PROVIDING FHTC FOR DAKHIN JHITKIPOTA ZONE - I WATER SUPPLY SCHEME IN NADIA DISTRICT UNDER NADIA DIVISION. | 922/ND | 24/02/2022 | 1080 | TAPU SAHA | 284.92 | 243.61 | 96.25 | 100
138 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme under Chapra Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08249 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1061/NACD-II | 25/09/2020 | 15 | TAPAS GHOSH | 4.99 | 0 | 0 | 0
139 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Helenchi Zone-I water supply scheme underKrishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District, under Nadia ArsenicCivil Division-II, P.H.E. Dte , SM/08252 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Helenchi Zone-I (Vill-Krishnapur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1179/NACD-II | 13/11/2020 | 15 | CHINMOY BISWAS | 4.99 | 0 | 0 | 0
140 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. , SM/09452 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. | 06/PFMS | 26/04/2022 | 0 | IJABUL SK. | 40.83 | 0 | 0 | 0
141 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. , SM/09452 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district under Nadia division. | 718/PFMS | 30/03/2022 | 0 | IJABUL SK. | 50 | 0 | 0 | 0
142 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. , SM/09452 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. | 641/PFMS | 16/03/2022 | 0 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 3.6 | 0 | 0 | 0
143 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. , SM/09452 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. and construction of 400 cum capacity 20 mtr. staging height RCC over head reservoir (including pile foundation), pipe connection and cost of pipes, specials and soil investigation for construction of one no. 400 cum OHR of staging height 20 mtr all complete for Augmentation of Ground Based Water Supply Scheme at Nazirpur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 634/ND | 10/02/2022 | 90 | IJABUL SK. | 354.81 | 120.52 | 100 | 70
144 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. , SM/09452 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator etc. for Augmentation to Accomodate FHTC at Pump House No.I under Nazirpur W/S Scheme District -Nadia NIET No.- 13 of EE/EMD of 2022-23 (Sl. No.-05) | 3805/EMD | 14/10/2022 | 30 | A.K. ENTERPRISE | 13.23 | 13.23 | 100 | 100
145 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. , SM/09452 | Augmentation | Material Requisition To Resource Division | 434/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0 | 0
146 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. , SM/09452 | Augmentation | Material Requisition To Resource Division | 1265/ND | 16/03/2022 | 0 | Resource Division | 11.72 | 0 | 0 | 0
147 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. , SM/09452 | Augmentation | Material Requisition To Resource Division | 1390/ND | 24/03/2022 | 0 | Resource Division | 16.87 | 0 | 0 | 0
148 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. , SM/09452 | Augmentation | Material Requisition To Resource Division | 4313/ND | 29/09/2022 | 0 | Resource Division | 20.05 | 0 | 0 | 0
149 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. , SM/09452 | Augmentation | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of 76 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Nazirpur to accommodate FHTC within Tehatta-I block underTehatta Sub-division under Nadia Division, P.H.E. Dte. | 207/ND | 13/01/2025 | 180 | TRANS ORGANICS INDIA PVT LTD | 217.81 | 0 | 0 | 0
150 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. , SM/09452 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete & Construction of 400 CUM Capacity 20 Mtr. Staging height RCC Over Head Rservoir (including pile foundation) Pipe connection and cost of pipes, specials for Augmentation of Ground Based Water Supply Scheme (Phase- II) at Nazirpur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 3376/ND | 14/06/2024 | 730 | M/S DIPAK ENTERPRISE | 217.72 | 12.26 | 5.63 | 25
151 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. , SM/09452 | Augmentation | Repairing and renovation works of Pump House and allied works of ground based piped water supply scheme for Nazirpur water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 7061/ND | 04/12/2024 | 150 | BISWAS ENTERPRISE | 12.53 | 0 | 0 | 100
152 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. , SM/09452 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- III) at village Nazirpur, Bagadoba, Chhitka, Aztullanagar under Tehatta-I Block to accommodate FHTC under Nadia Divn, PHE Dte. | 1805/ND | 22/04/2025 | 180 | M/S DIPAK ENTERPRISE | 71.65 | 0 | 0 | 30
153 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09787 | Augmentation | LAYING OF RISING MAIN AT MAHISNENGRA ZONE II WATER SUPPLY SCHEME UNDER RANAGHAT SUB DIVISION OF NADIA DIVISION, P.H.E. DTE. | 107/RSD | 23/02/2022 | 15 | M/S BISWAS ENTERPRISE | 1.83 | 1.42 | 100 | 90
154 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09787 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | 643/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.5 | 0 | 0 | 0
155 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09787 | Augmentation | Material Requisition To Resource Division | 1057/ND | 04/03/2022 | 0 | Resource Division | 3.96 | 0 | 0 | 0
156 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09787 | Augmentation | Material Requisition To Resource Division | 1880/ND | 26/04/2023 | 0 | Resource Division | 4.39 | 0 | 0 | 0
157 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09787 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 1.4 | 98.71 | 40
158 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09787 | Augmentation | WBSEDCL Quotation for New Service Connection to the ongoing AIRP premises under ZONE - II of MAHISNENGRA W/S Scheme in Krishnagar - I Block, P.H.E. Dte., Dist.- Nadia. (Application No. 3004547497) | BP-05-24-25 | 23/04/2024 | 0 | W.B.S.E.D.C.LTD (CHITRASALI C.C.CENTER) | 6.79 | 0 | 0 | 0
159 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09787 | Augmentation | Augmentation of Ground Water Based piped Water Supply scheme for Mahishnengra Zone-II to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division P.H.E. Dte. | 3223/ND | 26/07/2023 | 616 | CHOWDHURY & CO. | 94.44 | 28.49 | 30.17 | 80
160 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09787 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Mahishnengra Zone-II piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | 1277/RSD | 04/10/2024 | 45 | MANARAMA ENTERPRISE | 1.9 | 0 | 0 | 100
161 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09787 | Augmentation | Construction of 100m Boundary Wall(2.5m panel) having 200X200mm R.C.C. Column footing (1.0X1.0m) with 125mm thick brick panel wall and 200x300 RCC beam at GL including M.S gate at Mahisnengra Zone-II PWSS at H/W site under Ranaghat Sub -Division in Nadia District under Nadia Division P.H.Engineering Dte. | 2462/ND | 27/05/2025 | 90 | ABHAYANANDA ENTERPRISE | 8.74 | 0 | 0 | 100
162 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09787 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at MAHISNENGRA Zone-II W/S Scheme Block- Krishnagar-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/09787 | 1134/EMD | 04/06/2025 | 90 | MAHAMAYA ENTERPRISE. | 36.66 | 0 | 0 | 0
163 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09787 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
164 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ITLA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09788 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for ITLA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | 634/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.59 | 0 | 0 | 0
165 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ITLA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09788 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accomodate FHTC under ITLA W/S Scheme, Block- Krishnagar-1 , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 15) | 415/EMD | 20/01/2023 | 30 | ANJAN ENTERPRISE | 14.53 | 13.46 | 100 | 80
166 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ITLA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09788 | Augmentation | Material Requisition To Resource Division | 1259/ND | 16/03/2022 | 0 | Resource Division | 8.04 | 0 | 0 | 0
167 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ITLA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09788 | Augmentation | Material Requisition To Resource Division | 1020/ND | 03/03/2022 | 0 | Resource Division | 2.21 | 0 | 0 | 0
168 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ITLA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09788 | Augmentation | Material Requisition To Resource Division | 4323/ND | 29/09/2022 | 0 | Resource Division | 25.29 | 0 | 0 | 0
169 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ITLA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09788 | Augmentation | Repair and renovation works of R.C.C. Elevaced Reservoir 250 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Itla Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 1253/ND | 22/02/2024 | 346 | MAHALAXMI CONSTRUCTION | 24.89 | 4.66 | 18.74 | 75
170 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ITLA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09788 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Itla to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 1313/ND | 21/03/2022 | 90 | SHIBU BISWAS | 145.51 | 144.13 | 99.05 | 100
171 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ITLA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09788 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 57 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Itla PWSS under Nadia Division PHE Dte. | 2996/ND | 13/07/2023 | 720 | TARUN KUMAR BHATTACHARYA | 82.59 | 0 | 0 | 50
172 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons , SM/09966 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Joypur Part-III at Hanskhali Block by retrofitting of Ground Water based PWSS for Joypur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 07) | 433/NAD-I | 07/03/2022 | 60 | M/S GHOSH CONSTRUCTION | 60.4 | 56.94 | 100 | 100
173 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons , SM/09966 | Augmentation | Water Supply Arrangement in High School, Primary School, SSk & MSK under Jal Jeevan Mission (JJM) at Itaberia PWSS Hanskhali Block (Part-I) by Augmentation of Itaberia, Gobindapur & Joypur at Hanskhali Block, Dist- Nadia under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) | 3489/NAD-I | 02/01/2023 | 21 | BUDDHADEV MONDAL | 19.22 | 18.72 | 97.42 | 99
174 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons , SM/09966 | Augmentation | Repair of 450 cum capacity Over Head Reservoir, Painting and Pump House at Gobindapur W/S Scheme in Hanskhali Block under Nadia Arsenic Division-I, P.H.E Dte. (Sl. No. 10) | 1589/NAD-I | 05/09/2022 | 45 | APURBA MANDAL | 14.41 | 14.38 | 100 | 40
175 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons , SM/09966 | Augmentation | Construction of Boundary Wall, Toilet, pathway and other allied work at Joypur W/S scheme within Hanskhali Block under Nadia Arsenic Division -I, P.H.E.Dte.( Sl.no.01) | 1590 / NAD-I | 06/09/2022 | 45 | M/S DREAM INFRASTRUCTURE | 12.41 | 12.35 | 100 | 100
176 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons , SM/09966 | Augmentation | Construction of Boundary wall, Toilet, Pathway and all repair works at Itaberia W/S Scheme within Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (sl.no.03) | 1638 / NAD-I | 06/09/2022 | 45 | APURBA MANDAL | 12.04 | 11.99 | 100 | 100
177 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons , SM/09966 | Augmentation | Repair of 250 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at ITABERIA W/S Scheme & Betna W/S Scheme at Hanskhali Block under Nadia Arsenic Division-I , P.H.E.Dte. (Sl.no. 10) | 1583/NAD-I | 06/09/2022 | 45 | SATYABRATA CHAKRABORTY | 28.26 | 28.19 | 100 | 100
178 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons , SM/09966 | Augmentation | Repair of 250 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House and AIRP at Itaberia WS Scheme in Hanskhali Block under NAD I PHE Dte (Sl.no.12) | 2058 / NAD-I | 21/10/2022 | 45 | M/S D.C. RAKSHIT & COMPANY | 19.77 | 19.63 | 100 | 100
179 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons , SM/09966 | Augmentation | Repair of 350 cum capacity Over Head Reservoir, Painting of Boundary Wall of Head Work Site, Pump House and AIRP at Joypur W/S Scheme in Hanskhali Block under Nadia Arsenic Division - I P. H.E. Dte (Sl. No. 01) | 1258/NAD-I | 04/05/2023 | 15 | GHOSH CONSTRUCTION | 21.34 | 21.08 | 100 | 100
180 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons , SM/09966 | Augmentation | Construction of Boundary wall, Toilet , Pathway and other allied work at Gobindapur (Hanskhali) W/S Scheme within Hanskhali Block under Nadia Arsenic Division -I, P.H.E.Dte.(Sl.no. 02) | 1588 / NAD-I | 06/09/2022 | 45 | GOPAL KIRTYANIYA | 11.82 | 11.76 | 100 | 100
181 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons , SM/09966 | Augmentation | Construction of AIRP capacity (104m3/hr) in connection with augmentation of Ground Water Based PWSS for Chupria Zone-I under Jal Jeevan Mission at Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. | 1118/NAD-I | 19/07/2024 | 180 | HARBAUER INDIA PRIVATE LIMITED | 265.04 | 0 | 0 | 0
182 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons , SM/09966 | Augmentation | Water Supply Arrangement in High School, Primary School, SSk & MSK under Jal Jeevan Mission (JJM) at Joypur PWSS Hanskhali Block (Part-III) by Augmentation of Itaberia, Gobindapur & Joypur at Hanskhali Block, Dist- Nadia Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (sl.no.02) | 3514/NAD-I | 09/01/2023 | 21 | SUBIR KUMAR DEY | 19.99 | 16.35 | 100 | 100
183 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons , SM/09966 | Augmentation | Water Supply Arrangement in High School, Primary School, SSk & MSK under Jal Jeevan Mission (JJM) at Gobindapur PWSS Hanskhali Block (Part-II) by Augmentation of Itaberia, Gobindapur & Joypur at Hanskhali Block, Dist- Nadia under Nadia Arsenic Division-I, PHE Dte (sl.no.04) | 3513/NAD-I | 09/01/2023 | 21 | M/S DIPAK ENTERPRISE | 19.75 | 14.59 | 100 | 100
184 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons , SM/09966 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Itaberia Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Itaberia W/S Scheme under JJM (sl.no.11) | 1122 /NAD-I | 27/04/2023 | 15 | B.S. ENTERPRISE | 13.04 | 12.98 | 100 | 100
185 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons , SM/09966 | Augmentation | 'Construction and installation of MANIFOLD and allied works at OHR site under Gobindapur Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E [he. in connection with Augmentation of Gobindapur W/S Scheme under JIM (SL No. 10)". | 1071/NAD-I | 24/04/2023 | 733 | APURBA MANDAL | 13.03 | 0 | 0 | 100
186 | NADIA | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/08666 | Retrofitting | Providing Functional House Tap Connection from Teinpur Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | 606/PFMS | 11/03/2022 | 0 | OTHERS | 3.08 | 0 | 0 | 0
187 | NADIA | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/08666 | Retrofitting | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H.E. Dte., Kalyani, Nadia. Period of work 01-03-2022 to 28-02-2023 | 118/RSD | 28/02/2022 | 250 | SUMAN CHAKRABORTY | 3.85 | 0 | 0 | 75
188 | NADIA | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/08666 | Retrofitting | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 11-11-2022 to 31-01-2023= 80 days. | 678/RSD | 04/11/2022 | 80 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 1.19 | 0.67 | 100 | 75
189 | NADIA | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/08666 | Retrofitting | Material Requisition To Resource Division | 805/ND | 18/02/2022 | 0 | Resource Division | 3.33 | 0 | 0 | 0
190 | NADIA | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/08666 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Teinpur zone - I W/S scheme under Nadia Division, PHE Dte. | 5141/ND | 15/09/2021 | 60 | SAHA ENGINEERS | 37 | 26.29 | 71.05 | 100
191 | NADIA | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/08667 | Retrofitting | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | 40/PFMS | 27/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 1.04 | 0 | 0 | 0
192 | NADIA | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/08667 | Retrofitting | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | 39/PFMS | 27/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.36 | 0 | 0 | 0
193 | NADIA | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/08667 | Retrofitting | Hiring Diesel Luxury Car on daily basis (for12 months from 01.02.2022 to 31.01.2023) for the office use of the Assistant Engineer, Kalyani Sub - Division - II, P.H.E. Dte. | 144/ Kly SD-II | 31/01/2022 | 365 | SUMAN CHAKRABORTY | 4.8 | 1.17 | 100 | 65
194 | NADIA | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/08667 | Retrofitting | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 01-02-2023 to 31-07-2023= 183 days. | 92/RSD | 01/02/2023 | 183 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 3.2 | 0 | 0 | 25
195 | NADIA | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/08667 | Retrofitting | Material Requisition To Resource Division | 446/ND | 31/01/2022 | 0 | Resource Division | 1.19 | 0 | 0 | 0
196 | NADIA | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/08667 | Retrofitting | Material Requisition To Resource Division | 821/ND | 18/02/2022 | 0 | Resource Division | 5.5 | 0 | 0 | 0
197 | NADIA | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/08667 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Naserkuli zone- I W/S scheme under Nadia Division, PHE Dte. | 5144/ND | 15/09/2021 | 90 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 87.52 | 77.98 | 89.11 | 100
198 | NADIA | Nadia Division | Providing Functional House Tap Connection from Krishnaganj Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) , SM/08964 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Krishnaganj W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(PART-A) | 5693/ND | 03/11/2021 | 90 | NILAY KUMAR BHATTACHARYA | 85.63 | 84.56 | 98.75 | 0
199 | NADIA | Nadia Division | Providing Functional House Tap Connection from Krishnaganj Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) , SM/08964 | Retrofitting | Laying of additional HDPE pipeline for water supply scheme under Krishnaganj Block under Krishnagar Sub Division, Nadia Division, PHE Dte. | 7092/ND | 05/12/2024 | 90 | MANGES INDUSTRIAL CORPORATION | 177.21 | 0 | 0 | 0
200 | NADIA | Nadia Division | Providing Functional House Tap Connection from Krishnaganj Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) , SM/08964 | Retrofitting | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.01.2024 to 31.01.2024 | 1359/KLYSD-I | 28/12/2023 | 31 | SUMAN CHAKRABORTY | 4.89 | 4.89 | 100 | 100
201 | NADIA | Nadia Division | Providing Functional House Tap Connection from Krishnaganj Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) , SM/08964 | Retrofitting | Providing balance FHTC of Phase I (Retrofitting) of Krishnaganj Water Supply Scheme in Nadia District Under Krishnagar Sub-Division, of Nadia District under Nadia Division P.H.E. Dte. | 5335/ND | 21/12/2022 | 90 | NILAY KUMAR BHATTACHARYA | 96.45 | 95.66 | 100 | 100
202 | NADIA | Nadia Division | Providing Functional House Tap Connection from Krishnaganj Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) , SM/08964 | Retrofitting | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.02.2024 to 31.03.2024 | 115/KlySD-I | 31/01/2024 | 29 | SUMAN CHAKRABORTY | 4.89 | 4.89 | 100 | 100
203 | NADIA | Nadia Division | Providing Functional House Tap Connection from Krishnaganj Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) , SM/08964 | Retrofitting | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.03.2024 to 31.03.2024 | 326/KlySD-I | 29/02/2024 | 31 | SUMAN CHAKRABORTY | 4.89 | 4.89 | 100 | 100
204 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09686 | Retrofitting | Preparation of DPR for augmentation of existing Brittihuda, (Block -Chapra) piped water supply schemes | 145/AE-I/NACD-II | 16/11/2021 | 10 | UMWELT ENGINEER PVT LTD. | 3.89 | 3.89 | 100 | 100
205 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09686 | Retrofitting | Preparation of DPR for augmentation of existing Brittihuda (Phase-II), (Block -Chapra) piped water supply schemes | 757/NACD-II | 16/09/2021 | 10 | SIRCON ENGINEERING SERVICE | 4.95 | 4.95 | 100 | 100
206 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09686 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and also construction of steps with earth filling at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | 983/NACD-II | 27/12/2021 | 90 | IJABUL SEKH | 177.61 | 177.39 | 99.87 | 100
207 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09686 | Retrofitting | Making of Office Furniture including supply of Split type Air Conditioner and other allied works under Retrofitting of the Brittihuda PWSS under Chapra Block | 184/AE-I/NACD-II | 29/12/2021 | 20 | SURAJIT KUMAR GHOSH | 4.89 | 4.89 | 100 | 100
208 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09686 | Retrofitting | Rejuvenation of the offiec room including supply of Split type Air Conditioner and other allied works under Retrofitting of the Brittihuda PWSS under Chapra Block. | 185/AE-I/NACD-II | 29/12/2021 | 20 | SURAJIT KUMAR GHOSH | 4.97 | 3.3 | 66.34 | 100
209 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09686 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 521/NACD-II | 14/06/2021 | 45 | JOY HIND TUBEWELLS | 74.36 | 0 | 0 | 100
210 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09686 | Retrofitting | continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 562/NACD-II | 13/07/2021 | 45 | JOY HIND TUBEWELLS | 73.59 | 0 | 0 | 100
211 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09686 | Retrofitting | Relaying of D.I. Pipeline replacing the damaged old HDPE Rising Main Pipe line at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 140/AE-I/NACD-II | 01/11/2021 | 15 | GOUTAM HALDER | 3.37 | 3.37 | 100 | 100
212 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09686 | Retrofitting | Continuation work order for Special repairing works of damaged old pipe line at Brittihuda including ancillary FHTC works at Arangsarisa of Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 168/AE-I/NACD-II | 23/11/2021 | 15 | JOY HIND TUBEWELLS | 4.99 | 4.99 | 100 | 100
213 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09686 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair ) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 995/EE/NACD-II | 30/12/2021 | 45 | CHANDA CONSTRUCTION | 98.72 | 0 | 0 | 100
214 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09686 | Retrofitting | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 547/NACD-II | 07/07/2021 | 45 | JOY HIND TUBEWELLS | 73.68 | 0 | 0 | 100
215 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09686 | Retrofitting | Piling work at Krishnagar Karimpur Road side for pipe line protection at Brittihuda Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | 134/AE-I/NACD-II | 28/10/2021 | 15 | TAPAS GHOSH | 4.96 | 4.96 | 100 | 100
216 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09686 | Retrofitting | Jungle cutting and Earthwork in filling at Taldaha,Sakdaha and Brittihuda Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 819/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.53 | 0.22 | 100 | 100
217 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09686 | Retrofitting | Shifting of 01 no existing 63 KVA, 11/0.4 KV DTR I.R.O PHE Brittihuda PWSS head works site, Brittihuda under Chapra CCC. | 133 | 06/09/2024 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.68 | 0 | 0 | 0
218 | NADIA | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthning work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH D , SM/09092 | Retrofitting | Restoration of impact zone along Swarupganj UBI more to Anandabas road in connection to the work Providing FHTC (Functional Household Tap Connection) by retrofitting under "Jalswapno" in connection with " Shifting of existing PHE pipeline for implementation of Widening & strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Km under NH Divn-I RIDF-XXV within Gadigacha and other W/S Scheme under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. Sl.No. 03 | 244/KSD | 11/03/2022 | 7 | PAPAN ROY | 4.44 | 1.02 | 100 | 97
219 | NADIA | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthning work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH D , SM/09092 | Retrofitting | Providing FHTC (Functional Household Tap Connection) by retrofitting under "Jalswapno" in connection with " Shifting of existing PHE pipeline for implementation of Widening & strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Km under NH Divn-I RIDF-XXV within Gadigacha W/S Scheme under Krishnagar Sub-Divn under Nadia Divn, PHE Dte." | 7292/ND | 20/12/2021 | 60 | PAPAN ROY | 23.86 | 22.4 | 93.89 | 95
220 | NADIA | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthning work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH D , SM/09092 | Retrofitting | Material Requisition To Resource Division | 7449/ND | 27/12/2021 | 0 | Resource Division | 34.46 | 0 | 0 | 0
221 | NADIA | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthning work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH D , SM/09092 | Retrofitting | Material Requisition To Resource Division | 449/ND | 31/01/2022 | 0 | Resource Division | 0.81 | 0 | 0 | 0
222 | NADIA | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthning work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH D , SM/09092 | Retrofitting | Material Requisition To Resource Division | 4269/ND | 29/09/2022 | 0 | Resource Division | 2.51 | 0 | 0 | 0
223 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Construction of Boundary wall with Grill Gate at Mahatpur 4th site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | 239/AE-I/NACD-II | 17/02/2022 | 30 | BASUDEB SAHA | 3.81 | 3.79 | 99.44 | 100
224 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Continuation work order for Piling work at Krishnagar Karimpur Road side for pipe line protection at Brittihuda Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 211./AE-I/NACD-II | 20/01/2022 | 15 | TAPAS GHOSH | 4.92 | 4.92 | 99.97 | 100
225 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Repairing and paitning of Overhead Reservoir and other allied works under augmentation of Lakshmipur PWSS of Chapra Block. | 191./AE-I/NACD-II | 29/12/2021 | 25 | PRABIR KUMAR ROY | 4.81 | 4.81 | 99.99 | 100
226 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Construction of Boundary Wall at OHR Head Work site of Madhabpur W/s Scheme under Nadia Arsenic Civil Division - II P.H.E. Dte., Dist - Nadia. | 20./AE-II/NACD-II | 19/02/2021 | 10 | B.M. ENGINEERING & CONSTRUCTION | 4.96 | 4.62 | 93.24 | 100
227 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Reparing and painting of Overhead Reservoir and pump house of Gongra Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 05/AE-I/NACD-II | 04/04/2022 | 45 | GOUTAM HALDER | 5 | 5 | 100 | 100
228 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Continuation work order for Electrical and Civil works and other allied works under retrofitting of Mahatpur PWSS under Chapra Block. | 308/AE-I/NACD-II | 23/03/2022 | 20 | CHINMOY BISWAS | 4.92 | 4.92 | 100 | 100
229 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Construction of Boundary wall with Grill Gate at Mahatpur 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | 237/AE-I/NACD-II | 17/02/2022 | 30 | ROY CONSTRUCTION | 3.85 | 3.83 | 99.32 | 100
230 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Construction of Boundary wall with Grill Gate at Mahatpur 3rd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | 238/AE-I/NACD-II | 17/02/2022 | 30 | SHYAMAL KANTI GHOSH | 3.84 | 3.8 | 99.02 | 100
231 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | RESOURCE PAYMENT MAHATPUR | 258 | 26/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 61 | 0 | 0 | 0
232 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 42/NACD-II | 17/01/2022 | 45 | NILAY KUMAR BHATTACHARYA | 21.05 | 21.05 | 100 | 100
233 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Providing Functional School Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 351/NACD-II | 22/03/2023 | 20 | SAMARESH GHOSH | 1.1 | 0.87 | 79.08 | 90
234 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Structural Health assesment of existing shaft type OHR of Chapra Blocks and ancillary structures conducting Non-Destructive test and through visual observation under Nadia Arsenic Civil Division-II P.H.E Dte. | 1429/NACD-II | 15/12/2023 | 30 | SIRCON ENGINEERING SERVICE | 8.46 | 0 | 0 | 0
235 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Construction of Boundary wall with Grill Gate at Mahatpur Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | 108/NACD-II | 10/02/2022 | 45 | PARTHA DAS | 8.55 | 8.5 | 100 | 100
236 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 117/NACD-II | 15/02/2022 | 90 | M/S. R.K.ENTERPRISE | 173.44 | 172.38 | 100 | 100
237 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Route survey engaging qualified surveyors with modern instruments viz-GPS, Total station, DGPS, Auto levels etc over the command area of Mahatpur Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Mahatpur W/S Scheme in chapra Block of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte | 549/NACD_II | 11/05/2023 | 20 | LAKSHMI CONSTRUCTION | 9.09 | 9.09 | 100 | 100
238 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BRITTIHUDA (Block- Chapra), BARNIA (Block- Tehatt II ), MAHATPUR (Block- Chapra ), MATIARY (Block- Krishnaganj), BAGAKHALI (Z-I) (Block- Tehatta I ), BARA NALDAH (Block- Tehatta II ) W/S Scheme, , Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 01) | 1120/EMD | 16/03/2023 | 30 | B.T. PROJECTS PVT. LTD | 91.82 | 16.61 | 95.15 | 60
239 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Construction of pumphouse cum Chlorine room with sanitary and water supply arrangement at Kathgara Muslimpara mouza in Mahatpur Piped water supply scheme in Chapra Block under Nadia Arsenic Civil Division-II ,PHE Dte.Dist- Nadia. | 1391/NACD-II | 22/10/2024 | 30 | BABLU MALLICK | 6.22 | 0 | 0 | 1
240 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Repair and Renovation work at Mahatpur 2nd tube well Site under Mahatpur Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia | 1027/AE-I/NACD-II | 10/12/2024 | 30 | SUPRIO MAJUMDER | 3.2 | 0 | 0 | 0
241 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | New Sinking of 1 no. 250 mm X 150 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD)& strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Mouza Kathgara,Habitation of Muslim Para under Mahatpur Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II PHE Dte | 1322/NACD-II | 20/09/2024 | 45 | DHELA BABA ENTERPRISES | 10.4 | 0 | 0 | 0
242 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Mahatpur Piped Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1367/NACD-II | 08/12/2023 | 30 | M/S GHOSH CONSTRUCTION | 45.3 | 45.12 | 100 | 100
243 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at TENGRA W/S Scheme in Tengra Village Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 660/AE-I/NACD-II | 21/02/2024 | 15 | ASHIM ENTERPRISE | 3.91 | 3.86 | 100 | 100
244 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Continuation Work Order for Collection of Household Details at Prescribed Format through Mobile App/Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte. in soft copy for Bagakhali Zone-I & Mahatpur PWSS under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 898/AE-I/NACD-II | 09/09/2024 | 60 | JOY GOPAL GUPTI | 3.5 | 0 | 0 | 100
245 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Approximate expenditure for land registration and subsequent mutation process as compliance for PHED and Land Commissioner aiuthories to overcome the stalemate and initiation of due diligence processes in Krishnaganj Block under Nadia Arsenic Civil Division-II under Nadia District PHE Dte. | 933/AE-I/NACD-II | 04/10/2024 | 7 | SOMNATH GHOSH | 0.75 | 0.75 | 100 | 100
246 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under chapra Block of Nadia District through Jadavpur University. (Name of PWSS Gongra & Mahatpur) | 1267_NACD-II | 09/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
247 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Approximate expenditure for land registration and subsequent mutation process as compliance for PHED and Land Commissioner aiuthories to overcome the stalemate and initiation of due diligence processes in Krishnanagar-I Block under Nadia Arsenic Civil Division II under Nadia District PHE Dte. | 936/AE-I/NACD-II | 04/10/2024 | 7 | SOMNATH GHOSH | 0.75 | 0.75 | 100 | 100
248 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Laying of pipeline Including some Additional work at Mahatpur Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 833_AE-I/NACD-II | 01/08/2024 | 15 | BABA LOKNATH ENTERPRISE | 0.97 | 0.96 | 100 | 100
249 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Tengra & Mahatpur) | 411/NACD-II | 13/03/2024 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
250 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or damaged line repair due to construction of drain) at MAHATPUR ( Vill- MAHATPUR AND SURROUNDING AREA) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 221/NACD-II | 21/02/2024 | 360 | SAFTI PRIVATE LIMITED | 37.2 | 0 | 0 | 100
251 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Construction of 50 m3/hr capacity Iron Elimination Plant at mouza Mahatpur ,habitation Bhagabanpur under Mahatpur Public Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 49/NACD-II | 10/01/2025 | 179 | NILAY KUMAR BHATTACHARYA | 23.07 | 0 | 0 | 0
252 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Construction of pumphouse cum Chlorine room with sanitary and water supply arrangement at Bhagabanpur mouza in Mahatpur Piped water supply scheme in Chapra Block under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 132/NACD-II | 29/01/2025 | 30 | SHYAMAL KANTI GHOSH | 6.22 | 0 | 0 | 0
253 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Conversion of IEP to AIRP at Tengra Water Supply Scheme of capacity 36Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte. | 1360/NACD-II | 30/09/2024 | 60 | SUMIT GHOSH | 165.15 | 0 | 0 | 0
254 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Mahatpur Water Supply Scheme of capacity 172 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | 217/NACD-II | 16/02/2024 | 660 | HARBAUER INDIA (P) LTD | 358.83 | 28.51 | 7.94 | 50
255 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | New Sinking of 1 no. 250 mm X 150 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Mouza Mahatpur,Habitation of Bhagabanpur under Mahatpur Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II PHE Dte. | 1189/NACD-II | 02/09/2024 | 360 | SANDIP BISWAS | 10.4 | 0 | 0 | 88
256 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | New Sinking of 1 no. 250 mm X 150 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Mouza Mahatpur,Habitation of Jamredanga under Mahatpur Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II PHE Dte. | 1188/NACD-II | 02/09/2024 | 360 | SANDIP BISWAS | 10.4 | 0 | 0 | 85
257 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Construction of 50 m3/hr capacity Iron Elimination Plant at mouza Kathgara ,habitation Muslim Para under Mahatpur Public Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 997/NACD-II | 25/07/2024 | 542 | TAPU SAHA | 23.06 | 0 | 0 | 80
258 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Fatepur, Bahadurpur and Gongra Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1657/NACD-II | 30/12/2024 | 360 | CHANDAN ROY | 149.25 | 0 | 0 | 20
259 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Strengthening Work of existing boundary wall at Mahatpur Headwork site at Mahatpur Piped water supply scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | 1057/AE-I/NACD-II | 19/12/2024 | 30 | ST. ANTHONY ENTERPRISE | 3.96 | 0 | 0 | 100
260 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Construction of 50 m3/hr capacity Iron Elimination Plant at mouza Mahatpur ,habitation Jamredanga under Mahatpur Public Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 273/NACD-II | 03/03/2025 | 61 | SIRCON ENGINEERING SERVICES | 23.06 | 0 | 0 | 0
261 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Providing FHTC at leftout household alongwith necessary pipeline at Ichapur and Paliyanpur village under Madhabpur Water Supply Scheme and Mahatpur Water Supply Scheme at Chapra Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 114/AE-I/NACD-II | 04/06/2025 | 30 | ACHARJEE & ASSOCIATES | 4.61 | 0 | 0 | 0
262 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including laying of pipeline at TENGRA W/S Scheme in Tengra Village Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 673_AE-I/NACD-II | 28/03/2024 | 15 | ASHIM ENTERPRISE | 2.98 | 0 | 0 | 0
263 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Repair and Renovation work at Mahatpur 4th tube well Site under Mahatpur Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | 180/AE-I/NACD-II | 18/07/2025 | 30 | TAPAN SAHA | 3.23 | 0 | 0 | 0
264 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Laying of pipeline along reconnection due to construction of drain and land erosion at Mahatpur W/S Scheme in Chapra block in Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 1206/AE-I/NACD-II | 27/02/2025 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 0.92 | 0 | 0 | 100
265 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10199 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 800 cum for providing FHTC (Functional Household Tap Connection) for Mahatpur Water Supply Scheme in Chapra Block in Nadia District under Nadia Arsenic Civil Division- II, PHE Dte. | 938/NACD-II | 28/07/2025 | 90 | SANJOY BAKSHI | 27.51 | 0 | 0 | 0
266 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09815 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | 613/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.52 | 0 | 0 | 0
267 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09815 | Augmentation | Laying of distribution system including specials,valves & pipe supporting structure all complete based on actual estimate & Providing FHTC for Muktadaha Zone-I Water Supply Scheme under Nadia Division. | 1314/ND | 21/03/2022 | 90 | UMWELT ENGINEERS PVT LTD | 257.59 | 228.85 | 100 | 95
268 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09815 | Augmentation | Material Requisition To Resource Division | 1254/ND | 16/03/2022 | 0 | Resource Division | 10.25 | 0 | 0 | 0
269 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09815 | Augmentation | Material Requisition To Resource Division | 4286/ND | 29/09/2022 | 0 | Resource Division | 9.62 | 0 | 0 | 0
270 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09815 | Augmentation | Renovation of AIRP (Pressure Type ) of capacity 33.75 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Muktadaha Zone I PWSS under Nadia Division PHE Dte. | 1783/ND | 20/04/2023 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 201.98 | 24.44 | 100 | 90
271 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09815 | Augmentation | Quotation for Load enhacement charges and security deposit for Muktadaha Zone- 1, PH- 1 site. | BP-143-24-25 | 28/10/2024 | 0 | W.B.S.E.D.C.L (KARIMPUR C.C.C) | 0.18 | 0 | 0 | 0
272 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09815 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Mukatadaha Zone-I PWSS under Karimpur-I Block under Tehatta Sub Division under Nadia Division-,P.H.E Dte. under Jal Jeevan Mission(JJM) . | 425/ND | 27/01/2025 | 240 | GOPAL KIRTYANIYA | 32.88 | 0 | 0 | 95
273 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09815 | Augmentation | Laying of additional pipeline for providing balance FHTC and inerease functionality in Baro Jangal, Majlishpur, Basotipara Villages under Karimpur-I Block under Tehatta Sub-Division under Nadia Division, PHE Dte. | .4686/4533/P-3/ND | 09/10/2025 | 90 | JOY HIND TUBEWELL'S | 79.19 | 0 | 0 | 0
274 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09815 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Ground Based Water Supply Scheme under Karimpur-I Block under Nadia Division, P.H.E Dte. | 3336/ND | 15/07/2025 | 180 | THE TOWER CONSTRUCTION | 31.3 | 0 | 0 | 0
275 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. , SM/09816 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. | 614/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.57 | 0 | 0 | 0
276 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. , SM/09816 | Augmentation | laying of distribution pipe line including supply of 63mm dia UPVC pipe at Fazlnagar W/S scheme under Nadia Division P.H.E. Directorate. | 1191/PH | 03/12/2021 | 10 | A.P. POWER & CONCRETE | 0.61 | 0.57 | 100 | 100
277 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. , SM/09816 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer etc. for Augmentation to Accomodate FHTC at Pump House No.II (Zone-II) under Muktadaha W/S Scheme in Karimpur-I Block of Nadia District. NIET NO.- 13 of EE/EMD of 2022-23 (Sl. No.-02) | 3802/EMD | 14/10/2022 | 30 | AMIT DAS | 5.96 | 5.96 | 100 | 90
278 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. , SM/09816 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator etc. for Augmentation to Accommodate FHTC at Pump House No.I Zone II under Muktadaha WS Scheme, Dist. Nadia under Eastern Mechanical Division, PHE Dte. NIET No. 22 OF EE/EMD OF 2022-23 (Sl. No.- 02) | 6504/EMD | 01/12/2022 | 30 | WESTERN ENGINEERING CO. | 10.49 | 9.54 | 100 | 100
279 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. , SM/09816 | Augmentation | Material Requisition To Resource Division | 1449/ND | 25/03/2022 | 0 | Resource Division | 9.36 | 0 | 0 | 0
280 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. , SM/09816 | Augmentation | Material Requisition To Resource Division | 452/ND | 31/01/2022 | 0 | Resource Division | 1.56 | 0 | 0 | 0
281 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. , SM/09816 | Augmentation | Material Requisition To Resource Division | 1251/ND | 16/03/2022 | 0 | Resource Division | 1.42 | 0 | 0 | 0
282 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. , SM/09816 | Augmentation | Material Requisition To Resource Division | 4299/ND | 29/09/2022 | 0 | Resource Division | 0.79 | 0 | 0 | 0
283 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. , SM/09816 | Augmentation | Providing FHTC by Augmentation under jal swapna for Muktadaha Zone-II Water Supply scheme in Karimpur-I block of Nadia District under Nadia Division P.H.E. Dte. | 695/ND | 15/02/2022 | 60 | M/S KRISHNA MONDAL | 43.92 | 43.9 | 100 | 99
284 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. , SM/09816 | Augmentation | Wall Writing Work under Nadia Division P. H. Engineering Dte. | 1821/ND | 14/03/2024 | 31 | IMAGIN | 34.21 | 9.67 | 100 | 60
285 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. , SM/09816 | Augmentation | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | 6305/ND | 26/09/2024 | 30 | IMAGIN | 34.21 | 0 | 0 | 100
286 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. , SM/09816 | Augmentation | Construction of RCC Over Head Elevated Reservoir in connection with providing FHTC by augmentation under Jal Swapna for Muktadaha Zone-II Water Supply Scheme in Karimpur-I Block under RWS Nadia Sub-Divn. of Nadia District. | 1342/ND | 22/03/2022 | 960 | K.P. CONSTRUCTION | 48.71 | 31.37 | 64.41 | 95
287 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. , SM/09816 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 30 m3/hr capacity for Augmentation of Ground Based Water Supply Scheme at Muktadaha Zone-II including 3 Months Trial Run & 3 Years O&M to accommodate FHTC under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | 1493/ND | 04/03/2024 | 540 | MONDAL PRECISION PRIVATE LIMITED | 162.44 | 0 | 0 | 0
288 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. , SM/09816 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House and allied works for Muktadaha Zone-II PWSS and Murutia PWSS within Karimpur-I Block and Karimpur-II Block Under Tehatta Sub-Division under Nadia Division P.H.E. | 762/ND | 19/02/2025 | 90 | DEBASIS SAMADDAR | 74.08 | 0 | 0 | 0
289 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. , SM/09816 | Augmentation | Laying of additional pipeline for providing balance FHTC and inerease functionality in Baro Jangal, Majlishpur, Basotipara Villages under Karimpur-I Block under Tehatta Sub-Division under Nadia Division, PHE Dte. | .4686/4533/P-3/ND | 09/10/2025 | 90 | JOY HIND TUBEWELL'S | 79.19 | 0 | 0 | 0
290 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Preparation of DPR for augmentation of existing Bagakhali Zone-I, (Block -Tehatta-I) piped water supply schemes | 144/AE-I/NACD-II | 16/11/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 3.11 | 3.11 | 100 | 100
291 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Construction of Boundary wall with Grill Gate at Bagakhali Zone-I 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | 41/AE-II/NACD-II | 17/02/2022 | 30 | SHYAM SUNDAR SAHA | 4.08 | 4.05 | 99.29 | 100
292 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair and also piling work) at Bagakhali Zone-I ( Vill- Chhatina) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 996/NACD-II | 30/12/2021 | 45 | SANJIB DEY | 97.06 | 96.43 | 99.35 | 100
293 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 01/EE/NACD-II | 03/01/2022 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 95.95 | 95.91 | 100 | 100
294 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Khanjipur & Bagakhali Zone-I, W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 768./NACD-II | 22/09/2021 | 45 | TARUN KUMAR BHATTACHARYA | 84.44 | 40.26 | 61.56 | 100
295 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Head Work Site under Bagakhali Zone-I Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 1009/NACD-II | 29/11/2022 | 60 | DEBASISH DEY | 15.07 | 15.01 | 99.6 | 95
296 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte in soft copy for different PWSS under Nadia Arsenic Civil Division-II P.H.E. Dte. | 207./NACD-II | 07/02/2023 | 90 | JOY GOPAL GUPTI | 5.51 | 5.51 | 100 | 95
297 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair ) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 995/EE/NACD-II | 30/12/2021 | 45 | CHANDA CONSTRUCTION | 98.72 | 98.7 | 100 | 100
298 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Continuation Order for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte in soft copy for different PWSS under Nadia Arsenic Civil Division-II P.H.E. Dte. | 589/NACD-II | 22/05/2023 | 90 | JOY GOPAL GUPTI | 5.51 | 5.51 | 100 | 100
299 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bagakhali Zone-I) | 1149/NACD-II | 10/10/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
300 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BRITTIHUDA (Block- Chapra), BARNIA (Block- Tehatt II ), MAHATPUR (Block- Chapra ), MATIARY (Block- Krishnaganj), BAGAKHALI (Z-I) (Block- Tehatta I ), BARA NALDAH (Block- Tehatta II ) W/S Scheme, , Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 01) | 1120/EMD | 16/03/2023 | 30 | B.T. PROJECTS PVT. LTD | 91.82 | 9.88 | 78.39 | 60
301 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Repair and Renovation work at Bagakhali Zone-II H/W site with Plaster , Concrete,Earthwork in filling and other allied works under Nadia Arsenic Division-II,P.H.E.Dte. | 133/AE-II/NACD-II | 11/06/2024 | 30 | VAI ENTERPRISE | 4.81 | 0 | 0 | 0
302 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal | 414./NACD-II | 30/03/2023 | 366 | SAJAL SAHA | 4.98 | 0.37 | 7.35 | 0
303 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Continuation Work order for Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal. (From 01/04/2024- 30/06/2024) | 503/NACD-II | 01/04/2024 | 91 | SAJAL SAHA | 1.24 | 1.16 | 93.16 | 0
304 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Repair and Renovation work at Bagakhali Zone-I H/W site with Plaster , Concrete and other allied works. Under Nadia Arsenic Division-II,P.H.E.Dte. | 135/AE-II/NACD-II | 11/06/2024 | 30 | DEBASISH DEY | 2.79 | 0 | 0 | 0
305 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Bagakhali Zone-I W/S Scheme of Tehatta-I Block Mouza Ramjibanpur & Gopalpur of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 617/AE-I/NACD-II | 02/02/2024 | 15 | MALLICK ENTERPRISE | 0.86 | 0.86 | 100 | 100
306 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Bagakhali Zone-I W/S Scheme of Tehatta-I Block Mouza Bagakhali,Sahapur,Chatiana of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 616/AE-I/NACD-II | 02/02/2024 | 15 | MALLICK ENTERPRISE | 0.93 | 0.93 | 100 | 100
307 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Collection of Household Details at Prescribed Format through Mobile App/Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte. in soft copy for Bagakhali Zone-I PWSS under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 747/AE-I/NACD-II | 18/06/2024 | 60 | JOY GOPAL GUPTI | 4.84 | 4.84 | 100 | 98
308 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal | 414/NACD-II | 30/03/2023 | 366 | SAJAL SAHA | 4.98 | 4 | 100 | 100
309 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Continuation Work Order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bagakhali Zone-I (vILL- Sahapur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 223/NACD-II | 05/04/2022 | 90 | NANDY ENTERPRISES | 20.12 | 20 | 100 | 100
310 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Bhagakhali Zone-I & Jitpur Water Supply Scheme of capacity 27 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | 196/NACD-II | 12/02/2024 | 601 | SANDIP BISWAS | 103.73 | 0 | 0 | 80
311 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, Pincode:- 741101,West Bengal. (From 01/07/2024 to 30/06/2025) | 203/AE-II/NACD-II | 01/07/2024 | 365 | SAJAL SAHA | 4.98 | 4.52 | 90.79 | 0
312 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Bagakhali Zone-I and Bagakhali Zone-II Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1562/NACD-II | 05/12/2024 | 360 | DEBASIS SAMADDAR | 157.57 | 15.85 | 31.69 | 40
313 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09867 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bagakhali Zone-I W/s Scheme (Vill- Sahapur) in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. & Barnia Pwss under Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 128_NACD-II | 21/02/2022 | 90 | M/S NANDY ENTERPRISES | 102.45 | 0 | 0 | 100
314 | NADIA | Nadia Division | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/10715 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Karimpur-Jalangi Z-10A W/S Scheme in Karimpur-II Block of Nadia District under Nadia Division, P.H.E. Dte. | 320/TSD | 24/11/2021 | 30 | RADIANT | 2.66 | 2.66 | 100 | 100
315 | NADIA | Central Drilling | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/10715 | Augmentation | PROVIDING 300MM NOMINAL DIA UPVC PIPE CONFIRMING TO IS:12818:2010 AND OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL KARIMPUR-I BLOCK UNDER NADIA DIVISION CMSD-II (D), CDD PHE DTE | 287/CMSD -II (D) | 01/06/2022 | 15 | UNIVERSAL ENTERPRISES | 4.39 | 4.05 | 100 | 0
316 | NADIA | Central Drilling | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/10715 | Augmentation | PROVIDING 200MM NOMINAL DIA UPCVC PIPE CONFIRMING TO IS: 12818:2010 AND OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL KARIMPUR -II BLOCK UNDER NADIA DISTRICT CMSD-II(D) ,CDD PHE DTE | 282/ CMSD-II (D) | 01/06/2022 | 15 | UNIVERSAL ENTERPRISES | 4.44 | 0.72 | 100 | 0
317 | NADIA | Central Drilling | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/10715 | Augmentation | PROVIDING DRILLING CREWS AND OTHER MATERIALS FOR CONSTRUTION OF TUBE WELL 300 MM X 200MM X250 MTR DEPTH BY DEPARTMENTAL RIG MACHINE FOR KARIMPUR -II BLOCK UNDER NADIA DIST, CMSD-II(D) ,CDD,PHE DTE | 280/CMSD-II (D) | 01/06/2022 | 15 | UNIVERSAL ENTERPRISES | 3.52 | 3.52 | 100 | 0
318 | NADIA | Central Drilling | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/10715 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR JALANGI W/S SCH, KARIMPUR-I BLOCK UNDER NADIA DISTRICT, CDD, PHE DTE. | 1198/CDD | 11/11/2022 | 30 | DIPALI CONSTUCTION | 10.17 | 7.44 | 100 | 0
319 | NADIA | Central Drilling | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/10715 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR JALANGI W/S SCH, NADIA DISTRICT UNDER CMSD-II(D), CDD, PHE DTE. | 536/CMSD-II | 02/12/2022 | 10 | DIPALI CONSTUCTION | 0.98 | 0.74 | 100 | 0
320 | NADIA | Central Drilling | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/10715 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR JALANGI W/S SCH NADIA DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 542/CMSD-II | 07/12/2022 | 10 | ASHUTOSH DAS & CO | 0.98 | 0.7 | 100 | 0
321 | NADIA | Nadia Division | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/10715 | Augmentation | Material Requisition To Resource Division | 2295/ND | 29/05/2023 | 0 | Resource Division | 11.4 | 0 | 0 | 0
322 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/10715 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No. I , II under KARIMPUR JALANGI Zone X A WS Scheme, Block Karimpur-II, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-14) | 162/EMD | 06/01/2023 | 30 | S.B.ENTERPRISE | 9.73 | 8.78 | 93.58 | 70
323 | NADIA | Nadia Division | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/10715 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed Augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone X-A to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 254/ND | 16/01/2023 | 720 | SANJUKTA ENGINEERS | 157.12 | 108.69 | 81.04 | 98
324 | NADIA | Nadia Division | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/10715 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Karimpur Jalangi Zone-X(A) water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 7127/ND | 09/12/2024 | 360 | S.S.CONSULTANCY & CONSTRUCTION | 29.36 | 0 | 0 | 60
325 | NADIA | Nadia Division | Augmentation of Ground Water Based Jalangi Zone-X-A PWSS to accommodate FHTC in Karimpur-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/10715 | Augmentation | Laying of additional pipeline for Dakshin Gopalpur & Nandanpur mouzas under Karimpur Jalangi Zone- IX(A) PWSS under Tehatta Sub-Division under Nadia Division PHE Dte. | 7407/ND | 19/12/2024 | 270 | SHYAMAL SHIL | 54.11 | 0 | 0 | 30
326 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10573 | Augmentation | Survey , Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household under Gede W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Sl.No. 03) | 906/KSD | 29/11/2021 | 15 | HORIZEN | 2.48 | 2.39 | 25 | 100
327 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10573 | Augmentation | Material Requisition To Resource Division | 120/ND | 05/01/2023 | 0 | Resource Division | 10.97 | 0 | 0 | 0
328 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10573 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under GEDE W/S Scheme, Block- Krishnaganj , Dist. - Nadia. NIET No. 33 of EE/EMD of 2022-23 (Sl. No. -08) | 1177/EMD | 21/03/2023 | 30 | PS AND ASSOCIATES | 13.6 | 0 | 0 | 0
329 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10573 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
330 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10573 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 15 m3/hr at Gede Water Supply Scheme within Krishnaganj Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | 6222/ND | 23/09/2024 | 180 | GHOSH ENTERPRISE | 137.17 | 0 | 0 | 0
331 | NADIA | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10573 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Gede W/S Scheme (TW-I) , Krishanjganj Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 1233/CDD | 04/09/2023 | 370 | DEV AND COMPANY | 18.88 | 15.08 | 100 | 100
332 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10573 | Augmentation | Material Requisition To Resource Division | 261/ND | 11/01/2024 | 0 | Resource Division | 3.31 | 0 | 0 | 0
333 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10573 | Augmentation | WBSEDCL Quotation for New Service Connection to the newly constructed Head Work Site under GEDE W/S Scheme in Krishnaganj Block, P.H.E. Dte., Dist.- Nadia. (Application No. 3004956395) | BP-165-24-25 | 25/11/2024 | 0 | W.B.S.E.D.C.LTD (KRISHNAGANJ C.C.C) | 6.04 | 0 | 0 | 0
334 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10573 | Augmentation | Augmentation of Ground Based Water Supply Scheme at GEDE to accommodate FHTC within Krishnaganj Block under Krishnagar Sub-Division under Nadia Division, PHE Dte. | 3221/ND | 26/07/2023 | 740 | A.P. POWER & CONCRETE | 70.25 | 0 | 0 | 40
335 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10573 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Gede ground water based water supply scheme under Block_ Krishnaganj Dist. - Nadia under EMD, PHE Dte. SM/10573 | 1117/EMD | 04/06/2025 | 90 | KUNDU ELECTRICAL ENTERPRISE | 17.48 | 0 | 0 | 0
336 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/10009 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | 622/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.12 | 0 | 0 | 0
337 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/10009 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer etc. for Augmentation to Accomodate FHTC at Pump House No.II under Senpur W/S Scheme in Krishnagar-I Block of Nadia District. NIET NO.- 13 of EE/EMD of 2022-23 (Sl. No.-04) | 3804/EMD | 14/10/2022 | 30 | BISALAXMI ENTERPRISE | 6.12 | 6.02 | 98.38 | 0
338 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/10009 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator etc. for Augmentation to Accomodate FHTC at Pump House No.I under Senpur W/S Scheme in Krishnagar-I Block of Nadia District. NIET No.- 13 of EE/EMD of 2022-23 (Sl. No.-03) | 3803/EMD | 14/10/2022 | 30 | S.S.ENTERPRISES | 10.65 | 9.26 | 100 | 10
339 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/10009 | Augmentation | Supplementary works to completion of ongoing FHTC-related work at PH-II of Senpur W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | 598/EMSD-II | 22/08/2023 | 15 | BISALAXMI ENTERPRISE | 0.27 | 0.26 | 100 | 100
340 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/10009 | Augmentation | Supplementary works to completion of ongoing FHTC-related work at PH-I of Senpur W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | 753/EMSD-II | 09/10/2023 | 10 | S.S.ENTERPRISES | 0.88 | 0.84 | 100 | 100
341 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/10009 | Augmentation | Material Requisition To Resource Division | 1021/ND | 03/03/2022 | 0 | Resource Division | 15.96 | 0 | 0 | 0
342 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/10009 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 93.00 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Senpur PWSS under Nadia Division PHE Dte. | 1786/ND | 20/04/2023 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 234.23 | 41.65 | 100 | 57
343 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/10009 | Augmentation | Laying of Distribution system including specials, valves & pipe supporting structure all complete based on actual estimate & providing FHTC for Senpur Water supply Scheme in Nadia District under Nadia Division. | 1065/ND | 04/03/2022 | 90 | RADIANT | 388.55 | 295.38 | 100 | 80
344 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/10009 | Augmentation | Renovation of Settling Tank including construction of column and RCC wall inside the Settling Tank in Senpur Water Supply Scheme under RWS Nadia Sub Division under Nadia Division PHE. Dte. | 3989/ND | 22/07/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 17.12 | 16.95 | 100 | 100
345 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/10009 | Augmentation | WBSEDCL's Quotation of New Service Connection in Bulk Contract Demand to the Head Work Site under Senpur W/S Scheme in Krishnagar - I Block, PHE Dte., Dist.- Nadia. (Application No. 3004752314) |  | 18/06/2024 | 0 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 3.47 | 0 | 0 | 0
346 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/10009 | Augmentation | Additional work of Laying of pipe line including providing FHTC and all allied work in connection with Augmentation of Senpur PWSS within Krishnagar-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 5036/ND | 13/09/2024 | 450 | ROY ASSOCIATES | 56.45 | 0 | 0 | 20
347 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/10009 | Augmentation | Repair and Renovation Works of OHR, Boundary Wall at Head Work Site and Tube Well Site, Pump House at Head Work Site and Tube Well Sites, Contruction of Service Road at Head Work Site of Senpur Water Supply Scheme within Krishnagar -I Block under RWS Nadia Sub-Division under Nadia Division P.H.E. Dte. | 6410/ND | 01/10/2024 | 360 | M/S INDUSTRIAL CONSTRUCTION | 29.02 | 0 | 0 | 50
348 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/10009 | Augmentation | Additional work of providing FHTC and additional work of Laying Distribution System at Shimultala village within Krishnanagar-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 2851/ND | 18/06/2025 | 75 | SANDIP BISWAS | 46.75 | 0 | 0 | 0
349 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/10009 | Augmentation | Construction Of Chlorine storage Room (2m X 2m) At H/w Site of 13nos PWSS Under RWS Nadia Sub-Division PHE Dte. | 2853/ND | 18/06/2025 | 60 | ANJALI ENTERPRISE | 10.53 | 0 | 0 | 0
350 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part , SM/09970 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XI (Birohi) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 13) | 465/NAD-I | 10/03/2022 | 60 | GHOSH CONSTRUCTION | 91.98 | 87.29 | 100 | 100
351 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part , SM/09970 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-X (Subarnapur) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl No. 15) | 428/NAD-I | 07/03/2022 | 60 | IJABUL SEKH | 95.12 | 94.63 | 100 | 100
352 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part , SM/09970 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XIII (Digha) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 11) | 427/NAD-I | 07/03/2022 | 60 | SANJIB DEY | 81.56 | 77.79 | 100 | 100
353 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part , SM/09970 | Augmentation | Repair of 600 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Birohi Zone-XI under Surface W/S Scheme of Haringhata-Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 05) | 3157/NAD-I | 25/11/2022 | 60 | ONKAR ENTERPRISE | 24.53 | 24.44 | 100 | 100
354 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part , SM/09970 | Augmentation | Repair of 900 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House at Subarnapur Zone XI under Surface WS Scheme of Haringhata Chakdah Part under NAD -I PHE Dte (sl.no.07) | 3035 /NAD-I | 09/11/2022 | 60 | DIVINE | 33.26 | 30.28 | 100 | 100
355 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part , SM/09970 | Augmentation | Repair of 500 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall Pump House at Digha Zone-XIII under Surface W/S Scheme of Haringhata-Chakdah Part under NAD-I PHE Dte (Sl.no.06) | 1691/NAD-I | 08/09/2022 | 60 | CHOWDHURY & CO. | 28.14 | 27.56 | 100 | 100
356 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part , SM/09970 | Augmentation | Augmentation work for Zone-XI (Birohi) at Haringhata Block under Jal Jeevan Mission (JJM) by Augmentation of Surface Water Based PWSS for Haringhata Zone-X, (Subarnapur), Zone-XI (Birohi) and Zone-XIII (Digha) Part-III under Nadia Arsenic Division-I, PHE Dte. | 38/AE-I/NAD-I | 07/01/2023 | 15 | J & T ENTERPRISE | 4.83 | 4.83 | 100 | 100
357 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part , SM/09970 | Augmentation | Augmentation work for Zone-X (Subarnapur) at Haringhata Block under Jal Jeevan Mission (JJM) by Augmentation of Surface Water Based PWSS for Haringhata & Chakdah (Part) for Zone-X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha) Part-III under Nadia Arsenic Division-I, PHE Dte. | 39/AE-I/NAD-I | 07/01/2023 | 15 | M/S DIPAK ENTERPRISE | 4.83 | 4.83 | 100 | 100
358 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part , SM/09970 | Augmentation | Jackpushing of Pipeline at Ayeshpur More (Near Petrol Pump) at NH-34 and other allied works under JalJeevan Mission (JJM) for Zone-XI at Birohi at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-XI, Birohi under JJM underNadia Arsenic Division-I, PHE Dte. (SL.02) | 512 / NAD-I | 10/03/2023 | 30 | M/S DIPAK ENTERPRISE | 64.25 | 7.83 | 100 | 35
359 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part , SM/09970 | Augmentation | Jackpushing of Pipeline at Birohi More(Underpass) at NH-34 and other allied works under Jal Jeevan Mission (JJM) for Zone-XI at Birohi at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-XI,Birohi under JJM under Nadia Arsenic Division-I, PHE Dte. (SL.09) | 513 /NAD-I | 10/03/2023 | 30 | M/S DIPAK ENTERPRISE | 66.19 | 66.18 | 100 | 100
360 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone - X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part , SM/09970 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission for Zone-XIII, (Digha), Part-III at Haringhata Block by augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (sl.22) | 828/NAD-I | 31/03/2023 | 21 | NISHITH BANERJEE | 14.03 | 0 | 0 | 100
361 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/11815 | Augmentation | Name of Work : Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Baruipara W/S Scheme in Karimpur-I Block of Nadia District under Nadia Division, P.H.E. Dte. | 289/TSD | 24/11/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.82 | 4.82 | 100 | 100
362 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/11815 | Augmentation | Material Requisition To Resource Division | 4307/ND | 29/09/2022 | 0 | Resource Division | 41.46 | 0 | 0 | 0
363 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/11815 | Augmentation | Material Requisition To Resource Division | 1850/ND | 26/04/2023 | 0 | Resource Division | 56.81 | 0 | 0 | 0
364 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/11815 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 174 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Baruipara to accommodate FHTC within Karimpur-I block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | 4192/ND | 31/07/2024 | 180 | MONDAL ENTERPRISE | 381.95 | 0 | 0 | 0
365 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/11815 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Baruipara Ground Based Water Supply Scheme under Karimpur-I Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Baruipara at Karimpur-I Block by Augmentation of Ground Water based PWSS for Baruipara Water Supply Schemes under Nadia Division, PHE Dte. | 7364/ND | 18/12/2024 | 60 | M/S ARATI ENTERPRISE | 23.38 | 0 | 0 | 0
366 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/11815 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Baruipara W/S Scheme (T/W-I) , Karimpur-I Block under Nadia District, Central Drilling Division, P.H.E. Dte.(2ed Call) | 507/CDD | 01/06/2023 | 303 | UNIVERSAL ENTERPRISES | 18.86 | 14.69 | 100 | 100
367 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/11815 | Augmentation | Quotation charges for new service connection and security deposit at Baruipara PH-IV under EMSD-III,Nadia | BP-182 | 13/12/2024 | 0 | WBSEDCL KARIMPUR CCC | 3.86 | 0 | 0 | 0
368 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/11815 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Baruipara to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 3798/ND | 02/09/2022 | 1260 | M/S S.S ENTERPRISE | 732.02 | 577.34 | 78.87 | 74
369 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/11815 | Augmentation | Construction Of Pump House (3.6x 3.0m) Including Sanitary Arrangement and consruction of Boundary wall at 4th Tube Well Site of Baruipara Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | 1626/ND | 07/03/2024 | 450 | BISHAL CONSTRUCTION | 10.94 | 0 | 0 | 100
370 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/11815 | Augmentation | Laying pipe line for distribution system and rising main for Baruipara PWSS under augmentation of Baruipara PWSS under Tehatta Sub-Division PHE Dte. | 7262/ND | 13/12/2024 | 270 | M/S S.S ENTERPRISE | 54.36 | 0 | 0 | 0
371 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/11815 | Augmentation | Providing FHTC & Alied Pipelines and other Works for left out habitation under Karimpur -I Block under Tehatta Sub-Division under Nadia Division, PHE Dte. | 7464/ND | 20/12/2024 | 90 | APURBA MANDAL | 299.14 | 0 | 0 | 0
372 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/11815 | Augmentation | Additional pipeline for increasing Functionality in Basatipara, Mojlishpur and Borojangal villages through MANIFOLD under Karimpur-I Block under Tehatta Sub Division under Nadia Division-,P.H.E Dte. under Jal Jeevan Mission(JJM). | 3256/ND | 10/07/2025 | 180 | GOPAL KIRTYANIYA | 15.51 | 0 | 0 | 20
373 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/11815 | Augmentation | Laying of additional pipe lines and allied works to increase the functionality in Brojonathpur, Gandhina villages under Karimpur-I Block under Nadia Division, PHE Dte. | 4685/4533/P-3/ND | 09/10/2025 | 90 | JOY HIND TUBEWELL'S | 46.3 | 0 | 0 | 0
374 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/11815 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No. I,II III under Baruipara WS Scheme, Block Karimpur I, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-13) | 161-EMD | 06/01/2023 | 726 | P.K. ENGINEERING | 22.81 | 0 | 0 | 100
375 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KAMGACHI PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11509 | Augmentation | Material Requisition To Resource Division | 1884/ND | 26/04/2023 | 0 | Resource Division | 44.93 | 0 | 0 | 0
376 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KAMGACHI PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11509 | Augmentation | Material Requisition To Resource Division | 2312/ND | 29/05/2023 | 0 | Resource Division | 42.04 | 0 | 0 | 0
377 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KAMGACHI PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11509 | Augmentation | Material Requisition To Resource Division | 28/ND | 03/01/2024 | 0 | Resource Division | 32.2 | 0 | 0 | 0
378 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KAMGACHI PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11509 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Kamgachi Zone-II to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. (PART-II) | 5354/ND | 22/12/2022 | 1080 | JOY HIND TUBEWELL'S | 340.71 | 268.53 | 78.81 | 100
379 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KAMGACHI PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11509 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Kamgachi Zone-I to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. (PART-II) | 16/ND | 03/01/2023 | 1078 | KINGS & CO. | 415.48 | 285.42 | 68.7 | 85
380 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KAMGACHI PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11509 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
381 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-I to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte , SM/11978 | Augmentation | Material Requisition To Resource Division | 4931/ND | 25/11/2022 | 0 | Resource Division | 166.85 | 0 | 0 | 0
382 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-I to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte , SM/11978 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
383 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-I to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte , SM/11978 | Augmentation | Laying of distribution system including specials, valves & pipe supporting structure all complete and providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of ground based water supply scheme at Naserkhuli Zone-I to accommodate FHTC within Ranaghat-II Dev. block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 4238/ND | 28/09/2022 | 883 | SUPRITI ENTERPRISE | 533.43 | 334.09 | 89.96 | 100
384 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Soil Investigation for Construction of 3 (Three) Nos. of Overhead Reservoir of staging height of 20 mtr. Under Nadia Arsenic Civil Division-II P.H.E. Dte. Site - Sanatanpur W/s Scheme, Sikra W/s Scheme, Suruppur W/s Scheme | 253/AE-I/NACD-II | 25/02/2022 | 15 | G. MITRA & ASSOCIATES | 2.29 | 2.29 | 100 | 100
385 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
386 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
387 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Head Work Site under Sanatanpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 89/NACD-II | 10/01/2023 | 60 | NISHITH BANERJEE | 18.62 | 18.55 | 99.6 | 85
388 | NADIA | Eastern Mechanical | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Sanatanpur Piped Water SupplyScheme, Block: Hanskhali, Dist. Nadia Under EMD, PHE Dte. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 04) | 1577/EMD | 24/04/2023 | 30 | M/S. G.P. ENTERPRISE | 41.76 | 0 | 0 | 0
389 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Construction for priliminary work of the approch road at Head Works site of Sanatanpur Water Supply Scheme in Hanskhali Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | 416_1/AE_I/NACD-II | 08/08/2023 | 15 | KANIKA CONSTRUCTION | 0.99 | 0 | 0 | 0
390 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Sanatnpur water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | 18/AE-II/NACD-II | 11/04/2022 | 60 | CHANDAN ROY | 2.83 | 2.82 | 100 | 100
391 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Sanatanpur water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 219/NACD-II | 05/04/2022 | 60 | CHANDAN ROY | 5.38 | 5.33 | 100 | 100
392 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Sanatanpur and Hatkhola Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | 433/NACD-II | 07/07/2022 | 60 | B.M. ENGINEERING & CONSTRUCTION | 42.16 | 19.51 | 100 | 100
393 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Sanatanpur Water Supply Scheme of Hanskhali Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 631/NACD-II | 06/09/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.57 | 3.57 | 100 | 100
394 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Additional Parallal Pipeline Laying of Distribution system for smooth supply of water without damaging the higher dia pipelines and Providing Functional House Hold Tap Connection (FHTC) for Sanatanpur and adjoining mouzas under Sanatanpur Water Supply Scheme of Hanskhali Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 151/NACD-II | 17/01/2023 | 20 | GHOSH ENTERPRISE | 8.77 | 8.76 | 100 | 90
395 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of of site locations under Hanskhali Block of Nadia District through Jadavpur University. (Name of Scheme Sanatanpur) | 868/NACD-II | 10/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
396 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Material Requisition To Resource Division | 404/NACD-II | 04/07/2022 | 0 | Resource Division | 55.89 | 0 | 0 | 0
397 | NADIA | Eastern Mechanical | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Electricity bill for new service connection at Sanatanpur PH- II,LJ no. 24 KH-1609, Plot-160 | 21/PFMS/EMD | 11/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.68 | 0 | 0 | 0
398 | NADIA | Eastern Mechanical | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Electricity bill for new service connection at Sanatanpur PH- I,LJ no. 24 KH-995, Plot-658 | 20/PFMS/EMD | 08/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.98 | 0 | 0 | 0
399 | NADIA | Eastern Mechanical | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under SANATANPUR W/S Scheme (Block : Hanskhali) Dist.- Nadia. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 02) | 1575/EMD | 24/04/2023 | 30 | PADMA ENGINEERING CO. | 18.99 | 18.42 | 97 | 100
400 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 35 cum/Hour capacity for Sanatanpur Water Supply Scheme within Hanskhali block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1190/NACD-II | 02/09/2024 | 180 | MONDAL PRECISION PRIVATE LIMITED | 165.43 | 0 | 0 | 0
401 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Laying of Rising Main of Sanatanpur Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | 24/AE-II/NACD-II | 18/04/2022 | 30 | ARIT KUMAR PAL | 4.96 | 3.5 | 100 | 100
402 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Sanatanpur and adjoining mouzas under Sanatanpur Water Supply Scheme of Hanskhali Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | 305/NACD-II | 20/05/2022 | 90 | A.P. POWER & CONCRETE | 139.9 | 111.27 | 100 | 100
403 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Earth work in filling in ditches at Sanatanpur H/W site & 2nd Tube Well Site for development of land in connection with proposed T/W Sinking & Pump House construction at Sanatanpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 63/AE-II/NACD-II | 28/06/2022 | 20 | SUMIT GHOSH | 1.23 | 1.22 | 100 | 100
404 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Acceptance cum work order "Conversion of IEP to AIRP at Shyamnagar Water Supply Scheme of capacity 67 Cu.m/hr in Krishnaganj Block under Nadia Arsenic Civil Division -II, PHE Dte." | 185/NACD-II | 09/02/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 194.41 | 52.49 | 100 | 100
405 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Sanatanpur water supply scheme of Haskhali Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | 383/NACD-II | 24/03/2023 | 1096 | SUBHASH BOSE | 119.12 | 0 | 0 | 35
406 | NADIA | Nadia Arsenic Civil Division II | SANATANPUR PIPED WATER SUPPLY SCHEME , SM/10409 | New | Construction of 87 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Matiary Water Supply Scheme in Krishnaganj block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | 1311/NACD-II | 20/09/2024 | 180 | JOY HIND TUBEWELLS | 232.26 | 0 | 0 | 0
407 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11638 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 1/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. ( Sl.No .02 ) | 204/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.6 | 4.57 | 100 | 100
408 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11638 | Augmentation | Material Requisition To Resource Division | 116/ND | 05/01/2023 | 0 | Resource Division | 314.2 | 0 | 0 | 0
409 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11638 | Augmentation | Restoration of road from Dhubulia 33 KV Substation to Sujanpur (WB-14-250) | 301/PFMS | 02/10/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 18.01 | 0 | 0 | 0
410 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11638 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | 3537/ND | 11/08/2023 | 782 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 313.52 | 42.27 | 20
411 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11638 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 0 | 30
412 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11638 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub Division, PHE Dte for supervision of JJM works for the period of 01/01/2025 to 31/12/2025 | 2666/KSD | 31/12/2024 | 365 | AVINABA ENGINEERING CONCERN | 4.8 | 0 | 0 | 0
413 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11739 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 9A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 132/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.51 | 4.44 | 100 | 100
414 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11739 | Augmentation | Material Requisition To Resource Division | 108/ND | 05/01/2023 | 0 | Resource Division | 297.12 | 0 | 0 | 0
415 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11739 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 714.23 | 91.1 | 47
416 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Bahirgachi Zone-II water supply scheme underChapra Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08306 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Bahirgachhi Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1066/NACD-II | 25/09/2020 | 15 | BINOY DAS | 4.99 | 0 | 0 | 0
417 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIII, (Tarinipur), Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07447 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIII, (Tarinipur), Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) | 90/NAD-I | 22/01/2021 | 60 | APURBA MANDAL | 70.37 | 140.04 | 77.52 | 100
418 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIII, (Tarinipur), Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07447 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna Zone-II Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. (Sl no.-02) Tender No. 229/NAD-I/2020-2021. | 291/NAD-I | 04/02/2021 | 45 | CHANDAN ROY | 42.81 | 4.87 | 200 | 0
419 | NADIA | Nadia Division | Mini Piped Water Supply Scheme at Uttar Bishnupur Village, Block- Ranaghat-II, District- Nadia. , SM/12005 | New | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Mini Piped Water Supply Scheme Gazna (Part) (100 Households) to accommodate FHTC in Hanskhali block & Providing FHTC and allied works for- Ground Water Based Mini Piped Water Supply Scheme in Arsenic affected area at Uttar Bishnupur, Block : -Ranaghat-II, Nadia District under Nadia Division P.H.E Dte. | 3024/ND | 14/07/2023 | 366 | ABDUL ALIM MONDAL | 79.83 | 28.16 | 71.54 | 78
420 | NADIA | Nadia Division | Mini Piped Water Supply Scheme at Uttar Bishnupur Village, Block- Ranaghat-II, District- Nadia. , SM/12005 | New | Material Requisition To Resource Division | 271/ND | 11/01/2024 | 0 | Resource Division | 0.6 | 0 | 0 | 0
421 | NADIA | Nadia Division | Mini Piped Water Supply Scheme at Uttar Bishnupur Village, Block- Ranaghat-II, District- Nadia. , SM/12005 | New | New Service Connection charges for Uttar Bishunupur Mini Piped water supply scheme | 243/PFMS | 13/09/2024 | 0 | W.B.S.E.D.C.L (GROUP ARANGHATA C.C.C) | 0.21 | 0 | 0 | 0
422 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11873 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under NARAYANPUR W/S Scheme, Block- Karimpur II , Dist. - Nadia. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 09) | 1581/EMD | 24/04/2023 | 30 | CHANDIMATA ELECTRICALS | 15.43 | 0 | 0 | 0
423 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11873 | Augmentation | Material Requisition To Resource Division | 1906/ND | 27/04/2023 | 0 | Resource Division | 18.64 | 0 | 0 | 0
424 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11873 | Augmentation | Material Requisition To Resource Division | 2315/ND | 29/05/2023 | 0 | Resource Division | 0.92 | 0 | 0 | 0
425 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11873 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed Augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 200 Cum Capacity 20 Mtr. height RCC Over Head Reservoir (Excluding Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for construction of one no. 200 Cum OHR of Staging Height 20 Mtr. for Augmentation of Ground Based Water Supply Scheme at Narayanpur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 966/ND | 09/03/2023 | 1096 | M/S S.S ENTERPRISE | 759.95 | 205.75 | 40.95 | 55
426 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11807 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 2A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 117/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.13 | 4.09 | 100 | 100
427 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11807 | Augmentation | RESTORATION OF ROAD FLANK OF DEBAGRAM KATWAGHAT ROAD FROM CH. 0.00 KM TO 17.40 KMP. | 599/PFMS | 14/03/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 8.33 | 0 | 0 | 0
428 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11807 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 367.26 | 87.78 | 47
429 | NADIA | Nadia Arsenic Division I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14422 | New | Preparation of Detailed Project Report (DPR) for Parbatipur Water Supply Scheme at Ranaghat-I Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(SL.05) | 66 / NAD-I | 20/01/2023 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 10.97 | 10.87 | 100 | 100
430 | NADIA | Eastern Mechanical | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14422 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation NEW Tube Well in connection to Accommodate FHTC at Pump House No.-I & II (Zone-I and II) under Parbatipur ground water based water supply scheme under Block_ Ranaghat-I Dist. - Nadia under EMD, PHE Dte. (SM/14422) | 2688/EMD | 20/11/2024 | 30 | GOENKA ENTERPRISE | 47.91 | 0 | 0 | 0
431 | NADIA | Nadia Arsenic Division I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14422 | New | Material Requisition To Resource Division | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 33.39 | 0 | 0 | 0
432 | NADIA | Nadia Arsenic Division I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14422 | New | Material Requisition To Resource Division | 1750/NAD-I | 25/10/2024 | 0 | Resource Division | 39 | 0 | 0 | 0
433 | NADIA | Nadia Arsenic Division I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14422 | New | Material Requisition To Resource Division | 847/NAD-I | 04/06/2024 | 0 | Resource Division | 37.63 | 0 | 0 | 0
434 | NADIA | Nadia Arsenic Division I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14422 | New | Laying of Rising Main, Laying distribution system and Providing FHTC (Functional Household Tap Connection), Soil Investigation for the work of construction of 400 cum OHR staging height 20 mtr. Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials and construction of Pump House, Boundary Wall, Service Road and other allied Works at Head Work & 2nd site under Jal Jeevan Mission for Parbatipur Zone-II Water Supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E Dte.(Sl. NO. 06) | 1740/NAD-I | 19/07/2023 | 1095 | H I ENTERPRISE | 628.88 | 0 | 0 | 61
435 | NADIA | Nadia Arsenic Division I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14422 | New | Laying of Rising Main, Laying distribution system and Providing FHTC (Functional Household Tap Connection), Soil investigation for the work of construction of 400 cum OHR staging height 20 mtr., Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials and Construction of Pump house, Boundary Wall, Service Road and other allied Works at Head work & 2nd site under Jal Jeevan Mission for Parbatipur Zone- I Water Supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. | 1743/NAD-I | 19/07/2023 | 1095 | M/S TARAK CHANDRA PAUL | 633.23 | 0 | 0 | 54
436 | NADIA | Nadia Arsenic Division I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14422 | New | Interconnection of pipeline from manifold to different direction of distrtibution pipeline including laying of balance pipeline and FHTC along with allied works at Nrisinghapur (Chandkuri) under Parbatipur Piped Water Supply Scheme at Parbatipur & Gopalpur Mouzas under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 03) | 529/NAD-I | 03/07/2025 | 90 | CHOWDHURY & CO. | 192.83 | 0 | 0 | 0
437 | NADIA | Nadia Arsenic Division I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14422 | New | Augmentation of pipeline and FHTC including repair of Boundary wall at Saguna, Aluipara & Hijuli Mouzas and Parbatipur & Gopalpur Mouzas under Parbatipur Piped Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 05) | 123/NAD-I | 22/04/2025 | 60 | CHOWDHURY & CO. | 85.69 | 0 | 0 | 0
438 | NADIA | Nadia Arsenic Division I | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14422 | New | Laying of pipeline for functionally of FHTC including new FHTC connection at Phuliapara, Durlav para, Narasinghanagar, Chapatala & Beharia Mouza under Fulia G.P. & Gopalpur & Parbatipur mouza under Parbatipur PWSS under Nadia Arsenic Division-I, P.H.E. Dte. (2nd Call) [Sl. No. 04] | 664/NAD-I | 21/07/2025 | 120 | BUDDHADEV MONDAL | 87.35 | 0 | 0 | 0
439 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Ramnagar Water Supply Scheme In Hanskhali Block District Nadia. , SM/16363 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
440 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Gazna Water Supply Scheme In Hanskhali Block District Nadia. (Two Stage Pumping) , SM/16368 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
441 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Bagakhali(Zone-I & II) Water Supply Scheme in Tehatta-I Block, Dist.-Nadia. , SM/16329 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
442 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Bahadurpur Water Supply Scheme in Tehatta-I Block, Dist.-Nadia. , SM/16330 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
443 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Nischintapur Water Supply Scheme in Tehatta-I Block, Dist.-Nadia. , SM/16337 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
444 | NADIA | Eastern Mechanical | Mini Piped Water Supply Scheme at Dharammpur (Part-A) village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. , SM/16100 | New | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 0 | 80
445 | NADIA | Nadia Arsenic Civil Division II | Mini Piped Water Supply Scheme at Dharammpur (Part-A) village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. , SM/16100 | New | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Dharammpur (Part-A) of Tehatta-II Block under Nadia Arsenic Civil Division-II PHE Dte. | 583/NACD-II | 17/05/2023 | 90 | PAPAN ROY | 25.74 | 0 | 0 | 0
446 | NADIA | Nadia Arsenic Civil Division II | Mini Piped Water Supply Scheme at Shatikhali (Part-B) village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. , SM/16103 | New | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Shatikhali (Part-B) of Tehatta-II Block under Nadia Arsenic Civil Division-II PHE Dte | 563/NACD-II | 11/05/2023 | 90 | ASIT PRAMANIK | 29.47 | 0 | 0 | 0
447 | NADIA | Eastern Mechanical | Mini Piped Water Supply Scheme at Shatikhali (Part-B) village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. , SM/16103 | New | Quotation for New service connection charges and security deposit for Satiakhali Part- B. | BP-200-24-25 | 17/12/2024 | 0 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 0.79 | 0 | 0 | 0
448 | NADIA | Eastern Mechanical | Mini Piped Water Supply Scheme at Shatikhali (Part-B) village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. , SM/16103 | New | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 0 | 80
449 | NADIA | Eastern Mechanical | Mini Piped Water Supply Scheme at Jaba(Part-B) village, Block- Krishnagar-I, Nadia District, under Nadia Arsenic Civil Division-II. , SM/16108 | New | Quotation for new service connection and security deposit at Java (Part-B) PWSS, Krishnanagar- I | BP-107-24-25 | 09/09/2024 | 0 | W.B.S.E.D.C.L (GROUP KRISHNAGAR ROAD STATION C.C.C) | 0.1 | 0 | 0 | 0
450 | NADIA | Eastern Mechanical | Mini Piped Water Supply Scheme at Jaba(Part-B) village, Block- Krishnagar-I, Nadia District, under Nadia Arsenic Civil Division-II. , SM/16108 | New | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 0 | 80
451 | NADIA | Nadia Arsenic Civil Division II | Mini Piped Water Supply Scheme at Jaba(Part-B) village, Block- Krishnagar-I, Nadia District, under Nadia Arsenic Civil Division-II. , SM/16108 | New | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Jaba (Part-B) of Krishnagar-I Block under Nadia Arsenic Civil Division-II PHE Dte | 567/NACD_II | 11/05/2023 | 813 | SUMIT GHOSH | 28.39 | 14.63 | 51.53 | 100
452 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09868 | Augmentation | Preparation of DPR for augmentation of existing Bahirgachi Zone-I, (Block - Chapra) piped water supply schemes | 151/AE-I/NACD-II | 16/11/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.61 | 2.61 | 100 | 100
453 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09868 | Augmentation | Supply of CIDF Sluice valve and DI specials for vavle for facilitate Functional House Hold Connection of Bahirgachhi Zone-I Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | 280/AE-I/NACD-II | 04/03/2022 | 5 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.88 | 4.88 | 100 | 100
454 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09868 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bahirgachhi Zone-I ( Vill-Kukra Daha) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 821/NACD-II | 10/11/2022 | 60 | ABDUL ALIM MONDAL | 14.27 | 14.23 | 100 | 100
455 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09868 | Augmentation | Continuation work order for Supply of CIDF Sluice valve and DI specials for vavle for facilitate Functional House Hold Connection of Bahirgachhi Zone-I Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | 302/AE-I/NACD-II | 17/03/2022 | 5 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.77 | 4.77 | 100 | 100
456 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09868 | Augmentation | Functional House Hold Tap Connection for providing connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Remaining School only) Bahirgachhi Zone-I W/s Scheme at Chapra Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 349/NACD-II | 22/03/2023 | 20 | SAMARESH GHOSH | 1.04 | 1.03 | 99.51 | 85
457 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09868 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bahirgachi Zone-I) | 1115/NACD-II | 06/10/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
458 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09868 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline at BAHIRGACHI ZONE-I ( Vill- BAHIRGACHI AND SURROUNDING AREA) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 230/NACD-II | 21/02/2024 | 45 | SAFTI PRIVATE LIMITED | 38.98 | 0 | 0 | 0
459 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09868 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Bahirgachi Z-I Water Supply Scheme of capacity 40 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | 207/NACD-II | 15/02/2024 | 90 | SATYABRATA CHAKRABORTY | 143.08 | 0 | 0 | 0
460 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09868 | Augmentation | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Bahirgachi Zone-I W/S Scheme of Chapra Block Mouza Mathurapur & Kukradaha of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 613/AE-I/NACD-II | 02/02/2024 | 15 | MALLICK ENTERPRISE | 0.97 | 0.97 | 100 | 100
461 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09868 | Augmentation | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Bahirgachi Zone-I W/S Scheme of Chapra Block Mouza Bahirgachi of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 614/AE-I/NACD-II | 02/02/2024 | 15 | P. BISWAS & CO | 0.45 | 0.45 | 100 | 100
462 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09868 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to accommodate FHTC under Bahirgachi (Z-I) (Source Augmentation, Mathurapur) PWSS under Block_ Chapra Dist. - Nadia under EMD, PHE Dte. SM/09868 | 697/EMD | 04/04/2025 | 30 | M/S. MANDAL ENTERPRISE | 10.55 | 0 | 0 | 0
463 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09868 | Augmentation | Improvement of connecting road within Ichapur Road and the Head Works site of Madhabpur and Bahirgachhi Zone-I Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | 17/AE-I/NACD-II | 11/04/2025 | 60 | GHOSH ENTERPRISE | 4.84 | 0 | 0 | 0
464 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09868 | Augmentation | Comprehensive augmentation in technical regards including aquifer management with extraction, compliance of Ground water contamination removal as per IS 10500 with subsequent amendments and composite RCC Cum masonry structures at Mouza- Mathurapur (under Bahirgachi zone I Piped Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 330/NACD-II | 11/03/2025 | 60 | TARUN GHOSH | 54.03 | 0 | 0 | 0
465 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Joania Water Supply Scheme in Krishnagar-I Block, Dist.- Nadia. , SM/16831 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
466 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Chandpur Water Supply Scheme in Krishnagar-I Block, Dist.- Nadia. , SM/16838 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
467 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Paschim Bhatjangla Water Supply Scheme (Zone - I & II) in Krishnagar-I Block, Dist.- Nadia. , SM/16842 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
468 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Thanapara Water Supply Scheme in Karimpur-II Block of District Nadia , SM/16810 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
469 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Boalia Water Supply Scheme in Shantipur Block, Dist,- Nadia , SM/17265 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
470 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ITLA(PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17220 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 57 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Itla PWSS under Nadia Division PHE Dte. | 2996/ND | 13/07/2023 | 720 | TARUN KUMAR BHATTACHARYA | 82.59 | 0 | 0 | 50
471 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ITLA(PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17220 | Augmentation | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at ITLA (PHASE-II) Piped Water Supply Scheme, Block: KRISHNANAGAR-I, Dist. Nadia Under EMD, PHE Dte. | 6366/EMD | 17/10/2023 | 728 | JAL PRAVAHIKA PVT. LTD. | 41.6 | 0 | 0 | 100
472 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone II PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17206 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, Zone-II(Phase-II) under Teinpur ground water based water supply scheme under Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. | 6394/EMD | 30/10/2023 | 30 | D.S. ENTERPRISE | 8.45 | 0 | 0 | 0
473 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone II PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17206 | Augmentation | Proposed Augmentation of Laying Rising Main System and Sinking of Replacement Tube Well at Head Work Site of Teinpur Zone-II [Phase-II] Ground Based Piped Water Supply Scheme. | 1218/ND | 21/03/2023 | 60 | JOY HIND TUBEWELL'S | 14.37 | 9.64 | 100 | 85
474 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone II PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17206 | Augmentation | Laying of 160 mm dia HDPE pipe line, 75 mm & 125 mm UPVC Pipe line for Augmentation of Rising Main System for distribution pipeline with interconnection along with road restoration at village Dogachhi, Block Karimpur-II under Nadia Division, P.H.E. Dte. | 1803/ND | 22/04/2025 | 180 | SUBHASH BOSE | 32.54 | 0 | 0 | 51
475 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna Zone-I Part-I, at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme , SM/08009 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna, Zone-I, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 769/NAD-I | 04/05/2021 | 60 | MALLICK ENTERPRISE | 97.12 | 185.73 | 100 | 100
476 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna Zone-I Part-I, at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme , SM/08009 | Retrofitting | Material Requisition To Resource Division | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 1.73 | 0 | 0 | 0
477 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Anulia Water Supply Scheme in Ranagtat-I Block under District Nadia , SM/18196 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
478 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Tiorkhali Water Supply Scheme in Nabadwip Block of District Nadia , SM/17279 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
479 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Habibpur Water Supply Scheme in Ranagtat-I Block under District Nadia , SM/18199 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
480 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Kamgachi (Z-I & II) Water Supply Scheme in Ranagtat-I Block under District Nadia , SM/18201 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
481 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Radhakantapur Water Supply Scheme in Ranagtat-I Block under District Nadia , SM/18204 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
482 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Duttaphulia (Z-I & II) Water Supply Scheme in Ranagtat-II Block under District Nadia , SM/18211 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
483 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Kamalpur (Z-I & II) Water Supply Scheme in Ranagtat-II Block under District Nadia , SM/18215 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
484 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Banpur Water Supply Scheme in Krishnaganj Block, Dist.-Nadia. , SM/18067 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
485 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Kadipur Water Supply Scheme in Krishnaganj Block, Dist.-Nadia. , SM/18061 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
486 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & , SM/11455 | Augmentation | Interconnection between node point 1 to node point 105 in connection with augmentation work at Priyanagar under Zone-XI, Chanduria W/S Scheme under Jal Jeevan Mission under Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte.(SL.11) | 535 /NAD-I | 13/04/2023 | 21 | ABDUL ALIM MONDAL | 33.72 | 33.72 | 100 | 0
487 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & , SM/11455 | Augmentation | Jack Pushing of Clearwater Rising Main Pipeline at Chakdah Chowmataha Crossing along NH-12 and other allied works under Jal Jeevan Mission (JJM) for Joykrishnapur (Zone-II), Chanduria (Zone-XI), Simurali (Zone-X), Ghetugachi (Zone-IX), Baraberia (Zone-VIII), Rukminidanga (Zone-IV) at Chakdah Block under Surface Water based PWSS for Chakdah Water Supply Scheme in connection with Providing FHTC for Joykrishnapur (Zone-II), Chanduria (Zone-XI), Simurali (Zone-X), Ghetugachi (Zone-IX), Baraberia (Zone-VIII), Rukminidanga (Zone-IV) under Nadia Arsenic Division-I, PHE Dte. (Sl.no.13) | 1276 / NAD-I | 08/05/2023 | 21 | GBC INFRASTRUCTURE PRIVATE LIMITED | 58.64 | 58.53 | 99.8 | 0
488 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & , SM/11455 | Augmentation | Laying of rising main and distribution pipeline in revised alignment along NH-34 for Simurali (Zone-X), Chanduria (Zone-XII), Joykrishnapur (Zone-II) in connection with providing FHTC for Simurali(Zone-X), Chanduria (Zone-XII), Joykrishnapur (Zone-II) under JJM by Augmentation of Surface Water Based PWSS for Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, P.H.E.Dte. (sl.01) | 1254/ NAD-I | 04/05/2023 | 21 | BUDDHADEV MONDAL | 42.85 | 42.82 | 99.93 | 0
489 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & , SM/11455 | Augmentation | Repair of 550 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at Simurali Zone-XI under Surface W/S Scheme of Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no. 06) | 1433 / NAD-I | 16/08/2022 | 45 | ONKAR ENTERPRISE | 29.88 | 29.51 | 100 | 100
490 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & , SM/11455 | Augmentation | Retrofitting work at Sanyalchar bablatala to Sanyalchar High School under Chanduria(Zone-XI) W/S Scheme in connection with augmentation of Chanduria W/S Scheme under Jal Jeevan Mission under Nadia Arsenic Division-I, P.H.E Dte (sl.no.06) | 1459/NAD-I | 29/05/2023 | 21 | SHYAMAL SHIL | 13.29 | 12.42 | 100 | 100
491 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & , SM/11455 | Augmentation | Retrofitting work at Tangra & Bagdob for augmentation of Surface water based PWSS for providing FHTC at Purba Bishnupur ( Zone V) of Surfac water based piped water supply scheme for Chakdah ( Part ) under JJM within Chakdah Block under Nadia Arsenic Division-I , PHE Dte. (SL.No.11) | 1400/NAD-I | 16/05/2023 | 25 | CHANDAN ROY | 47.15 | 1.58 | 100 | 100
492 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & , SM/11455 | Augmentation | Interconnection from Node point 178 to node point 188 for Augmentation work at Tetulberia, Khorgachi,mollabelia village under Joykrishna ( Zone- II ) Water supply scheme under Jal Jeevan Mission for Chakdah Water bsaed PWSS within Chakdah Block ( Part ) under Nadia Arsenic Division-I, PHE Dte.(SL.07) | 1383/NAD-I | 16/05/2023 | 21 | M/S A.K. CONSTRUCTION | 25.14 | 20.15 | 100 | 100
493 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & , SM/11455 | Augmentation | Construction of Pathway from Madnapur PWD road to Tantipara and allied works in connection with Augmentation of Surface Water Based W/S Scheme for Arsenic affected areas of Chakdah (Part Block) of Nadia district Zone-X (Chanduria) under Nadia Arsenic Division-I, P.H.E. Dte. | 378/AE-II/NAD-I | 29/08/2023 | 7 | GREEN VIEW PROJECT INDIA | 2.5 | 1.22 | 100 | 100
494 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & , SM/11455 | Augmentation | Interconnection between node 6 to node 382, node 340 to node 355 and providing FHTC (Functional Household Tap Connection) for augmentation work at Suturgachi, Simurali Railgate and Santipally in connection with augmentation of Simurali Zone-X W/S Scheme under Chakdah (Part) W/S Scheme under Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. (Sl.no.17) | 2117/NAD-I | 04/09/2023 | 21 | BUDDHADEV MONDAL | 74.38 | 73.61 | 100 | 100
495 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & , SM/11455 | Augmentation | Interconnection between Inlet and outlet pipe and OHR and bypass arrangement at Joykrishnapur ( Zone- II ) under Chakdah surface water supply scheme inconnection with augmentation of Joykrishnapur W/S Scheme under JJM under Nadia Arsenic Division- I P.H.E Dte(Sl.no.15) | 2156/NAD-I | 08/09/2023 | 21 | TARUN KUMAR BHATTACHARYA | 13.76 | 11.07 | 100 | 100
496 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & , SM/11455 | Augmentation | Construction of Boundary wall and pathway and Room at Head work site of Joykrishnapur OHR Site (Zone-II), Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Jeeva Mission for Zone-II (Joykrishnapur) Part-II, Providing FHTC under Jal Jeevan Mission (JJM) Zone -VIII (Barberia) Part-IV, Providing FHTC under Jal Jeevan Mission (JJM) Zone-X (Simurali) Part-IV and Providing FHTC under Jal Jeevan Mission (JJM) Zone-IV (Rukminidanga) Part-III at Chakdah Block by Augmentation of Surface Water Based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.02) | 1709/NAD-I | 14/07/2023 | 443 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 608.25 | 294.6 | 48.43 | 75
497 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & , SM/11455 | Augmentation | Interconnection between node point 3 and 76 of Balagarichar W/S Scheme for augmentation work at Uttar Ghughia village under Chakdah (Part) Water supply scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.04) | 1412/NAD-I | 18/05/2023 | 30 | MESSRS FREEDOM CONSTRUCTION | 62.36 | 18.77 | 100 | 100
498 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & , SM/11455 | Augmentation | Retrofitting work Kajir baganunder Chanduria (Zone-XI) W/S Scheme in connection with augmentation of Chanduria W/S Scheme under Jal Jeevan Mission under Nadia Arsenic Division-I, P.H.E. Dte. | 377/AE-II/NAD-I | 29/08/2023 | 7 | ASHIM ENTERPRISE | 1.17 | 0.83 | 100 | 100
499 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & , SM/11455 | Augmentation | Retrofitting work at Inayetpur and Ektarpur under Simurali (Zone-IX) W/S Scheme under Surface based Chakdah (Part) Water Supply Scheme under JJM under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no.06) | 2114/NAD-I | 01/09/2023 | 15 | BIDYUT KUMAR | 30.26 | 29.78 | 100 | 100
500 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & , SM/11455 | Augmentation | Interconnection between Washout/Overflowpipe and delivery pipe at Baeberia H/W site under Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of surface water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 516/AE-II/NAD-I | 05/12/2023 | 7 | BUDDHADEV MONDAL | 2.53 | 2.46 | 100 | 100
501 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & , SM/11455 | Augmentation | Retrofitting work of at Manosapota and Malichaghar at Chanduria under Chanduria (Zone-XI) W/S Scheme under Surface based Chakdah (Part) W/S Scheme under JJM under Nadia Arsenic Division-I, P.H.E. Dte. | 2725/NAD-I | 06/12/2023 | 21 | SUMAN CHAKRABORTY | 18.82 | 17.85 | 100 | 100
502 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & , SM/11455 | Augmentation | Replacement of pipeline and allied works under Jal Jeevan Mission (JJM) for Chanduria area under Chakdah Block by augmentation of Surface Water Based W/S Scheme for arsenic affected areas of Chakdah (Part Block) of Nadia Dist. Zone-XI (Chanduria) under Nadia Arsenic Division-I, PHE Dte. | 10/AE-II/NAD-I | 04/01/2024 | 7 | PRADIP KUMAR BANIK | 2.68 | 2.31 | 100 | 100
503 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & , SM/11455 | Augmentation | Construction of approach road at the Head Work site of Goruimari W/S Scheme under Chakdah Surface PWSS under JJM within Chakdah Block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | 2111/NAD-I | 18/12/2024 | 236 | M/S LAXMI ENTERPRISE | 18.35 | 0 | 0 | 100
504 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11697 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 9B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 133/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.23 | 4.19 | 100 | 100
505 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11697 | Augmentation | Schedule for Additional Survey, Design Drawing & DPR Preparation for ZONE 9B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 134/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 0.81 | 0.75 | 100 | 98
506 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11697 | Augmentation | Material Requisition To Resource Division | 90/ND | 05/01/2023 | 0 | Resource Division | 147.73 | 0 | 0 | 0
507 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11697 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 559.72 | 58.56 | 47
508 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11697 | Augmentation | Additional Work for Ground Improvement of OHR foundation, renovation of OHR & other allied works of Northern Sector Part-I, Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 6095/ND | 19/09/2024 | 240 | UMWELT ENGINEER PVT LTD | 225.66 | 0 | 0 | 75
509 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XI, (Chanduria), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme , SM/08002 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XI, Chanduria, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 772/NAD-I | 04/05/2021 | 60 | M/S NIBHAS SINHA | 95.81 | 155.41 | 100 | 100
510 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase- A) , SM/07417 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase- A) | 183/PFMS | 15/09/2021 | 0 | NEERMAN | 86.15 | 0 | 0 | 0
511 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase- A) , SM/07417 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase- A) | 484/PFMS | 03/02/2022 | 0 | LEMNISCATE | 0.72 | 0 | 0 | 0
512 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase- A) , SM/07417 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-IX, within Kaliganj Block (Phase-A, Retrofitting)" | 165/ND | 13/01/2021 | 90 | NEERMAN | 95.28 | 1.77 | 1.86 | 0
513 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase- A) , SM/07417 | Retrofitting | Hiring of Diesel Ambassador Car/maxi cab for the office of the Assistant Engineer, Debagram Sub-Diovision,PHE Dte,Debagram,Nadia with effect from 01.08.2021 to 31.07.2022 | 399/DSD | 29/07/2021 | 365 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0 | 0
514 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase- A) , SM/07417 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-IX within Kaliganj Block (Phase-B) | 2767/ND | 14/07/2021 | 90 | M/S K.P. CONSTRUCTION | 91.11 | 0 | 0 | 0
515 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- B) , SM/07420 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT NORTHERN SECTOR | 459/DW | 30/03/2021 | 0 | SATYABRATA CHAKRABORTY | 59.75 | 0 | 0 | 0
516 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- B) , SM/07420 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- B) | 486/PFMS | 03/02/2022 | 0 | LEMNISCATE | 0.47 | 0 | 0 | 0
517 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- B) , SM/07420 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block ( Phase -B) | 4087/ND | 31/12/2020 | 90 | SATYABRATA CHAKRABORTY | 97.02 | 71.87 | 74.08 | 0
518 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- B) , SM/07420 | Retrofitting | Material Requisition To Resource Division | 822/ND | 18/02/2022 | 0 | Resource Division | 13.84 | 0 | 0 | 0
519 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- B) , SM/07420 | Retrofitting | Material Requisition To Resource Division | 816/ND | 18/02/2022 | 0 | Resource Division | 16.68 | 0 | 0 | 0
520 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (Darrappur), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07450 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (Darrappur), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | 283/NAD-I | 03/02/2021 | 90 | KINGS AND CO | 93.82 | 181.06 | 192.99 | 100
521 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-VI within Nakashipara Block (Phase-A). , SM/07452 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VI within Nakashipara Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte.(SL.4) | 351/PFMS | 08/12/2021 | 0 | UNICON INDIA | 64.21 | 0 | 0 | 0
522 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-VI within Nakashipara Block (Phase-A). , SM/07452 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-VI within Nakashipara Block (Phase-A). | 595/PFMS | 08/03/2022 | 0 | UNICON INDIA | 21.34 | 0 | 0 | 0
523 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-VI within Nakashipara Block (Phase-A). , SM/07452 | Retrofitting | Material Requisition To Resource Division | 799/ND | 18/02/2022 | 0 | Resource Division | 11.22 | 0 | 0 | 0
524 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-VI within Nakashipara Block (Phase-A). , SM/07452 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VI within Nakashipara Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte.(SL.4) | 888/ND | 19/02/2021 | 90 | UNICON INDIA | 96.71 | 0 | 0 | 0
525 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-VI within Nakashipara Block (Phase-A). , SM/07452 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 3.66 | 100 | 81
526 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme , SM/07456 | Retrofitting | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme. |  | 24/03/2021 | 0 | S.S. ENTERPRISE | 44.96 | 0 | 0 | 0
527 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme , SM/07456 | Retrofitting | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme | 264/PFMS | 08/10/2021 | 0 | S.S. ENTERPRISE | 35.02 | 0 | 0 | 0
528 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme , SM/07456 | Retrofitting | PROVIDING FHTC AT BABLARI DEYANGANJ W/S SCHEME UNDER JAL SWAPNO PROGRAM. | 89/PPMS | 15/07/2021 | 0 | S.S. ENTERPRISE | 44.96 | 0 | 0 | 0
529 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme , SM/07456 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Bablari Dewanganj W/S scheme in Nadia District under Nadia Division P.H.E. Dte. | 44/ND | 06/01/2021 | 90 | S.S. ENTERPRISE | 97.07 | 14.72 | 100 | 100
530 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme , SM/07456 | Retrofitting | Material Requisition To Resource Division | 93/ND | 06/01/2022 | 0 | Resource Division | 7.71 | 0 | 0 | 0
531 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme , SM/07456 | Retrofitting | Material Requisition To Resource Division | 792/ND | 18/02/2022 | 0 | Resource Division | 3.71 | 0 | 0 | 0
532 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-A) , SM/07457 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT PART-2, Z-4 | 460/DW | 30/03/2021 | 0 | H I ENTERPRISE | 72.4 | 0 | 0 | 0
533 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-A) , SM/07457 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-II, Z-IV, NABADWIP BLOCK, PHASE-A. | 490/PFMS | 03/02/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 0.41 | 0 | 0 | 0
534 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-A) , SM/07457 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block ( Phase -A) | 245/ND | 15/01/2021 | 90 | H I ENTERPRISE | 97.1 | 36.81 | 37.91 | 0
535 | NADIA | Nadia Division | Retrofitting of Providing FHTC at Ground Water based Ber Ramchandrapur Zone-II Water Supply Scheme within Karimpur-1 Block (Phase-1) , SM/07491 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT BER-RAM CHANRAPUR Z-II | 460/DW | 30/03/2021 | 0 | JOYGOPAL GUPTI | 22.23 | 0 | 0 | 0
536 | NADIA | Nadia Division | Retrofitting of Providing FHTC at Ground Water based Ber Ramchandrapur Zone-II Water Supply Scheme within Karimpur-1 Block (Phase-1) , SM/07491 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Ber Ramchandrapur Zone-II W/S scheme (Phase-I) of Rectrofitting in Nadia District under Nadia Division P.H.E. Dte. | 4040/ND | 30/12/2020 | 60 | JOYGOPAL GUPTI | 32.2 | 3.12 | 9.69 | 100
537 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kulgachi Water Supply Scheme under Jal Swapno Programme , SM/07494 | Retrofitting | Providing Functional House Tap Connection from Kulgachi Water Supply Scheme under Jal Swapno Programme | 534/PFMS | 23/02/2022 | 0 | SHYAMAL SHIL | 54.42 | 0 | 0 | 0
538 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kulgachi Water Supply Scheme under Jal Swapno Programme , SM/07494 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Kulgachi W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I, Retrofitting) | 45/ND | 06/01/2021 | 90 | SHYAMAL SHIL | 92.07 | 56.93 | 61.83 | 0
539 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kulgachi Water Supply Scheme under Jal Swapno Programme , SM/07494 | Retrofitting | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Maidanpur ii) Kulgachhi iii) Monipota iv) Habibpur v) Magurkhali. | 372/ Kly SD-I | 17/03/2023 | 184 | HORIZEN | 4.99 | 0.58 | 100 | 10
540 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-I within Kaliganj Block (Phase-A). , SM/06996 | Retrofitting | PREPERATION OF DETAILS PROJECT FOR FHTC AT SURFACE WATER BASED W/S SCHEME ( N.SECTOR) , PART-II, ZONE-I, PHASE-A & B UNDER , NADIA DIVISION , PHE ,DTE | 139/FHTC | 17/08/2021 | 0 | LEMNISCATE | 0.45 | 0 | 0 | 0
541 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-I within Kaliganj Block (Phase-A). , SM/06996 | Retrofitting | PREPERATION OF DETAILS PROJECT FOR FHTC AT SURFACE WATER BASED W/S SCHEME ( N.SECTOR) , PART-II, ZONE-I, PHASE-A & B UNDER , NADIA DIVISION , PHE ,DTE | 139/FHTC | 17/08/2021 | 0 | LEMNISCATE | 0.48 | 0 | 0 | 0
542 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-I within Kaliganj Block (Phase-A). , SM/06996 | Retrofitting | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H.E. Dte., Kalyani, Nadia. Period of work 01-03-2022 to 28-02-2023 | 118/RSD | 28/02/2022 | 250 | SUMAN CHAKRABORTY | 3.85 | 0.97 | 100 | 75
543 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-I within Kaliganj Block (Phase-A). , SM/06996 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme(Northern Sector), Part-I,Zone-I within Kaliganj Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte. | 4083/ND | 31/12/2020 | 90 | ALOKE ENTERPRISE | 97.02 | 89.26 | 100 | 100
544 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-I within Kaliganj Block (Phase-A). , SM/06996 | Retrofitting | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 01-03-2021 to 28-02-2022 (250 working days) | 172/RSD | 22/02/2021 | 365 | SUMAN CHAKRABORTY | 3.85 | 0.75 | 100 | 0
545 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-IV within Kaliganj Block (Phase-B). , SM/07001 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT NORTHERN SECTORPART-1 Z-4 | 446/DW | 25/03/2021 | 0 | M/S NIBHAS SINHA | 28.95 | 0 | 0 | 0
546 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-IV within Kaliganj Block (Phase-B). , SM/07001 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme(northern sector),Part-I,Zone-IV within Kaliganj block(Phase-B) in Nadia District under Nadia Division P.H.Engineering Dte. | 3593/ND | 08/12/2020 | 90 | M/S NIBHAS SINHA | 96.81 | 131.5 | 135.83 | 0
547 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-IV within Kaliganj Block (Phase-B). , SM/07001 | Retrofitting | Hiring of Diesel Ambassador Car/maxi cab for the office of the Assistant Engineer, Debagram Sub-Division, P.H. Engineering Dte., Debagram, Nadia with effect from 01/08/22 to 31/07/23 | 312/D/DSD | 29/07/2022 | 365 | TARUN KUMAR BHATTACHARYA | 4.8 | 1.54 | 100 | 70
548 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-IV within Kaliganj Block (Phase-B). , SM/07001 | Retrofitting | Hiring Diesel Maxi Cub having car No WB-51/B-3194 for office of the Assistant Engineer, RWS Nadia Sub-Division, PHE Dte. for the period from 01.08.2021 to 31.07.2022 | 896/PH | 30/07/2021 | 365 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0 | 100
549 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VI, (Balia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08853 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Chakdah Zone-VI (Balia), Part-II at Chakdah Block by retrofitting of Ground Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1565/NAD-I | 13/12/2021 | 90 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT LTD. | 214.98 | 204.67 | 100 | 100
550 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VI, (Balia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08853 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-IV, Balia (Part-II) at Chak Amdanga, Silinda, Balia, Balarampur village at Chakdah Block retrofitting of Surface Water Based PWSS FOR Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (SL.NO.10) | 3216/NAD-I | 30/11/2022 | 30 | BIDYUT KUMAR | 31.54 | 29.46 | 100 | 100
551 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I,Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block , SM/08860 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. under Nadia Arsenic Division-I, P.H.E. Dte. | 1448/NAD-I | 12/11/2021 | 90 | DIVINE | 151.18 | 150.68 | 100 | 100
552 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I,Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block , SM/08860 | Retrofitting | Construction of Boundary wall, pathway and other allied works at Head Work Tubewell site of Ground water based piped supply scheme of Halalpur-Krishnapur Zone-I Piped Water Supply Scheme within Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E. Dte. Length of Boundary wall - 138 metre. | 76/NAD-I | 17/01/2022 | 20 | MONDAL ENTERPRISE | 9.94 | 3.22 | 100 | 100
553 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I,Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block , SM/08860 | Retrofitting | Repairing and renovation of Rising main and allied works at Halalpur Krishnapur Zone-I under Ranaghat-II, Block under Halalpur Krishnapur Zone-I Water Supply Scheme in the District of Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | 253/AE-I/NAD-I | 21/10/2022 | 15 | BUDDHADEV MONDAL | 0.93 | 0.92 | 100 | 100
554 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I,Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block , SM/08860 | Retrofitting | Laying of UPVC pipe line at Jaffarnagar ,near Headwork Site under Raghunathpur Hijuli-I Gram Panchayet under Halalpur Zone-I Water Supply Scheme under Ranahghat -II Block under Nadia Arsenic Division-I, P.H.E Dte. | 254/AE-I/NAD-I | 21/10/2022 | 15 | BUDDHADEV MONDAL | 0.96 | 0.96 | 100 | 100
555 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I,Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block , SM/08860 | Retrofitting | Laying of UPVC pipeline and retrofitting work at different loations i.e; Halalpur Krishnapur ,Madanpur,Goalpur,Beharia and Nabla Mouzas for smooth water supply in coneection with Retrofitting under JJM of Ground Water Based PWSS of Halalpur Krishnapur Zone-I W/S Scheme at Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E Dte.(sl.no.14) | 11118 / NAD-I | 27/04/2023 | 21 | CHOWDHURY & CO. | 23.38 | 23.38 | 99.99 | 0
556 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I,Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block , SM/08860 | Retrofitting | Retrofitting work for Halalpur Krishnapur Zone-I & Zone-II form Puratan Chapra Primary School to Kharida Chapra Primary School at Ranaghat-II Block under Jal Jeevan Mission (JJM) by Retrofitting of Ground Water Based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 57/AE-I/NAD-I | 17/01/2023 | 15 | BANERJEE ENTERPRISE | 3.88 | 3.6 | 100 | 99
557 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I,Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block , SM/08860 | Retrofitting | Retrofitting work for Halalpur Krishnapur Zone-I & Zone-II from Pragati Sangha Club to Purba Para Kalimandir at Ranaghat-II Block under Jal Jeevan Mission (JJM) by Retrofitting of Ground Water Based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 142/AE-I/NAD-I | 29/03/2023 | 15 | CONSTRUCTURE | 3.63 | 3.63 | 100 | 100
558 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I,Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block , SM/08860 | Retrofitting | Retrofitting work for Halalpur Krishnapur Zone-I & Zone-II from Purba Para Kalimandir to Paschim Sangha at Ranaghat-II Block under Jal Jeevan Mission (JJM) by Retrofitting of Ground Water Based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 143/AE-I/NAD-I | 29/03/2023 | 15 | CONSTRUCTURE | 3.38 | 3.38 | 100 | 100
559 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I,Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block , SM/08860 | Retrofitting | Material Requisition To Resource Division | 147/NAD-I | 28/01/2022 | 0 | Resource Division | 1.99 | 0 | 0 | 0
560 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX, (Chandmari), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divi , SM/08833 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-IX (Chandmari) Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 1613/NAD-I | 28/12/2021 | 90 | SATYABRATA CHAKRABORTY | 248.68 | 247.52 | 100 | 100
561 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX, (Chandmari), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divi , SM/08833 | Retrofitting | Retrofitting work under Jal Jeevan Mission (JJM) for Zone-IX at North, South Chandmari, Muratipur at Kanchrapara G.P. by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) W/S Scheme for Zone-IX, Chandmari, Part-II under Nadia Arsenic Division-I , PHE Dte.(SL.06) | 1465/NAD-I | 30/05/2023 | 21 | BUDDHADEV MONDAL | 22.58 | 22.58 | 100 | 0
562 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III (Mosra) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08838 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Chakdah Zone-III (Mosra), Part-II at Chakdah Block by retrofitting of Ground Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1539/NAD-I | 06/12/2021 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 214.03 | 212.04 | 100 | 100
563 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Gayeshpur Zone-II, at Santipur Block by retrofitting of Ground Water based PWSS for Gayeshpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08863 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Gayeshpur, Zone-II at Santipur Block by retrofitting of Ground Water based PWSS for Gayeshpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1417/NAD-I | 08/11/2021 | 60 | M/S R.K. ENTERPRISE | 65.48 | 61.93 | 100 | 100
564 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Gayeshpur Zone-II, at Santipur Block by retrofitting of Ground Water based PWSS for Gayeshpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08863 | Retrofitting | Repair of Over Head Reservoir Painting at Gayeshpur Zone II WS Scheme in Santipur Block under NAD- I PHE Dte. (SL. NO. 04) | 3024 / NAD-I | 07/11/2022 | 45 | BIDYUT KUMAR | 15.46 | 14.82 | 100 | 100
565 | NADIA | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dhubulia-Mayapur Road 0.00 Kmp to 11.12 kmp under Sur , SM/08890 | Retrofitting | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dhubulia-Mayapur Road 0.00 Kmp to 11.12 kmp under Surface water based water supply scheme (Northern Sector Part-III ) under Krishnagar Sub-division under Nadia Division , PH.E Dte. (Block- Nabadwip and Krishnagar-II) | 697/PFMS | 28/03/2022 | 0 | H I ENTERPRISE | 146.02 | 0 | 0 | 0
566 | NADIA | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dhubulia-Mayapur Road 0.00 Kmp to 11.12 kmp under Sur , SM/08890 | Retrofitting | Providing FHTC (Functional Household Tap Connection) by retrofitting under "Jalswapno" with Utility Shifting of water pipeline in connection to the work under Nadia Highway Division - I PWD (Roads) Dte. along and across Dhubulia Mayapur Road 0.00 Kpm to 11.12 Kpm under Surface Based Water Supply Scheme (Northern Sector part III) under Krishnagar Sub Division under Nadia Divn,PHE Dte. | 7434/ND | 27/12/2021 | 90 | H I ENTERPRISE | 193.5 | 23.32 | 100 | 100
567 | NADIA | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dhubulia-Mayapur Road 0.00 Kmp to 11.12 kmp under Sur , SM/08890 | Retrofitting | Restoration of impact zone along Dhubulia Mayapur road in connection to the work ¿Providing FHTC by retrofitting Utility Shifting of water pipeline in connection to the work under Nadia Highway Division - I PWD (Roads) Dte. along and across Dhubulia Mayapur Road 0.00 Kpm to 11.12 Kpm under Surface Based Water Supply Scheme (Northern Sector part III) under Krishnagar Sub Division under Nadia Divn,PHE Dte.¿ | 243/KSD | 11/03/2022 | 7 | H I ENTERPRISE | 4.04 | 3.95 | 100 | 99
568 | NADIA | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dhubulia-Mayapur Road 0.00 Kmp to 11.12 kmp under Sur , SM/08890 | Retrofitting | Preparation of DPR for Augmentation for Intake, WTP & Rising Main of Surface Water Based Water Supply Scheme for Northern Sector Part-III in Krishnagar-II & Nabadwip (Part) Block of Nadia District under Nadia Division, PHE Dte.(including Survey, Design and Estimate). | 4547/ND | 21/10/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 9.35 | 9.35 | 100 | 100
569 | NADIA | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dhubulia-Mayapur Road 0.00 Kmp to 11.12 kmp under Sur , SM/08890 | Retrofitting | Material Requisition To Resource Division | 6830/ND | 17/11/2021 | 0 | Resource Division | 99.96 | 0 | 0 | 0
570 | NADIA | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dhubulia-Mayapur Road 0.00 Kmp to 11.12 kmp under Sur , SM/08890 | Retrofitting | Material Requisition To Resource Division | 454/ND | 31/01/2022 | 0 | Resource Division | 2.13 | 0 | 0 | 0
571 | NADIA | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dhubulia-Mayapur Road 0.00 Kmp to 11.12 kmp under Sur , SM/08890 | Retrofitting | Material Requisition To Resource Division | 427/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0 | 0
572 | NADIA | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dhubulia-Mayapur Road 0.00 Kmp to 11.12 kmp under Sur , SM/08890 | Retrofitting | Material Requisition To Resource Division | 783/ND | 18/02/2022 | 0 | Resource Division | 10.87 | 0 | 0 | 0
573 | NADIA | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dhubulia-Mayapur Road 0.00 Kmp to 11.12 kmp under Sur , SM/08890 | Retrofitting | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | 7571/ND | 27/12/2024 | 31 | IMAGIN | 34.21 | 0 | 0 | 0
574 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08843 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara/JalSwapna for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) | 1434/NAD-I | 09/11/2021 | 90 | APURBA MANDAL | 117.48 | 115.42 | 100 | 100
575 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08843 | Retrofitting | Charges of entry of household date in JJM website along with Household Aadhar details and Geo tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(Sl No.-03) | 309 / AE-I / NAD-I | 30/12/2022 | 90 | SUMAN CHAKRABORTY | 4.85 | 4.85 | 100 | 0
576 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08843 | Retrofitting | Retrofitting work at Rabonbor mouza near Shyamal Biswas house and near Sailen Halder house under Parniamatpur Water Supply Scheme under Ranaghat-I Block under Providing FHTC under Jal Jeevan Mission (JJM) for Parniamatpur Phase-II under Nadia Arsenic Division-I, P.H.E. Dte. | 86/AE-I/NAD-I | 06/02/2023 | 15 | BISWAS CONSTRUCTION | 4.64 | 4.64 | 100 | 100
577 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08843 | Retrofitting | Charges of entry of household date in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division -I, P.H.E. Dte.(sl.03) | 241 / AE-I / NAD-I | 29/09/2022 | 90 | SUMAN CHAKRABORTY | 4.85 | 4.85 | 100 | 100
578 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08843 | Retrofitting | Supply of 1(one) no. Motor Cab (Luxury Taxi) on hire basis for official use of the Assistant Engineer-I, Nadia Arsenic Division- I, P.H.E. Dte. for the period from 15.07.2021 to 14.07.2022 i.e. for 1(one) year. | 129 /AE-I/NAD-I | 14/07/2021 | 365 | SUMAN CHAKRABORTY | 4.27 | 4.16 | 100 | 100
579 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08843 | Retrofitting | Retrofitting work at Nandighat mouza (Jl No 126) under Jal Jeevan Mission (JJM) for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.01) | 2240/NAD-I | 21/09/2023 | 21 | GANGULY ENTERPRISE | 11.86 | 11.86 | 100 | 100
580 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08843 | Retrofitting | Retrofitting work under Jal Jeevan Mission (JJM) at Nandighat, Sardarpara & Baganpara under Anulia G.P. under Parniamatpur Phase-II at Ranaghat-I Block by retrofitting Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.06) | 2206/NAD-I | 13/09/2023 | 15 | SAORSA | 42.45 | 42.25 | 100 | 100
581 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Bankar Dhopadi to accomodate FHTC in Nabadwip Block of Nadia District under Nadia Division, PHE Dte. , SM/09526 | Retrofitting | Retrofitting of Ground Water Based Piped Water Supply Scheme For Bankar Dhopadi to accomodate FHTC in Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | 712/PFMS | 30/03/2022 | 0 | M/S S.S ENTERPRISE | 17.59 | 0 | 0 | 0
582 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Bankar Dhopadi to accomodate FHTC in Nabadwip Block of Nadia District under Nadia Division, PHE Dte. , SM/09526 | Retrofitting | Renovation of AIRP (Gravity Type) of capacity 29 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Bankar Dhopadi PWSS under Nadia Division PHE Dte. | 2994/ND | 13/07/2023 | 90 | TARUN KUMAR BHATTACHARYA | 70.11 | 0 | 0 | 0
583 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Bankar Dhopadi to accomodate FHTC in Nabadwip Block of Nadia District under Nadia Division, PHE Dte. , SM/09526 | Retrofitting | Material Requisition To Resource Division | 7453/ND | 27/12/2021 | 0 | Resource Division | 16.14 | 0 | 0 | 0
584 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Bankar Dhopadi to accomodate FHTC in Nabadwip Block of Nadia District under Nadia Division, PHE Dte. , SM/09526 | Retrofitting | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Bankar Dhopadi to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 65/ND | 05/01/2022 | 75 | M/S S.S ENTERPRISE | 46.02 | 11.56 | 100 | 75
585 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Bankar Dhopadi to accomodate FHTC in Nabadwip Block of Nadia District under Nadia Division, PHE Dte. , SM/09526 | Retrofitting | Repair and renovation works of R.C.C. Elevated Reservoir 140 cum, Repair & Renovation of Boundary wall and allied works at 1st and 2nd Pump House at Bankar Dhopadi Water Supply Scheme within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 5127/ND | 17/11/2023 | 90 | BISWAS CONSTRUCTION | 17.56 | 12.22 | 100 | 80
586 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA KHANJEPUR WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09249 | Retrofitting | Construction of Boundary wall with Grill Gate at Khanjipur Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | 54/AE-II/NACD-II | 17/02/2022 | 30 | SANJIB BISWAS | 3.86 | 3.84 | 99.52 | 100
587 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA KHANJEPUR WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09249 | Retrofitting | SUPPLY & DELIVARY OF MS METIRIALS & ELECTRICAL ACCESORIES INCLUD AB CABLE TO WBSEDCL FOR NEW SERVICES CONNECTION AT PH-II UNDER KHANJEPUR. |  | 02/02/2022 | 0 | M/S G.P. ENTERPRISE | 7.83 | 0 | 0 | 0
588 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA KHANJEPUR WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09249 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged pipe line repair) at Tengra & Khanjipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 862/NACD-II | 08/11/2021 | 45 | PALCON | 47.75 | 47.71 | 100 | 100
589 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA KHANJEPUR WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09249 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Khanjipur & Bagakhali Zone-I, W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 768./NACD-II | 22/09/2021 | 45 | TARUN KUMAR BHATTACHARYA | 84.44 | 0 | 0 | 100
590 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA KHANJEPUR WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09249 | Retrofitting | Providing Functional House Hold Tap Connection including laying of pipeline at Khanjipur W/S Scheme in Tehatta-I Block under Nadia Arsenic Civil DivisionII, P.H.E. Dte | 521/AE-I/NACD-II | 18/12/2023 | 15 | GHOSH ENTERPRISE | 0.97 | 0 | 0 | 0
591 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA KHANJEPUR WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09249 | Retrofitting | Relaying of D.I. Pipeline replacing the damaged old UPVC Pipe at Khanjipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 469/NACD-II | 21/07/2022 | 30 | PAPAN ROY | 6.47 | 5.01 | 100 | 100
592 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA KHANJEPUR WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09249 | Retrofitting | Rejuvenation of Khanjipur W/S Scheme in Tehatta- Block of Nadia | 230 /EMD | 15/02/2022 | 45 | INDIA ENTERPRISE | 5.99 | 5.99 | 100 | 100
593 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA KHANJEPUR WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09249 | Retrofitting | Material Requisition To Resource Division | 539/NACD-II | 12/08/2022 | 0 | Resource Division | 11.62 | 0 | 0 | 0
594 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA KHANJEPUR WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09249 | Retrofitting | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KHANJIPUR , Block-Tehatta I and TALDAH , Block-Krishnaganj, Bahirgachhi (Z-II) Block-Chapra, Bagakhali (Z-II) W/S Scheme, Block-Tehatta I Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 03) | 1122/EMD | 16/03/2023 | 30 | ANJAN ENTERPRISE | 46.98 | 2.61 | 20.94 | 80
595 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA KHANJEPUR WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09249 | Retrofitting | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Khanjipur) | 1320/NACD-II | 01/12/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
596 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA KHANJEPUR WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09249 | Retrofitting | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Khanjipur, Bahadurpur and Mobarakpur PWSS in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 295_AE-II/NACD-II | 30/08/2024 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.87 | 3.87 | 100 | 100
597 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA KHANJEPUR WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09249 | Retrofitting | Renovation of Arsenic cum Iron treatment Plant of Khanjipur PWSS (Capacity- 21 m3/hr) and ancillary works of Rajapur W/s Scheme at Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 38/NACD-II | 09/01/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 61.75 | 1.06 | 100 | 70
598 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09250 | Retrofitting | Construction of Path Way & Earth filling at H/w site of Bahirgachhi Zone-II Piped Water Supply Scheme under NACD - II, P.H.E. Dte. | 81//AE-I/NACD-II | 27/08/2021 | 15 | SHYAMAL SHIL | 2.77 | 2.77 | 99.9 | 100
599 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09250 | Retrofitting | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bahirgachhi Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 874/NACD-II | 09/11/2021 | 45 | CHAKRABORTTY ENTERPRISE | 17.84 | 17.65 | 98.91 | 100
600 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09250 | Retrofitting | Rejuvenation of Bahirgachi Zone-II W/S Scheme in chapra block of Nadia, W/O-473/EMD, T.no.06/EMD | 473/EMD | 16/03/2022 | 30 | DAS ENTERPRISE | 6.02 | 6.02 | 100 | 100
601 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09250 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Bahirgachhi Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 274/EE/NACD-II | 22/02/2021 | 21 | SOMNATH CHATTERJEE | 30.67 | 0 | 0 | 100
602 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09250 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged pipe line repair) at Bahirgachhi Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 736/NACD-II | 13/09/2021 | 45 | CHAKRABORTTY ENTERPRISE | 50.01 | 50 | 100 | 100
603 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09250 | Retrofitting | Functional House Hold Tap Connection for providing connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Remaining School only) Bahirgachhi Zone-II W/s Scheme at Chapra Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 350/NACD-II | 22/03/2023 | 20 | SAMARESH GHOSH | 0.78 | 0.78 | 99 | 100
604 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09250 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bagakhali Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 863/NACD-II | 08/11/2021 | 45 | IJABUL SEKH | 60.77 | 0 | 0 | 100
605 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09250 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bahirgachhi Zone-II (Vill-Mirgipota,Choruitipi) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1013/NACD-II | 29/11/2022 | 45 | GHOSH & CO. | 9.65 | 9.34 | 100 | 100
606 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09250 | Retrofitting | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bahirgachhi Zone -II) | 1294/NACD-II | 23/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
607 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09250 | Retrofitting | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KHANJIPUR , Block-Tehatta I and TALDAH , Block-Krishnaganj, Bahirgachhi (Z-II) Block-Chapra, Bagakhali (Z-II) W/S Scheme, Block-Tehatta I Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 03) | 1122/EMD | 16/03/2023 | 30 | ANJAN ENTERPRISE | 46.98 | 0 | 0 | 80
608 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09250 | Retrofitting | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bahirgachhi Zone -II | 1302/NACD-II | 29/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
609 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09250 | Retrofitting | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Bahirgachi Zone-II W/S Scheme of Chapra Block Mouza Ramnagar & Mrigipota of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 612/AE-I/NACD-II | 02/02/2024 | 15 | MALLICK ENTERPRISE | 0.97 | 0.96 | 100 | 100
610 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09250 | Retrofitting | Renovation of Arsenic cum Iron treatment Plant of Bahirgachhi Zone-II PWSS (Capacity- 23 m3/hr) and Bhatgachhi PWSS ancillary works of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 35/NACD-II | 09/01/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 100.51 | 49.52 | 100 | 80
611 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09250 | Retrofitting | Repair and Renovation work at Bahirgachi Zone-II 2nd Tube Well Site under Bahirgachi Zone-II Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | 899/AE-I/NACD-II | 10/09/2024 | 150 | M/S FREEDOM CONSTRUCTION | 3.96 | 0 | 0 | 100
612 | NADIA | Nadia Division | Providing Functional House Tap Connection from Hudachapra Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/08673 | Retrofitting | Providing Functional House Tap Connection from Hudachapra Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | 596/PFMS | 08/03/2022 | 0 | M/S S.S ENTERPRISE | 0.63 | 0 | 0 | 0
613 | NADIA | Nadia Division | Providing Functional House Tap Connection from Hudachapra Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/08673 | Retrofitting | Providing Functional House Tap Connection from Hudachapra Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | 606/PFMS | 11/03/2022 | 0 | OTHERS | 4.85 | 0 | 0 | 0
614 | NADIA | Nadia Division | Providing Functional House Tap Connection from Hudachapra Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/08673 | Retrofitting | Providing Functional House Tap Connection from Hudachapra Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | 563/PFMS | 25/02/2022 | 0 | M/S S.S ENTERPRISE | 50 | 0 | 0 | 0
615 | NADIA | Nadia Division | Providing Functional House Tap Connection from Hudachapra Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/08673 | Retrofitting | Providing Functional House Tap Connection from Hudachapra Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | 166/PFMS | 26/09/2022 | 0 | M/S S.S ENTERPRISE | 9.37 | 0 | 0 | 0
616 | NADIA | Nadia Division | Providing Functional House Tap Connection from Hudachapra Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/08673 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Huda Chapra Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.E. Dte.(Phase-A) | 5179/ND | 20/09/2021 | 75 | M/S S.S ENTERPRISE | 70.82 | 3.16 | 100 | 100
617 | NADIA | Nadia Division | Providing Functional House Tap Connection from Hudachapra Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/08673 | Retrofitting | Material Requisition To Resource Division | 810/ND | 18/02/2022 | 0 | Resource Division | 5.23 | 0 | 0 | 0
618 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme under Karimpur-II Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08250 | Retrofitting | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 902/NACD-II | 22/11/2021 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 73.33 | 0 | 0 | 0
619 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme under Karimpur-II Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08250 | Retrofitting | Material Requisition To Resource Division | 608/NACD-II | 04/08/2021 | 0 | Resource Division | 59.68 | 0 | 0 | 0
620 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Helenchi Zone-II water supply scheme under Krishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08253 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 871/NACD-II | 08/11/2021 | 45 | JOY HIND TUBEWELLS | 82.99 | 0 | 0 | 100
621 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Helenchi Zone-III water supply scheme under Krishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08254 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Helenchi Zone-III (Vill-Bhajanghat) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 1180/NACD-II | 13/11/2020 | 25 | SUMIT GHOSH | 4.99 | 0 | 0 | 0
622 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10421 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | 56/PFMS | 22/06/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.84 | 0 | 0 | 0
623 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10421 | Augmentation | Special repair and renovation work at Nathna pump house no: 2(Head work site) under Nathna w/s zone:1, Tehatta -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | 495/ Kly SD-I | 06/04/2023 | 30 | M/S DREAM INFRASTRUCTURE | 2 | 1.94 | 97.05 | 10
624 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10421 | Augmentation | Special repair and renovation work at Nathna pump house no: 1 under Nathna w/s zone:1, Tehatta -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | 496/ Kly SD-1 | 06/04/2023 | 30 | GANGULY ENTERPRISE | 2.37 | 2.25 | 94.66 | 10
625 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10421 | Augmentation | Laying of Distribution system including specials, valves & pipe supporting structure all complete & providing FHTC at Augmentation of ground water based water supply scheme for Natna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division PHe Dte. | 3292/ND | 27/07/2022 | 90 | JOY HIND TUBEWELL'S | 172.64 | 172.47 | 100 | 100
626 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10421 | Augmentation | Repairing and renovation of Boundary Wall at Nathna pump house no: 2 (Head Work site) under Nathna w/s zone:1, Tehatta -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | 494/ Kly SD-I | 06/04/2023 | 30 | M/S BISWAS ENTERPRISE | 4.84 | 4.84 | 100 | 5
627 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10421 | Augmentation | Material Requisition To Resource Division | 3524/ND | 05/08/2022 | 0 | Resource Division | 4.6 | 0 | 0 | 0
628 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10421 | Augmentation | Material Requisition To Resource Division | 4329/ND | 29/09/2022 | 0 | Resource Division | 10.55 | 0 | 0 | 0
629 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10421 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 36 m3/hr at Nathna Zone-I Water Supply Scheme within Tehatta-I Block under Nadia Division, P.H.E. Dte. | 4340/ND | 07/08/2024 | 180 | MERCURY ENGINEERING COMPANY | 166.08 | 0 | 0 | 0
630 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10421 | Augmentation | Collection of Household data through mobile app for FHTC Connection (Phase-II) under Nadia Division, P.H.E. Dte. | 208/KLYSD-I | 09/02/2024 | 182 | HORIZEN | 4.85 | 4.85 | 100 | 100
631 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10421 | Augmentation | Laying additional pipe line for distribution system and rising main for Nathna Zone-II PWSS under augmentation of Nathna Zone-II PWSS (Phase-II) under Nadia Division PHE Dte. | 7051/ND | 02/12/2024 | 270 | JOY HIND TUBEWELL'S | 100.01 | 0 | 0 | 75
632 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10421 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Nathna Zone-II Ground Based Water Supply Scheme under Tehatta-I Block under Nadia Division, P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Nathna Zone-II at Tehatta-I Block by Augmentation of Ground Water based PWSS for Nathna Zone-II Water Supply Schemes under Nadia Division, PHE Dte. | 420/ND | 27/01/2025 | 240 | NIVEDITA CONSTRUCTION | 22.08 | 0 | 0 | 0
633 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10421 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- III) at village Nazirpur, Bagadoba, Chhitka, Aztullanagar under Tehatta-I Block to accommodate FHTC under Nadia Divn, PHE Dte. | 1805/ND | 22/04/2025 | 180 | M/S DIPAK ENTERPRISE | 71.65 | 0 | 0 | 30
634 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division , SM/10080 | Augmentation | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division | 703/PFMS | 30/03/2022 | 0 | HORIZEN | 2.45 | 0 | 0 | 0
635 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division , SM/10080 | Augmentation | Material Requisition To Resource Division | 362/ND | 24/01/2023 | 0 | Resource Division | 0.76 | 0 | 0 | 0
636 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division , SM/10080 | Augmentation | Material Requisition To Resource Division | 2299/ND | 29/05/2023 | 0 | Resource Division | 5.62 | 0 | 0 | 0
637 | NADIA | Eastern Mechanical | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division , SM/10080 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No. I and II under Kulgachi WS Scheme, Block KrishnagarI, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-09) | 158/EMD | 06/01/2023 | 30 | ABHISEK ENGINEERING CONCERN | 16.76 | 0 | 0 | 80
638 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division , SM/10080 | Augmentation | Repairing and renovation of Pump House ,boundary wall of ground basaedpiped water supply scheme for Kulgachi water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 6837/ND | 12/11/2024 | 90 | DAS CONSTRUCTION | 11.4 | 0 | 0 | 0
639 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division , SM/10080 | Augmentation | Conversion of IEP to AIRP of capacity 30 Cu.m/hr at Kulgachi Water Supply Scheme within Tehatta-II Block block under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 4575/ND | 21/08/2024 | 180 | B.M. ENGINEERING & CONSTRUCTION | 129.23 | 0 | 0 | 0
640 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division , SM/10080 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Kulgachi Ground Based Water Supply Scheme under Tehatta-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Kulgachi at Tehatta-II Block by Augmentation of Ground Water based PWSS for Kulgachi Water Supply Schemes under | 7369/ND | 18/12/2024 | 60 | CONSTRUCTURE | 19.15 | 0 | 0 | 0
641 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division , SM/10080 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 150 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for Augmentation of Ground Based Water Supply Scheme at Kulgachi to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 477/ND | 02/02/2023 | 365 | A P POWER AND CONCRETE, 5D,HEMCHANDRA NASKAR ROAD, KOLKATA-700010 | 138.28 | 42.88 | 31.01 | 45
642 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division , SM/10080 | Augmentation | Laying of additional pipeline for Kulgachhi Mouza under Kulgachhi PWSS under Tehatta Sub-Division under Nadia Division PHE Dte. | 2265/ND | 15/05/2025 | 45 | A.P. POWER & CONCRETE | 11.86 | 0 | 0 | 0
643 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-IV PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10526 | Augmentation | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-IV PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | 29/PFMS | 20/05/2022 | 0 | RADIANT | 3 | 0 | 0 | 0
644 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-IV PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10526 | Augmentation | Material Requisition To Resource Division | 145/ND | 06/01/2023 | 0 | Resource Division | 20.74 | 0 | 0 | 0
645 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-IV PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10526 | Augmentation | Material Requisition To Resource Division | 1851/ND | 26/04/2023 | 0 | Resource Division | 8.39 | 0 | 0 | 0
646 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-IV PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10526 | Augmentation | Material Requisition To Resource Division | 1912/ND | 27/04/2023 | 0 | Resource Division | 0.69 | 0 | 0 | 0
647 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-IV PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10526 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KARIMPUR JALANGI (Z-IV, V & XB) W/S Scheme, Block-Karimpur I , Dist. - Nadia. NIET NO. - 33 OF EE/EMD OF 2022-23 (SL. NO. - 03) | 1198/EMD | 22/03/2023 | 771 | AVINABA ENGINEERING CONCERN | 62.41 | 0 | 0 | 80
648 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-IV PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10526 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Karimpur Jalangi Zone-IV Ground Based Water Supply Scheme under Karimpur- I Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Karimpur Jalangi Zone-IV at Karimpur I Block by Augmentation of Ground Water based PWSS for Karimpur Jalangi Zone-IV Water Supply Schemes under Nadia Division, PHE Dte. | 7360/ND | 18/12/2024 | 60 | A.K.ADHIKARY | 23.35 | 0 | 0 | 0
649 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-IV PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10526 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 93.44 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-IV to accommodate FHTC within Karimpur-I block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | 4168/ND | 30/07/2024 | 180 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 244.34 | 0 | 0 | 0
650 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-IV PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10526 | Augmentation | Reimbursement of additional GST due to enhancement of rate from 12% to 18% vide notification no 03/2022-central tax rate dt 13.07.2022 for the work of Laying Of Distribution System Including Specials, Valves & Pipe Carrying Structure All Complete, Proposed Augmentation Of Rising Main System, Providing FHTC Including Supplying, Laying, Fitting, Fixing Of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE 100, PN16) Pipe With All Necessary Specials, Saddle Piece Etc., Construction Of 500 Cum Capacity 20 Mtr. Staging Height Rcc Over Head Reservoir (Excluding Pile Foundation), Pipe Connection And Cost Of Pipes, Specials And Soil Investigation All Complete For Augmentation Of Ground Based Water Supply Scheme At Karimpur Jalangi Zone-IV To Accommodate FHTC Under Tehatta Sub-Divn Under Nadia Divn, PHE Dte." | 152/PFMS | 31/07/2024 | 0 | UMWELT ENGINEER PVT LTD | 24.01 | 0 | 0 | 0
651 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-IV PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10526 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., construction of 500 cum capacity 20 mtr. Staging height rcc over head reservoir(excluding pile foundation), pipe connection and cost of pipes,specials and soil investigation all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-IV to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 4227/ND | 27/09/2022 | 1057 | UMWELT ENGINEERS PVT LTD | 561.44 | 509.76 | 90.79 | 89
652 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-IV PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10526 | Augmentation | Repairing and renovation works of Pump House and allied works of ground based piped water supply scheme for Karimpur Jalangi Zone-IV water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 7409/ND | 19/12/2024 | 180 | BISHAL CONSTRUCTION | 13.72 | 0 | 0 | 90
653 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-IV PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10526 | Augmentation | Laying of additional pipeline for Hazrakhali, Fulkhali, Betbaria, Marttajapur, Mollahad, Chaugachha, Haripur & Arabpur mouzas under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 246/ND | 14/01/2025 | 270 | JOY HIND TUBEWELL'S | 153.86 | 0 | 0 | 30
654 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. , SM/09794 | Augmentation | Material Requisition To Resource Division | 4928/ND | 25/11/2022 | 0 | Resource Division | 11.62 | 0 | 0 | 0
655 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. , SM/09794 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | 632/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.43 | 0 | 0 | 0
656 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. , SM/09794 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for JJM works for the period 90 days w.e.f. 01/04/2023.(as and when required). | 376/KSD | 28/03/2023 | 90 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 0
657 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. , SM/09794 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC at Pump House No.- I & II under DURGAPUR CHOWGACHA W/S Scheme, Block- Krishnaganj , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 11) | 413/EMD | 20/01/2023 | 30 | SHRESTHA | 8.93 | 7.54 | 100 | 99
658 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. , SM/09794 | Augmentation | Supplementary works to completion of ongoing FHTC-related work under Durgapur Chowgacha W/S Scheme (Block - Krishnaganj), PHE Dte., Dist.-Nadia. | 755/EMSD-II | 09/10/2023 | 10 | SHRESTHA | 0.93 | 0.93 | 100 | 100
659 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. , SM/09794 | Augmentation | Material Requisition To Resource Division | 1032/ND | 03/03/2022 | 0 | Resource Division | 22.03 | 0 | 0 | 0
660 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. , SM/09794 | Augmentation | Material Requisition To Resource Division | 2159/ND | 18/05/2022 | 0 | Resource Division | 11.58 | 0 | 0 | 0
661 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. , SM/09794 | Augmentation | Material Requisition To Resource Division | 1394/ND | 24/03/2022 | 0 | Resource Division | 28.51 | 0 | 0 | 0
662 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. , SM/09794 | Augmentation | Material Requisition To Resource Division | 1003/ND | 10/03/2023 | 0 | Resource Division | 16.45 | 0 | 0 | 0
663 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. , SM/09794 | Augmentation | Material Requisition To Resource Division | 2420/ND | 05/06/2023 | 0 | Resource Division | 12.64 | 0 | 0 | 0
664 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. , SM/09794 | Augmentation | Material Requisition To Resource Division | 2292/ND | 29/05/2023 | 0 | Resource Division | 24.68 | 0 | 0 | 0
665 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. , SM/09794 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 81 m3/hr at Durgapur Chowgacha Water Supply Scheme within Krishnaganj Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | 1897/ND | 15/03/2024 | 180 | MANGES INDUSTRIAL CORPORATION | 227.13 | 0 | 0 | 0
666 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. , SM/09794 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 450 cum capacity 20 Mtr. staging height RCC Over Head Reservoir & Soil Investigation for Augmentation of Ground Based Water Supply Scheme at Durgapur Chowgacha to accommodate FHTC within Krishnaganj block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 4542/ND | 21/10/2022 | 365 | UMWELT ENGINEER PVT LTD, 140 RAJADANGA CHAKRABORTY PARA, 1ST FLOOR, KASBA, KOLKATA-700107. | 615 | 558.32 | 90.72 | 92
667 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. , SM/09794 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab for official use for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for JJM works for the period 90 days w.e.f. 01.01.2023 (as and when required). | 1331/KSD | 29/12/2022 | 90 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 100
668 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. , SM/09794 | Augmentation | Construction of Additional Boundary wall and allied works at Headwork Site at Durgapur Chowgacha Water Supply Scheme within Krishnaganj block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 1474/ND | 25/03/2025 | 300 | NILAY KUMAR BHATTACHARYA | 15.55 | 0 | 0 | 60
669 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. , SM/09794 | Augmentation | Construction and installation of Manifold at OHR site, Providing leftout FHTC with laying of additional distribution system and allied works in connection to the Augmentation of Durgapur Chowgacha Water Supply Scheme under Krishnaganj Block under Nadia Division, P.H.E Dte. | 875/ND | 25/02/2025 | 60 | M/S GHOSH CONSTRUCTION | 67.59 | 0 | 0 | 10
670 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. , SM/09794 | Augmentation | Pipeline Crossing by adopting Trenchless Technologies (i.e. Jack Push Method etc) and allied works for Railway in connection to the Augmentation of Ground Based Water Supply Scheme at Adityapur Village to accommodate FHTC within Krishnaganj block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 3323/ND | 15/07/2025 | 90 | MANGES INDUSTRIAL CORPORATION | 39.16 | 0 | 0 | 0
671 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc , SM/09964 | Augmentation | Phase-II FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIA Darappur, at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. ( Sl.No. 03) | 965/NAD-I | 07/07/2022 | 60 | M/S K.P. CONSTRUCTION | 78.62 | 51.82 | 65.91 | 40
672 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc , SM/09964 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-VI (BALIA) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 429/NAD-I | 07/03/2022 | 60 | BIDYUT KUMAR | 87.82 | 81.95 | 100 | 100
673 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc , SM/09964 | Augmentation | Repair of 250 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House Darrappur Z-VIA under Surface W/S Scheme of Chakdah (Part) under Nadia Arsenic Division -I, P.H.E.Dte. (Sl.no. 06) | 1531/ NAD-I | 30/08/2022 | 45 | MAA LAXMI ENTERPRISE | 17.21 | 17.1 | 100 | 100
674 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc , SM/09964 | Augmentation | Repair of 700 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at Ballavpur Zone- VII under Surface (Sl.no.07) | 1964 / NAD-I | 14/10/2022 | 45 | D.C. RAKSHIT & SONS INDIA PVT LTD | 29.25 | 28.66 | 100 | 100
675 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc , SM/09964 | Augmentation | Material Requisition To Resource Division | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 14.93 | 0 | 0 | 0
676 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc , SM/09964 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-VII, (Ballavpur), Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 514/NAD-I | 28/03/2022 | 60 | MANGES INDUSTRIAL CORPORATION | 125 | 111.93 | 100 | 100
677 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc , SM/09964 | Augmentation | Repair of 550 cum capacity Over Head Reservoir, Boundary Wall, Switch Room and other allied works at Balia (Zone-VI) under Chakdah Surface W/S Scheme in Chakdah Block under Nadia Arsenic Division ? I, P. H..E. Dte (SL NO. 04) | 1367/NAD-I | 12/05/2023 | 30 | M/S COSMOPOLITAN TRADERS | 23.55 | 21.53 | 100 | 100
678 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc , SM/09964 | Augmentation | Retrofitting work at Lakshmipur and Srinagar under Ballavpur W/S Scheme in connection with augmentation of Ballavpur W/S Scheme under Chakdah (Part) W/S Scheme under JJM under NadiaArsenic Division-I, PHE Dte. (sl.no.18) | 2243/NAD-I | 21/09/2023 | 15 | MANGES INDUSTRIAL CORPORATION | 9.54 | 9.45 | 100 | 100
679 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate , SM/09969 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-III (Jalkar Bhomra) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte ( Sl No. 08) | 424/NAD-I | 07/03/2022 | 60 | MONDAL ENTERPRISE | 90.02 | 84.48 | 100 | 100
680 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate , SM/09969 | Augmentation | Laying of UPVC Pipeline at different locations of Jalkar Bhomra(Zone-III),Madanpur(Zone-XII) and Birohi(Zone-XI) under Kastodanga-I & II, Madanpur-I & II and Birohi-I G.P. respectively under Haringhata & Chakdah (Part) Surface Water Supply scheme Under Nadia Arsenic Division-I,PHE Dte. | 89/ AE-I/NAD-I | 28/04/2022 | 15 | AVINABA ENGINEERING CONCERN | 4.82 | 4.82 | 100 | 100
681 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate , SM/09969 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-IV (Uttar Duttapara) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. ( Sl. NO. 09) | 425/NAD-I | 07/03/2022 | 60 | SARKAR AGENCY | 91.65 | 91.25 | 100 | 100
682 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate , SM/09969 | Augmentation | Augmentation work for Balance Portion of Zone-XI (Birohi) and Zone-III (Jalkar Bhomra) in connection with Augmentation of Zone-III (Jalkar Bhomra) Part-III at Haringhata Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.1) | 237 /AE-I/NAD-I | 18/05/2023 | 7 | BUDDHADEV MONDAL | 4.81 | 4.81 | 99.97 | 0
683 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate , SM/09969 | Augmentation | Shifting and Laying of D.I. (K9) Pipes at Kalyani More along (NH-34) in connection with Augmenation of Zone-IV (Uttar Duttapara) Part-III under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.02) | 238 /AE-I/NAD-I | 18/05/2023 | 7 | BUDDHADEV MONDAL | 4.56 | 4.56 | 99.93 | 0
684 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate , SM/09969 | Augmentation | Augmentation Work of Zone-IV (Uttar Duttapara) Part-III under JJM in connection with Surface Water based PWSS for Haringhata and Chakdah (Part) in Haringhata Block under Nadia Arsenic Division-I, P.H.E. Dte(sl.03) | 1253 / NAD-I | 04/05/2023 | 30 | CHOWDHURY & CO. | 95.64 | 95.19 | 99.52 | 0
685 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate , SM/09969 | Augmentation | Repair of 900 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House at Jalkar Bhomra, Zone-III under Surface W/S Scheme of Haringhata-Chakdah Part under NAD I PHE Dte (Sl.no.09) | 1702 / NAD-I | 09/09/2022 | 60 | GHOSH CONSTRUCTION | 33.26 | 30.48 | 100 | 100
686 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate , SM/09969 | Augmentation | Retrofiting of work in Kastodanga -II, G.P. at Jalkar Bhomra (Zone-III) under Surface Water based PWSS for arsenic affected areas of Haringhata and Chakdah (Part) Block under Nadia Arsenic Division -I P.H.E. Dte. (Sl No.-06) | 166 /AE-I/ NAD-I | 04/07/2022 | 15 | MONDAL ENTERPRISE | 4.84 | 4.84 | 100 | 100
687 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate , SM/09969 | Augmentation | Repair of 600 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Uttar Duttapara, Zone-IV under Surface W/S Scheme of Haringhata-Chakdah (Part) under JJM under Nadia Arsenic Division - I P. H.E. Dte (sl.21) | 830/NAD-I | 31/03/2023 | 21 | MS MAA BHABANI ENTERPRISE | 24.42 | 24.38 | 100 | 100
688 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate , SM/09969 | Augmentation | Providing FHTC (Functional Household Tap Connection) and Recoonection at Ayeshpur,Sonakhali at Birohi-I G.P & Dakshin Rajapur at Birohi-II G.P under Jal Jeevan Mission (JJM) for Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Birohi under Nadia Arsenic Division-I, PHE Dte. | 463/AE-I/NAD-I | 05/10/2023 | 30 | MANAJIT BISWAS | 3.99 | 3.98 | 100 | 100
689 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MOBARAKPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09259 | Augmentation | Construction of Boundary wall with Grill Gate at Mobarakpur 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | 52/AE-II/NACD-II | 17/02/2022 | 30 | MUKHERJEE CONSTRUCTION | 3.47 | 3.44 | 99.04 | 100
690 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MOBARAKPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09259 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Mobarakpur W/s Scheme (Vill - Haripur) in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 268/NACD-II | 22/02/2021 | 21 | SANJIB DEY | 30.48 | 0 | 0 | 100
691 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MOBARAKPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09259 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Mobarakpur W/s Scheme (Vill - Mobarakpur) in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 267/NACD-II | 22/02/2021 | 21 | CHANDAN ROY | 30.39 | 0 | 0 | 100
692 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MOBARAKPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09259 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | 982/EE/NACD-II | 27/12/2021 | 45 | M/S. R.K.ENTERPRISE | 152.25 | 137.15 | 100 | 100
693 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MOBARAKPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09259 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mobarakpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | 173/NACD-II | 21/03/2022 | 90 | PATHIK PABAN NANDI | 98.64 | 98.42 | 100 | 100
694 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED MOBARAKPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09259 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SHYAMNAGAR(Block-Krishnaganj), MOBARAKPUR(Block-Tehatt-I), PATHARGHAT(Block-Tehatt-I) W/S Scheme, Dist. - Nadia. | 1505/EMD. | 18/04/2023 | 30 | DIPALI CONSTRUCTION | 19.37 | 6.37 | 100 | 80
695 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MOBARAKPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09259 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Mobarakpur) | 1278/NACD-II | 14/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
696 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED MOBARAKPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09259 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SHYAMNAGAR(Block-Krishnaganj), MOBARAKPUR(Block-Tehatt-I), PATHARGHAT(Block-Tehatt-I) W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 03) | 1505/EMD | 18/04/2023 | 30 | DIPALI CONSTRUCTION | 19.37 | 0 | 0 | 90
697 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MOBARAKPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09259 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Mobarakpur Water Supply Scheme in Tehatta-I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 330/1/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.68 | 1.68 | 100 | 100
698 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MOBARAKPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09259 | Augmentation | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-II Block of Nadia District through Jadavpur University. (Name of PWSS Barnia) | 1271/NACD-II | 09/11/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
699 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MOBARAKPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09259 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Mobarakpur Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II, P.H.E Dte | 721/NACD-II | 07/06/2024 | 296 | GHOSH ENTERPRISE | 19.42 | 0 | 0 | 100
700 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MOBARAKPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09259 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Mobarakpur, Binodnagar & Taranipur Water Supply Scheme of capacity 93 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | 152/NACD-II | 02/02/2024 | 598 | B.M. ENGINEERING & CONSTRUCTION | 241.81 | 0 | 0 | 0
701 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone I , SM/09108 | Retrofitting | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone I | 619/PFMS | 14/03/2022 | 0 | UMWELT ENGINEERS PVT LTD | 3.96 | 0 | 0 | 0
702 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone I , SM/09108 | Retrofitting | Material Requisition To Resource Division | 96/ND | 06/01/2022 | 0 | Resource Division | 9.75 | 0 | 0 | 0
703 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone I , SM/09108 | Retrofitting | Material Requisition To Resource Division | 784/ND | 18/02/2022 | 0 | Resource Division | 5.49 | 0 | 0 | 0
704 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone I , SM/09108 | Retrofitting | Material Requisition To Resource Division | 1258/ND | 16/03/2022 | 0 | Resource Division | 8.29 | 0 | 0 | 0
705 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone I , SM/09108 | Retrofitting | Continuation for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | 4689/ND | 28/08/2024 | 45 | IMAGIN | 19.44 | 19.44 | 100 | 100
706 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone I , SM/09108 | Retrofitting | Continuation of Wall Writing Work under Nadia Division P. H. Engineering Dte. | 3445/ND | 20/06/2024 | 30 | IMAGIN | 20.46 | 10.23 | 100 | 100
707 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone I , SM/09108 | Retrofitting | Continuation for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | 4141/ND | 29/07/2024 | 45 | IMAGIN | 19.44 | 19.44 | 100 | 100
708 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone I , SM/09108 | Retrofitting | Providing FHTC (Functional Household Tap Connection) by Augmentation under Jal Swapna for Ghoralia Zone-I Water Supply Scheme in Nadia District under Nadia Division. | 351/ND | 25/01/2022 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 416.69 | 282.62 | 67.83 | 71
709 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone I , SM/09108 | Retrofitting | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
710 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10523 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Karimpur-Jalangi Z-5 W/S Scheme in Karimpur-I Block of Nadia District under Nadia Division, P.H.E. Dte. | 314/TSD | 24/11/2021 | 30 | RADIANT | 2.98 | 2.98 | 100 | 100
711 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10523 | Augmentation | Material Requisition To Resource Division | 5285/ND | 19/12/2022 | 0 | Resource Division | 31.89 | 0 | 0 | 0
712 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10523 | Augmentation | Material Requisition To Resource Division | 2283/ND | 29/05/2023 | 0 | Resource Division | 16.79 | 0 | 0 | 0
713 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10523 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KARIMPUR JALANGI (Z-IV, V & XB) W/S Scheme, Block-Karimpur I , Dist. - Nadia. NIET NO. - 33 OF EE/EMD OF 2022-23 (SL. NO. - 03) | 1198/EMD | 22/03/2023 | 771 | AVINABA ENGINEERING CONCERN | 62.41 | 0 | 0 | 80
714 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10523 | Augmentation | Repairing and renovation works of Pump House and allied works of ground based piped water supply scheme for Karimpur Jalangi Zone-V water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 7060/ND | 04/12/2024 | 90 | BANERJEE ENTERPRISE | 12.66 | 0 | 0 | 0
715 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10523 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 300 cum capacity 20 mtr. staging height RCC Over Head reservoir (Excluding pile Foundation), pipe connection and cost of pipes, specials and soil investigation all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-V to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 4386/ND | 13/10/2022 | 1024 | APURBA MANDAL | 339.55 | 257.42 | 75.81 | 95
716 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10523 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Karimpur Jalangi Zone-V Ground Based Water Supply Scheme under Karimpur I Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Karimpur Jalangi Zone-V at Karimpur I Block by Augmentation of Ground Water based PWSS for Karimpur Jalangi Zone-V Water Supply Schemes under Nadia Division, PHE Dte. | 456/ND | 29/01/2025 | 60 | DEL DELTA CONSTRUCTION | 23.39 | 0 | 0 | 0
717 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10523 | Augmentation | Laying distribution system for Augmentation of Ground Water Based Water Supply Scheme for Karimpur Jalangi Zone-V [Part-B] under Tehatta Sub-Division under Nadia Division PHE.Dte. | 1915/ND | 15/03/2024 | 300 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 73.46 | 4.03 | 5.49 | 30
718 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10523 | Augmentation | Laying of additional pipeline for Hazrakhali, Fulkhali, Betbaria, Marttajapur, Mollahad, Chaugachha, Haripur & Arabpur mouzas under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 246/ND | 14/01/2025 | 270 | JOY HIND TUBEWELL'S | 153.86 | 0 | 0 | 30
719 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-V PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10523 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 49.81 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-V to accommodate FHTC under Tehatta Sub-division under Nadia Division P.H.E. Dte. | 4353/ND | 07/08/2024 | 180 | G.D. CONSTRUCTION AND CO. | 181.93 | 0 | 0 | 0
720 | NADIA | Eastern Mechanical | EXTENSION OF INTAKE STRUCTURE UNDER SURFACE WATER BASED WATER SUPPLY SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT (NORTHERN SECTOR) PART-II , SM/10692 | Augmentation | Dismantling the existing Electro-Mechanical system from Barge and re-installation on the newly constructed Barge by providing axially split casing pumping machinery for the Surface based water supply scheme for Arsenic affected block of Nakashipara in the district of Nadia. | 1541/EMD | 12/06/2024 | 183 | TRADERS & ENGINEERS PVT. LTD. | 108.54 | 0 | 0 | 0
721 | NADIA | Nadia Division | EXTENSION OF INTAKE STRUCTURE UNDER SURFACE WATER BASED WATER SUPPLY SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT (NORTHERN SECTOR) PART-II , SM/10692 | Augmentation | Material Requisition To Resource Division | 6973/ND | 21/11/2024 | 0 | Resource Division | 356.75 | 0 | 0 | 0
722 | NADIA | Nadia Division | EXTENSION OF INTAKE STRUCTURE UNDER SURFACE WATER BASED WATER SUPPLY SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT (NORTHERN SECTOR) PART-II , SM/10692 | Augmentation | Survey, Design, Construction, Supply, Erection & Commissioning of Raw Water Intake Structure (Floating Barge type), Pump House for drawing 34.52 MLD raw water from the river Hooghly with all related accessories, Substation Building with Laying of 700mm dia. DI(K9) Raw Water Pipe Line from Intake Pump House and connecting to the existing raw water main (Approx. 3450 Mtr. length), River Bank Protection works, Boundary Wall, Internal Road and Surface Water Drainage system at the Intake point on EPC-turnkey basis including 3(Three) months trial run & 6 (Six) months defect liability period and 5 (Five) year subsequent Operation and Maintenance complete for the surface water based water supply scheme for arsenic affected Block of Nakashipara in the district Nadia under PHE Dte | 4774/ND | 16/10/2023 | 366 | TRADERS AND ENGINEERS PRIVATE LIMITED | 1551.6 | 672.95 | 43.39 | 7
723 | NADIA | Nadia Division | EXTENSION OF INTAKE STRUCTURE UNDER SURFACE WATER BASED WATER SUPPLY SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT (NORTHERN SECTOR) PART-II , SM/10692 | Augmentation | Repairing of HDPE pipeline at raw water rising main at Kashiadanga Intake point site, Gotpara site & Bypass connection system for different OHR site including with all necessary specials, valves all complete for Northern Sector Part-II under Nakashipara Block of Nadia District under Nadia Division PHE Dte. | 2976/ND | 25/06/2025 | 90 | BANERJEE CONSTRUCTION | 22.06 | 0 | 0 | 20
724 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. , SM/10598 | Augmentation | Material Requisition To Resource Division | 126/ND | 05/01/2023 | 0 | Resource Division | 30.06 | 0 | 0 | 0
725 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. , SM/10598 | Augmentation | Material Requisition To Resource Division | 1997/ND | 08/05/2023 | 0 | Resource Division | 30.69 | 0 | 0 | 0
726 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. , SM/10598 | Augmentation | Material Requisition To Resource Division | 1997/ND | 08/05/2023 | 0 | Resource Division | 31.11 | 0 | 0 | 0
727 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. , SM/10598 | Augmentation | Material Requisition To Resource Division | 2319/ND | 29/05/2023 | 0 | Resource Division | 24.61 | 0 | 0 | 0
728 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. , SM/10598 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MAHISUNRA W/S Scheme, Block-NABADWIP, PALASIPARA W/S Scheme, Block-Tehatta-II AND TOPLA W/S Scheme, Block-Karimpur-II Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No. - 05) | 499/EMD | 24/01/2023 | 30 | WEST BENGAL ENGINEERING CO. | 90.14 | 6.39 | 25.15 | 15
729 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. , SM/10598 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Mahisunra W/S Scheme (Phase-II,T/W-I& II) , Nabadwip Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 510/CDD | 01/06/2023 | 30 | UNIVERSAL ENTERPRISES | 37.73 | 0 | 0 | 10
730 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. , SM/10598 | Augmentation | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of capacity 156 m3/hr at Mahisura Water Supply Scheme within Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | 6571/ND | 21/10/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 348.3 | 0 | 0 | 0
731 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. , SM/10598 | Augmentation | Laying of Distribution System including Specials, Valves and Pipe Supporting Structure for providing FHTC in connection to Augmentation of Ground Water Based Piped Water Supply Scheme of Mahisura (Phase-II) in Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, PHE Dte. | 1298/ND | 23/02/2024 | 90 | PATHIK PABAN NANDI | 63.92 | 56.11 | 87.78 | 80
732 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. , SM/10598 | Augmentation | Proposed Augmentation of Rising Main System, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 1 No. Pump House at proposed Head Work site & Tube Well site, Construction of R.C.C. Elevated Reservoir of 900 Cum capacity (including pile foundation), and Soil Investigation for construction of OHR all complete for Augmentation of Ground Based Water Supply Scheme at Mahisura (Phase-II) to accommodate FHTC within Nabadwip Block under Krishnanagar Sub-division under Nadia Division, PHE Dte. | 1385/ND | 29/03/2023 | 1009 | M/S GHOSH CONSTRUCTION, SUKUL ROAD,P.O.-KRISHNAGAR, DIST. NADIA, PIN-741101, WB | 401.97 | 143.35 | 35.66 | 40
733 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | ContinuationWork order for Supply of CIDF Sluice, Non return valves and DI Mechanical collar Vavle for relaying of rising main of Barnia Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | 212/AE-I/NACD-II | 20/01/2022 | 7 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.96 | 4.96 | 100 | 100
734 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Repairing of Filter units Solar Powered Community Water Purification plant at site 'Border Out post (BOP) Gede of 54 BN BSF' | 282/AE-I/NACD-II | 04/03/2022 | 5 | JOY HIND TUBEWELLS | 4.98 | 4.98 | 100 | 100
735 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Repairing of Filter units Solar Powered Community Water Purification plant at site 'Border Out post (BOP) Gede of 54 BN BSF' | 283/AE-I/NACD-II | 04/03/2022 | 5 | JOY HIND TUBEWELLS | 4.98 | 4.98 | 100 | 100
736 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Supply of 15mm x 10mm MS Bush (26000 nos.) | 284/AE-I/NACD-II | 04/03/2022 | 5 | JOY HIND TUBEWELLS | 4.94 | 4.94 | 100 | 100
737 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Continuation work order for Supply of 15mm x 10mm dia M.S Bush under Nadia Arsenic Civil Division-II, PHE Dte. | 15/AE-I/NACD-II | 12/04/2022 | 5 | JOY HIND TUBEWELLS | 4.94 | 4.94 | 100 | 100
738 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair and also DI Laying in distribution at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 993/NACD-II | 30/12/2021 | 45 | J.D.J. ENTERPRISE | 98.17 | 16.24 | 100 | 100
739 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Relaying of D.I. Pipeline replacing the damaged old UPVC Pipe at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division -II, PHE Dte. | 98/NACD-II | 10/02/2022 | 45 | PRABIR KUMAR ROY | 14.31 | 0 | 0 | 100
740 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 42/NACD-II | 17/01/2022 | 45 | NILAY KUMAR BHATTACHARYA | 21.05 | 0 | 0 | 100
741 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 117/NACD-II | 15/02/2022 | 90 | M/S. R.K.ENTERPRISE | 173.44 | 0 | 0 | 100
742 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Construction of Boundary wall with Grill Gate at Barnia Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | 235/AE-I/NACD-II | 17/02/2022 | 30 | SAMAR ENTERPRISE | 4.7 | 4.61 | 100 | 100
743 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Material Requisition To Resource Division | 167 | 17/03/2022 | 0 | Resource Division | 20.91 | 0 | 0 | 0
744 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BRITTIHUDA (Block- Chapra), BARNIA (Block- Tehatt II ), MAHATPUR (Block- Chapra ), MATIARY (Block- Krishnaganj), BAGAKHALI (Z-I) (Block- Tehatta I ), BARA NALDAH (Block- Tehatta II ) W/S Scheme, , Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 01) | 1120/EMD | 16/03/2023 | 30 | B.T. PROJECTS PVT. LTD | 91.82 | 0.71 | 4.02 | 60
745 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Continuation Work order for Structural Health assesment of existing shaft type OHR of Tehatta-II Blocks ( and ancillary structures conductingNon-Destructive test and through visual observation under Nadia Arsenic Civil Division-II P.H.E Dte. | 114/NACD-II | 29/01/2024 | 30 | SIRCON ENGINEERING SERVICE | 0.69 | 0 | 0 | 0
746 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly Introduced hydraulics at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 528/AE-I/NACD-II | 18/12/2023 | 15 | SANJIB BISWAS | 0.97 | 0.97 | 100 | 100
747 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Technical framework for Conclusive ATR Regarding WBCMRO Grievance portal at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 530/AE-I/NACD-II | 18/12/2023 | 15 | SANJIB BISWAS | 0.97 | 0.97 | 100 | 100
748 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Provisioning of solution as per CMRO Grievance in all complete including newly added pipeline (parallel or damaged line repair due to construction of drain) at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 529/AE-I/NACD-II | 18/12/2023 | 15 | USHA CONSTRUCTION | 0.97 | 0.97 | 100 | 100
749 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Exigent Repair of Pipeline due to construction stotm water drain by PRI Body at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 531/AE-I/NACD-II | 18/12/2023 | 15 | USHA CONSTRUCTION | 0.97 | 0.97 | 100 | 100
750 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Structural Health assesment of existing shaft type OHR of Tehatta-II Blocks ( and ancillary structures conducting Non-Destructive test and through visual observation under Nadia Arsenic Civil Division-II P.H.E Dte. | 1428/NACD-II | 15/12/2023 | 30 | SIRCON ENGINEERING SERVICE | 7.77 | 7.77 | 100 | 100
751 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Barnia Piped Water Supply Scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1304/NACD_II | 30/11/2023 | 30 | USHA CONSTRUCTION | 25.6 | 25.32 | 100 | 100
752 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Providing Functional House Hold Tap Connection 13 numbers at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 556/AE-I/NACD-II | 10/01/2024 | 15 | USHA CONSTRUCTION | 0.97 | 0.96 | 100 | 100
753 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Wall writing work in various Gram Panchayats in Tehatta-II Block at Barnia PWSS under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 757/AE-I/NACD-II | 19/06/2024 | 15 | IMAGIN | 0.93 | 0.93 | 100 | 100
754 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Continuation work order for Provisioning of solution as per CMRO Grievance in all complete including newly added pipeline (parallel or damaged line repair due to construction of drain) at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 669/AE-I/NACD-II | 18/03/2024 | 15 | USHA CONSTRUCTION | 0.97 | 0.96 | 100 | 100
755 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection 13 numbers at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 670/AE-I/NACD-II | 18/03/2024 | 15 | USHA CONSTRUCTION | 0.97 | 0.96 | 100 | 100
756 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Provisioning of hydraulics as per IS 4985 with latest edition at within the command area of Barnia W/s Scheme at Tehatta II Development Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 557_AE-I/NACD-II | 10/01/2024 | 15 | USHA CONSTRUCTION | 0.97 | 0.92 | 100 | 100
757 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly Introduced hydraulics at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 685/AE-I/NACD-II | 03/04/2024 | 15 | SANJIB BISWAS | 0.97 | 0.95 | 100 | 100
758 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Continuation work order for Exigent Repair of Pipeline due to construction stotm water drain by PRI Body at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 683/AE-I/NACD-II | 03/04/2024 | 15 | USHA CONSTRUCTION | 0.96 | 0.93 | 100 | 100
759 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Continuation work order for Technical framework for Conclusive ATR Regarding WBCMRO Grievance portal at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 686/AE-I/NACD-II | 03/04/2024 | 15 | SANJIB BISWAS | 0.97 | 0.95 | 100 | 100
760 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Continuation work order for Provisioning of hydraulics as per IS 4985 with latest edition at within the command area of Barnia W/s Scheme at Tehatta II Development Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 671/AE-I/NACD-II | 18/03/2024 | 15 | USHA CONSTRUCTION | 0.96 | 0.94 | 100 | 100
761 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Construction of pumphouse cum Chlorine room with sanitary and water supply arrangement at Abhaynagar mouza in Barnia Piped water supply scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II, PHE Dte. Dist- Nadia | 48/NACD-II | 10/01/2025 | 270 | NAMDAR ALI | 6.22 | 0 | 0 | 100
762 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Construction of 50 m3/hr capacity Iron Elimination Plant at Mouza Abhaynagar underBarnia Public Water Supply Scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 1127/NACD-II | 21/08/2024 | 61 | PAPAN ROY | 23.07 | 0 | 0 | 60
763 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | New Sinking of 1 no. 250 mm X 150 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Mouza Ujirpur under Barnia Water Supply Scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II PHE Dte. | 1390/NACD-II | 22/10/2024 | 135 | GENUINE | 10.41 | 0 | 0 | 100
764 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Construction of 50 m3/hr capacity Iron Elimination Plant at Mouza UjirPur underBarnia Public Water Supply Scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 1306/NACD-II | 20/09/2024 | 364 | USHA CONSTRUCTION | 22.96 | 0 | 0 | 60
765 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Barnia Water Supply Scheme of capacity 160 Cu.m/hr in Tehatta-II Block under Nadia Arsenic Civil Division -II, PHE Dte." | 218/NACD-II | 16/02/2024 | 421 | MONDAL PRECISION PRIVATE LIMITED | 363.16 | 244.08 | 67.21 | 20
766 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Abhaynagar and Ujirpur and Komthana mouza of Barnia W/s Scheme of Tehatta-2 Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1608/NACD-II | 16/12/2024 | 270 | USHA CONSTRUCTION | 153.16 | 0 | 0 | 50
767 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC under Barnia (Source Augmentation, Abhaynagar) ground water based water supply scheme under Block_ Tehatta-II Dist. - Nadia under EMD, PHE Dte. | 699/EMD | 04/04/2025 | 30 | SMILE | 10.79 | 0 | 0 | 0
768 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC under Barnia (Source Augmentation,Ujjinpur) ground water based water supply scheme under Block_ Tehatta-II Dist. - Nadia under EMD, PHE Dte. | 698/EMD | 04/04/2025 | 30 | STANDARD ENGINEERING | 11.86 | 0 | 0 | 0
769 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Laying of distribution system including providing FHTC at left out households for Bahadurpur, Khaspu, Dhopahat and Rajapur W/s Scheme and restoration of the damaged portion of roads in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte and Brittihuda W/S Scheme & Barnia W/S Scheme included. | 736/NACD-II | 18/06/2025 | 90 | JOY HIND TUBEWELLS | 186.42 | 0 | 0 | 40
770 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Construction of Switch Room (3.50 mtr x 2.70 mtr) in Barnia Public Water Suply Scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | 108/AE-I/NACD-II | 04/06/2025 | 60 | M/S RAJESH CONSTRUCTION | 3.28 | 0 | 0 | 0
771 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bagakhali Zone-I W/s Scheme (Vill- Sahapur) in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. & Barnia Pwss under Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 128_NACD-II | 21/02/2022 | 90 | M/S NANDY ENTERPRISES | 102.45 | 0 | 0 | 100
772 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10093 | Augmentation | Supply of flow control devices in the closed water conduit at Barnia PWSS in Tehatta-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 223/AE-I/NACD-II | 01/09/2025 | 20 | MAKALI ENGINEERING CORPORATION | 4.79 | 0 | 0 | 100
773 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-II) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. , SM/10726 | Augmentation | Proposed Augmentation of Rising Main System, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 1 No. Pump House at proposed Head Work site & Tube Well site, Construction of R.C.C. Elevated Reservoir of 750 Cum capacity (including pile foundation), and Soil Investigation for construction of OHR all complete for Augmentation of Ground Based Water Supply Scheme at Bhimpur (Phase-II) to accommodate FHTC within Krishnagar-I Block under Krishnanagar Sub-division under Nadia Division, PHE Dte. | 3218/ND | 26/07/2023 | 366 | SINGHA ROY & CO. | 339.59 | 0 | 0 | 0
774 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-II) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. , SM/10726 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Bhimpur (Phase-II) W/S Scheme (TW-I) , Krishnagar-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 1654/CDD | 17/10/2023 | 30 | MENAKA ENTERPRISE | 18.88 | 0 | 0 | 0
775 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-II) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. , SM/10726 | Augmentation | Material Requisition To Resource Division | 84/ND | 05/01/2023 | 0 | Resource Division | 106.78 | 0 | 0 | 0
776 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-II) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. , SM/10726 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BANPUR W/S Scheme, Block- Krishnaganj, ARABPUR W/S Scheme, Block-Karimpur, BHIMPUR W/S Scheme, Block-Krishnagar AND MONIPOTA W/S Scheme, Block- Krishnagar-I, Dist. - Nadia. | 5127/EMD | 04/09/2023 | 666 | C.M.S. ENGINEERING CONCERN. | 70.97 | 4.44 | 12.78 | 12
777 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-II) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. , SM/10726 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 1.4 | 98.71 | 40
778 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-II) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. , SM/10726 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 136 m3/hr at Bhimpur Water Supply Scheme within Krishnagar-I Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | 6221/ND | 23/09/2024 | 180 | GHOSH ENTERPRISE | 315.76 | 0 | 0 | 0
779 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-II) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. , SM/10726 | Augmentation | Material Requisition To Resource Division | 260/ND | 11/01/2024 | 0 | Resource Division | 16.52 | 0 | 0 | 0
780 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-II) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. , SM/10726 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
781 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -VII, (Kumarpur), Zone-VIII, (Tarinipur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09940 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-VIII (Tarinipur) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 06) | 422/NAD-I | 07/03/2022 | 60 | M/S K.P. CONSTRUCTION | 73.17 | 67.83 | 100 | 100
782 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -VII, (Kumarpur), Zone-VIII, (Tarinipur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09940 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone- VII, Kumarpur Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 15) | 439/NAD-I | 07/03/2022 | 45 | MALI CONSTRUCTION | 39.65 | 39.62 | 100 | 100
783 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -VII, (Kumarpur), Zone-VIII, (Tarinipur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09940 | Augmentation | Shifting of different dia D.I pipe and HDPE Pipe from the Office Premises of Nadia Arsenic Division -I to nearest Zone-VIII (Tarinipur) OHR site under Haringhata and Chakdah (Part) Surface Based W/S Scheme at Chakdah Block under Nadia Arsenic Division-I, P.H.E. Dte. | 267/AE-I/NAD-I | 09/11/2022 | 15 | BUDDHADEV MONDAL | 3.46 | 3.46 | 100 | 100
784 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -VII, (Kumarpur), Zone-VIII, (Tarinipur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09940 | Augmentation | Repair of 900 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Tarinipur, Zone-VIII under Surface W/S Scheme of Haringhata- Chakdah (Part) under Nadia Arsenic Division-I PHE Dte (Sl.no.08) | 1639 / NAD-I | 06/09/2022 | 60 | REAL TIME | 33.3 | 30.74 | 100 | 100
785 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -VII, (Kumarpur), Zone-VIII, (Tarinipur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09940 | Augmentation | Repair of 250 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Kumarpur, Zone-VII under Surface W/S Scheme of Haringhata-Chakdah (Part) under Nadia Arsenic Division-I P.H.E Dte. (Sl. No. 12) | 2064/NAD-I | 28/10/2022 | 45 | GANGULY ENTERPRISE | 13.95 | 13.92 | 100 | 100
786 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -VII, (Kumarpur), Zone-VIII, (Tarinipur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09940 | Augmentation | Augmentation work at Zone-VIII (Tarinipur) under Augmentation work of Zone-VII (Kumarpur) and Zone-VIII (Tarinipur), Part-III at Santipur Block under Surface Water Based PWSS for Haringhata & Chakdah(Part) under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.03) | 2242/NAD-I | 21/09/2023 | 15 | NISHITH BANERJEE | 12.9 | 12.9 | 100 | 100
787 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -VII, (Kumarpur), Zone-VIII, (Tarinipur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09940 | Augmentation | Laying of UPVC Pipeline and other allied works under JJM at Khalderpara, Babudangapara for Kumarpur Zone-VII at Haringhata Block by retrofitting work of Surface based W/S Scheme Water PWSS of Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte. | 529/AE-I/NAD-I | 24/11/2023 | 30 | M/S K..M. ENTERPRISE | 4.36 | 4.35 | 100 | 100
788 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -VII, (Kumarpur), Zone-VIII, (Tarinipur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09940 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) incluidng restoration of road for Tarinipur at Sarati G.P. at Kalyani under Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 530/AE-I/NAD-I | 24/11/2023 | 30 | M/S S.K ENTERPRISE | 4.85 | 4.84 | 100 | 100
789 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11510 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Badkulla Zone-II W/S Scheme in Hanskhali Block of Nadia District under Nadia Division, P.H.E. Dte. | 1056/RSD | 02/12/2021 | 30 | RADIANT | 3.29 | 2.97 | 100 | 100
790 | NADIA | Central Drilling | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11510 | Augmentation | Providlng drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utillsing Departmental Machineries for Badkulla W/S Scheme (Z-11,1/W-l), Hanskhali Block under Nadia District, CentralDrilling Division, P.H.E. Dte (znd Call). | 1052/CDD | 16/08/2023 | 30 | MENAKA ENTERPRISE | 18.6 | 0 | 0 | 0
791 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11510 | Augmentation | Material Requisition To Resource Division | 1881/ND | 26/04/2023 | 0 | Resource Division | 100.61 | 0 | 0 | 0
792 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11510 | Augmentation | Supply, Delivery and Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under BADKULLA Z-II WS Scheme, Block- Hanskhali , Dist. - Nadia. | 4712/EMD | 04/08/2023 | 30 | KASHINATH PAL & CO. | 9.79 | 0 | 0 | 0
793 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11510 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
794 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11510 | Augmentation | Construction of 125.00 Cum/Hr capacity Arsenic-cum-Iron Removal plant at Badkulla -II Water Supply Scheme under Ranaghat Sub-Division under Nadia Division PHED. | 4280/ND | 05/08/2024 | 180 | MANGES INDUSTRIAL CORPORATION | 303.09 | 0 | 0 | 0
795 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11510 | Augmentation | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Pump house No-1 site at Badkulla Zone-II Water supply scheme under Ranaghat Sub ¿ Division, PHE Dte. | 1186/RSD | 25/09/2024 | 75 | AVIRUP CONSTRUCTION | 4.46 | 0 | 0 | 90
796 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11510 | Augmentation | Material Requisition To Resource Division | 7557/ND | 27/12/2024 | 0 | Resource Division | 8.68 | 0 | 0 | 0
797 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11510 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 250 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of OHR all complete for augmentation of Ground Water Based Water Supply Scheme for Badkulla Zone-II to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering | 3216/ND | 26/07/2023 | 366 | SATYABRATA CHAKRABORTY | 371.16 | 161.3 | 43.46 | 50
798 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11510 | Augmentation | Providing leave out functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Fulia Township Zone-I to accommodate FHTC in Santipur block and allied works of Badkulla Zone II of Nadia District under Nadia Division P.H.Engineering Dte. | 1804/ND | 22/04/2025 | 180 | APURBA MANDAL | 64.83 | 0 | 0 | 90
799 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11510 | Augmentation | Construction of R.C.C Elevated Reservoir of 700 Cum. Capacity of staging height 20M at Head works site with Annular combined pile raft foundation for Badkulla Zone-II Water Supply Scheme under Nadia Division P.H.Engineering Dte. | 2523/ND | 29/05/2025 | 365 | SATYABRATA CHAKRABORTY | 164.42 | 0 | 0 | 0
800 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11809 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 3/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 140/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.91 | 3.87 | 100 | 100
801 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11809 | Augmentation | Material Requisition To Resource Division | 125/ND | 05/01/2023 | 0 | Resource Division | 73.72 | 0 | 0 | 0
802 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11809 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
803 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11809 | Augmentation | Reconstruction of Top Dome and other related work for 455 cum RCC elevated reservoir of Surface Water Based Water Supply Scheme for Zone-III /A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, P.H.E. Dte. | 6096/ND | 19/09/2024 | 90 | M/S SANJAY ADHIKARI | 9.82 | 9.75 | 100 | 5
804 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11809 | Augmentation | Material Requisition To Resource Division | 230/ND | 11/01/2024 | 0 | Resource Division | 10.27 | 0 | 0 | 0
805 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11809 | Augmentation | Restoration work of damaged road flank of Dharmadha - Muragacha Road due to laying pipe line under ''NJJM'' Project in Nakashipara Block of Nadia District under Nadia Division, PHE Dept. of Dharmada - Muragacha Road from 0.80 kmp to 1.50 kmp (one side) & from 1.50 kmp to 3.70 kmp (both side) of Krishnagar Highway Sub-Division-I under Nadia Highway Division-I in the district of Nadia during the year 2024-2025. |  | 26/07/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 14.83 | 0 | 0 | 0
806 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11809 | Augmentation | Restoration work of damaged road flank of Dharmadha - Muragacha Road due to laying pipe line under ''NJJM'' Project in Nakashipara Block of Nadia District under Nadia Division, PHE Dept. of Dharmada - Muragacha Road from 0.80 kmp to 1.50 kmp (one side) & from 1.50 kmp to 3.70 kmp (both side) of Krishnagar Highway Sub-Division-I under Nadia Highway Division-I in the district of Nadia during the year 2024-2025. | 149/PFMS | 06/08/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 7.41 | 0 | 0 | 0
807 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11809 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4588/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 288.84 | 99.58 | 19
808 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11809 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
809 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11809 | Augmentation | Reconstruction of Staff room, Chlorination room, Godown, Boundary wall, Service road and etc. of Surface Water Based Water Supply Scheme for Zone-III /A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, P.H.E. Dte. | 6097/ND | 19/09/2024 | 360 | M/S SANJAY ADHIKARI | 55.82 | 6.94 | 12.43 | 5
810 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11809 | Augmentation | Construction of Bituminous Approch Road for GLR site at Surface water based water supply Scheme under Northern Sector Part II at Nakashipara Block under Nadia Division PHE Dte. | 3260/ND | 10/07/2025 | 90 | GBC INFRASTRUCTURE PRIVATE LIMITED | 95.58 | 0 | 0 | 5
811 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11809 | Augmentation | Additional Work for Installation of SCADA System in connection with Augmentation of Surface Water Based Piped Water Supply Scheme for Northern Sector Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 3447/ND | 23/07/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 732.35 | 0 | 0 | 15
812 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. , SM/10728 | Augmentation | Survey , Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household under Teorkhali W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Sl.No. 12) | 915/KSD | 29/11/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.39 | 3.38 | 100 | 100
813 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. , SM/10728 | Augmentation | Fencing for Land at Chapra Bangaljhi and Teorkhali Water supply scheme at new 3rd Tube Well site under Krishnagar Sub-Division PHED. | 219/KSD | 03/03/2023 | 15 | SANJIB DEY | 0.45 | 0.22 | 99.96 | 0
814 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. , SM/10728 | Augmentation | Continuation of Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 90 days w.e.f. 01/10/2023 (as and when required) | 1450/KSD | 18/09/2023 | 90 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 0
815 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. , SM/10728 | Augmentation | Material Requisition To Resource Division | 109/ND | 05/01/2023 | 0 | Resource Division | 31.18 | 0 | 0 | 0
816 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. , SM/10728 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 1.4 | 98.71 | 40
817 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. , SM/10728 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 104 m3/hr at Teorkhali Water Supply Scheme within Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | 1895/ND | 15/03/2024 | 180 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 268.24 | 0 | 0 | 0
818 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. , SM/10728 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 366 days w.e.f. 01/01/2024 to 31/12/2024 | 1838/KSD | 28/12/2023 | 366 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0 | 0
819 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. , SM/10728 | Augmentation | Sinking of 1 no. Tubewell 300mm. x 200mm. dia 200 mtr deep by direct rotary rig method and construction of pump house (3.6 mtr. x 3.0 mtr.) and boundary wall at 3rd tube well site for Teorkhali water supply scheme under Krishnagar Sub-Division under Nadia Division, PHE,Dte. (Sm/10728) | 2100/ND | 15/05/2023 | 90 | MONDAL ENTERPRISE | 29.84 | 25.7 | 100 | 75
820 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. , SM/10728 | Augmentation | Material Requisition To Resource Division | 625/ND | 30/01/2024 | 0 | Resource Division | 9.92 | 0 | 0 | 0
821 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. , SM/10728 | Augmentation | New service connection at Ph-3 of Teorkhali water supply scheme, Block-Nabadwip, Dist-Nadia | BP-51-24-25 | 21/06/2024 | 0 | WBSEDCL SWARUPGANJ C.C.C. | 7.71 | 0 | 0 | 0
822 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. , SM/10728 | Augmentation | Name of Work: Laying of Distribution System including specials & valves, pipe supporting structure all complete, proposed augmentation of Rising Main, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction of R.C.C. Elevated Reservoir of 600 Cum capacity(including pile foundation) and Soil investigation for construction of one No. 600 Cum OHR at Tiorkhali to accommodate FHTC within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 3510/ND | 10/08/2023 | 1097 | MONDAL ENTERPRISE | 579.26 | 331.41 | 57.21 | 35
823 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. , SM/10728 | Augmentation | Repair & Renovation of Pump House, Boundary wall, Store Room and allied works at 1st and 2nd Pump House at Tiorkhali Water Supply Scheme within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 6183/ND | 27/12/2023 | 485 | BIPLAB GUHA | 17.98 | 10.44 | 58.09 | 35
824 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. , SM/10728 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-III under TIORKHALI ground water based water supply scheme under Block_ KRISHNANAGAR, Dist. - Nadia under EMD, PHE Dte. [SM/10728] | 2151/EMD | 30/08/2024 | 182 | SWAPAN ENTERPRISE | 13.8 | 0 | 0 | 95
825 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/11506 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Subarnabehar W/S Scheme in Krishnagar - I Block of Nadia District under Nadia Division. PART - A | 1189/PH | 03/12/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.82 | 4.82 | 100 | 100
826 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/11506 | Augmentation | Material Requisition To Resource Division | 3894/ND | 08/09/2022 | 0 | Resource Division | 82.06 | 0 | 0 | 0
827 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/11506 | Augmentation | Material Requisition To Resource Division | 4328/ND | 29/09/2022 | 0 | Resource Division | 39.36 | 0 | 0 | 0
828 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/11506 | Augmentation | Material Requisition To Resource Division | 3375/ND | 04/08/2023 | 0 | Resource Division | 3.11 | 0 | 0 | 0
829 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/11506 | Augmentation | Laying of Distribution System including specials, valves all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Subarnabehar Zone-I to accommodate FHTC within Krishnagar-I Block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. (SM/11506) | 4383/ND | 13/10/2022 | 798 | MONDAL ENTERPRISE | 493.02 | 462.47 | 93.81 | 100
830 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/11506 | Augmentation | Providing last mile connectivity including FHTC to cover Shyamnagar and Berij village in connection with Augmentation of Ground Water Based Piped Water Supply Scheme for Subarna Bihar ZONE-I in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | 474/KlySD-II | 07/03/2024 | 45 | M/S BISWAS ENTERPRISE | 2.15 | 1.75 | 81.25 | 82
831 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/11506 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 231 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Subarnabihar Zone I PWSS under Nadia Division PHE Dte. | 1784/ND | 20/04/2023 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 222.99 | 0 | 0 | 65
832 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/11506 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augomentation in connection to Accommodate FHTC at Pump House No.-I under Subarnabehar Zone-I ground water based water supply scheme under Block_ Krishnanagar-I Dist. - Nadia under EMD, PHE Dte. | 1311/EMD | 09/05/2024 | 30 | DAS ENTERPRISE (BARANAGAR) | 12.77 | 11.82 | 100 | 100
833 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/11506 | Augmentation | Repair and renovation works of R.C.C. Elevated Existing Over Head Reservoir of capacity 1000 Cu.M for Subarnabehar Zone-I Water Supply Scheme in Nadia District under Kalyani Sub-Divn-II, under Nadia Division, PHE Dte. | 1300/ND | 23/02/2024 | 60 | S.S.CONSULTANCY & CONSTRUCTION | 16.66 | 9.95 | 100 | 96
834 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/11506 | Augmentation | Special repair and renovation of Existing Boundary Wall at Head work site of Subarnabihar Zone I water supply scheme in Nadia District under Kalyani Sub-Divn-II, under Nadia Division, PHE Dte. | 1301/ND | 23/02/2024 | 45 | ABHAYANANDA ENTERPRISE | 6.81 | 6.44 | 100 | 98
835 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/11506 | Augmentation | Special repair and renovation of pump house and allied works for Head work site (Existing) at Subarnabihar Zone I water supply scheme in Nadia District under Nadia Division PHE. Dte | 472/KlySD-II | 07/03/2024 | 30 | RAIHANA ENTERPRISE | 1 | 1 | 100 | 100
836 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/11506 | Augmentation | Special repair and renovation of Existing Boundary Wall " for 2nd ,3rd, 4th & 5th Tube Well site at Subarnabihar Zone I water supply scheme in Nadia District under Kalyani Sub-Divn-II, under Nadia Division, PHE Dte. | 1903/ND | 15/03/2024 | 45 | CONSTRUCTURE | 5.07 | 4.79 | 100 | 95
837 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/11506 | Augmentation | Special repair and renovation of pump house and allied works for 2nd ,3rd, 4th & 5th Tube Well site(Existing) at Subarnabihar Zone I water supply scheme in Nadia Distric under Nadia Division PHE. Dte | 475/KlySD-II | 11/03/2024 | 60 | DAFADAR ENTERPRISE | 1.61 | 1.59 | 100 | 98
838 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/11506 | Augmentation | Laying of distribution pipeline along with FHTC additionally to cover the remaining portion of Subarnabihar Zone-I Water Supply Scheme withih Krishnagar ¿I Block under Kalyani Sub-Division-II under Nadia Division, PHE Dte. | 3451/ND | 20/06/2024 | 360 | BUDDHADEV MONDAL | 65.26 | 9.87 | 15.12 | 75
839 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/11506 | Augmentation | Installation of Manifold, laying of dedicated pipeline and other necessary allied works for Subarnabihar Zone-I Water Supply Scheme in Krishnagar-I Block under Nadia Division PHE Dte. | 2115/ND | 02/05/2025 | 240 | BUDDHADEV MONDAL | 88.11 | 0 | 0 | 35
840 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/11506 | Augmentation | Laying of delivery main for Usidpur and Subarnabihar (P) Mouza under Krishnagar-I Block in Nadia District. | 2288/ND | 19/05/2025 | 60 | M/S GHOSH CONSTRUCTION | 63.02 | 0 | 0 | 99
841 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/11506 | Augmentation | Construction of Boundary wall to protect the aditional space of Subarnabihar Zone I water Supply Scheme under nadia Division PHE Dte. | 2849/ND | 18/06/2025 | 60 | M/S K.P.PAL | 6.48 | 0 | 0 | 0
842 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11837 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 1/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 136/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.94 | 3.79 | 100 | 100
843 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11837 | Augmentation | Material Requisition To Resource Division | 92/ND | 05/01/2023 | 0 | Resource Division | 89.07 | 0 | 0 | 0
844 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11837 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
845 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11837 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 350 cum for Providing FHTC (Functional Household Tap Connection) for Zone -I/B (Northern Sector Part-II) Water Supply Scheme in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 1252/ND | 22/02/2024 | 90 | U-TURN CONSTRUCTION | 20.98 | 10.9 | 44.7 | 10
846 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11837 | Augmentation | Material Requisition To Resource Division | 246/ND | 11/01/2024 | 0 | Resource Division | 6.14 | 0 | 0 | 0
847 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11837 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- I/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4278/ND | 21/09/2023 | 643 | PRASUN ENTERPRISE | 301.15 | 110.17 | 36.59 | 25
848 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11837 | Augmentation | Additional Work for Installation of SCADA System in connection with Augmentation of Surface Water Based Piped Water Supply Scheme for Northern Sector Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 3447/ND | 23/07/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 732.35 | 0 | 0 | 15
849 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DHORADAHA PWSS PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11874 | Augmentation | Material Requisition To Resource Division | 2298/ND | 29/05/2023 | 0 | Resource Division | 0.92 | 0 | 0 | 0
850 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DHORADAHA PWSS PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11874 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed Augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Dhoradaha to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 382/ND | 27/01/2023 | 90 | SATYABRATA CHAKRABORTY | 457.46 | 189.91 | 67.95 | 65
851 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DHORADAHA PWSS PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11874 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House and allied works of ground basaedpiped water supply scheme for Dhoradaha water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 305/ND | 17/01/2025 | 270 | J.P. CONSTRUCTION & SUPPLIERS | 35.46 | 0 | 0 | 45
852 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Sinking of 2 nos. 300 mm X 200 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Baruihuda Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 175/NACD-II | 24/01/2023 | 30 | B.M. ENGINEERING & CONSTRUCTION | 27.71 | 25.99 | 93.8 | 100
853 | NADIA | Eastern Mechanical | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Providing Electro Mechanical Equipments and Allied Works for Arsenic Removal Plant at BARUIHUDA Piped Water Supply Scheme, Block Krishnagar-I, Dist. Nadia Under EMD, PHE Dte. | 4710/EMD | 04/08/2023 | 30 | DEY ENTERPRISE | 53.06 | 0 | 0 | 0
854 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Construction of approch road at Head Works site of Baruihuda Water Supply Scheme in Krishnanagar-1 Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | 413_1AE-I/NACD-II | 08/08/2023 | 15 | MANGES INDUSTRIAL CORPORATION. | 0.98 | 0 | 0 | 0
855 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Material Requisition To Resource Division | 375/NACD-II | 24/03/2023 | 0 | Resource Division | 44.86 | 0 | 0 | 0
856 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL | 235/1 | 21/02/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
857 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. | 23 | 19/04/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.04 | 0 | 0 | 0
858 | NADIA | Eastern Mechanical | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | New Service Connection under AE-III Baruihuda | BP-106-23-24 | 31/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0 | 0
859 | NADIA | Eastern Mechanical | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | New Service Connection under AE-III Baruihuda | BP-105-23-24 | 31/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.95 | 0 | 0 | 0
860 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Soil Investigation for Construction of 01 (One) No of Overhead Reservoir, Construction of 500 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap, Laying of Distribution system including providing Functional House Hold Tap Connection (FHTC) and Laying of Rising Main and other necessary allied works at Baruihuda water supply scheme of Krishnagar-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia. | 396/NACD-II | 28/03/2023 | 731 | MANGES INDUSTRIAL CORPORATION. | 423.86 | 138.08 | 32.58 | 40
861 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Construction of 92 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Baruihuda Water Supply Scheme in Krishnagar-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | 1034/NACD-II | 05/08/2024 | 180 | GHOSH ENTERPRISE | 239.9 | 0 | 0 | 0
862 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Baruihuda water supply scheme under Krishnanagar- I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia. | 1338/NACD-II | 05/12/2023 | 45 | JAYBRATO HALDER | 29.32 | 7.43 | 20.94 | 100
863 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Renovation of Arsenic cum Iron treatment Plant of Damodarkhali PWSS (Capacity- 56 m3/hr) and ancillary works of Baruihuda W/S Scheme at Krishnagar-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 37/NACD-II | 09/01/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 100.41 | 78.35 | 100 | 100
864 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Material Requisition To Resource Division | 75/NACD-II | 15/01/2024 | 0 | Resource Division | 12.32 | 0 | 0 | 0
865 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Track crossing proposal with Application ID: ER-SDAH-2023-WL-84. Payment of way leave plan & survey charges | 295 | 27/12/2023 | 0 | EASTERN RAILWAY | 0.2 | 0 | 0 | 0
866 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Track crossing proposal with Application ID: ER-SDAH-2023-WL-83 payment of Wayleave Facility charge. | 359 | 04/03/2024 | 0 | EASTERN RAILWAY | 8.98 | 0 | 0 | 0
867 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Track crossing proposal with Application ID: ER-SDAH-2023-WL-82 payment of Wayleave Facility charge. | 358 | 04/03/2024 | 0 | EASTERN RAILWAY | 8.98 | 0 | 0 | 0
868 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Track crossing proposal with Application ID: ER-SDAH-2023-WL-83. Payment of way leave plan & survey charges | 294 | 27/12/2023 | 0 | EASTERN RAILWAY | 0.14 | 0 | 0 | 0
869 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Track crossing proposal with Application ID: ER-SDAH-2023-WL-82. Payment of way leave plan & survey charges | 293 | 27/12/2023 | 0 | EASTERN RAILWAY | 0.14 | 0 | 0 | 0
870 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Track crossing proposal with Application ID: ER-SDAH-2023-WL-84 payment of Wayleave Facility charge. | 360 | 04/03/2024 | 0 | EASTERN RAILWAY | 12.73 | 0 | 0 | 0
871 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Baruihuda water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia | 232/NACD-II | 21/02/2024 | 45 | ARIT KUMAR PAL | 11.29 | 0 | 0 | 100
872 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Construction and installation of MANIFOLD and allied works at OHR site under Shyamnagar Piped Water Supply Scheme in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 09/NACD-II | 06/02/2025 | 90 | SUMIT GHOSH | 105.58 | 0 | 0 | 0
873 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Conversion of IEP to AIRP at KADIPUR Water Supply Scheme of capacity 55 Cu.m/hr in Krishnaganj Block & CHANDERGHAT, PANINALA & BARUIHUDA Water Supply Scheme under Nadia Arsenic Civil Division -II, PHE Dte. | 1147/NACD-II | 23/08/2024 | 60 | MERCURY ENGINEERING COMPANY. | 173.69 | 0 | 0 | 0
874 | NADIA | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Supply of documents for way leave permission from the Eastern Railways authority at 1 no. location on Ranaghat-Krishnagar & Ranaghat -Shantipur Railway track under Baruihuda Piped Water Supply Scheme for Krishnagar-I Block under Nadia Arsenic Civil Division-II, PHE Dte.[Period of Work : 01-03-2025 to 28-02-2026] | 1189/AE-I/NACD-II | 25/02/2025 | 60 | SUMAN CHAKRABORTY | 1.92 | 0 | 0 | 100
875 | NADIA | Eastern Mechanical | BARUIHUDA PIPED WATER SUPPLY SCHEME , SM/14423 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under BARUIHUDA W/S Scheme (Block : Krishnagar I) Dist.- Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 12) | 1611/EMD | 26/04/2023 | 555 | M/S DAS ENTERPRISE | 19.54 | 0 | 0 | 100
876 | NADIA | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14234 | New | Providing, Laying of Rising Main, Laying Distribution system and FHTC (Functional Household Tap Connection), Soil investigation for the work of construction of 100 cum OHR staging height 20 mtr. Construction of 100 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including Raft foundation), pipe connection and cost of pipes, specials and construction of Pump house, Boundary Wall, Service and allied Works at head work & 2nd site at Raynagar Zone-II under Jal Jeevan Mission for Raynagar Zone-II Water Supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E. Dte. | 1765/NAD-I | 24/07/2023 | 366 | MINTU CHAKRABORTY | 337.06 | 0 | 0 | 0
877 | NADIA | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14234 | New | Preparation of Detailed Project Report (DPR) for Raynagar Water Supply Scheme at Ranaghat-II Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(sl.no.06) | 3288 / NAD-I | 08/12/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 8.5 | 8.41 | 100 | 100
878 | NADIA | Eastern Mechanical | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14234 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for NEW Tube Well in connection to Accommodate FHTC at Pump House No.-I and II (Zone-I and II) under Raynagar ground water based water supply scheme under Block_ Ranaghat-II Dist. - Nadia under EMD, PHE Dte. (SM/14234) | 2690/EMD | 20/11/2024 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 46.24 | 0 | 0 | 0
879 | NADIA | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14234 | New | Material Requisition To Resource Division | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 8.49 | 0 | 0 | 0
880 | NADIA | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14234 | New | Duttaphulia-Aranghata Road from CH. 35.00 Km. to CH. 40.00 Km. Restoration estimate due to excavations for underground Water Supply pipeline by Nadia Arsenic Division-I, PHE Dte. | 222/PFMS | 12/09/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO.-II, PW (ROADS) DIRECTORATE. | 60.83 | 0 | 0 | 0
881 | NADIA | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14234 | New | Nokari- Aishmali Road from CH. 2.95 Km. to CH. 6.20 Km. Restoration work arising out of damage of black top for laying of pipe line for "Integrated surface water besed PWSS for Ranaghat -I and Ranaghat -II, Block by Nadia Arsenic Division-I, PHE Dte. | 221/PFMS | 12/09/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO.-II, PW (ROADS) DIRECTORATE. | 62.96 | 0 | 0 | 0
882 | NADIA | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14234 | New | Duttaphulia-Aranghata Road from CH. 40.00 Km. to CH. 44.766 Km. Restoration estimate due to the cause of excavations for underground Water Supply pipeline layout Proposal of PHE along the R/S of Quality Control sub-Division-I, under Nadia Highway Division-I, in the District Nadia during 2023-2024. |  | 18/12/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO.-II, PW (ROADS) DIRECTORATE. | 64.84 | 0 | 0 | 0
883 | NADIA | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14234 | New | "Providing Laying of Rising Main ,Laying distribution system and FHTC Soil investigation for the work of construction of 200 cum OHR staging heigjt 20 mtr , Construction of 200 cum capacity 20 mtr . staging hieght RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials and Construction of Pump house , Boundary Wall , Service and Allied Works at head work & 2nd site under Jal Jivan Mission for Raynagar Zone -II Water Supply Scheme within Ranaghat -I Block under Nadia Arsenic Division -I P.H.E.Dte." (Sl.no.02) | 2292/NAD-I | 27/09/2023 | 730 | TAPU SAHA | 386.21 | 0 | 0 | 70
884 | NADIA | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14234 | New | Balance work for revamping / upgradation of the hydraulic parameters at Kalipara,Gobindapur, Jhinukghata and Raynagar mouzas in reference to Gobindapur PWSS and Raynagar PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 04) | 127/NAD-I | 22/04/2025 | 60 | CHOWDHURY & CO. | 96.3 | 0 | 0 | 0
885 | NADIA | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14234 | New | Work for revamping / upgradation of the hydraulic parameters of distribution network in reference to Raynagar and Joypur W/S Scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 01) | 75/NAD-I | 16/04/2025 | 153 | S B CONSTRUCTION | 57.7 | 0 | 0 | 75
886 | NADIA | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14234 | New | Continuation work order for Hiring of 1 (One) no inspection vehicle (Diesel Luxury Taxi/Maxi Cab/Motor Cab) on Daily basis for monitoring of JJM works by the Junior Engineers at the office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. (Period- 01/02/2025 to 31/07/2025) | 17/AE-1/NAD-I | 31/01/2025 | 181 | M/S DIPAK ENTERPRISE | 0.86 | 0 | 0 | 0
887 | NADIA | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14234 | New | Balance work for revamping / upgradation of the hydraulic parameters at Gayesh, Daluigram & Jafar-nagar mouzas in reference to Halalpur-Krisnapur PWSS & Raynagar PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) | 154/NAD-I | 28/04/2025 | 60 | TAPU SAHA | 86.49 | 0 | 0 | 0
888 | NADIA | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14234 | New | Balance Work for revamping / upgradation of the hydraulic parameters of distribution network towards Badkulla in reference to Raynagar and Joypur water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 03) | 138/NAD-I | 23/04/2025 | 60 | BUDDHADEV MONDAL | 95.86 | 0 | 0 | 0
889 | NADIA | Nadia Arsenic Division I | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14234 | New | Balance Work to complete revamping/upgradation of the hydraulic parameters at distribution network at the part of Betna Mouza and Raynagar Mouza in reference to Raynagar PWSS under Nadia Arsenic Division-I, PHE Dte. As a part of Jal Jeevan Mission. (2nd Call) (Sl. NO. 02) | 1043/NAD-I | 25/09/2025 | 120 | M/S A.K. CONSTRUCTION | 61.71 | 0 | 0 | 0
890 | NADIA | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13791 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Badkulla Zone-I W/S Scheme in Hanskhali Block of Nadia District under Nadia Division, P.H.E. Dte. | 1053/RSD | 02/12/2021 | 30 | RADIANT | 3.29 | 2.94 | 100 | 100
891 | NADIA | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13791 | Augmentation | Material Requisition To Resource Division | 1872/ND | 26/04/2023 | 0 | Resource Division | 140.17 | 0 | 0 | 0
892 | NADIA | Eastern Mechanical | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13791 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BADKULLA (ZONE-I) W/S Scheme, Block- Hanskhali , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 01) | 405/EMD | 20/01/2023 | 30 | S.G. ENTERPRISE | 30.45 | 0 | 0 | 0
893 | NADIA | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13791 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
894 | NADIA | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13791 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 125 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Badkulla-I to accommodate FHTC within Hanskhali block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | 4281/ND | 05/08/2024 | 180 | GHOSH ENTERPRISE | 301.62 | 0 | 0 | 0
895 | NADIA | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13791 | Augmentation | Construction of Jhama Bats Road from Mamjoan road to headwork site of Badkulla-I water supply scheme under Ranaghat Sub Division under Nadia Division P.H. Engineering Dte. | 876(A)RSD | 20/08/2024 | 31 | M/S TARAK CHANDRA PAUL | 4.9 | 4.63 | 100 | 100
896 | NADIA | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13791 | Augmentation | Material Requisition To Resource Division | 7556/ND | 27/12/2024 | 0 | Resource Division | 4.29 | 0 | 0 | 0
897 | NADIA | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13791 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 700 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for Construction of OHR all complete for augmentation of Ground Water Based Water Supply Scheme for Badkulla Zone-I to accommodate FHTC in Hanskhali block under Ranaghat Sub-Division of Nadia District under Nadia Division P.H.Engineering Dte. | 3217/ND | 26/07/2023 | 706 | M/S TARAK CHANDRA PAUL | 676.67 | 223.38 | 33.01 | 82
898 | NADIA | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13791 | Augmentation | Supplying and laying of distribution system for Augmentation of Ground water based water supply scheme for Badkulla-I to accommodate FHTC under Ranaghat Sub-Division PHED. | 6502/ND | 03/10/2024 | 179 | M/S TARAK CHANDRA PAUL | 87.28 | 20.65 | 23.65 | 70
899 | NADIA | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13791 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Badkulla Zone-I piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | 1136/RSD | 11/09/2024 | 45 | M/S DREAM INFRASTRUCTURE | 1.9 | 0 | 0 | 100
900 | NADIA | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13791 | Augmentation | Construction of 130m Boundary Wall(2.5m panel) having 200X200mm R.C.C. Column footing (1.0X1.0m) with 125mm thick brick panel wall and 200x300 RCC beam at GL including M.S gate at Badkulla Zone-I PWSS at H/W site under Ranaghat Sub -Division in Nadia District under Nadia Division P.H.Engineering Dte. | 458/ND | 29/01/2025 | 90 | M/S 2S CONSTRUCTION | 11.35 | 0 | 0 | 75
901 | NADIA | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13791 | Augmentation | Construction of R.C.C Elevated Reservoir of 700 Cum. Capacity of staging height 20M at Head works site with Annular combined pile raft foundation for Badkulla Zone-II Water Supply Scheme under Nadia Division P.H.Engineering Dte. | 2523/ND | 29/05/2025 | 365 | SATYABRATA CHAKRABORTY | 164.42 | 0 | 0 | 0
902 | NADIA | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13791 | Augmentation | Supplying and laying of distribution system for Augmentation of Ground water based water supply scheme for Badkulla-I to accommodate FHTC under Ranaghat Sub-Division PHED. | 1664/ND | 08/04/2025 | 90 | M/S TARAK CHANDRA PAUL | 46.5 | 0 | 0 | 50
903 | NADIA | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13791 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
904 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BADKULLA ZONE-I (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15276 | Augmentation | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali BlocK,. under Ranaghat Sub-Division, PHE Dte. | 1271/ND | 23/03/2023 | 60 | AUXILIARY TUBEWELL DRILLERS | 48.99 | 13.36 | 40.89 | 40
905 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BADKULLA ZONE-I (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15276 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under BADKULLA ZONE-I ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte.(SM/15276) | 1125/EMD | 04/06/2025 | 90 | INDIA ENTERPRISE | 31.42 | 0 | 0 | 0
906 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANPUR (PHASE-II) IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15280 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BANPUR W/S Scheme, Block- Krishnaganj, ARABPUR W/S Scheme, Block-Karimpur, BHIMPUR W/S Scheme, Block-Krishnagar AND MONIPOTA W/S Scheme, Block- Krishnagar-I, Dist. - Nadia. | 5127/EMD | 04/09/2023 | 666 | C.M.S. ENGINEERING CONCERN. | 70.97 | 0 | 0 | 12
907 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANPUR (PHASE-II) IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15280 | Augmentation | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Santipur & Krishnaganj Block, under Ranaghat Sub-Division, PHE Dte. | 1273/ND | 23/03/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 47.83 | 13.69 | 100 | 95
908 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANPUR (PHASE-II) IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15280 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Banpur ground water based water supply scheme under Block_ Krishnaganj Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15280) | 228/EMD | 06/02/2025 | 30 | BINAPANI ENTERPRISE | 11.76 | 0 | 0 | 0
909 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Dakhin Bishnupur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14242 | New | Preparation of Detailed Project Report (DPR) for Dakshin Bishnupur Water Supply Scheme atRanaghat-I Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. (sl.02) | 47/ NAD-I | 09/12/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 5.28 | 5.15 | 100 | 100
910 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Dakhin Bishnupur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14242 | New | Material Requisition To Resource Division | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 13.77 | 0 | 0 | 0
911 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Dakhin Bishnupur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14242 | New | Material Requisition To Resource Division | 2106/NAD-I | 01/09/2023 | 0 | Resource Division | 72.02 | 0 | 0 | 0
912 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Dakhin Bishnupur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14242 | New | Supply of 1(one) no. Motor Cab (Luxury Taxi) on hire basis for official use of the Assistant Engineer-I, Nadia Arsenic Division - I, P.H.E. Dte. for the period from 15.07.2022 to 14.07.2023 i.e. for 1(one) year. | 172 / AE-I / NAD -I | 14/07/2022 | 365 | SUMAN CHAKRABORTY | 4.8 | 0 | 0 | 75
913 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Dakhin Bishnupur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14242 | New | Augmentation for providing FHTC (Functional Household Tap Connection) at Narasinghanagar, Chapatala & Beharia Mouzas in Beharia PWSS and different Mouzas under Dakshin Bishnupur PWSS under Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. | 2173/NAD-1 | 30/12/2024 | 60 | SUMAN CHAKRABORTY | 96.23 | 0 | 0 | 0
914 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Dakhin Bishnupur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14242 | New | Collection of Household Details at prescribed Format through Mobile App/Hard Copy including Geo- Reference as directed by EIC and submission of same to PHE Dte in soft copy at different piped water supply scheme under Nadia Arsenic Division-I, PHED. Name of PWSS:- 1) Haringhata (Zone-I & II) 2) Gobindapur 3) Haringhata Zone-V Part-IV 4) CHakdah Zone-XII 5) Arranghata 6) Haringhata Zone-I, II & III 7) Par Naimatpur (Phase-I) 8) Par Naimatpur (Phase-II) 9) Par Naimatpur (Phase-III) 10) Ramnagar 11) Chakdah Zone-VI & VI A & VII 13) Sabdalpur 14) Haringhata Zone-II 15) Chakdah Zone-X 17) Haringhata Zone-I & Zone- II 18) Chakdah Zone-II & IV VII & VIII & X 19) Halalpur-Krishnapur 20) Dakshin Bishnupur. | 380/AE-I/NAD-I | 31/08/2023 | 90 | TECH VISION | 4.89 | 4.89 | 100 | 100
915 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Dakhin Bishnupur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14242 | New | Continuation work order for Supply and installation of sign board related to JJM Matters at different piped water supply schemes under Nadia Arsenic Division-I, PHE Dte. | 07/AE-I/NAD-I | 04/01/2024 | 30 | BIBHAS PAL | 0.88 | 0.88 | 100 | 100
916 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Dakhin Bishnupur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14242 | New | Bill for Restoration work due to laying of pipe line on PMGSY road for HARADHAN GORAGACHA under WBSRDA Nadia division (Length 4.00 km.) under office of the Executive Engineer, Nadia Arsenic Division - I, PHE Dte. | 277/PFMS | 30/09/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 25.08 | 0 | 0 | 0
917 | NADIA | Eastern Mechanical | Detailed Project Report for Dakhin Bishnupur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14242 | New | New Service Connection for DAKSHIN BISHUNUPUR Water supply scheme | BP-198-24-25 | 17/12/2024 | 0 | W.B.S.E.D.C.L (AISHTAL CCC) | 4.9 | 0 | 0 | 0
918 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Dakhin Bishnupur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14242 | New | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE-100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle peice etc. all complete with Rising Main System incluidng specials & Valves & Laying of Distribution System including Specials, Valves & Pipe Supporting Structure, Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials, Construction of Boundary Wall [H/W Site (160.0 m length), 2nd T/W Site (45.0 m length)], Pump House for H/W Site (4.88 M X 3.60 M), 2nd T/W Site (3.60 M X 3.0 M), Land Development and allied works with Approach Road (105.0 m Length and 3.0 m Wide), Restoration Work for Bituminous Road and Soil Investigation for the work of Construction of RCC Elevated Reservoir of capacity 300 m3 Staging Height 20 Mtr. at Ground Water Based PWSS for Dakshin Bishnupur in Ranaghat-I Block of Nadia District under Nadia Arsenic Division-I, P.H.E Dte. | 1764/NAD-I | 24/07/2023 | 1096 | SUPRITI ENTERPRISE | 566.66 | 225.47 | 39.79 | 60
919 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Dakhin Bishnupur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14242 | New | Continuation Work Order 1(One) no. Motor Cab (Luxury Taxi) on hire basis for official use of the Assistant Engineer, Nadia Arsenic Division-I, P.H.E. Dte. for the period from 15.07.2023 to 14.01.2024 i.e, for 6 months. | 292/AE-I/NAD-I | 14/07/2023 | 184 | SUMAN CHAKRABORTY | 0.98 | 0 | 0 | 0
920 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Dakhin Bishnupur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14242 | New | Supply of vehicle on hire basis for official use of the Assistant Engineer-I, Nadia Arsenic Division-I, P.H.E. Dte. (Period from 15/01/2025 to 14/07/2025). | 05/AE-I/NAD-I | 14/01/2025 | 181 | SUMAN CHAKRABORTY | 0.86 | 0 | 0 | 0
921 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Dakhin Bishnupur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14242 | New | Repair of different type road different Water Supply Scheme under Shantipur block and Habibpur G.P. under Dakshin Bishnupur PWSS under Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | 124/NAD-I | 22/04/2025 | 30 | RAKESH ENTERPRISE | 20.44 | 0 | 0 | 0
922 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Dakhin Bishnupur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14242 | New | Balance Laying of pipeline for FHTC connection and restoration of road at different areas of Baganchara, Bagdebipur, Karanchapali, Kulia, Kutubpur Mouzas at Baganchara GP and Beleati & Aramdanga village under Dakshin Bishnupur PWSS Under Nadia Arsenic Division-I, PHE Dte. SL.NO. (Sl.01) | 2698/NAD-I | 13/03/2025 | 90 | KINGS AND CO | 129.57 | 0 | 0 | 0
923 | NADIA | Eastern Mechanical | Detailed Project Report for Dakhin Bishnupur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14242 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Dakshin Bishnupur ground water based water supply scheme under Block_ Ranaghat_I Dist. - Nadia under EMD, PHE Dte. (SM/14242) | 236/EMD | 06/02/2025 | 30 | SHIVAM ENTERPRISE | 21.04 | 0 | 0 | 0
924 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Dakhin Bishnupur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14242 | New | Continuation Work for Hiring of additional vehicle for supervision of JJM works including identification of land for JJM projects under Nadia Arsenic Division-I, P.H.E. Dte. W.e.f. 01/08/2025 to 31/01/2026. | 110/AE-I/NAD-I | 31/07/2025 | 184 | OM TRANSPORT | 0.86 | 0 | 0 | 0
925 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-IV within Krishnagar-II and Nabadwip (Part) Block. (Phase-E) , SM/08959 | Retrofitting | Making cabinet for keeping file and other official records at General Section & Divisional Accountant Room and Cash Section of Nadia Division Office building Kalyani nadia. | 360/Kly SD-I | 25/04/2022 | 30 | CHINMOY BISWAS | 4.99 | 0 | 0 | 100
926 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-IV within Krishnagar-II and Nabadwip (Part) Block. (Phase-E) , SM/08959 | Retrofitting | Laying of New pipe line in connection with FHTC at surface water based water supply scheme Nortern Sector Part-III, within Krishnagar -II Block(Phase-E) (Sl.No. 02) | 574/KSD | 13/06/2022 | 15 | GHOSH ENTERPRISE | 4.99 | 4.98 | 100 | 100
927 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-IV within Krishnagar-II and Nabadwip (Part) Block. (Phase-E) , SM/08959 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-IV within Krishnagar-II and Nabadwip (Part) Block. (Phase-E) | 699/PFMS | 28/03/2022 | 0 | GHOSH ENTERPRISE | 100 | 0 | 0 | 0
928 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-IV within Krishnagar-II and Nabadwip (Part) Block. (Phase-E) , SM/08959 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-IV within Krishnagar-II and Nabadwip (Part) Block. (Phase-E) | 724/PFMS | 30/03/2022 | 0 | GHOSH ENTERPRISE | 15.83 | 0 | 0 | 0
929 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-IV within Krishnagar-II and Nabadwip (Part) Block. (Phase-E) , SM/08959 | Retrofitting | Laying of New UPVC pipe line in connection with "Providing FHTC at P.H.E. Dte. surface water based water supply scheme Nortern Sector Part-III, Zone-IV within Krishnagar Block(Phase-E)" Sl.No .02 | 167/KSD | 23/02/2022 | 15 | GHOSH ENTERPRISE | 4.94 | 4.89 | 98.98 | 100
930 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-IV within Krishnagar-II and Nabadwip (Part) Block. (Phase-E) , SM/08959 | Retrofitting | Providing Functional Household Tap Connection(FHTC) at Surface Water Based Water Supply Scheme (Northern Sector) Part-III,Zone-IV within Krishnagar & Nabadwip(Part) Block(Phase-E) | 7206/ND | 15/12/2021 | 90 | GHOSH ENTERPRISE | 178.58 | 48.05 | 100 | 100
931 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-IV within Krishnagar-II and Nabadwip (Part) Block. (Phase-E) , SM/08959 | Retrofitting | Material Requisition To Resource Division | 807/ND | 18/02/2022 | 0 | Resource Division | 16.81 | 0 | 0 | 0
932 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-IV within Krishnagar-II and Nabadwip (Part) Block. (Phase-E) , SM/08959 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Sonda (Zone-I) W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Phase-I, Retrofitting). | 47/ND | 06/01/2021 | 90 | TARUN KUMAR BHATTACHARYA | 93.83 | 0 | 0 | 0
933 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-IV within Krishnagar-II and Nabadwip (Part) Block. (Phase-E) , SM/08959 | Retrofitting | Material Requisition To Resource Division | 296/ND | 15/01/2024 | 0 | Resource Division | 7.3 | 0 | 0 | 0
934 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-IV within Krishnagar-II and Nabadwip (Part) Block. (Phase-E) , SM/08959 | Retrofitting | Material Requisition To Resource Division | 297/ND | 15/01/2024 | 0 | Resource Division | 5.76 | 0 | 0 | 0
935 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-IV within Krishnagar-II and Nabadwip (Part) Block. (Phase-E) , SM/08959 | Retrofitting | Material Requisition To Resource Division | 298/ND | 15/01/2024 | 0 | Resource Division | 12.95 | 0 | 0 | 0
936 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-IV within Krishnagar-II and Nabadwip (Part) Block. (Phase-E) , SM/08959 | Retrofitting | Material Requisition To Resource Division | 299/ND | 15/01/2024 | 0 | Resource Division | 13.29 | 0 | 0 | 0
937 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-IV within Krishnagar-II and Nabadwip (Part) Block. (Phase-E) , SM/08959 | Retrofitting | Reimbursement of additional GST due to enhancement of rate from 12% to 18% vide notification no- 03/2022- Central Tax Rate dt- 13.07.2022 of Providing Functional Household Tap Connection (FHTC) at Surface water-based Water Supply Scheme (Northern Sector) part- III, Zone-IV within Krishnagar & Nabadwip (Part) Block, (Phase-E ) | 157/PFMS | 04/08/2024 | 0 | GHOSH ENTERPRISE | 2.55 | 0 | 0 | 0
938 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ramnagar, Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Ramnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08821 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ramnagar, Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Ramnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1408/NAD-I | 08/11/2021 | 60 | SANDIP BISWAS | 68.26 | 67.73 | 100 | 100
939 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dhantala, Part-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08829 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara/Jal Swapna for Dhantala Part-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 1610/NAD-I | 28/12/2021 | 90 | UMWELT ENGINEER PVT. LTD. | 164.47 | 163.67 | 100 | 100
940 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dhantala, Part-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08829 | Retrofitting | Revamping / upgardation of hydraulic parameter of distribution network and providing FHTC for Doula, Debipur Chandpur Biraberia Dhantala & Notungram and Hizuli (Part) Village and under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in connection with Dhantala PWSS & Hizuli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | 800/NAD-I | 18/08/2025 | 90 | BIDYUT KUMAR | 182.15 | 0 | 0 | 0
941 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Huda Chapra Water Supply Scheme In Hanskhali Block District Nadia. , SM/16369 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
942 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Betai(Zone-I & II) Water Supply Scheme in Tehatta-I Block, Dist.-Nadia. , SM/16331 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
943 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Chanderghat Water Supply Scheme in Tehatta-I Block, Dist.-Nadia. , SM/16332 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
944 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Khanjipur Water Supply Scheme in Tehatta-I Block, Dist.-Nadia. , SM/16333 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
945 | NADIA | Eastern Mechanical | Implementation of Affordable IoT at Betna W/S Scheme , SM/16354 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
946 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Gopinathpur Water Supply Scheme in Tehatta-II Block, Dist.-Nadia. , SM/16345 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
947 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Gobrapota & Naldaha Water Supply Scheme in Krishnagar-I Block, Dist.- Nadia. , SM/16829 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
948 | NADIA | Eastern Mechanical | Solarizations of WBSEDCL Energized Electrical installation including Net Metering at Different Pipe Water Supply Scheme at Krishnagar - I Block in Nadia District under Eastern Mechanical Division, PHE, Directorate. , SM/16848 | Solarisation | Solarisation of WBSEDCL Energised Electrical installation including net metering at different Pipe Water Supply Scheme at Krishnagar-I Block in Nadia District under E.M.D. P.H.E. Dte. | 6351/EMD | 16/10/2023 | 183 | BALAJI UDDYOG | 409.36 | 0 | 0 | 0
949 | NADIA | Eastern Mechanical | Solarizations of WBSEDCL Energized Electrical Installations including Net Metering at Different piped water supply schemes at Santipur & Nabadwip Blocks in Nadia District under Eastern Mechanical Division PHE Dte , SM/16851 | Solarisation | Solarisation of WBSEDCL Energised Electrical installation including net metering at different Pipe Water Supply Scheme at Santipur & Nabadwip Blocks in Nadia District under E.M.D. P.H.E. Dte. | 6348/EMD | 16/10/2023 | 728 | B.K. ENTERPRISE | 362.5 | 0 | 0 | 0
950 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Dakshin Jhitkipota Water Supply Scheme (Zone - I & II) in Krishnagar-I Block, Dist.- Nadia. , SM/16841 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
951 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Madhpur Water Supply Scheme in Karimpur-II Block of District Nadia , SM/16805 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
952 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Anandapur Water Supply Scheme in Karimpur-I Block, District-Nadia , SM/16790 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
953 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Ghoralia Water Supply Scheme (Zone - I & II) in Shantipur Block, Dist,- Nadia , SM/17268 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
954 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Gobindapur Water Supply Scheme (Z-I & II ) in Shantipur Block, Dist,- Nadia , SM/17270 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
955 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Nrisinghapur Water Supply Scheme in Shantipur Block, Dist,- Nadia , SM/17272 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
956 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Saguna Water Supply Scheme in Shantipur Block, Dist,- Nadia , SM/17273 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
957 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Bankar Dhopadi Water Supply Scheme in Nabadwip Block of District Nadia , SM/17275 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
958 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MADHUGARI PWSS (PHASE-III) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17205 | Augmentation | Material Requisition To Resource Division | 3788/ND | 24/08/2023 | 0 | Resource Division | 3.21 | 0 | 0 | 0
959 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MADHUGARI PWSS (PHASE-III) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17205 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MADHUGARI W/S Scheme, Block- Karimpur-1 , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 20) | 420/EMDdt.20.01.2023 | 17/03/2023 | 30 | KARUNAMOY ENGINEERING | 9.86 | 9.57 | 100 | 100
960 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MADHUGARI PWSS (PHASE-III) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17205 | Augmentation | Proposed Augmentation of Laying Rising Main System and Sinking of Replacement Tube Well at Head Work Site & 2nd Tube Well Site of Madhugari [Phase-III] Ground Based Piped Water Supply Scheme. | 1194/ND | 21/03/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 28.53 | 19.22 | 100 | 70
961 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MADHUGARI PWSS (PHASE-III) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17205 | Augmentation | Repairing Works (existing OHR, Pump House, Boundary wall etc.) of Madhugari Water Supply Scheme, Karimpur-I Block Under R.W.S. Nadia Sub-Division P.H.E. Dte. | 3431/ND | 19/06/2024 | 360 | M/S DURGA SECURITIES & SERVICES | 22.18 | 5.71 | 110.09 | 100
962 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Bagberia Water Supply Scheme in Chapra Block, Dist.-Nadia. , SM/18046 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
963 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Pansila Water Supply Scheme in Nabadwip Block of District Nadia , SM/17278 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
964 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Tarapur Water Supply Scheme in Ranagtat-I Block under District Nadia , SM/18205 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
965 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Dubli (Z-I & II) Water Supply Scheme in Ranagtat-II Block under District Nadia , SM/18210 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
966 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Naserkuli (Z-I & II) Water Supply Scheme in Ranagtat-II Block under District Nadia , SM/18218 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
967 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Tungi Water Supply Scheme in Krishnaganj Block, Dist.-Nadia. , SM/18069 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
968 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Maidanpur Water Supply Scheme in Chapra Block, Dist.-Nadia. , SM/18059 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
969 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09269 | Augmentation | Construction of Boundary wall with Grill Gate at Bahadurpur 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | 40/AE-II/NACD-II | 17/02/2022 | 30 | TAPAN SAHA | 4.45 | 4.41 | 99 | 100
970 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09269 | Augmentation | Supply and delivery of PCC Pole, MS material and allied works to WBSEDC Ltd. for Bahadurpur PWSS, W/O-879/EMSD-III, T.No.45/SD-III | 879/EMSD-III | 29/07/2022 | 30 | M/S G.P. ENTERPRISE | 0.75 | 0 | 0 | 0
971 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09269 | Augmentation | Continuation work order for Collection on House Hold Details at prescribed Format through Mobile App/Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for different PWSS under Nadia Arsenic Civil Division-II, PHE Dte | 216/AE-I/NACDII | 01/02/2022 | 5 | JOY GOPAL GUPTI | 4.91 | 4.91 | 100 | 100
972 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09269 | Augmentation | Supply & delivery of PCC pole MS material and allied electrical accessories to WBSEDCL Ltd ( Nazirpur CCC) for Bahadurpur PWSS PH.- II under EMSD III Dist. Nadia | 879/EMSD III | 29/07/2022 | 4 | M/S. G.P. ENTERPRISE | 0.75 | 0.75 | 100 | 100
973 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09269 | Augmentation | SUPPLY OF 11 KV AB CABLE & ALLIED ELECTRICAL ACCESSORIES TO WBSEDCL NAZIRPUR CCC FOR BAHADURPUR PWSS | 30 | 26/04/2022 | 0 | T. N. BANERJEE | 2.05 | 0 | 0 | 0
974 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09269 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged pipeline repair) at Krishnagar & Bahadurpur (Vill- Krishnagar, Chak Chilakhali) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 08/NACD-II | 04/01/2022 | 45 | MITRA CONSTRUCTION | 34.08 | 0 | 0 | 100
975 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09269 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged pipe line repair) at Krishnagar & Bahadurpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 948/NACD-II | 09/12/2021 | 45 | MITRA CONSTRUCTION | 45.4 | 45.38 | 100 | 100
976 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09269 | Augmentation | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Head Work Site under Bahadurpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 1011/NACD-II | 29/11/2022 | 60 | NAMDAR ALI | 12.93 | 12.73 | 98.43 | 90
977 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09269 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SAKDA (Block-Krishnaganj), BAHADURPUR(Block-Tehatt-I), BETBERIA(Block-Chapra) W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 01) | 1507/EMD | 18/04/2023 | 30 | SWAPAN KUMAR BHANJA | 14.69 | 4.88 | 100 | 100
978 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09269 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Bahadurpur Water Supply Scheme in Tehatta-I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 327/1/AE-I/NACD-II | 13/07/2023 | 7 | RISHAN ENGINEERING CONSULTANCY | 0.86 | 0.84 | 100 | 100
979 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09269 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Bahadurpur) | 1303/NACD-II | 29/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
980 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09269 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged pipe line repair) at Krishnagar & Bahadurpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 867/NACD-II | 08/11/2021 | 45 | MITRA CONSTRUCTION | 46.77 | 46.68 | 100 | 100
981 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09269 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Bahadurpur & Rajapur Water Supply Scheme of capacity 16 Cu.m/hr under in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | 424/NACD-II | 15/03/2024 | 420 | CHAKRABORTTI ENTERPRISE | 92.52 | 0 | 0 | 70
982 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09269 | Augmentation | Repair and Renovation work at Bahadurpur HW Site & 2nd pump house site with Reinforced Barbed Tape , Flooring ,Plaster ,Painting, Pathway , and other allied works Under Nadia Arsenic Division-II,P.H.E.Dte | 148/AE-II/NACD-II | 11/06/2024 | 420 | SREE GURU ENTERPRISE | 2.55 | 0 | 0 | 0
983 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09269 | Augmentation | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Fatepur, Bahadurpur and Gongra Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1657/NACD-II | 30/12/2024 | 360 | CHANDAN ROY | 149.25 | 0 | 0 | 20
984 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09269 | Augmentation | Laying of distribution system including providing FHTC at left out households for Bahadurpur, Khaspu, Dhopahat and Rajapur W/s Scheme and restoration of the damaged portion of roads in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte and Brittihuda W/S Scheme & Barnia W/S Scheme included. | 736/NACD-II | 18/06/2025 | 90 | JOY HIND TUBEWELLS | 186.42 | 0 | 0 | 40
985 | NADIA | Nadia Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10083 | Augmentation | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | 672/PFMS | 24/03/2022 | 0 | RADIANT | 3.09 | 0 | 0 | 0
986 | NADIA | Central Drilling | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10083 | Augmentation | Providing Drilling Crew and other allied works for construction of Tube Well (300mm x 200mm x250 Mtrs. Depth) by utilising Departmental machineries for Dhoradaha W/S Scheme (T/W-I) karimpur-II Block under Nadia District, CDD PHE Dte. | 136/CDD | 17/04/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 18.87 | 11.42 | 100 | 100
987 | NADIA | Nadia Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10083 | Augmentation | Material Requisition To Resource Division | 1905/ND | 27/04/2023 | 0 | Resource Division | 105.7 | 0 | 0 | 0
988 | NADIA | Nadia Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10083 | Augmentation | Material Requisition To Resource Division | 2296/ND | 29/05/2023 | 0 | Resource Division | 26.74 | 0 | 0 | 0
989 | NADIA | Nadia Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10083 | Augmentation | Construction Of Pump House (3.6x 3.0m) Including Sanitary Arrangemen and Consruction of Boundary wall at Tube well No-3 Site at Dhoradaha Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | 1629/ND | 07/03/2024 | 364 | BANERJEE ENTERPRISE | 12.74 | 1.31 | 10.26 | 70
990 | NADIA | Nadia Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10083 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed Augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Dhoradaha to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 382/ND | 27/01/2023 | 90 | SATYABRATA CHAKRABORTY | 457.46 | 93.98 | 52.8 | 65
991 | NADIA | Nadia Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10083 | Augmentation | Providing FHTC including Laying Distribution System in connection with J.J.M. Work under village Baruipota, Teinpur to cover up left out portion under Karimpur-II Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 134/ND | 08/01/2025 | 360 | M/S FREEDOM CONSTRUCTION | 57.04 | 0 | 0 | 70
992 | NADIA | Nadia Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10083 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House and allied works of ground basaedpiped water supply scheme for Dhoradaha water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 305/ND | 17/01/2025 | 270 | J.P. CONSTRUCTION & SUPPLIERS | 35.46 | 0 | 0 | 45
993 | NADIA | Nadia Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10083 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Dhoradaha Ground Based Water Supply Scheme under Karimpur-II Block under Nadia Division, P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhoradaha at Karimpur-II Block by Augmentation of Ground Water based PWSS for Dhoradaha Water Supply Schemes under Nadia Division, PHE Dte. | 416/ND | 27/01/2025 | 240 | BANERJEE CONSTRUCTION | 23.41 | 0 | 0 | 40
994 | NADIA | Nadia Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10083 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
995 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VII within Kaliganj Block (Phase-B) , SM/07429 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT PART-1 Z-VII | 459/DW | 30/03/2021 | 0 | M/S DIPAK ENTERPRISE | 64.73 | 0 | 0 | 0
996 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VII within Kaliganj Block (Phase-B) , SM/07429 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-VII, within Kaliganj Block (Phase-B, Retrofitting)" | 163/ND | 13/01/2021 | 90 | M/S DIPAK ENTERPRISE | 97.11 | 58.4 | 60.14 | 0
997 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VII within Kaliganj Block (Phase-B) , SM/07429 | Retrofitting | Laying of pipeline from Mira Bazar Baroari temple to traffic more under Mira - I G.P under Zone -VII of Surface Water Based Water Supply Scheme (Northern Sector), Part-I, within Kaliganj Block under Debagram Sub Division, P.H.Engineering Dte.(S.I. No -03.) | 585/DSD | 31/12/2021 | 30 | AVINABA ENGINEERING CONCERN | 0.64 | 0.6 | 92.73 | 0
998 | NADIA | Nadia Division | Providing Functional House Tap Connection from Itla Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08053 | Retrofitting | PROVIDING FHTC AT ITLA W/S SCHEME (PHASE-I RETROFITTING). |  | 13/03/2021 | 0 | M/S K.P. CONSTRUCTION | 23.03 | 0 | 0 | 0
999 | NADIA | Nadia Division | Providing Functional House Tap Connection from Itla Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08053 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN-METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC ALL COMPLETE AT ITLA W/S SCHEME UNDER NADIA DIVISION, PHE , DTE . PHASE-1, RETROFITTING PART-B. | 67/PPMS | 15/07/2021 | 0 | M/S K.P. CONSTRUCTION | 23.03 | 0 | 0 | 0
1000 | NADIA | Nadia Division | Providing Functional House Tap Connection from Itla Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08053 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Itla W/S scheme in Nadia District under Nadia Division P.H.E. Dte." (Phase-I, Retrofitting) | 2992/ND | 29/07/2021 | 90 | JOYGOPAL GUPTI | 82.18 | 97.91 | 119.14 | 0
1001 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VII within Nakashipara Block (Phase-B) , SM/08138 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VII within Nakashipara Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte.(SL.4) | 353/PFMS | 08/12/2021 | 0 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 83.87 | 0 | 0 | 0
1002 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VII within Nakashipara Block (Phase-B) , SM/08138 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VII within Nakashipara Block (Phase-B) | 488/PFMS | 03/02/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 0.41 | 0 | 0 | 0
1003 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VII within Nakashipara Block (Phase-B) , SM/08138 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VII within Nakashipara Block (Phase-B) | 493/PFMS | 03/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.47 | 0 | 0 | 0
1004 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VII within Nakashipara Block (Phase-B) , SM/08138 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VII within Nakashipara Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte.(SL.4) | 866/ND | 18/02/2021 | 90 | ALOKE ENTERPRISE | 97.09 | 0 | 0 | 0
1005 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VII within Nakashipara Block (Phase-B) , SM/08138 | Retrofitting | Material Requisition To Resource Division | 4303/ND | 29/09/2022 | 0 | Resource Division | 0.02 | 0 | 0 | 0
1006 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II, (Hapania), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07899 | Retrofitting | Laying work of Upvc pipeline at Hapania,Singa, Thansara and other Mouzas under Nagarukhra -II G.P. under Zone-II (Hapania) under Surface Based Haringhata & Chakdah (Part) W/S Scheme under Haringhata Block in the district of Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | 88 /AE-I/NAD-I | 28/04/2022 | 15 | TARUN KUMAR BHATTACHARYA | 4.84 | 0 | 0 | 100
1007 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II, (Hapania), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07899 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II, (Hapania), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 06) | 154/NAD-I | 25/01/2021 | 60 | SATYABRATA CHAKRABORTY | 95.8 | 191.26 | 100 | 100
1008 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II, (Hapania), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07899 | Retrofitting | Inter-Connection with M.S Pipeline to Distribution Pipeline of Surface Water Based Piped Water Supply Scheme for arsenic affected areas of Haringhata & Chakdah (Part) (Hapania Zone-II) under Haringhata Block under Office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. Tender No.-04/NAD-I/2021-2022. | 87/AE-I/NAD-I | 05/05/2021 | 30 | SATYABRATA CHAKRABORTY | 4.17 | 8.34 | 200 | 0
1009 | NADIA | Nadia Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07486 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME ATPART-C | 460/DW | 30/03/2021 | 0 | JOYGOPAL GUPTI | 18.33 | 0 | 0 | 0
1010 | NADIA | Nadia Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07486 | Retrofitting | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) |  | 12/04/2021 | 0 | SUBHASIS MAJUMDER | 16.31 | 0 | 0 | 0
1011 | NADIA | Nadia Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07486 | Retrofitting | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) |  | 12/04/2021 | 0 | BIDYUT KUMAR | 14.57 | 0 | 0 | 0
1012 | NADIA | Nadia Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07486 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN- METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC. ALL COMPLETE AT ANANDAPUR W/S SCHEME PHASE-1,PART-A RETROFITTING, UNDER NADIA DIVISION, PHE , DTE. | 76/PPMS | 15/07/2021 | 0 | BIDYUT KUMAR | 14.57 | 0 | 0 | 0
1013 | NADIA | Nadia Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07486 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN- METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC. ALL COMPLETE AT ANANDAPUR W/S SCHEME PHASE-1 UNDER NADIA DIVISION, PHE , DTE. | 83/PPMS | 15/07/2021 | 0 | SUBHASIS MAJUMDER | 16.31 | 0 | 0 | 0
1014 | NADIA | Nadia Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07486 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Anandapur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-C) | 400/ND | 22/01/2021 | 45 | JOYGOPAL GUPTI | 32.34 | 2.04 | 6.31 | 0
1015 | NADIA | Nadia Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07486 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Anandapur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-B) | 399/ND | 22/01/2021 | 45 | SUBHASIS MAJUMDER | 32.36 | 2.6 | 100 | 100
1016 | NADIA | Nadia Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07486 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Anandapur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-A) | 398/ND | 22/01/2021 | 45 | BIDYUT KUMAR | 32.35 | 4.03 | 100 | 0
1017 | NADIA | Nadia Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07486 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Topla W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-A) | 404/ND | 22/01/2021 | 45 | NILAY KUMAR BHATTACHARYA | 32.33 | 19.62 | 100 | 0
1018 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Bansbaria water supply scheme under Krishnagar-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07936 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Bansberia (Vill-Bansberia) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1188/NACD-II | 13/11/2020 | 25 | S.B. CONSTRUCTION | 4.98 | 0 | 0 | 0
1019 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Bahadurpur water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07941 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Bahadurpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1058/NACD-II | 25/09/2020 | 15 | AMARENDRA NATH PANDAY | 4.99 | 0 | 0 | 0
1020 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Tengra water supply scheme under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07962 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Tengra (Vill-Tengra) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1196/NACD-II | 13/11/2020 | 25 | SANJOY BAKSHI | 4.99 | 0 | 0 | 0
1021 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-VII within Kaliganj Block (Phase-A). , SM/07003 | Retrofitting | PROVIDING HOUSE CONNECTION INCLUDING SUPPLY OF 15MM DIA GI/PVC PIPE OF AVERAGE LENGTH OF 10MM DIA CUM GUN-METAL FERRULE, SADDLE PIECE 15MM AT KALIGANJ BLOCK | 382/DW | 04/02/2021 | 0 | PROJECT INDIA | 78.41 | 0 | 0 | 0
1022 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-VII within Kaliganj Block (Phase-A). , SM/07003 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme(northern sector),Part-I,Zone-VII within Kaliganj block(Phase-A) in Nadia District under Nadia Division P.H.Engineering Dte. | 3592/ND | 08/12/2020 | 90 | PROJECT INDIA | 96.53 | 36.25 | 37.55 | 0
1023 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-VII within Kaliganj Block (Phase-A). , SM/07003 | Retrofitting | Hiring Diesel Luxury Car on daily basis (for 12 months from 01.02.2021 to 31.01.2022) for the office use of the Assistant Engineer, Kalyani Sub Division II, P.H.E. Dte | 198 / KLYSD -II | 29/01/2021 | 365 | SUMAN CHAKRABORTY | 4.8 | 2.56 | 100 | 0
1024 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Chanderghat water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07963 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Chanderghat (Vill-Chanderghat) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1177/NACD-II | 13/11/2020 | 25 | CHANDAN ROY | 4.98 | 0 | 0 | 0
1025 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone II , SM/09089 | Retrofitting | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone II | 618/PFMS | 14/03/2022 | 0 | UMWELT ENGINEERS PVT LTD | 2.84 | 0 | 0 | 0
1026 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone II , SM/09089 | Retrofitting | Material Requisition To Resource Division | 94/ND | 06/01/2022 | 0 | Resource Division | 0.66 | 0 | 0 | 0
1027 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone II , SM/09089 | Retrofitting | Material Requisition To Resource Division | 819/ND | 18/02/2022 | 0 | Resource Division | 6.28 | 0 | 0 | 0
1028 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone II , SM/09089 | Retrofitting | Material Requisition To Resource Division | 1260/ND | 16/03/2022 | 0 | Resource Division | 0.66 | 0 | 0 | 0
1029 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone II , SM/09089 | Retrofitting | Providing FHTC Connection and Laying of different dia UPVC pipeline(Dedicated line ) near 2nd pump house towards Ghoralia More along with other repearing works at GHORALIA ZONE -II Water Supply Scheme under Tehatta Sub-Division under NADIA DIVISION , P.H.E. Dte. | 7261/ND | 13/12/2024 | 60 | M/S DIPAK ENTERPRISE | 18.28 | 0 | 0 | 0
1030 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone II , SM/09089 | Retrofitting | Providing FHTC (Functional Household Tap Connection) by Augmentation under Jal Swapna for Ghoralia Zone-II Water Supply Scheme in Santipur Block of Nadia District under Nadia Division, PHE Dte. | 337/ND | 25/01/2022 | 90 | S.S. ENTERPRISE | 108.63 | 88.37 | 100 | 98
1031 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone II , SM/09089 | Retrofitting | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | 7571/ND | 27/12/2024 | 31 | IMAGIN | 34.21 | 0 | 0 | 0
1032 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone II , SM/09089 | Retrofitting | Repair and renovation works of R.C.C. Elevated Reservoir capacity of 136 CUM, existing Pump Houses and construction of shed for CWR at Existing Headwork site along with other allied Works at Ghoralia Zone II water supply scheme under Tehatta Subdivision of Nadia Division. | 763/ND | 19/02/2025 | 180 | M/S ARATI ENTERPRISE | 27.7 | 0 | 0 | 60
1033 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ramnagar, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Ramnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08820 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ramnagar, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Ramnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1407/NAD-I | 08/11/2021 | 60 | M/S PRADIP KUMAR PAL | 69.04 | 66.46 | 100 | 100
1034 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ramnagar, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Ramnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08820 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Augmentation of RAMNAGAR Water Supply Scheme in Hanskhali Block under Nadia Arsenic Division-1, PHE Dte. (Sl. NO. 01) | 318/AE-II/NAD-I | 14/07/2023 | 7 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 4.4 | 3.62 | 100 | 100
1035 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ramnagar, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Ramnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08820 | Retrofitting | Material Requisition To Resource Division | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 1.73 | 0 | 0 | 0
1036 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ramnagar, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Ramnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08820 | Retrofitting | Construction and installation of MANIFOLD and allied works at OHR site under Ramnagar Ground Based Water Supply Scheme under Hnaskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Ramnagar (Part-I) under JJM (Sl.no.08) | 1773/NAD-I | 26/07/2023 | 15 | SUMAN CHAKRABORTY | 13.01 | 12.94 | 100 | 90
1037 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ukhilnara Zone-I, Part-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Ukhilnara Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08827 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ukhilnara, Zone-I, Part-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Ukhilnara, Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1405/NAD-I | 08/11/2021 | 60 | M/S UMA CONSTRUCTION | 63.86 | 49.51 | 77.52 | 100
1038 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ukhilnara Zone-I, Part-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Ukhilnara Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08827 | Retrofitting | Repairing, painting of Boundary wall, Pump House and other llied work at Ukhilnara Zone-II (2nd T/W Site) Water supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E. Dte. | 291/AE-I/NAD-I | 12/07/2023 | 7 | GANGULY ENTERPRISE | 4.7 | 4.66 | 100 | 100
1039 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ukhilnara Zone-I, Part-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Ukhilnara Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08827 | Retrofitting | Material Requisition To Resource Division | 139/NAD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0 | 0
1040 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-I (Palagachha) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08857 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Chakdah Zone-I (Palagachha) at Chakdah Block by retrofitting of Ground Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1540/NAD-I | 06/12/2021 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 164.35 | 139.41 | 100 | 100
1041 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-I (Palagachha) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08857 | Retrofitting | Shifting and repairing of clear water rising main and distribution pipeline from Palagacha more to Singher Bagan more along NH-34 of Surface based ChakdahW/S Scheme under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (sl.05) | 500 / NAD-I | 10/03/2023 | 21 | BUDDHADEV MONDAL | 32.9 | 32.88 | 100 | 100
1042 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XII, (Madanpur), at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE , SM/08832 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-XII, (Madanpur) at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 11/NAD-I | 05/01/2022 | 90 | UMWELT ENGINEER PVT. LTD. | 378.71 | 378.54 | 100 | 100
1043 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, (Subarnapur), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divi , SM/08836 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-X (Subarnapur) Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 1614/NAD-I | 28/12/2021 | 90 | GHOSH BROTHERS | 356.08 | 152.92 | 100 | 90
1044 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, (Subarnapur), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divi , SM/08836 | Retrofitting | Retrofitting work for Zone-IX (Chandmari) at Kanchrapara G.P. and Zone-X (Subarnapur) under Jal Jeevan Mission (JJM) by retrofitting of Surface Water Based PWSS for Haringhata & Chakdah (Part) for Zone-X (Subarnapur) Part-II under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (SL.03) | 501 / NAD-I | 10/03/2023 | 21 | BUDDHADEV MONDAL | 30.99 | 30.99 | 100 | 100
1045 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, (Subarnapur), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divi , SM/08836 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission for Madanpur at Madanpur-I G.P by retrofitting of Surface Water based Piped Water Supply Scheme for Haringhata- Chakdah(Part) in connection with retrofitting work ofZone-X (Subarnapur),Part-II under Nadia Arsenic Division-I, PHE Dte. (sl.13) | 1158 / NAD-I | 28/04/2023 | 21 | CHOWDHURY & CO. | 92.76 | 58.29 | 100 | 100
1046 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, (Subarnapur), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divi , SM/08836 | Retrofitting | Jackpushing of Clear Water Rising Main at Majher Char Crossing at WBHDCL Road and other allied works under Jal Jeevan Mission (JJM) for Zone-X, (Subarnapur) at Subarnapur Mouza at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-X, (Subarnapur) Part-II under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 03) | 1702/NAD-I | 13/07/2023 | 21 | M/S DIPAK ENTERPRISE | 89.84 | 61.1 | 100 | 100
1047 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, (Subarnapur), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divi , SM/08836 | Retrofitting | Jackpushing of Distribution Pipeline at Buddhapark Crossing at WBHDCL Road and other allied works under Jal Jeevan Mission (JJM) for Zone-X, (Subarnapur) at Subarnapur Mouza at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-X, (Subarnapur) Part-II under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 02) | 1701/NAD-I | 13/07/2023 | 25 | M/S DIPAK ENTERPRISE | 93.64 | 93.64 | 100 | 100
1048 | NADIA | Nadia Division | Providing Functional House Tap Connection from MuktadahaZone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/09044 | Retrofitting | Material Requisition To Resource Division | 1024/ND | 03/03/2022 | 0 | Resource Division | 0.7 | 0 | 0 | 0
1049 | NADIA | Nadia Division | Providing Functional House Tap Connection from MuktadahaZone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/09044 | Retrofitting | URGENT RESTORATION OF CARRIAGE WAY & FLANF OF BADKULLA- ARANGHATA ROAD AT CH. 5.7 KM. " ARISING DUE TO LAYING OF PHED W/S SCHEME PIPE LINE, HIGHWAY DIVISION -II, PW ROADS. | 242/1/PFMS | 18/08/2023 | 0 | OTHERS | 0.98 | 0 | 0 | 0
1050 | NADIA | Nadia Division | Providing Functional House Tap Connection from MuktadahaZone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/09044 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 4.72 | 100 | 81
1051 | NADIA | Nadia Division | Providing Functional House Tap Connection from MuktadahaZone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/09044 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Muktadaha Zone-II W/S scheme in Nadia District under Nadia Division P.H.E. Dte | 5688/ND | 03/11/2021 | 60 | CHOWDHURY & CO. | 39.38 | 30.52 | 77.49 | 100
1052 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Digri water supply scheme underKrishnagar-I Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08303 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Digri (Vill-Digri) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1192/NACD-II | 13/11/2020 | 25 | M/S RAJESH CONSTRUCTION | 4.99 | 0 | 0 | 0
1053 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme underTehatta-II Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08304 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Barnia (Vill- Barnia) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1189/NACD-II | 13/11/2020 | 25 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 4.99 | 0 | 0 | 0
1054 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kamalpur Zone I Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/08672 | Retrofitting | Providing Functional House Tap Connection from Kamalpur Zone I Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | 606/PFMS | 11/03/2022 | 0 | OTHERS | 7.21 | 0 | 0 | 0
1055 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kamalpur Zone I Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/08672 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Kamalpur Z-I Water Supply scheme Ranaghat-II block in Nadia District under Nadia Division P.H.E. Dte.(Phase-A) | 5176/ND | 20/09/2021 | 90 | CHANDAN ROY | 88.23 | 87.01 | 98.61 | 0
1056 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kamalpur Zone I Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/08672 | Retrofitting | Material Requisition To Resource Division | 798/ND | 18/02/2022 | 0 | Resource Division | 7.77 | 0 | 0 | 0
1057 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Balibanga water supply scheme under Chapra Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08255 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Baliadanga W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1060/NACD-II | 25/09/2020 | 15 | SHYAMAL KANTI GHOSH | 4.99 | 0 | 0 | 0
1058 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. , SM/09453 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. | 729/PFMS | 30/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.23 | 0 | 0 | 0
1059 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. , SM/09453 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No.I & II under Anandapur W/S Scheme, Block-Karimpur- 1, Dist. - Nadia. NIET No.- 18 of EE/EMD of 2022-23 (Sl. No.- 01) | 6182/EMD | 14/11/2022 | 30 | H.K. DAS & CO. | 14.64 | 13.81 | 94.32 | 0
1060 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. , SM/09453 | Augmentation | Material Requisition To Resource Division | 1255/ND | 16/03/2022 | 0 | Resource Division | 1.1 | 0 | 0 | 0
1061 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. , SM/09453 | Augmentation | Material Requisition To Resource Division | 453/ND | 31/01/2022 | 0 | Resource Division | 0.6 | 0 | 0 | 0
1062 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. , SM/09453 | Augmentation | Material Requisition To Resource Division | 4312/ND | 29/09/2022 | 0 | Resource Division | 10.92 | 0 | 0 | 0
1063 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. , SM/09453 | Augmentation | LAYING OF PIPELINE UNDER PALASHIPARA PWSS FROM PALASHIPARA BAZAR TO BURNIA BUS STAND. | 241/1/PFMS | 18/08/2023 | 0 | OTHERS | 49.99 | 0 | 0 | 0
1064 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. , SM/09453 | Augmentation | LAYING OF DISTRIBUTION SYSTEM INCLUDING SPECIALS, VALVES & PIPE CARRYING STRUCTURE ALL COMPLETE, PROPOSED AUGMENTATION OF RISING MAIN SYSTEM AND PROVIDING FHTC INCLUDING SUPPLYING, LAYING, FITTING, FIXING OF 15MM NB PVC (SCHEDULE 80)/20MM OD HDPE (PE100, PN16) PIPE WITH ALL NECESSARY SPECIALS, SADDLE PIECE ETC. ALL COMPLETE FOR AUGMENTATION OF GROUND BASED WATER SUPPLY SCHEME AT ANANDAPUR TO ACCOMMODATE FHTC UNDER TEHATTA SUB-DIVN UNDER NADIA DIVN, PHE DTE | 896/ND | 23/02/2022 | 90 | IJABUL SK. | 205.15 | 182.17 | 88.8 | 95
1065 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. , SM/09453 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 57 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Anandapur to accommodate FHTC within Karimpur-I block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | 4229/ND | 02/08/2024 | 180 | B.M. ENGINEERING & CONSTRUCTION | 191.51 | 0 | 0 | 0
1066 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. , SM/09453 | Augmentation | Laying of additional pipeline for Fazilnagar Mouza and Anandapur Mouza under Fazilnagar PWSS and Anandapur PWSS under Tehatta Sub-Division under Nadia Division P.H.Engineering Dte. | 4904/ND | 10/09/2024 | 90 | PATHIK PABAN NANDI | 37.63 | 0 | 0 | 0
1067 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. , SM/09453 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- II) at Anandapur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 7036/ND | 29/11/2024 | 420 | SAFTI PRIVATE LIMITED | 29.2 | 0 | 0 | 65
1068 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. , SM/09453 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground basaedpiped water supply scheme for Anandapur water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 7124/ND | 09/12/2024 | 90 | M/S A.K.CONSTRUCTION | 31.58 | 0 | 0 | 0
1069 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. , SM/09453 | Augmentation | Laying of additional pipe lines and allied works to increase the functionality in Brojonathpur, Gandhina villages under Karimpur-I Block under Nadia Division, PHE Dte. | 4685/4533/P-3/ND | 09/10/2025 | 90 | JOY HIND TUBEWELL'S | 46.3 | 0 | 0 | 0
1070 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10416 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | 12/PFMS | 11/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.18 | 0 | 0 | 0
1071 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10416 | Augmentation | Material Requisition To Resource Division | 157/ND | 06/01/2023 | 0 | Resource Division | 27.89 | 0 | 0 | 0
1072 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10416 | Augmentation | Material Requisition To Resource Division | 1886/ND | 26/04/2023 | 0 | Resource Division | 10.67 | 0 | 0 | 0
1073 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10416 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
1074 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10416 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Nathna W/S Scheme (Z-II,T/W-I & II) , Tehatta-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 902/CDD | 18/07/2023 | 120 | SANKAR PRASAD DUTTA & CO. | 37.16 | 30.75 | 100 | 50
1075 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10416 | Augmentation | Collection of Household data through mobile app for FHTC Connection (Phase-I), under Nadia Division, P.H.E. Dte. | 207/KLYSD-I | 09/02/2024 | 182 | HORIZEN | 4.85 | 4.85 | 100 | 100
1076 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10416 | Augmentation | Quotation for new service connection at Pump House No-II under Natna w/s Scheme, Dist-Nadia. | BP-378-23-24 | 22/03/2024 | 0 | W.B.S.E.D.C.L (TEHATTA CCC) | 5.88 | 0 | 0 | 0
1077 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10416 | Augmentation | Quotation for new service connection at Pump House No-I under Natna w/s scheme, Dist-Nadia. | BP-377-23-24 | 22/03/2024 | 0 | W.B.S.E.D.C.L (TEHATTA CCC) | 6.29 | 0 | 0 | 0
1078 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10416 | Augmentation | Supplying, Laying, Fitting & Fixing of Distribution System including all type of specials, valves,pipes all complete, Augmentation of Rising Main, Providing FHTC including Supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction of 4.88 mtr. x 3.66 mtr. Size pump house including Sanitary Arrangement at H/W Site and 2nd Tube Well Site, Construction of OHR of 300 Cum capacity, Soil investigation for construction of OHR of 300 Cum capacity, Construction Of Boundary Wall At HW Site, Construction Of Boundary Wall At 2nd Tube Well Site And Construction Of Service Road At 2nd Tube Well Site for Natna Zone-II to accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | 3538/ND | 11/08/2023 | 748 | JOY HIND TUBEWELL'S, BELEDANGA GHOSHPARA 2ND LANE, P.O. KRISHNAGAR, DIST. NADIA. PIN-741101. | 560.77 | 216.06 | 38.53 | 55
1079 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10416 | Augmentation | Laying additional pipe line for distribution system and rising main for Nathna Zone-II PWSS under augmentation of Nathna Zone-II PWSS (Phase-II) under Nadia Division PHE Dte. | 7051/ND | 02/12/2024 | 270 | JOY HIND TUBEWELL'S | 100.01 | 0 | 0 | 75
1080 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10416 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 53 m3/hr at Nathna Zone-II Water Supply Scheme within Tehatta-I Block under Nadia Division, P.H.E. Dte. | 7106/ND | 06/12/2024 | 360 | JOY HIND TUBEWELL'S | 185.75 | 0 | 0 | 0
1081 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10416 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Nathna ground water based water supply scheme under Block_ Tehatta-I Dist. - Nadia under EMD, PHE Dte. SM/10416 | 1126/EMD | 04/06/2025 | 90 | DITHI ENTERPRISE | 16.89 | 0 | 0 | 0
1082 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10416 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MADHPUR W/S Scheme, Block- Karimpur-I AND NATNA W/S Scheme, Block- Tehatta-I, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 03) | 497/EMD | 24/01/2023 | 730 | KARTICK BAL | 56.7 | 24.72 | 58.22 | 30
1083 | NADIA | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10419 | Augmentation | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. | 31/PFMS | 20/05/2022 | 0 | RADIANT | 2.99 | 0 | 0 | 0
1084 | NADIA | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10419 | Augmentation | Material Requisition To Resource Division | 150/ND | 06/01/2023 | 0 | Resource Division | 2.34 | 0 | 0 | 0
1085 | NADIA | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10419 | Augmentation | Material Requisition To Resource Division | 4316/ND | 29/09/2022 | 0 | Resource Division | 21.75 | 0 | 0 | 0
1086 | NADIA | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10419 | Augmentation | Material Requisition To Resource Division | 1900/ND | 27/04/2023 | 0 | Resource Division | 14.22 | 0 | 0 | 0
1087 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10419 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I , II Zone-VII under Karimpur-Jalangi ground water based water supply scheme under Block_ Karimpur-I Dist. - North 24PGS under EMD, PHE Dte. | 872/EMD | 15/03/2024 | 261 | TARUN KUMAR BHATTACHARYA | 25.34 | 0 | 0 | 100
1088 | NADIA | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10419 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Karimpur Jalangi Zone-VII water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 7058/ND | 04/12/2024 | 360 | TULIP ENGINEER'S CO-OP SOCIETY LTD | 31.24 | 0 | 0 | 40
1089 | NADIA | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10419 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- II) at Karimpur Jalangi Zone-VIPart-A & B W/S to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 2035/ND | 29/04/2025 | 90 | BALAJI UDDYOG | 111.41 | 0 | 0 | 0
1090 | NADIA | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10419 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-VII to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 3403/ND | 01/08/2022 | 1088 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 326.43 | 278.26 | 87.18 | 98
1091 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10081 | Augmentation | New Service connection for Madhpur w/s scheme p.h No 2 | 2865/EMD | 21/07/2022 | 30 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.34 | 0 | 0 | 0
1092 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10081 | Augmentation | New Service connection for Madhpur w/s scheme p.h No 1 | 2866/EMD | 21/07/2022 | 30 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.01 | 0 | 0 | 0
1093 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10081 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | 640/PFMS | 16/03/2022 | 0 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 2.95 | 0 | 0 | 0
1094 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10081 | Augmentation | New Service connection bill for Madhpur W/s scheme | BP-2022-23-25 | 02/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.01 | 0 | 0 | 0
1095 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10081 | Augmentation | New Service connection bill for Madhupur W/s scheme | BP-2022-23-24 | 02/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.34 | 0 | 0 | 0
1096 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10081 | Augmentation | Material Requisition To Resource Division | 4319/ND | 29/09/2022 | 0 | Resource Division | 4.87 | 0 | 0 | 0
1097 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10081 | Augmentation | Supplementary quotation for argumentation of DTR from 25KVA to 63KVA at Madhpur Ref. ID 860261053 | 137/PFMS/EMD | 23/02/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.89 | 0 | 0 | 0
1098 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10081 | Augmentation | New Service Connection for madhpur Aplication No.3004022790 | 138/PFMS/EMD | 23/02/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.01 | 0 | 0 | 0
1099 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10081 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Madhpur Ground Based Water Supply Scheme under Karimpur-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Madhpur at Karimpur-II Block by Augmentation of Ground Water based PWSS for Madhpur Water Supply Schemes under Nadia Division, PHE Dte. | 7368/ND | 18/12/2024 | 60 | K.K. MARKETING | 17.61 | 0 | 0 | 0
1100 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10081 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 31.44 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Madhpur PWSS under Nadia Division PHE Dte. | 1456/ND | 31/03/2023 | 90 | APURBA MANDAL | 58.68 | 0 | 0 | 21
1101 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10081 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Madhpur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 3383/ND | 29/07/2022 | 90 | SUBHASIS MAJUMDER | 69.32 | 46.57 | 67.18 | 85
1102 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10081 | Augmentation | Laying of additional pipeline for Madhpur PWSS".under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 4078/ND | 26/07/2024 | 360 | SUBHASIS MAJUMDER | 16.52 | 6.34 | 38.41 | 40
1103 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10081 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House and allied works of ground basaed piped water supply scheme for Madhpur water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 7266/ND | 13/12/2024 | 360 | SUMAN CHAKRABORTY | 29.68 | 0 | 0 | 0
1104 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10081 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MADHPUR W/S Scheme, Block- Karimpur-I AND NATNA W/S Scheme, Block- Tehatta-I, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 03) | 497/EMD | 24/01/2023 | 730 | KARTICK BAL | 56.7 | 10 | 89.12 | 30
1105 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. , SM/10527 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. | 22/PFMS | 20/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.18 | 0 | 0 | 0
1106 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. , SM/10527 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 93 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Pansila PWSS under Nadia Division PHE Dte. | 2998/ND | 13/07/2023 | 90 | TARUN KUMAR BHATTACHARYA | 90.1 | 0 | 0 | 0
1107 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. , SM/10527 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under PANSILA W/S Scheme, Block-Nabadwip , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 08) | 501/EMDdt.24.01.2023 | 16/03/2023 | 30 | ASHOKE ADHIKARY | 15.59 | 23.83 | 100 | 100
1108 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. , SM/10527 | Augmentation | Material Requisition To Resource Division | 4088/ND | 21/09/2022 | 0 | Resource Division | 84.05 | 0 | 0 | 0
1109 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. , SM/10527 | Augmentation | Material Requisition To Resource Division | 4321/ND | 29/09/2022 | 0 | Resource Division | 17.77 | 0 | 0 | 0
1110 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. , SM/10527 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Pansila to accommodate FHTC within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 3418/ND | 02/08/2022 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 452.17 | 390.57 | 100 | 95
1111 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. , SM/10527 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 450 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Pansila Water Supply Scheme within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 5122/ND | 17/11/2023 | 90 | INDUSTRIAL CONSTRUCTION | 29.08 | 21.22 | 100 | 70
1112 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. , SM/10527 | Augmentation | Reimbursement of additional GST due to enhancement of rate from 12% to 18% vide notification no 03/2022-Central Tax Rate dt 13/7/2022 of Laying and Distribution system including specials,valves and pipe carrying structure all complete,proposed augmentation of rising main system and providing FHTC including supplying ,laying,fitting,fixing of 15mm NB PVC(Schedule 80)/20mm OD HDPE (PE 100,PN 16) pipe with all necessary specials,saddle piece etc all complete for augmentation of ground based water supply scheme at Pansila to accomodate FHTC within Nabadwip block under Krishnagar Sub-Division under Nadia Divn,PHE Dte | 151/PFMS | 31/07/2024 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 18.57 | 0 | 0 | 0
1113 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. , SM/10527 | Augmentation | Laying of UPVC Pipeline and providing FHTC including supplying, laying, fitting, fixing with all necessary specials, saddle piece etc. all complete for Ground Based piped water supply scheme in Bankar Dhopadi village to accommodate FHTC within Nabadwip block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | 2975/ND | 25/06/2025 | 120 | SARKAR CONSTRUCTION | 91.91 | 0 | 0 | 0
1114 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. , SM/10527 | Augmentation | Construction and installation of Manifold at OHR site and allied works in connection to the Augmentation of Pansila Water Supply Scheme under Nabadwip Block under Nadia Division, P.H.E Dte. | 5355/6043/ND | 03/12/2025 | 60 | KESHOB ENTERPRISE | 28.71 | 0 | 0 | 0
1115 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED CHANDERGHAT PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09255 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Chanderghat W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 919/NACD-II | 26/11/2021 | 45 | SINGHA ROY & CO. | 11.55 | 11.54 | 99.86 | 100
1116 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED CHANDERGHAT PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09255 | Augmentation | Construction of Boundary wall with Grill Gate at Chanderghat Water Supply Scheme at Head Work site under Nadia Arsenic Civil Division-II PHE Dte | 100/NACD-II | 10/02/2022 | 45 | M/S FREEDOM CONSTRUCTION | 11.26 | 11.17 | 99.25 | 100
1117 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED CHANDERGHAT PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09255 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at MobarakpurW/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | 50/NACD-II | 19/01/2022 | 90 | PATHIK PABAN NANDI | 127.95 | 0 | 0 | 100
1118 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED CHANDERGHAT PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09255 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Chenderghat W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 835/NACD-II | 28/10/2021 | 45 | SINGHA ROY & CO. | 23.48 | 23.43 | 100 | 100
1119 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED CHANDERGHAT PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09255 | Augmentation | Restoration of damaged distribution pipe line laying, broken due to construction of Drain by the local panchayat at Chanderghat (Purba para) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 521/NACD-II | 05/08/2022 | 30 | CHANDAN ROY | 11.7 | 11.16 | 100 | 100
1120 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED CHANDERGHAT PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09255 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) under Chanderghat Mouza at Chanderghat Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 231/NACD-II | 21/02/2024 | 45 | SAFTI PRIVATE LIMITED | 21.65 | 4.57 | 21.11 | 60
1121 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED CHANDERGHAT PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09255 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Chanderhat Water Supply Scheme of capacity 53 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | 178/NACD-II | 08/02/2024 | 60 | TARUN KUMAR BHATTACHARYA | 161.99 | 0 | 0 | 0
1122 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED CHANDERGHAT PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09255 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under CHANDERGHAT(Block-Tehatt-I), FATEPUR(Block-Tehatt-I), KADIPUR(Block-Krishnaganj) W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 02) | 1506/EMD | 18/04/2023 | 30 | BARISAL TRADING CO. | 17.08 | 16.18 | 100 | 100
1123 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED CHANDERGHAT PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09255 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Chanderghat Water Supply Scheme in Tehatta-I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 325_2/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.43 | 1.41 | 100 | 100
1124 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED CHANDERGHAT PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09255 | Augmentation | Relaying of D.I. Pipeline by replacing the damaged old UPVC Pipe for rising main from 1st pump house to 2nd pump house at Chanderghat W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 20/AE-I/NACD-II | 11/04/2025 | 120 | PRADIP KUMAR BANIK | 4.61 | 0 | 0 | 100
1125 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED CHANDERGHAT PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09255 | Augmentation | Conversion of IEP to AIRP at KADIPUR Water Supply Scheme of capacity 55 Cu.m/hr in Krishnaganj Block & CHANDERGHAT, PANINALA & BARUIHUDA Water Supply Scheme under Nadia Arsenic Civil Division -II, PHE Dte. | 1147/NACD-II | 23/08/2024 | 60 | MERCURY ENGINEERING COMPANY. | 173.69 | 0 | 0 | 0
1126 | NADIA | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-I Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) , SM/08963 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Bara Andulia(Zone-I) W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(PART-A) | 5690/ND | 03/11/2021 | 90 | H I ENTERPRISE | 98.23 | 95.03 | 96.74 | 0
1127 | NADIA | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-I Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) , SM/08963 | Retrofitting | Hiring Diesel Luxury Car on daily basis (for12 months from 01.02.2022 to 31.01.2023) for the office use of the Assistant Engineer, Kalyani Sub - Division - II, P.H.E. Dte. | 144/ Kly SD-II | 31/01/2022 | 365 | SUMAN CHAKRABORTY | 4.8 | 1.94 | 53.59 | 65
1128 | NADIA | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-I Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) , SM/08963 | Retrofitting | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Kalyani Sub-Division-I, PHE Dte. | 287/Kly SD-I | 31/03/2022 | 365 | SATYABRATA CHAKRABORTY | 4.8 | 3.14 | 100 | 100
1129 | NADIA | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-I Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) , SM/08963 | Retrofitting | Material Requisition To Resource Division | 441/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0 | 0
1130 | NADIA | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-I Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) , SM/08963 | Retrofitting | Material Requisition To Resource Division | 782/ND | 18/02/2022 | 0 | Resource Division | 4.39 | 0 | 0 | 0
1131 | NADIA | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-I Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) , SM/08963 | Retrofitting | Material Requisition To Resource Division | 1022/ND | 03/03/2022 | 0 | Resource Division | 7.9 | 0 | 0 | 0
1132 | NADIA | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-I Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) , SM/08963 | Retrofitting | Laying Of Additional Distribution System Including Specials to provide FHTC at Leftout Household in connection with JJM In Ground Based Piped Water Supply Scheme at Bara Andulia Zone I To Accommodate FHTC Within Chapra Block Under Krishnanagar Sub-division Under Nadia Division, PHE Dte. | 4504/ND | 18/09/2025 | 90 | S.S.INFRASTRUCTURE | 68.11 | 0 | 0 | 0
1133 | NADIA | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-I Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) , SM/08963 | Retrofitting | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
1134 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte , SM/10423 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte | 13/PFMS | 11/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.6 | 0 | 0 | 0
1135 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte , SM/10423 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No.- I AND II under Iswarchandrapur W/S Scheme, Block Tehatta II, Dist. Nadia. NIET No. 23 of EE/EMD of 2022-23 (Sl. No.- 01) | 152/EMD | 06/01/2023 | 30 | M/S. G.P. ENTERPRISE | 21.36 | 21.09 | 98.74 | 0
1136 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte , SM/10423 | Augmentation | Material Requisition To Resource Division | 4308/ND | 29/09/2022 | 0 | Resource Division | 5.94 | 0 | 0 | 0
1137 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte , SM/10423 | Augmentation | Material Requisition To Resource Division | 155/ND | 06/01/2023 | 0 | Resource Division | 0.96 | 0 | 0 | 0
1138 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte , SM/10423 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Iswarchandrapur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 3382/ND | 29/07/2022 | 90 | M/S SHIL & CO. | 79.62 | 77.47 | 100 | 98
1139 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte , SM/10423 | Augmentation | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Iswarchandrapur PWSS within Tehatta-II Block under RWS Sub-Division under Nadia Division, PHE Dte. | 1255/ND | 22/02/2024 | 45 | M/S SHIL & CO. | 6.19 | 6.14 | 100 | 95
1140 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte , SM/10423 | Augmentation | Repairing Works (existing OHR, Pump House, Boundary wall etc.) for Iswarchandrapur Water Supply Scheme Under RWS Nadia Sub-Divn.PHE Dte. | 1178/ND | 21/02/2024 | 90 | U-TURN CONSTRUCTION | 25.12 | 15.39 | 100 | 75
1141 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte , SM/10423 | Augmentation | Health Check up of existing Over Head Reservoir(OHR) based on inspection and Non-destructive Test (NDT) at Iswarchandrapur PWSS, Tehatta-II Block under Nadia Division, PHE Dte. | 3374/ND | 14/06/2024 | 15 | JADAVPUR UNIVERSITY | 3.48 | 3.48 | 100 | 100
1142 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte , SM/10423 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 30 cum/hr at Iswarchandrapur water supply scheme including 3 Months Trial Run & 3 Years O&M within Tehatta-II block under RWS Nadia Sub-division under Nadia Division, P.H.E. Dte. | 1491/ND | 04/03/2024 | 180 | SATYABRATA CHAKRABORTY | 162.34 | 0 | 0 | 45
1143 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte , SM/10423 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under ISWARCHANDRAPUR ground water based water supply scheme under Block_ Tehatta-I Dist. - Nadia under EMD, PHE Dte. SM/10423 | 1122/EMD | 04/06/2025 | 90 | M/S DILIP MITRA | 16.93 | 0 | 0 | 0
1144 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Matikumra Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10661 | Augmentation | FHTC under Jaldhara/Jalswapna for Matikumra Phasa -I at Ranaghat -II Block by augmentation of Ground Water Based PWSS Matikumra Ws scheme under Nadia Arsenic Division -I , P.H.E.Dte. (Sl.no.05) | 1938/NAD-I | 12/10/2022 | 90 | SATYABRATA CHAKRABORTY | 416.57 | 403.65 | 100 | 100
1145 | NADIA | Eastern Mechanical | Augmentation to accommodate FHTC for Matikumra Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10661 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejumination Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II and III (Zone-I) (Phase-I) under Matikumra ground water based water supply scheme under Block_ Ranaghat-II Dist. - Nadia under EMD, PHE Dte. (SM/10661) | 2686/EMD | 20/11/2024 | 30 | M/S DILIP MITRA | 31.76 | 0 | 0 | 0
1146 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Matikumra Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10661 | Augmentation | Construction and installation of MANIFOLD andallied works at OHR site under Matikumra Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Matikumra (Phase-I) Piped W/S Scheme (Sl.no.20) | 1449/NAD-I | 26/05/2023 | 15 | M/S DIPAK ENTERPRISE | 13.02 | 12.45 | 100 | 100
1147 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Matikumra Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10661 | Augmentation | Reconnection at Ukhilnara Chowmatha, laying of pipeline from Ukhilnara Zone-I headwork site to Ukhilnara Chowmatha at Payrandanga G.P in Ukhilnara Zone-I PWSS & Reparing and laying of pipeline at Golabazar ,Matikumra Bazar and 2nd T/W site at Nokari G.P under Jal Jeevan Mission (JJM) for Ranaghat-I & Ranaghat-II Block by retrofitting of Ground Water based PWSS for Matikumra Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 90/AE-I/NAD-I | 22/02/2024 | 30 | GANGULY ENTERPRISE | 3.88 | 3.74 | 100 | 100
1148 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Matikumra Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10661 | Augmentation | Augmentation of AIRP of Ground Water Based Piped Water Supply Scheme for Goalpur Zone-II, (30 cum/hr) including augmentation of Matikumra Water Supply Scheme under Jal Jeevan Mission (JJM) under Nadia Arsenic Division -I, P.H.E. Dte. | 1882/NAD-I | 11/11/2024 | 180 | BALAJI UDDYOG | 129.1 | 0 | 0 | 0
1149 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Matikumra Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10661 | Augmentation | Augmentation of FHTC and Laying of balanced Pipeline at the command areas of Gayeshpur, Panpara (Part) and Matikumra Mouza under Matikumra Water Supply scheme Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) | 531/NAD-I | 03/07/2025 | 60 | M/S DIPAK ENTERPRISE | 49.93 | 0 | 0 | 0
1150 | NADIA | Eastern Mechanical | Augmentation to accommodate FHTC for Matikumra Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10661 | Augmentation | Providing Boundary Illumination with allied works at Matikumra (Phase-I) under Block_ Ranaghat-II Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/10661) | 1155/EMD | 04/06/2025 | 90 | KASHINATH PAL & CO. | 4.34 | 0 | 0 | 0
1151 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Retrofitting work of existing pipelines at Debagram, Ranaghat-II Block in connection with providing FHTC undr JJM under Debagram W/S Scheme under Nadia Arsenic Division-I , PHE Dte. (Sl. No. 09) | 1385/NAD-I | 16/05/2023 | 21 | GHOSH ENTERPRISE | 23.15 | 21.9 | 94.6 | 0
1152 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Debagram Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Debagram W/S Scheme (Phase-I) under JJM(Sl.no.01) | 719/NAD-I | 27/03/2023 | 15 | CHANDAN ROY | 12.95 | 12.52 | 100 | 100
1153 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Retrofitting works at Debogramunder Debogram W/S Schemeunder JJM under Ranaghat- II Block under Nadia Arsenic Division-I,P.H.E. Dte. | 375/AE-II/NAD-I | 29/08/2023 | 7 | JYOTIRMOY ENTERPRISE | 3.76 | 3.51 | 100 | 100
1154 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Retrofitting work of Debagram, Ranaghat-II Block in connection with providing FHTC under Debagram W/S Scheme under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.03) | 2096/NAD-I | 31/08/2023 | 15 | UMWELT ENGINEER PVT. LTD. | 23.14 | 22.71 | 100 | 100
1155 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Material Requisition To Resource Division | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 22.55 | 0 | 0 | 0
1156 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Surging of existing Tube Well situated at the 3rd Tube Well site at Debogram Water Supply Scheme in Connection with Jal Jeevan Mission under Hanskhali Block to increase the yield of the Tube Well under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 03) | 205/AE-II/NAD-I | 24/09/2024 | 7 | SUMAN CHAKRABORTY | 0.64 | 0 | 0 | 0
1157 | NADIA | Eastern Mechanical | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejumination Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II , III and IV (Phase-I) under DEBGRAM ground water based water supply scheme under Block_ Ranaghat-II Dist. Nadia under EMD, PHE Dte. (SM/10662) | 2678/EMD | 20/11/2024 | 30 | DEY ENTERPRISE | 41.01 | 0 | 0 | 0
1158 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Debagram Phase-I at Ranaghat-II Block by Augmentation of Ground Water Based PWSS for Debagram W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | 1475/NAD-I | 22/08/2022 | 90 | GHOSH ENTERPRISE | 320.01 | 256.29 | 100 | 100
1159 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Arsenic Division-I PHE Dte. Schemes:- i)Debagram ii)Dhantala iii)Dubli Zone-I iv)Dubli Zone-II v)Zone-IX (Chandmari) vi)Zone-XII (Madanpur) vii)Nabla | 168/AE-I/NAD-I | 12/04/2023 | 15 | TECH VISION | 4.84 | 4.84 | 100 | 41
1160 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Continuation Work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | 448/AE-I/NAD-I | 29/09/2023 | 91 | SUMAN CHAKRABORTY | 4.85 | 4.85 | 100 | 100
1161 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Providing FHtC (Functional Household Tap Connection) under Jaldhara/jalswapna for Debagram Phase-I at Ranaghat-II Block by Augmentation of Ground Water Based PWSS for Debagram W/S Scheme under Nadia Arsenic Division-I ,PHE Dte | 213/PFMS | 26/09/2024 | 0 | GHOSH ENTERPRISE | 13.73 | 0 | 0 | 0
1162 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Field Level Survey of different School/Anganwadi Centre (AWC) by GPs enabled Mobile Application for uploading of data at IMIS website in Nadia District under Nadia Arsenic Division-I, PHE Dte. | 467/AE-I/NAD-I | 09/10/2023 | 630 | TECH VISION | 1.15 | 1.08 | 94.53 | 100
1163 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Laying of additional pipelines and FHTC at south west part of Betna W/S Scheme under JJM at Betna W/S Scheme inconnection with Betna and Debogram water supply scheme under Ranaghat - II block within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 09) | 1621/NAD-I | 27/09/2024 | 182 | M/S A.K. CONSTRUCTION | 68.67 | 11.51 | 16.76 | 75
1164 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Laying of additional pipelines and FHTC at north east part of Betna W/S Scheme under JJM at Betna W/S Scheme inconnection with Betna and Debogram water supply scheme under Ranaghat - II block within Hanskhali Block under Nadia Arsenic Division-I,P.H.E. Dte. (Sl. No. 08) | 1515/NAD-I | 19/09/2024 | 422 | MUKHERJEE CONSTRUCTION | 96.45 | 0 | 0 | 75
1165 | NADIA | Eastern Mechanical | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Providing Boundary Illumination with allied works at Debagram (Phase-I) under Block_ Ranaghat-II Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/10662) | 1163/EMD | 04/06/2025 | 90 | S.S.ENTERPRISES | 4.34 | 0 | 0 | 0
1166 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Construction of Boundary wall and pathway and Toilet at 2nd, 3rd and 4th Tubewell site of Aranghata and 3rd site of Debogram water supply Scheme in Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E. Dte. Under JJM. (Sl. No. 09) | 155/NAD-I | 28/04/2025 | 60 | GOUTAM DEY | 34.34 | 0 | 0 | 0
1167 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Continuation Work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | 18/AE-I/NAD-I | 31/01/2025 | 89 | SUMAN CHAKRABORTY | 4.85 | 0 | 0 | 0
1168 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Revamping / upgradation of the hydraulic parameters for Uttor Bhayna, Hatibanda, Aishmali, Nasra and Hijuli ( P ) villages in connection with Debogram, Nasra and Hijuli PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) | 530/NAD-I | 03/07/2025 | 120 | BUDDHADEV MONDAL | 53.23 | 0 | 0 | 0
1169 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Debagram Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10662 | Augmentation | Providing FHTC and laying dedicated pipeline for Sijdia, Dakhin Rameswarpur,Anatapur, Mithapur & aismali Village in connection with Debagram Water Supply Scheme under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in under Nadia Arsenic Division-I, PHE Dte. | 581/NAD-I | 10/07/2025 | 60 | SUMAN CHAKRABORTY | 96.78 | 0 | 0 | 0
1170 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. , SM/09798 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. | 621/PFMS | 30/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.44 | 0 | 0 | 0
1171 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. , SM/09798 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No. I under Murutia W/S Scheme, Block Karimpur-II, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-03) | 154/EMD | 06/01/2023 | 30 | TALUKDER & CO. | 13.64 | 13.33 | 100 | 20
1172 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. , SM/09798 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer etc. rejuvenation to Accommodate FHTC at Pump House No. III under Murutia WS Scheme, Block KarimpurII, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-05) | 156/EMD | 06/01/2023 | 30 | MUKHERJEE ART CENTRE | 8.75 | 8.75 | 100 | 98
1173 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. , SM/09798 | Augmentation | Material Requisition To Resource Division | 1256/ND | 16/03/2022 | 0 | Resource Division | 88.59 | 0 | 0 | 0
1174 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. , SM/09798 | Augmentation | Material Requisition To Resource Division | 4271/ND | 29/09/2022 | 0 | Resource Division | 27.23 | 0 | 0 | 0
1175 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. , SM/09798 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer etc. rejuvenation to Accommodate FHTC at Pump House No. II under Murutia W/S Scheme, Block Karimpur -II, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-04) | 155/EMD | 06/01/2023 | 30 | K.S.P. ENTERPRISE | 8.76 | 2.31 | 20.94 | 100
1176 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. , SM/09798 | Augmentation | Laying of Distribution System including Specials & Valves, Pipe supporting structure all complete based on actual estimate & Providing FHTC at Murutia Water Supply Scheme in Nadia District under Nadia Division. | 967/ND | 28/02/2022 | 1350 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 469.7 | 215.26 | 45.83 | 65
1177 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. , SM/09798 | Augmentation | Construction and Installation of 120.00 cum capacity Arsenic-Cum-Iron Removal Plant (AIRP) at Murutia PWSS including 3 Months Trial Run & 3 Years O&M under Nadia Division, P.H.E. Dte | 1250/ND | 22/02/2024 | 720 | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 300.56 | 0 | 0 | 60
1178 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. , SM/09798 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Murutia PWSS under Karimpur-II Block under Tehatta Sub Division under Nadia Division-,P.H.E Dte. under Jal Jeevan Mission(JJM) . | 422/ND | 27/01/2025 | 120 | M/S SANJAY ADHIKARI | 29.73 | 0 | 0 | 0
1179 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. , SM/09798 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House and allied works for Muktadaha Zone-II PWSS and Murutia PWSS within Karimpur-I Block and Karimpur-II Block Under Tehatta Sub-Division under Nadia Division P.H.E. | 762/ND | 19/02/2025 | 90 | DEBASIS SAMADDAR | 74.08 | 0 | 0 | 0
1180 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BETBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09266 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Betbaria W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 167/NACD-II | 09/02/2021 | 21 | B.M. ENGINEERING & CONSTRUCTION | 59.73 | 0 | 0 | 100
1181 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BETBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09266 | Augmentation | Construction of Boundary wall with Grill Gate at Betberia 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | 240/AE-I/NACD-II | 17/02/2022 | 30 | SAHA ENGINEERS | 4.04 | 4.04 | 99.88 | 100
1182 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BETBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09266 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Betberia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 865/NACD-II | 08/11/2021 | 45 | SHIBU BISWAS | 53.1 | 53.07 | 100 | 100
1183 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BETBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09266 | Augmentation | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Betberia Water Supply Scheme at Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | 1015/NACD-II | 29/11/2022 | 60 | BISHAL CONSTRUCTION | 9.95 | 9.76 | 100 | 90
1184 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED BETBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09266 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SAKDA (Block-Krishnaganj), BAHADURPUR(Block-Tehatt-I), BETBERIA(Block-Chapra) W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 01) | 1507/EMD | 18/04/2023 | 30 | SWAPAN KUMAR BHANJA | 14.69 | 4.88 | 100 | 100
1185 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BETBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09266 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Betberia) | 1146/NACD-II | 10/10/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
1186 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BETBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09266 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Betberia Water Supply Scheme of capacity 39Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | 397/NACD-II | 13/03/2024 | 60 | M/S. R.K.ENTERPRISE | 150.86 | 0 | 0 | 0
1187 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BETBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09266 | Augmentation | Repair and Renovation work at Betberia Headwork Site under Betberia Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | 1028/AE-I/NACD-II | 10/12/2024 | 30 | JAYBRATO HALDER | 3.53 | 0 | 0 | 0
1188 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BETBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09266 | Augmentation | Repair and Renovation work at Betberia 2nd tube well Site under Betberia Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | 904/AE-I/NACD-II | 10/09/2024 | 30 | ARIT KUMAR PAL | 4.83 | 0 | 0 | 0
1189 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BETBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09266 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Betberia Water Supply Scheme in Chapra Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 328/1/AE-I/NACD-II | 13/07/2023 | 7 | RISHAN ENGINEERING CONSULTANCY | 0.46 | 0.46 | 100 | 100
1190 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BETBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09266 | Augmentation | Structural Health assesment of existing shaft type OHR of Chapra Blocks and ancillary structures conducting Non Destructive test and through visual observation under Nadia Arsenic Civil Division-II P.H.E Dte. | 1434/NACD-II | 15/12/2023 | 30 | RISHAN ENGINEERING CONSULTANCY | 8.46 | 8.44 | 100 | 100
1191 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BETBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09266 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Betberia W/S Scheme & Hridaypur W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 748_NACD-II | 14/06/2024 | 45 | SAFTI PRIVATE LIMITED | 18.22 | 0 | 0 | 100
1192 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09268 | Augmentation | Providing Functional House Hold Tap Connection(Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10mm dia gun-Metal ferrule,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline(parallel or extension) at Shyamnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 271/EE/NACD-II | 22/02/2021 | 21 | SANDIP BISWAS | 52.44 | 0 | 0 | 100
1193 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09268 | Augmentation | Construction of Boundary wall with Grill Gate at Shyamnagar Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte | 46/AE-II/NACD-II | 17/02/2022 | 30 | R.M. TRADING | 4.97 | 4.97 | 99.9 | 100
1194 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09268 | Augmentation | Construction of Boundary wall with Grill Gate at Shyamnagar Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | 59/AE-II/NACD-II | 28/06/2022 | 30 | R.M. TRADING | 2.74 | 2.72 | 99.48 | 100
1195 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09268 | Augmentation | Construction of RCC Column for supporting pipeline for future extension ( Near Khalbualia Bridge) alongwith Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Shyamnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 453/NACD-II | 14/07/2022 | 45 | SANJIB DEY | 8.58 | 8.51 | 100 | 100
1196 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09268 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Shyamnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 190/NACD-II | 15/02/2021 | 21 | SANDIP BISWAS | 36.12 | 0 | 0 | 100
1197 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09268 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Shyamnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 870/NACD-II | 08/11/2021 | 45 | BIDYUT KUMAR | 34.62 | 34.61 | 100 | 100
1198 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09268 | Augmentation | Continuation work Order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara (Vill- Falia) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 112/NACD-II | 11/02/2022 | 90 | MONDAL ENTERPRISE | 45.84 | 0 | 0 | 100
1199 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09268 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SHYAMNAGAR(Block-Krishnaganj), MOBARAKPUR(Block-Tehatt-I), PATHARGHAT(Block-Tehatt-I) W/S Scheme, Dist. - Nadia. | 1505/EMD. | 18/04/2023 | 30 | DIPALI CONSTRUCTION | 19.37 | 6.37 | 100 | 80
1200 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09268 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SHYAMNAGAR(Block-Krishnaganj), MOBARAKPUR(Block-Tehatt-I), PATHARGHAT(Block-Tehatt-I) W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 03) | 1505/EMD | 18/04/2023 | 30 | DIPALI CONSTRUCTION | 19.37 | 0 | 0 | 90
1201 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09268 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Shyamnagar Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | 25/AE-II/NACD-II | 15/02/2024 | 15 | SUMIT GHOSH | 0.97 | 0 | 0 | 0
1202 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09268 | Augmentation | New pipeline laying by providing 200 mm dia D.I. pipe over existing columns to cross the PWD Bridge and PVC pipe for supplying water to Khalboalia village under krishnaganj Block and also Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at ( Vill- Khalboalia) Shyamnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 520/NACD-II | 05/08/2022 | 60 | SANJIB DEY | 96.93 | 96.88 | 100 | 100
1203 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09268 | Augmentation | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Shyamnagar W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 1199/NACD-II | 23/12/2022 | 15 | R.M. TRADING | 0.89 | 0.83 | 100 | 100
1204 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09268 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Shyamnagar Water Supply Scheme in Krishnaganj Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 323_2/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 2.29 | 2.01 | 100 | 100
1205 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09268 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Shyamnagar Water Supply Scheme of capacity 67 Cu.m/hr in Krishnaganj Block under Nadia Arsenic Civil Division -II, PHE Dte." | 185/NACD-II | 09/02/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 194.41 | 194.41 | 100 | 100
1206 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09268 | Augmentation | Quotation for load enhancement at Pump House No-I of Shyamanagar (Krishnaganj Block) w/s scheme under EMSD-III,PHE Dte.,Nadia | BP-73-24-25 | 30/07/2024 | 0 | W.B.S.E.D.C.LTD (KRISHNAGANJ C.C.C) | 0.44 | 0 | 0 | 0
1207 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09268 | Augmentation | Repair and Renovation work with Reinforced Barbed Tape , OverHead Reservoir Plaster , Painting and other allied works at Shyamnagar HeadWork site and 2nd Pump house site under Shyamnagar Piped Water Supply Scheme in Krishnaganj Block under Nadia Arsenic Division-II,P.H.E.Dte. | 1639/NACD-II | 23/12/2024 | 119 | SAMAR ENTERPRISE | 10.13 | 0 | 0 | 100
1208 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09268 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Shyamnagar Piped Water Supply Scheme in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 09/NACD-II | 06/02/2025 | 90 | SUMIT GHOSH | 105.58 | 0 | 0 | 0
1209 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09268 | Augmentation | Relaying of rising main and other necessary allied works at Shyamnagar Water Supply Scheme in Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 21/AE-I/NACD-II | 11/04/2025 | 60 | NISHITH BANERJEE | 3.66 | 0 | 0 | 0
1210 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040804, 19336040808, 19336040806, 19336040807, 19336040819" | 137/AE-I/NACD-II | 14/07/2022 | 45 | TAPAS GHOSH | 4.87 | 3.64 | 100 | 0
1211 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030213, 19336030214, 19336030516, 19336030206, 19336030212" | 149/AE-I/NACD-II | 14/07/2022 | 45 | PRABIR KUMAR ROY | 4.87 | 4.34 | 89.11 | 0
1212 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Nabadwip Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | 945/NACD-II | 21/11/2022 | 60 | ROY CONSTRUCTION | 28.22 | 23.68 | 83.91 | 0
1213 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Santipur Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | 948/NACD-II | 21/11/2022 | 90 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 65 | 56.35 | 86.7 | 75
1214 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Ranaghat-I Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | 946/NACD-II | 21/11/2022 | 60 | INVENT ENGINEER'S COOP SOCIETY LTD. | 35.73 | 31.22 | 87.38 | 75
1215 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030403, 19336030401, 19336030323, 19336040603, 19336040605" | 144/AE-I/NACD-II | 14/07/2022 | 45 | SHOVON KUMAR MODAK | 4.86 | 3.22 | 66.24 | 0
1216 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040422, 19336040414, 19336040415, 19336040406, 19336040403" | 159/AE-I/NACD-II | 14/07/2022 | 45 | BINOY DAS | 4.87 | 3.8 | 100 | 0
1217 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040421, 19336040516, 19336040408, 19336040405" | 161/AE-I/NACD-II | 14/07/2022 | 45 | PARTHA DAS | 3.89 | 3.58 | 100 | 0
1218 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040608, 19336040712, 19336040713, 19336040708, 19336040706" | 145/AE-I/NACD-II | 14/07/2022 | 45 | DEBASISH DEY | 4.87 | 3.77 | 100 | 0
1219 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040604, 19336040707, 19336040607, 19336030205, 19336030207" | 147/AE-I/NACD-II | 14/07/2022 | 45 | M/S FREEDOM CONSTRUCTION | 4.87 | 4.85 | 100 | 0
1220 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030209, 19336030204, 19336030226, 19336030221, 19336030215" | 148/AE-I/NACD-II | 14/07/2022 | 45 | ARIT KUMAR PAL | 4.87 | 4.45 | 100 | 0
1221 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030217, 19336030518, 19336030210, 19336030203, 19336030211" | 150/AE-I/NACD-II | 14/07/2022 | 45 | TAPAN SAHA | 4.86 | 4.81 | 100 | 0
1222 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030208, 19336030222, 19336030216, 19336040216, 19336040316" | 151/AE-I/NACD-II | 14/07/2022 | 45 | MUKHERJEE CONSTRUCTION | 4.86 | 3.48 | 100 | 0
1223 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040110, 19336040202, 19336040204, 19336040208, 19336040203" | 155/AE-I/NACD-II | 14/07/2022 | 45 | SAHA ENGINEERS | 4.86 | 3.54 | 100 | 0
1224 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040919, 19336040920, 19336040908, 19336040916, 19336040420" | 158/AE-I/NACD-II | 14/07/2022 | 45 | M/S. ASIT KUMAR BISWAS | 4.87 | 3.93 | 100 | 0
1225 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040302, 19336040301, 19336040218, 19336040320, 19336040513" | 152/AE-I/NACD-II | 14/07/2022 | 45 | BABLU MALLICK | 4.87 | 3.65 | 100 | 0
1226 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040215, 19336040220, 19336040303, 19336040304, 19336040307" | 153/AE-I/NACD-II | 14/07/2022 | 45 | SAMAR ENTERPRISE | 4.86 | 3.82 | 100 | 0
1227 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040214, 19336040217, 19336040309, 19336040323, 19336040105" | 154/AE-I/NACD-II | 14/07/2022 | 45 | BIPLAB GUHA | 4.87 | 3.18 | 100 | 0
1228 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030504, 19336030503, 19336030513, 19336030501, 19336030502" | 136/AE-I/NACD-II | 14/07/2022 | 45 | SHYAMAL KANTI GHOSH | 4.87 | 3.78 | 100 | 0
1229 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040821, 19336040823, 19336040820, 19336040803, 19336040813" | 138/AE-I/NACD-II | 14/07/2022 | 45 | SUMIT GHOSH | 4.87 | 4.62 | 100 | 0
1230 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040822, 19336030612, 19336030616, 19336030712, 19336030624" | 139/AE-I/NACD-II | 14/07/2022 | 45 | M/S TARUN GHOSH & CO. | 4.87 | 4.51 | 100 | 0
1231 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030813, 19336030802, 19336030725, 19336030714, 19336030814" | 141/AE-I/NACD-II | 14/07/2022 | 45 | GHOSH ENTERPRISE | 4.87 | 3.54 | 100 | 0
1232 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030119, 19336030109, 19336030104, 19336030307, 19336030308" | 143/AE-I/NACD-II | 14/07/2022 | 45 | GHOSH & CO. | 4.86 | 4.06 | 100 | 0
1233 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130223, 19336130301, 19336130302, 19336130303, 19336130304" | 88/AE-II/NACD-II | 07/07/2022 | 45 | S.B. CONSTRUCTION | 4.94 | 4.03 | 100 | 0
1234 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040205, 19336040102, 19336040206, 19336040201, 19336040409" | 156/AE-I/NACD-II | 14/07/2022 | 45 | A.K ADHIKARY | 4.86 | 3.7 | 100 | 0
1235 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040401, 19336040419, 19336040404, 19336040402, 19336040416" | 160/AE-I/NACD-II | 14/07/2022 | 45 | M/S SREE KRISHNA ENTERPRISE. | 4.86 | 3.57 | 100 | 0
1236 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130305, 19336130311, 19336130316, 193361300418, 19336130506" | 89/AE-II/NACD-II | 07/07/2022 | 45 | CHINMOY BISWAS | 4.94 | 4.7 | 100 | 0
1237 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040913, 19336040912, 19336040911, 19336040905, 19336040906" | 157/AE-I/NACD-II | 14/07/2022 | 45 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 4.86 | 3.81 | 100 | 0
1238 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130507, 19336130503, 19336130510, 19336130601, 19336130603" | 90/AE-II/NACD-II | 07/07/2022 | 45 | SANJIT DAS | 4.94 | 4.35 | 100 | 0
1239 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130922, 19336131023, 19336131102, 19336131008" | 94/AE-II/NACD-II | 07/07/2022 | 45 | AMIT KARMAKAR | 3.95 | 3.57 | 100 | 0
1240 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130615, 19336130620, 19336130522, 19336130701, 19336130703" | 91/AE-II/NACD-II | 07/07/2022 | 45 | BASUDEB SAHA | 4.94 | 4.35 | 100 | 0
1241 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130706, 19336130709, 19336130710, 19336130717, 19336130802" | 92/AE-II/NACD-II | 07/07/2022 | 45 | SREE GURU ENTERPRISE | 4.94 | 3.57 | 100 | 0
1242 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030710, 19336030622, 19336030617, 19336030723, 19336030716" | 140/AE-I/NACD-II | 14/07/2022 | 45 | SURAJIT KUMAR GHOSH | 4.87 | 3.09 | 100 | 0
1243 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040609, 19336040617, 19336040610, 19336040606, 19336040710" | 146/AE-I/NACD-II | 14/07/2022 | 45 | DEBARSHI BANERJEE | 4.86 | 4.72 | 100 | 0
1244 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Krishnagar-I Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | 943/NACD-II | 21/11/2022 | 60 | PAPAN ROY | 38.09 | 33.77 | 100 | 70
1245 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Krishnagar-II Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | 944/NACD-II | 21/11/2022 | 60 | R.M. TRADING | 22.31 | 21.02 | 100 | 75
1246 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130822, 19336130902, 19336130903, 19336130905, 19336130913" | 93/AE-II/NACD-II | 07/07/2022 | 45 | ROY CONSTRUCTION | 4.94 | 3.64 | 100 | 0
1247 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Tehatta-II Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | 955/NACD-II | 21/11/2022 | 90 | SOMNATH CHATTERJEE | 70.82 | 56.96 | 80.43 | 40
1248 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030722, 19336030804, 19336030816, 19336030818, 19336030913" | 142/AE-I/NACD-II | 14/07/2022 | 45 | VAI ENTERPRISE | 4.86 | 2.46 | 100 | 100
1249 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Karimpur-II Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | 952/NACD-II | 21/11/2022 | 90 | CHAKRABORTTI ENTERPRISE | 56.82 | 49.34 | 100 | 90
1250 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Hanskhali Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | 949/NACD-II | 21/11/2022 | 90 | A.P. POWER & CONCRETE | 91.66 | 85.42 | 100 | 90
1251 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Kaliganj Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | 950/NACD-II | 21/11/2022 | 90 | DEBASIS SAMADDAR | 87.28 | 86.93 | 100 | 100
1252 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Karimpur-I Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | 951/NACD-II | 21/11/2022 | 90 | SANJIB DEY | 85.41 | 78.84 | 100 | 85
1253 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Nakashipara Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | 953/NACD-II | 21/11/2022 | 90 | NILAY KUMAR BHATTACHARYA | 87.34 | 87.15 | 100 | 100
1254 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Chakdah Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | 941/NACD-II | 21/11/2022 | 90 | SANJOY BAKSHI | 94.61 | 94.1 | 100 | 100
1255 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under Hanskhali BLOCK from existing piped water supply scheme. (Phase_II) | 1175/NACD-II | 22/12/2022 | 90 | NATIONAL CONSTRUCTION | 19.31 | 13.28 | 100 | 80
1256 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Haringhata Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | 942/NACD-II | 21/11/2022 | 60 | SUMAN CHAKRABORTY | 49.18 | 24.18 | 49.16 | 100
1257 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under Ranaghat_II Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II PHE Dte. (Phase-II) | 947/NACD-II | 21/11/2022 | 1080 | ASIT PRAMANIK | 72.07 | 70.96 | 98.47 | 95
1258 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under TEHATTA-I BLOCK from existing piped water supply scheme. (Phase-II) | 1176/NACD-II | 22/12/2022 | 960 | M/S K.P. CONSTRUCTION | 44.29 | 37.69 | 85.1 | 55
1259 | NADIA | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) , SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Tehatta-I Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | 954/NACD-II | 21/11/2022 | 819 | J.D. CONSTRUCTION | 93.05 | 75.07 | 86.01 | 95
1260 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-III) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10521 | Augmentation | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-III) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | 25/PFMS | 20/05/2022 | 0 | ENVIROTECH SOLUTIONS | 2.55 | 0 | 0 | 0
1261 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-III) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10521 | Augmentation | Material Requisition To Resource Division | 4278/ND | 29/09/2022 | 0 | Resource Division | 2.44 | 0 | 0 | 0
1262 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-III) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10521 | Augmentation | Material Requisition To Resource Division | 3897/ND | 08/09/2022 | 0 | Resource Division | 26.95 | 0 | 0 | 0
1263 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-III) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10521 | Augmentation | Material Requisition To Resource Division | 3790/ND | 24/08/2023 | 0 | Resource Division | 1.6 | 0 | 0 | 0
1264 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-III) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10521 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Teinpur Zone-III to accommodate FHTC within Karimpur-II block under RWS Sub-Division under Nadia Division, PHE Dte. | 3819/ND | 05/09/2022 | 90 | B.S. ENTERPRISE | 102.68 | 95.67 | 100 | 95
1265 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-III) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10521 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under TEINPUR (ZONE-I ,II, III & IV) W/S Scheme, Block- Karimpur-II , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 06) | 500/EMD | 24/01/2023 | 30 | M/S DILIP MITRA | 64.62 | 10.18 | 100 | 85
1266 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-III) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10521 | Augmentation | Renovation of AIRP and Construction of Backwash chamber for AIRP at Head Work Site at Teinpur Zone-III PWSS under Nadia Division PHE Dte. Capacity- 40.30 cum/hr | 782/ND | 05/02/2024 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 83.94 | 41.69 | 100 | 70
1267 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-III) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10521 | Augmentation | Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | 3450/ND | 20/06/2024 | 45 | IMAGIN | 19.44 | 5.3 | 100 | 100
1268 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-III) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10521 | Augmentation | Repairing Works (existing OHR, Pump House, Boundary wall etc.) for Tenpur (Zone-III) Water Supply Scheme, Karimpur-I Block Under RWS Nadia Sub Division, P.H.E. Dte. | 1176/ND | 21/02/2024 | 720 | B K ENGINEERING | 29.16 | 15.73 | 53.94 | 65
1269 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-III) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10521 | Augmentation | Additional work of Laying Distribution System and additional work of providing FHTC in connection with Augmentation of Teinpur Zone - III PWSS within Karimpur-II Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 3904/ND | 16/07/2024 | 315 | PRADIP KUMAR BANIK | 20.67 | 0 | 0 | 70
1270 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10737 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Karimpur-Jalangi Z-10B W/S Scheme in Karimpur-II Block of Nadia District under Nadia Division, P.H.E. Dte. | 321/TSD | 24/11/2021 | 30 | RADIANT | 2.44 | 2.44 | 100 | 100
1271 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10737 | Augmentation | Material Requisition To Resource Division | 2313/ND | 29/05/2023 | 0 | Resource Division | 5.45 | 0 | 0 | 0
1272 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10737 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KARIMPUR JALANGI (Z-IV, V & XB) W/S Scheme, Block-Karimpur I , Dist. - Nadia. NIET NO. - 33 OF EE/EMD OF 2022-23 (SL. NO. - 03) | 1198/EMD | 22/03/2023 | 771 | AVINABA ENGINEERING CONCERN | 62.41 | 0 | 0 | 80
1273 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10737 | Augmentation | Construction of barbed wire fencing with concrete pillars at Hatisala Karimpur-Jalangi Zone-X(B) water supply scheme (New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM | 1120/TSD | 21/02/2024 | 7 | NIVEDITA CONSTRUCTION | 1.46 | 1.3 | 100 | 100
1274 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10737 | Augmentation | Quotation charges for new service connection and security deposit at Karimpur Jalangi Zone-X,B (Hatisala) PH-II under EMSD-III,Nadia | BP-179 | 13/12/2024 | 0 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 7.19 | 0 | 0 | 0
1275 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10737 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangement at H.W Site and consruction of Boundary wall at Head Work Site At Karimpur Jalangi Zone- X(B) Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | 1633/ND | 07/03/2024 | 720 | M/S BAPI ENTERPRISE | 24.15 | 0 | 0 | 80
1276 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10737 | Augmentation | Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Jone-XB to accommodate FHTC Tehatta Sub-Division under Nadia Division, PHE Dte. | 242/ND | 13/01/2023 | 818 | CHOWDHURY & CO. | 79.52 | 35.55 | 73.95 | 90
1277 | NADIA | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10460 | Augmentation | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | 28/PFMS | 20/05/2022 | 0 | RADIANT | 3.53 | 0 | 0 | 0
1278 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10460 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KAMGACHI(Z-I) W/S Scheme, Block- RANAGHAT I , Dist. - Nadia. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 07) | 1579/EMD | 24/04/2023 | 30 | CINZANO | 32.65 | 0 | 0 | 0
1279 | NADIA | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10460 | Augmentation | Material Requisition To Resource Division | 1870/MD | 26/04/2023 | 0 | Resource Division | 53.35 | 0 | 0 | 0
1280 | NADIA | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10460 | Augmentation | Material Requisition To Resource Division | 2124/ND | 16/05/2023 | 0 | Resource Division | 71.38 | 0 | 0 | 0
1281 | NADIA | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10460 | Augmentation | Material Requisition To Resource Division | 2309/ND | 29/05/2023 | 0 | Resource Division | 28.03 | 0 | 0 | 0
1282 | NADIA | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10460 | Augmentation | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Pump house No-1 site at Kamgachi Zone-I Water supply scheme under Ranaghat Sub ¿ Division, PHE Dte. | 1279(A)RSD | 04/10/2024 | 75 | M/S SAYAN ENTERPRISE | 4.46 | 0 | 0 | 0
1283 | NADIA | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10460 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Banpur ii) Dakshinpara (Zone-I)iii) Dakshinpara (Zone-II) iv) Kamgachi (Zone-I)(Part-I) v)Kamgachi (Zone-I)(Part-II)vi)Kamgachi (Zone-II)(Part-I) vii) Kamgachi (Zone-II)(Part-II) | 246/Kly SD-I | 27/02/2023 | 181 | HORIZEN | 4.99 | 1.59 | 100 | 100
1284 | NADIA | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10460 | Augmentation | Material Requisition To Resource Division | 27/ND | 03/01/2024 | 0 | Resource Division | 61.68 | 0 | 0 | 0
1285 | NADIA | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10460 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Kamgachi Zone-II to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. (PART-I) | 5352/ND | 22/12/2022 | 1080 | TANMOY ROY CHOWDHURY | 221.89 | 162.85 | 73.39 | 85
1286 | NADIA | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10460 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Kamgachi Zone-I to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. (PART-I) | 5353/ND | 22/12/2022 | 1086 | JAL PRAVAHIKA PRIVATE LIMITED | 240.61 | 145.44 | 60.45 | 85
1287 | NADIA | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10460 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Kamgachi Zone-I piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | 1276/RSD | 04/10/2024 | 45 | SAGAR ENTERPRISE | 1.9 | 0 | 0 | 100
1288 | NADIA | Nadia Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10460 | Augmentation | Construction of Jhama Bats Road from Main road to headwork site of Kamgachi water supply scheme under Ranaghat Sub Division under Nadia Division P.H. Engineering Dte. | 204/RSD | 06/02/2025 | 30 | M/S MALLICK ENTERPRISE | 6.35 | 0 | 0 | 100
1289 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Preparation of DPR for augmentation of existing Helenchi Zone-I, (Block-Krishnaganj) piped water supply schemes | 153/AE-I/NACD-II | 16/11/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.91 | 2.91 | 100 | 100
1290 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Construction of Boundary wall with Grill Gate at Helenchi ZoneI Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | 105/NACD-II | 10/02/2022 | 45 | NISHITH BANERJEE | 8.61 | 8.6 | 99.9 | 100
1291 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-I, (Vill- Sibnibash) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 64/NACD-II | 25/01/2022 | 45 | JOY GOPAL GUPTI | 21.43 | 21.43 | 99.99 | 100
1292 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Construction of Boundary wall with Grill Gate at Helenchi Zone-III Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte | 43/AE-II/NACD-II | 17/02/2022 | 30 | SUMIT GHOSH | 4.29 | 4.28 | 100 | 100
1293 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-I, (Vill- Sibnibash) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 991/NACD-II | 30/12/2021 | 45 | JOY GOPAL GUPTI | 95.14 | 95.14 | 100 | 100
1294 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-I W/s Scheme (Vill- Krishnapur) in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 125/NACD-II | 21/02/2022 | 90 | A.P. POWER & CONCRETE | 105.67 | 86.15 | 100 | 100
1295 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Construction of boundary wall with grill gate and barbed wire fencing at Helenchi Zone-I water supply scheme Head work site under Nadia Arsenic Civil Division-II, PHE Dte, Nadia District. | 1016/NACD-II | 29/11/2022 | 60 | SANJIB BISWAS | 18.63 | 18.43 | 98.91 | 95
1296 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Construction of Approach Road with land Development at Helenchi Zone-I Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | 66/AE-II/NACD-II | 28/06/2022 | 30 | NISHITH BANERJEE | 2.35 | 2.29 | 100 | 100
1297 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Functional House Hold Tap Connection for left out Household regarding Har Ghar Jal Certification including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Vill- Par Chandan Nagar, Shibnibas, Pabakhali) Helenchi Zone-I W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 148/NACD-II | 17/01/2023 | 20 | A.K ADHIKARY | 5.95 | 5.95 | 100 | 100
1298 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HELENCHI (Z-I, Z-II, Z-III) (Block- Krishnaganj ) AND BANSBERIA,CHANDPUR & DAMODARKHALI (Block- Krishnagar I) W/S Scheme, , Dist. - Nadia. NIET NO.- 31 of EE/EMD of 2022-23 (Sl. No.- 02) | 1121/EMD | 16/03/2023 | 30 | M.S. ENTERPRISE | 65.68 | 8.84 | 100 | 90
1299 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Shifting of S/S Structure at Sbibniwas under KNJCCC at PH-II Z-I under Helenchi W/S Scheme. |  | 31/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.96 | 0 | 0 | 0
1300 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Shifting of S/S structure at Sbibniwas under KNJ CCC related to Helenchi Zone -I PH-2 | 164 | 14/09/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.96 | 0 | 0 | 0
1301 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Helenchi Zone-I W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1195/NACD-II | 23/12/2022 | 15 | DYNAMIC CONSTRUCTION | 1.05 | 1.03 | 100 | 100
1302 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Helenchi Zone-I Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | 18/AE-II/NACD-II | 15/02/2024 | 15 | M/S SHILL & CO. | 0.97 | 0.95 | 100 | 100
1303 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Helenchi Z-I Water Supply Scheme of capacity 65 Cu.m/hr in Krishnaganj Block under Nadia Arsenic Civil Division -II, PHE Dte" | 175/NACD-II | 07/02/2024 | 419 | MONDAL PRECISION PRIVATE LIMITED | 204.32 | 163.45 | 80 | 20
1304 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Chakdignagar ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. WBPHED/EE/EMD/NIeT-37 of 2023-24 (Sl. No. 7) | 948/EMD | 18/03/2024 | 410 | KARTICK BAL | 22.35 | 0 | 0 | 90
1305 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Continuation Work Order for Laying of pipeline at Helenchi Zone-I Water Supply Scheme under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | 1247/AE-I/NACD-II | 20/03/2025 | 161 | M/S SHILL & CO. | 0.95 | 0 | 0 | 100
1306 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Continuation Work Order for System reconfiguration for hydraulic efficiency at Helenchi Zone-I Piped Water Supply Scheme under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | 1248/AE-I/NACD-II | 20/03/2025 | 161 | SHYAMAL SHIL | 0.96 | 0 | 0 | 100
1307 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Laying of Distribution System including providing FHTC at left out households and repairing of damaged Pipeline for Helenchi Zone-I W/S Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 940/NACD-II | 28/07/2025 | 60 | SANJOY BAKSHI | 22.92 | 0 | 0 | 0
1308 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09871 | Augmentation | Continuation Work Order for System reconfiguration for hydraulic efficiency at Helenchi Zone-I Piped Water Supply Scheme under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | 1248_1/AE-I/NACD-II | 20/03/2025 | 161 | SREE KRISHNA ENTERPRISE. | 0.92 | 0 | 0 | 100
1309 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10571 | Augmentation | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | 53/PFMS | 22/06/2022 | 0 | HORIZEN | 2.53 | 0 | 0 | 0
1310 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10571 | Augmentation | Special repair & renovation of boundary wall & allied works in the premises at pump house no 2 of Dakshinpra-II W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | 468/A/RSD | 26/07/2022 | 30 | MASUM CONSTRUCTION | 3.15 | 3.13 | 99.49 | 90
1311 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10571 | Augmentation | Special repair & renovation of head work site pump house & allied works of Dakshinpara-II W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte | 555/RSD | 30/08/2022 | 30 | DURGADAS BASU | 2.15 | 1.78 | 100 | 85
1312 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10571 | Augmentation | Material Requisition To Resource Division | 23/ND | 03/01/2023 | 0 | Resource Division | 8.8 | 0 | 0 | 0
1313 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10571 | Augmentation | Material Requisition To Resource Division | 1866/ND | 26/04/2023 | 0 | Resource Division | 19.87 | 0 | 0 | 0
1314 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10571 | Augmentation | Material Requisition To Resource Division | 2308/ND | 29/05/2023 | 0 | Resource Division | 1.48 | 0 | 0 | 0
1315 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10571 | Augmentation | Special repair & renovation of pump house & allied works in the premises at pump house no-I of Dakshinpara-II W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | 555/A/RSD | 30/08/2022 | 30 | TINA CONSTRUCTION | 2.5 | 2.16 | 100 | 80
1316 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10571 | Augmentation | Special repair & renovation & repair of AIRP pump house & allied works of Dakshinpara-II W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | 476/RSD | 27/07/2022 | 30 | CONSTRUCTURE | 1.96 | 1.41 | 100 | 90
1317 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10571 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under DAKSHINPARA (Zone-I & II) W/S Scheme, Block- Hanskhali , AND GOPINATHPUR W/S Scheme, Block- Tehatta-II, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 01) | 496/EMDdt.24.01.2023 | 17/03/2023 | 656 | GLACIER ENGINEERING CO. | 66.71 | 8.5 | 100 | 100
1318 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10571 | Augmentation | Providing functional household tap connection including supplying,laying,fitting,fixing of 15mm NB PVC(schedule 80/20 mm) OD HDPE(PE 100 , PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply scheme for dakshinpara Zone-II to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.E. Dte. | 5331/ND | 21/12/2022 | 45 | NEERMAN | 96.27 | 60.98 | 63.35 | 91
1319 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10571 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Dakshinpara-II PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 35.00 Cu.m/hr | 134/ND | 09/01/2024 | 450 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 60.46 | 0 | 0 | 91
1320 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10571 | Augmentation | Construction and installation of MANIFOLD and allied works at Head Works site under Dakshinpara Zone-II Ground Based Water Supply Scheme under Hanskhali Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) | 2433/ND | 26/05/2025 | 90 | M/S S.K. ENTERPRISE | 12.34 | 0 | 0 | 0
1321 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10571 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at DAKSHINPARA (ZONE-II) W/S Scheme Block- HANSKHALI under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/10571 | 1141/EMD | 04/06/2025 | 90 | PADMA ENGINEERING CO. | 32.63 | 0 | 0 | 0
1322 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Utter Tajpur W/S Scheme (Phase-I) of Retrofitting under Jal Swapno Programme , SM/07421 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT UTTAR TAJPUR | 459/DW | 30/03/2021 | 0 | SARKAR AGENCY | 42.99 | 0 | 0 | 0
1323 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Utter Tajpur W/S Scheme (Phase-I) of Retrofitting under Jal Swapno Programme , SM/07421 | Retrofitting | Providing Functional Household Tap Connection from Utter Tajpur W/S Scheme (Phase-I) of Retrofitting under Jal Swapno Programme | 268/PFMS | 08/10/2021 | 0 | LEMNISCATE | 16.36 | 0 | 0 | 0
1324 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Utter Tajpur W/S Scheme (Phase-I) of Retrofitting under Jal Swapno Programme , SM/07421 | Retrofitting | Continuation for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department. | 470/Kly SD-1 | 31/03/2023 | 91 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 4.89 | 4.89 | 100 | 20
1325 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Utter Tajpur W/S Scheme (Phase-I) of Retrofitting under Jal Swapno Programme , SM/07421 | Retrofitting | Hiring of Diesel Ambassador Car/maxi cab for the office of the Assistant Engineer, Debagram Sub-Diovision,PHE Dte,Debagram,Nadia with effect from 01.08.2021 to 31.07.2022 | 399/DSD | 29/07/2021 | 365 | TARUN KUMAR BHATTACHARYA | 4.8 | 1.87 | 64.57 | 0
1326 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Utter Tajpur W/S Scheme (Phase-I) of Retrofitting under Jal Swapno Programme , SM/07421 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Uttar Tajpur W/S scheme (Phase-I) of Rectrofitting in Nadia District under Nadia Division P.H.E. Dte. | 60/ND | 07/01/2021 | 90 | SARKAR AGENCY | 96.79 | 54.04 | 55.83 | 100
1327 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Duttapulia Zone-I Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. , SM/10652 | Augmentation | Retrofitting work at Bhatbhanha, Kulgachi chak, Daluabari, Andipur Chak, Uttar Rameswarpur, Kalipur, Andipur, Kalinanagar, Kulgacchi Mouza inconnection with Augmentation to accomodate FHTC under JJM for Duttaphulia Zone- I Ground water based piped water supply scheme (Phase- II ) Block- Ranaghat -II under JJM Dist- Nadia under Nadia Arsenic Division-I , PHE Dte. (sl.14) | 831 / NAD-I | 31/03/2023 | 45 | MANGES INDUSTRIAL CORPORATION | 41.26 | 38.04 | 100 | 38
1328 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Duttapulia Zone-I Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. , SM/10652 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Duttaphulia Zone-I Part-II at Ranaghat-II Block by augmentation of Ground Water based PWSS for Duttaphulia Zone-I Water SUpply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 1784/NAD-I | 22/09/2022 | 90 | MANGES INDUSTRIAL CORPORATION | 424.43 | 421.16 | 100 | 100
1329 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Duttapulia Zone-I Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. , SM/10652 | Augmentation | Continuation Work order for ¿Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.¿ | 144/AE-I/NAD-I | 31/03/2023 | 90 | SUMAN CHAKRABORTY | 4.85 | 4.85 | 100 | 100
1330 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Matikumra Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. , SM/10653 | Augmentation | Providing FHTC under Jaldhara/ Jal Swapna for matikumra Phase -II at Ranaghat -II Block by augmentation of Ground Water bassed PWSS for Matikumra Water Supply Sch. under Nadia Arsenic Division -I , P.H.E.Dte. (Sl.no.04) | 1769 / NAD-I | 20/09/2022 | 90 | KINGS AND CO | 436.53 | 425.81 | 100 | 65
1331 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u , SM/09939 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XI (Chandmari) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 14) | 466/NAD-I | 10/03/2022 | 60 | CALCON CONSTRUCTION | 91.89 | 87.21 | 100 | 100
1332 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u , SM/09939 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XII (Madanpur) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 464/NAD-I | 10/03/2022 | 60 | H I ENTERPRISE | 93.56 | 88.78 | 100 | 100
1333 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u , SM/09939 | Augmentation | Repair of 700 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Chandmari Zone-XI under Surface W/S Scheme of Haringhata-Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte | 3154 / NAD-I | 25/11/2022 | 60 | NEERMAN | 25.87 | 25.78 | 99.67 | 99
1334 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u , SM/09939 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XII at Madanpur I & II G.P at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-XII, Madanpur,Part-III under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 12) | 34/NAD-I | 17/01/2023 | 60 | CHOWDHURY & CO. | 96.1 | 96.09 | 99.99 | 90
1335 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u , SM/09939 | Augmentation | Repair of 410 cum Over Head Reservoir (Two Nos) Painting and repairing of H/W Boundary Wall, Pump House at Madanpur Zone-XII under Surface W/S Scheme Haringhata-Chakdah (Part) under Nadia Arsenic Division-I PHE Dte. (Sl.no.04) | 1692 / NAD-I | 08/09/2022 | 45 | CHOWDHURY & CO. | 36.08 | 36.01 | 100 | 100
1336 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u , SM/09939 | Augmentation | Augmentation work for Zone-XII (Madanpur) at Madanpur G.P at Chakdah block under Jal Jeevan Mission (JJM) by Augmentation of Surface Water Based PWSS for Haringhata-Chakdah (Part) for Zone-XII (Madanpur) Part-III under Nadia Arsenic Division-I, PHE Dte. (SL no-01) | 37/AE-I/NAD-I | 07/01/2023 | 15 | BUDDHADEV MONDAL | 4.84 | 4.84 | 100 | 100
1337 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u , SM/09939 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission for Madanpur at Madanpur-I G.P by retrofitting of Surface Water based Piped Water Supply Scheme for Haringhata- Chakdah(Part) in connection with retrofitting work ofZone-X (Subarnapur),Part-II under Nadia Arsenic Division-I, PHE Dte. (sl.13) | 1158 / NAD-I | 28/04/2023 | 21 | CHOWDHURY & CO. | 92.76 | 34.46 | 100 | 100
1338 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u , SM/09939 | Augmentation | Jackpushing of Clear Water Rising Main at Majher Char Crossing at WBHDCL Road and other allied works under Jal Jeevan Mission (JJM) for Zone-X, (Subarnapur) at Subarnapur Mouza at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-X, (Subarnapur) Part-II under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 03) | 1702/NAD-I | 13/07/2023 | 21 | M/S DIPAK ENTERPRISE | 89.84 | 28.74 | 100 | 100
1339 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u , SM/09939 | Augmentation | Water Supply Arrangement in High School, PrimarySchool, SSk & MSK under Jal Jeevan Mission (JJM) atHaringhata Block under Zone-IX (Chandmari) underAugmentation of Zone-IV (Chandmari) & Zone-XIIMadanpur, Part-III at Surface Water Based Water Suupply Scheme of Haringhata & Chakdah (Part)Water Supply Scheme of Haringhata & Chakdah (Part)under Nadia Arsenic Division-I, PHE Dte. (SL.NO.05) | 178/ NAD-I | 09/02/2023 | 21 | M/S KALIMATA ENTERPRISE | 20.46 | 18.1 | 100 | 100
1340 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u , SM/09939 | Augmentation | Grouting and Renovation of 700 cum capacity OverHead Reservoir at Chandmari,Zone-IX under Surface water supply scheme of Haringhata-Chakdah(Part) under Nadia Arsenic Division - I P. H.E. Dte (Sl. NO. 01) | 469/AE-I/NAD-I | 09/10/2023 | 30 | NEERMAN | 4.79 | 4.79 | 100 | 100
1341 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u , SM/09939 | Augmentation | Providing domestic Water Supply to the 36 nos. temporary dwelling units constructed near Buddha Park, Kalyani for rehabilitation of families of Majher Char area including W/S at Sahidpally and Majherchar at Kanchrapara GP at Kalyani block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) W/S Scheme for Zone-XI Chandmari under Nadia Arsenic Division-I, PHE Dte. (Sl.no.02) | 2300/NAD-I | 29/09/2023 | 21 | M/S DIPAK ENTERPRISE | 12.7 | 12.59 | 100 | 100
1342 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u , SM/09939 | Augmentation | Road Restoration under for Madanpur-I and Madanpur-II GP at Kalyani Block under providing FHTC (Functional Household Tap Connection) under Jaldhara/Jalswapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water Based PWSS for Haringhata & Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 06) | 166/NAD-I | 29/04/2025 | 30 | MANAJIT BISWAS | 31.06 | 0 | 0 | 100
1343 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/C (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11831 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 2C of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 119/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.38 | 3.34 | 100 | 100
1344 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/C (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11831 | Augmentation | Material Requisition To Resource Division | 102/ND | 05/01/2023 | 0 | Resource Division | 61.79 | 0 | 0 | 0
1345 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/C (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11831 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 410.91 | 90.41 | 47
1346 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11843 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 5A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 145/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.63 | 4.61 | 100 | 100
1347 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11843 | Augmentation | Material Requisition To Resource Division | 121/ND | 05/01/2023 | 0 | Resource Division | 82.72 | 0 | 0 | 0
1348 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11843 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
1349 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11843 | Augmentation | Material Requisition To Resource Division | 238/ND | 11/01/2024 | 0 | Resource Division | 30.56 | 0 | 0 | 0
1350 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11843 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- V/A (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4526/ND | 04/10/2023 | 626 | MONDAL ENTERPRISE | 614.58 | 270.79 | 44.06 | 25
1351 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11843 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 273 cum. for Surface Water Based Piped Water Supply Scheme for Zone- V/ A (NORTHERN SECTOR, PART-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, PHE Dte. | 4738/ND | 13/10/2023 | 60 | BIDYUT KUMAR | 14.83 | 13.6 | 91.71 | 20
1352 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11843 | Augmentation | Construction of OHR, chlorine room, service road, repairing of boundary wall, store room, and restoration of bituminous road, land improvement etc. of Surface Water Based Water Supply Scheme for Zone- V / A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11843]. | 5468/ND | 08/12/2023 | 711 | MINTU CHAKRABORTY | 244.4 | 55.89 | 22.87 | 5
1353 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11843 | Augmentation | Reconstruction of Boundary wall, Staff room, Chlorination room, Godown etc. of Surface Water Based Water Supply Scheme for Zone-V/A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, P.H.E. Dte. | 89/ND | 07/01/2025 | 90 | MINTU CHAKRABORTY | 51.27 | 0 | 0 | 5
1354 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11843 | Augmentation | Allied protection work and pipe crossing work at Jagadanandapur Mouza under Northern Sector Part-II under Nakashipara Block of Nadia District. | 1644/ND | 07/04/2025 | 60 | MONDAL ENTERPRISE | 18.05 | 0 | 0 | 1
1355 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11843 | Augmentation | Additional Work for Installation of SCADA System in connection with Augmentation of Surface Water Based Piped Water Supply Scheme for Northern Sector Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 3447/ND | 23/07/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 732.35 | 0 | 0 | 15
1356 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
1357 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
1358 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | Construction of Boundary Wall with grill gate at Head Work site of Maniknagar Water Supply Scheme Santipur Block under Nadia Arsenic Civil Division - II P.H.E. Dte. | 81/NACD-II | 09/01/2023 | 60 | SURAJIT KUMAR GHOSH | 14.21 | 11.13 | 78.32 | 80
1359 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement for Tube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Maniknagar water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | 17/AE-I/NACD-II | 13/04/2022 | 60 | NISHITH BANERJEE | 2.83 | 2.6 | 100 | 100
1360 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Maniknagar water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 204/NACD-II | 05/04/2022 | 60 | NISHITH BANERJEE | 5.37 | 5.35 | 100 | 100
1361 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Paninala and Maniknagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 432/NACD-II | 07/07/2022 | 60 | JOY HIND TUBEWELLS | 43.35 | 19.15 | 100 | 100
1362 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | Earth work in filling in ditches at Maniknagar H/W Site for development of land in connection with proposed T/W Sinking & Pump House construction at Maniknagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 466/NACD-II | 20/07/2022 | 20 | SAHA ENGINEERS | 7.48 | 7.47 | 100 | 100
1363 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | Construction of Boundary Wall with grill gate at 2nd Tube well site of Maniknagar W/s Scheme of Santipur Block under Nadia Arsenic Civil Division - II P.H.E. Dte., Dist - Nadia. | 119/NACD-II | 11/01/2023 | 60 | SAHA CONSTRUCTION & GENERAL ORDER SUPPLIERS | 4.39 | 4.32 | 100 | 85
1364 | NADIA | Eastern Mechanical | Manik Nagar Piped W/S Scheme , SM/10407 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) & II under Maniknagar W/S Scheme (Block : Shantipur) Dist.- Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 05) | 1124/EMD | 16/03/2023 | 30 | NITESH MANAGEMENT | 18.84 | 18.83 | 100 | 90
1365 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Santipur Block of Nadia District through Jadavpur University. (Name of PWSS: Maniknagar) | 858/NACD-II | 08/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
1366 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Maniknagar Water Supply Scheme of Santipur Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 624/NACD-II | 06/09/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.85 | 3.85 | 100 | 100
1367 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | Material Requisition To Resource Division | 403/NACD-II | 04/07/2022 | 0 | Resource Division | 39.71 | 0 | 0 | 0
1368 | NADIA | Eastern Mechanical | Manik Nagar Piped W/S Scheme , SM/10407 | New | Electric Bill payment of WBSEDCL for the month of january 2023 | BP-132-22-23 | 31/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.38 | 0 | 0 | 0
1369 | NADIA | Eastern Mechanical | Manik Nagar Piped W/S Scheme , SM/10407 | New | Electric Bill payment of WBSEDCL for the month of january 2023 | BP-133-22-23 | 31/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.24 | 0 | 0 | 0
1370 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | Laying of Rising Main of Maniknagar Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | 27/AE-I/NACD-II | 13/04/2022 | 60 | BIDYUT KUMAR | 4.69 | 4.65 | 100 | 100
1371 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | Construction of approch road at Head Works site of Maniknagar Water Supply Scheme in Shantipur Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | 414/AE-I/NACD-II | 08/08/2023 | 15 | JOY HIND TUBEWELLS | 0.96 | 0.94 | 100 | 100
1372 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Maniknagar and adjoining mouzas under Maniknagar Water Supply Scheme of Santipur Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | 336/NACD-II | 02/06/2022 | 90 | M/S ROY CHOWDHURY & CO. | 107.96 | 91.85 | 90.81 | 100
1373 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | Providing Functional House Hold Tap Connection for Swajal village at Mahatopara of Maniknagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 752/AE-I/NACD-II | 19/06/2024 | 15 | S.M. ENTERPRISE | 0.91 | 0.87 | 100 | 100
1374 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | Providing Functional House Hold Tap Connection for Swajal village at Kapalipara of Maniknagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 753/AE-I/NACD-II | 19/06/2024 | 15 | ACHARJEE & ASSOCIATES | 0.91 | 0 | 0 | 100
1375 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | Acceptance cum work order "Construction of 35 m3/hr capacity IEP at Maniknagar PWSS in Shantipur Block under Nadia Arsenic Civil Division-II,P.H.E. Dte." | 314/NACD-II | 01/03/2024 | 306 | PRITI ENTERPRISE | 19.86 | 8.5 | 42.8 | 80
1376 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | Laying of D.I. pipeline with allied works at Maniknagar Piped Water Supply Scheme in Shantipur Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 42_AE-I/NACD-II | 29/04/2025 | 90 | SURAJIT KUMAR GHOSH | 0.96 | 0 | 0 | 100
1377 | NADIA | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme , SM/10407 | New | Construction of 250 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Maniknagar water supply scheme of Sanitpur Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | 1138/NACD-II | 16/12/2022 | 720 | JOY HIND TUBEWELLS | 95.18 | 82.98 | 87.19 | 100
1378 | NADIA | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME , SM/12419 | New | Material Requisition To Resource Division | 1087/NACD-II | 09/12/2022 | 0 | Resource Division | 0.44 | 0 | 0 | 0
1379 | NADIA | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME , SM/12419 | New | Sinking of 2 nos. 200 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (200 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Chakdignagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 1131/NACD-II | 16/12/2022 | 30 | JOY HIND TUBEWELLS | 20.39 | 19.8 | 100 | 100
1380 | NADIA | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME , SM/12419 | New | Material Requisition To Resource Division | 380/NACD-II | 24/03/2023 | 0 | Resource Division | 2.85 | 0 | 0 | 0
1381 | NADIA | Eastern Mechanical | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME , SM/12419 | New | NEW SERVICE CONNECTION CHARGES FOR WBSEDCL UNDER CHAKDINAGAR PHE-II P.O. KALIRHAT | BP-149-23-24 | 24/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.95 | 0 | 0 | 0
1382 | NADIA | Eastern Mechanical | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME , SM/12419 | New | New service connection for Chakdinagar PH-I P.O.- Kalirhat | BP-248-23-24 | 20/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.87 | 0 | 0 | 0
1383 | NADIA | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME , SM/12419 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL | 235/4 | 21/02/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0 | 0
1384 | NADIA | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME , SM/12419 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. | 23 | 19/04/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
1385 | NADIA | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME , SM/12419 | New | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Chakdignagar water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia | 94/NACD-II | 22/01/2024 | 360 | ZOOM CONSTRUCTION & INTERIO | 20.02 | 7.32 | 36.57 | 90
1386 | NADIA | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME , SM/12419 | New | Acceptance cum work order "Construction of 30 m3/hr capacity IEP at Chakdignagar PWSS in Krishnanagar-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte." | 338/NACD-II | 05/03/2024 | 61 | GHOSH & CO. | 19.79 | 0 | 0 | 0
1387 | NADIA | Eastern Mechanical | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME , SM/12419 | New | Supply, delivery, installation and commissioning of electro-mechanical accessories in connection with installation of Clear Water Pumping machinery in Chakdignagar PWSS, Block- Krishnagar-I, District- Nadia. Under EMD PHE Dte | 810./EMD | 11/03/2024 | 30 | M/S. G.P. ENTERPRISE | 9.66 | 0 | 0 | 0
1388 | NADIA | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME , SM/12419 | New | Additional instrumentation with augmentation of backwashing system with appropriate wattage including recirculation in compliance with 12699: 1989 as well as reaffirmation there into for contamination removal of various valent systems at Chakdignagar Piped Water Supply Scheme in Krishnagar-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 1512/NACD-II | 25/11/2024 | 30 | SANDIP BISWAS | 20.55 | 0 | 0 | 0
1389 | NADIA | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME , SM/12419 | New | Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Chakdignagar water supply scheme under Krishnanagar- I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia. | 1252/NACD-II | 08/11/2023 | 45 | SHYAM SUNDAR SAHA | 26.42 | 25.76 | 100 | 100
1390 | NADIA | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME , SM/12419 | New | Providing 1 no. Guard at Chakdignagar Head work Water Supply Scheme for guarding of various Departmental materials under Nadia Arsenic Civil Division-II,P.H.E. Dte.[Period of work :01/02/2024 to 31/05/2024] | 600/AE-I/NACD-II | 31/01/2024 | 121 | M/S S.K. CONSTRUCTION | 0.96 | 0.69 | 100 | 100
1391 | NADIA | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME , SM/12419 | New | Material Requisition To Resource Division | 78/NACD-II | 15/01/2024 | 0 | Resource Division | 2.85 | 0 | 0 | 0
1392 | NADIA | Eastern Mechanical | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME , SM/12419 | New | Load enhancement charges and security deposit for Chakdignagar PWSS PH-II | BP-173-24-25 | 05/12/2024 | 0 | W.B.S.E.D.C.L (GROUP KRISHNAGAR ROAD STATION C.C.C) | 3.06 | 0 | 0 | 0
1393 | NADIA | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME , SM/12419 | New | Provisioning of automation as well as adsorption technology with augmentation of backwashing system with appropriate wattage including recirculation in compliance with 12699: 1989 as well as reaffirmation there into for contamination removal of various valent systems at Chak Dignagar corresponding Piped Water Supply Scheme in Krishnagar I Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 41/NACD-II | 10/01/2025 | 30 | SANDIP BISWAS | 39.26 | 0 | 0 | 0
1394 | NADIA | Eastern Mechanical | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME , SM/12419 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Chakdignagar ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. WBPHED/EE/EMD/NIeT-37 of 2023-24 (Sl. No. 7) | 948/EMD | 18/03/2024 | 410 | KARTICK BAL | 22.35 | 0 | 0 | 90
1395 | NADIA | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME , SM/12419 | New | Laying of Distraibution system including providing Functional House Hold Tap Connection (FHTC) for Chakdignagar and adjoining mouzas under Chakdignagar W/s Scheme of Krishnagar-I Block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist-Nadia. | 152/NACD-II | 17/01/2023 | 960 | JOY GOPAL GUPTI | 36.69 | 29.93 | 81.84 | 100
1396 | NADIA | Nadia Arsenic Division I | Ground Water Based Piped Water Supply Scheme for BAGANCHARA to accommodate FHTC in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. , SM/12018 | Augmentation | Route Survey for providing FHTC (Functional Household Tap Connection) under JJM (Jal Jeevan Mission) by Augmentation of Baganchra under Ground Water Based PWSS for Baganchra Water Supply Scheme at Santipur Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | 221/AE-I/NAD-I | 02/09/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 4.78 | 4.78 | 100 | 100
1397 | NADIA | Nadia Arsenic Division I | Ground Water Based Piped Water Supply Scheme for BAGANCHARA to accommodate FHTC in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. , SM/12018 | Augmentation | Structural stability report for repair/reconstruction of existing overhead reservoir at Baganchara Water Supply Scheme. | 379/PFMS | 06/12/2023 | 0 | JADAVPUR UNIVERSITY | 1.77 | 0 | 0 | 0
1398 | NADIA | Nadia Arsenic Division I | Ground Water Based Piped Water Supply Scheme for BAGANCHARA to accommodate FHTC in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. , SM/12018 | Augmentation | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE(PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete with Laying of Distribution System Including Specials, Valves & Pipe Supporting Structure, Construction of Boundary Wall, Chlorine Room, and Approach Road (60.0m Length and 3.0m Wide) and Toilet at Head Work Site and 2nd T/W Site and Repair of 450 cum capacity Over Head Reservoir, Painting and Pump House at Ground Water Based Piped Water Supply Scheme for Baganchara in Santipur Block of Nadia District under Nadia Arsenic Division-I, PHE Dte. (Sl.no.04) | 1896/NAD-I | 14/08/2023 | 731 | KINGS AND CO | 706.54 | 214.43 | 30.35 | 22
1399 | NADIA | Nadia Arsenic Division I | Ground Water Based Piped Water Supply Scheme for BAGANCHARA to accommodate FHTC in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. , SM/12018 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site for Baganchara Piped Water Supply Schemes under Nadia Arsenic Division-I, PHE Dte. | 1314/NAD-I | 22/08/2024 | 60 | K K MARKETING | 13.01 | 0 | 0 | 0
1400 | NADIA | Nadia Arsenic Division I | Ground Water Based Piped Water Supply Scheme for BAGANCHARA to accommodate FHTC in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. , SM/12018 | Augmentation | Surging of existing Tube Well Situated at Head Site of Baganchara Water Supply Scheme in connection with Jal Jeevan Mission under Santipur Block to increase the yield of the tube well under Nadia Arsenic Division-I, P.H.E. Dte. | 69/AE-I/NAD-I | 12/02/2024 | 15 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 0.64 | 0.64 | 100 | 100
1401 | NADIA | Nadia Arsenic Division I | Ground Water Based Piped Water Supply Scheme for BAGANCHARA to accommodate FHTC in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. , SM/12018 | Augmentation | Material Requisition To Resource Division | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 30.8 | 0 | 0 | 0
1402 | NADIA | Nadia Arsenic Division I | Ground Water Based Piped Water Supply Scheme for BAGANCHARA to accommodate FHTC in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. , SM/12018 | Augmentation | Construction of AIRP capacity (111m3/hr) in connection with augmentation of Ground Water Based PWSS for Baganchara under Jal Jeevan Mission at Santipur Block under Nadia Arsenic Division-I, PHE Dte. | 1079/NAD-I | 15/07/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 278.95 | 0 | 0 | 65
1403 | NADIA | Nadia Arsenic Division I | Ground Water Based Piped Water Supply Scheme for BAGANCHARA to accommodate FHTC in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. , SM/12018 | Augmentation | DI Rising main line at Baganchara PWSS under Santipur Block in connection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. | 232/AE-I/NAD-I | 25/07/2024 | 623 | MANARAMA ENTERPRISE | 3.96 | 0 | 0 | 85
1404 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muragachha Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Divisi , SM/11640 | Augmentation | Construction of AIRP capacity (104m3/hr) in connection with augmentation of Ground Water Based PWSS for Chupria Zone-I under Jal Jeevan Mission at Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. | 1118/NAD-I | 19/07/2024 | 180 | HARBAUER INDIA PRIVATE LIMITED | 265.04 | 0 | 0 | 0
1405 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muragachha Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Divisi , SM/11640 | Augmentation | Repair of damages pipeline and other allied work at 2nd site of Muragachha Zone-I, water supply scheme, Block- Hanskhali under Nadia Arsenic Division-I, P.H.E. Dte. | 497/AE-I/NAD-I | 31/10/2023 | 7 | DAYANIDHI CONSTRUCTIONS | 0.97 | 0.74 | 100 | 100
1406 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muragachha Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Divisi , SM/11640 | Augmentation | Repair of damages pipeline and other allied work at 2nd site of Muragachha Zone-II, water supply scheme, Block- Hanskhali under Nadia Arsenic Division-I, P.H.E. Dte. | 498/AE-I/NAD-I | 31/10/2023 | 7 | M/S T.S. ENTERPRISE | 0.95 | 0.66 | 100 | 100
1407 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muragachha Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Divisi , SM/11640 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Muragachha Zone-II Ground Based Water Supply Scheme under Hanskhali Block under Nadia Arsenic Division-I,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Muragachha Zone-I & Zone-II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Schemes under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 04) | 1135/NAD-I | 24/07/2024 | 60 | GHOSH & CO | 17.57 | 17.5 | 100 | 100
1408 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muragachha Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Divisi , SM/11640 | Augmentation | Augmentation of Muragaccha Zone - I PWSS by providing dedicated pipeline under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission.(Sl. No. 06) | 2040/NAD-I | 06/12/2024 | 146 | MESSRS FREEDOM CONSTRUCTION | 95.13 | 0 | 0 | 0
1409 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muragachha Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Divisi , SM/11640 | Augmentation | Providing FHTC under Jalswapna / Jaldhara for Muragachha Z-I & II ( Part -III) at Hanskhali Block by Augmentation of Ground Water based pipe PWSS for Muragachha W/S Scheme. under Nadia Arsenic Division -I, P.H.E. Dte. (Sl .no. 06) | 2050 / NAD-I | 21/10/2022 | 831 | MONDAL PRECISION PRIVATE LIMITED | 282.77 | 221.92 | 95.36 | 100
1410 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muragachha Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Divisi , SM/11640 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Murgachha Zone-I Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under 1304536.00 26091.00 Initially Nil, Rs. 1005/- per copy of tender document including 2911(ii) to be purchased by the successful bidder at 15 Days Page 3Muragachha Zone-I & II (Part-III) Piped W/S Scheme (sl.16) | 1160 / NAD-I | 28/04/2023 | 734 | SANJIB DEY | 13.05 | 0 | 0 | 100
1411 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11652 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 9/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 157/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.66 | 4.63 | 100 | 100
1412 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11652 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 700 cum. for Providing FHTC (Functional Household Tap Connection) for Zone IX/A Water Supply Scheme in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 4007/ND | 07/09/2023 | 60 | CHANDAN ROY | 27.44 | 9.67 | 35.22 | 37
1413 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11652 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 1.4 | 98.71 | 40
1414 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11652 | Augmentation | Material Requisition To Resource Division | 248/ND | 11/01/2024 | 0 | Resource Division | 7.22 | 0 | 0 | 0
1415 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11652 | Augmentation | Restoration of Bholadanga welcome gate to Bangoria over Bridge via NH 34 | 302/PFMS | 02/10/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 20.27 | 0 | 0 | 0
1416 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11652 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4588/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 300.51 | 60.72 | 19
1417 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11652 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
1418 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/11546 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Magurkhali W/S Scheme in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte. | 1063/RSD | 02/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.76 | 4.76 | 100 | 100
1419 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/11546 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Magurkhali W/S Scheme (T/W-I), Ranaghat-II Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 901/CDD | 18/07/2023 | 30 | UTTAM KUMAR CHATTERJEE | 18.6 | 0 | 0 | 0
1420 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/11546 | Augmentation | Special repair & renovation of boundary wall & allied works in the premises at pump house no 1of Magurkhali W/S scheme of Ranaghat-II block under Ranaghat Sub-Division, P.H.E. Dte. | 560/RSD | 31/08/2022 | 30 | M/S ARNAB CONSTRUCTION | 4.68 | 3.52 | 100 | 100
1421 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/11546 | Augmentation | Special repair & renovation of boundary wall & allied works in the premises at pump house no 3 of Magurkhali W/S scheme of Ranaghat-II block under Ranaghat Sub-Division, P.H.E. Dte. | 560/A/RSD | 31/08/2022 | 30 | ASOKE KUMAR DUTTA | 4.49 | 2.17 | 100 | 100
1422 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/11546 | Augmentation | Material Requisition To Resource Division | 24/ND | 03/01/2023 | 0 | Resource Division | 24.14 | 0 | 0 | 0
1423 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/11546 | Augmentation | Material Requisition To Resource Division | 2311/ND | 29/05/2023 | 0 | Resource Division | 44.59 | 0 | 0 | 0
1424 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/11546 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MAGURKHALI W/S Scheme, Block- RANAGHAT II , Dist. - Nadia. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 08) | 1580/EMD | 24/04/2023 | 753 | ESENCE ENGINEERING CONCERN | 21.64 | 0 | 0 | 100
1425 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/11546 | Augmentation | Material Requisition To Resource Division | 7560/ND | 27/12/2024 | 0 | Resource Division | 8.2 | 0 | 0 | 0
1426 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/11546 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Magurkhali to accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division P.H.Engineering Dte. | 5355/ND | 22/12/2022 | 1071 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 586.94 | 480.1 | 81.8 | 90
1427 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/11546 | Augmentation | Additional work of Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Magurkhali to accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division P.H.Engineering Dte. | 4344/ND | 07/08/2024 | 419 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 78.93 | 0 | 0 | 60
1428 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/11546 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Magurkhali under Ranaghat Sub-Division under Nadia Division PHE Dte. | 201/RSD | 06/02/2025 | 45 | SAYANTAN PANDEY | 2.15 | 0 | 0 | 100
1429 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/11546 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
1430 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/C(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11551 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 4/C of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. ( Sl.No .10 ) | 212/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.48 | 4.44 | 100 | 100
1431 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/C(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11551 | Augmentation | Material Requisition To Resource Division | 87/ND | 05/01/2023 | 0 | Resource Division | 200.92 | 0 | 0 | 0
1432 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/C(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11551 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | 3537/ND | 11/08/2023 | 782 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 349.83 | 50.57 | 20
1433 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/C(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11551 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 0 | 30
1434 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/C(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11551 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub Division, PHE Dte for supervision of JJM works for the period of 01/01/2025 to 31/12/2025 | 2666/KSD | 31/12/2024 | 365 | AVINABA ENGINEERING CONCERN | 4.8 | 0 | 0 | 0
1435 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/C(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11551 | Augmentation | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3829/ND | 13/08/2025 | 120 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0 | 0
1436 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12373 | Augmentation | Material Requisition To Resource Division | 98/ND | 05/01/2023 | 0 | Resource Division | 149.04 | 0 | 0 | 0
1437 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12373 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
1438 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12373 | Augmentation | Material Requisition To Resource Division | 237/ND | 11/01/2024 | 0 | Resource Division | 23.66 | 0 | 0 | 0
1439 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12373 | Augmentation | Restoration work of road damage due to laying pipe line under ¿NJJM¿ Project in Nakashipara Block of Nadia District under Nadia Division, PHE Dept. of Arbetai ¿ Sahapara Road from 9.80 kmp to 11.88 kmp of Krishnagar Sub-Division-I under Nadia Highway Division-I in the district Nadia during the year 2024-2025. |  | 26/07/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 12.59 | 0 | 0 | 0
1440 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12373 | Augmentation | RESTORATION OF ROAD FLANK OF ARBETAI SAHAPARA ROAD FROM CH. 0.00 KM TO 9.80 KMP. | 601/PFMS | 14/03/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 28.69 | 0 | 0 | 0
1441 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12373 | Augmentation | Restoration work of road damage due to laying pipe line under ¿NJJM¿ Project in Nakashipara Block of Nadia District under Nadia Division, PHE Dept. of Arbetai ¿ Sahapara Road from 9.80 kmp to 11.88 kmp of Krishnagar Sub-Division-I under Nadia Highway Division-I in the district Nadia during the year 2024-2025. | 148/PFMS | 28/08/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 6.3 | 0 | 0 | 0
1442 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12373 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- V/C (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4528/ND | 04/10/2023 | 716 | M/S DIPAK ENTERPRISE | 645.85 | 386.75 | 59.88 | 50
1443 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12373 | Augmentation | Construction of OHR, staff room, chlorine room, service road and restoration of bituminous road, land improvement etc. of Surface Water Based Water Supply Scheme for Zone-V / C (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/12373]. | 148/ND | 09/01/2024 | 729 | MINTU CHAKRABORTY | 252.66 | 0 | 0 | 10
1444 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12373 | Augmentation | Additional Work for Installation of SCADA System in connection with Augmentation of Surface Water Based Piped Water Supply Scheme for Northern Sector Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 3447/ND | 23/07/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 732.35 | 0 | 0 | 15
1445 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11650 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 8A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 130/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.26 | 4.16 | 100 | 100
1446 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11650 | Augmentation | Material Requisition To Resource Division | 107/ND | 05/01/2023 | 0 | Resource Division | 128.41 | 0 | 0 | 0
1447 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11650 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 346.75 | 76.83 | 47
1448 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11839 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 3/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 141/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.35 | 3.34 | 100 | 100
1449 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11839 | Augmentation | Material Requisition To Resource Division | 95/ND | 05/01/2023 | 0 | Resource Division | 59.33 | 0 | 0 | 0
1450 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11839 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 1.4 | 98.71 | 40
1451 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11839 | Augmentation | Material Requisition To Resource Division | 231/ND | 11/01/2024 | 0 | Resource Division | 2.04 | 0 | 0 | 0
1452 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11839 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4588/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 141.2 | 68.92 | 19
1453 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11839 | Augmentation | Construction of OHR, repair and renovation of staff room, repair of boundary wall, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-III / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11839]. | 6112/ND | 21/12/2023 | 730 | MONDAL ENTERPRISE | 201.12 | 0 | 0 | 5
1454 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11839 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
1455 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11839 | Augmentation | Construction of Bituminous Approch Road for GLR site at Surface water based water supply Scheme under Northern Sector Part II at Nakashipara Block under Nadia Division PHE Dte. | 3260/ND | 10/07/2025 | 90 | GBC INFRASTRUCTURE PRIVATE LIMITED | 95.58 | 0 | 0 | 5
1456 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(A) PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11871 | Augmentation | Material Requisition To Resource Division | 142/ND | 06/01/2023 | 0 | Resource Division | 27.61 | 0 | 0 | 0
1457 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(A) PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11871 | Augmentation | Material Requisition To Resource Division | 1852/ND | 26/04/2023 | 0 | Resource Division | 22.01 | 0 | 0 | 0
1458 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(A) PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11871 | Augmentation | Material Requisition To Resource Division | 2324/ND | 29/05/2023 | 0 | Resource Division | 0.92 | 0 | 0 | 0
1459 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(A) PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11871 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed Augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone X-A to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 254/ND | 16/01/2023 | 720 | SANJUKTA ENGINEERS | 157.12 | 23.02 | 100 | 98
1460 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(A) PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11871 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Karimpur Jalangi Zone-X (A) Ground Based Water Supply Scheme under Karimpur-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Karimpur Jalangi Zone-X (A) at Karimpur-II Block by Augmentation of Ground Water based PWSS for Karimpur Jalangi Zone-X (A) Water Supply Schemes under Nadia Division, PHE Dte. | 418/ND | 27/01/2025 | 300 | S.B.CONSTRUCTION | 23.54 | 0 | 0 | 50
1461 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11810 | Augmentation | Additional Route Survey, Design Drawing & DPR Preparation for ZONE 5B-A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 147/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 0.84 | 0.78 | 100 | 100
1462 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11810 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 5B-B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 148/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.04 | 4.04 | 100 | 100
1463 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11810 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 5B-A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 146/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.91 | 4.75 | 100 | 100
1464 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11810 | Augmentation | Material Requisition To Resource Division | 119/ND | 05/01/2023 | 0 | Resource Division | 253.22 | 0 | 0 | 0
1465 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11810 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
1466 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11810 | Augmentation | Construction of Additional Boundary Wall ( 85.00 m Length ), Service Road and other related work for 1000 cum RCC elevated reservior of Surface Water Based Water Supply Scheme for Zone-V/B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. | 7246/ND | 12/12/2024 | 60 | U-TURN CONSTRUCTION | 17.16 | 0 | 0 | 0
1467 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11810 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 1000 m3. for Surface Water Based Piped Water Supply Scheme for Zone- V/ B (NORTHERN SECTOR, PART-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, PHE Dte. | 4739/ND | 13/10/2023 | 60 | U-TURN CONSTRUCTION | 35.83 | 29.88 | 100 | 65
1468 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11810 | Augmentation | Reconstruction of Top Dome and other related work for 273 cum RCC elevated reservoir of Surface Water Based Water Supply Scheme for Zone-V /A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, P.H.E. Dte. | 6098/ND | 19/09/2024 | 90 | BIDYUT KUMAR | 13.22 | 0 | 0 | 10
1469 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11810 | Augmentation | Material Requisition To Resource Division | 236/ND | 11/01/2024 | 0 | Resource Division | 19.68 | 0 | 0 | 0
1470 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11810 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- V/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4527/ND | 04/10/2023 | 782 | KINGS & CO. | 672.01 | 326.05 | 48.52 | 25
1471 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11810 | Augmentation | Jack pushing & pipe crossing work at Jugpur Mouza under Northern Sector Part-II under Nakashipara Block of Nadia District. | 1645/ND | 07/04/2025 | 90 | MONDAL ENTERPRISE | 95.97 | 0 | 0 | 1
1472 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11810 | Augmentation | Construction of Bituminous Approch Road for GLR site at Surface water based water supply Scheme under Northern Sector Part II at Nakashipara Block under Nadia Division PHE Dte. | 3260/ND | 10/07/2025 | 90 | GBC INFRASTRUCTURE PRIVATE LIMITED | 95.58 | 0 | 0 | 5
1473 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11810 | Augmentation | Additional Work for Installation of SCADA System in connection with Augmentation of Surface Water Based Piped Water Supply Scheme for Northern Sector Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 3447/ND | 23/07/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 732.35 | 0 | 0 | 15
1474 | NADIA | Nadia Division | Indrakpur Piped Water Supply Scheme. , SM/13820 | New | Continuation of Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 90 days w.e.f. 01/10/2023 (as and when required) | 1450/KSD | 18/09/2023 | 90 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 0
1475 | NADIA | Nadia Division | Indrakpur Piped Water Supply Scheme. , SM/13820 | New | Sinking of 2 nos. Tubewell 300mm. x 200mm. dia 200 mtr deep by direct rotary rig method at headwork and 2nd tube well site for Indrakpur water supply scheme under Krishnagar Sub-Division under Nadia Division, PHE DTe. (SM/13820) | 2104/ND | 15/05/2023 | 60 | AUXILIARY TUBEWELL DRILLERS | 32.6 | 24.86 | 100 | 70
1476 | NADIA | Nadia Division | Indrakpur Piped Water Supply Scheme. , SM/13820 | New | Material Requisition To Resource Division | 1854/ND | 26/04/2023 | 0 | Resource Division | 15.8 | 0 | 0 | 0
1477 | NADIA | Eastern Mechanical | Indrakpur Piped Water Supply Scheme. , SM/13820 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Indrakpur ground water based water supply scheme under Block_ Nabadwip Dist. - Nadia under EMD, PHE Dte. | 6968/EMD | 15/12/2023 | 91 | S.G. TECHNICAL SERVICES | 28.7 | 6.88 | 23.97 | 95
1478 | NADIA | Nadia Division | Indrakpur Piped Water Supply Scheme. , SM/13820 | New | Collection of Household data through mobile app for FHTC Connection of Ground Water Based Indrakpur, Gadigachha, Karimpur-Jalangi (Zone-VI), Sandha, Udaypur PWSS, Mini PWSS at Gazna (Part) and Surface Based PWSS for Northern Sector (Part-I) (Zone-IA) under Nadia Division, P.H.E. Dte. | 984/KLYSD-I | 11/09/2023 | 90 | TECHVISION | 4.85 | 4.85 | 100 | 100
1479 | NADIA | Nadia Division | Indrakpur Piped Water Supply Scheme. , SM/13820 | New | Survey, Design and Preparation of DPR in connection with Indrakpur piped water supply scheme in Nabadwip Block under Krishnanagar Sub Division under Nadia Division, PHE Dte | 49/KSD | 15/01/2024 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.82 | 2.79 | 100 | 80
1480 | NADIA | Nadia Division | Indrakpur Piped Water Supply Scheme. , SM/13820 | New | Material Requisition To Resource Division | 269/ND | 11/01/2024 | 0 | Resource Division | 5.7 | 0 | 0 | 0
1481 | NADIA | Eastern Mechanical | Indrakpur Piped Water Supply Scheme. , SM/13820 | New | Supplementary quotation for revised estimate due to row issue I.F.O. PHE Dte. for 3PH NSC to pump house-II at Indrakpur | BP-119-24-25 | 20/09/2024 | 0 | WBSEDCL NABADWIP CCC | 1.91 | 0 | 0 | 0
1482 | NADIA | Nadia Division | Indrakpur Piped Water Supply Scheme. , SM/13820 | New | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | 3784/ND | 12/08/2025 | 31 | IMAGIN | 34.21 | 0 | 0 | 0
1483 | NADIA | Nadia Division | Indrakpur Piped Water Supply Scheme. , SM/13820 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 30 m3/hr at Indrakpur Water Supply Scheme within Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | 6735/ND | 05/11/2024 | 360 | B.M. ENGINEERING & CONSTRUCTION | 159.53 | 0 | 0 | 5
1484 | NADIA | Nadia Division | Indrakpur Piped Water Supply Scheme. , SM/13820 | New | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
1485 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshin Jhikipota Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08056 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Dakshin Jhitkipota Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | 2051/ND | 13/05/2021 | 60 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 41.49 | 30.78 | 100 | 100
1486 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshin Jhikipota Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08056 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Dakshin Jhitkipota Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | 2049/ND | 13/05/2021 | 60 | S.K. CONSTRUCTION | 43.81 | 34.72 | 100 | 100
1487 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshin Jhikipota Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08056 | Retrofitting | laying of distribution pipe line 125 mm dia UPVC pipe etc. for Providing functional household tap connection at Dakhin Jhitkipota zone- I W/S scheme under Nadia Division PHED. | 214/PH | 12/07/2022 | 30 | TAPU SAHA | 4.2 | 4.2 | 100 | 100
1488 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshin Jhikipota Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08056 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Dakshin Jhitkipota Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | 2912/ND | 23/07/2021 | 45 | PAPAN ROY | 8.8 | 7.12 | 80.95 | 100
1489 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobindapur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. , SM/15550 | Augmentation | "Retrofitting work at villages Batangachi, Barajiakur and Bagdiain connection with Retrofitting of Ground Water Based PWSS for Goibindapur Zone-II at Santipur Block under Nadia Arsenic Division-I,PHE Dte."(Sl.no.02) | 1380/NAD-I | 15/05/2023 | 1430 | SAHA ENGINEERS | 60.15 | 0 | 0 | 26
1490 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobindapur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. , SM/15550 | Augmentation | Providing Boundary Illumination with allied works at Gobindapur Zone-II Part-II under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15550) | 1152/EMD | 04/06/2025 | 90 | M/S DAS ENTERPRISE | 4.34 | 0 | 0 | 0
1491 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GAZNA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15539 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augomentation in connection to Accommodate FHTC at Pump House No.-I/II under Gazna ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. | 1306/EMD | 09/05/2024 | 30 | RAJ & ENTERPRISE | 7.67 | 7.66 | 100 | 100
1492 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GAZNA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15539 | Augmentation | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | 6290/ND | 26/09/2024 | 45 | IMAGIN | 19.44 | 0 | 0 | 100
1493 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GAZNA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15539 | Augmentation | New single phase service connection at Gazna (Part) water supply scheme at Hanskhali block, Dist.-Nadia | BP-21-24-25 | 21/05/2024 | 0 | W.B.S.E.D.C.LTD (BAGULA C.C.C) | 0.26 | 0 | 0 | 0
1494 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GAZNA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15539 | Augmentation | Replacemt of damaged & typically choked UPVC pipe line for augmentation of Ground Water Based Water Supply Scheme for Gazna PWSS of Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. (Balance) A- Part. | 4802/ND | 17/10/2023 | 90 | SANDIP BISWAS | 99.5 | 0 | 0 | 96
1495 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GAZNA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15539 | Augmentation | Renovation of Semi-Gravity & Semi-Pressure Type AIRP at Gazna Water Supply Scheme of capacity 58.5 Cu.m/hr. | 783/ND | 05/02/2024 | 90 | APURBA MANDAL | 44.96 | 17.72 | 78.81 | 84
1496 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GAZNA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15539 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Gazna ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15539) | 232/EMD | 06/02/2025 | 30 | MAA KALI ENTERPRISE | 11.76 | 0 | 0 | 0
1497 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GAZNA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15539 | Augmentation | Sinking of Rig Bored Tube well (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | 1269/ND | 23/03/2023 | 780 | JOY HIND TUBEWELL'S | 65.37 | 12.87 | 100 | 100
1498 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramnagar Water Supply Scheme, Part-IV under Jal Jeevan Mission(JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte.. , SM/15548 | Augmentation | Augmentation of AIRP capacity (71cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Ramnagar, under Jal Jeevan Mission at Hanskhali Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.10) | 1795/NAD-I | 31/07/2023 | 30 | ASIT PRAMANIK | 93.55 | 0 | 0 | 0
1499 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HUDA CHAPRA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15279 | Augmentation | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | 1270/ND | 23/03/2023 | 60 | AUXILIARY TUBEWELL DRILLERS | 65.32 | 0 | 0 | 0
1500 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HUDA CHAPRA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15279 | Augmentation | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | 6290/ND | 26/09/2024 | 45 | IMAGIN | 19.44 | 0 | 0 | 100
1501 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Goalpur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. , SM/15546 | Augmentation | Augmentation Work at Umapur and Goalpur Mouzas at Santipur Block by Augmentation of Ground Water based PWSS for Goalpur Zone-II, Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Goalpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.04) | 2115/NAD-I | 04/09/2023 | 15 | BUDDHADEV MONDAL | 50.03 | 49.83 | 100 | 100
1502 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Goalpur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. , SM/15546 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Goalpur Zone-II, Ground Based Water Supply Scheme under Santipur under Office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E Dte.in connection with Augmentation under JJM under Goalpur Zone-II, Part-III, Piped Water Supply Scheme (Sl.No.-35) | 1772/NAD-I | 26/07/2023 | 15 | MANISHIKA CONSTRUCTION | 13.04 | 12.83 | 100 | 100
1503 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Goalpur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. , SM/15546 | Augmentation | Interconnection inbetween new pump to rising main line , Pathway & delivery line from manifold to distribution line at Shantipur Block of ground water based PWSS for Goalpur Zone-II water supply scheme in connection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 03) | 450/AE-I/NAD-I | 29/09/2023 | 30 | CONSTRUCTURE | 4.83 | 4.17 | 100 | 100
1504 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Goalpur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. , SM/15546 | Augmentation | Dedicated line at Dhakuria and delivery line from manifold to distribution line at Shantipur Block of ground water based PWSS for Goalpur Zone-I water supply scheme in connection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 04) | 451/AE-I/NAD-I | 29/09/2023 | 30 | M/S G.M ASSOCIATES | 4.82 | 4.81 | 100 | 100
1505 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Goalpur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. , SM/15546 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, Zone-II under Goalpur ground water based water supply scheme under Block_ Santipur Dist. - Nadia under EMD, PHE Dte. | 6392/EMD | 30/10/2023 | 30 | ASHUTOSH DAS & CO. | 11.76 | 10.85 | 100 | 100
1506 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Goalpur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. , SM/15546 | Augmentation | Augmentation of AIRP of Ground Water Based Piped Water Supply Scheme for Goalpur Zone-II, (30 cum/hr) including augmentation of Matikumra Water Supply Scheme under Jal Jeevan Mission (JJM) under Nadia Arsenic Division -I, P.H.E. Dte. | 1882/NAD-I | 11/11/2024 | 180 | BALAJI UDDYOG | 129.1 | 0 | 0 | 0
1507 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Goalpur Zone II Water Supply Scheme, Part-II under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. , SM/15546 | Augmentation | Providing Boundary Illumination with allied works at Goalpur Zone II Part-II under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15546) | 1167/EMD | 04/06/2025 | 90 | SHRESTHA | 4.34 | 0 | 0 | 0
1508 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Nabla Water Supply Scheme, Part-IV under Jal Jeevan Mission(JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. , SM/15547 | Augmentation | Providing Boundary Illumination with allied works at Nabla Part-IV under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15547) | 1156/EMD | 04/06/2025 | 90 | S M ELECTRICALS | 4.34 | 0 | 0 | 0
1509 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Beharia Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15549 | Augmentation | Construction and installation of MANIFOLD andallied works at OHR site under Behria Ground Based Water Supply Scheme under Santipur under Office of Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. in connection with Augmentation under JJM under Beharia Part-III, Piped Water Supply Scheme (Sl.no.33) | 1364/NAD-I | 12/05/2023 | 15 | DEBASISH DEY | 12.2 | 6.27 | 100 | 100
1510 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Beharia Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15549 | Augmentation | Augmentation of AIRP capacity (119cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Beharia, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (sl.no.01) | 1880/NAD-I | 10/08/2023 | 30 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 158.74 | 158.74 | 100 | 100
1511 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR FATEPUR (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15281 | Augmentation | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | 6290/ND | 26/09/2024 | 45 | IMAGIN | 19.44 | 0 | 0 | 100
1512 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR FATEPUR (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15281 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Fatepur PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 45.00 Cu.m/hr. | 839/ND | 06/02/2024 | 455 | ZEOLITE FRESH INDIA | 58.36 | 0 | 0 | 60
1513 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR FATEPUR (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15281 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Fatepur ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15281) | 231/EMD | 06/02/2025 | 237 | RAJ & ENTERPRISE | 11.76 | 0 | 0 | 100
1514 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR FATEPUR (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15281 | Augmentation | Sinking of Rig Bored Tube well (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | 1269/ND | 23/03/2023 | 780 | JOY HIND TUBEWELL'S | 65.37 | 12.97 | 98.73 | 100
1515 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURBA KHAMARSIMULIA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15134 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Purba Khamarsimulia PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 105.00 Cu.m/hr | 136/ND | 09/01/2024 | 90 | M/S R.K.ENTERPRISE | 99.27 | 0 | 0 | 0
1516 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURBA KHAMARSIMULIA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15134 | Augmentation | Supplying and laying of distribution system including providing Functional Household Tap Connection (FHTC) for Augmentation of Purbakhamar Simulia Piped Water Supply Scheme under Ranaghat Sub-Division, under Nadia Division, PHE Dte.. | 5224/ND | 24/11/2023 | 755 | B.M. ENGINEERING & CONSTRUCTION | 215.24 | 28.13 | 82.71 | 75
1517 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURBA KHAMARSIMULIA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15134 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Puba Khamarsimulia ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15134) | 235/EMD | 06/02/2025 | 237 | ANUPAMA ENGINEERING WORKS | 11.76 | 0 | 0 | 100
1518 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURBA KHAMARSIMULIA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15134 | Augmentation | Sinking of Rig Bored Tube well (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | 1269/ND | 23/03/2023 | 780 | JOY HIND TUBEWELL'S | 65.37 | 13.55 | 100 | 100
1519 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MONIPOTA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15135 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BANPUR W/S Scheme, Block- Krishnaganj, ARABPUR W/S Scheme, Block-Karimpur, BHIMPUR W/S Scheme, Block-Krishnagar AND MONIPOTA W/S Scheme, Block- Krishnagar-I, Dist. - Nadia. | 5127/EMD | 04/09/2023 | 666 | C.M.S. ENGINEERING CONCERN. | 70.97 | 0 | 0 | 12
1520 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MONIPOTA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15135 | Augmentation | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Krishnagar-I Block, under Ranaghat Sub-Division, PHE Dte. | 1268/ND | 23/03/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 47.83 | 12.7 | 100 | 45
1521 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MONIPOTA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15135 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Monipota PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 65.00 Cu.m/hr | 135/ND | 09/01/2024 | 360 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 74.19 | 56.25 | 87.15 | 50
1522 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MONIPOTA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15135 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Monipota ground water based water supply scheme under Block_ Krishnanagar_I Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15135) | 234/EMD | 06/02/2025 | 30 | M/S.A.K. BANERJEE. | 11.76 | 0 | 0 | 0
1523 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JOANIA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15138 | Augmentation | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Krishnagar-I Block, under Ranaghat Sub-Division, PHE Dte. | 1268/ND | 23/03/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 47.83 | 15.94 | 100 | 45
1524 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JOANIA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15138 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Joania PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 55.00 Cu.m/hr | 6008/ND | 14/12/2023 | 720 | ASIT PRAMANIK | 64.95 | 8.99 | 13.84 | 80
1525 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JOANIA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15138 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Banpur ground water based water supply scheme under Block_ Krishnaganj Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15280) | 228/EMD | 06/02/2025 | 30 | BINAPANI ENTERPRISE | 11.76 | 0 | 0 | 0
1526 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JOANIA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15138 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Joania ground water based water supply scheme under Block_ Krishnanagar_I Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15138) | 233/EMD | 06/02/2025 | 30 | SHRESTHA | 11.76 | 0 | 0 | 0
1527 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JOANIA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15138 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No.- I AND II under Joania WS Scheme, Block Krishnagar I, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-06) | 157/EMDdt.06.01.2023 | 08/02/2023 | 726 | MASSK ENGINEERING WORKS | 14.9 | 0 | 0 | 100
1528 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II, (Hapania), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divisi , SM/08830 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-II (Hapania) Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 1611/NAD-I | 28/12/2021 | 90 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT LTD. | 404.05 | 389.71 | 100 | 100
1529 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II, (Hapania), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divisi , SM/08830 | Retrofitting | Laying UPVC pipeline at different location of Z-II ( Hapania ) under Nagarukhra -I & II G.P. under Surface Based Haringhata & Chakdah (Part) Surface Water Supply scheme under Nadia Arsenic -I, P.H.E. Dte. (01) | 88 / AE-I/NAD-I | 28/04/2022 | 15 | TARUN KUMAR BHATTACHARYA | 4.84 | 4.8 | 100 | 100
1530 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II, (Hapania), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divisi , SM/08830 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muratipur at Kanchrapara G.P. and Hapania at Nagrukhra-II G.P. by retrofitting of surface water based PWSS Water Supply Scheme for Haringhata-Chakdah (Part) in connection with retrofitting work of Zone-II, Hapania Part-II under Nadia Arsenic Division-I, PHE Dte. (sl.02) | 1255 /NAD-I | 04/05/2023 | 30 | BUDDHADEV MONDAL | 37.15 | 37.14 | 99.97 | 0
1531 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II, (Hapania), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divisi , SM/08830 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-II , Hapania at Nagarukhra G.P at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-II, Hapania, Part-III under Nadia Arsenic Division-I, PHE Dte. (sl. 18) | 303 /NAD-I | 27/02/2023 | 60 | MONDAL ENTERPRISE | 96.62 | 1.43 | 100 | 74
1532 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Muragacha Water Supply Scheme (Zone I & II) In Hanskhali Block District Nadia. , SM/16362 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1533 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Nutangram Water Supply Scheme In Hanskhali Block District Nadia. , SM/16370 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1534 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Purba Khamar Simulia Water Supply Scheme In Hanskhali Block District Nadia. , SM/16372 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1535 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Mobarakpur Water Supply Scheme in Tehatta-I Block, Dist.-Nadia. , SM/16334 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1536 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/10067 | Augmentation | Material Requisition To Resource Division | 4930/ND | 25/11/2022 | 0 | Resource Division | 108.85 | 0 | 0 | 0
1537 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/10067 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | 705/PFMS | 30/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.04 | 0 | 0 | 0
1538 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/10067 | Augmentation | Fencing for Land at Chapra Bangaljhi and Teorkhali Water supply scheme at new 3rd Tube Well site under Krishnagar Sub-Division PHED. | 219/KSD | 03/03/2023 | 15 | SANJIB DEY | 0.45 | 0.22 | 99.96 | 0
1539 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/10067 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for JJM works for the period 90 days w.e.f. 01/04/2023.(as and when required). | 376/KSD | 28/03/2023 | 90 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 0
1540 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/10067 | Augmentation | Material Requisition To Resource Division | 2158/ND | 18/05/2022 | 0 | Resource Division | 107.67 | 0 | 0 | 0
1541 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/10067 | Augmentation | Material Requisition To Resource Division | 1395/ND | 24/03/2022 | 0 | Resource Division | 46.6 | 0 | 0 | 0
1542 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/10067 | Augmentation | Material Requisition To Resource Division | 2326/ND | 29/05/2023 | 0 | Resource Division | 16.29 | 0 | 0 | 0
1543 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/10067 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for ChapraBangaljhi W/S Scheme (T/W-III & IV) , Chapra Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 131/CDD | 17/04/2023 | 503 | PADMA ENGINEERING & CO. | 37.3 | 14.16 | 37.96 | 50
1544 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/10067 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 174 m3/hr at Chapra Bangaljhi Water Supply Scheme within Chapra Block under Krishnagar Sub- Divn. under Nadia Division, P.H.E. Dte. | 1898/ND | 15/03/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 385.52 | 0 | 0 | 0
1545 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/10067 | Augmentation | Construction of Pump House (3.6Mtr. X 3.0 Mtr.) and allied works at 3rd T/W Site at Chapra Bangaljhi Water Supply Scheme Under Krishnagar Sub-dividion Under Nadia Division. | 733/KSD | 07/06/2023 | 60 | BABLU MALLICK | 4.98 | 4.85 | 100 | 100
1546 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/10067 | Augmentation | Construction of Boundary Wall and allied works at 3rd T/W Site Chapra Bangaljhi Water Supply Scheme Under Krishnagar Sub-dividion Under Nadia Division | 734/KSD | 07/06/2023 | 60 | AMIT KARMAKAR | 4.95 | 4.94 | 100 | 100
1547 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/10067 | Augmentation | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Chapra Bangaljhi Water Supply Scheme within Chapra block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 6210/ND | 28/12/2023 | 60 | S.B.CONSTRUCTION | 12.16 | 11.7 | 100 | 20
1548 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/10067 | Augmentation | Quotation for new service connection charges and security deposit for PH-3 under Chapra Bangaljhi w/s scheme,under EMSD-III,PHE Dte,Nadia | BP-156-24-25 | 06/11/2024 | 0 | W.B.S.E.D.C.L (GROUP CHAPRA C.C.C) | 4.99 | 0 | 0 | 0
1549 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/10067 | Augmentation | Quotation charges and security deposit for new power connection at Pump House -IV of Chapra Bangaljhi w/s scheme under EMSD-III,PHE Dte., Nadia. | BP-194-24-25 | 17/12/2024 | 0 | W.B.S.E.D.C.L (GROUP CHAPRA C.C.C) | 4.84 | 0 | 0 | 0
1550 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/10067 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme, Construction of 900 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of 900 CUM OHR at Chapra Bangaljhi to accommodate FHTC within Chapra block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 4540/ND | 21/10/2022 | 1097 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 689.72 | 384.75 | 55.78 | 60
1551 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/10067 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accomodate FHTC under CHAPRA BANGALJHI W/S Scheme, Block-CHAPRA , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 07) | 410/EMD | 20/01/2023 | 712 | ASHUTOSH DAS & CO. | 37.79 | 18.64 | 49.34 | 50
1552 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/10067 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab for official use for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for JJM works for the period 90 days w.e.f. 01.01.2023 (as and when required). | 1331/KSD | 29/12/2022 | 90 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 100
1553 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Tehatta Water Supply Scheme in Tehatta-I Block, Dist.-Nadia. , SM/16341 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1554 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Palasipara Water Supply Scheme in Tehatta-II Block, Dist.-Nadia. , SM/16347 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1555 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Karimpur Jalangi (Zone - IV to VII) Water Supply Scheme in Karimpur-I Block of District Nadia , SM/16796 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1556 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Senpur Water Supply Scheme in Krishnagar-I Block, Dist.- Nadia. , SM/16843 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1557 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Dhoradaha Water Supply Scheme in Karimpur-II Block of District Nadia , SM/16800 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1558 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Kulgachi Water Supply Scheme in Krishnagar-I Block, Dist.- Nadia. , SM/16833 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1559 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Monipota Water Supply Scheme in Krishnagar-I Block, Dist.- Nadia. , SM/16835 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1560 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Murutia Water Supply Scheme in Karimpur-II Block of District Nadia , SM/16807 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1561 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Narayanpur Water Supply Scheme in Karimpur-II Block of District Nadia , SM/16808 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1562 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Fulia Township Water Supply Scheme in Shantipur Block, Dist,- Nadia , SM/17266 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1563 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Gayespur Water Supply Scheme (Zone - I & II) in Shantipur Block, Dist,- Nadia , SM/17267 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1564 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BADKULLA ZONE-II (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17687 | Augmentation | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali BlocK,. under Ranaghat Sub-Division, PHE Dte. | 1271/ND | 23/03/2023 | 60 | AUXILIARY TUBEWELL DRILLERS | 48.99 | 13.28 | 81.3 | 40
1565 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BADKULLA ZONE-II (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17687 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, Zone-II (Phase-II) under Badkulla ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. | 6395/EMD | 30/10/2023 | 30 | M/S. G.P. ENTERPRISE | 12.61 | 11.74 | 100 | 100
1566 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Ber Ramchandrapur Zone II PWSS (PHASE-II) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17203 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I & II Zone-II(Phase-II) under Ber Ramchandrapur ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. | 6393/EMD | 30/10/2023 | 30 | SHIVAM ENTERPRISE | 16.27 | 0 | 0 | 0
1567 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Ber Ramchandrapur Zone II PWSS (PHASE-II) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17203 | Augmentation | Material Requisition To Resource Division | 3787/ND | 24/08/2023 | 0 | Resource Division | 2.94 | 0 | 0 | 0
1568 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Ber Ramchandrapur Zone II PWSS (PHASE-II) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17203 | Augmentation | Proposed Augmentation of Laying Rising Main System and Sinking of Replacement Tube Well at Head Work Site & 2nd Tube Well Site of Ber Ramchandrapur Zone-II [Phase-II] Ground Based Piped Water Supply Scheme. | 1193/ND | 21/03/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 28.7 | 18.62 | 97.74 | 70
1569 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Subarnabihar ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17211 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 231 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Subarnabihar Zone I PWSS under Nadia Division PHE Dte. | 1784/ND | 20/04/2023 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 222.99 | 150.15 | 100 | 65
1570 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Subarnabihar ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17211 | Augmentation | Providing, installation and commissioning of Electro-Mechanical Equipment and allied works for Arsenic Removal Plant in connection to Accommodate FHTC under Subarna Behar ground water based water supply scheme under Block_ Krishnanagar-I Dist. - Nadia, under EMD, PHE Dte. | 184/EMD | 29/01/2025 | 204 | DAS ENTERPRISE (M) | 51.34 | 0 | 0 | 0
1571 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone IV PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17212 | Augmentation | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at Teinpur Zone-IV (Phase-II) Piped Water Supply Scheme Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. | 6360/EMD | 17/10/2023 | 30 | M/S SAJAHAN CHOWDHURY | 42.1 | 0 | 0 | 0
1572 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone IV PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17212 | Augmentation | Renovation and modification of AIRP (Pressure Type) of capacity 20.87 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site in Teinpur Zone IV PWSS under Nadia Division PHE Dte. | 1807/ND | 24/04/2023 | 547 | MONDAL PRECISION PRIVATE LIMITED | 39.12 | 12.54 | 47.28 | 90
1573 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone IV PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17212 | Augmentation | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Teinpur Zone-IV PWSS within Karimpur-II Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 3260/ND | 10/06/2024 | 450 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 82.42 | 0 | 0 | 80
1574 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PANSILA(PHASE-II) IN NABADWIP BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17213 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 93 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Pansila PWSS under Nadia Division PHE Dte. | 2998/ND | 13/07/2023 | 90 | TARUN KUMAR BHATTACHARYA | 90.1 | 0 | 0 | 0
1575 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PANSILA(PHASE-II) IN NABADWIP BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17213 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under PANSILA W/S Scheme, Block-Nabadwip , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 08) | 501/EMDdt.24.01.2023 | 16/03/2023 | 30 | ASHOKE ADHIKARY | 15.59 | 4.75 | 100 | 100
1576 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PANSILA(PHASE-II) IN NABADWIP BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17213 | Augmentation | Providing Electro-Mechanical Equipment and Allied Works for Arsenic Removal Plant at PANSILA (PHASE-II) Piped Water SupplyScheme, Block: NABADWIP, Dist. Nadia Under EMD, PHE Dte. | 6363/EMD | 17/10/2023 | 685 | GOENKA ENTERPRISE | 53.53 | 0 | 0 | 30
1577 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Badalangi Padmala(Zone-I & II) Water Supply Scheme in Chapra Block, Dist.-Nadia. , SM/18045 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1578 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Halalpur Krishnapur (Z-I & II) Water Supply Scheme in Ranagtat-II Block under District Nadia , SM/18214 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1579 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Matikumra Water Supply Scheme in Ranagtat-II Block under District Nadia , SM/18217 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1580 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Bara Andulia(Zone-I & II) Water Supply Scheme in Chapra Block, Dist.-Nadia. , SM/18049 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1581 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Gongra Water Supply Scheme in Chapra Block, Dist.-Nadia. , SM/18054 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1582 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Lakshmipur Water Supply Scheme in Chapra Block, Dist.-Nadia. , SM/18055 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1583 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-III within Nakashipara Block (Phase-B) , SM/07501 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT PART-II, Z-III | 460/DW | 30/03/2021 | 0 | UMWELT ENGINEERS PVT LTD | 77.39 | 0 | 0 | 0
1584 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-III within Nakashipara Block (Phase-B) , SM/07501 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-III within Nakashipara Block ( Phase -B) | 244/ND | 15/01/2021 | 90 | UMWELT ENGINEERS PVT LTD | 97.08 | 24.58 | 25.31 | 0
1585 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | Material Requisition To Resource Division | 131/ND | 06/01/2023 | 0 | Resource Division | 1214.5 | 0 | 0 | 0
1586 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | Collection of Household data through mobile app for FHTC Connection of Surface Based PWSS for Northern Sector (Part-I) (Zone-IXA to Zone-IXB) under Nadia Division, P.H.E. Dte. | 913/KLYSD-I | 29/08/2023 | 184 | TECHVISION | 0.97 | 0.97 | 100 | 100
1587 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | New Service connection and security deposit for Debagram (Zone- 5B) OHR site. | BP-147-24-25 | 28/10/2024 | 0 | WBSEDCL DEBOGRAM CCC | 3.81 | 0 | 0 | 0
1588 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | New Service connection and security deposit for Ghoraikhetra (zone- 4B) OHR site. | BP-149-24-25 | 28/10/2024 | 0 | WBSEDCL DEBOGRAM CCC | 3.42 | 0 | 0 | 0
1589 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | Quotation for new service connection charges and security deposit for Dakshin Hazrapota OHR site. | BP-145-24-25 | 28/10/2024 | 0 | WBSEDCL.MATIARY.CCC | 11.45 | 0 | 0 | 0
1590 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | New Service connection and security deposit for Asachiya (Zone- 3B) OHR site. | BP-148-24-25 | 28/10/2024 | 0 | WBSEDCL DEBOGRAM CCC | 3.65 | 0 | 0 | 0
1591 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | Quotation for new service connection charges and security deposit for Bathangachi OHR (Zone-6B) site. | BP-146-24-25 | 28/10/2024 | 0 | WBSEDCL.PALASSEY.CCC | 4.28 | 0 | 0 | 0
1592 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | Service connection charges and Security deposit for new bulk power supply to Kaliganj GLR, Nadia, Pin code- 741136. | BP-79-24-25 | 02/08/2024 | 0 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 39.52 | 0 | 0 | 0
1593 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | Quotation for new service connection charges and security deposit for Juranpur OHR site. | BP-144-24-25 | 28/10/2024 | 0 | WBSEDCL.MATIARY.CCC | 3.86 | 0 | 0 | 0
1594 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | Quotation for new service connection and security deposit for Chhota chandghar OHR (Zone-9B) site | BP-151-24-25 | 28/10/2024 | 0 | WBSEDCL.PALASSEY.CCC | 7.98 | 0 | 0 | 0
1595 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | Payment to Ministry of Railway regarding railway crossing, Application ID- ER-SDAH-2024-WL-136 | 307/PFMS | 02/10/2024 | 0 | MINISTRY OF RAILWAYS, EASTERN RAILWAY, SEALDAH DIVISION | 6.59 | 0 | 0 | 0
1596 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | Quotation for earnest Money deposit for bulk power supply for Kaliganj GLR Project. | BP-24-24-25 | 21/05/2024 | 0 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 0.05 | 0 | 0 | 0
1597 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | Payment to Ministry of Railway regarding railway crossing, Application ID- ER-SDAH-2024-WL-112 | 306/PFMS | 02/10/2024 | 0 | MINISTRY OF RAILWAYS, EASTERN RAILWAY, SEALDAH DIVISION | 4.99 | 0 | 0 | 0
1598 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | Quotation for new service connection and security deposit for Bhurulia OHR (Zone- 7B) site, plaseey. | BP-150-24-25 | 28/10/2024 | 0 | WBSEDCL.PALASSEY.CCC | 4.47 | 0 | 0 | 0
1599 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 2686.7 | 66.34 | 47
1600 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | Augmentation of pumping machinery and electrical equipments at Intake, WTP alongwith implementation of SCADA System for surface water based water supply scheme, Arsenic affected area, Northern Sector, Part-I (Block - Kaliganj) in the district of Nadia, P. H. E. Dte. | 6263/EMD | 10/10/2023 | 600 | ORIENTAL ENGINEERING CO. | 308.87 | 0 | 0 | 25
1601 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | Providing Axially Split Centrifugal Pumping machinery for GLR alongwith secondary disinfection arrangement for surface water based water supply scheme, Arsenic Affected Area, Northern Sector, Part-I (Block - Kaliganj) in the district of Nadia, P. H. E. Dte. | 6262/EMD | 10/10/2023 | 600 | ORIENTAL ENGINEERING CO. | 271.65 | 0 | 0 | 25
1602 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | Additional Work for Ground Improvement of OHR foundation, renovation of OHR & other allied works of Northern Sector Part-I, Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 6095/ND | 19/09/2024 | 240 | UMWELT ENGINEER PVT LTD | 225.66 | 127.18 | 90.95 | 75
1603 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 470.02 | 64.65 | 52
1604 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18388 | Augmentation | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3829/ND | 13/08/2025 | 120 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0 | 0
1605 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Matiari Water Supply Scheme in Krishnaganj Block, Dist.-Nadia. , SM/18063 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
1606 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09251 | Retrofitting | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Bansbaria (Vill- Poragachha) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 288/NACD-II | 23/02/2021 | 21 | SANDIP BISWAS | 35.39 | 0 | 0 | 100
1607 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09251 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair due to construction of road) at Bansbaria W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1019/NACD-II | 29/11/2022 | 60 | S.B. CONSTRUCTION | 27.03 | 27.03 | 100 | 100
1608 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09251 | Retrofitting | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HELENCHI (Z-I, Z-II, Z-III) (Block- Krishnaganj ) AND BANSBERIA,CHANDPUR & DAMODARKHALI (Block- Krishnagar I) W/S Scheme, , Dist. - Nadia. NIET NO.- 31 of EE/EMD of 2022-23 (Sl. No.- 02) | 1121/EMD | 16/03/2023 | 30 | M.S. ENTERPRISE | 65.68 | 5.87 | 100 | 90
1609 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09251 | Retrofitting | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Krishnagar-I Block of Nadia District through Jadavpur University. (Name of PWSS Bansberia) | 1058/NACD-II | 20/09/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
1610 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09251 | Retrofitting | Renovation work at Bansberia Head Work Site under Bansberia Piped Water Supply Scheme at Krishnagar-I Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | 926/AE-I/NACD-II | 30/09/2024 | 30 | JYOTIRMOY ENTERPRISE | 4.61 | 0 | 0 | 0
1611 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09251 | Retrofitting | Renovation of Arsenic cum Iron treatment Plant of Bansberia PWSS (Capacity- 31 m3/hr) and ancillary works of Krishnagar-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte | 89/NACD-II | 18/01/2024 | 60 | MONDAL PRECISION PRIVATE LIMITED | 78.06 | 74.16 | 100 | 100
1612 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09251 | Retrofitting | Supply of Water Level Indicator at Bansberia in Krishnagar-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 1158/AE-I/NACD-II | 31/01/2025 | 45 | M/S S.K. CONSTRUCTION | 0.77 | 0 | 0 | 100
1613 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11738 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 6B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 127/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.26 | 4.23 | 100 | 100
1614 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11738 | Augmentation | Material Requisition To Resource Division | 105/ND | 05/01/2023 | 0 | Resource Division | 223 | 0 | 0 | 0
1615 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11738 | Augmentation | Collection of Household data through mobile app for FHTC Connection of Surface Based PWSS for Northern Sector (Part-I) (Zone-VA to Zone-VIIIB) under Nadia Division, P.H.E. Dte. | 994/KLYSD-I | 14/09/2023 | 90 | TECHVISION | 4.85 | 4.85 | 100 | 100
1616 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11738 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 540.18 | 96.68 | 47
1617 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11738 | Augmentation | Additional Work for Ground Improvement of OHR foundation, renovation of OHR & other allied works of Northern Sector Part-I, Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 6095/ND | 19/09/2024 | 240 | UMWELT ENGINEER PVT LTD | 225.66 | 0 | 0 | 75
1618 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Construction of barbed wire fencing with concrete pillars at Hanspukuria Zone-II (2nd T.W). water supply scheme( New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . | 931/TSD | 14/03/2023 | 7 | PRABIR KUMAR ROY | 0.46 | 0.46 | 100 | 0
1619 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Hanspukuria W/S Scheme in Tehatta-II Block of Nadia District under Nadia Division, P.H.E. Dte. | 298/TSD | 24/11/2021 | 30 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 4.07 | 4.07 | 100 | 100
1620 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Material Requisition To Resource Division | 153/ND | 06/01/2023 | 0 | Resource Division | 154.79 | 0 | 0 | 0
1621 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Material Requisition To Resource Division | 1026/ND | 13/03/2023 | 0 | Resource Division | 1.39 | 0 | 0 | 0
1622 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Material Requisition To Resource Division | 2310/ND | 29/05/2023 | 0 | Resource Division | 13.8 | 0 | 0 | 0
1623 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Construction Of Pump House (5.4m X 3.6m) & (3.6m X 3.0m) Including Sanitary Arrangement At Head Work Site & 2nd tube well Site and construction of Boundary wall at Head works site & 2nd tube well site of Hanspukuria Zone - II Ground water based water supply scheme under Tehatta Sub-Division PHE Dte. | 1630/ND | 07/03/2024 | 180 | J.P. CONSTRUCTION & SUPPLIERS | 34.04 | 14.57 | 42.81 | 65
1624 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 50 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Hasnpukuria Zone-I to accommodate FHTC within Tehatta-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | 4701/ND | 29/08/2024 | 180 | MONDAL PRECISION PRIVATE LIMITED | 181.86 | 0 | 0 | 0
1625 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Hanspukuria Zone-I water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 6836/ND | 12/11/2024 | 90 | BUDDHADEV MONDAL | 32.88 | 0 | 0 | 0
1626 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Construction of barbed wire fencing with concrete pillars at Hanspukuria Zone-II water supply scheme 1st T.W. H.W.Site (New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . | 1117/TSD | 21/02/2024 | 7 | PRABIR KUMAR ROY | 2.13 | 2.05 | 100 | 100
1627 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Sinking of 01 nos Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at Headwork site , Hanspukuria Zone-II PWSS Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | 1097/ND | 19/02/2024 | 30 | TULIP ENGINEER'S CO-OP SOCIETY LTD | 17.39 | 12.21 | 100 | 100
1628 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Material Requisition To Resource Division | 3503/ND | 24/06/2024 | 0 | Resource Division | 12.39 | 0 | 0 | 0
1629 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Quotation for New service connection charges and security deposit for Hanspukuria 2nd T/W. | BP-172-24-25 | 05/12/2024 | 0 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 3.02 | 0 | 0 | 0
1630 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Quotation charges and security deposit for new power connection at Hanspukuria (Zone-II) head worksite under Eastern Mechanical Subdivision-III, Nadia | BP-193-24-25 | 16/12/2024 | 0 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 9.18 | 0 | 0 | 0
1631 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Hanspukuria Zone-I to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 5351/ND | 22/12/2022 | 731 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 203.73 | 177.3 | 87.02 | 95
1632 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 300 cum capacity 20 mtr. height RCC over head reservoir (with pile foundation), pipe connection and cost of pipes, specials. and Soil investigation for construction of one No. 300 Cum OHR of staging height 20 mtr. for Augmentation of Ground Based Water Supply Scheme at Hanspukuria Zone-II to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 480/ND | 02/02/2023 | 731 | M/S DIPAK ENTERPRISE, GHOSH PARA,WORD NO.-4, KALYANI, NADIA-741235 WEST BENGAL | 291.32 | 121.61 | 41.75 | 65
1633 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Hanspukuria Zone-I Ground Based Water Supply Scheme under Tehatta-II Block under Nadia Division, P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Hanspukuria Zone-I at Tehatta-II Block by Augmentation of Ground Water based PWSS for Hanspukuria Zone-I Water Supply Schemes under Nadia Division, PHE Dte. | 7358/ND | 18/12/2024 | 60 | SAHA CONSTRUCTION & CO | 20.43 | 0 | 0 | 0
1634 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 50 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Hasnpukuria Zone-II to accommodate FHTC within Tehatta-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | 4700/ND | 29/08/2024 | 360 | MONDAL PRECISION PRIVATE LIMITED | 181.28 | 0 | 0 | 0
1635 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejumination Tube Well and New Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II , III , IV Zone-I & Pump House No.-I ,II (Zone-II) under Hanspukuria ground water based water supply scheme under Block_ Tehatta-II Dist. - Nadia under EMD, PHE Dte. (SM/11918) | 238/EMD | 06/02/2025 | 30 | DEY ENTERPRISE | 72.07 | 0 | 0 | 25
1636 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia , SM/11918 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Hanspukuria ground water based water supply scheme under Block_ Tehatta-II Dist. - Nadia under EMD, PHE Dte. SM/11918 | 1109/EMD | 04/06/2025 | 90 | ANJAN ENTERPRISE | 20.8 | 0 | 0 | 0
1637 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11836 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 1/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 135/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.91 | 3.8 | 100 | 100
1638 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11836 | Augmentation | Material Requisition To Resource Division | 91/ND | 05/01/2023 | 0 | Resource Division | 64.78 | 0 | 0 | 0
1639 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11836 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
1640 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11836 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 137 cum. for Providing FHTC (Functional Household Tap Connection) for Zone -I/A (Northern Sector, Part-II) Water Supply Scheme in Nakashipara Block of Nadia District under Nadia Division, PHE Dte.¿ | 3998/ND | 07/09/2023 | 60 | M/S ARATI ENTERPRISE | 13.1 | 13.09 | 100 | 65
1641 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11836 | Augmentation | Material Requisition To Resource Division | 235/ND | 11/01/2024 | 0 | Resource Division | 3.79 | 0 | 0 | 0
1642 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11836 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- I/A (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4281/ND | 21/09/2023 | 642 | PRASUN ENTERPRISE | 268.05 | 70.56 | 26.32 | 25
1643 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11836 | Augmentation | Construction of OHR, repair and renovation of staff room, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-I / A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, P.H.E. Dte. [SM/11836]. | 5556/ND | 12/12/2023 | 729 | M/S DIPAK ENTERPRISE, GHOSH PARA,WARD NO-4, KALYANI, NADIA-741235 WEST BENGAL | 150.28 | 0 | 0 | 5
1644 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11836 | Augmentation | Additional Work for Installation of SCADA System in connection with Augmentation of Surface Water Based Piped Water Supply Scheme for Northern Sector Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 3447/ND | 23/07/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 732.35 | 0 | 0 | 15
1645 | NADIA | Central Drilling | Providing Functional Household Tap Connection from Kishorpur Water Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting) , SM/08130 | Retrofitting | PROVIDING 200 MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KISHOREPUR W/S (REPLACEMENT TW-HW) KARIMPUR -II BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | 282/CMSD-II (D) | 01/06/2022 | 15 | UNIVERSAL ENTERPRISES | 4.44 | 0 | 0 | 0
1646 | NADIA | Central Drilling | Providing Functional Household Tap Connection from Kishorpur Water Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting) , SM/08130 | Retrofitting | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KISHOREPUR W/S (REPLACEMENT TW-HW) IN KARIMPUR-II BLOCK UNDER NADIA DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 281/CMSD-II (D) | 01/06/2022 | 15 | UNIVERSAL ENTERPRISES | 2.07 | 1.63 | 100 | 0
1647 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Kishorpur Water Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting) , SM/08130 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Kishorpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retrofitting) | 421/PFMS | 19/01/2022 | 0 | SANDIP BISWAS | 93.47 | 0 | 0 | 0
1648 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Kishorpur Water Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting) , SM/08130 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Kishorpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retrofitting) | 2769/ND | 14/07/2021 | 90 | SANDIP BISWAS | 96.61 | 0 | 0 | 100
1649 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Kishorpur Water Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting) , SM/08130 | Retrofitting | Material Requisition To Resource Division | 433/ND | 31/01/2022 | 0 | Resource Division | 1 | 0 | 0 | 0
1650 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-C) , SM/07435 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME ATPART-1 Z-3 | 460/DW | 30/03/2021 | 0 | M/S NIBHAS SINHA | 50.76 | 0 | 0 | 0
1651 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-C) , SM/07435 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME (NORTHERN SECTOR) PART-I, ZONE-III WITHIN KALIGANJ BLOCK (PHASE-C) |  | 17/03/2021 | 0 | M/S NIBHAS SINHA | 50.76 | 0 | 0 | 0
1652 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-C) , SM/07435 | Retrofitting | PROVIDING FHTC SURFCE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-I, Z-III, WITHIN KALIGANJ BLOCK, PHASE-C | 475/PFMS | 03/02/2022 | 0 | M/S NIBHAS SINHA | 4.67 | 0 | 0 | 0
1653 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-C) , SM/07435 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-III, within Kaliganj Block (Phase-C, Retrofitting) | 161/ND | 13/01/2021 | 90 | M/S NIBHAS SINHA | 97.11 | 41.46 | 100 | 0
1654 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, (Simurali), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme , SM/07999 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, Shimurali, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 865/NAD-I | 15/06/2021 | 60 | ALOK ENTERPRISE | 80.87 | 80.7 | 100 | 100
1655 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, (Simurali), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme , SM/07999 | Retrofitting | Hiring of 1 (One) no Diesel Luxury Taxi/Maxi Cab/Motor Cab on Daily basis for monitoring of JJM works and progress of JJM works (Such as identification of land etc) under the office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. | 383/AE-I/NAD-I | 01/09/2023 | 182 | ANURADHA DHARA | 2.4 | 1.66 | 69.3 | 20
1656 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Masra), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme , SM/08003 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, Masra, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 773/NAD-I | 04/05/2021 | 60 | H I ENTERPRISE | 95.74 | 106.72 | 162.32 | 100
1657 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Masra), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme , SM/08003 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna Zone-II Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. -01) Tender no.- 230/NAD-I/2020-2021. | 290/NAD-I | 04/02/2021 | 45 | CHANDAN ROY | 43.9 | 0 | 0 | 100
1658 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Masra), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme , SM/08003 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ukilnara Zone - II at Ranaghat - I Block by retrofitting of Ground Water based PWSS for Ukilnara - Zone - II Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte.(Sl. No.-08) Tender No. 234/NAD-I/2020-2021. | 292/NAD-I | 04/02/2021 | 45 | M/S UMA CONSTRUCTION | 43.74 | 25.38 | 57.19 | 100
1659 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Masra), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme , SM/08003 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, Masra, Part-I, Ukhilnara -II, at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 292 / NAD-I | 04/02/2021 | 45 | M/S UMA CONSTRUCTION | 43.74 | 1.9 | 6.98 | 60
1660 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Masra), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme , SM/08003 | Retrofitting | Supply of 1(one )no. Motor Cab ( Luxury Taxi) on hire basis for official use of the Executive Engineer , Nadia Arsenic Division -I, P.H.E.Dte. for the period from ( 15.07.22 to 14.07.23i.e. for 1(one) year .(sl.01) | 173 / AE-I/NAD-I | 14/07/2021 | 365 | AVINABA ENGINEERING CONCERN | 5.34 | 4.07 | 100 | 100
1661 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX, (Ghetugachhi), Part-II at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme , SM/08005 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara Jal Swapna for Zone IX Ghetugachi Part II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah Part Water Supply Scheme under Nadia Arsenic Division I PHE Dte | 783/NAD-I | 05/05/2021 | 60 | TAPU SAHA | 68.94 | 131.63 | 100 | 100
1662 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XII, (Balagarichar), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdaha (Part) Water Supply Scheme , SM/08007 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XII, Balagarichar, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 774/NAD-I | 04/05/2021 | 60 | PALCON | 39.63 | 76.69 | 97.02 | 100
1663 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XII, (Balagarichar), Part-II at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme , SM/08008 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XII, Balagarichar, Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 775/NAD-I | 04/05/2021 | 60 | PRIYA CONSTRUCTION | 66.11 | 124.65 | 94.51 | 100
1664 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Sabdalpur, at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Sabdalpur Water Supply Scheme , SM/08021 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara/JalSwapna for Sabdalpur, at Ranaghat-II Block by retrofitting of Ground Water Based PWSS for Sabdalpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 954/NAD-I | 09/07/2021 | 90 | TARUN KUMAR BHATTACHARYA | 182.15 | 238.68 | 78.05 | 100
1665 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-B) , SM/07458 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-B) | 282/PFMS | 08/10/2021 | 0 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 60.5 | 0 | 0 | 0
1666 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-B) , SM/07458 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-B) |  | 04/10/2021 | 0 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 60.5 | 0 | 0 | 0
1667 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-B) , SM/07458 | Retrofitting | PROVIDIDING FHTC AT SURFACE WATER BAESD WATER SUPPLY SCHEME NORTHERN SECTOR , PART-II,ZONE-VIII, WITHIN NAKASHIPARA BLOCK, PHASE-B. | 487/PFMS | 03/02/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 0.41 | 0 | 0 | 0
1668 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-B) , SM/07458 | Retrofitting | PROVIDIDING FHTC AT SURFACE WATER BAESD WATER SUPPLY SCHEME NORTHERN SECTOR , PART-II,ZONE-VIII, WITHIN NAKASHIPARA BLOCK, PHASE-B. | 492/PFMS | 03/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.47 | 0 | 0 | 0
1669 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-B) , SM/07458 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VIII within Nakashipara Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte.(SL.8) | 867/ND | 18/02/2021 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 97.09 | 27.09 | 100 | 0
1670 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-B) , SM/07458 | Retrofitting | Material Requisition To Resource Division | 233/ND | 11/01/2024 | 0 | Resource Division | 8.75 | 0 | 0 | 0
1671 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (Darrappur), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07445 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (Darrappur), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. Tender No.- 217/NAD-I/2020-2021. | 277/NAD-I | 03/02/2021 | 90 | H I ENTERPRISE | 90.31 | 177.47 | 121.28 | 100
1672 | NADIA | Nadia Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08134 | Retrofitting | Providing Functional House Tap Connection from Badlangi Padmamala Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | 279/PFMS | 08/10/2021 | 0 | TAPU SAHA | 33.12 | 0 | 0 | 0
1673 | NADIA | Nadia Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08134 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Badlangi Padmamala Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | 2045/ND | 13/05/2021 | 60 | TAPU SAHA | 42.45 | 0 | 0 | 100
1674 | NADIA | Nadia Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08134 | Retrofitting | Material Requisition To Resource Division | 104/ND | 06/01/2022 | 0 | Resource Division | 0.86 | 0 | 0 | 0
1675 | NADIA | Nadia Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08134 | Retrofitting | Material Requisition To Resource Division | 436/ND | 31/01/2022 | 0 | Resource Division | 0.63 | 0 | 0 | 0
1676 | NADIA | Nadia Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08134 | Retrofitting | Material Requisition To Resource Division | 1027/ND | 03/03/2022 | 0 | Resource Division | 6.33 | 0 | 0 | 0
1677 | NADIA | Nadia Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08134 | Retrofitting | Material Requisition To Resource Division | 4019/ND | 16/09/2022 | 0 | Resource Division | 24.55 | 0 | 0 | 0
1678 | NADIA | Nadia Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08134 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 1.94 | 100 | 81
1679 | NADIA | Nadia Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08134 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Badlangi Padmamala Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | 2390/ND | 10/06/2021 | 45 | BIPLAB GUHA | 9.23 | 17.76 | 192.41 | 100
1680 | NADIA | Nadia Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08134 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Badlangi Padmamala Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | 2046/ND | 13/05/2021 | 60 | TAPU SAHA | 42.45 | 68.03 | 160.24 | 100
1681 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block (Phase-B) , SM/07430 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block (Phase-B) | 305/PFMS | 01/11/2021 | 0 | MAHAVIR PUMPS MFG PVT. LTD. | 30 | 0 | 0 | 0
1682 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block (Phase-B) , SM/07430 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block (Phase-B). |  | 20/03/2021 | 0 | MAHABIR PUMPS MFG PVT. LTD. | 22.98 | 0 | 0 | 0
1683 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block (Phase-B) , SM/07430 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT PART-I Z-VIII | 460/DW | 30/03/2021 | 0 | MAHABIR PUMPS MFG PVT. LTD. | 22.98 | 0 | 0 | 0
1684 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block (Phase-B) , SM/07430 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block (Phase-B) | 586/PFMS | 04/03/2022 | 0 | MAHAVIR PUMPS MFG PVT. LTD. | 4.18 | 0 | 0 | 0
1685 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block (Phase-B) , SM/07430 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block (Phase-B) | 554/PFMS | 23/02/2022 | 0 | MAHAVIR PUMPS MFG PVT. LTD. | 25 | 0 | 0 | 0
1686 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block (Phase-B) , SM/07430 | Retrofitting | Laying of main distribution pipeline at zone-III and VIII of Surface water based water supply scheme, part-I within Kaliganj Block damaged during 4- laning of NH-34. | 56/DSD | 07/02/2022 | 15 | TARUN KUMAR BHATTACHARYA | 3.43 | 3.25 | 94.7 | 0
1687 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block (Phase-B) , SM/07430 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-VIII, within Kaliganj Block (Phase-B, Retrofitting)" | 164/ND | 13/01/2021 | 90 | MAHABIR PUMPS MFG PVT. LTD. | 97.11 | 9.26 | 100 | 100
1688 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-V within Kaliganj Block (Phase-B) , SM/07431 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME PART -1 Z-V | 459/DW | 30/03/2021 | 0 | M/S SHIL & CO. | 63.52 | 0 | 0 | 0
1689 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-V within Kaliganj Block (Phase-B) , SM/07431 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME(NORTHERN SECTOR)PART-I,ZONE-V, WITHIN KALIGANJ BLOCK (PHASE-B,RETROFITTING) |  | 12/03/2021 | 0 | M/S SHIL & CO. | 63.52 | 0 | 0 | 0
1690 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-V within Kaliganj Block (Phase-B) , SM/07431 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-V within Kaliganj Block (Phase-B) | 286/PFMS | 08/10/2021 | 0 | M/S SHIL & CO. | 18.5 | 0 | 0 | 0
1691 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-V within Kaliganj Block (Phase-B) , SM/07431 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-V within Kaliganj Block (Phase-B) | 606/PFMS | 11/03/2022 | 0 | OTHERS | 5.97 | 0 | 0 | 0
1692 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-V within Kaliganj Block (Phase-B) , SM/07431 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-V, within Kaliganj Block (Phase-B, Retrofitting)" | 162/ND | 13/01/2021 | 90 | M/S SHIL & CO. | 97.11 | 8.37 | 100 | 0
1693 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-III, Zone-III within Krishnagar-II Nabadwip (Part) Block (Phase-A). , SM/07469 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED W/S SCHEME NORTHERN SECTOR , PART-3, ZONE-3 WITHIN KRISHNAGAR-2 NABADWIP BLOCK PHASE-A | 239/PFMS | 05/10/2021 | 0 | M/S S & P CONSTRUCTION | 73.75 | 0 | 0 | 0
1694 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-III, Zone-III within Krishnagar-II Nabadwip (Part) Block (Phase-A). , SM/07469 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-III, Zone-III within Krishnagar-II Nabadwip (Part) Block (Phase-A). |  | 29/09/2021 | 0 | M/S S & P CONSTRUCTION | 73.75 | 0 | 0 | 0
1695 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-III, Zone-III within Krishnagar-II Nabadwip (Part) Block (Phase-A). , SM/07469 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-III, Z-III, WITHIN KRISHNAGAR-2 AND NABADWIP BLOCK, PHASE-A. | 499/PFMS | 03/02/2022 | 0 | M/S R. DUTTA & CO. | 0.46 | 0 | 0 | 0
1696 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-III, Zone-III within Krishnagar-II Nabadwip (Part) Block (Phase-A). , SM/07469 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-III, within Krishnagar-II & Nabadwip Block (Phase-A, Retrofitting)" | 774/ND | 10/02/2021 | 90 | M/S S & P CONSTRUCTION | 97.07 | 41.73 | 42.99 | 0
1697 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase-C) , SM/07474 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-IX within Kaliganj Block (Phase-C) | 410/PFMS | 21/12/2021 | 0 | M/S K.P. CONSTRUCTION | 71.05 | 0 | 0 | 0
1698 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase-C) , SM/07474 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-IX within Kaliganj Block (Phase-C) | 2768/ND | 14/07/2021 | 90 | M/S K.P. CONSTRUCTION | 92.27 | 19.29 | 20.9 | 100
1699 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-III within Krishnagar-II, Nabadwip (Part) Block (Phase-B) , SM/07495 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-III within Krishnagar-II, Nabadwip (Part) Block (Phase-B) | 271/PFMS | 08/10/2021 | 0 | UNICON INDIA | 61.22 | 0 | 0 | 0
1700 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-III within Krishnagar-II, Nabadwip (Part) Block (Phase-B) , SM/07495 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED W/S SCHEME NORTHERN SECTOR PART-II, ZONE-III, WITHIN KRISHNAGAR-II AND NABADWIP BLOCK PHASE-B RETROFITTING. | 87/PPMS | 15/07/2021 | 0 | UNICON INDIA | 29.58 | 0 | 0 | 0
1701 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-III within Krishnagar-II, Nabadwip (Part) Block (Phase-B) , SM/07495 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-III, within Krishnagar-II & Nabadwip Block (Phase-B, Retrofitting)" | 775/ND | 10/02/2021 | 90 | UNICON INDIA | 97.6 | 0 | 0 | 0
1702 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-A) , SM/07502 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-A) | 281/PFMS | 08/10/2021 | 0 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 59.73 | 0 | 0 | 0
1703 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-A) , SM/07502 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-A) |  | 04/10/2021 | 0 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 59.73 | 0 | 0 | 0
1704 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-A) , SM/07502 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block ( Phase -A) in Nadia District under Nadia Division P.H.E. Dte. SLNo.7 | 894/ND | 19/02/2021 | 90 | ALOKE ENTERPRISE | 97.09 | 25.6 | 100 | 0
1705 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-A) , SM/07502 | Retrofitting | Material Requisition To Resource Division | 4318/ND | 29/09/2022 | 0 | Resource Division | 12.46 | 0 | 0 | 0
1706 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Taldaha water supply scheme under Krishnaganj Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07297 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Taldaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 08/NACD-II | 05/01/2021 | 90 | SINGHA ROY & CO. | 61.3 | 60.04 | 198.46 | 0
1707 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Maheshpur water supply scheme under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07937 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Maheshpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1069/NACD-II | 25/09/2020 | 15 | PARTHA DAS | 4.99 | 0 | 0 | 0
1708 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Bagakhali Zone-II water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07942 | Retrofitting | Work Order for the work of "Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Bagakhali Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte." | 1053/NACD-II | 25/09/2020 | 15 | M/S TARUN GHOSH & CO. | 5 | 0 | 0 | 0
1709 | NADIA | Nadia Division | Providing Functional House Tap Connection from Fatepur Water Supply Scheme under Jal Swapno Program in Nadia District , SM/06995 | Retrofitting | EXTENSION OF PIPE LINE FOR FHTC KALIGANJ, PART-1 Z-IV | 174/FHTC | 10/09/2021 | 0 | UMWELT ENGINEERS PVT LTD | 4.71 | 0 | 0 | 0
1710 | NADIA | Nadia Division | Providing Functional House Tap Connection from Fatepur Water Supply Scheme under Jal Swapno Program in Nadia District , SM/06995 | Retrofitting | EXTENSION OF PIPE LINE FOR FHTC KALIGANJ, PART-1 Z-IV | 174/FHTC | 10/09/2021 | 0 | UMWELT ENGINEERS PVT LTD | 4.58 | 0 | 0 | 0
1711 | NADIA | Nadia Division | Providing Functional House Tap Connection from Fatepur Water Supply Scheme under Jal Swapno Program in Nadia District , SM/06995 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PIPE G.I/PVC PIPE OF AVERAGE LENGTH OF 10MM DIA GUN-METAL FERRULE, SADDLE PIECE 15MM DIA BIB COCK ETC AT SUBERNA BIHAR W/S SCHEME PART-B | 473/DW | 07/02/2022 | 0 | ROY CONSTRUCTION | 0.73 | 0 | 0 | 0
1712 | NADIA | Nadia Division | Providing Functional House Tap Connection from Fatepur Water Supply Scheme under Jal Swapno Program in Nadia District , SM/06995 | Retrofitting | Providing functional household tap connection(Part) including supply of 15mm dia PVC pipe of average length of 15mm,10mm dia Gun-Metal Ferrule,Saddle piece(as required size) 15mm dia cock etc. all complete from Fatepur W/S Scheme in Nadia District under Nadia Division P.H.E.Dte. | 4081/ND | 31/12/2020 | 90 | MONDAL PRECISION PRIVATE LIMITED | 96.54 | 160.93 | 166.71 | 0
1713 | NADIA | Nadia Division | Providing Functional House Tap Connection from Fatepur Water Supply Scheme under Jal Swapno Program in Nadia District , SM/06995 | Retrofitting | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Executive Engineer, Nadia Division, PHE Dte. | 286/Kly SD-I | 31/03/2022 | 365 | ARROWTOWN DEALERS PVT. LTD | 4.8 | 2.91 | 100 | 0
1714 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-V within Kaliganj Block (Phase-A). , SM/07004 | Retrofitting | PREPERATION OF DETAILS PROJECT FOR FHTC AT SURFACE WATER BASED W/S SCHEME ( N.SECTOR) , PART-II, ZONE-I, PHASE-A & B UNDER , NADIA DIVISION , PHE ,DTE | 139/FHTC | 17/08/2021 | 0 | LEMNISCATE | 0.47 | 0 | 0 | 0
1715 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-V within Kaliganj Block (Phase-A). , SM/07004 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PIPE G.I/PVC PIPE OF AVERAGE LENGTH OF 10MM DIA GUN-METAL FERRULE, SADDLE PIECE 15MM DIA BIB COCK ETC AT SUBERNA BIHAR W/S SCHEME PART-B | 473/DW | 07/02/2022 | 0 | ROY CONSTRUCTION | 0.73 | 0 | 0 | 0
1716 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-V within Kaliganj Block (Phase-A). , SM/07004 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme(northern sector),Part-I,Zone-V within Kaliganj block(Phase-A) in Nadia District under Nadia Division P.H.Engineering Dte. | 3588/ND | 08/12/2020 | 90 | TARUN KUMAR BHATTACHARYA | 96.83 | 178.16 | 183.99 | 0
1717 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-V within Kaliganj Block (Phase-A). , SM/07004 | Retrofitting | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Executive Engineer, Nadia Division, PHE Dte. (Period- 01/04/2023 to 30/09/2023) | 465/ Kly SD-1 | 31/03/2023 | 183 | ARROWTOWN DEALERS PVT. LTD | 2.4 | 0.54 | 79.7 | 0
1718 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-V within Kaliganj Block (Phase-A). , SM/07004 | Retrofitting | Hiring Diesel Luxury Car on daily basis (for 12 months from 01.02.2021 to 31.01.2022) for the office use of the Assistant Engineer, Kalyani Sub Division II, P.H.E. Dte | 198 / KLYSD -II | 29/01/2021 | 365 | SUMAN CHAKRABORTY | 4.8 | 0.91 | 100 | 0
1719 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-V within Kaliganj Block (Phase-A). , SM/07004 | Retrofitting | Material Requisition To Resource Division | 448/ND | 31/01/2022 | 0 | Resource Division | 1.26 | 0 | 0 | 0
1720 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-V within Kaliganj Block (Phase-A). , SM/07004 | Retrofitting | Material Requisition To Resource Division | 812/ND | 18/02/2022 | 0 | Resource Division | 7.7 | 0 | 0 | 0
1721 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bhanderkhola Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07834 | Retrofitting | Providing Functional House Tap Connection from Bhanderkhola Water Supply Scheme under Jal Swapno Programme (Phase-I). |  | 24/03/2021 | 0 | S.S. ENTERPRISE | 53.42 | 0 | 0 | 0
1722 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bhanderkhola Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07834 | Retrofitting | Providing Functional House Tap Connection from Bhanderkhola Water Supply Scheme under Jal Swapno Programme (Phase-I) |  | 04/10/2021 | 0 | S.S. ENTERPRISE | 29.31 | 0 | 0 | 0
1723 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bhanderkhola Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07834 | Retrofitting | 1ST RA FOR PROVIDING FHTC BHANDERKHOLA W/S SCHEME, PHASE-1, RETROFITTING. | 88/PPMS | 15/07/2021 | 0 | S.S. ENTERPRISE | 53.42 | 0 | 0 | 0
1724 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bhanderkhola Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07834 | Retrofitting | Providing Functional House Tap Connection from Bhanderkhola Water Supply Scheme under Jal Swapno Programme (Phase-I) | 265/PFMS | 08/10/2021 | 0 | S.S ENTERPRISE | 29.31 | 0 | 0 | 0
1725 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bhanderkhola Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07834 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Bhanderkhola W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I, Retrofitting) | 46/ND | 06/01/2021 | 90 | S.S. ENTERPRISE | 93.24 | 6.85 | 100 | 100
1726 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bhanderkhola Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07834 | Retrofitting | Material Requisition To Resource Division | 1017/ND | 03/03/2022 | 0 | Resource Division | 5.55 | 0 | 0 | 0
1727 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08849 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata, Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1541/NAD-I | 06/12/2021 | 90 | JOY HIND TUBE WELLS | 123.89 | 122.54 | 100 | 100
1728 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08849 | Retrofitting | Providing FHTC (Functional Household Tap Connection) at Patkabari, Hatibanda and Uttor Bishnupur under Jaldhara Jal Swapna from Arranghata Zone-I PWSS Part-III at Ranaghat-II Block by retrofitting under under Nadia Arsenic Division- I, P.H.E Dte. (Sl. No. 14) | 3044/NAD-I | 09/11/2022 | 30 | M/S R.K. ENTERPRISE | 32.39 | 28.34 | 100 | 100
1729 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08849 | Retrofitting | Construction of Boundary wall, Toilet, Pathway OHR Repair and other allied work in connection with Augmentation of Arranghata Zone-I water supply Scheme within Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E. Dte. (sl.no.16) | 569/NAD-I | 16/03/2023 | 60 | REAL TIME | 59.28 | 55.62 | 100 | 100
1730 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08849 | Retrofitting | Interconnection between Manifold and delivery main and approach road at arranghata Zone-I W/S Scheme in Ranaghat-II block and Chupria Zone-I in Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 01) | 2006/NAD-I | 29/11/2024 | 260 | BUDDHADEV MONDAL | 40.2 | 0 | 0 | 50
1731 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08849 | Retrofitting | Construction of Pathway Repair of 700 cum OHR and other allied work at Arranghata W/S Scheme under JJM within Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E. Dte. (3rd Call) | 1928/NAD-I | 25/11/2024 | 308 | REAL TIME | 20.49 | 0 | 0 | 100
1732 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08849 | Retrofitting | Construction of Boundary wall and pathway and Toilet at 2nd, 3rd and 4th Tubewell site of Aranghata and 3rd site of Debogram water supply Scheme in Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E. Dte. Under JJM. (Sl. No. 09) | 155/NAD-I | 28/04/2025 | 60 | GOUTAM DEY | 34.34 | 0 | 0 | 0
1733 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08849 | Retrofitting | Work for revamping / upgradation of the hydraulic parameters at Head work site towards Petua and Barberia Mouza in reference to Aranghata and Duttaphulia PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 06) | 77/NAD-I | 16/04/2025 | 60 | DEBASIS SAMADDAR | 95.65 | 0 | 0 | 0
1734 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08849 | Retrofitting | Work for revamping / upgradation of the hydraulic parameters at Head work site to Shibnarayanpur and allied works in reference to Aranghata Zone-I water supply scheme under Nadia Arsenic Division-I, P.H.E. Dte as a part of Jal Jeevan Mission. (2nd Call) [Sl. No. 04] | 720/NAD-I | 29/07/2025 | 60 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD. | 49.04 | 0 | 0 | 0
1735 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna Zone-I, Part-II, at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte , SM/08819 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara/Jal Swapna for Bhayna Zone-I Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 10/NAD-I | 05/01/2022 | 90 | TARUN KUMAR BHATTACHARYA | 202.09 | 201.23 | 81.95 | 100
1736 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna Zone-I, Part-II, at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte , SM/08819 | Retrofitting | Retrofitting work at Bhayna Zone-I water supply scheme in Hanskhali Block in Nadia District under JJM under Nadia Arsenic Division-I , PHE Dte. | 427/AE-I/NAD-I | 20/09/2023 | 30 | PALCON | 1.5 | 1.5 | 100 | 100
1737 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna Zone-I, Part-II, at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte , SM/08819 | Retrofitting | Material Requisition To Resource Division | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 1.73 | 0 | 0 | 0
1738 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Saguna, Part-II at Santipur Block by retrofitting of Ground Water based PWSS for Saguna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08823 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Saguna, Part-II at Santipur Block by retrofitting of Ground Water based PWSS for Saguna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1413/NAD-I | 08/11/2021 | 60 | M/S TARAK CHANDRA PAUL | 79.19 | 79.14 | 100 | 100
1739 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Saguna, Part-II at Santipur Block by retrofitting of Ground Water based PWSS for Saguna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08823 | Retrofitting | Surging of exisiting Tube Well Situated at 2nd Tube Well Site of Saguna Water Supply Scheme in connection with Jal Jeevan Mission under Santipur Block to increase the yield of the tube well under Nadia Arsenic Division-I P.H.E. Dte. | 192/AE-I/NAD-I | 21/06/2024 | 15 | APURBA MANDAL | 0.64 | 0 | 0 | 0
1740 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Matiary water supply scheme underKrishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08309 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Matiary W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1062/NACD-II | 25/09/2020 | 15 | ROY CONSTRUCTION | 4.99 | 0 | 0 | 0
1741 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Boalia, at Santipur Block by retrofitting of Ground Water based PWSS for Boalia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08864 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Boalia at Santipur Block by retrofitting of Ground Water based PWSS for Boalia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1538/NAD-I | 06/12/2021 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 430.7 | 432.06 | 100 | 100
1742 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Boalia, at Santipur Block by retrofitting of Ground Water based PWSS for Boalia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08864 | Retrofitting | Material Requisition To Resource Division | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 1.73 | 0 | 0 | 0
1743 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Itaberia at Hanskhali Block by retrofitting of Ground Water based PWSS for Itaberia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08811 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Itaberia at Hanskhali Block by retrofitting of Ground Water based PWSS for Itaberia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1409/NAD-I | 08/11/2021 | 60 | CHANDAN ROY | 89.54 | 89.4 | 100 | 100
1744 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Itaberia at Hanskhali Block by retrofitting of Ground Water based PWSS for Itaberia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08811 | Retrofitting | Route Survey, Design Drawing for Augmentation of ITABERIA Water Supply Scheme in Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. | 494/AE-II/NAD-I | 24/11/2023 | 7 | SUMAN CHAKRABORTY | 2.83 | 2.82 | 100 | 100
1745 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Joypur Part-I, at Hanskhali Block by retrofitting of Ground Water based PWSS for Joypur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte , SM/08812 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Joypur Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Joypur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1415/NAD-I | 08/11/2021 | 60 | M/S S.CHOUDHURY | 84.96 | 84.62 | 100 | 100
1746 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Joypur Part-I, at Hanskhali Block by retrofitting of Ground Water based PWSS for Joypur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte , SM/08812 | Retrofitting | Construction and installation of MANIFOLD and allied works at OHR site of Joypur and Mamjoani Water Supply Scheme in connection with Duttaphulia Zone-I under Nadia Arsenic Division-I, PHE Dte. as a part of JJM (Sl. No. 01) | 39/NAD-I | 07/04/2025 | 242 | REAL TIME | 39.28 | 0 | 0 | 50
1747 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) underJaldhara / Jal Swapna for Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08840 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 12/NAD-I | 05/01/2022 | 90 | UMWELT ENGINEER PVT. LTD. | 299.45 | 89.42 | 100 | 98
1748 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) underJaldhara / Jal Swapna for Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08840 | Retrofitting | Repair of 800 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at Barberia Zone-VIII under Surface W/S Scheme of Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no.05) | 1385/NAD-I | 12/08/2022 | 45 | TARUN KUMAR BHATTACHARYA | 32.36 | 32.3 | 100 | 100
1749 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) underJaldhara / Jal Swapna for Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08840 | Retrofitting | Retrofitting work at Ghetugachi G.P for Surface water based P.W.S.S for Chakdah ( Part ) in connection with providing FHTC at Barberia ( Zone- VIII ) Part- II under JJM within Chakdah Block under Nadia Arsenic Division-I , PHE Dte. (Sl.no.01) | 1685/NAD-I | 12/07/2023 | 21 | TAPAS GHOSH | 22.22 | 20.79 | 100 | 100
1750 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) underJaldhara / Jal Swapna for Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08840 | Retrofitting | Interconnection in between outlet pipe of OHR and delivery main at different H/W site in Chakdah SurfaceWater Based PWSS at Chakdah Block under JJM under Nadia Arsenic Division-I,PHE Dte. (sl.15) | 826/NAD-I | 31/03/2023 | 45 | BIPLAB GUHA | 39.73 | 36.71 | 100 | 58
1751 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) underJaldhara / Jal Swapna for Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08840 | Retrofitting | Retrofitting work at Mukundupur of Balagarichar W/S Scheme and Dakshin Panchpota, Kadambagachi of Barberia W/S Scheme in connection with providing FHTC Zone-VIII (Barberia) Part-II under Barberia W/S Scheme under Jal Jeevan Mission under Chakdah (Part) W/S Scheme under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.10) | 2154/NAD-I | 08/09/2023 | 764 | SUMAN CHAKRABORTY | 91.29 | 54.84 | 60.07 | 100
1752 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08841 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur, Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1418/NAD-I | 08/11/2021 | 60 | TAPU SAHA | 69.94 | 65.19 | 57.81 | 99
1753 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08841 | Retrofitting | Retrofitting work at Haradham village under Parniamatpur W/S Scheme under Ranaghat-I Block under Providing FHTC under Jal Jeevan Mission (JJM) for Parniamatpur Phase-I under Nadia Arsenic Division-I, P.H.E. Dte. | 84/AE-1/NAD-I | 03/02/2023 | 15 | AURGHA BHATTACHARYA | 2.05 | 1.89 | 100 | 100
1754 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08841 | Retrofitting | Retrofitting work at Rabonbor mouza near Sampa Biswas house and near Abodh Halder house under Parniamatpur Water Supply Scheme under Ranaghat-I Block under Providing FHTC under Jal Jeevan Mission (JJM) for Parniamatpur Phase-II under Nadia Arsenic Division-I, P.H.E. Dte. (SL No-2) | 85/AE-1/NAD-I | 06/02/2023 | 15 | GANGULY ENTERPRISE | 4.83 | 4.51 | 100 | 100
1755 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08841 | Retrofitting | Retrofitting work at Dakshin Haradham mouza (JI No 137) under Jal Jeevan Mission (JJM) for parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 165/AE-I/NAD-I | 11/04/2023 | 15 | MS ENTERPRISE | 0.97 | 0.97 | 100 | 0
1756 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08841 | Retrofitting | Retrofitting work at Paschim Sambhupur mouza (JI No 133) under Jal Jeevan Mission (JJM) for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Paniamatpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 163/AE-I/NAD-I | 10/04/2023 | 15 | GANGULY ENTERPRISE | 0.97 | 0.97 | 100 | 0
1757 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08841 | Retrofitting | Retrofitting work at Sibpur mouza (JI No 134) under Jal Jeevan Mission (JJM) for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground water based PWSS for parniamatpur Water Supply Scheme under Nadia Arsenic division-I, P.H.E. Dte. | 164/AE-I/NAD-I | 10/04/2023 | 15 | MS ENTERPRISE | 0.97 | 0.97 | 100 | 100
1758 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08841 | Retrofitting | Material Requisition To Resource Division | 143/NAD-I | 28/01/2022 | 0 | Resource Division | 0.8 | 0 | 0 | 0
1759 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-I Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofit , SM/08847 | Retrofitting | Construction of Boundary wall at H/W site of Goalsalua, Zone-I Water Supply Scheme under Nadia Arsenic Division-I,P.H.E. Dte. Length of Boundary wall - 208 metre. | 72/NAD-I | 17/01/2022 | 30 | NISHITH BANERJEE | 19.68 | 17.09 | 100 | 100
1760 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-I Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofit , SM/08847 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua, Zone-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Goalsalua Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1403/NAD-I | 08/11/2021 | 45 | BIDYUT KUMAR | 53.89 | 53.63 | 100 | 100
1761 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-I Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofit , SM/08847 | Retrofitting | Laying of additional pipeline for providing FHTC (Functional Household Tap Connection)at Salua Gatepara & pipeline connection with Manifold under JJM at Ranaghat-II Block of Ground Water Based PWSS for Goalsalua Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | 327/AE-II/NAD-I | 09/12/2024 | 15 | GOUTAM DEY | 4 | 0 | 0 | 0
1762 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-I Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofit , SM/08847 | Retrofitting | Construction and installation of MANIFOLD and allied works at OHR site under Goalsalua Zone-I Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Goalsalua Zone-I under JJM.(sl.no.06) | 1123 / NAD-I | 27/04/2023 | 15 | MANAJIT BISWAS | 13.03 | 12.7 | 100 | 100
1763 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-I Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofit , SM/08847 | Retrofitting | Balance work for revamping/upgradation of the hydraulic parameters at Hatisala and Goalsalua mouzas in reference to Goalsalua mouzas in reference to Goalsalua W/S Scheme under Nadia Arsenic Division-I, PHE Dte. as a part of JJM (Sl. No. 03) | 170/NAD-I | 29/04/2025 | 60 | PAPAN ROY | 44.03 | 0 | 0 | 0
1764 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-I Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofit , SM/08847 | Retrofitting | Jackpushing & other allied works near Bankim Nagar station (BNCA to PNCB) in between Mast No - 77/24 and 77/26 in the district of Nadia to provide FHTC at Kesaipur under Goalsalua PWSS under Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. (2nd Call) [Sl. No. 03] | 1042/NAD-I | 25/09/2025 | 90 | SUMAN CHAKRABORTY | 39.44 | 0 | 0 | 0
1765 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. , SM/09205 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. | 629/PFMS | 16/03/2022 | 0 | UMWELT ENGINEERS PVT LTD | 3.23 | 0 | 0 | 0
1766 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. , SM/09205 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Bablari Dewanganj to accommodate FHTC within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 338/ND | 25/01/2022 | 90 | JOY HIND TUBEWELL'S | 156.61 | 98.71 | 63.03 | 80
1767 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. , SM/09205 | Augmentation | Supply delivery & installation of submersible P/m alongwith allaied electrical mechanical works voltage stabilizer and automatic chlorinator etc. rejuvenation to Accomodate FHTC at P.h no.I & II under Bablari Dewanganj w/s scheme Block--Nabawdip Dist- Nadia | 6183/EMD | 14/11/2022 | 30 | M.S. ENTERPRISE | 15.63 | 14.89 | 100 | 75
1768 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. , SM/09205 | Augmentation | Material Requisition To Resource Division | 4293/ND | 29/09/2022 | 0 | Resource Division | 4.16 | 0 | 0 | 0
1769 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. , SM/09205 | Augmentation | Additional Laying of UPVC Pipeline and providing FHTC including supplying, laying, fitting, fixing of 15 mm NB PVC pipe with all necessary specials, saddle piece etc.in connection to the Augmentation of Ground Based piped water supply scheme at Bablari-Dewanganj to accommodate FHTC within Nabadwip block under Krishnanagar Sub-Division under Nadia Division, PHE Dte. | 1847/ND | 26/04/2023 | 60 | A.K.ADHIKARY | 15.77 | 1.6 | 100 | 95
1770 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. , SM/09205 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 250 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Bablari Dewanganj Water Supply Scheme within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 5125/ND | 17/11/2023 | 90 | SANJIB DEY | 24.91 | 21.14 | 100 | 98
1771 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. , SM/09205 | Augmentation | Providig FHTC at leftout household in connection to the Augmentation of Ground Based piped water supply scheme at Bablari Dewanganj to accommodate FHTC within Nabadwip block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | 1372/ND | 28/02/2024 | 315 | A.K.ADHIKARY | 21.74 | 20.85 | 100 | 70
1772 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. , SM/09205 | Augmentation | Conversion of IEP to AIRP of capacity 46 Cu.m/hr at Bablari Dewanganj Water Supply Scheme within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 1906/ND | 15/03/2024 | 560 | DEBASIS SAMADDAR | 104.21 | 0 | 0 | 70
1773 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. , SM/09205 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
1774 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09247 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-III W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 857/NACD-II | 08/11/2021 | 45 | S.K. CONSTRUCTION | 95.18 | 95.18 | 100 | 100
1775 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09247 | Retrofitting | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Helenchi Zone-III W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1197/NACD-II | 23/12/2022 | 15 | SUMIT GHOSH | 1.61 | 0 | 0 | 100
1776 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09247 | Retrofitting | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HELENCHI (Z-I, Z-II, Z-III) (Block- Krishnaganj ) AND BANSBERIA,CHANDPUR & DAMODARKHALI (Block- Krishnagar I) W/S Scheme, , Dist. - Nadia. NIET NO.- 31 of EE/EMD of 2022-23 (Sl. No.- 02) | 1121/EMD | 16/03/2023 | 30 | M.S. ENTERPRISE | 65.68 | 21.17 | 100 | 90
1777 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09247 | Retrofitting | Providing Functional House Hold Tap Connection including laying of pipeline at Helenchi Zone-III Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | 19/AE-II/NACD-II | 15/02/2024 | 15 | M/S SREE KRISHNA ENTERPRISE. | 0.97 | 0 | 0 | 0
1778 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09247 | Retrofitting | Jungle cutting at Mahatpur,Patharghata,Baliadanga,Helenchi Zone-III,Joyghata and Damodarkhali Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 820/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.16 | 0 | 100 | 100
1779 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09247 | Retrofitting | Renovation of Arsenic cum Iron treatment Plant of Helenchi Z-III PWSS (Capacity- 49 m3/hr) and ancillary works of Krishnaganj Block under Nadia Arsenic Civil Division-II P.H.E. Dte | 233/NACD-II | 21/02/2024 | 60 | B.M. ENGINEERING & CONSTRUCTION | 96.32 | 0 | 0 | 5
1780 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09247 | Retrofitting | Construction and installation of MANIFOLD, dedicated line and Distribution network for new FHTC at Taldaha Piped Water Supply Scheme and laying distribution network for FHTC and Repairing of Top Dome and related work for 250 cum RCC elevated reservoir at Helenchi Zone- III in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1571/NACD-II | 06/12/2024 | 270 | BIDYUT KUMAR | 105.92 | 0 | 0 | 40
1781 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-II WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09248 | Retrofitting | Construction of Boundary wall with Grill Gate at Helenchi ZoneII Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | 106/NACD-II | 10/02/2022 | 45 | BASUDEB SAHA | 5.37 | 5.21 | 97.09 | 100
1782 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-II WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09248 | Retrofitting | Special repairing for house connection and relaying of UPVC pipe line at Helenchi Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 59/AE-II/NACD-II | 23/02/2022 | 15 | VAI ENTERPRISE | 4.97 | 4.97 | 99.89 | 100
1783 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-II WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09248 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 871/NACD-II | 08/11/2021 | 45 | JOY HIND TUBEWELLS | 82.99 | 82.99 | 100 | 100
1784 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-II WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09248 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-I W/s Scheme (Vill- Krishnapur) in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 125/NACD-II | 21/02/2022 | 90 | A.P. POWER & CONCRETE | 105.67 | 0 | 0 | 100
1785 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-II WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09248 | Retrofitting | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Helenchi Zone-II W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1196/NACD-II | 23/12/2022 | 15 | BABLU MALLICK | 0.85 | 0.83 | 100 | 100
1786 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-II WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09248 | Retrofitting | Rejuvenation of Helenchi Zone-II W/S scheme in Krishnganj Block of Nadia under EMSD-III PHE Dte. | 472/ EMD | 16/03/2022 | 30 | BINAPANI ENTERPRISE | 5.38 | 5.38 | 100 | 100
1787 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-II WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09248 | Retrofitting | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HELENCHI (Z-I, Z-II, Z-III) (Block- Krishnaganj ) AND BANSBERIA,CHANDPUR & DAMODARKHALI (Block- Krishnagar I) W/S Scheme, , Dist. - Nadia. NIET NO.- 31 of EE/EMD of 2022-23 (Sl. No.- 02) | 1121/EMD | 16/03/2023 | 30 | M.S. ENTERPRISE | 65.68 | 0 | 0 | 90
1788 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-II WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09248 | Retrofitting | Functional House Hold Tap Connection for left out Household regarding Har Ghar Jal Certification including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Vill- Khatura) Helenchi Zone-II W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 149/NACD-II | 17/01/2023 | 20 | ZOOM CONSTRUCTION & INTERIO | 4.23 | 3.81 | 100 | 100
1789 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-II WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09248 | Retrofitting | Retrofitting of OHR, AIRP of Helenchi Zone-II as well as providing of FHTC as per consultation with ISA under Krishnaganj BLock in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1213/NACD-II | 17/10/2023 | 60 | M/S FREEDOM CONSTRUCTION | 93.16 | 93.14 | 100 | 90
1790 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-II WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09248 | Retrofitting | Renovation of Arsenic cum Iron treatment Plant of Helenchi Z-II PWSS (Capacity- 39 m3/hr) and ancillary works of Krishnaganj Block under Nadia Arsenic Civil Division-II P.H.E. Dte | 36/NACD-II | 09/01/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 120.13 | 103.57 | 100 | 100
1791 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-II WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09248 | Retrofitting | Material Requisition To Resource Division | 76/NACD-II | 15/01/2024 | 0 | Resource Division | 5.36 | 0 | 0 | 0
1792 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-II WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09248 | Retrofitting | Repair and Renovation work with Reinforced Barbed Tape ,Overhead Reservoir Plaster , Painting and other allied works at Helenchi Zone - II Headwork site and 2nd Pump house site under Helenchi Zone-II Piped Water Supply Scheme in Krishnaganj Block under Nadia Arsenic Division-II,P.H.E.Dte. | 08/NACD-II | 06/01/2025 | 60 | M/S INDUSTRIAL CONSTRUCTION | 9.66 | 0 | 0 | 100
1793 | NADIA | Nadia Division | Providing Functional House Tap Connection from Muktadaha Zone-I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/08664 | Retrofitting | Providing Functional House Tap Connection from Muktadaha Zone-I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | 606/PFMS | 11/03/2022 | 0 | OTHERS | 4.58 | 0 | 0 | 0
1794 | NADIA | Nadia Division | Providing Functional House Tap Connection from Muktadaha Zone-I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/08664 | Retrofitting | Providing Functional House Tap Connection from Muktadaha Zone-I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | 82/PFMS | 13/07/2022 | 0 | SANJIB DEY | 1.8 | 0 | 0 | 0
1795 | NADIA | Nadia Division | Providing Functional House Tap Connection from Muktadaha Zone-I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/08664 | Retrofitting | Material Requisition To Resource Division | 806/ND | 18/02/2022 | 0 | Resource Division | 4.94 | 0 | 0 | 0
1796 | NADIA | Nadia Division | Providing Functional House Tap Connection from Muktadaha Zone-I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/08664 | Retrofitting | Material Requisition To Resource Division | 1031/ND | 03/03/2022 | 0 | Resource Division | 8.59 | 0 | 0 | 0
1797 | NADIA | Nadia Division | Providing Functional House Tap Connection from Muktadaha Zone-I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/08664 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Muktadaha zone - I W/S scheme under Nadia Division, PHE Dte. | 5143/ND | 15/09/2021 | 75 | M/S NIBHAS SINHA | 68.32 | 42.45 | 62.13 | 100
1798 | NADIA | Nadia Division | Providing Functional House Tap Connection from Muktadaha Zone-I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/08664 | Retrofitting | providing house connection including supply of 15mm dia G.I/ PVC pipe of average length of 15 mtr, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete at Muktadaha Zone - I W/S scheme under Nadia Division P.H.Engineering Dte. (Part-A) | 927/PH | 10/08/2021 | 15 | B.M ENTERPRISE | 1.38 | 1.26 | 91.33 | 100
1799 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. , SM/09538 | Augmentation | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. | 612/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.69 | 0 | 0 | 0
1800 | NADIA | Eastern Mechanical | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. , SM/09538 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I & II Z-I under Bayra W/S Scheme District of 24 Pgs. (N) | 6186 EMD | 14/08/2022 | 30 | MA ANNAPURNA ENTERPRISE | 5.47 | 0 | 0 | 100
1801 | NADIA | Eastern Mechanical | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. , SM/09538 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator etc. Rejuvention to accommodate FHTC) at Z-I under Badelangi Padmamala W/S Scheme Block Chapra under District of Nadia) | 6186 / EMD | 14/08/2022 | 30 | MA ANNAPURNA ENTERPRISE | 5.47 | 5.47 | 100 | 0
1802 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. , SM/09538 | Augmentation | Material Requisition To Resource Division | 4297/ND | 29/09/2022 | 0 | Resource Division | 0.01 | 0 | 0 | 0
1803 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. , SM/09538 | Augmentation | Laying of Distribution system including specials & valves,Pipe supporting structure all complete based on actual estimate & providing FHTC for Badlangi Padmamala Zone-I Water Supply Scheme in Nadia District under Nadia Division.. | 954/ND | 25/02/2022 | 90 | APURBA MANDAL | 239.05 | 213.81 | 100 | 88
1804 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. , SM/09538 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir, Pump House, Boundary Wall and Construction of Service Road for Badlangi Padmamala Zone-I Water Supply Scheme under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 6113/ND | 21/12/2023 | 360 | CHOWDHURY & CO | 27.25 | 0 | 0 | 90
1805 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. , SM/09538 | Augmentation | Collection of Household data through mobile app for FHTC Connection (Phase-VI), under Nadia Division, P.H.E. Dte. | 222/KLYSD-I | 09/02/2024 | 182 | HORIZEN | 4.85 | 4.85 | 100 | 100
1806 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. , SM/09538 | Augmentation | Conversion of IEP to AIRP of capacity 62 Cu.m/hr at Badlangi Padmamala Zone-I Water Supply Scheme within Chapra block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. | 1912/ND | 15/03/2024 | 180 | B.M. ENGINEERING & CONSTRUCTION | 174.54 | 0 | 0 | 35
1807 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. , SM/09538 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site of Badlangi Padmamala Zone-I Water Supply scheme under RWS Sub Division under Nadia Division-,P.H.E Dte. | 7451/ND | 20/12/2024 | 180 | ROY ASSOCIATES | 85.97 | 0 | 0 | 25
1808 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10417 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | 15/PFMS | 11/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.8 | 0 | 0 | 0
1809 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10417 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under Gobrapota Naldaha W/S Scheme, Block- Krishnagar-I , Dist. - Nadia. NIET No. 33 of EE/EMD of 2022-23 (Sl. No.- 10) | 1175/EMD | 21/03/2023 | 30 | SWAPAN KUMAR BHANJA | 18.62 | 14.2 | 76.23 | 75
1810 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10417 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete and Construction Of 350 Cum Capacity 20 Mtr. Staging Height Rcc Over Head Reservoir (With Pile Foundation), Pipe Connection And Cost Of Pipes, Specials, Soil investigation for the work of construction of 350 cum OHR staging height 20 mtr., Construction Of 1 (One) No. Pump House (4.88m X 3.66m) Including Sanitary Arrangement And Construction Of Boundary Wall for Augmentation of Ground Based Water Supply Scheme at GOBRAPOTA to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte | 3509/ND | 10/08/2023 | 366 | M/S GHOSH CONSTRUCTION, SUKUL ROAD, P.O-KRISHNAGAR, DIST.NADIA, PIN-741101, WB | 587.44 | 0 | 0 | 0
1811 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10417 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Gobrapota W/S Scheme (TW-I) , Krishnagar-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 1658/CDD | 17/10/2023 | 30 | MENAKA ENTERPRISE | 18.88 | 0 | 0 | 0
1812 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10417 | Augmentation | Material Requisition To Resource Division | 122/ND | 05/01/2023 | 0 | Resource Division | 99.77 | 0 | 0 | 0
1813 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10417 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 1.4 | 98.71 | 40
1814 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10417 | Augmentation | Construction of 2 nos Pump House (3.6mtr. X 3.0 mtr.) at 1st & 2nd T/W site for Gobrapota water supply scheme under Krishnagar Sub-Division under Nadia Division PHE Dte. | 3263/ND | 10/06/2024 | 45 | M/S RAJESH CONSTRUCTION | 12.17 | 0 | 0 | 0
1815 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10417 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 62 m3/hr at Gobrapota Water Supply Scheme within Krishnagar-I Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | 6220/ND | 23/09/2024 | 180 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 198.01 | 0 | 0 | 0
1816 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10417 | Augmentation | Material Requisition To Resource Division | 264/ND | 11/01/2024 | 0 | Resource Division | 17.22 | 0 | 0 | 0
1817 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PASCHIM NOAPARA of Ranaghat-I Block, & SAGUNA of Santipur Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Re , SM/09957 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Paschim Noapara, Part-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 517/NAD-I | 28/03/2022 | 60 | GHOSH BROTHERS | 171.71 | 106.69 | 100 | 100
1818 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PASCHIM NOAPARA of Ranaghat-I Block, & SAGUNA of Santipur Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Re , SM/09957 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Saguna Part-III at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Saguna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 12) | 437/NAD-I | 07/03/2022 | 60 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD. | 63.41 | 52.13 | 100 | 100
1819 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PASCHIM NOAPARA of Ranaghat-I Block, & SAGUNA of Santipur Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Re , SM/09957 | Augmentation | Construction of Boundary wall, Pathway and all repair works at 2nd T/W Site and all repair works at H/W site of Saguna under Nadia Arsenic Division-I, PHE Dte. ( Sl.no 11) | 1592 / NAD-I | 06/09/2022 | 45 | PAPAN ROY | 11.31 | 8.33 | 100 | 85
1820 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PASCHIM NOAPARA of Ranaghat-I Block, & SAGUNA of Santipur Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Re , SM/09957 | Augmentation | Construction of Boundary Wall, Pathway and all repair works at 2nd T/W site and all repair works at H/W site of Paschim Noapara W/S Scheme under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no.02) | 2009/NAD-I | 19/10/2022 | 30 | J & T ENTERPRISE | 6.93 | 6.73 | 100 | 100
1821 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PASCHIM NOAPARA of Ranaghat-I Block, & SAGUNA of Santipur Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Re , SM/09957 | Augmentation | Repair of 450 cum capacity Over Head Reservoir and other allied works at Saguna WS Scheme in Santipur Block under NAD I PHE Dte (Sl.no.04) | 2049 / NAD-I | 21/10/2022 | 45 | M/S ARATI ENTERPRISE | 14.01 | 13.2 | 100 | 100
1822 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PASCHIM NOAPARA of Ranaghat-I Block, & SAGUNA of Santipur Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Re , SM/09957 | Augmentation | Repair of 350 cum capacity Over Head Reservoir and other allied works at Paschim Noapara W/S Scheme in Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E Dte.(Sl.no.07) | 1443/NAD-I | 17/09/2022 | 45 | MONDAL ENTERPRISE | 12.83 | 11.65 | 100 | 100
1823 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PASCHIM NOAPARA of Ranaghat-I Block, & SAGUNA of Santipur Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Re , SM/09957 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Hijuli, Ghoshpara, Aluipara & adjacent areas of Shantipur Block by retrofitting of Ground Water Based PWSS for Saguna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | 2744/NAD-I | 08/12/2023 | 15 | DEBASIS SAMADDAR | 57.4 | 49.02 | 85.4 | 70
1824 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PASCHIM NOAPARA of Ranaghat-I Block, & SAGUNA of Santipur Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Re , SM/09957 | Augmentation | Pipeline connection with Manifold to dedicated line under Jal Jeevan Mission (JJM) at Shantipur Block under Ground Water based PWSS for Saguna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | 95/AE-I/NAD-I | 27/02/2024 | 15 | ROY ASSOCIATES | 2.89 | 2.89 | 100 | 100
1825 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PASCHIM NOAPARA of Ranaghat-I Block, & SAGUNA of Santipur Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Re , SM/09957 | Augmentation | Retrofitting pipeline works for providing FHTC (Functional Household Tap Connection) at Aluipara & Srirampur para under JJM at Shantipur Block of Ground Water Based PWSS for Saguna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 04) | 1543/NAD-I | 23/09/2024 | 405 | TAPAS GHOSH | 10.69 | 0 | 0 | 80
1826 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VI within Kaliganj Block. (Phase-C) , SM/08961 | Retrofitting | Laying additional distribution pipeline for providing FHTC at Sherpur Village zone-VI Phase- C, Part- I , Surface water based Water Supply Scheme, Nadia Northern Sector , Kaliganj Block. | 175/A/DSD | 18/04/2022 | 30 | BALAJEE ENTERPRISE | 1.54 | 1.52 | 100 | 100
1827 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VI within Kaliganj Block. (Phase-C) , SM/08961 | Retrofitting | Laying additional distribution pipeline for providing FHTC at zone-VI Phase- C, Part- I , Surface water based Water Supply Scheme, Nadia Northern Sector , Kaliganj Block. | 48/DSD | 07/02/2022 | 15 | BALAJEE ENTERPRISE | 4.95 | 4.93 | 100 | 100
1828 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VI within Kaliganj Block. (Phase-C) , SM/08961 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-VI within Kaliganj Block(Phase-C) | 7058/ND | 06/12/2021 | 90 | BALAJEE ENTERPRISE | 176.9 | 169.22 | 95.66 | 0
1829 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VI within Kaliganj Block. (Phase-C) , SM/08961 | Retrofitting | Material Requisition To Resource Division | 429/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0 | 0
1830 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VI within Kaliganj Block. (Phase-C) , SM/08961 | Retrofitting | Material Requisition To Resource Division | 4309/ND | 29/09/2022 | 0 | Resource Division | 24.88 | 0 | 0 | 0
1831 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VI within Kaliganj Block. (Phase-C) , SM/08961 | Retrofitting | Filling fine sand over upvc pipeline for road restoration work at nimtala juranpur road(both side of road) in connection with augmentation of surface water based w/s scheme for Arsenic affected areas of Nadia district( Northern sector part-I) under Nadia Division PHE Dte. | 918KlySD-I | 07/06/2024 | 15 | UMWELT ENGINEER PVT LTD | 13.46 | 10.31 | 100 | 100
1832 | NADIA | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia , SM/10422 | Augmentation | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia | 10/PFMS | 11/05/2022 | 0 | HORIZEN | 2.89 | 0 | 0 | 0
1833 | NADIA | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia , SM/10422 | Augmentation | Material Requisition To Resource Division | 4320/ND | 29/09/2022 | 0 | Resource Division | 0.02 | 0 | 0 | 0
1834 | NADIA | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia , SM/10422 | Augmentation | Material Requisition To Resource Division | 2584/ND | 13/06/2023 | 0 | Resource Division | 15.12 | 0 | 0 | 0
1835 | NADIA | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia , SM/10422 | Augmentation | Material Requisition To Resource Division | 1879/ND | 26/04/2023 | 0 | Resource Division | 13.4 | 0 | 0 | 0
1836 | NADIA | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia , SM/10422 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Purba Khamarsimulia PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 105.00 Cu.m/hr | 136/ND | 09/01/2024 | 90 | M/S R.K.ENTERPRISE | 99.27 | 0 | 0 | 0
1837 | NADIA | Eastern Mechanical | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia , SM/10422 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I , II under Purba Khamar Simulia ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. | 1308/EMD | 09/05/2024 | 30 | SHIVAM ENTERPRISE | 23.6 | 21.7 | 100 | 100
1838 | NADIA | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia , SM/10422 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete by augmentation of Purba Khamarsimulia Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.Engineering Dte. | 3404/ND | 01/08/2022 | 724 | B.M. ENGINEERING & CONSTRUCTION | 330.45 | 252.33 | 76.36 | 92
1839 | NADIA | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia , SM/10422 | Augmentation | Supplying and laying of distribution system including providing Functional Household Tap Connection (FHTC) for Augmentation of Purbakhamar Simulia Piped Water Supply Scheme under Ranaghat Sub-Division, under Nadia Division, PHE Dte.. | 5224/ND | 24/11/2023 | 755 | B.M. ENGINEERING & CONSTRUCTION | 215.24 | 134.98 | 74.48 | 75
1840 | NADIA | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia , SM/10422 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Purba Khamarsimulia under Ranaghat Sub-Division under Nadia Division PHE Dte. | 1427/RSD | 19/11/2024 | 45 | MANARAMA ENTERPRISE | 2.15 | 0 | 0 | 100
1841 | NADIA | Eastern Mechanical | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia , SM/10422 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at PURBA KHAMAR SIMULIA W/S Scheme Block- Hanskhali under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10422] | 1147/EMD | 04/06/2025 | 90 | M.S. ENTERPRISE | 51.04 | 0 | 0 | 0
1842 | NADIA | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia , SM/10422 | Augmentation | Supplying and laying of distribution and rising main for Augmentation of Ground water based water supply scheme of Purba Khamarsimulia under Hanskhali Block under Ranaghat Sub-Division under Nadia Division P.H.Engineering Dte. | 2264/ND | 15/05/2025 | 90 | B.M. ENGINEERING & CONSTRUCTION | 75.28 | 0 | 0 | 0
1843 | NADIA | Nadia Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia , SM/10422 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
1844 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09270 | Augmentation | OUTSTANDING BILL PAYMENT FOR SUPPLY OF MATERIALS FOR THANAPARA, DAMODARKHALI, MADHABPUR, BALIADANGA AS FRAMED BY RESOURCE DIVISION PHE DTE. |  | 05/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0 | 0
1845 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09270 | Augmentation | SUPPLY OF MATERIALS FOR THANAPARA,DAMODARKHALI,MADHABPUR AND BALIADANGA W/S. SCHEME UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. |  | 07/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0 | 0
1846 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09270 | Augmentation | Outstanding as framed by Resource Division for supply of materials for augmentation/retrofitting of Thanapara, Damodarkhali & Madhabpur under Nadia Arsenic Civil Division-II, PHE dte. | 212, 213, 214 | 18/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 124.39 | 0 | 0 | 0
1847 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09270 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Madhabpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 281/NACD-II | 22/02/2021 | 21 | JOY HIND TUBEWELLS | 60 | 0 | 0 | 100
1848 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09270 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Madhabpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 274/NACD-II | 22/02/2021 | 21 | JOY HIND TUBEWELLS | 60.6 | 0 | 0 | 100
1849 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09270 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Madhabpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 864/NACD-II | 08/11/2021 | 45 | H. I. ENTERPRISE | 56.74 | 56.72 | 100 | 100
1850 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09270 | Augmentation | Raising the height of the Boundary wall with Barbed Weir fencing with angle and also fabrication of new Grill Gate for protection work at Madhabpur Water Supply Scheme H/W site under Nadia Arsenic Civil Division-II PHE Dte. | 477/NACD-II | 27/07/2022 | 45 | SAMAR ENTERPRISE | 4.99 | 4.72 | 100 | 100
1851 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09270 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Madhabpur Water Supply Scheme in Chapra Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 326/1/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.61 | 1.61 | 100 | 100
1852 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09270 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Madhabpur W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | 523/AE-I/NACD-II | 18/12/2023 | 15 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 0.96 | 0.76 | 100 | 100
1853 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09270 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Madhabpur W/S Scheme Village:- Ichhapur under Habitation of Amtalapara,purbapara and bakultala in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 638/AE-I/NACD-II | 12/02/2024 | 15 | PRADUT GHOSH | 0.96 | 0.93 | 100 | 100
1854 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09270 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Madhabpur W/S Scheme Village:- Ichhapur under Habitation of Ichhapur,Bat Tala and Bagdipara in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 637/AE-I/NACD-II | 12/02/2024 | 15 | SUJAUDDIN SHAIKH | 0.97 | 0.92 | 100 | 100
1855 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09270 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Madhabpur W/S Scheme Village:- Ichhapur under Habitation of Baroyaritala in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 639/AE-I/NACD-II | 12/02/2024 | 15 | RAJIB DUTTA | 0.96 | 0.95 | 100 | 100
1856 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09270 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Madhabpur W/S Scheme village:- Patia under Habitation of Purba Para and Biswas Para in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1097/AE-I/NACD-II | 31/12/2024 | 120 | SHYAMAL KANTI GHOSH | 0.97 | 0 | 0 | 100
1857 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09270 | Augmentation | Sinking of 2 nos. 300 mm X 200 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at new proposed site of Gongra Zone-I and Zone-II in Chapra Block under Gongra Public Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 1527/NACD-II | 27/11/2024 | 270 | SANDIP BISWAS | 21.68 | 0 | 0 | 55
1858 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Karuigachhi and adjoining mouzas under Karuigachhi Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | 303/NACD-II | 20/05/2022 | 90 | JOY HIND TUBEWELLS | 152.87 | 147.26 | 96.33 | 100
1859 | NADIA | Eastern Mechanical | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | NEW SERVICE CONNECTION CHARGES FOR KARUIGACHHI W/S SCHEME P .H NO I &II | 2868/EMD | 21/07/2022 | 30 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.24 | 0 | 0 | 0
1860 | NADIA | Eastern Mechanical | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | NEW SERVICE CONNECTION FOR KARUIGACHI W/S SCHEME FOR P.H NO 1 | 2869/EMD | 21/07/2022 | 30 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.07 | 0 | 0 | 0
1861 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Soil Investigation for Construction of 3 (Three) Nos. of Overhead Reservoir of staging height of 20 mtr. Under Nadia Arsenic Civil Division-II P.H.E. Dte. Site - Jitpur W/s Scheme, Kanainagar W/s Scheme, Karuigachhi W/s Scheme | 250/AE-I/NACD-II | 25/02/2022 | 15 | PROSENJIT DAS | 2.44 | 2.44 | 100 | 100
1862 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Soil Investigation for Construction of 3 (Three) Nos. of Overhead Reservoir of staging height of 20 mtr. Under Nadia Arsenic Civil Division-II P.H.E. Dte. Site - Mrigi W/s Scheme, Panchdara Abhaynagar W/s Scheme, Paninala W/s Scheme | 252/AE-I/NACD-II | 25/02/2022 | 15 | PROSENJIT DAS | 2.44 | 0 | 0 | 100
1863 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
1864 | NADIA | Eastern Mechanical | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | New service connection charges bill KARUIGACHHI W/s Scheme | BP-2022-23-29 | 02/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.16 | 0 | 0 | 0
1865 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
1866 | NADIA | Eastern Mechanical | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | New Service connection bill for KARUIGACHHI PIPED WATER SUPPLY SCHEME | BP-2022-23-28 | 02/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.07 | 0 | 0 | 0
1867 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Karuigachhi 2nd Tubwell site within Karuigachhi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 118/NACD-II | 11/01/2023 | 60 | MAYA ENTERPRISE | 4.78 | 4.41 | 92.25 | 85
1868 | NADIA | Eastern Mechanical | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Supply delivery of PCC Pole MS materials and electrical accessories including stringing and sagging of LTOH line to WBSEDCL for new connectionat PH-II under Karuigachi W/S Scheme. | 1395/SD-III | 14/08/2022 | 30 | R.N.S. TRADING | 1.03 | 1.03 | 100 | 0
1869 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Karuigachhi water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | 19/AE-I/NACD-II | 13/04/2022 | 60 | NIVEDITA CONSTRUCTION | 2.83 | 2.81 | 100 | 100
1870 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Karuigachhi water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 210/NACD-II | 05/04/2022 | 60 | NIVEDITA CONSTRUCTION | 5.38 | 5.33 | 100 | 100
1871 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Bhatgachhi and Karuigachhi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 246/NACD-II | 19/04/2022 | 60 | JOY HIND TUBEWELLS | 41.88 | 0 | 0 | 100
1872 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Karuigachhi Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 621/NACD-II | 06/09/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.96 | 3.96 | 100 | 100
1873 | NADIA | Eastern Mechanical | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Supply delivery of PCC Pole M.s materials and Electrical accessories and installation DTR of HTOH line to WBSEDCL for new service connection at PH-I under Karuigachi W/S Scheme | 1227/EMSD-III | 21/10/2022 | 30 | M/S G.P. ENTERPRISE | 5.17 | 5.17 | 100 | 10
1874 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Karuigachhi) | 917/NACD-II | 01/09/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
1875 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Material Requisition To Resource Division | 396/NACD-II | 04/07/2022 | 0 | Resource Division | 38.34 | 0 | 0 | 0
1876 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Karuigachhi Water Supply Scheme at Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | 79/NACD-II | 10/01/2023 | 60 | A.S. CONSTRUCTION | 14.61 | 14.21 | 97.28 | 85
1877 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 38 cum/Hour capacity for Karuigachhi Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1153/NACD-II | 27/08/2024 | 180 | PUSPA ENTERPRISE | 168.65 | 0 | 0 | 0
1878 | NADIA | Eastern Mechanical | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Headworks) under Karuigachhi W/S Scheme Dist.-Nadia. NIET NO.- 16 of EE/EMD OF 2022-23 (Sl. No.- 03) | 5011/EMD | 03/11/2022 | 30 | M/S. G.P. ENTERPRISE | 10.13 | 10 | 100 | 100
1879 | NADIA | Eastern Mechanical | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Karuigachhi W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 04) | 5012/EMD | 03/11/2022 | 30 | JAL PRAVAHIKA PVT. LTD. | 10.11 | 10.09 | 100 | 100
1880 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Construction of approch road at Head Works site of Karuigachi Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | 404/AE-I/NACD-II | 08/08/2023 | 15 | SANDIP BISWAS | 0.97 | 0.96 | 100 | 100
1881 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Continuation work order for Construction of approch road at Head Works site of Karuigachi Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | 837_AE-I/NACD-II | 01/08/2024 | 15 | SANDIP BISWAS | 0.93 | 0.92 | 100 | 100
1882 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Karuigachi) | 433/NACD-II | 15/03/2024 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
1883 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Karuigachhi water supply scheme of Chapra Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist-Nadia. | 525/NACD-II | 08/05/2023 | 1097 | SANDIP BISWAS | 116.49 | 49.12 | 42.16 | 95
1884 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Construction and installation of MANIFOLD and allied works at OHR site under Bagberia Piped Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1582/NACD-II | 11/12/2024 | 270 | SANDIP BISWAS | 111.44 | 0 | 0 | 75
1885 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Conversion of IEP to AIRP at Balidanga Water Supply Scheme of capacity 58 Cu.m/hr in Chapra Block including other works at Bhatgachhi & Karuigachhi Water Supply Scheme under Nadia Arsenic Civil Division -II, PHE Dte. | 1048/NACD-II | 07/08/2024 | 60 | DEBASIS SAMADDAR | 185.55 | 0 | 0 | 0
1886 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Continuation Work Order for Construction of approch road at Head Works site of Karuigachi Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | 1165/AE-I/NACD-II | 31/01/2025 | 15 | SANDIP BISWAS | 0.97 | 0 | 0 | 0
1887 | NADIA | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME , SM/10106 | New | Laying of Rising Main of Karuigachhi Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | 25/AE-I/NACD-II | 13/04/2022 | 1020 | SURAJIT KUMAR GHOSH | 4.28 | 2.43 | 70.08 | 90
1888 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-A). , SM/07497 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-A). |  | 25/03/2021 | 0 | UMWELT ENGINEERS PVT LTD | 59.66 | 0 | 0 | 0
1889 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-A). , SM/07497 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-V within Nakashipara Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte.(SL.2) | 971/ND | 25/02/2021 | 90 | UMWELT ENGINEERS PVT LTD | 97 | 171.23 | 176.53 | 0
1890 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-A). , SM/07497 | Retrofitting | Material Requisition To Resource Division | 818/ND | 18/02/2022 | 0 | Resource Division | 4.12 | 0 | 0 | 0
1891 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10524 | Augmentation | Material Requisition To Resource Division | 5202/ND | 14/12/2022 | 0 | Resource Division | 38.66 | 0 | 0 | 0
1892 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10524 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | 21/PFMS | 20/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.87 | 0 | 0 | 0
1893 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10524 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC at under GANGNAPUR W/S Scheme, Block-Ranaghat , Dist. - Nadia. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 11) | 1583/EMD | 24/04/2023 | 30 | A.S. ENTERPRISE | 25.94 | 0 | 0 | 0
1894 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10524 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Gangnapur W/S Scheme (TW-I) , Ranaghat-II Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 1234/CDD | 04/09/2023 | 30 | DEV AND COMPANY | 18.88 | 0 | 0 | 0
1895 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10524 | Augmentation | Providing functional household tap connection including supply of 15mm dia PVC pipe of average length of 15 mtr along with laying of different dia UPVC pipe line and other allied works etc all complete for AUGMENTATION Of GANGNAPUR W/S scheme (for Gangnapur & Korabari Mouza) under Ranaghat Sub Division of Nadia Division P.H.Engineering Dte. | 3530/ND | 05/08/2022 | 90 | APURBA MANDAL | 393.18 | 388.5 | 100 | 80
1896 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10524 | Augmentation | Material Requisition To Resource Division | 4289/ND | 29/09/2022 | 0 | Resource Division | 24.31 | 0 | 0 | 0
1897 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10524 | Augmentation | Laying of different dia UPVC pipe and other allied works etc. all complete for augmentation of Gangnapur W/S Scheme (for Gangnapur and Korabari Mouza) under Ranaghat Sub-Division of Nadia Division P.H. Engineering Dte. | 920/RSD | 13/09/2023 | 40 | APURBA MONDAL, VILL+P.O. BADKULLA, DIST.NADIA, PIN-741121 W.B | 3.91 | 3.87 | 100 | 100
1898 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10524 | Augmentation | Balance Laying of different dia UPVC pipe and other allied works etc. all complete for augmentation of Gangnapur W/S Scheme (for Gangnapur and Korabari Mouza) under Ranaghat Sub-Division of Nadia Division P.H. Engineering Dte. | 923/RSD | 14/09/2023 | 30 | APURBA MONDAL, VILL+P.O. BADKULLA, DIST.NADIA, PIN-741121 W.B | 4.59 | 4.58 | 100 | 100
1899 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10524 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
1900 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09811 | Augmentation | Repairing and renovation of pump house, compressor room , boundary , extension of drain & other allied works at Ber ramchandrapur pump house no: 1 under Ber ramchandrapur zone:1 Karimpur -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | 676/ Kly SD-I | 26/07/2022 | 30 | CHOWDHURY & CO. | 4 | 3.99 | 100 | 100
1901 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09811 | Augmentation | PROVIDING DRILLING CREWS & OTHER MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 120 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR BERRAMCHANDRAPUR ZONE-I W/S SCH (2ND TUBE WELL SITE), KARIMPUR-I BLOCK UNDER NADIA DISTRICT, CMSD-I (D), CDD, PHE DTE. | 375/CMSD-I | 05/08/2022 | 15 | UNIVERSAL ENTERPRISES | 3.7 | 3.7 | 100 | 0
1902 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09811 | Augmentation | PROVIDING 300MM & 200MM NOMNAL DIA UPVC PIPE CONFORMING TO IS 12818:2010 & OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BERRAMCHANDRAPUR ZONE-I (2ND TUBE WELL) W/S SCH, KARIMPUR BLOCK UNDER NADIA DISTRICT CMSD-I (D), CDD, PHE DTE. | 376/CMSD-I | 05/08/2022 | 15 | UNIVERSAL ENTERPRISES | 3.8 | 3.8 | 100 | 0
1903 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09811 | Augmentation | SUPPLY & DELIVERY PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED & OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BERRAMCHANDRAPUR ZONE-I (2ND TUBE WELL SITE) W/S SCH, KARIMPUR BLOCK UNDER CMSD-I (D), CDD, PHE DTE. | 377/CMSD-I | 05/08/2022 | 15 | UNIVERSAL ENTERPRISES | 2.07 | 1.7 | 100 | 0
1904 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09811 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | 620/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.78 | 0 | 0 | 0
1905 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09811 | Augmentation | Laying of distribution system including specials, Valves & Pipe supporting structure all complete based on actual estimate & providing FHTC for Ber Ramchandrapur Zone-I Water Supply Scheme in Nadia District under Nadia Division. | 1207/ND | 14/03/2022 | 90 | SANDIP BISWAS | 115.92 | 115.91 | 100 | 100
1906 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09811 | Augmentation | Repairing and renovation of pump house, dismantling part of boundary wall & re - construction it, land development , & construction of bath room with other allied works at Ber ramchandrapur pump house no: II under Ber ramchandrapur zone:1 Karimpur -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | 677/ Kly SD-I | 26/07/2022 | 30 | RAJAT ENTERPRISE | 4.98 | 4.98 | 100 | 100
1907 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09811 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accomodate FHTC under BERRAMCHANDRAPUR (Zone-I) W/S Scheme, Block- Karimpur-I , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 06) | 409/EMD | 20/01/2023 | 30 | SHIVAM ENTERPRISE | 15.53 | 14.87 | 100 | 100
1908 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09811 | Augmentation | Material Requisition To Resource Division | 1263/ND | 16/03/2022 | 0 | Resource Division | 5.58 | 0 | 0 | 0
1909 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09811 | Augmentation | Material Requisition To Resource Division | 1033/ND | 03/03/2022 | 0 | Resource Division | 4.64 | 0 | 0 | 0
1910 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09811 | Augmentation | Material Requisition To Resource Division | 2506/ND | 08/06/2022 | 0 | Resource Division | 2.86 | 0 | 0 | 0
1911 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09811 | Augmentation | Conversion of IEP to AIRP of capacity 32 Cu.m/hr at Ber Ramchandrapur Zone-I Water Supply Scheme within Karimpur-I block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. | 1908/ND | 15/03/2024 | 120 | M/S R.K.ENTERPRISE | 124.95 | 0 | 0 | 0
1912 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09811 | Augmentation | Interconnection of newly sunk tubewell at 2nd Pump House including cleaning of rising main and allied works at Ber Ramchandrapur Zone-I Water Supply Scheme, Karimpur-I Block, Nadia. | 1162/Kly SD-1 | 16/12/2022 | 15 | SANDIP BISWAS | 0.95 | 0.95 | 99.87 | 100
1913 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA , SM/10688 | Augmentation | Material Requisition To Resource Division | 5101/ND | 08/12/2022 | 0 | Resource Division | 3.64 | 0 | 0 | 0
1914 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA , SM/10688 | Augmentation | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA | 48/PFMS | 22/06/2022 | 0 | HORIZEN | 2.8 | 0 | 0 | 0
1915 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA , SM/10688 | Augmentation | Conversion of IEP to AIRP of capacity 120 Cu.m/hr at Gopinathpur Water Supply Scheme within Tehatta-II Block block under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 6841/ND | 12/11/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 172.22 | 0 | 0 | 0
1916 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA , SM/10688 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground basaed piped water supply scheme for Gopinathpur water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 7125/ND | 09/12/2024 | 90 | REAL TIME | 37.78 | 0 | 0 | 0
1917 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA , SM/10688 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under DAKSHINPARA (Zone-I & II) W/S Scheme, Block- Hanskhali , AND GOPINATHPUR W/S Scheme, Block- Tehatta-II, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 01) | 496/EMDdt.24.01.2023 | 17/03/2023 | 656 | GLACIER ENGINEERING CO. | 66.71 | 37.35 | 88.81 | 100
1918 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA , SM/10688 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., construction of 400 cum capacity 20 mtr. staging height rcc over head reservoir (including pile foundation), pipe connection and cost of pipes, specials. and soil investigation all complete for Augmentation of Ground Based Water Supply Scheme at Gopinathpur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 4226/ND | 27/09/2022 | 1131 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 766.15 | 346.25 | 45.19 | 65
1919 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA , SM/10688 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Gopinathpur Ground Based Water Supply Scheme under Tehatta-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Gopinathpur at Tehatta-II Block by Augmentation of Ground Water based PWSS for Tehatta-II Water Supply Schemes under Nadia Division, PHE Dte. | 419/ND | 27/01/2025 | 60 | DAS CONSTRUCTION | 26.96 | 0 | 0 | 0
1920 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA , SM/10688 | Augmentation | Laying pipe line of rising main at Gopinathpur Under Augmentation of Gopinathpur PWSS under Tehatta Sub-Division Under Nadia Division PHE Dte. | 7452/ND | 20/12/2024 | 270 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 54.97 | 0 | 0 | 0
1921 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA , SM/10688 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at GOPINATHPUR W/S Scheme Block- Tehatta-II under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10688] | 1138/EMD | 04/06/2025 | 90 | ABHISEK ENGINEERING CONCERN | 52.38 | 0 | 0 | 0
1922 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA , SM/10688 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
1923 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | 731/PFMS | 30/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.17 | 0 | 0 | 0
1924 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | 732/PFMS | 30/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.26 | 0 | 0 | 0
1925 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Construction of barbed wire fencing with concrete pillars at Baraya Zone-II (2nd T.W). water supply scheme( New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . | 930/TSD | 14/03/2023 | 7 | PRABIR KUMAR ROY | 0.7 | 0.69 | 99.76 | 0
1926 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No.- I & II under Baraia W/S Scheme, Block-Tehatta-II, Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 04) | 408/EMD | 20/01/2023 | 30 | PADMA ENGINEERING CO. | 22.18 | 21.91 | 100 | 55
1927 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Material Requisition To Resource Division | 152/ND | 06/01/2023 | 0 | Resource Division | 26.67 | 0 | 0 | 0
1928 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Construction of 250 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of 250 CUM OHR at Bareya Zone-II W/S. scheme under Nadia Division P.H.E. Dte. in the District of Nadia . | 3980/ND | 22/07/2024 | 365 | CHOWDHURY & CO. | 130.34 | 0 | 0 | 0
1929 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Bareya Zone-II Ground Based Water Supply Scheme under Tehatta-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Bareya Zone-II at Bareya Zone-II Block by Augmentation of Ground Water based PWSS for Bareya Zone-II Water Supply Schemes under Nadia Division, PHE Dte. | 7361/ND | 18/12/2024 | 60 | M/S DURGA SECURITIES & SERVICES | 20.41 | 0 | 0 | 0
1930 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Quotation charges and security deposit for new power connection at Baraia(Zone-II) head worksite under Eastern Mechanical Subdivision-III, Nadia | BP-195-24-25 | 17/12/2024 | 0 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 14.83 | 0 | 0 | 0
1931 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Quotation charges and security deposit for new power connection at Baraia(Zone-II) PH-II under Eastern Mechanical Subdivision-III, Nadia | BP-176 | 13/12/2024 | 0 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 4.04 | 0 | 0 | 0
1932 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Sinking of 80 mm dia. Shallow Tube Well for requirement of drilling water for Baraia PWSS, District - Nadia and other PWSS under CMSD-II (D), CDD, PHE Dte. | 91/CMSD-II | 17/04/2023 | 684 | PADMA ENGINEERING & CO. | 0.89 | 0 | 0 | 15
1933 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Construction Of Pump House (3.6x 3.0m) Including Sanitary Arrangement and construction of boundary wall at Tube well No-2 Site at Bareya Water Supply Scheme(Z-II) Under Tehatta Sub-Division PHE Dte.) | 1625/ND | 07/03/2024 | 360 | ROY ASSOCIATES | 12.15 | 0 | 0 | 0
1934 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Repairing and renovation works of Pump House and allied works of ground based piped water supply scheme for Bareya Zone-I water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 6695/ND | 29/10/2024 | 90 | SHREEOM ENTERPRISE | 13.79 | 0 | 0 | 0
1935 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of 54 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Bareya Zone-I to accommodate FHTC within Tehatta-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | 4315/ND | 06/08/2024 | 360 | MONDAL PRECISION PRIVATE LIMITED | 186.88 | 0 | 0 | 0
1936 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangement and construction of Boundary wall at Head Work Site of Bareya Zone-II Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | 4076/ND | 26/07/2024 | 180 | MANAJIT BISWAS | 22.65 | 0 | 0 | 40
1937 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- II) at Bareya Zone-I to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 4077/ND | 26/07/2024 | 420 | SANJIB DEY | 58.82 | 0 | 0 | 75
1938 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Bareya Zone-II to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 4074/ND | 26/07/2024 | 450 | CHOWDHURY & CO. | 185.28 | 0 | 0 | 10
1939 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under BARAIA ground water based water supply scheme under Block_ Tehatta-II Dist. - Nadia under EMD, PHE Dte. SM/10269 | 1118/EMD | 04/06/2025 | 90 | GHOSH AND GHOSH | 17.48 | 0 | 0 | 0
1940 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 42 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Bareya Zone-II to accommodate FHTC within Tehatta-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | 4143/ND | 29/07/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 173.48 | 0 | 0 | 0
1941 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Bareya Zone-I Ground Based Water Supply Scheme under Tehatta-II Block under Nadia Division, P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Bareya Zone-I at Tehatta-II Block by Augmentation of Ground Water based PWSS for Bareya Zone-I Water Supply Schemes under Nadia Division, PHE Dte. | 2460/ND | 27/05/2025 | 60 | S.D. CONSTRUCTION | 23.36 | 0 | 0 | 0
1942 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. , SM/10269 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Bareya Zone-I to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 1249/ND | 16/03/2022 | 468 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 196.39 | 189.23 | 99.62 | 100
1943 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10597 | Augmentation | Material Requisition To Resource Division | 143/ND | 06/01/2023 | 0 | Resource Division | 107.61 | 0 | 0 | 0
1944 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10597 | Augmentation | Material Requisition To Resource Division | 2322/ND | 29/05/2023 | 0 | Resource Division | 16.74 | 0 | 0 | 0
1945 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10597 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Tehatta (Phase-2) Ground Based Water Supply Scheme under Tehatta-I Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tehatta (Phase-2) at Tehatta- I Block by Augmentation of Ground Water based PWSS for Tehatta (Phase-2) Water Supply Schemes under Nadia Division, PHE Dte. | 7362/ND | 18/12/2024 | 60 | MANISHIKA CONSTRUCTION | 20.92 | 0 | 0 | 0
1946 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10597 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 135 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Tehatta to accommodate FHTC within Tehatta-I block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | 4230/ND | 02/08/2024 | 180 | TARUN KUMAR BHATTACHARYA | 315.65 | 0 | 0 | 0
1947 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10597 | Augmentation | Collection of Household data through mobile app for FHTC Connection at followingschemes under Nadia Division PHE Dte.Schemes: i) Hanspukuria (Zone-II) ii) Tehatta (Phase-II) iii) Dhoradaha iv)Karimpur Jalangi(Zone-XA) v)Karimpur Jalangi(Zone-XB) vi) Hanspukuria (Zone-I) | 371/ Kly SD-I | 17/03/2023 | 184 | HORIZEN | 4.96 | 4.96 | 100 | 100
1948 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10597 | Augmentation | Sinking of Tube Well at Tehatta PH-2 including dismantling of old pump house for entry of tube well rig, construction of pump house and boundary wall under Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatta (Phase-II) at Tehatta-I block under Nadia Division, PHE Dte. | 1545/ND | 05/04/2023 | 540 | JOY HIND TUBEWELL'S | 36.83 | 11.46 | 44.35 | 100
1949 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10597 | Augmentation | Reimbursement of additional GST due to enhancement of rate from 12% to 18% vide notification no 03/2022 central tax rate dt-13.07.2022 | 126/PFMS | 23/07/2024 | 0 | H I ENTERPRISE | 24.42 | 0 | 0 | 0
1950 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10597 | Augmentation | Laying of additional pipeline for Tehatta PWSS".under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 4576/ND | 21/08/2024 | 240 | SHYAMAL SHIL | 21.44 | 0 | 0 | 0
1951 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10597 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube well and Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I,II,III,IV under Tehatta ground water based water supply scheme under Block_ Tehatta-I Dist. - Nadia under EMD, PHE Dte. [SM/10597] | 694/EMD | 04/04/2025 | 30 | C.M.S. ENGINEERING CONCERN. | 51.99 | 0 | 0 | 0
1952 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10597 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- III) at village Nazirpur, Bagadoba, Chhitka, Aztullanagar under Tehatta-I Block to accommodate FHTC under Nadia Divn, PHE Dte. | 1805/ND | 22/04/2025 | 180 | M/S DIPAK ENTERPRISE | 71.65 | 0 | 0 | 30
1953 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatatta(Phase-II) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10597 | Augmentation | Augmentation of rising main system, providing FHTC, construction of 700 cum capacity 20 mtr. staging height RCC over head reservoir (including pile foundation), pipe connection and cost of pipes, specials and soil investigation for augmentation of ground water based piped water supply scheme for Tehatta Phase-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | 478/ND | 02/02/2023 | 789 | H I ENTERPRISE, VILL&P.O- DHALTITHA, P.S. BASIRHAT, NORTH 24 PARGANAS, PIN-743412(WB) | 354.33 | 227.46 | 81.57 | 90
1954 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for CHUPRIA ZONE-I, BLOCK- Hanskhali, Dist-Nadia. , SM/09971 | Augmentation | Repair of 450 cum capacity Over Head Reservoir ,Painting and Pump House at Chupria, Zone-I under Surface W/S Scheme in Hanskhali Block under Nadia Arsenic Division-I, P. H.E. Dte (Sl. No.16) | 153/NAD-I | 07/02/2023 | 30 | PAPAN ROY | 13.66 | 13.61 | 100 | 100
1955 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for CHUPRIA ZONE-I, BLOCK- Hanskhali, Dist-Nadia. , SM/09971 | Augmentation | Construction of Boundary wall, Toilet, Pathway and other allied work at H/W Site (Length-135.0 m) and 2nd T/W Site (Length-55.0m) in Chupria Zone-I water supply Scheme within Hanskhali Block under Nadia Arsenic Division-I,P.H.E. Dte. (SL.NO.17) | 104 / NAD-I | 31/01/2023 | 45 | GOPAL KIRTYANIA | 24.03 | 23.95 | 100 | 40
1956 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for CHUPRIA ZONE-I, BLOCK- Hanskhali, Dist-Nadia. , SM/09971 | Augmentation | Retrofitting work at Chupria Zone-I under Jal Jeevan Mission (JJM) for Chupria Zone-I W/S Scheme at Hanskhali Block in connection with augmentation of Ground Water based W/S Scheme for Chupria Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte.(Sl.no.19) | 2155/NAD-I | 08/09/2023 | 21 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 71.93 | 68.58 | 95.34 | 80
1957 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for CHUPRIA ZONE-I, BLOCK- Hanskhali, Dist-Nadia. , SM/09971 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Chupria Zone-I Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Chupria Zone-I W/S Scheme under JJM (SL.NO.12) | 1116 / NAD-I | 27/04/2023 | 15 | SAHA CONSTRUCTION &CO | 13.05 | 3.45 | 20.94 | 100
1958 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for CHUPRIA ZONE-I, BLOCK- Hanskhali, Dist-Nadia. , SM/09971 | Augmentation | Providing FHTC under Jaldhara/Jalswapna for Gobindapur Z-I Santipur Bolck by Augmentation of Ground Water Based PWSS for Chupria (Zone -I) Part -I at Hanskhali Block by retrofitting of Grond Water based PWSS for CHUPRIA Water Supply Sceme under Nadia Arsenic Division-I , P.H.E.Dte (Sl.no.01) | 1673 / NAD-I | 07/09/2022 | 539 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 565.67 | 513.64 | 90.8 | 85
1959 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for CHUPRIA ZONE-I, BLOCK- Hanskhali, Dist-Nadia. , SM/09971 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Arsenic Division-I PHE Dte. Schemes:- i)Chupria Zone-I ii)Garapota iii)Itaberia iv)Muragachha Zone-I v)Muragachha Zone-II vi)Zone-I (Palagachha) vii)Zone-II (joykrishnapur) | 169/AE-I/NAD-I | 12/04/2023 | 1275 | TECH VISION | 4.84 | 4.84 | 100 | 100
1960 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10595 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Barakulta W/S Scheme in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte. | 1062/RSD | 02/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.76 | 4.16 | 100 | 100
1961 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10595 | Augmentation | Material Requisition To Resource Division | 5103/ND | 08/12/2022 | 0 | Resource Division | 154.18 | 0 | 0 | 0
1962 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10595 | Augmentation | Special repair & renovation of head work site pump house & allied works of Barakulta W/S scheme of Ranaghat-I block under Ranaghat Sub-Division, P.H.E. Dte. | 461/A/RSD | 22/07/2022 | 30 | PALLAB KARMAKAR | 2.25 | 1.92 | 100 | 90
1963 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10595 | Augmentation | Special repair & renovation & repair of IEP pump house & allide works of Barakulta W/S scheme of Ranaghat-I block under Ranaghat Sub-Division, P.H.E. Dte. | 461/RSD | 22/07/2022 | 30 | RENUKA ENTERPRISE | 1.49 | 1.22 | 100 | 90
1964 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10595 | Augmentation | River crossing at Anjana River Barakulta including construction of anchor block Barakulta W/S Scheme of Ranaghat -I block under Ranaghat Sub-Division,P.H.E.Dte. | 5330/ND | 21/12/2022 | 45 | CHOWDHURY & CO. | 15.3 | 15.29 | 100 | 100
1965 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10595 | Augmentation | Special repair & renovation of pump house & allied works in the premises at pump house no-I of Barakulta W/S scheme of Ranaghat-I block under Ranaghat Sub-Division, P.H.E. Dte. | 462/RSD | 22/07/2022 | 30 | JYOTIRMOY ENTERPRISE | 2.54 | 2.3 | 100 | 85
1966 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10595 | Augmentation | Special repair & renovation of boundary wall & allied works in the premises at pump house no 2 of Barakulta W/S scheme of Ranaghat-I block under Ranaghat Sub-Division, P.H.E. Dte. | 462/A/RSD | 22/07/2022 | 30 | M/S LOKENATH ENTERPRISE | 2.84 | 2.36 | 100 | 95
1967 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10595 | Augmentation | Material Requisition To Resource Division | 4322/ND | 29/09/2022 | 0 | Resource Division | 19.74 | 0 | 0 | 0
1968 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10595 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Barakulta to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. | 3529/ND | 05/08/2022 | 90 | TAPU SAHA | 354 | 277.54 | 78.4 | 94
1969 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10595 | Augmentation | Construction and installation of MANIFOLD and allied works at Head Works site under Barakulta Ground Based Water Supply Scheme under Ranaghat-I Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) | 2435/ND | 26/05/2025 | 180 | M/S G.M ASSOCIATES | 12.36 | 0 | 0 | 0
1970 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA KULTA to Accommodate FHTC in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10595 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
1971 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of RUKMINIDANGA (ZONE-IV) at Chakdaha Block, District-Nadia of Surface Water based PWSS for Chakdaha (Part) for FHTC (Functional Household Tap Con , SM/09937 | Augmentation | Repair of 550 cum capacity Over Head Reservoir Boundary Wall Switch Room and other allied works at Rukminidanga ZoneV at under Chakdah Surface WS Scheme in Chakdah Block under NAD I PHE Dte (Sl.no.05) | 1596/NAD-I | 06/09/2022 | 60 | SAHA ENGINEERS | 28.04 | 23.37 | 100 | 100
1972 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of RUKMINIDANGA (ZONE-IV) at Chakdaha Block, District-Nadia of Surface Water based PWSS for Chakdaha (Part) for FHTC (Functional Household Tap Con , SM/09937 | Augmentation | Material Requisition To Resource Division | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 26.12 | 0 | 0 | 0
1973 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of RUKMINIDANGA (ZONE-IV) at Chakdaha Block, District-Nadia of Surface Water based PWSS for Chakdaha (Part) for FHTC (Functional Household Tap Con , SM/09937 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-IV, (Rukminidanga), Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 644/NAD-I | 29/04/2022 | 336 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT LTD. | 359.23 | 314.08 | 87.43 | 100
1974 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Debagram Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. , SM/10654 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/JalSwapna for Debogram Phase-II at Ranaghat-II Block by augmentation of Ground Water based PWSS for Debogram Water Supply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | 1688/NAD-I | 08/09/2022 | 90 | UMWELT ENGINEER PVT. LTD. | 399.59 | 351.69 | 100 | 99
1975 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Debagram Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. , SM/10654 | Augmentation | Providing FHTC and laying dedicated pipeline for Kamargaria & Debogram Village in connection with Debagram Water Supply Scheme within Nadia Arsenic Division-I, PHE Dte under Jal Jeevan Mission. (Sl. No. 04) | 157/NAD-I | 28/04/2025 | 60 | M/S A.K. CONSTRUCTION | 82.68 | 0 | 0 | 0
1976 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Debagram Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. , SM/10654 | Augmentation | Providing FHTC and laying dedicated pipeline for Sijdia, Dakhin Rameswarpur,Anatapur, Mithapur & aismali Village in connection with Debagram Water Supply Scheme under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in under Nadia Arsenic Division-I, PHE Dte. | 581/NAD-I | 10/07/2025 | 60 | SUMAN CHAKRABORTY | 96.78 | 0 | 0 | 0
1977 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Debagram Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. , SM/10654 | Augmentation | Laying of additional pipelines under JJM at Garapota W/S Scheme in connection with Debagram W/ Scheme under Ranaghat-II block within Hanskhali Block Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 01) | 229/AE-II/NAD-I | 12/11/2024 | 15 | JAGADANADAPUR CO-OPT LABOUR CONTTRACT AND CONSTRUTION SOCITY LTD. | 4.85 | 0 | 0 | 0
1978 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Earth work in filling in ditches at Dhopahat 2nd Tube Well Site for development of land in connection with proposed T/W Sinking & Pump House construction at Dhopahat Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 64/AE-II/NACD-II | 28/06/2022 | 20 | GHOSH ENTERPRISE | 3.2 | 3.2 | 100 | 100
1979 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
1980 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
1981 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Dhopahat water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 212/NACD-II | 05/04/2022 | 60 | NAMDAR ALI | 5.37 | 5.36 | 99.87 | 100
1982 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Dhopahat and adjoining mouzas under Dhopahat Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | 288/NACD-II | 12/05/2022 | 90 | SINGHA ROY & CO. | 253.93 | 213.88 | 84.23 | 85
1983 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Dhopahat and Khaspu Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 242/NACD-II | 19/04/2022 | 60 | AUXILIARY TUBE WELL DRILLERS | 43.18 | 29.26 | 100 | 100
1984 | NADIA | Eastern Mechanical | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Dhopahat Piped Water SupplyScheme, Block: Tehatta-I, Dist. Nadia Under EMD, PHE Dte. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 16) | 6253/EMD | 19/11/2022 | 30 | S.G. ENTERPRISE | 40.81 | 0 | 0 | 0
1985 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Additional Earth work in filling in ditches at Dhopahat 2nd Tube Well Site for development of land in connection by hand roller in connection with proposed T/W Sinking & Pump House construction at Dhopahat Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 284./NACD-II | 01/03/2023 | 20 | M/S SHAIKH ENTERPRISE | 2.45 | 2.45 | 99.89 | 100
1986 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Dhopahat Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 632/NACD-II | 06/09/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.84 | 4.84 | 100 | 100
1987 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Dhopahat) | 869/NACD-II | 10/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
1988 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Material Requisition To Resource Division | 398/NACD-II | 04/07/2022 | 0 | Resource Division | 47.43 | 0 | 0 | 0
1989 | NADIA | Eastern Mechanical | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Electricity bill for new service connection at Dhopotto-I | 142/PFMS/EMD | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 16.47 | 0 | 0 | 0
1990 | NADIA | Eastern Mechanical | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Electricity bill for new service connection at dhopahat-II W/S Scheme | 143/PFMS/EMD | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.48 | 0 | 0 | 0
1991 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Laying of Rising Main of Dhopahat Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. (Sl. No. 01) | 220/NACD-II | 05/04/2022 | 30 | GOUTAM HALDER | 5.37 | 5.33 | 100 | 100
1992 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Dhopahat water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | 17/AE-II/NACD-II | 11/04/2022 | 60 | NAMDAR ALI | 2.83 | 2.81 | 100 | 100
1993 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Construction of Boundary wall with Grill Gate at Dhopahat Water Supply Scheme H/W site under Nadia Arsenic Civil Division-II PHE Dte. | 522/NACD-II | 05/08/2022 | 60 | CHANDAN ROY | 27.92 | 19.01 | 68.61 | 85
1994 | NADIA | Eastern Mechanical | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) under Dhopahat W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No.- 21 of EE/EMD of 2022-23 (Sl. No.-01) | 6369/EMD | 23/11/2022 | 30 | ABHISEK ENGINEERING CONCERN | 10 | 9.89 | 100 | 80
1995 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Dhopahat 2nd Tubwell Site within Dhopahat Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 122/NACD-II | 11/01/2023 | 60 | BASUDEB SAHA | 6.57 | 6.49 | 100 | 85
1996 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Construction of 350 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Dhopahat water supply scheme of Tehatta-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | 360/NACD-II | 22/03/2023 | 366 | SINGHA ROY & CO. | 143.35 | 68.84 | 48.02 | 27
1997 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Construction of 87 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Matiary Water Supply Scheme in Krishnaganj block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | 1311/NACD-II | 20/09/2024 | 180 | JOY HIND TUBEWELLS | 232.26 | 0 | 0 | 0
1998 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Laying of distribution system including providing FHTC at left out households for Thanarpara Zone-III (Vill- Char Gaurbhanga, Falia, Yusufpur) , Jitpur , Taranipur & Dhopahat W/S Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1627/NACD-II | 19/12/2024 | 270 | M.R. CONSTRUCTION | 117.87 | 0 | 0 | 40
1999 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 50 cum/Hour capacity for Dhopahat Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1312/NACD-II | 20/09/2024 | 360 | JOY HIND TUBEWELLS | 181.56 | 0 | 0 | 0
2000 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Laying of distribution system including providing FHTC at left out households for Bahadurpur, Khaspu, Dhopahat and Rajapur W/s Scheme and restoration of the damaged portion of roads in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte and Brittihuda W/S Scheme & Barnia W/S Scheme included. | 736/NACD-II | 18/06/2025 | 90 | JOY HIND TUBEWELLS | 186.42 | 0 | 0 | 40
2001 | NADIA | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Construction of Pump House cum Chlorine room with sanitary arrangement at Thanarpara Zone-II Headwork site according to departmental drawing at Thanarpara Zone-II & Dhopahat Piped Water Supply Scheme under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 403_NACD-II | 26/03/2025 | 150 | ROY CONSTRUCTION | 6.14 | 0 | 0 | 100
2002 | NADIA | Eastern Mechanical | Dhopahat Piped Water Supply Scheme , SM/09942 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.II under Dhopahat W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 02) | 6263/EMD | 19/11/2022 | 864 | BARISAL TRADING CO. | 9.88 | 8.89 | 91.28 | 10
2003 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11828 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 1A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 114/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.16 | 3.94 | 100 | 100
2004 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11828 | Augmentation | Preparation of DPR for Augmentation for Intake, WTP & Rising Main of Surface Water Based Water Supply Scheme for Northern Sector Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte.(including Survey, Design and Estimate). | 4525/ND | 21/10/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 15.1 | 15.1 | 100 | 0
2005 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11828 | Augmentation | Material Requisition To Resource Division | 71/ND | 05/01/2023 | 0 | Resource Division | 345.52 | 0 | 0 | 0
2006 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11828 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 317.07 | 49.48 | 47
2007 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11830 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 2B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 118/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.38 | 4.33 | 100 | 100
2008 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11830 | Augmentation | Material Requisition To Resource Division | 101/ND | 05/01/2023 | 0 | Resource Division | 170.21 | 0 | 0 | 0
2009 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11830 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 1.4 | 98.71 | 40
2010 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11830 | Augmentation | Restoration Work of road damaged of Debagram Tehattaghat Road from 0.00 Kmp. to 14.00 kmp., Under Plassey Highway Sub-Division Under Nadia Highway Division No.-I in the District Of Nadia During the Year 2024-2025. | 160/PFMS | 13/08/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 4.44 | 0 | 0 | 0
2011 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11830 | Augmentation | Restoration Work of road damaged of Debagram Tehattaghat Road from 0.00 Kmp. to 14.00 kmp., Under Plassey Highway Sub-Division Under Nadia Highway Division No.-I in the District Of Nadia During the Year 2024-2025. |  | 02/08/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 8.88 | 0 | 0 | 0
2012 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11830 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 754.29 | 88.07 | 47
2013 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09872 | Augmentation | Preparation of DPR for augmentation of existing Matiary, (Block-Krishnaganj) piped water supply schemes | 149/AE-I/NACD-II | 16/11/2021 | 10 | UMWELT ENGINEER PVT LTD. | 3.02 | 3.02 | 100 | 100
2014 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09872 | Augmentation | Construction of Boundary wall with Grill Gate at Matiary Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | 45/AE-II/NACD-II | 17/02/2022 | 30 | BABLU MALLICK | 4.18 | 4.09 | 97.96 | 100
2015 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09872 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Matiary W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 527/NACD-II | 14/06/2021 | 45 | S.K. CONSTRUCTION | 64 | 63.98 | 100 | 100
2016 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09872 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and Pump house repair at Gongra W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 735/NACD-II | 13/09/2021 | 45 | APURBA MANDAL | 65.58 | 65.49 | 100 | 100
2017 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09872 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair, & also Rising Main replacement by DI pipe) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 984/NACD-II | 27/12/2021 | 90 | MONDAL ENTERPRISE | 149.3 | 149.25 | 100 | 100
2018 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09872 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 127/NACD-II | 21/02/2022 | 90 | MALLICK ENTERPRISE | 159.32 | 0 | 0 | 100
2019 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09872 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and Pump house repair at Gongra W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 859/EE/NACD-II | 08/11/2021 | 45 | PRIYA CONSTRUCTION | 53.27 | 53.18 | 100 | 100
2020 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09872 | Augmentation | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Matiary W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1193/NACD-II | 23/12/2022 | 15 | ROY CONSTRUCTION | 1.71 | 1.59 | 100 | 100
2021 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09872 | Augmentation | Material Requisition To Resource Division | 81/NACD-II | 01/02/2022 | 0 | Resource Division | 112.78 | 0 | 0 | 0
2022 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09872 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BRITTIHUDA (Block- Chapra), BARNIA (Block- Tehatt II ), MAHATPUR (Block- Chapra ), MATIARY (Block- Krishnaganj), BAGAKHALI (Z-I) (Block- Tehatta I ), BARA NALDAH (Block- Tehatta II ) W/S Scheme, , Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 01) | 1120/EMD | 16/03/2023 | 30 | B.T. PROJECTS PVT. LTD | 91.82 | 0 | 0 | 60
2023 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09872 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Matiari Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 20/AE-II/NACD-II | 15/02/2024 | 15 | SANJIB DEY | 0.97 | 0 | 0 | 100
2024 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09872 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHRSpecially) under Krishnaganj Block of Nadia District through Jadavpur University. (Name of PWSS Matiary) | 866/NACD-II | 04/07/2024 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
2025 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09872 | Augmentation | Jungle cutting and Earthwork in filling at Maheshpur, Maitari and Thanarapara Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 818/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.76 | 0 | 0 | 100
2026 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09872 | Augmentation | Material Requisition To Resource Division | 985/NACD-II | 23/07/2024 | 0 | Resource Division | 15.62 | 0 | 0 | 0
2027 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09872 | Augmentation | Exigent connection of higher specification components as per IS Code 8329 with its latest version in the mouza in the JL No. 52 at Matiari Piped Water Supply Scheme under Krishnaganj Development Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 313AE-II/NACD-II | 06/09/2024 | 390 | A.K ADHIKARY | 3.49 | 0 | 0 | 100
2028 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09872 | Augmentation | Construction of 87 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Matiary Water Supply Scheme in Krishnaganj block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | 1311/NACD-II | 20/09/2024 | 180 | JOY HIND TUBEWELLS | 232.26 | 0 | 0 | 0
2029 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09872 | Augmentation | Repair and Renovation work at Matiary H/W and 2nd Pump house site with Reinforced Barbed Tape , Plaster , Painting and other allied works.Under Nadia Arsenic Division-II,P.H.E.Dte. | 140./AE-II/NACD-II | 11/06/2024 | 30 | MUKHERJEE CONSTRUCTION | 4.83 | 0 | 0 | 100
2030 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130518, 19336130521, 19336130107, 19336131005 | 46 /AE-II/ NACD-II | 10/06/2022 | 45 | TAPAS GHOSH | 4.57 | 3.73 | 100 | 0
2031 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040322, 19336040321, 19336040319, 19336040311 | 90/AE-I/NACD-II | 10/06/2022 | 45 | PARTHA DAS | 4.47 | 3.38 | 75.72 | 0
2032 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under TEHATTA-II BLOCK from existing piped water supply scheme. AWC Code : 19336310701, 19336310721, 19336310702, 19336310715 | 74/AE-II/NACD-II | 07/07/2022 | 45 | GHOSH ENTERPRISE | 4.58 | 2.84 | 62.03 | 0
2033 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under TEHATTA-II BLOCK from existing piped water supply scheme. AWC Code : 19336310704, 19336310707, 19336310710 | 76/AE-II/NACD-II | 07/07/2022 | 45 | NAMDAR ALI | 3.43 | 0.98 | 28.59 | 0
2034 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KARIMPUR-II BLOCK from existing piped water supply scheme. AWC Code : 19336320323, 19336320406, 19336320402, 19336320313" | 79/AE-II/NACD-II | 07/07/2022 | 45 | SOURAV & CO. | 4.26 | 0 | 0 | 0
2035 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336030918 19336030917, 19336030916, 19336030704 | 94/AE-I/NACD-II | 10/06/2022 | 45 | SANDIP ROY | 4.47 | 2.27 | 50.8 | 0
2036 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under TEHATTA-I BLOCK from existing piped water supply scheme. AWC Code : 19336300111, 19336300214, 19336300208" | 83/AE-II/NACD-II | 07/07/2022 | 45 | CHINMOY BISWAS | 3.43 | 2.17 | 63.14 | 0
2037 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under TEHATTA-I BLOCK from existing piped water supply scheme. AWC Code : 19336290102, 19336300107,19336300115" | 82/AE-II/NACD-II | 07/07/2022 | 45 | M/S RAJESH CONSTRUCTION | 3.43 | 2.15 | 62.68 | 90
2038 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under TEHATTA-I BLOCK from existing piped water supply scheme. AWC Code : 19336300117, 19336290513, 19336290501, 19336300405" | 85/AE-II/NACD-II | 07/07/2022 | 45 | M/S TARUN GHOSH & CO. | 4.58 | 0 | 0 | 0
2039 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KALIGANJ BLOCK from existing piped water supply scheme. (Phase_I) | 1174/NACD-II | 22/12/2022 | 90 | M. H. SUPPLIERS | 17.92 | 11.54 | 64.39 | 0
2040 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under SANTIPUR BLOCK from existing piped water supply scheme under Nadia Arsenic Civil Division-II PHE Dte. (Phase-I) | 868/NACD-II | 17/11/2022 | 60 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 25.78 | 21.35 | 82.81 | 0
2041 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Karimpur-I Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-I) | 871/NACD-II | 17/11/2022 | 90 | SUMIT GHOSH | 66.98 | 47.48 | 70.88 | 0
2042 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under TEHATTA-I BLOCK from existing piped water supply scheme. AWC Code : 19336300203, 19336300205, 19336300501" | 84/AE-II/NACD-II | 07/07/2022 | 45 | SANJIT DAS | 3.43 | 1.09 | 31.8 | 0
2043 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040312, 19336040325, 19336040324, 19336040512 | 89/AE-I/NACD-II | 10/06/2022 | 45 | JAYBRATO HALDER | 4.47 | 3.01 | 67.26 | 0
2044 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130306, 19336130320, 19336130617, 19336130619 | 44 /AE-II/ NACD-II | 10/06/2022 | 45 | AMIT KARMAKAR | 4.57 | 3.49 | 100 | 0
2045 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040904, 19336040918, 19336040907, 19336040909 | 83/AE-I/NACD-II | 10/06/2022 | 45 | S.B. CONSTRUCTION | 4.47 | 4 | 100 | 0
2046 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040711 19336030219, 19336030224, 19336030225, | 92/AE-I/NACD-II | 10/06/2022 | 45 | SHOVON KUMAR MODAK | 4.47 | 3.13 | 100 | 0
2047 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040104, 19336040103, 19336040106, 19336040101 | 87/AE-I/NACD-II | 10/06/2022 | 45 | GHOSH ENTERPRISE | 4.47 | 3.73 | 100 | 0
2048 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040308, 19336040310, 19336040313, 19336040314 | 88/AE-I/NACD-II | 10/06/2022 | 45 | TAPAN SAHA | 4.47 | 4.02 | 100 | 0
2049 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040701 19336040703, 19336040705, 19336040709 | 93/AE-I/NACD-II | 10/06/2022 | 45 | DEBASISH DEY | 4.47 | 3.07 | 100 | 0
2050 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336030709 19336030707, 19336030607, 19336030610 | 96/AE-I/NACD-II | 10/06/2022 | 45 | BISHAL CONSTRUCTION | 4.47 | 2.89 | 100 | 0
2051 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336030223, 19336030218, 19336030220, 19336040306, | 91/AE-I/NACD-II | 10/06/2022 | 45 | PRADIP KUMAR BANIK | 4.46 | 3.07 | 100 | 0
2052 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040824, 19336040902, 19336040901, 19336040903 | 82/AE-I/NACD-II | 10/06/2022 | 45 | ARIT KUMAR PAL | 4.47 | 3.49 | 100 | 0
2053 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040211, 19336040209, 19336040213, 19336040210 | 84/AE-I/NACD-II | 10/06/2022 | 45 | M/S TARUN GHOSH & CO. | 4.47 | 3.82 | 100 | 0
2054 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040517, 19336040514, 19336040510, 19336040508 | 85/AE-I/NACD-II | 10/06/2022 | 45 | M/S FREEDOM CONSTRUCTION | 4.47 | 4.12 | 100 | 0
2055 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040117, 19336040120, 19336040118, 19336040119 | 86/AE-I/NACD-II | 10/06/2022 | 45 | SUMIT GHOSH | 4.47 | 2.7 | 100 | 0
2056 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130912, 19336130901, 19336130312, 19336130318 | 43 /AE-II/ NACD-II | 10/06/2022 | 45 | SHYAM SUNDAR SAHA | 4.57 | 2.8 | 100 | 0
2057 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130609, 19336130607, 19336130605, 19336130625 | 45 /AE-II/ NACD-II | 10/06/2022 | 45 | SUBHASIS MOJUMDER | 4.57 | 3.06 | 100 | 0
2058 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336131014, 19336131003, 19336131107, 19336131110 | 47 /AE-II/ NACD-II | 10/06/2022 | 45 | R.M. TRADING | 4.57 | 3.28 | 100 | 0
2059 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under TEHATTA-II BLOCK from existing piped water supply scheme. AWC Code : 19336310102, 19336310414, 19336310402, 19336310407 | 75/AE-II/NACD-II | 07/07/2022 | 45 | SANJIB BISWAS | 4.58 | 3.95 | 100 | 0
2060 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under TEHATTA-II BLOCK from existing piped water supply scheme. AWC Code : 19336310620, 19336310708, 19336310711 | 77/AE-II/NACD-II | 07/07/2022 | 45 | M/S SREE KRISHNA ENTERPRISE. | 3.43 | 3.01 | 100 | 0
2061 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040805 19336030713, 19336030711, 19336030613 | 97/AE-I/NACD-II | 10/06/2022 | 45 | SHYAMAL KANTI GHOSH | 4.47 | 2.48 | 100 | 0
2062 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under TEHATTA-I BLOCK from existing piped water supply scheme. AWC Code : 19336290502, 19336300708, 19336300524, 19336300508" | 86/AE-II/NACD-II | 07/07/2022 | 45 | M/S FREEDOM CONSTRUCTION | 4.58 | 4.04 | 100 | 0
2063 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KRISHNAGAR-I BLOCK from existing piped water supply scheme. AWC Code: 19336150206, 19336150211, 19336150107, 19336150504 | 135/AE-I/NACD-II | 14/07/2022 | 45 | M/S S.K. CONSTRUCTION | 4.57 | 4.01 | 100 | 0
2064 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336131111, 19336130124, 19336130220, 19336130222" | 87/AE-II/NACD-II | 07/07/2022 | 45 | ST. ANTHONY ENTERPRISE | 4.57 | 3.64 | 100 | 0
2065 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KARIMPUR-II BLOCK from existing piped water supply scheme. AWC Code : 19336320503, 19336320411, 19336320414, 19336320508" | 80/AE-II/NACD-II | 07/07/2022 | 45 | SHYAM SUNDAR SAHA | 4.26 | 3.83 | 100 | 0
2066 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under TEHATTA-II BLOCK from existing piped water supply scheme. AWC Code : 19336310403, 19336310705, 19336310401" | 78/AE-II/NACD-II | 07/07/2022 | 45 | BISHAL CONSTRUCTION | 3.43 | 2.96 | 100 | 0
2067 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under CHAKDAH BLOCK from existing piped water supply scheme under Nadia Arsenic Civil Division-II PHE Dte. (Phase-I) | 860/NACD-II | 17/11/2022 | 60 | M/S FREEDOM CONSTRUCTION | 42.41 | 41.85 | 100 | 100
2068 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Tehatta-I Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-I) | 875/NACD-II | 17/11/2022 | 60 | ABDUL ALIM MONDAL | 10.94 | 8.91 | 100 | 0
2069 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Krishnaganj Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-I) | 873/NACD-II | 17/11/2022 | 60 | MALI CONSTRUCTION | 25.34 | 25.34 | 100 | 100
2070 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Tehatta-II Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-I) | 876/NACD-II | 17/11/2022 | 60 | TRISHA ENTERPRISE AND CO. | 20.91 | 14.49 | 100 | 0
2071 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336030811 19336030806, 19336030915, 19336030919 | 95/AE-I/NACD-II | 10/06/2022 | 45 | SURAJIT KUMAR GHOSH | 4.47 | 2.13 | 100 | 0
2072 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130723, 19336130907, 19336130908, 19336130909 | 42/AE-II/ NACD-II | 10/06/2022 | 45 | BIPLAB BHOWMICK | 4.57 | 3.25 | 100 | 100
2073 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KARIMPUR-II BLOCK from existing piped water supply scheme. AWC Code : 19336320317, 19336320413, 19336320422" | 81/AE-II/NACD-II | 07/07/2022 | 45 | BIPLAB BHOWMICK | 3.2 | 2.94 | 100 | 90
2074 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under NABADWIP BLOCK from existing piped water supply scheme under Nadia Arsenic Civil Division-II PHE Dte. (Phase-I) | 865/NACD-II | 17/11/2022 | 60 | TAPAS GHOSH | 34.99 | 34.95 | 100 | 100
2075 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KRISHNAGAR-II BLOCK from existing piped water supply scheme under Nadia Arsenic Civil Division-II PHE Dte. (Phase-I) | 864/NACD-II | 17/11/2022 | 90 | SANDIP BISWAS | 63.77 | 63.55 | 100 | 100
2076 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Chapra Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-I) | 861/NACD-II | 17/11/2022 | 60 | BIPLAB GUHA | 49.24 | 49.15 | 100 | 85
2077 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwari Centers underKrishnagar-I Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-I) | 863/NACD-II | 17/11/2022 | 90 | TARUN GHOSH | 53.5 | 52.74 | 100 | 100
2078 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Karimpur-II Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-I) | 872/NACD-II | 17/11/2022 | 60 | SOUMYADIP MISRA | 49.95 | 49.85 | 100 | 100
2079 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KALIGANJ BLOCK from existing piped water supply scheme under Nadia Arsenic Civil Division-II PHE Dte. (Phase-I) | 870/NACD-II | 17/11/2022 | 90 | BIDYUT KUMAR | 89.27 | 82.21 | 100 | 50
2080 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Nakashipara Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-I) | 874/NACD-II | 17/11/2022 | 90 | JOY GOPAL GUPTI | 71.15 | 64.59 | 100 | 64
2081 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under Hanskhali BLOCK from existing piped water supply scheme under Nadia Arsenic Civil Division-II PHE Dte. (Phase-I) | 869/NACD-II | 17/11/2022 | 90 | SHYAMAL SHIL | 91.75 | 91.65 | 100 | 70
2082 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under Hanskhali BLOCK from existing piped water supply scheme. (Phase_I) | 1173/NACD-II | 22/12/2022 | 90 | CHOWDHURY CONSTRUCTION | 44.56 | 44.53 | 100 | 100
2083 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under RANAGHAT-I BLOCK from existing piped water supply scheme under Nadia Arsenic Civil Division-II PHE Dte. (Phase-I) | 866/NACD-II | 17/11/2022 | 1170 | M/S GHOSH CONSTRUCTION | 92.58 | 61.16 | 66.06 | 90
2084 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under RANAGHAT-II BLOCK from existing piped water supply scheme under Nadia Arsenic Civil Division-II PHE Dte. (Phase-I) | 867/NACD-II | 17/11/2022 | 1080 | M/S SUKANTA ENTERPRISE | 75.76 | 20.75 | 27.39 | 60
2085 | NADIA | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) , SM/09876 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Haringhata Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-I) | 862/NACD-II | 17/11/2022 | 812 | CHANDAN ROY | 68.15 | 51.65 | 71.82 | 92
2086 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-I) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. , SM/10429 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-I) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. | 55/PFMS | 22/06/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.91 | 0 | 0 | 0
2087 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-I) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. , SM/10429 | Augmentation | Laying of Distribution System including Specials, Valves & Pipe Supporting Structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. and Construction of boundary wall at head work site all complete for Augmentation of Ground Based Water Supply Scheme at Bhimpur (Phase-I) to accommodate FHTC with Krishnagar-I Block under Krishnagar Sub-Division, PHE Dte. | 3219/ND | 26/07/2023 | 90 | RADIANT | 585.67 | 0 | 0 | 0
2088 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-I) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. , SM/10429 | Augmentation | Material Requisition To Resource Division | 83/ND | 05/01/2023 | 0 | Resource Division | 148.12 | 0 | 0 | 0
2089 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-I) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. , SM/10429 | Augmentation | Material Requisition To Resource Division | 259/ND | 11/01/2024 | 0 | Resource Division | 21.56 | 0 | 0 | 0
2090 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc , SM/12021 | Augmentation | Material Requisition To Resource Division | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 6.22 | 0 | 0 | 0
2091 | NADIA | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc , SM/12021 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under GAYESPUR (Z-I) W/S Scheme, Block- Shantipur , Dist. - Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 07) | 1606/EMD | 26/04/2023 | 30 | STANDARD ENGINEERING | 15.65 | 12.22 | 100 | 100
2092 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc , SM/12021 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Nabla Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Nabla Part-III Piped W/S Scheme (sl.no.21) | 1162 / NAD-I | 28/04/2023 | 15 | CHOWDHURY & CO. | 13.07 | 13.06 | 100 | 100
2093 | NADIA | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc , SM/12021 | Augmentation | Supply & delivery of automatically controlled Diaphragm type Chlorinator at Gayeshpur Zone-I P/H-I W/S Sch for accommodate FHTC work, Under ESMD-II PHE Dte. | 752/EMSD-II | 09/10/2023 | 10 | STANDARD ENGINEERING | 0.9 | 0.9 | 100 | 100
2094 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc , SM/12021 | Augmentation | Material Requisition To Resource Division | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 4.31 | 0 | 0 | 0
2095 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc , SM/12021 | Augmentation | Providing FHTC under Jaldhara/Jalswapna for Gobindapur Z-I Santipur Bolck by Augmentation of Ground Water Based PWSS for Gobindapur Z-I W/S scheme under Nadia Arsenic Division-I , P.H.E.Dte (Sl.no.04) | 1672 / NAD-I | 07/09/2022 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 534.08 | 0 | 0 | 70
2096 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc , SM/12021 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Boalia, Part-III at Santipur Block bY Augmentation of Ground Water Based PWSS for Boalia W/S Scheme, Providing FHTC under Jal Jeevan Mission (JJM) for Gayeshpur Zone-I, Part-III at Santipur Block by Augmentation of Ground Water Based PWSS for Gayeshpur W/S Scheme, Providing FHTC under Jal Jeevan Mission (JJM) for Gayeshpur Zone-II, Part-III at Santipur Block by Augmentation of Ground Water Based PWSS for Gayeshpur W/S Scheme, Construction of Boundary wall, Toilet, Pathway and other allied work at Boalia Water Supply Scheme within Santipur Block, Construction of Boundary wall, Toilet, Pathway and other allied work at Gayeshpur Zone-I Water Supply Scheme, Construction of Boundary wall, Toilet, Pathway and other allied work at Gayeshpur Zone-II Water Supply Scheme, Repair of 550 cum capacity Over Head Reservoir and other allied works at Boalia water supply scheme AND Repair of 250 cum capacity Over Head Reservoir and other allied works at Gayeshpur Zone-I water supply scheme underNadia Arsenic Division-I , PHE Dte. (Sl.no. 03) | 1697/NAD-I | 13/07/2023 | 1095 | JAL PRAVHAHIKA PVT. LTD., | 493.44 | 241.23 | 48.89 | 45
2097 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc , SM/12021 | Augmentation | Augmentation of AIRP capacity (216cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.09) | 1899/NAD-I | 14/08/2023 | 691 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 167.06 | 0 | 0 | 70
2098 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc , SM/12021 | Augmentation | Conversion of IEP to AIRP (Pressure Type) at Gayeshpur Zone-I W/S Scheme under Santipur Block of capacity 60 cum/hr. underaugmentation of Gayeshpur Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.04) | 1900/NAD-I | 14/08/2023 | 626 | HARBAUER INDIA PRIVATE LIMITED | 134.01 | 101.18 | 75.5 | 23
2099 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc , SM/12021 | Augmentation | Construction of AIRP capacity (111m3/hr) in connection with augmentation of Ground Water Based PWSS for Baganchara under Jal Jeevan Mission at Santipur Block under Nadia Arsenic Division-I, PHE Dte. | 1079/NAD-I | 15/07/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 278.95 | 0 | 0 | 65
2100 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc , SM/12021 | Augmentation | Construction and installation of Manifold and allied works at OHR site under for Goalpur Zone-I PWSS including augmentation works under Gayeshpur Zone-I PWSS at Shantipur Block under Nadia Arsenic Division-I,P.H.E. Dte. (Sl. No. 03) | 1968/NAD-I | 28/11/2024 | 300 | M/S DREAM INFRASTRUCTURE | 16.83 | 0 | 0 | 80
2101 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc , SM/12021 | Augmentation | Laying of UPVC pipeline including providing FHTC at Goalpur and Boalia W/S Scheme, Shnatipur Block under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 05) | 1566/NAD-I | 26/09/2024 | 45 | CONSTRUCTURE | 13.85 | 0 | 0 | 78
2102 | NADIA | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Sc , SM/12021 | Augmentation | Providing Boundary Illumination with allied works at Boalia, Nabla, Gayeshpur Z-1 and Gayeshpur Z II, Part III under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/12021) | 1169/EMD | 04/06/2025 | 90 | SWAPAN ENTERPRISE | 17.35 | 0 | 0 | 0
2103 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11649 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 5A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 124/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.88 | 4.88 | 100 | 100
2104 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11649 | Augmentation | Material Requisition To Resource Division | 74/ND | 05/01/2023 | 0 | Resource Division | 66.06 | 0 | 0 | 0
2105 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11649 | Augmentation | Collection of Household data through mobile app for FHTC Connection of Surface Based PWSS for Northern Sector (Part-I) (Zone-IB to Zone-IVB) under Nadia Division, P.H.E. Dte. | 985/KLYSD-I | 11/09/2023 | 90 | TECHVISION | 4.85 | 4.85 | 100 | 100
2106 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11649 | Augmentation | Health Check up of existing Over Head Reservoir(OHR) based on inspection and Non-destructive Test (NDT) at Northern Sector Part-I (Zone-5A) PWSS at Kaligunj Block under Nadia Division, PHE Dte. | 4279/ND | 05/08/2024 | 15 | JADAVPUR UNIVERSITY | 3.48 | 3.48 | 100 | 100
2107 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11649 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 739.79 | 82.18 | 47
2108 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11649 | Augmentation | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3829/ND | 13/08/2025 | 120 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0 | 0
2109 | NADIA | Nadia Arsenic Division I | Surface Water Based Piped Water Supply Scheme Saguna Zone-VI (Part-II) for Arsenic Affected Areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE. Dte. , SM/11489 | Augmentation | Route Survey for providing FHTC (Functional Household Tap Connection) under JJM (Jal Jeevan Mission) by Augmentation of Zone-VI (Saguna) Part -II of Surface Water Based PWSS for Haringhata and Chakdah (Part) at Chakdah Block at Nadia District under Nadia Arsenic Division -I, P.H.E. Dte.(Sl.No.-02) | 169 / AE-I/NAD-I | 08/07/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 4.81 | 4.81 | 100 | 100
2110 | NADIA | Nadia Arsenic Division I | Surface Water Based Piped Water Supply Scheme Saguna Zone-VI (Part-II) for Arsenic Affected Areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE. Dte. , SM/11489 | Augmentation | Material Requisition To Resource Division | 02/NAD-I | 02/01/2024 | 0 | Resource Division | 128.4 | 0 | 0 | 0
2111 | NADIA | Nadia Arsenic Division I | Surface Water Based Piped Water Supply Scheme Saguna Zone-VI (Part-II) for Arsenic Affected Areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE. Dte. , SM/11489 | Augmentation | Material Requisition To Resource Division | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 18.48 | 0 | 0 | 0
2112 | NADIA | Nadia Arsenic Division I | Surface Water Based Piped Water Supply Scheme Saguna Zone-VI (Part-II) for Arsenic Affected Areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE. Dte. , SM/11489 | Augmentation | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete with Laying Of Distribution System Including Specials, Valves & Pipe Supporting Structure, Construction Of Boundary Wall (675m Length), Chlorine Room, Drain (I300 m Length) and Approach Road (60.0m Length and 3.0m Wide),Construction of 600 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials and Soil Investigation for the work of Construction of R.C.C Elevated Reservoir of Capacity 600 m3 Staging Height 20Mtr. at Surface Water Based Piped Water Supply Scheme for Saguna ZONE-VI (PART-II) in Chakdah Block of Nadia Districtunder Nadia Arsenic Division-I, PHE Dte. (Sl.no.09) | 1690/NAD-I | 13/07/2023 | 1095 | APURBA MANDAL | 529.72 | 148.39 | 28.01 | 30
2113 | NADIA | Nadia Arsenic Division I | Surface Water Based Piped Water Supply Scheme Saguna Zone-VI (Part-II) for Arsenic Affected Areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE. Dte. , SM/11489 | Augmentation | Laying of Pipeline for FHTC works under Surface Water Based PWSS Saguna Zone-VI (Part-II) for arsenic affected areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | 1117/NAD-I | 19/07/2024 | 300 | APURBA MANDAL | 95.96 | 0 | 0 | 85
2114 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11609 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 3/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. ( Sl.No .05 ) | 207/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.42 | 4.37 | 100 | 100
2115 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11609 | Augmentation | Material Requisition To Resource Division | 86/ND | 05/01/2023 | 0 | Resource Division | 222.47 | 0 | 0 | 0
2116 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11609 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 366 days w.e.f. 01/01/2024 to 31/12/2024 | 1838/KSD | 28/12/2023 | 366 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0 | 0
2117 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11609 | Augmentation | RESTORATION OF ROAD FROM SALIGRAM POST OFFICE - CHUPIPOTA VILLAGE under Package No. WB/14/135 | 300/PFMS | 02/10/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 10.95 | 0 | 0 | 0
2118 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11609 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | 3537/ND | 11/08/2023 | 782 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 452.19 | 75.96 | 20
2119 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11609 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 0 | 30
2120 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11609 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub Division, PHE Dte for supervision of JJM works for the period of 01/01/2025 to 31/12/2025 | 2666/KSD | 31/12/2024 | 365 | AVINABA ENGINEERING CONCERN | 4.8 | 0 | 0 | 0
2121 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11609 | Augmentation | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3829/ND | 13/08/2025 | 120 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0 | 0
2122 | NADIA | Nadia Division | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/11919 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Palsunda W/S Scheme in Tehatta-II Block of Nadia District under Nadia Division, P.H.E. Dte. | 308/TSD | 24/11/2021 | 30 | RADIANT | 3.08 | 2.95 | 100 | 100
2123 | NADIA | Nadia Division | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/11919 | Augmentation | Material Requisition To Resource Division | 1908/ND | 27/04/2023 | 0 | Resource Division | 144.56 | 0 | 0 | 0
2124 | NADIA | Nadia Division | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/11919 | Augmentation | Material Requisition To Resource Division | 2300/ND | 29/05/2023 | 0 | Resource Division | 31.86 | 0 | 0 | 0
2125 | NADIA | Nadia Division | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/11919 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 120 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Polsunda to accommodate FHTC within Tehatta-II block under Nadia Division, P.H.E. Dte. | 4191/ND | 31/07/2024 | 180 | MONDAL ENTERPRISE | 297.09 | 0 | 0 | 0
2126 | NADIA | Nadia Division | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/11919 | Augmentation | Making barbed wire fencing with concrete pillars at Polsunda water supply scheme (New Land)H.W.Site under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . | 1116/TSD | 21/02/2024 | 7 | PRABIR KUMAR ROY | 2.94 | 2.84 | 100 | 100
2127 | NADIA | Nadia Division | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/11919 | Augmentation | Laying of 63mm dia UPVC Pipe line for Revision of drawing to accommodate FHTC & Construction of Jhama Bats Road for the approach way to headwork site of Palsunda water supply scheme under Kalyani Sub Division I under Nadia Division P.H.Engineering Dte. | 3454/ND | 20/06/2024 | 60 | MONDAL ENTERPRISE | 54.5 | 54.32 | 100 | 98
2128 | NADIA | Nadia Division | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/11919 | Augmentation | Lying distribution system for providing FHTC at Palsunda Mouza in connection with Augmentation of Ground Based Water Supply Scheme at Palsunda to accommodate FHTC under Nadia Division, PHE Dte. | 3455/ND | 20/06/2024 | 90 | MONDAL ENTERPRISE | 96.94 | 25.86 | 21.07 | 100
2129 | NADIA | Eastern Mechanical | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/11919 | Augmentation | Quotation charges and security deposit for new power connection at Palsunda-III head worksite under Eastern Mechanical Subdivision-III, Nadia | BP-183 | 13/12/2024 | 0 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 7.79 | 0 | 0 | 0
2130 | NADIA | Eastern Mechanical | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/11919 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under KARIMPUR JALANGI(Z-8) W/S Scheme, Block- Karimpur II, PALSONDHA W/S Scheme, Block- Tehatta II, & MAIDANPUR W/S Scheme, Block- Chapra, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 06) | 1179/EMD | 21/03/2023 | 940 | CREATIVE WATER & PROCESS TECHNOLOGIES PVT. LTD. | 77.9 | 0 | 0 | 85
2131 | NADIA | Nadia Division | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. , SM/11919 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 650 Cum Capacity 20 Mtr. Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of OHR all complete for Augmentation of Ground Based Water Supply Scheme at Palsunda to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 1720/ND | 17/04/2023 | 1096 | MONDAL ENTERPRISE, MASJID BARI ROAD,UTTAR BALURIA, P.O.NABAPALLY, P.S. BARASAT NORTH 24 PGS. | 593.41 | 339.64 | 57.23 | 45
2132 | NADIA | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME , SM/11965 | New | Material Requisition To Resource Division | 1089/NACD-II | 09/12/2022 | 0 | Resource Division | 33.57 | 0 | 0 | 0
2133 | NADIA | Eastern Mechanical | BINODNAGAR PIPED WATER SUPPLY SCHEME , SM/11965 | New | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at BINODNAGAR Piped Water SupplyScheme, Block: Tehatta-I, Dist. Nadia Under EMD, PHE Dte. | 4709/EMD | 04/08/2023 | 30 | M/S DILIP MITRA | 40.82 | 0 | 0 | 0
2134 | NADIA | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME , SM/11965 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Binodnagar) | 888/NACD-II | 18/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
2135 | NADIA | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME , SM/11965 | New | Material Requisition To Resource Division | 374/NACD-II | 24/03/2023 | 0 | Resource Division | 11.09 | 0 | 0 | 0
2136 | NADIA | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME , SM/11965 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL | 235/7 | 21/02/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0 | 0
2137 | NADIA | Eastern Mechanical | BINODNAGAR PIPED WATER SUPPLY SCHEME , SM/11965 | New | New Service Connection at Pump House-I under Binodnagar Water Supply Scheme | BP-109-23-24 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.57 | 0 | 0 | 0
2138 | NADIA | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME , SM/11965 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. | 23 | 19/04/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
2139 | NADIA | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME , SM/11965 | New | Sinking of 2 nos. 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Binodnagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 1133/NACD-II | 16/12/2022 | 30 | GENUINE | 21.45 | 16.99 | 100 | 100
2140 | NADIA | Eastern Mechanical | BINODNAGAR PIPED WATER SUPPLY SCHEME , SM/11965 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under BINODNAGAR W/S Scheme (Block : Tehatta I) Dist.- Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 10) | 1609/EMD | 26/04/2023 | 30 | ABHISEK ENGINEERING CONCERN | 18.99 | 18.79 | 100 | 80
2141 | NADIA | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME , SM/11965 | New | Construction of approch road at Head Works site of Binodnagar Water Supply Scheme in Tehatta-1 Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | 408/AE-I/NACD-II | 08/08/2023 | 15 | B.M. ENGINEERING & CONSTRUCTION | 0.97 | 0.96 | 100 | 100
2142 | NADIA | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME , SM/11965 | New | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Binodnagar water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia | 1170/NACD-II | 11/10/2023 | 45 | R.M. TRADING | 11.32 | 10.75 | 100 | 90
2143 | NADIA | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME , SM/11965 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Binodnagar and Putimari PWSS in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 294_AE-II/NACD-II | 30/08/2024 | 20 | MAKALI ENGINEERING CORPORATION | 4.17 | 4.17 | 100 | 100
2144 | NADIA | Eastern Mechanical | BINODNAGAR PIPED WATER SUPPLY SCHEME , SM/11965 | New | Quotation for new Service connection at P.H-II under Binodnagar W/S Scheme, Dist-Nadia | BP-283-23-24 | 16/02/2024 | 0 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 4.61 | 0 | 0 | 0
2145 | NADIA | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME , SM/11965 | New | Soil Investigation for Construction of 01 (One) No of Overhead Reservoir, Construction of 01 (One) No of 350 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap, Laying of Distribution system including providing Functional House Hold Tap Connection (FHTC) and Laying of Rising Main and other necessary allied works at Binodnagar Water Supply Scheme and other necessary allied works in this connection of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 397/NACD-II | 28/03/2023 | 903 | B.M. ENGINEERING & CONSTRUCTION | 298.5 | 59.33 | 19.88 | 52
2146 | NADIA | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME , SM/11965 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 46.51 cum/Hour capacity for Binodnagar Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1475/NACD-II | 12/11/2024 | 395 | B.M. ENGINEERING & CONSTRUCTION | 177.87 | 0 | 0 | 0
2147 | NADIA | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME , SM/11965 | New | Acceptance cum work order "Conversion of IEP to AIRP at Mobarakpur, Binodnagar & Taranipur Water Supply Scheme of capacity 93 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | 152/NACD-II | 02/02/2024 | 598 | B.M. ENGINEERING & CONSTRUCTION | 241.81 | 0 | 0 | 0
2148 | NADIA | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME , SM/11965 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-II Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. & including Binodnagar PWSS,Manoharpur PWSS, Rajapur PWSS & Taranipur PWSS. | 428/NACD-II | 07/04/2025 | 180 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 19.28 | 0 | 0 | 30
2149 | NADIA | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME , SM/11965 | New | Continuation Work Order for Installation of Sign Board for Demarcation of Land for Binodnagar & other PWSS at Tehatta-I, Barnia & other PWSS at Tehatta-II, Karimpur-II, Jayrampur & other PWSS at Karimpur-I & Maniknagar PWSS at Shantipur Block under Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 02/AE-I/NACD-II | 02/04/2025 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 3.75 | 0 | 0 | 0
2150 | NADIA | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | Material Requisition To Resource Division | 1091/NACD-II | 09/12/2022 | 0 | Resource Division | 27.83 | 0 | 0 | 0
2151 | NADIA | Eastern Mechanical | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at RAJAPUR Piped Water Supply Scheme, Block: Tehatta-I, Dist. Nadia Under EMD, PHE Dte. | 4711/EMD | 04/08/2023 | 30 | INDIA ENTERPRISE | 40.8 | 0 | 0 | 0
2152 | NADIA | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | Construction for priliminary work of the approch road at Head Works site of Rajapur Water Supply Scheme in Tehatta-1 Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | 410/AE-I/NACD-II | 08/08/2023 | 15 | JOY HIND TUBEWELLS | 0.97 | 0 | 0 | 0
2153 | NADIA | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | Sinking of 2 nos. 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Rajapur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 1136/NACD-II | 16/12/2022 | 30 | AUXILIARY TUBE WELL DRILLERS | 21.03 | 18.4 | 100 | 100
2154 | NADIA | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-I Block of Nadia District through Jadavpur University (Name of PWSS Rajapur) | 1154/NACD-II | 10/10/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
2155 | NADIA | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | Material Requisition To Resource Division | 376/NACD-II | 24/03/2023 | 0 | Resource Division | 12.69 | 0 | 0 | 0
2156 | NADIA | Eastern Mechanical | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | New Service Connection at Pump House-II under Rajapur Water Supply Scheme | BP-110-23-24 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.66 | 0 | 0 | 0
2157 | NADIA | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL | 235/8 | 21/02/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0 | 0
2158 | NADIA | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. | 23 | 19/04/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
2159 | NADIA | Eastern Mechanical | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | New Service Connection at Pump House-I under Rajapur Water Supply Scheme | BP-111-23-24 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.88 | 0 | 0 | 0
2160 | NADIA | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Rajapur water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 1132/NACD-II | 09/10/2023 | 45 | SANJIT DAS | 11.34 | 11.27 | 100 | 90
2161 | NADIA | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | Renovation of Arsenic cum Iron treatment Plant of Khanjipur PWSS (Capacity- 21 m3/hr) and ancillary works of Rajapur W/s Scheme at Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 38/NACD-II | 09/01/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 61.75 | 49.88 | 100 | 70
2162 | NADIA | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | Material Requisition To Resource Division | 74/NACD-II | 15/01/2024 | 0 | Resource Division | 12.69 | 0 | 0 | 0
2163 | NADIA | Eastern Mechanical | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | Supplimentary Quotation for new service connection against Application No-3004365000 for NSC at Rajapur P.H-II w/s scheme | BP-07-24-25 | 23/04/2024 | 0 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 0.74 | 0 | 0 | 0
2164 | NADIA | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | Soil Investigation for Construction of 01 (One) No of Overhead Reservoir, Construction of 01 (One) No of 350 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap, Laying of Distribution system including providing Functional House Hold Tap Connection (FHTC) and Laying of Rising Main and other necessary allied works at Rajapur Water Supply Scheme and other necessary allied works in this connection of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 401/NACD-II | 28/03/2023 | 1094 | JOY HIND TUBEWELLS | 442.76 | 303.63 | 68.58 | 40
2165 | NADIA | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | Acceptance cum work order "Conversion of IEP to AIRP at Bahadurpur & Rajapur Water Supply Scheme of capacity 16 Cu.m/hr under in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | 424/NACD-II | 15/03/2024 | 420 | CHAKRABORTTI ENTERPRISE | 92.52 | 0 | 0 | 70
2166 | NADIA | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 53.24 cum/Hour capacity for Rajapur Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1399/NACD-II | 23/10/2024 | 360 | JOY HIND TUBEWELLS | 185.73 | 0 | 0 | 0
2167 | NADIA | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | Acceptance cum work order "Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Rajapur water supply scheme under Tehatta- I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia." | 408/NACD-II | 13/03/2024 | 315 | DEBASIS SAMADDAR | 26.21 | 4.77 | 18.2 | 1
2168 | NADIA | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-II Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. & including Binodnagar PWSS,Manoharpur PWSS, Rajapur PWSS & Taranipur PWSS. | 428/NACD-II | 07/04/2025 | 180 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 19.28 | 0 | 0 | 30
2169 | NADIA | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/11966 | New | Laying of distribution system including providing FHTC at left out households for Bahadurpur, Khaspu, Dhopahat and Rajapur W/s Scheme and restoration of the damaged portion of roads in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte and Brittihuda W/S Scheme & Barnia W/S Scheme included. | 736/NACD-II | 18/06/2025 | 90 | JOY HIND TUBEWELLS | 186.42 | 0 | 0 | 40
2170 | NADIA | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District , SM/14063 | New | Route Survey, Design of Distribution Network and Preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno for Anjangarh Water Supply Scheme in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte. | 424/RSD | 08/05/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.45 | 2.45 | 99.72 | 0
2171 | NADIA | Central Drilling | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District , SM/14063 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR ANJANGARH W/S SCHEME (TW-I & II), RANAGHAT-I BLOCK UNDER NADIA DISTRICT, CDD, PHE DTE. | 1230/CDD | 04/09/2023 | 30 | MENAKA ENTERPRISE | 37.76 | 29.02 | 100 | 100
2172 | NADIA | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District , SM/14063 | New | Material Requisition To Resource Division | 1871/ND | 26/04/2023 | 0 | Resource Division | 11.91 | 0 | 0 | 0
2173 | NADIA | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District , SM/14063 | New | Material Requisition To Resource Division | 2586/ND | 13/06/2023 | 0 | Resource Division | 11.91 | 0 | 0 | 0
2174 | NADIA | Eastern Mechanical | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District , SM/14063 | New | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at Anjangarh Piped Water Supply Scheme Block_ Ranaghat-I Dist. - Nadia under EMD, PHE Dte. 2024_PHED_664112_3 | 925/EMD | 15/03/2024 | 30 | DEY ENTERPRISE | 42.34 | 0 | 0 | 0
2175 | NADIA | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District , SM/14063 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 30 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Anjangarh to accommodate FHTC within Ranaghat-I block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | 4126/ND | 29/07/2024 | 180 | G.D. CONSTRUCTION AND CO. | 161.1 | 0 | 0 | 0
2176 | NADIA | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District , SM/14063 | New | Material Requisition To Resource Division | 272/ND | 11/01/2024 | 0 | Resource Division | 3.55 | 0 | 0 | 0
2177 | NADIA | Eastern Mechanical | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District , SM/14063 | New | New Service connection Charges for ANJANGARH Piped Water supply scheme PUMP House No- II | BP-37-24-25 | 31/05/2024 | 0 | WBSEDCL BADKULLA CCC | 3.8 | 0 | 0 | 0
2178 | NADIA | Eastern Mechanical | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District , SM/14063 | New | NEW SERVICE CONNECTION CHARGES FOR ANJANGARH PWSS PH-I (HEAD WORK SITE) | BP-52-24-25 | 21/06/2024 | 0 | WBSEDCL BADKULLA CCC | 7.88 | 0 | 0 | 0
2179 | NADIA | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District , SM/14063 | New | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | 3784/ND | 12/08/2025 | 31 | IMAGIN | 34.21 | 0 | 0 | 0
2180 | NADIA | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District , SM/14063 | New | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 100 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials SOIL INVESTIGATION FOR CONSTRUCTION OF OHR all complete for Ground Water Based Water Supply Scheme for Anjangarh to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. | 963/ND | 09/03/2023 | 815 | M/S BISWAS BROTHERS, VIVEKNAGAR, P.O-NOAPARA, P.S-BARASAT, KOLKATA-700125 | 135.42 | 78.87 | 58.24 | 95
2181 | NADIA | Eastern Mechanical | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District , SM/14063 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Anjangarh ground water based water supply scheme under Block_ Ranaghat-I Dist. - Nadia under EMD, PHE Dte. | 803/EMD | 11/03/2024 | 475 | S.G. ENTERPRISE | 25.38 | 0 | 0 | 85
2182 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MADHPUR (PHASE-II) IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15537 | Augmentation | Material Requisition To Resource Division | 141/ND | 06/01/2023 | 0 | Resource Division | 1.24 | 0 | 0 | 0
2183 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MADHPUR (PHASE-II) IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15537 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 31.44 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Madhpur PWSS under Nadia Division PHE Dte. | 1456/ND | 31/03/2023 | 90 | APURBA MANDAL | 58.68 | 0 | 0 | 21
2184 | NADIA | Nadia Division | Retrofitting of Providing FHTC at Ground Water based Ber Ramchandrapur Zone-I Water Supply Scheme within Karimpur-I Block (Phase-1) , SM/07492 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT BER-RAM CHANDRAPUR Z-1 | 460/DW | 30/03/2021 | 0 | JOY HIND TUBEWELL'S | 40.81 | 0 | 0 | 0
2185 | NADIA | Nadia Division | Retrofitting of Providing FHTC at Ground Water based Ber Ramchandrapur Zone-I Water Supply Scheme within Karimpur-I Block (Phase-1) , SM/07492 | Retrofitting | Retrofitting of Providing FHTC at Ground Water based Ber Ramchandrapur Zone-I Water Supply Scheme within Karimpur-I Block (Phase-1). | 232/PFMS | 05/10/2021 | 0 | MALI CONSTRUCTION | 2.35 | 0 | 0 | 0
2186 | NADIA | Nadia Division | Retrofitting of Providing FHTC at Ground Water based Ber Ramchandrapur Zone-I Water Supply Scheme within Karimpur-I Block (Phase-1) , SM/07492 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Ber Ramchandrapur Zone-I W/S scheme (Phase-I) of Rectrofitting in Nadia District under Nadia Division P.H.E. Dte. | 59/ND | 07/01/2021 | 75 | JOY HIND TUBEWELL'S | 55.08 | 1.98 | 3.59 | 100
2187 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-II Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofi , SM/08846 | Retrofitting | Construction of Boundary wall, pathway and others allied works at Head Work site of Goalsalua, Zone-II under Nadia Arsenic Division-I, P.H.E. Dte. Length of Boundary wall - 156 metre. | 73/NAD-I | 17/01/2022 | 30 | D.K. CONSTRUCTION | 17.59 | 13.75 | 100 | 95
2188 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-II Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofi , SM/08846 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Goalsalua Zone-II Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 77/NAD-I | 17/01/2022 | 90 | M/S NIBHAS SINHA | 110.34 | 106.66 | 100 | 100
2189 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-II Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofi , SM/08846 | Retrofitting | Augmentaton of Distribution pipeline at Rajapur , Kesaipur village under Goalsalua Zone II water supply scheme at Ranaghat-II Block by providing FHTCs & dedicated pipeline from common manifold under Nadia Arsenic Division-I, PHE Dte as a part of JJM. (Sl. NO. 05) | 2057/NAD-I | 09/12/2024 | 60 | SUMIT GHOSH | 91.9 | 0 | 0 | 0
2190 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-II Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofi , SM/08846 | Retrofitting | Laying Dedicated Pipe line to supply water for Pachberia Coloni Area under Goalsalua Zone II Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 06) | 1949/NAD-I | 27/11/2024 | 60 | BIPLAB GUHA | 70.82 | 0 | 0 | 0
2191 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-II Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofi , SM/08846 | Retrofitting | Construction and installation of MANIFOLD and allied works at OHR site under Goalsalua Zone-II Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Goalsalua Zone-II under JJM (Sl.no.07) | 1458/NAD-I | 29/05/2023 | 15 | ROY ASSOCIATES | 13.04 | 0 | 0 | 100
2192 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Fatepur Water Supply Scheme In Hanskhali Block District Nadia (Two Stage Pumping) , SM/16367 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2193 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Nazirpur Water Supply Scheme in Tehatta-I Block, Dist.-Nadia. , SM/16336 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2194 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte , SM/09575 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | 608/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.82 | 0 | 0 | 0
2195 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte , SM/09575 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer etc for Augmentation to Accommodate FHTC at Pump House No.II Zone II under Paschim Bhatjangla WS Scheme, Block Krishnagar 1, Dist. Nadia under Eastern Mechanical Division, PHE Dte. NIET No.- 22 of EE/EMD of 2022-23 (Sl. No.- 03) | 6505/EMD | 01/12/2022 | 30 | M/S. PS & ASSOCIATES | 4.38 | 4.28 | 100 | 90
2196 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte , SM/09575 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. for Augmentation to Accomodate FHTC at Pump House No.I(Zone-II) under Paschim Bhatjangla W/S Scheme, Block-Krishnagar 1, District of Nadia. NIET No.- 14 of EE/EMD of 2022-23 (Sl. No.- 03) | 3912EMD | 19/10/2022 | 30 | STANDARD ENGINEERING | 7.97 | 7.97 | 100 | 80
2197 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte , SM/09575 | Augmentation | Supplementary works to completion of ongoing FHTC-related work at PH-I of Paschim Bhatjangla (Zone - II) W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | 616/EMSD-II | 24/08/2023 | 15 | STANDARD ENGINEERING | 0.21 | 0.21 | 100 | 100
2198 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte , SM/09575 | Augmentation | Material Requisition To Resource Division | 4294/ND | 29/09/2022 | 0 | Resource Division | 1.21 | 0 | 0 | 0
2199 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte , SM/09575 | Augmentation | Material Requisition To Resource Division | 1262/ND | 16/03/2022 | 0 | Resource Division | 1.72 | 0 | 0 | 0
2200 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte , SM/09575 | Augmentation | Deposit works, and new service connection under bhatjangla W/S Scheme. | BP-240-23-24 | 04/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.21 | 0 | 0 | 0
2201 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte , SM/09575 | Augmentation | Providing FHTC by augmentation under Jal Swapna for Paschim Bhatjangla Zone-II Water Supply Scheme in Krishnagar-I Block of Nadia District. | 67/ND | 05/01/2022 | 90 | JAGANNATH ENTERPRISE | 68.71 | 46.42 | 67.56 | 100
2202 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte , SM/09575 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Banpur ii) Dakshinpara (Zone-I)iii) Dakshinpara (Zone-II) iv) Kamgachi (Zone-I)(Part-I) v)Kamgachi (Zone-I)(Part-II)vi)Kamgachi (Zone-II)(Part-I) vii) Kamgachi (Zone-II)(Part-II) | 246/Kly SD-I | 27/02/2023 | 181 | HORIZEN | 4.99 | 3.4 | 100 | 100
2203 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte , SM/09575 | Augmentation | Additional Laying of UPVC Pipeline and providing FHTC including supplying, laying, fitting, fixing of 15 mm NB PVC pipe with all necessary specials, saddle piece etc.in connection to the Augmentation of Ground Based piped water supply scheme at Bablari-Dewanganj to accommodate FHTC within Nabadwip block under Krishnanagar Sub-Division under Nadia Division, PHE Dte. | 1847/ND | 26/04/2023 | 60 | A.K.ADHIKARY | 15.77 | 13.78 | 100 | 95
2204 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte , SM/09575 | Augmentation | Supplimentary works to completion of ongoing FHTC-related work at PH-II of Paschim Bhatjangla (Zone-II) W/S Scheme (Block - Krishnagar - I), PHE Dte., dist.- Nadia. | 593/EMSD-II | 21/08/2023 | 15 | M/S. PS & ASSOCIATES | 0.15 | 0.15 | 100 | 100
2205 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte , SM/09575 | Augmentation | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 9.24 | 100 | 81
2206 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte , SM/09575 | Augmentation | Wall Writing Work under Nadia Division P. H. Engineering Dte. | 1821/ND | 14/03/2024 | 31 | IMAGIN | 34.21 | 1.2 | 100 | 60
2207 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte , SM/09575 | Augmentation | Additional work of Laying Distribution System and additional work of Providing FHTC in connection with Augmentation of Paschim Bhatjangla Zone-II Water Supply Scheme under RWS Nadia Sub-Division, PHE Dte. | 147/ND | 09/01/2024 | 450 | M/S A.K. ENTERPRISE | 33.76 | 17.82 | 52.77 | 70
2208 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte , SM/09575 | Augmentation | Construction Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 31.00 cum/hr at Paschim Bhatjangla water supply scheme including 3 Months Trial Run & 3 Years O&M within Krishnagar-I block under RWS Nadia Sub-division under Nadia Division, P.H.E. Dte | 1251/ND | 22/02/2024 | 180 | APURBA MANDAL | 163.44 | 0 | 0 | 45
2209 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte , SM/09575 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir, Pump House, Boundary Wall and Construction of Service Road for Paschim Bhatjangla Zone-II Water Supply Scheme under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 6117/ND | 21/12/2023 | 540 | KESHOB ENTERPRISE | 29.88 | 5.93 | 19.86 | 80
2210 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte , SM/09575 | Augmentation | Sinking of 1 No. Big Dia Tubewell 300mm. x 200mm & 200 mtr deep by Direct Rotary Rig Method using PVC pipe & UPVC deep well screen (RDS) pipes with Ribs etc. including inter connection of Rising Main System for Paschim Bhatjangla Zone-II Water Supply Scheme at Head Work Site under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 5035/ND | 13/09/2024 | 45 | ZEST INFRACON | 16.29 | 0 | 0 | 60
2211 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Barnia Water Supply Scheme in Tehatta-II Block, Dist.-Nadia. , SM/16344 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2212 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Bhandar Khola Water Supply Scheme in Krishnagar-I Block, Dist.- Nadia. , SM/16826 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2213 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Dignagar Water Supply Scheme in Krishnagar-I Block, Dist.- Nadia. , SM/16828 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2214 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Arabpur Water Supply Scheme in Karimpur-I Block of District Nadia , SM/16792 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2215 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Baruipara Water Supply Scheme in Karimpur-I Block of District Nadia , SM/16793 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2216 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Karimpur Water Supply Scheme in Karimpur-I Block of District Nadia , SM/16795 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2217 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Uttar Tajpur Water Supply Scheme in Karimpur-I Block of District Nadia , SM/16799 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2218 | NADIA | Eastern Mechanical | Mini Piped Water Supply Scheme at Shatikhali (Part-A) village, Block- Tehatta-II, Nadia District, Under Nadia Arsenic Civil Division-II. , SM/16102 | New | Quotation for new service connection charges and security deposit for Satiakhali part- A | BP-199-24-25 | 17/12/2024 | 0 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 0.1 | 0 | 0 | 0
2219 | NADIA | Eastern Mechanical | Mini Piped Water Supply Scheme at Shatikhali (Part-A) village, Block- Tehatta-II, Nadia District, Under Nadia Arsenic Civil Division-II. , SM/16102 | New | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 0 | 80
2220 | NADIA | Nadia Arsenic Civil Division II | Mini Piped Water Supply Scheme at Shatikhali (Part-A) village, Block- Tehatta-II, Nadia District, Under Nadia Arsenic Civil Division-II. , SM/16102 | New | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Shatikhali (Part-A) of Tehatta-II Block under Nadia Arsenic Civil Division-II PHE Dte | 562/NACD-II | 11/05/2023 | 990 | M/S GHOSH CONSTRUCTION | 30.05 | 19.76 | 65.77 | 80
2221 | NADIA | Eastern Mechanical | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Ranaghat-I & II Blocks in Nadia District under Eastern Mechanical Division PHE Dte. , SM/16847 | Solarisation | Solarisation of WBSEDCL Energised Electrical installation including net metering at different Pipe Water Supply Scheme at Ranaghat-I & Ranaghat-II Blocks in Nadia District under E.M.D. P.H.E. Dte. | 6421/EMD | 31/10/2023 | 182 | EQUIPMENTS AND SPARES AGENCIES | 619.7 | 0 | 0 | 0
2222 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Fazilnagar Water Supply Scheme in Karimpur-II Block of District Nadia , SM/16802 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2223 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Digri Water Supply Scheme in Krishnagar-I Block, Dist.- Nadia. , SM/16836 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2224 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Bansbaria Water Supply Scheme in Krishnagar-I Block, Dist.- Nadia. , SM/16839 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2225 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Dafarpota Water Supply Scheme (Zone - I & II) in Krishnagar-I Block, Dist.- Nadia. , SM/16840 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2226 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Bhaluka Water Supply Scheme in Krishnagar-I Block, Dist.- Nadia. , SM/16825 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2227 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Baganchara Water Supply Scheme in Shantipur Block, Dist,- Nadia , SM/17263 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2228 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Beharia Water Supply Scheme in Shantipur Block, Dist,- Nadia , SM/17264 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2229 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Preparation of Detailed Project Report (DPR) for Integrated Surface Water Based PWSS for Ranaghat-I & Ranaghat-II Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.03) | 1610/NAD-I | 22/06/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 57.65 | 57.65 | 100 | 100
2230 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Material Requisition To Resource Division | 1085/NAD-I | 25/04/2023 | 0 | Resource Division | 1599.91 | 0 | 0 | 0
2231 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Material Requisition To Resource Division | 1887/NAD-I | 11/08/2023 | 0 | Resource Division | 1117.16 | 0 | 0 | 0
2232 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Material Requisition To Resource Division | 1874/NAD-I | 10/08/2023 | 0 | Resource Division | 1012.08 | 0 | 0 | 0
2233 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Bill for Wayleave/Track crossing proposal with Application ID ER-SDAH-2023-WL-31 in IR-RBCS has been approved in-principle subject to the payment of Wayleave facility. | 146/PFMS | 04/07/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 6.15 | 0 | 0 | 0
2234 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-49 in IR-RBCS is pending for payment. | 179/PFMS | 04/08/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.15 | 0 | 0 | 0
2235 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-73 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 345/PFMS | 23/11/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0 | 0
2236 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-49 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 221/PFMS | 20/09/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 9.96 | 0 | 0 | 0
2237 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Bill for Wayleave/Track crossing proposal with Application ID ER-SDAH-2023-WL-32 in IR-RBCS has been approved in-principle subject to the payment of Wayleave facility. | 147/PFMS | 04/07/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.91 | 0 | 0 | 0
2238 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-52 in IR-RBCS is pending for payment. | 177/PFMS | 04/08/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0 | 0
2239 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-50 in IR-RBCS is pending for payment. | 178/PFMS | 04/08/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.22 | 0 | 0 | 0
2240 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-75 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 349/PFMS | 23/11/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.32 | 0 | 0 | 0
2241 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Bill for Taherpur flag to Badkulla station railway crossing for JJM works under Office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 220/PFMS | 20/09/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.25 | 0 | 0 | 0
2242 | NADIA | Eastern Mechanical | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Earnest money for new service connection at Ranaghat GLR-1 of integrated surface water based PWSS. | BP-126-23-24 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.05 | 0 | 0 | 0
2243 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-71 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 348/PFMS | 23/11/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0 | 0
2244 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-74 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 346/PFMS | 23/11/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0 | 0
2245 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-50 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 240/PFMS | 20/09/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 14.94 | 0 | 0 | 0
2246 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Shifting of Electric Pole from the proposed GLR Site inside the Campus of water Management Research Station, Begopara (Patuli) Ranaghat-II Block, under Nadia Arsenic Division-I, PHE Dte. | 396/PFMS | 18/12/2023 | 0 | WBSEDCL | 0.06 | 0 | 0 | 0
2247 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-51 in IR-RBCS is pending for payment. | 180/PFMS | 04/08/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.3 | 0 | 0 | 0
2248 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-51 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 340/PFMS | 13/11/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 19.06 | 0 | 0 | 0
2249 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-72 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 347/PFMS | 23/11/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0 | 0
2250 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Supply of documents for way leave permission from the Eastern Railways authority at 2 nos of locations on Ranaghat-Krishnagar, Ranaghat -Shantipur&Ranaghat-Bongaon Railway track under Intregrated surface Water Based PWSS for Ranaghat-I & II Block under Nadia Arsenic Division-I, PHE Dte. Intersection Name: 1) AV24- AV28 Birnagar Rail Gate) 2) AV61- AV64 Taherpur Rail Gate) | 309/AE-I/NAD-I | 28/07/2023 | 90 | SUMAN CHAKRABORTY | 3.84 | 3.84 | 100 | 100
2251 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Name of Work: Supply of documents for way leave permission from the Eastern Railways authority at 9 nos of locations on Ranaghat- Krishnagar, Ranaghat- Shantipur & Ranaghat-Bongaon Railway track under Intregrated Surface Water Based PWSS for Ranaghat-I & II Block under Nadia Arsenic Division-I, PHE Dte. | 2343/NAD-I | 03/10/2023 | 25 | SATYABRATA CHAKRABORTY | 17.28 | 17.28 | 100 | 100
2252 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Pond side earth protection with Eucalyptus bullah piling at Kamgachi GLR Site within Ranaght-II Block under Nadia Arsenic Division-I,P.H.E. Dte. | 96/AE-I/NAD-I | 27/02/2024 | 15 | R R ENTERPRISE | 4.38 | 4.25 | 100 | 100
2253 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-75 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 442/PFMS | 12/01/2024 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 20.56 | 0 | 0 | 0
2254 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-73 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 439/PFMS | 12/01/2024 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.27 | 0 | 0 | 0
2255 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-74 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 441/PFMS | 12/01/2024 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 4.93 | 0 | 0 | 0
2256 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-72 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 438/PFMS | 12/01/2024 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.27 | 0 | 0 | 0
2257 | NADIA | Eastern Mechanical | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | New Service Connection and security deposit for new bulk power supply at Kamgachi Zone-I W/S Scheme. | BP-258-23-24 | 29/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 43.18 | 0 | 0 | 0
2258 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-71 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 437/PFMS | 12/01/2024 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.35 | 0 | 0 | 0
2259 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | SHIFTING OF POLE AT GANGNAPUR PHE | 100/PFMS | 11/07/2024 | 0 | W.B.S.E.D.C.L (GANGNAPURC.C.C) | 0.41 | 0 | 0 | 0
2260 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Laying of DI Rising Main of Ranaghat I & II Block, Construction of 4 Nos. 100 Cum GLR, 1 No 50 Cum GLR, Construction of 900, 500, 150& 2 Nos. 1500 M3 OHR at Different Location, 6 Nos. Chlorine Room & 5 Nos. Pump House of Integrated Surface Water Based PWSS for Ranaghat-I and Ranaghat-II Block under Nadia Arsenis Division-I P.H.E. Dte (Sl.no.01) | 1897/NAD-I | 14/08/2023 | 1095 | AMAL DUTTA ROY | 3770.77 | 809.9 | 21.48 | 90
2261 | NADIA | Eastern Mechanical | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Providing Electro-Mechanical Equipment for 11/0.433 KV Sub-station along with pumping station and disinfection arrangement for GLR-I at Kamgachi under Surface based Water Supply Scheme for Ranaghat-I Block in the District of Nadia. | 6260/EMD | 10/10/2023 | 629 | WEST BENGAL ENGINEERING CO. | 733.62 | 432.78 | 58.99 | 53
2262 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Laying and repairing of damaged UPVC pipeline of different existing piped water supply schemes under PHED at Ranaghat-I & II Block due to laying of DI Secondary Rising main under Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block, including restoration of village roads by Jhama Metal, Rail/National Way Crossing of pipeline, Pipe Carriage and allied works Under Nadia Arsenic Division-I, P.H.E. Dte. | 1748/NAD-I | 24/10/2024 | 270 | AMAL DUTTA ROY | 474.38 | 0 | 0 | 80
2263 | NADIA | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/18257 | New | Carriage of DI pipes including Pipe carrying structure, road restoration, repair of damaged UPVC pipeline, crossing of pipeline by jack pushing, pathway and allied works related to Integrated Surface Water Based Water Supply Scheme under Ranaghat-I & II Blocks under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 04) | 786/NAD-I | 12/08/2025 | 120 | AMAL DUTTA ROY | 559.99 | 0 | 0 | 0
2264 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Senpur (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17210 | Augmentation | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Senpur (Phase-II) Piped Water Supply Scheme, Block: Krishnagar-I, Dist. Nadia Under EMD, PHE Dte. | 6362/EMD | 17/10/2023 | 30 | TARUN KUMAR BHATTACHARYA | 53.52 | 0 | 0 | 0
2265 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Senpur (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17210 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 93.00 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Senpur PWSS under Nadia Division PHE Dte. | 1786/ND | 20/04/2023 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 234.23 | 169.94 | 100 | 57
2266 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Senpur (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17210 | Augmentation | WBSEDCL's Quotation of new service connection in Bulk contract demand to the Head Work site under Senpur W/S Scheme in Krishnagar-I Block , PHE Dte. Nadia (Application No.3004752314) | BP-53-24-25 | 21/06/2024 | 0 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 3.47 | 0 | 0 | 0
2267 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10663 | Augmentation | Route Survey for preparation of DPR for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for DUTTAPULIA ZONE-I Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic-I Division, PHE Dte. (Sl. No.-07) | 68/AE-II/N.A.D.-I | 24/02/2022 | 30 | UMWELT ENGINEER PVT. LTD. | 4.74 | 4.74 | 100 | 100
2268 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10663 | Augmentation | Distribution Design for preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Duttapulia Zone - I Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | 69/AE-II/NAD-I | 24/02/2022 | 30 | UMWELT ENGINEER PVT. LTD. | 3.5 | 3.5 | 100 | 100
2269 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10663 | Augmentation | Retrofitting work at .Barberia Colony Paschimpara, Dakshinpara, Kushberia, Paschim para Mouza inconnection with Augmentation to accommodate FHTC under JJM for Duttaphulia Zone- I Ground water based piped water supply scheme (Phase- I) Block- Ranaghat -II under JJM Dist- Nadia under Nadia Arsenic Division-I, PHE Dte. (sl.no10) | 570/NAD-I | 16/03/2023 | 21 | MONDAL ENTERPRISE | 34.86 | 28.92 | 82.97 | 0
2270 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10663 | Augmentation | Material Requisition To Resource Division | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 14.67 | 0 | 0 | 0
2271 | NADIA | Eastern Mechanical | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10663 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejumination Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II and III (Zone-I) (Phase-I) under Duttapulia ground water based water supply scheme under Block_ Ranaghat-II Dist. - Nadia under EMD, PHE Dte. (SM/10663) | 2679/EMD | 20/11/2024 | 30 | GHOSE ENGINEERING SYNDICATE | 32.64 | 0 | 0 | 0
2272 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10663 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Duttaphulia Zone-I (Part-I) at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Duttaphulia Zone-I Water Supply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | 1941/NAD-I | 13/10/2022 | 90 | MONDAL ENTERPRISE | 323.87 | 314.2 | 100 | 95
2273 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10663 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Duttaphulia Zone-I Ground Based Water Supply Scheme under Ranaghat- II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Duttaphulia Zone-I (Phase-I) under JJM (Sl.no.10) | 1365 /NAD-I | 12/05/2023 | 15 | M/S ARATI ENTERPRISE | 13.04 | 12.94 | 100 | 100
2274 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10663 | Augmentation | Work for revamping / upgradation of the hydraulic parameters at Mamjoani mouzas in reference to Mamjoani water supply scheme & Duttaphulia water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 07) | 76/NAD-1 | 16/04/2025 | 240 | JOYGOPAL GUPTI | 96.49 | 0 | 0 | 57
2275 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10663 | Augmentation | Work for revamping / upgradation of the hydraulic parameters at Kamdanga and Nasra Mouza in reference to Nasra and Aranghata water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) | 158/NAD-I | 28/04/2025 | 60 | SAFTI PRIVATE LIMITED | 77.16 | 0 | 0 | 0
2276 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10663 | Augmentation | Work for revamping / upgradation of the hydraulic parameters at Head work site towards Petua and Barberia Mouza in reference to Aranghata and Duttaphulia PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 06) | 77/NAD-I | 16/04/2025 | 60 | DEBASIS SAMADDAR | 95.65 | 0 | 0 | 0
2277 | NADIA | Eastern Mechanical | Augmentation to accommodate FHTC under Duttapulia, Zone-I Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10663 | Augmentation | Providing Boundary Illumination with allied works at Duttapulia, Zone-I (Phase-I) under Block_ Ranaghat-II, Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/10663) | 1165/EMD | 04/06/2025 | 90 | TAMAL ENTERPRISE | 4.34 | 0 | 0 | 0
2278 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Bahirgachi(Zone-I & II) Water Supply Scheme in Chapra Block, Dist.-Nadia. , SM/18047 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2279 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Ukhil Nara Water Supply Scheme in Ranagtat-I Block under District Nadia , SM/18206 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2280 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Aranghata Narayanpur Water Supply Scheme in Ranagtat-II Block under District Nadia , SM/18207 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2281 | NADIA | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Providing drilling crew and other allied works lbr construction olTube Well (300mm X200rrnr X 250 Mtrs. Depth) by utilising Depanmental Machineries for Fulia Tor'r,nship WiS Scherne (Z- Il, 'l'/W-l),Santipur Block r-rnder Nadia District, Central Drilling Division, P.H E. Dte. | 1006/CDD | 09/08/2023 | 30 | UTTAM KUMAR CHATTERJEE | 18.88 | 0 | 0 | 0
2282 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Route Survey, Design of Distribution Network and Preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno for Fulia Township (Zone-II) Water Supply Scheme in Santipur Block of Nadia District under Nadia Division, P.H.E. Dte. | 421/RSD | 08/05/2023 | 15 | HORIZEN | 3.1 | 3.1 | 100 | 100
2283 | NADIA | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBEWELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR FULIA TOWNSHIP W/S SCHEME (Z-II, TW-I), SANTIPUR BLOCK UNDER NADIA DISTRICT, CDD, PHE DTE. | 878/CDD | 11/07/2023 | 30 | UTTAM KUMAR CHATTERJEE | 18.88 | 15 | 100 | 100
2284 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 1.8 | 91.3 | 40
2285 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 210 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Fulia Township Zone-II to accommodate FHTC within Santipur block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | 4314/ND | 06/08/2024 | 180 | MONDAL PRECISION PRIVATE LIMITED | 452.47 | 0 | 0 | 0
2286 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, II , III, IV , V and VI (New) , Zone-II under Fulia Town Ship ground water based water supply scheme under Block_ Santipur Dist. - Nadia under EMD, PHE Dte. [SM-18374] | 2156/EMD | 30/08/2024 | 30 | CONCORD EMC ENCLAVE LLP | 75.36 | 0 | 0 | 0
2287 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Tube well No-3 site at Fulia Zone-II Water supply scheme under Ranaghat Sub ¿ Division, PHE Dte. | 925/RSD | 14/09/2023 | 75 | HANDICRAFT CONSTRUCTION | 4.46 | 1.11 | 20.94 | 100
2288 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Tube well No-4 site at Fulia Zone-II Water supply scheme under Ranaghat Sub - Division, PHE Dte. | 926/RSD | 14/09/2023 | 75 | B K ENGINEERING | 4.46 | 0 | 0 | 100
2289 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Fencing with R.C.C. pillar (9 nos Govt. Land) at different locations under Fulia Zone- I & II water supply scheme under Ranaghat Sub-Division, P.H.E. Dte. | 911/RSD | 13/09/2023 | 15 | APURBA MONDAL, VILL+P.O. BADKULLA, DIST.NADIA, PIN-741121 W.B | 3.22 | 3.17 | 100 | 100
2290 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangemen At Hw Site At Fulia Zone-II Water Supply Scheme Under Ranaghat Sub-Division PHE Dte.) | 5189/ND | 22/11/2023 | 90 | MRINAL DASGUPTA | 6.89 | 6.76 | 100 | 100
2291 | NADIA | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Badkulla/FULIA TOWNSHIP (Z-II) PWSS W/S Scheme(TW-II) , under Nadia District, Central Drilling Division, P.H.E. Dte | 1660/CDD | 17/10/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 18.85 | 14.41 | 100 | 100
2292 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Material Requisition To Resource Division | 3688/ND | 03/07/2024 | 0 | Resource Division | 44.99 | 0 | 0 | 0
2293 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Material Requisition To Resource Division | 7562/ND | 27/12/2024 | 0 | Resource Division | 51.02 | 0 | 0 | 0
2294 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | New Power Connection Charges for FULIA Water Supply Scheme Z-II, Pump House - IV | BP-191-24-25 | 13/12/2024 | 0 | W.B.S.E.D.C.L (FULIA C.C.C) | 7.91 | 0 | 0 | 0
2295 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | New Power connection charges for FULIA Water supply scheme Z-II Pump House No- V | BP-189-24-25 | 13/12/2024 | 0 | W.B.S.E.D.C.L (FULIA C.C.C) | 3.85 | 0 | 0 | 0
2296 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | service connection charges for fulia township | BP-65-24-25 | 10/07/2024 | 0 | W.B.S.E.D.C.L (FULIA C.C.C) | 9.54 | 0 | 0 | 0
2297 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | New power connection charges for FULIA Water Supply scheme Z - II , Pump House No - II | BP-190-24-25 | 13/12/2024 | 0 | W.B.S.E.D.C.L (FULIA C.C.C) | 3.52 | 0 | 0 | 0
2298 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | New power connection charges for FULIA Water supply scheme -II, Pump House No-III | BP-188-24-25 | 13/12/2024 | 0 | W.B.S.E.D.C.L (FULIA C.C.C) | 3.46 | 0 | 0 | 0
2299 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials,saddle piece etc. all complete Construction Of 1000 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection And Cost Of Pipes, Specials & Soil Investigation For Construction Of One No. 1000 Cum OHR Of Staging Height 20 Mtr. for augmentation of Ground Water Based Water Supply Scheme For Fulia Township Zone-II to accommodate FHTC in Santipur block of Nadia District under Nadia Division P.H.Engineering Dte. | 3539/ND | 11/08/2023 | 731 | AMAL DUTTA ROY | 915.05 | 348.75 | 38.11 | 81
2300 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Tube well No-5 site at Fulia Zone-II Water supply scheme under Ranaghat Sub-Division, PHE Dte. | 124/RSD | 29/01/2024 | 60 | M/S ASIT ROY BHOWMICK | 4.36 | 0 | 0 | 100
2301 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Construction of 94.00 mtr long Boundary Wall (2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125mm thick brick panel wall and 200x300 mm tie beam at GL including M.S gate at Fulia Zone-II, Pump House no-VI under Ranaghat Sub-Div , Nadia Division PHE. Dte. | 659/ND | 11/02/2025 | 90 | SADHANA CONSTRUCTION CO. | 8.07 | 0 | 0 | 0
2302 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Construction of 49.00 mtr long Boundary Wall (2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125mm thick brick panel wall and 200x300 mm tie beam at GL including M.S gate at Fulia Zone-II, Pump House no-V under Ranaghat Sub-Division, Nadia Division PHE. Dte. | 88/RSD | 14/01/2025 | 75 | M/S KM ENTERPRISE | 5.43 | 0 | 0 | 0
2303 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Construction of 421.00 mtr long Boundary Wall(2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125 mm thick brick panel wall and 200x300 mm tie beam at GL including M.S gate at Fulia Zone-II, H/W under Ranaghat Sub-Div , Nadia Division PHE. Dte. | 628/ND | 10/02/2025 | 90 | GOPAL KIRTYANIYA | 33.5 | 0 | 0 | 0
2304 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Construction and installation of MANIFOLD and allied works at Head Works site under Fulia Zone-II Ground Based Water Supply Scheme under Santipur Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) | 3255/ND | 10/07/2025 | 90 | MANARAMA ENTERPRISE | 11.7 | 0 | 0 | 0
2305 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Construction of 87.00 mtr long Boundary Wall (2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125mm thick brick panel wall and 200x300 mm tie beam at GL including M.S gate at Fulia Zone-II, Pump House no-III under Ranaghat Sub-Div , Nadia Division PHE. Dte. | 2465/ND | 27/05/2025 | 180 | DEY ENTERPRISE | 9.28 | 0 | 0 | 0
2306 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/18374 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
2307 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Madhabpur Water Supply Scheme in Chapra Block, Dist.-Nadia. , SM/18056 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2308 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Krishnaganj Majhdia Water Supply Scheme in Krishnaganj Block, Dist.-Nadia. , SM/18062 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2309 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-II within Krishnagar-II & Nabadwip (Part) Block (Phase-A) , SM/07453 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT PART-3 Z-2 | 460/DW | 30/03/2021 | 0 | IJABUL SK. | 73.34 | 0 | 0 | 0
2310 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-II within Krishnagar-II & Nabadwip (Part) Block (Phase-A) , SM/07453 | Retrofitting | PROVIDIDING FHTC AT SURFACE WATER BAESD WATER SUPPLY SCHEME NORTHERN SECTOR , PART-II,ZONE-VIII, WITHIN KRISHNAGAR-II & NABADWIP ( PART) BLOCK, PHASE-A. | 500/PFMS | 03/02/2022 | 0 | M/S R. DUTTA & CO. | 0.47 | 0 | 0 | 0
2311 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-II within Krishnagar-II & Nabadwip (Part) Block (Phase-A) , SM/07453 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-II, within Krishnagar-II & Nabadwip Block (Phase-A, Retrofitting)" | 772/ND | 10/02/2021 | 90 | IJABUL SK. | 97.11 | 18.25 | 18.79 | 0
2312 | NADIA | Nadia Division | Augmentation of Ground Water Based Habibpur PWSS to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10420 | Augmentation | Augmentation of Ground Water Based Habibpur PWSS to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | 54/PFMS | 22/06/2022 | 0 | RADIANT | 3.21 | 0 | 0 | 0
2313 | NADIA | Nadia Division | Augmentation of Ground Water Based Habibpur PWSS to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10420 | Augmentation | Material Requisition To Resource Division | 695/ND | 17/02/2023 | 0 | Resource Division | 69.17 | 0 | 0 | 0
2314 | NADIA | Nadia Division | Augmentation of Ground Water Based Habibpur PWSS to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10420 | Augmentation | Material Requisition To Resource Division | 1869/ND | 26/04/2023 | 0 | Resource Division | 28.48 | 0 | 0 | 0
2315 | NADIA | Nadia Division | Augmentation of Ground Water Based Habibpur PWSS to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10420 | Augmentation | Material Requisition To Resource Division | 3542/ND | 11/08/2023 | 0 | Resource Division | 105.14 | 0 | 0 | 0
2316 | NADIA | Nadia Division | Augmentation of Ground Water Based Habibpur PWSS to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10420 | Augmentation | Material Requisition To Resource Division | 2293/ND | 29/05/2023 | 0 | Resource Division | 21.56 | 0 | 0 | 0
2317 | NADIA | Nadia Division | Augmentation of Ground Water Based Habibpur PWSS to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. , SM/10420 | Augmentation | Providing Functional Household Tap Connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Habibpur to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. (PART-I) | 240/ND | 13/01/2023 | 812 | M/S DIPAK ENTERPRISE | 401.25 | 334.94 | 83.48 | 95
2318 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Continuation work order for Supply of 10 mm NB Gun-metal Ferrule conforming to IS:2692-1989 for Water Tap connection in each house hold from existing distribution system within scheme jurisdiction in different piped Water Supply Scheme within Nadia Arsenic Civil Division-II PHE Dte. at NACD-II office godown, Krishnagar, Nadia. | 477/NACD-II | 07/05/2021 | 10 | INDIA PIPE FITTING CO. | 4.73 | 9.46 | 200 | 100
2319 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Continuation work order for Supply of 10 mm NB Gun-metal Ferrule conforming to IS:2692-1989 for Water Tap connection in each house hold from existing distribution system within scheme jurisdiction in different piped Water Supply Scheme within Nadia Arsenic Civil Division-II PHE Dte. at NACD-II office godown, Krishnagar, Nadia. | 488/NACD-II | 13/05/2021 | 10 | INDIA PIPE FITTING CO. | 4.73 | 9.46 | 200 | 100
2320 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Supply and installation of Corona Guard (Brand- Eureka Forbes)(6 nos) and disinfection work at different office chambers at Nadia arsenic Civil Division-II, PHE Dte. Krishnagar, Nadia. | 312/NACD-II | 05/03/2021 | 5 | ABHISEK ENGINEERING CONCERN | 4.91 | 9.82 | 200 | 100
2321 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bagbaria W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 519/NACD-II | 14/06/2021 | 45 | M/S SHILL & CO. | 55.01 | 75.3 | 200 | 100
2322 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Work of Survery, Design, Drawing & DPR preparation for CHANDPUR Water Supply Scheme in KRISHNANAGAR-I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 3/AE-I/NACD-II | 06/05/2021 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.92 | 5.84 | 200 | 100
2323 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Work of Survey, Design, Drawing & DPR preparation for HELENCHI ZONE-III Water Supply Scheme in KRISHNAGANJ Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 5/AE-I/NACD-II | 06/05/2021 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 4.29 | 8.58 | 200 | 100
2324 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Work of Survey, Design, Drawing & DPR preparation for HELENCHI ZONE-II Water Supply Scheme in KRISHNAGANJ Block of Nadia Arsenic Civil Division-II, PHE Dte. | 6/AE-I/NACD-II | 06/05/2021 | 7 | UMWELT ENGINEER PVT LTD. | 3.15 | 6.3 | 200 | 100
2325 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Work of Survey, Design, Drawing & DPR preparation for BAHIRGACHHI ZONE-II Water Supply Scheme in CHAPRA Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 1/AE-I/NACD-II | 06/05/2021 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.66 | 5.31 | 200 | 100
2326 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Work of Survey, Design, Drawing & DPR preparation for BANSBERIA Water Supply Scheme in KRISHNANAGAR-I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 2/AE-I/NACD-II | 06/05/2021 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.94 | 5.87 | 200 | 100
2327 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 767/NACD-II | 22/09/2021 | 45 | JOY HIND TUBEWELLS | 94.04 | 188.28 | 200 | 100
2328 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Providing Functional House Hold Tap Connection (Phase-II) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Helenchi Zone-III ( Village- Bhajanghat) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 16/AE-II/NACD-II | 13/08/2021 | 15 | SUMIT GHOSH | 4.96 | 9.9 | 200 | 100
2329 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Special repairing works of damaged old pipe line at Brittihuda including anciliary FHTC works at Arangsarisa of Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, | 136/AE-I/NACD-II | 28/10/2021 | 15 | JOY HIND TUBEWELLS | 5 | 10 | 200 | 100
2330 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and also Bamboo Pilling at Baranaldaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 737/NACD-II | 13/09/2021 | 45 | M/S ANUBHAB CONSTRUCTION | 62.35 | 124.69 | 200 | 100
2331 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Refixing of existing ferrule connection broken due to heavy vehicular traffic including road restoration work at Madhabpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-Il P.H.E. Dte. | 15/AE-II/NACD-II | 13/08/2021 | 10 | JOY HIND TUBEWELLS | 3.43 | 6.85 | 200 | 100
2332 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Continuation Work Order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Digri (Vill- Digri) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 687/NACD-II | 03/09/2021 | 10 | M/S RAJESH CONSTRUCTION | 4.99 | 9.97 | 200 | 100
2333 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr,Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Barnia (Vill- Avaynagar) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 130/AE-I/NACD-II | 14/09/2021 | 15 | M/S FREEDOM CONSTRUCTION | 4.5 | 8.99 | 200 | 100
2334 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Repair and Renovation work at Tengra 2nd tube well Site under Tengra Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia | 1025/AE-I/NACD-II | 10/12/2024 | 30 | SHOVON KUMAR MODAK | 4.05 | 0 | 0 | 0
2335 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Tengra Water Supply Scheme in CHAPRA Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 320_1/AE-I/NACD-II | 13/07/2023 | 7 | RISHAN ENGINEERING CONSULTANCY | 0.86 | 0.47 | 100 | 100
2336 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Conversion of IEP to AIRP at Tengra Water Supply Scheme of capacity 36Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte. | 1360/NACD-II | 30/09/2024 | 60 | SUMIT GHOSH | 165.15 | 0 | 0 | 0
2337 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09261 | Augmentation | Laying of 75mm dia pipeline alongwith FHTC reconnection Tengra W/S Scheme at Chapra block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1204/AE-I/NACD-II | 27/02/2025 | 45 | ASHIM ENTERPRISE | 0.96 | 0 | 0 | 0
2338 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Construction of Boundary wall with Grill Gate at Brittihuda 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | 241/AE-I/NACD-II | 17/02/2022 | 30 | TAPAS GHOSH | 3.41 | 3.36 | 98.58 | 100
2339 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Construction of Boundary wall with Grill Gate at Brittihuda 3rd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | 242/AE-I/NACD-II | 17/02/2022 | 30 | SURAJIT KUMAR GHOSH | 3.41 | 3.37 | 98.83 | 100
2340 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Construction of Boundary wall with Grill Gate at Brittihuda 4th site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | 243/AE-I/NACD-II | 17/02/2022 | 30 | CHINMOY BISWAS | 3.41 | 3.39 | 99.39 | 100
2341 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Construction of Boundary wall with Grill Gate at Brittihuda 5th site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | 244/AE-I/NACD-II | 17/02/2022 | 30 | M/S RAJESH CONSTRUCTION | 4.05 | 3.99 | 98.42 | 100
2342 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Baliadanga W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 124/NACD-II | 21/02/2022 | 90 | SINGHA ROY & CO. | 138.93 | 0 | 0 | 100
2343 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 127/NACD-II | 21/02/2022 | 90 | MALLICK ENTERPRISE | 159.32 | 159.1 | 100 | 100
2344 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-I, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal.(From-01/03/2022 to 28/02/2023) | 276//AE-I/NACD-II | 25/02/2022 | 12 | BABLU KUMAR SINGH | 4.98 | 2.32 | 46.63 | 100
2345 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Functional House Hold Tap Connection for providing connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Remaining School only) Brittihuda W/s Scheme at Chapra Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 296/NACD-II | 09/03/2023 | 20 | BISWANATH DAS | 2.05 | 0 | 0 | 85
2346 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Brittihuda PWSS in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte | 520/AE-I/NACD-II | 18/12/2023 | 7 | MAKALI ENGINEERING CORPORATION | 0.58 | 0 | 0 | 0
2347 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Continuation Work Order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 224/NACD-II | 05/04/2022 | 90 | MALLICK ENTERPRISE | 154.65 | 154.65 | 100 | 100
2348 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal.(From 01/03/2022 to 28/02/2023) | 55//AE-II/NACD-II | 17/02/2022 | 365 | SAJAL SAHA | 4.98 | 0.72 | 100 | 100
2349 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-I, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal.(From-01/03/2023 to 31/03/2023) | 253/NACD-II | 27/02/2023 | 31 | BABLU KUMAR SINGH | 0.42 | 0.38 | 100 | 100
2350 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Route survey engaging qualified surveyors with modern instruments viz-GPS, Total station, DGPS, Auto levels etc over the command area of Brittihuda Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Brittihuda W/S Scheme in chapra Block of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 550/NACD_II | 11/05/2023 | 20 | MALLICK ENTERPRISE | 10.11 | 10.11 | 100 | 100
2351 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Material Requisition To Resource Division | 373/NACD-II | 24/03/2023 | 0 | Resource Division | 12.32 | 0 | 0 | 0
2352 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BRITTIHUDA (Block- Chapra), BARNIA (Block- Tehatt II ), MAHATPUR (Block- Chapra ), MATIARY (Block- Krishnaganj), BAGAKHALI (Z-I) (Block- Tehatta I ), BARA NALDAH (Block- Tehatta II ) W/S Scheme, , Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 01) | 1120/EMD | 16/03/2023 | 30 | B.T. PROJECTS PVT. LTD | 91.82 | 17.39 | 82.08 | 60
2353 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Brittihuda Piped Water Supply Scheme under Nadia Arsenic Civil Division-II,P.H.E Dte. | 468/NACD-II | 20/04/2023 | 30 | M/S GHOSH CONSTRUCTION | 29.12 | 24.73 | 84.92 | 85
2354 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Gongra Water Supply Scheme of capacity 58 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | 176/NACD-II | 07/02/2024 | 60 | ACQUA CONSTRUCTION CONSORTIUM | 177.79 | 0 | 0 | 0
2355 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Repair and Renovation work at Brittihuda 5th tube well Site under Brittihuda Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | 1023/AE-I/NACD-II | 10/12/2024 | 30 | PRADUT GHOSH | 4.11 | 0 | 0 | 0
2356 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Balance Laying of a dedicated UPVC pipeline for supplying drinking water from newly constructed manifold at Head Works site towards Arangsarisha, Deulia Village of Brittihuda W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1414/NACD-II | 14/12/2023 | 90 | M/S GHOSH CONSTRUCTION | 151.57 | 150.12 | 100 | 100
2357 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-I, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, Pincode:- 741101,West Bengal. (From 01/07/2024 to 30/06/2025) | 792/AE-I/NACD-II | 01/07/2024 | 365 | BABLU KUMAR SINGH | 4.98 | 3.18 | 63.93 | 0
2358 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Supply of Water Level Indicator at Brittihuda,Mahatpur,Bahirgachhi Zone-1,Bahirgachhi Zone-II,Bagberia,Betberia PWSS in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 1191/AE-I/NACD-II | 25/02/2025 | 45 | MAYA ENTERPRISE | 4.58 | 0 | 0 | 0
2359 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Conversion of IEP to AIRP at Tengra Water Supply Scheme of capacity 36Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte. | 1360/NACD-II | 30/09/2024 | 60 | SUMIT GHOSH | 165.15 | 0 | 0 | 0
2360 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Construction of 50 m3/hr capacity Iron Elimination Plant at Mouza-Pitambarpur under habitation Mallickpara under Brittihuda Public Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 131/NACD-II | 29/01/2025 | 59 | MALLICK ENTERPRISE | 23.07 | 0 | 0 | 0
2361 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Brittihuda Water Supply Scheme of capacity 220 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | 235/NACD-II | 21/02/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 446.92 | 393.29 | 88 | 90
2362 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Construction of pumphouse with sanitary and water supply arrangement at Pitambarpur mouza in Brittihuda Piped water supply scheme in Chapra Block under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 1617/NACD-II | 18/12/2024 | 30 | M/S ARATI ENTERPRISE | 6.19 | 0 | 0 | 0
2363 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Repair and Renovation work at Brittihuda 2nd tube well Site under Brittihuda Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | 902/AE-I/NACD-II | 10/09/2024 | 210 | NISHITH BANERJEE | 4.2 | 0 | 0 | 100
2364 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Laying of Distribution Pipeline along with Parallal Line along with FHTC reconnection and leftout FHTC at Brittihuda W/s Scheme at Chapra block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1568/NACD-II | 06/12/2024 | 270 | SANJIB DEY | 101.89 | 0 | 0 | 45
2365 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Road Reastoration work along Charatala Uttar Para of Brittihuda Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | 18/AE-I/NACD-II | 11/04/2025 | 30 | SUMIT GHOSH | 4.8 | 0 | 0 | 100
2366 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC under Brittihuda (Source Augmentation, Pritambarpur) ground water based water supply scheme under Block_ Chapra Dist. - Nadia under EMD, PHE Dte. | 702/EMD | 04/04/2025 | 30 | M/S. G.P. ENTERPRISE | 11.6 | 0 | 0 | 0
2367 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Laying of distribution system including providing FHTC at left out households for Bahadurpur, Khaspu, Dhopahat and Rajapur W/s Scheme and restoration of the damaged portion of roads in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte and Brittihuda W/S Scheme & Barnia W/S Scheme included. | 736/NACD-II | 18/06/2025 | 90 | JOY HIND TUBEWELLS | 186.42 | 0 | 0 | 40
2368 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Road Reastoration work along Brittihuda Ghosh Para of Brittihuda Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | 115/AE-I/NACD-II | 04/06/2025 | 30 | SUMIT GHOSH | 4.78 | 0 | 0 | 0
2369 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Construction of pumphouse cum Chlorine room with sanitary and water supply arrangement at Gokhrapota mouza in Brittihuda Piped water supply scheme in Chapra Block under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 344/NACD-II | 13/03/2025 | 30 | SOMNATH GHOSH | 6.22 | 0 | 0 | 65
2370 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 900 cum for providing FHTC (Functional Household Tap Connection) for Brittihuda Water Supply Scheme in Chapra Block in Nadia District under Nadia Arsenic Civil Division- II, PHE Dte. | 939/NACD-II | 28/07/2025 | 90 | M/S.K.P.CONSTRUCTION | 29.21 | 0 | 0 | 0
2371 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Construction of 50 m3/hr capacity Iron Elimination Plant Mouza-Pitambarpur under habitation Balirmathpara under Brittihuda Public Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 1173/NACD-II | 09/09/2025 | 61 | SANJIB DEY | 23.07 | 0 | 0 | 0
2372 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10094 | Augmentation | Supply of flow control devices in the closed water conduit at Brittihuda PWSS in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 224/AE-I/NACD-II | 01/09/2025 | 20 | MAKALI ENGINEERING CORPORATION | 4.57 | 0 | 0 | 100
2373 | NADIA | Eastern Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/18661 | Augmentation | Implementation of SCADA system at Intake, WTP and OHR sites of surface based water supply scheme for Chakdah (Part) in the district of Nadia. | 6193/EMD | 05/10/2023 | 183 | G.B. CONSTRUCTION | 615.17 | 0 | 0 | 0
2374 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/18661 | Augmentation | Preparation of Detailed Project Report (DPR) for Augmentation of Surface Water Based PWSS for Chakdah (Part) Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.01) | 1829/NAD-I | 07/08/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 74.61 | 74.61 | 100 | 100
2375 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/18661 | Augmentation | Material Requisition To Resource Division | 1884/NAD-I | 11/08/2023 | 0 | Resource Division | 3612.51 | 0 | 0 | 0
2376 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/18661 | Augmentation | Construction of pathway and allied works for WTP Chakdah in connection with Augmentation of Chakdah WTP under JJM within Chakdah Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) | 1709/NAD-I | 21/10/2024 | 21 | MALI CONSTRUCTION | 39.68 | 0 | 0 | 0
2377 | NADIA | Eastern Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/18661 | Augmentation | Supply, delivery & installation of Rotary Assembly for Horizontal split case pump at Chakdah WTP, Pump No.-V, under Eastern Mechanical Division, P.H.E. Dte. | 6399/EMD | 30/10/2023 | 90 | ORIENTAL ENGINEERING CO. | 9.85 | 9.85 | 100 | 100
2378 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/18661 | Augmentation | Restoration of damages pipelines at PWD Bridge at Raninagar village in Balagorichar (Zone-XII) under augmentation of surface water based PWSS for Chakdah Part at Chakdah Block under Nadia Arsenic Division-I, PHE Dte. | 143/AE-II/NAD-I | 07/06/2024 | 330 | MESSRS FREEDOM CONSTRUCTION | 4.05 | 3.75 | 100 | 100
2379 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/18661 | Augmentation | Material Requisition To Resource Division | 1952/NAD-I | 28/11/2024 | 0 | Resource Division | 38.55 | 0 | 0 | 0
2380 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/18661 | Augmentation | Augmentation of Water Treatment Plant, Intake & Rising Main for Surface Water Based Piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR including Soil Test, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 29 Nos. distribution zone for Chakdah (Part) in Chakdah Block of Nadia District under Nadia Arsenic Division-I, PHE Dte (Sl.no 01) | 2110/NAD-I | 01/09/2023 | 547 | GBC INFRASTRUCTURE PRIVATE LIMITED | 8630 | 1017.68 | 11.79 | 10
2381 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/18661 | Augmentation | Continuation work order of Casual hiring of vehicle on an as and when required basis for Jal-Jeevan Mission site inspection under Nadia arsenic Division-I, PHE Dte. | 500/AE-II/NAD-I | 28/03/2025 | 184 | BUDDHADEV MONDAL | 0.86 | 0 | 0 | 0
2382 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division , SM/10079 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division | 638/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.23 | 0 | 0 | 0
2383 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division , SM/10079 | Augmentation | Material Requisition To Resource Division | 2163/ND | 18/05/2022 | 0 | Resource Division | 76.79 | 0 | 0 | 0
2384 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division , SM/10079 | Augmentation | Material Requisition To Resource Division | 3235/ND | 21/07/2022 | 0 | Resource Division | 1.26 | 0 | 0 | 0
2385 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division , SM/10079 | Augmentation | Material Requisition To Resource Division | 3304/ND | 27/07/2022 | 0 | Resource Division | 10.78 | 0 | 0 | 0
2386 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division , SM/10079 | Augmentation | Material Requisition To Resource Division | 2302/ND | 29/05/2023 | 0 | Resource Division | 6.23 | 0 | 0 | 0
2387 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division , SM/10079 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 58 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Bhanderkhola PWSS under Nadia Division PHE Dte. | 2997/ND | 13/07/2023 | 90 | TARUN KUMAR BHATTACHARYA | 87.75 | 44.39 | 92.77 | 68
2388 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division , SM/10079 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Bhanderkhola to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 2079/ND | 11/05/2022 | 90 | M/S GHOSH CONSTRUCTION | 180.3 | 176.2 | 100 | 100
2389 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division , SM/10079 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 250 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Bhanderkhola Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 5126/ND | 17/11/2023 | 90 | ONKAR ENTERPRISE | 24.91 | 0 | 0 | 100
2390 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division , SM/10079 | Augmentation | Providig FHTC at leftout household in connection to the Augmentation of Ground Based piped water supply scheme at Bhanderkhola to accommodate FHTC within Krishnagar I block under Krishnanagar Sub-Division under Nadia Division, PHE Dte. | 1371/ND | 28/02/2024 | 60 | M/S GHOSH CONSTRUCTION | 32.47 | 25.99 | 100 | 100
2391 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division , SM/10079 | Augmentation | Construction and installation of Manifold at OHR site and allied works in connection to the Augmentation of Bhanderkhola Water Supply Scheme under Krishnagar I Block under Nadia Division, P.H.E Dte. | 494/ND | 30/01/2025 | 240 | SANJIB DEY | 27.42 | 0 | 0 | 80
2392 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11835 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 8B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 131/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.1 | 3.05 | 100 | 100
2393 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11835 | Augmentation | Material Requisition To Resource Division | 114/ND | 05/01/2023 | 0 | Resource Division | 106.06 | 0 | 0 | 0
2394 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11835 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 169.25 | 57.61 | 47
2395 | NADIA | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District , SM/08129 | Retrofitting | PROVIDING 300MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KISHOREPUR W/S (REPLACEMENT TW-HW), KARIMPUR II BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | 283/CMSD-II (D) | 01/06/2022 | 15 | DEV ENTERPRISE | 4.39 | 0 | 0 | 0
2396 | NADIA | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District , SM/08129 | Retrofitting | PROVIDING 200MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT UTTAR TAJPUR W/S SCHEME (REPLACEMENT TW-II), KARIMPUR-I BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | 286/CMSD-II (D) | 01/06/2022 | 15 | DEV ENTERPRISE | 4.44 | 0 | 0 | 0
2397 | NADIA | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District , SM/08129 | Retrofitting | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER BASED & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT FAZILNAGAR W/S (REPLACEMENT TW-II) IN KARIMPUR-II BLOCK UNDER NADIA DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 277/CMSD-II (D) | 01/06/2022 | 15 | DEV ENTERPRISE | 2.07 | 0 | 0 | 0
2398 | NADIA | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District , SM/08129 | Retrofitting | PROVIDING DRILLING CREWS & OTHER MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR UTTAR TAJPUR W/S SCHEME (REPLACEMENT TW-II), KARIMPUR-I BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | 284/CMSD-II (D) | 01/06/2022 | 15 | DEV ENTERPRISE | 3.52 | 0 | 0 | 0
2399 | NADIA | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District , SM/08129 | Retrofitting | PROVIDING 200MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT UTTAR TAJPUR W/S SCHEME (REPLACEMENT TW-II), KARIMPUR-I BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | 286/CMSD-II(D) | 01/06/2022 | 15 | DEY ENTERPRISE | 4.44 | 1.1 | 100 | 0
2400 | NADIA | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District , SM/08129 | Retrofitting | PROVIDING 300 MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KISHOREPUR W/S (REPLACEMENT TW-HW), KARIMPUR -II BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | 283/CMSD-II(D) | 01/06/2022 | 15 | DEY ENTERPRISE | 4.39 | 3.94 | 100 | 0
2401 | NADIA | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District , SM/08129 | Retrofitting | PROVIDING DRILLING CREWS & OTHER MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR UTTAR TAJPUR W/S SCHEME (REPLACEMENT TW-II), KARIMPUR-I BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | 284/CMSD-II(D) | 01/06/2022 | 15 | DEY ENTERPRISE | 3.52 | 3.52 | 100 | 0
2402 | NADIA | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District , SM/08129 | Retrofitting | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT FAZILNAGAR W/S (REPLACEMENT TW-II) IN KARIMPUR--II BLOCK UNDER NADIA DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 277/CMSD-II(D) | 01/06/2022 | 15 | DEY ENTERPRISE | 2.07 | 1.63 | 100 | 0
2403 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District , SM/08129 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Fazilnagar W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | 2155/ND | 21/05/2021 | 60 | A.P. POWER & CONCRETE | 42.43 | 32.04 | 100 | 100
2404 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District , SM/08129 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Fazilnagar W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | 2930/ND | 26/07/2021 | 45 | TULIP ENGINEER'S CO-OP SOCIETY LTD | 7.58 | 6.37 | 100 | 0
2405 | NADIA | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District , SM/08129 | Retrofitting | MISCELLANEOUS REPAIRING OF KORES/DR/1000 (MP09GF2033) AND SUPPORT TRUCK (WMK4719) UNDER CMSD-II (D), CDD, PHE DTE. | 161/CMSD-II (D) | 07/07/2021 | 15 | CHAKRABORTY MINING & ENGINEERING | 0.75 | 0.75 | 100 | 0
2406 | NADIA | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District , SM/08129 | Retrofitting | REPAIRING OF MUD PUMP FLUID CHAMBER, TRANSMISSION LINE AND OTHERS WORKS ALONG WITH SUPPLY OF DRILLING ACCESSORYU OF RIG MACHINE- JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. | 72/CMSD-I | 30/03/2022 | 15 | PADMA ENGINEERING & CO. | 4 | 0.83 | 100 | 0
2407 | NADIA | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District , SM/08129 | Retrofitting | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | 1724/CDD | 29/12/2022 | 30 | DEY ENTERPRISE | 13.83 | 0.23 | 100 | 0
2408 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District , SM/08129 | Retrofitting | Material Requisition To Resource Division | 1016/ND | 03/03/2022 | 0 | Resource Division | 15.9 | 0 | 0 | 0
2409 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District , SM/08129 | Retrofitting | Material Requisition To Resource Division | 3302/ND | 27/07/2022 | 0 | Resource Division | 17.79 | 0 | 0 | 0
2410 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District , SM/08129 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Fazilnagar W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte."(PART- B) | 2156/ND | 21/05/2021 | 60 | IJABUL SK. | 42.68 | 61.87 | 144.94 | 100
2411 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIA, (Darappur), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdaha (Part) Water Supply Scheme , SM/08001 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIA, Darappur, at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 771/NAD-I | 04/05/2021 | 60 | M/S DIPAK ENTERPRISE | 96.96 | 191.19 | 100 | 100
2412 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Birnagar Part-II, at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Birnagar Water Supply Scheme , SM/08018 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Birnagar, Part-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Birnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 766/NAD-I | 04/05/2021 | 60 | CALCON CONSTRUCTION | 63.98 | 78.39 | 61.37 | 100
2413 | NADIA | Nadia Division | Providing Functional House Tap Connection from Baruipara Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08133 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Baruipara W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retrofitting) | 2876/ND | 20/07/2021 | 90 | CHAKRABORTTI ENTERPRISE | 93.37 | 133.35 | 142.83 | 0
2414 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIII, (BARBERIA), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme , SM/07900 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jalswapna for Zone-VIII, (Barberia), Part-I at Chakdah Block by retrofitting of Surface Water Based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) | 312/NAD-I | 08/02/2021 | 90 | MONDAL PRECESION PVT. LTD. | 95.18 | 125.29 | 65.96 | 100
2415 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Banpur Water Scheme (for Banpur & Fulbari Mouzas) under Jal Swapno Programme , SM/07470 | Retrofitting | onal Household Tap Connection from Banpur Water Scheme (for Banpur & Fulbari Mouzas) under Jal Swapno Programme |  | 13/04/2021 | 0 | SUMAN CHAKRABORTY | 15.79 | 0 | 0 | 0
2416 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Banpur Water Scheme (for Banpur & Fulbari Mouzas) under Jal Swapno Programme , SM/07470 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN- METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC. ALL COMPLETE AT BANPUR W/S SCHEME PART-A, UNDER NADIA DIVISION, PHE , DTE. | 75/PPMS | 15/07/2021 | 0 | PALCON | 17.37 | 0 | 0 | 0
2417 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Banpur Water Scheme (for Banpur & Fulbari Mouzas) under Jal Swapno Programme , SM/07470 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN- METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC. ALL COMPLETE AT BANPUR W/S SCHEME PART-B, UNDER NADIA DIVISION, PHE , DTE. | 77/PPMS | 15/07/2021 | 0 | SUMAN CHAKRABORTY | 15.79 | 0 | 0 | 0
2418 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Banpur Water Scheme (for Banpur & Fulbari Mouzas) under Jal Swapno Programme , SM/07470 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Banpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.PART-C | 505/ND | 27/01/2021 | 45 | SUMAN CHAKRABORTY | 35.26 | 62.05 | 175.97 | 0
2419 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Banpur Water Scheme (for Banpur & Fulbari Mouzas) under Jal Swapno Programme , SM/07470 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Banpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.PART-A | 503/ND | 27/01/2021 | 45 | PALCON | 23.44 | 0 | 0 | 0
2420 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Banpur Water Scheme (for Banpur & Fulbari Mouzas) under Jal Swapno Programme , SM/07470 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Banpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.PART-B | 504/ND | 27/01/2021 | 45 | SUMAN CHAKRABORTY | 35.26 | 13.59 | 100 | 0
2421 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme , SM/07471 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT GAZNA W/S SCHEME | 460/DW | 30/03/2021 | 0 | SANJOY BAKSHI | 12.7 | 0 | 0 | 0
2422 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme , SM/07471 | Retrofitting | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme |  | 24/03/2021 | 0 | APURBA MANDAL | 34.69 | 0 | 0 | 0
2423 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme , SM/07471 | Retrofitting | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme. |  | 24/03/2021 | 0 | APURBA MANDAL | 34.35 | 0 | 0 | 0
2424 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme , SM/07471 | Retrofitting | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme | 515/PFMS | 03/02/2022 | 0 | APURBA MANDAL | 3.12 | 0 | 0 | 0
2425 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme , SM/07471 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Gazna W/S scheme in Nadia District under Nadia Division P.H.E. Dte.PART-C | 508/ND | 27/01/2021 | 45 | APURBA MANDAL | 37.85 | 71.79 | 189.68 | 100
2426 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme , SM/07471 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Gazna W/S scheme in Nadia District under Nadia Division P.H.E. Dte.PART-A | 506/ND | 27/01/2021 | 45 | SANJOY BAKSHI | 13.11 | 0 | 0 | 0
2427 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme , SM/07471 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Gazna W/S scheme in Nadia District under Nadia Division P.H.E. Dte.PART-B | 507/ND | 27/01/2021 | 45 | APURBA MANDAL | 37.85 | 69.39 | 183.33 | 100
2428 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme , SM/07471 | Retrofitting | Replacemt of damaged & typically choked UPVC pipe line for augmentation of Ground Water Based Water Supply Scheme for Gazna PWSS of Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. (Balance) A- Part. | 4802/ND | 17/10/2023 | 90 | SANDIP BISWAS | 99.5 | 0 | 0 | 96
2429 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of PATHARGHATA water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07298 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Patharghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 06/NACD-II | 05/01/2021 | 60 | APURBA MANDAL | 47.69 | 94.39 | 197.91 | 0
2430 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-I within Kaliganj Block (Phase-B). , SM/06997 | Retrofitting | Additional work for extension of pipe line at Hutguchha, basorkhola & Kaliganj for Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Kaliganj Block (Phase-c). | 562/DW | 25/02/2022 | 0 | M/S NIBHAS SINHA | 4.65 | 0 | 0 | 0
2431 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-I within Kaliganj Block (Phase-B). , SM/06997 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme(Northern Sector),Part-I,Zone-I Within Kaliganj Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte. | 4080/ND | 31/12/2020 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 97.03 | 173.99 | 179.32 | 0
2432 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-I within Kaliganj Block (Phase-B). , SM/06997 | Retrofitting | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Executive Engineer, Nadia Division, PHE Dte. | 286/Kly SD-I | 31/03/2022 | 365 | ARROWTOWN DEALERS PVT. LTD | 4.8 | 1.49 | 78.84 | 0
2433 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-I within Kaliganj Block (Phase-B). , SM/06997 | Retrofitting | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 01-03-2021 to 28-02-2022 (250 working days) | 172/RSD | 22/02/2021 | 365 | SUMAN CHAKRABORTY | 3.85 | 1.02 | 100 | 0
2434 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-IV within Kaliganj Block (Phase-A). , SM/06998 | Retrofitting | PREPERATION OF DETAILS PROJECT FOR FHTC AT SURFACE WATER BASED W/S SCHEME ( N.SECTOR) , PART-II, ZONE-I, PHASE-A & B UNDER , NADIA DIVISION , PHE ,DTE | 139/FHTC | 17/08/2021 | 0 | LEMNISCATE | 0.44 | 0 | 0 | 0
2435 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-IV within Kaliganj Block (Phase-A). , SM/06998 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme(Northern Sector),Part-I,Zone-IV within Kaliganj Block(Phase-A) in Nadia District under Nadia Division,P.H.E.Dte. | 4082/ND | 31/12/2020 | 90 | UMWELT ENGINEERS PVT LTD | 96.95 | 185.04 | 190.86 | 0
2436 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-A). , SM/06999 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT NORTHERN SECTORPART-1 Z-3 | 447/DW | 25/03/2021 | 0 | M/S S & P CONSTRUCTION | 18.28 | 0 | 0 | 0
2437 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-A). , SM/06999 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme(northern sector),Part-I,Zone-III within Kaliganj block(Phase-A) in Nadia District under Nadia Division P.H.Engineering Dte. | 3590/ND | 08/12/2020 | 90 | M/S S & P CONSTRUCTION | 97.06 | 144.5 | 148.88 | 0
2438 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-A). , SM/06999 | Retrofitting | Continuation of Hiring Diesel cab having contract permit from regional transport authority for the office use of the Assistant Engineer, Kalyani Sub-Division-1, Nadia Division PHE Dte at D.C Building, Kalyani, Nadia w.e.f 01/10/2021 to 31/03/2022 (6 months)) | 441/Kly SD-I | 30/09/2021 | 182 | SATYABRATA CHAKRABORTY | 2.4 | 0.54 | 22.35 | 0
2439 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-A). , SM/06999 | Retrofitting | Hiring Diesel Maxi Cub having car No WB-51/B-3194 for office of the Assistant Engineer, RWS Nadia Sub-Division, PHE Dte. for the period from 01.08.2021 to 31.07.2022 | 896/PH | 30/07/2021 | 365 | TARUN KUMAR BHATTACHARYA | 4.8 | 0.51 | 100 | 100
2440 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Sakdaha water supply scheme under Krishnaganj Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07833 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Sakdaha (Bazarpara) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1056/NACD-II | 25/09/2020 | 15 | M/S. ASIT KUMAR BISWAS | 4.98 | 0 | 0 | 0
2441 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna Programme covering Mashunda Village by retrofitting of Paschim Noapara Water Supply Scheme under Ranaghat-I Block under Nadia District under Nadia Arsenic Division-I, PHE Dte , SM/08854 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Masunda village at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1419/NAD-I | 08/11/2021 | 60 | PRIYA CONSTRUCTION | 77.38 | 75.9 | 100 | 100
2442 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna Programme covering Mashunda Village by retrofitting of Paschim Noapara Water Supply Scheme under Ranaghat-I Block under Nadia District under Nadia Arsenic Division-I, PHE Dte , SM/08854 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Paschim Noapara at Ranaghat-I Block by augmentation of Ground Water Based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte . (Sl.no.12) | 2409/NAD-I | 10/10/2023 | 30 | JOYGOPAL GUPTI | 86.45 | 86.09 | 100 | 100
2443 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dubli Zone-I, at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dubli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08856 | Retrofitting | Providing Functioanal Household Tap Connection (FHTC) under Jaldhara/Jal Swapna for Dubli, Zone-I at Ranaghat-II Block by retrofitting of GRound Water based PWSS for Dubli, Zone-I Water Supply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | 1587/NAD-I | 22/12/2021 | 90 | SUPRITI ENTERPRISE | 205.54 | 193.94 | 100 | 100
2444 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dubli Zone-I, at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dubli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08856 | Retrofitting | Construction of Boundary wall and pathway Head work site of Duttaphulia Zone- II and Dubli Zone- I water supply Scheme in Ranaghat-II Block in connection with Duttaphulia Zone-I W/S Scheme under JJM under Nadia Arsenic Division-I,P.H.E. Dte. (sl.02) | 137/NAD-I | 23/04/2025 | 60 | CFS MANAGEMENT PRIVATE LIMITED | 38.99 | 0 | 0 | 0
2445 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dubli Zone-II, at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dubli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08858 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dubli, Zone-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dubli Zone-II Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1435/NAD-I | 09/11/2021 | 90 | MONDAL ENTERPRISE | 147.05 | 146.55 | 100 | 100
2446 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dubli Zone-II, at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dubli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08858 | Retrofitting | Material Requisition To Resource Division | 145/NAD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0 | 0
2447 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09042 | Retrofitting | Continuation work order for Engagement of 01 no of Bacteriologist /Analyst for operation and maintenance of Bacteriological testing unit of Nadia Divisional Laboratory Under Kalyani SD-1, P.H.Engineering Dte WEF: 01/09/2023 to 30/11/2023 (Three months) | 901/KlySD-I | 25/08/2023 | 92 | GOUTAM DAM | 0.5 | 0.17 | 33.33 | 100
2448 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09042 | Retrofitting | Continuation work order for Engagement of 01 no of Chemist /Analyst for operation and maintenance of physico-Chemical testing unit of Nadia Divisional Laboratory at W.T.P, Haringhata Under Kalyani SD-1, PHE Dte in the district of Nadia. WEF:01/09/2023 to 30/11/2023 (Three months) | 900/KLYSD-I | 25/08/2023 | 92 | JOYDEV JANA | 0.5 | 0.17 | 33.33 | 100
2449 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09042 | Retrofitting | Continuation work order for Engagement of 01 no of Sampling assistant for operation and maintenance of physic-chemical testing unit and bacteriological testing unit of Nadia Water Testing Laboratory under PHE Dte. WEF: 01/09/2023 to 30/11/2023 (Three months) | 902/KLYSD-I | 28/08/2023 | 92 | SUCHITRA GHOSH | 0.23 | 0.08 | 33.33 | 100
2450 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09042 | Retrofitting | laying of distribution pipe line180mm dia UPVC pipe etc. for Providing functional household tap connection at Naserkuli zone- I W/S scheme under Nadia Division P.H.E. Dte. | 1464/PH | 03/03/2022 | 10 | SAIKAT GHOSH | 1.26 | 1.26 | 100 | 100
2451 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09042 | Retrofitting | Engagement of 01 no of Chemist cum Operator of Atomic Absorption Spectrophotometer (AAS) at Nadia District Water Testing Laboratory under Nadia Division, P.H.E Dte WEF: 01/01/2023 to 31/03/2023 (Three months). | 1231/Kly SD-I | 30/12/2022 | 90 | M/S S.K. ENTERPRISE | 0.8 | 0.27 | 100 | 0
2452 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09042 | Retrofitting | Continuation work order for Engagement of 01 no of Sampling assistant for operation and maintenance of physic-chemical testing unit and bacteriological testing unit of Nadia Water Testing Laboratory under PHE Dte. WEF: 01/06/2023 to 31/08/2023 (Three months) | 658/KLYSD-I | 24/05/2023 | 92 | SUCHITRA GHOSH | 0.23 | 0.08 | 100 | 70
2453 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09042 | Retrofitting | Continuation work order for Engagement of 01 no of Chemist /Analyst for operation and maintenance of physico-Chemical testing unit of Nadia Divisional Laboratory at W.T.P, Haringhata Under Kalyani SD-1, PHE Dte in the district of Nadia. WEF: 01/06/2023 to 31/08/2023 (Three months) | 656/KLYSD-I | 24/05/2023 | 92 | JOYDEV JANA | 0.5 | 0.17 | 100 | 70
2454 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09042 | Retrofitting | Continuation work order for Engagement of 01 no of Chemist cum Operator of Atomic Absorption Spectrophotometer (AAS) at Nadia District Water Testing Laboratory under Nadia Division, P.H.E Dte WEF: 01/07/2023 to 30/09/2023 (Three months). | 710/KlySD-I | 19/06/2023 | 92 | M/S S.K. ENTERPRISE | 0.8 | 0.8 | 100 | 100
2455 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09042 | Retrofitting | Continuation work order for Engagement of 01 no of Bacteriologist /Analyst for operation and maintenance of Bacteriological testing unit of Nadia Divisional Laboratory Under Kalyani SD-1, P.H.Engineering Dte WEF: 01/06/2023 to 31/08/2023 (Three months) | 657/KlySD-I | 24/05/2023 | 92 | GOUTAM DAM | 0.5 | 0.17 | 100 | 70
2456 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09042 | Retrofitting | Material Requisition To Resource Division | 802/ND | 18/02/2022 | 0 | Resource Division | 2.2 | 0 | 0 | 0
2457 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09042 | Retrofitting | PAYMENT FOR NGO LAB | 281/PFMS | 19/09/2023 | 0 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.4 | 0 | 0 | 0
2458 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09042 | Retrofitting | PAYMENT FOR NGO LAB. | 280/PFMS | 19/09/2023 | 0 | BINAY BADAL DINESH CLUB | 0.4 | 0 | 0 | 0
2459 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09042 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 5.42 | 100 | 81
2460 | NADIA | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09042 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Kamalpur Z-II Water Supply scheme Ranaghat-II block in Nadia District under Nadia Division P.H.E. Dte. | 5701/ND | 03/11/2021 | 1123 | PRIYA CONSTRUCTION | 63.6 | 49.83 | 88.04 | 100
2461 | NADIA | Nadia Division | Providing Functional House Tap Connection from NutangramWater Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09043 | Retrofitting | Providing Functional House Tap Connection from NutangramWater Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | 606/PFMS | 11/03/2022 | 0 | OTHERS | 2.04 | 0 | 0 | 0
2462 | NADIA | Nadia Division | Providing Functional House Tap Connection from NutangramWater Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09043 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 mtr , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Nutungram Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.E. Dte. | 5700/ND | 03/11/2021 | 60 | A.P. POWER & CONCRETE | 46.05 | 45.83 | 99.53 | 0
2463 | NADIA | Nadia Division | Providing Functional House Tap Connection from NutangramWater Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09043 | Retrofitting | Material Requisition To Resource Division | 102/ND | 06/01/2022 | 0 | Resource Division | 6.62 | 0 | 0 | 0
2464 | NADIA | Nadia Division | Providing Functional House Tap Connection from NutangramWater Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09043 | Retrofitting | Material Requisition To Resource Division | 1059/ND | 04/03/2022 | 0 | Resource Division | 8.22 | 0 | 0 | 0
2465 | NADIA | Nadia Division | Providing Functional House Tap Connection from NutangramWater Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09043 | Retrofitting | Material Requisition To Resource Division | 438/ND | 31/01/2022 | 0 | Resource Division | 0.62 | 0 | 0 | 0
2466 | NADIA | Nadia Division | Providing Functional House Tap Connection from NutangramWater Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09043 | Retrofitting | Material Requisition To Resource Division | 813/ND | 18/02/2022 | 0 | Resource Division | 2.2 | 0 | 0 | 0
2467 | NADIA | Nadia Division | Providing Functional House Tap Connection from NutangramWater Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/09043 | Retrofitting | Providing Left-out Functional Household tap Connection including supply of 15mm dia PVC pipe of average length of 15 mtr along with laying of different dia UPVC pipe and other allied works etc. all complete for augmentation of Natungram W/S Scheme under Ranaghat Sub-Division of Nadia Division P.H. Engineering Dte. | 919/RSD | 13/09/2023 | 545 | J & T ENTERPRISE | 1.2 | 0 | 0 | 100
2468 | NADIA | Nadia Division | Providing Functional House Tap Connection from ChapraBangaljhi Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) , SM/09222 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Chapra Bangaljhi W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(PART-A) | 5692/ND | 03/11/2021 | 90 | M/S GHOSH CONSTRUCTION | 86.03 | 83.18 | 96.69 | 0
2469 | NADIA | Nadia Division | Providing Functional House Tap Connection from ChapraBangaljhi Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) , SM/09222 | Retrofitting | Material Requisition To Resource Division | 426/ND | 31/01/2022 | 0 | Resource Division | 3.58 | 0 | 0 | 0
2470 | NADIA | Nadia Division | Providing Functional House Tap Connection from ChapraBangaljhi Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) , SM/09222 | Retrofitting | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 174 m3/hr at Chapra Bangaljhi Water Supply Scheme within Chapra Block under Krishnagar Sub- Divn. under Nadia Division, P.H.E. Dte. | 1898/ND | 15/03/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 385.52 | 0 | 0 | 0
2471 | NADIA | Nadia Division | Providing Functional House Tap Connection from ChapraBangaljhi Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) , SM/09222 | Retrofitting | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | 7571/ND | 27/12/2024 | 31 | IMAGIN | 34.21 | 0 | 0 | 0
2472 | NADIA | Nadia Division | Providing Functional House Tap Connection from ChapraBangaljhi Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) , SM/09222 | Retrofitting | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
2473 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08862 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1414/NAD-I | 08/11/2021 | 45 | JOY HIND TUBE WELLS | 44.57 | 44.25 | 100 | 100
2474 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08862 | Retrofitting | Material Requisition To Resource Division | 142/NAD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0 | 0
2475 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08862 | Retrofitting | Interconnection between 1st and 2nd Tubewell Rising Main at Chupria Zone-II W/S Scheme in Hanskhali block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 04) | 2371/NAD-I | 06/10/2023 | 21 | BISWAS CONSTRUCTION | 14.67 | 13.26 | 100 | 100
2476 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Joypur Part-II, at Hanskhali Block by retrofitting of Ground Water based PWSS for Joypur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08813 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Joypur Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Joypur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1416/NAD-I | 08/11/2021 | 60 | GHOSH ENTERPRISE | 86.93 | 86.53 | 100 | 100
2477 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Joypur Part-II, at Hanskhali Block by retrofitting of Ground Water based PWSS for Joypur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08813 | Retrofitting | Wall writing on smooth wall surface (Preferably on Govt. premises / Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and two coat best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Nadia all completed as per direction of EIC. | 466/NAD-I | 15/03/2024 | 92 | IMAGIN | 11.2 | 11.19 | 100 | 100
2478 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Gobindapur at Hanskhali block by retrofitting of Ground Water Based PWSS for Gobindapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte , SM/08815 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Part-I (Gobindapur) at Hanskhali Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 50/NAD-I | 11/01/2022 | 90 | M/S DIPAK ENTERPRISE | 128.71 | 128.56 | 100 | 100
2479 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Gobindapur at Hanskhali block by retrofitting of Ground Water Based PWSS for Gobindapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte , SM/08815 | Retrofitting | Route Survey for preparation of DPR for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for GOBINDAPUR ZONE-II Water Supply Scheme of Nadia District under Nadia Arsenic-I Division, PHE Dte. (Sl. No.-04) | 61/AE-I/N.A.D.-I | 24/02/2021 | 30 | UMWELT ENGINEER PVT. LTD. | 3.68 | 3.68 | 100 | 100
2480 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Gobindapur at Hanskhali block by retrofitting of Ground Water Based PWSS for Gobindapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte , SM/08815 | Retrofitting | Route Survey for preparation of DPR for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for GOBINDAPUR ZONE-I Water Supply Scheme under Nadia Arsenic-I Division, PHE Dte. | 59/AE-I/N.A.D.-I | 24/02/2021 | 30 | UMWELT ENGINEER PVT. LTD. | 4.6 | 4.6 | 100 | 100
2481 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Gobindapur at Hanskhali block by retrofitting of Ground Water Based PWSS for Gobindapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte , SM/08815 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Hanskhali BDO, BL&LRO, Ration Deptt, Animal Husbandary,Health etc, at Hanskhali Block by retrofitting of Ground Water based PWSS for Gobindapur (Hanskhali) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 266/AE-I/NAD-I | 09/11/2022 | 15 | BUDDHADEV MONDAL | 4.66 | 4.66 | 100 | 100
2482 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Gobindapur at Hanskhali block by retrofitting of Ground Water Based PWSS for Gobindapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte , SM/08815 | Retrofitting | Construction of Boundary wall, Land Development, Construction of Pathway & other allied works at Headwork site of Gobindapur (Hanskhali) under Hanskhali Dev. Block water supply scheme under Nadia Arsenic Division-I, P.H.E. Dte. Length of Boundary wall - 145 mtr. metre. | 74/NAD-I | 17/01/2022 | 30 | NISHITH BANERJEE | 16.71 | 0 | 0 | 70
2483 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Gobindapur at Hanskhali block by retrofitting of Ground Water Based PWSS for Gobindapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte , SM/08815 | Retrofitting | Balance work for revamping / upgradation of the hydraulic parameters at Kalipara,Gobindapur, Jhinukghata and Raynagar mouzas in reference to Gobindapur PWSS and Raynagar PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 04) | 127/NAD-I | 22/04/2025 | 60 | CHOWDHURY & CO. | 96.3 | 0 | 0 | 0
2484 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Gobindapur at Hanskhali block by retrofitting of Ground Water Based PWSS for Gobindapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte , SM/08815 | Retrofitting | Balance work for revamping / upgradation of the hydraulic parameters at Gobindapur Colony and Hijuli mauza in reference to Gobindapur PWSS and Hijuli PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission (Sl. NO. 08) | 231/NAD-I | 13/05/2025 | 60 | TARUN GHOSH | 89.24 | 0 | 0 | 0
2485 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08844 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Zone-II Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 48/NAD-I | 11/01/2022 | 90 | M/S MALLICK ENTERPRISE | 126.06 | 125.49 | 100 | 100
2486 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08844 | Retrofitting | Laying of additional pipelines and other allied works Chupria Zone-II W/S Scheme within Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. | 1315/NAD-I | 22/08/2024 | 374 | MS MAA BHABANI ENTERPRISE | 9.72 | 0 | 0 | 0
2487 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08844 | Retrofitting | Interconnection between Manifold and delivery main and approach road at arranghata Zone-I W/S Scheme in Ranaghat-II block and Chupria Zone-I in Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 01) | 2006/NAD-I | 29/11/2024 | 260 | BUDDHADEV MONDAL | 40.2 | 0 | 0 | 50
2488 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08848 | Retrofitting | Providing FHTC (Functional Household Tap Connection) by retrofitting/rejuvenation under Jaldhara/Jal Swapna for Arranghata Zone-I Water Supply Scheme, Phase-I at Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. | 645/NAD-I | 29/04/2022 | 90 | M/S R.K. ENTERPRISE | 260.46 | 213.67 | 100 | 100
2489 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08848 | Retrofitting | Material Requisition To Resource Division | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 19.86 | 0 | 0 | 0
2490 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09574 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | 631/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.21 | 0 | 0 | 0
2491 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09574 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Zone-I under Dafarpota W/S Scheme, Block-Krishnagar 1, Dist. - Nadia. NIET No.- 18 of EE/EMD of 2022-23 (SSl. No.- 04) | 6185/EMD | 14/11/2022 | 30 | GHOSH AND GHOSH | 10.82 | 9.36 | 100 | 80
2492 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09574 | Augmentation | Material Requisition To Resource Division | 97/ND | 06/01/2022 | 0 | Resource Division | 7.54 | 0 | 0 | 0
2493 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09574 | Augmentation | Material Requisition To Resource Division | 1450/ND | 25/03/2022 | 0 | Resource Division | 18.89 | 0 | 0 | 0
2494 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09574 | Augmentation | Material Requisition To Resource Division | 1393/ND | 24/03/2022 | 0 | Resource Division | 30.99 | 0 | 0 | 0
2495 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09574 | Augmentation | Material Requisition To Resource Division | 3305/ND | 27/07/2022 | 0 | Resource Division | 1.41 | 0 | 0 | 0
2496 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09574 | Augmentation | New Service Connection at Pump House I Zone-I under Dafarpota W/S Scheme. | BP-164-23-24 | 11/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.57 | 0 | 0 | 0
2497 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09574 | Augmentation | Providing balance FHTC Of Retrofitting (Phase-I) Under JJM in Ground Based piped water supply scheme at Dafarpota Zone I to accommodate FHTC within Krishnagar I block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | 3896/ND | 16/07/2024 | 60 | SINGHA ROY & CO. | 34.11 | 0 | 0 | 0
2498 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09574 | Augmentation | Supplementary works to completion of ongoing FHTC-related work at PH-I of Dafarpota (Zone-I) W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | 603/EMSD-II | 22/08/2023 | 15 | GHOSH AND GHOSH | 0.52 | 0.44 | 100 | 100
2499 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09574 | Augmentation | Special repair and renovation of 1st Pump House and Allied Works ," and Earthwork infilling in !st Tubewell site of Dafarpota -I Water supply scheme under Krishnagar Sub-Division PHED Sl.01 | 512/KSD | 30/05/2022 | 30 | DEBASHISH DEY | 3.37 | 3.12 | 100 | 100
2500 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09574 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. and Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of 900 CUM OHR all complete for Augmentation of Ground Based Water Supply Scheme at Dafarpota Zone-I to accommodate FHTC within Krishnagar-1 block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 623/ND | 09/02/2022 | 90 | SINGHA ROY & CO. | 253.11 | 185.88 | 73.44 | 70
2501 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/09574 | Augmentation | Construction and installation of Manifold and allied works at OHR site in connection to Ground Based Piped Water Supply Scheme at Dafarpota Zone II To Accommodate FHTC Within Krishnagar I Block Under Krishnanagar Sub-division Under Nadia Division,phe Dte. | 2848/ND | 18/06/2025 | 90 | SAHA ENGINEERS | 18.01 | 0 | 0 | 0
2502 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte , SM/09576 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. for Augmentation to Accomodate FHTC at Pump House No. I (Zone-II) under Sonda W/S Scheme, Block-Krishnagar 1, District of Nadia. NIET No.- 14 of EE/EMD of 2022-23 (Sl. No.-02) | 3911/EMD | 19/10/2022 | 30 | DAS ENTERPRISE | 9.39 | 0 | 0 | 0
2503 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte , SM/09576 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80) / 20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Sonda-II to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 64/ND | 05/01/2022 | 45 | ROY CONSTRUCTION | 15.67 | 13.4 | 85.5 | 95
2504 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte , SM/09576 | Augmentation | Supplementary works to completion of ongoing FHTC-related work at PH-I of Sonda (Zone - II) W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | 687/EMSD-II | 13/09/2023 | 15 | DAS ENTERPRISE (BARANAGAR) | 0.99 | 0 | 0 | 100
2505 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte , SM/09576 | Augmentation | Supplementary works to completion of ongoing FHTC-related work at PH-I of Sonda (Zone - II) W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | 687/EMSD-IIDt.13/09/2023 | 14/08/2022 | 30 | DAS ENTERPRISE (BARANAGAR) | 0.99 | 0.99 | 100 | 100
2506 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte , SM/09576 | Augmentation | Material Requisition To Resource Division | 7452/ND | 27/12/2021 | 0 | Resource Division | 9.44 | 0 | 0 | 0
2507 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte , SM/09576 | Augmentation | Material Requisition To Resource Division | 4298/ND | 29/09/2022 | 0 | Resource Division | 0.33 | 0 | 0 | 0
2508 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte , SM/09576 | Augmentation | Conversion of IEP to AIRP of capacity 9 Cu.m/hr at Sonda Water Supply Scheme within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 1904/ND | 15/03/2024 | 60 | SUMIT GHOSH | 63.49 | 0 | 0 | 0
2509 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte , SM/09576 | Augmentation | Repair and renovation works of R.C.C. Elevaced Reservoir 50 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Sonda Zone II Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 5368/ND | 04/12/2023 | 90 | REAL TIME | 21.55 | 20.73 | 100 | 100
2510 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte , SM/09576 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. for Augmentation to Accomodate FHTC at Pump House No. I (Zone-II) under Sonda W/S Scheme, Block-Krishnagar 1, District of Nadia. NIET No.- 14 of EE/EMD of 2022-23 (Sl. No.-02) | 3911EMD | 09/10/2022 | 30 | DAS ENTERPRISE (BARANAGAR) | 9.39 | 8.37 | 100 | 0
2511 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte , SM/09576 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer etc. for Augmentation to Accomodate FHTC at Pump House No.II(Zone-II) under Sonda W/S Scheme, Block-Krishnagar 1, District of Nadia. NIET No.- 14 of EE/EMD of 2022-23 (Sl. No.01) | 3942/EMD | 20/10/2022 | 863 | BIJAN ENTERPRISE | 5.34 | 0 | 0 | 50
2512 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karimpur to Accommodate FHTC , SM/09033 | Augmentation | Material Requisition To Resource Division | 7048/ND | 06/12/2021 | 0 | Resource Division | 35.82 | 0 | 0 | 0
2513 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karimpur to Accommodate FHTC , SM/09033 | Augmentation | Material Requisition To Resource Division | 785/ND | 18/02/2022 | 0 | Resource Division | 16.47 | 0 | 0 | 0
2514 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karimpur to Accommodate FHTC , SM/09033 | Augmentation | Wall Writing Work under Nadia Division P. H. Engineering Dte. | 1821/ND | 14/03/2024 | 31 | IMAGIN | 34.21 | 14.06 | 100 | 60
2515 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karimpur to Accommodate FHTC , SM/09033 | Augmentation | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | 6305/ND | 26/09/2024 | 30 | IMAGIN | 34.21 | 0 | 0 | 100
2516 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karimpur to Accommodate FHTC , SM/09033 | Augmentation | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Karimpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte."(Phase-1 Retro fitting) " | 350/ND | 25/01/2022 | 1080 | TARUN KUMAR BHATTACHARYA | 404.96 | 363.29 | 89.71 | 100
2517 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karimpur to Accommodate FHTC , SM/09033 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 206 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Karimpur to accommodate FHTC within Karimpur-I block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | 4166/ND | 30/07/2024 | 360 | HARBAUER INDIA (P) LTD. | 444.71 | 0 | 0 | 30
2518 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karimpur to Accommodate FHTC , SM/09033 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- II) at Karimpur W/S to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 7465/ND | 20/12/2024 | 90 | CHOWDHURY & CO. | 128.29 | 0 | 0 | 0
2519 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karimpur to Accommodate FHTC , SM/09033 | Augmentation | Route survey, Design of distribution network for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Patabukahuda, Natna & Uttampur villages in Karimpur-I Block of Nadia District under Nadia Division, P.H.E. Dte. | 240/TSD | 02/05/2025 | 30 | ENVIROTECH SOLUTIONS | 0.96 | 0 | 0 | 100
2520 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karimpur to Accommodate FHTC , SM/09033 | Augmentation | Route survey, Design of distribution network for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Karimpur & Abhaypur villages in Karimpur-I Block of Nadia District under Nadia Division, P.H.E. Dte. | 239/TSD | 02/05/2025 | 30 | ENVIROTECH SOLUTIONS | 0.93 | 0 | 0 | 100
2521 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karimpur to Accommodate FHTC , SM/09033 | Augmentation | Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department. | 289/Kly SD-I | 31/03/2022 | 90 | SUMAN CHAKRABORTY | 4.89 | 4.89 | 100 | 100
2522 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09246 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Taldaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 868/NACD-II | 08/11/2021 | 45 | SANJOY BAKSHI | 62.77 | 62.73 | 100 | 100
2523 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09246 | Retrofitting | Construction of Boundary wall with Grill Gate at Taldaha Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | 50/AE-II/NACD-II | 17/02/2022 | 30 | GHOSH ENTERPRISE | 4.04 | 4 | 100 | 100
2524 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09246 | Retrofitting | Rejuvanation of Taldaha W/ Scheme in krishnaganj block nadia under EMSD-III Phe Dte. | 231/EMD | 15/02/2022 | 212 | ABHISEK ENGINEERING CONCERN | 7.43 | 7.43 | 100 | 100
2525 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09246 | Retrofitting | Functional House Hold Tap Connection for left out Household regarding Har Ghar Jal Certification including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Vill- Goari, Gopipur & Mathurapur) Taldaha W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 145/NACD-II | 17/01/2023 | 20 | CHANDRA NATH GHOSH | 2.27 | 2.26 | 100 | 100
2526 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09246 | Retrofitting | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Taldaha W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1191/NACD-II | 23/12/2022 | 15 | BABLU MALLICK | 1.13 | 0.8 | 100 | 100
2527 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09246 | Retrofitting | Providing Functional House Hold Tap Connection including laying of pipeline at Taldaha Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | 21/AE-II/NACD-II | 15/02/2024 | 15 | SHYAMAL SHIL | 0.97 | 0 | 0 | 0
2528 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09246 | Retrofitting | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KHANJIPUR , Block-Tehatta I and TALDAH , Block-Krishnaganj, Bahirgachhi (Z-II) Block-Chapra, Bagakhali (Z-II) W/S Scheme, Block-Tehatta I Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 03) | 1122/EMD | 16/03/2023 | 30 | ANJAN ENTERPRISE | 46.98 | 0 | 0 | 80
2529 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09246 | Retrofitting | Renovation of Arsenic cum Iron treatment Plant of Taldaha PWSS (Capacity- 43 m3/hr) and ancillary works of Krishnaganj Block under Nadia Arsenic Civil Division-II P.H.E. Dte | 90/NACD-II | 18/01/2024 | 60 | MONDAL PRECISION PRIVATE LIMITED | 94.35 | 84.91 | 100 | 99
2530 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09246 | Retrofitting | Wall writing work in various Gram Panchayats in Krishnaganj Block at Taldaha PWSS under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 758/AE-I/NACD-II | 19/06/2024 | 15 | IMAGIN | 0.93 | 0.93 | 100 | 100
2531 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09246 | Retrofitting | Jungle cutting and Earthwork in filling at Taldaha,Sakdaha and Brittihuda Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 819/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.53 | 0.19 | 100 | 100
2532 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09246 | Retrofitting | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Krishnaganj Block of Nadia District through Jadavpur University. (Name of PWSS Taldaha) | 867/NACD-II | 04/07/2024 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
2533 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09246 | Retrofitting | Material Requisition To Resource Division | 79/NACD-II | 15/01/2024 | 0 | Resource Division | 6.16 | 0 | 0 | 0
2534 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09246 | Retrofitting | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Kadipur & Taldaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | 52/NACD-II | 20/01/2022 | 45 | B.M. ENGINEERING & CONSTRUCTION | 27.75 | 26.75 | 100 | 100
2535 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09246 | Retrofitting | Construction and installation of MANIFOLD, dedicated line and Distribution network for new FHTC at Taldaha Piped Water Supply Scheme and laying distribution network for FHTC and Repairing of Top Dome and related work for 250 cum RCC elevated reservoir at Helenchi Zone- III in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1571/NACD-II | 06/12/2024 | 270 | BIDYUT KUMAR | 105.92 | 10.24 | 19.34 | 40
2536 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) , SM/08953 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within Nakashipara Block. (Phase-C) | 688/PFMS | 29/03/2022 | 0 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 51.63 | 0 | 0 | 0
2537 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) , SM/08953 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) | 680/PFMS | 25/03/2022 | 0 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 59 | 0 | 0 | 0
2538 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) , SM/08953 | Retrofitting | Providing Functional Household Tap connection(FHTC)at Surface Water Based Water Supply Scheme(Northern Sector) Part-II,Zone-I,II &III within Nakashipara Block(Phase-C) | 7204/ND | 15/12/2021 | 90 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 189.26 | 63.92 | 100 | 100
2539 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) , SM/08953 | Retrofitting | Laying additional distribution pipeline for providing FHTC at zone-I II & III, Part- II Phase C, Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | 51/DSD | 07/02/2022 | 15 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.85 | 4.83 | 100 | 100
2540 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) , SM/08953 | Retrofitting | Laying additional distribution pipeline for providing FHTC at zone-I II & III, Part- II Phase C, Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | 53/DSD | 07/02/2022 | 15 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.68 | 4.63 | 100 | 100
2541 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) , SM/08953 | Retrofitting | Material Requisition To Resource Division | 800/ND | 18/02/2022 | 0 | Resource Division | 22.04 | 0 | 0 | 0
2542 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) , SM/08953 | Retrofitting | Material Requisition To Resource Division | 229/ND | 11/01/2024 | 0 | Resource Division | 16.4 | 0 | 0 | 0
2543 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) , SM/08953 | Retrofitting | Construction of OHR, repair and renovation of staff room, repair of boundary wall, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-III / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11839]. | 6112/ND | 21/12/2023 | 730 | MONDAL ENTERPRISE | 201.12 | 0 | 0 | 5
2544 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) , SM/08958 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) | 35/PFMS | 23/05/2022 | 0 | MAHAVIR PUMPS MFG PVT. LTD. | 51.4 | 0 | 0 | 0
2545 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) , SM/08958 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) | 660/PFMS | 23/03/2022 | 0 | MAHAVIR PUMPS MFG PVT. LTD. | 4.34 | 0 | 0 | 0
2546 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) , SM/08958 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) | 654/PFMS | 21/03/2022 | 0 | MAHAVIR PUMPS MFG PVT. LTD. | 33 | 0 | 0 | 0
2547 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) , SM/08958 | Retrofitting | Providing Functional household Tap Connection (FHTC) at Surface Water Based Water Supply Scheme (Northern Sector) Part-II, Zone-VI & IX within Nakashipara Block (Phase-D) | 7255/ND | 17/12/2021 | 90 | MAHAVIR PUMPS MFG PVT. LTD. | 180.19 | 74.78 | 100 | 100
2548 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) , SM/08958 | Retrofitting | Material Requisition To Resource Division | 814/ND | 18/02/2022 | 0 | Resource Division | 10.98 | 0 | 0 | 0
2549 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) , SM/08958 | Retrofitting | Material Requisition To Resource Division | 232/ND | 11/01/2024 | 0 | Resource Division | 19.22 | 0 | 0 | 0
2550 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) , SM/08958 | Retrofitting | Material Requisition To Resource Division | 233/ND | 11/01/2024 | 0 | Resource Division | 20.91 | 0 | 0 | 0
2551 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) , SM/08958 | Retrofitting | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4589/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 0 | 0 | 50
2552 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dafarpota Zone I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/08665 | Retrofitting | Providing Functional House Tap Connection from Dafarpota Zone I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | 606/PFMS | 11/03/2022 | 0 | OTHERS | 6.11 | 0 | 0 | 0
2553 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dafarpota Zone I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/08665 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Daforpota (Zone-I) W/S scheme in Nadia District under Nadia Division, PHE Dte. (Phase-I, Retrofitting) (Part-A) | 5145/ND | 15/09/2021 | 75 | SOMNATH CHATTERJEE | 63.36 | 59.97 | 94.65 | 0
2554 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dafarpota Zone I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/08665 | Retrofitting | Material Requisition To Resource Division | 803/ND | 18/02/2022 | 0 | Resource Division | 6.6 | 0 | 0 | 0
2555 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dafarpota Zone I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/08665 | Retrofitting | Providing balance FHTC Of Retrofitting (Phase-I) Under JJM in Ground Based piped water supply scheme at Dafarpota Zone I to accommodate FHTC within Krishnagar I block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | 3896/ND | 16/07/2024 | 60 | SINGHA ROY & CO. | 34.11 | 0 | 0 | 0
2556 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dafarpota Zone I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. , SM/08665 | Retrofitting | Hiring of 1 (One) no Diesel Cab having contract permit from regional transport authority for office use of the Executive Engineer, Nadia Division, P.H.E. Dte. for a period of 183 ( One Hundred Eighty Three) Days on (F.N). | 689/KLYSD-I | 01/06/2023 | 183 | AVINABA ENGINEERING CONCERN | 2.4 | 2.35 | 100 | 100
2557 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI within Nakashipara Block.(Phase-C) , SM/08669 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI within Nakashipara Block.(Phase-C) | 576/PFMS | 04/03/2022 | 0 | TARUN KUMAR BHATTACHARYA | 21.16 | 0 | 0 | 0
2558 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI within Nakashipara Block.(Phase-C) , SM/08669 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI within Nakashipara Block.(Phase-C) | 548/PFMS | 23/02/2022 | 0 | TARUN KUMAR BHATTACHARYA | 35 | 0 | 0 | 0
2559 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI within Nakashipara Block.(Phase-C) , SM/08669 | Retrofitting | Laying additional distribution pipeline for providing FHTC at zone-VI Phase- C, Part- II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | 47/DSD | 07/02/2022 | 15 | TARUN KUMAR BHATTACHARYA | 2.19 | 1.12 | 51.31 | 0
2560 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI within Nakashipara Block.(Phase-C) , SM/08669 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-II, Zone-VI within Nakashipara Block (Phase-C) | 5182/ND | 20/09/2021 | 90 | TARUN KUMAR BHATTACHARYA | 86.53 | 23.52 | 100 | 100
2561 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI within Nakashipara Block.(Phase-C) , SM/08669 | Retrofitting | Material Requisition To Resource Division | 4275/ND | 29/09/2022 | 0 | Resource Division | 0.02 | 0 | 0 | 0
2562 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshinpara Zone-I Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/08674 | Retrofitting | Providing Functional House Tap Connection from Dakshinpara Zone-I Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | 606/PFMS | 11/03/2022 | 0 | OTHERS | 8.13 | 0 | 0 | 0
2563 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshinpara Zone-I Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/08674 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Dakshinpara Z-I Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.E. Dte.(Phase-A) | 5177/ND | 20/09/2021 | 90 | M/S KALIMATA ENTERPRISE | 88.33 | 87.91 | 99.53 | 0
2564 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshinpara Zone-I Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/08674 | Retrofitting | Material Requisition To Resource Division | 99/ND | 06/01/2022 | 0 | Resource Division | 2.65 | 0 | 0 | 0
2565 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshinpara Zone-I Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/08674 | Retrofitting | Material Requisition To Resource Division | 793/ND | 18/02/2022 | 0 | Resource Division | 8.77 | 0 | 0 | 0
2566 | NADIA | Nadia Division | Providing Functional House Tap Connection from Dakshinpara Zone-I Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) , SM/08674 | Retrofitting | Material Requisition To Resource Division | 1035/ND | 03/03/2022 | 0 | Resource Division | 15.16 | 0 | 0 | 0
2567 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | 611/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.18 | 0 | 0 | 0
2568 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | 695/PFMS | 28/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 38.35 | 0 | 0 | 0
2569 | NADIA | Eastern Mechanical | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I & II Z-II under Bayra W/S Scheme District of 24 Pgs. (N) | 6184 EMD | 14/08/2022 | 30 | TALUKDER & CO. | 8.94 | 0 | 0 | 100
2570 | NADIA | Eastern Mechanical | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator etc. Rejuvention to accommodate FHTC) at PH-I & II (Zone-II) under Badelangi Padmamala W/S Scheme Block Chapra under District of Nadia) | 6184 / EMD | 14/08/2022 | 30 | TALUKDER & CO. | 8.94 | 8.94 | 100 | 0
2571 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Material Requisition To Resource Division | 4296/ND | 29/09/2022 | 0 | Resource Division | 22.45 | 0 | 0 | 0
2572 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Laying of Distribution System including specials & valves, pipe supporting structure all complete and Providing FHTC including supplying,laying,fitting, fixing of 15mm NB PVC(schedule 80)/ 20mm OD HDPE(PE100,PN16) pipe with all necessary specials,10mm gun metal ferrule,saddale piece etc.by retrofitting under Jal Swapna for Badlangi Padmamala Zone-II Water Supply Scheme in Nadia District under Nadia Division PHE Dte. | 662/ND | 11/02/2022 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 458.3 | 313.34 | 100 | 78
2573 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Collection of Household data through mobile app for FHTC Connection (Phase-V), under Nadia Division, P.H.E. Dte. | 221/KLYSD-I | 09/02/2024 | 182 | TECHVISION | 4.85 | 4.85 | 100 | 100
2574 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Collection of Household data through mobile app for FHTC Connection (Phase-VII), under Nadia Division, P.H.E. Dte. | 1220/KlySD-I | 09/08/2024 | 184 | TECHVISION | 4.85 | 4.85 | 100 | 100
2575 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Wall Writing Work under Nadia Division P. H. Engineering Dte. | 1821/ND | 14/03/2024 | 31 | IMAGIN | 34.21 | 3.16 | 100 | 60
2576 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir, Pump House, Boundary Wall and Construction of Srevice Road for Badlangi Padmamala Zone-II Water Supply Scheme under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 1303/ND | 23/02/2024 | 90 | B.S. ENTERPRISE | 34.23 | 23.34 | 100 | 100
2577 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Collection of Household data through mobile app for FHTC Connection (Phase-VIII), under Nadia Division, P.H.E. Dte. | 1221/KlySD-I | 09/08/2024 | 184 | TECHVISION | 4.85 | 4.85 | 100 | 100
2578 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | 6305/ND | 26/09/2024 | 30 | IMAGIN | 34.21 | 0 | 0 | 100
2579 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Reimbursement of Additional GST due to enhancement of rate from 12% to 18% vide notification no. 03/2022 central Tax Rate dt. 13.07.2022. of Laying of Distribution System including specials & valves,pipe supporting structure all complete and Providing FHTC including supplying,laying,fitting,fixing of 15mm NB PVC(schedule 80)/20mm OD HDPE(PE100,PN16) pipe with all necessary specials,10mm gun metal ferrule,saddle piece etc. by retroffitting under Jal Swapna for Badlangi Padmamala Zone-II Water Supply Scheme in Nadia District under Nadia Division PHE Dte. | 150/PFMS | 31/07/2024 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 6.5 | 0 | 0 | 0
2580 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Additional work of Laying Distribution System and additional work of providing FHTC in connection with Augmentation of Badlangi Padmamala Zone - II PWSS in Pathuria & Dompukur Mouza within Chapra Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 3432/ND | 19/06/2024 | 360 | S.S.INFRASTRUCTURE | 73.72 | 0 | 0 | 80
2581 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Conversion of IEP to AIRP of capacity 120 Cu.m/hr at Badlangi Padmamala Zone-II Water Supply Scheme within Chapra block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. | 1913/ND | 15/03/2024 | 720 | MONDAL PRECISION PRIVATE LIMITED | 194.64 | 0 | 0 | 20
2582 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Additional work of Laying Distribution System and additional work of providing FHTC in connection with Augmentation of Badlangi Padmamala Zone - II PWSS in Bania Khari & Chotta Andulia Mouza within Chapra Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 3899/ND | 16/07/2024 | 180 | J.P. CONSTRUCTION & SUPPLIERS | 75.72 | 8.73 | 11.53 | 60
2583 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site of Badlangi Padmamala Zone-I Water Supply scheme under RWS Sub Division under Nadia Division-,P.H.E Dte. | 7451/ND | 20/12/2024 | 180 | ROY ASSOCIATES | 85.97 | 0 | 0 | 25
2584 | NADIA | Eastern Mechanical | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under BADELANGI PADMAMALA ZONE-II ground water based water supply scheme under Block_ CHAPRA Dist. - Nadia under EMD, PHE Dte. SM/09450 | 1113/EMD | 04/06/2025 | 90 | BIDYUT KUMAR MUKHERJEE | 20.78 | 0 | 0 | 0
2585 | NADIA | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/09450 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site of Badlangi Padmamala Zone-II Water Supply scheme under RWS Sub Division under Nadia Division-,P.H.E Dte. | 874/ND | 25/02/2025 | 180 | S.D. CONSTRUCTION | 25.17 | 0 | 0 | 40
2586 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-I) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. , SM/10418 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-I) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. | 14/PFMS | 11/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.6 | 0 | 0 | 0
2587 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-I) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. , SM/10418 | Augmentation | Continuation of Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period of 90 days w.e.f 01/07/2023 (as and when required). | 800/KSD | 16/06/2023 | 92 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 0
2588 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-I) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. , SM/10418 | Augmentation | Material Requisition To Resource Division | 124/ND | 05/01/2023 | 0 | Resource Division | 14.44 | 0 | 0 | 0
2589 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-I) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. , SM/10418 | Augmentation | Material Requisition To Resource Division | 2317/ND | 29/05/2023 | 0 | Resource Division | 15.4 | 0 | 0 | 0
2590 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-I) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. , SM/10418 | Augmentation | Laying of Distribution System including Specials, Valves & Pipe Supporting Structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. and Construction of boundary wall at head work site all complete for Augmentation of Ground Based Water Supply Scheme at Mahisura (Phase-I) to accommodate FHTC with Nabadwip Block under Krishnagar Sub-Division, PHE Dte. (SM/10418) | 1388/ND | 29/03/2023 | 90 | PATHIK PABAN NANDI | 373.94 | 348.71 | 93.25 | 60
2591 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-I) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. , SM/10418 | Augmentation | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of capacity 156 m3/hr at Mahisura Water Supply Scheme within Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | 6571/ND | 21/10/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 348.3 | 0 | 0 | 0
2592 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-I) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. , SM/10418 | Augmentation | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Mahisura Water Supply Scheme within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 6116/ND | 21/12/2023 | 60 | DEL DELTA CONSTRUCTION | 11.42 | 11.02 | 100 | 100
2593 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-I) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. , SM/10418 | Augmentation | RESTORATION OF ROAD FROM MOHISURA TO BANKAR DHOPADI under Package No. WB/14/116 | 321/PFMS | 05/10/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 6.38 | 0 | 0 | 0
2594 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatata (Phase-I) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10461 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatata (Phase-I) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | 23/PFMS | 20/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.14 | 0 | 0 | 0
2595 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatata (Phase-I) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10461 | Augmentation | Laying of Distribution system including specials, valves & pipe supporting structure all complete & Providing FHTC at Augmentation of Ground Water Based Water Supply Scheme for Tehatta(Phase-I) to accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division PHE Dte. | 3419/ND | 02/08/2022 | 90 | H I ENTERPRISE | 465.49 | 460.45 | 100 | 93
2596 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatata (Phase-I) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10461 | Augmentation | Material Requisition To Resource Division | 4288/ND | 29/09/2022 | 0 | Resource Division | 0.04 | 0 | 0 | 0
2597 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatata (Phase-I) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10461 | Augmentation | Material Requisition To Resource Division | 4020/ND | 16/09/2022 | 0 | Resource Division | 70.86 | 0 | 0 | 0
2598 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatata (Phase-I) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10461 | Augmentation | Material Requisition To Resource Division | 112/ND | 05/01/2023 | 0 | Resource Division | 2.19 | 0 | 0 | 0
2599 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatata (Phase-I) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10461 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 135 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Tehatta to accommodate FHTC within Tehatta-I block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | 4230/ND | 02/08/2024 | 180 | TARUN KUMAR BHATTACHARYA | 315.65 | 0 | 0 | 0
2600 | NADIA | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. , SM/10462 | Augmentation | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. | 30/PFMS | 20/05/2022 | 0 | RADIANT | 2.61 | 0 | 0 | 0
2601 | NADIA | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. , SM/10462 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-IX(A) to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 3278/ND | 26/07/2022 | 90 | A ONE CONSTRUCTION | 138.52 | 133.83 | 100 | 99
2602 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. , SM/10462 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under Karimpur jalangi (Zone-IX,A & B) W/S Scheme, Block-Tehatta-II, Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 19) | 419EMD | 20/01/2023 | 30 | SINHA ELECTRICALS | 14.88 | 13.14 | 100 | 85
2603 | NADIA | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. , SM/10462 | Augmentation | Material Requisition To Resource Division | 4300/ND | 29/09/2022 | 0 | Resource Division | 9.31 | 0 | 0 | 0
2604 | NADIA | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. , SM/10462 | Augmentation | Material Requisition To Resource Division | 3523/ND | 05/08/2022 | 0 | Resource Division | 25.05 | 0 | 0 | 0
2605 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. , SM/10462 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No. I , II under KARIMPUR JALANGI Zone X A WS Scheme, Block Karimpur-II, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-14) | 162/EMD | 06/01/2023 | 30 | S.B.ENTERPRISE | 9.73 | 0 | 0 | 70
2606 | NADIA | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. , SM/10462 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Karimpur Jalangi Zone-IX A Ground Based Water Supply Scheme under Karimpur II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Karimpur Jalangi Zone-IX A at Karimpur II Block by Augmentation of Ground Water based PWSS for Karimpur Jalangi Zone-IX A Water Supply Schemes under Nadia Division, PHE Dte. | 7366/ND | 18/12/2024 | 60 | SUBIR KUMAR DEY | 21.9 | 0 | 0 | 0
2607 | NADIA | Nadia Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. , SM/10462 | Augmentation | Laying of additional pipeline for Dakshin Gopalpur & Nandanpur mouzas under Karimpur Jalangi Zone- IX(A) PWSS under Tehatta Sub-Division under Nadia Division PHE Dte. | 7407/ND | 19/12/2024 | 270 | SHYAMAL SHIL | 54.11 | 0 | 0 | 30
2608 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of MAMJOANI & RAMNAGAR under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , Constr , SM/09959 | Augmentation | Construction of Boundary wall, Toilet Pathway and all repair works at 2nd T W allied site and all repair works at HW site of Mamjoani under NAD I PHE Dte (Sl.no.08) | 1963 / NAD-I | 14/10/2022 | 60 | D.K. CONSTRUCTION | 13.16 | 11.7 | 88.91 | 0
2609 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of MAMJOANI & RAMNAGAR under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , Constr , SM/09959 | Augmentation | Construction of Boundary wall Pathway Toilet and all repair works at 2 nd TW Site and all repair works at HW site of Ramnagar WS Scheme under NAD I PHE Dte (Sl.no.03) | 1595 / NAD-I | 06/09/2022 | 45 | SANJIB DEY | 10.06 | 8.56 | 100 | 93
2610 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of MAMJOANI & RAMNAGAR under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , Constr , SM/09959 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Dhara/Jal Swapna for Mamjoani Part-III at Hanskhali Block by retrofitting of Ground Water based PWSS for Mamjoani Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 13) | 438/NAD-I | 07/03/2022 | 600 | SHYAMAL SHIL | 88.34 | 83.23 | 100 | 100
2611 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of MAMJOANI & RAMNAGAR under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , Constr , SM/09959 | Augmentation | Phase -II FHTC under Jaldhara/ Jal Swapna for Ramnagar at Hanskhali Block by retrofitting of Ground Water Based PWSS for Ramnagar Water Supply scheme under Nadia Arsenic Division -I, P.H.E. Dte. (Sl. no -05) | 962 / NAD-I | 07/07/2022 | 60 | M/S K.P. CONSTRUCTION | 81.96 | 57.6 | 88.3 | 100
2612 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of MAMJOANI & RAMNAGAR under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , Constr , SM/09959 | Augmentation | Work for revamping / upgradation of the hydraulic parameters at Mamjoani mouzas in reference to Mamjoani water supply scheme & Duttaphulia water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 07) | 76/NAD-1 | 16/04/2025 | 240 | JOYGOPAL GUPTI | 96.49 | 0 | 0 | 57
2613 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , , SM/09961 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Chupria Zone-II Part-III at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 08) | 434/NAD-I | 07/03/2022 | 60 | M/S SHIL AND CO. | 45.66 | 43.22 | 100 | 100
2614 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , , SM/09961 | Augmentation | Providing FHTC under Jaldhara / Jalswapna for Garapota P-III at Hanskhali block by retrofitting of Ground Water Based PWSS W/S Scheme under Nadia Arsenic Division -I , P.H.E. Dte. (Sl. No. 12) | 1512 / NAD-I | 26/08/2022 | 21 | SAHA ENGINEERS | 43.43 | 43.43 | 100 | 100
2615 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , , SM/09961 | Augmentation | Operation & Maintenance of Distribution System and Rising Main Pipeline (CI/DI/UPVC) and Iron Elimination Plant of Different Ground Based Piped Water Supply Scheme for arsenic affected areas of Joypur, Itaberia, Chupria Z-I, Chupria Z-II, Gobindapur ( Hanskhali ) and Garapota & adjoining mouzas for the period of 1 year under Nadia Arsenic Division - I, P.H. Engineering Dte. (Sl.no. 01) | 1920 / NAD-I | 30/09/2022 | 365 | APURBA MANDAL | 28.6 | 0 | 0 | 0
2616 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , , SM/09961 | Augmentation | Construction of Boundary wall, Toilet, Pathway and other allied work at Head Work T/W site in connectionwith Augmentation of Chupria Zone-II water supply Scheme within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. (SL.19) | 579/NAD-I | 17/03/2023 | 15 | DIPANKAR DUTTA | 18.87 | 8.18 | 43.35 | 48
2617 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , , SM/09961 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Garapota Bazar to H/O Chayan Biswas, Boro Chupria & Paschim Garapota to H/O Sanjiban Biswas, Boro Chupria at Hanskhali Block by retrofitting of Ground Water Based PWSS for Chupria W/S Scheme underNadia Arsenic Division-I, P.H.E. Dte. (Sl.20) | 827 / NAD-I | 31/03/2023 | 30 | JAGADANADAPUR CO-OPT LABOUR CONTTRACT AND CONSTRUTION SOCITY LTD. | 32.85 | 20.68 | 62.96 | 0
2618 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , , SM/09961 | Augmentation | Construction of Boundary Wall Toilet Pathway and other allied work at Chupria Zone II WS Scheme within Hanskhali Block under NAD- I PHE Dte (Sl.no.01) | 1594 /NAD-I | 06/09/2022 | 45 | SUBIR KUMAR DEY | 12.65 | 12.59 | 100 | 100
2619 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , , SM/09961 | Augmentation | Repair of 450 cum capacity Over Head Reservoir ,Painting and Pump House at Chupria, Zone-II underSurface W/S Scheme in Hanskhali Block under NadiaArsenic Division - I P. H.E. Dte (Sl.no.14) | 154 /NAD-I | 07/02/2023 | 30 | APURBA MANDAL | 22.4 | 22.33 | 100 | 45
2620 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , , SM/09961 | Augmentation | Retrofitting work at Kautaknagar, Ramdulalpur, under Mayurhat-I G.P. for Ground Water Based PWSS at Hanskhali Block in connection with augmenttaion of Garapota W/S Scheme under Jal Jeevna Mission (JJM) under Nadia Arsenic Division-I , PHE Dte. (Sl.no.09) | 1457 /NAD-I | 29/05/2023 | 21 | TAPU SAHA | 21.99 | 21.99 | 100 | 100
2621 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , , SM/09961 | Augmentation | Construction of Boundary wall, Toilet, Pathway and other allied work at Head Work T/W site in connection with Augmentation of Garapota water supply Scheme within Hanskhali Block under Nadia Arsenic Division-I,P.H.E. Dte. ( sl.no.12) | 580/NAD-I | 17/03/2023 | 21 | ONKAR ENTERPRISE | 19.03 | 18.76 | 100 | 100
2622 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , , SM/09961 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under GARAPOTA,BHAYNA(Z-I), BHAYNA(Z-II) & MAMJOANI W/S Scheme, Block-HANSKHALI , Dist. - Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 04) | 1604/EMD | 26/04/2023 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 61.43 | 52.83 | 93.56 | 80
2623 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , , SM/09961 | Augmentation | Repair of 550 cum capacity Over Head Reservoir, Painting of Pump House in connection with Augmentation of Garapota W/S Scheme in Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (Sl.no.23) | 892/NAD-I | 04/04/2023 | 30 | S B CONSTRUCTION | 26.31 | 23.54 | 100 | 75
2624 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , , SM/09961 | Augmentation | Shifting of LT OH line by erection of 2nos PCC pole 8meter long at Garapota (Ph-1) at Hanskhali block, Dist.-Nadia | BP-20-24-25 | 21/05/2024 | 0 | W.B.S.E.D.C.LTD (BAGULA C.C.C) | 0.41 | 0 | 0 | 0
2625 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , , SM/09961 | Augmentation | Conversion of IEP to AIRP (Pressure Type) at Garapota W/S Scheme under Hanskhali Block of capacity 120 cum/hr. under augmentation of Garapota W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.05) | 1901/NAD-I | 14/08/2023 | 592 | HARBAUER INDIA PRIVATE LIMITED | 166.14 | 42.92 | 25.83 | 56
2626 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ , SM/09965 | Augmentation | Shifting of UPVC distribution main pipe line from Palagacha more to WTP of Palagacha (Zone-I) W/S Scheme under Chakdah Surface W/S Scheme under Nadia Arsenic Division-I PHE Dte.(sl.no.03) | 1424 / NAD-I | 12/08/2022 | 30 | G.B. CONSTRUCTION | 29.6 | 24.88 | 84.05 | 0
2627 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ , SM/09965 | Augmentation | Water Supply Arrangement in High School, PrimarySchool, SSK & MSK under Jal Jeevan Mission (JJM) atMosra (Zone-III) Kalyani Block under Palagachha (Zone-I) & Mosra (Zone-III) Dist.-Nadia of Surface Water Based PWSS for Chakdah (Part) Surface Water Based Water Supply Scheme of Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte. (sl.no. 07) | 242 / NAD-I | 17/02/2023 | 15 | M/S S.K ENTERPRISE | 10.79 | 9.26 | 85.81 | 60
2628 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ , SM/09965 | Augmentation | Retrofitting work at DD Brick Field at Palagacha in connection with augmentation of Zone-I, Palagacha W/S Scheme under Surface Water Based PWSS for Chakdah (Part) under Jal Jeevan Mission under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte.(sl.03) | 170//AE-II/NAD-I | 27/03/2023 | 21 | K K MARKETING | 4.48 | 4.28 | 95.65 | 0
2629 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ , SM/09965 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-I, (Palagachha), Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 516/NAD-I | 28/03/2022 | 60 | SHYAMAL SHIL | 134.14 | 134.07 | 100 | 100
2630 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ , SM/09965 | Augmentation | Repair of 550 cum capacity Over Head Reservoir Boundary Wall Switch Room and other allied works at Masra (Zone- III) under Chakdah Surface WS Scheme in Chakdah Block under NAD I PHE Dte (Sl.no.09) | 1969 / NAD-I | 14/10/2022 | 60 | RAM KRISHNA CHAKRABORTY | 26.49 | 23.33 | 100 | 100
2631 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ , SM/09965 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Masra (Zone-III), (Part-II) Water Supply Scheme under Chakdah (Part) Surface Water Based W/S Scheme under Nadia Arsenic Division-I, PHE Dte. Sl. No.- 11 | 3329/NAD-I | 15/12/2022 | 45 | KESHOB ENTERPRISE | 28.27 | 27.95 | 100 | 0
2632 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ , SM/09965 | Augmentation | Water Supply Arrangement in High School, Primary School, SSk & MSK under Jal Jeevan Mission (JJM) at Palagachha Zone-I Chakdah Block Palagachha (Zone-I) & Mosra (Zone-III) at Chakdah Block, Dist- Nadia of Surface Water Based PWSS for Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 01) | 33/NAD-I | 17/01/2023 | 15 | SUNIL KUMAR DATTA | 11.95 | 10.98 | 100 | 100
2633 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ , SM/09965 | Augmentation | Supply and installation of Butterfly Valve at Back Wash OHR at Palagachha under JJM under Nadia Arsenic Division-I,P.H.E. Dte. (Sl. No. 01) | 246/AE-II/NAD-I | 18/05/2023 | 7 | SATYABRATA CHAKRABORTY | 2.76 | 2.65 | 100 | 100
2634 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ , SM/09965 | Augmentation | Retrofitting work at RanjanPally, Lalpur and Singher Bagan under Palagacha W/S Scheme under JJM within Chakdah Block under Nadia Arsenic Division-I, PHE Dte. (Sl.no.05) | 2118/NAD-I | 04/09/2023 | 15 | MANAJIT BISWAS | 13.58 | 13.07 | 100 | 100
2635 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ , SM/09965 | Augmentation | Retrofitting works at Balir math and Palagachha (Zone-I) W/S Scheme under Surface Water Based PWSS for Chakdah (Part) water supply scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 09) | 3042/NAD-I | 09/11/2022 | 60 | BUDDHADEV MONDAL | 9.28 | 9.27 | 100 | 100
2636 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ , SM/09965 | Augmentation | Repair of 350 cum capacity Over Head Reservoir Boundary Wall Switch Room and other allied works at Palagacha Zone-I under Chakdah Surface W/S Scheme in Chakdah Block under NAD I PHE Dte (Sl.no.10) | 1597/NAD-I | 06/09/2022 | 45 | M/S PRADIP KUMAR PAL | 12.72 | 12.31 | 100 | 100
2637 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ , SM/09965 | Augmentation | Phase-III FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III (Masra), at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 08) | 3446/NAD-I | 21/12/2022 | 30 | SUMIT GHOSH | 39.83 | 34.06 | 100 | 100
2638 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ , SM/09965 | Augmentation | Retrofitting work for clear water rising main & distribution main at Palagachha Zone-I W/S Scheme in connection with Augmentation of Palagachha (Zone-I) & Masra (Zone-III) under JJM under Nadia Arsenic Division-I , PHE Dte. (Sl. No. 12)" | 1411/NAD-I | 18/05/2023 | 21 | THE TOWER CONSTRUCTION | 36.38 | 30.5 | 100 | 75
2639 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ , SM/09965 | Augmentation | Retrofitting work at Node Point 180 to 180 at Lalpur of Palagacha (Zone-I) W/S Scheme under Chakdah Surface W/S Scheme at Chakdah Block under Jal Jeevan Mission under Nadia Arsenic Division-I, P.H.E. Dte | 376/AE-II/NAD-I | 29/08/2023 | 7 | M/S K..M. ENTERPRISE | 4.71 | 4.29 | 100 | 100
2640 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ , SM/09965 | Augmentation | Retrofittng work at Mahanala due to construction of N.H.-34 road under Palagacha (Zone-I ) within Chakdah Surface W/S Scheme under JJM under Nadia Arsenic Division-I ,PHE Dte. (Sl.no.04) | 2113/NAD-I | 01/09/2023 | 15 | K K MARKETING | 6.82 | 4.77 | 100 | 100
2641 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Construction of Boundary wall with Grill Gate at Joyghata Water Supply Scheme at Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | 102/NACD-II | 10/02/2022 | 45 | BIPLAB GUHA | 6.45 | 6.37 | 98.71 | 100
2642 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Construction of Boundary wall with Grill Gate at Joyghata 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | 51/AE-II/NACD-II | 17/02/2022 | 30 | PARTHA DAS | 4.47 | 4.44 | 99.41 | 100
2643 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Reparing and renovation of inside of OHR at Joyghata Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 67/AE-II/NACD-II | 28/06/2022 | 30 | BIPLAB GUHA | 2.9 | 2.9 | 100 | 100
2644 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Joyghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 269/NACD-II | 22/02/2021 | 21 | SUBHASIS MOJUMDER | 46.67 | 0 | 0 | 100
2645 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and also construction of Soak Pit at Joyghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 738/NACD-II | 13/09/2021 | 45 | CHANDAN ROY | 46.43 | 46.24 | 100 | 100
2646 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Joyghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 869/NACD-II | 08/11/2021 | 45 | USHA CONSTRUCTION | 63.38 | 63.37 | 100 | 100
2647 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Continuation work order for Supply of CIDF Sluice valve and DI specials for vavle to facilitate Functional House Hold Connection of Joyghata Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | 112/AE-II/NACD-II | 10/03/2022 | 5 | MAKALI ENGINEERING CORPORATION | 4.75 | 4.75 | 100 | 100
2648 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Supply of CIDF Sluice valve and DI specials for vavle to facilitate Functional House Hold Connection of Joyghata Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | 108/AE-II/NACD-II | 04/03/2022 | 5 | MAKALI ENGINEERING CORPORATION | 4.89 | 4.89 | 100 | 100
2649 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Functional House Hold Tap Connection for left out Household regarding Har Ghar Jal Certification including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Vill- Ghuguragachhi) Joyghata W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 147/NACD-II | 17/01/2023 | 20 | CHANDRA NATH GHOSH | 3.15 | 0 | 0 | 100
2650 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Joyghata W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1198/NACD-II | 23/12/2022 | 15 | SUBHASIS MOJUMDER | 2.49 | 2.41 | 100 | 100
2651 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Joyghata Water Supply Scheme in Krishnaganj Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 323/1/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.18 | 1.18 | 100 | 100
2652 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Newly added pipeline at Joyghata Piped Water Supply Scheme ( Vill- Joyghata) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 555/AE-I/NACD-II | 10/01/2024 | 15 | BIPLAB GUHA | 0.97 | 0.97 | 100 | 100
2653 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Joyghata Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | 22/AE-II/NACD-II | 15/02/2024 | 15 | SUPRIO MAJUMDER | 0.97 | 0.93 | 100 | 100
2654 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Krishnaganj Block of Nadia District through Jadavpur University. (Name of PWSS Joyghata) | 862/NACD-II | 03/07/2024 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
2655 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Jungle cutting at Mahatpur,Patharghata,Baliadanga,Helenchi Zone-III,Joyghata and Damodarkhali Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 820/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.16 | 0.01 | 100 | 100
2656 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Repair and Renovation work at Joyghata H/W and 2nd Pump house site with Reinforced Barbed Tape , Plaster , Painting and other allied works.Under Nadia Arsenic Division-II,P.H.E.Dte. | 137/AE-II/NACD-II | 11/06/2024 | 30 | PRADIP KUMAR BANIK | 2.97 | 2.96 | 100 | 100
2657 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at 2nd TW site of Joyghata W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 245/AE-II/NACD-II | 31/07/2024 | 15 | SUBHASIS MOJUMDER | 0.85 | 0.85 | 100 | 100
2658 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Joyghata W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 246/AE-II/NACD-II | 31/07/2024 | 15 | SUPRIO MAJUMDER | 0.86 | 0.86 | 100 | 100
2659 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Material Requisition To Resource Division | 984/NACD-II | 23/07/2024 | 0 | Resource Division | 16.59 | 0 | 0 | 0
2660 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Quotation charges and security deposit for new power connection at Joyghata Mini scheme under Eastern Mechanical Subdivision-III, Nadia | BP-174 | 13/12/2024 | 0 | WBSEDCL KARIMPUR CCC | 0.09 | 0 | 0 | 0
2661 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Exigent connection of higher specification components as per IS Code 8329 with its latest version in the mouza in the JL No. 008 at Joyghata Piped Water Supply Scheme under Krishnaganj Development Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 312AE-II/NACD-II | 06/09/2024 | 359 | PAPAN ROY | 3.31 | 0 | 0 | 100
2662 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejuvenation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under JOYGHATA ground water based water supply scheme under Block_ KRISHNAGANJ Dist. - Nadia under EMD, PHE Dte. [SM/09252] | 2684/EMD | 20/11/2024 | 285 | M/S GHOSH ENTERPRISE | 20.24 | 0 | 0 | 100
2663 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED JOYGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09252 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Joyghata Water Supply Scheme of capacity 64 Cu.m/hr under Krishnaganj Block & Jayrampur water Supply Scheme under Karimpur-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | 140/NACD-II | 01/02/2024 | 600 | GHOSH ENTERPRISE | 202.08 | 0 | 0 | 0
2664 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09254 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Sakdaha (Vill- Bhagaban pur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 297./NACD-II | 25/02/2021 | 15 | M/S. ASIT KUMAR BISWAS | 4.67 | 2.14 | 45.89 | 100
2665 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09254 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Sakdaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 734./NACD-II | 13/09/2021 | 45 | M/S K.P. CONSTRUCTION | 50.23 | 50.12 | 99.78 | 100
2666 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09254 | Augmentation | Construction of Boundary wall with Grill Gate at Sakdaha Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | 107/NACD-II | 10/02/2022 | 45 | SAMAR ENTERPRISE | 5.63 | 5.34 | 100 | 100
2667 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09254 | Augmentation | Supply of CIDF Sluice valve and DI specials for vavle to facilitate Functional House Hold Connection of Sakdaha Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | 109/AE-II/NACD-II | 04/03/2022 | 5 | MAKALI ENGINEERING CORPORATION | 4.98 | 4.98 | 100 | 100
2668 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09254 | Augmentation | Continuation work order for Supply of CIDF Sluice valve and DI specials for vavle to facilitate Functional House Hold Connection of Sakdaha Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | 113/AE-II/NACD-II | 10/03/2022 | 5 | MAKALI ENGINEERING CORPORATION | 4.93 | 4.93 | 100 | 100
2669 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09254 | Augmentation | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Sakdaha W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1192/NACD-II | 23/12/2022 | 15 | M/S. ASIT KUMAR BISWAS | 1.33 | 1.27 | 100 | 100
2670 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09254 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SAKDA (Block-Krishnaganj), BAHADURPUR(Block-Tehatt-I), BETBERIA(Block-Chapra) W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 01) | 1507/EMD | 18/04/2023 | 30 | SWAPAN KUMAR BHANJA | 14.69 | 4.88 | 100 | 100
2671 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09254 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Sakdaha Water Supply Scheme in Krishnaganj Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 322_2/AE-I/NACD-II | 13/07/2023 | 7 | RISHAN ENGINEERING CONSULTANCY | 0.71 | 0.71 | 100 | 100
2672 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09254 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Krishnaganj Block of Nadia District through Jadavpur University. (Name of PWSS Sakdaha) | 863/NACD-II | 03/07/2024 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
2673 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09254 | Augmentation | Additional work for the Sakdaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 162/AE-II/NACD-II | 14/06/2024 | 15 | M/S. ASIT KUMAR BISWAS | 0.51 | 0.5 | 100 | 100
2674 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09254 | Augmentation | Repair and Renovation work at Sakdaha H/W and 2nd Pump house site with Reinforced Barbed Tape , Plaster , Painting , and other allied works.Under Nadia Arsenic Division-II,P.H.E.Dte. | 138/AE-II/NACD-II | 11/06/2024 | 201 | BABLU MALLICK | 3.96 | 3.31 | 100 | 100
2675 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09254 | Augmentation | Jungle cutting and Earthwork in filling at Taldaha,Sakdaha and Brittihuda Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 819/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.53 | 0.1 | 100 | 100
2676 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09254 | Augmentation | Providing of Hydraulic Connectivity in the Left out habitations at sakdaha water supply scheme as per IS Code 10500:2012 in the Block of Krishnaganj, Nadia Under Nadia Arsenic Civil Division-II, P.H.E Dte. | 129/AE-II/NACD-II | 10/06/2024 | 15 | SHYAMAL SHIL | 4.85 | 4.81 | 100 | 100
2677 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09254 | Augmentation | Provisioning of Har Ghar Jal an Integral Component of Jal Jeevan Mission with necessary addition and alteration at sakdaha water supply scheme in the Krishnagar Sadar Sub Division, Nadia under Nadia Arsenic Civil Division-II, P.H.E Dte. | 130/AE-II/NACD-II | 10/06/2024 | 15 | SHYAMAL SHIL | 4.83 | 4.81 | 100 | 100
2678 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09254 | Augmentation | Acceptance cum Work Order "Sinking of 2 nos. 300 mm X 200 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at the new proposed sites of Sakdah Zone-I and Zone-II in Krishnaganj Block under Sakdah Public Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. Alternate Site - Thanapara Zone-II 2nd T/w Site, Maliapota, Patharghata." | 570/NACD-II | 08/05/2025 | 135 | B.M. ENGINEERING & CONSTRUCTION | 21.67 | 0 | 0 | 40
2679 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED FATEPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09263 | Augmentation | Construction of Boundary wall with Grill Gate at Fatepur Water Supply Scheme at Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | 101/NACD-II | 10/02/2022 | 45 | CHANDAN ROY | 10.75 | 10.73 | 99.76 | 100
2680 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED FATEPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09263 | Augmentation | Construction of Boundary wall with Grill Gate at Fatepur 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | 38/AE-II/NACD-II | 17/02/2022 | 30 | M/S. ASIT KUMAR BISWAS | 3.19 | 3.16 | 100 | 100
2681 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED FATEPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09263 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Fatepur Water Supply Scheme of capacity 26 Cu.m/hr in Tehatta -I Block under Nadia Arsenic Civil Division -II, PHE Dte." | 186/NACD-II | 09/02/2024 | 60 | MONDAL ENTERPRISE | 111.31 | 0 | 0 | 0
2682 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED FATEPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09263 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC at under FATEPUR W/S Scheme, Block-Hanskhali , Dist. - Nadia. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 10) | 1582/EMD | 24/04/2023 | 30 | PERPETUAL ENTERPRISE | 11.05 | 10.98 | 100 | 100
2683 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED FATEPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09263 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Fatepur Water Supply Scheme in Tehatta_I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 322/1/AE-I/NACD-II | 13/07/2023 | 7 | RISHAN ENGINEERING CONSULTANCY | 0.71 | 0.71 | 100 | 100
2684 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED FATEPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09263 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Fatepur) | 155/NACD-II | 05/02/2024 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
2685 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED FATEPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09263 | Augmentation | Repair and Renovation work at Fatepur H.W site with Reinforced Barbed Tape ,Plaster ,Painting ,Valve Slab, Concreting, and other allied works Under Nadia Arsenic Division-II,P.H.E.Dte | 149./AE-II/NACD-II | 11/06/2024 | 30 | SUJAUDDIN SHAIKH | 4.13 | 4.12 | 100 | 100
2686 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED FATEPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09263 | Augmentation | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Fatepur, Bahadurpur and Gongra Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1657/NACD-II | 30/12/2024 | 360 | CHANDAN ROY | 149.25 | 0 | 0 | 20
2687 | NADIA | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
2688 | NADIA | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
2689 | NADIA | Eastern Mechanical | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Paninala Piped Water Supply Scheme, Block: Dist. Nadia Under EMD, PHE Dte. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.-14) | 6040/EMD | 07/11/2022 | 30 | M/S S.R. ENTERPRISE | 41.38 | 0 | 0 | 0
2690 | NADIA | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement for Tube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Paninala water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | 16/AE-I/NACD-II | 13/04/2022 | 60 | SUMIT GHOSH | 2.83 | 2.81 | 100 | 100
2691 | NADIA | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Paninala water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 203/NACD-II | 05/04/2022 | 60 | SUMIT GHOSH | 5.37 | 5.32 | 100 | 100
2692 | NADIA | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Paninala and Maniknagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 432/NACD-II | 07/07/2022 | 60 | JOY HIND TUBEWELLS | 43.35 | 20.3 | 100 | 100
2693 | NADIA | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Paninala Water Supply Scheme of Krishnagar-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 620/NACD-II | 06/09/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.94 | 3.94 | 100 | 100
2694 | NADIA | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Paninala Water Supply Scheme at Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | 82/NACD-II | 10/01/2023 | 60 | ZOOM CONSTRUCTION & INTERIO | 17.3 | 17.29 | 100 | 85
2695 | NADIA | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Krishnagar-I Block of Nadia District through Jadavpur University. (Name of PWSS Paninala) | 889/NACD-II | 18/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
2696 | NADIA | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Hridaypur) | 892/NACD-II | 21/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 0 | 0 | 100
2697 | NADIA | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Material Requisition To Resource Division | 401/NACD-II | 04/07/2022 | 0 | Resource Division | 55.85 | 0 | 0 | 0
2698 | NADIA | Eastern Mechanical | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | New service connection charges for Paninala Ph. 1 J1-43 kh-1378 | 140/PFMS/EMD | 06/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.64 | 0 | 0 | 0
2699 | NADIA | Eastern Mechanical | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | New service connection charges for Paninala Ph. 2 J1-43 kh-950 | 141/PFMS/EMD | 06/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.69 | 0 | 0 | 0
2700 | NADIA | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Paninala 2nd Tubewell site within Paninala Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 120/NACD-II | 11/01/2023 | 60 | SREE GURU ENTERPRISE | 5.14 | 3.54 | 68.95 | 65
2701 | NADIA | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 31 cum/Hour capacity for Paninala Water Supply Scheme within Krishnagar-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1145/NACD-II | 23/08/2024 | 180 | MAMATA USHA ENTERPRISE | 160.26 | 0 | 0 | 0
2702 | NADIA | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Laying of Rising Main of Paninala Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. (Sl. No. 02) | 221/NACD-II | 05/04/2022 | 30 | TAPAS GHOSH | 5.64 | 5.63 | 100 | 100
2703 | NADIA | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Paninala and adjoining mouzas under Paninala Water Supply Scheme of Krishnagar-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | 376/NACD-II | 22/06/2022 | 90 | KINGS & CO. | 242.52 | 163.21 | 100 | 90
2704 | NADIA | Eastern Mechanical | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Headworks) under Paninala W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. NNo.- 07) | 5015/EMD | 03/11/2022 | 30 | HARA PROSAD DAS | 10.11 | 9.97 | 100 | 100
2705 | NADIA | Eastern Mechanical | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Paninala W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 08) | 5016/EMD | 03/11/2022 | 30 | NEW RANBEE ENGINEERING | 10.13 | 9.93 | 100 | 90
2706 | NADIA | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Earth work in filling in ditches and Drum Sheet Walling at Paninala Water Supply Scheme under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1070/NACD-II | 08/12/2022 | 30 | TAPAS GHOSH | 16.37 | 16.3 | 100 | 100
2707 | NADIA | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Construction for priliminary work of the approch road at Head Works site of Paninala Water Supply Scheme in Krishnagar-1 Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | 515/AE-I/NACD-II | 18/12/2023 | 15 | M/S GHOSH CONSTRUCTION | 0.97 | 0.96 | 100 | 100
2708 | NADIA | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Construction of a single Storied Warehouse with Steel Truss Roof at Paninala Water Supply Scheme Head Work Site under Nadia Arsenic Civil Division-II, PHE Dte. | 325/NACD-II | 04/03/2024 | 540 | AMIT KARMAKAR | 40.55 | 0 | 0 | 60
2709 | NADIA | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME , SM/10403 | New | Conversion of IEP to AIRP at KADIPUR Water Supply Scheme of capacity 55 Cu.m/hr in Krishnaganj Block & CHANDERGHAT, PANINALA & BARUIHUDA Water Supply Scheme under Nadia Arsenic Civil Division -II, PHE Dte. | 1147/NACD-II | 23/08/2024 | 60 | MERCURY ENGINEERING COMPANY. | 173.69 | 0 | 0 | 0
2710 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09685 | Retrofitting | Preparation of DPR for augmentation of existing Barnia, (Block -Tehatta-II) piped water supply schemes | 148/AE-I/NACD-II | 16/11/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 3.63 | 3.63 | 100 | 100
2711 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09685 | Retrofitting | Preparation of DPR for augmentation of existing Barnia (Phase-II), (Block -Tehatta-II) piped water supply schemes | 751/NACD-II | 15/09/2021 | 10 | SIRCON ENGINEERING SERVICE | 4.73 | 4.73 | 100 | 100
2712 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09685 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair and also DI Laying in distribution at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 993/NACD-II | 30/12/2021 | 45 | J.D.J. ENTERPRISE | 98.17 | 78.66 | 100 | 100
2713 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09685 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 275/EE/NACD-II | 22/02/2021 | 21 | USHA CONSTRUCTION | 51.53 | 0 | 0 | 100
2714 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09685 | Retrofitting | Restoration by UPVC Pipeline for replacing the damaged pipeline at Barnia Bazar and also construction of RCC slab for at Barnia Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 135/AE-I/NACD-II | 28/10/2021 | 15 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 3.21 | 3.2 | 100 | 100
2715 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09685 | Retrofitting | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Barnia (Village- Charakpota) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 824/NACD-II | 25/10/2021 | 45 | JOY HIND TUBEWELLS | 68.53 | 68.53 | 100 | 100
2716 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09685 | Retrofitting | Supply of CIDF Sluice, Non return valves and DI Mechanical collar Vavle for relaying of rising main of Barnia Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | 165/AE-I/NACD-II | 22/11/2021 | 7 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.97 | 4.97 | 100 | 100
2717 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09685 | Retrofitting | Continuation work order for for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 850/NACD-II | 02/11/2021 | 45 | JOY HIND TUBEWELLS | 73.72 | 73.72 | 100 | 100
2718 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09685 | Retrofitting | Relaying of D.I. Pipeline replacing the damaged old UPVC Pipe at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division -II, PHE Dte. | 98/NACD-II | 10/02/2022 | 45 | PRABIR KUMAR ROY | 14.31 | 13.74 | 100 | 100
2719 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09685 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | 982/EE/NACD-II | 27/12/2021 | 45 | M/S. R.K.ENTERPRISE | 152.25 | 14.58 | 96.59 | 100
2720 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Patharghata water supply scheme (Phase-II) under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09696 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Patharghata (Vill- Gabindapur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 994/NACD-II | 30/12/2021 | 45 | MALLICK ENTERPRISE | 46 | 45.98 | 99.95 | 100
2721 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Patharghata water supply scheme (Phase-II) under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09696 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Patharghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-Il, P,H.E. Dte." | 126/NACD-II | 21/02/2022 | 90 | J.D. CONSTRUCTION | 106.8 | 106.79 | 100 | 100
2722 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Patharghata water supply scheme (Phase-II) under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09696 | Retrofitting | Jungle cutting at Mahatpur,Patharghata,Baliadanga,Helenchi Zone-III,Joyghata and Damodarkhali Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 820/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.16 | 0.02 | 100 | 100
2723 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Patharghata water supply scheme (Phase-II) under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09696 | Retrofitting | Laying of distribution system and also dedicated pipe line including providing FHTC at left out households for Patharghata (Gobindapur, Patharghata) & Puthimari (Vill-Puthimari) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 247/NACD-II | 27/02/2025 | 180 | SANDIP BISWAS | 101.71 | 0 | 0 | 0
2724 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAGAR (Rural) to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10440 | Augmentation | Emergent laying of UPVC pipe 90mm Dia and 110mm Dia on Baikuntha sarak from 2no Pumphouse to khayaghat para due to existing pipeline damaged at the time of construction of PMGSY road and Providing FHTC from Krishnagar Rural water supply Scheme under Krishnagar Sub-Division P.H.E Dte under Nadia Division P.H.E Dte | 245/KSD | 11/03/2022 | 7 | GOUTAM HALDER | 4.98 | 4.97 | 100 | 100
2725 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAGAR (Rural) to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10440 | Augmentation | Material Requisition To Resource Division | 4929/ND | 25/11/2022 | 0 | Resource Division | 36.28 | 0 | 0 | 0
2726 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAGAR (Rural) to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10440 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAGAR (Rural) to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | 20/PFMS | 20/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.51 | 0 | 0 | 0
2727 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAGAR (Rural) to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10440 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for JJM works for the period 90 days w.e.f. 01/04/2023.(as and when required). | 376/KSD | 28/03/2023 | 90 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 0
2728 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAGAR (Rural) to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10440 | Augmentation | Material Requisition To Resource Division | 2289/ND | 29/05/2023 | 0 | Resource Division | 22.96 | 0 | 0 | 0
2729 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAGAR (Rural) to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10440 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 450 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of 450 CUM OHR all complete for Augmentation of Ground Based Water Supply Scheme at Krishnagar Rural to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 4413/ND | 14/10/2022 | 1083 | DAFFODIL | 488.87 | 293.09 | 59.95 | 70
2730 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAGAR (Rural) to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10440 | Augmentation | Providing, installation and commissioning of Electro-Mechanical Equipments and allied works for submersible pumping machinery of Pump House No.-I and II for Augumentation Tube Well and Arsenic Removal Plant in connection to Accommodate FHTC under Krishnagar(Rural) ground water based water supply scheme under Block_ Krishnanagar-I Dist. - Nadia under EMD, PHE Dte. [SM/10440] | 2154/EMD | 30/08/2024 | 30 | HARA PROSAD DAS | 48.83 | 0 | 0 | 0
2731 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAGAR (Rural) to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10440 | Augmentation | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Krishnagar Rural Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 151/ND | 09/01/2024 | 60 | MONDAL ENTERPRISE | 12.12 | 12.03 | 100 | 100
2732 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAGAR (Rural) to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10440 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab for official use for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for JJM works for the period 90 days w.e.f. 01.01.2023 (as and when required). | 1331/KSD | 29/12/2022 | 90 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 100
2733 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAGAR (Rural) to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10440 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 86 m3/hr at Krishnagar Rural Water Supply Scheme within Krishnagar-I Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | 1896/ND | 15/03/2024 | 540 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 234.28 | 0 | 0 | 70
2734 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAGAR (Rural) to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/10440 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
2735 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA , SM/10517 | Augmentation | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA | 19/PFMS | 20/05/2022 | 0 | HORIZEN | 2.67 | 0 | 0 | 0
2736 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA , SM/10517 | Augmentation | Material Requisition To Resource Division | 4276/ND | 29/09/2022 | 0 | Resource Division | 7.53 | 0 | 0 | 0
2737 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA , SM/10517 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BANPUR W/S Scheme, Block- Krishnaganj, ARABPUR W/S Scheme, Block-Karimpur, BHIMPUR W/S Scheme, Block-Krishnagar AND MONIPOTA W/S Scheme, Block- Krishnagar-I, Dist. - Nadia. | 5127/EMD | 04/09/2023 | 666 | C.M.S. ENGINEERING CONCERN. | 70.97 | 7.19 | 85.13 | 12
2738 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA , SM/10517 | Augmentation | Laying of additional pipeline for Fazilnagar Mouza and Phulkhali Mouza under Fazilnagar PWSS and Arabpur PWSS".under Tehatta Sub-Division under Nadia Division P.H.Engineering Dte. | 4905/ND | 10/09/2024 | 90 | PATHIK PABAN NANDI | 41.67 | 0 | 0 | 0
2739 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA , SM/10517 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Arabpur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 3817/ND | 05/09/2022 | 90 | BIDYUT KUMAR | 129.72 | 123.6 | 95.28 | 98
2740 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA , SM/10517 | Augmentation | Laying of additional pipeline for Arabpur PWSS"under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 4532/ND | 20/08/2024 | 180 | BIDYUT KUMAR | 12.99 | 0 | 0 | 100
2741 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA , SM/10517 | Augmentation | Laying of additional pipeline for Hazrakhali, Fulkhali, Betbaria, Marttajapur, Mollahad, Chaugachha, Haripur & Arabpur mouzas under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 246/ND | 14/01/2025 | 270 | JOY HIND TUBEWELL'S | 153.86 | 0 | 0 | 30
2742 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA , SM/10517 | Augmentation | Laying of additional pipeline for providing balance FHTC and inerease functionality in Baro Jangal, Majlishpur, Basotipara Villages under Karimpur-I Block under Tehatta Sub-Division under Nadia Division, PHE Dte. | .4686/4533/P-3/ND | 09/10/2025 | 90 | JOY HIND TUBEWELL'S | 79.19 | 0 | 0 | 0
2743 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10518 | Augmentation | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | 24/PFMS | 20/05/2022 | 0 | ENVIROTECH SOLUTIONS | 2.43 | 0 | 0 | 0
2744 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10518 | Augmentation | Material Requisition To Resource Division | 4324/ND | 29/09/2022 | 0 | Resource Division | 2.3 | 0 | 0 | 0
2745 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10518 | Augmentation | Material Requisition To Resource Division | 3898/ND | 08/09/2022 | 0 | Resource Division | 18.84 | 0 | 0 | 0
2746 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10518 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20 mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Teinpur Zone-IV to accommodate FHTC within Karimpur-II block under RWS Sub-Divn under Nadia Divn, PHE Dte. | 3381/ND | 29/07/2022 | 90 | CHOWDHURY & CO. | 71.97 | 70.03 | 100 | 100
2747 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10518 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under TEINPUR (ZONE-I ,II, III & IV) W/S Scheme, Block- Karimpur-II , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 06) | 500/EMD | 24/01/2023 | 30 | M/S DILIP MITRA | 64.62 | 10.18 | 100 | 85
2748 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10518 | Augmentation | Renovation and modification of AIRP (Pressure Type) of capacity 20.87 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site in Teinpur Zone IV PWSS under Nadia Division PHE Dte. | 1807/ND | 24/04/2023 | 547 | MONDAL PRECISION PRIVATE LIMITED | 39.12 | 6.58 | 52.26 | 90
2749 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10518 | Augmentation | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Teinpur Zone-IV PWSS within Karimpur-II Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 3260/ND | 10/06/2024 | 450 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 82.42 | 0 | 0 | 80
2750 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09264 | Augmentation | Construction of Boundary wall with Grill Gate at Krishnagar Water Supply Scheme at Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | 103/NACD-II | 10/02/2022 | 45 | DEBASISH DEY | 12.04 | 11.96 | 99.37 | 100
2751 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09264 | Augmentation | Upgradation of D.G panel Board of NACD-II office building from 40 KVA to 63.5 KVA at Krishnagar under Nadia Arsenic Civil Division-II P.H.E. Dte. | 217/AE-I/NACD-II | 01/02/2022 | 7 | ABHISEK ENGINEERING CONCERN | 4.78 | 4.78 | 100 | 100
2752 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09264 | Augmentation | Earth work in filling at H/W site of Krishnagar ( Eastern site) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 233/AE-I/NACD-II | 17/02/2022 | 7 | CHANDAN ROY | 4.95 | 4.94 | 99.72 | 100
2753 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09264 | Augmentation | Earth work in filling at H/W site of Krishnagar (Western site) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 234/AE-I/NACD-II | 17/02/2022 | 7 | PAPAN ROY | 4.98 | 4.97 | 99.79 | 100
2754 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09264 | Augmentation | Continuation work order for Earth work in filling at H/W site of Krishnagar ( Eastern site) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 306/AE-I/NACD-II | 23/03/2022 | 7 | CHANDAN ROY | 4.95 | 4.94 | 99.79 | 100
2755 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09264 | Augmentation | Continuation work order for Earth work in filling at H/W site of Krishnagar (Western site) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 307/AE-I/NACD-II | 23/03/2022 | 7 | PAPAN ROY | 4.96 | 4.96 | 99.87 | 100
2756 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09264 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged pipeline repair) at Krishnagar & Bahadurpur (Vill- Krishnagar, Chak Chilakhali) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 08/NACD-II | 04/01/2022 | 45 | MITRA CONSTRUCTION | 34.08 | 34.06 | 100 | 100
2757 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09264 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged pipe line repair) at Krishnagar & Bahadurpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 948/NACD-II | 09/12/2021 | 45 | MITRA CONSTRUCTION | 45.4 | 0 | 0 | 100
2758 | NADIA | Central Drilling | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09264 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KRISHNAGAR W/S SCH, UNDER NADIA DISTRICT, CDD, PHE DTE. | 509/CMSD-II | 11/11/2022 | 7 | M/S SAIKAT ENTERPRISE | 0.98 | 0.75 | 100 | 0
2759 | NADIA | Central Drilling | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09264 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR KRISHNAGAR W/S SCH, UNDER NADIA DISTRICT, CDD, PHE DTE. | 1195/CDD | 11/11/2022 | 30 | M/S SAIKAT ENTERPRISE | 10.22 | 9.44 | 100 | 0
2760 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09264 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-II Block of Nadia District through Jadavpur University. (Name of PWSS Krishnagar) | 1147/NACD-II | 10/10/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
2761 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09264 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Krishnagar Water Supply Scheme in Tehatta-II Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 324_2/AE-I/NACD-II | 13/07/2023 | 7 | RISHAN ENGINEERING CONSULTANCY | 0.61 | 0.57 | 100 | 100
2762 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09264 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) of Ramchandrapur habitation at Krishnanagar W/s Scheme at Tehatta-2 Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 641/AE-I/NACD-II | 12/02/2024 | 15 | TAPAN SAHA | 0.91 | 0.85 | 100 | 100
2763 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09264 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) of Pascim Para , Ramchandrapur Ghat habitation at Krishnanagar W/s Scheme at Tehatta-2 Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 642/AE-I/NACD-II | 12/02/2024 | 15 | PRITI ENTERPRISE | 0.93 | 0.9 | 100 | 100
2764 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09264 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) of Muslim Para habitation at Krishnanagar W/s Scheme at Tehatta-2 Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 643/AE-I/NACD-II | 12/02/2024 | 15 | PRITI ENTERPRISE | 0.9 | 0.89 | 100 | 100
2765 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09264 | Augmentation | Conversion of IEP to AIRP at Krishnagar Water Supply Scheme of capacity 21 Cu.m/hr in Tehatta-II Block under Nadia Arsenic Civil Division -II, PHE Dte. | 1125/NACD-II | 21/08/2024 | 299 | BIPLAB GUHA | 85.92 | 0 | 0 | 60
2766 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09264 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) of Purba Para habitation at Krishnanagar W/s Scheme at Tehatta-2 Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 640/AE-I/NACD-II | 12/02/2024 | 15 | BABLU MALLICK | 0.96 | 0 | 0 | 0
2767 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09264 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I/II, under Krishnanagar ground water based water supply scheme under Block_ Tehatta-II Dist. - Nadia under EMD, PHE Dte. [SM/09264] | 693/EMD | 04/04/2025 | 30 | JOYSHREE CONCERN | 13.82 | 0 | 0 | 0
2768 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09267 | Augmentation | Construction of Boundary wall with Grill Gate at Patharghata Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | 53/AE-II/NACD-II | 17/02/2022 | 30 | SURAJIT KUMAR GHOSH | 4.26 | 4.25 | 99.81 | 100
2769 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09267 | Augmentation | Damaged pipe line repair and piling work at Patharghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 37/AE-II/NACD-II | 17/02/2022 | 30 | SAHA ENGINEERS | 4.69 | 4.69 | 99.92 | 100
2770 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09267 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Patharghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 528/NACD-II | 14/06/2021 | 45 | M/S K.P. CONSTRUCTION | 47.57 | 32.75 | 100 | 0
2771 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09267 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and also construction of Steps with earth filling at Patharghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 872/NACD-II | 08/11/2021 | 45 | SANDIP BISWAS | 75.41 | 75.37 | 100 | 100
2772 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09267 | Augmentation | Preparation of DPR for augmentation of existing Patharghata (Phase-II), (Block -Tehatta-I) piped water supply schemes | 758/NACD-II | 16/09/2021 | 10 | SIRCON ENGINEERING SERVICE | 4.64 | 4.64 | 100 | 100
2773 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09267 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Patharghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-Il, P,H.E. Dte." | 126/NACD-II | 21/02/2022 | 90 | J.D. CONSTRUCTION | 106.8 | 0 | 0 | 100
2774 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09267 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SHYAMNAGAR(Block-Krishnaganj), MOBARAKPUR(Block-Tehatt-I), PATHARGHAT(Block-Tehatt-I) W/S Scheme, Dist. - Nadia. | 1505/EMD. | 18/04/2023 | 30 | DIPALI CONSTRUCTION | 19.37 | 6.41 | 100 | 80
2775 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09267 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Patherghata) | 1297/NACD-II | 29/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
2776 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09267 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Patharghata W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 527/AE-I/NACD-II | 18/12/2023 | 15 | TOTAN DAS | 0.97 | 0 | 0 | 0
2777 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09267 | Augmentation | Continuation work order Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-I, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal. (From 01/04/2024 to 30/06/2024) | 505/NACD-II | 01/04/2024 | 91 | BABLU KUMAR SINGH | 1.24 | 1.15 | 92.57 | 0
2778 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09267 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I , II Zone-I under Rajapura ground water based water supply scheme under Block_ Sandeshkhali-I Dist. - North 24PGS under EMD, PHE Dte. WBPHED/EE/EMD/NIeT-37 of 2023-24 (Sl no. 12) | 944/EMD | 18/03/2024 | 30 | PADMA ENGINEERING CO. | 25.48 | 0 | 0 | 0
2779 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09267 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-I, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal | 413/NACD-II | 30/03/2023 | 366 | BABLU KUMAR SINGH | 4.98 | 0.38 | 7.53 | 0
2780 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09267 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Patharghata Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1254/NACD-II | 08/11/2023 | 30 | SAHA ENGINEERS | 20.63 | 12.83 | 100 | 100
2781 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09267 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-I, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal | 413/NACD-II | 30/03/2023 | 366 | BABLU KUMAR SINGH | 4.98 | 3.97 | 100 | 60
2782 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09267 | Augmentation | Conversion of IEP to AIRP at Patharghata Water Supply Scheme of capacity 96 Cu.m/hr in Tehatta - I Block under Nadia Arsenic Civil Division -II, PHE Dte. | 1396/NACD-II | 22/10/2024 | 360 | JOY HIND TUBEWELLS | 258.38 | 0 | 0 | 0
2783 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09267 | Augmentation | Laying of distribution system and also dedicated pipe line including providing FHTC at left out households for Patharghata (Gobindapur, Patharghata) & Puthimari (Vill-Puthimari) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 247/NACD-II | 27/02/2025 | 180 | SANDIP BISWAS | 101.71 | 0 | 0 | 0
2784 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MAIDANPUR PWSS BLOCK: CHAPRA DISTRICT: NADIA , SM/10572 | Augmentation | Survey , Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household under Maidanpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Sl.No. 02) | 905/KSD | 29/11/2021 | 15 | HORIZEN | 3.2 | 2.61 | 100 | 93
2785 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MAIDANPUR PWSS BLOCK: CHAPRA DISTRICT: NADIA , SM/10572 | Augmentation | Material Requisition To Resource Division | 127/ND | 05/01/2023 | 0 | Resource Division | 11.98 | 0 | 0 | 0
2786 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MAIDANPUR PWSS BLOCK: CHAPRA DISTRICT: NADIA , SM/10572 | Augmentation | Material Requisition To Resource Division | 2320/ND | 29/05/2023 | 0 | Resource Division | 13.63 | 0 | 0 | 0
2787 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MAIDANPUR PWSS BLOCK: CHAPRA DISTRICT: NADIA , SM/10572 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 50 m3/hr at Maidanpur Water Supply Scheme within Chapra Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | 1893/ND | 15/03/2024 | 180 | MERCURY ENGINEERING COMPANY | 184.37 | 0 | 0 | 0
2788 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MAIDANPUR PWSS BLOCK: CHAPRA DISTRICT: NADIA , SM/10572 | Augmentation | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Maidanpur Water Supply Scheme within Chapra block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 157/ND | 09/01/2024 | 60 | M/S S.K. ENTERPRISE | 18.07 | 16.13 | 100 | 90
2789 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MAIDANPUR PWSS BLOCK: CHAPRA DISTRICT: NADIA , SM/10572 | Augmentation | Laying distribution system [LDS] for providing Functional Household Tap Connection (FHTC), Rising main with Inter-Connection in between Tube wells including specials and valves, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials and Soil Investigation for Construction of One No. 300 Cum OHR of Staging Height 20 Mtr. by Augmentation for Maidanpur Piped Water Supply Scheme within Chapra Block under Krishnagar Sub Divn. under Nadia Divn. PHE Dte. in the District of Nadia. | 479/ND | 02/02/2023 | 850 | JOY HIND TUBEWELL'S | 332.37 | 188.33 | 56.66 | 80
2790 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR MAIDANPUR PWSS BLOCK: CHAPRA DISTRICT: NADIA , SM/10572 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under KARIMPUR JALANGI(Z-8) W/S Scheme, Block- Karimpur II, PALSONDHA W/S Scheme, Block- Tehatta II, & MAIDANPUR W/S Scheme, Block- Chapra, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 06) | 1179/EMD | 21/03/2023 | 940 | CREATIVE WATER & PROCESS TECHNOLOGIES PVT. LTD. | 77.9 | 0 | 0 | 85
2791 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MAIDANPUR PWSS BLOCK: CHAPRA DISTRICT: NADIA , SM/10572 | Augmentation | Laying of dedicated pipeline for Pipragachhi and part of Elangi Mouza for augmentation of Elangi Water Supply Scheme in Chapra Block, Nadia under Nadia Division PHE Dte. | 1773/ND | 21/04/2025 | 180 | TULIP ENGINEER'S CO-OP SOCIETY LTD | 86.27 | 0 | 0 | 0
2792 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11512 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Karimpur-Jalangi Z-9B W/S Scheme in Karimpur-II Block of Nadia District under Nadia Division, P.H.E. Dte. | 319/TSD | 24/11/2021 | 30 | RADIANT | 2.42 | 2.42 | 100 | 100
2793 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11512 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KARIMPUR JALANGI (Z-IX B) W/S Scheme, Block-Karimpur II , Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No. 05) | 1180/EMD | 21/03/2023 | 30 | MA ANNAPURNA ENTERPRISE | 12.87 | 11 | 100 | 10
2794 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11512 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under Karimpur jalangi (Zone-IX,A & B) W/S Scheme, Block-Tehatta-II, Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 19) | 419EMD | 20/01/2023 | 30 | SINHA ELECTRICALS | 14.88 | 1.34 | 100 | 85
2795 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11512 | Augmentation | Material Requisition To Resource Division | 1902/ND | 27/04/2023 | 0 | Resource Division | 18.83 | 0 | 0 | 0
2796 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11512 | Augmentation | Sinking of 01 no Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at Karimpur Jalangi PWSS Zone-IX(B) Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | 1098/ND | 19/02/2024 | 270 | BUDDHADEV MONDAL | 17.38 | 0 | 0 | 100
2797 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11512 | Augmentation | Construction of barbed wire fencing with concrete pillars at Karimpur-Jalangi Zone-IX(B). water supply scheme (New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . | 1121/TSD | 21/02/2024 | 7 | NIVEDITA CONSTRUCTION | 1.51 | 1.35 | 100 | 100
2798 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11512 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction Of 200 Cum Capacity 20 Mtr. Height RCC Over Head Reservoir (without pile foundation), Pipe Connection and cost of Pipes, Specials and Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of cum. O.H.R. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-IXB to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 965/ND | 09/03/2023 | 1030 | SHYAMAL SHIL, PALLISREE, P.O.KRISHNAGAR, DIST- NADIA,PIN-741101 | 175.66 | 42.49 | 24.19 | 45
2799 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11512 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangement and Construction of Boundary wall at Head Work Site at Karimpur - Jalangi (IX-B )Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | 1632/ND | 07/03/2024 | 506 | MONDAL ENTERPRISE | 23.85 | 9.92 | 41.59 | 15
2800 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11512 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 26.25 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-IX B to accommodate FHTC within Karimpur-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | 7105/ND | 06/12/2024 | 360 | JOY HIND TUBEWELL'S | 151.86 | 0 | 0 | 0
2801 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11829 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 1B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 116/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.79 | 3.76 | 100 | 100
2802 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11829 | Augmentation | Material Requisition To Resource Division | 113/ND | 05/01/2023 | 0 | Resource Division | 297.54 | 0 | 0 | 0
2803 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11829 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
2804 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11829 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 719.98 | 85.78 | 47
2805 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11833 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 7A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 128/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.32 | 4.18 | 100 | 100
2806 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11833 | Augmentation | Material Requisition To Resource Division | 77/ND | 05/01/2023 | 0 | Resource Division | 126.75 | 0 | 0 | 0
2807 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11833 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 197 | 29.08 | 47
2808 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11833 | Augmentation | Additional Work for Ground Improvement of OHR foundation, renovation of OHR & other allied works of Northern Sector Part-I, Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 6095/ND | 19/09/2024 | 240 | UMWELT ENGINEER PVT LTD | 225.66 | 0 | 0 | 75
2809 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12375 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 7/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 153/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.32 | 4.27 | 100 | 100
2810 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12375 | Augmentation | Material Requisition To Resource Division | 79/ND | 05/01/2023 | 0 | Resource Division | 870.46 | 0 | 0 | 0
2811 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12375 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
2812 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12375 | Augmentation | Material Requisition To Resource Division | 233/ND | 11/01/2024 | 0 | Resource Division | 8.75 | 0 | 0 | 0
2813 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12375 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- VII/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4282/ND | 21/09/2023 | 534 | SATYABRATA CHAKRABORTY | 397.18 | 116.24 | 46.86 | 14
2814 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12375 | Augmentation | Construction of OHR, staff room, chlorine room, service road, boundary wall and restoration of bituminous road, land improvement etc. of Surface Water Based Water Supply Scheme for Zone-VII / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. | 212/ND | 10/01/2024 | 730 | PRASUN ENTERPRISE | 262.05 | 0 | 0 | 5
2815 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12375 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 5.92 | 98.73 | 30
2816 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12375 | Augmentation | Laying of additional upvc pipeline and installation of sluice valves at Zone -7A of Surface water based water supply scheme Northern Sector in Nadia District, Part- II under Debagram Sub- Division undrer Nadia Division ,PHE Dte. | 3261/ND | 10/06/2024 | 363 | MINTU CHAKRABORTY | 96.03 | 0 | 0 | 4
2817 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12375 | Augmentation | Additional Work for Installation of SCADA System in connection with Augmentation of Surface Water Based Piped Water Supply Scheme for Northern Sector Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 3447/ND | 23/07/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 732.35 | 0 | 0 | 15
2818 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11845 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 7/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 152/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.47 | 4.44 | 100 | 100
2819 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11845 | Augmentation | Material Requisition To Resource Division | 78/ND | 05/01/2023 | 0 | Resource Division | 168.95 | 0 | 0 | 0
2820 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11845 | Augmentation | Material Requisition To Resource Division | 241/ND | 11/01/2024 | 0 | Resource Division | 6.45 | 0 | 0 | 0
2821 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11845 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- VII/A (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4279/ND | 21/09/2023 | 638 | MINTU CHAKRABORTY | 476.23 | 178.65 | 37.51 | 24
2822 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11845 | Augmentation | Laying of additional upvc pipeline and installation of sluice valves at Zone -7A of Surface water based water supply scheme Northern Sector in Nadia District, Part- II under Debagram Sub- Division undrer Nadia Division ,PHE Dte. | 3261/ND | 10/06/2024 | 363 | MINTU CHAKRABORTY | 96.03 | 0 | 0 | 4
2823 | NADIA | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
2824 | NADIA | Eastern Mechanical | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | New connection charges for Kanainagra PHE II | 107/PFMS/EMD | 16/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.57 | 0 | 0 | 0
2825 | NADIA | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
2826 | NADIA | Eastern Mechanical | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | New connection charges for Kanainagra PHE I | 106/PFMS/EMD | 16/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.95 | 0 | 0 | 0
2827 | NADIA | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Kanainagar Water Supply Scheme Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | 85/NACD-II | 10/01/2023 | 60 | SUMIT GHOSH | 14.7 | 11.76 | 80.01 | 85
2828 | NADIA | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Kanainagar water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | 12/AE-II/NACD-II | 11/04/2022 | 60 | A.K ADHIKARY | 2.83 | 2.81 | 100 | 100
2829 | NADIA | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Kanainagar water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 207/NACD-II | 05/04/2022 | 60 | A.K ADHIKARY | 5.37 | 5.35 | 100 | 100
2830 | NADIA | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Kanainagar and Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 244/NACD-II | 19/04/2022 | 60 | B.M. ENGINEERING & CONSTRUCTION | 42.4 | 38.44 | 100 | 100
2831 | NADIA | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Kanainagar Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 627/NACD-II | 06/09/2022 | 20 | MAKALI ENGINEERING CORPORATION | 4.94 | 4.94 | 100 | 100
2832 | NADIA | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Kanainagar 2nd Tubewell Site within Kanainagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 124/NACD-II | 11/01/2023 | 60 | CHINMOY BISWAS | 5.66 | 5.36 | 100 | 85
2833 | NADIA | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Material Requisition To Resource Division | 409/NACD-II | 04/07/2022 | 0 | Resource Division | 51.88 | 0 | 0 | 0
2834 | NADIA | Eastern Mechanical | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Electriciyy bill pay for the new service connection at Kanaigar PHE II | 153/PFMS/EMD | 13/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.76 | 0 | 0 | 0
2835 | NADIA | Eastern Mechanical | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Electriciyy bill pay for the new service connection at Kanaigar PHE I | 154/PFMS/EMD | 13/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.63 | 0 | 0 | 0
2836 | NADIA | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Laying of Rising Main of Kanainagar Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | 20/AE-II/NACD-II | 18/04/2022 | 30 | CHINMOY BISWAS | 4.98 | 4.96 | 100 | 100
2837 | NADIA | Eastern Mechanical | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) under Kanainagar W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No.- 21 of EE/EMD of 2022-23 (Sl. No.- 03) | 6370/EMD | 23/11/2022 | 30 | S.R. CONCERN | 10.05 | 9.96 | 100 | 100
2838 | NADIA | Eastern Mechanical | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.II under Kanainagar W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 04) | 6262/EMD | 19/11/2022 | 30 | TARUN KUMAR BHATTACHARYA | 10.05 | 9.89 | 100 | 100
2839 | NADIA | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Construction of approch road at Head Works site of Kanainagar Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | 415/AE-I/NACD-II | 08/08/2023 | 15 | B.M. ENGINEERING & CONSTRUCTION | 0.97 | 0.97 | 100 | 100
2840 | NADIA | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Kanainagar and Dhopahat PWSS in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 296_AE-II/NACD-II | 30/08/2024 | 20 | MAKALI ENGINEERING CORPORATION | 4.81 | 4.81 | 100 | 100
2841 | NADIA | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Bagakhali Zone-I and Bagakhali Zone-II Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1562/NACD-II | 05/12/2024 | 360 | DEBASIS SAMADDAR | 157.57 | 0 | 0 | 40
2842 | NADIA | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Fatepur, Bahadurpur and Gongra Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1657/NACD-II | 30/12/2024 | 360 | CHANDAN ROY | 149.25 | 0 | 0 | 20
2843 | NADIA | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 54 cum/Hour capacity for Kanainagar Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 165/NACD-II | 06/02/2025 | 180 | TARUN KUMAR BHATTACHARYA | 186.86 | 0 | 0 | 0
2844 | NADIA | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Kanainagar and adjoining mouzas under Kanainagar Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | 340/NACD-II | 03/06/2022 | 1064 | B.M. ENGINEERING & CONSTRUCTION | 285.26 | 235.34 | 82.55 | 90
2845 | NADIA | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME , SM/10406 | New | Construction of 350 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Kanainagar water supply scheme of Tehatta-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | 370/NACD-II | 23/03/2023 | 740 | B.M. ENGINEERING & CONSTRUCTION | 143.29 | 108.55 | 75.89 | 35
2846 | NADIA | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
2847 | NADIA | Eastern Mechanical | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | New connection charges for Swaruppur PHE I Tehatta Nadia. Memo no. 3004031081/Quot/03 |  | 21/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.1 | 0 | 0 | 0
2848 | NADIA | Eastern Mechanical | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | New Service Connection for Pump House -I under Suruppur W/S Scheme at Tehatta Nadia | 93/EMD | 26/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.1 | 0 | 0 | 0
2849 | NADIA | Eastern Mechanical | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | New connection charges for Swaruppur PHE I Tehatta Nadia. Memo no. 3004031086/Quot/03 |  | 21/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.23 | 0 | 0 | 0
2850 | NADIA | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
2851 | NADIA | Eastern Mechanical | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New |  |  | 21/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.1 | 0 | 0 | 0
2852 | NADIA | Eastern Mechanical | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | New service connection charges at P.H No. II under Suruppur Tehatta Nadia | 94/EMD | 26/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.23 | 0 | 0 | 0
2853 | NADIA | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Suruppur 2nd Tubewell Site within Suruppur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 129/NACD-II | 11/01/2023 | 60 | SANJIT DAS | 5.83 | 5.76 | 98.67 | 80
2854 | NADIA | Eastern Mechanical | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | Supply delivery of PCC pole, M.s and electrical accessories including stringing of LTOH line to wbsedcl for new service connection at PH-II under Suruppur W/S Scheme. under EMSD-III | 1366/EMSD-III | 14/08/2022 | 30 | DEBJYOTI BASU | 0.72 | 0.72 | 100 | 0
2855 | NADIA | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | Construction of approch road at Head Works site of Suruppur Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | 467./AE-I/NACD-II | 03/10/2023 | 15 | MAJUMDER SYNDICATE | 0.97 | 0 | 0 | 0
2856 | NADIA | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Suruppur and adjoining mouzas under Suruppur Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | 302/NACD-II | 20/05/2022 | 90 | JOY GOPAL GUPTI | 104.51 | 104.4 | 100 | 85
2857 | NADIA | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Suruppur water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 216/NACD-II | 05/04/2022 | 60 | TAPAN SAHA | 5.38 | 5.32 | 100 | 100
2858 | NADIA | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Jitpur and Suruppur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 243/NACD-II | 19/04/2022 | 60 | B.M. ENGINEERING & CONSTRUCTION | 42.4 | 0 | 0 | 100
2859 | NADIA | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Suruppur water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | 14/AE-II/NACD-II | 11/04/2022 | 60 | TAPAN SAHA | 2.83 | 2.81 | 100 | 100
2860 | NADIA | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Suruppur Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 630/NACD-II | 06/09/2022 | 20 | MAKALI ENGINEERING CORPORATION | 3.42 | 3.42 | 100 | 100
2861 | NADIA | Eastern Mechanical | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.II under Suruppur W/S Scheme (Block : Tehatta-II) Dist.- Nadia. NIET No.- 21 OF EE/EMD OF 2022-23 (Sl. No.- 12) | 6490/EMD | 30/11/2022 | 30 | DEBJYOTI BASU | 9.96 | 9.91 | 100 | 87
2862 | NADIA | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | Material Requisition To Resource Division | 410/NACD-II | 04/07/2022 | 0 | Resource Division | 35.99 | 0 | 0 | 0
2863 | NADIA | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Suruppur Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | 90/NACD-II | 10/01/2023 | 960 | PARTHA DAS | 17.71 | 14.12 | 79.74 | 85
2864 | NADIA | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | Construction of Toilet with sanitary and water supply arrangement at Suruppur 2nd tube well site within Suruppur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 168/AE-II/NACD-II | 14/06/2024 | 15 | D.K.CONSTRUCTION | 0.97 | 0 | 0 | 0
2865 | NADIA | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | Laying of Rising Main of Suruppur Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | 25/AE-II/NACD-II | 18/04/2022 | 30 | BASUDEB SAHA | 4.41 | 4.39 | 100 | 100
2866 | NADIA | Eastern Mechanical | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) under Suruppur W/S Scheme (Block : Tehatta-II) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 11) | 6257/EMD | 19/11/2022 | 30 | M/S DILIP MITRA | 9.96 | 9.46 | 100 | 80
2867 | NADIA | Eastern Mechanical | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | Supply, delivery of PCC pole,M.S materials and Electricalaccessories and Installation DTR including stringing andSagging of HTOH line to WBSEDCL for newconnection at Pump House-1 under Suruppur water supplyscheme,under EMSD-III,PHE Dte,Nadia. | 264SD-III | 28/02/2023 | 30 | M/S DILIP MITRA | 3.71 | 3.71 | 100 | 100
2868 | NADIA | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | Construction of 250 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Suruppur water supply scheme of Tehatta-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | 160/NACD-II | 17/01/2023 | 853 | JOY HIND TUBEWELLS | 94.17 | 33.17 | 35.22 | 10
2869 | NADIA | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Manoharpur & Suruppur water supply scheme under Karimpur-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia. | 135/NACD-II | 09/01/2025 | 225 | NISHITH BANERJEE | 32.78 | 0 | 0 | 50
2870 | NADIA | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME , SM/10411 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 22 cum/Hour capacity for Suruppur Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1236/NACD-II | 10/09/2024 | 180 | SINGHA ROY & CO. | 146.67 | 0 | 0 | 0
2871 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE , SM/12019 | Augmentation | Construction of Boundary Wall, Toilet , Pathway and other allied works at Bhayana Z-I W/S Scheme within Hanshkhali Block under Nadia Arsenic Division -I, P.H.E.Dte. ( Sl.No. 20) | 1586 / NAD-I | 06/09/2022 | 45 | CHANDAN ROY | 13.37 | 12.05 | 100 | 100
2872 | NADIA | Central Drilling | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE , SM/12019 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250mm x 150mm x 300mtrs Depth ) by utilising Departmental Machineries for Bhayna W/S Scheme(Z-II)Ranaghat-I Block under Nadia District ,CDD,PHE Dte. | 1826/CDD | 06/01/2023 | 30 | M/S SAIKAT ENTERPRISE | 15.55 | 10.73 | 100 | 100
2873 | NADIA | Central Drilling | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE , SM/12019 | Augmentation | Hiring of Diesel driven motor cab (BS-IV & above) having contract carriage permit along with driver for the office of the Assistant Engineer, S&WSD, CDD, PHE Dte. | 79/S&WSD | 27/07/2023 | 60 | NAGENDRA PATRA | 0.44 | 1.07 | 100 | 33
2874 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE , SM/12019 | Augmentation | Material Requisition To Resource Division | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 12.32 | 0 | 0 | 0
2875 | NADIA | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE , SM/12019 | Augmentation | New Service connection at bagula under Bhayna W/S Scheme. | BP-211-23-24 | 17/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.15 | 0 | 0 | 0
2876 | NADIA | Central Drilling | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE , SM/12019 | Augmentation | Hiring of Diesel driven Motor Cab (BS-IV & Above) (Non AC) having contract carriage permit along with driver for the office of The Assistant Engineer, Store & Workshop Sub-division, Central Drilling Division, P.H.E. Dte. | 164/S&WSD | 19/12/2023 | 183 | NAGENDRA PATRA | 0.86 | 2.26 | 261.82 | 63
2877 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE , SM/12019 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Bhayna Zone-I GroundWater Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation in connection with JJM under Bhayna Zone-I & Zone-II Part-III Piped W/S Scheme (Sl.no28) | 1451/NAD-I | 26/05/2023 | 15 | PALCON | 12.98 | 12.9 | 100 | 100
2878 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE , SM/12019 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Bhayna Zone-II Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Bhayna Zone-I & Zone-II (Part-III) Piped W/S Scheme (Sl.no.29) | 1361 /NAD-I | 12/05/2023 | 15 | NISHITH BANERJEE | 13.04 | 13.01 | 100 | 100
2879 | NADIA | Central Drilling | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE , SM/12019 | Augmentation | Continuation for hiring of Diesel driven Motor Cab(BS-IV & Above) having contract carriage permit along with driver for the office of The Assistant Engineer, Store & Workshop Sub-division, Central Drilling Division, P.H.E. Dte. | 117/S&WSD | 30/10/2023 | 61 | NAGENDRA PATRA | 0.29 | 0.74 | 100 | 50
2880 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE , SM/12019 | Augmentation | Interconnection between Common Manifold and distribution main at Bhayna Zone-I W/S Scheme under JJM in connection with Garapota and Bhayna W/S Scheme within Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (Sl. no. 03) | 1501/NAD-I | 18/09/2024 | 45 | B.S. ENTERPRISE | 19.54 | 11.43 | 100 | 100
2881 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE , SM/12019 | Augmentation | Supply, delivery and storage at site of automatically controlled diapharm type Chlorinatore dosing pump. Under Augmentation of Ground Water Based PWSS for Bhayna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | 141/AE-II/NAD-I | 07/06/2024 | 30 | MANARAMA ENTERPRISE | 2.89 | 2.89 | 100 | 100
2882 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE , SM/12019 | Augmentation | Material Requisition To Resource Division | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 8.62 | 0 | 0 | 0
2883 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhaya Zone- I and Zone- II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE , SM/12019 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhayna Zone-I & II Part-III at Hanskhali block by Augmentation of Ground water based PWSS for Bhayna W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.01) | 1686/NAD-I | 12/07/2023 | 790 | TAPU SAHA | 390.82 | 113.4 | 29.01 | 80
2884 | NADIA | Central Drilling | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N , SM/12020 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 300 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR HALALPUR-KRISHNAPUR W/S SCHEME (Z-I), RANAGHAT BLOCK UNDER NADIA DISTRICT, CDD, PHE DTE. | 1451/CDD | 30/11/2022 | 30 | M/S SAIKAT ENTERPRISE | 15.55 | 10.4 | 66.83 | 0
2885 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N , SM/12020 | Augmentation | Retrofitting work for Halalpur Krishnapur Zone-I & Zone-II from Kharida Chapra Primary School to Purba Sangha at Ranaghat-II Block under Jal Jeevan Mission (JJM) by Retrofitting of Ground Water Based PWSS for Halalpur Krishnapur Water Supply Scheme under Retrofitting of Ground Water Based PWSS of Halalpur- Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 100/AE-I/NAD-i | 20/02/2023 | 15 | MONDAL ENTERPRISE | 3.56 | 3.56 | 100 | 0
2886 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N , SM/12020 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Halalpur-Krishnapur Zone-I Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Halalpur-Krishnapur Zone-I & II (Part-III) Piped W/S Scheme (sl.19) | 1161 / NAD-I | 28/04/2023 | 15 | B.S. ENTERPRISE | 13.04 | 12.61 | 100 | 100
2887 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N , SM/12020 | Augmentation | Material Requisition To Resource Division | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 15.4 | 0 | 0 | 0
2888 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N , SM/12020 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM), Construction of Boundary wall, Toilet, Pathway and other allied work at Head Work Site & 2nd T/W Site, Repair of 350 cum capacity Over Head Reservoir, Painting and Pump House at Halalpur Krishnapur Zone-I & Repair of 180 cum capacity Over Head Reservoir, Painting and repairing of H/W Boudary wall, Pump House at Halapur Zone-II for Halalpur Krishnapur Zone-I & II at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1742/NAD-I | 19/07/2023 | 90 | SATYABRATA CHAKRABORTY | 377.65 | 64.63 | 17.11 | 40
2889 | NADIA | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N , SM/12020 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HALALPUR KRISHNAPUR (Z-II),GOALSALUA(Z-I) & GOALSALUA(Z-II) W/S Scheme, Block- Ranaghat-II , Dist. - Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 01) | 1601/EMD | 26/04/2023 | 30 | M/S DILIP MITRA | 56.44 | 18.77 | 100 | 100
2890 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N , SM/12020 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Halalpur-Krishnapur Zone-II Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Muragachha Zone-I & II (Part-III) Piped W/S Scheme (Sl.no.18) | 1430/NAD-I | 24/05/2023 | 15 | D.K. CONSTRUCTION | 12.98 | 12.38 | 100 | 100
2891 | NADIA | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N , SM/12020 | Augmentation | Providing Boundary Illumination with allied works at Halalpur Krishnapur Zone-I and Zone II Part III under Block_ Ranaghat II Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/12020) | 1154/EMD | 04/06/2025 | 90 | KASHINATH PAL & CO. | 8.68 | 0 | 0 | 0
2892 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N , SM/12020 | Augmentation | Balance work for revamping / upgradation of the hydraulic parameters at Gayesh, Daluigram & Jafar-nagar mouzas in reference to Halalpur-Krisnapur PWSS & Raynagar PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) | 154/NAD-I | 28/04/2025 | 60 | TAPU SAHA | 86.49 | 0 | 0 | 0
2893 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Halalpur Krishnapur Zone- I and Zone- II Part-III at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under N , SM/12020 | Augmentation | Interconnection of M.S pipeline with Manifold at Halalpur Krishnapur Z-1 Water Supply Scheme including fixing of Sign Board for dematcation of Land at different location under the judisdiction of Nadia Arsenic Division-I ,PHE Dte. under JJM. (Sl. No. 08) | 168/NAD-I | 29/04/2025 | 60 | BUDDHADEV MONDAL | 9.81 | 0 | 0 | 60
2894 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11508 | Augmentation | Material Requisition To Resource Division | 158/ND | 06/01/2023 | 0 | Resource Division | 22.47 | 0 | 0 | 0
2895 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11508 | Augmentation | Material Requisition To Resource Division | 2306/ND | 29/05/2023 | 0 | Resource Division | 26.43 | 0 | 0 | 0
2896 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11508 | Augmentation | Plumbing & allied Works for toilet & guard room at Habibpur under Ranaghat Sub-Division under Nadia Division PHE. Dte. | 795(A)RSD | 02/08/2024 | 20 | SKYLINE CONSTRUCTION | 0.95 | 0.95 | 100 | 100
2897 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11508 | Augmentation | Guard Room Repair at Habibpur water supply scheme under Ranaghat Sub-Division under Nadia Division PHE. Dte. | 794/RSD | 02/08/2024 | 20 | SKYLINE CONSTRUCTION | 0.94 | 0.93 | 100 | 100
2898 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11508 | Augmentation | Toilet construction of Guard Room of Habibpur water supply scheme under Ranaghat Sub-Division under Nadia Division PHE. Dte. | 795/RSD | 02/08/2024 | 20 | SKYLINE CONSTRUCTION | 0.82 | 0.78 | 100 | 100
2899 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11508 | Augmentation | "Restoration work arising out of damage of Hard Shoulder for Laying of UPVC Pipe Line by Nadia Division, PHED" under Nadia Highway Division No-II in the District of Nadia during the year 2023-24 Pt.-II "NH Tarapur to Balagarhghat Road from Ch 0.00 Km to Ch1.80 Km". | 228/PFMS | 11/09/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-II, P.W. (ROADS) DIRECTORATE | 6 | 0 | 0 | 0
2900 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11508 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Habibpur to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. (PART-II) | 4990/ND | 30/11/2022 | 856 | M/S GHOSH CONSTRUCTION | 335.48 | 265.28 | 79.07 | 100
2901 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11508 | Augmentation | Construction of Boundary wall at Habibpur W/S Scheme under Ranaghat Sub-Division, Nadia Division PHE Dte. | 875/RSD | 20/08/2024 | 31 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 3.78 | 0 | 0 | 100
2902 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11508 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Habibpur under Ranaghat Sub-Division under Nadia Division PHE Dte. | 1416/RSD | 19/11/2024 | 45 | SARKAR ENTERPRISE | 2.16 | 0 | 0 | 80
2903 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11508 | Augmentation | Balanced UPVC pipe line for Providing Functional Household Tap Connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Habibpur to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. | 2156/ND | 06/05/2025 | 90 | M/S DIPAK ENTERPRISE | 164.59 | 0 | 0 | 0
2904 | NADIA | Nadia Division | MINI PIPED WATER SUPPLY SCHEME AT GAZNA (PART) VILLAGE, BLOCK- HANSKHALI, DISTRICT NADIA , SM/14064 | New | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Mini Piped Water Supply Scheme Gazna (Part) (100 Households) to accommodate FHTC in Hanskhali block & Providing FHTC and allied works for- Ground Water Based Mini Piped Water Supply Scheme in Arsenic affected area at Uttar Bishnupur, Block : -Ranaghat-II, Nadia District under Nadia Division P.H.E Dte. | 3024/ND | 14/07/2023 | 366 | ABDUL ALIM MONDAL | 79.83 | 33.64 | 83.12 | 78
2905 | NADIA | Nadia Division | MINI PIPED WATER SUPPLY SCHEME AT GAZNA (PART) VILLAGE, BLOCK- HANSKHALI, DISTRICT NADIA , SM/14064 | New | Material Requisition To Resource Division | 273/ND | 11/01/2024 | 0 | Resource Division | 0.6 | 0 | 0 | 0
2906 | NADIA | Eastern Mechanical | MINI PIPED WATER SUPPLY SCHEME AT GAZNA (PART) VILLAGE, BLOCK- HANSKHALI, DISTRICT NADIA , SM/14064 | New | Supply, & Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for Mini Piped Water Supply Scheme[Gazna(part) Block-Hanskhali, Uttar Bishnupur Block-Ranaghat-II, Augmentation to Accomodate FHTC , Dist. - Nadia. under EMD, PHE Dte. | 1307/EMD | 09/05/2024 | 388 | ORIENTAL ENGINEERING CO. | 12.61 | 0 | 0 | 45
2907 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Itaberia Water Supply Scheme Part-III under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15552 | Augmentation | Augmentation of AIRP capacity (60cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Itaberia, under Jal Jeevan Mission at Hanskhali Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.06) | 1969/NAD-I | 21/08/2023 | 30 | B.M. ENGINEERING & CONSTRUCTION | 112.08 | 0 | 0 | 0
2908 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Itaberia Water Supply Scheme Part-III under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15552 | Augmentation | Balance work for revamping / upgradation of the hydraulic parameters at Muchiphulbari, Dhakuria & Baranberia Mouza in connection with Itaberia PWSS & Duttaphulia PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 06) | 167/NAD-I | 29/04/2025 | 181 | MS MAA BHABANI ENTERPRISE | 95.54 | 0 | 0 | 0
2909 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Itaberia Water Supply Scheme Part-III under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15552 | Augmentation | Supply, delivery and installation commissioning of Domestic Ultrasonic (153 RWM) type water meter with Software for data communication at Patkabari, Hatibhanda, Madna, Jaganath, Sahapur & Dhakuria village under augmentation of ground watwer based PWSS for Itaberia W/S Scheme Part-III under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, PHE Dte. (Sl.04) | 131/NAD-I | 22/04/2025 | 60 | SHANTA COLIBRI (INDIA) PVT. LTD. | 5.43 | 0 | 0 | 0
2910 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhayna Zone- II Water Supply Scheme, Part-IV under Jal Jeevan Mission(JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. , SM/15543 | Augmentation | Load enhancement of Bhayna Z-1 (Ph-1) water supply scheme at Hanskhali block, Dist.-Nadia | BP-22-24-25 | 21/05/2024 | 0 | W.B.S.E.D.C.LTD (BAGULA C.C.C) | 1.28 | 0 | 0 | 0
2911 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhayna Zone- II Water Supply Scheme, Part-IV under Jal Jeevan Mission(JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. , SM/15543 | Augmentation | Augmentation of AIRP capacity (19cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Bhayna Zone-II under Jal Jeevan Mission at Hanskhali Block, under Nadia Arsenic Division -I, PHE Dte. (SL.02) | 1796/NAD-I | 31/07/2023 | 30 | M/S R.K. ENTERPRISE | 46.11 | 0 | 0 | 0
2912 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR TOPLA (PHASE-II) IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15536 | Augmentation | Renovation of AIRP (Pressure Type) of capacity 93 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Topla PWSS under Nadia Division PHE Dte. | 3584/ND | 14/08/2023 | 90 | APURBA MANDAL | 68.26 | 0 | 0 | 0
2913 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHINPARA ZONE-II (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15538 | Augmentation | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | 1270/ND | 23/03/2023 | 60 | AUXILIARY TUBEWELL DRILLERS | 65.32 | 0 | 0 | 0
2914 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHINPARA ZONE-II (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15538 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under DAKSHINPARA (Zone-I & II) W/S Scheme, Block- Hanskhali , AND GOPINATHPUR W/S Scheme, Block- Tehatta-II, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 01) | 496/EMDdt.24.01.2023 | 17/03/2023 | 656 | GLACIER ENGINEERING CO. | 66.71 | 1.39 | 100 | 100
2915 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHINPARA ZONE-II (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15538 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Dakshinpara-II PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 35.00 Cu.m/hr | 134/ND | 09/01/2024 | 450 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 60.46 | 43.63 | 79.59 | 91
2916 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHINPARA ZONE-II (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15538 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Dakshinpara Zone-II ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15538) | 230/EMD | 06/02/2025 | 30 | SK ENTERPRISE | 11.76 | 0 | 0 | 0
2917 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHINPARA ZONE-I (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15139 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under DAKSHINPARA (Zone-I & II) W/S Scheme, Block- Hanskhali , AND GOPINATHPUR W/S Scheme, Block- Tehatta-II, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 01) | 496/EMDdt.24.01.2023 | 17/03/2023 | 656 | GLACIER ENGINEERING CO. | 66.71 | 1.39 | 100 | 100
2918 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHINPARA ZONE-I (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15139 | Augmentation | SHIFTING OF HTOH LINE AT DAKSHINPARA ZONE-I WATER SUPPLY SCHEME. | 540/PFMS | 13/02/2024 | 0 | WBSEDCL | 2.28 | 0 | 0 | 0
2919 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHINPARA ZONE-I (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15139 | Augmentation | SHIFTING OF HTOH LINE AT DAKSHINPARA ZONE-I WATER SUPPLY SCHEME. | 539/PFMS | 13/02/2024 | 0 | WBSEDCL | 1.86 | 0 | 0 | 0
2920 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHINPARA ZONE-I (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15139 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Dakshinpara Zone-I PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 45.00 Cu.m/hr | 133/ND | 09/01/2024 | 450 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 68.46 | 0 | 0 | 95
2921 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHINPARA ZONE-I (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15139 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Dakshinpara Zone-I ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. (Phase-II) (SM/15139) | 229/EMD | 06/02/2025 | 30 | M/S CHANDIMATA ELECTRICALS | 11.76 | 0 | 0 | 0
2922 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHINPARA ZONE-I (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15139 | Augmentation | Sinking of Rig Bored Tube well (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | 1269/ND | 23/03/2023 | 780 | JOY HIND TUBEWELL'S | 65.37 | 0 | 0 | 100
2923 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Mamjoani Water Supply Scheme In Hanskhali Block District Nadia. , SM/16361 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2924 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Natna Water Supply Scheme in Tehatta-I Block, Dist.-Nadia. , SM/16335 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2925 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Garapota Water Supply Scheme In Hanskhali Block District Nadia. , SM/16357 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2926 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Palsunda Water Supply Scheme in Tehatta-II Block, Dist.-Nadia. , SM/16348 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2927 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Krishnagar Water Supply Scheme in Krishnagar-I Block, Dist.- Nadia. , SM/16832 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2928 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Mahishnengra Water Supply Scheme (Zone - I & II) in Krishnagar-I Block, Dist.- Nadia. , SM/16834 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2929 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GHORALIA ZONE-II (PHASE-II) IN SANTIPUR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17217 | Augmentation | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Ghoralia Zone-II (Phase-II) Piped Water Supply Scheme, Block: Santipur, Dist. Nadia Under EMD, PHE Dte. | 6367/EMD | 17/10/2023 | 30 | ABHISEK ENGINEERING CONCERN | 42.09 | 0 | 0 | 0
2930 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GHORALIA ZONE-II (PHASE-II) IN SANTIPUR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17217 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under ELANGI(Zone-II) & GHORALIA (Zone-II) W/S Scheme, Block- Chapra & Shantipurrespectively , Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 05) | 1503EMD | 18/04/2023 | 30 | MA ANNAPURNA ENTERPRISE | 11.19 | 5.03 | 100 | 60
2931 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GHORALIA ZONE-II (PHASE-II) IN SANTIPUR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17217 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 28 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at GHORALIA ZONE-II PWSS under Nadia Division PHE Dte. | 1805 / ND | 24/04/2023 | 90 | MONDAL PRECISION PRIVATE LIMITED | 58.81 | 24.71 | 42.01 | 75
2932 | NADIA | Eastern Mechanical | Solarisation of WBSEDCL Energised Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Hanskhali Block in Nadia District under Eastern Mechanical Division PHE, Dte. , SM/17183 | Solarisation | Solarisation of WBSEDCL Energised Electrical installation including net metering at different Pipe Water Supply Scheme at Hanskhali Block in Nadia District under E.M.D. P.H.E. Dte. | 6456/EMD | 02/11/2023 | 730 | SWITCHING AVO ELECTRO POWER LTD. | 316.41 | 0 | 0 | 10
2933 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone I PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17195 | Augmentation | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Tenipur Zone-I Piped Water Supply Scheme, Block: Karimpur-II Dist. Nadia Under EMD, PHE Dte. | 6733/EMD | 29/11/2023 | 30 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 42.1 | 0 | 0 | 0
2934 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone I PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17195 | Augmentation | Proposed Augmentation of Laying Rising Main System and Sinking of Replacement Tube Well at Head Work Site of Teinpur Zone-I [Phase-II] Ground Based Piped Water Supply Scheme. | 1217/ND | 21/03/2023 | 60 | JOY HIND TUBEWELL'S | 14.38 | 9.82 | 100 | 85
2935 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone I PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17195 | Augmentation | Renovation and modification of AIRP (Pressure Type) & Construction of Backwash chamber for AIRP at Head Work Site in Teinpur ZONE-I PWSS under Nadia Division PHE Dte. Capacity- 15.5 cum/hr. | 781/ND | 05/02/2024 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 37.22 | 17.52 | 100 | 93
2936 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone I PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17195 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under TEINPUR (ZONE-I ,II, III & IV) W/S Scheme, Block- Karimpur-II , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 06) | 500EMD | 24/01/2024 | 30 | M/S DILIP MITRA | 64.62 | 20.49 | 100 | 85
2937 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone I PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17195 | Augmentation | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Teinpur Zone-IV PWSS within Karimpur-II Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 3260/ND | 10/06/2024 | 450 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 82.42 | 0 | 0 | 80
2938 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone I PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17195 | Augmentation | Laying of 160 mm dia HDPE pipe line, 75 mm & 125 mm UPVC Pipe line for Augmentation of Rising Main System for distribution pipeline with interconnection along with road restoration at village Dogachhi, Block Karimpur-II under Nadia Division, P.H.E. Dte. | 1803/ND | 22/04/2025 | 180 | SUBHASH BOSE | 32.54 | 0 | 0 | 51
2939 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Muktadaha zone I (PHASE-II) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17207 | Augmentation | Renovation of AIRP (Pressure Type ) of capacity 33.75 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Muktadaha Zone I PWSS under Nadia Division PHE Dte. | 1783/ND | 20/04/2023 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 201.98 | 168.48 | 100 | 90
2940 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Muktadaha zone I (PHASE-II) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17207 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at Muktadaha zone I (PHASE-II) W/S Scheme Block- Karimpur-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/17207 | 1142/EMD | 04/06/2025 | 90 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT LTD) | 32.62 | 0 | 0 | 0
2941 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Muktadaha zone I (PHASE-II) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17207 | Augmentation | Laying of additional pipeline for providing balance FHTC and inerease functionality in Baro Jangal, Majlishpur, Basotipara Villages under Karimpur-I Block under Tehatta Sub-Division under Nadia Division, PHE Dte. | .4686/4533/P-3/ND | 09/10/2025 | 90 | JOY HIND TUBEWELL'S | 79.19 | 0 | 0 | 0
2942 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VII, (Ballabhpur) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte , SM/08839 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-VII, (Ballabhpur) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 13/NAD-I | 05/01/2022 | 90 | H I ENTERPRISE | 243.49 | 241.76 | 100 | 100
2943 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Mahisura Water Supply Scheme in Nabadwip Block of District Nadia , SM/17277 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2944 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Bara Kulta Water Supply Scheme in Ranagtat-I Block under District Nadia , SM/18197 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2945 | NADIA | Eastern Mechanical | Providing Pumping Machinery and Electrical Equipment for GLR and Boosting Stations at Different OHR sites in Ranaghat-II Block in Connection with Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II, in the District of Nadia, P.H.E. Dte. , SM/19098 | Augmentation | Providing pumping machinery and electrical equipment for secondary Boosting station at different OHR sites in Ranaghat-II block in connection with integrated surface water based PWSS in the Dist. of Nadia , P.H.E, Dte. | 312/EMD | 07/02/2024 | 182 | A.G ENTERPRISE. | 110.43 | 0 | 0 | 0
2946 | NADIA | Eastern Mechanical | Providing Pumping Machinery and Electrical Equipment for GLR and Boosting Stations at Different OHR sites in Ranaghat-II Block in Connection with Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II, in the District of Nadia, P.H.E. Dte. , SM/19098 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR RANAGHAT-II GLR (PATULI) | BP-54-24-25 | 21/06/2024 | 0 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 69.14 | 0 | 0 | 0
2947 | NADIA | Eastern Mechanical | Providing Pumping Machinery and Electrical Equipment for GLR and Boosting Stations at Different OHR sites in Ranaghat-II Block in Connection with Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II, in the District of Nadia, P.H.E. Dte. , SM/19098 | Augmentation | Providing Mechanical / Electrical Equipment for 11/0.433 KV Sub-station along with pumping station and disinfection arrangement at Ranaghat-II Block GLR Site of surface water based water supply scheme, Arsenic Affected Area, in the district of Nadia, P. H. E. Dte. | 83/EMD | 11/01/2024 | 721 | WEST BENGAL ENGINEERING CO. | 852.36 | 0 | 0 | 25
2948 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Balibanga Water Supply Scheme in Chapra Block, Dist.-Nadia. , SM/18048 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2949 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Brittihuda Water Supply Scheme in Chapra Block, Dist.-Nadia. , SM/18051 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2950 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Elangi (Zone-I & II) Water Supply Scheme in Chapra Block, Dist.-Nadia. , SM/18053 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2951 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Maheshpur Water Supply Scheme in Chapra Block, Dist.-Nadia. , SM/18058 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2952 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Joyghata Water Supply Scheme in Krishnaganj Block, Dist.-Nadia. , SM/18060 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2953 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18389 | Augmentation | Material Requisition To Resource Division | 88/ND | 05/01/2023 | 0 | Resource Division | 1297.82 | 0 | 0 | 0
2954 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18389 | Augmentation | Payment to Ministry of Railway regarding railway crossing, Application ID- ER-SDAH-2024-WL-134 | 310/PFMS | 02/10/2024 | 0 | MINISTRY OF RAILWAYS, EASTERN RAILWAY, SEALDAH DIVISION | 5.09 | 0 | 0 | 0
2955 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18389 | Augmentation | Payment to Ministry of Railway regarding railway crossing, Application ID- ER-SDAH-2024-WL-111 | 309/PFMS | 02/10/2024 | 0 | MINISTRY OF RAILWAYS, EASTERN RAILWAY, SEALDAH DIVISION | 8.94 | 0 | 0 | 0
2956 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18389 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | 3537/ND | 11/08/2023 | 782 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 1083.72 | 27.88 | 20
2957 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18389 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 0 | 30
2958 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18389 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub Division, PHE Dte for supervision of JJM works for the period of 01/01/2025 to 31/12/2025 | 2666/KSD | 31/12/2024 | 365 | AVINABA ENGINEERING CONCERN | 4.8 | 0 | 0 | 0
2959 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18389 | Augmentation | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3829/ND | 13/08/2025 | 120 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0 | 0
2960 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Shyamnagar Water Supply Scheme in Krishnaganj Block, Dist.-Nadia. , SM/18065 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2961 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Taldaha Water Supply Scheme in Krishnaganj Block, Dist.-Nadia. , SM/18066 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
2962 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10473 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Karimpur-Jalangi Z-8(I&II) W/S Scheme in Karimpur-II Block of Nadia District under Nadia Division, P.H.E. Dte. | 317/TSD | 24/11/2021 | 30 | RADIANT | 4.72 | 4.72 | 100 | 100
2963 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10473 | Augmentation | Material Requisition To Resource Division | 148/ND | 06/01/2023 | 0 | Resource Division | 43.02 | 0 | 0 | 0
2964 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10473 | Augmentation | Material Requisition To Resource Division | 1853/ND | 26/04/2023 | 0 | Resource Division | 33.06 | 0 | 0 | 0
2965 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10473 | Augmentation | Material Requisition To Resource Division | 2285/ND | 29/05/2023 | 0 | Resource Division | 25.03 | 0 | 0 | 0
2966 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10473 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Betai Zone-I ii) Karimpur Jalangi Zone-IXB iii)Fatepur iv)Anjangarh v)Kamalpur Zone-II vi) Shyamnagar vii)Karimpur Jalangi Zone-VIII | 497/ Kly SD-I | 06/04/2023 | 183 | TECHVISION | 4.96 | 4.96 | 100 | 100
2967 | NADIA | Central Drilling | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10473 | Augmentation | Providing drilling crew and other allied works for construction of tube well (300mm x 200mm x 250 mtrs depth) by utilising departmental machineries for karimpur jalangi w/s scheme, (zone- IV & VIII), karimpur-I & II block under Nadia district, CDD, PHE Dte. | 137/CDD | 17/04/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 37.28 | 23.71 | 100 | 100
2968 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10473 | Augmentation | Quotation charges for new service connection and security deposit at Karimpur Jalangi Zone-IX,B (Garaimari) PH-II under EMSD-III,Nadia | BP-192-24-25 | 16/12/2024 | 0 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 10.76 | 0 | 0 | 0
2969 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10473 | Augmentation | Quotation charges for new service connection and security deposit at Karimpur Jalangi Zone-VIII (Barbakpur) PH-III under EMSD-III,Nadia | BP-177 | 13/12/2024 | 0 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 5.28 | 0 | 0 | 0
2970 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10473 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 250 cum capacity 20 mtr. height RCC Over Head Reservoir (excluding pile foundation), pipe connection and cost of pipes, specials and Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of 250 cum. O.H.R. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-VIII to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. (SM/10473) | 843/ND | 28/02/2023 | 855 | M/S TAPAS KUMAR CHAKRABORTY | 545.01 | 107.3 | 19.69 | 40
2971 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10473 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under KARIMPUR JALANGI(Z-8) W/S Scheme, Block- Karimpur II, PALSONDHA W/S Scheme, Block- Tehatta II, & MAIDANPUR W/S Scheme, Block- Chapra, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 06) | 1179/EMD | 21/03/2023 | 940 | CREATIVE WATER & PROCESS TECHNOLOGIES PVT. LTD. | 77.9 | 0 | 0 | 85
2972 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10473 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Karimpur Jalangi Zone-VIII water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 7128/ND | 09/12/2024 | 360 | THE TOWER CONSTRUCTION | 34.05 | 0 | 0 | 60
2973 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Hiring of Diesel SUV car for office use of the Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte. Krishnagar, Nadia. for the period 01.11.2022 to 31.03.2023.(Five months) | 785//NACD-II | 28/10/2022 | 151 | TARUN KUMAR BHATTACHARYA | 2.07 | 0 | 0 | 100
2974 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte in soft copy for different PWSS under Nadia Arsenic Civil Division-II P.H.E. Dte. | 164/AE-I/NACD-II | 28/07/2022 | 92 | JOY GOPAL GUPTI | 4.75 | 4.75 | 100 | 100
2975 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bagberia) | 1117/NACD-II | 06/10/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
2976 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Material Requisition To Resource Division | 910/NACD-II | 24/11/2021 | 0 | Resource Division | 7.39 | 0 | 0 | 0
2977 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Material Requisition To Resource Division | 133 | 25/02/2022 | 0 | Resource Division | 92.34 | 0 | 0 | 0
2978 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Bagberia & Hatkhola Water Supply Scheme of capacity 35 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | 197/NACD-II | 12/02/2024 | 90 | SINGHA ROY & CO. | 159.46 | 4.75 | 5.96 | 30
2979 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:- Bagberia under Habitation of Baganpara Part in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 597/AE-I/NACD-II | 29/01/2024 | 15 | PARTHA DAS | 0.91 | 0 | 0 | 0
2980 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Bagberia Water Supply Scheme in CHAPRA Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 324/1/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.21 | 0.98 | 100 | 100
2981 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte." | 532/AE-I/NACD-II | 18/12/2023 | 15 | SUBHANKAR ROY | 0.97 | 0.93 | 100 | 100
2982 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:-Bagberia under Habitation of Karmakar Para and HajraPara in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 623/AE-I/NACD-II | 02/02/2024 | 15 | SHYAMAL KANTI GHOSH | 0.93 | 0.92 | 100 | 100
2983 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:-Bagberia under Habitation of Schoolpara ,Hatpara, Christanpara in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte¿ | 624/AE-I/NACD-II | 02/02/2024 | 15 | SREE GURU ENTERPRISE | 0.93 | 0.86 | 100 | 100
2984 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:- Dangna under Habitation of Muslimpara and Ghosh Para in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | 619/AE-I/NACD-II | 02/02/2024 | 15 | SUBHANKAR ROY | 0.93 | 0.89 | 100 | 100
2985 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:-Bagberia under Habitation of Baganpara Part in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | 625/AE-I/NACD-II | 02/02/2024 | 15 | NIVEDITA CONSTRUCTION | 0.91 | 0.89 | 100 | 100
2986 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:-Bagberia under Habitation of Daspara in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 622/AE-I/NACD-II | 02/02/2024 | 15 | BINOY DAS | 0.93 | 0.91 | 100 | 100
2987 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:-Bagberia under Habitation of Masjidpara in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 620/AE-I/NACD-II | 02/02/2024 | 15 | SHOVON KUMAR MODAK | 0.97 | 0.93 | 100 | 100
2988 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:-Bagberia under Habitation of Clubpara and Dilar Para &Rajbangsi Para in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dt | 621/AE-I/NACD-II | 02/02/2024 | 15 | NAMDAR ALI | 0.97 | 0.84 | 100 | 100
2989 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:- Dangna under Habitation of Ghosh Para in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 618/AE-I/NACD-II | 02/02/2024 | 15 | ST. ANTHONY ENTERPRISE | 0.96 | 0.88 | 100 | 100
2990 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:- Bagberia under Habitation of Gajantala in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 596/AE-I/NACD-II | 29/01/2024 | 15 | BK ENGINEERING | 0.91 | 0.91 | 100 | 100
2991 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Quotation for load enhancement and security deposit charges at PH-I of Bagberia PWSS,Nadia | BP-169-24-25 | 05/12/2024 | 0 | W.B.S.E.D.C.L (GROUP CHAPRA C.C.C) | 3.46 | 0 | 0 | 0
2992 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Bagberia Piped Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1582/NACD-II | 11/12/2024 | 270 | SANDIP BISWAS | 111.44 | 0 | 0 | 75
2993 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09257 | Augmentation | Repair and Renovation work at Bagberia 2nd tube well Site under Bagberia Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | 1024/AE-I/NACD-II | 10/12/2024 | 30 | M/S FREEDOM CONSTRUCTION | 4.76 | 0 | 0 | 0
2994 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte , SM/11507 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Subarnabehar W/S Scheme in Krishnagar - I Block of Nadia District under Nadia Division. PART - B | 1190/PH | 03/12/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 1.69 | 1.68 | 100 | 100
2995 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte , SM/11507 | Augmentation | continuation order of Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Subarnabehar zone - II W/S Scheme in Krishnagar - I Block of Nadia District under Nadia Division. | 1198/PH | 07/12/2021 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 1.6 | 1.6 | 100 | 100
2996 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte , SM/11507 | Augmentation | Material Requisition To Resource Division | 241/ND | 13/01/2023 | 0 | Resource Division | 85.16 | 0 | 0 | 0
2997 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte , SM/11507 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
2998 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte , SM/11507 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 65 m3/hr at Subarnabihar Zone-II Water Supply Scheme including 3 Months Trial Run & 3 Years O&M within Krishnanagar-I Block under Nadia Division, P.H.E. Dte. | 1354/ND | 27/02/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 204.6 | 0 | 0 | 0
2999 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte , SM/11507 | Augmentation | WBSEDCL Quotation for New Service Connection to the newly Head Work Site under SUBARNA BEHAR (ZONE-II) W/S Scheme in KRISHNAGAR - 1 Block, P.H.E. Dte., Dist.- Nadia. (Application No. 3005020477) | BP-170-24-25 | 05/12/2024 | 0 | W.B.S.E.D.C.L (GROUP KRISHNAGAR ROAD STATION C.C.C) | 6.39 | 0 | 0 | 0
3000 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte , SM/11507 | Augmentation | Supplying, Laying, Fitting & Fixing of Distribution System including all type of specials, valves, pipes all complete, Proposed augmentation of Rising Main, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction & Soil investigation of 350 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (With Pile Foundation), Pipe Connection and Cost of Pipes, Specials, Construction of 1 (One) No. Pump House (4.88m X 3.66m) Including Sanitary Arrangement, HW Site & 1 (One) No. Pump House (4.88m X 3.66m) Including Sanitary Arrangement Tw Site-2, Construction of Boundary Wall, Service Road (60 Mtr. Length X 3 Mtr. Width) at Head Work Site & Service Road (15 Mtr. Length X 2 Mtr. Width) at Tube Well Site for Subarna Behar ZONE-II in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | 3194/ND | 26/07/2023 | 1096 | M/S GHOSH CONSTRUCTION, SUKUL ROAD, P.O-KRISHNAGAR, DIST.NADIA, PIN-741101, WB | 440.53 | 0 | 0 | 5
3001 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte , SM/11507 | Augmentation | Laying of additional pipeline as per the revised drawing for augmentation of Subarnabihar Zone-II Water Supply Scheme in Krishnagar-I Block under Nadia Division PHE Dte. | 2287/ND | 19/05/2025 | 90 | M/S GHOSH CONSTRUCTION | 91.02 | 0 | 0 | 0
3002 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09789 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | 644/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.51 | 0 | 0 | 0
3003 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09789 | Augmentation | Providing functional household tap connection ( Final part ) including supply of 15mm dia PVC pipe of average length of 15 mtr along with laying of different dia UPVC pipe line and other allied works etc all complete for JOANIA W/S scheme (for Hazrapal, Joania, Kursi, Malipota, Sardanga, Tiabali Mouza) under Ranaghat Sub Division of Nadia Division P.H.Engineering Dte. | 1374/ND | 23/03/2022 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 230.28 | 158.17 | 100 | 86
3004 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09789 | Augmentation | Special repair & renovation of pump house & allied works in the premises at Pump house no-II of Joania W/S scheme of Krishnanagar-I block under Ranaghat Sub-Division, P.H.E. Dte. | 557/RSD | 30/08/2022 | 30 | K.K. MARKETING | 2.62 | 2.25 | 100 | 100
3005 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09789 | Augmentation | Special repair & renovation & repair of CWR pump house & allied works of Joania W/S scheme of Krishnanagar block under Ranaghat Sub-Division, P.H.E. Dte. | 557/A/RSD | 30/08/2022 | 30 | M/S ASIT ROY BHOWMIK | 2 | 1.83 | 100 | 90
3006 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09789 | Augmentation | Material Requisition To Resource Division | 4287/ND | 29/09/2022 | 0 | Resource Division | 4.29 | 0 | 0 | 0
3007 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09789 | Augmentation | Material Requisition To Resource Division | 1882/ND | 26/04/2023 | 0 | Resource Division | 14.1 | 0 | 0 | 0
3008 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09789 | Augmentation | Special repair & renovation of head work site pump house & allied works of Joania W/S scheme of Krishnanagar block under Ranaghat Sub-Division, P.H.E. Dte | 556/A/RSD | 30/08/2022 | 30 | ANJALI ENTERPRISE | 2.22 | 2.04 | 100 | 90
3009 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09789 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at JOANIA W/S Scheme Block- Krishnagar-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/09789 | 1136/EMD | 04/06/2025 | 90 | M/S DILIP MITRA | 36.67 | 0 | 0 | 0
3010 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09789 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
3011 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09789 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No.- I AND II under Joania WS Scheme, Block Krishnagar I, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-06) | 157/EMDdt.06.01.2023 | 08/02/2023 | 726 | MASSK ENGINEERING WORKS | 14.9 | 0 | 0 | 100
3012 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA , SM/10691 | Augmentation | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA | 47/PFMS | 22/06/2022 | 0 | HORIZEN | 2.7 | 0 | 0 | 0
3013 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA , SM/10691 | Augmentation | Construction of barbed wire fencing with concrete pillars at Palashipara (3rd T.W). water supply scheme( New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . | 932/TSD | 14/03/2023 | 7 | PRABIR KUMAR ROY | 0.65 | 0.63 | 97.66 | 0
3014 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA , SM/10691 | Augmentation | Material Requisition To Resource Division | 140/ND | 06/01/2023 | 0 | Resource Division | 7.35 | 0 | 0 | 0
3015 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA , SM/10691 | Augmentation | Material Requisition To Resource Division | 1025/ND | 13/03/2023 | 0 | Resource Division | 30.79 | 0 | 0 | 0
3016 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA , SM/10691 | Augmentation | Material Requisition To Resource Division | 2290/ND | 29/05/2023 | 0 | Resource Division | 34.16 | 0 | 0 | 0
3017 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA , SM/10691 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MAHISUNRA W/S Scheme, Block-NABADWIP, PALASIPARA W/S Scheme, Block-Tehatta-II AND TOPLA W/S Scheme, Block-Karimpur-II Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No. - 05) | 499/EMD | 24/01/2023 | 30 | WEST BENGAL ENGINEERING CO. | 90.14 | 34.7 | 100 | 15
3018 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA , SM/10691 | Augmentation | Sinking of 01 no Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at Palashipara Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | 1225/ND | 22/02/2024 | 244 | M/S DIPAK ENTERPRISE | 17.38 | 0 | 0 | 100
3019 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA , SM/10691 | Augmentation | Quotation charges and security deposit for new power connection at Palashipara PH-III head worksite under Eastern Mechanical Subdivision-III, Nadia | BP-178 | 13/12/2024 | 0 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 3.49 | 0 | 0 | 0
3020 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA , SM/10691 | Augmentation | Reimbursement of additional GST due to enhancement of rate from 12% to 18% vide notification no 03/2022-central tax rate dt 13.07.2022 for the work of Laying Of Distribution System Including Specials, Valves & Pipe Carrying Structure All Complete ,rising main with interconnction in between tubewell including specials and valves, Providing FHTC Including Supplying, Laying, Fitting, Fixing Of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE 100, PN16) Pipe With All Necessary Specials, Saddle Piece Etc., Construction Of 400 Cum Capacity 20 Mtr. Staging Height Rcc Over Head Reservoir (including Pile Foundation), Pipe Connection And Cost Of Pipes, Specials And Soil Investigation All Complete For Augmentation Of Ground Based Water Supply Scheme At Palashipara to Accommodate FHTC Under Tehatta Sub-Divn Under Nadia Divn, PHE Dte | 131/PFMS | 27/07/2024 | 0 | GHOSH ENTERPRISE | 25.43 | 0 | 0 | 0
3021 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA , SM/10691 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at PALASHIPARA W/S Scheme Block- Tehatta-II under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10691] | 1140/EMD | 04/06/2025 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 52.38 | 0 | 0 | 0
3022 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA , SM/10691 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Rising main with Inter-Connection in between Tube wells including specials and valves, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 400 cum capacity 20 mtr. staging height RCC Over Head Reservoir (including pile Foundation), pipe connection and cost of pipes, specials and Soil investigation all complete for Augmentation of Ground Based Water Supply Scheme at Palashipara to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 4412 /ND | 14/10/2022 | 841 | GHOSH ENTERPRISE, B-2/183, KALYANI. P.O.& P.S. KALYANI, DIST.NADIA, PIN-741235,W.B | 514.08 | 479.49 | 93.27 | 95
3023 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA , SM/10691 | Augmentation | Construction Of Pump House (3.6x 3.0m) Including Sanitary Arrangement and Consruction of Boundary wall at 3rd Tube well Site at Palashipara Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | 1100/ND | 19/02/2024 | 360 | ROY CONSTRUCTION | 11.29 | 0 | 0 | 90
3024 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA , SM/10691 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 120 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Palshipara to accommodate FHTC within Tehatta-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | 4228/ND | 02/08/2024 | 180 | B.M. ENGINEERING & CONSTRUCTION | 296.87 | 0 | 0 | 0
3025 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA , SM/10691 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
3026 | NADIA | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dharmada-Muragaca Road 3.00 Kmp to 6.00kmp under Surf , SM/08889 | Retrofitting | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dharmada-Muragaca Road 3.00 Kmp to 6.00kmp under Surface water based water supply scheme (Northern Sector Part-III ) under Krishnagar Sub-division under Nadia Division, PH.E Dte. (Block- Krishnagar-II) | 555/PFMS | 23/02/2022 | 0 | APURBA MANDAL | 67.83 | 0 | 0 | 0
3027 | NADIA | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dharmada-Muragaca Road 3.00 Kmp to 6.00kmp under Surf , SM/08889 | Retrofitting | Providing FHTC(functional household tap connection ) by retrofitting under''Jalswapno"with utility shifting of water pipeline in connection to the work under Nadia Highway Division -I PWD(Roads) Dte. along Dharmada-Muragachha road3.00 kmp to 6.00kmp under surface based Water Supply scheme(Northern sector part III) under Krishnagar sub-division under Nadia Divn,PHE Dte. | 5695/ND | 03/11/2021 | 90 | APURBA MANDAL | 75.34 | 2.35 | 50 | 100
3028 | NADIA | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dharmada-Muragaca Road 3.00 Kmp to 6.00kmp under Surf , SM/08889 | Retrofitting | Material Requisition To Resource Division | 6831/ND | 17/11/2021 | 0 | Resource Division | 1.13 | 0 | 0 | 0
3029 | NADIA | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dharmada-Muragaca Road 3.00 Kmp to 6.00kmp under Surf , SM/08889 | Retrofitting | Material Requisition To Resource Division | 4310/ND | 29/09/2022 | 0 | Resource Division | 8.09 | 0 | 0 | 0
3030 | NADIA | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dharmada-Muragaca Road 3.00 Kmp to 6.00kmp under Surf , SM/08889 | Retrofitting | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.12.2023 to 31.12.2023 | 1260/KLYSD-I | 30/11/2023 | 31 | SUMAN CHAKRABORTY | 4.89 | 4.82 | 100 | 100
3031 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Madhugari Water Scheme Phase -I of Retrofitting under Jal Swapno Programme in Nadia District , SM/08127 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Madhugari W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte."(PART- B) | 2158/ND | 21/05/2021 | 45 | M/S KRISHNA MONDAL | 21.21 | 16.7 | 100 | 0
3032 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Madhugari Water Scheme Phase -I of Retrofitting under Jal Swapno Programme in Nadia District , SM/08127 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Madhugari W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | 2157/ND | 21/05/2021 | 45 | M/S KRISHNA MONDAL | 21.2 | 16.08 | 100 | 100
3033 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Madhugari Water Scheme Phase -I of Retrofitting under Jal Swapno Programme in Nadia District , SM/08127 | Retrofitting | Detailed study of Households/Habitations of Chhota Naldaha, Chilakhali, Chupria, Maheshpur, Nutangram, Pumlia, Sahebnagar, Tehatta, Uttampur and Teinpur Villages under Nadia District under the jurisdiction of Nadia Division, PHE Dte. | 1209/KLYSD-I | 17/11/2023 | 15 | TECHVISION | 2.79 | 2.79 | 100 | 100
3034 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Madhugari Water Scheme Phase -I of Retrofitting under Jal Swapno Programme in Nadia District , SM/08127 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 1.21 | 100 | 81
3035 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Birnagar Part-I, at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Birnagar Water Supply Scheme , SM/08010 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Birnagar, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Birnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 765/NAD-I | 04/05/2021 | 60 | UNICON INDIA | 93.41 | 133.1 | 142.81 | 100
3036 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia Part-II, at Santipur Block by retrofitting of Ground Water based PWSS for Beharia Water Supply Scheme , SM/08019 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Part-II at Santipur Block by retrofitting of Ground Water based PWSS for Beharia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 777/NAD-I | 05/05/2021 | 60 | J.D.J. ENTERPRISE | 97.11 | 29.74 | 100 | 50
3037 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia Part-II, at Santipur Block by retrofitting of Ground Water based PWSS for Beharia Water Supply Scheme , SM/08019 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Mouza-Beharia at Santipur Block by augmentation of Ground Water Based PWSS for Beharia W/S Scheme under Nadia Arsenic Division-I, PHE Dte (SL.NO.03) | 3326 / NAD-I | 16/12/2022 | 45 | CHOWDHURY & CO. | 67.83 | 67.7 | 99.81 | 100
3038 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia Part-II, at Santipur Block by retrofitting of Ground Water based PWSS for Beharia Water Supply Scheme , SM/08019 | Retrofitting | Pipeline connection with manifold to dedicated line under Jal Jeevan Mission (JJM) at Shantipur Block by retrofitting o Ground Water based PWSS for Beharia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. ¿ 01) | 28/AE-I/NAD-I | 19/01/2024 | 15 | DEBASHISH DEY | 0.96 | 0 | 0 | 100
3039 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VII, (Kumarpur), Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07451 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VII, (Kumarpur), Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 01) Tender No. - 208/NAD-I/2020-2021. | 91/NAD-I | 13/01/2021 | 45 | APURBA MANDAL | 46.77 | 19.08 | 39.12 | 100
3040 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VII, (Kumarpur), Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07451 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, Masra, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 773/NAD-I | 04/05/2021 | 60 | H I ENTERPRISE | 95.74 | 59.38 | 200 | 100
3041 | NADIA | Nadia Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08051 | Retrofitting | Providing Functional House Tap Connection from Badlangi Padmamala Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | 277/PFMS | 08/10/2021 | 0 | GHOSH CONSTRUCTION | 29.07 | 0 | 0 | 0
3042 | NADIA | Nadia Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08051 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Badlangi Padmamala Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | 2047/ND | 13/05/2021 | 60 | ONKAR ENTERPRISE | 41.53 | 57.46 | 138.36 | 100
3043 | NADIA | Nadia Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08051 | Retrofitting | Continuation for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department. | 578/ Kly SD-I | 30/06/2022 | 92 | SUMAN CHAKRABORTY | 4.89 | 4.89 | 100 | 0
3044 | NADIA | Nadia Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08051 | Retrofitting | Material Requisition To Resource Division | 95/ND | 06/01/2022 | 0 | Resource Division | 3.22 | 0 | 0 | 0
3045 | NADIA | Nadia Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08051 | Retrofitting | Material Requisition To Resource Division | 435/ND | 31/01/2022 | 0 | Resource Division | 2.39 | 0 | 0 | 0
3046 | NADIA | Nadia Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08051 | Retrofitting | Material Requisition To Resource Division | 3300/ND | 27/07/2022 | 0 | Resource Division | 22.42 | 0 | 0 | 0
3047 | NADIA | Nadia Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08051 | Retrofitting | Laying of Distribution System including specials & valves, pipe supporting structure all complete and Providing FHTC including supplying,laying,fitting, fixing of 15mm NB PVC(schedule 80)/ 20mm OD HDPE(PE100,PN16) pipe with all necessary specials,10mm gun metal ferrule,saddale piece etc.by retrofitting under Jal Swapna for Badlangi Padmamala Zone-II Water Supply Scheme in Nadia District under Nadia Division PHE Dte. | 662/ND | 11/02/2022 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 458.3 | 0 | 0 | 78
3048 | NADIA | Nadia Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08051 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Badlangi Padmamala Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | 2048/ND | 13/05/2021 | 60 | GHOSH CONSTRUCTION | 41.53 | 0 | 0 | 100
3049 | NADIA | Nadia Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08051 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Badlangi Padmamala Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | 2050/ND | 13/05/2021 | 45 | SUMIT GHOSH | 12.28 | 22.55 | 183.64 | 100
3050 | NADIA | Nadia Division | Providing Functional House Tap Connection from Madhpur Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08052 | Retrofitting | PROVIDING HOUSE CONNECTION INCLUDING SUPPLY OF 15MM DIA G.I/UPVC PIPE OF AVERAGE LENGTH OF 15 MTR. 10MM DIA GUN-METAL FERRULE, SADDLE PICE (AS REQUIRED SIZE), 15MM DIA BIB COCK ETC ALL COMPLETE AT MADHPUR W/S SCHEME UNDER NADIA DIVISION, PHE DTE (PART-B) |  | 26/02/2021 | 0 | CHAKRABORTTI ENTERPRISE | 23.9 | 0 | 0 | 0
3051 | NADIA | Nadia Division | Providing Functional House Tap Connection from Madhpur Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08052 | Retrofitting | PROVIDING HOUSE CONNECTION INCLUDING SUPPLY OF 15MM DIA G.I/UPVC PIPE OF AVERAGE LENGTH OF 15 MTR. 10MM DIA GUN-METAL FERRULE, SADDLE PICE (AS REQUIRED SIZE), 15MM DIA BIB COCK ETC ALL COMPLETE AT MADHPUR W/S SCHEME UNDER NADIA DIVISION, PHE DTE (PART-A) |  | 26/02/2021 | 0 | GHOSH ENTERPRISE | 23.95 | 0 | 0 | 0
3052 | NADIA | Nadia Division | Providing Functional House Tap Connection from Madhpur Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08052 | Retrofitting | Madhpur Water Supply Scheme Balance work of FHTC. | 200/TSD | 14/03/2022 | 10 | M/S CHANDIMATA CONSTRUCTION | 4.41 | 4.41 | 99.97 | 100
3053 | NADIA | Nadia Division | Providing Functional House Tap Connection from Madhpur Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08052 | Retrofitting | Providing Functional House Tap Connection from Madhpur Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | 606/PFMS | 11/03/2022 | 0 | OTHERS | 4.09 | 0 | 0 | 0
3054 | NADIA | Nadia Division | Providing Functional House Tap Connection from Madhpur Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08052 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Madhpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retrofitting) | 5361/ND | 30/09/2021 | 60 | M/S CHANDIMATA CONSTRUCTION | 55.05 | 48.6 | 88.28 | 0
3055 | NADIA | Nadia Division | Providing Functional House Tap Connection from Madhpur Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08052 | Retrofitting | Material Requisition To Resource Division | 801/ND | 18/02/2022 | 0 | Resource Division | 4.41 | 0 | 0 | 0
3056 | NADIA | Nadia Division | Providing Functional House Tap Connection from Madhpur Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08052 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 1.99 | 100 | 81
3057 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Barakulta Water Supply Scheme (For Byaspur & Takshali Mouzas) under Jal Swapno Program in Nadia District , SM/08057 | Retrofitting | Providing Functional Household Tap Connection from Barakulta Water Supply Scheme (For Byaspur & Takshali Mouzas) under Jal Swapno Program in Nadia District | 263/PFMS | 08/10/2021 | 0 | TARUN KUMAR BHATTACHARYA | 68.99 | 0 | 0 | 0
3058 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Barakulta Water Supply Scheme (For Byaspur & Takshali Mouzas) under Jal Swapno Program in Nadia District , SM/08057 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Barakulta W/S scheme(for Byaspur & Takshali Mouzas) in Nadia District under Nadia Division P.H.E. Dte. | 2192/ND | 24/05/2021 | 90 | TARUN KUMAR BHATTACHARYA | 86.32 | 16 | 18.53 | 100
3059 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Barakulta Water Supply Scheme (For Byaspur & Takshali Mouzas) under Jal Swapno Program in Nadia District , SM/08057 | Retrofitting | Material Requisition To Resource Division | 4330/ND | 29/09/2022 | 0 | Resource Division | 8.96 | 0 | 0 | 0
3060 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Dafarpota(Zone-II) water supply scheme under Jal Swapno Program in Nadia District (Phase-II, Retrofitting) , SM/08058 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Daforpota (Zone-II) W/S scheme in Nadia District under Nadia Division P.H.E. Dte." (Phase - I, Retrofitting) | 2994/ND | 29/07/2021 | 60 | SANJOY BAKSHI | 24.91 | 38.49 | 154.52 | 0
3061 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Dafarpota(Zone-II) water supply scheme under Jal Swapno Program in Nadia District (Phase-II, Retrofitting) , SM/08058 | Retrofitting | Material Requisition To Resource Division | 789/ND | 18/02/2022 | 0 | Resource Division | 2.37 | 0 | 0 | 0
3062 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II Nabadwip (Part) Block (Phase-A). , SM/07468 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II Nabadwip (Part) Block (Phase-A). | 181/PFMS | 15/09/2021 | 0 | SATYABRATA CHAKRABORTY | 74.21 | 0 | 0 | 0
3063 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II Nabadwip (Part) Block (Phase-A). , SM/07468 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II Nabadwip (Part) Block (Phase-A). |  | 24/03/2021 | 0 | SATYABRATA CHAKRABORTY | 21.89 | 0 | 0 | 0
3064 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II Nabadwip (Part) Block (Phase-A). , SM/07468 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-III, Z-IV, WITHIN KRISHNAGAR-2 AND NABADWIP BLOCK, PHASE-A. | 498/PFMS | 03/02/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 0.82 | 0 | 0 | 0
3065 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II Nabadwip (Part) Block (Phase-A). , SM/07468 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-IV, within Krishnagar-II & Nabadwip Block (Phase-A, Retrofitting)" | 776/ND | 10/02/2021 | 90 | SATYABRATA CHAKRABORTY | 97.11 | 43.78 | 45.08 | 0
3066 | NADIA | Nadia Division | Providing Functional House Tap Connection from Pansila Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07472 | Retrofitting | Continuation for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department. | 1072/Kly SD-I | 30/11/2022 | 90 | SUMAN CHAKRABORTY | 4.89 | 4.89 | 100 | 0
3067 | NADIA | Nadia Division | Providing Functional House Tap Connection from Pansila Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07472 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Pansila W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Phase-I, Retrofitting)" (Part-2) | 2028/ND | 12/05/2021 | 45 | TARUN KUMAR BHATTACHARYA | 23.76 | 21.17 | 100 | 0
3068 | NADIA | Nadia Division | Providing Functional House Tap Connection from Pansila Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07472 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Pansila W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Phase-I, Retrofitting) (Part-3) | 2029/ND | 12/05/2021 | 60 | TARUN KUMAR BHATTACHARYA | 35.27 | 28.21 | 100 | 100
3069 | NADIA | Nadia Division | Providing Functional House Tap Connection from Pansila Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07472 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Pansila W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Phase-I, Retrofitting) (Part-1). | 2027/ND | 12/05/2021 | 60 | TARUN KUMAR BHATTACHARYA | 35.26 | 31.73 | 100 | 100
3070 | NADIA | Nadia Division | Providing Functional House Tap Connection from Pansila Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07472 | Retrofitting | Material Requisition To Resource Division | 787/ND | 18/02/2022 | 0 | Resource Division | 1.1 | 0 | 0 | 0
3071 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-III within Nakashipara Block (Phase-A) , SM/07499 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-III within Nakashipara Block (Phase-A). |  | 24/03/2021 | 0 | MADE & TRADE CO. | 89.45 | 0 | 0 | 0
3072 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-III within Nakashipara Block (Phase-A) , SM/07499 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-II, Z-III, WITHIN NAKASHIPARA BLOCK, PHASE-A. | 497/PFMS | 03/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.45 | 0 | 0 | 0
3073 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-III within Nakashipara Block (Phase-A) , SM/07499 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-III within Nakashipara Block ( Phase -A) | 243/ND | 15/01/2021 | 90 | MADE & TRADE CO. | 96.84 | 192.02 | 198.28 | 0
3074 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-II within Nakashipara Block (Phase-A) , SM/07500 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-II within Nakashipara Block (Phase-A) | 592/PFMS | 04/03/2022 | 0 | MONDAL PRECISION PRIVATE LIMITED | 62.51 | 0 | 0 | 0
3075 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-II within Nakashipara Block (Phase-A) , SM/07500 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-II within Nakashipara Block (Phase-A) | 565/PFMS | 25/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.45 | 0 | 0 | 0
3076 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-II within Nakashipara Block (Phase-A) , SM/07500 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-II within Nakashipara Block ( Phase -A) | 242/ND | 15/01/2021 | 90 | MONDAL PRECISION PRIVATE LIMITED | 96.61 | 31.18 | 100 | 100
3077 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-II within Nakashipara Block (Phase-A) , SM/07500 | Retrofitting | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- II/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4651/ND | 10/10/2023 | 720 | SATYABRATA CHAKRABORTY | 484.95 | 0 | 0 | 15
3078 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-C) , SM/07505 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-C) |  | 04/10/2021 | 0 | UMWELT ENGINEERS PVT LTD | 62.5 | 0 | 0 | 0
3079 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-C) , SM/07505 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) | 280/PFMS | 08/10/2021 | 0 | UMWELT ENGINEERS PVT LTD | 62.5 | 0 | 0 | 0
3080 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-C) , SM/07505 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-IV within Nakashipara Block(Phase-C) in Nadia District under Nadia Division P.H.E.Dte.(SL.1) | 972/ND | 25/02/2021 | 90 | UMWELT ENGINEERS PVT LTD | 97 | 27.21 | 100 | 0
3081 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-C) , SM/07505 | Retrofitting | Material Requisition To Resource Division | 4282/ND | 29/09/2022 | 0 | Resource Division | 12.52 | 0 | 0 | 0
3082 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-C) , SM/07505 | Retrofitting | Construction of OHR, repair and renovation of staff room, repair of boundary wall, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-IV / C (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11842]. | 5557/ND | 12/12/2023 | 722 | APURBA MANDAL | 239.4 | 0 | 0 | 10
3083 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Lakshmipur water supply scheme under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07299 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Lakshmipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1361/NACD-II | 29/12/2020 | 60 | APURBA MANDAL | 44.32 | 88.07 | 198.72 | 0
3084 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Damodarkhali water supply scheme under Krishnagar-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07935 | Retrofitting | Work of Survey, Design, Drawing & DPR preparation for DAMODARKHALI Water Supply Scheme in KRISHNANAGAR-I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 4/AE-I/NACD-II | 06/05/2021 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 3.88 | 4 | 200 | 0
3085 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Damodarkhali water supply scheme under Krishnagar-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07935 | Retrofitting | Material Requisition To Resource Division | 852/NACD-II | 03/11/2021 | 0 | Resource Division | 119.54 | 0 | 0 | 0
3086 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-II Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08851 | Retrofitting | Material Requisition To Resource Division | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 24.52 | 0 | 0 | 0
3087 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-II Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08851 | Retrofitting | Providing FHTC (Functional Household Tap Connection) by retrofitting/rejuvenation under Jaldhara/Jal Swapna for Arranghata Zone-II W/S Scheme, Phase-II at Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. | 643/NAD-I | 29/04/2022 | 90 | UNICON INDIA | 335.39 | 0 | 0 | 10
3088 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-II Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08851 | Retrofitting | Providing FHTC (Functional Household Tap Connection) by retrofitting/rejuvenatioin under Jal Jeevan Mission Aranghata Zone- II W/S Scheme, Part - II at Ranaghat- II Block under Nadia Arsenic Division-I, PHE Dte. (Sl.no.01) | 1696/NAD-I | 13/07/2023 | 782 | ORIENT CONSTRUCTION | 311.77 | 207.55 | 66.57 | 90
3089 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-II Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08851 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Dhara / Jal Swapna for Aranghata Zone-II Part -III under Jal Jeevan Mission at Ranaghat -II Block by retrofitting of ground Water based PWSS for Aranghata Zone-II Water Supply Scheme under Nadia Arsenic Division -I, PHE Dte. | 461/NAD-I | 15/03/2024 | 382 | DIVINE | 329.47 | 0 | 0 | 75
3090 | NADIA | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia Highway Division I PWD (Roads)Dte along Dharmada-Muragaca Road 0.00 Kmp to 3.00kmp under Surf , SM/08888 | Retrofitting | FHTC in connection with Utility Shifting of Water pipeline in connection to the work under Nadia Highway Division-I(PWD Road) dte. along Dharmadah-Muragachha Road 0.00 Kmp to 3.00 Kmp under surface water based water supply scheme (Northern Sector Part-II) under Debagram Sub-Division under Nadia Division,PHE Dte. | 216/PFMS | 28/09/2022 | 0 | TARUN KUMAR BHATTACHARYA | 87.14 | 0 | 0 | 0
3091 | NADIA | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia Highway Division I PWD (Roads)Dte along Dharmada-Muragaca Road 0.00 Kmp to 3.00kmp under Surf , SM/08888 | Retrofitting | FHTC in connection with Utility Shifting of Water pipeline in connection to the work under Nadia Highway Division-I(PWD Road) dte. along Dharmadah-Muragachha Road 0.00 Kmp to 3.00 Kmp under surface water based water supply scheme (Northern Sector Part-II) under Debagram Sub-Division under Nadia Division,PHE Dte. | 7329/ND | 22/12/2021 | 90 | TARUN KUMAR BHATTACHARYA | 108.36 | 7.15 | 7.58 | 98
3092 | NADIA | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia Highway Division I PWD (Roads)Dte along Dharmada-Muragaca Road 0.00 Kmp to 3.00kmp under Surf , SM/08888 | Retrofitting | Material Requisition To Resource Division | 808/ND | 18/02/2022 | 0 | Resource Division | 6.92 | 0 | 0 | 0
3093 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Shyamnagar water supply scheme under Krishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08248 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Shyamnagar (Vill-Bishnupur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1183/NACD-II | 13/11/2020 | 25 | R.M. TRADING | 4.99 | 0 | 0 | 0
3094 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/09451 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | 607/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.82 | 0 | 0 | 0
3095 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/09451 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accomodate FHTC under DAKSHIN JHITKIPOTA(Z-1I) W/S Scheme, Block-Krishnagar-I, Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 09) | 411EMD | 20/01/2023 | 30 | M.S.C. ENTERPRISE | 14.9 | 13.74 | 100 | 90
3096 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/09451 | Augmentation | Continuation for Payment of remuneration for engagement of 10 nos. personnel (One Chemist / Bacteriologist and one Lab Assistant) at 5 Nos. Sub-District Laboratories under Nadia Division, P.H.E. Dte. on contractual basis w.e.f. 01.07.2023 to 31.08.2023 (Two Month). | 2831/ND | 28/06/2023 | 61 | CLIFFORD FACILITY SERVICES PVT. LTD | 2.73 | 2.73 | 100 | 100
3097 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/09451 | Augmentation | Material Requisition To Resource Division | 444/ND | 31/01/2022 | 0 | Resource Division | 1.39 | 0 | 0 | 0
3098 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/09451 | Augmentation | Material Requisition To Resource Division | 4295/ND | 29/09/2022 | 0 | Resource Division | 12.3 | 0 | 0 | 0
3099 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/09451 | Augmentation | Material Requisition To Resource Division | 1998/ND | 08/05/2023 | 0 | Resource Division | 0.92 | 0 | 0 | 0
3100 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/09451 | Augmentation | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. bill for the month of Juluy under AE/EMSD-II Bhatjangla Dist Nadia |  | 13/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.09 | 0 | 0 | 0
3101 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/09451 | Augmentation | LAYING OF PIPELINE UNDER PALASHIPARA PWSS FROM PALASHIPARA BAZAR TO BURNIA BUS STAND. | 241/1/PFMS | 18/08/2023 | 0 | OTHERS | 49.99 | 0 | 0 | 0
3102 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/09451 | Augmentation | LAYING OF DISTRIBUTION SYSTEM INCLUDING SPECIALS, VALVES & PIPE SUPPORTING STRUCTURE ALL COMPLETE BASED ON ACTUAL ESTIMATE & PROVIDING FHTC FOR DAKHIN JHITKAPOTA ZONE - II WATER SUPPLY SCHEME IN NADIA DISTRICT UNDER NADIA DIVISION. | 923/ND | 24/02/2022 | 90 | SATYABRATA CHAKRABORTY | 282.53 | 120.35 | 42.6 | 68
3103 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/09451 | Augmentation | Continuation of Wall Writing Work under Nadia Division P. H. Engineering Dte. | 3445/ND | 20/06/2024 | 30 | IMAGIN | 20.46 | 5.11 | 100 | 100
3104 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/09451 | Augmentation | Wall Writing Work under Nadia Division P. H. Engineering Dte. | 1821/ND | 14/03/2024 | 31 | IMAGIN | 34.21 | 5.78 | 100 | 60
3105 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/09451 | Augmentation | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues Under Jal Jeevan Mission (JJM) Support Activities. [Phase-II] | 6161/ND | 26/12/2023 | 183 | IMAGIN | 74.48 | 11.92 | 100 | 100
3106 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/09451 | Augmentation | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | 6305/ND | 26/09/2024 | 30 | IMAGIN | 34.21 | 0 | 0 | 100
3107 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/09451 | Augmentation | Payment to Ministry of Railway regarding railway crossing, Application ID- ER-SDAH-2024-WL-134, (1) AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION, (2) AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | 311/PFMS | 02/10/2024 | 0 | MINISTRY OF RAILWAYS, EASTERN RAILWAY, SEALDAH DIVISION | 0 | 0 | 0 | 0
3108 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/09451 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 83 m3/hr at Dakshin Jhitkipota Zone-II Water Supply Scheme including 3 Months Trial Run & 3 Years O&M within Krishnagar-I block under Krishnagar Sub-division under Nadia Division, P.H.E. Dte. | 1320/ND | 27/02/2024 | 360 | WIST WATER SOLUTIONS PVT LTD | 230.17 | 0 | 0 | 31
3109 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/09451 | Augmentation | Repair and renovation works of R.C.C. Elevaced Reservoir 350 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Dakshin Jhitkipota Zone-II Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 4580/ND | 21/08/2024 | 405 | MONDAL CONSTRUCTION | 20.42 | 0 | 0 | 0
3110 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte , SM/09451 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at DAKSHIN JHITKIPOTA ZONE-II W/S Scheme Block- Krishnagar-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/09451] | 1145/EMD | 04/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 38.68 | 0 | 0 | 0
3111 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10414 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | 11/PFMS | 11/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.93 | 0 | 0 | 0
3112 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10414 | Augmentation | Material Requisition To Resource Division | 156/ND | 06/01/2023 | 0 | Resource Division | 40.09 | 0 | 0 | 0
3113 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10414 | Augmentation | Material Requisition To Resource Division | 2316/ND | 29/05/2023 | 0 | Resource Division | 27.29 | 0 | 0 | 0
3114 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10414 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 83 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Betai Zone-II to accommodate FHTC under Tehatta Sub-division under Nadia Division, PHE Dte. | 4350/ND | 07/08/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 227.43 | 0 | 0 | 0
3115 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10414 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BETAI (ZONE-I) W/S Scheme, Block-Tehatta-I, Dist. - Nadia. NIET NO. 25 OF EE/EMD OF 2022-23 (SL. NO. 05) | 811/EMD | 16/02/2023 | 685 | A.K. ENTERPRISE | 24.7 | 18.36 | 75.87 | 80
3116 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10414 | Augmentation | Construction of 4.88 mtr. x 3.66 mtr. Size pump house including Sanitary Arrangement at third Tube well site under Betai Zone I Water Supply Scheme under Nadia Division PHE Dte. | 4322/ND | 26/09/2023 | 90 | TOTAN DAS | 6.75 | 6.45 | 100 | 100
3117 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10414 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Betai W/S Scheme (Z-I,T/W-I) , Tehatta-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 898/CDD | 18/07/2023 | 237 | DIPALI CONSTUCTION | 18.57 | 14.44 | 100 | 100
3118 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10414 | Augmentation | Collection of Household data through mobile app for FHTC Connection (Phase-IV), under Nadia Division, P.H.E. Dte. | 210/KLYSD-I | 09/02/2024 | 182 | HORIZEN | 4.85 | 4.85 | 100 | 100
3119 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10414 | Augmentation | Quotation for new service connection at P.H-III under Betai Zone-I W/S Scheme, Dist-Nadia | BP-284-23-24 | 16/02/2024 | 0 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 10.9 | 0 | 0 | 0
3120 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10414 | Augmentation | Laying of Distribution System Including Specials, Valves & Pipe Supporting Structure All Complete, Augmentation Of Rising Main System, Providing FHTC, Construction Of 550 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (With Pile Foundation), Pipe Connection And Cost Of Pipes, Specials And Soil Investigation For Construction Of One No. 550 Cum OHR Of Staging Height 20 Mtr Under Augmentation Of Ground Water Based Water Supply Scheme For Betai Zone-I To Accommodate FHTC under Nadia Divn, PHE Dte. | 875/ND | 01/03/2023 | 366 | M/S S.S ENTERPRISE | 610.04 | 327.51 | 53.69 | 54
3121 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10414 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 122 cum/hour capacity for Augmentation of Ground Based Water Supply Scheme at Betai Zone-I to accommodate FHTC including 3 Months Trial Run & 3 Years O&M under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | 1492/ND | 04/03/2024 | 540 | MONDAL PRECISION PRIVATE LIMITED | 302.94 | 0 | 0 | 0
3122 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10414 | Augmentation | Construction of Boundary wall at Head Work Site & 2nd Tube Well ,3rd Tube Well site of Betai Zone- I Ground water based water supply scheme under Tehatta Sub-Division PHE Dte. | 1627/ND | 07/03/2024 | 361 | GANGULY ENTERPRISE | 23.18 | 4.04 | 17.44 | 40
3123 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10414 | Augmentation | Continuation for Hiring of Diesel Driven Motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Calcutta Mechanical Sub Division-ll (D),CDD, P.H.Enginering Dte. for supervision of JJM Related works. | 153/CMSD-II(D) | 30/07/2024 | 184 | MD NIZAMUDDIN | 0.87 | 2.15 | 246.39 | 0
3124 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. , SM/10414 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Betai Zone-I ground water based water supply scheme under Block_Tehatta-I Dist. - Nadia under EMD, PHE Dte. SM/10414 | 1119/EMD | 04/06/2025 | 90 | MA ANNAPURNA ENTERPRISE | 24.48 | 0 | 0 | 0
3125 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10472 | Augmentation | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | 27/PFMS | 20/05/2022 | 0 | ENVIROTECH SOLUTIONS | 2.56 | 0 | 0 | 0
3126 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10472 | Augmentation | Sinking of 1 no. Tubewell 300mm. x 200mm. dia and 150 mtr deep by direct rotary rig method for Teinpur Zone-II PWSS within Karimpur-II block under RWS Nadia sub-division under Nadia Division, PHE Dte. (SM / 10472) | 2105/ND | 15/05/2023 | 45 | MANISHIKA CONSTRUCTION | 14.18 | 12.16 | 100 | 100
3127 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10472 | Augmentation | Material Requisition To Resource Division | 3896/ND | 08/09/2022 | 0 | Resource Division | 39.48 | 0 | 0 | 0
3128 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10472 | Augmentation | Material Requisition To Resource Division | 4327/ND | 29/09/2022 | 0 | Resource Division | 2.69 | 0 | 0 | 0
3129 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10472 | Augmentation | Material Requisition To Resource Division | 3786/ND | 24/08/2023 | 0 | Resource Division | 1.6 | 0 | 0 | 0
3130 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10472 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under TEINPUR (ZONE-I ,II, III & IV) W/S Scheme, Block- Karimpur-II , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 06) | 500/EMD | 24/01/2023 | 30 | M/S DILIP MITRA | 64.62 | 10.18 | 100 | 85
3131 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10472 | Augmentation | Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | 3450/ND | 20/06/2024 | 45 | IMAGIN | 19.44 | 8.84 | 100 | 100
3132 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10472 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Teinpur Zone-II to accommodate FHTC within Karimpur-II block under RWS Sub-Division under Nadia Division, PHE Dte. | 3818/ND | 05/09/2022 | 810 | CHANDAN ROY | 183.58 | 148.46 | 80.87 | 100
3133 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10472 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site of Teinpur zone-II PWSS under Karimpur-II Block under RWS Sub Division under Nadia Division-,P.H.E Dte. | 7003/ND | 26/11/2024 | 360 | DURGADAS BASU | 22.95 | 0 | 0 | 40
3134 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10472 | Augmentation | Repairing Works Of Tenpur (Zone-II) Water Supply Scheme,Karimpur-I Block Under RWS Nadia Sub Division, P.H.E. Dte. | 3264/ND | 10/06/2024 | 540 | DURGADAS BASU | 25.29 | 10.53 | 41.65 | 45
3135 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10472 | Augmentation | Conversion of IEP to AIRP of capacity 32 Cu.m/hr at Teinpur Zone-II Water Supply Scheme within Karimpur-II block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. | 1910/ND | 15/03/2024 | 120 | MONDAL ENTERPRISE | 124.86 | 0 | 0 | 30
3136 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10472 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House and allied works for Fazilnagar within Karimpur-II Block Under Tehatta Sub-Division under Nadia Division P.H.E. Dte. | 660/ND | 11/02/2025 | 270 | U-TURN CONSTRUCTION | 50.44 | 0 | 0 | 70
3137 | NADIA | Nadia Division | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia , SM/10076 | Augmentation | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia | 673/PFMS | 24/03/2022 | 0 | RADIANT | 2.79 | 0 | 0 | 0
3138 | NADIA | Nadia Division | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia , SM/10076 | Augmentation | Material Requisition To Resource Division | 1397/ND | 24/03/2022 | 0 | Resource Division | 31.75 | 0 | 0 | 0
3139 | NADIA | Nadia Division | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia , SM/10076 | Augmentation | Material Requisition To Resource Division | 149/ND | 06/01/2023 | 0 | Resource Division | 43.07 | 0 | 0 | 0
3140 | NADIA | Nadia Division | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia , SM/10076 | Augmentation | Material Requisition To Resource Division | 1904/ND | 27/04/2023 | 0 | Resource Division | 57.16 | 0 | 0 | 0
3141 | NADIA | Nadia Division | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia , SM/10076 | Augmentation | Material Requisition To Resource Division | 4221/ND | 19/09/2023 | 0 | Resource Division | 42 | 0 | 0 | 0
3142 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia , SM/10076 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MAHISBATHAN W/S Scheme, Block- Karimpur-II & ANDHARKOTA W/S Scheme, Block- Karimpur-I, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 01) | 1200/EMD | 22/03/2023 | 30 | KARTICK BAL | 61.1 | 26.46 | 86.62 | 70
3143 | NADIA | Nadia Division | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia , SM/10076 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 1.4 | 24.68 | 40
3144 | NADIA | Nadia Division | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia , SM/10076 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete And Construction of 550 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of 550 CUM OHR for Augmentation of Ground Based Water Supply Scheme at Mahisbathan to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 3449/ND | 09/08/2023 | 731 | M/S DIPAK ENTERPRISE, GHOSH PARA,WARD NO-4, KALYANI, NADIA-741235 WEST BENGAL | 560.56 | 283.85 | 50.64 | 55
3145 | NADIA | Nadia Division | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia , SM/10076 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangemen At Hw Site At Mahisbathan Water Supply Scheme Under Kalyani Sub Division I PHE Dte) | 4531/ND | 20/08/2024 | 180 | M/S BISWAS ENTERPRISE | 6.96 | 0 | 0 | 0
3146 | NADIA | Nadia Division | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia , SM/10076 | Augmentation | Construction of boundary wall and repairing of pump house cum chlorin room at head work site,2nd tubewell site and alide work under Mahisbathan PWSS kalyani sub division-I under Nadia Division PHE Dte. | 280/ND | 16/01/2025 | 90 | ZOOM CONSTRUCTION & INTERIO | 45.1 | 0 | 0 | 0
3147 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia , SM/10076 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Mahishbathan ground water based water supply scheme under Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. SM/10076 | 1107/EMD | 04/06/2025 | 90 | S.P CONSTRUCTION | 20.8 | 0 | 0 | 0
3148 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VIII (BARBERIA), Zone-X (SHIMURALI) & Zone-XI (CHANDURIA) at chakdaha , SM/09962 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Dhara/Jal Swapna for Zone-VIII (Barberia) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 430/NAD-I | 07/03/2022 | 60 | SANDIP BISWAS | 85.12 | 76.25 | 100 | 100
3149 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VIII (BARBERIA), Zone-X (SHIMURALI) & Zone-XI (CHANDURIA) at chakdaha , SM/09962 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X (Shimurali) Part III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 04) | 431/NAD-I | 07/03/2022 | 60 | CHAKRABORTTI ENTERPRISE | 67.64 | 61.1 | 100 | 100
3150 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VIII (BARBERIA), Zone-X (SHIMURALI) & Zone-XI (CHANDURIA) at chakdaha , SM/09962 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XI (Chanduria) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 05) | 432/NAD-I | 07/03/2022 | 60 | SANJOY BAKSHI | 78.61 | 78.29 | 100 | 100
3151 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VIII (BARBERIA), Zone-X (SHIMURALI) & Zone-XI (CHANDURIA) at chakdaha , SM/09962 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 12/NAD-I | 05/01/2022 | 90 | UMWELT ENGINEER PVT. LTD. | 299.45 | 209.36 | 100 | 98
3152 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VIII (BARBERIA), Zone-X (SHIMURALI) & Zone-XI (CHANDURIA) at chakdaha , SM/09962 | Augmentation | Repair of 950 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at Chanduria Zone-XI under Surface W/S Scheme of Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte.( Sl.no . 04) | 1636/NAD-I | 06/09/2022 | 45 | M/S R.K. ENTERPRISE | 37.67 | 37.52 | 100 | 100
3153 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VIII (BARBERIA), Zone-X (SHIMURALI) & Zone-XI (CHANDURIA) at chakdaha , SM/09962 | Augmentation | Retrofitting work of Chanduria Zone XI at Priyanagar New Kautukpur Kautukpur Jibannagar village under Chakdah Block of PWSS for Chakdah Surface water supply scheme under NAD I PHE Dte ( Sl.no. 09) | 1960 / NAD-I | 12/10/2022 | 60 | MADE AND TRADE CO. | 15.76 | 15.75 | 100 | 100
3154 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VIII (BARBERIA), Zone-X (SHIMURALI) & Zone-XI (CHANDURIA) at chakdaha , SM/09962 | Augmentation | Retrofitting work of Barberia, Zone-VIII, at Chakdah Block of PWSS for Chakdah Surface Water Supply Scheme under Nadia arsenic Division-I, P.H.E. Dte. (Sl No.-01) | 87/ AE-II/ NAD-I | 30/06/2022 | 30 | UMWELT ENGINEER PVT. LTD. | 3.89 | 3.89 | 100 | 100
3155 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BALIBANGA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09253 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Baliadanga ( Vill- Baro Baliadanga) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 38/NACD-II | 14/01/2022 | 45 | TARUN GHOSH | 79.94 | 79.93 | 99.99 | 100
3156 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BALIBANGA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09253 | Augmentation | OUTSTANDING BILL PAYMENT FOR SUPPLY OF MATERIALS FOR THANAPARA, DAMODARKHALI, MADHABPUR, BALIADANGA AS FRAMED BY RESOURCE DIVISION PHE DTE. |  | 05/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0 | 0
3157 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BALIBANGA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09253 | Augmentation | RESOURCES PAYMENT FOR MATERIALS | 223 | 02/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 19.04 | 0 | 0 | 0
3158 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BALIBANGA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09253 | Augmentation | Outstanding bill payment |  | 02/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 19.04 | 0 | 0 | 0
3159 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BALIBANGA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09253 | Augmentation | SUPPLY OF MATERIALS FOR THANAPARA,DAMODARKHALI,MADHABPUR AND BALIADANGA W/S. SCHEME UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. |  | 07/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0 | 0
3160 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BALIBANGA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09253 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Baliadanga W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 124/NACD-II | 21/02/2022 | 90 | SINGHA ROY & CO. | 138.93 | 138.92 | 100 | 100
3161 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BALIBANGA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09253 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Balibanga) | 1295/NACD-II | 23/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
3162 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED BALIBANGA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09253 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BALIBANGA, GONGRA, LAKSHMIPUR, MAHESHPUR & TENGRA(Block-Chapra) W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 06) | 1502/EMD | 18/04/2023 | 30 | M.S.C. ENTERPRISE | 8.84 | 8.84 | 100 | 70
3163 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BALIBANGA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09253 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Baliadanga W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | 526./AE-I/NACD-II | 18/12/2023 | 15 | SHYAMAL KANTI GHOSH | 0.97 | 0.96 | 100 | 100
3164 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BALIBANGA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09253 | Augmentation | Laying UPVC pipeline for supplying drinking water to Baliadanga village including reconnection of existing FHTCs in Chapra Block of Baliadanga W/S Scheme under Nadia Arsenic Civil Division-II, PHE Dte | 517/AE-I/NACD-II | 18/12/2023 | 15 | JOY HIND TUBEWELLS | 0.97 | 0.97 | 100 | 100
3165 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BALIBANGA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09253 | Augmentation | Jungle cutting at Mahatpur,Patharghata,Baliadanga,Helenchi Zone-III,Joyghata and Damodarkhali Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 820/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.16 | 0.01 | 100 | 100
3166 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BALIBANGA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09253 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Baliadanga Water Supply Scheme in CHAPRA Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 320/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 0.96 | 0.96 | 100 | 100
3167 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED BALIBANGA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09253 | Augmentation | Conversion of IEP to AIRP at Balidanga Water Supply Scheme of capacity 58 Cu.m/hr in Chapra Block including other works at Bhatgachhi & Karuigachhi Water Supply Scheme under Nadia Arsenic Civil Division -II, PHE Dte. | 1048/NACD-II | 07/08/2024 | 60 | DEBASIS SAMADDAR | 185.55 | 0 | 0 | 0
3168 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Earth work in filling in ditches at Khaspu 2nd Tube Well Site for development of land in connection with proposed T/W Sinking & Pump House construction at Khaspu Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 62/AE-II/NACD-II | 28/06/2022 | 15 | BASUDEB SAHA | 0.6 | 0.6 | 100 | 100
3169 | NADIA | Eastern Mechanical | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | New connection charges for Khaspur PHE I Tehatta Nadia. Memo no. 3004031111/Quot/03 |  | 21/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.5 | 0 | 0 | 0
3170 | NADIA | Eastern Mechanical | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | New connection charges for Khaspur PHE I Tehatta Nadia. Memo no. 3004031098/Quot/03 |  | 21/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.07 | 0 | 0 | 0
3171 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
3172 | NADIA | Eastern Mechanical | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | New Service Connection for PH No.-I under Khaspur Tehatta Nadia | 91/EMD | 26/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.07 | 0 | 0 | 0
3173 | NADIA | Eastern Mechanical | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | New Service Connection for PH No.-II under Khaspur Tehatta Nadia | 92/EMD | 26/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.5 | 0 | 0 | 0
3174 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
3175 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Dhopahat and Khaspu Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 242/NACD-II | 19/04/2022 | 60 | AUXILIARY TUBE WELL DRILLERS | 43.18 | 9.78 | 70.24 | 100
3176 | NADIA | Eastern Mechanical | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Supply delivery of PCC pole, M.S materials and electrical accessories including stringing and sagging of LTOH line to WBSEDCL for new service connection P.H No. II under Khaspur w/s scheme under EMSD III, PHE Dte. Dhubulia Nadia. | 108/EMSDIII18.01.23 | 14/08/2022 | 122 | MA ANNAPURNA ENTERPRISE | 3.12 | 3.12 | 100 | 0
3177 | NADIA | Eastern Mechanical | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | PCC pole M.S materials and electrical accessories including stringing and sagging of HTOH line to WBSEDCL for new service connection at PH-I under Khaspu W/S scheme. | 103/EMSD-I | 18/01/2023 | 30 | SHIVAM ENTERPRISE | 3.8 | 3.8 | 100 | 0
3178 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Khaspu water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 218/NACD-II | 05/04/2022 | 60 | PAPAN ROY | 5.37 | 5.37 | 100 | 100
3179 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Laying of Rising Main of Khaspu Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | 21/AE-II/NACD-II | 18/04/2022 | 30 | A.K ADHIKARY | 4.14 | 4.12 | 100 | 100
3180 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Khaspu Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 626/NACD-II | 06/09/2022 | 20 | RAMASISH ENTERPRISE | 4.6 | 4.6 | 100 | 100
3181 | NADIA | Eastern Mechanical | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) under Khaspu W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 05) | 6261/EMD | 19/11/2022 | 30 | SHIVAM ENTERPRISE | 9.98 | 9.91 | 100 | 90
3182 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Khaspu Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | 86/NACD-II | 10/01/2023 | 60 | BURIMA CONSTRUCTION | 16.35 | 16.34 | 100 | 100
3183 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Khaspu 2nd Tubewell Site within Khaspu Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 125/NACD-II | 11/01/2023 | 60 | SHYAMAL KANTI GHOSH | 6.31 | 5.06 | 100 | 85
3184 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS: Khaspu) | 862/NACD-II | 10/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
3185 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Khaspu water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | 16/AE-II/NACD-II | 11/04/2022 | 60 | PAPAN ROY | 2.83 | 2.81 | 100 | 100
3186 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Material Requisition To Resource Division | 405/NACD-II | 04/07/2022 | 0 | Resource Division | 35.72 | 0 | 0 | 0
3187 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Khaspu and adjoining mouzas under Khaspur Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | 293/NACD-II | 18/05/2022 | 90 | SUDHAMAY MAJUMDAR | 169.33 | 147.1 | 86.87 | 100
3188 | NADIA | Eastern Mechanical | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.II under Khaspu W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 06) | 6260/EMD | 19/11/2022 | 30 | A.D. CONCERN | 10 | 9.78 | 100 | 100
3189 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Construction of approch road at Head Works site of Khaspu Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | 412/AE-I/NACD-II | 08/08/2023 | 15 | BIDYUT KUMAR | 0.97 | 0.93 | 100 | 100
3190 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Khaspu) | 435/NACD-II | 15/03/2024 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
3191 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Khaspu, Patharghata and Chanderghat PWSS in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 293_AE-II/NACD-II | 30/08/2024 | 20 | MAKALI ENGINEERING CORPORATION | 4.83 | 4.83 | 100 | 100
3192 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Construction of 75 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Thanarpara Zone-III Water Supply Scheme in Karimpur-II block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | 1207/NACD-II | 04/09/2024 | 180 | SINGHA ROY & CO. | 215.53 | 0 | 0 | 0
3193 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 34 cum/Hour capacity for Khaspu Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1191/NACD-II | 02/09/2024 | 180 | MONDAL PRECISION PRIVATE LIMITED | 164.15 | 86.62 | 60 | 35
3194 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Laying of distribution system including providing FHTC at left out households for Bahadurpur, Khaspu, Dhopahat and Rajapur W/s Scheme and restoration of the damaged portion of roads in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte and Brittihuda W/S Scheme & Barnia W/S Scheme included. | 736/NACD-II | 18/06/2025 | 90 | JOY HIND TUBEWELLS | 186.42 | 0 | 0 | 40
3195 | NADIA | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME , SM/10402 | New | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Khaspu water supply scheme of Tehatta-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | 526/NACD-II | 08/05/2023 | 694 | BIDYUT KUMAR | 117.34 | 85.28 | 74.19 | 65
3196 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. , SM/10034 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | 728/PFMS | 30/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.09 | 0 | 0 | 0
3197 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. , SM/10034 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | 87/PFMS | 22/07/2022 | 0 | M/S S.S ENTERPRISE | 187.3 | 0 | 0 | 0
3198 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. , SM/10034 | Augmentation | Material Requisition To Resource Division | 1253/ND | 16/03/2022 | 0 | Resource Division | 19.78 | 0 | 0 | 0
3199 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. , SM/10034 | Augmentation | Material Requisition To Resource Division | 445/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0 | 0
3200 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. , SM/10034 | Augmentation | Material Requisition To Resource Division | 1019/ND | 03/03/2022 | 0 | Resource Division | 22.52 | 0 | 0 | 0
3201 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. , SM/10034 | Augmentation | Material Requisition To Resource Division | 2507/ND | 08/06/2022 | 0 | Resource Division | 4.25 | 0 | 0 | 0
3202 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. , SM/10034 | Augmentation | Material Requisition To Resource Division | 1392/ND | 24/03/2022 | 0 | Resource Division | 16.87 | 0 | 0 | 0
3203 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. , SM/10034 | Augmentation | Material Requisition To Resource Division | 3307/ND | 27/07/2022 | 0 | Resource Division | 30.17 | 0 | 0 | 0
3204 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. , SM/10034 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 83 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Betai Zone-II to accommodate FHTC under Tehatta Sub-division under Nadia Division, PHE Dte. | 4350/ND | 07/08/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 227.43 | 0 | 0 | 0
3205 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. , SM/10034 | Augmentation | Collection of Household data through mobile app for FHTC Connection (Phase-III), under Nadia Division, P.H.E. Dte. | 209/KLYSD-I | 09/02/2024 | 182 | TECHVISION | 4.86 | 4.86 | 100 | 100
3206 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. , SM/10034 | Augmentation | Laying of Distribution System including specials, valves & pipe Supporting structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. and Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of 400 CUM OHR , all complete for Augmentation of Ground Based Water Supply Scheme at Betai Zone-II to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 1956/ND | 28/04/2022 | 1351 | M/S S.S ENTERPRISE | 601.69 | 278.85 | 46.34 | 90
3207 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. , SM/10034 | Augmentation | Construction of Boundary wall at Head Work Site and 2nd Tube Well Site of Betai Zone-II Ground water based water supply scheme under Tehatta Sub-Division PHE Dte. | 1628/ND | 07/03/2024 | 360 | NAMDAR ALI | 21.11 | 0 | 0 | 12
3208 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. , SM/10034 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Betai Zone-I ground water based water supply scheme under Block_Tehatta-I Dist. - Nadia under EMD, PHE Dte. SM/10414 | 1119/EMD | 04/06/2025 | 90 | MA ANNAPURNA ENTERPRISE | 24.48 | 0 | 0 | 0
3209 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. , SM/10034 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Betai Zone-II ground water based water supply scheme under Block_Tehatta-II Dist. - Nadia under EMD, PHE Dte. SM/10034 | 1120/EMD | 04/06/2025 | 90 | M/S CHANDIMATA ELECTRICALS | 24.48 | 0 | 0 | 0
3210 | NADIA | Nadia Division | Augmentation of ground water based Narayanpur PWSS to accommodate FHTC in Karimpur-II Block within Nadia District under Nadia Division , SM/10077 | Augmentation | Augmentation of ground water based Narayanpur PWSS to accommodate FHTC in Karimpur-II Block within Nadia District under Nadia Division | 671/PFMS | 24/03/2022 | 0 | RADIANT | 3.13 | 0 | 0 | 0
3211 | NADIA | Nadia Division | Augmentation of ground water based Narayanpur PWSS to accommodate FHTC in Karimpur-II Block within Nadia District under Nadia Division , SM/10077 | Augmentation | Material Requisition To Resource Division | 2287/ND | 29/05/2023 | 0 | Resource Division | 21 | 0 | 0 | 0
3212 | NADIA | Nadia Division | Augmentation of ground water based Narayanpur PWSS to accommodate FHTC in Karimpur-II Block within Nadia District under Nadia Division , SM/10077 | Augmentation | Laying additional pipe line for distribution system and rising main for Betai Zone-I and Narayanpur PWSS Under augmentetion of Betai Zone-I PWSS and Narayanpur PWSS under Tehatta Sub-Division under Nadia Division PHE Dte. | 7263/ND | 13/12/2024 | 180 | M/S S.S ENTERPRISE | 99.98 | 0 | 0 | 0
3213 | NADIA | Nadia Division | Augmentation of ground water based Narayanpur PWSS to accommodate FHTC in Karimpur-II Block within Nadia District under Nadia Division , SM/10077 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Narayanpur ii) Palsunda iii) Dogachhi Zone-II iv)Dogachhi Zone-I | 679/KlySD-I | 31/05/2023 | 6 | TECHVISION | 4.79 | 4.79 | 100 | 100
3214 | NADIA | Nadia Division | Augmentation of ground water based Narayanpur PWSS to accommodate FHTC in Karimpur-II Block within Nadia District under Nadia Division , SM/10077 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed Augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 200 Cum Capacity 20 Mtr. height RCC Over Head Reservoir (Excluding Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for construction of one no. 200 Cum OHR of Staging Height 20 Mtr. for Augmentation of Ground Based Water Supply Scheme at Narayanpur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 966/ND | 09/03/2023 | 1096 | M/S S.S ENTERPRISE | 759.95 | 45.4 | 17.63 | 55
3215 | NADIA | Nadia Division | Augmentation of ground water based Narayanpur PWSS to accommodate FHTC in Karimpur-II Block within Nadia District under Nadia Division , SM/10077 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Narayanpur water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 6840/ND | 12/11/2024 | 360 | BISWAS CONSTRUCTION | 34.64 | 0 | 0 | 100
3216 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-II Part-I, at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme , SM/08016 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur-Krishnapur, Zone-II, Part-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Halalpur-Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 767/NAD-I | 04/05/2021 | 60 | IJABUL SEKH | 94.5 | 187.11 | 100 | 100
3217 | NADIA | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthning work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH D , SM/09091 | Retrofitting | Providing FHTC (Functional Household Tap Connection) by retrofitting under "Jalswapno" in connection with " Shifting of existing PHE pipeline for implementation of Widening & strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Km under NH Divn-I RIDF-XXV within Pansila W/S Scheme under Krishnagar Sub-Divn under Nadia Divn, PHE Dte." | 7506/ND | 29/12/2021 | 60 | S.B.CONSTRUCTION | 12.31 | 10.54 | 85.62 | 0
3218 | NADIA | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthning work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH D , SM/09091 | Retrofitting | Material Requisition To Resource Division | 4268/ND | 29/09/2022 | 0 | Resource Division | 0.92 | 0 | 0 | 0
3219 | NADIA | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthning work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH D , SM/09091 | Retrofitting | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | 7571/ND | 27/12/2024 | 31 | IMAGIN | 34.21 | 0 | 0 | 0
3220 | NADIA | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH , SM/09093 | Retrofitting | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH Divn-I RIDF-XXV within Bankar Dhopadi W/S Scheme under Krishnagar Sub- Divn under Nadia Divn, PHE Dte | 710/PFMS | 30/03/2022 | 0 | OTHERS | 17.48 | 0 | 0 | 0
3221 | NADIA | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH , SM/09093 | Retrofitting | Providing FHTC (Functional Household Tap Connection) by retrofitting under "Jalswapno" in connection with " Shifting of existing PHE pipeline for implementation of Widening & strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Km under NH Divn-I RIDF-XXV within Bankar Dhopadi W/S Scheme under Krishnagar Sub-Divn under Nadia Divn, PHE Dte." | 7294/ND | 20/12/2021 | 60 | SK RAJU | 32.6 | 5.33 | 100 | 0
3222 | NADIA | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH , SM/09093 | Retrofitting | Material Requisition To Resource Division | 7451/ND | 27/12/2021 | 0 | Resource Division | 11.31 | 0 | 0 | 0
3223 | NADIA | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH , SM/09093 | Retrofitting | Material Requisition To Resource Division | 4325/ND | 29/09/2022 | 0 | Resource Division | 1.26 | 0 | 0 | 0
3224 | NADIA | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH , SM/09093 | Retrofitting | Additional FHTC by retrofitting unfer jalswapno in connection with shifting of existing pipeline for implementation of widening and strengthening work of Swarupganj UBI more to Anandabas Road from 0.00 km to 6.10 km under NH Divn-I RIDF-XXV within Bankar Dhopadi Water supply scheme under Krishnagar Sub-Division PHED. (Sl.No. 01) | 573/KSD | 13/06/2022 | 60 | SUBHASIS MAJUMDER | 4.57 | 4.34 | 100 | 97
3225 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Continuation Work Order for Supply of CIDF Sluice, Non return valves and DI Mechanical collar Vavle for relaying of rising main of Thanapara Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | 213/AE-I/NACD-II | 20/01/2022 | 7 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.98 | 4.98 | 100 | 100
3226 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 116/NACD-II | 15/02/2022 | 90 | JOY HIND TUBEWELLS | 153.21 | 153.21 | 100 | 100
3227 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement at Thanapara Tube Well No-4 area according to departmental drawing (Size 3.60 mtr x 3.00 mtr ) of Thanapara water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | 58/AE-II/NACD-II | 23/02/2022 | 45 | M/S SANTOSHI MAA ENTERPRISE | 3.82 | 2.82 | 73.78 | 100
3228 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Continuation Work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 202/NACD-II | 01/04/2022 | 90 | JOY HIND TUBEWELLS | 151.4 | 151.35 | 99.96 | 100
3229 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Repairing and Renovation of I.E Plant at Thanapara Water Supply Scheme - Capacity - 166 cum/hr, Block -Karimpur-II under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 747/NACD-II | 29/09/2022 | 30 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 9.69 | 9.65 | 100 | 100
3230 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Continuation work Order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara (Vill- Falia) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 112/NACD-II | 11/02/2022 | 90 | MONDAL ENTERPRISE | 45.84 | 45.8 | 100 | 100
3231 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara (Vill- Saguna) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 03./NACD-II | 03/01/2022 | 45 | M/S SHILL & CO. | 88.07 | 88.01 | 100 | 100
3232 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mobarakpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | 173/NACD-II | 21/03/2022 | 90 | PATHIK PABAN NANDI | 98.64 | 0 | 0 | 100
3233 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Hiring of 1(one) number vehicle for day to day inspection of ongoing JJM & other works related with nadia Arsenic Civil Division-II, P.H.E. Dte. | 71/AE-II/NACD-II | 28/06/2022 | 365 | TARUN KUMAR BHATTACHARYA | 2.07 | 4.25 | 100 | 50
3234 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Continuation Work Order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 224/NACD-II | 05/04/2022 | 90 | MALLICK ENTERPRISE | 154.65 | 0 | 0 | 100
3235 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Supply, delivery and installation of submersible pumping machinery along with other allied electro-mechanical works voltage stabilizer etc. Augmentation to accommodate FHTC at for newly sunk TW (TW No. - IV) at Thanarpara water supply scheme, Karimpur II Block, Nadia under E.M.D. PHE Dte. NIET No.- 25 of EE/EMD of 2022-23 (Sl. No.- 21) | 6805/EMD | 21/12/2022 | 30 | SMILE | 8.71 | 8.71 | 100 | 0
3236 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara ( Vill-Thanapara, Kalopur, Subhrajpur, Char Gourbhanga) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1018/NACD-II | 29/11/2022 | 60 | A.P. POWER & CONCRETE | 31.49 | 28.56 | 100 | 85
3237 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Head Work Site under Thanapara Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 1129/NACD-II | 16/12/2022 | 60 | MUKHERJEE CONSTRUCTION | 17.21 | 17.2 | 100 | 95
3238 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal.(From 01/03/2023 to 31/03/2023) | 252/NACD-II | 27/02/2023 | 31 | SAJAL SAHA | 0.42 | 0.4 | 100 | 100
3239 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Sinking of 1 nos. of 300 mm X 200 mm dia, 180 mtr deep Tube Well (as replacement of old defunct T/W) by Direct Rotary Method with UPVC pipe (CD) & strainer, (300 mm dia 36 mtr. long housing pipe &200 mm dia 30 mtr. long strainer) at Thanapara 3rd Tube Well site and 3rd Pump House site and also Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) under Thanapara (Vill.- Gourbhanga) at Thanapara Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 546/NACD-II | 11/05/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 40.55 | 40.4 | 100 | 100
3240 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Karimpur-II Block of Nadia District through Jadavpur University. (Name of PWSS Thanapara) | 911/NACD-II | 29/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
3241 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Karimpur-II Block of Nadia District through Jadavpur University. (Name of PWSS Thanapara) | 1279/NACD-II | 14/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
3242 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Material Requisition To Resource Division | 372/NACD-II | 24/03/2023 | 0 | Resource Division | 12.32 | 0 | 0 | 0
3243 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Laying of distribution system including providing FHTC at left out households for Thanarpara Zone-I (Vill-Natidanga, Char Adityapur, Thanarpara) and Thanarpara Zone-II (Vill- Sobharajpur, Saguna) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1281/NACD-II | 16/11/2023 | 90 | SUJATA CONSTRUCTION | 270.68 | 0 | 0 | 0
3244 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Construction of approch road at Head Works site of Thanapara Zone-II Water Supply Scheme in Karimpur-II Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | 249/AE-II/NACD-II | 31/07/2024 | 15 | B.M. ENGINEERING & CONSTRUCTION | 0.97 | 0 | 0 | 0
3245 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Repair and Renovation work at Thanapara H/W site with Pathway ,Plastering ,Pump House Painting, Flooring,, PVC Water tank other allied works Under Nadia Arsenic Division-II,P.H.E.Dte. | 145./AE-II/NACD-II | 11/06/2024 | 30 | SOURAV & CO. | 2.91 | 0 | 0 | 0
3246 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Thanapara Water Supply Scheme of capacity 166 Cu.m/hr in Karimpur-II Block under Nadia Arsenic Civil Division -II, PHE Dte." | 236/NACD-II | 21/02/2024 | 540 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 354.2 | 247.94 | 70 | 65
3247 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Executive Engineer, of Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal | 412./NACD-II | 30/03/2023 | 366 | TARUN KUMAR BHATTACHARYA | 4.98 | 2.69 | 54.07 | 0
3248 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Continuation work order for Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Executive Engineer, of Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,WestBengal (From 01/04/2024 to 30/06/2024) | 504/NACD-II | 01/04/2024 | 91 | TARUN KUMAR BHATTACHARYA | 1.24 | 1.01 | 80.91 | 0
3249 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Continuation Work Order for Hiring of 1(one) number vehicle for day to day inspection of ongoing JJM & other works related with Nadia Arsenic Civil Division-II, P.H.E. Dte. (From 01/04/2024 to 30/06/2024) | 78/AE-II/NACD-II | 01/04/2024 | 91 | TARUN KUMAR BHATTACHARYA | 1.24 | 0.97 | 78 | 0
3250 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Continuation Work Order for Hiring of 1(one) number vehicle for day to day inspection of ongoing JJM & other works related with nadia Arsenic Civil Division-II, P.H.E. Dte. (From 01/07/2023 to 31/03/2024) | 202/1/AE-II/NACD-II | 30/06/2023 | 275 | TARUN KUMAR BHATTACHARYA | 3.74 | 0.35 | 9.31 | 0
3251 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-III & Taranipur Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | 1398/NACD-II | 22/10/2024 | 90 | PAPAN ROY | 16.66 | 0 | 0 | 60
3252 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Continuation Work Order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Kadipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 222/NACD-II | 05/04/2022 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 36.28 | 57.15 | 66.67 | 100
3253 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal.(From 01/03/2022 to 28/02/2023) | 55//AE-II/NACD-II | 17/02/2022 | 365 | SAJAL SAHA | 4.98 | 1.39 | 100 | 100
3254 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Functional House Hold Tap Connection for providing connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Remaining School only) Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 150/NACD-II | 17/01/2023 | 20 | DUTTA CONSTRUCTION | 2.68 | 2.64 | 100 | 100
3255 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Thanarpara Piped Water Supply Scheme in Karimpur-II Block under Nadia Arsenic Civil Division-II, P.H.E Dte | 87/NACD-II | 18/01/2024 | 318 | B.M. ENGINEERING & CONSTRUCTION | 24.4 | 24.34 | 100 | 85
3256 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Sinking of 3 nos. Tube Well at H/W site ,2nd and 3rd T/W site of 300 mm X 200 mm dia, 150 mtr deep by Direct Rotary Method with UPVC pipe (CD) & Fibre Glass strainer, ( 300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Thanapara Zone-III & Manoharpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | 1047/NACD-II | 07/08/2024 | 90 | B.M. ENGINEERING & CONSTRUCTION | 34.68 | 16.07 | 100 | 100
3257 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Rendering consultancy services for Geotechnical Investigation and Report preparation of 3rd site locations under Karimpur-II Block of Nadia District through Jadavpur University. (Name of Scheme Thanapara) | 972/NACD-II | 19/07/2024 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
3258 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Rendering consultancy services for Geotechnical Investigation and Report preparation of 2nd site locations under Karimpur-II Block of Nadia District through Jadavpur University. (Name of Scheme Thanapara) | 971/NACD-II | 19/07/2024 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
3259 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Repair and Renovation work at Thanapara 2nd & 4th pump house site with Reinforced Barbed Tape, Pathway, Plaster and other allied works Under Nadia Arsenic Division-II,P.H.E.Dte. | 160/AE-II/NACD-II | 14/06/2024 | 30 | TAPAN SAHA | 2.61 | 2.5 | 100 | 100
3260 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Wall writing work in various Gram Panchayats in Karimpur-II Block at Thanapara PWSS under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 756/AE-I/NACD-II | 19/06/2024 | 15 | IMAGIN | 0.93 | 0 | 0 | 100
3261 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Jungle cutting and Earthwork in filling at Maheshpur, Maitari and Thanarapara Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 818/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.76 | 0 | 0 | 100
3262 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Continuation Work Order for Hiring of 1(one) number vehicle for day to day inspection of ongoing JJM & other works related with nadia Arsenic Civil Division-II, P.H.E. Dte. (From 01/07/2023 to 31/03/2024) | 202/1/AE-II/NACD-II | 30/06/2023 | 275 | TARUN KUMAR BHATTACHARYA | 3.74 | 2.64 | 100 | 30
3263 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Executive Engineer, of Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal | 412/NACD-II | 30/03/2023 | 366 | TARUN KUMAR BHATTACHARYA | 4.98 | 0.92 | 100 | 20
3264 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Material Requisition To Resource Division | 983/NACD-II | 23/07/2024 | 0 | Resource Division | 16.39 | 0 | 0 | 0
3265 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Manoharpur ground water based water supply scheme under Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. | 865/EMD | 14/03/2024 | 30 | CINZANO | 22.25 | 0 | 0 | 85
3266 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Sinking of Tube Well at H/W site of 300 mm X 200 mm dia, 150 mtr deep by Direct Rotary Method with UPVC pipe (CD) & Fibre Glass Strainer, ( 300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Thanapara Zone-II & Jayrampur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 149/NACD-II | 04/02/2025 | 45 | MANISHIKA CONSTRUCTION | 11.56 | 0 | 0 | 0
3267 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Hiring of 1(one) number vehicle for day to day inspection of ongoing JJM & other works related with nadia Arsenic Civil Division-II, P.H.E. Dte.under Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, Pincode:- 741101,West Bengal. (From 01/07/2024 to 30/06/2025) | 204/AE-II/NACD-II | 01/07/2024 | 365 | TARUN KUMAR BHATTACHARYA | 4.98 | 4.02 | 80.72 | 0
3268 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Construction of 75 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Thanarpara Zone-III Water Supply Scheme in Karimpur-II block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | 1207/NACD-II | 04/09/2024 | 180 | SINGHA ROY & CO. | 215.53 | 0 | 0 | 0
3269 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Laying of distribution system including providing FHTC at left out households for Thanarpara Zone-III (Vill- Char Gaurbhanga, Falia, Yusufpur) , Jitpur , Taranipur & Dhopahat W/S Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1627/NACD-II | 19/12/2024 | 270 | M.R. CONSTRUCTION | 117.87 | 0 | 0 | 40
3270 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Acceptance cum work order "Construction of 50 m3/hr capacity IEP at Thanarpara Zone-II PWSS in Karimpur-II Block under Nadia Arsenic Civil Division-II, P.H.E. Dte." | 432/NACD-II | 15/03/2024 | 671 | EVEREST CONSULTANT SERVICES. | 23.11 | 0 | 0 | 50
3271 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Executive Engineer, under Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, Pincode:- 741101,West Bengal. (From 01/07/2024 to 30/06/2025) | 791/AE-I/NACD-II | 01/07/2024 | 365 | TARUN KUMAR BHATTACHARYA | 4.98 | 3.45 | 69.36 | 0
3272 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-II Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. & including Binodnagar PWSS,Manoharpur PWSS, Rajapur PWSS & Taranipur PWSS. | 428/NACD-II | 07/04/2025 | 180 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 19.28 | 0 | 0 | 30
3273 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/10200 | Augmentation | Construction of Pump House cum Chlorine room with sanitary arrangement at Thanarpara Zone-II Headwork site according to departmental drawing at Thanarpara Zone-II & Dhopahat Piped Water Supply Scheme under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 403_NACD-II | 26/03/2025 | 150 | ROY CONSTRUCTION | 6.14 | 0 | 0 | 100
3274 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | Repairing and renovation of pump house, Dismantling of boundary wall & re-construction , & construction of bath room with other allied works at Uttar tajpur pump house no: II under Uttar tajpur W/S, Karimpur -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | 679/ Kly SD-I | 26/07/2022 | 30 | K.K. MARKETING | 4.99 | 4.99 | 100 | 100
3275 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | PROVIDING 300MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT FAZILNAGAR P/W SCHEME (REPLACEMENT TW-III), KARIMPUR -II BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | 279/CMSD-II(D) | 01/06/2022 | 15 | OSMAN SEKH | 4.39 | 4.05 | 100 | 0
3276 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | PROVIDING DRILLING CREWS & OTHER MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MMX200MMX250 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR FAZILNAGAR W/S SCHEME (REPLACEMENT TW-III), KARIMPUR-II BLOCK UNDER NADIA DISTRICT, CMSD-II(D), CDD, PHE DTE. | 276/CMSD-II(D) | 01/06/2022 | 35213 | OSMAN SEKH | 3.52 | 1.85 | 100 | 0
3277 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | Repairing and renovation of pump house, extension of boundary wall , & construction of drain with other allied works at Uttar tajpur pump house no: I under Uttar tajpur W/S , Karimpur -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | 678/Kly SD-I | 26/07/2022 | 30 | S.M. ENTERPRISE | 4.83 | 4.83 | 100 | 100
3278 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT UTTAR TAJPUR W/S SCHEME (REPLACEMENT TW-II), KARIMPUR-I BLOCK UNDER NADIA DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 285/CMSD-II(D) | 01/06/2022 | 15 | OSMAN SEKH | 2.07 | 1.63 | 100 | 0
3279 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | PROVIDING 200 MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT FAZILNAGAR W/S SCHEME (REPLACEMENT TW-III) KARIMPUR-II BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | 278/CMSD-II(D) | 01/06/2022 | 15 | OSMAN SEKH | 4.44 | 0.79 | 100 | 0
3280 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | Interconnection of newly sunk tubewell at 2nd Pump House including cleaning of rising main and delivery pipeline of Utter Tajpur Water Supply Scheme, Karimpur-I Block, Nadia. | 873/Kly SD-I | 20/09/2022 | 15 | M/S SHAIKH ENTERPRISE | 1 | 1 | 100 | 100
3281 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | 623/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.13 | 0 | 0 | 0
3282 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 250 mtrs. Depth) by utilising Departmental machineries for Kharagpur SG Hospital W/S Scheme, under Paschim Midnapore District, CDD PHE Dte. | 1350/CDD | 24/11/2022 | 30 | PADMA ENGINEERING & CO. | 18.38 | 3.67 | 63.48 | 0
3283 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete based on actual Estimate & Providing FHTC for Uttar Tajpur water supply scheme in Nadia District under Nadia Division | 1246/ND | 16/03/2022 | 90 | M/S MALLICK ENTERPRISE | 167.79 | 167.77 | 100 | 100
3284 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | Continuation for hiring of diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the DIC, CMSD-II(D), CDD PHE Dte. | 549/CMSD-II(D) | 19/12/2022 | 7 | ASHUTOSH PAL | 0.28 | 0.28 | 100 | 0
3285 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | Supply delivery & installation of submersible pumping machinery and allied works for newly sunk Tube well (replacement) at PH No. II in connection with ongoing FHTC works by Civil wing under Uttar Tajpur PWSS Dist. Nadia | 196/EMSD II | 29/07/2022 | 243 | T.N. BANERJEE | 3 | 3 | 100 | 100
3286 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | Material Requisition To Resource Division | 1252/ND | 16/03/2022 | 0 | Resource Division | 1.18 | 0 | 0 | 0
3287 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | Material Requisition To Resource Division | 1029/ND | 03/03/2022 | 0 | Resource Division | 4.4 | 0 | 0 | 0
3288 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 45 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Uttar Tajpur PWSS under Nadia Division PHE Dte. | 1806 / ND | 24/04/2023 | 90 | APURBA MANDAL | 85.67 | 0 | 0 | 60
3289 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | Providing FHTC including Laying Distribution System in connection with J.J.M. Work under village Madhugari to cover up left out portion under Karimpur-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 7165/ND | 10/12/2024 | 300 | S.S. ENTERPRISE | 58.08 | 0 | 0 | 65
3290 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I & II, under Uttartajpur ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. [SM/09812] | 2153/EMD | 30/08/2024 | 366 | RAJ & ENTERPRISE | 14.54 | 0 | 0 | 80
3291 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Uttartajpur PWSS under Karimpur-I Block under Tehatta Sub Division under Nadia Division-,P.H.E Dte. under Jal Jeevan Mission(JJM) . | 423/ND | 27/01/2025 | 300 | NISHITH BANERJEE | 26.22 | 0 | 0 | 60
3292 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09812 | Augmentation | Laying of additional pipe lines and allied works to increase the functionality in Brojonathpur, Gandhina villages under Karimpur-I Block under Nadia Division, PHE Dte. | 4685/4533/P-3/ND | 09/10/2025 | 90 | JOY HIND TUBEWELL'S | 46.3 | 0 | 0 | 0
3293 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09866 | Augmentation | Preparation of DPR for augmentation of existing Bagakhali Zone-II, (Block -Tehatta-I) piped water supply schemes | 143/AE-I/NACD-II | 16/11/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.57 | 2.57 | 100 | 100
3294 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09866 | Augmentation | Construction of Boundary wall with Grill Gate at Bagakhali Zone-II 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | 39/AE-II/NACD-II | 17/02/2022 | 30 | SOURAV & CO. | 3.13 | 3.09 | 100 | 100
3295 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09866 | Augmentation | Earth work in filling in ditches at Bagakhali Zone-II H/W Site at Bagakhali Zone-II Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 65/AE-II/NACD-II | 28/06/2022 | 15 | TARUN GHOSH | 0.56 | 0.56 | 100 | 100
3296 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09866 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Bagakhali Zone - II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 283/NACD-II | 23/02/2021 | 21 | BIDYUT KUMAR | 19.4 | 0 | 0 | 100
3297 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09866 | Augmentation | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Head Work Site under Bagakhali Zone-II Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 1010/NACD-II | 29/11/2022 | 60 | GOUTAM HALDER | 14.43 | 14.41 | 99.87 | 90
3298 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09866 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bagakhali Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 863/NACD-II | 08/11/2021 | 45 | IJABUL SEKH | 60.77 | 60.44 | 100 | 100
3299 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09866 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Bagakhali Zone-II) | 1148/NACD-II | 10/10/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
3300 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09866 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Bagakhali Z-II Water Supply Scheme of capacity 30 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | 384/NACD-II | 12/03/2024 | 90 | SHYAMAL SHIL | 94.56 | 0 | 0 | 0
3301 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09866 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KHANJIPUR , Block-Tehatta I and TALDAH , Block-Krishnaganj, Bahirgachhi (Z-II) Block-Chapra, Bagakhali (Z-II) W/S Scheme, Block-Tehatta I Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 03) | 1122/EMD | 16/03/2023 | 30 | ANJAN ENTERPRISE | 46.98 | 0 | 0 | 80
3302 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09866 | Augmentation | New Sinking of 1 no. 250 mm X 150 mm dia, 150 mtr deep Tube Well (as replacement of old defunct T/W) by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Bagakhali Zone-II Head Work site under Bagakhali Zone-II Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | 83/NACD-II | 16/01/2024 | 45 | SANDIP BISWAS | 10.4 | 9.86 | 100 | 100
3303 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09866 | Augmentation | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Bagakhali Zone-II W/S Scheme of Tehatta-I Block of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 615/AE-I/NACD-II | 02/02/2024 | 15 | LAKSHMI CONSTRUCTION | 0.79 | 0.79 | 100 | 100
3304 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09866 | Augmentation | Acceptance cum work order "New Sinking of 1 no. 250 mm X 150 mm dia, 150 mtr deep Tube Well ( as replacement of old defunct T/W) by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Bagakhali Zone-II 2nd Tubewell site under Bagakhali Zone-II Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte." | 344/NACD-II | 06/03/2024 | 45 | SHYAMAL SHIL | 10.4 | 8.85 | 100 | 100
3305 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09866 | Augmentation | Relaying of D.I. Pipeline by replacing the damaged old UPVC Pipe for rising main from 1st pump house to 2nd pump house at Bagakhali Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 142/AE-II/NACD-II | 11/06/2024 | 30 | SANJIB BISWAS | 4.17 | 4.17 | 100 | 100
3306 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09866 | Augmentation | Repair and Renovation work at Bagakhali Zone-II H/W site with Earth work in filling in foundation trenches or plinth with good earth . Under Nadia Arsenic Division-II,P.H.E.Dte. | 134/AE-II/NACD-II | 11/06/2024 | 30 | SURAJIT KUMAR GHOSH | 4.85 | 4.78 | 100 | 100
3307 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09866 | Augmentation | Continuation Work Order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bagakhali Zone-I (vILL- Sahapur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 223/NACD-II | 05/04/2022 | 90 | NANDY ENTERPRISES | 20.12 | 0 | 0 | 100
3308 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09866 | Augmentation | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Bagakhali Zone-I and Bagakhali Zone-II Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1562/NACD-II | 05/12/2024 | 360 | DEBASIS SAMADDAR | 157.57 | 19.44 | 33.77 | 40
3309 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09869 | Augmentation | Preparation of DPR for augmentation of existing Baranaldaha, (Block -Tehatta-II) piped water supply schemes | 147/AE-I/NACD-II | 16/11/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.87 | 2.87 | 100 | 100
3310 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09869 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Baranaldaha (Vill- Kolony para) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | 890/NACD-II | 16/11/2021 | 45 | M/S ANUBHAB CONSTRUCTION | 52.36 | 52.2 | 99.71 | 100
3311 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09869 | Augmentation | Construction of Boundary wall with Grill Gate at Bara Naldaha Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | 236/AE-I/NACD-II | 17/02/2022 | 365 | BIPLAB GUHA | 4.84 | 4.83 | 99.79 | 100
3312 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09869 | Augmentation | Repairing of Distribution system of UPVC pipes, bamboo pilling & earth filling at Pashimpara under Baranaldaha Ground water based PWSS under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 32 /AE-I/NACD-II | 24/06/2021 | 10 | TAPAN SAHA | 2.08 | 2.08 | 99.98 | 100
3313 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09869 | Augmentation | Continuation work Order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and also Bamboo Pilling at Baranaldaha (Vill- Choto Naldaha) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 825/NACD-II | 25/10/2021 | 45 | M/S ANUBHAB CONSTRUCTION | 60.17 | 60.14 | 100 | 100
3314 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09869 | Augmentation | Damaged pipe line repair due to construction of drain at Baranaldaha W/s Scheme (Vill- Baranaldaha) in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 600/NACD-II | 01/09/2022 | 30 | TAPAN SAHA | 9.7 | 9.62 | 100 | 100
3315 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09869 | Augmentation | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-II Block of Nadia District through Jadavpur University. (Name of PWSS Baranaldaha) | 1285/NACD-II | 21/11/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
3316 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09869 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BRITTIHUDA (Block- Chapra), BARNIA (Block- Tehatt II ), MAHATPUR (Block- Chapra ), MATIARY (Block- Krishnaganj), BAGAKHALI (Z-I) (Block- Tehatta I ), BARA NALDAH (Block- Tehatta II ) W/S Scheme, , Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 01) | 1120/EMD | 16/03/2023 | 30 | B.T. PROJECTS PVT. LTD | 91.82 | 7.33 | 72.01 | 60
3317 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09869 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or damaged line repair due to construction of drain) at Bara Naldaha ( Vill- Colonypara, Baranaldaha) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 547/NACD-II | 11/05/2023 | 60 | SUBHASIS MOJUMDER | 37.82 | 21.39 | 56.56 | 60
3318 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09869 | Augmentation | Barbed wire fencing & painting of Headwork site and 2nd T/W site Boundary wall of Baranaldaha PWSS at Tehatta-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte | 744/AE-I/NACD-II | 18/06/2024 | 30 | A.S.CONSTRUCTION | 4.25 | 0 | 0 | 0
3319 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09869 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Baranaldah Water Supply Scheme of capacity 67 Cu.m/hr in Tehatta-II Block under Nadia Arsenic Civil Division -II, PHE Dte." | 206/NACD-II | 15/02/2024 | 90 | RITE WATER SOLUTION (INDIA) PRIVATE LIMITED | 176.73 | 0 | 0 | 0
3320 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09869 | Augmentation | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Baranaldaha W/S Scheme in Tehatta-II Block of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 611/AE-I/NACD-II | 02/02/2024 | 15 | ECOCARE | 0.92 | 0.92 | 100 | 100
3321 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09869 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Bara Naldaha Piped Water Supply Scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 145/NACD-II | 06/02/2024 | 45 | M/S S. K. ENTERPRISE | 28.62 | 28.6 | 100 | 100
3322 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09869 | Augmentation | Renovation of Head Work site and 2nd T/W site of Baranaldaha PWSS at Tehatta-II Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 745/AE-I/NACD-II | 18/06/2024 | 193 | TAPAN SAHA | 4.69 | 4.62 | 100 | 100
3323 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09869 | Augmentation | Comprehensive augmentation in technical regards including aquifer management with extraction, compliance of Ground water contamination removal as per IS 10500 with subsequent amendments and composite RCC Cum masonry structures at Mouza- Baranaldaha (Habitation - Colony Para) under Baranaldaha Piped Water Supply Scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1618/NACD-II | 18/12/2024 | 240 | JOY HIND TUBEWELLS | 52.9 | 0 | 0 | 60
3324 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09869 | Augmentation | Repair and renovation of Boundary wall with Grill Gate and Barbed wire fencing and Painting of Pump House, Boundary Wall at HW site of Krishnagar Water Supply Scheme and BaraNaldaha Water Supply Scheme of Tehatta -II Block Nadia Arsenic Civil Division-II PHE Dte. | 111/AE-I/NACD-II | 04/06/2025 | 60 | BASUDEB SAHA | 4.35 | 0 | 0 | 0
3325 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09869 | Augmentation | Construction of Boundary Wall at North & Eastern side with Grill Gate and Barbed wire fencing at 2nd TubeWell site of Krishnagar Water Supply Scheme and Baranaldaha water Supply Scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 112/AE-I/NACD-II | 04/06/2025 | 60 | PAPAN ROY | 4.5 | 0 | 0 | 0
3326 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. , SM/09869 | Augmentation | Construction of Boundary Wall at South & Western side with Grill Gate and Barbed wire fencing at 2nd TubeWell site of Krishnagar water Supply Scheme and Baranaldaha water Supply Scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 113/AE-I/NACD-II | 04/06/2025 | 60 | PARTHA DAS | 4.5 | 0 | 0 | 0
3327 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. , SM/10716 | Augmentation | Material Requisition To Resource Division | 4882/ND | 23/11/2022 | 0 | Resource Division | 73.95 | 0 | 0 | 0
3328 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. , SM/10716 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. | 43/PFMS | 09/06/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.93 | 0 | 0 | 0
3329 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. , SM/10716 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works etc. rejuvenation to Accommodate FHTC at Pump House No.I and II under Anulia WS Scheme, Block Ranaghat 1, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-10) | 159/EMD | 06/01/2023 | 30 | KARTICK BAL | 27.77 | 24.21 | 100 | 40
3330 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. , SM/10716 | Augmentation | Material Requisition To Resource Division | 4331/ND | 29/09/2022 | 0 | Resource Division | 0.06 | 0 | 0 | 0
3331 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. , SM/10716 | Augmentation | Material Requisition To Resource Division | 2123/ND | 16/05/2023 | 0 | Resource Division | 77.07 | 0 | 0 | 0
3332 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. , SM/10716 | Augmentation | Surging of 01(One) nos. 150 x 100mm dia tube well at second tube well site of Anulia water supply scheme under Ranaghat Sub-Division Nadia Division P.H.E Dte. | 931/RSD | 14/09/2023 | 7 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 0.55 | 0.55 | 100 | 100
3333 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. , SM/10716 | Augmentation | Estimate for Surging of 01(One) nos. 150 x 100mm dia tube well Head works site of Anulia water supply scheme under Ranaghat Sub-Division Nadia Division P.H.E Dte. | 932/RSD | 14/09/2023 | 7 | APURBA MONDAL, VILL+P.O. BADKULLA, DIST.NADIA, PIN-741121 W.B | 0.55 | 0.49 | 100 | 100
3334 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. , SM/10716 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. | 3528/ND | 05/08/2022 | 90 | M/S NANDY ENTERPRISE | 475.17 | 309.5 | 65.13 | 95
3335 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. , SM/10716 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Anulia under Ranaghat Sub-Division under Nadia Division PHE Dte. | 1410/RSD | 19/11/2024 | 45 | SURJA ENTERPRISE | 2.15 | 0 | 0 | 0
3336 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. , SM/10716 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
3337 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA , SM/10567 | Augmentation | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | 50/PFMS | 22/06/2022 | 0 | HORIZEN | 2.69 | 0 | 0 | 0
3338 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA , SM/10567 | Augmentation | Material Requisition To Resource Division | 696/ND | 17/02/2023 | 0 | Resource Division | 21.74 | 0 | 0 | 0
3339 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA , SM/10567 | Augmentation | Material Requisition To Resource Division | 1874/ND | 26/04/2023 | 0 | Resource Division | 12.46 | 0 | 0 | 0
3340 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA , SM/10567 | Augmentation | Material Requisition To Resource Division | 2583/ND | 13/06/2023 | 0 | Resource Division | 21.74 | 0 | 0 | 0
3341 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA , SM/10567 | Augmentation | Material Requisition To Resource Division | 2297/ND | 29/05/2023 | 0 | Resource Division | 10.28 | 0 | 0 | 0
3342 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA , SM/10567 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Monipota to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division P.H.Engineering Dte. | 376/ND | 27/01/2023 | 795 | SUMAN CHAKRABORTY | 196.42 | 120.17 | 61.18 | 100
3343 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA , SM/10567 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Monipota PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 65.00 Cu.m/hr | 135/ND | 09/01/2024 | 360 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 74.19 | 9.58 | 99.39 | 50
3344 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA , SM/10567 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Monipota ground water based water supply scheme under Block_ Krishnanagar_I Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15135) | 234/EMD | 06/02/2025 | 30 | M/S.A.K. BANERJEE. | 11.76 | 0 | 0 | 0
3345 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA , SM/10567 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at MONIPOTA W/S Scheme Block- KRISHNAGAR - I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10567 | 1144/EMD | 04/06/2025 | 90 | GOENKA ENTERPRISE | 37.8 | 0 | 0 | 0
3346 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA , SM/10567 | Augmentation | Construction of 51m Boundary Wall (2.5m panel) having 200X200mm R.C.C. Column footing (1.0X1.0m) with 125mm thick brick panel wall and 200x300 RCC beam at GL including M.S gate at Monipota PWSS at PH-2 site. | 85/RSD | 14/01/2025 | 75 | BISHAL CONSTRUCTION | 4.6 | 0 | 0 | 0
3347 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA , SM/10567 | Augmentation | Restoration of Delivery pipe line and laying of distribution pipe line in Rowtara village under Monipota Ground water based water supply scheme under Ranaghat Sub-Division under Nadia Division PHED. | 1806/ND | 22/04/2025 | 91 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 28.82 | 0 | 0 | 70
3348 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA , SM/10567 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Monipota under Ranaghat Sub-Division under Nadia Division PHE Dte. | 202/RSD | 06/02/2025 | 45 | SAYANTAN PANDEY | 2.15 | 0 | 0 | 70
3349 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA , SM/10567 | Augmentation | Construction and installation of MANIFOLD and allied works at Head Works site under Monipota Ground Based Water Supply Scheme under Krishnagar-I Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) | 2401/ND | 23/05/2025 | 90 | R M TRADING | 11.91 | 0 | 0 | 0
3350 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA , SM/10567 | Augmentation | Special repair & renovation of head work site pump house & allied works of Monipota W/S scheme of Krishnanagar-I block under Ranaghat Sub-Division, P.H.E. Dte. | 558/RSD | 30/08/2022 | 600 | ROMI TRADERS | 2.22 | 1.5 | 80.69 | 80
3351 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA , SM/10567 | Augmentation | Special repair & renovation & repair of CWR pump house & allied works of Monipota W/S scheme of Krishnanagar block under Ranaghat Sub-Division, P.H.E. Dte | 558/A/RSD | 30/08/2022 | 510 | M/S PHANINDRA NATH ROY | 2 | 0 | 0 | 85
3352 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10659 | Augmentation | Distribution Design for preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Duttapulia Zone - II Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | 71/AE-II/NAD-I | 24/02/2022 | 30 | UMWELT ENGINEER PVT. LTD. | 4.8 | 4.8 | 100 | 100
3353 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10659 | Augmentation | Route Survey for preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Duttapulia Zone - II Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | 70/AE-II/NAD-I | 24/02/2022 | 30 | UMWELT ENGINEER PVT. LTD. | 4.67 | 4.67 | 100 | 100
3354 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10659 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Arsenic Division-I PHE Dte. Schemes:- i)Matikumra ii)Duttaphulia Zone-I iii)Duttaphulia Zone-II | 166/AE-I/NAD-I | 12/04/2023 | 15 | TECH VISION | 4.84 | 4.84 | 100 | 40
3355 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10659 | Augmentation | Retrofitting work at Duttaphulia Mouza inconnection with Augmentation to accomodate FHTC under JJM for Duttaphulia Zone- II Ground water based piped watrer supply scheme ( Phase- I ) Block- Ranaghat -II Dist- Nadia under Nadia Arsenic Division-I , P.H.E Dte.(Sl.No. 08)" | 1384/NAD-I | 16/05/2023 | 30 | MESSRS FREEDOM CONSTRUCTION | 72.08 | 71.49 | 100 | 100
3356 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10659 | Augmentation | Material Requisition To Resource Division | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 20.94 | 0 | 0 | 0
3357 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10659 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Duttaphulia Zone-II Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Duttaphulia Zone-II (Phase-I) under JJM (Sl.no.09) | 1362 / NAD-I | 12/05/2023 | 15 | DULAL MAJUMDER | 13.03 | 12.95 | 100 | 100
3358 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10659 | Augmentation | Surging of existing Tube Well situated at the 5th Tube Well site at Duttaphulia Zone-II Water Supply Scheme in Connection with Jal Jeevan Mission under Hanskhali Block to increase the yield of the Tube Well under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 02) | 204/AE-II/NAD-I | 24/09/2024 | 7 | M/S DIPAK ENTERPRISE | 0.64 | 0.64 | 100 | 100
3359 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10659 | Augmentation | Surging of existing Tube Well situated at thr 2nd Tube Well site at Duttaphulia Zone-II Water Supply Scheme in Connection with Jal Jeevan Mission under Hanskhali Block to increase the yield of the Tube Well under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 01) | 201/AE-II/NAD-I | 24/09/2024 | 7 | BUDDHADEV MONDAL | 0.64 | 0 | 0 | 100
3360 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10659 | Augmentation | Restoration of damages pipelines from Duttaphulia more to BSF camp in Ranaghat- II, Block under Nadia Arsenic Division-I,PHE Dte. | 142/AE-II/NAD-I | 07/06/2024 | 30 | BUDDHADEV MONDAL | 4.19 | 4.19 | 100 | 100
3361 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10659 | Augmentation | Material Requisition To Resource Division | 68/NAD-I | 16/01/2024 | 0 | Resource Division | 3.72 | 0 | 0 | 0
3362 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10659 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Duttaphulia Zone-II (Part-I) at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Duttaphulia Zone-I Water SUpply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | 1463/NAD-I | 18/08/2022 | 414 | APURBA MANDAL | 321.95 | 248.83 | 77.29 | 85
3363 | NADIA | Eastern Mechanical | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10659 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejumination Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II , III , IV and V (Zone-II) (Phase-I) under Duttapulia ground water based water supply scheme under Block_ Ranaghat-II Dist. - Nadia under EMD, PHE Dte. (SM/10659) | 2680/EMD | 20/11/2024 | 222 | S.S.ENTERPRISES | 50.99 | 0 | 0 | 0
3364 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10659 | Augmentation | Balance work for revamping / upgradation of the hydraulic parameters at Muchiphulbari, Dhakuria & Baranberia Mouza in connection with Itaberia PWSS & Duttaphulia PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 06) | 167/NAD-I | 29/04/2025 | 181 | MS MAA BHABANI ENTERPRISE | 95.54 | 0 | 0 | 0
3365 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10659 | Augmentation | Providing FHTC and laying dedicated pipeline for Gangsara & Duttaphulia Village in connection Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme , Under Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. (Sl.05) | 74/NAD-I | 16/04/2025 | 60 | SHYAMAL SHIL | 94.18 | 0 | 0 | 0
3366 | NADIA | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. , SM/10659 | Augmentation | Construction of Boundary wall and pathway Head work site of Duttaphulia Zone- II and Dubli Zone- I water supply Scheme in Ranaghat-II Block in connection with Duttaphulia Zone-I W/S Scheme under JJM under Nadia Arsenic Division-I,P.H.E. Dte. (sl.02) | 137/NAD-I | 23/04/2025 | 60 | CFS MANAGEMENT PRIVATE LIMITED | 38.99 | 0 | 0 | 0
3367 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA , SM/11511 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Topla W/S Scheme in Karimpur-II Block of Nadia District under Nadia Division, P.H.E. Dte. | 305/TSD | 24/11/2021 | 30 | HORIZEN | 3.19 | 2.81 | 100 | 100
3368 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA , SM/11511 | Augmentation | Material Requisition To Resource Division | 5102/ND | 08/12/2022 | 0 | Resource Division | 45.9 | 0 | 0 | 0
3369 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA , SM/11511 | Augmentation | Renovation of AIRP (Pressure Type) of capacity 93 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Topla PWSS under Nadia Division PHE Dte. | 3584/ND | 14/08/2023 | 90 | APURBA MANDAL | 68.26 | 0 | 0 | 0
3370 | NADIA | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA , SM/11511 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR TOPLA W/S SCH, KARIMPUR-II BLOCK UNDER NADIA DISTRICT, CDD, PHE DTE. | 1197/CDD | 11/11/2022 | 30 | ASHUTOSH DAS & CO | 10.19 | 7.45 | 100 | 0
3371 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA , SM/11511 | Augmentation | Material Requisition To Resource Division | 4317/ND | 29/09/2022 | 0 | Resource Division | 18.41 | 0 | 0 | 0
3372 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA , SM/11511 | Augmentation | Material Requisition To Resource Division | 2288/ND | 29/05/2023 | 0 | Resource Division | 18.41 | 0 | 0 | 0
3373 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA , SM/11511 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MAHISUNRA W/S Scheme, Block-NABADWIP, PALASIPARA W/S Scheme, Block-Tehatta-II AND TOPLA W/S Scheme, Block-Karimpur-II Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No. - 05) | 499/EMD | 24/01/2023 | 30 | WEST BENGAL ENGINEERING CO. | 90.14 | 29.92 | 99.62 | 15
3374 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA , SM/11511 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Habibpur(PART-II) ii) Madhugari (Phase-II) iii) Krishnaganj (Phase-I) iv) Naserkuli (Zone-I) v) Topla | 245/ Kly SD-I | 27/02/2023 | 181 | HORIZEN | 4.96 | 4.96 | 100 | 100
3375 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA , SM/11511 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Rising main from First Tube Well, 2nd Tube well with 3rd tube well and Inter-Connection in between Tube wells and OHR including specials and valves and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Topla to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. (SM/11511) | 4387/ND | 13/10/2022 | 90 | M/S DIPAK ENTERPRISE | 314.83 | 229.19 | 72.8 | 75
3376 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA , SM/11511 | Augmentation | Construction Of Pump House (3.6x 3.0m) Including Sanitary Arrangement At Tube well No-3 Site and construction of Boundary wall at 3rd Tube Well Site At Topla Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | 1634/ND | 07/03/2024 | 720 | BISWAS ENTERPRISE | 11.78 | 0 | 0 | 80
3377 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA , SM/11511 | Augmentation | Sinking of 01 nos Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at 3rd Tube well Site Topla PWSS Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | 7481/ND | 23/12/2024 | 30 | ZEST INFRACON | 17.55 | 0 | 0 | 0
3378 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA , SM/11511 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Topla water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 7126/ND | 09/12/2024 | 270 | MONDAL ENTERPRISE | 34.35 | 0 | 0 | 80
3379 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA , SM/11511 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Topla Ground Based Water Supply Scheme under Karimpur-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Topla at Karimpur-II Block by Augmentation of Ground Water based PWSS for Topla Water Supply Schemes under Nadia Division, PHE Dte. | 2263/ND | 15/05/2025 | 60 | SOURAV & CO | 23.57 | 0 | 0 | 0
3380 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11834 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 7B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 129/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.82 | 4.81 | 100 | 100
3381 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11834 | Augmentation | Material Requisition To Resource Division | 106/ND | 05/01/2023 | 0 | Resource Division | 168.02 | 0 | 0 | 0
3382 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11834 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 685.36 | 75.13 | 47
3383 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11834 | Augmentation | Additional Work for Ground Improvement of OHR foundation, renovation of OHR & other allied works of Northern Sector Part-I, Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 6095/ND | 19/09/2024 | 240 | UMWELT ENGINEER PVT LTD | 225.66 | 18.99 | 49.21 | 75
3384 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11842 | Augmentation | Temporary arrangement of Reservoir (Vat), Drinking Water Arrangement, 40 mm Temporary Tubewell and Temporary Latrine at different C.P.M.F. / S.P.F. Camp for the ensuing General Assembly Election 2021 within Kaliganj PS under Debagram Sub-Divn, PHE Dte (Gr-1-Kaliganj karmatirtha Near panighata, newly constructed building) | 143/DSD | 19/03/2021 | 7 | GHOSH ENTERPRISE | 3.29 | 0 | 0 | 100
3385 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11842 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 4C of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 144/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.26 | 4.23 | 100 | 100
3386 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11842 | Augmentation | Material Requisition To Resource Division | 97/ND | 05/01/2023 | 0 | Resource Division | 107.24 | 0 | 0 | 0
3387 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11842 | Augmentation | Material Requisition To Resource Division | 240/ND | 11/01/2024 | 0 | Resource Division | 9.87 | 0 | 0 | 0
3388 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11842 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4589/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 239.23 | 37.21 | 50
3389 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11842 | Augmentation | Construction of OHR, repair and renovation of staff room, repair of boundary wall, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-IV / C (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11842]. | 5557/ND | 12/12/2023 | 722 | APURBA MANDAL | 239.4 | 14.66 | 6.37 | 10
3390 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11842 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
3391 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11842 | Augmentation | Construction of Bituminous Approch Road for GLR site at Surface water based water supply Scheme under Northern Sector Part II at Nakashipara Block under Nadia Division PHE Dte. | 3260/ND | 10/07/2025 | 90 | GBC INFRASTRUCTURE PRIVATE LIMITED | 95.58 | 0 | 0 | 5
3392 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Soil Investigation for Construction of 3 (Three) Nos. of Overhead Reservoir of staging height of 20 mtr. Under Nadia Arsenic Civil Division-II P.H.E. Dte. Site - Mrigi W/s Scheme, Panchdara Abhaynagar W/s Scheme, Paninala W/s Scheme | 252/AE-I/NACD-II | 25/02/2022 | 15 | PROSENJIT DAS | 2.44 | 2.44 | 100 | 100
3393 | NADIA | Eastern Mechanical | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | New connection charges for Mrigi PHE I | 108/PFMS/EMD | 16/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.37 | 0 | 0 | 0
3394 | NADIA | Eastern Mechanical | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | New connection charges for Mrigi PHE II | 109/PFMS/EMD | 16/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.29 | 0 | 0 | 0
3395 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
3396 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
3397 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Laying of Rising Main of Mrigi Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | 22/AE-II/NACD-II | 18/04/2022 | 30 | R.M. TRADING | 3.73 | 1.67 | 44.9 | 85
3398 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Mrigi water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 208/NACD-II | 05/04/2022 | 60 | ROY CONSTRUCTION | 5.37 | 5.37 | 100 | 100
3399 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Kanainagar and Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 244/NACD-II | 19/04/2022 | 60 | B.M. ENGINEERING & CONSTRUCTION | 42.4 | 0 | 0 | 100
3400 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Mrigi water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | 13/AE-II/NACD-II | 11/04/2022 | 60 | ROY CONSTRUCTION | 2.83 | 2.83 | 100 | 100
3401 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Mrigi Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 628/NACD-II | 06/09/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.14 | 4.14 | 100 | 100
3402 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Earth work in filling in ditches at Mrigi 2nd Tube Well Site for development of land in connection with proposed T/W Sinking & Pump House construction at Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 60/AE-II/NACD-II | 28/06/2022 | 15 | SURAJIT KUMAR GHOSH | 2.26 | 2.26 | 100 | 100
3403 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Mrigi) | 1153/NACD-II | 10/10/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
3404 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Material Requisition To Resource Division | 402/NACD-II | 04/07/2022 | 0 | Resource Division | 26.26 | 0 | 0 | 0
3405 | NADIA | Eastern Mechanical | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Electriciyy bill pay for the new service connection at Migri PHE II |  | 03/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.22 | 0 | 0 | 0
3406 | NADIA | Eastern Mechanical | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Electricity bill pay for the new service connection at Mrigi PHE I | 152/PFMS/EMD | 13/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.41 | 0 | 0 | 0
3407 | NADIA | Eastern Mechanical | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Electriciyy bill pay for the new service connection at Migri PHE I |  | 03/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.41 | 0 | 0 | 0
3408 | NADIA | Eastern Mechanical | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Electricity bill pay for the new service connection at Mrigi PHE II | 151/PFMS/EMD | 13/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.22 | 0 | 0 | 0
3409 | NADIA | Eastern Mechanical | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Mrigi Piped Water SupplyScheme, Block: Tehatta-I, Dist. Nadia Under EMD, PHE Dte. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 20) | 6265/EMD | 19/11/2022 | 30 | CONCORD ENGINEERING | 41.28 | 0 | 0 | 0
3410 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Mrigi Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | 87/NACD-II | 10/01/2023 | 60 | PRADUT GHOSH | 16.44 | 9.84 | 59.86 | 85
3411 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Mrigi and adjoining mouzas under Mrigi Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | 284/NACD-II | 11/05/2022 | 90 | CHANDA CONSTRUCTION | 217.71 | 162.98 | 74.86 | 90
3412 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 34 cum/Hour capacity for Mrigi Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1069/NACD-II | 12/08/2024 | 180 | MANGES INDUSTRIAL CORPORATION. | 164.31 | 0 | 0 | 0
3413 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Mrigi 2nd Tubewell Site within Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 126/NACD-II | 11/01/2023 | 60 | GHOSH ENTERPRISE | 9 | 7.94 | 100 | 85
3414 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Smoothening of site by land filling of existing undulation by filling the ditches at Mrigi 2nd Tube Well Site for development of land and compaction by hand roller in connection with T/W Sinking at Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | 518/AE-I/NACD-II | 18/12/2023 | 15 | R.M. TRADING | 0.96 | 0.95 | 100 | 100
3415 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Construction of approch road at Head Works site of Mrigi Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | 516/AE-I/NACD-II | 18/12/2023 | 15 | CHANDA CONSTRUCTION | 0.97 | 0.96 | 100 | 100
3416 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Geotechnical protection work to counterbalance the uneven earth pressure in consultation with relevant I.S. Codes in Mrigi Water Supply Scheme in Tehatta -I Block in Nadia District under Nadia Arsenic Civil Division-II PHE Dte. | 164/NACD-II | 07/02/2024 | 15 | TARUN GHOSH | 12.36 | 9.85 | 100 | 100
3417 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Earthwork for protection of the existing structures and hydraulic arrangement in the ongoing Mrigi Public Water Supply Scheme (Phase-II) | 166/AE-II/NACD-II | 14/06/2024 | 15 | R.M.TRADING | 0.95 | 0.95 | 100 | 100
3418 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Smoothening of site by land filling of existing undulation by filling the ditches at Mrigi 2nd Tube Well Site for development of land and compaction by hand roller in connection with T/W Sinking at Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte.(Phase-I) | 165_AE-II/NACD-II | 14/06/2024 | 30 | M/S RAJESH CONSTRUCTION | 0.97 | 0.96 | 100 | 100
3419 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Earthwork for protection of the existing structures and hydraulic arrangement in the ongoing Mrigi Public Water Supply Scheme (Phase-III) | 291AE-II/NACD-II | 30/08/2024 | 15 | M/S RAJESH CONSTRUCTION | 0.96 | 0.96 | 100 | 100
3420 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Smoothening of site by land filling of existing undulation by filling the ditches at Mrigi 2nd Tube Well Site for development of land and compaction by hand roller in connection with T/W Sinking at Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte.(Phase-II) | 248/AE-II/NACD-II | 31/07/2024 | 15 | R.M.TRADING | 0.95 | 0.95 | 100 | 100
3421 | NADIA | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME , SM/10408 | New | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Mrigi water supply scheme of Tehatta-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | 393/NACD-II | 28/03/2023 | 731 | CHANDA CONSTRUCTION | 113 | 73.26 | 64.84 | 88
3422 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA , SM/11740 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Bagula Zone-I W/S Scheme in Hanskhali Block of Nadia District under Nadia Division, P.H.E. Dte. | 1049/RSD | 02/12/2021 | 30 | HORIZEN | 3.01 | 2.59 | 100 | 100
3423 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA , SM/11740 | Augmentation | Material Requisition To Resource Division | 1864/ND | 26/04/2023 | 0 | Resource Division | 58.87 | 0 | 0 | 0
3424 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA , SM/11740 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
3425 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA , SM/11740 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 50 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Bagula Zone-I to accommodate FHTC within Hanskhali block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | 4341/ND | 07/08/2024 | 180 | AMIT KUMAR BOSE | 181.56 | 0 | 0 | 0
3426 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA , SM/11740 | Augmentation | Material Requisition To Resource Division | 255/ND | 11/01/2024 | 0 | Resource Division | 10.78 | 0 | 0 | 0
3427 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA , SM/11740 | Augmentation | Material Requisition To Resource Division | 7563/ND | 27/12/2024 | 0 | Resource Division | 31.61 | 0 | 0 | 0
3428 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA , SM/11740 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 250 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of OHR all complete for augmentation of Ground Water Based Water Supply Scheme for Bagula Zone-I to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | 3215/ND | 26/07/2023 | 1096 | BANERJEE CONSTRUCTION, RAJA RAM MOHAN PALLY,BARASAT, KOLKATA-700124 | 222.67 | 0 | 0 | 65
3429 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA , SM/11740 | Augmentation | Construction of 55.0 m Boundary Wall (2.5m panel) having 200X200mm R.C.C. Column footing (1.0X1.0m) with 125mm thick brick panel wall and 200x300 RCC beam at GL including M.S gate at Bagula Zone-I PWSS 2nd Tube Well site. | 84/RSD | 14/01/2025 | 75 | B P ENTERPRISE | 4.87 | 0 | 0 | 0
3430 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA , SM/11740 | Augmentation | Construction of Pile foundation, Pile Cap, Padestal, Tie Beam for Construction of 250 cum capacity 20 Mtr. staging height RCC Over Head Reservoir for BAGULA ZONE-I Piped Water Supply scheme under Nadia Division P.H.E. Dte. in the District of Nadia | 2175/ND | 07/05/2025 | 90 | BANERJEE CONSTRUCTION | 50.8 | 0 | 0 | 100
3431 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA , SM/11740 | Augmentation | Construction of 111.60 m Boundary Wall(2.5m panel) having 200X200mm R.C.C. Column footing (1.0X1.0m) with 125mm thick brick panel wall and 200x300 RCC beam at GL including M.S gate at Bagula Zone-I PWSS 1st Tube Well site under Ranaghat Sub -Division in Nadia District under Nadia Division P.H.Engineering Dte. | 459/ND | 29/01/2025 | 90 | BUDDHADEV MONDAL | 9.5 | 0 | 0 | 0
3432 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11743 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 8/C of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 156/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.85 | 3.81 | 100 | 100
3433 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11743 | Augmentation | Material Requisition To Resource Division | 1525/ND | 04/04/2023 | 0 | Resource Division | 113.96 | 0 | 0 | 0
3434 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11743 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
3435 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11743 | Augmentation | Material Requisition To Resource Division | 247/ND | 11/01/2024 | 0 | Resource Division | 10.06 | 0 | 0 | 0
3436 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11743 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4588/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 179.16 | 59.64 | 19
3437 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11743 | Augmentation | Construction of OHR, staff room, chlorine room, service road, boundary wall and restoration of bituminous road, land improvement etc. of Surface Water Based Water Supply Scheme for Zone-VIII / C (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11743]. | 5369/ND | 04/12/2023 | 730 | KINGS & CO,11/1H/4, PRIYANATH MUKHERJEE ROAD, KOLKATA-700002. | 224.26 | 11.43 | 5.09 | 1
3438 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11743 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 5.92 | 98.73 | 30
3439 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11743 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
3440 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11743 | Augmentation | Additional Work for Installation of SCADA System in connection with Augmentation of Surface Water Based Piped Water Supply Scheme for Northern Sector Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 3447/ND | 23/07/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 732.35 | 0 | 0 | 15
3441 | NADIA | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | Material Requisition To Resource Division | 1090/NACD-II | 09/12/2022 | 0 | Resource Division | 63.84 | 0 | 0 | 0
3442 | NADIA | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | Sinking of 2 nos. 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Tarinipur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 1137/NACD-II | 16/12/2022 | 30 | AUXILIARY TUBE WELL DRILLERS | 21.03 | 19.17 | 91.19 | 100
3443 | NADIA | Eastern Mechanical | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at TARINIPUR Piped Water Supply Scheme, Block: Tehatta-I, Dist. Nadia Under EMD, PHE Dte. | 4707/EMD | 04/08/2023 | 30 | HARA PROSAD DAS | 51.92 | 0 | 0 | 0
3444 | NADIA | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | Material Requisition To Resource Division | 379/NACD-II | 24/03/2023 | 0 | Resource Division | 11.38 | 0 | 0 | 0
3445 | NADIA | Eastern Mechanical | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | New Service Connection under Ae, EMSD-III, Taranipur PH_I | BP-108-23-24 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.34 | 0 | 0 | 0
3446 | NADIA | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL | 235/9 | 21/02/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0 | 0
3447 | NADIA | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. | 23 | 19/04/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
3448 | NADIA | Eastern Mechanical | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | New Service Connection under Ae, EMSD-III, Taranipur PH_I | BP-107-23-24 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.78 | 0 | 0 | 0
3449 | NADIA | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | Additional instrumentation with augmentation of backwashing system with appropriate wattage including recirculation in compliance with 12699: 1989 as well as reaffirmation there into for contamination removal of various valent systems at Taranipur Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 1521/NACD-II | 26/11/2024 | 30 | NEER UDYOG | 31.56 | 0 | 0 | 0
3450 | NADIA | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | Acceptance cum work order "Construction of 50 m3/hr capacity IEP at Taranipur PWSS in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte." | 324/NACD-II | 04/03/2024 | 61 | NEER UDYOG | 23.2 | 0 | 0 | 0
3451 | NADIA | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-III & Taranipur Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | 1398/NACD-II | 22/10/2024 | 90 | PAPAN ROY | 16.66 | 12.85 | 77.1 | 60
3452 | NADIA | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Taranipur water supply scheme under Nadia Arsenic Civil Division-II, PHE Dte. Dist- Nadia. | 1386/NACD-II | 12/12/2023 | 45 | CHINMOY BISWAS | 11.33 | 11.26 | 100 | 100
3453 | NADIA | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Taranipur water supply scheme under Tehatta- I Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | 165/NACD-II | 07/02/2024 | 60 | M/S K.P. CONSTRUCTION | 32.46 | 28.03 | 100 | 100
3454 | NADIA | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | Soil Investigation for Construction of 01 (One) No of Overhead Reservoir, Construction of 01 (One) No of 350 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap, Laying of Distribution system including providing Functional House Hold Tap Connection (FHTC) and Laying of Rising Main and other necessary allied works at Taranipur Water Supply Scheme and other necessary allied works in this connection of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 402/NACD-II | 28/03/2023 | 904 | B.M. ENGINEERING & CONSTRUCTION | 345.19 | 172.16 | 49.87 | 43
3455 | NADIA | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | Incorporation of the system of adsorption by Inorganic sustances for multivalent metalloid expulsion for improving potability in coordination with IS 10500 With latest edition at Taranipur Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 47/NACD-II | 10/01/2025 | 30 | NEER UDYOG | 29.92 | 0 | 0 | 0
3456 | NADIA | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | Laying of distribution system including providing FHTC at left out households for Thanarpara Zone-III (Vill- Char Gaurbhanga, Falia, Yusufpur) , Jitpur , Taranipur & Dhopahat W/S Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1627/NACD-II | 19/12/2024 | 270 | M.R. CONSTRUCTION | 117.87 | 0 | 0 | 40
3457 | NADIA | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | Conversion of IEP to AIRP at Patharghata Water Supply Scheme of capacity 96 Cu.m/hr in Tehatta - I Block under Nadia Arsenic Civil Division -II, PHE Dte. | 1396/NACD-II | 22/10/2024 | 360 | JOY HIND TUBEWELLS | 258.38 | 0 | 0 | 0
3458 | NADIA | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | Acceptance cum work order "Conversion of IEP to AIRP at Mobarakpur, Binodnagar & Taranipur Water Supply Scheme of capacity 93 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | 152/NACD-II | 02/02/2024 | 598 | B.M. ENGINEERING & CONSTRUCTION | 241.81 | 0 | 0 | 0
3459 | NADIA | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Bagakhali Zone-I and Bagakhali Zone-II Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1562/NACD-II | 05/12/2024 | 360 | DEBASIS SAMADDAR | 157.57 | 0 | 0 | 40
3460 | NADIA | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-II Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. & including Binodnagar PWSS,Manoharpur PWSS, Rajapur PWSS & Taranipur PWSS. | 428/NACD-II | 07/04/2025 | 180 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 19.28 | 0 | 0 | 30
3461 | NADIA | Eastern Mechanical | TARANIPUR PIPED WATER SUPPLY SCHEME , SM/11964 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under TARINIPUR W/S Scheme (Block : Tehatta I) Dist.- Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 08) | 1607/EMD | 26/04/2023 | 616 | SHIVAM ENTERPRISE | 18.99 | 18.74 | 100 | 70
3462 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Garapota, Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Hanskhali Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08825 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara/Jal Swapna for Garapota, Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Garapota, Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Garapota Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 1586/NAD-I | 22/12/2021 | 90 | TAPU SAHA | 116 | 115.29 | 100 | 100
3463 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-V within Nakashipara Block.(Phase-C) , SM/08954 | Retrofitting | Providing Functional Household Tap Connection(FHTC) at Surface Water Based Water Supply Scheme(Northern Sector) Part-II,Zone-VA & VB within NAKASHIPARA BLOCK(PHASE-C) | 7051/ND | 06/12/2021 | 90 | GHOSH BROTHERS | 179.71 | 154.65 | 86.06 | 100
3464 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-V within Nakashipara Block.(Phase-C) , SM/08954 | Retrofitting | Material Requisition To Resource Division | 455/ND | 31/01/2022 | 0 | Resource Division | 1.49 | 0 | 0 | 0
3465 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-V within Nakashipara Block.(Phase-C) , SM/08954 | Retrofitting | Material Requisition To Resource Division | 4280/ND | 29/09/2022 | 0 | Resource Division | 24.76 | 0 | 0 | 0
3466 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-V within Nakashipara Block.(Phase-C) , SM/08954 | Retrofitting | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | 7571/ND | 27/12/2024 | 31 | IMAGIN | 34.21 | 0 | 0 | 0
3467 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-V within Nakashipara Block.(Phase-C) , SM/08954 | Retrofitting | Collection of Household data through mobile app for FHTC Connection (Phase-X), under Nadia Division, P.H.E. Dte. | 149/KlySD-I | 28/01/2025 | 181 | TECHVISION | 4.86 | 0 | 0 | 0
3468 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/13878 | Augmentation | Route Survey, Design of Distribution Network and Preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno for Fulia Township (Zone-III) Water Supply Scheme in Santipur Block of Nadia District under Nadia Division, P.H.E. Dte. | 423/RSD | 08/05/2023 | 15 | HORIZEN | 2.7 | 2.7 | 100 | 0
3469 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/13878 | Augmentation | Material Requisition To Resource Division | 1885/ND | 26/04/2023 | 0 | Resource Division | 7.4 | 0 | 0 | 0
3470 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/13878 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.7 | 40
3471 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/13878 | Augmentation | Providing, installation and commissioning of Electro-Mechanical Equipments and allied works for submersible pumping machinery of Pump House No.-I and II (New) for Augumentation Tube Well and Arsenic Removal Plant in connection to Accommodate FHTC under Fulia Town Ship (Zone-III) ground water based water supply scheme under Block_ Santipur Dist. - Nadia under EMD, PHE Dte. [SM-13878] | 2157/EMD | 30/08/2024 | 30 | PADMA ENGINEERING CO. | 26.83 | 0 | 0 | 0
3472 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/13878 | Augmentation | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of 30 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Fulia Township Zone-III to accommodate FHTC within Santipur block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | 4231/ND | 02/08/2024 | 180 | SATYABRATA CHAKRABORTY | 160.53 | 0 | 0 | 0
3473 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/13878 | Augmentation | New power connection charges for FULIA Water Supply scheme Z-III , Pump House NO-I (HEAD WORKSITE) | BP-184 | 13/12/2024 | 0 | W.B.S.E.D.C.L (FULIA C.C.C) | 9.47 | 0 | 0 | 0
3474 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/13878 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme to Accommodate FHTC, Construction & Soil Investigation of 100 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection and Cost of Pipes, Specials for FULIA Zone-III of Nadia District under Nadia Division PHE Dte | 3222/ND | 26/07/2023 | 1096 | SANJOY BAKSHI, 11,AHIBHUSAN HALDER LANE, SASTITALA.PO-KRISHNAGAR,DIST-NADIA, PIN-741101 | 237.03 | 138.86 | 58.58 | 51
3475 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/13878 | Augmentation | Construction of 137.00 mtr long Boundary Wall(2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125 mm thick brick panel wall and 200x300 m tie beam at GL including M.S gate at Fulia Zone-III H/W under Ranaghat Sub-Div , Nadia Division PHE. Dte. | 658/ND | 11/02/2025 | 90 | MUKHERJEE CONSTRUCTION | 11.66 | 0 | 0 | 0
3476 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/13878 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangemen At Head work Site At Fulia Zone-III Water Supply Scheme Under Ranaghat Sub-Division PHE Dte. | 662/ND | 11/02/2025 | 90 | ABHAYANANDA ENTERPRISE | 6.88 | 0 | 0 | 100
3477 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/13878 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
3478 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Joypur Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15551 | Augmentation | Augmentation of AIRP capacity (86cum/hr ) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Joypur under Jal Jeevan Mission at Hanskhali Block, under Nadia Arsenic Division -I, PHE Dte.(Sl.no.07) | 1886/NAD-I | 11/08/2023 | 30 | APURBA MANDAL | 139.79 | 44.73 | 32 | 32
3479 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Joypur Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15551 | Augmentation | "Work for revamping / upgradation of the hydraulic parameters in distribution network from OHR towards Joypur Pry School in reference to Hijuli and Joypur water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission.(SI. No. 02) | 40/NAD-I | 07/04/2025 | 60 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD | 93.13 | 0 | 0 | 0
3480 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Joypur Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15551 | Augmentation | Balance Work for revamping / upgradation of the hydraulic parameters at distribution network towards Chttosali more in reference to Hijuli and Joypur water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 04) | 156/NAD-I | 28/04/2025 | 60 | M/S DIPAK ENTERPRISE | 95.47 | 0 | 0 | 0
3481 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Joypur Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15551 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site of Joypur and Mamjoani Water Supply Scheme in connection with Duttaphulia Zone-I under Nadia Arsenic Division-I, PHE Dte. as a part of JJM (Sl. No. 01) | 39/NAD-I | 07/04/2025 | 242 | REAL TIME | 39.28 | 0 | 0 | 50
3482 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMALPUR ZONE-II (PHASE-II) IN RANAGHAT - II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15136 | Augmentation | Renovation of Partly-Gravity & Partly-Pressure Type AIRP of Capacity 25 Cu. M./ Hr. and Construction of Back Wash Chamber for AIRP at Head Work Site at Kamalpur Zone-II Piped water Supply Scheme under Ranaghat Sub-Division under Nadia Division, PHE Dte. | 1457/ND | 31/03/2023 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 58.65 | 43.64 | 100 | 100
3483 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMALPUR ZONE-I (PHASE-II) IN RANAGHAT - II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15137 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
3484 | NADIA | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. , SM/14243 | New | Preparation of Detailed Project Report (DPR) for Hijuli Water Supply Scheme at Ranaghat-II Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(sl.04) | 39 /NAD-I | 17/01/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 14.36 | 14.25 | 100 | 100
3485 | NADIA | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. , SM/14243 | New | Material Requisition To Resource Division | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 31.88 | 0 | 0 | 0
3486 | NADIA | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. , SM/14243 | New | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete with Rising Main System including specials & valves. & LAYING OF DISTRIBUTION SYSTEM INCLUDING SPECIALS, VALVES & PIPE SUPPORTING STRUCTURE, Construction of 300/100/200/200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials , Soil Investigation for the work of Construction of R.C.C Elevated Reservoir of Capacity 300/100/200/200 m3 Staging Height 20 Mtr, CONSTRUCTION OF BOUNDARY WALL [ H/W Site(160.0 m length), 2nd T/W Site(50.0 m length)], Pump House for H/W Site(5.4 M X 3.60 M),2nd T/W Site(3.60 M X 3.0 M) , Land Development and aliied works with Approach Road (105.0m Length and 3.0m Wide), RESTORATION WORK FOR BITUMINOUS ROAD, Hijuli (Zone-I,II,III & IV) Ground Water Based Piped Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, PHE Dte. | 2351/NAD-I | 03/10/2023 | 730 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 1541.25 | 0 | 0 | 3
3487 | NADIA | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. , SM/14243 | New | Continuation work order for Hiring of 1 (One) no inspection vehicle (Diesel Luxury Taxi/Maxi Cab/Motor Cab) on Daily basis for monitoring of JJM works by the Junior Engineers at the office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. (Period- 01/08/2024 to 31/01/2025) | 228/AE-I/NAD-I | 24/07/2024 | 184 | M/S DIPAK ENTERPRISE | 0.86 | 0 | 0 | 0
3488 | NADIA | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. , SM/14243 | New | "Work for revamping / upgradation of the hydraulic parameters in distribution network from OHR towards Joypur Pry School in reference to Hijuli and Joypur water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission.(SI. No. 02) | 40/NAD-I | 07/04/2025 | 60 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD | 93.13 | 0 | 0 | 0
3489 | NADIA | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. , SM/14243 | New | Balance Work for revamping / upgradation of the hydraulic parameters at distribution network towards Chttosali more in reference to Hijuli and Joypur water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 04) | 156/NAD-I | 28/04/2025 | 60 | M/S DIPAK ENTERPRISE | 95.47 | 0 | 0 | 0
3490 | NADIA | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. , SM/14243 | New | Work revamping / upgradation of the hydraulic parameters at distribution network at the part of Malsadaha, Ulasi, Silberia, Nasra (P) and Hijuli (P) Mouzas in reference to Hijuli and Nasra PWSS under Nadia Arsenic Division-I, P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. NO. 02) | 359/NAD-I | 09/06/2025 | 90 | M/S DIPAK ENTERPRISE | 246.94 | 0 | 0 | 0
3491 | NADIA | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. , SM/14243 | New | Balance work for revamping / upgradation of the hydraulic parameters at Gobindapur Colony and Hijuli mauza in reference to Gobindapur PWSS and Hijuli PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission (Sl. NO. 08) | 231/NAD-I | 13/05/2025 | 60 | TARUN GHOSH | 89.24 | 0 | 0 | 0
3492 | NADIA | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. , SM/14243 | New | Revamping / upgradation of the hydraulic parameters for Uttor Bhayna, Hatibanda, Aishmali, Nasra and Hijuli ( P ) villages in connection with Debogram, Nasra and Hijuli PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) | 530/NAD-I | 03/07/2025 | 120 | BUDDHADEV MONDAL | 53.23 | 0 | 0 | 0
3493 | NADIA | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. , SM/14243 | New | Continuation work order for Hiring of 1 (One) no inspection vehicle (Diesel Luxury Taxi/Maxi Cab/Motor Cab) on Daily basis for monitoring of JJM works by the Junior Engineers at the office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. (Period- 01/02/2025 to 31/07/2025) | 14/AE-I/NAD-I | 30/01/2025 | 181 | M/S DIPAK ENTERPRISE | 0.86 | 0 | 0 | 0
3494 | NADIA | Eastern Mechanical | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. , SM/14243 | New | Providing Boundary Illumination with allied works at Hijuli under Block_ Ranaghat-II Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/14243) | 1168/EMD | 04/06/2025 | 90 | SHRESTHA | 4.34 | 0 | 0 | 0
3495 | NADIA | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. , SM/14243 | New | Revamping / upgardation of hydraulic parameter of distribution network and providing FHTC for Doula, Debipur Chandpur Biraberia Dhantala & Notungram and Hizuli (Part) Village and under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in connection with Dhantala PWSS & Hizuli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | 800/NAD-I | 18/08/2025 | 90 | BIDYUT KUMAR | 182.15 | 0 | 0 | 0
3496 | NADIA | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. , SM/14243 | New | Shifting of Manifold and interconnection between old and new OHR and revamping /upgradation of hydraulic parameter in the distribution network at bhayna (P) paschim harin danga and hijuli part In connection with hijuli PWSS under Nadia Arsenic Division I, P.H.E. Dte. | 721/NAD-I | 29/07/2025 | 60 | TAPU SAHA | 51.24 | 0 | 0 | 0
3497 | NADIA | Nadia Arsenic Division I | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte. , SM/14243 | New | Balance Work for revamping/upgradation of the hydraulic parameters at distribution network at the part of Satpota and Hijuli (P) in connection with Hijuli PWSS under Nadia Arsenic Division-I, PHE Dte. As a part of Jal Jeevan Mission. (Sl. No. 01) | 1044/NAD-I | 25/09/2025 | 90 | NISHITH BANERJEE | 36.07 | 0 | 0 | 0
3498 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-III and IX within Kaliganj Block.(Phase-D) , SM/08957 | Retrofitting | Providing Functional Household Tap Connection(FHTC) at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-III & IX within KALIGANJ BLOCK(Phase-D). | 7052/ND | 06/12/2021 | 90 | TARUN KUMAR BHATTACHARYA | 180.22 | 168.03 | 93.24 | 0
3499 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-III and IX within Kaliganj Block.(Phase-D) , SM/08957 | Retrofitting | Material Requisition To Resource Division | 796/ND | 18/02/2022 | 0 | Resource Division | 16.5 | 0 | 0 | 0
3500 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-III and IX within Kaliganj Block.(Phase-D) , SM/08957 | Retrofitting | Filling fine sand over upvc pipeline for road restoration work at nimtala juranpur road(both side of road) in connection with augmentation of surface water based w/s scheme for Arsenic affected areas of Nadia district( Northern sector part-I) under Nadia Division PHE Dte. | 918KlySD-I | 07/06/2024 | 15 | UMWELT ENGINEER PVT LTD | 13.46 | 3.13 | 100 | 100
3501 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-III and IX within Kaliganj Block.(Phase-D) , SM/08957 | Retrofitting | Material Requisition To Resource Division | 316/ND | 15/01/2024 | 0 | Resource Division | 7.11 | 0 | 0 | 0
3502 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-III and IX within Kaliganj Block.(Phase-D) , SM/08957 | Retrofitting | Material Requisition To Resource Division | 317/ND | 15/01/2024 | 0 | Resource Division | 8.18 | 0 | 0 | 0
3503 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-III and IX within Kaliganj Block.(Phase-D) , SM/08957 | Retrofitting | Material Requisition To Resource Division | 315/ND | 15/01/2024 | 0 | Resource Division | 16.25 | 0 | 0 | 0
3504 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-III and IX within Kaliganj Block.(Phase-D) , SM/08957 | Retrofitting | Material Requisition To Resource Division | 314/ND | 15/01/2024 | 0 | Resource Division | 11.76 | 0 | 0 | 0
3505 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Gobindapur Water Supply Scheme In Hanskhali Block District Nadia. , SM/16358 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
3506 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Bagula Water Supply Scheme (Zone-I & II) In Hanskhali Block District Nadia. , SM/16365 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
3507 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Putimari Water Supply Scheme in Tehatta-I Block, Dist.-Nadia. , SM/16339 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
3508 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Hanspukuria Water Supply Scheme in Tehatta-II Block, Dist.-Nadia. , SM/16346 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
3509 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Bhimpur Water Supply Scheme in Krishnagar-I Block, Dist.- Nadia. , SM/16827 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
3510 | NADIA | Eastern Mechanical | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Karimpur-I & II Blocks in Nadia District under Eastern Mechanical Division PHE Dte. , SM/16846 | Solarisation | Solarisation of WBSEDCL Energised Electrical installation including net metering at different Pipe Water Supply Scheme at Karimpur-I & II Blocks in Nadia District under E.M.D. P.H.E. Dte. | 6454/EMD | 02/11/2023 | 182 | A.K. INDUSTRIES | 444.61 | 0 | 0 | 10
3511 | NADIA | Eastern Mechanical | Mini Piped Water Supply Scheme at Chak Rudranagar village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II , SM/16104 | New | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 0 | 80
3512 | NADIA | Nadia Arsenic Civil Division II | Mini Piped Water Supply Scheme at Chak Rudranagar village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II , SM/16104 | New | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Chak Rudranagar of Tehatta-II Block under Nadia Arsenic Civil Division-II PHE Dte | 564/NACD-II | 11/05/2023 | 960 | A.K ADHIKARY | 22.6 | 0 | 0 | 70
3513 | NADIA | Nadia Arsenic Civil Division II | Mini Piped Water Supply Scheme at Jayghata village, Block- Karimpur-II, Nadia District , under Nadia Arsenic Civil Division-II. , SM/16109 | New | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Jayghata of Karimpur- II Block under Nadia Arsenic Civil Division-II PHE Dte | 568/NACD-II | 11/05/2023 | 990 | GIYASUDDIN SEKH | 30.27 | 22.83 | 75.41 | 90
3514 | NADIA | Eastern Mechanical | Mini Piped Water Supply Scheme at Jayghata village, Block- Karimpur-II, Nadia District , under Nadia Arsenic Civil Division-II. , SM/16109 | New | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 0 | 80
3515 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Sonda Water Supply Scheme (Zone - I & II) in Krishnagar-I Block, Dist.- Nadia. , SM/16844 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
3516 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Subarna Behar Water Supply Scheme in Krishnagar-I Block, Dist.- Nadia. , SM/16845 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
3517 | NADIA | Eastern Mechanical | Solarizations of WBSEDCL Energized Electrical installation including Net Metering at Different Pipe Water Supply Scheme at Tehatta - I and Tehatta - II Blocks in Nadia District under Eastern Mechanical Division, PHE, Directorate. , SM/16849 | Solarisation | Solarisation of WBSEDCL Energised Electrical installation including net metering at different Pipe Water Supply Scheme at Tehatta-I & Tehatta-II Blocks in Nadia District under E.M.D. P.H.E. Dte. | 6352/EMD | 16/10/2023 | 183 | BALAJI UDDYOG | 409.59 | 0 | 0 | 0
3518 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Dogachi Water Supply Scheme in Karimpur-II Block of District Nadia , SM/16801 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
3519 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Karimpur Jalangi (Zone - VIII to X) Water Supply Scheme in Karimpur-II Block of District Nadia , SM/16803 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
3520 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Mahisbathan Water Supply Scheme in Karimpur-II Block of District Nadia , SM/16806 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
3521 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Bablari Dewanganj Water Supply Scheme in Nabadwip Block of District Nadia , SM/17274 | IOT | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No.I & II under Bablari Dewanganj W/S Scheme, Block-Nabadwip, Dist. - Nadia. NIET No.- 18 of EE/EMD of 2022-23 (Sl. No.- 02) | 6183/EMD | 14/11/2022 | 30 | M.S. ENTERPRISE | 15.63 | 0 | 0 | 0
3522 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Bablari Dewanganj Water Supply Scheme in Nabadwip Block of District Nadia , SM/17274 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
3523 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Gadigacha Water Supply Scheme in Nabadwip Block of District Nadia , SM/17276 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
3524 | NADIA | Nadia Division | Gotpara Piped Water Supply Scheme , SM/17685 | New | Route Survey, Design Drawing & DPR preparation for Gotpara water supply scheme under Debagram Sub- Division under Nadia Division, PHE Dte. | 319/DSD | 17/08/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.28 | 2.28 | 100 | 100
3525 | NADIA | Eastern Mechanical | Gotpara Piped Water Supply Scheme , SM/17685 | New | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at GOTPARA Piped Water Supply Scheme Block_ Nakashipara Dist. - Nadia under EMD, PHE Dte. | 811/EMD | 11/03/2024 | 30 | R.N.S. TRADING | 42.44 | 0 | 0 | 0
3526 | NADIA | Nadia Division | Gotpara Piped Water Supply Scheme , SM/17685 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 10 m3/hr at Gotpara Water Supply Scheme within Nakashipara Block under Debagram Sub-Divn. under Nadia Division, P.H.E. Dte. | 1901/ND | 15/03/2024 | 180 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 132.89 | 0 | 0 | 0
3527 | NADIA | Nadia Division | Gotpara Piped Water Supply Scheme , SM/17685 | New | Sinking of 1 No. 250mm. X 150mm. Dia 200 Mtr. deep Tube Well by Direct Rotary Rig Method using UPVC pipe having 250 mm Dia 48 Mtr. Long Housing Pipe & 150 mm. Dia Well Pipe & Deep Well Screen Pipe (RDS Strainer) at Gotpara Pipe Water Supply Scheme, at Nakashipara Block under Debagram Sub-Division under Nadia Division, PHE Dte. | 5117/ND | 17/11/2023 | 30 | B.M. ENGINEERING & CONSTRUCTION | 11.88 | 9.95 | 100 | 100
3528 | NADIA | Nadia Division | Gotpara Piped Water Supply Scheme , SM/17685 | New | Material Requisition To Resource Division | 276/ND | 11/01/2024 | 0 | Resource Division | 4.29 | 0 | 0 | 0
3529 | NADIA | Eastern Mechanical | Gotpara Piped Water Supply Scheme , SM/17685 | New | Quotation for New Connection at PH-I under Goat Para W/S Scheme under EMSD-III,PHE Dte. | BP-68-24-25 | 15/07/2024 | 0 | WBSEDCL BETHUADAHARI (NORTH) CCC | 9.3 | 0 | 0 | 0
3530 | NADIA | Nadia Division | Noachar Piped Water Supply Scheme , SM/17686 | New | Route Survey, Design Drawing & DPR preparation for Noachar water supply scheme under Debagram Sub- Division under Nadia Division, PHE Dte. | 321/DSD | 17/08/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.05 | 2.05 | 100 | 100
3531 | NADIA | Nadia Division | Noachar Piped Water Supply Scheme , SM/17686 | New | Material Requisition To Resource Division | 3642/ND | 16/08/2023 | 0 | Resource Division | 1.43 | 0 | 0 | 0
3532 | NADIA | Nadia Division | Noachar Piped Water Supply Scheme , SM/17686 | New | Material Requisition To Resource Division | 4222/ND | 19/09/2023 | 0 | Resource Division | 1.64 | 0 | 0 | 0
3533 | NADIA | Nadia Division | Noachar Piped Water Supply Scheme , SM/17686 | New | Construction of 10.00 cum/hr capacity Arsenic-Cum-Iron Removal Plant (AIRP) at Noachar PWSS including 3 Months Trial Run & 3 Years O&M under Kaliganj Block under Nadia Division, P.H.E. Dte. | 1494/ND | 04/03/2024 | 180 | SATYABRATA CHAKRABORTY | 133.17 | 0 | 0 | 0
3534 | NADIA | Nadia Division | Noachar Piped Water Supply Scheme , SM/17686 | New | Sinking of 1 No. 250mm. X 150mm. Dia 200 Mtr. deep Tube Well by Direct Rotary Rig Method using UPVC pipe having 250 mm Dia 48 Mtr. Long Housing Pipe & 150 mm. Dia Well Pipe & Deep Well Screen Pipe (RDS Strainer) at Noachar Pipe Water Supply Scheme, at Kaliganj Block under Nadia Division, PHE Dte. | 5118/ND | 17/11/2023 | 30 | B.M. ENGINEERING & CONSTRUCTION | 11.88 | 8.41 | 100 | 100
3535 | NADIA | Nadia Division | Noachar Piped Water Supply Scheme , SM/17686 | New | Construction of Jhama Bats Road for the approach way to headwork site of Noachar water supply scheme under Kalyani Sub Division I under Nadia Division P.H.Engineering Dte. | 105/KLYSD-I | 25/01/2024 | 30 | CHOWDHURY & CO. | 4.92 | 4.89 | 100 | 100
3536 | NADIA | Nadia Division | Noachar Piped Water Supply Scheme , SM/17686 | New | Laying distribution system for providing FHTC at Noarchar Mouza in connection with Augmentation of Ground Based Water Supply Scheme at Noachar to accommodate FHTC under Nadia Division, PHE Dte. | 1764/ND | 12/03/2024 | 45 | CHOWDHURY & CO. | 9.73 | 9.44 | 100 | 100
3537 | NADIA | Nadia Division | Noachar Piped Water Supply Scheme , SM/17686 | New | Material Requisition To Resource Division | 275/ND | 11/01/2024 | 0 | Resource Division | 2.33 | 0 | 0 | 0
3538 | NADIA | Eastern Mechanical | Noachar Piped Water Supply Scheme , SM/17686 | New | Quotation for new service connection at Nayachar water supply scheme. | BP-58-24-25 | 02/07/2024 | 0 | WBSEDCL DAINHAT CCC | 3.13 | 0 | 0 | 0
3539 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Uttar Tajpur PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17204 | Augmentation | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at UTTAR TAJPUR (PHASE-II) Piped Water Supply Scheme, Block:KARIMPUR-II, Dist. Nadia Under EMD, PHE Dte. | 6359/EMD | 17/10/2023 | 30 | SANKAR PRASAD DUTTA & CO | 41.45 | 0 | 0 | 0
3540 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Uttar Tajpur PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17204 | Augmentation | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Uttartajpur PWSS within Karimpur-I Block underTehatta Sub-Division under Nadia Division, PHE Dte. | 7264/ND | 13/12/2024 | 45 | GOUTAM DEY | 12.19 | 0 | 0 | 0
3541 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Uttar Tajpur PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17204 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 45 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Uttar Tajpur PWSS under Nadia Division PHE Dte. | 1806 / ND | 24/04/2023 | 90 | APURBA MANDAL | 85.67 | 0 | 0 | 60
3542 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Uttar Tajpur PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17204 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Uttartajpur PWSS under Karimpur-I Block under Tehatta Sub Division under Nadia Division-,P.H.E Dte. under Jal Jeevan Mission(JJM) . | 423/ND | 27/01/2025 | 300 | NISHITH BANERJEE | 26.22 | 0 | 0 | 60
3543 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONDA ZONE-I IN KRISHNAGAR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17208 | Augmentation | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at Sonada Zone-I Piped Water Supply Scheme Block_ Krishnanagar-I Dist. - Nadia under EMD, PHE Dte. | 6361/EMD | 17/10/2023 | 30 | A.G ENTERPRISE. | 41.9 | 0 | 0 | 0
3544 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONDA ZONE-I IN KRISHNAGAR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17208 | Augmentation | Renovation of AIRP (Semi-Gravity Type) of capacity 34 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Sonda Zone-I PWSS under Nadia Division PHE Dte. | 2995/ND | 13/07/2023 | 628 | TARUN KUMAR BHATTACHARYA | 62.48 | 3.06 | 9.6 | 40
3545 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone III PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17209 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, Zone-III(Phase-II) under Teinpur ground water based water supply scheme under Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. N.I.E.T No. 20 of EE / EMD of 2023-2024 (2023_PHED_554048_21) | 6787/EMD | 30/11/2023 | 30 | T.D.K. ENTERPRISE | 8.45 | 0 | 0 | 0
3546 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone III PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17209 | Augmentation | Proposed Augmentation of Laying Rising Main System and Sinking of Replacement Tube Well at Head Work Site of Teinpur Zone-III [Phase-II] Ground Based Piped Water Supply Scheme. | 1219/ND | 21/03/2023 | 60 | JOY HIND TUBEWELL'S | 14.37 | 9.86 | 100 | 80
3547 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone III PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17209 | Augmentation | Renovation of AIRP and Construction of Backwash chamber for AIRP at Head Work Site at Teinpur Zone-III PWSS under Nadia Division PHE Dte. Capacity- 40.30 cum/hr | 782/ND | 05/02/2024 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 83.94 | 15.68 | 100 | 70
3548 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone III PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17209 | Augmentation | Laying of 160 mm dia HDPE pipe line, 75 mm & 125 mm UPVC Pipe line for Augmentation of Rising Main System for distribution pipeline with interconnection along with road restoration at village Dogachhi, Block Karimpur-II under Nadia Division, P.H.E. Dte. | 1803/ND | 22/04/2025 | 180 | SUBHASH BOSE | 32.54 | 0 | 0 | 51
3549 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHIN JHITKAPOTA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17214 | Augmentation | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at DAKSHIN JHITKAPOTA ZONE-I (PHASE-II) Piped Water Supply Scheme, Block: Krishnagar-I, Dist. Nadia Under EMD, PHE Dte. | 6365/EMD | 17/10/2023 | 30 | M.S. ENTERPRISE | 53.53 | 0 | 0 | 0
3550 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHIN JHITKAPOTA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17214 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accommodate FHTC under DAKSHIN JHITKIPOTA(Z-1) W/S Scheme, Block-Krishnagar-I, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 09) | 1176/EMD | 21/03/2023 | 30 | SRI KRISHNA NIRMAN | 14.96 | 13.63 | 100 | 99
3551 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHIN JHITKAPOTA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17214 | Augmentation | Supplementary works to completion of ongoing FHTC-related work under Dakshin Jhitkipota (Zone-I) W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | 754/EMSD-II | 09/10/2023 | 10 | SRI KRISHNA NIRMAN | 0.63 | 0.63 | 100 | 100
3552 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHIN JHITKAPOTA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17214 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 95 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at DAKSHIN JHITKAPOTA ZONE I PWSS under Nadia Division PHE Dte. | 2999/ND | 13/07/2023 | 630 | B.M. ENGINEERING & CONSTRUCTION | 97.4 | 0 | 0 | 50
3553 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDAR KHOLA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17215 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No. I AND II under Bhandarkhola W/S Scheme, Block KrishnagarI, Dist. Nadia. NIET No. 23 of EE/EMD of 2022-23 (Sl. No.- 02) | 153/EMD | 06/01/2023 | 30 | P.K. ENTERPRISE | 15.11 | 13.41 | 100 | 65
3554 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDAR KHOLA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17215 | Augmentation | Suplimentary works to completion of ongoing FHTC-related work at BHANDERKHOLA W/S Scheme (Block-Krishnagar-I) PHE Dte.,Dist.-Nadia. | 666/EMSD-II | 05/09/2023 | 15 | P.K. ENTERPRISE | 0.69 | 0.64 | 100 | 100
3555 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDAR KHOLA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17215 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 58 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Bhanderkhola PWSS under Nadia Division PHE Dte. | 2997/ND | 13/07/2023 | 90 | TARUN KUMAR BHATTACHARYA | 87.75 | 15.34 | 38.44 | 68
3556 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PASCHIM BHATJUNGLA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17216 | Augmentation | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at Paschim Bhatjungla Zone-I (Phase-II) Piped Water Supply Scheme Block_ Krishnanagar-I Dist. - Nadia under EMD, PHE Dte. | 6372/EMD | 17/10/2023 | 30 | MAHADEV ENTERPRISE | 53.53 | 0 | 0 | 0
3557 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PASCHIM BHATJUNGLA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17216 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 104 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at PASCHIM BHATJUNGLA ZONE I PWSS under Nadia Division PHE Dte. | 1785/ND | 20/04/2023 | 722 | B.M. ENGINEERING & CONSTRUCTION | 120.62 | 64.89 | 53.8 | 70
3558 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PASCHIM BHATJUNGLA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17216 | Augmentation | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Paschim Bhatjangla Zone-I PWSS within Krishnagar-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 4073/ND | 26/07/2024 | 445 | SANDIP BISWAS | 148.49 | 0 | 0 | 70
3559 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Kalaighata Water Supply Scheme in Block - Ranaghat-I, District-Nadia , SM/18200 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
3560 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Par Niamatpur Water Supply Scheme in Ranagtat-I Block under District Nadia , SM/18202 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
3561 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Paschim Noapara Water Supply Scheme in Ranaghat-I Block District Nadia , SM/18203 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
3562 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Dhantala Water Supply Scheme in Ranagtat-II Block under District Nadia , SM/18209 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
3563 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR CHANDPUR WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09245 | Retrofitting | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Chandpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | 27/NACD-II | 10/01/2022 | 45 | M/S ANUBHAB CONSTRUCTION | 9.28 | 9.28 | 100 | 100
3564 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR CHANDPUR WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09245 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Chandpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 856/NACD-II | 08/11/2021 | 45 | M/S ANUBHAB CONSTRUCTION | 71.49 | 71.48 | 100 | 100
3565 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR CHANDPUR WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09245 | Retrofitting | Special reparing of damaged distribution pipe line due to construction of drain at Damodakhali and Chandpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 02/AE-I/NACD-II | 06/04/2022 | 45 | M/S SREE KRISHNA ENTERPRISE. | 5 | 5 | 100 | 100
3566 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR CHANDPUR WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09245 | Retrofitting | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HELENCHI (Z-I, Z-II, Z-III) (Block- Krishnaganj ) AND BANSBERIA,CHANDPUR & DAMODARKHALI (Block- Krishnagar I) W/S Scheme, , Dist. - Nadia. NIET NO.- 31 of EE/EMD of 2022-23 (Sl. No.- 02) | 1121/EMD | 16/03/2023 | 30 | M.S. ENTERPRISE | 65.68 | 5.87 | 100 | 90
3567 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR CHANDPUR WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09245 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline at Chandpur Pwss ( Vill- Chandpur, Krishnagar-I) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 548/NACD-II | 11/05/2023 | 60 | M/S SREE KRISHNA ENTERPRISE. | 7.31 | 7.12 | 100 | 100
3568 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR CHANDPUR WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09245 | Retrofitting | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Krishnagar-I Block of Nadia District through Jadavpur University. (Name of PWSS Chandpur) | 1057/NACD-II | 20/09/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
3569 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR CHANDPUR WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09245 | Retrofitting | Renovation work at Chandpur Head Work Site & 2nd tube well under Chandpur Piped Water Supply Scheme at Krishnagar-I Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia | 1056/AE-I/NACD-II | 19/12/2024 | 30 | TOTAN DAS | 4.27 | 0 | 0 | 0
3570 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR CHANDPUR WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09245 | Retrofitting | Renovation of Arsenic cum Iron treatment Plant of Chandpur PWSS (Capacity- 30 m3/hr) and ancillary works of Krishnagar-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte | 88/NACD-II | 18/01/2024 | 60 | MONDAL PRECISION PRIVATE LIMITED | 79.46 | 74.11 | 100 | 90
3571 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09258 | Augmentation | Construction of Soak Pit and land development and also concrete road construction for smooth movement within OHR site at Nischintapur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 36/AE-II/NACD-II | 17/02/2022 | 30 | A.K ADHIKARY | 4.99 | 4.98 | 99.79 | 100
3572 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09258 | Augmentation | Drawal of HT OH power line incld. errection of PCC pole inst. of electrical Transformer & supply of materials under supervision of WBSEDCL for new service connection at PH- II under Nischintapur w/s scheme NACD II under EMD PHE dte | 4426/ EMD | 30/06/2021 | 365 | ABHISEK ENGINEERING CONCERN | 1.08 | 1.08 | 100 | 100
3573 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09258 | Augmentation | Construction of Boundary wall with Grill Gate at Nischintapur Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | 49/AE-II/NACD-II | 17/02/2022 | 30 | NAMDAR ALI | 4.56 | 4.54 | 99.72 | 100
3574 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09258 | Augmentation | Reparing of vertical distribution line and also renovation of inside of OHR at Nischintapur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 454/NACD-II | 14/07/2022 | 30 | A.K ADHIKARY | 4.92 | 4.92 | 100 | 100
3575 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09258 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Nischintapur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 866/NACD-II | 08/11/2021 | 45 | TAPU SAHA | 51.28 | 47 | 100 | 100
3576 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09258 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Nischintapur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 733/NACD-II | 13/09/2021 | 45 | USHA CONSTRUCTION | 66.93 | 66.91 | 100 | 100
3577 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09258 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Nischintapur) | 1299/NACD-II | 29/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 0 | 0
3578 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09258 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under PUTIMARI(Block-Tehatt-I), NISCHINTAPUR(Block-Tehatt-I), W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 04) | 1504/EMD | 18/04/2023 | 30 | SRI KRISHNA NIRMAN | 10.69 | 5.24 | 100 | 80
3579 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09258 | Augmentation | Laying of D.I. Pipeline as rising main from 2nd Tube Well Site to head work site and also construction of column for supporting the pipeline at Nischintapur Water Supply Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1082/NACD-II | 09/12/2022 | 30 | SUPER CONSTRUCTION | 7.15 | 5.75 | 100 | 100
3580 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09258 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Nischintapur) | 1301/NACD-II | 29/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
3581 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09258 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Nischintapur Water Supply Scheme in Tehatta-I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 321_1/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.43 | 1.43 | 100 | 100
3582 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09258 | Augmentation | Quotation for load enhancement of power supply at PH-I of Nischintapur W/S scheme ,under EMSD-III, PHE Dte., Nadia | BP-163-24-25 | 25/11/2024 | 0 | W.B.S.E.D.C.L (TEHATTA CCC) | 4.34 | 0 | 0 | 0
3583 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Betberia Water Supply Scheme in Chapra Block, Dist.-Nadia. , SM/18050 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
3584 | NADIA | Eastern Mechanical | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | NEW SERVICE CONNECTION CHARGES FOR BHATGACHHI W/S SCHEME P.H. NO P.H. NO 1 | 2870/EMD | 21/07/2022 | 30 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.04 | 0 | 0 | 0
3585 | NADIA | Eastern Mechanical | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | New Service connection for BHATGACHHI w/s scheme p.h No:-1 | 2867/EMD | 21/07/2022 | 30 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.2 | 0 | 0 | 0
3586 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Soil Investigation for Construction of 3 (Three) Nos. of Overhead Reservoir of staging height of 20 mtr. Under Nadia Arsenic Civil Division-II P.H.E. Dte. Site - Bhatgachhi W/s Scheme, Dhopahat W/s Scheme, Hatkhola W/s Scheme | 249/AE-I/NACD-II | 25/02/2022 | 15 | PROSENJIT DAS | 2.44 | 2.44 | 100 | 100
3587 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
3588 | NADIA | Eastern Mechanical | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | New Service connection bill for BHATGACHHI PIPED WATER SUPPLY SCHEME | BP-2022-23-27 | 02/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.16 | 0 | 0 | 0
3589 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
3590 | NADIA | Eastern Mechanical | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | New Service connection bill for BHATGACHHI PIPED WATER SUPPLY SCHEME | BP-2022-23-26 | 02/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.04 | 0 | 0 | 0
3591 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
3592 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Bhatgachhi and adjoining mouzas under Bhatgachhi Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | 299/NACD-II | 19/05/2022 | 90 | SATYABRATA CHAKRABORTY | 236.84 | 199.25 | 84.13 | 100
3593 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Additional Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Bhatgachhi and adjoining mouzas under Bhatgachhi Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | 523/NACD-II | 05/08/2022 | 60 | INVENT ENGINEER'S COOP SOCIETY LTD. | 71.56 | 66.55 | 93 | 100
3594 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Bhatgachhi 2nd Tubwell site within Bhatgachhi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 116/NACD-II | 11/01/2023 | 60 | M/S SANTOSHI MAA ENTERPRISE | 5.12 | 4.84 | 94.54 | 85
3595 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Bhatgachhi water supply scheme of Chapra Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | 355/NACD-II | 22/03/2023 | 366 | SUDHAMAY MAJUMDAR | 116.75 | 0 | 0 | 5
3596 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Construction for priliminary work of the approch road at Head Works site of Bhatgachhi Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | 405/AE-I/NACD-II | 08/08/2023 | 15 | SUDHAMAY MAJUMDAR | 0.96 | 0 | 0 | 0
3597 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement for Tube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Bhatgachhi water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | 18/AE-I/NACD-II | 13/04/2022 | 60 | PRADIP KUMAR BANIK | 2.83 | 2.81 | 100 | 100
3598 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Bhatgachhi and Karuigachhi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 246/NACD-II | 19/04/2022 | 60 | JOY HIND TUBEWELLS | 41.88 | 39.98 | 100 | 100
3599 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Earthwork in filling in approach road at Bhatgachhi Water Supply Scheme at Bhatgachhi H/W site under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 112/AE-I/NACD-II | 28/06/2022 | 30 | M/S RAJESH CONSTRUCTION | 4.83 | 4.81 | 100 | 100
3600 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Bhatgachhi Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 619/NACD-II | 06/09/2022 | 20 | RAMASISH ENTERPRISE | 4.39 | 4.39 | 100 | 100
3601 | NADIA | Eastern Mechanical | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Supply delivery of PCC Pole M.s materials and Electrical accessories and installation DTR of HTOH line to WBSEDCL for new service connection at PH-I under Bhatgachi W/S Scheme | 1231/EMSD-III | 21/10/2022 | 30 | KUNDU ELECTRICAL ENTERPRISE | 4.19 | 4.19 | 100 | 10
3602 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bhatgachhi) | 887/NACD-II | 18/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
3603 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Bhatgachhi water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 209/NACD-II | 05/04/2022 | 60 | PRADIP KUMAR BANIK | 5.38 | 5.32 | 100 | 100
3604 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Material Requisition To Resource Division | 399/NACD-II | 04/07/2022 | 0 | Resource Division | 51.43 | 0 | 0 | 0
3605 | NADIA | Eastern Mechanical | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | New Service Connection under AE-III Bhatgachi | BP-101-23-24 | 31/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.39 | 0 | 0 | 0
3606 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Laying of Rising Main of Bhatgachhi Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | 23/AE-I/NACD-II | 13/04/2022 | 60 | SOURAV & CO. | 4.53 | 1.86 | 41.09 | 90
3607 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Acceptance cum work order "Construction of 100 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir at Head Works site of Tengra Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | 337/NACD-II | 05/03/2024 | 365 | CHATTERJEE CONSTRUCTION | 94.23 | 0 | 0 | 0
3608 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 43 cum/Hour capacity for Bhatgachhi Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1151/NACD-II | 27/08/2024 | 180 | SINGHA ROY & CO. | 173.86 | 0 | 0 | 0
3609 | NADIA | Eastern Mechanical | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro-mechanical works,Voltage Stabilizar and Automatic Chlorinator ( in connection with Aug.work related to FHTC) at Pump Hose No.I(Headworks) under Bhatgachhi W/S Scheme District of Nadia NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 01) | 5093/EMD | 04/11/2022 | 30 | KUNDU ELECTRICAL ENTERPRISE | 10.11 | 10.03 | 100 | 90
3610 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations new vested land under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bhatgachhi) | 1068/NACD-II | 12/08/2024 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
3611 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Renovation of Arsenic cum Iron treatment Plant of Bahirgachhi Zone-II PWSS (Capacity- 23 m3/hr) and Bhatgachhi PWSS ancillary works of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 35/NACD-II | 09/01/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 100.51 | 34.9 | 100 | 80
3612 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Bhatgachhi Water Supply Scheme at Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | 77/NACD-II | 10/01/2023 | 305 | M/S FREEDOM CONSTRUCTION | 14.78 | 10.57 | 71.5 | 86
3613 | NADIA | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Conversion of IEP to AIRP at Balidanga Water Supply Scheme of capacity 58 Cu.m/hr in Chapra Block including other works at Bhatgachhi & Karuigachhi Water Supply Scheme under Nadia Arsenic Civil Division -II, PHE Dte. | 1048/NACD-II | 07/08/2024 | 60 | DEBASIS SAMADDAR | 185.55 | 0 | 0 | 0
3614 | NADIA | Eastern Mechanical | BHATGACHHI PIPED WATER SUPPLY SCHEME , SM/10099 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Bhatgachhi W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 02) | 5010/EMD | 03/11/2022 | 760 | R.N.S. TRADING | 10.2 | 9.19 | 91.29 | 80
3615 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-I, (Palagachha), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme , SM/07902 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Dhara /Jal Swapna for Zone-I, (Palagachha) Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. Tender No. 219/NAD-I/2020-2021. | 313/NAD-I | 08/02/2021 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 97.1 | 176.58 | 115.33 | 100
3616 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11742 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 8/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 155/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.29 | 3.22 | 100 | 100
3617 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11742 | Augmentation | Material Requisition To Resource Division | 1524/ND | 04/04/2023 | 0 | Resource Division | 66.26 | 0 | 0 | 0
3618 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11742 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
3619 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11742 | Augmentation | Material Requisition To Resource Division | 245/ND | 11/01/2024 | 0 | Resource Division | 9.65 | 0 | 0 | 0
3620 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11742 | Augmentation | Restoration of T 02 - Bethuadahari to Thegahri Ghat under Package no. WB 14-197. | 262/PFMS | 26/09/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 2.51 | 0 | 0 | 0
3621 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11742 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4588/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 119.6 | 60.39 | 19
3622 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11742 | Augmentation | Construction of OHR, staff room, chlorine room, service road, repairing of boundary wall and restoration of bituminous road, land improvement etc. of Surface Water Based Water Supply Scheme for Zone-VIII / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11742]. | 5370/ND | 04/12/2023 | 741 | GHOSH CONSTRUCTION | 172.65 | 16.1 | 9.33 | 10
3623 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11742 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 5.06 | 84.28 | 30
3624 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11742 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
3625 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11844 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 6/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 149/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.35 | 4.34 | 100 | 100
3626 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11844 | Augmentation | Additional Survey, Design Drawing & DPR Preparation for ZONE 6/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 150/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 0.87 | 0.83 | 100 | 98
3627 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11844 | Augmentation | Material Requisition To Resource Division | 99/ND | 05/01/2023 | 0 | Resource Division | 282.19 | 0 | 0 | 0
3628 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11844 | Augmentation | Material Requisition To Resource Division | 239/ND | 11/01/2024 | 0 | Resource Division | 3.51 | 0 | 0 | 0
3629 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11844 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4589/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 236.21 | 57.97 | 50
3630 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11844 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
3631 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11734 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 4A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 122/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.82 | 4.74 | 100 | 100
3632 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11734 | Augmentation | Material Requisition To Resource Division | 73/ND | 05/01/2023 | 0 | Resource Division | 359 | 0 | 0 | 0
3633 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11734 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
3634 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11734 | Augmentation | Restoration of road Chakundi More to Chakundi Ghat. | 304/PFMS | 02/10/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 8.17 | 0 | 0 | 0
3635 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11734 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 370.4 | 69.53 | 47
3636 | NADIA | Nadia Division | Providing FHTC by Augmentation for Fatepur PWSS Block: Hanskhali, District: Nadia , SM/10428 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Fatepur W/S Scheme in Hanskhali Block of Nadia District under Nadia Division, P.H.E. Dte. | 1050/RSD | 02/12/2021 | 30 | HORIZEN | 2.74 | 2.59 | 100 | 100
3637 | NADIA | Nadia Division | Providing FHTC by Augmentation for Fatepur PWSS Block: Hanskhali, District: Nadia , SM/10428 | Augmentation | Material Requisition To Resource Division | 1875/ND | 26/04/2023 | 0 | Resource Division | 17.01 | 0 | 0 | 0
3638 | NADIA | Nadia Division | Providing FHTC by Augmentation for Fatepur PWSS Block: Hanskhali, District: Nadia , SM/10428 | Augmentation | Material Requisition To Resource Division | 2314/ND | 29/05/2023 | 0 | Resource Division | 3.28 | 0 | 0 | 0
3639 | NADIA | Nadia Division | Providing FHTC by Augmentation for Fatepur PWSS Block: Hanskhali, District: Nadia , SM/10428 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 100 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of OHR all complete for augmentation of Ground Water Based Water Supply Scheme for Fatepur to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | 964/ND | 09/03/2023 | 1057 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 175.81 | 87.93 | 50.01 | 92
3640 | NADIA | Nadia Division | Providing FHTC by Augmentation for Fatepur PWSS Block: Hanskhali, District: Nadia , SM/10428 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Fatepur PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 45.00 Cu.m/hr. | 839/ND | 06/02/2024 | 455 | ZEOLITE FRESH INDIA | 58.36 | 0 | 0 | 60
3641 | NADIA | Eastern Mechanical | Providing FHTC by Augmentation for Fatepur PWSS Block: Hanskhali, District: Nadia , SM/10428 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at Fatepur W/S Scheme Block- Hanskhali under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/10428 | 1149/EMD | 04/06/2025 | 90 | DEY ENTERPRISE | 33.38 | 0 | 0 | 0
3642 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Muragachha Zone-I Part-II, at Hanskhali Block by retrofitting of Ground Water based PWSS for Muragachha Water Supply Scheme , SM/08012 | Retrofitting | Providing FHTC Functional Household Tap Connection under Jaldhara Jal Swapna for Muragachha Zone I Part II at Hanskhali Block by retrofitting of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Division I PHE Dte. | 781/NAD-I | 05/05/2021 | 60 | MONDAL ENTERPRISE | 89.68 | 133.41 | 149.04 | 100
3643 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Radhakantapur Part-II, at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Radhakantapur Water Supply Scheme , SM/08013 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Radhakantapur, Part-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Radhakantapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 778/NAD-I | 05/05/2021 | 60 | M/S R.K. ENTERPRISE | 97.1 | 188.25 | 98.74 | 100
3644 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Gayeshpur Zone-I, at Santipur Block by retrofitting of Ground Water based PWSS for Gayeshpur Water Supply Scheme , SM/08014 | Retrofitting | Providing FHTC Functional Household Tap Connection under Jaldhara Jal Swapna for Gayeshpur Zone I at Santipur Block by retrofitting of Ground Water based PWSS for Gayeshpur Water Supply Scheme under Nadia Arsenic Division I PHE Dte. | 782/NAD-I | 05/05/2021 | 60 | APURBA MANDAL | 96.99 | 186.81 | 100 | 100
3645 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIII, (Tarinipur), Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07446 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIII, (Tarinipur), Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte.¿ (Sl. No. 02) | 96/NAD-I | 13/01/2021 | 60 | GHOSH ENTERPRISE | 79.67 | 156.3 | 100 | 100
3646 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIII, (Tarinipur), Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07446 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, Masra, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 773/NAD-I | 04/05/2021 | 60 | H I ENTERPRISE | 95.74 | 0 | 200 | 100
3647 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Balance Portion of Zone-XI, (Birohi) at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07449 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Balance Portion of Zone-XI, (Birohi), at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 95/NAD-I/20-21 | 13/01/2021 | 60 | TAPU SAHA | 75.09 | 137.67 | 124.08 | 100
3648 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Krishnagar & Nabadwip (Part) Block (Phase-A) , SM/07455 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Krishnagar & Nabadwip (Part) Block (Phase-A). | 163/PFMS | 07/09/2021 | 0 | TARUN KUMAR BHATTACHARYA | 93.03 | 0 | 0 | 0
3649 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Krishnagar & Nabadwip (Part) Block (Phase-A) , SM/07455 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-III, Z-I, WITHIN KRISHNAGAR AND NABADWIP BLOCK , PHASE-A. | 501/PFMS | 03/02/2022 | 0 | M/S R. DUTTA & CO. | 0.45 | 0 | 0 | 0
3650 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Krishnagar & Nabadwip (Part) Block (Phase-A) , SM/07455 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-I, within Krishnagar-II & Nabadwip Block (Phase-A, Retrofitting) | 770/ND | 10/02/2021 | 90 | TARUN KUMAR BHATTACHARYA | 97.09 | 0 | 0 | 0
3651 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Krishnagar & Nabadwip (Part) Block (Phase-A) , SM/07455 | Retrofitting | Providing additional FHTC in connection with Surface based WSS (Northern Sector) Part-III , Zone I within Krishnagar II & Nabadwip (Part) Block (Phase-A) | 490/KSD | 25/04/2023 | 15 | TARUN KUMAR BHATTACHARYA | 0.96 | 0 | 0 | 90
3652 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase-B) , SM/07476 | Retrofitting | Schedule for laying of pipe line and allied work upto Kaliganj BDO office under Zone-V of Surface Water Based Water Supply Scheme, Nadia District Northern Sector (Part-I) under Debagram Sub Division P.H.E Dte. | 175/D/DSD | 18/04/2022 | 30 | TARUN KUMAR BHATTACHARYA | 2.22 | 2.05 | 100 | 0
3653 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase-B) , SM/07476 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-IX within Kaliganj Block (Phase-B) | 2767/ND | 14/07/2021 | 90 | M/S K.P. CONSTRUCTION | 91.11 | 80.29 | 100 | 0
3654 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase-B) , SM/07476 | Retrofitting | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Maidanpur ii) Kulgachhi iii) Monipota iv) Habibpur v) Magurkhali. | 372/ Kly SD-I | 17/03/2023 | 184 | HORIZEN | 4.99 | 1.7 | 100 | 10
3655 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase-B) , SM/07476 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 3.43 | 100 | 81
3656 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VI within Nakashipara Block (Phase-B) , SM/07504 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VI within Nakashipara Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte.(SL.5) | 412/PFMS | 21/12/2021 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 89.1 | 0 | 0 | 0
3657 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VI within Nakashipara Block (Phase-B) , SM/07504 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-II, Z-VI, WITHIN NAKASHIPARA BLOCK, PHASE-B. | 494/PFMS | 03/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.73 | 0 | 0 | 0
3658 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VI within Nakashipara Block (Phase-B) , SM/07504 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VI within Nakashipara Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte.(SL.5) | 970/ND | 25/02/2021 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 97 | 0 | 0 | 100
3659 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VI within Nakashipara Block (Phase-B) , SM/07504 | Retrofitting | Material Requisition To Resource Division | 4281/ND | 29/09/2022 | 0 | Resource Division | 12.5 | 0 | 0 | 0
3660 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Chandpur water supply scheme under Krishnagar-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07934 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Chandpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 856/NACD-II | 08/11/2021 | 45 | M/S ANUBHAB CONSTRUCTION | 71.49 | 0 | 0 | 100
3661 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Bagbaria water supply scheme under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07938 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Bagberia (Vill-Bagberia) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 1185/NACD-II | 13/11/2020 | 25 | M/S GHOSH CONSTRUCTION | 4.99 | 0 | 0 | 0
3662 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Gongra water supply scheme under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07960 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Gongra (Vill-Gongra) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1193/NACD-II | 13/11/2020 | 25 | JOY GOPAL GUPTI | 4.99 | 0 | 0 | 0
3663 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Tarapur, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Tarapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08817 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Tarapur Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Tarapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1420/NAD-I | 08/11/2021 | 60 | CHAKRABORTTI ENTERPRISE | 68.76 | 59.6 | 100 | 100
3664 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Tarapur, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Tarapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08817 | Retrofitting | Construction of Boundary wall & other allied works at 2nd Tubewell site of Ground water based piped supply scheme of Tarapur under Nadia Arsenic Division-I,P.H.E. Dte. Length of Boundary wall - 57 metre. | 75/NAD-I | 17/01/2022 | 20 | M/S S.K ENTERPRISE | 6.9 | 6.47 | 100 | 100
3665 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Tarapur, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Tarapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08817 | Retrofitting | Material Requisition To Resource Division | 144/NAD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0 | 0
3666 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Tarapur, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Tarapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08817 | Retrofitting | Construction and installation of MANIFOLD and allied works at OHR site under Tarapur Ground Based Water Supply Scheme under Ranaghat-I under Nadia Arsenic Division-I,P.H.E Dte. in connection with Retrofitting under JJM of Tarapur (Part-I) Piped W/S Scheme (sl.no.14) | 1429/NAD-I | 24/05/2023 | 15 | SAORSA | 13.03 | 12.49 | 100 | 100
3667 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ukhilnara Zone-I, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08826 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ukhilnara, Zone-I Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Ukhilnara, Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1404NAD-I | 08/11/2021 | 60 | UNICON INDIA | 77.99 | 61.09 | 78.32 | 100
3668 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ukhilnara Zone-I, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08826 | Retrofitting | Collection of Water Sample form different water supply scheme for testing at laboratory through collection to be engaged through agency under Nadia Arsenic Division- I PHE Dte. | 191/AE-I/NAD-I | 29/07/2022 | 365 | M/S ARATI ENTERPRISE | 4.78 | 4.77 | 100 | 100
3669 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XIII, (Digha), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divisi , SM/08834 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Haringhata & Chakdah Zone-XIII (Digha), Part-II at Haringhata Block by retrofitting of Ground Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1566/NAD-I | 13/12/2021 | 90 | SATYABRATA CHAKRABORTY | 132.3 | 122.27 | 60.56 | 100
3670 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XIII, (Digha), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divisi , SM/08834 | Retrofitting | Supply of 1(one) no. Motor Cab (Luxury Taxi) on hire basis for official use of the Assistant Engineer-I, Nadia Arsenic Division - I, P.H.E. Dte. for the period from 15.07.2020 to 14.07.2021 i.e. for 1(one) year. | 155 / AE-I / NAD-I | 14/07/2020 | 365 | SUMAN CHAKRABORTY | 2.25 | 2.25 | 100 | 100
3671 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XIII, (Digha), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divisi , SM/08834 | Retrofitting | Augmentation of Existing structure and other allied works under Zone-XIII (Digha) Part-II under Surface Based PWSS for Haringhata & Chakdah(Part) under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (sl.01) | 829 / NAD-I | 31/03/2023 | 15 | TARUN KUMAR BHATTACHARYA | 13.23 | 13.21 | 100 | 90
3672 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XIII, (Digha), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divisi , SM/08834 | Retrofitting | Supply of 1(one) no. Motor Cab (Luxury Taxi) on hire basis for official use of the Assistant Engineer-I, Nadia Arsenic Division - I, P.H.E. Dte. for the period from 15.07.2022 to 14.07.2023 i.e. for 1(one) year. | 172 / AE-I / NAD -I | 14/07/2022 | 365 | SUMAN CHAKRABORTY | 4.8 | 2.66 | 100 | 75
3673 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) underJaldhara / Jal Swapna for Zone-II, (Joykrishnapur) at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08861 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II (Joykrishnapur) at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 52/NAD-I | 11/01/2022 | 90 | GHOSH ENTERPRISE | 270 | 247.17 | 100 | 100
3674 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) underJaldhara / Jal Swapna for Zone-II, (Joykrishnapur) at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08861 | Retrofitting | Material Requisition To Resource Division | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 25.02 | 0 | 0 | 0
3675 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Kadipur water supply scheme underKrishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08301 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Kadipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1070/NACD-II | 25/09/2020 | 15 | SANJIT DAS | 4.99 | 0 | 0 | 0
3676 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Baranaldaha water supply scheme underTehatta-II Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08308 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Baranaldaha (Vill-Dakshin Para) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 208/NACD-II | 19/02/2021 | 15 | TAPAN SAHA | 4.94 | 0 | 0 | 0
3677 | NADIA | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-IIWater Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/09046 | Retrofitting | Providing Functional House Tap Connection from Teinpur Zone-IIWater Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | 696/PFMS | 28/03/2022 | 0 | MALI CONSTRUCTION | 38.98 | 0 | 0 | 0
3678 | NADIA | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-IIWater Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/09046 | Retrofitting | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H.E. Dte., Kalyani, Nadia. Period of work 01-03-2022 to 28-02-2023 | 118/RSD | 28/02/2022 | 250 | SUMAN CHAKRABORTY | 3.85 | 1.8 | 77.45 | 75
3679 | NADIA | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-IIWater Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/09046 | Retrofitting | Material Requisition To Resource Division | 440/ND | 31/01/2022 | 0 | Resource Division | 1.19 | 0 | 0 | 0
3680 | NADIA | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-IIWater Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/09046 | Retrofitting | Material Requisition To Resource Division | 820/ND | 18/02/2022 | 0 | Resource Division | 3.44 | 0 | 0 | 0
3681 | NADIA | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-IIWater Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. , SM/09046 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Teinpur Zone-II W/S scheme in Nadia District under Nadia Division P.H.E. Dte. | 5687/ND | 03/11/2021 | 90 | MALI CONSTRUCTION | 67.51 | 7.32 | 100 | 100
3682 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division , SM/09572 | Augmentation | Supply, delivery and installation of voltage stabilizar under Natungram W/s scheme under EMSD II PHED. Nadia | 306/EMSD II | 05/05/2021 | 40 | SANKAR PROSAD DUTTA & CO. | 4.15 | 4.15 | 100 | 100
3683 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division , SM/09572 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division | 730/PFMS | 30/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.76 | 0 | 0 | 0
3684 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division , SM/09572 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division | 03/PFMS | 26/04/2022 | 0 | M/S DIPAK ENTERPRISE | 0.16 | 0 | 0 | 0
3685 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division , SM/09572 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district under Nadia division | 714/PFMS | 30/03/2022 | 0 | M/S DIPAK ENTERPRISE | 50 | 0 | 0 | 0
3686 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division , SM/09572 | Augmentation | Providing Functional Household Tap Connection (part) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (as required size), 15 mm dia Bib Cock etc. all complete at Natungram Water Supply Scheme at Hanskhali Block in Nadia District under Nadia Division PHE Dte. | 696/ND | 15/02/2022 | 90 | M/S DIPAK ENTERPRISE | 68.56 | 16.75 | 100 | 99
3687 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division , SM/09572 | Augmentation | Material Requisition To Resource Division | 443/ND | 31/01/2022 | 0 | Resource Division | 0.6 | 0 | 0 | 0
3688 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division , SM/09572 | Augmentation | Material Requisition To Resource Division | 4314/ND | 29/09/2022 | 0 | Resource Division | 5.42 | 0 | 0 | 0
3689 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division , SM/09572 | Augmentation | Material Requisition To Resource Division | 1862/ND | 26/04/2023 | 0 | Resource Division | 17.96 | 0 | 0 | 0
3690 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division , SM/09572 | Augmentation | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of 30 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Nutangram to accommodate FHTC within Hanskhali block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | 136/ND | 08/01/2025 | 180 | APURBA MANDAL | 160.04 | 0 | 0 | 0
3691 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division , SM/09572 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Nutangram under Ranaghat Sub-Division under Nadia Division PHE Dte. | 1425/RSD | 19/11/2024 | 178 | SAGAR ENTERPRISE | 2.15 | 0 | 0 | 100
3692 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division , SM/09572 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under NUTANGRAM ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. SM/09572 | 1123/EMD | 04/06/2025 | 90 | SHRESTHA | 17.48 | 0 | 0 | 0
3693 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09244 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Damodarkhali W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 985/NACD-II | 27/12/2021 | 90 | SUPRITI ENTERPRISE | 111.19 | 111.18 | 99.99 | 100
3694 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09244 | Retrofitting | Change of Media of AIRP at Damodarkhali H/W site under Damodarkhali W/S scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. | 36/AE-I/NACD-II | 02/05/2022 | 10 | RUPALI ELECTRONICS | 4.93 | 4.93 | 100 | 100
3695 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09244 | Retrofitting | RESOURCE PAYMENT DAMODARKHALI | 257 | 26/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 20.38 | 0 | 0 | 0
3696 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09244 | Retrofitting | OUTSTANDING BILL PAYMENT FOR SUPPLY OF MATERIALS FOR THANAPARA, DAMODARKHALI, MADHABPUR, BALIADANGA AS FRAMED BY RESOURCE DIVISION PHE DTE. |  | 05/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0 | 0
3697 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09244 | Retrofitting | Outstanding as framed by Resource Division for supply of materials for augmentation/retrofitting of Thanapara, Damodarkhali & Madhabpur under Nadia Arsenic Civil Division-II, PHE dte. | 212, 213, 214 | 18/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 124.39 | 0 | 0 | 0
3698 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09244 | Retrofitting | RESOURCE PAYMENT DAMODARKHALI | 256 | 26/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 33.72 | 0 | 0 | 0
3699 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09244 | Retrofitting | SUPPLY OF MATERIALS FOR THANAPARA,DAMODARKHALI,MADHABPUR AND BALIADANGA W/S. SCHEME UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. |  | 07/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0 | 0
3700 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09244 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) & also construction of Soak Pit at Damodarkhali W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 522/NACD-II | 14/06/2021 | 45 | SHYAMAL SHIL | 51.46 | 40.46 | 100 | 100
3701 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09244 | Retrofitting | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or daaged line repair) & also construction of Soak Pit at Damodarkhali W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 569/NACD-II | 14/07/2021 | 45 | SHYAMAL SHIL | 6.11 | 6.11 | 100 | 100
3702 | NADIA | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09244 | Retrofitting | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HELENCHI (Z-I, Z-II, Z-III) (Block- Krishnaganj ) AND BANSBERIA,CHANDPUR & DAMODARKHALI (Block- Krishnagar I) W/S Scheme, , Dist. - Nadia. NIET NO.- 31 of EE/EMD of 2022-23 (Sl. No.- 02) | 1121/EMD | 16/03/2023 | 30 | M.S. ENTERPRISE | 65.68 | 5.87 | 100 | 90
3703 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09244 | Retrofitting | Material Requisition To Resource Division | 955/NACD-II | 14/12/2021 | 0 | Resource Division | 64.9 | 0 | 0 | 0
3704 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09244 | Retrofitting | Construction and installation of MANIFOLD and allied works at OHR site under Damodarkhali Piped Water Supply Scheme in Krishnagar-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 711/NACD-II | 07/06/2024 | 45 | GHOSH ENTERPRISE | 19.1 | 0 | 0 | 100
3705 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09244 | Retrofitting | Jungle cutting at Mahatpur,Patharghata,Baliadanga,Helenchi Zone-III,Joyghata and Damodarkhali Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 820/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.16 | 0.01 | 100 | 100
3706 | NADIA | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09244 | Retrofitting | Renovation of Arsenic cum Iron treatment Plant of Damodarkhali PWSS (Capacity- 56 m3/hr) and ancillary works of Baruihuda W/S Scheme at Krishnagar-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 37/NACD-II | 09/01/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 100.41 | 20.2 | 100 | 100
3707 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) , SM/08952 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) | 46/PFMS | 13/06/2022 | 0 | MONDAL PRECISION PRIVATE LIMITED | 72.81 | 0 | 0 | 0
3708 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) , SM/08952 | Retrofitting | Laying additional distribution pipeline for providing FHTC at Digha, Birpur , sarbari & Patpukur villeges under zone VIII , Part-II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | 309/DSD | 27/07/2022 | 30 | MONDAL PRECISION PRIVATE LIMITED | 4.78 | 3.06 | 64.03 | 0
3709 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) , SM/08952 | Retrofitting | Laying additional distribution pipeline for providing FHTC at Birpur Patpukur Teghari villeges under zone VIII , Part-II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | 310/DSD | 27/07/2022 | 30 | MONDAL PRECISION PRIVATE LIMITED | 4.77 | 3.09 | 64.77 | 0
3710 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) , SM/08952 | Retrofitting | Laying additional distribution pipeline for providing FHTC at Birpur Petuabhanga & Digha villeges under zone VIII , Part-II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | 311/DSD | 27/07/2022 | 30 | MONDAL PRECISION PRIVATE LIMITED | 4.84 | 3.42 | 70.76 | 0
3711 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) , SM/08952 | Retrofitting | Laying additional distribution pipeline for providing FHTC at Sarbari & Digha villeges under zone VIII , Part-II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | 312/DSD | 27/07/2022 | 30 | MONDAL PRECISION PRIVATE LIMITED | 4.85 | 1.95 | 40.18 | 0
3712 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) , SM/08952 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Surface Water based Water Supply Scheme (Northern Sector) Part-II,Zone-VIII within Nakashipara Block(Phase-C) | 7315/ND | 21/12/2021 | 90 | MONDAL PRECISION PRIVATE LIMITED | 180.04 | 47.52 | 100 | 100
3713 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) , SM/08952 | Retrofitting | Material Requisition To Resource Division | 4272/ND | 29/09/2022 | 0 | Resource Division | 24.89 | 0 | 0 | 0
3714 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) , SM/08952 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-V within Nakashipara Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte.(SL.3) | 868/ND | 18/02/2021 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 97.09 | 0 | 0 | 0
3715 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) , SM/08952 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VI within Nakashipara Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte.(SL.4) | 888/ND | 19/02/2021 | 90 | UNICON INDIA | 96.71 | 0 | 0 | 0
3716 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) , SM/08952 | Retrofitting | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- VII/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4282/ND | 21/09/2023 | 534 | SATYABRATA CHAKRABORTY | 397.18 | 0 | 0 | 14
3717 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) , SM/08952 | Retrofitting | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4588/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 13.77 | 99.6 | 19
3718 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) , SM/08952 | Retrofitting | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4589/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 0 | 0 | 50
3719 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VII within Kaliganj Block. (PhaseC) , SM/08955 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Surface Water Based Water Supply Scheme (northern Sector)Part-I,Zone-VII within Kaliganj Block (Phase-C) | 7314/ND | 21/12/2021 | 90 | ORIENT CONSTRUCTION | 180.23 | 0 | 0 | 0
3720 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VII within Kaliganj Block. (PhaseC) , SM/08955 | Retrofitting | Material Requisition To Resource Division | 4291/ND | 29/09/2022 | 0 | Resource Division | 24.87 | 0 | 0 | 0
3721 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VII within Kaliganj Block. (PhaseC) , SM/08955 | Retrofitting | Material Requisition To Resource Division | 311/ND | 15/01/2024 | 0 | Resource Division | 18.65 | 0 | 0 | 0
3722 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VII within Kaliganj Block. (PhaseC) , SM/08955 | Retrofitting | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4589/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 0 | 0 | 50
3723 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09537 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | 610/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.34 | 0 | 0 | 0
3724 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09537 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No.(Zone-I) under Elangi W/S Scheme, Block-Chapra, Dist. - Nadia. NIET No.- 18 of EE//EMD of 2022-23 (Sl. No.- 06) | 6187/ EMD | 14/11/2022 | 30 | WESTERN ENGINEERING CO. | 7.76 | 7.76 | 100 | 100
3725 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09537 | Augmentation | Additional Work in connection with "Shifting of existing PHE pipeline for implementation of Widening & strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Km under NH Divn-I RIDF-XXV within Gadigacha W/S Scheme under Krishnagar Sub-Divn under Nadia Divn, PHE Dte." | 218/KSD | 03/03/2023 | 30 | PAPAN ROY | 0.24 | 0.24 | 100 | 100
3726 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09537 | Augmentation | Material Requisition To Resource Division | 1030/ND | 03/03/2022 | 0 | Resource Division | 4.96 | 0 | 0 | 0
3727 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09537 | Augmentation | Material Requisition To Resource Division | 103/ND | 06/01/2022 | 0 | Resource Division | 2.06 | 0 | 0 | 0
3728 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09537 | Augmentation | Material Requisition To Resource Division | 3308/ND | 27/07/2022 | 0 | Resource Division | 5.55 | 0 | 0 | 0
3729 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09537 | Augmentation | Special repair and renovation Pump House and Allied Works at Head Work Site of Elangi Zone I water supply scheme in Nadia District under Nadia Division PHE Dte. | 483/KlySD-II | 15/03/2024 | 60 | B K ENGINEERING | 3.14 | 2.81 | 100 | 90
3730 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09537 | Augmentation | Continuation of Wall Writing Work under Nadia Division P. H. Engineering Dte. | 3445/ND | 20/06/2024 | 30 | IMAGIN | 20.46 | 5.11 | 100 | 100
3731 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09537 | Augmentation | Repairing of Existing Boundary Wall for 2nd Tubewell Site at Elangi Zone I water supply scheme in Nadia District under Nadia Division PHE Dte. | 71/KlySD-II | 07/06/2024 | 60 | SREEMA ENTERPRISE | 2.78 | 2.71 | 100 | 98
3732 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09537 | Augmentation | Repairing of Existing Boundary Wall at Head work site of Elangi Zone I water supply scheme in Nadia District under Kalyani Sub-Divn-II, under Nadia Division, PHE Dte. | 1902/ND | 15/03/2024 | 45 | CHOWDHURY CONSTRUCTION | 6.8 | 6.77 | 100 | 70
3733 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09537 | Augmentation | Repair and renovation works of R.C.C. Elevated Existing Over Head Reservoir of capacity 250 Cu.M for Elangi Zone-I Water Supply Scheme in Nadia District under Kalyani Sub-Divn-II, under Nadia Division, PHE Dte. | 1299/ND | 23/02/2024 | 60 | S.S.INFRASTRUCTURE | 11.25 | 10.68 | 100 | 95
3734 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09537 | Augmentation | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | 6305/ND | 26/09/2024 | 30 | IMAGIN | 34.21 | 0 | 0 | 100
3735 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09537 | Augmentation | Material Requisition To Resource Division | 2582/ND | 18/04/2024 | 0 | Resource Division | 22.2 | 0 | 0 | 0
3736 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09537 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Elangi Zone-I Ground Based Water Supply Scheme under Chapra Block under Nadia Division P.H.E Dte. | 7007/ND | 26/11/2024 | 195 | TULIP ENGINEER'S CO-OP SOCIETY LTD | 21.45 | 0 | 0 | 95
3737 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09537 | Augmentation | Conversion of IEP to AIRP of capacity 56 Cu.m/hr at Elangi Zone-I Water Supply Scheme within Chapra Block under Nadia Divn, PHE Dte | 4822/ND | 05/09/2024 | 360 | ZEOLITE FRESH INDIA | 129.41 | 0 | 0 | 0
3738 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09537 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipment and allied works at ELANGI ZONE-II W/S Scheme Block- Chapra under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/09813] | 1146/EMD | 04/06/2025 | 90 | R.N.S. TRADING | 33.06 | 0 | 0 | 0
3739 | NADIA | Nadia Division | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia , SM/10413 | Augmentation | Material Requisition To Resource Division | 5171/ND | 13/12/2022 | 0 | Resource Division | 13.09 | 0 | 0 | 0
3740 | NADIA | Nadia Division | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia , SM/10413 | Augmentation | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia | 51/PFMS | 22/06/2022 | 0 | HORIZEN | 2.78 | 0 | 0 | 0
3741 | NADIA | Nadia Division | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia , SM/10413 | Augmentation | Material Requisition To Resource Division | 1876/ND | 26/04/2023 | 0 | Resource Division | 5.56 | 0 | 0 | 0
3742 | NADIA | Nadia Division | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia , SM/10413 | Augmentation | Material Requisition To Resource Division | 2301/ND | 29/05/2023 | 0 | Resource Division | 22.33 | 0 | 0 | 0
3743 | NADIA | Eastern Mechanical | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia , SM/10413 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under PAYRADANGA W/S Scheme, Block- Hanskhali , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 09) | 502/EMD | 24/01/2023 | 30 | BARISAL TRADING CO. | 29.84 | 12.63 | 42.33 | 30
3744 | NADIA | Central Drilling | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia , SM/10413 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Pyradanga W/S Scheme (TW-I) , Hanskhali Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 1236/CDD | 04/09/2023 | 270 | RAJ & ENTERPRISE | 18.7 | 16.17 | 100 | 100
3745 | NADIA | Nadia Division | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia , SM/10413 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction of 500 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials & Soil investigation for construction of one no. 500 cum OHR of staging height 20 mtr. for augmentation of Ground Water Based Water Supply Scheme for Payradanga to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | 4543/ND | 21/10/2022 | 1095 | AMAL DUTTA ROY, 204/1A, LINTON STREET, KOLKATTA-700014 | 504.52 | 386.63 | 76.63 | 96
3746 | NADIA | Nadia Division | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia , SM/10413 | Augmentation | Balance Laying Distribution System including all complete for augmentation of Ground Water Based Water Supply Scheme for Payradanga to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | 5223/ND | 24/11/2023 | 362 | AMAL DUTTA ROY | 128.22 | 78.15 | 60.94 | 95
3747 | NADIA | Nadia Division | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia , SM/10413 | Augmentation | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of 90 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Payradanga to accommodate FHTC within Hanskhali block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | 5045/ND | 13/09/2024 | 540 | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 237.16 | 0 | 0 | 70
3748 | NADIA | Eastern Mechanical | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia , SM/10413 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Payradanga ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. SM/10413 | 1106/EMD | 04/06/2025 | 90 | A.K. ENTERPRISE | 20.79 | 0 | 0 | 0
3749 | NADIA | Nadia Division | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division , SM/10075 | Augmentation | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division | 674/PFMS | 24/03/2022 | 0 | RADIANT | 2.82 | 0 | 0 | 0
3750 | NADIA | Central Drilling | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division , SM/10075 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x 250 Mtrs. Depth) by utilising Departmental Machineries for Andharkota W/S Scheme (T/W-I) Karimpur -I Block under nadia District, CDD PHE Dte. | 508/CDD | 01/06/2023 | 30 | UNIVERSAL ENTERPRISES | 18.86 | 12.77 | 100 | 100
3751 | NADIA | Nadia Division | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division , SM/10075 | Augmentation | Material Requisition To Resource Division | 1907/ND | 27/04/2023 | 0 | Resource Division | 67.35 | 0 | 0 | 0
3752 | NADIA | Nadia Division | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division , SM/10075 | Augmentation | Material Requisition To Resource Division | 2291/ND | 29/05/2023 | 0 | Resource Division | 27.26 | 0 | 0 | 0
3753 | NADIA | Eastern Mechanical | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division , SM/10075 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MAHISBATHAN W/S Scheme, Block- Karimpur-II & ANDHARKOTA W/S Scheme, Block- Karimpur-I, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 01) | 1200/EMD | 22/03/2023 | 30 | KARTICK BAL | 61.1 | 26.46 | 86.62 | 70
3754 | NADIA | Nadia Division | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division , SM/10075 | Augmentation | Construction of Arsenic-cum-Iron Removal Plant (AIRP) of 47.81 cum/Hour capacity at existing headwork site for Augmentation of Ground Based Water Supply Scheme at Andharkota to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 4368/ND | 09/08/2024 | 180 | CARBON SERVICES INDIA | 178.59 | 0 | 0 | 0
3755 | NADIA | Eastern Mechanical | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division , SM/10075 | Augmentation | Quotation charges and security deposit for new power connection at Andharkota PH-III under Eastern Mechanical Subdivision-III, Nadia | BP-175 | 13/12/2024 | 0 | WBSEDCL KARIMPUR CCC | 14.8 | 0 | 0 | 0
3756 | NADIA | Nadia Division | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division , SM/10075 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction Of 300 Cum Capacity 20 Mtr. Staging Height Rcc Over Head Reservoir (Excluding Pile Foundation), Pipe Connection And Cost Of Pipes, Specials & Soil Investigation all complete for Augmentation of Ground Based Water Supply Scheme at Andharkota to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 4466/ND | 18/10/2022 | 1460 | M/S S.S ENTERPRISE | 444.3 | 207.11 | 46.62 | 55
3757 | NADIA | Nadia Division | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division , SM/10075 | Augmentation | Construction of Arsenic-cum-Iron Removal Plant (AIRP) of 56.13 cum/Hour capacity at proposed headwork site for Augmentation of Ground Based Water Supply Scheme at Andharkota to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 4480/ND | 14/08/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 189.2 | 0 | 0 | 0
3758 | NADIA | Nadia Division | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division , SM/10075 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House and allied works of ground based piped water supply scheme for Andherkota water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 7122/ND | 09/12/2024 | 360 | GHOSH CONSTRUCTION | 31.29 | 0 | 0 | 70
3759 | NADIA | Eastern Mechanical | Providing FHTC by augmentation for Madhugari water supply scheme with in Karimpur-I Block in Nadia District under Nadia Division P.H.E. Dte. (Phase-II) , SM/10084 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, (Phase-II) under Madhugari ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. | 6396/EMD | 30/10/2023 | 30 | S.P. ENTERPRISE (KOLKATA) | 16.32 | 0 | 0 | 0
3760 | NADIA | Nadia Division | Providing FHTC by augmentation for Madhugari water supply scheme with in Karimpur-I Block in Nadia District under Nadia Division P.H.E. Dte. (Phase-II) , SM/10084 | Augmentation | Material Requisition To Resource Division | 1577/ND | 06/04/2023 | 0 | Resource Division | 0.41 | 0 | 0 | 0
3761 | NADIA | Nadia Division | Providing FHTC by augmentation for Madhugari water supply scheme with in Karimpur-I Block in Nadia District under Nadia Division P.H.E. Dte. (Phase-II) , SM/10084 | Augmentation | Material Requisition To Resource Division | 2307/ND | 29/05/2023 | 0 | Resource Division | 0.62 | 0 | 0 | 0
3762 | NADIA | Nadia Division | Providing FHTC by augmentation for Madhugari water supply scheme with in Karimpur-I Block in Nadia District under Nadia Division P.H.E. Dte. (Phase-II) , SM/10084 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Madhugari to accommodate FHTC within Karimpur-I block under RWS Sub-Division under Nadia Division, PHE Dte. | 5334/ND | 21/12/2022 | 75 | SANJIB DEY | 74.59 | 68.34 | 100 | 60
3763 | NADIA | Eastern Mechanical | Providing FHTC by augmentation for Madhugari water supply scheme with in Karimpur-I Block in Nadia District under Nadia Division P.H.E. Dte. (Phase-II) , SM/10084 | Augmentation | Repairing rectification of electro-mechanical works related to installation of submersible pump sets and others accessories in connection with JJM under Madhugari PWSS, Block- Karimpur-I, under EMSD-III, PHE Dte. | 1220/EMSD-III | 28/06/2024 | 30 | SMILE | 2.42 | 2.41 | 100 | 100
3764 | NADIA | Nadia Division | Providing FHTC by augmentation for Madhugari water supply scheme with in Karimpur-I Block in Nadia District under Nadia Division P.H.E. Dte. (Phase-II) , SM/10084 | Augmentation | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Madhugari PWSS within Karimpur-I Block under RWS Sub-Division under Nadia Division, PHE Dte. | 1254/ND | 22/02/2024 | 495 | S.S. ENTERPRISE | 19.88 | 17.32 | 87.11 | 100
3765 | NADIA | Nadia Division | Providing FHTC by augmentation for Madhugari water supply scheme with in Karimpur-I Block in Nadia District under Nadia Division P.H.E. Dte. (Phase-II) , SM/10084 | Augmentation | Conversion of IEP to AIRP of capacity 38 Cu.m/hr at Madhugari Water Supply Scheme within Karimpur-I block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. | 1911/ND | 15/03/2024 | 600 | MONDAL PRECISION PRIVATE LIMITED | 140.38 | 0 | 0 | 65
3766 | NADIA | Nadia Division | Providing FHTC by augmentation for Madhugari water supply scheme with in Karimpur-I Block in Nadia District under Nadia Division P.H.E. Dte. (Phase-II) , SM/10084 | Augmentation | Repairing Works (existing OHR, Pump House, Boundary wall etc.) of Madhugari Water Supply Scheme, Karimpur-I Block Under R.W.S. Nadia Sub-Division P.H.E. Dte. | 3431/ND | 19/06/2024 | 360 | M/S DURGA SECURITIES & SERVICES | 22.18 | 10.49 | 75.72 | 100
3767 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT , SM/09967 | Augmentation | Repair of 350 cum capacity Over Head Reservoir and Painting of all structures with repair works & other allied works at Dubli Zone -II W/S Scheme within Ranaghat -Ii Block under Nadia Arsenic Division -I, P.H.E.DTE. (Sl.no. 26) | 1587 / NAD-I | 06/09/2022 | 45 | SATYABRATA CHAKRABORTY | 17.14 | 0 | 0 | 0
3768 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT , SM/09967 | Augmentation | Retrofitting work from Ukhilnara More towards Payradanga Station under Ukhilnara Zone-I Water Supply Scheme under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte. (Sl.no. 03) | 107/ AE-II/NAD-I | 02/03/2023 | 15 | GANGULY ENTERPRISE | 2.64 | 2.64 | 100 | 0
3769 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT , SM/09967 | Augmentation | Construction of M.S. Manifold of 1000mm thickness for improvement of Water Supply at Head Work Site under Ukhilnara Zone-I Ground Water Based Water Supply Scheme under Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E. Dte. in connection with Augmentation of Ukhilnara Zone-I W/S Scheme underJJM (sl.no.01) | 1153 /NAD-I | 28/04/2023 | 15 | GANGULY ENTERPRISE | 13.05 | 0 | 0 | 0
3770 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT , SM/09967 | Augmentation | Repair of 100 cum capacity and other allied works at Ukhilnara Zone-II W/S Scheme in Ranaghat -I Block under Nadia Arsenic Division -I , P.H.E.Dte. (Sl no. 17) | 1320 / NAD -I | 04/08/2022 | 45 | INVENT ENGINEER'S CO - OPERATIVE SOCIETY LTD. | 11.32 | 6.45 | 100 | 100
3771 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT , SM/09967 | Augmentation | CONSTRUCTION OF BOUNDARY WALL,TOILET ,PATHWAY AND ALL REPAIR WORKS AT 2nd T/W AND OTHER ALLIE WORKS AT DUBLI Z-II W/S SCHEME AT RANAGHAT -II BLOCK , UNDER NADIA ARSENIC DIVISION -I , P.H.E.DTE. ( SL NO.21) | 1515 / NAD-I | 26/08/2022 | 45 | DAS CONSTRUCTION | 16.36 | 8.05 | 100 | 100
3772 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT , SM/09967 | Augmentation | Phase -II FHTC under Jaldhara/ Jal Swapna for Dubli Z-I & II at Ranaghat -II Block by retrofitting of Ground Water Based PWSS for Dubli Water Supply scheme under Nadia Arsenic Division -I, P.H.E. Dte. (Sl. no -08) | 960 / NAD-I | 07/07/2022 | 60 | BIPLAB GUHA | 55.81 | 55.44 | 100 | 85
3773 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT , SM/09967 | Augmentation | Construction of Boundary Wall, Toilet , Pathway and all repair works at nd T/W site and other allied works at Ukhilnara Z-I W/S Scheme at Ranaghat -I Block under Nadia Arsenic Division -I, P.H.E.Dte. ( Sl. No. 23) | 1514 / NAD-I | 26/08/2022 | 45 | NISHITH BANERJEE | 22.91 | 18.58 | 100 | 100
3774 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT , SM/09967 | Augmentation | Repairs and Renovation work of Arsenic cum Iron Removal Plant having Capacity 16 m3/hr including Civil Structures of Ukhilnara Zone-II W/S Sch. within Ranaghat -I Block under Nadia Arsenic Division -I , P.H.E. Dte. (SL.No. 22) | 1513 / NAD-I | 26/08/2022 | 45 | SUNIL KUMAR DATTA | 7.1 | 6.78 | 100 | 100
3775 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT , SM/09967 | Augmentation | Repair of 450 cum capacity over head reservoir and painting of all structures with repair Works & other allied works at Dubli Z-I W/S scheme in Ranaghat -II Block under Nadia Arsenic Division -I (Sl.no. 24) | 1584 / NAD-I | 06/09/2022 | 45 | SATYABRATA CHAKRABORTY | 15.84 | 15.67 | 100 | 100
3776 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT , SM/09967 | Augmentation | Construction of Boundary Wall Toilet Pathway and other allied works at 2nd and 3rd TW site of Dubli Zone I WS Scheme within Ranaghat II Block under NADI PHE Dte (sl.no.01) | 3328/NAD-I | 15/12/2022 | 45 | B.M. ENTERPRISE | 20.53 | 18.65 | 100 | 100
3777 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT , SM/09967 | Augmentation | Repair of 180 cum capacity Over Head Reservoir and painting of all structures with repair works and other allied works at Ukhilnara Zone-I W/S Scheme in Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no.06) | 1442/NAD-I | 17/09/2022 | 45 | MONDAL ENTERPRISE | 14.98 | 14.91 | 100 | 100
3778 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT , SM/09967 | Augmentation | Retrofitting in Uzirpukuria North at Dubli Zone-I W/S Scheme under Ground Water Based PWSS for arsenic affected areas of Dubli W/S Scheme under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte. (Sl. No. 01) | 28/AE-II/NAD-I | 10/02/2023 | 15 | BUDDHADEV MONDAL | 4.8 | 4.79 | 100 | 100
3779 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT , SM/09967 | Augmentation | Shifting of pipeline From Headwork site to Ukhilnara More due to widening of PWD Road under Ukhilnara Zone-I Water Supply Scheme under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte (sl.01) | 106/AE-II/ NAD-I | 02/03/2023 | 15 | GANGULY ENTERPRISE | 1.86 | 1.86 | 100 | 50
3780 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT , SM/09967 | Augmentation | Retrofitting work at Mistripara under Ukhilnara Zone-I Water Supply Scheme under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte (sl.02) | 169 / AE-II/NAD-I | 27/03/2023 | 21 | MALI CONSTRUCTION | 2.79 | 2.33 | 100 | 100
3781 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT , SM/09967 | Augmentation | Improvement of AIRP for Dubli Zone-I (105 cum/hr.) W/S Scheme in connection with Augmentation of AIRP for Ground Water Based Piped Water Supply Scheme for Dubli Zone-I, under Jal Jeevan Mission at Ranaghat-II Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.14) | 2151/NAD-I | 08/09/2023 | 21 | SATYABRATA CHAKRABORTY | 63.28 | 59.67 | 100 | 100
3782 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT , SM/09967 | Augmentation | Laying of UPVC Pipeline under JJM for Ukhilnara Zone-II at Payradanga G.P. at Ranaghat-I Block of Ground Water Based PWSS for Ukhilnara Zone-II W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 2752/NAD-I | 11/12/2023 | 315 | GANGULY ENTERPRISE | 9.32 | 7.64 | 81.95 | 90
3783 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT , SM/09967 | Augmentation | Augmentation & Retrofitting work under Jal Jeevan Mission (JJM) for UKILNARA ZONE-I at Ranaghat-I Block of Ground Water based PWSS for Ukilnara Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1897/NAD-I | 18/11/2024 | 300 | GANGULY ENTERPRISE | 29.52 | 0 | 0 | 0
3784 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. , SM/10650 | Augmentation | Retrofitting work at Baranbria, Srirampur, Kalupur, Kani Bamni, Bagdia Mouza inconnection with Augmentation to accommodate FHTC under JJM for Duttaphulia Zone-II Ground water based PWSS (Phase-II) Block ¿ Ranaghat-II, Dist (sl.11) | 537 / NAD-I | 13/03/2023 | 21 | M/S TARAK CHANDRA PAUL | 31.77 | 30.88 | 100 | 0
3785 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. , SM/10650 | Augmentation | Material Requisition To Resource Division | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 38.85 | 0 | 0 | 0
3786 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. , SM/10650 | Augmentation | FHTC under Jaldhara / Jalswapna for Duttaphulia Z-II Part -II at Ranaghat-II Block by augmentation of Ground water Based PWSS for Duttaphulia Z-II W/S scheme under Nadia Arsenic Division-I, P.H.E. Dte (Sl.no. 03) | 1939 /NAD-I | 12/10/2022 | 90 | M/S TARAK CHANDRA PAUL | 557.43 | 553.79 | 100 | 100
3787 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. , SM/10650 | Augmentation | Retrofitting work at Ramnagar and Duttaphulia at Hanskhali Block under Jal Jeevna Mission in connection with augmentation of Duttaphulia Zone-II W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.08) | 2160/NAD-I | 11/09/2023 | 21 | MESSRS FREEDOM CONSTRUCTION | 75.74 | 73.64 | 100 | 100
3788 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/10068 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | 636/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.5 | 0 | 0 | 0
3789 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/10068 | Augmentation | Sinking of 1 no. Tubewell 300mm. x 200mm. dia 200 mtr deep by direct rotary rig method and construction of pump house (3.6 mtr. x 3.0 mtr.) and boundary wall at 3rd tube well site for Bhaluka Water Supply Scheme under Krishnagar Sub-Division under Nadia Division, PHE Dte. (Sm/10068) | 2102/ND | 15/05/2023 | 90 | B.M. ENGINEERING & CONSTRUCTION | 29.75 | 0 | 0 | 0
3790 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/10068 | Augmentation | Material Requisition To Resource Division | 2160/ND | 18/05/2022 | 0 | Resource Division | 152.87 | 0 | 0 | 0
3791 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/10068 | Augmentation | Material Requisition To Resource Division | 1388/ND | 24/03/2022 | 0 | Resource Division | 33.49 | 0 | 0 | 0
3792 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/10068 | Augmentation | Material Requisition To Resource Division | 3306/ND | 27/07/2022 | 0 | Resource Division | 36.72 | 0 | 0 | 0
3793 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/10068 | Augmentation | Repair & Renovation of Pump House, Boundary wall, Store Room and allied works at 1st and 2nd Pump House at Bhaluka Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 152/ND | 09/01/2024 | 60 | JOYGOPAL GUPTI | 18.06 | 18.02 | 100 | 100
3794 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/10068 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Costruction of R.C.C eleveted reservoir 750 CUM all complete & Soil Investigation for Augmentation of Ground Based Water Supply Scheme at Bhaluka to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 1887/ND | 25/04/2022 | 1163 | M/S S.S ENTERPRISE | 786.78 | 589.92 | 74.98 | 80
3795 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/10068 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BHALUKA W/S Scheme, Block-Krishnagar-1, Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 02) | 406/EMD | 20/01/2023 | 919 | M.S. ENTERPRISE | 29.23 | 0 | 0 | 50
3796 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/10068 | Augmentation | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of capacity 137 m3/hr at Bhaluka Water Supply Scheme within Krishnagar-I Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | 5046/ND | 13/09/2024 | 360 | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 318.54 | 47.91 | 15.04 | 70
3797 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. , SM/10068 | Augmentation | Construction of Additional Boundary wall and allied works at Headwork Site at Bhaluka Water Supply Scheme within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 2289/ND | 19/05/2025 | 240 | JOYGOPAL GUPTI | 29.78 | 0 | 0 | 50
3798 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09256 | Augmentation | Repairing and paitning of Overhead Reservoir and other allied works under augmentation of Lakshmipur PWSS of Chapra Block. | 191/AE-I/NACD-II | 29/12/2021 | 25 | PRABIR KUMAR ROY | 4.81 | 0 | 0 | 100
3799 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09256 | Augmentation | Raising the height of Boundary wall at H/W site and also Construction of Soak Pit at Lakshmipur Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | 03/AE-I/NACD-II | 06/04/2022 | 45 | PRABIR KUMAR ROY | 5 | 2.37 | 47.37 | 100
3800 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09256 | Augmentation | Supply of CIDF Sluice valve and DI specials for vavle to facilitate Functional House Hold Connection of Lakshmipur Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | 281/AE-I/NACD-II | 04/03/2022 | 5 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.94 | 4.94 | 100 | 100
3801 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09256 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Helenchi Zone-I (Vill- Shimlibas) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 627/NACD-II | 10/08/2021 | 15 | M/S TARUN GHOSH & CO. | 4.51 | 4.51 | 100 | 100
3802 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09256 | Augmentation | Continuation work order for Supply of CIDF Sluice valve and DI specials for vavle to facilitate Functional House Hold Connection of Lakshmipur Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | 303/AE-I/NACD-II | 17/03/2022 | 5 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.9 | 4.9 | 100 | 100
3803 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09256 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Lakshmipur (Vill- Kalyandaha, Lakshmipur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1014/NACD-II | 29/11/2022 | 60 | PRABIR KUMAR ROY | 17.93 | 17.87 | 100 | 100
3804 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09256 | Augmentation | Restoration of damaged distribution pipe line and parallel pipeline laying due to construction of PMGSY Road and Extension of Boundary Wall at Lakshmipur (Vill-Kalyandaha) Head Work Site W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1020/NACD-II | 29/11/2022 | 30 | PRADIP KUMAR BANIK | 4.85 | 4.81 | 100 | 100
3805 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09256 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Lakshmipur) | 1116/NACD-II | 06/10/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
3806 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09256 | Augmentation | Conversion of IEP to AIRP at Laksmipur Water Supply Scheme of capacity 60 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte. | 1308/NACD-II | 20/09/2024 | 60 | JOY HIND TUBEWELLS | 165.22 | 0 | 0 | 0
3807 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09256 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Lakshmipur Water Supply Scheme in Chapra Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 325/1/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.11 | 1.1 | 100 | 100
3808 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09256 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Lakshmipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 858/NACD-II | 08/11/2021 | 45 | M/S GHOSH CONSTRUCTION | 82.39 | 82.36 | 100 | 100
3809 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-I, II AND III within Krishnagar-II and Nabadwip (Part) Block. (Phase-C) , SM/08960 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-I,II & III within Krishnagar & Nabadwip(Part) Block (Phase-C) | 5694/ND | 03/11/2021 | 90 | MALLICK ENTERPRISE | 86.12 | 83.6 | 97.06 | 0
3810 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-I, II AND III within Krishnagar-II and Nabadwip (Part) Block. (Phase-C) , SM/08960 | Retrofitting | Material Requisition To Resource Division | 4302/ND | 29/09/2022 | 0 | Resource Division | 12.75 | 0 | 0 | 0
3811 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-I, II AND III within Krishnagar-II and Nabadwip (Part) Block. (Phase-C) , SM/08960 | Retrofitting | Material Requisition To Resource Division | 293/ND | 15/01/2024 | 0 | Resource Division | 10.84 | 0 | 0 | 0
3812 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-I, II AND III within Krishnagar-II and Nabadwip (Part) Block. (Phase-C) , SM/08960 | Retrofitting | Material Requisition To Resource Division | 294/ND | 15/01/2024 | 0 | Resource Division | 20.53 | 0 | 0 | 0
3813 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-I, II AND III within Krishnagar-II and Nabadwip (Part) Block. (Phase-C) , SM/08960 | Retrofitting | Material Requisition To Resource Division | 295/ND | 15/01/2024 | 0 | Resource Division | 19.84 | 0 | 0 | 0
3814 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-I, II AND III within Krishnagar-II and Nabadwip (Part) Block. (Phase-C) , SM/08960 | Retrofitting | Material Requisition To Resource Division | 300/ND | 15/01/2024 | 0 | Resource Division | 4.4 | 0 | 0 | 0
3815 | NADIA | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-II Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) , SM/08962 | Retrofitting | Providing Functional House Tap Connection from Baraandulia Zone-II Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) | 654/PFMS | 25/02/2022 | 0 | B.M ENTERPRISE | 60 | 0 | 0 | 0
3816 | NADIA | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-II Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) , SM/08962 | Retrofitting | Providing Functional House Tap Connection from Baraandulia Zone-II Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) | 575/PFMS | 04/03/2022 | 0 | B.M ENTERPRISE | 1.53 | 0 | 0 | 0
3817 | NADIA | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-II Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) , SM/08962 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Bara Andulia(Zone-II) W/S scheme in Nadia District under Nadia Division P.H.E. Dte. [Part-A]. | 5691/ND | 03/11/2021 | 75 | B.M ENTERPRISE | 64.01 | 1.69 | 100 | 100
3818 | NADIA | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-II Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) , SM/08962 | Retrofitting | Material Requisition To Resource Division | 781/ND | 18/02/2022 | 0 | Resource Division | 6.59 | 0 | 0 | 0
3819 | NADIA | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-II Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) , SM/08962 | Retrofitting | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
3820 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MAHESHPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09265 | Augmentation | Painting works at Maheshpur Head Work site boundary wall,including road restoration work and other anciliary works at Maheshpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 01/AE-I/NACD-II | 06/04/2022 | 45 | TARUN GHOSH | 4.91 | 4.8 | 97.78 | 100
3821 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MAHESHPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09265 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mahespur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 881/NACD-II | 12/11/2021 | 45 | M/S ASHA CONSTRUCTION | 79.08 | 78.54 | 100 | 100
3822 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MAHESHPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09265 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Maheshpur) | 1118/NACD-II | 06/10/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
3823 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MAHESHPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09265 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Maheshpur Water Supply Scheme in Chapra Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 328_2/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.14 | 1.14 | 100 | 100
3824 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MAHESHPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09265 | Augmentation | Jungle cutting and Earthwork in filling at Maheshpur, Maitari and Thanarapara Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 818/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.76 | 0 | 0 | 100
3825 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED MAHESHPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09265 | Augmentation | Quotation for load enhancement and security deposit charges at PH-I of Mahespur PWSS | BP-170-24-25 | 05/12/2024 | 0 | W.B.S.E.D.C.L (GROUP CHAPRA C.C.C) | 3.83 | 0 | 0 | 0
3826 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MAHESHPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09265 | Augmentation | Repair and Renovation work at Maheshpur 2nd tube well Site under Maheshpur Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia | 1026/AE-I/NACD-II | 10/12/2024 | 30 | ACHARJEE & ASSOCIATES | 3.37 | 0 | 0 | 100
3827 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MAHESHPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09265 | Augmentation | Comprehensive augmentation in technical regards including aquifer management with extraction, compliance of Ground water contamination removal as per IS 10500 with subsequent amendments and composite RCC Cum masonry structures mouza Maheshpur under Maheshpur Piped Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1580/NACD-II | 09/12/2024 | 60 | M/S FREEDOM CONSTRUCTION | 54.01 | 0 | 0 | 60
3828 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED MAHESHPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09265 | Augmentation | Supply of Water Level Indicator at Maheshpur, Gongra, Madhabpur, Laxmipur, Balibanga PWSS in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1192/AE-I/NACD-II | 25/02/2025 | 30 | RAJIB DUTTA | 3.83 | 0 | 0 | 0
3829 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED MAHESHPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09265 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC under Maheshpur (Source Augmentation, Maheshpur) ground water based water supply scheme under Block_ Chapra Dist. - Nadia under EMD, PHE Dte. | 704/EMD | 04/04/2025 | 30 | M/S DILIP MITRA | 11.4 | 0 | 0 | 0
3830 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PUTHIMARI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09271 | Augmentation | Construction of Boundary wall with Grill Gate at Putimari Water Supply Scheme at Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | 104/NACD-II | 10/02/2022 | 45 | ROY CONSTRUCTION | 10.02 | 9.96 | 99.37 | 100
3831 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PUTHIMARI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09271 | Augmentation | Construction of Boundary wall with Grill Gate at Putimari 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | 42/AE-II/NACD-II | 17/02/2022 | 30 | SREE GURU ENTERPRISE | 4.2 | 4.16 | 98.94 | 100
3832 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PUTHIMARI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09271 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Putimari W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 861/NACD-II | 08/11/2021 | 45 | MANGES INDUSTRIAL CORPORATION. | 58.71 | 58.63 | 100 | 100
3833 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED PUTHIMARI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09271 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under PUTIMARI(Block-Tehatt-I), NISCHINTAPUR(Block-Tehatt-I), W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 04) | 1504/EMD | 18/04/2023 | 30 | SRI KRISHNA NIRMAN | 10.69 | 5.24 | 100 | 80
3834 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PUTHIMARI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09271 | Augmentation | Replacement of Existing Distribution main pipeline by D.I. Pipe in the Head Work site at Puthimari Water Supply Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 467/NACD-II | 20/04/2023 | 30 | AMAR KRISHNA DEY | 2.82 | 2.79 | 100 | 95
3835 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PUTHIMARI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09271 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Puthimari Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1305/NACD_II | 30/11/2023 | 30 | PRABIR KUMAR ROY | 22.3 | 22.15 | 100 | 95
3836 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PUTHIMARI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09271 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Puthimari) | 1298/NACD-II | 29/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
3837 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PUTHIMARI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09271 | Augmentation | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Puthimari Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Puthimari W/S Scheme in Tehatta-I Block of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1427/NACD-II | 15/12/2023 | 20 | SIRCON ENGINEERING SERVICE | 2.67 | 0 | 0 | 100
3838 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED PUTHIMARI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09271 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I , II Zone-VII under Karimpur-Jalangi ground water based water supply scheme under Block_ Karimpur-I Dist. - North 24PGS under EMD, PHE Dte. | 872/EMD | 15/03/2024 | 261 | TARUN KUMAR BHATTACHARYA | 25.34 | 0 | 0 | 100
3839 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PUTHIMARI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09271 | Augmentation | Relaying of D.I. Pipeline by replacing the damaged old UPVC pipe for rising main from 1st pump house to 2nd pump house at Puthimari Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 314AE-II/NACD-II | 06/09/2024 | 30 | ARIT KUMAR PAL | 4.62 | 4.18 | 100 | 100
3840 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PUTHIMARI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09271 | Augmentation | Repair and Renovation work at Putimari 2nd pump house site with Reinforced Barbed Tape , Painting ,Plaster and other allied works Under Nadia Arsenic Division-II,P.H.E.Dte. | 167/AE-II/NACD-II | 14/06/2024 | 15 | BIPLAB KUMAR GUPTA | 0.96 | 0.94 | 100 | 100
3841 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PUTHIMARI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09271 | Augmentation | Material Requisition To Resource Division | 986/NACD-II | 23/07/2024 | 0 | Resource Division | 28.32 | 0 | 0 | 0
3842 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND BASED WATER BASED PUTHIMARI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09271 | Augmentation | Load enhancement charge of Putimary P.H-I under EMSD-III, PHE Dte. | BP-160-24-25 | 14/11/2024 | 0 | W.B.S.E.D.C.L (TEHATTA CCC) | 3.06 | 0 | 0 | 0
3843 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PUTHIMARI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09271 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Puthimari Water Supply Scheme of capacity 57 Cu.m/hr in Tehatta-I under Nadia Arsenic Civil Division -II, PHE Dte." | 215/NACD-II | 16/02/2024 | 361 | MONDAL PRECISION PRIVATE LIMITED | 175.72 | 140.58 | 80 | 20
3844 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED PUTHIMARI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09271 | Augmentation | Laying of distribution system and also dedicated pipe line including providing FHTC at left out households for Patharghata (Gobindapur, Patharghata) & Puthimari (Vill-Puthimari) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 247/NACD-II | 27/02/2025 | 180 | SANDIP BISWAS | 101.71 | 0 | 0 | 0
3845 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10522 | Augmentation | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | 26/PFMS | 20/05/2022 | 0 | ENVIROTECH SOLUTIONS | 2.44 | 0 | 0 | 0
3846 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10522 | Augmentation | Material Requisition To Resource Division | 4277/ND | 29/09/2022 | 0 | Resource Division | 1.23 | 0 | 0 | 0
3847 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10522 | Augmentation | Material Requisition To Resource Division | 3895/ND | 08/09/2022 | 0 | Resource Division | 16.85 | 0 | 0 | 0
3848 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10522 | Augmentation | Material Requisition To Resource Division | 3789/ND | 24/08/2023 | 0 | Resource Division | 1.6 | 0 | 0 | 0
3849 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10522 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Teinpur Zone-I to accommodate FHTC within Karimpur-II block under RWS Sub-Division under Nadia Division, PHE Dte. | 3380/ND | 29/07/2022 | 60 | M/S FREEDOM CONSTRUCTION | 42.67 | 42.1 | 100 | 86
3850 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10522 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under TEINPUR (ZONE-I ,II, III & IV) W/S Scheme, Block- Karimpur-II , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 06) | 500/EMD | 24/01/2023 | 30 | M/S DILIP MITRA | 64.62 | 10.71 | 34.32 | 85
3851 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10522 | Augmentation | Renovation and modification of AIRP (Pressure Type) & Construction of Backwash chamber for AIRP at Head Work Site in Teinpur ZONE-I PWSS under Nadia Division PHE Dte. Capacity- 15.5 cum/hr. | 781/ND | 05/02/2024 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 37.22 | 18.21 | 100 | 93
3852 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/10522 | Augmentation | Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | 3450/ND | 20/06/2024 | 45 | IMAGIN | 19.44 | 5.3 | 100 | 100
3853 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09813 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | 615/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.16 | 0 | 0 | 0
3854 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09813 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under ELANGI(Zone-II) & GHORALIA (Zone-II) W/S Scheme, Block- Chapra & Shantipurrespectively , Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 05) | 1503EMD | 18/04/2023 | 30 | MA ANNAPURNA ENTERPRISE | 11.19 | 5.03 | 100 | 60
3855 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09813 | Augmentation | Different Electro-Mechanical Extra works for completion FHTC Augmentation works at Elangi Zone-II and Ghoralia Zone-II under EMSD-III,P.H.E.Dte. Dist-Nadia. | 759/EMSD-III | 24/07/2023 | 15 | MA ANNAPURNA ENTERPRISE | 0.32 | 0.32 | 100 | 100
3856 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09813 | Augmentation | Material Requisition To Resource Division | 1250/ND | 16/03/2022 | 0 | Resource Division | 0.86 | 0 | 0 | 0
3857 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09813 | Augmentation | Material Requisition To Resource Division | 4315/ND | 29/09/2022 | 0 | Resource Division | 2.17 | 0 | 0 | 0
3858 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09813 | Augmentation | Material Requisition To Resource Division | 3791/ND | 24/08/2023 | 0 | Resource Division | 1.54 | 0 | 0 | 0
3859 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09813 | Augmentation | Laying Of Distribution System including Specials, Valves & Pipe Supporting Structure All Complete Based On Actual Estimate & Providing FHTC for Elangi ZONE - II Water Supply Scheme in Nadia District under Nadia Division PHE Dte.. | 965/ND | 28/02/2022 | 1350 | MADE & TRADE CO. | 310.84 | 94.7 | 30.46 | 46
3860 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09813 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipment and allied works at ELANGI ZONE-II W/S Scheme Block- Chapra under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/09813] | 1146/EMD | 04/06/2025 | 90 | R.N.S. TRADING | 33.06 | 0 | 0 | 0
3861 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09813 | Augmentation | Conversion of IEP to AIRP of capacity 36 Cu.m/hr at Elangi Zone-II Water Supply Scheme within Chapra Block block under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 1557/ND | 28/03/2025 | 180 | APURBA MANDAL | 129.36 | 0 | 0 | 0
3862 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09813 | Augmentation | Laying of dedicated pipeline for Pipragachhi and part of Elangi Mouza for augmentation of Elangi Water Supply Scheme in Chapra Block, Nadia under Nadia Division PHE Dte. | 1773/ND | 21/04/2025 | 180 | TULIP ENGINEER'S CO-OP SOCIETY LTD | 86.27 | 0 | 0 | 0
3863 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. , SM/09813 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Elangi Zone-II PWSS under Chapra Block under Tehatta Sub- Division,P.H.E Dte. | 421/ND | 27/01/2025 | 240 | M/S DIPAK ENTERPRISE | 73.39 | 0 | 0 | 40
3864 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IV, (Rukminidanga), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme , SM/08004 | Retrofitting | Providing FHTC Functional Household Tap Connection under Jaldhara Jal Swapna for Zone IV Rukminidanga Part I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah Part Water Supply Scheme under Nadia Arsenic Division I PHE Dte | 785/NAD-I | 05/05/2021 | 60 | CHANDAN ROY | 97.05 | 181.51 | 100 | 100
3865 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XIII, (Digha), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07895 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XIII, (Digha), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. Tender No. 204/NAD-I/2020-2021. | 152/NAD-I | 25/01/2021 | 60 | M/S NIBHAS SINHA | 89.4 | 175.52 | 126.52 | 100
3866 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DIGRI TO ACCOMMODATE FHTC IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09870 | Augmentation | Preparation of DPR for augmentation of existing Digri, (Block - Krishnagar-I) piped water supply schemes | 152/AE-I/NACD-II | 16/11/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.89 | 2.89 | 100 | 100
3867 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DIGRI TO ACCOMMODATE FHTC IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09870 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Digri W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 02/NACD-II | 03/01/2022 | 45 | SOMNATH CHATTERJEE | 72.6 | 72.6 | 100 | 100
3868 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DIGRI TO ACCOMMODATE FHTC IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09870 | Augmentation | Continuation Work Order for Construction of roof shed for AIRP room at Digri Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 183/AE-I/NACD-II | 20/12/2021 | 15 | M/S RAJESH CONSTRUCTION | 1.46 | 1.46 | 99.99 | 100
3869 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DIGRI TO ACCOMMODATE FHTC IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09870 | Augmentation | Repairng of FHTC work damaged due to construction work of local authorities and ancilary works at Digri Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | 04/AE-I/NACD-II | 06/04/2022 | 45 | M/S RAJESH CONSTRUCTION | 2.3 | 2.3 | 99.6 | 100
3870 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DIGRI TO ACCOMMODATE FHTC IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09870 | Augmentation | Change of Media of AIRP at Digri H/W site under Digri W/S scheme under Nadia Arsenic Civil Division-II P.H.E Dte. | 35/AE-I/NACD-II | 02/05/2022 | 10 | RUPALI ELECTRONICS | 4.93 | 4.93 | 100 | 100
3871 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DIGRI TO ACCOMMODATE FHTC IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09870 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) & also construction of Soak Pit at Digri W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 523/NACD-II | 14/06/2021 | 45 | M/S GHOSH CONSTRUCTION | 52.42 | 0 | 0 | 100
3872 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DIGRI TO ACCOMMODATE FHTC IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09870 | Augmentation | Construction of roof shed for AIRP room at Digri Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 137/AE-I/NACD-II | 28/10/2021 | 15 | M/S RAJESH CONSTRUCTION | 1.99 | 1.99 | 100 | 100
3873 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DIGRI TO ACCOMMODATE FHTC IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09870 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Digri (Vill- Pakurgachhi, Adapota Digri) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1012/NACD-II | 29/11/2022 | 60 | M/S RAJESH CONSTRUCTION | 27.76 | 26.09 | 100 | 100
3874 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DIGRI TO ACCOMMODATE FHTC IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09870 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Krishnagar-I Block of Nadia District through Jadavpur University. (Name of PWSS Digri) | 973/NACD-II | 12/09/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
3875 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DIGRI TO ACCOMMODATE FHTC IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09870 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Automatic Chlorinator etc Augmentation to Accomodate FHTC under Digri W/S Scheme, Block- Krishnagar I , Dist. - Nadia. NIET No. 31 of EE/EMD of 2022-23 (Sl. No. 04) | 1123EMD | 16/03/2023 | 30 | SOMNATH ENTERPRISE | 6.2 | 5.89 | 100 | 90
3876 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DIGRI TO ACCOMMODATE FHTC IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09870 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Digri Piped Water Supply Scheme in Krishnagar-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 98/NACD-II | 22/01/2024 | 45 | M/S RAJESH CONSTRUCTION | 23.52 | 6.08 | 25.85 | 40
3877 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DIGRI TO ACCOMMODATE FHTC IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09870 | Augmentation | Jungle cutting and Earthwork in filling at Maheshpur, Maitari and Thanarapara Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 818/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.76 | 0 | 0 | 100
3878 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DIGRI TO ACCOMMODATE FHTC IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09870 | Augmentation | Renovation of Arsenic cum Iron treatment Plant of Digri PWSS (Capacity- 75 m3/hr) and ancillary works of Krishnagar-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte | 220/NACD-II | 21/02/2024 | 471 | B.M. ENGINEERING & CONSTRUCTION | 125.21 | 0 | 0 | 50
3879 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10569 | Augmentation | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | 52/PFMS | 22/06/2022 | 0 | HORIZEN | 2.52 | 0 | 0 | 0
3880 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10569 | Augmentation | Special repair & renovation of boundary wall & allied works in the premises at pump house no 2 of Dakshinpara-I W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | 468/RSD | 26/07/2022 | 30 | RAJ & ENTERPRISE | 4.84 | 4.8 | 100 | 100
3881 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10569 | Augmentation | Material Requisition To Resource Division | 4290/ND | 29/09/2022 | 0 | Resource Division | 4.99 | 0 | 0 | 0
3882 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10569 | Augmentation | Material Requisition To Resource Division | 2585/ND | 13/06/2023 | 0 | Resource Division | 2.92 | 0 | 0 | 0
3883 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10569 | Augmentation | Material Requisition To Resource Division | 1878/ND | 26/04/2023 | 0 | Resource Division | 15.87 | 0 | 0 | 0
3884 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10569 | Augmentation | Material Requisition To Resource Division | 2325/ND | 29/05/2023 | 0 | Resource Division | 4.99 | 0 | 0 | 0
3885 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10569 | Augmentation | Special repair & renovation of hed work site pump house & allide works of Dakshinpara-I W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | 463/A/RSD | 22/07/2022 | 30 | CHAYA ENTERPRISE | 2.28 | 0.89 | 100 | 100
3886 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10569 | Augmentation | Special repair & renovation of pump house & allied works in the premises at pump house no-I of Dakshinpara-I W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | 467/A/RSD | 26/07/2022 | 30 | SWARASHI CONSTRUCTION | 2.54 | 1.76 | 100 | 90
3887 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10569 | Augmentation | Special repair & renovation & repair of AIRP pump house & allied works of Dakshinpara-I W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | 463/RSD | 22/07/2022 | 30 | SREE GURU CONSTRUCATION | 2 | 0.95 | 100 | 100
3888 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10569 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under DAKSHINPARA (Zone-I & II) W/S Scheme, Block- Hanskhali , AND GOPINATHPUR W/S Scheme, Block- Tehatta-II, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 01) | 496/EMDdt.24.01.2023 | 17/03/2023 | 656 | GLACIER ENGINEERING CO. | 66.71 | 8.5 | 100 | 100
3889 | NADIA | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10569 | Augmentation | : providing drilling crew and other allied works for construction of Tube well ( 300mm X200mm X 250 IVltrs. Depth) by utilising Departmental Machineries for Dakshinpara w/s scheme (Z-l' TW-l) , Hanskhali Block under Nadia District, CentraiDrilling Divlsion, P.H.E' Dte (2nd Call) | 1051/CDD | 16/08/2023 | 300 | MENAKA ENTERPRISE | 18.6 | 13.44 | 100 | 100
3890 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10569 | Augmentation | Replacement of damaged & typically choked UPVC pipe line for augmentation of Ground Water Based Water Supply Scheme for Dakshinpara Zone -I PWSS of Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | 4894/ND | 02/11/2023 | 481 | SHYAMAL SHIL | 34.58 | 31.13 | 90.01 | 96
3891 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10569 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20 mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Dakshinpara Zone-I to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | 4040/ND | 19/09/2022 | 900 | SHYAMAL SHIL | 112.12 | 79.14 | 70.59 | 97
3892 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10569 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Dakshinpara Zone-I PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 45.00 Cu.m/hr | 133/ND | 09/01/2024 | 450 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 68.46 | 0 | 0 | 95
3893 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10569 | Augmentation | Laying of Rising Main for Dakshinpara Zone-I W/S Scheme under JJM, Ranaghat Sub-Division, Nadia Division PHE. Dte. | 877(A)RSD | 20/08/2024 | 15 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 2.61 | 0 | 0 | 100
3894 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10569 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at DAKSHINPARA (ZONE-I) W/S Scheme Block- HANSKHALI under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/10569 | 1133/EMD | 04/06/2025 | 90 | MAHADEV ENTERPRISE | 36.73 | 0 | 0 | 0
3895 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA , SM/10569 | Augmentation | Construction and installation of MANIFOLD and allied works at Head Works site under Dakshinpara Zone-I Ground Based Water Supply Scheme under Hanskhali Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) | 2327/ND | 20/05/2025 | 180 | T.T ENTERPRISE | 12.24 | 0 | 0 | 0
3896 | NADIA | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Earthwork in filling in ditches at Madhupur Water Supply Scheme at Madhupur H/W site under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 113/AE-I/NACD-II | 28/06/2022 | 30 | JOY HIND TUBEWELLS | 4.84 | 4.84 | 99.92 | 100
3897 | NADIA | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Soil Investigation for Construction of 3 (Three) Nos. of Overhead Reservoir of staging height of 20 mtr. Under Nadia Arsenic Civil Division-II P.H.E. Dte. Site - Khaspu W/s Scheme, Madhupur W/s Scheme, Maniknagar W/s Scheme | 251/AE-I/NACD-II | 25/02/2022 | 15 | G. MITRA & ASSOCIATES | 2.29 | 2.29 | 100 | 100
3898 | NADIA | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
3899 | NADIA | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
3900 | NADIA | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Madhupur and adjoining mouzas under Madhupur Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | 349/NACD-II | 08/06/2022 | 90 | M/S. DIVINE | 148.51 | 125.91 | 84.78 | 85
3901 | NADIA | Eastern Mechanical | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Madhupur Piped Water Supply Scheme, Block: Dist. Nadia Under EMD, PHE Dte. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.-13) | 5020/EMD | 03/11/2022 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 41.25 | 0 | 0 | 0
3902 | NADIA | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Madhupur 2nd Tubewell site within Madhupur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 144/NACD-II | 17/01/2023 | 60 | GANGULY ENTERPRISE | 4.8 | 4.67 | 97.35 | 85
3903 | NADIA | Eastern Mechanical | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Supply, delivery of PCC Pole, M.s materials and electrical accessories including stringing and sagging of LTOH line to WBSEDCL for new service connection at PH-II under Madhupur W/S Scheme. | 1137/EMSD-III | 14/08/2022 | 30 | NEW RANBEE ENGINEERING | 0.19 | 0.19 | 100 | 0
3904 | NADIA | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Laying of Rising Main of Madhupur Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | 26/AE-I/NACD-II | 13/04/2022 | 60 | AMARENDRA NATH PANDAY | 3.95 | 0 | 0 | 90
3905 | NADIA | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Construction for priliminary work of the approch road at Head Works site of Madhupur Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | 416/AE-I/NACD-II | 08/08/2023 | 15 | B.D. COSNTRUCTION | 0.86 | 0 | 0 | 0
3906 | NADIA | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Madhupur and Sikra Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 245/NACD-II | 19/04/2022 | 60 | JOY HIND TUBEWELLS | 41.88 | 40.57 | 100 | 100
3907 | NADIA | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Madhupur water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | 22/AE-I/NACD-II | 13/04/2022 | 60 | AMARENDRA NATH PANDAY | 2.83 | 2.81 | 100 | 100
3908 | NADIA | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Madhupur water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 211/NACD-II | 05/04/2022 | 60 | AMARENDRA NATH PANDAY | 5.38 | 5.33 | 100 | 100
3909 | NADIA | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Madhupur Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 622/NACD-II | 06/09/2022 | 20 | MAKALI ENGINEERING CORPORATION | 3.62 | 3.62 | 100 | 100
3910 | NADIA | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Chapra Block of Nadia District through Jadavpur University. (Name of Scheme Madhupur) | 857/NACD-II | 08/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
3911 | NADIA | Eastern Mechanical | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Supply delivery of PCC Pole, MS materials and electrical accessories and installation of DTR including strings and sagging of HTOH line to WBSEDCL for new service connection at PH-I under Madhupur W/S scheme under EMSD-III | 1230EMD | 14/08/2022 | 30 | NEW RANBEE ENGINEERING | 4.03 | 4.03 | 100 | 100
3912 | NADIA | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Material Requisition To Resource Division | 397/NACD-II | 04/07/2022 | 0 | Resource Division | 27.35 | 0 | 0 | 0
3913 | NADIA | Eastern Mechanical | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Erection of 02 nos 8mtr PCC Pole with allied works IRO Madhupur PHE I under Chapra CCC | BP-146-23-24 | 23/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.27 | 0 | 0 | 0
3914 | NADIA | Eastern Mechanical | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Madhupur W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 06) | 5014/EMD | 03/11/2022 | 30 | M/S. SAJAHAN CHOWDHURY | 10.12 | 10.08 | 100 | 100
3915 | NADIA | Eastern Mechanical | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Headworks) under Madhupur W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. NNo.- 05) | 5013/EMD | 03/11/2022 | 30 | M/S.A.K. BANERJEE. | 10.14 | 9.99 | 100 | 90
3916 | NADIA | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Madhupur Water Supply Scheme at Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | 80/NACD-II | 10/01/2023 | 60 | NIVEDITA CONSTRUCTION | 15.8 | 15.77 | 100 | 100
3917 | NADIA | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Madhupur water supply scheme of Chapra Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | 382/NACD-II | 24/03/2023 | 1073 | SUBHASH BOSE | 119.12 | 9.44 | 7.92 | 76
3918 | NADIA | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME , SM/10103 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 35 cum/Hour capacity for Madhupur Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1146/NACD-II | 23/08/2024 | 180 | MAMATA USHA ENTERPRISE | 164.41 | 0 | 0 | 0
3919 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (Darrappur), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Div , SM/09938 | Augmentation | Repair, Renovation of Haringhata WTP (including 500 cum Back Wash OHR) and Intake with different units and Boundary Wall of WTP under Surface W/S Scheme Haringhata-Chakdah (Part) under Nadia Arsenic Division-I PHE Dte (Sl.no. 02) | 1908 / NAD-I | 29/09/2022 | 60 | TARUN KUMAR BHATTACHARYA | 55.33 | 55.13 | 100 | 100
3920 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (Darrappur), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Div , SM/09938 | Augmentation | Repair of 250 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Darrappur, Zone-V under Surface W/S Scheme of Haringhata-Chakdah (Part) under NAD I PHE Dte (Sl.no. 13) | 3217/ NAD-I | 30/11/2022 | 45 | CHANDAN ROY | 14.38 | 14.34 | 100 | 100
3921 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (Darrappur), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Div , SM/09938 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-V (Darrappur) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 10) | 426/NAD-I | 07/03/2022 | 60 | NATIONAL CONSTRUCTION | 93.56 | 75.43 | 53.19 | 100
3922 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme , SM/10019 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme | 637/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.38 | 0 | 0 | 0
3923 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme , SM/10019 | Augmentation | Material Requisition To Resource Division | 1391/ND | 24/03/2022 | 0 | Resource Division | 32.81 | 0 | 0 | 0
3924 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme , SM/10019 | Augmentation | Material Requisition To Resource Division | 377/ND | 27/01/2022 | 0 | Resource Division | 32.97 | 0 | 0 | 0
3925 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme , SM/10019 | Augmentation | Material Requisition To Resource Division | 379/ND | 27/01/2022 | 0 | Resource Division | 50.46 | 0 | 0 | 0
3926 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme , SM/10019 | Augmentation | Material Requisition To Resource Division | 4311/ND | 29/09/2022 | 0 | Resource Division | 35.85 | 0 | 0 | 0
3927 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme , SM/10019 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 700 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials. and Soil investigation for construction of one new 700 CUM OHR for Augmentation of Ground Based Water Supply Scheme at Dignagar to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 1648/ND | 06/04/2022 | 365 | TARUN KUMAR BHATTACHARYA | 923.7 | 426 | 46.12 | 53
3928 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme , SM/10019 | Augmentation | Continuation of Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 01-08-2023 to 31-01-2024= 184 days. | 736/RSD | 28/07/2023 | 184 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 3.22 | 0 | 0 | 100
3929 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme , SM/10019 | Augmentation | Sinking of 1 no. Tubewell 300mm. x 200mm. dia 200 mtr deep by direct rotary rig method and construction of pump house (3.6 mtr. x 3.0 mtr.) and boundary wall at 3rd tube well site for Dignagar water supply scheme under Krishnagar Sub-Division under Nadia Division, PHE Dte. (Sm/10019) | 2101/ND | 15/05/2023 | 504 | JOY HIND TUBEWELL'S | 29.87 | 12.47 | 55.36 | 100
3930 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme , SM/10019 | Augmentation | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Dignagar Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 5559/ND | 12/12/2023 | 60 | DEY ENTERPRISE | 12.15 | 9.7 | 100 | 100
3931 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme , SM/10019 | Augmentation | WBSEDCL's Quotation for New Service Connection charges to the newly constructed Pump House - III of Dignagar W/S Scheme in Krishnagar-I Block, Dist- Nadia. (Application No. 3004728299) | BP-50-24-25 | 21/06/2024 | 0 | W.B.S.E.D.C.LTD (DIGNAGAR C.C.C) | 8.4 | 0 | 0 | 0
3932 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme , SM/10019 | Augmentation | Conversion of IEP to AIRP of capacity 132 Cu.m/hr at Dignagar Water Supply Scheme within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 1907/ND | 15/03/2024 | 360 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 208.9 | 62.61 | 29.97 | 50
3933 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme , SM/10019 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at Dignagar W/S Scheme Block- Krishnanagar-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/10019 | 1139/EMD | 04/06/2025 | 90 | INDIA ENTERPRISE | 51.72 | 0 | 0 | 0
3934 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme , SM/10019 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under DIGNAGAR W/S Scheme, Block-Krishnagar-I , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 10) | 412/EMD | 20/01/2023 | 758 | M/S GHOSH ENTERPRISE | 16.13 | 0 | 0 | 80
3935 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-B) , SM/07835 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-B) |  | 12/04/2021 | 0 | TARUN KUMAR BHATTACHARYA | 41.39 | 0 | 0 | 0
3936 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-B) , SM/07835 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED W/S SCHEME NORTHERN SECTOR PART-2, ZONE-1 WITHIN NAKASHIPARA BLOCK PHASE-B | 74/PPMS | 15/07/2021 | 0 | TARUN KUMAR BHATTACHARYA | 41.39 | 0 | 0 | 0
3937 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-B) , SM/07835 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-B) | 283/PFMS | 08/10/2021 | 0 | TARUN KUMAR BHATTACHARYA | 31.7 | 0 | 0 | 0
3938 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-B) , SM/07835 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block ( Phase -B) | 241/ND | 15/01/2021 | 90 | TARUN KUMAR BHATTACHARYA | 96.72 | 17.64 | 100 | 0
3939 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-B) , SM/07835 | Retrofitting | Material Requisition To Resource Division | 4305/ND | 29/09/2022 | 0 | Resource Division | 12.6 | 0 | 0 | 0
3940 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-B) , SM/07835 | Retrofitting | Construction of OHR, repair and renovation of staff room, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-I / A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, P.H.E. Dte. [SM/11836]. | 5556/ND | 12/12/2023 | 729 | M/S DIPAK ENTERPRISE, GHOSH PARA,WARD NO-4, KALYANI, NADIA-741235 WEST BENGAL | 150.28 | 0 | 0 | 5
3941 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11513 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Karimpur-Jalangi Z-6 (I&II) W/S Scheme in Karimpur-I Block of Nadia District under Nadia Division, P.H.E. Dte. | 315/TSD | 24/11/2021 | 30 | RADIANT | 4.54 | 4.54 | 100 | 100
3942 | NADIA | Central Drilling | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11513 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300 mm x 200 mm x 250Mtrs. Depth) by utilising Departmental machineries for Karimpur jalangi W/S Scheme (Z-VI TW-I & II) Karimpur-I Block under Nadia District CDD PHE Dte. | 98/CDD | 17/04/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 37.28 | 27.4 | 100 | 100
3943 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11513 | Augmentation | Material Requisition To Resource Division | 1901/ND | 27/04/2023 | 0 | Resource Division | 60.25 | 0 | 0 | 0
3944 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11513 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KARIMPUR JALANGI(Z-6) W/S Scheme, Block- Karimpur I, & KAMALPUR (Z-II) W/S Scheme, Block-Ranaghat II, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 04) | 1197/EMD | 22/03/2023 | 30 | P.K. ENGINEERING | 48.95 | 0 | 0 | 0
3945 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11513 | Augmentation | Quotation charges for new service connection and security deposit at Karimpur Jalangi (Zone-VI,B) PH-I under EMSD-III,Nadia | BP-180 | 13/12/2024 | 0 | WBSEDCL KARIMPUR CCC | 10.19 | 0 | 0 | 0
3946 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11513 | Augmentation | Quotation for new service connection and security deposit for Karimpur Jalangi Zone- 6, Part- B (H/W site) | BP-196-24-25 | 17/12/2024 | 0 | WBSEDCL KARIMPUR CCC | 15.95 | 0 | 0 | 0
3947 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11513 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-VI Part A & Karimpur Jalangi Zone-VI Part B to accommodate FHTC and Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of 200 CUM OHR for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-VI Part B for Ground Based Water Supply Scheme at Karimpur Jalangi Zone-VI (A&B) under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 3028/ND | 14/07/2023 | 366 | BALAJI UDDYOG, 153/2B, A.P.C. ROAD, 1ST FLOOR, KOLKATA- 700006. | 520.9 | 311.8 | 59.86 | 55
3948 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11513 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Karimpur Jalangi Zone-VI water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 6839/ND | 12/11/2024 | 360 | MS MAA BHABANI ENTERPRISE | 31.29 | 0 | 0 | 50
3949 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11513 | Augmentation | Laying of additional pipeline for providing balance FHTC and inerease functionality in Baro Jangal, Majlishpur, Basotipara Villages under Karimpur-I Block under Tehatta Sub-Division under Nadia Division, PHE Dte. | .4686/4533/P-3/ND | 09/10/2025 | 90 | JOY HIND TUBEWELL'S | 79.19 | 0 | 0 | 0
3950 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11513 | Augmentation | Laying of additional pipe lines and allied works to increase the functionality in Brojonathpur, Gandhina villages under Karimpur-I Block under Nadia Division, PHE Dte. | 4685/4533/P-3/ND | 09/10/2025 | 90 | JOY HIND TUBEWELL'S | 46.3 | 0 | 0 | 0
3951 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11832 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 3A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 120/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.63 | 4.6 | 100 | 100
3952 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11832 | Augmentation | Material Requisition To Resource Division | 103/ND | 05/01/2023 | 0 | Resource Division | 240.03 | 0 | 0 | 0
3953 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11832 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
3954 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11832 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 498.82 | 77.87 | 47
3955 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12374 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 6/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 151/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.51 | 4.51 | 100 | 100
3956 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12374 | Augmentation | Material Requisition To Resource Division | 100/ND | 05/01/2023 | 0 | Resource Division | 358.26 | 0 | 0 | 0
3957 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12374 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
3958 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12374 | Augmentation | Restoration of Muragacha Ghosh Para to Dharmada Hospital via Mirpur Kachkuli under (RIDF XXVIII) | 320/PFMS | 05/10/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 16.91 | 0 | 0 | 0
3959 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12374 | Augmentation | RESTORATION OF L071-BTHUADHRI PHE TO DAFADR PARA (BIL KUMARI) under Package No. WB/14/227 | 303/PFMS | 02/10/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 17.55 | 0 | 0 | 0
3960 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12374 | Augmentation | Restoration of T 09 - Barabigha to fakir Danga to Arbetai under Package no. WB 14-ADB37. | 261/PFMS | 26/09/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 14.21 | 0 | 0 | 0
3961 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12374 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4589/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 255.77 | 63.59 | 50
3962 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12374 | Augmentation | Construction of OHR, staff room, chlorine room, service road, boundary wall and restoration of bituminous road, land improvement etc. of Surface Water Based Water Supply Scheme for Zone-VI / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/12374]. | 211/ND | 10/01/2024 | 730 | SARKAR CONSTRUCTION | 348.98 | 1.7 | 0.49 | 10
3963 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12374 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 5.92 | 98.73 | 30
3964 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12374 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
3965 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11841 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 4B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 143/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.63 | 3.91 | 100 | 100
3966 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11841 | Augmentation | Material Requisition To Resource Division | 123/ND | 05/01/2023 | 0 | Resource Division | 114.87 | 0 | 0 | 0
3967 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11841 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 1.4 | 98.71 | 40
3968 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11841 | Augmentation | Material Requisition To Resource Division | 242/ND | 11/01/2024 | 0 | Resource Division | 12.52 | 0 | 0 | 0
3969 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11841 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4589/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 175.61 | 52.66 | 50
3970 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11841 | Augmentation | Construction of OHR, repair and renovation of staff room, repair of boundary wall, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-IV / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11841]. | 6152/ND | 26/12/2023 | 728 | SATYABRATA CHAKRABORTY | 233.13 | 11.7 | 6.23 | 5
3971 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11841 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
3972 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11841 | Augmentation | Construction of Bituminous Approch Road for GLR site at Surface water based water supply Scheme under Northern Sector Part II at Nakashipara Block under Nadia Division PHE Dte. | 3260/ND | 10/07/2025 | 90 | GBC INFRASTRUCTURE PRIVATE LIMITED | 95.58 | 0 | 0 | 5
3973 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-II within Kaliganj Block (Phase-B). , SM/07005 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT NORTHERN SECTOR PART-1 Z-2 | 460/DW | 30/03/2021 | 0 | TARUN KUMAR BHATTACHARYA | 46.42 | 0 | 0 | 0
3974 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-II within Kaliganj Block (Phase-B). , SM/07005 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme(northern sector),Part-I,Zone-II within Kaliganj block(Phase-B) in Nadia District under Nadia Division P.H.Engineering Dte. | 3587/ND | 08/12/2020 | 90 | TARUN KUMAR BHATTACHARYA | 96.83 | 86.71 | 89.54 | 0
3975 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II, Nabadwip (Part) Block (Phase-D) , SM/07432 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II, Nabadwip (Part) Block (Phase-D) | 180/PFMS | 15/09/2021 | 0 | MAHAVIR PUMPS MFG PVT. LTD. | 79.37 | 0 | 0 | 0
3976 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II, Nabadwip (Part) Block (Phase-D) , SM/07432 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II, Nabadwip (Part) Block (Phase-D) |  | 25/03/2021 | 0 | MAHABIR PUMPS MFG PVT. LTD. | 11.54 | 0 | 0 | 0
3977 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II, Nabadwip (Part) Block (Phase-D) , SM/07432 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-IV, within Krishnagar-II & Nabadwip Block (Phase-D, Retrofitting)" | 779/ND | 10/02/2021 | 90 | MAHABIR PUMPS MFG PVT. LTD. | 97.11 | 23.08 | 23.77 | 0
3978 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II, Nabadwip (Part) Block (Phase-D) , SM/07432 | Retrofitting | Material Requisition To Resource Division | 301/ND | 15/01/2024 | 0 | Resource Division | 2.48 | 0 | 0 | 0
3979 | NADIA | Eastern Mechanical | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | New connection charges for Jitpur PHE I Tehatta Nadia. Memo no. 3004031067/Quot/03 |  | 21/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.2 | 0 | 0 | 0
3980 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
3981 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
3982 | NADIA | Eastern Mechanical | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | New connection charges for Jitpur PHE I Tehatta Nadia. Memo no. 3004031024/Quot/03 |  | 21/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.91 | 0 | 0 | 0
3983 | NADIA | Eastern Mechanical | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | New Service Connection for PH No.-I under Jitpur Tehatta Nadia | 90/EMD | 26/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.91 | 0 | 0 | 0
3984 | NADIA | Eastern Mechanical | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | New Service Connection for PH No.-II under Jitpur Tehatta Nadia | 89/EMD | 26/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.2 | 0 | 0 | 0
3985 | NADIA | Eastern Mechanical | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Supply, delivery of PCC Pole, M.s materials and electrical accessories including stringing and sagging of LTOH line to WBSEDCL for new service connection at PH-II under Jitpur W/S Scheme. | 1365/EMSD-III | 14/08/2022 | 30 | S.P. ENTERPRISE (SILIGURI) | 0.39 | 0.39 | 100 | 0
3986 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Jitpur water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | 15/AE-II/NACD-II | 11/04/2022 | 60 | R.M. TRADING | 2.83 | 2.81 | 100 | 100
3987 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Jitpur water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 217/NACD-II | 05/04/2022 | 60 | R.M. TRADING | 5.38 | 5.37 | 100 | 100
3988 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Jitpur and Suruppur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 243/NACD-II | 19/04/2022 | 60 | B.M. ENGINEERING & CONSTRUCTION | 42.4 | 38.59 | 100 | 100
3989 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Laying of Rising Main of Jitpur Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | 19/AE-II/NACD-II | 18/04/2022 | 30 | SANJIT DAS | 4.98 | 4.92 | 100 | 85
3990 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Jitpur Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 625/NACD-II | 06/09/2022 | 20 | RAMASISH ENTERPRISE | 4.44 | 4.44 | 100 | 100
3991 | NADIA | Eastern Mechanical | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.II under Jitpur W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 08) | 6259/EMD | 14/08/2022 | 30 | S.P. ENTERPRISE | 9.86 | 9.85 | 100 | 90
3992 | NADIA | Eastern Mechanical | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Supply delivery of PCC Pole materials and electrical accessories and installation DTR including sagging of HTOH line to WBSEDCL for new service connection at PH-I under Jitpur W/S Scheme. | 262/EMSD-III | 28/02/2023 | 30 | R.M.D. TRADING | 3.47 | 3.47 | 100 | 80
3993 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-I Block of Nadia District through Jadavpur University (Name of PWSS Jitpur) | 1155/NACD-II | 10/10/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
3994 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Jitpur and adjoining mouzas under Jitpur Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | 297/NACD-II | 19/05/2022 | 90 | USHA CONSTRUCTION | 134.8 | 134.5 | 100 | 100
3995 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Material Requisition To Resource Division | 408/NACD-II | 04/07/2022 | 0 | Resource Division | 44.15 | 0 | 0 | 0
3996 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Jitpur Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | 84/NACD-II | 10/01/2023 | 60 | BABLU MALLICK | 21.46 | 18.43 | 85.89 | 85
3997 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 34 cum/Hour capacity for Jitpur Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte | 1116/NACD-II | 16/08/2024 | 180 | DEBAPRASAD MONDAL | 163.12 | 0 | 0 | 0
3998 | NADIA | Eastern Mechanical | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) under Jitpur W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No.- 21 of EE/EMD of 2022-23 (Sl. No.- 07) | 6491/EMD | 30/11/2022 | 30 | RMD TRADING | 9.97 | 9.87 | 100 | 100
3999 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Construction of Pathway at Jitpur 2nd tube well site within Jitpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 392./AE-I/NACD-II | 31/07/2023 | 45 | SREE GURU ENTERPRISE | 4.22 | 4.2 | 100 | 100
4000 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Jitpur 2nd Tubwell Site within Jitpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 123/NACD-II | 11/01/2023 | 60 | SOURAV & CO. | 6.62 | 6.55 | 100 | 85
4001 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or damaged line repair due to construction of drain) at Jitpur ( Vill- Chalk Jaliapara, Khaspara) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 247/AE-II/NACD-II | 31/07/2024 | 15 | SUBHASIS MOJUMDER | 0.99 | 0.99 | 100 | 100
4002 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or damaged line repair due to construction of drain) at Jitpur ( Vill- Chalk Jaliapara) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 164_AE-II/NACD-II | 14/06/2024 | 15 | SUPRIO MAJUMDER | 0.96 | 0.95 | 100 | 100
4003 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Acceptance cum work order "Conversion of IEP to AIRP at Bhagakhali Zone-I & Jitpur Water Supply Scheme of capacity 27 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | 196/NACD-II | 12/02/2024 | 601 | SANDIP BISWAS | 103.73 | 0 | 0 | 80
4004 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Laying of distribution system including providing FHTC at left out households for Thanarpara Zone-III (Vill- Char Gaurbhanga, Falia, Yusufpur) , Jitpur , Taranipur & Dhopahat W/S Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1627/NACD-II | 19/12/2024 | 270 | M.R. CONSTRUCTION | 117.87 | 0 | 0 | 40
4005 | NADIA | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME , SM/10405 | New | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Jitpur water supply scheme of Tehatta-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | 369/NACD-II | 23/03/2023 | 729 | B.M. ENGINEERING & CONSTRUCTION | 117.24 | 85.1 | 73.5 | 100
4006 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA , SM/11741 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Bagula Zone-II W/S Scheme in Hanskhali Block of Nadia District under Nadia Division, P.H.E. Dte. | 1066/RSD | 02/12/2021 | 30 | HORIZEN | 3.01 | 2.91 | 100 | 100
4007 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA , SM/11741 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangemen At Hw Site At Bagula Zone-II Water Supply Scheme Under Ranaghat Sub-Division PHE Dte.) | 5188/ND | 22/11/2023 | 90 | M/S S.K. ENTERPRISE | 6.88 | 0 | 0 | 0
4008 | NADIA | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA , SM/11741 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Bagula (Z-II) PWSS W/S Scheme (TW-I) ,Hanskhali Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 1661/CDD | 17/10/2023 | 30 | RAJ & ENTERPRISE | 18.71 | 0 | 0 | 0
4009 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA , SM/11741 | Augmentation | Material Requisition To Resource Division | 1865/ND | 26/04/2023 | 0 | Resource Division | 12.06 | 0 | 0 | 0
4010 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA , SM/11741 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
4011 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA , SM/11741 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augomentation in connection to Accommodate FHTC at Pump House No.-II under Bagula Zone-II ground water based water supply scheme under Block_ Krishnanagar-I Dist. - Nadia under EMD, PHE Dte. | 1305/EMD | 09/05/2024 | 448 | ANUPAMA ENGINEERING WORKS | 9.26 | 0 | 0 | 0
4012 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA , SM/11741 | Augmentation | Material Requisition To Resource Division | 256/ND | 11/01/2024 | 0 | Resource Division | 25.16 | 0 | 0 | 0
4013 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA , SM/11741 | Augmentation | Material Requisition To Resource Division | 7558/ND | 27/12/2024 | 0 | Resource Division | 3.66 | 0 | 0 | 0
4014 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA , SM/11741 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, construction of 550 cum capacity 20 mtr. Staging height RCC over head reservoir (including pile foundation), pipe connection and cost of pipes, specials and soil investigation for construction of one no. 550 cum OHR of staging height 20 mtr. for augmentation of Ground Water Based Water Supply Scheme for BAGULA Zone-II to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | 3540/ND | 11/08/2023 | 731 | AMAL DUTTA ROY | 565.73 | 92.68 | 16.38 | 55
4015 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA , SM/11741 | Augmentation | Construction of 120.00 Cum/Hr capacity Arsenic-cum-Iron Removal plant at Bagula Zone-II Water Supply Scheme under Ranaghat Sub-Division under Nadia Division PHE Dte. | 4124/ND | 29/07/2024 | 360 | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 296.58 | 0 | 0 | 70
4016 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA , SM/11741 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Bagula Zone-II under Ranaghat Sub-Division under Nadia Division PHE Dte. | 1413/RSD | 19/11/2024 | 45 | J & T ENTERPRISE | 2.15 | 0 | 0 | 100
4017 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta , SM/12022 | Augmentation | Construction of Approach Road and allied work at site of Arranghata Z-I W/S scheme within Ranaghat -II Block under Nadia Arsenic Division -I ( Sl.no. 01) | 1585 / NAD-I | 06/09/2022 | 45 | B.K. ENGINEERING | 12.4 | 11.95 | 100 | 100
4018 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta , SM/12022 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Dubli Zone-II Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Dubli Zone-II W/S Scheme under JJM (sl.03) | 1155 / NAD-I | 28/04/2023 | 15 | BISWAS ENTERPRISE | 13.04 | 12.33 | 100 | 100
4019 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta , SM/12022 | Augmentation | Providing FHTC (Functional Household Tap Connection) at Jugolkishore G.P. under Jal Jeevan Mission (JJM) for Ranaghat-II Block of Goalsalua Zone-I Ground Water based PWSS under Nadia Arsenic Division-I, PHE Dte. | 167/NAD-I | 07/02/2024 | 15 | GOUTAM DEY | 4.91 | 0 | 0 | 0
4020 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta , SM/12022 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Debagram Phase-I at Ranaghat-II Block by Augmentation of Ground Water Based PWSS for Debagram W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | 1475/NAD-I | 22/08/2022 | 90 | GHOSH ENTERPRISE | 320.01 | 0 | 0 | 100
4021 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta , SM/12022 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Dubli Zone-I Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Dubli Zone-I W/S Scheme under JJM (sl.02) | 1154 / NAD-I | 28/04/2023 | 15 | BUDDHADEV MONDAL | 13.02 | 12.36 | 100 | 100
4022 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta , SM/12022 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Arranghata Zone-I Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Arranghata Zone-I (Phase-II) W/S Scheme under JJM (Sl.no.05) | 1425/NAD-I | 23/05/2023 | 15 | M/S BISWAS BROTHERS | 12.98 | 12.95 | 100 | 100
4023 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta , SM/12022 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Paschim Noapara Ground Based Water Supply Scheme under Ranaghat-I, under Office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E Dte. in connection with Augmentation of Paschim Noapara Water Supply Scheme under JJM (Sl.No.-04) | 720/NAD-I | 27/03/2023 | 15 | DAS CONSTRUCTION | 13.04 | 12.5 | 100 | 100
4024 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta , SM/12022 | Augmentation | Retrofitting work at Chandpur More area under Ranaghat-II block Augmentation of Ground Water Based PWSS for Dhantala W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.02) | 369/AE-II/NAD-I | 24/08/2023 | 7 | REKHA ENTERPRISE | 2.31 | 2.3 | 100 | 60
4025 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta , SM/12022 | Augmentation | Retrofitting work under Jal Jeevan Mission (JJM) for Gourisail area under Ranaghat-II Block by Augmentation of Ground Water Based PWSS forDubli Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.22) | 2207/NAD-I | 13/09/2023 | 30 | GHOSH ENTERPRISE | 95.24 | 91.63 | 100 | 100
4026 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta , SM/12022 | Augmentation | Retrofitting work including FHTC (Functional Household Tap Connection) of Garapota and Duttaphulia at Block Hanskhali under Jal Jeevna Mission in connection with augmentation of Duttaphulia Zone-II W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.07) | 2253/NAD-I | 22/09/2023 | 21 | M/S A.K. CONSTRUCTION | 78.25 | 77.97 | 100 | 100
4027 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta , SM/12022 | Augmentation | Culvert crossing and restoration of pipeline including jointing with manifold and other allied works under Paschim Noapara Water Supply Scheme , Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 01) | 1555/NAD-I | 25/09/2024 | 45 | JOYGOPAL GUPTI | 6.11 | 2.54 | 29.42 | 100
4028 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta , SM/12022 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Dhara / Jal Swapna for Aranghata Zone-II Part -III under Jal Jeevan Mission at Ranaghat -II Block by retrofitting of ground Water based PWSS for Aranghata Zone-II Water Supply Scheme under Nadia Arsenic Division -I, PHE Dte. | 461/NAD-I | 15/03/2024 | 382 | DIVINE | 329.47 | 0 | 0 | 75
4029 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta , SM/12022 | Augmentation | Providing FHTC and laying dedicated pipeline for Uzirpukuria, Humaniapota, Purba Simulia Village under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in connection with Dubli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) | 248/NAD-I | 15/05/2025 | 60 | SUMAN CHAKRABORTY | 58.02 | 0 | 0 | 0
4030 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta , SM/12022 | Augmentation | Laying dedicated pipeline to supply water for Sabdalpur and Hosenpur under Jal Jeevan Mission (JJM) at Ranaghat-II Block of Sabdalpur Ground Water Based PWSS for under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 07) | 133/NAD-I | 22/04/2025 | 60 | MANISHIKA CONSTRUCTION | 52.42 | 0 | 0 | 0
4031 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhantala, Sabdalpur,Aranghata, Dubli & Goalsalua of Ranaghat -II Block, Paschim Noapara of Ranaghat-I Block & Garapota of Hanskhali Block, District - Nadia by Augmenta , SM/12022 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Arranghata Zone-II Ground Based Water Supply Scheme under Ranaghat- II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Arranghata Zone- II (Phase-I) under JJM (sl.06) | 1157/NAD-I | 28/04/2023 | 728 | BISWAS CONSTRUCTION | 13.01 | 0 | 0 | 100
4032 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11548 | Augmentation | Additional Survey, Design Drawing & DPR Preparation for ZONE 2 of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte ( Sl.No .04 ) | 206/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 1.23 | 1.23 | 100 | 100
4033 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11548 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 2 of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. ( Sl.No .03 ) | 205/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.62 | 4.59 | 100 | 100
4034 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11548 | Augmentation | Material Requisition To Resource Division | 85/ND | 05/01/2023 | 0 | Resource Division | 208.54 | 0 | 0 | 0
4035 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11548 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 366 days w.e.f. 01/01/2024 to 31/12/2024 | 1838/KSD | 28/12/2023 | 366 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0 | 0
4036 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11548 | Augmentation | Restoration work of jhama shoulder damaged due to laying of pipe line under JJM project for Mayapur Youth Hostel Road from 0.0 Km to 0.47 Km under Nadia Highway Division-I, P.W.D (Roads) Directorate. | 363/PFMS | 19/12/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 0.74 | 0 | 0 | 0
4037 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11548 | Augmentation | RESTORATION OF ROAD FLANK OF MAHESHGANJ MAYAPUR ROAD FROM CH. 0.50 KM TO 2.50 KMP. | 600/PFMS | 14/03/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 3.01 | 0 | 0 | 0
4038 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11548 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | 3537/ND | 11/08/2023 | 782 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 475.37 | 63.91 | 20
4039 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11548 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 0 | 30
4040 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11548 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub Division, PHE Dte for supervision of JJM works for the period of 01/01/2025 to 31/12/2025 | 2666/KSD | 31/12/2024 | 365 | AVINABA ENGINEERING CONCERN | 4.8 | 0 | 0 | 0
4041 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11548 | Augmentation | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3829/ND | 13/08/2025 | 120 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0 | 0
4042 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11610 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 3/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. ( Sl.No .06 ) | 208/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.67 | 3.62 | 100 | 100
4043 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11610 | Augmentation | Material Requisition To Resource Division | 118/ND | 05/01/2023 | 0 | Resource Division | 20.12 | 0 | 0 | 0
4044 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11610 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | 3537/ND | 11/08/2023 | 782 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 426.26 | 70.2 | 20
4045 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11610 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 0 | 30
4046 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11610 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub Division, PHE Dte for supervision of JJM works for the period of 01/01/2025 to 31/12/2025 | 2666/KSD | 31/12/2024 | 365 | AVINABA ENGINEERING CONCERN | 4.8 | 0 | 0 | 0
4047 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11610 | Augmentation | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3829/ND | 13/08/2025 | 120 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0 | 0
4048 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12376 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 9/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 158/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.47 | 4.39 | 100 | 100
4049 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12376 | Augmentation | Material Requisition To Resource Division | 1526/ND | 04/04/2023 | 0 | Resource Division | 390.11 | 0 | 0 | 0
4050 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12376 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
4051 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12376 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4588/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 308.69 | 65.23 | 19
4052 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12376 | Augmentation | Construction of OHR, staff room, chlorine room, service road, boundary wall and restoration of bituminous road, land improvement etc. of Surface Water Based Water Supply Scheme for Zone-IX / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/12376]. | 213/ND | 10/01/2024 | 730 | PRASUN ENTERPRISE | 256.2 | 7.6 | 2.97 | 3
4053 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12376 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 5.92 | 98.73 | 30
4054 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12376 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
4055 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/12376 | Augmentation | Additional Work for Installation of SCADA System in connection with Augmentation of Surface Water Based Piped Water Supply Scheme for Northern Sector Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 3447/ND | 23/07/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 732.35 | 0 | 0 | 15
4056 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-V, (Darrappur) Part-IV, Repair and Renovation of different units of Haringhata WTP at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata , SM/11456 | Augmentation | Supplying, ,installation and commissioning of different equipments at the Conference Room under Haringhata WTP to make it compatible for video conferencing facility including supply & installation of surveillance system under Office of the Executive Engineer , Nadia Arsenic Division - I , PHE Dte. under Public Health Engineering Department, Govt. of West Bengal | 601/NAD-I | 20/04/2022 | 45 | ALTAVISTA TECH SOLUTIONS | 24.44 | 0 | 0 | 43
4057 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-V, (Darrappur) Part-IV, Repair and Renovation of different units of Haringhata WTP at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata , SM/11456 | Augmentation | Charges of entry of household data in JJM with Household Aadhar details ......... Geo Tagging ..... in different Block of Nadia District under Nadia Arsenic Division -I, P.H.E.Dte. (Sl.no.03) | 163 / AE-I/NAD-I | 04/07/2022 | 90 | SUMAN CHAKRABORTY | 4.85 | 4.85 | 100 | 100
4058 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-V, (Darrappur) Part-IV, Repair and Renovation of different units of Haringhata WTP at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata , SM/11456 | Augmentation | Repair of 450 cum capacity Over Head Reservoir, for Chakdah WTP under Chakdah Surface W/S Scheme in Chakdah Block under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no. 08) | 1637 / NAD-I | 06/09/2022 | 45 | M/S R.K. ENTERPRISE | 13.75 | 11.47 | 100 | 55
4059 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-V, (Darrappur) Part-IV, Repair and Renovation of different units of Haringhata WTP at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata , SM/11456 | Augmentation | Providing FHTC Functional Household Tap Connection under Jal Jeevan Mission JJM Zone -V Darrappur Part -IV at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata and Chakdah Part W/S Scheme under Nadia Arsenic Division- I P.H.E Dte. (Sl. No. 17) | 3041/NAD-I | 09/11/2022 | 45 | M/S DIPAK ENTERPRISE | 71.77 | 70.32 | 100 | 80
4060 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-V, (Darrappur) Part-IV, Repair and Renovation of different units of Haringhata WTP at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata , SM/11456 | Augmentation | Road Restoration under Jal Jeevan Mission (JJM) for Birohi-I and Fatepur G.P. and Haringhata Block under Providing FHTC (Functional Househod Tap Connection) under Jaldhara/Jalswapna for Zone-III (Jalkar Bhomra), Part-II at Haringhata Block by retrofitting of Surface Water Based PWSS for Haringhata & Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | 582/NAD-I | 10/07/2025 | 60 | SUMAN CHAKRABORTY | 10.33 | 0 | 0 | 100
4061 | NADIA | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME , SM/12421 | New | Material Requisition To Resource Division | 1088/NACD-II | 09/12/2022 | 0 | Resource Division | 0.55 | 0 | 0 | 0
4062 | NADIA | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME , SM/12421 | New | Sinking of 2 nos. 200 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (200 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Manoharpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 1132/NACD-II | 16/12/2022 | 30 | GENUINE | 20.4 | 16.66 | 81.64 | 100
4063 | NADIA | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME , SM/12421 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Karimpur-II Block of Nadia District through Jadavpur University. (Name of PWSS Manoharpur) | 916/NACD-II | 01/09/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
4064 | NADIA | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME , SM/12421 | New | Material Requisition To Resource Division | 378/NACD-II | 24/03/2023 | 0 | Resource Division | 3.14 | 0 | 0 | 0
4065 | NADIA | Eastern Mechanical | MANOHARPUR PIPED WATER SUPPLY SCHEME , SM/12421 | New | New Service connection at PH-I under Manoharpur W/S scheme. | BP-136-23-24 | 16/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.46 | 0 | 0 | 0
4066 | NADIA | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME , SM/12421 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. | 23 | 19/04/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
4067 | NADIA | Eastern Mechanical | MANOHARPUR PIPED WATER SUPPLY SCHEME , SM/12421 | New | New Service connection at PH-II under Manoharpur W/S scheme. | BP-137-23-24 | 16/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.48 | 0 | 0 | 0
4068 | NADIA | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME , SM/12421 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL | 235/5 | 21/02/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0 | 0
4069 | NADIA | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME , SM/12421 | New | Laying of Distraibution system including providing Functional House Hold Tap Connection (FHTC) for Manoharpur and adjoining mouzas under Manoharpur W/s Scheme of Karimpur-II Block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist-Nadia. | 153/NACD-II | 17/01/2023 | 30 | NATIONAL CONSTRUCTION | 40.06 | 30.43 | 75.96 | 75
4070 | NADIA | Eastern Mechanical | MANOHARPUR PIPED WATER SUPPLY SCHEME , SM/12421 | New | Supply, delivery, installation and commissioning of electro-mechanical accessories in connection with installation of Clear Water Pumping machinery in MANOHARPUR PWSS, Block_ KARIMPUR-II, District- Nadia. Under EMD PHE Dte. 2024_PHED_664112_4 | 926/EMD | 15/03/2024 | 30 | DIPALI CONSTRUCTION | 9.65 | 0 | 0 | 0
4071 | NADIA | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME , SM/12421 | New | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Manoharpur water supply scheme under Nadia Arsenic Civil Division-II, PHE Dte. Dist- Nadia | 1363/NACD-II | 08/12/2023 | 45 | EVEREST CONSULTANT SERVICES. | 20.96 | 18.27 | 100 | 80
4072 | NADIA | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME , SM/12421 | New | Sinking of 3 nos. Tube Well at H/W site ,2nd and 3rd T/W site of 300 mm X 200 mm dia, 150 mtr deep by Direct Rotary Method with UPVC pipe (CD) & Fibre Glass strainer, ( 300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Thanapara Zone-III & Manoharpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | 1047/NACD-II | 07/08/2024 | 90 | B.M. ENGINEERING & CONSTRUCTION | 34.68 | 17.34 | 100 | 100
4073 | NADIA | Eastern Mechanical | MANOHARPUR PIPED WATER SUPPLY SCHEME , SM/12421 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Manoharpur ground water based water supply scheme under Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. | 865/EMD | 14/03/2024 | 30 | CINZANO | 22.25 | 0 | 0 | 85
4074 | NADIA | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME , SM/12421 | New | Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Manoharpur & Suruppur water supply scheme under Karimpur-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia. | 135/NACD-II | 09/01/2025 | 225 | NISHITH BANERJEE | 32.78 | 0 | 0 | 50
4075 | NADIA | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME , SM/12421 | New | Construction of 75 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Thanarpara Zone-III Water Supply Scheme in Karimpur-II block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | 1207/NACD-II | 04/09/2024 | 180 | SINGHA ROY & CO. | 215.53 | 0 | 0 | 0
4076 | NADIA | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME , SM/12421 | New | Acceptance cum work order "Construction of 30 m3/hr capacity IEP at Manoharpur PWSS in Karimpur-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte." | 399/NACD-II | 13/03/2024 | 601 | MASUM CONSTRUCTION | 19.23 | 0 | 0 | 75
4077 | NADIA | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME , SM/12421 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-II Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. & including Binodnagar PWSS,Manoharpur PWSS, Rajapur PWSS & Taranipur PWSS. | 428/NACD-II | 07/04/2025 | 180 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 19.28 | 0 | 0 | 30
4078 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/19042 | Augmentation | Preparation of Detailed Project Report (DPR) for Augmentation of Surface Water Based PWSS fo Haringhata & Chakdah (Part) Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(Sl.no.02) | 2614/NAD-I | 22/11/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 92.86 | 92.86 | 100 | 100
4079 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/19042 | Augmentation | Interconnection between outlet pipe of OHR and delivery main at different H/W sites in Haringhata and Chakdah (Part) surface water based PWSS at Haringhata block in connection with JJM under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) | 1710/NAD-I | 21/10/2024 | 21 | TARUN KUMAR BHATTACHARYA | 36.87 | 0 | 0 | 0
4080 | NADIA | Eastern Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/19042 | Augmentation | Implementation of SCADA system at Intake, WTP and OHR sites of surface based water supply scheme for Haringhata & Chakdah (Part) in the District of Nadia. | 1523/EMD | 07/06/2024 | 183 | G.B. CONSTRUCTION | 592.09 | 0 | 0 | 0
4081 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/19042 | Augmentation | Augmentation work of Clariflocculator-I of Haringhata & Chakdah (Part) WTP (33.39) MLD under JJM in connection with Augmentation of Surface Water Based PWSS for Haringhata & Chakdah (Part) at Chakdah & Haringhata block in the district of Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | 2699/NAD-I | 05/12/2023 | 21 | G.B. CONSTRUCTION | 95.48 | 95.14 | 100 | 100
4082 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/19042 | Augmentation | Augmentation of different units in connection with augmentation of Surface Based PWSS for Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte (sl.03) | 2610/NAD-I | 22/11/2023 | 30 | CHOWDHURY & CO. | 95.73 | 95.45 | 100 | 100
4083 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/19042 | Augmentation | Augmentation work of Filter Bed & different units of Haringhata & Chakdah (Part) WTP (33.39 MLD) under JJM in connection with augementation of Surface Water Based W/S Scheme for Haringhata &Chakdah (Part) at Chakdah & Haringhata Block in the didtrict of Nadia under Nadia Arsenic Division - I P. H.E. Dte | 08/NAD-I | 03/01/2024 | 25 | TARUN KUMAR BHATTACHARYA | 24.29 | 24.17 | 100 | 100
4084 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/19042 | Augmentation | Material Requisition To Resource Division | 2054/NAD-I | 09/12/2024 | 0 | Resource Division | 112.27 | 0 | 0 | 0
4085 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/19042 | Augmentation | Material Requisition To Resource Division | 2090/NAD-I | 16/12/2024 | 0 | Resource Division | 207.24 | 0 | 0 | 0
4086 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/19042 | Augmentation | Material Requisition To Resource Division | 1167/NAD-I | 29/07/2024 | 0 | Resource Division | 438.24 | 0 | 0 | 0
4087 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/19042 | Augmentation | Material Requisition To Resource Division | 276/NAD-I | 23/02/2024 | 0 | Resource Division | 250.42 | 0 | 0 | 0
4088 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/19042 | Augmentation | Augmentation of Water Treatment Plant, Intake & Rising Main for Surface Water Based Piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR including Soil Test, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 26 Nos. distribution zone for Haringhata & Chakdah (Part) in Haringhata & Chakdah Block of Nadia District under Nadia Arsenic Division-I, PHE Dte | 2730/NAD-I | 07/12/2023 | 548 | G.B. CONSTRUCTION & UMWELT JV | 10913.55 | 2891.16 | 26.49 | 3
4089 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/19042 | Augmentation | Shifting and relaying of distribution pipeline under Haringhata-Chakdah(P) Zone-III from pond side to inner location for preventing bacteriological contamination of distribution water and providing secondary chlorination system and including internal electrification and yard lighting at all the 13 (thirteen) nos of existing zones of Surface Water based water supply schemes for Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | 2804/NAD-I | 25/03/2025 | 45 | TARUN KUMAR BHATTACHARYA | 35.7 | 0 | 0 | 0
4090 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/19042 | Augmentation | Augmentation of WTP & Intake in all respect along with ancillary works to make all the units, SCADA compatible all complete at Chakdah WTP under Augmentation of Chakdah Part & Haringhata & Chakdah (Part) under Nadia Arsenic Division I, PHE Dte. (Sl. NO. 01) | 97/NAD-I | 17/04/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 855.87 | 0 | 0 | 0
4091 | NADIA | Nadia Arsenic Division I | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE. , SM/19042 | Augmentation | Replacing of old filter media from filter bed and supply, placing by new filter media of different size, Replacing the control chamber of the filter bed , construction of shed over filter bed & installation of SCADA system and ancillary works at HARINGHATA WTP under Augmentation of HARINGHATA & CHAKDAH(Part) under Nadia Arsenic Division I, PHE Dte. (sl.02) | 96/NAD-I | 17/04/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 839.8 | 0 | 0 | 0
4092 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11735 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 4B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 123/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.07 | 4.03 | 100 | 100
4093 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11735 | Augmentation | Material Requisition To Resource Division | 104/ND | 05/01/2023 | 0 | Resource Division | 112.63 | 0 | 0 | 0
4094 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11735 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 457.66 | 79.88 | 47
4095 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11737 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 6A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 126/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.85 | 4.8 | 100 | 100
4096 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11737 | Augmentation | Material Requisition To Resource Division | 76/ND | 05/01/2023 | 0 | Resource Division | 260.19 | 0 | 0 | 0
4097 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11737 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 448.13 | 81.76 | 47
4098 | NADIA | Nadia Arsenic Division I | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/13758 | New | Preparation of Detailed Project Report (DPR) for Gosair Char Water Supply Scheme at Ranaghat-I Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(sl.no.03) | 3286 /NAD-I | 08/12/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 2.92 | 2.87 | 100 | 100
4099 | NADIA | Nadia Arsenic Division I | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/13758 | New | Providing, Laying of Rising Main, Laying distribution system and FHTC (Functional Household Tap Connection) under Jal Jivam Mission, Soil investigation for the work of construction of 100 cum OHR staging height 20 mtr, Construction of 100 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including Raft foundation), pipe connection and cost of pipes, specials, Construction of Pump house, Boundary Wall, Service and Allied Works at head work & 2nd site for Gosair Char Water Supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I , PHE Dte. | 2370/NAD-I | 06/10/2023 | 779 | SANJOY BAKSHI | 294.57 | 48.62 | 16.51 | 60
4100 | NADIA | Eastern Mechanical | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/13758 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for New Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Gosai Char ground water based water supply scheme under Block_ Ranaghat-I Dist. - Nadia under EMD, PHE Dte. [SM/13758] | 2682/EMD | 20/11/2024 | 30 | WESTERN ENGINEERING CO. | 21.26 | 0 | 0 | 0
4101 | NADIA | Nadia Arsenic Division I | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/13758 | New | Material Requisition To Resource Division | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 3.09 | 0 | 0 | 0
4102 | NADIA | Nadia Arsenic Division I | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/13758 | New | Material Requisition To Resource Division | 845/NAD-I | 04/06/2024 | 0 | Resource Division | 1.87 | 0 | 0 | 0
4103 | NADIA | Eastern Mechanical | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/13758 | New | New Service Connection for Gosaichar Water supply scheme | BP-197-24-25 | 17/12/2024 | 0 | W.B.S.E.D.C.L (AISHTAL CCC) | 4.98 | 0 | 0 | 0
4104 | NADIA | Nadia Arsenic Division I | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/13758 | New | Collection of Household Details at prescribed Format through Mobile App/Hard Copy including Geo-Reference as directed by EIC and submission of same to PHE Dte in soft copy at different piped water supply scheme under Nadia Arsenic Division-I, PHED. Name of PWSS:- 1) Nasra 2) Baganchara 3) Haringhata & Chakdah Zone-VI Part-II 4) Haringhata & Chakdah Zone-VI Part-I 5) Haringhata & Chakdah Zone-VI 6) Gosaichar 7) Saguna 8) Birnagar 9) Parbatipur Zone-I 10) Parbatipur Zone-II 11) Hijuli etc. (Sl. NO. 01) | 977/NAD-I | 25/06/2024 | 359 | TECH VISION | 9.88 | 5.95 | 60.24 | 100
4105 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA , SM/11925 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Udaypur W/S Scheme in Santipur Block of Nadia District under Nadia Division, P.H.E. Dte. | 1058/RSD | 02/12/2021 | 30 | HORIZEN | 3.35 | 2.95 | 100 | 100
4106 | NADIA | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA , SM/11925 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Udaypur W/S Scheme (T/W-I),Santipur Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 512/CDD | 01/06/2023 | 30 | UTTAM KUMAR CHATTERJEE | 18.88 | 0 | 0 | 0
4107 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA , SM/11925 | Augmentation | Material Requisition To Resource Division | 1863/ND | 26/04/2023 | 0 | Resource Division | 46.68 | 0 | 0 | 0
4108 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA , SM/11925 | Augmentation | Material Requisition To Resource Division | 3543/ND | 11/08/2023 | 0 | Resource Division | 75.5 | 0 | 0 | 0
4109 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA , SM/11925 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 90 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Udaypur to accommodate FHTC within Santipur block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | 4125/ND | 29/07/2024 | 180 | MERCURY ENGINEERING COMPANY | 237.16 | 0 | 0 | 0
4110 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA , SM/11925 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Udaypur piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | 1137/RSD | 11/09/2024 | 45 | MAA SARADA CONSTRUCTION | 1.9 | 1.76 | 100 | 100
4111 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA , SM/11925 | Augmentation | Material Requisition To Resource Division | 254/ND | 11/01/2024 | 0 | Resource Division | 12.33 | 0 | 0 | 0
4112 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA , SM/11925 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete & Construction & Soil investigation of 700 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection and Cost of Pipes, Specials for augmentation of Ground Water Based Water Supply Scheme for UDAYPUR to accommodate FHTC in Santipur block of Nadia District under Nadia Division P.H.Engineering Dte. | 3027/ND | 14/07/2023 | 1096 | SANDIP BISWAS, RAMESWAR NATH LANE, CHOWDHURYPARA, PO- KRISHNAGAR, NADIA, 741101. | 468.16 | 296.83 | 63.4 | 75
4113 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA , SM/11925 | Augmentation | Construction of Pump house and Boundary wall at head work site in related to augmentation of Ground Water Based Piped Water Supply Scheme for Udaypur Water Supply scheme under Santipur Block in Nadia District under Nadia Division P.H.Engineering Dte. | 845/ND | 06/02/2024 | 604 | S.M. CONSTRUCTION | 24.18 | 0 | 0 | 70
4114 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA , SM/11925 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under Augmentation of Udaypur PWSS. | 206/RSD | 06/02/2025 | 45 | GITARANI ENTERPRISE | 3.19 | 0 | 0 | 100
4115 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA , SM/11925 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Udaypur ground water based water supply scheme under Block_Santipur Dist. - Nadia under EMD, PHE Dte.(SM/11925) | 1128/EMD | 04/06/2025 | 90 | SHIVAM ENTERPRISE | 24.59 | 0 | 0 | 0
4116 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA , SM/11925 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
4117 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11870 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 3B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 121/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.04 | 4.02 | 100 | 100
4118 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11870 | Augmentation | Material Requisition To Resource Division | 72/ND | 05/01/2023 | 0 | Resource Division | 91.95 | 0 | 0 | 0
4119 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11870 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 344.85 | 56.43 | 47
4120 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11808 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 2/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 137/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.29 | 3.78 | 100 | 100
4121 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11808 | Augmentation | Material Requisition To Resource Division | 93/ND | 05/01/2023 | 0 | Resource Division | 102.91 | 0 | 0 | 0
4122 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11808 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
4123 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11808 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 700 cum. For Surface Water Based Piped Water Supply Scheme for Zone II/A (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte.¿ | 3999/ND | 07/09/2023 | 60 | S.B.CONSTRUCTION | 27.73 | 27.66 | 100 | 50
4124 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11808 | Augmentation | Material Requisition To Resource Division | 228/ND | 11/01/2024 | 0 | Resource Division | 10.18 | 0 | 0 | 0
4125 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11808 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- II/A (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4280/ND | 21/09/2023 | 811 | ONKAR ENTERPRISE | 284.27 | 85.42 | 30.05 | 4
4126 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11808 | Augmentation | Additional work for Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes etc. all complete for Zone- II/A (Northern Sector Part-II) under Nakashipara Block of Nadia District. | 1473/ND | 25/03/2025 | 60 | ONKAR ENTERPRISE | 72.83 | 0 | 0 | 0
4127 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11808 | Augmentation | Additional Work for Installation of SCADA System in connection with Augmentation of Surface Water Based Piped Water Supply Scheme for Northern Sector Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 3447/ND | 23/07/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 732.35 | 0 | 0 | 15
4128 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09814 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | 616/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.71 | 0 | 0 | 0
4129 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09814 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer etc. for Augmentation to Accomodate FHTC at Pump House No.II (Zone-II) under Ber Ramchandrapur W/S Scheme, Block-Karimpur-I, District of Nadia. NIET No. 14 of EE/EMD of 2022-23 (Sl. No. -06) | 3943/EMD | 20/10/2022 | 30 | MAA TARA CONSTRUCTION | 8.2 | 8.04 | 100 | 70
4130 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09814 | Augmentation | Material Requisition To Resource Division | 1026/ND | 03/03/2022 | 0 | Resource Division | 2.13 | 0 | 0 | 0
4131 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09814 | Augmentation | Material Requisition To Resource Division | 1261/ND | 16/03/2022 | 0 | Resource Division | 1.44 | 0 | 0 | 0
4132 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09814 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. for Augmentation to Accomodate FHTC at Pump House No.I(Zone-II) under Berramchandrapur W/S Scheme, Block-Karimpur- 1,District of Nadia. NIET No.- 14 of EE/EMD of 2022-23 (Sl. No.- 05) | 3913/EMD | 19/10/2022 | 30 | C.M.S. ENGINEERING CONCERN. | 10.73 | 9.48 | 100 | 97
4133 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09814 | Augmentation | Providing FHTC by Augmentation under jal swapna for Ber Ramchandrapur Zone-II Water Supply scheme in Karimpur-I block of Nadia District under Nadia Division P.H.E. Dte. | 694/ND | 15/02/2022 | 90 | SUDHAMAY MAJUMDAR | 77.58 | 41.39 | 53.36 | 100
4134 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09814 | Augmentation | Additional work of Laying Distribution System and additional work of providing FHTC in connection with Augmentation of Ber Ramchandrapur Zone-II PWSS within Karimpur-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | 1763/ND | 12/03/2024 | 420 | MALI CONSTRUCTION | 38.98 | 0 | 0 | 80
4135 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09814 | Augmentation | Conversion of IEP to AIRP of capacity 30 Cu.m/hr at Ber Ramchandrapur Zone-II Water Supply Scheme within Karimpur-I block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. | 1909/ND | 15/03/2024 | 600 | ASIT PRAMANIK | 124.74 | 0 | 0 | 80
4136 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. , SM/09814 | Augmentation | Repairing Works (existing OHR, Pump House, Boundary wall etc.) for Ber Ramchandrapur Z-II Water Supply Scheme Under R.W.S. Nadia Sub-Division P.H.E. Dte. | 4579/ND | 21/08/2024 | 540 | MONDAL CONSTRUCTION | 22.28 | 0 | 0 | 80
4137 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Krishnagar water supply scheme under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07961 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Krishnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1071/NACD-II | 25/09/2020 | 15 | PAPAN ROY | 4.97 | 0 | 0 | 0
4138 | NADIA | Nadia Division | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. , SM/09573 | Augmentation | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. | 727/PFMS | 30/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.77 | 0 | 0 | 0
4139 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. , SM/09573 | Augmentation | Rejuenation of Kishorepur PWSS regarding FHTC in Karimpur II Block of Nadia Distric | 927/EMD | 27/05/2022 | 304 | ABHISEK ENGINEERING CONCERN | 16.28 | 16.28 | 100 | 100
4140 | NADIA | Nadia Division | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. , SM/09573 | Augmentation | Material Requisition To Resource Division | 1264/ND | 16/03/2022 | 0 | Resource Division | 2.3 | 0 | 0 | 0
4141 | NADIA | Nadia Division | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. , SM/09573 | Augmentation | Material Requisition To Resource Division | 3301/ND | 27/07/2022 | 0 | Resource Division | 9.25 | 0 | 0 | 0
4142 | NADIA | Nadia Division | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. , SM/09573 | Augmentation | Conversion of IEP to AIRP of capacity 60 Cu.m/hr at Kishorepur Water Supply Scheme within Karimpur-II Block block under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 4343/ND | 07/08/2024 | 180 | M/S R.K.ENTERPRISE | 129.29 | 0 | 0 | 0
4143 | NADIA | Nadia Division | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. , SM/09573 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Kishorepur water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | 7059/ND | 04/12/2024 | 90 | M/S CHANDIMATA CONSTRUCTION | 30.07 | 0 | 0 | 0
4144 | NADIA | Nadia Division | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. , SM/09573 | Augmentation | Name of Work: Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Kishorepur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 650/ND | 11/02/2022 | 1080 | MAHAVIR PUMPS MFG PVT. LTD. | 321.89 | 243.97 | 75.79 | 91
4145 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. , SM/09573 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under KISHOREPUR ground water based water supply scheme under Block_ KISHOREPUR Dist. - Nadia under EMD, PHE Dte. SM/09573 | 1115/EMD | 04/06/2025 | 90 | WIZARDTECH SOLUTION | 17.48 | 0 | 0 | 0
4146 | NADIA | Nadia Division | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. , SM/09573 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Kishorepur Ground Based Water Supply Scheme under Karimpur II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Kishorepur at Karimpur II Block by Augmentation of Ground Water based PWSS for Kishorepur Water Supply Schemes under Nadia Division, PHE Dte. | 7367/ND | 18/12/2024 | 120 | ROY ASSOCIATES | 24.03 | 0 | 0 | 0
4147 | NADIA | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-II Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District , SM/08132 | Retrofitting | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-II Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District | 292/PFMS | 08/10/2021 | 0 | JAGANNATH ENTERPRISE | 19.98 | 0 | 0 | 0
4148 | NADIA | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-II Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District , SM/08132 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | 2431/ND | 14/06/2021 | 60 | JAGANNATH ENTERPRISE | 33.43 | 8.56 | 100 | 0
4149 | NADIA | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-II Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District , SM/08132 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte."(PART- C) | 2957/ND | 27/07/2021 | 45 | CHOWDHURY & CO. | 8.82 | 7.41 | 100 | 100
4150 | NADIA | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-II Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District , SM/08132 | Retrofitting | Material Requisition To Resource Division | 100/ND | 06/01/2022 | 0 | Resource Division | 1.77 | 0 | 0 | 0
4151 | NADIA | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-II Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District , SM/08132 | Retrofitting | Material Requisition To Resource Division | 786/ND | 18/02/2022 | 0 | Resource Division | 1.08 | 0 | 0 | 0
4152 | NADIA | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-II Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District , SM/08132 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | 2154/ND | 21/05/2021 | 60 | SAKTI ENTERPRISE | 33.45 | 51.22 | 153.15 | 100
4153 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur Water Supply Scheme Part-II under Jal Jeevan Mission (JJM) at Santipur block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15553 | Augmentation | Road Restoration Work along PMGSY Road under Nrisinghapur Ground Water Supply Scheme at Santipur Block under Nadia Arsenic Division-I, PHE Dte. | 2595/NAD-I | 17/11/2023 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 48.14 | 22 | 100 | 100
4154 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur Water Supply Scheme Part-II under Jal Jeevan Mission (JJM) at Santipur block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15553 | Augmentation | Laying of pipeline including FHTC connections near Nirsinghapur Health Centre at Nirsinghapur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 03) | 248/AE-I/NAD-I | 20/09/2024 | 30 | TUHIN CONSTRUCTION | 0.96 | 0.96 | 100 | 100
4155 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur Water Supply Scheme Part-II under Jal Jeevan Mission (JJM) at Santipur block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15553 | Augmentation | Laying of pipeline at Nirsinghapur Utterpara including water connection at Nirsinghapur High School and allied works under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 02) | 247/AE-I/NAD-I | 20/09/2024 | 30 | TUHIN CONSTRUCTION | 0.97 | 0.93 | 100 | 100
4156 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur Water Supply Scheme Part-II under Jal Jeevan Mission (JJM) at Santipur block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15553 | Augmentation | Augmentation of AIRP capacity (216cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.09) | 1899/NAD-I | 14/08/2023 | 691 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 167.06 | 0 | 0 | 70
4157 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur Water Supply Scheme Part-II under Jal Jeevan Mission (JJM) at Santipur block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15553 | Augmentation | Providing Boundary Illumination with allied works at Nrisinghapur Part-II under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15553) | 1158/EMD | 04/06/2025 | 90 | S M ELECTRICALS | 4.34 | 0 | 0 | 0
4158 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHISHNENGRA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15540 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accomodate FHTC under MAHISNENGRA (Zone-I) W/S Scheme, Block- Krishnagar-1 , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 16) | 416/EMDdt.20.01.23 | 17/02/2023 | 30 | GOENKA ENTERPRISE | 14.03 | 12.85 | 100 | 90
4159 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHISHNENGRA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15540 | Augmentation | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Krishnagar-I Block, under Ranaghat Sub-Division, PHE Dte. | 1268/ND | 23/03/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 47.83 | 8.77 | 100 | 45
4160 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHISHNENGRA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15540 | Augmentation | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | 6290/ND | 26/09/2024 | 45 | IMAGIN | 19.44 | 0 | 0 | 100
4161 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGULA ZONE-II (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15541 | Augmentation | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | 1272/ND | 23/03/2023 | 60 | AUXILIARY TUBEWELL DRILLERS | 48.99 | 0 | 0 | 66
4162 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Mamjoani Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Mamjoani Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08859 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Mamjoani Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Mamjoani Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 53/NAD-I | 11/01/2022 | 90 | TIRUPATI ENTERPRISES | 163.2 | 155.42 | 100 | 100
4163 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Mamjoani Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Mamjoani Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08859 | Retrofitting | Retrofitting work at Mamjoani (Part-I) W/S Scheme within Hanskhali Block under Nadia Arsenic Division-I,P.H.E. Dte. | 225/AE-II/NAD-I | 07/12/2022 | 15 | PURNIMA ELECTRICS & DECORATORS | 2.59 | 2.58 | 100 | 100
4164 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Mamjoani Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Mamjoani Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08859 | Retrofitting | Construction and installation of MANIFOLD and allied works at OHR site of Joypur and Mamjoani Water Supply Scheme in connection with Duttaphulia Zone-I under Nadia Arsenic Division-I, PHE Dte. as a part of JJM (Sl. No. 01) | 39/NAD-I | 07/04/2025 | 242 | REAL TIME | 39.28 | 0 | 0 | 50
4165 | NADIA | Central Drilling | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) , SM/16182 | New | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Char Brahmanagar W/S Scheme (TW-III) , Krishnagar-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 1657/CDD | 17/10/2023 | 30 | SNEHASISH GHOSH | 16.33 | 0 | 0 | 0
4166 | NADIA | Nadia Division | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) , SM/16182 | New | Material Requisition To Resource Division | 128/ND | 05/01/2023 | 0 | Resource Division | 119.68 | 0 | 0 | 0
4167 | NADIA | Nadia Division | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) , SM/16182 | New | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 1.4 | 98.71 | 40
4168 | NADIA | Eastern Mechanical | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) , SM/16182 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation NEW Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II and III under Char Brahmanagar ground water based water supply scheme under Block_ Nabadwip Dist. - Nadia under EMD, PHE Dte. (SM/16182) | 2677/EMD | 20/11/2024 | 30 | HINDUSTAN ENGINEERING CORPORATION(E & M) | 36.01 | 0 | 0 | 0
4169 | NADIA | Central Drilling | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) , SM/16182 | New | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Char Brahmanagar W/S Scheme (TW-I) ,Krishnagar-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 1655/CDD | 17/10/2023 | 289 | GENUINE | 16.88 | 3.43 | 20.94 | 100
4170 | NADIA | Nadia Division | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) , SM/16182 | New | Material Requisition To Resource Division | 262/ND | 11/01/2024 | 0 | Resource Division | 25.02 | 0 | 0 | 0
4171 | NADIA | Nadia Division | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) , SM/16182 | New | Material Requisition To Resource Division | 3315/ND | 11/06/2024 | 0 | Resource Division | 20.41 | 0 | 0 | 0
4172 | NADIA | Eastern Mechanical | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) , SM/16182 | New | Quotation for new service connection for Char Bramhanagar Ph-2, under Nabadwip block, District-Nadia | BP-203-24-25 | 17/12/2024 | 0 | WBSEDCL SWARUPGANJ C.C.C. | 9.86 | 0 | 0 | 0
4173 | NADIA | Eastern Mechanical | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) , SM/16182 | New | Quotation for new service connection for Char Bramhanagar Ph-1, under Nabadwip block, District-Nadia | BP-202-24-25 | 17/12/2024 | 0 | WBSEDCL SWARUPGANJ C.C.C. | 12.62 | 0 | 0 | 0
4174 | NADIA | Nadia Division | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) , SM/16182 | New | Laying of Distribution System including specials & valves, Laying of proposed Rising Main, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC/20mm OD HDPE pipe with all necessary specials, Soil investigation for construction of one No. 600 Cum OHR, Construction of R.C.C. Elevated Reservoir of 600 Cum capacity(including pile foundation), Construction of Pump House at Proposed H/W, 2nd T/W and 3rd Tube Well site, Construction of boundary wall with gate at Proposed H/W, 2nd T/W and 3rd Tube Well site at Char Brahmanagar within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 3448/ND | 09/08/2023 | 876 | H I ENTERPRISE, VILL&P.O- DHALTITHA, P.S. BASIRHAT, NORTH 24 PARGANAS, PIN-743412(WB) | 634.32 | 246.58 | 38.87 | 30
4175 | NADIA | Nadia Division | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) , SM/16182 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 120 m3/hr at Char Brahmanagar Water Supply Scheme within Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | 4521/ND | 20/08/2024 | 360 | MONDAL PRECISION PRIVATE LIMITED | 296.98 | 0 | 0 | 0
4176 | NADIA | Nadia Division | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) , SM/16182 | New | Construction Of Approach Road To The Headwork Site With Pilling Work, Land Development Of Head Worksite, Restoration Of Concrete Roads And Allied Works Of Char Brahmanagar Water Supply Scheme Under Krishnagar Subdivision Under Nadia Division PHED. | 6625/ND | 25/10/2024 | 150 | H I ENTERPRISE | 74.95 | 0 | 0 | 50
4177 | NADIA | Nadia Division | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) , SM/16182 | New | Additional Laying of UPVC Pipeline for providing leftout FHTC including supplying, laying, fitting, fixing with all necessary specials, saddle piece etc. all complete for Ground Based piped water supply scheme in Char Majhdia Char Brahmanagar to accommodate FHTC within Nabadwip block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | 3072/ND | 01/07/2025 | 90 | H I ENTERPRISE | 90.88 | 0 | 0 | 40
4178 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Itaberia Water Supply Scheme In Hanskhali Block District Nadia. , SM/16359 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4179 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Jaypur Water Supply Scheme In Hanskhali Block District Nadia. , SM/16360 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4180 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Badkulla Water Supply Scheme (Zone-I & II) In Hanskhali Block District Nadia. , SM/16364 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4181 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bankar Dhopadi Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District , SM/08131 | Retrofitting | PROVIDING FHTC ..FROM PASILA W/S SCHEME , PHASE-1 | 472/PFMS | 02/02/2022 | 0 | SANJIB DEY | 70.26 | 0 | 0 | 0
4182 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bankar Dhopadi Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District , SM/08131 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Bankar Dhopadi W/S scheme in Nadia District under Nadia Division P.H.E. Dte." (Phase-I, Retrofitting) | 2993/ND | 29/07/2021 | 90 | SANJIB DEY | 80.08 | 3.93 | 100 | 100
4183 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bankar Dhopadi Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District , SM/08131 | Retrofitting | Material Requisition To Resource Division | 788/ND | 18/02/2022 | 0 | Resource Division | 0.8 | 0 | 0 | 0
4184 | NADIA | Nadia Division | Providing Functional House Tap Connection from Bankar Dhopadi Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District , SM/08131 | Retrofitting | Material Requisition To Resource Division | 791/ND | 18/02/2022 | 0 | Resource Division | 1.12 | 0 | 0 | 0
4185 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Bara Naldaha Water Supply Scheme in Tehatta-II Block, Dist.-Nadia. , SM/16342 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4186 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Ber Ramchandrapur (Zone-I & Zone-II) Water Supply Scheme in Karimpur-I Block of District Nadia , SM/16794 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4187 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Madhugari Water Supply Scheme in Karimpur-I Block of District Nadia , SM/16797 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4188 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Muktadaha (Zone - I & Zone - II) Water Supply Scheme in Karimpur-I Block of District Nadia , SM/16798 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4189 | NADIA | Nadia Arsenic Civil Division II | Mini Piped Water Supply Scheme at Dharammpur (Part-B) village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. , SM/16101 | New | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Dharammpur (Part-B) of Tehatta-II Block under Nadia Arsenic Civil Division-II PHE Dte. | 584/NACD_II | 17/05/2023 | 990 | PAPAN ROY | 26.96 | 0 | 0 | 0
4190 | NADIA | Eastern Mechanical | Mini Piped Water Supply Scheme at Dharammpur (Part-B) village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. , SM/16101 | New | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 0 | 80
4191 | NADIA | Nadia Arsenic Civil Division II | Mini Piped Water Supply Scheme at Labangola village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. , SM/16105 | New | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Labangola of Tehatta- II Block under Nadia Arsenic Civil Division-II PHE Dte | 565/NACD_II | 11/05/2023 | 90 | BIPLAB GUHA | 28.05 | 5.6 | 19.98 | 81
4192 | NADIA | Nadia Arsenic Civil Division II | Mini Piped Water Supply Scheme at Labangola village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. , SM/16105 | New | Providing 1 no. Guard at Labongola Mini Public Water Supply Scheme in Tehatta-II Block for guarding of various Departmental materials under Nadia Arsenic Civil Division-II,P.H.E. Dte.[Period of work :01/07/2024 to 31/10/2024] | 787/AE-I/NACD-II | 01/07/2024 | 123 | ZOOM CONSTRUCTION & INTERIO | 0.91 | 0 | 0 | 0
4193 | NADIA | Eastern Mechanical | Mini Piped Water Supply Scheme at Labangola village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. , SM/16105 | New | Quotation for new Service connection charges and security deposit for Labangola PWSS | BP-201-24-25 | 17/12/2024 | 0 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 0.1 | 0 | 0 | 0
4194 | NADIA | Eastern Mechanical | Mini Piped Water Supply Scheme at Labangola village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. , SM/16105 | New | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 0 | 80
4195 | NADIA | Eastern Mechanical | Mini Piped Water Supply Scheme at Chak Ramnagar village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II, , SM/16106 | New | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 0 | 80
4196 | NADIA | Nadia Arsenic Civil Division II | Mini Piped Water Supply Scheme at Chak Ramnagar village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II, , SM/16106 | New | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Chak Ramnagar of Tehatta-II Block under Nadia Arsenic Civil Division-II PHE Dte | 566/NACD_II | 11/05/2023 | 801 | BIDYUT KUMAR | 28.38 | 0 | 0 | 70
4197 | NADIA | Eastern Mechanical | Mini Piped Water Supply Scheme at Jaba(Part-A) village, Block- Krishnagar-I, Nadia District, under Nadia Arsenic Civil Division-II. , SM/16107 | New | Quotation for new service connection and security deposit for Java (part- A), Krishnanagar- I | BP-106-24-25 | 09/09/2024 | 0 | W.B.S.E.D.C.L (GROUP KRISHNAGAR ROAD STATION C.C.C) | 0.1 | 0 | 0 | 0
4198 | NADIA | Nadia Arsenic Civil Division II | Mini Piped Water Supply Scheme at Jaba(Part-A) village, Block- Krishnagar-I, Nadia District, under Nadia Arsenic Civil Division-II. , SM/16107 | New | Sinking of Tube well, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Jaba (Part-A) of Krishnagar-I Block under Nadia Arsenic Civil Division-II PHE Dte | 345/NACD-II | 21/03/2023 | 821 | M/S FREEDOM CONSTRUCTION | 29.83 | 23.63 | 79.2 | 60
4199 | NADIA | Eastern Mechanical | Mini Piped Water Supply Scheme at Jaba(Part-A) village, Block- Krishnagar-I, Nadia District, under Nadia Arsenic Civil Division-II. , SM/16107 | New | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 0 | 80
4200 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-IV within Nakashipara Block.(Phase-D) , SM/08670 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-IV within Nakashipara Block.(Phase-D) | 582/PFMS | 04/03/2022 | 0 | SHYAMAL SHIL | 8.22 | 0 | 0 | 0
4201 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-IV within Nakashipara Block.(Phase-D) , SM/08670 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-II, Zone-IV within Nakashipara Block (Phase-D) | 5181/ND | 20/09/2021 | 90 | SHYAMAL SHIL | 89.79 | 85.01 | 94.68 | 0
4202 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-IV within Nakashipara Block.(Phase-D) , SM/08670 | Retrofitting | Material Requisition To Resource Division | 809/ND | 18/02/2022 | 0 | Resource Division | 12.23 | 0 | 0 | 0
4203 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Itla Water Supply Scheme in Krishnagar-I Block, Dist.- Nadia. , SM/16830 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4204 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Teinpur (Zone - I to IV) Water Supply Scheme in Karimpur-II Block of District Nadia , SM/16809 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4205 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Andharkota Water Supply Scheme in Karimpur-I Block of District Nadia , SM/16791 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4206 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KULGACHHI (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17232 | Augmentation | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at KULGACHI (Phase-II) Piped Water Supply Scheme, Block: Krishnagar-I, Dist. Nadia Under EMD, PHE Dte. | 6364/EMD | 17/10/2023 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 49.3 | 0 | 0 | 0
4207 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KULGACHHI (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17232 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No. I and II under Kulgachi WS Scheme, Block KrishnagarI, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-09) | 158EMD,Dt.06.01.23 | 27/03/2023 | 30 | ABHISEK ENGINEERING CONCERN | 15.5 | 1.31 | 100 | 100
4208 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KULGACHHI (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17232 | Augmentation | Supplementary works to completion of ongoing FHTC-related work under Kulgachi W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | 956/EMSD-II | 26/12/2023 | 10 | ABHISEK ENGINEERING CONCERN | 0.69 | 0.69 | 100 | 100
4209 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KULGACHHI (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17232 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 67 Cu.m/hr at Head Work Site at Kulgachi PWSS under Nadia Division PHE Dte. | 1599/ND | 10/04/2023 | 721 | B.M. ENGINEERING & CONSTRUCTION | 72.07 | 0.65 | 3.58 | 100
4210 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GHORALIA ZONE-I (PHASE-II) IN SANTIPUR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17218 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under GHORALIA(Zone-1) W/S Scheme, Block- Shantipur , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 12) | 414/EMDdt.20.01.23 | 17/03/2023 | 30 | D.S. ENTERPRISE | 5.99 | 5.77 | 100 | 100
4211 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GHORALIA ZONE-I (PHASE-II) IN SANTIPUR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17218 | Augmentation | Renovation of AIRP (Pressure Type) of capacity 95 Cu.m/hr at Head Work Site at GHORALIA ZONE- I PWSS under Nadia Division PHE Dte. | 1804 / ND | 24/04/2023 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 49.9 | 38.79 | 88.72 | 78
4212 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GHORALIA ZONE-I (PHASE-II) IN SANTIPUR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17218 | Augmentation | Supply Delivery and installation of Changeover switch and Electrical wiring and other allied works at Ghoralia (Z-I) P/H- I W/S Scheme in the District of Nadia, Under EMSD-II PHE Dte. | 983/EMSD-II | 27/12/2023 | 10 | D.S. ENTERPRISE | 0.6 | 0.6 | 100 | 100
4213 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANKAR DHOPADI IN NABADWIP BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17219 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 29 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Bankar Dhopadi PWSS under Nadia Division PHE Dte. | 2994/ND | 13/07/2023 | 90 | TARUN KUMAR BHATTACHARYA | 70.11 | 0 | 0 | 0
4214 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANKAR DHOPADI IN NABADWIP BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17219 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BANKER DHOPADI W/S Scheme, Block- Nabadwip , Dist. - Nadia. NIET NO. 28 OF EE/EMD OF 2022-23 (SL. NO. 02) | 813/EMDdt.16.02.2023 | 16/03/2023 | 30 | UTTAM KUMAR CHATTERJEE | 14.15 | 12.98 | 100 | 100
4215 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANKAR DHOPADI IN NABADWIP BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17219 | Augmentation | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at Bankar Dhopadi Piped Water Supply Scheme Block_ Nabadwip Dist. - Nadia under EMD, PHE Dte. | 6373/EMD | 17/10/2023 | 532 | AHALYA ENGINEERING WORKS | 42.1 | 0 | 0 | 0
4216 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Fazilnagar PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17202 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer etc. rejuvenation to Accommodate FHTC at Pump House No.- II under Fazilnagar W/S Scheme,, Block-Karimpur-II, Dist. - Nadia. NIET No.- 18 of EE/EMD of 2022-23 (Sl. No.- 09) | 6273/EMD | 18/11/2022 | 30 | SRI KRISHNA NIRMAN | 5.85 | 5.85 | 100 | 0
4217 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Fazilnagar PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17202 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer etc. rejuvenation to Accomodate FHTC at Pump House No.- III under Fazilnagar W/S Scheme, Block-Karimpur-II, Dist. - Nadia. NIET No.- 18 of EEW/EMD of 2022-23 (Sl. No.- 10) | 6274/EMD | 18/11/2022 | 30 | ASHOKE ADHIKARY | 8.74 | 8.74 | 100 | 0
4218 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Fazilnagar PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17202 | Augmentation | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at Fazilnagar (Phase-II) Piped Water Supply Scheme Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. | 6370/EMD | 17/10/2023 | 30 | R.N.S. TRADING | 53.72 | 0 | 0 | 0
4219 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Fazilnagar PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17202 | Augmentation | Augmentation of FHTC (Part-B) of Fazilnagar Pipe Water Supply Scheme. | 4903/ND | 10/09/2024 | 60 | PATHIK PABAN NANDI | 34.31 | 0 | 0 | 0
4220 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Fazilnagar PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17202 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No.- I under Fazilnagar W/S Scheme, Block-Karimpur-II, Dist. - Nadia. NIET No.- 18 of EE/EMD of 2022-23 (Sl. No.- 08) | 6189/EMDdt.14-11.2022 | 16/03/2023 | 30 | GHOSE ENGINEERING SYNDICATE | 13.61 | 12.91 | 100 | 100
4221 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Fazilnagar PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17202 | Augmentation | Proposed Augmentation of Laying Rising Main System and Sinking of Replacement Tube Well at Head Work Site & 2nd Tube Well Site of Fazil Nagar [Phase-II] Ground Based Piped Water Supply Scheme. | 1248/ND | 22/03/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 29.32 | 21.23 | 100 | 70
4222 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Fazilnagar PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17202 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 117 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Fazilnagar PWSS under Nadia Division PHE Dte. | 1787/ND | 20/04/2023 | 886 | B.M. ENGINEERING & CONSTRUCTION | 118.29 | 0 | 0 | 30
4223 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr , SM/09958 | Augmentation | Construction of Boundary Wall, Toilet, Pathway and other allied work at Dhantala W/S Scheme within Ranaghat -II Block under Nadia Arsenic Division -I, P.H.E.Dte. ( Sl.no. 02) | 1582 /NAD-I | 06/09/2022 | 45 | GHOSH CONSTRUCTION | 24.96 | 20.22 | 100 | 100
4224 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr , SM/09958 | Augmentation | Repair of 550 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House and AIRP at Dhantala WS Scheme atRanaghat II Block under NAD I PHE Dte(sl.no.02) | 3037/NAD-I | 09/11/2022 | 45 | TAPU SAHA | 25.33 | 25.28 | 100 | 100
4225 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr , SM/09958 | Augmentation | Construction of Boundary Wall Toilet Pathway and other allied work at Sabdalpur W S Scheme within Ranaghat II Block under NAD I PHE Dte. (sl.no.04) | 3034/NAD-I | 09/11/2022 | 45 | M/S LAXMI ENTERPRISE | 12.78 | 9.05 | 100 | 100
4226 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr , SM/09958 | Augmentation | Repair of 350 cum capacity Over Head Reservoir Painting and repairing of H W Boundary Wall Pump House and AIRP at Sabdalpur W/S Scheme at Ranaghat-II Block under Nadia Arsenic Division-I P.H.E Dte (Sl.No.03) | 3045/NAD-I | 09/11/2022 | 45 | MONDAL CONSTRUCTION | 31.43 | 26.84 | 100 | 100
4227 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr , SM/09958 | Augmentation | Retrofitting Work for Provoiding FHTC at Bholadanga under Jal Jeevan Mission (JJM) at Ranaghat-II Block under Ground Water based PWSS for Sabdalpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1198/NAD-I | 01/08/2024 | 60 | M/S K..M. ENTERPRISE | 9.49 | 0 | 0 | 0
4228 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr , SM/09958 | Augmentation | Phase-II FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dhantala at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (sl.no.01) | 963 / NAD-I | 07/07/2022 | 60 | M/S K.P. CONSTRUCTION | 75.57 | 65.61 | 100 | 60
4229 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr , SM/09958 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Sabdalpur Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Sabdalpur W/S Scheme under JJM (SL.NO.03) | 1115 / NAD-I | 27/04/2023 | 15 | ASIT PRAMANIK | 13.01 | 12.31 | 100 | 100
4230 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr , SM/09958 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Dhantala Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Dhantala W/S Scheme under JJM. (Sl.no.02) | 1688/NAD-I | 12/07/2023 | 15 | SANJIB DEY | 13.04 | 12.45 | 100 | 100
4231 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr , SM/09958 | Augmentation | Augmentation of AIRP for Ground Water Based Piped Water Supply Scheme for Dhantala (125 Cum) under Jal Jeevan Mission at Ranaghat-II Block, under Nadia Arsenic Division -I, PHE Dte. | 2779/NAD-I | 18/12/2023 | 21 | APURBA MANDAL | 10.62 | 10.1 | 100 | 100
4232 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr , SM/09958 | Augmentation | Pipeline connection from Manifold to Distribution Main (Left Part) and Rejoining with Existing Distribution Line (Right Part) under Jal Jeevan Mission (JJM) at Ranaghat-II Block under Ground Water Based PWSS for Sabdalpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1197/NAD-I | 01/08/2024 | 60 | MANAJIT BISWAS | 9.81 | 9.46 | 100 | 100
4233 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr , SM/09958 | Augmentation | Phase-II FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Sabdalpur, at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Sabdalpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (sl.no. 04) | 966 / NAD-I | 07/07/2022 | 1998 | M/S K.P. CONSTRUCTION | 65.89 | 46.32 | 70.29 | 70
4234 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr , SM/09958 | Augmentation | Laying dedicated pipeline to supply water for Sabdalpur and Hosenpur under Jal Jeevan Mission (JJM) at Ranaghat-II Block of Sabdalpur Ground Water Based PWSS for under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 07) | 133/NAD-I | 22/04/2025 | 60 | MANISHIKA CONSTRUCTION | 52.42 | 0 | 0 | 0
4235 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGULA ZONE-I (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17688 | Augmentation | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | 1272/ND | 23/03/2023 | 60 | AUXILIARY TUBEWELL DRILLERS | 48.99 | 27.06 | 82.85 | 66
4236 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGULA ZONE-I (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17688 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, Zone-I(Phase-II) under Bagula ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. | 6398/EMD | 30/10/2023 | 30 | A.K. ENTERPRISE | 12.6 | 11.73 | 100 | 100
4237 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Helenchi(Zone-I,II & III) Water Supply Scheme in Krishnaganj Block, Dist.-Nadia. , SM/18070 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4238 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Chapra Bangalji Water Supply Scheme in Chapra Block, Dist.-Nadia. , SM/18052 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4239 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Mahatpur Water Supply Scheme in Chapra Block, Dist.-Nadia. , SM/18057 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4240 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Water Supply Scheme for Boalia Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15544 | Augmentation | Construction and installation of MANIFOLD including UPVC pipeline and allied works at OHR site under Boalia Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Schemes under Nadia Arsenic Division-I, PHE Dte. " | 2745/NAD-I | 08/12/2023 | 445 | MS MAA BHABANI ENTERPRISE | 20.18 | 5.31 | 20.94 | 100
4241 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Water Supply Scheme for Boalia Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15544 | Augmentation | Augmentation of AIRP capacity (123cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Boalia, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.03) | 1898/NAD-I | 14/08/2023 | 748 | M/S R.K. ENTERPRISE | 170.25 | 0 | 0 | 75
4242 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Water Supply Scheme for Boalia Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15544 | Augmentation | Providing Boundary Illumination with allied works at Boalia Part-IV under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15544) | 1162/EMD | 04/06/2025 | 90 | BIJAN ENTERPRISE | 4.33 | 0 | 0 | 0
4243 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Water Supply Scheme for Boalia Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15544 | Augmentation | Providing Boundary Illumination with allied works at Gayeshpur Zone II Part-IV under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15544) | 1166/EMD | 04/06/2025 | 90 | TALUKDER & CO. | 4.34 | 0 | 0 | 0
4244 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
4245 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
4246 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  | 21/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
4247 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Sikra 2nd Tubwell site within Sikra Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 121/NACD-II | 11/01/2023 | 60 | ASHIM ENTERPRISE | 4.9 | 4.69 | 95.62 | 85
4248 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Sikra Water Supply Scheme at Head Work Site site under Nadia Arsenic Civil Division-II PHE Dte. | 83/NACD-II | 10/01/2023 | 60 | SANDIP KUMAR NEOGI | 14.39 | 14.33 | 99.59 | 85
4249 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Construction for priliminary work of the approch road at Head Works site of Sikra Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | 407/AE-I/NACD-II | 08/08/2023 | 15 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 0.85 | 0 | 0 | 0
4250 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Construction of approch road at Head Works site of Panchdara Abhaynagar Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | 468./AE-I/NACD-II | 03/10/2023 | 15 | AMIT KUMAR BOSE | 0.97 | 0 | 0 | 0
4251 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Sikra water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia | 21/AE-I/NACD-II | 13/04/2022 | 60 | BIPLAB GUHA | 2.83 | 2.81 | 100 | 100
4252 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Sikra water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 206/NACD-II | 05/04/2022 | 60 | BIPLAB GUHA | 5.38 | 5.33 | 100 | 100
4253 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Madhupur and Sikra Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 245/NACD-II | 19/04/2022 | 60 | JOY HIND TUBEWELLS | 41.88 | 0 | 0 | 100
4254 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Sikra Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 623/NACD-II | 06/09/2022 | 20 | MAKALI ENGINEERING CORPORATION | 3.9 | 3.9 | 100 | 100
4255 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS: Sikra) | 863/NACD-II | 10/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
4256 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Material Requisition To Resource Division | 406/NACD-II | 04/07/2022 | 0 | Resource Division | 32.18 | 0 | 0 | 0
4257 | NADIA | Eastern Mechanical | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Electricity bill for new service connection at Shikra under EMSD-III | 150/PFMS/EMD | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.81 | 0 | 0 | 0
4258 | NADIA | Eastern Mechanical | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Electricity bill for new service connection at Shikra W/S Scheme | 149/PFMS/EMD | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.26 | 0 | 0 | 0
4259 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Laying of Rising Main of Sikra Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | 28/AE-I/NACD-II | 13/04/2022 | 60 | SAHA ENGINEERS | 3.93 | 3.4 | 100 | 100
4260 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Sikra and adjoining mouzas under Sikra Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | 360/NACD-II | 15/06/2022 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 231.09 | 183.34 | 100 | 90
4261 | NADIA | Eastern Mechanical | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Sikra W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 10) | 5018/EMD | 03/11/2022 | 30 | M/S DILIP MITRA | 10.12 | 10.06 | 100 | 100
4262 | NADIA | Eastern Mechanical | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Headworks) under Sikra W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 09) | 5017/EMD | 03/11/2022 | 30 | S.P. ENTERPRISE | 10.12 | 10.05 | 100 | 100
4263 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Sikra) | 434/NACD-II | 15/03/2024 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
4264 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Sikra water supply scheme of Chapra Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | 395/NACD-II | 28/03/2023 | 1097 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 119.11 | 35.57 | 29.86 | 85
4265 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Construction and installation of MANIFOLD and allied works at OHR site under Bagberia Piped Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1582/NACD-II | 11/12/2024 | 270 | SANDIP BISWAS | 111.44 | 0 | 0 | 75
4266 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 45 cum/Hour capacity for Sikra Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1030/NACD-II | 02/08/2024 | 360 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 176.18 | 0 | 0 | 70
4267 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 45 cum/Hour capacity for Hatkhola Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1152/NACD-II | 27/08/2024 | 540 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 176.21 | 0 | 0 | 66
4268 | NADIA | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME , SM/10410 | New | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Fatepur, Bahadurpur and Gongra Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1657/NACD-II | 30/12/2024 | 360 | CHANDAN ROY | 149.25 | 0 | 0 | 20
4269 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-II to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte , SM/11547 | Augmentation | Material Requisition To Resource Division | 4932/ND | 25/11/2022 | 0 | Resource Division | 38.64 | 0 | 0 | 0
4270 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-II to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte , SM/11547 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Naserkhuli W/S Scheme (Z- II, T/W-II),Ranaghat-II Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 511/CDD | 01/06/2023 | 30 | UTTAM KUMAR CHATTERJEE | 18.88 | 0 | 0 | 0
4271 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-II to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte , SM/11547 | Augmentation | Material Requisition To Resource Division | 4326/ND | 29/09/2022 | 0 | Resource Division | 18.4 | 0 | 0 | 0
4272 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-II to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte , SM/11547 | Augmentation | Material Requisition To Resource Division | 2284/ND | 29/05/2023 | 0 | Resource Division | 18.4 | 0 | 0 | 0
4273 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-II to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte , SM/11547 | Augmentation | SHIFTING OF LT OH POLE AT NASERKHULI Z-II HEAD WORK SITE PWSS | 242/PFMS | 13/09/2024 | 0 | WBSEDCL RANAGHAT (EAST) CCC | 0.53 | 0 | 0 | 0
4274 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-II to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte , SM/11547 | Augmentation | Laying of distribution system including specials, valves & pipe supporting structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of ground based water supply scheme at Naserkhuli Zone-II to accommodate FHTC within Ranaghat-II Dev. Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. (sm/11547) | 4382/ND | 13/10/2022 | 880 | M/S GHOSH CONSTRUCTION | 332.64 | 313.69 | 94.3 | 96
4275 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-II to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte , SM/11547 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
4276 | NADIA | Nadia Division | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte , SM/09817 | Augmentation | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte | 726/PFMS | 30/03/2022 | 0 | HORIZEN | 2.47 | 0 | 0 | 0
4277 | NADIA | Nadia Division | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte , SM/09817 | Augmentation | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 mtr , Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Hudachapra Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.E. Dte. | 1288/ND | 17/03/2022 | 60 | USHA CONSTRUCTION | 59.49 | 53.62 | 100 | 95
4278 | NADIA | Nadia Division | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte , SM/09817 | Augmentation | Providing Left-out Functional Household tap Connection including supply of 15mm dia PVC pipe of average length of 15 mtr along with laying of different dia UPVC pipe and other allied works etc. all complete for augmentation of Huda Chapra W/S Scheme under Ranaghat Sub-Division of Nadia Division P.H. Engineering Dte. | 924/RSD | 14/09/2023 | 30 | USHA CONSTRUCTION | 4.95 | 4.89 | 100 | 100
4279 | NADIA | Nadia Division | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte , SM/09817 | Augmentation | Material Requisition To Resource Division | 4285/ND | 29/09/2022 | 0 | Resource Division | 0.52 | 0 | 0 | 0
4280 | NADIA | Nadia Division | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte , SM/09817 | Augmentation | Material Requisition To Resource Division | 1868/ND | 26/04/2023 | 0 | Resource Division | 19.29 | 0 | 0 | 0
4281 | NADIA | Nadia Division | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte , SM/09817 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 30 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Hudachapra to accommodate FHTC within Hanskhali block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | 4282/ND | 05/08/2024 | 180 | MANGES INDUSTRIAL CORPORATION | 160.4 | 0 | 0 | 0
4282 | NADIA | Nadia Division | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte , SM/09817 | Augmentation | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 19.16 | 100 | 81
4283 | NADIA | Eastern Mechanical | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte , SM/09817 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under HUDA CHAPRA ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. SM/09817 | 1116/EMD | 04/06/2025 | 90 | P.K. ENTERPRISE | 17.48 | 0 | 0 | 0
4284 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Retrofitting work at Radhakantapur Mouza at Ranaghat-I Block by augmentation of Ground Water based PWSS of Radhakantapur water supply scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 02) | 2053/NAD-I | 21/10/2022 | 45 | M/S DIPAK ENTERPRISE | 61.28 | 60.47 | 100 | 100
4285 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Water Supply Arrangement in High School, PrimarySchool, SSK & MSK under Jal Jeevan Mission (JJM) atRanaghat-I Block underRdahakantapur PWSS underAugmentation of Ground Water Based Water SupplyScheme of Tarapur, Kalaighata, Radhakantapur, Praniamatpur & Birnagar Part-III at Ranaghat-I Block (sl.06) | 204 /NAD-I | 15/02/2023 | 21 | SATYABRATA CHAKRABORTY | 33.07 | 0 | 0 | 35
4286 | NADIA | Central Drilling | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 300 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR TARAPUR W/S SCHEME, RANAGHAT-I BLOCK UNDER NADIA DISTRICT, CDD, PHE DTE. | 1825/CDD | 06/01/2023 | 30 | M/S SAIKAT ENTERPRISE | 15.55 | 10.29 | 66.19 | 0
4287 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Retrofitting works at Paharpur Mouza at Ranaghat-I Block by augmentation of Ground Water Based PWSS of Radhakantapur W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) | 3038/NAD-I | 09/11/2022 | 45 | BISWAS CONSTRUCTION | 9.17 | 9.17 | 100 | 100
4288 | NADIA | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under RADHAKANTAPUR W/S Scheme, Block-RanaghatII , Dist. - Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No. - 06) | 1605/EMD | 26/04/2023 | 30 | SWAPAN KUMAR BHANJA | 19.21 | 18.95 | 100 | 100
4289 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Jackpushing of pipeline at Sahidpally and different Augmentation work of Radhakantapur, Part-III under Jal Jeevan Mission (JJM) at Ranaghat-I Block by Augmentation of Ground Water Based Piped Water Supply Scheme for Radhakantapur W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte (Sl.n.08) | 2119/NAD-I | 04/09/2023 | 21 | M/S DIPAK ENTERPRISE | 65.68 | 65.66 | 100 | 100
4290 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Jackpushing of pipeline between Majherchar and Sahidpally and different Augmentation works of Tarapur and Kalaighata Part-III under Jal Jeevan Mission (JJM) at Ranaghat-I Block by augmentation of Ground Water based PWSS for Tarapur & Kalaighata under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.13) | 2122/NAD-I | 04/09/2023 | 21 | M/S DIPAK ENTERPRISE | 96.43 | 96.43 | 100 | 100
4291 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Shifting and Laying of Pipeline under Jal Jeevan Mission (JJM) for Ganguly Para, Chatterjee Para and Augmentation works of Parniamatpur by Augmentation of Ground Water based PWSS for Parniamatpur Water Supply Scheme, Part-III under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.07) | 2116/NAD-I | 04/09/2023 | 21 | BUDDHADEV MONDAL | 17.56 | 17.54 | 100 | 100
4292 | NADIA | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HALALPUR KRISHNAPUR(Z-I), PAR-NIAMATPUR W/S Scheme, Block- Ranaghat-II , Dist. - Nadia NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 02) | 1602/EMD | 26/04/2023 | 30 | PADMA ENGINEERING CO. | 38.83 | 31.03 | 79.9 | 50
4293 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Par Niamatpur Ground Based Water Supply Scheme under Ranaghat-I under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Parniamatpur Part-III Piped W/S Scheme (Sl.no.26) | 1450/NAD-I | 26/05/2023 | 15 | SAORSA | 13.01 | 12.48 | 100 | 100
4294 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Radhakantapur Ground Based Water Supply Scheme under Ranaghat-I under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Radhakantapur Part-III Piped W/S Scheme (Sl.no.25) | 1689/NAD-I | 12/07/2023 | 15 | KESHOB ENTERPRISE | 13.04 | 11.73 | 100 | 100
4295 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur, Birnagar Part-III at Ranaghat-I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakantapur, Parniamatpur, Birnagar Water Supply Scheme, Repair of 250 cum capacity Over Head Reservoir and other allied works at Tarapur water supply scheme. Repair of Pump House & other units of AIRP and other allied works at Kalaighata water supply scheme Construction of Boundary wall, Toilet, Pathway and other allied work at Kalaighata Water supply Scheme, Repair of Pump House and construction of Boundary Wall and other allied works at Radhakantapur water supply scheme, Repair of Over Head Reservoir and other allied works at Radhakantapur water supply scheme, Construction of Boundary wall, Toilet, Pathway andother allied work at Parniamatpur Water supply Scheme, Repair of 250 cum capacity Over Head Reservoir and other allied works at Parniamatpur water supply scheme, Repairing,Painting of Boundary wall,Toilet,Pathway and other allied works at Birnagar water supply scheme, Repair of 250 cum capacity Over Head Reservoir, Painting and repairing of H/W Boudary wall, Pump House and AIRP at Birnagar water supply scheme, under Nadia Arsenic Division-I, PHEDte. (Sl.no.02) | 1698/NAD-I | 13/07/2023 | 365 | M/S DIPAK ENTERPRISE | 481.09 | 478.14 | 100 | 100
4296 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Laying of UPVC pipeline and other allied works near House of Richa Master at Uttarpara Tarapur Mouza by retrofitting of Ground Water Based PWSS under Ranaghat-I Block by Augmentation of Tarapur Part-III W/S Scheme under Ranaghat-l Block Under Nadia Arsenic Division-I,P.H.E Dte. | 423/AE-I/NAD-I | 20/09/2023 | 30 | ASHIM ENTERPRISE | 3.72 | 3.72 | 100 | 100
4297 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Retrofitting work of laying of UPVC pipeline and other allied works at Parniamatpur Mouza under JJM by Augmentation of Ground Water Based PWSS of Parniamatpur Part-III W/S Scheme under Ranaghat-l Block Under Nadia Arsenic Division-I,P.H.E Dte. | 422/AE-I/NAD-I | 20/09/2023 | 30 | M/S RANA ENTERPRISE | 3.16 | 3.16 | 100 | 100
4298 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Laying of UPVC pipelineat Uttarpara Tarapur Mouza by retrofitting of GRound Water Based PWSS under JJM at Ranaghat-I block by augmentation of Tarpur Part-III W/S Scheme under Nadia Arsenic Division-I,P.H.E Dte. | 424/AE-I/NAD-I | 20/09/2023 | 30 | KUHELI ENTERPRISE | 4.82 | 4.82 | 100 | 100
4299 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Laying of UPVC pipeline at Gazipur Mouza by retrofitting of Ground Water Based PWSS under Ranaghat-I Block by Augmentation of Tarapur Part-III W/S Scheme under Ranaghat-l Block Under Nadia Arsenic Division-I,P.H.E Dte. | 425/AE-I/NAD-I | 20/09/2023 | 30 | DAFADAR ENTERPRISE | 4.84 | 4.84 | 100 | 100
4300 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Lyaing of UPVC Pipeline at Sureshnagar, Tarapur Mouza by retrofitting of Ground Water Based PWSS under JJM at Ranaghat-I Block by Augmentation of Tarapur Part-III W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 426/AE-I/NAD-I | 20/09/2023 | 30 | SAGAR ENTERPRISE | 4.81 | 4.8 | 100 | 100
4301 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Retrofitting work of laying of UPVC pipeline and other allied works near Colony Para Bridge at Kalaighata Mouza under JJM by Augmentation of Ground Water Based PWSS of Kalaighata Part-III W/S Scheme under Ranaghat-I Block under Nadia Arsenic | 420/AE-I/NAD-I | 20/09/2023 | 30 | M/S PHANINDRA NATH ROY | 4.32 | 4.3 | 100 | 100
4302 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Retrofitting work of laying of UPVC pipeline and other allied works from Kalaighata Kheyaghat to Mathpara Kali Mandir at Kalaighata Mouza under JJM by Augmentation of Ground Water Based PWSS of Kalaighata Part-III W/S Scheme under Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E Dte. | 421/AE-I/NAD-I | 20/09/2023 | 30 | MANARAMA ENTERPRISE | 4.66 | 4.66 | 100 | 100
4303 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Augmentation Work under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata and Parniamatpur PWSS Part- III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata and Parniamatpur Water Supply Schemes under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.02) | 2205/NAD-I | 13/09/2023 | 25 | M/S R.K. ENTERPRISE | 7.09 | 7.07 | 100 | 100
4304 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Retrofitting work of laying of UPVC pipeline and other allied works near House of Saroda Nath at Kalaighata Mouza under JJM by Augmentation of Ground Water Based PWSS of Kalaighata Part-III W/S Scheme under Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E. Dte. | 419/AE-I/NAD-I | 20/09/2023 | 30 | MRINAL DASGUPTA | 4.76 | 4.71 | 100 | 100
4305 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Material Requisition To Resource Division | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 9.86 | 0 | 0 | 0
4306 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Augmentation of distribution pipeline at Gazipur & Tarapur Mouzas including balance FHTC connections at Tarapur PWSS at Ranaghat-I Block under Arsenic Division-I,P.H.E. Dte (Sl. No. 10) | 1924/NAD-I | 22/11/2024 | 320 | BISWAS CONSTRUCTION | 19.11 | 0 | 0 | 80
4307 | NADIA | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Providing Boundary Illumination with allied works at Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III under Block_ Ranaghat -I Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/12023) | 1160/EMD | 04/06/2025 | 90 | PIONEER ELECTRICALS | 21.71 | 0 | 0 | 0
4308 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Augmentation of Pipeline including FHTC by changing bibcock or stop cock or stand post or washing & refixing ferrule at at Tengridanga, Madhyapara & Mahatpur areas under Gayeshpur Gram Panchayet and Kalaighata village under Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat-I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte.. (Sl. No. 02) | 165/NAD-I | 29/04/2025 | 180 | M /S SHAIKH ENTERPRISE | 12.39 | 0 | 0 | 100
4309 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakan , SM/12023 | Augmentation | Augmentation of FHTC and Laying of balanced Pipeline at Gazipur, Tarapur, Girish Nagar, Jhau Mahal, Suresh Nagar under Tarapur GP at Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. | 580/NAD-I | 10/07/2025 | 60 | BISWAS CONSTRUCTION | 27.98 | 0 | 0 | 0
4310 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Bahirgachi Zone-I water supply scheme underChapra Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08305 | Retrofitting | Quotation for Nischintapur W/S scheme |  | 28/09/2020 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 1.78 | 0 | 0 | 0
4311 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Bahirgachi Zone-I water supply scheme underChapra Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08305 | Retrofitting | QUOTATION FOR NISCHINTAPUR WATER SUPPLY SCHEME |  | 28/09/2021 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 1.78 | 0 | 0 | 0
4312 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Bahirgachi Zone-I water supply scheme underChapra Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08305 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Bahirgachhi Zone-I (Vill- Bahirgachhi) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1186/NACD-II | 13/11/2020 | 25 | ST. ANTHONY ENTERPRISE | 4.98 | 0 | 0 | 0
4313 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Monipota Water Scheme (for Bishnupur & Raotara Mouzas) under Jal Swapno Programme in Nadia District , SM/08125 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Monipota W/S scheme(for Bishnupur and Raotara Mouza) in Nadia District under Nadia Division P.H.E. Dte. | 2190/ND | 24/05/2021 | 90 | PROJECT INDIA | 92.56 | 1.56 | 1.65 | 100
4314 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Monipota Water Scheme (for Bishnupur & Raotara Mouzas) under Jal Swapno Programme in Nadia District , SM/08125 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Monipota W/S scheme(for Bishnupur and Raotara Mouza) in Nadia District under Nadia Division P.H.E. Dte. | 350/PFMS | 08/12/2021 | 0 | PROJECT INDIA | 92.59 | 0 | 0 | 0
4315 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Monipota Water Scheme (for Bishnupur & Raotara Mouzas) under Jal Swapno Programme in Nadia District , SM/08125 | Retrofitting | Material Requisition To Resource Division | 4332/ND | 29/09/2022 | 0 | Resource Division | 8.13 | 0 | 0 | 0
4316 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Joania Water Scheme (for Hazrapole, Kursi, Joania & Malipota Mouzas) under Jal Swapno Programme in Nadia District , SM/08126 | Retrofitting | Providing Functional Household Tap Connection from Joania Water Scheme (for Hazrapole, Kursi, Joania & Malipota Mouzas) under Jal Swapno Programme in Nadia District. | 182/PFMS | 15/09/2021 | 0 | UMWELT ENGINEERS PVT LTD | 61.06 | 0 | 0 | 0
4317 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Joania Water Scheme (for Hazrapole, Kursi, Joania & Malipota Mouzas) under Jal Swapno Programme in Nadia District , SM/08126 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Joania W/S scheme(for Hazrapole, Kursi, Joania & Malipota Mouzas) in Nadia District under Nadia Division P.H.E. Dte. | 2191/ND | 24/05/2021 | 90 | UMWELT ENGINEERS PVT LTD | 93.31 | 31.67 | 33.95 | 0
4318 | NADIA | Nadia Division | Providing Functional Household Tap Connection from Joania Water Scheme (for Hazrapole, Kursi, Joania & Malipota Mouzas) under Jal Swapno Programme in Nadia District , SM/08126 | Retrofitting | Material Requisition To Resource Division | 1058/ND | 04/03/2022 | 0 | Resource Division | 8.47 | 0 | 0 | 0
4319 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Krishnagar-II, Nabadwip (Part) Block (Phase-B) , SM/07434 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Krishnagar-II, Nabadwip (Part) Block (Phase-B) | 235/PFMS | 05/10/2021 | 0 | TARUN KUMAR BHATTACHARYA | 82.3 | 0 | 0 | 0
4320 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Krishnagar-II, Nabadwip (Part) Block (Phase-B) , SM/07434 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-I, within Krishnagar-II & Nabadwip Block (Phase-B, Retrofitting)" | 771/ND | 10/02/2021 | 90 | TARUN KUMAR BHATTACHARYA | 97.08 | 0 | 0 | 0
4321 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Krishnagar-II, Nabadwip (Part) Block (Phase-B) , SM/07434 | Retrofitting | Material Requisition To Resource Division | 302/ND | 15/01/2024 | 0 | Resource Division | 2.48 | 0 | 0 | 0
4322 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VII, (BALLAVPUR), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme , SM/08000 | Retrofitting | Providing FHTC Functional Household Tap Connection under Jaldhara Jal Swapna for Zone VII Ballavapur Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah Part Water Supply Scheme under Nadia Arsenic Division I PHE Dte | 786/NAD-I | 05/05/2021 | 60 | H I ENTERPRISE | 97 | 179.07 | 100 | 100
4323 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Muragachha Zone-I Part-I, at Hanskhali Block by retrofitting of Ground Water based PWSS for Muragachha Water Supply Scheme , SM/08011 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Muragachha, Zone-I, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 770/NAD-I | 04/05/2021 | 60 | MONDAL ENTERPRISE | 68.28 | 100 | 95.83 | 100
4324 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Radhakantapur Part-I, at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Radhakantapur Water Supply Scheme , SM/08015 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Radhakantapur, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Radhakantapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 780/NAD-I | 05/05/2021 | 60 | TAPU SAHA | 88.27 | 165.66 | 200 | 0
4325 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia Part-I, at Santipur Block by retrofitting of Ground Water based PWSS for Beharia Water Supply Scheme , SM/08017 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Part-I at Santipur Block by retrofitting of Ground Water based PWSS for Beharia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 779/NAD-I | 05/05/2021 | 60 | GHOSH CONSTRUCTION | 97.11 | 97.07 | 50 | 100
4326 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block [Phase-A] , SM/07418 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME ATPART-1 Z-8 | 460/DW | 30/03/2021 | 0 | OTHERS | 80.19 | 0 | 0 | 0
4327 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block [Phase-A] , SM/07418 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block [Phase-A] | 485/PFMS | 03/02/2022 | 0 | LEMNISCATE | 0.48 | 0 | 0 | 0
4328 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block [Phase-A] , SM/07418 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block ( Phase -A) | 4089ND | 31/12/2020 | 90 | UMWELT ENGINEERS PVT LTD | 96.87 | 14.61 | 15.08 | 0
4329 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block [Phase-A] , SM/07418 | Retrofitting | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Executive Engineer, Nadia Division, PHE Dte. (Period- 01/04/2023 to 30/09/2023) | 465/ Kly SD-1 | 31/03/2023 | 183 | ARROWTOWN DEALERS PVT. LTD | 2.4 | 0 | 0 | 0
4330 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block [Phase-A] , SM/07418 | Retrofitting | Hiring of Diesel Ambassador Car/maxi cab for the office of the Assistant Engineer, Debagram Sub-Diovision,PHE Dte,Debagram,Nadia with effect from 01.08.2021 to 31.07.2022 | 399/DSD | 29/07/2021 | 365 | TARUN KUMAR BHATTACHARYA | 4.8 | 1.19 | 100 | 0
4331 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar- II & Nabadwip (Part) Block (Phase-B) , SM/07454 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar- II & Nabadwip (Part) Block (Phase-B). |  | 24/03/2021 | 0 | PROJECT INDIA | 49.93 | 0 | 0 | 0
4332 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar- II & Nabadwip (Part) Block (Phase-B) , SM/07454 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-IV, within Krishnagar-II & Nabadwip Block (Phase-B, Retrofitting)" | 777/ND | 10/02/2021 | 90 | PROJECT INDIA | 97.04 | 192.48 | 198.35 | 0
4333 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar- II & Nabadwip (Part) Block (Phase-B) , SM/07454 | Retrofitting | Material Requisition To Resource Division | 442/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0 | 0
4334 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-C) , SM/08137 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED W/S SCHEME N/ SECTOR PART-2, Z-9, NAKASHIPARA BLOCK, PHASE--C | 262/PFMS | 08/10/2021 | 0 | TARUN KUMAR BHATTACHARYA | 84.44 | 0 | 0 | 0
4335 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-C) , SM/08137 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block ( Phase -C) in Nadia District under Nadia Division P.H.E. Dte Sl.No.3 | 889/ND | 19/02/2021 | 90 | TARUN KUMAR BHATTACHARYA | 96.89 | 4.27 | 4.41 | 0
4336 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-C) , SM/08137 | Retrofitting | Laying additional distribution pipeline for providing FHTC at zone- Nagla, Raripara, Badbelgao, Bholadangavilleges under VI & IX , Part- II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block | 159/DSD | 17/03/2022 | 30 | MAHAVIR PUMPS MFG PVT. LTD. | 4.24 | 4.21 | 99.23 | 0
4337 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-C) , SM/08137 | Retrofitting | Laying additional distribution pipeline for providing FHTC at Dogachhia, Deluigachi, Jalsukha and Saligram villages of zone VI & IX , Part- II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | 160/DSD | 17/03/2022 | 30 | MAHAVIR PUMPS MFG PVT. LTD. | 3.92 | 3.91 | 99.8 | 0
4338 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-C) , SM/08137 | Retrofitting | Material Requisition To Resource Division | 4273/ND | 29/09/2022 | 0 | Resource Division | 12.54 | 0 | 0 | 0
4339 | NADIA | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-I Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District , SM/08050 | Retrofitting | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-I Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District | 531/PFMS | 23/02/2022 | 0 | M/S SHUBHA ENTERPRISE | 11.19 | 0 | 0 | 0
4340 | NADIA | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-I Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District , SM/08050 | Retrofitting | Material Requisition To Resource Division | 815/ND | 18/02/2022 | 0 | Resource Division | 11 | 0 | 0 | 0
4341 | NADIA | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-I Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District , SM/08050 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | 2153/ND | 21/05/2021 | 45 | M/S SHUBHA ENTERPRISE | 10.99 | 0 | 0 | 100
4342 | NADIA | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-I Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District , SM/08050 | Retrofitting | Laying of parallel new UPVC pipe line in Sansad-X in Deypara GP opposite Jahangirpur Helipada ground to complte FHTC under Paschim Bhatjungla Zone-I W/S scheme under RWS Nadia Sub-Division, PHE Dte. | 2908/ND | 23/07/2021 | 60 | BIPLAB GUHA | 23.33 | 22.97 | 98.47 | 100
4343 | NADIA | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-I Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District , SM/08050 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | 2152/ND | 21/05/2021 | 60 | ORIENT CONSTRUCTION | 42.68 | 19.83 | 54.63 | 100
4344 | NADIA | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-I Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District , SM/08050 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | 2151/ND | 21/05/2021 | 60 | BOSE & CO | 42.67 | 32.08 | 75.18 | 100
4345 | NADIA | Nadia Division | Providing Functional House Tap Connection from Subernabehar Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08054 | Retrofitting | Providing Functional House Tap Connection from Subernabehar Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | 288/PFMS | 08/10/2021 | 0 | M/S S.S ENTERPRISE | 21.54 | 0 | 0 | 0
4346 | NADIA | Nadia Division | Providing Functional House Tap Connection from Subernabehar Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08054 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY AT SUBERNABIHAR W/S , PHASE-1 | 482/PFMS | 03/02/2022 | 0 | SHYAMAL SHIL | 3.94 | 0 | 0 | 0
4347 | NADIA | Nadia Division | Providing Functional House Tap Connection from Subernabehar Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08054 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Subarnabehar W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | 2159/ND | 21/05/2021 | 60 | M/S S.S ENTERPRISE | 42.27 | 9.23 | 100 | 0
4348 | NADIA | Nadia Division | Providing Functional House Tap Connection from Subernabehar Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08054 | Retrofitting | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Subarnabehar W/S Scheme in Krishnagar - I Block of Nadia District under Nadia Division. PART - B | 1190/PH | 03/12/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 1.69 | 0 | 0 | 100
4349 | NADIA | Nadia Division | Providing Functional House Tap Connection from Subernabehar Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08054 | Retrofitting | Laying of D I Pipe line in place of UPVC pipe including other allied works from OHR to both side of head work site for providing FHTC under Jal Swapna at Subarnabehar w/s scheme under Nadia Division PHED. | 215/PH | 12/07/2022 | 30 | SURAJIT KUMAR GHOSH | 4.65 | 0 | 0 | 92
4350 | NADIA | Nadia Division | Providing Functional House Tap Connection from Subernabehar Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08054 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Subarnabehar W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | 2432/ND | 14/06/2021 | 60 | SANJOY BAKSHI | 42.57 | 61.63 | 144.8 | 100
4351 | NADIA | Nadia Division | Providing Functional House Tap Connection from Subernabehar Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). , SM/08054 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Subarnabehar W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | 2391/ND | 10/06/2021 | 45 | ROY CONSTRUCTION | 9.03 | 16.29 | 180.37 | 100
4352 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX, (Chandmari), Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07894 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX, (Chandmari), Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl No.- 01) Tender No.- 205/NAD-I/2020-2021. | 157/NAD-I | 25/01/2021 | 60 | GHOSH ENTERPRISE | 97.08 | 194.13 | 130.43 | 100
4353 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-I, (Fatepur), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07896 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-I, (Fatepur), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl No.- 03) | 159/NAD-I | 25/01/2021 | 60 | TARUN KUMAR BHATTACHARYA | 96.53 | 189.63 | 116.52 | 100
4354 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-I, (Fatepur), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07896 | Retrofitting | Reconnection of Functional household tap connection including additional restoration and renovation work of pump house, boundary wall and path way at Zone-I,Fatepur under Surface based Water Supply PWSS of Haringhata & Chakdah (Part) under Haringhata Block under Nadia Arsenic Division-I,P.H.E Dte | 31/AE-I/NAD-I | 19/01/2024 | 30 | SHYAMAL SHIL | 3.2 | 3.12 | 100 | 100
4355 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/07897 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 04) Tender No. 196/NAD-I/2020-2021. | 155/NAD-I | 25/01/2021 | 60 | UNICON INDIA | 97.03 | 190.37 | 114.6 | 100
4356 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VI, (BALIA), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme , SM/07901 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Dhara/Jal Swapna for Zone-VI, (Balia) Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte (Sl. NO. 02) Tender No. - 225/NAD-I/2020-2021. | 314/NAD-I | 08/02/2021 | 90 | UMWELT ENGINEER PVT. LTD. | 97.05 | 155.86 | 160.93 | 100
4357 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07473 | Retrofitting | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) |  | 12/04/2021 | 0 | CHANDAN ROY | 14.57 | 0 | 0 | 0
4358 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07473 | Retrofitting | use Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) |  | 12/04/2021 | 0 | USHA CONSTRUCTION | 20.02 | 0 | 0 | 0
4359 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07473 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN- METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC. ALL COMPLETE AT ARABPUR W/S SCHEME PHASE-1, PART-B, RETROFITTING, UNDER NADIA DIVISION, PHE , DTE. | 68/PPMS | 15/07/2021 | 0 | USHA CONSTRUCTION | 20.02 | 0 | 0 | 0
4360 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07473 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN- METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC. ALL COMPLETE AT ARABPUR W/S SCHEME PHASE-1, PART-A,RETROFITTING UNDER NADIA DIVISION, PHE , DTE. | 79/PPMS | 15/07/2021 | 0 | CHANDAN ROY | 14.57 | 0 | 0 | 0
4361 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07473 | Retrofitting | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) | 287/PFMS | 08/10/2021 | 0 | CHANDAN ROY | 8.5 | 0 | 0 | 0
4362 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07473 | Retrofitting | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) | 289/PFMS | 08/10/2021 | 0 | SANJIB DEY | 12 | 0 | 0 | 0
4363 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07473 | Retrofitting | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) | 78/PFMS | 15/07/2021 | 0 | SANJIB DEY | 9.86 | 0 | 0 | 0
4364 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07473 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Arabpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte."(Phase-I Retro fitting)(PART-B) | 402/ND | 22/01/2021 | 45 | USHA CONSTRUCTION | 32.19 | 8.48 | 100 | 0
4365 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07473 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Arabpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte."(Phase-I Retro fitting)(PART-A) | 401/ND | 22/01/2021 | 45 | CHANDAN ROY | 32.17 | 3.76 | 100 | 0
4366 | NADIA | Nadia Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07473 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Arabpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte."(Phase-I Retro fitting)(PART-C) | 403/ND | 22/01/2021 | 45 | SANJIB DEY | 32.2 | 5.25 | 100 | 0
4367 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II & Nabadwip (Part) Block (Phase-C) , SM/07475 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME (N/S), PART-III, ZONE-IV, WITHIN KRISHAGAR -II & NABADWIP BLOCK PHASE-C | 304/PFMS | 01/11/2021 | 0 | MAHAVIR PUMPS MFG PVT. LTD. | 65 | 0 | 0 | 0
4368 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II & Nabadwip (Part) Block (Phase-C) , SM/07475 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-IV, within Krishnagar-II & Nabadwip Block (Phase-C, Retrofitting)" | 778/ND | 10/02/2021 | 90 | MAHABIR PUMPS MFG PVT. LTD. | 97.12 | 24.73 | 25.46 | 100
4369 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II & Nabadwip (Part) Block (Phase-C) , SM/07475 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 2.2 | 100 | 81
4370 | NADIA | Nadia Division | Retrofitting of Providing FHTC at Ground Water based Elangi Water Supply Scheme Zone-1(Phase-1) , SM/07489 | Retrofitting | Retrofitting of Providing FHTC at Ground Water based Elangi Water Supply Scheme Zone-1(Phase-1) | 81/PFMS | 13/07/2022 | 0 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 3.86 | 0 | 0 | 0
4371 | NADIA | Nadia Division | Retrofitting of Providing FHTC at Ground Water based Elangi Water Supply Scheme Zone-1(Phase-1) , SM/07489 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Elangi Zone-I W/S scheme (Phase-I) of Rectrofitting in Nadia District under Nadia Division P.H.E. Dte. | 61/ND | 07/01/2021 | 90 | S.K. CONSTRUCTION | 96.72 | 95.73 | 98.98 | 100
4372 | NADIA | Nadia Division | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07493 | Retrofitting | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) |  | 16/04/2021 | 0 | NILAY KUMAR BHATTACHARYA | 12.07 | 0 | 0 | 0
4373 | NADIA | Nadia Division | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07493 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME ATTOPLA W/S SCHEME | 460/DW | 30/03/2021 | 0 | SOMNATH CHATTERJEE | 18.55 | 0 | 0 | 0
4374 | NADIA | Nadia Division | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07493 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN-METAL FERRULE ........AT TOPLA W/S SCHEME PHASE-I RETROFITTING | 72/PPMS | 15/07/2021 | 0 | SANDIP BISWAS | 9.28 | 0 | 0 | 0
4375 | NADIA | Nadia Division | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07493 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN-METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC ALL COMPLETE AT TOPLA W/S SCHEME UNDER NADIA DIVISION, PHE , DTE . PHASE-1, RETROFITTING PART-B. | 69/PPMS | 15/07/2021 | 0 | NILAY KUMAR BHATTACHARYA | 12.07 | 0 | 0 | 0
4376 | NADIA | Nadia Division | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07493 | Retrofitting | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) | 606/PFMS | 11/03/2022 | 0 | OTHERS | 11.34 | 0 | 0 | 0
4377 | NADIA | Nadia Division | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07493 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Topla W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-C) | 406/ND | 22/01/2021 | 45 | SOMNATH CHATTERJEE | 32.31 | 22.45 | 69.49 | 0
4378 | NADIA | Nadia Division | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07493 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Topla W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-A) | 404/ND | 22/01/2021 | 45 | NILAY KUMAR BHATTACHARYA | 32.33 | 0 | 0 | 0
4379 | NADIA | Nadia Division | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) , SM/07493 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Topla W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-B) | 405/ND | 22/01/2021 | 45 | SANDIP BISWAS | 32.33 | 22.61 | 100 | 0
4380 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-B) , SM/07498 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED W/S SCHEME NORTHERN SECTOR PART-II,ZONE-IV,WITHIN NAKASHIPARA BLOCK PHASE-B. | 90/PPMS | 15/07/2021 | 0 | M/S S.S ENTERPRISE | 69.17 | 0 | 0 | 0
4381 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-B) , SM/07498 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-B). |  | 25/03/2021 | 0 | M/S S.S ENTERPRISE | 69.17 | 0 | 0 | 0
4382 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-B) , SM/07498 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-B) | 293/PFMS | 08/10/2021 | 0 | M/S S.S ENTERPRISE | 17.6 | 0 | 0 | 0
4383 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-B) , SM/07498 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-II, Z-IV, WITHIN NAKASHIPARA BLOCK, PHASE-B. | 496/PFMS | 03/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.71 | 0 | 0 | 0
4384 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-B) , SM/07498 | Retrofitting | :Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block ( Phase -B) | 246/ND | 15/01/2021 | 90 | M/S S.S ENTERPRISE | 96.93 | 7.55 | 100 | 0
4385 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-B) , SM/07498 | Retrofitting | Construction of OHR, repair and renovation of staff room, repair of boundary wall, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-IV / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11841]. | 6152/ND | 26/12/2023 | 728 | SATYABRATA CHAKRABORTY | 233.13 | 0 | 0 | 5
4386 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-B) , SM/07503 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED W/S SCHEME NORTHERN SECTOR PART-II, ZONE-V,WITHIN NAKASHIPARA BLOCK PHASE-B. | 84/PPMS | 15/07/2021 | 0 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 63.71 | 0 | 0 | 0
4387 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-B) , SM/07503 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-B) | 553/PFMS | 23/02/2022 | 0 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 21.99 | 0 | 0 | 0
4388 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-B) , SM/07503 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-B) | 495/PFMS | 03/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.46 | 0 | 0 | 0
4389 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-B) , SM/07503 | Retrofitting | Continuation for Payment of remuneration for engagement of 10 nos. personnel (One Chemist / Bacteriologist and one Lab Assistant) at 5 Nos. Sub-District Laboratories under Nadia Division, P.H.E. Dte. on contractual basis w.e.f. 01.05.2023 to 30.06.2023 (Two Month). | 1939/ND | 28/04/2023 | 61 | CLIFFORD FACILITY SERVICES PVT. LTD | 2.73 | 1.36 | 100 | 50
4390 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-B) , SM/07503 | Retrofitting | Material Requisition To Resource Division | 4333/ND | 29/09/2022 | 0 | Resource Division | 12.52 | 0 | 0 | 0
4391 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-B) , SM/07503 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-V within Nakashipara Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte.(SL.3) | 868/ND | 18/02/2021 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 97.09 | 0 | 0 | 0
4392 | NADIA | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-B) , SM/07503 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 1.65 | 100 | 81
4393 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-B). , SM/07000 | Retrofitting | PREPERATION OF DETAILS PROJECT FOR FHTC AT SURFACE WATER BASED W/S SCHEME ( N.SECTOR) , PART-II, ZONE-I, PHASE-A & B UNDER , NADIA DIVISION , PHE ,DTE | 139/FHTC | 17/08/2021 | 0 | LEMNISCATE | 0.69 | 0 | 0 | 0
4394 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-B). , SM/07000 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-B). | 594/DW | 11/03/2022 | 0 | RADIANT | 3.17 | 0 | 0 | 0
4395 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-B). , SM/07000 | Retrofitting | CONSTRUCTION OF 2 NOS. PORTICO AND OTHER ALLIED WORK FOR NEW OFFICE BUILDING FOR ACCOMMODATING DIVISION OFFICE ALONG WITH 4 NOS SUB. DIVSIONAL OFFICES FOR MONITORING OF JAL SWAPNO PROGRAM. | 685/OBDW | 30/03/2022 | 0 | AMBRUS CONSTRUCTION | 4.98 | 0 | 0 | 0
4396 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-B). , SM/07000 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme(northern sector),Part-I,Zone-III within Kaliganj block(Phase-B) in Nadia District under Nadia Division P.H.Engineering Dte. | 3591/ND | 08/12/2020 | 90 | IJABUL SK. | 97.01 | 159.39 | 164.29 | 0
4397 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-B). , SM/07000 | Retrofitting | Hiring Diesel Maxi Cub having car No WB-51/B-3194 for office of the Assistant Engineer, RWS Nadia Sub-Division, PHE Dte. for the period from 01.08.2021 to 31.07.2022 | 896/PH | 30/07/2021 | 365 | TARUN KUMAR BHATTACHARYA | 4.8 | 1.26 | 43.22 | 100
4398 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Saguna, Part-I at Santipur Block by retrofitting of Ground Water based PWSS for Saguna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08822 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Saguna, Part-I at Santipur Block by retrofitting of Ground Water based PWSS for Saguna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1412/NAD-I | 08/11/2021 | 60 | H I ENTERPRISE | 87.11 | 83.82 | 100 | 100
4399 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Saguna, Part-I at Santipur Block by retrofitting of Ground Water based PWSS for Saguna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08822 | Retrofitting | Construction and installation of MANIFOLD and allied works at OHR site under Saguna Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Saguna (Part-I) under JJM(Sl.no.12) | 1426/NAD-I | 23/05/2023 | 15 | ROY ASSOCIATES | 13.04 | 13.04 | 100 | 100
4400 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-II Phase-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08850 | Retrofitting | Providing FHTC (Functional Household Tap Connection) by retrofitting/rejuvenation under Jaldhara/Jal Swapna for Arranghata Zone-I Water Supply Scheme, Phase-I at Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. | 645/NAD-I | 29/04/2022 | 90 | M/S R.K. ENTERPRISE | 260.46 | 41.8 | 100 | 100
4401 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-II Phase-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08850 | Retrofitting | Material Requisition To Resource Division | 146/NAD-I | 28/01/2022 | 0 | Resource Division | 0.6 | 0 | 0 | 0
4402 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-II Phase-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08850 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Arranghata Zone-II Phase-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Zone-II Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1480/NAD-I | 24/11/2021 | 90 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 167.42 | 131.2 | 78.36 | 100
4403 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-II Phase-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08850 | Retrofitting | Providing FHTC (Functional Household Tap Connection) by retrofitting/rejuvenation under Jaldhara/Jal Swapna for Arranghata Zone-II W/S Scheme, Phase-II at Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. | 643/NAD-I | 29/04/2022 | 90 | UNICON INDIA | 335.39 | 0 | 0 | 10
4404 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X (Shimurali) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08855 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X (Shimurali) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 51/NAD-I | 11/01/2022 | 90 | APURBA MANDAL | 203.19 | 202.99 | 69.43 | 100
4405 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dhantala, Part-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08828 | Retrofitting | Providing FHTC (Functional Household Tap Connection under Jaldhara/Jal Swapna for Dhantala Part-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | 1402/NAD-I | 08/11/2021 | 60 | M/S DIPAK ENTERPRISE | 85.84 | 85.5 | 100 | 100
4406 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dhantala, Part-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08828 | Retrofitting | Material Requisition To Resource Division | 138/NAD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0 | 0
4407 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dhantala, Part-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. , SM/08828 | Retrofitting | Revamping / upgardation of hydraulic parameter of distribution network and providing FHTC for Doula, Debipur Chandpur Biraberia Dhantala & Notungram and Hizuli (Part) Village and under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in connection with Dhantala PWSS & Hizuli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | 800/NAD-I | 18/08/2025 | 90 | BIDYUT KUMAR | 182.15 | 0 | 0 | 0
4408 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic , SM/08831 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-III (Jalkar Bhomra) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 1612/NAD-I | 28/12/2021 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 304.75 | 300.59 | 100 | 100
4409 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic , SM/08831 | Retrofitting | Material Requisition To Resource Division | 3502/NAD-I | 05/01/2023 | 0 | Resource Division | 15.41 | 0 | 0 | 0
4410 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-I, (Fatepur), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divisio , SM/08835 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-I (Fatepur) Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 1615/NAD-I | 28/12/2021 | 90 | BKB INFRA PROJECTS PRIVATE LIMITED | 244.09 | 242.27 | 100 | 100
4411 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Jayghata water supply scheme underKrishnaganj Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08302 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Joyghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1068/NACD-II | 25/09/2020 | 15 | BIPLAB GUHA | 4.99 | 0 | 0 | 0
4412 | NADIA | Central Drilling | Gadigachha Piped Water Supply Scheme. , SM/09223 | New | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT HOWRAH DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 86/ CMSD-II (D) | 24/02/2021 | 30 | ASHUTOSH DAS & CO | 4.83 | 3.83 | 100 | 0
4413 | NADIA | Nadia Division | Gadigachha Piped Water Supply Scheme. , SM/09223 | New | Continuation of Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 90 days w.e.f. 01/10/2023 (as and when required) | 1450/KSD | 18/09/2023 | 90 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 0
4414 | NADIA | Nadia Division | Gadigachha Piped Water Supply Scheme. , SM/09223 | New | Survey , Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household under Gadigacha W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Sl.No. 14) | 917/KSD | 29/11/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.23 | 4.18 | 100 | 0
4415 | NADIA | Nadia Division | Gadigachha Piped Water Supply Scheme. , SM/09223 | New | Material Requisition To Resource Division | 132/ND | 06/01/2023 | 0 | Resource Division | 29.03 | 0 | 0 | 0
4416 | NADIA | Nadia Division | Gadigachha Piped Water Supply Scheme. , SM/09223 | New | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 366 days w.e.f. 01/01/2024 to 31/12/2024 | 1838/KSD | 28/12/2023 | 366 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0 | 0
4417 | NADIA | Nadia Division | Gadigachha Piped Water Supply Scheme. , SM/09223 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 81 m3/hr at Gadigacha Water Supply Scheme within Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | 1894/ND | 15/03/2024 | 180 | G.D. CONSTRUCTION AND CO. | 226.16 | 0 | 0 | 0
4418 | NADIA | Nadia Division | Gadigachha Piped Water Supply Scheme. , SM/09223 | New | Material Requisition To Resource Division | 270/ND | 11/01/2024 | 0 | Resource Division | 23.16 | 0 | 0 | 0
4419 | NADIA | Nadia Division | Gadigachha Piped Water Supply Scheme. , SM/09223 | New | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | 3784/ND | 12/08/2025 | 31 | IMAGIN | 34.21 | 0 | 0 | 0
4420 | NADIA | Nadia Division | Gadigachha Piped Water Supply Scheme. , SM/09223 | New | Laying of Distribution System including specials & valves, pipe Supporting structure all complete, Proposed augmentation of Rising Main, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Soil investigation for construction of one No. 450 Cum OHR, Construction of R.C.C. Elevated Reservoir of 450 Cum capacity(including pile foundation) at Gadigachha in Nabadwip Block under Nadia Division,PHE Dte. | 3026/ND | 14/07/2023 | 1096 | JOY HIND TUBEWELL'S | 431.93 | 232.55 | 53.84 | 45
4421 | NADIA | Eastern Mechanical | Gadigachha Piped Water Supply Scheme. , SM/09223 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Gadigachha ground water based water supply scheme under Block_Nabadwip Dist. - Nadia under EMD, PHE Dte. SM/09223 | 1127/EMD | 04/06/2025 | 90 | ASHUTOSH DAS & CO. | 36.75 | 0 | 0 | 0
4422 | NADIA | Nadia Division | Gadigachha Piped Water Supply Scheme. , SM/09223 | New | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
4423 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme (Northern Sector) Part-II Zone-II within Nakashipara Block (Phase-B) , SM/08887 | Retrofitting | PROVIDING FHTC ..FROM NORTHRN SECTOR , PART-II, Z-II, PHASE-B, WITHIN NAKASHIPARA BLOCK W/S SCHEME | 471/PFMS | 02/02/2022 | 0 | TARUN KUMAR BHATTACHARYA | 71.78 | 0 | 0 | 0
4424 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme (Northern Sector) Part-II Zone-II within Nakashipara Block (Phase-B) , SM/08887 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme (Northern Sector) Part-II Zone-II within Nakashipara Block (Phase-B) | 60/PFMS | 22/06/2022 | 0 | TARUN KUMAR BHATTACHARYA | 5.49 | 0 | 0 | 0
4425 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme (Northern Sector) Part-II Zone-II within Nakashipara Block (Phase-B) , SM/08887 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-II, Zone-II within Nakashipara Block (Phase-B) | 5364/ND | 30/09/2021 | 90 | TARUN KUMAR BHATTACHARYA | 86.48 | 1.64 | 100 | 100
4426 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme (Northern Sector) Part-II Zone-II within Nakashipara Block (Phase-B) , SM/08887 | Retrofitting | Material Requisition To Resource Division | 451/ND | 31/01/2022 | 0 | Resource Division | 3.98 | 0 | 0 | 0
4427 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme (Northern Sector) Part-II Zone-II within Nakashipara Block (Phase-B) , SM/08887 | Retrofitting | Material Requisition To Resource Division | 4283/ND | 29/09/2022 | 0 | Resource Division | 12.57 | 0 | 0 | 0
4428 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme (Northern Sector) Part-II Zone-II within Nakashipara Block (Phase-B) , SM/08887 | Retrofitting | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Naserkuli Zone-II ii) Subarna Behar Zone-I iii) Mahisunra Phase- I iv)Mahisunra Phase-II v)Bablari Dewanganj | 673/KlySd-I | 30/05/2023 | 184 | HORIZEN | 4.62 | 4.62 | 100 | 100
4429 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme (Northern Sector) Part-II Zone-II within Nakashipara Block (Phase-B) , SM/08887 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 8.74 | 100 | 81
4430 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Paschim Noapara, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte , SM/08814 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Paschim Noapara, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1406/NAD-I | 08/11/2021 | 60 | IJABUL SEKH | 83.14 | 82.5 | 100 | 100
4431 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Paschim Noapara, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte , SM/08814 | Retrofitting | Material Requisition To Resource Division | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 1.73 | 0 | 0 | 0
4432 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Mamjoani Part-II Construction of Arsenic-cum Iron Removal Plant (AIRP), and other allied works at Hankhali Block by retrofitting of Ground Water based PWSS for Mamjoani W , SM/08845 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Mamjoani, Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Mamjoani Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | 1411/NAD-I | 08/11/2021 | 60 | SANJOY BAKSHI | 73.62 | 70.47 | 100 | 100
4433 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-V and VIII within Kaliganj Block.(Phase-C) , SM/08668 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-V&VIII within Kaliganj Block (Phase-C) | 5180/ND | 20/09/2021 | 90 | SATYABRATA CHAKRABORTY | 89.77 | 85.38 | 95.11 | 0
4434 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-V and VIII within Kaliganj Block.(Phase-C) , SM/08668 | Retrofitting | Material Requisition To Resource Division | 4292/ND | 29/09/2022 | 0 | Resource Division | 12.54 | 0 | 0 | 0
4435 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-V and VIII within Kaliganj Block.(Phase-C) , SM/08668 | Retrofitting | Material Requisition To Resource Division | 312/ND | 15/01/2024 | 0 | Resource Division | 2.62 | 0 | 0 | 0
4436 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-V and VIII within Kaliganj Block.(Phase-C) , SM/08668 | Retrofitting | Material Requisition To Resource Division | 313/ND | 15/01/2024 | 0 | Resource Division | 5.4 | 0 | 0 | 0
4437 | NADIA | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-V and VIII within Kaliganj Block.(Phase-C) , SM/08668 | Retrofitting | Material Requisition To Resource Division | 319/ND | 15/01/2024 | 0 | Resource Division | 12.55 | 0 | 0 | 0
4438 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS , SM/10074 | Augmentation | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS | 702/PFMS | 30/03/2022 | 0 | HORIZEN | 2.8 | 0 | 0 | 0
4439 | NADIA | Eastern Mechanical | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS , SM/10074 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC at under SHYAMNAGAR W/S Scheme, Block-Tehatta I , Dist. - Nadia. NIET No. 36 of EE/EMD of 2022-23 (Sl. No.- 12) | 1584/EMD | 24/04/2023 | 30 | P.K. ENTERPRISE | 16.13 | 15.47 | 100 | 80
4440 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS , SM/10074 | Augmentation | Augmentation of Distribution System of Ground Based Piped Water Supply Scheme at Shyamnagar to accommodate FHTC within Tehatta I Block under Kalyani Sub Division I under Nadia Division PHE Dte. | 4276/ND | 21/09/2023 | 60 | MONDAL ENTERPRISE | 20.56 | 20.56 | 100 | 100
4441 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS , SM/10074 | Augmentation | Material Requisition To Resource Division | 1389/ND | 24/03/2022 | 0 | Resource Division | 29.18 | 0 | 0 | 0
4442 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS , SM/10074 | Augmentation | Material Requisition To Resource Division | 151/ND | 06/01/2023 | 0 | Resource Division | 1.84 | 0 | 0 | 0
4443 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS , SM/10074 | Augmentation | Material Requisition To Resource Division | 2318/ND | 29/05/2023 | 0 | Resource Division | 24.17 | 0 | 0 | 0
4444 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS , SM/10074 | Augmentation | Laying distribution system for providing FHTC at Chilakhali Mouza in connection with Augmentation of Ground Based Water Supply Scheme at Shyamnagar to accommodate FHTC under Nadia Division, PHE Dte. | 1818/ND | 14/03/2024 | 90 | M/S.ROY CHOWDHURY & CO | 54.33 | 38.71 | 41.66 | 100
4445 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS , SM/10074 | Augmentation | Repair & Renovation of Pump House, Boundary wall and allied works at Head Work site under Shyamnagar PWSS under Tehatta-I Block in Nadia District Under Nadia Division P.H.Engineering Dte. | 1099/ND | 19/02/2024 | 60 | K.K. MARKETING | 9.87 | 9.51 | 100 | 100
4446 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS , SM/10074 | Augmentation | Repair & Renovation of Pump House and Construction of Boundary wall, Service Road and allied works at 2nd T.W site under Shyamnagar PWSS under Tehatta-I Block in Nadia District Under Nadia Division P.H.Engineering Dte. | 1725/ND | 12/03/2024 | 60 | BABLU MALLICK | 10.44 | 9.3 | 100 | 100
4447 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS , SM/10074 | Augmentation | Construction of Jhama Bats Road from Palassey Betai road to headwork site of Shyamnagar water supply scheme under Kalyani Sub Division I under Nadia Division P.H.Engineering Dte. | 481KLYSD-I | 15/03/2024 | 30 | MONDAL ENTERPRISE | 6.03 | 5.81 | 100 | 100
4448 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS , SM/10074 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 500 cum Capacity 20 Mtr. Staging Height Rcc Over Head Reservoir (Including Pile Foundation), Pipe Connection And Cost of Pipes, Specials and Soil Investigation for Augmentation of Ground Based Water Supply Scheme at Shyamnagar to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 844/ND | 28/02/2023 | 1096 | MONDAL ENTERPRISE, MASJID BARI ROAD,UTTAR BALURIA, P.O.NABAPALLY, P.S. BARASAT NORTH 24 PGS. | 580.91 | 517.22 | 89.04 | 58
4449 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS , SM/10074 | Augmentation | Construction and Installation of 120.00 cum capacity Arsenic-Cum-Iron Removal Plant (AIRP) at Shyamnagar PWSS including 3 Months Trial Run & 3 Years O&M under Nadia Division, P.H.E. Dte. | 1588/ND | 06/03/2024 | 180 | MONDAL ENTERPRISE | 300.5 | 0 | 0 | 50
4450 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10082 | Augmentation | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | 704/PFMS | 30/03/2022 | 0 | TECHVISION | 2.87 | 0 | 0 | 0
4451 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10082 | Augmentation | Material Requisition To Resource Division | 431/ND | 31/01/2022 | 0 | Resource Division | 0.76 | 0 | 0 | 0
4452 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10082 | Augmentation | Material Requisition To Resource Division | 4306/ND | 29/09/2022 | 0 | Resource Division | 17.81 | 0 | 0 | 0
4453 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10082 | Augmentation | Augmentation of FHTC (Part-B) of Fazilnagar Pipe Water Supply Scheme. | 4903/ND | 10/09/2024 | 60 | PATHIK PABAN NANDI | 34.31 | 0 | 0 | 0
4454 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10082 | Augmentation | Laying of additional pipeline for Fazilnagar Mouza and Phulkhali Mouza under Fazilnagar PWSS and Arabpur PWSS".under Tehatta Sub-Division under Nadia Division P.H.Engineering Dte. | 4905/ND | 10/09/2024 | 90 | PATHIK PABAN NANDI | 41.67 | 0 | 0 | 0
4455 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10082 | Augmentation | Repairing existing Damage Pipe line from Fazilnagar Durgamandir Towards Lalnagar Under Fazilnagar PWSS.under Tehatta Sub-Division under Nadia Division P.H.Engineering Dte. | 1820/ND | 14/03/2024 | 90 | PATHIK PABAN NANDI | 29.99 | 0 | 0 | 0
4456 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10082 | Augmentation | Repairing of Existing Damage Pipe line from Fazilnagar towards Charmoktarpur via Pearpur under Fazilnagar PWSS under Nadia Division PHE Dte. | 4087/ND | 26/07/2024 | 60 | PATHIK PABAN NANDI | 33.36 | 0 | 0 | 0
4457 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10082 | Augmentation | Laying of additional pipeline for Fazilnagar Mouza and Anandapur Mouza under Fazilnagar PWSS and Anandapur PWSS under Tehatta Sub-Division under Nadia Division P.H.Engineering Dte. | 4904/ND | 10/09/2024 | 90 | PATHIK PABAN NANDI | 37.63 | 0 | 0 | 0
4458 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10082 | Augmentation | Laying distribution system for providing FHTC (Functional Household Tap Connection) by Augmentation & Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Fazil Nagar Piped Water Supply Scheme at Karimpur - II block under Nadia Division P.H.E. Dte. | 2005/ND | 05/05/2022 | 90 | PATHIK PABAN NANDI | 271.88 | 219.13 | 80.6 | 100
4459 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10082 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 117 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Fazilnagar PWSS under Nadia Division PHE Dte. | 1787/ND | 20/04/2023 | 886 | B.M. ENGINEERING & CONSTRUCTION | 118.29 | 0 | 0 | 30
4460 | NADIA | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. , SM/10082 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Fazilnagar PWSS under Karimpur-II Block under Tehatta Sub Division under Nadia Division-,P.H.E Dte. under Jal Jeevan Mission(JJM). | 424/ND | 27/01/2025 | 360 | REAL TIME | 34.74 | 0 | 0 | 60
4461 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn , SM/09960 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Betna Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Betna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 10) | 436/NAD-I | 07/03/2022 | 30 | B.M. ENTERPRISE | 25.11 | 21.53 | 85.75 | 100
4462 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn , SM/09960 | Augmentation | Construction of Boundary Wall Toilet Pathway and other work at Goalsalua Zone II WS Scheme within Ranaghat II Block under NAD-I PHE Dte ( Sl.no.05) | 1940 / NAD-I | 12/10/2022 | 60 | BUDDHADEV MONDAL | 12.94 | 6.89 | 53.22 | 50
4463 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn , SM/09960 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chak Dakshinpara & Fulbari villages at Hanskhali Block by retrofitting of Ground Water based PWSS for Betna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte.(Sl No. - 11) Tender No.- 224/NAD-I/2020-2021. | 294/NAD-I | 04/02/2021 | 45 | K.P. CONSTRUCTION | 43.55 | 18.21 | 41.8 | 0
4464 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn , SM/09960 | Augmentation | Construction of Boundary Wall Toilet Pathway and other allied work at Betna WS Scheme within Hanskhali Block under NAD I PHE Dte(Sl.no.11) | 1961/ NAD-I | 12/10/2022 | 45 | BANERJEE ENTERPRISE | 11.54 | 6.92 | 59.95 | 0
4465 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn , SM/09960 | Augmentation | Rejuvenation of Goalsalua (Z-i) PWSS regarding FHTC in Ranaghat II Block of Nadia Dist. | 926/EMD | 27/05/2022 | 365 | SUSANTA KUMAR DAS | 12.16 | 12.16 | 100 | 0
4466 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn , SM/09960 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Goalsalua Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Goalsalua Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 09) | 435/NAD-I | 07/03/2022 | 30 | MANISHIKA CONSTRUCTION | 23.94 | 20.88 | 100 | 100
4467 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn , SM/09960 | Augmentation | Repair of 250 cum capacity Over Head Reservoir Painting and Pump House at Goalsalua Zone II WS Scheme in Ranaghat II Block under NAD I PHE Dte (Sl.no.07) | 3036 /NAD-I | 09/11/2022 | 60 | TAPU SAHA | 20.13 | 17.91 | 100 | 100
4468 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn , SM/09960 | Augmentation | Construction of Boundary Wall, Toilet, Pathway and other allied work at Goalsalua Zone-I Water Supply Scheme within Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. ( SL.NO.13) | 3327/NAD-I | 15/12/2022 | 45 | M/S AKSHAY HALDER | 11.93 | 7.81 | 100 | 100
4469 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn , SM/09960 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BETNA W/S Scheme, Block-Hanskhali , Dist. - Nadia. NIET No. 39 of EE/EMD of 2022-23 (Sl. No.- 03) | 1603/EMD | 26/04/2023 | 30 | TALUKDER & CO. | 14.46 | 13.07 | 100 | 100
4470 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn , SM/09960 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HALALPUR KRISHNAPUR (Z-II),GOALSALUA(Z-I) & GOALSALUA(Z-II) W/S Scheme, Block- Ranaghat-II , Dist. - Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 01) | 1601/EMD | 26/04/2023 | 30 | M/S DILIP MITRA | 56.44 | 35.31 | 100 | 100
4471 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn , SM/09960 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Betna Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I, P.H.E Dte. in connection with Augmentation of Betna W/S Scheme under JJM (Sl.No.05) | 1378/NAD-I | 15/05/2023 | 25 | TAPAS GHOSH | 12.52 | 12.51 | 100 | 90
4472 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn , SM/09960 | Augmentation | Load enhancement at Betna ph-1 at Hanskhali Block, Dist.-Nadia | BP-27-24-25 | 24/05/2024 | 0 | W.B.S.E.D.C.LTD (CHITRASALI C.C.CENTER) | 1.27 | 0 | 0 | 0
4473 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn , SM/09960 | Augmentation | Water Supply Arrangment in High School, PrimarySchool, SSK & MSK under Jal Jeevan Mission (JJM) atGoalsalua (Zone-I) PWSS, Ranaghat-II Block by Augmentation of Goalsalua Zone-I &II underRanaghat-II Block & Betnaunder Hanskhali Block under Nadia Arsenic Division-I, PHE Dte (sl.10) | 205 /NAD-I | 15/02/2023 | 689 | M/S ASOKE GHOSH & BROTHERS | 90.79 | 44.8 | 68.82 | 30
4474 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-V (Purba Bishnupur), & Zone-IX (Ghetugachhi), at chakdaha Block, by retr , SM/09963 | Augmentation | Laying of UPVC pipeline at different location of Zone-II (Hapania) under Nagarukhra-I & II G.P. under 'surface water based piped water supply scheme of HARINGHATA & CHAKDAHA under Office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 88/AE-I/NAD-I | 28/04/2022 | 15 | TARUN KUMAR BHATTACHARYA | 4.84 | 0 | 0 | 90
4475 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-V (Purba Bishnupur), & Zone-IX (Ghetugachhi), at chakdaha Block, by retr , SM/09963 | Augmentation | Laying of UPVC pipeline at different location of Jalkar Bhomra (Zone-III) Madanpur (Zone-XII) Birohi (Zone-XI) under Kastodanga-I & II Madanpur-I & II Birohi-I G.P. respectively under 'surface water based piped water supply scheme of HARINGHATA & CHAKDAHA under Office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 89/AE-I/NAD-I | 28/04/2022 | 15 | AVINABA ENGINEERING CONCERN | 4.82 | 0 | 0 | 85
4476 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-V (Purba Bishnupur), & Zone-IX (Ghetugachhi), at chakdaha Block, by retr , SM/09963 | Augmentation | Phase-III FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX Ghetugachi, at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. ( Sl. no. 02) | 964/NAD-I | 07/07/2022 | 60 | B.S. ENTERPRISE | 65.97 | 52.76 | 79.98 | 100
4477 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-V (Purba Bishnupur), & Zone-IX (Ghetugachhi), at chakdaha Block, by retr , SM/09963 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-V, (Purba Bishnupur), Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 515/NAD-I | 28/03/2022 | 60 | APURBA MANDAL | 156.91 | 155.28 | 100 | 100
4478 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-V (Purba Bishnupur), & Zone-IX (Ghetugachhi), at chakdaha Block, by retr , SM/09963 | Augmentation | Repair of 800 cum capacity Over Head Reservoir Boundary Wall Switch Room and other allied works at Purba Bishnupur Zone-V under Chakdah Surface WS Scheme in Chakdah Block under NAD-I PHE Dte (Sl.no.11) | 1670/ NAD-I | 07/09/2022 | 60 | TAPU SAHA | 33.13 | 29.11 | 100 | 100
4479 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-V (Purba Bishnupur), & Zone-IX (Ghetugachhi), at chakdaha Block, by retr , SM/09963 | Augmentation | Repair of 350 cum capacity Over Head Reservoir Two Nos Painting and repairing of HW Boundary Wall, Pump House at Ghetugachi Zone IX under urface WS Scheme of Chakdah Part under NAD I PHE Dte (Sl.no.12) | 1985 / NAD-I | 18/10/2022 | 45 | U TURN CONSTRUCTION | 22.32 | 20.02 | 100 | 100
4480 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-V (Purba Bishnupur), & Zone-IX (Ghetugachhi), at chakdaha Block, by retr , SM/09963 | Augmentation | Retrofitting work at Tangra & Bagdob for augmentation of Surface water based PWSS for providing FHTC at Purba Bishnupur ( Zone V) of Surfac water based piped water supply scheme for Chakdah ( Part ) under JJM within Chakdah Block under Nadia Arsenic Division-I , PHE Dte. (SL.No.11) | 1400/NAD-I | 16/05/2023 | 25 | CHANDAN ROY | 47.15 | 43.79 | 100 | 100
4481 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-V (Purba Bishnupur), & Zone-IX (Ghetugachhi), at chakdaha Block, by retr , SM/09963 | Augmentation | Retrofitting work along Simurali-Kalibazar Road of Ghetugachi (Zone-IX) Water Supply Scheme under Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.08) | 1839/NAD-I | 07/08/2023 | 15 | PURNIMA ELECTRICS & DECORATORS | 9.19 | 7.72 | 100 | 100
4482 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-V (Purba Bishnupur), & Zone-IX (Ghetugachhi), at chakdaha Block, by retr , SM/09963 | Augmentation | Material Requisition To Resource Division | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 20.28 | 0 | 0 | 0
4483 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09968 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-II (Hapania) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 07) | 423/NAD-I | 07/03/2022 | 60 | SUMAN CHAKRABORTY | 85.3 | 80.85 | 100 | 100
4484 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09968 | Augmentation | Jackpushing of Clear Water Rising Main at Kalyani More Crossing at NH-34 and other allied works under Jal Jeevan Mission (JJM) for Zone-I Fatepur at Haringhta Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme for Zone-I, (Fatepur), Part-III under Nadia Arsenic Division-I, PHE Dte. (Sl.no.08) | 1283 /NAD-I | 08/05/2023 | 30 | GBC INFRASTRUCTURE PRIVATE LIMITED | 55.87 | 55.81 | 99.89 | 0
4485 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09968 | Augmentation | Repairing of existing structure of WTP and it's different units and other allied works under Zone-I (Fatepur) & Zone-II (Hapania) under Surface Based PWSS for Harinnghata & Chakdah (Part) under JJM under Zone-I & Zone-II, Part-III under Nadia Arsenic Division-I, PHE Dte. (Sl.10 | 998 /NAD-I | 17/04/2023 | 25 | SUMAN CHAKRABORTY | 45.59 | 45.49 | 99.79 | 0
4486 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09968 | Augmentation | Repair of 1100 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Hapania Zone-II under Surface W/S Scheme of Haringhata-Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte.(Sl. No. 04) | 3447/NAD-I | 21/12/2022 | 45 | B.S. ENTERPRISE | 37.53 | 37.46 | 100 | 100
4487 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09968 | Augmentation | Repair of 700 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House at Fatepur ZoneI under Surface WS Scheme of Haringhata Chakdah Part under NAD I PHE Dte (Sl.no.05) | 1817/ NAD-I | 26/09/2022 | 60 | SHYAMAL SHIL | 25.68 | 25.11 | 100 | 100
4488 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09968 | Augmentation | Repairing of existing structure of WTP and other alliedworks under Zone-I (Fatepur) & Zone-II (Hapania)under Surface Water Based PWSS for Haringhata&Chakdah(Part) under Zone-I (Fatepur) & Zone-II(Hapania), Part-III under Nadia Arsenic Division-I, P.H.E. Dte. (sl.11) | 200 / NAD-I | 15/02/2023 | 60 | SUMAN CHAKRABORTY | 63.13 | 62.91 | 100 | 55
4489 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09968 | Augmentation | Augmentation work for Zone-I (Fatepur) G.P. at Haringhata Block under Jal Jeevna Mission (JJM) by Augmentation of Surface Water Based PWSS forHaringhata & Chakdah (Part) for Zone-I (Fatepur) Part-III under Nadia Arsenic Division-I, PHE Dte. (SL.09) | 259/NAD-I | 20/02/2023 | 60 | BKB INFRA PROJECTS PRIVATE LIMITED | 40.51 | 40.51 | 100 | 100
4490 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09968 | Augmentation | Augmentation work at Panchkahania Mouza under JJM in connection with Augmentation of Zone-I (Fatepur) Part-III at Haringhata Block by Augmentation Surface Water Based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 266/AE-I/NAD-I | 05/06/2023 | 7 | M/S ARATI ENTERPRISE | 0.93 | 0.93 | 100 | 100
4491 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09968 | Augmentation | Augmentation work at Bhabanipur Mouza under JJM in connection with Augmentation of Zone-I (Fatepur) Part-III at Haringhata Block by Augmentation Surface Water Based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 268/AE-I/NAD-I | 05/06/2023 | 7 | MALI CONSTRUCTION | 0.9 | 0.9 | 100 | 100
4492 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09968 | Augmentation | Augmentation work at Satyapole Mouza under JJM in connection with Augmenation of Zone-I (Fatepur) Part-III at Haringhata Block by Augmentation Surface Water Based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte | 269/AE-I/NAD-I | 05/06/2023 | 7 | M/S ARATI ENTERPRISE | 0.89 | 0.89 | 100 | 100
4493 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09968 | Augmentation | Augmentation work at Behara Mouza under JJM in connection with Augmentation of Zone-I (Fatepur) Part-III at Haringhata Block by Augmentation Surface Water Based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 267/AE-I/NAD-I | 05/06/2023 | 7 | MALI CONSTRUCTION | 0.91 | 0.91 | 100 | 100
4494 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09968 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-I (Fatepur) at Haringhta Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-I, Fatepur,Part-III under Nadia Arsenic Division-I, PHE Dte. (sl.no.15) | 3515 / NAD-I | 09/01/2023 | 60 | MALI CONSTRUCTION | 97.06 | 97.01 | 100 | 70
4495 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme , SM/09968 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-II , Hapania at Nagarukhra G.P at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-II, Hapania, Part-III under Nadia Arsenic Division-I, PHE Dte. (sl. 18) | 303 /NAD-I | 27/02/2023 | 60 | MONDAL ENTERPRISE | 96.62 | 95.16 | 100 | 74
4496 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09260 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Maheshpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 526/NACD-II | 14/06/2021 | 45 | TARUN GHOSH | 66.44 | 132.76 | 200 | 100
4497 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09260 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Chenderghat W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 732/NACD-II | 13/09/2021 | 45 | SINGHA ROY & CO. | 65.96 | 131.79 | 200 | 100
4498 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09260 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection (Phase -I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipe line (Parallel or extension or damaged line repair) and Bamboo Pilling at Mahatpur(Vill- Pukura) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 641/NACD-II | 13/08/2021 | 45 | NILAY KUMAR BHATTACHARYA | 59.57 | 119.1 | 200 | 100
4499 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09260 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and Pump house repair at Gongra W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 859/EE/NACD-II | 08/11/2021 | 45 | PRIYA CONSTRUCTION | 53.27 | 0 | 0 | 100
4500 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09260 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-III W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 766/NACD-II | 22/09/2021 | 45 | SANDIP BISWAS | 84.78 | 169.54 | 200 | 100
4501 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09260 | Augmentation | Functional House Hold Tap Connection for providing connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Remaining School only) Gongra W/s Scheme at Chapra Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 438/NACD-II | 12/04/2023 | 20 | BIPLAB BHOWMICK | 1.47 | 0 | 0 | 100
4502 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09260 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and Pump house repair at Gongra W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 859/NACD-II | 08/11/2021 | 45 | PRIYA CONSTRUCTION | 53.27 | 0 | 0 | 0
4503 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09260 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Gongra Water Supply Scheme of capacity 58 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | 176/NACD-II | 07/02/2024 | 60 | ACQUA CONSTRUCTION CONSORTIUM | 177.79 | 0 | 0 | 0
4504 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09260 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Gongra Water Supply Scheme in CHAPRA Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 320_2/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.29 | 1.29 | 100 | 100
4505 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09260 | Augmentation | Sinking of 2 nos. 300 mm X 200 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at new proposed site of Gongra Zone-I and Zone-II in Chapra Block under Gongra Public Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 1527/NACD-II | 27/11/2024 | 270 | SANDIP BISWAS | 21.68 | 0 | 0 | 55
4506 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09260 | Augmentation | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Fatepur, Bahadurpur and Gongra Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1657/NACD-II | 30/12/2024 | 360 | CHANDAN ROY | 149.25 | 0 | 0 | 20
4507 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KADIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09262 | Augmentation | Construction of Boundary wall with Grill Gate at Kadipur Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | 44/AE-II/NACD-II | 17/02/2022 | 30 | SANJIT DAS | 4.99 | 4.99 | 99.91 | 100
4508 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KADIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09262 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Kadipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 265/NACD-II | 22/02/2021 | 21 | NILAY KUMAR BHATTACHARYA | 55.81 | 0 | 0 | 100
4509 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KADIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09262 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Kadipur & Taldaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 769/NACD-II | 22/09/2021 | 45 | B.M. ENGINEERING & CONSTRUCTION | 88.87 | 88.86 | 100 | 100
4510 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KADIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09262 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Kadipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 860/NACD-II | 08/11/2021 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 36.37 | 36.31 | 100 | 100
4511 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KADIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09262 | Augmentation | Construction of Soak pit for disposing of back wash water from IEP and also construction of pathway for smooth movement at Kadipur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 1017/NACD-II | 29/11/2022 | 20 | SANJIT DAS | 2 | 1.99 | 100 | 100
4512 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KADIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09262 | Augmentation | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Kadipur W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1194/NACD-II | 23/12/2022 | 15 | SANJIT DAS | 2.07 | 2.04 | 100 | 100
4513 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KADIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09262 | Augmentation | Functional House Hold Tap Connection for left out Household regarding Har Ghar Jal Certification including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Vill- Mukundapur) Kadipur W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 146/NACD-II | 17/01/2023 | 20 | CHANDRA NATH GHOSH | 1.61 | 1.61 | 100 | 100
4514 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KADIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09262 | Augmentation | Continuation Work Order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Kadipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 222/NACD-II | 05/04/2022 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 36.28 | 36.28 | 82.63 | 100
4515 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KADIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09262 | Augmentation | Continuation work order for Survey, Design, Drawing & DPR preparation for Kadipur Water Supply Scheme in Krishnaganj Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | 326_2/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.29 | 1.29 | 100 | 100
4516 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KADIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09262 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Kadipur Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 24/AE-II/NACD-II | 15/02/2024 | 15 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 0.97 | 0.95 | 100 | 100
4517 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KADIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09262 | Augmentation | Reparing of damaged Rising Main at Kadipur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 755/AE-I/NACD-II | 19/06/2024 | 15 | SANJIT DAS | 0.87 | 0.86 | 100 | 100
4518 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KADIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09262 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Kadipur & Taldaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | 52/NACD-II | 20/01/2022 | 45 | B.M. ENGINEERING & CONSTRUCTION | 27.75 | 0 | 0 | 100
4519 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KADIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09262 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Kadipur (Vill- Mukundapur, Kadaghata,Chak Pratappur) W/S Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 726/NACD-II | 10/06/2024 | 359 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 105.56 | 0 | 0 | 55
4520 | NADIA | Nadia Arsenic Civil Division II | AUGMENTATION OF GROUND BASED WATER BASED KADIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. , SM/09262 | Augmentation | Conversion of IEP to AIRP at KADIPUR Water Supply Scheme of capacity 55 Cu.m/hr in Krishnaganj Block & CHANDERGHAT, PANINALA & BARUIHUDA Water Supply Scheme under Nadia Arsenic Civil Division -II, PHE Dte. | 1147/NACD-II | 23/08/2024 | 60 | MERCURY ENGINEERING COMPANY. | 173.69 | 0 | 0 | 0
4521 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/10037 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | 630/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.11 | 0 | 0 | 0
4522 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/10037 | Augmentation | Continuation of Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period of 90 days w.e.f 01/07/2023 (as and when required). | 800/KSD | 16/06/2023 | 92 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 0
4523 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/10037 | Augmentation | Material Requisition To Resource Division | 2161/ND | 18/05/2022 | 0 | Resource Division | 214.18 | 0 | 0 | 0
4524 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/10037 | Augmentation | Material Requisition To Resource Division | 1396/ND | 24/03/2022 | 0 | Resource Division | 33.5 | 0 | 0 | 0
4525 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/10037 | Augmentation | Material Requisition To Resource Division | 4270/ND | 29/09/2022 | 0 | Resource Division | 8.85 | 0 | 0 | 0
4526 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/10037 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BARA ANDULIA W/S Scheme, Block- Chapra , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 03) | 407/EMD | 20/01/2023 | 30 | CONCORD ENGINEERING | 26.28 | 0 | 0 | 0
4527 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/10037 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 250 lVltrs' Depth) by utilizing Departmental Machineries for Bara Andulia w/s scheme (Z-t, T/w-l & ll) , Chapra Block under Nadia District, Central Drilling Division, p.H.E. Dte. | 1227/CDD | 04/09/2023 | 300 | MENAKA ENTERPRISE | 37.76 | 15.23 | 40.34 | 50
4528 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/10037 | Augmentation | Quotation for new service connection charges and security deposit for PH-4 under Bara-Andulia(Zone-I) w/s scheme, Under EMSD-III,PHE Dte,Nadia | BP-157-24-25 | 06/11/2024 | 0 | W.B.S.E.D.C.L (GROUP CHAPRA C.C.C) | 5.06 | 0 | 0 | 0
4529 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/10037 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction Of 750 Cum Capacity 20 Mtr. Staging Height Rcc Over Head Reservoir (Including Pile Foundation), Pipe Connection And Cost Of Pipes, Specials & Soil Investigation For Construction Of One No. 750 Cum Ohr Of Staging Height 20 Mtr. for Augmentation of Ground Based Water Supply Scheme at Bara Andulia-I to accommodate FHTC within Chapra block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 2055/ND | 10/05/2022 | 1332 | TARUN KUMAR BHATTACHARYA | 640.03 | 313.16 | 48.93 | 48
4530 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/10037 | Augmentation | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Bara Andulia Zone I Water Supply Scheme within Chapra block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 6115/ND | 21/12/2023 | 485 | SAHA ENGINEERS | 12.16 | 8.93 | 73.42 | 20
4531 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/10037 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 120 m3/hr at Bara Andulia Zone-I Water Supply Scheme within Chapra Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | 1899/ND | 15/03/2024 | 360 | HARBAUER INDIA (P) LTD. | 300.5 | 0 | 0 | 20
4532 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte , SM/10037 | Augmentation | Laying Of Additional Distribution System Including Specials to provide FHTC at Leftout Household in connection with JJM In Ground Based Piped Water Supply Scheme at Bara Andulia Zone I To Accommodate FHTC Within Chapra Block Under Krishnanagar Sub-division Under Nadia Division, PHE Dte. | 4504/ND | 18/09/2025 | 90 | S.S.INFRASTRUCTURE | 68.11 | 0 | 0 | 0
4533 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09697 | Retrofitting | Preparation of DPR for augmentation of existing Thanapara, (Block -Karimpur-II) piped water supply schemes | 150/AE-I/NACD-II | 16/11/2021 | 10 | UMWELT ENGINEER PVT LTD. | 3.88 | 3.88 | 100 | 100
4534 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09697 | Retrofitting | Preparation of DPR for augmentation of existing Thanapara (Phase-II), (Block -Karimpur-II) piped water supply schemes | 750/NACD-II | 15/09/2021 | 10 | SIRCON ENGINEERING SERVICE | 4.94 | 4.94 | 100 | 100
4535 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09697 | Retrofitting | Construction of Boundary wall with Grill Gate at Thanapara Water Supply Scheme 4th Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | 99/NACD-II | 10/02/2022 | 45 | TAPAN SAHA | 7.74 | 6.6 | 85.28 | 100
4536 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09697 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara (Vill- Saguna) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 03/NACD-II | 03/01/2022 | 45 | M/S SHILL & CO. | 88.07 | 0 | 0 | 100
4537 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09697 | Retrofitting | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 902./NACD-II | 22/11/2021 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 73.33 | 73.31 | 99.97 | 100
4538 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09697 | Retrofitting | Construction of Boundary wall with Grill Gate at Thanapara Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | 47/AE-II/NACD-II | 17/02/2022 | 30 | BISHAL CONSTRUCTION | 4.9 | 4.69 | 95.76 | 100
4539 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09697 | Retrofitting | Sinking of 1 no. 300 mm X 200 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at 4th pump house site with UPVC pipe (CD) & strainer, ( 300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Thanapara Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 91/NACD-II | 08/02/2022 | 45 | JOY HIND TUBEWELLS | 12.33 | 12.33 | 99.99 | 100
4540 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09697 | Retrofitting | Construction of Boundary wall with Grill Gate at Thanapara Water Supply Scheme 3rd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | 48/AE-II/NACD-II | 17/02/2022 | 30 | BIPLAB BHOWMICK | 3.64 | 3.63 | 100 | 100
4541 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09697 | Retrofitting | Outstanding as framed by Resource Division for supply of materials for augmentation/retrofitting of Thanapara, Damodarkhali & Madhabpur under Nadia Arsenic Civil Division-II, PHE dte. | 212, 213, 214 | 18/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 124.39 | 0 | 0 | 0
4542 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09697 | Retrofitting | SUPPLY OF MATERIALS FOR THANAPARA,DAMODARKHALI,MADHABPUR AND BALIADANGA W/S. SCHEME UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. |  | 07/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0 | 0
4543 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09697 | Retrofitting | OUTSTANDING BILL PAYMENT FOR SUPPLY OF MATERIALS FOR THANAPARA, DAMODARKHALI, MADHABPUR, BALIADANGA AS FRAMED BY RESOURCE DIVISION PHE DTE. |  | 05/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0 | 0
4544 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09697 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair, & also Rising Main replacement by DI pipe) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 529/NACD-II | 14/06/2021 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 78.79 | 78.72 | 100 | 100
4545 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09697 | Retrofitting | Supply of CIDF Sluice, Non return valves and DI Mechanical collar Vavle for relaying of rising main of Thanapara Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | 166/AE-I/NACD-II | 22/11/2021 | 7 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.97 | 4.97 | 100 | 100
4546 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09697 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair, & also Rising Main replacement by DI pipe) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 984/NACD-II | 27/12/2021 | 90 | MONDAL ENTERPRISE | 149.3 | 0 | 0 | 100
4547 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09697 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 01/EE/NACD-II | 03/01/2022 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 95.95 | 0 | 0 | 100
4548 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09697 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara (Vill- Saguna) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 03./NACD-II | 03/01/2022 | 45 | M/S SHILL & CO. | 88.07 | 0 | 0 | 100
4549 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10525 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Kamalpur Zone-I W/S Scheme in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte. | 1060/RSD | 02/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.64 | 4.64 | 100 | 100
4550 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10525 | Augmentation | Additional Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Kamalpur Zone-I W/S Scheme in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte. | 1119/RSD | 21/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 0.78 | 0.56 | 100 | 100
4551 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10525 | Augmentation | Material Requisition To Resource Division | 5104/ND | 08/12/2022 | 0 | Resource Division | 188.62 | 0 | 0 | 0
4552 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10525 | Augmentation | Material Requisition To Resource Division | 4301/ND | 29/09/2022 | 0 | Resource Division | 0.05 | 0 | 0 | 0
4553 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10525 | Augmentation | Material Requisition To Resource Division | 1859/ND | 26/04/2023 | 0 | Resource Division | 84.8 | 0 | 0 | 0
4554 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10525 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Kamalpur Zone-I piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | 1278(A)RSD | 04/10/2024 | 45 | KUHELI ENTERPRISE | 1.89 | 0 | 0 | 0
4555 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10525 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Kamalpur Zone-I to accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division P.H.Engineering Dte. | 3697/ND | 26/08/2022 | 90 | HANNAN BUILDERS PRIVATE LIMITED | 592.18 | 546.44 | 92.28 | 95
4556 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10525 | Augmentation | Laying 315 mm and 110 mm dia uPVC pipe line in place of damaged 315 mm and 110 mm dia uPVC pipe from Purba Naoapara to Kamalpur for smooth running of Ground Water Based Water Supply Scheme for Kamalpur Zone-I in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. | 910/RSD | 13/09/2023 | 30 | M/S BISWAS ENTERPRISE | 4.72 | 0 | 0 | 0
4557 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10525 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Kamalpur Zone-I under Ranaghat Sub-Division under Nadia Division PHE Dte. | 1418/RSD | 19/11/2024 | 45 | RENUKA ENTERPRISE | 2.15 | 0 | 0 | 100
4558 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10525 | Augmentation | Repairing of PH-III and Construction of Sanitary arrangement under augmentation of Kamalpur Zone-I under Ranaghat Sub-Division under Nadia Division PHE Dte. | 1419/RSD | 19/11/2024 | 45 | MAA ENTERPRISE | 2.15 | 0 | 0 | 100
4559 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10525 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at KAMALPUR ZONE-I W/S Scheme Block- Ranaghat-II under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10525] | 1137/EMD | 04/06/2025 | 90 | H.K. DAS & CO. | 52.38 | 0 | 0 | 0
4560 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-I to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10525 | Augmentation | Construction and installation of MANIFOLD and allied works at Head Works site under Kamalpur Zone-I Ground Based Water Supply Scheme under Ranaghat-II Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) | 2374/ND | 22/05/2025 | 90 | AREOCON | 11.89 | 0 | 0 | 0
4561 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Nischintapur water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07939 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Nischintapur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1072/NACD-II | 25/09/2020 | 15 | A.K ADHIKARY | 4.98 | 0 | 0 | 0
4562 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. , SM/10268 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. | 635/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.6 | 0 | 0 | 0
4563 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. , SM/10268 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of R.C.C. Elevated Reservoir of 600 Cum capacity (including pile foundation), Soil Investigation for construction of OHR, Construction of 1 No. Pump House at proposed Head Work site and Construction of boundary wall with gate all complete for Augmentation of Ground Based Water Supply Scheme at Bara Andulia Zone-II to accommodate FHTC within Chapra block under Krishnanagar Sub-division under Nadia Division, PHE Dte. | 3220/ND | 26/07/2023 | 366 | GHOSH ENTERPRISE | 467.16 | 0 | 0 | 0
4564 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. , SM/10268 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilizing Departmental Machineries for Bara Andulia W/S Scheme (Z-II, T/W-I) , Chapra Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 1231/CDD | 04/09/2023 | 30 | MENAKA ENTERPRISE | 18.88 | 0 | 0 | 0
4565 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. , SM/10268 | Augmentation | Material Requisition To Resource Division | 82/ND | 05/01/2023 | 0 | Resource Division | 234.57 | 0 | 0 | 0
4566 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. , SM/10268 | Augmentation | Supply, Delivery and Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under Bara Andulia Z-II) WS Scheme, Block-Chapra , Dist. - Nadia. | 4713/EMD | 04/08/2023 | 30 | INDTECH ASSOCIATES | 29.24 | 6.89 | 23.57 | 60
4567 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. , SM/10268 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 1.4 | 98.71 | 40
4568 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. , SM/10268 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 116 m3/hr at Bara Andulia Zone-II Water Supply Scheme within Chapra Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | 7090/ND | 05/12/2024 | 180 | APURBA MANDAL | 288.79 | 0 | 0 | 0
4569 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. , SM/10268 | Augmentation | Material Requisition To Resource Division | 258/ND | 11/01/2024 | 0 | Resource Division | 10.9 | 0 | 0 | 0
4570 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. , SM/10268 | Augmentation | Quotation for new service connection charges and security deposit for PH-3 under Bara-Andulia(Zone-I) w/s scheme, Under EMSD-III,PHE Dte,Nadia | BP-158-24-25 | 06/11/2024 | 0 | W.B.S.E.D.C.L (GROUP CHAPRA C.C.C) | 3.71 | 0 | 0 | 0
4571 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Sinking of 3 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site and 3rd Tubewell site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Panchdara Abhaynagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 431/NACD-II | 07/07/2022 | 45 | JOY HIND TUBEWELLS | 32.55 | 28.25 | 100 | 100
4572 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Earth work in filling in ditches at Panchdara Abhaynagar H/W Site for development of land in connection with proposed T/W Sinking & Pump House construction at Panchdara Abhaynagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | 61/AE-II/NACD-II | 28/06/2022 | 20 | VAI ENTERPRISE | 4.75 | 4.74 | 100 | 100
4573 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
4574 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
4575 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Panchdhara Abhaynagar 3rd Tubewell Site within Panchdhara Abhaynaga Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 128/NACD-II | 11/01/2023 | 60 | JOY GURU ENTERPRISE | 4.5 | 4.2 | 93.29 | 90
4576 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Construction of 600 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Panchdara Abhaynagar water supply scheme of Tehatta-II Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | 540/NACD-II | 10/05/2023 | 366 | AMIT KUMAR BOSE | 155.99 | 0 | 0 | 0
4577 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Panchdara Abhaynagar water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 256/NACD-II | 25/04/2022 | 60 | PARTHA DAS | 5.37 | 5.37 | 100 | 100
4578 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Panchdara Abhaynagar water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | 10/AE-II/NACD-II | 11/04/2022 | 60 | PARTHA DAS | 2.83 | 2.83 | 100 | 100
4579 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-3 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Panchdara Abhaynagar water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia | 11/AE-II/NACD-II | 11/04/2022 | 60 | PARTHA DAS | 2.83 | 2.83 | 100 | 100
4580 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Panchdara Abhaynagar Water Supply Scheme of Tehatta-II Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 629/NACD-II | 06/09/2022 | 20 | RAMASISH ENTERPRISE | 6.88 | 6.88 | 100 | 100
4581 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Material Requisition To Resource Division | 416/NACD-II | 05/07/2022 | 0 | Resource Division | 3 | 0 | 0 | 0
4582 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Material Requisition To Resource Division | 400/NACD-II | 04/07/2022 | 0 | Resource Division | 40.34 | 0 | 0 | 0
4583 | NADIA | Eastern Mechanical | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Electricity bill for new service connection at Panchdhara Abhaynagar | 148/PFMS/EMD | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.13 | 0 | 0 | 0
4584 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL | 235/2 | 21/02/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0 | 0
4585 | NADIA | Eastern Mechanical | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Electricity bill for new service connection at panchdhara abhaynagar | 146/PFMS/EMD | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.71 | 0 | 0 | 0
4586 | NADIA | Eastern Mechanical | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Shifting of 1 Nos. PCC pole along with LTOH line for obstruction in construction work by PHE dept. | BP-91-23-24 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.12 | 0 | 0 | 0
4587 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Restoration of road flank of Plassey Betai road from 12.50 Kmp to 16.50 Kmp at Panchdhara Avaynagar w/s. scheme Block Tehatta-II under Nadia Arsenic Civil Division II, PHE Dte against estimate order No. 1450 DT. 21.08.2023 & this office memo no. 890/ NACD-II dt. 21.08.2023 |  | 07/09/2023 | 0 | EXECUTIVE ENGINEER,NADIA HIGHWAY DIVISION NO-I, P.W.(ROADS) DIRECTORATE | 39.9 | 0 | 0 | 0
4588 | NADIA | Eastern Mechanical | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Electricity bill for new service connection at panchdhara abhaynagar | 147/PFMS/EMD | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.52 | 0 | 0 | 0
4589 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. | 23 | 19/04/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
4590 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Regarding restoration of flank of Plassey Betai Road from 12.50 Kmp to 16.50 Kmp | 152 | 08/09/2023 | 0 | EXECUTIVE ENGINEER,NADIA HIGHWAY DIVISION NO-I, P.W.(ROADS) DIRECTORATE | 20 | 0 | 0 | 0
4591 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Panchdara Abhynagar and adjoining mouzas under Panchdara Abhynagar Water Supply Scheme of Tehatta-II Block, under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | 460/NACD-II | 18/07/2022 | 90 | GHOSH BROTHERS | 520.23 | 350.38 | 67.35 | 80
4592 | NADIA | Eastern Mechanical | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.III under Panchdara W/S Scheme (Block : Tehatta-II) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 15) | 6254/EMD | 19/11/2022 | 30 | HARA PROSAD DAS | 10 | 9.07 | 90.7 | 70
4593 | NADIA | Eastern Mechanical | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.II under Panchdara W/S Scheme (Block : Tehatta-II) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 14) | 6255/EMD | 19/11/2022 | 30 | MASSK ENGINEERING WORKS | 9.96 | 0 | 0 | 80
4594 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Panchdhara Abhaynagar 2nd Tubewell Site within Panchdhara Abhaynaga Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 127/NACD-II | 11/01/2023 | 60 | VAI ENTERPRISE | 5.7 | 4.78 | 83.83 | 90
4595 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Panchdhara Abhaynagar Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | 88/NACD-II | 10/01/2023 | 60 | SHYAM SUNDAR SAHA | 15.89 | 11.53 | 72.58 | 90
4596 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 113 cum/Hour capacity for Panchdara Abhaynagar Water Supply Scheme within Tehatta-II block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1031/NACD-II | 02/08/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 282.81 | 0 | 0 | 0
4597 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-II Block of Nadia District through Jadavpur University. (Name of PWSS Panchdhara Abhynagar) | 1263/NACD-II | 09/11/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
4598 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Material Requisition To Resource Division | 80/NACD-II | 15/01/2024 | 0 | Resource Division | 13.52 | 0 | 0 | 0
4599 | NADIA | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Laying of Rising Main of Panchdara Abhyanagar Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | 23/AE-II/NACD-II | 18/04/2022 | 1191 | PARTHA DAS | 4.96 | 0 | 0 | 100
4600 | NADIA | Eastern Mechanical | PANCHDARA ABHYNAGAR PIPED W/S SCHEME , SM/10613 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) under Panchdara W/S Scheme (Block : Tehatta-II) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 13) | 6256/EMD | 19/11/2022 | 30 | BISALAXMI ENTERPRISE | 9.99 | 8.15 | 85.45 | 100
4601 | NADIA | Nadia Division | Providing FHTC at Ground Water based Senpur Water Supply Scheme within Krishnagar-1 Block (Phase-1) of Retrofitting. , SM/07490 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT SENPUR W/S SCHEME | 460/DW | 30/03/2021 | 0 | M/S KALIMATA ENTERPRISE | 67.02 | 0 | 0 | 0
4602 | NADIA | Nadia Division | Providing FHTC at Ground Water based Senpur Water Supply Scheme within Krishnagar-1 Block (Phase-1) of Retrofitting. , SM/07490 | Retrofitting | Laying of D I Pipe line in place of UPVC pipe including other allied works from OHR to both side of head work site for providing FHTC under Jal Swapna at Subarnabehar w/s scheme under Nadia Division PHED. | 215/PH | 12/07/2022 | 30 | SURAJIT KUMAR GHOSH | 4.65 | 2.66 | 100 | 92
4603 | NADIA | Nadia Division | Providing FHTC at Ground Water based Senpur Water Supply Scheme within Krishnagar-1 Block (Phase-1) of Retrofitting. , SM/07490 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 7.34 | 100 | 81
4604 | NADIA | Nadia Division | Providing FHTC at Ground Water based Senpur Water Supply Scheme within Krishnagar-1 Block (Phase-1) of Retrofitting. , SM/07490 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Senpur W/S scheme (Phase-I) of Rectrofitting in Nadia District under Nadia Division P.H.E. Dte. | 62/ND | 07/01/2021 | 90 | M/S KALIMATA ENTERPRISE | 96.97 | 0 | 0 | 100
4605 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10568 | Augmentation | Material Requisition To Resource Division | 5172/ND | 13/12/2022 | 0 | Resource Division | 6.18 | 0 | 0 | 0
4606 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10568 | Augmentation | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | 49/PFMS | 22/06/2022 | 0 | HORIZEN | 2.69 | 0 | 0 | 0
4607 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10568 | Augmentation | Material Requisition To Resource Division | 4279/ND | 29/09/2022 | 0 | Resource Division | 8.45 | 0 | 0 | 0
4608 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10568 | Augmentation | Material Requisition To Resource Division | 1867/ND | 26/04/2023 | 0 | Resource Division | 23.96 | 0 | 0 | 0
4609 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10568 | Augmentation | Material Requisition To Resource Division | 2323/ND | 29/05/2023 | 0 | Resource Division | 8.45 | 0 | 0 | 0
4610 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10568 | Augmentation | Balance Laying distribution system for augmentation of Ground Water Based Water Supply Scheme for Banpur to accommodate FHTC in Krishnaganj block of Nadia District under Nadia Division P.H. Engineering Dte. | 123/RSD | 29/01/2024 | 30 | A.P. POWER & CONCRETE | 4.76 | 0 | 0 | 100
4611 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10568 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Banpur piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | 1143/RSD | 11/09/2024 | 45 | ILA CONSTRUCTION | 1.89 | 0 | 0 | 85
4612 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10568 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at BANPUR W/S Scheme Block- KRISHNAGANJ under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10568] | 1143/EMD | 04/06/2025 | 90 | AHALYA ENGINEERING WORKS | 37.79 | 0 | 0 | 0
4613 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10568 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under Augmentation of Banpur PWSS. | 205/RSD | 06/02/2025 | 45 | ABHAYANANDA ENTERPRISE | 2.52 | 0 | 0 | 100
4614 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10568 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
4615 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BANPUR PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/10568 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Banpur to accommodate FHTC in Krishnaganj block of Nadia District under Nadia Division P.H.Engineering Dte. | 4041/ND | 19/09/2022 | 590 | A.P. POWER & CONCRETE | 146.68 | 137.1 | 99.87 | 96
4616 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S , SM/09972 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Beharia, Nabla, Goalpur Zone-I and Goalpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla, Goalpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 05) | 421/NAD-I | 07/03/2022 | 60 | CHOWDHURY & CO. | 95.27 | 90.4 | 100 | 100
4617 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S , SM/09972 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Nabla, Part-IV at Santipur block by retrofitting/augmentation of Ground Water Based PWSS for Nabla W/S scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 18) | 1319/NAD-I | 04/08/2022 | 30 | CHOWDHURY & CO. | 55.7 | 55.69 | 100 | 100
4618 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S , SM/09972 | Augmentation | Repair of 550 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House and AIRP at Beharia WS Scheme Santipur Block under NAD PHE Dte (Sl.no.01) | 1831 / NAD-I | 27/09/2022 | 45 | PALCON | 24.15 | 24.1 | 100 | 100
4619 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S , SM/09972 | Augmentation | Construction of Boundary wall , Toilet, Pathway and other allied work at Goalpur Z-II WAter Supply scheme within Santipur block under Nadia Arsenic Division -I , P.H.E.Dte. ( Sl.no. 01) | 219 / AE-I/NAD-I | 02/09/2022 | 30 | BUDDHADEB MONDAL | 0.97 | 0.97 | 100 | 100
4620 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S , SM/09972 | Augmentation | Repair of 136 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall Pump House and AIRP at Nabla W/S Scheme Santipur Block under NAD- I PHE Dte (Sl.no.03) | 1799 /NAD-I | 26/09/2022 | 45 | M/S S & P CONSTRUCTION | 15.29 | 15.24 | 100 | 100
4621 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S , SM/09972 | Augmentation | Repair of 100 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Goalpur, Zone-I W/S Scheme of Santipur Block under NAD- I, PHE Dte ( Sl.no.18) | 1725 / NAD-I | 13/09/2022 | 45 | MONDAL ENTERPRISE | 11.12 | 11.09 | 100 | 100
4622 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S , SM/09972 | Augmentation | Construction of Boundary Wall, Toilet, Pathway and other allied work at Nabla W/S Scheme within Santipur Block under NAD I PHE Dte (sl.no. 15) | 3093/NAD-I | 21/11/2022 | 45 | G S CONSTRUCTION AND CO. | 14.24 | 14.12 | 100 | 100
4623 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S , SM/09972 | Augmentation | Construction of Boundary wall Toilet Pathway and other allied work at Goalpur Zone I WS Scheme within Santipur Block under Nadia Arsenic Division-I, PHE Dte ( Sl.No.02) | 1798 / NAD-I | 26/09/2022 | 45 | N.H. ENTERPRISE | 14.18 | 14.08 | 100 | 100
4624 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S , SM/09972 | Augmentation | Repair of 700 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House and AIRP at Goalpur Zone-II under Nadia Arsenic Division -I, P.H.E.DTE. | 3157 / NAD-I | 25/11/2022 | 60 | DAS CONSTRUCTION | 11.08 | 11.04 | 100 | 100
4625 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S , SM/09972 | Augmentation | Construction of Boundary Wall, Toilet, Pathway and other allied work at Beharia W/S Scheme within Santipur Block under NAD I PHE Dte (sl.no.16) | 2010 / NAD-I | 19/10/2022 | 45 | S S CONSUTANCYAND CONSTRUCTION | 13.08 | 13.05 | 100 | 100
4626 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S , SM/09972 | Augmentation | Augmentation work of laying of UPVC and M.S. pipeline and other allied works at Goalpur mouza under Jal Jeevan Mission (JJM) under Goalpur Zone-II, Part-III at Santipur Block under Ground Water Based PWSS for Goalpur Zone-II under Nadia Arsenic Division-I, P.H.E. Dte. (sl.17) | 536 / NAD-I | 13/03/2023 | 21 | CHOWDHURY & CO. | 14.94 | 14.94 | 100 | 30
4627 | NADIA | Central Drilling | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S , SM/09972 | Augmentation | Providing Drilling Crew and other allied works for construction of TW (250mm x 150mm x 300mtr. depth) by utilising Departmental Machineries for Goalpur WS Scheme (Z-II), Santipur-I Block under Nadia District, CDD,PHE Dte. | 1452/CDD | 30/11/2022 | 30 | M/S SAIKAT ENTERPRISE | 15.55 | 10.86 | 100 | 0
4628 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S , SM/09972 | Augmentation | Construction and installation of MANIFOLD andallied works at OHR site under Behria Ground Based Water Supply Scheme under Santipur under Office of Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. in connection with Augmentation under JJM under Beharia Part-III, Piped Water Supply Scheme (Sl.no.33) | 1364/NAD-I | 12/05/2023 | 15 | DEBASISH DEY | 12.2 | 5.49 | 100 | 100
4629 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S , SM/09972 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Malipota. Phulia Para at Santipur block by retrofitting of Ground Water Based PWSS for Beharia W/S Scheme under Nadia Arsenic Division- I, PHE Dte (Sl.no.12) | 2121/NAD-I | 04/09/2023 | 21 | CHOWDHURY & CO. | 12.91 | 12.86 | 100 | 100
4630 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-II to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10596 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Kamalpur Zone-II W/S Scheme in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte. | 1061/RSD | 02/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.64 | 2.95 | 100 | 100
4631 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-II to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10596 | Augmentation | Material Requisition To Resource Division | 1516/ND | 04/04/2023 | 0 | Resource Division | 0.96 | 0 | 0 | 0
4632 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-II to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10596 | Augmentation | Material Requisition To Resource Division | 1860/ND | 26/04/2023 | 0 | Resource Division | 12.64 | 0 | 0 | 0
4633 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-II to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10596 | Augmentation | Material Requisition To Resource Division | 2286/ND | 29/05/2023 | 0 | Resource Division | 1.29 | 0 | 0 | 0
4634 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-II to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10596 | Augmentation | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Kamalpur Z-II Water Supply scheme Ranaghat-II block in Nadia District under Nadia Division P.H.E. Dte. | 5701/ND | 03/11/2021 | 1123 | PRIYA CONSTRUCTION | 63.6 | 0 | 0 | 100
4635 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-II to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10596 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Kamalpur Zone-II under Ranaghat Sub-Division under Nadia Division PHE Dte. | 1420/RSD | 19/11/2024 | 45 | M/S DAYANIDHI CONSTRUCTIONS | 2.15 | 0 | 0 | 100
4636 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-II to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10596 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at KAMALPUR ZONE-II W/S Scheme Block- Ranaghat-II under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10596] | 1148/EMD | 04/06/2025 | 90 | M/S. G.P. ENTERPRISE | 29.62 | 0 | 0 | 0
4637 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KAMALPUR ZONE-II to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. , SM/10596 | Augmentation | Augmentation of Ground Water Based piped Water Supply scheme for Kamalpur Zone-II to accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division P.H.E. Dte. | 893/ND | 02/03/2023 | 810 | CHOWDHURY & CO. | 94.41 | 19.07 | 20.94 | 85
4638 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Nrisinghapur Ground Water Based Piped Water Supply Scheme , Block-Santipur, District-Nadia. , SM/10651 | Augmentation | Material Requisition To Resource Division | 3155/NAD_I | 25/11/2022 | 0 | Resource Division | 57.42 | 0 | 0 | 0
4639 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Nrisinghapur Ground Water Based Piped Water Supply Scheme , Block-Santipur, District-Nadia. , SM/10651 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Nrisinghapur Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM of Nrisinghapur Piped W/S Scheme (sl.15) | 1159 /NAD-I | 28/04/2023 | 15 | CHOWDHURY & CO. | 13.02 | 0 | 0 | 0
4640 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Nrisinghapur Ground Water Based Piped Water Supply Scheme , Block-Santipur, District-Nadia. , SM/10651 | Augmentation | Collection of Household data through mobile app for FHTC Connection at Following schemes under Nadia Arsenic Division-I PHE Dte. Schemes:- i)Nrisinghapur ii)Gobindapur Zone-I iii)Gobindapur Zone-II | 167/AE-I/NAD-I | 12/04/2023 | 15 | HORIZEN | 4.84 | 4.84 | 100 | 44
4641 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Nrisinghapur Ground Water Based Piped Water Supply Scheme , Block-Santipur, District-Nadia. , SM/10651 | Augmentation | Road Restoration Work along PMGSY Road under Nrisinghapur Ground Water Supply Scheme at Santipur Block under Nadia Arsenic Division-I, PHE Dte. | 2595/NAD-I | 17/11/2023 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 48.14 | 26.09 | 100 | 100
4642 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Nrisinghapur Ground Water Based Piped Water Supply Scheme , Block-Santipur, District-Nadia. , SM/10651 | Augmentation | Providing FHTC under Jaldhara/Jal Swapna for Nrisinghapur at Santipur Block by augmentation of Ground water Based PWSS for Nrisinghapur W/S Scheme under Nadia Arsenic Division -I ,P.H.E.Dte.(Sl.No.05) | 1689 / NAD-I | 08/09/2022 | 45 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 864.56 | 856.94 | 100 | 75
4643 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia , SM/10660 | Augmentation | Material Requisition To Resource Division | 3155/NAD_I | 25/11/2022 | 0 | Resource Division | 52.05 | 0 | 0 | 0
4644 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia , SM/10660 | Augmentation | Material Requisition To Resource Division | 108/NAD-I | 31/01/2023 | 0 | Resource Division | 92.4 | 0 | 0 | 0
4645 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia , SM/10660 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well at Pump House No.-I and II ,Zone-I and New Tube Well at Pump House No.-III, Zone-I in connection to Accommodate FHTC under Gobindapur ground water based water supply scheme under Block_ Santipur Dist. - Nadia under EMD, PHE Dte. [SM-10660] | 2681/EMD | 20/11/2024 | 30 | M/S. G.P. ENTERPRISE | 20.56 | 0 | 0 | 0
4646 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia , SM/10660 | Augmentation | Augmentation work at villages Panchpota, Koehua Para, Bagdia, Beale Danda, Promoth Nagar in connection with Augmentation of Ground Water Based Piped Water Supply Scheme for Gobindapur Zone-I at Santipur Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.No.05) | 1379/NAD-I | 15/05/2023 | 30 | ALOK ENTERPRISE | 49.8 | 43.95 | 100 | 80
4647 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia , SM/10660 | Augmentation | Augmentation of Rising main line at Gobindapur zone-I in connection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. (sL.NO.16) | 2301/NAD-I | 29/09/2023 | 15 | M/S DIPAK ENTERPRISE | 18.43 | 18.37 | 100 | 100
4648 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia , SM/10660 | Augmentation | Providing FHTC under Jaldhara/Jalswapna for Gobindapur Z-I Santipur Bolck by Augmentation of Ground Water Based PWSS for Gobindapur Z-I W/S scheme under Nadia Arsenic Division-I , P.H.E.Dte (Sl.no.04) | 1672 / NAD-I | 07/09/2022 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 534.08 | 329.34 | 65.87 | 70
4649 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia , SM/10660 | Augmentation | "Retrofitting work at villages Batangachi, Barajiakur and Bagdiain connection with Retrofitting of Ground Water Based PWSS for Goibindapur Zone-II at Santipur Block under Nadia Arsenic Division-I,PHE Dte."(Sl.no.02) | 1380/NAD-I | 15/05/2023 | 1430 | SAHA ENGINEERS | 60.15 | 16.34 | 73.68 | 26
4650 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia , SM/10660 | Augmentation | Conversion of IEP to AIRP (Pressure Type) at Gobindapur, Zone-I W/S Scheme under Santipur Block of capacity 110 cum/hr. under augmentation of Gobindapur, Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte.(Sl.no.06) | 1902/NAD-I | 14/08/2023 | 818 | MULTITEX ENGINEERING INDUSTRIES | 159.34 | 58.16 | 36.5 | 60
4651 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia , SM/10660 | Augmentation | Retrofitting Pipeline work for providing FHTC (Functional Household Tap Connection) and dedicated line from manifold at Shantipur Block of Ground Water Based PWSS for Gobindapur (Zne-I & II) W/S Scheme inconnection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, P.H.E. Dte. | 2751/NAD-I | 11/12/2023 | 983 | SAHA ENGINEERS | 15.75 | 0 | 0 | 85
4652 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-I BLOCK-Santipur, Dist-Nadia , SM/10660 | Augmentation | Providing Boundary Illumination with allied works at GOBINDAPUR ZONE-I under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/10660) | 1153/EMD | 04/06/2025 | 90 | M/S DAS ENTERPRISE | 4.34 | 0 | 0 | 0
4653 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-XII (BALAGARICHAR), WTP & INTAKE at Chakdaha Block, by retrofitting of , SM/09936 | Augmentation | Repair Renovation of Chakdah WTP and intake with different units and Boundary Wall of WTP under Surface W/S Scheme of Chakdah (Part) block under Nadia Arsenic Division-I PHE Dte (Sl. NO. 09) | 1533/NAD-I | 31/08/2022 | 60 | PALCON | 52.63 | 44.03 | 100 | 95
4654 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-XII (BALAGARICHAR), WTP & INTAKE at Chakdaha Block, by retrofitting of , SM/09936 | Augmentation | Phase-III FHTC ((Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-XII, (Balagarichar) at Chakdah Block by retrofitting of Surface Water Based PWSS for Chakdah (Part) Water Supply under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 12) | 3043/NAD-I | 09/11/2022 | 45 | M/S A.K. CONSTRUCTION | 33.39 | 32.59 | 100 | 100
4655 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-XII (BALAGARICHAR), WTP & INTAKE at Chakdaha Block, by retrofitting of , SM/09936 | Augmentation | Repair of 250 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at BalagariChar Zone-XII under Surface W/S Scheme of Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte (Sl.no.03) | 1763 / NAD-I | 19/09/2022 | 45 | BISHALAXMI ENTERPRISE | 20.08 | 19.34 | 100 | 100
4656 | NADIA | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-XII (BALAGARICHAR), WTP & INTAKE at Chakdaha Block, by retrofitting of , SM/09936 | Augmentation | Interconnection between node point 3 and 76 of Balagarichar W/S Scheme for augmentation work at Uttar Ghughia village under Chakdah (Part) Water supply scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.04) | 1412/NAD-I | 18/05/2023 | 30 | MESSRS FREEDOM CONSTRUCTION | 62.36 | 42.96 | 100 | 100
4657 | NADIA | Nadia Arsenic Division I | Detailed Project Report on retrofitting of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-II BLOCK-Santipur, Dist-Nadia. , SM/09941 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Gobindapur Zone-II at Santipur Block by retrofitting of Ground Water based PWSS for Gobindapur W/S Scheme under Nadia Arsenic Division-I, P.H.E Dte. (Sl. No. 02) | 765/NAD-I | 07/06/2022 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 637.9 | 632.37 | 99.13 | 100
4658 | NADIA | Nadia Arsenic Division I | Detailed Project Report on retrofitting of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-II BLOCK-Santipur, Dist-Nadia. , SM/09941 | Retrofitting | Material Requisition To Resource Division | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 28.78 | 0 | 0 | 0
4659 | NADIA | Nadia Arsenic Division I | Detailed Project Report on retrofitting of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-II BLOCK-Santipur, Dist-Nadia. , SM/09941 | Retrofitting | Material Requisition To Resource Division | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 12.69 | 0 | 0 | 0
4660 | NADIA | Nadia Arsenic Division I | Detailed Project Report on retrofitting of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-II BLOCK-Santipur, Dist-Nadia. , SM/09941 | Retrofitting | Construction and installation of MANIFOLD and allied works at OHR site under Gobindapur Zone-II Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection with Retrofitting under JJM under Gobindapur Zone-II Piped W/S Scheme (Sl.no.32) | 1363/ NAD-I | 12/05/2023 | 15 | SANDIP ROY | 12.75 | 0 | 0 | 100
4661 | NADIA | Nadia Arsenic Division I | Detailed Project Report on retrofitting of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-II BLOCK-Santipur, Dist-Nadia. , SM/09941 | Retrofitting | Repair of 550 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House repair, Construction of Rigid Pavement and Boundary Wall for 2nd & 3rd T/W site at Gobindapur Zone-II Water Supply Scheme in Santipur Block under Nadia Arsenic Division-I, PHE Dte. (sl.no.14) | 3448 / NAD-I | 21/12/2022 | 1572 | THE CALCUTTA CONSTRUCTION | 38.03 | 14.71 | 38.69 | 100
4662 | NADIA | Nadia Arsenic Division I | Detailed Project Report on retrofitting of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-II BLOCK-Santipur, Dist-Nadia. , SM/09941 | Retrofitting | "Retrofitting work at villages Batangachi, Barajiakur and Bagdiain connection with Retrofitting of Ground Water Based PWSS for Goibindapur Zone-II at Santipur Block under Nadia Arsenic Division-I,PHE Dte."(Sl.no.02) | 1380/NAD-I | 15/05/2023 | 1430 | SAHA ENGINEERS | 60.15 | 0 | 0 | 26
4663 | NADIA | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME , SM/12624 | New | Material Requisition To Resource Division | 1085/NACD-II | 09/12/2022 | 0 | Resource Division | 26.69 | 0 | 0 | 0
4664 | NADIA | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME , SM/12624 | New | Sinking of 2 nos. 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Hridaypur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 1134/NACD-II | 16/12/2022 | 30 | JOY HIND TUBEWELLS | 21.46 | 20.98 | 97.75 | 100
4665 | NADIA | Eastern Mechanical | HRIDAYPUR PIPED WATER SUPPLY SCHEME , SM/12624 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under HRIDAYPUR W/S Scheme (Block : Tehatta I) Dist.- Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 11) | 1610/EMD | 26/04/2023 | 30 | SARKAR ELECTRICAL | 19 | 0 | 0 | 0
4666 | NADIA | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME , SM/12624 | New | Securitization arrangement by composite RCC Masonry structures without harming the T & P in the proposed sites of Hridaypur water supply scheme under Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia | 1396/NACD-II | 13/12/2023 | 45 | PAPAN ROY | 25.75 | 0 | 0 | 0
4667 | NADIA | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME , SM/12624 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Hridaypur) | 892/NACD-II | 21/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
4668 | NADIA | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME , SM/12624 | New | Material Requisition To Resource Division | 377/NACD-II | 24/03/2023 | 0 | Resource Division | 17.35 | 0 | 0 | 0
4669 | NADIA | Eastern Mechanical | HRIDAYPUR PIPED WATER SUPPLY SCHEME , SM/12624 | New | New Service connection under AE-III Hridaypur | BP-95-23-24 | 31/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.17 | 0 | 0 | 0
4670 | NADIA | Eastern Mechanical | HRIDAYPUR PIPED WATER SUPPLY SCHEME , SM/12624 | New | New Service Connection under AE-III Hridaypur | BP-96-23-24 | 31/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.64 | 0 | 0 | 0
4671 | NADIA | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME , SM/12624 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL | 235/3 | 21/02/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
4672 | NADIA | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME , SM/12624 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. | 23 | 19/04/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.04 | 0 | 0 | 0
4673 | NADIA | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME , SM/12624 | New | Soil Investigation for Construction of 01 (One) No of Overhead Reservoir, Construction of 01 (One) No of 400 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap, Laying of Distribution system including providing Functional House Hold Tap Connection (FHTC) and Laying of Rising Main and other necessary allied works at Hridaypur Water Supply Scheme and other necessary allied works in this connection of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 466/NACD-II | 20/04/2023 | 366 | RADIANT | 591.46 | 134.67 | 22.77 | 26
4674 | NADIA | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME , SM/12624 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 73 cum/Hour capacity for Hridaypur Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1052/NACD-II | 07/08/2024 | 180 | ALOK ENTERPRISE (A UNIT OF SAKETTREXIM PVT LTD.) | 212.91 | 0 | 0 | 0
4675 | NADIA | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME , SM/12624 | New | Portal framed structural arrangement as well as Water supply/Sanitation arrangement and left out hydraulics in the proposed sites of Hridaypur Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II, PHE Dte. Nadia. | 431/NACD-II | 15/03/2024 | 45 | BIPLAB BHOWMICK | 11.31 | 0 | 0 | 0
4676 | NADIA | Eastern Mechanical | HRIDAYPUR PIPED WATER SUPPLY SCHEME , SM/12624 | New | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at HRIDAYPUR Piped Water Supply Scheme, Block_ Krishnagar-I, Dist. Nadia Under EMD, PHE Dte. WBPHED/EE/EMD/NIeT-37 of 2023-24 (Sl. No.19) | 946/EMD | 18/03/2024 | 30 | M.S. ENTERPRISE | 52.66 | 0 | 0 | 0
4677 | NADIA | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME , SM/12624 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in Hridaypur Piped Water Supply Scheme and other schemes in different Blocks in the District of Nadia under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 873/AE-I/NACD-II | 23/08/2024 | 45 | TECH VISION | 4.77 | 4.77 | 100 | 100
4678 | NADIA | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME , SM/12624 | New | Material Requisition To Resource Division | 77/NACD-II | 15/01/2024 | 0 | Resource Division | 17.35 | 0 | 0 | 0
4679 | NADIA | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME , SM/12624 | New | Providing Functional House Hold Tap Connection including laying of pipeline at Betberia W/S Scheme & Hridaypur W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 748_NACD-II | 14/06/2024 | 45 | SAFTI PRIVATE LIMITED | 18.22 | 0 | 0 | 100
4680 | NADIA | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME , SM/12624 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in Hridaypur Piped Water Supply Scheme and other schemes in different Blocks in the District of Nadia under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 1150/AE-I/NACD-II | 31/01/2025 | 45 | TECH VISION | 4.77 | 0 | 0 | 0
4681 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11840 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 4A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 142/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.94 | 3.94 | 100 | 100
4682 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11840 | Augmentation | Material Requisition To Resource Division | 96/ND | 05/01/2023 | 0 | Resource Division | 297.03 | 0 | 0 | 0
4683 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11840 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 900 cum. for Providing FHTC (Functional Household Tap Connection) for Zone -IV/A (NORTHERN SECTOR, PART-II) Water Supply Scheme in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 4001/ND | 07/09/2023 | 60 | JOY HIND TUBEWELL'S | 33.19 | 0 | 0 | 45
4684 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11840 | Augmentation | Material Requisition To Resource Division | 244/ND | 11/01/2024 | 0 | Resource Division | 7.83 | 0 | 0 | 0
4685 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11840 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4589/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 393.56 | 95.41 | 50
4686 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11840 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
4687 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11840 | Augmentation | Construction of Bituminous Approch Road for GLR site at Surface water based water supply Scheme under Northern Sector Part II at Nakashipara Block under Nadia Division PHE Dte. | 3260/ND | 10/07/2025 | 90 | GBC INFRASTRUCTURE PRIVATE LIMITED | 95.58 | 0 | 0 | 5
4688 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11611 | Augmentation | Additional Survey, Design Drawing & DPR Preparation for ZONE 4/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. (Sl.No .08 ) | 210/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 1.23 | 1.23 | 100 | 100
4689 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11611 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 4/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. ( Sl.No .07) | 209/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.81 | 4.75 | 100 | 100
4690 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11611 | Augmentation | Material Requisition To Resource Division | 110/ND | 05/01/2023 | 0 | Resource Division | 104.9 | 0 | 0 | 0
4691 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11611 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 366 days w.e.f. 01/01/2024 to 31/12/2024 | 1838/KSD | 28/12/2023 | 366 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0 | 0
4692 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11611 | Augmentation | RESTORATION OF ROAD FROM JHITKIPOTA - BANAGRAM ARPAN MUKHERJEE ROAD under Package No. WB/14/157 | 299/PFMS | 02/10/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 7.71 | 0 | 0 | 0
4693 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11611 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | 3537/ND | 11/08/2023 | 782 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 711.74 | 78.88 | 20
4694 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11611 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 0 | 30
4695 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11611 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub Division, PHE Dte for supervision of JJM works for the period of 01/01/2025 to 31/12/2025 | 2666/KSD | 31/12/2024 | 365 | AVINABA ENGINEERING CONCERN | 4.8 | 0 | 0 | 0
4696 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11611 | Augmentation | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3829/ND | 13/08/2025 | 120 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0 | 0
4697 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22. | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
4698 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
4699 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Hatkhola and adjoining mouzas under Hatkhola Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | 298/NACD-II | 19/05/2022 | 90 | TIRUPATI ENTERPRISES | 188.27 | 170.2 | 90.4 | 100
4700 | NADIA | Eastern Mechanical | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at HATKHOLA Piped Water SupplyScheme, Block: Chapra, Dist. Nadia Under EMD, PHE Dte. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 03) | 1576/EMD | 24/04/2023 | 30 | M/S. SAJAHAN CHOWDHURY | 40.81 | 0 | 0 | 0
4701 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement for Tube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Hatkhola water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | 20/AE-I/NACD-II | 13/04/2022 | 60 | JAYBRATO HALDER | 2.83 | 2.81 | 100 | 100
4702 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Hatkhola water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 205/NACD-II | 05/04/2022 | 60 | JAYBRATO HALDER | 5.37 | 5.32 | 100 | 100
4703 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Sanatanpur and Hatkhola Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | 433/NACD-II | 07/07/2022 | 60 | B.M. ENGINEERING & CONSTRUCTION | 42.16 | 20.16 | 100 | 100
4704 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Hatkhola Water Supply Scheme at Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | 78/NACD-II | 10/01/2023 | 60 | JAYBRATO HALDER | 16.97 | 16.94 | 100 | 85
4705 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Hatkhola) | 880/NACD_II | 17/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
4706 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Hatkhola Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | 618/NACD-II | 06/09/2022 | 20 | MAKALI ENGINEERING CORPORATION | 3.86 | 3.86 | 100 | 100
4707 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Material Requisition To Resource Division | 407/NACD-II | 04/07/2022 | 0 | Resource Division | 33.97 | 0 | 0 | 0
4708 | NADIA | Eastern Mechanical | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Electricity bill for new service connection at Hatkhola under EMSD-III | 144/PFMS/EMD | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.55 | 0 | 0 | 0
4709 | NADIA | Eastern Mechanical | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Electricity bill for new service connection at Hatkhola under EMSD-III | 145/PFMS/EMD | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3 | 0 | 0 | 0
4710 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Hatkhola water supply scheme of Chapra Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | 361/NACD-II | 22/03/2023 | 366 | MITRA CONSTRUCTION | 117.35 | 53.07 | 45.23 | 53
4711 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Continuation work order for Construction for priliminary work of the approch road at Head Works site of Hatkhola Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | 836_AE-I/NACD-II | 01/08/2024 | 15 | MITRA CONSTRUCTION | 0.84 | 0 | 0 | 0
4712 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Acceptance cum work order "Construction of 100 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir at Head Works site of Tengra Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | 337/NACD-II | 05/03/2024 | 365 | CHATTERJEE CONSTRUCTION | 94.23 | 0 | 0 | 0
4713 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Acceptance cum work order "Conversion of IEP to AIRP at Bagberia & Hatkhola Water Supply Scheme of capacity 35 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | 197/NACD-II | 12/02/2024 | 90 | SINGHA ROY & CO. | 159.46 | 0 | 0 | 30
4714 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Laying of Rising Main of Hatkhola Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | 24/AE-I/NACD-II | 13/04/2022 | 60 | M/S. ASIT KUMAR BISWAS | 4.14 | 3.14 | 100 | 100
4715 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Hatkhola 2nd Tubwell site within Hatkhola Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 117/NACD-II | 11/01/2023 | 60 | SOMNATH GHOSH | 5.04 | 5.04 | 100 | 100
4716 | NADIA | Eastern Mechanical | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under HATKHOLA W/S Scheme (Block : Chapra) Dist.- Nadia. NIET No.-36 of EE/EMD of 2022-23 (Sl. No.- 01) | 1574/EMD | 24/04/2023 | 30 | BISALAXMI ENTERPRISE | 18.99 | 18.76 | 100 | 100
4717 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Construction for priliminary work of the approch road at Head Works site of Hatkhola Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | 406/AE-I/NACD-II | 08/08/2023 | 15 | MITRA CONSTRUCTION | 0.85 | 0.82 | 100 | 100
4718 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Hatkhola) | 420/NACD-II | 14/03/2024 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
4719 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 45 cum/Hour capacity for Hatkhola Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 1152/NACD-II | 27/08/2024 | 540 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 176.21 | 0 | 0 | 66
4720 | NADIA | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME , SM/10404 | New | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Fatepur, Bahadurpur and Gongra Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | 1657/NACD-II | 30/12/2024 | 360 | CHANDAN ROY | 149.25 | 0 | 0 | 20
4721 | NADIA | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME , SM/12423 | New | Material Requisition To Resource Division | 1086/NACD-II | 09/12/2022 | 0 | Resource Division | 16.04 | 0 | 0 | 0
4722 | NADIA | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME , SM/12423 | New | Soil Investigation for Construction of 01 (One) No of Overhead Reservoir, Construction of 01 (One) No of 100 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap, Laying of Distribution system including providing Functional House Hold Tap Connection (FHTC) and Laying of Rising Main and other necessary allied works at Jayrampur PWSS of Karimpur-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia. | 400/NACD-II | 28/03/2023 | 366 | M/S. R.M. CONSTRUCTION | 173.44 | 0 | 0 | 10
4723 | NADIA | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME , SM/12423 | New | Construction of approch road at Head Works site of Jayrampur Water Supply Scheme in Karimpur-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | 409/AE-I/NACD-II | 08/08/2023 | 15 | BASUDEB SAHA | 0.97 | 0 | 0 | 0
4724 | NADIA | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME , SM/12423 | New | Sinking of 2 nos. 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Jayrampur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 1135/NACD-II | 16/12/2022 | 30 | JOY HIND TUBEWELLS | 21.46 | 20.09 | 100 | 100
4725 | NADIA | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME , SM/12423 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Karimpur-I Block of Nadia District through Jadavpur University. (Name of PWSS Jayrampur) | 1289/NACD-II | 21/11/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
4726 | NADIA | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME , SM/12423 | New | Material Requisition To Resource Division | 381/NACD-II | 24/03/2023 | 0 | Resource Division | 5.57 | 0 | 0 | 0
4727 | NADIA | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME , SM/12423 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. | 23 | 19/04/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
4728 | NADIA | Eastern Mechanical | JAYRAMPUR PIPED WATER SUPPLY SCHEME , SM/12423 | New | New Service connection at PH-I under Jayrampur W/S scheme. | BP-138-23-24 | 16/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.52 | 0 | 0 | 0
4729 | NADIA | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME , SM/12423 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL | 235/6 | 21/02/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0 | 0
4730 | NADIA | Eastern Mechanical | JAYRAMPUR PIPED WATER SUPPLY SCHEME , SM/12423 | New | New Service connection at PH-II under Jayrampur W/S scheme. | BP-138-23-24 | 16/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.08 | 0 | 0 | 0
4731 | NADIA | Eastern Mechanical | JAYRAMPUR PIPED WATER SUPPLY SCHEME , SM/12423 | New | Supply, delivery, installation and commissioning of electro-mechanical accessories in connection with installation of Clear Water Pumping machinery in JAYRAMPUR PWSS, Block_ KARIMPUR-I, District- Nadia. Under EMD PHE Dte. | 812/EMD | 11/03/2024 | 30 | STANDARD ENGINEERING | 9.68 | 0 | 0 | 0
4732 | NADIA | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME , SM/12423 | New | Acceptance cum work order "Construction of 25 m3/hr capacity IEP at Jayrampur PWSS in Karimpur-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte." | 313/NACD-II | 01/03/2024 | 61 | HYDROTECH ASSOCIATES | 18.68 | 0 | 0 | 0
4733 | NADIA | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME , SM/12423 | New | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Jayrampur water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | 1251/NACD-II | 08/11/2023 | 45 | BASUDEB SAHA | 11.38 | 11.32 | 100 | 100
4734 | NADIA | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME , SM/12423 | New | Sinking of Tube Well at H/W site of 300 mm X 200 mm dia, 150 mtr deep by Direct Rotary Method with UPVC pipe (CD) & Fibre Glass Strainer, ( 300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Thanapara Zone-II & Jayrampur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | 149/NACD-II | 04/02/2025 | 45 | MANISHIKA CONSTRUCTION | 11.56 | 0 | 0 | 0
4735 | NADIA | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME , SM/12423 | New | Acceptance cum work order "Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Jayrampur water supply scheme under Karimpur-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia." | 409/NACD-II | 13/03/2024 | 540 | JAYBRATO HALDER | 33.53 | 0 | 0 | 70
4736 | NADIA | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME , SM/12423 | New | Acceptance cum work order "Conversion of IEP to AIRP at Joyghata Water Supply Scheme of capacity 64 Cu.m/hr under Krishnaganj Block & Jayrampur water Supply Scheme under Karimpur-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | 140/NACD-II | 01/02/2024 | 600 | GHOSH ENTERPRISE | 202.08 | 0 | 0 | 0
4737 | NADIA | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME , SM/12423 | New | Incorporation of the system of adsorption by Inorganic sustances for multivalent metalloid expulsion for improving potability in coordination with IS 10500 With latest edition at Jayrampur Piped Water Supply Scheme in Karimpur-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 1650/NACD-II | 27/12/2024 | 30 | HYDROTECH ASSOCIATES | 20.92 | 0 | 0 | 0
4738 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Fatepur water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07300 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Fatepur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 07/NACD-II | 05/01/2021 | 75 | MITRA CONSTRUCTION | 50.76 | 0 | 0 | 0
4739 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Fatepur water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07300 | Retrofitting | Rejuvenate the existing media of pressure filter & polishing unit by acid & soda washing and replacing some portion of activated Alumina and Catalytic media as per requirement including supply of valves, specials & pipes for AIRP of Bansberia W/S scheme. | 1144/NACD-II | 03/11/2020 | 30 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 4.8 | 9.59 | 200 | 0
4740 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Fatepur water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07300 | Retrofitting | Rejuvenate the existing media of pressure filter & polishing unit by acid & soda washing and replacing some portion of activated Alumina and Catalytic media as per requirement including supply of valves, specials & pipes for AIRP of Khanjipur W/S scheme. | 1143/NACD-II | 03/11/2020 | 30 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 4.79 | 9.58 | 200 | 0
4741 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Fatepur water supply scheme under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District , SM/07300 | Retrofitting | Name of work:-Rejuvenate the existing media of pressure filtter & polishing unit by acid & soda washing and replacing some portion of activated Alumina and Catalytic media as per requirement including supply of valves, specials & pipes for AIRP of Chandpur W/S scheme. | 1145/NACD-II | 03/11/2020 | 30 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 4.83 | 9.65 | 200 | 0
4742 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11550 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 4/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. (Sl.No .09 ) | 211/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.04 | 3.99 | 100 | 100
4743 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11550 | Augmentation | Material Requisition To Resource Division | 111/ND | 05/01/2023 | 0 | Resource Division | 216.05 | 0 | 0 | 0
4744 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11550 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | 3537/ND | 11/08/2023 | 782 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 441.51 | 61.71 | 20
4745 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11550 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 0 | 30
4746 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11550 | Augmentation | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3829/ND | 13/08/2025 | 120 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0 | 0
4747 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11608 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 1/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. (Sl.No .01 ) | 203/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.92 | 4.91 | 100 | 100
4748 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11608 | Augmentation | Material Requisition To Resource Division | 115/ND | 05/01/2023 | 0 | Resource Division | 299.06 | 0 | 0 | 0
4749 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11608 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 366 days w.e.f. 01/01/2024 to 31/12/2024 | 1838/KSD | 28/12/2023 | 366 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0 | 0
4750 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11608 | Augmentation | RESTORATION OF ROAD FROM SONDANGA INDRAPALLY TO BALAINAGAR under Package No. WB/14/ADB/36 | 319/PFMS | 05/10/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 2.02 | 0 | 0 | 0
4751 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11608 | Augmentation | Restoration work of Core Side in Stretches of Road Damaged due to laying of pipe line under JJM project for Dhubulia Belpukur Road from 0.0 Km to 5.30 Km under Nadia Highway Division-I, P.W.D (Roads) Directorate. | 362/PFMS | 19/12/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 9.39 | 0 | 0 | 0
4752 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11608 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | 3537/ND | 11/08/2023 | 782 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 503.76 | 85.88 | 20
4753 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11608 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 0 | 30
4754 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11608 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub Division, PHE Dte for supervision of JJM works for the period of 01/01/2025 to 31/12/2025 | 2666/KSD | 31/12/2024 | 365 | AVINABA ENGINEERING CONCERN | 4.8 | 0 | 0 | 0
4755 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/12363 | Augmentation | Survey , Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household under Tungi W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Sl.No. 01) | 904/KSD | 29/11/2021 | 15 | HORIZEN | 3.86 | 2.74 | 100 | 100
4756 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/12363 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works etc. rejuvenation to Accomodate FHTC at Pump House No.I and II under Tungi WS Scheme, Block Krishnaganj, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-11) | 160/EMD | 06/01/2023 | 30 | KUNDU ELECTRICAL ENTERPRISE | 21.11 | 19.47 | 100 | 10
4757 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/12363 | Augmentation | Supplementary works to completion of ongoing FHTC-related work at PH-I & II of Tungi W/S Scheme (Block - Krishnaganj), PHE Dte., Dist.-Nadia. | 599/EMSD-II | 22/08/2023 | 15 | KUNDU ELECTRICAL ENTERPRISE | 0.87 | 0.82 | 100 | 100
4758 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/12363 | Augmentation | Material Requisition To Resource Division | 117/ND | 05/01/2023 | 0 | Resource Division | 28.88 | 0 | 0 | 0
4759 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/12363 | Augmentation | Laying of Distribution System including specials & valves, pipe supporting structure all complete based on actual., proposed augmentation of Rising Main, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete. , Construction of R.C.C. Elevated Reservoir of 550 Cum capacity(including pile foundation) , Soil investigation for construction of one No. 550 Cum OHR, Construction of 1 No. Pump House at proposed Head Work site and Construction of boundary wall with gate for Tungi Water Supply Scheme in Krishnagunj Block of Nadia District under Nadia Division,PHE Dte. | 3520/ND | 10/08/2023 | 875 | MANGES INDUSTRIAL CORPORATION | 494.78 | 44.53 | 9 | 25
4760 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/12363 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
4761 | NADIA | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/12363 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Tungi W/S Scheme (TW-I) , Krishanjganj Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 1232/CDD | 04/09/2023 | 454 | PADMA ENGINEERING & CO. | 18.88 | 13.24 | 100 | 100
4762 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/12363 | Augmentation | Material Requisition To Resource Division | 263/ND | 11/01/2024 | 0 | Resource Division | 35.85 | 0 | 0 | 0
4763 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/12363 | Augmentation | WBSEDCL Quotation for New Service Connection to the newly Head Work Site under TUNGI W/S Scheme in Krishnaganj Block, P.H.E. Dte., Dist.- Nadia. (Application No. 3004956363) | BP-167-24-25 | 25/11/2024 | 0 | W.B.S.E.D.C.LTD (KRISHNAGANJ C.C.C) | 4.96 | 0 | 0 | 0
4764 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/12363 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 120 cum/hr at Tungi water supply scheme including 3 Months Trial Run & 3 Years O&M within krishnaganj block under Krishnagar Sub-division under Nadia Division, P.H.E. Dte. | 1304/ND | 23/02/2024 | 540 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 300.57 | 0 | 0 | 50
4765 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/12363 | Augmentation | Additional Laying of Distribution System and allied works for Water Supply Scheme under Krishnaganj Block under Krishnagar Sub Division, Nadia Division, PHE Dte. | 91/ND | 07/01/2025 | 45 | A.P. POWER & CONCRETE | 22.87 | 0 | 0 | 0
4766 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/12363 | Augmentation | Construction of 900 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (Including pile foundation), pipe connection and cost of pipes, specials for Ref. Drawing No.PC-I/OHR/16/2012 (Sheet No.1&2) and Laying of additional UPVC Pipeline in connection to the Ground Based piped water supply scheme at Tungi to accommodate FHTC within Krishnaganj block under Krishnanagar Sub-Division under Nadia Division, PHE Dte. | 7091/ND | 05/12/2024 | 365 | MANGES INDUSTRIAL CORPORATION | 334.65 | 0 | 0 | 5
4767 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA , SM/12363 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Tungi ground water based water supply scheme under Block_ Krishnaganj Dist. - Nadia under EMD, PHE Dte. SM/12363 | 1124/EMD | 04/06/2025 | 90 | SHREE BISHNU CONSTRUCTION | 31.04 | 0 | 0 | 0
4768 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11736 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 5B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | 125/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.94 | 3.94 | 100 | 100
4769 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11736 | Augmentation | Material Requisition To Resource Division | 75/ND | 05/01/2023 | 0 | Resource Division | 293.45 | 0 | 0 | 0
4770 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11736 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 617.13 | 82.74 | 47
4771 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11736 | Augmentation | Additional Work for Ground Improvement of OHR foundation, renovation of OHR & other allied works of Northern Sector Part-I, Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | 6095/ND | 19/09/2024 | 240 | UMWELT ENGINEER PVT LTD | 225.66 | 0 | 0 | 75
4772 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11838 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 2/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 139/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.72 | 3.71 | 100 | 100
4773 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11838 | Augmentation | Preparation of DPR for Augmentation for Intake, WTP & Rising Main of Surface Water Based Water Supply Scheme for Northern Sector Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte.(including Survey, Design and Estimate). | 4546/ND | 21/10/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 17.77 | 17.77 | 100 | 0
4774 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11838 | Augmentation | Material Requisition To Resource Division | 94/ND | 05/01/2023 | 0 | Resource Division | 264.51 | 0 | 0 | 0
4775 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11838 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- II/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4651/ND | 10/10/2023 | 720 | SATYABRATA CHAKRABORTY | 484.95 | 179.65 | 41.6 | 15
4776 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11838 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
4777 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11838 | Augmentation | Construction of OHR, repair and renovation of staff room, repair of boundary wall, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-II / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11838]. | 210/ND | 10/01/2024 | 365 | SARKAR CONSTRUCTION | 271.6 | 5.67 | 2.09 | 5
4778 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11838 | Augmentation | Additional work for Providing FHTC, Supplying, laying of distribution system including with all necessary specials, UPVC/HDPE Pipes etc. all complete for Zone- II/B (Northern Sector Part-II) under Nakashipara Block of Nadia District. | 2852/ND | 18/06/2025 | 75 | SATYABRATA CHAKRABORTY | 68.32 | 0 | 0 | 0
4779 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11838 | Augmentation | Additional Work for Installation of SCADA System in connection with Augmentation of Surface Water Based Piped Water Supply Scheme for Northern Sector Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 3447/ND | 23/07/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 732.35 | 0 | 0 | 15
4780 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme under Chapra Block by providing Functional House Tap Conectionunder Jal Sapno Mission in Nadia District , SM/08251 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | 1054 /NACD-II | 25/09/2020 | 15 | PRADUT GHOSH | 4.99 | 0 | 0 | 0
4781 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11872 | Augmentation | Material Requisition To Resource Division | 144/ND | 06/01/2023 | 0 | Resource Division | 5.67 | 0 | 0 | 0
4782 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11872 | Augmentation | Material Requisition To Resource Division | 2294/ND | 29/05/2023 | 0 | Resource Division | 0.92 | 0 | 0 | 0
4783 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11872 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 30 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-X B to accommodate FHTC within Karimpur-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | 206/ND | 13/01/2025 | 180 | TRANS ORGANICS INDIA PVT LTD | 161.36 | 0 | 0 | 0
4784 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/11872 | Augmentation | Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Jone-XB to accommodate FHTC Tehatta Sub-Division under Nadia Division, PHE Dte. | 242/ND | 13/01/2023 | 818 | CHOWDHURY & CO. | 79.52 | 18.43 | 100 | 90
4785 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division , SM/10078 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division | 639/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.54 | 0 | 0 | 0
4786 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division , SM/10078 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No. I and II under Kulgachi WS Scheme, Block KrishnagarI, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-09) | 158EMD,Dt.06.01.23 | 27/03/2023 | 30 | ABHISEK ENGINEERING CONCERN | 15.5 | 14.19 | 100 | 100
4787 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division , SM/10078 | Augmentation | Material Requisition To Resource Division | 2162/ND | 18/05/2022 | 0 | Resource Division | 24.2 | 0 | 0 | 0
4788 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division , SM/10078 | Augmentation | Material Requisition To Resource Division | 1018/ND | 03/03/2022 | 0 | Resource Division | 4.31 | 0 | 0 | 0
4789 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division , SM/10078 | Augmentation | Material Requisition To Resource Division | 146/ND | 06/01/2023 | 0 | Resource Division | 0.76 | 0 | 0 | 0
4790 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division , SM/10078 | Augmentation | Material Requisition To Resource Division | 3303/ND | 27/07/2022 | 0 | Resource Division | 4.82 | 0 | 0 | 0
4791 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division , SM/10078 | Augmentation | Providing FHTC at leftout household in connection to the Augmentation of Ground Based piped water supply scheme at Kulgachi to accommodate FHTC within Krishnagar I block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | 3897/ND | 16/07/2024 | 60 | MANAJIT BISWAS | 25.71 | 0 | 0 | 0
4792 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division , SM/10078 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Kulgachi to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 3153/ND | 15/07/2022 | 90 | M/S DIPAK ENTERPRISE | 250 | 248.87 | 100 | 86
4793 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division , SM/10078 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Maidanpur ii) Kulgachhi iii) Monipota iv) Habibpur v) Magurkhali. | 372/ Kly SD-I | 17/03/2023 | 184 | HORIZEN | 4.99 | 2.7 | 100 | 10
4794 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division , SM/10078 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 350 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Kulgachi Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 5124/ND | 17/11/2023 | 90 | BUDDHADEV MONDAL | 27.76 | 18.91 | 100 | 100
4795 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division , SM/10078 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
4796 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division , SM/10078 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 67 Cu.m/hr at Head Work Site at Kulgachi PWSS under Nadia Division PHE Dte. | 1599/ND | 10/04/2023 | 721 | B.M. ENGINEERING & CONSTRUCTION | 72.07 | 46.69 | 100 | 100
4797 | NADIA | Nadia Division | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA , SM/15520 | New | Survey , Design and preperation of DPR in connection with Sandha piped water supply scheme in Krishnanagar I Block under Krishnanagar Sub Division under Nadia Division, PHE Dte. | 680/KSD | 26/05/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.51 | 2.45 | 97.72 | 100
4798 | NADIA | Nadia Division | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA , SM/15520 | New | Sinking of 2 nos. Tubewell 300mm. x 200mm. dia 200 mtr deep by direct rotary rig method at headwork and 2nd tube well site for Sandha (SAF) water supply scheme under Krishnagar Sub-division under Nadia Division, PHE Dte. (SM/15520) | 2103/ND | 15/05/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 32.45 | 26.36 | 100 | 100
4799 | NADIA | Nadia Division | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA , SM/15520 | New | Material Requisition To Resource Division | 89/ND | 05/01/2023 | 0 | Resource Division | 14.87 | 0 | 0 | 0
4800 | NADIA | Nadia Division | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA , SM/15520 | New | Material Requisition To Resource Division | 274/ND | 11/01/2024 | 0 | Resource Division | 12.03 | 0 | 0 | 0
4801 | NADIA | Eastern Mechanical | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA , SM/15520 | New | New Service Connection charge for PH.No. 2 under Sandhya, 9th Battalian | BP-267-23-24 | 09/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.07 | 0 | 0 | 0
4802 | NADIA | Eastern Mechanical | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA , SM/15520 | New | New Service Connection charge for PH.No. 1 under Sandhya, 9th Battalian | BP-268-23-24 | 09/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.36 | 0 | 0 | 0
4803 | NADIA | Nadia Division | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA , SM/15520 | New | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | 3784/ND | 12/08/2025 | 31 | IMAGIN | 34.21 | 0 | 0 | 0
4804 | NADIA | Nadia Division | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA , SM/15520 | New | Laying of Distribution System including specials & valves, Laying of proposed Rising Main, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, repair and renovation works of R.C.C. Elevaced Reservoir of 90 and 270 Cum capacity, repair and renovation works of Pump Houses and other allied works at Sandha (State Arm Force) within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 3025/ND | 14/07/2023 | 366 | CHANDAN ROY, 35, M. M. GHOSH STREET, P.O. -KRISHNAGAR, DIST. NADIA, PIN -741101. | 247.85 | 101.13 | 40.8 | 55
4805 | NADIA | Eastern Mechanical | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA , SM/15520 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under SANDHA ground water based water supply scheme under Block_ Krishnanagar-I Dist. - Nadia under EMD, PHE Dte. | 6967/EMD | 15/12/2023 | 564 | CINZANO | 27.44 | 0 | 0 | 90
4806 | NADIA | Nadia Division | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA , SM/15520 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 50 m3/hr at Sandha SAP Water Supply Scheme within Krishnagar-I Block under Nadia Division, P.H.E. Dte. | 1900/ND | 15/03/2024 | 360 | JOY HIND TUBEWELL'S | 184.49 | 0 | 0 | 0
4807 | NADIA | Nadia Division | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA , SM/15520 | New | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
4808 | NADIA | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/15522 | Augmentation | sinking of 80mm dia. Shallow tubewell for requirement of drilling water for Fulia Township (Z-I) PWSS, District Nadia and other PWSS under CMSD-II (D), CDD, PHE Dte. | 103/CMSD-II(D) | 20/04/2023 | 15 | UNIVERSAL ENTERPRISES | 0.88 | 0 | 0 | 0
4809 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/15522 | Augmentation | Material Requisition To Resource Division | 1883/ND | 26/04/2023 | 0 | Resource Division | 33.17 | 0 | 0 | 0
4810 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/15522 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 1.4 | 98.71 | 40
4811 | NADIA | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/15522 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Fulia Township W/S Scheme (Z- I, T/W-III),Santipur Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 516/CDD | 01/06/2023 | 611 | M/S S.K.GHOSH & CO. | 18.88 | 0 | 0 | 0
4812 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/15522 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, II and III , Zone-I under Fulia Town Ship (Zone-I) ground water based water supply scheme under Block_ Santipur Dist. - Nadia under EMD, PHE Dte. [SM-15522] | 2155/EMD | 30/08/2024 | 30 | KARTICK BAL | 42.39 | 34.97 | 82.51 | 70
4813 | NADIA | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/15522 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x 250 Mtrs. Depth) by utilising departmental machineries for Fulia Township W/S Scheme (Z-I, T/W I & II). Santipur Block under Nadia District, Central Drilling Division, PHE Dte. | 515/CDD | 01/06/2023 | 455 | UNIVERSAL ENTERPRISES | 37.73 | 19.28 | 56.71 | 100
4814 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/15522 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangemen At Hw Site At Fulia Zone-I Water Supply Scheme Under Ranaghat Sub-Division PHE Dte.) | 4698/ND | 11/10/2023 | 90 | M/S BISWAS ENTERPRISE | 6.88 | 6.74 | 100 | 100
4815 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/15522 | Augmentation | Material Requisition To Resource Division | 7561/ND | 27/12/2024 | 0 | Resource Division | 23.37 | 0 | 0 | 0
4816 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/15522 | Augmentation | New Power Connection charges for FULIA Water Supply Scheme Z -I , Pump House No- II | BP-185 | 13/12/2024 | 0 | W.B.S.E.D.C.L (FULIA C.C.C) | 5.36 | 0 | 0 | 0
4817 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/15522 | Augmentation | New Power Connection Charges for FULIA Water Supply Scheme Z - I , HEAD WORK SITE (PH-I) | BP-186 | 13/12/2024 | 0 | W.B.S.E.D.C.L (FULIA C.C.C) | 14.29 | 0 | 0 | 0
4818 | NADIA | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/15522 | Augmentation | New Power Connection Charges for FULIA Water Supply Scheme Z- I , Pump House No- III | BP-187 | 13/12/2024 | 0 | W.B.S.E.D.C.L (FULIA C.C.C) | 5.21 | 0 | 0 | 0
4819 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/15522 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete Construction Of 700 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection And Cost Of Pipes, Specials & Soil Investigation For Construction Of One No. 700 Cum OHR Of Staging Height 20 Mtr. for augmentation of Ground Water Based Water Supply Scheme For Fulia Township Zone-I to accommodate FHTC in Santipur block of Nadia District under Nadia Division P.H.Engineering Dte. | 3450/ND | 09/08/2023 | 731 | APURBA MONDAL, VILL+P.O. BADKULLA, DIST.NADIA, PIN-741121 W.B | 746.37 | 411.66 | 55.16 | 85
4820 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/15522 | Augmentation | Construction of 56.00 mtr long Boundary Wall (2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125mm thick brick panel wall and 200x300 mm tie beam at GL including M.S gate at Fulia Zone-I Pump House-III under Ranaghat Sub-Division, Nadia Division PHE. Dte. | 87/RSD | 14/01/2025 | 75 | ROMI TRADERS | 4.77 | 0 | 0 | 0
4821 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/15522 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 135 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Fulia Township Zone-I to accommodate FHTC within Santipur block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | 137/ND | 08/01/2025 | 180 | MONDAL ENTERPRISE | 245 | 0 | 0 | 0
4822 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/15522 | Augmentation | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Pump house No-2 site at Fulia Zone-I Water supply scheme under Ranaghat Sub ¿ Division, PHE Dte. | 1184/RSD | 25/09/2024 | 75 | ASHIM ENTERPRISE | 4.46 | 0 | 0 | 100
4823 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/15522 | Augmentation | Providing leave out functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Fulia Township Zone-I to accommodate FHTC in Santipur block and allied works of Badkulla Zone II of Nadia District under Nadia Division P.H.Engineering Dte. | 1804/ND | 22/04/2025 | 180 | APURBA MANDAL | 64.83 | 0 | 0 | 90
4824 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/15522 | Augmentation | Construction of 44 mtr long Boundary Wall(2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125mm thick brick panel wall and 200x300 mm tie beam at GL including M.S gate at Fulia Zone-I Pump House-II under Ranaghat Sub-Div, Nadia Division PHE. Dte. | 86/RSD | 14/01/2025 | 75 | BRICK FARM | 4.05 | 0 | 0 | 0
4825 | NADIA | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA , SM/15522 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0 | 0
4826 | NADIA | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Saguna Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15542 | Augmentation | Augmentation of AIRP capacity (78cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Saguna, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.11) | 1903/NAD-I | 14/08/2023 | 30 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 141.34 | 141.34 | 100 | 100
4827 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Saguna Water Supply Scheme Part-IV under Jal Jeevan Mission (JJM) at Santipur Block, Nadia under Nadia Arsenic Division-I, P.H.E. Dte. , SM/15542 | Augmentation | Providing Boundary Illumination with allied works at Saguna under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15542) | 1159/EMD | 04/06/2025 | 90 | DEEP ENTERPRISE | 4.32 | 0 | 0 | 0
4828 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14196 | New | Preparation of Detailed Project Report (DPR) for Birnagar (Part) Water Supply Scheme at Ranaghat-I Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(sl.no.01) | 3287 / NAD-I | 08/12/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 3.74 | 3.65 | 100 | 100
4829 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14196 | New | Augmentation work of 2 no Gobindanagar near Indira More & Birnagar at Ranaghat-I Block under augmentation of Ground Water Based PWSS of Birnagar Part-III under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.16) | 2123/NAD-I | 04/09/2023 | 21 | CHOWDHURY & CO. | 75.32 | 75.22 | 100 | 100
4830 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14196 | New | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10mm gun metal ferrule, saddle piece etc. all complete with Rising Main System including specials & Valves & Pipe supporting Structure, Construction of 100 cum capacity 20 mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials, Construction of Boundary Wall [H/W Site (160.0 m length), 2nd T/W Site(45.0 length)], Pump House for H/W Site (4.88 M X 3.60 M), 2nd T/W Site (3.60 M X 3.0 M), Land Development, Restoration of Bituminous Road and allied works with Approach Road (105.0 m length and 3.0m wide), Soil Investigation for the work of Construction of RCC Elevated Reservoir of capacity 100 M3 Staging Height 20 mtr. and Restoration Work for Bituminous Road at Ground Water Based Piped W/S Scheme for Birnagar (Part) in Ranaghat-I Block of Nadia District under Nadia Arsenic Division-I, P.H.E Dte. | 1741/NAD-I | 19/07/2023 | 1170 | M/S MALLICK ENTERPRISE | 341.12 | 45.03 | 13.2 | 75
4831 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14196 | New | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for at Madanpur-I & II G.P. and different augmentation works of Radhakantapur and Birnagar Part-III under Jal Jeevan Mission (JJM) at Ranaghat-I block by augmentation of Ground Water Based PWSS for Radhakantapur and Birnagar under Nadia Arsenic Division-I, PHE Dte. (Sl.no.11) | 2120/NAD-I | 04/09/2023 | 21 | CHOWDHURY & CO. | 96.13 | 79.5 | 82.7 | 70
4832 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14196 | New | Material Requisition To Resource Division | 846/NAD-I | 04/06/2024 | 0 | Resource Division | 1.52 | 0 | 0 | 0
4833 | NADIA | Eastern Mechanical | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14196 | New | Providing Boundary Illumination with allied works at Birnagar (Part) under Block_ Ranaghat-I Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/14196) | 1161/EMD | 04/06/2025 | 90 | WESTERN ENGINEERING CO. | 4.31 | 0 | 0 | 0
4834 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. , SM/09799 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | 67/PFMS | 28/06/2022 | 0 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 87.34 | 0 | 0 | 0
4835 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. , SM/09799 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | 633/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.99 | 0 | 0 | 0
4836 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. , SM/09799 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works etc. rejuvenation to Accomodate FHTC at Pump House No.I & II under Krishnaganj Majdia W/S Scheme, Block- Krishnaganj, Dist. - Nadia. NIET No.- 18 of EE/EMD of 2022-23 (Sl. No.- 07) | 6188/EMD | 14/11/2022 | 30 | S.G. TECHNICAL SERVICES | 12 | 0 | 0 | 0
4837 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. , SM/09799 | Augmentation | Continuation of Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period of 90 days w.e.f 01/07/2023 (as and when required). | 800/KSD | 16/06/2023 | 92 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 0
4838 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. , SM/09799 | Augmentation | Material Requisition To Resource Division | 1023/ND | 03/03/2022 | 0 | Resource Division | 11.25 | 0 | 0 | 0
4839 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. , SM/09799 | Augmentation | Material Requisition To Resource Division | 450/ND | 31/01/2022 | 0 | Resource Division | 3.58 | 0 | 0 | 0
4840 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. , SM/09799 | Augmentation | Material Requisition To Resource Division | 1257/ND | 16/03/2022 | 0 | Resource Division | 16.73 | 0 | 0 | 0
4841 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. , SM/09799 | Augmentation | Laying of additional HDPE pipeline for water supply scheme under Krishnaganj Block under Krishnagar Sub Division, Nadia Division, PHE Dte. | 7092/ND | 05/12/2024 | 90 | MANGES INDUSTRIAL CORPORATION | 177.21 | 0 | 0 | 0
4842 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. , SM/09799 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 103 m3/hr at Krishnaganj Majhdia Water Supply Scheme within Krishnaganj Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | 1892/ND | 15/03/2024 | 180 | B.M. ENGINEERING & CONSTRUCTION | 266.82 | 0 | 0 | 0
4843 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. , SM/09799 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Krishnaganj Majdia to accommodate FHTC within Krishnaganj block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 966/ND | 28/02/2022 | 90 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 495.71 | 342.32 | 100 | 82
4844 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. , SM/09799 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 450 cum, Repair & Renovation of Pump House, Store, Guard Room, Boundary wall and allied works at 1st and 2nd Pump House at Krishnaganj Majhdia Water Supply Scheme within Krishnaganj block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 5123/ND | 17/11/2023 | 90 | CHOWDHURY & CO. | 34.94 | 34.44 | 100 | 98
4845 | NADIA | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. , SM/09799 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Krishnaganj Majdia W/S Scheme (TW-I) , Krishnagar-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | 1659/CDD | 17/10/2023 | 180 | MENAKA ENTERPRISE | 18.88 | 15.05 | 100 | 100
4846 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. , SM/09799 | Augmentation | Construction of Pump House (3.6mtr. X 3.0 mtr.) and Boundary Wall at 3rd T/W site for Krishnaganj Majhdia water supply scheme under Krishnagar Sub-Division under Nadia Division PHE Dte. | 3262/ND | 10/06/2024 | 45 | D.K. CONSTRUCTION | 17.11 | 14.69 | 100 | 80
4847 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. , SM/09799 | Augmentation | WBSEDCL SUPPLEMENTARY Quotation for New Service Connection to the newly constructed Pump House No. - III under KRISHNAGANJ MAJDIA W/S Scheme in Krishnaganj Block, P.H.E. Dte., Dist.- Nadia. (Application ID. 100000120534) | BP-164-24-25 | 25/11/2024 | 0 | W.B.S.E.D.C.LTD (KRISHNAGANJ C.C.C) | 3.49 | 0 | 0 | 0
4848 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. , SM/09799 | Augmentation | WBSEDCL Quotation for New Service Connection to the newly constructed Pump House No. - III under KRISHNAGANJ MAJDIA W/S Scheme in Krishnaganj Block, P.H.E. Dte., Dist.- Nadia. (Application No. 3004847470) | BP-88-24-25 | 28/08/2024 | 0 | W.B.S.E.D.C.LTD (KRISHNAGANJ C.C.C) | 0.56 | 0 | 0 | 0
4849 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. , SM/09799 | Augmentation | Additional Laying of Distribution System and allied works for Water Supply Scheme under Krishnaganj Block under Krishnagar Sub Division, Nadia Division, PHE Dte. | 91/ND | 07/01/2025 | 45 | A.P. POWER & CONCRETE | 22.87 | 0 | 0 | 0
4850 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. , SM/09799 | Augmentation | Construction and installation of Manifold and allied works at OHR site in connection to Retrofitting (Phase-I) Under JJM In Ground Based Piped Water Supply Scheme at Krishnaganj Majhdia To Accommodate FHTC Within Krishnaganj Block Under Krishnanagar Sub-division Under Nadia Division, PHE Dte. | 496/ND | 30/01/2025 | 60 | CHOWDHURY & CO. | 39.44 | 0 | 0 | 0
4851 | NADIA | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. , SM/09799 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Krishnaganj Majhdia ground water based water supply scheme under Block_ Krishnaganj Dist. - Nadia under EMD, PHE Dte. SM/09799 | 1108/EMD | 04/06/2025 | 90 | S.P. ENTERPRISE (KOLKATA) | 20.79 | 0 | 0 | 0
4852 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14244 | New | Preparation of Detailed Project Report (DPR) for Nasra Water Supply Scheme at Ranaghat-II Block atNadia District under Nadia Arsenic Division-I,P.H.E. Dte. (sl.04) | 38/ NAD-I | 16/01/2023 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 6.74 | 6.67 | 100 | 100
4853 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14244 | New | Material Requisition To Resource Division | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 19.27 | 0 | 0 | 0
4854 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14244 | New | Material Requisition To Resource Division | 294/NAD-I | 28/02/2024 | 0 | Resource Division | 16.87 | 0 | 0 | 0
4855 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14244 | New | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete with Rising Main System including specials & valves. & LAYING OF DISTRIBUTION SYSTEM INCLUDING SPECIALS, VALVES & PIPE SUPPORTING STRUCTURE, Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials at Ground Water Based Piped Water Supply Scheme for Nasra (Zone-I), Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials at Ground Water Based Piped Water Supply Scheme for Nasra (Zone-II), CONSTRUCTION OF BOUNDARY WALL [ H/W Site(160.0 m length),2nd T/W Site(45.0 m length),3rd T/W(45.0 m length),4th T/W(45.0 m length)],Pump House for H/W Site(4.88 M X 3.60 M),2nd T/W Site(3.60 M X 3.0 M) ,Land Development,Restoration of Bituminous Road and aliied works with Approach Road (195.0m Length and 3.0m Wide), Soil investigation for the work of construction of R.C.C. Elevated Reserviour of Capacity 300 m3 of Height 20 Mtr. for Nasra (Zone-I), Soil investigation for the work of construction of R.C.C. Elevated Reserviour of Capacity 200 m3 of Height 20 Mtr. for Nasra (Zone-II) and RESTORATION WORK FOR BITUMINOUS ROAD at Ground Water Based Piped Water Supply Scheme for Nasra (Zone-I&II) in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, PHE Dte. | 2381/NAD-I | 06/10/2023 | 1095 | BIDYUT KUMAR | 804.39 | 121.76 | 15.14 | 70
4856 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14244 | New | Work for revamping / upgradation of the hydraulic parameters at Kamdanga and Nasra Mouza in reference to Nasra and Aranghata water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) | 158/NAD-I | 28/04/2025 | 60 | SAFTI PRIVATE LIMITED | 77.16 | 0 | 0 | 0
4857 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14244 | New | Work revamping / upgradation of the hydraulic parameters at distribution network at the part of Malsadaha, Ulasi, Silberia, Nasra (P) and Hijuli (P) Mouzas in reference to Hijuli and Nasra PWSS under Nadia Arsenic Division-I, P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. NO. 02) | 359/NAD-I | 09/06/2025 | 90 | M/S DIPAK ENTERPRISE | 246.94 | 0 | 0 | 0
4858 | NADIA | Nadia Arsenic Division I | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14244 | New | Revamping / upgradation of the hydraulic parameters for Uttor Bhayna, Hatibanda, Aishmali, Nasra and Hijuli ( P ) villages in connection with Debogram, Nasra and Hijuli PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) | 530/NAD-I | 03/07/2025 | 120 | BUDDHADEV MONDAL | 53.23 | 0 | 0 | 0
4859 | NADIA | Eastern Mechanical | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte. , SM/14244 | New | Providing Boundary Illumination with allied works at Nasra under Block_ Ranaghat-II under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/14244) | 1157/EMD | 04/06/2025 | 90 | S M ELECTRICALS | 4.34 | 0 | 0 | 0
4860 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PAIRADANGA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15277 | Augmentation | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | 1270/ND | 23/03/2023 | 60 | AUXILIARY TUBEWELL DRILLERS | 65.32 | 0 | 0 | 0
4861 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PAIRADANGA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15277 | Augmentation | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | 6290/ND | 26/09/2024 | 45 | IMAGIN | 19.44 | 0 | 0 | 100
4862 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PAIRADANGA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15277 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Pairadanga ground water based water supply scheme under Block_ Hanskali_I Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15277) | 237/EMD | 06/02/2025 | 30 | ABHISEK ENGINEERING CONCERN | 23.53 | 0 | 0 | 0
4863 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PAIRADANGA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15277 | Augmentation | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.04.2025 to 31.07.2025 | 584/KlySD-I | 28/03/2025 | 122 | SUMAN CHAKRABORTY | 4.89 | 0 | 0 | 100
4864 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PAIRADANGA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15277 | Augmentation | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.08.2025 to 31.01.2026 | 1488/KlySD-I | 30/07/2025 | 184 | SUMAN CHAKRABORTY | 4.89 | 0 | 0 | 0
4865 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR NUTANGRAM (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/15278 | Augmentation | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | 1270/ND | 23/03/2023 | 60 | AUXILIARY TUBEWELL DRILLERS | 65.32 | 0 | 0 | 0
4866 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Dakshinpara Water Supply Scheme (Zone-I & II) In Hanskhali Block District Nadia (Two Stage Pumping). , SM/16366 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4867 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Pairadanga Water Supply Scheme In Hanskhali Block District Nadia. , SM/16371 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4868 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Bhayana Water Supply Scheme (Zone-I & II) In Hanskhali Block District Nadia. , SM/16355 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4869 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Chupria Water Supply Scheme (Zone-I & II) In Hanskhali Block District Nadia. , SM/16356 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4870 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Patharghata Water Supply Scheme in Tehatta-I Block, Dist.-Nadia. , SM/16338 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4871 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Shyamnagar Water Supply Scheme in Tehatta-I Block, Dist.-Nadia. , SM/16340 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4872 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Baraia Water Supply Scheme in Tehatta-II Block, Dist.-Nadia. , SM/16343 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4873 | NADIA | Eastern Mechanical | Solarizations of WBSEDCL Energized Electrical installation including Net Metering at Different Pipe Water Supply Scheme at Chapra and Krishnaganj Blocks in Nadia District under Eastern Mechanical Division, PHE, Directorate. , SM/16850 | Solarisation | Solarisation of WBSEDCL Energised Electrical installation including net metering at different Pipe Water Supply Scheme at Chapra & Krishnaganj Blocks in Nadias District under E.M.D. P.H.E. Dte. | 6349/EMD | 16/10/2023 | 183 | B.K. ENTERPRISE | 536.5 | 0 | 0 | 0
4874 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Kisorepur Water Supply Scheme in Karimpur-II Block of District Nadia , SM/16804 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4875 | NADIA | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-III Water Supply Scheme (Phase-I) of Retrofitting under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. , SM/08663 | Retrofitting | Providing Functional House Tap Connection from Teinpur Zone-III Water Supply Scheme (Phase-I) of Retrofitting under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. | 606/PFMS | 11/03/2022 | 0 | OTHERS | 8.14 | 0 | 0 | 0
4876 | NADIA | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-III Water Supply Scheme (Phase-I) of Retrofitting under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. , SM/08663 | Retrofitting | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 01-02-2023 to 31-07-2023= 183 days. | 92/RSD | 01/02/2023 | 183 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 3.2 | 0.66 | 44.15 | 25
4877 | NADIA | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-III Water Supply Scheme (Phase-I) of Retrofitting under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. , SM/08663 | Retrofitting | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 11-11-2022 to 31-01-2023= 80 days. | 678/RSD | 04/11/2022 | 80 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 1.19 | 0.21 | 41.74 | 75
4878 | NADIA | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-III Water Supply Scheme (Phase-I) of Retrofitting under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. , SM/08663 | Retrofitting | Material Requisition To Resource Division | 804/ND | 18/02/2022 | 0 | Resource Division | 8.78 | 0 | 0 | 0
4879 | NADIA | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-III Water Supply Scheme (Phase-I) of Retrofitting under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. , SM/08663 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Teinpur zone - III W/S scheme under Nadia Division, PHE Dte. | 5142/ND | 15/09/2021 | 90 | BIDYUT KUMAR | 85.7 | 69.53 | 81.14 | 100
4880 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Damodarkhali Water Supply Scheme in Krishnagar-I Block, Dist.- Nadia. , SM/16837 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4881 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Topla Water Supply Scheme in Karimpur-II Block of District Nadia , SM/16811 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4882 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Goalpur Water Supply Scheme (Zone - I & II) in Shantipur Block, Dist,- Nadia , SM/17269 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4883 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Nabla Water Supply Scheme in Shantipur Block, Dist,- Nadia , SM/17271 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4884 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (Purba Bishnupur) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE , SM/08852 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-V,(Purba Bishnupur) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | 14/NAD-I | 05/01/2022 | 90 | M/S TARAK CHANDRA PAUL | 277.36 | 277.33 | 100 | 100
4885 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (Purba Bishnupur) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE , SM/08852 | Retrofitting | Retrofitting work for Purba Bishnupur Zone V of Surface Water based PWSS for Chakdah Part water supply scheme under NAD - I PHE Dte (SL.06) | 1473 / NAD-I | 22/08/2022 | 60 | APURBA MANDAL | 32.4 | 27.39 | 100 | 100
4886 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Birnagar Water Supply Scheme in Ranagtat-I Block under District Nadia , SM/18198 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4887 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Debagram Water Supply Scheme in Ranagtat-II Block under District Nadia , SM/18208 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4888 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Gangnapur Water Supply Scheme in Ranagtat-II Block under District Nadia , SM/18212 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4889 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Goalsalua (Z-I & II) Water Supply Scheme in Ranagtat-II Block under District Nadia , SM/18213 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4890 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR UDAYPUR (PHASE-II) IN SANTIPUR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17689 | Augmentation | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Santipur & Krishnaganj Block, under Ranaghat Sub-Division, PHE Dte. | 1273/ND | 23/03/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 47.83 | 26.02 | 100 | 95
4891 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR UDAYPUR (PHASE-II) IN SANTIPUR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. , SM/17689 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, (Phase-II) under Udaypur ground water based water supply scheme under Block_ Santipur Dist. - Nadia under EMD, PHE Dte. | 6397/EMD | 30/10/2023 | 580 | GHOSH AND GHOSH | 12.74 | 0 | 0 | 85
4892 | NADIA | Eastern Mechanical | Implementation of Affordable Iot System at Magurkhali Water Supply Scheme in Ranagtat-II Block under District Nadia , SM/18216 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4893 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Durgapur Changacha Water Supply Scheme in Krishnaganj Block, Dist.-Nadia. , SM/18068 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4894 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Material Requisition To Resource Division | 147/ND | 06/01/2023 | 0 | Resource Division | 1858.7 | 0 | 0 | 0
4895 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Quotation for service connection charge and security deposit for new power connection at Majhergram OHR Site under Northern Sector, Part-II SWB Project , PHE Dte. | BP-109-24-25 | 09/09/2024 | 0 | WBSEDCL BETHUADAHARI (NORTH) CCC | 3.86 | 0 | 0 | 0
4896 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Quotation for New power connection at Gopalpur OHR ( Zone-II/B) under Northern Sector, Part-II SWB Project. | BP-75-24-25 | 30/07/2024 | 0 | MURAGACHA DHARMADA CCC | 0.3 | 0 | 0 | 0
4897 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Payment to Ministry of Railway regarding railway crossing, Application ID- ER-SDAH-2024-WL-135 | 308/PFMS | 02/10/2024 | 0 | MINISTRY OF RAILWAYS, EASTERN RAILWAY, SEALDAH DIVISION | 12.52 | 0 | 0 | 0
4898 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Quotation for new service connection and security deposit at Kalibus OHR (Zone-VII/B) under Northern Sector, Part-II SWB Project,PHE Dte. | BP-108-24-25 | 09/09/2024 | 0 | WBSEDCL BETHUADAHARI CCC | 3.95 | 0 | 0 | 0
4899 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Quotation for service connection charge and security deposit for new power connection at Bilkumarik OHR(Zone-VI/B) Site under Northern Sector, Part-II SWB Project , PHE Dte. | BP-111-24-25 | 09/09/2024 | 0 | WBSEDCL DEBOGRAM CCC | 2.64 | 0 | 0 | 0
4900 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Quotation for earnest money deposit for Bulk power supply at Nakashipara GLR project. | BP-23-24-25 | 21/05/2024 | 0 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 0.05 | 0 | 0 | 0
4901 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Quotation for New power connection at Gachha OHR ( Zone-IX/B) under Northern Sector, Part-II SWB Project. | BP-76-24-25 | 30/07/2024 | 0 | MURAGACHA DHARMADA CCC | 0.3 | 0 | 0 | 0
4902 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Quotation for New HT Bulk connection at Nakashipara GLR Project under Easter Mechanical Division, Dist-Nadia | BP-69-24-25 | 26/07/2024 | 0 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 39.38 | 0 | 0 | 0
4903 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Quotation for New power connection at Digha OHR ( Zone-VIII/C) under Northern Sector, Part-II SWB Project. | BP-77-24-25 | 30/07/2024 | 0 | MURAGACHA DHARMADA CCC | 0.3 | 0 | 0 | 0
4904 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Quotation for service connection charge and security deposit for new power connection at Sonadanga OHR Site under Northern Sector, Part-II SWB Project , PHE Dte. | BP-110-24-25 | 09/09/2024 | 0 | WBSEDCL BETHUADAHARI (NORTH) CCC | 3.74 | 0 | 0 | 0
4905 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Quotation for New power connection at Teghari OHR ( Zone-VIII/B) under Northern Sector Part-II SWB Project. | BP-74-24-25 | 30/07/2024 | 0 | MURAGACHA DHARMADA CCC | 0.3 | 0 | 0 | 0
4906 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Augmentation of pumping machinery and electrical equipments at WTP along with implementation of SCADA System for surface water based water supply scheme, Arsenic affected area, Northern Sector, Part-II (Block - Nakasipara) in the district of Nadia, P. H. E. Dte. | 6261/EMD | 10/10/2023 | 630 | MACHINE SUPLIERS SYNDICATE (P) LTD. | 234.62 | 0 | 0 | 40
4907 | NADIA | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Providing Axially Split Centrifugal Pumping machinery for GLR along with secondary disinfection arrangement for surface water based water supply scheme, Arsenic Affected Area, Northern Sector, Part-II (Block - Nakasipara) in the district of Nadia, P. H. E. Dte. | 6264/EMD | 10/10/2023 | 752 | WEST BENGAL ENGINEERING CO. | 276.03 | 122.7 | 44.45 | 60
4908 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Augmentation of Water Treatment Plant (augmented to 34.52 MLD), repairing & renovation of Rising Main from WTP to different ESR and zonal OHR and soil test, design & construction of Boosting Station along with allied civil work including 6 (six) months trial run for Surface Water Based Piped Water Supply Scheme for Northern Sector, Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 4773/ND | 16/10/2023 | 747 | GB CONSTRUCTION | 6109.51 | 4711.68 | 77.12 | 9
4909 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 5.93 | 98.75 | 30
4910 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
4911 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Jack pushing & pipe crossing work at Khidirpur Mouza under Northern Sector Part-II under Nakashipara Block of Nadia District. | 1646/ND | 07/04/2025 | 90 | MONDAL ENTERPRISE | 97.53 | 0 | 0 | 1
4912 | NADIA | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/18387 | Augmentation | Additional Work for Installation of SCADA System in connection with Augmentation of Surface Water Based Piped Water Supply Scheme for Northern Sector Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 3447/ND | 23/07/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 732.35 | 0 | 0 | 15
4913 | NADIA | Eastern Mechanical | Implementation of Affordable IoT System at Sakdaha Water Supply Scheme in Krishnaganj Block, Dist.-Nadia. , SM/18064 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | 2205/EMD | 04/09/2024 | 153 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 20
4914 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09687 | Retrofitting | Preparation of DPR for augmentation of existing Mahatpur, (Block -Chapra) piped water supply schemes | 146/AE-I/NACD-II | 16/11/2021 | 10 | UMWELT ENGINEER PVT LTD. | 3.79 | 3.79 | 100 | 100
4915 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09687 | Retrofitting | Preparation of DPR for augmentation of existing Mahatpur (Phase-II), (Block -Chapra) piped water supply schemes | 756/NACD-II | 16/09/2021 | 10 | SIRCON ENGINEERING SERVICE | 4.84 | 4.84 | 100 | 100
4916 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09687 | Retrofitting | Relaying of Rising Main by D.I. pipeline replacing the damaged old UPVC Pipe at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division -II, P.H.E. Dte. | 97/NACD-II | 10/02/2022 | 45 | M/S RAJESH CONSTRUCTION | 13.55 | 13.55 | 99.97 | 100
4917 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09687 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair ) at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 992/NACD-II | 30/12/2021 | 45 | SANDIP BISWAS | 97.95 | 97.86 | 99.9 | 100
4918 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09687 | Retrofitting | Installation of Electrical appliances and other allied works under retrofitting of Mahatpur PWSS under Chapra Block. | 192/AE-I/NACD-II | 29/12/2021 | 20 | CHINMOY BISWAS | 4.84 | 4.84 | 100 | 100
4919 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09687 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and also construction of steps with earth filling at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | 981/NACD-II | 27/12/2021 | 90 | SINGHA ROY & CO. | 145.05 | 144.95 | 99.93 | 100
4920 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09687 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and Bamboo Pilling at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 525/NACD-II | 14/06/2021 | 45 | NILAY KUMAR BHATTACHARYA | 68.03 | 0 | 0 | 100
4921 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09687 | Retrofitting | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Mahatpur (Vill- Jamnidanga) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | 289/NACD-II | 23/02/2021 | 21 | JOY HIND TUBEWELLS | 41.12 | 0 | 0 | 100
4922 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09687 | Retrofitting | Construction of Boundary wall with Grill Gate at Mahatpur Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | 108/NACD-II | 10/02/2022 | 45 | PARTHA DAS | 8.55 | 0 | 0 | 100
4923 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09687 | Retrofitting | Material Requisition To Resource Division | 990/NACD-II | 28/12/2021 | 0 | Resource Division | 93.39 | 0 | 0 | 0
4924 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09687 | Retrofitting | Electrical and Civil works and other allied works under retrofitting of Mahatpur PWSS under Chapra Block | 186/AE-I/NACD-II | 29/12/2021 | 20 | CHINMOY BISWAS | 4.96 | 4.96 | 100 | 100
4925 | NADIA | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte , SM/09687 | Retrofitting | Jungle cutting at Mahatpur,Patharghata,Baliadanga,Helenchi Zone-III,Joyghata and Damodarkhali Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | 820/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.16 | 0.1 | 100 | 100
4926 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. , SM/09206 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. | 706/PFMS | 30/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.63 | 0 | 0 | 0
4927 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. , SM/09206 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. | 713/PFMS | 30/03/2022 | 0 | SUMAN CHAKRABORTY | 27.16 | 0 | 0 | 0
4928 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. , SM/09206 | Augmentation | Laying of Distribution system for providing FHTC at Dafarpota (Zone-II) Water Supply Scheme in Nadia District under Krishnagar Sub-Division ,P.H.E.Dte. | 5336/ND | 21/12/2022 | 30 | PURNIMA ELECTRICS & DECORATORS | 12.79 | 7.61 | 100 | 100
4929 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. , SM/09206 | Augmentation | Material Requisition To Resource Division | 98/ND | 06/01/2022 | 0 | Resource Division | 5.53 | 0 | 0 | 0
4930 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. , SM/09206 | Augmentation | Material Requisition To Resource Division | 4284/ND | 29/09/2022 | 0 | Resource Division | 2.66 | 0 | 0 | 0
4931 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. , SM/09206 | Augmentation | Repair and renovation works of R.C.C. Elevaced Reservoir 50 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Dafarpota Zone II Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 6083/ND | 19/12/2023 | 90 | M/S CHANDIMATA CONSTRUCTION | 21.51 | 0 | 0 | 0
4932 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. , SM/09206 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Dafarpota Zone-II to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 66/ND | 05/01/2022 | 75 | SUMAN CHAKRABORTY | 52.5 | 19.99 | 100 | 90
4933 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. , SM/09206 | Augmentation | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.10.2023 to 30.11.2023 | 1034/KLYSD-I | 29/09/2023 | 30 | SUMAN CHAKRABORTY | 4.89 | 0.19 | 100 | 100
4934 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. , SM/09206 | Augmentation | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.12.2023 to 31.12.2023 | 1260/KLYSD-I | 30/11/2023 | 31 | SUMAN CHAKRABORTY | 4.89 | 0.06 | 100 | 100
4935 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. , SM/09206 | Augmentation | Emergent Repairing work in connection with Augmentation of Ground Based piped water supply scheme at Bablari Dewanganj W/S scheme within Nabadwip block under Krishnaganj Sub-Division under Nadia Division. | 220/KSD | 03/03/2023 | 15 | SAMAR ENTERPRISE | 0.3 | 0.24 | 100 | 100
4936 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. , SM/09206 | Augmentation | Wall Writing Work under Nadia Division P. H. Engineering Dte. | 1821/ND | 14/03/2024 | 31 | IMAGIN | 34.21 | 0.34 | 100 | 60
4937 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. , SM/09206 | Augmentation | Conversion of IEP to AIRP of capacity 10 Cu.m/hr at Daforpota Zone-II Water Supply Scheme within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 1905/ND | 15/03/2024 | 540 | SANDIP BISWAS | 63.46 | 0 | 0 | 70
4938 | NADIA | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. , SM/09206 | Augmentation | Continuation of Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 01-02-2024 to 31-07-2024= 182 days. | 125/RSD | 29/01/2024 | 182 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 3.18 | 0 | 0 | 50
4939 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11651 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 8/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | 154/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.41 | 4.36 | 100 | 100
4940 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11651 | Augmentation | Material Requisition To Resource Division | 1523/ND | 04/04/2023 | 0 | Resource Division | 77.13 | 0 | 0 | 0
4941 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11651 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 2.8 | 98.71 | 40
4942 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11651 | Augmentation | Material Requisition To Resource Division | 243/ND | 11/01/2024 | 0 | Resource Division | 5.33 | 0 | 0 | 0
4943 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11651 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | 4588/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 229.03 | 78.35 | 19
4944 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11651 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 5.92 | 98.73 | 30
4945 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11651 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
4946 | NADIA | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION , SM/11651 | Augmentation | Additional Work for Installation of SCADA System in connection with Augmentation of Surface Water Based Piped Water Supply Scheme for Northern Sector Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | 3447/ND | 23/07/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 732.35 | 0 | 0 | 15
4947 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. , SM/09525 | Retrofitting | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. | 04/PFMS | 26/04/2022 | 0 | M/S A.K.CONSTRUCTION | 0.73 | 0 | 0 | 0
4948 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. , SM/09525 | Retrofitting | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. | 01/PFMS | 26/04/2022 | 0 | M/S A.K.CONSTRUCTION | 11.48 | 0 | 0 | 0
4949 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. , SM/09525 | Retrofitting | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Sonda-I to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 63/ND | 05/01/2022 | 60 | M/S A.K.CONSTRUCTION | 33.87 | 10.03 | 100 | 100
4950 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. , SM/09525 | Retrofitting | Material Requisition To Resource Division | 7450/ND | 27/12/2021 | 0 | Resource Division | 11.02 | 0 | 0 | 0
4951 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. , SM/09525 | Retrofitting | Conversion of IEP to AIRP of capacity 9 Cu.m/hr at Sonda Water Supply Scheme within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 1904/ND | 15/03/2024 | 60 | SUMIT GHOSH | 63.49 | 0 | 0 | 0
4952 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. , SM/09525 | Retrofitting | Repair and renovation works of R.C.C. Elevated Reservoir 180 cum and allied works at 1st Pump House at Sonda Zone I Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | 5591/ND | 14/12/2023 | 292 | DAS CONSTRUCTION | 14.12 | 3.73 | 20.94 | 100
4953 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. , SM/09525 | Retrofitting | Renovation of AIRP (Semi-Gravity Type) of capacity 34 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Sonda Zone-I PWSS under Nadia Division PHE Dte. | 2995/ND | 13/07/2023 | 628 | TARUN KUMAR BHATTACHARYA | 62.48 | 5.5 | 17.96 | 40
4954 | NADIA | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. , SM/09525 | Retrofitting | Construction and installation of Manifold at OHR site and allied works in connection to the Augmentation of Sonda Zone II Water Supply Scheme under Krishnagar I Block under Nadia Division, P.H.E Dte. | 495/ND | 30/01/2025 | 180 | N.H. ENTERPRISE | 32.38 | 0 | 0 | 0
4955 | NADIA | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX, (Ghetugachhi), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme , SM/08006 | Retrofitting | Providing FHTC Functional Household Tap Connection under Jaldhara Jal Swapna for Zone IX Ghetugachi Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah Part Water Supply Scheme under Nadia Arsenic Division I PHE Dte | 784/NAD-I | 05/05/2021 | 60 | GHOSH ENTERPRISE | 92.92 | 173.95 | 93.65 | 100
4956 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Dogachhi W/S Scheme in Karimpur-II Block of Nadia District under Nadia Division, P.H.E. Dte. | 312/TSD | 24/11/2021 | 30 | RADIANT | 3.4 | 3.4 | 100 | 100
4957 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Construction of barbed wire fencing with concrete pillars at Dogachhi-Zone-II. water supply scheme(Sahebpara) (New Land 2nd T.W) under Tehatta Sub-Division PHE Dte. in JJM project . | 932/1/TSD | 14/03/2023 | 7 | NIVEDITA CONSTRUCTION | 0.71 | 0.71 | 100 | 0
4958 | NADIA | Central Drilling | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR DOGACHI (ZONE-I) W/S SCH, KARIMPUR-II BLOCK, UNDER NADIA DISTRICT, CDD, PHE DTE. | 1196/CDD | 11/11/2022 | 30 | M/S SAIKAT ENTERPRISE | 10.22 | 7.76 | 100 | 0
4959 | NADIA | Central Drilling | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Supply and delivery of Pea size Gravels at site for construction of Tube Well (300mm X 200mm X 150 Mtrs. Depth) by utilising Departmental Machineries for Dogachi Zone-I W/S Scheme, Karimpur-II Block under Nadia District under CMSD-II(D), CDD, PHE, Dte. | 535/CMSD-II | 02/12/2022 | 380 | M/S SAIKAT ENTERPRISE | 0.98 | 0.67 | 100 | 100
4960 | NADIA | Central Drilling | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | ADDITIONAL TRANSPORTATION OF DEPARTMENTAL RIG UNIT NO. SUPER RR WITH COMPRESSOR AND PUMP UNIT FROM DOGACHI UNDERCMSD-II (D), CDD, PHE DTE. | 562/CMSD-II | 30/12/2022 | 10 | PADMA ENGINEERING & CO. | 0.75 | 0.75 | 100 | 100
4961 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Material Requisition To Resource Division | 1903/ND | 27/04/2023 | 0 | Resource Division | 92.46 | 0 | 0 | 0
4962 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Material Requisition To Resource Division | 2321/ND | 29/05/2023 | 0 | Resource Division | 34.62 | 0 | 0 | 0
4963 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Material Requisition To Resource Division | 3641/ND | 16/08/2023 | 0 | Resource Division | 12.39 | 0 | 0 | 0
4964 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Sinking of 01 nos Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at 2nd Tubewell site, Dogachhi Zone-II PWSS Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | 4573/ND | 21/08/2024 | 30 | ZEST INFRACON | 17.4 | 0 | 0 | 0
4965 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Laying of Distribution System at Dogachi Mouza for Dogachi Piped Water Supply Scheme Zone-II in connection with Augmentation of Ground Based Water Supply Scheme at Dogachi PWSS to accommodate FHTC under Nadia Division, PHE Dte. | 3990/ND | 22/07/2024 | 60 | SUNIL KUMAR DATTA | 20.07 | 4.12 | 20.51 | 100
4966 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Sinking of 01 nos Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at Headwork site, Dogachhi Zone-II PWSS Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | 4574/ND | 21/08/2024 | 30 | ZEST INFRACON | 17.4 | 0 | 0 | 0
4967 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Construction of barbed wire fencing with concrete pillars at Dogachhi Zone-II (H/W) Site. water supply scheme(Sahebpara New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . | 1118/TSD | 21/02/2024 | 7 | NIVEDITA CONSTRUCTION | 1.71 | 1.6 | 100 | 100
4968 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangement At H.W Site & another Pump House (3.6m X 3.0m) Including Sanitary Arrangemet At 2nd Tube well site at Dogachi zone II Water Supply Scheme Under Kalyani Sub Division I PHE Dte.) | 3423/ND | 19/06/2024 | 90 | NIVEDITA CONSTRUCTION | 12.43 | 12.39 | 100 | 100
4969 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Laying of Distribution System for Dogachi Piped Water Supply Scheme Zone-I in connection with Augmentation of Ground Based Water Supply Scheme at Dogachi Zone-I to accommodate FHTC under Nadia Division, PHE Dte. | 3991/ND | 22/07/2024 | 144 | MALI CONSTRUCTION | 40.01 | 27.18 | 61.39 | 70
4970 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | (Horizontal) boring and Drum Sheet Walling for Dogachi Piped Water Supply Scheme Zone-I at Karimpur-II, Block at Nadia District under Nadia Division, PHE Dte. | 370/KlySD-I | 01/03/2024 | 31 | JOY HIND TUBEWELL'S | 13.42 | 13.4 | 100 | 100
4971 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 300 Cum Capacity 20 Mtr. Height RCC Over Head Reservoir (Excluding Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for construction of OHR all complete for Augmentation of Ground Based Water Supply Scheme at Dogachhi Zone-II to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 1398/ND | 29/03/2023 | 1008 | SUBHASH BOSE | 312.69 | 179.99 | 57.56 | 20
4972 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 350 Cum Capacity 20 Mtr. Height RCC Over Head Reservoir (Excluding Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for construction of OHR all complete for Augmentation of Ground Based Water Supply Scheme at Dogachhi Zone-I to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | 1719/ND | 17/04/2023 | 989 | JOY HIND TUBEWELL'S | 441.71 | 320.61 | 72.58 | 70
4973 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 77 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Dogachi Zone-I to accommodate FHTC under Nadia Division, PHE DTE. | 4349/ND | 07/08/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 218.56 | 0 | 0 | 70
4974 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube well and Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-Z-I & II under Dogachi ground water based water supply scheme under Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. [SM/13039] | 692/EMD | 04/04/2025 | 30 | PADMA ENGINEERING CO. | 50.38 | 0 | 0 | 0
4975 | NADIA | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II of Z-I & Z-II under DOGACHI ground water based water supply scheme under Block_ KARIMPUR-II Dist. - Nadia under EMD, PHE Dte. SM/13039 | 1121/EMD | 04/06/2025 | 90 | A.G ENTERPRISE. | 41.59 | 0 | 0 | 0
4976 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 51 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Dogachi Zone-II to accommodate FHTC within Karimpur-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | 5078/ND | 17/09/2024 | 180 | MANGES INDUSTRIAL CORPORATION | 183.53 | 0 | 0 | 0
4977 | NADIA | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE , SM/13039 | Augmentation | Laying of Distribution System and allied works for Dogachi Piped Water Supply Scheme Zone-I in connection with Augmentation of Ground Based Water Supply Scheme at Dogachi Zone-I to accommodate FHTC under Nadia Division, PHE Dte. | 1663/ND | 08/04/2025 | 60 | MALI CONSTRUCTION | 26.66 | 0 | 0 | 0
4978 | NADIA | Nadia Arsenic Division I | Surface Water Based Piped Water Supply Scheme Saguna Zone-VI (Part-I) for Arsenic Affected Areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE. Dte. , SM/11490 | Augmentation | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete with Laying of Distribution System Including Specials, Valves & Pipe Supporting Structure, Construction of Boundary Wall (675m Length), Chlorine Room, Drain (I300 m Length) and Approach Road (60.0m Length and 3.0m Wide), Construction of 900 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials and Soil Investigation for the work of Construction of R.C.C Elevated Reservoir of Capacity 900 m3 Staging Height 20Mtr. at Surface Water Based Piped Water Supply Scheme for Saguna ZONE-VI(PART-I) in Chakdah Block of Nadia District under Nadia Arsenic Division-I, PHE Dte. | 1708/NAD-I | 14/07/2023 | 366 | MONDAL ENTERPRISE | 676.94 | 0 | 0 | 0
4979 | NADIA | Nadia Arsenic Division I | Surface Water Based Piped Water Supply Scheme Saguna Zone-VI (Part-I) for Arsenic Affected Areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE. Dte. , SM/11490 | Augmentation | Route Survey for providing FHTC (Functional Household Tap Connection) under JJM (Jal Jeevan Mission) by Augmentation of Zone-VI (Saguna) Part -I of Surface Water Based PWSS for Haringhata and Chakdah (PArt) at Chakdah Block at Nadia District under Nadia Arsenic Division -I, P.H.E. Dte.(Sl.No.-01) | 168 / AE-I / NAD-I | 08/07/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 4.78 | 4.78 | 100 | 100
4980 | NADIA | Nadia Arsenic Division I | Surface Water Based Piped Water Supply Scheme Saguna Zone-VI (Part-I) for Arsenic Affected Areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE. Dte. , SM/11490 | Augmentation | Material Requisition To Resource Division | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 31.72 | 0 | 0 | 0
4981 | NADIA | Nadia Arsenic Division I | Surface Water Based Piped Water Supply Scheme Saguna Zone-VI (Part-I) for Arsenic Affected Areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE. Dte. , SM/11490 | Augmentation | Laying of Pipeline for FHTC works under Surface Water Based PWSS Saguna Zone-VI (Part-II) for arsenic affected areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | 1117/NAD-I | 19/07/2024 | 300 | APURBA MANDAL | 95.96 | 0 | 0 | 85
4982 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-II within Kaliganj Block (Phase-A). , SM/07002 | Retrofitting | PREPERATION OF DETAILS PROJECT FOR FHTC AT SURFACE WATER BASED W/S SCHEME ( N.SECTOR) , PART-II, ZONE-I, PHASE-A & B UNDER , NADIA DIVISION , PHE ,DTE | 139/FHTC | 17/08/2021 | 0 | LEMNISCATE | 0.46 | 0 | 0 | 0
4983 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-II within Kaliganj Block (Phase-A). , SM/07002 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT NORTHERN SECTOR PART-1 Z-2 | 445/DW | 25/03/2021 | 0 | MONDAL ENTERPRISE | 44.33 | 0 | 0 | 0
4984 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-II within Kaliganj Block (Phase-A). , SM/07002 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PIPE G.I/PVC PIPE OF AVERAGE LENGTH OF 10MM DIA GUN-METAL FERRULE, SADDLE PIECE 15MM DIA BIB COCK ETC AT SUBERNA BIHAR W/S SCHEME PART-B | 473/DW | 07/02/2022 | 0 | ROY CONSTRUCTION | 0.73 | 0 | 0 | 0
4985 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-II within Kaliganj Block (Phase-A). , SM/07002 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme(northern sector),Part-I,Zone-II within Kaliganj block(Phase-A) in Nadia District under Nadia Division P.H.Engineering Dte. | 3589/ND | 08/12/2020 | 90 | MONDAL ENTERPRISE | 97.01 | 90.15 | 92.93 | 0
4986 | NADIA | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-II within Kaliganj Block (Phase-A). , SM/07002 | Retrofitting | Hiring of Diesel Ambassador Car/maxi cab for the office of the Assistant Engineer, Debagram Sub-Division, P.H. Engineering Dte., Debagram, Nadia with effect from 01/08/22 to 31/07/23 | 312/D/DSD | 29/07/2022 | 365 | TARUN KUMAR BHATTACHARYA | 4.8 | 1.11 | 38.26 | 70
4987 | NADIA | Nadia Division | Collection of Information and subsequent Geo tagging of various newly installed drinking water sources for successful water quality monitoring and surveillance through Integrated Water Quality Management Information System (IWQ-MIS) for District Specific , SM/11956 | Support-MIS | Collection of Information and subsequent Geo tagging of various newly installed drinking water sources for successful water quality monitoring and surveillance through Integrated Water Quality Management Information System (IWQ-MIS) for District Specific Water Quality Dashboard of Nadia. | 1115/Kly SD-1 | 05/12/2022 | 30 | HORIZEN | 4.39 | 1.31 | 100 | 30
4988 | NADIA | Nadia Division | Detailed field study and data acquisition of different components of Distribution System, Transmission main (raw and clear water) and Household Connection lines along with all valves and other relevant information of Piped Water Supply Schemes under Nadia , SM/13526 | Support-MIS | Detailed field study and data acquisition of different components of Distribution System, transmission main (raw and clear water) and Household Connections along with all valves and other relevant information of Piped Water Supply Schemes under Nadia Division, PHE Dte. | 5395/ND | 23/12/2022 | 1095 | HORIZEN | 48.32 | 18.89 | 39.1 | 35
4989 | NADIA | Nadia Division | Providing consultancy services including supply of necessary instruments, chemicals and glass ware for NABL Accreditation of Nadia District Water Testing Laboratory, Kalyani. , SM/06873 | Support-WQMSP | SUPPLY OF RESIDUAL CHLORINE TESTING UNIT KIT .........NADIA , DIVISION, PHE, DTE | 377/DW | 27/01/2021 | 0 | MRINAL DASGUPTA | 0.81 | 0 | 0 | 0
4990 | NADIA | Nadia Division | Providing consultancy services including supply of necessary instruments, chemicals and glass ware for NABL Accreditation of Nadia District Water Testing Laboratory, Kalyani. , SM/06873 | Support-WQMSP | PROVIDING CONSULTANCY SERVICE INCLUDING SUPPLY OF NECESSARY INSTRUMENT ......WATER TESTING LAB AT KALYANI | 458/DW | 30/03/2021 | 0 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 16.28 | 0 | 0 | 0
4991 | NADIA | Nadia Division | Providing consultancy services including supply of necessary instruments, chemicals and glass ware for NABL Accreditation of Nadia District Water Testing Laboratory, Kalyani. , SM/06873 | Support-WQMSP | SUPPLY, DELIVERY, INSTALLATION, ........NADIA, DIVSION, PHE, DTE. | 377/DW | 27/01/2021 | 0 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.99 | 0 | 0 | 0
4992 | NADIA | Nadia Division | Providing consultancy services including supply of necessary instruments, chemicals and glass ware for NABL Accreditation of Nadia District Water Testing Laboratory, Kalyani. , SM/06873 | Support-WQMSP | RECURRING EXPENDITURE OF LABORATORIES (NABL) | 62/NABL | 08/07/2021 | 0 | OTHERS | 0.06 | 0 | 0 | 0
4993 | NADIA | Nadia Division | Providing consultancy services including supply of necessary instruments, chemicals and glass ware for NABL Accreditation of Nadia District Water Testing Laboratory, Kalyani. , SM/06873 | Support-WQMSP | INRACSTRUCTURE DEVELOPMENT REGARDING NABL .... NADIA DIVISION, PHE, DTE | 203/DW | 22/09/2021 | 0 | SUMAN CHAKRABORTY | 1.98 | 0 | 0 | 0
4994 | NADIA | Nadia Division | Supply, Delivery, Installation of Computer and Peripheral for the Official Use under The Office of the Executive Engineer Nadia Division and Different Sub-Division Offices under Nadia Division, PHE Dte. , SM/10400 | Support-MIS | Supply, Delivery, Installation of Computer and Peripheral for the Official Use under The Office of the Executive Engineer Nadia Division and Different Sub-Division Offices under Nadia Division, PHE Dte. | 70/PFMS | 05/07/2022 | 0 | IONET | 4.15 | 0 | 0 | 0
4995 | NADIA | Nadia Division | Supply, Delivery, Installation of Computer and Peripheral for the Official Use under The Office of the Executive Engineer Nadia Division and Different Sub-Division Offices under Nadia Division, PHE Dte. , SM/10400 | Support-MIS | SUPPLY AND INSTALLATION OF CANON MULTI FUNCTIONAL MACHINE. | 156/PFMS | 22/09/2022 | 0 | IONET | 4.89 | 0 | 0 | 0
4996 | NADIA | Nadia Division | Supply, Delivery, Installation of Computer and Peripheral for the Official Use under The Office of the Executive Engineer Nadia Division and Different Sub-Division Offices under Nadia Division, PHE Dte. , SM/10400 | Support-MIS | SUPPLY, INSTALLATION OF HP LASER. | 153/PFMS | 22/09/2022 | 0 | IONET | 2.24 | 0 | 0 | 0
4997 | NADIA | Nadia Division | Supply, Delivery, Installation of Computer and Peripheral for the Official Use under The Office of the Executive Engineer Nadia Division and Different Sub-Division Offices under Nadia Division, PHE Dte. , SM/10400 | Support-MIS | Supply, Delivery, Installation of Computer and Peripheral for the Official Use under The Office of the Executive Engineer Nadia Division and Different Sub-Division Offices under Nadia Division, PHE Dte. | 71/PFMS | 05/07/2022 | 0 | IONET | 0.03 | 0 | 0 | 0
4998 | NADIA | Nadia Division | Supply, Delivery, Installation of Computer and Peripheral for the Official Use under The Office of the Executive Engineer Nadia Division and Different Sub-Division Offices under Nadia Division, PHE Dte. , SM/10400 | Support-MIS | SUPPLY AND INSTILLATION OF HP INTEL CORE i5 COMPUTER SET. | 155/PFMS | 22/09/2022 | 0 | IONET | 3.6 | 0 | 0 | 0
4999 | NADIA | Nadia Division | Supply, Delivery, Installation of Computer and Peripheral for the Official Use under The Office of the Executive Engineer Nadia Division and Different Sub-Division Offices under Nadia Division, PHE Dte. , SM/10400 | Support-MIS | Supply, Delivery, Installation of Computer and Peripheral for the Official Use under The Office of the Executive Engineer Nadia Division and Different Sub-Division Offices under Nadia Division, PHE Dte. | 69/PFMS | 05/07/2022 | 0 | IONET | 0.04 | 0 | 0 | 0
5000 | NADIA | Nadia Division | Supply, Delivery, Installation of Computer and Peripheral for the Official Use under The Office of the Executive Engineer Nadia Division and Different Sub-Division Offices under Nadia Division, PHE Dte. , SM/10400 | Support-MIS | SUPPLY, INSTALLATION OF HP MULTI FUNCTION MACHINES IN THE OFFICE OF THE EXECUTIVE ENGINEER, NADIA DIVISION, PHE DTE. | 289/PFMS | 17/11/2022 | 0 | IONET | 2.94 | 0 | 0 | 0
5001 | NADIA | Nadia Division | Supply, Delivery, Installation of Computer and Peripheral for the Official Use under The Office of the Executive Engineer Nadia Division and Different Sub-Division Offices under Nadia Division, PHE Dte. , SM/10400 | Support-MIS | SUPPLY, DELIVERY AND INSTALLATION OF DELL NEW INSPIRATION 24i7 AIO (5410) OF THE OFFICE OF THE EXECUTIVE ENGINEER, NADIA DIVISION, PHE DTE. | 297/PFMS | 22/11/2022 | 0 | IONET | 1.63 | 0 | 0 | 0
5002 | NADIA | Nadia Division | Supply, Delivery, Installation of Computer and Peripheral for the Official Use under The Office of the Executive Engineer Nadia Division and Different Sub-Division Offices under Nadia Division, PHE Dte. , SM/10400 | Support-MIS | SUPPLY OF COMPUTER PERIPHERALS. | 108/PFMS | 12/08/2022 | 0 | IONET | 1.92 | 0 | 0 | 0
5003 | NADIA | Nadia Division | Supply, Delivery, Installation of Computer and Peripheral for the Official Use under The Office of the Executive Engineer Nadia Division and Different Sub-Division Offices under Nadia Division, PHE Dte. , SM/10400 | Support-MIS | Supply, Delivery, Installation of Computer and Peripheral for the Official Use under The Office of the Executive Engineer Nadia Division and Different Sub-Division Offices under Nadia Division, PHE Dte. | 68/PFMS | 05/07/2022 | 0 | IONET | 4.5 | 0 | 0 | 0
5004 | NADIA | Nadia Division | Supply, Delivery, Installation of Computer and Peripheral for the Official Use under The Office of the Executive Engineer Nadia Division and Different Sub-Division Offices under Nadia Division, PHE Dte. , SM/10400 | Support-MIS | SUPPLY OF HP 1000 STANDER DISPLAY. | 154/PFMS | 22/09/2022 | 0 | IONET | 4.15 | 0 | 0 | 0
5005 | NADIA | Nadia Division | Supply, Delivery, Installation of Computer and Peripheral for the Official Use under The Office of the Executive Engineer Nadia Division and Different Sub-Division Offices under Nadia Division, PHE Dte. , SM/10400 | Support-MIS | SUPPLY, DELIVERY AND INSTALLATION OF DELL NEW INSPIRATION 24i7 AIO (5410) OF THE OFFICE OF THE EXECUTIVE ENGINEER, NADIA DIVISION, PHE DTE. |  | 11/11/2022 | 0 | IONET | 1.63 | 0 | 0 | 0
5006 | NADIA | Nadia Division | Supply, Delivery, Installation of Computer and Peripheral for the Official Use under The Office of the Executive Engineer Nadia Division and Different Sub-Division Offices under Nadia Division, PHE Dte. , SM/10400 | Support-MIS | SUPPLY AND INSTALLATION OF EPSON PLOTTER MACHINE. | 157/PFMS | 22/09/2022 | 0 | IONET | 4.85 | 0 | 0 | 0
5007 | NADIA | Nadia Division | SUPPLY, COMMISSIONING & MONITORING OF INTELLIGENT DISINFECTION SYSTEMS FOR FREE COMPLETE DISINFECTION OF DRINKING WATER SUPPLIED THROUGH PIPED WATER SUPPLY SCHEMES WITH MONITORING OF DOSAGE STRENGTH FOR ADDITIONAL 4 NOS AT BARAKULTA WATER SUPPLY SCHEME UN , SM/14142 | Support-WQMSP | Supply , Commissioning & Monitoring of Intelligent Disinfection systems for free complete disinfection of drinking water supplied through piped water supply schemes with monitoring of dosage strength for 5 nos at Barakulta water supply scheme under Nadia Division ,P.H.Engineering Dte. | 66/ND | 05/01/2023 | 90 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 12.58 | 9.84 | 97.78 | 70
5008 | NADIA | Nadia Division | Feasibility study for identification of suitable location of proposed intake for drawl of 30.08 MLD Raw water from river Bhagirathi at Nakashipara block for water supply project at Northern Sector (Part-II) in Nadia District under PHED, Govt Of West Benga , SM/13312 | Support-M&E | HYDROGRAPHIC SURVEY CHARGE. | 349/PFMS | 03/01/2023 | 0 | SHYAMA PRASAD MOOKERJEE PORT, KOLKATA | 52.65 | 0 | 0 | 0
5009 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Continuation of work order for Arrear Payment for enhanced monthly remuneration of laboratory personnel of Nadia District Water Testing Laboratory at W.T.P, Haringhata under Kalyani Sub-Division-1 PH Engineering Dte in the district of Nadia. W.e.f. 01/09/2023 to 30/11/2023 (Three months) | 909/KLYSD-I | 28/08/2023 | 92 | M/S S.K. ENTERPRISE | 0.84 | 0.21 | 100 | 100
5010 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment for enhancement of monthly remuneration of 02 Nos personnel (State Lab Sr. Chemist, State Lab Chemist/ Bacteriologest, ) at 01 Nos State Laboratory under Nadia Division, PHE Dte. on contractual basis. | 886/KLYSD-I | 21/08/2023 | 7 | M/S S.K. ENTERPRISE | 0.69 | 0.69 | 100 | 100
5011 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Continuation of work order for Monthly remuneration of one(01) no of lab assistant, one(01) no of Lab attendant and one(01) no sampling assistant through agency at Habibpur SD lab & Nadia District Laboratory under Nadia Division, PHE Dte. W.e.f. 01/09/2023 to 30/11/2023 (Three months) | 933/KLYSD-I | 31/08/2023 | 91 | M/S S.K. ENTERPRISE | 0.75 | 0.34 | 100 | 100
5012 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment for enhancement of monthly remuneration of 01 Nos personnel(State Lab Sr.Chemist) at'Kalyani State Referral Laboratory"under Nadia division,PHE Dte.on contractual basis W.e.f.01.09.2023 to 30.09.2023 | 1202/KLYSD-I | 10/11/2023 | 30 | M/S S.K. ENTERPRISE | 0.18 | 0.18 | 100 | 100
5013 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR HARANAGAR NGO LAB FOR THE MONTH OF NOV-23. | 424/PFMS | 13/12/2023 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5014 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BARA ANDULIA MOHILA SAMITY NGO LAB FOR THE MONTH OF NOV-23. | 426/PFMS | 13/12/2023 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5015 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BINOY BADAL DINESH CLUB NGO LAB FOR THE MONTH OF NOV-23. | 427/PFMS | 13/12/2023 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5016 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR WBCADC RANAGHAT-II NGO LAB FOR THE MONTH OF NOV-23. | 423/PFMS | 13/12/2023 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.33 | 0 | 0 | 0
5017 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA ZILLA GANATANTRIC MOHILA SAMITY NGO LAB FOR THE MONTH OF NOV-23. | 425/PFMS | 13/12/2023 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5018 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Operational Charges of NGO Managed Laboratory for Bara Andulia Mohila Samity. | 449/PFMS | 22/12/2023 | 0 | BARA ANDULIA MAHILA SAMITY | 0.4 | 0 | 0 | 0
5019 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of 25 Nos personnel (Sub-District Chemist, Sub- District Bacteriologest, Sub-District Lab-Assistant, Sub-District Sampling Assistant, Sub- District Lab attendant and District Chemist, District Bacteriologest, District Lab-Assistant, District Sampling Assistant, District Lab attendant ) at 04 Nos Sub-District Laboratories & 01 District Laboratory under Nadia Division, PHE Dte. on contractual basis with effecct from 01-09-2023 to 31-08-2024. | 3841/ND | 28/08/2023 | 365 | CLIFFORD FACILITY SERVICES PVT. LTD | 50.56 | 43.18 | 100 | 30
5020 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Remuneration of State Water Testing laboratory personnel for the month of October of 2022-2023 at W.T.P, Haringhata under Nadia Division, P.H.E. Dte. Kalyani Nadia. | 1029/KLYSD-I | 29/09/2023 | 61 | M/S S.K. ENTERPRISE | 0.34 | 0.34 | 100 | 100
5021 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | AD-HOC BONUS BILL FOR 01 NO BACTERIOLOGIST, 01 NO CHEMIST, 01 NO LAB ASSISTANT FOR BARA ANDULIA MAHILA SAMITY NGO LABORATORY PERSONNEL FOR THE YEAR 2022-2023 |  | 22/12/2023 | 0 | BARA ANDULIA MAHILA SAMITY | 0.16 | 0 | 0 | 0
5022 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | AD-HOC BONUS BILL FOR 01 NO BACTERIOLOGIST, 01 NO CHEMIST, 01 NO LAB ASSISTANT FOR NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED NGO LABORATORY PERSONNEL FOR THE YEAR 2022-2023 |  | 22/12/2023 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.16 | 0 | 0 | 0
5023 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | AD-HOC BONUS BILL FOR 01 NO BACTERIOLOGIST, 01 NO CHEMIST, 01 NO LAB ASSISTANT FOR BINAY BADAL DINESH CLUB NGO LABORATORY PERSONNEL FOR THE YEAR 2022-2023 |  | 22/12/2023 | 0 | BINAY BADAL DINESH CLUB | 0.16 | 0 | 0 | 0
5024 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 46/PFMS | 14/05/2024 | 0 | BARA ANDULIA MAHILA SAMITY | 0.45 | 0 | 0 | 0
5025 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 72/PFMS | 13/06/2024 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.45 | 0 | 0 | 0
5026 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 174/PFMS | 14/08/2024 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.45 | 0 | 0 | 0
5027 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 348/PFMS | 26/11/2024 | 0 | BINAY BADAL DINESH CLUB | 0.45 | 0 | 0 | 0
5028 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of Operational Charges of NGO managed Water Testing Laboratory at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. Financial Year: 2024-2025, Instalment: 1st | 185/PFMS | 21/08/2024 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.4 | 0 | 0 | 0
5029 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 110/PFMS | 16/07/2024 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.45 | 0 | 0 | 0
5030 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | AD-HOC BONUS BILL FOR 01 NO BACTERIOLOGIST, 01 NO CHEMIST, 01 NO LAB ASSISTANT FOR HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO LABORATORY PERSONNEL FOR THE YEAR 2022-2023 |  | 22/12/2023 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.16 | 0 | 0 | 0
5031 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 519/PFMS | 09/02/2024 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.45 | 0 | 0 | 0
5032 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 590/PFMS | 12/03/2024 | 0 | BINAY BADAL DINESH CLUB | 0.61 | 0 | 0 | 0
5033 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Operational charges of NGO Managed Laboratories (BINAY BADAL DINESH CLUB) at Nadia District. | 20/PFMS | 24/04/2024 | 0 | BINAY BADAL DINESH CLUB | 0.35 | 0 | 0 | 0
5034 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 49/PFMS | 14/05/2024 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.45 | 0 | 0 | 0
5035 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 48/PFMS | 14/05/2024 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.45 | 0 | 0 | 0
5036 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 73/PFMS | 13/06/2024 | 0 | BINAY BADAL DINESH CLUB | 0.45 | 0 | 0 | 0
5037 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 238/PFMS | 10/09/2024 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.45 | 0 | 0 | 0
5038 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 357/PFMS | 10/12/2024 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.45 | 0 | 0 | 0
5039 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 354/PFMS | 10/12/2024 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.45 | 0 | 0 | 0
5040 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | AD-HOC BONUS BILL FOR 01 NO BACTERIOLOGIST, 01 NO CHEMIST, 01 NO LAB ASSISTANT FOR W.B.C.A.D.C. RANAGHAT-II NGO LABORATORY PERSONNEL FOR THE YEAR 2022-2023 |  | 22/12/2023 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.16 | 0 | 0 | 0
5041 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA BARA ANDULIA MAHILA SAMITY NGO LAB FOR THE MONTH OF DEC-23. | 469/PFMS | 11/01/2024 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5042 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 587/PFMS | 12/03/2024 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.61 | 0 | 0 | 0
5043 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 586/PFMS | 12/03/2024 | 0 | BARA ANDULIA MAHILA SAMITY | 0.61 | 0 | 0 | 0
5044 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 02/PFMS | 10/04/2024 | 0 | BARA ANDULIA MAHILA SAMITY | 0.45 | 0 | 0 | 0
5045 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 351/PFMS | 26/11/2024 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.45 | 0 | 0 | 0
5046 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 113/PFMS | 16/07/2024 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.45 | 0 | 0 | 0
5047 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of Operational Charges of NGO managed Water Testing Laboratory at Haranagar SKUS LTD NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. 1st installment. | 186/PFMS | 21/08/2024 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.4 | 0 | 0 | 0
5048 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 69/PFMS | 13/06/2024 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.45 | 0 | 0 | 0
5049 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 355/PFMS | 10/12/2024 | 0 | BINAY BADAL DINESH CLUB | 0.45 | 0 | 0 | 0
5050 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO LAB FOR THE MONTH OF DEC-23. | 467/PFMS | 11/01/2024 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5051 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED NGO LAB FOR THE MONTH OF DEC-23. | 468/PFMS | 11/01/2024 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5052 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | CHARGES FOR NGO LABORATORY MAINTAINING. |  | 15/02/2024 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.35 | 0 | 0 | 0
5053 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Operational charges of NGO managed Laboratories (HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD.) at Nadia District. | 19/PFMS | 24/04/2024 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.35 | 0 | 0 | 0
5054 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 01/PFMS | 10/04/2024 | 0 | BINAY BADAL DINESH CLUB | 0.45 | 0 | 0 | 0
5055 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 05/PFMS | 10/04/2024 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.45 | 0 | 0 | 0
5056 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 03/PFMS | 10/04/2024 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.45 | 0 | 0 | 0
5057 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Arrangement for annual operational charges of Binoy Badal Dinesh Club NGO managed Water testing Laboratory under Nadia Division, PHE Dte. for 1st instalment of 2023-2024. | 96/PFMS | 03/07/2024 | 0 | BINAY BADAL DINESH CLUB | 0.4 | 0 | 0 | 0
5058 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 237/PFMS | 10/09/2024 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.45 | 0 | 0 | 0
5059 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 111/PFMS | 16/07/2024 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.45 | 0 | 0 | 0
5060 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BINAY BADAL DINESH CLUB NGO LAB FOR THE MONTH OF DEC-23. | 470/PFMS | 11/01/2024 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5061 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 588/PFMS | 12/03/2024 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.61 | 0 | 0 | 0
5062 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 234/PFMS | 10/09/2024 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.45 | 0 | 0 | 0
5063 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 327/PFMS | 05/10/2024 | 0 | BINAY BADAL DINESH CLUB | 0.63 | 0 | 0 | 0
5064 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 70/PFMS | 13/06/2024 | 0 | BARA ANDULIA MAHILA SAMITY | 0.45 | 0 | 0 | 0
5065 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 171/PFMS | 14/08/2024 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.45 | 0 | 0 | 0
5066 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 175/PFMS | 14/08/2024 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.45 | 0 | 0 | 0
5067 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 236/PFMS | 10/09/2024 | 0 | BARA ANDULIA MAHILA SAMITY | 0.45 | 0 | 0 | 0
5068 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 173/PFMS | 14/08/2024 | 0 | BARA ANDULIA MAHILA SAMITY | 0.45 | 0 | 0 | 0
5069 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 358/PFMS | 10/12/2024 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.45 | 0 | 0 | 0
5070 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 112/PFMS | 16/07/2024 | 0 | BINAY BADAL DINESH CLUB | 0.45 | 0 | 0 | 0
5071 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 520/PFMS | 09/02/2024 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.45 | 0 | 0 | 0
5072 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 356/PFMS | 10/12/2024 | 0 | BARA ANDULIA MAHILA SAMITY | 0.45 | 0 | 0 | 0
5073 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of Operational Charges of NGO managed Water Testing Laboratory at Binay Badal Dinesh Club NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. Financial Year: 2023-2024, Instalment: 2nd Period of Instalment month: 01-10-2023 to 31-03-2024 | 184/PFMS | 21/08/2024 | 0 | BINAY BADAL DINESH CLUB | 0.35 | 0 | 0 | 0
5074 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 235/PFMS | 10/09/2024 | 0 | BINAY BADAL DINESH CLUB | 0.45 | 0 | 0 | 0
5075 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 347/PFMS | 26/11/2024 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.45 | 0 | 0 | 0
5076 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 349/PFMS | 26/11/2024 | 0 | BARA ANDULIA MAHILA SAMITY | 0.45 | 0 | 0 | 0
5077 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 71/PFMS | 13/06/2024 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.45 | 0 | 0 | 0
5078 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 326/PFMS | 05/10/2024 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.63 | 0 | 0 | 0
5079 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity managed Water Testing Laboratory under Nadia Division, PHE Dte. | 522/PFMS | 09/02/2024 | 0 | BARA ANDULIA MAHILA SAMITY | 0.45 | 0 | 0 | 0
5080 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 521/PFMS | 09/02/2024 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.45 | 0 | 0 | 0
5081 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 47/PFMS | 14/05/2024 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.45 | 0 | 0 | 0
5082 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 45/PFMS | 14/05/2024 | 0 | BINAY BADAL DINESH CLUB | 0.45 | 0 | 0 | 0
5083 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 330/PFMS | 05/10/2024 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.63 | 0 | 0 | 0
5084 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 109/PFMS | 16/07/2024 | 0 | BARA ANDULIA MAHILA SAMITY | 0.45 | 0 | 0 | 0
5085 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR W.B.C.A.D.C. RANAGHAT-II NGO LAB FOR THE MONTH OF DEC-23. | 466/PFMS | 11/01/2024 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.33 | 0 | 0 | 0
5086 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 523/PFMS | 09/02/2024 | 0 | BINAY BADAL DINESH CLUB | 0.45 | 0 | 0 | 0
5087 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 589/PFMS | 12/03/2024 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.61 | 0 | 0 | 0
5088 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 04/PFMS | 10/04/2024 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.45 | 0 | 0 | 0
5089 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 329/PFMS | 05/10/2024 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.63 | 0 | 0 | 0
5090 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. | 172/PFMS | 14/08/2024 | 0 | BINAY BADAL DINESH CLUB | 0.45 | 0 | 0 | 0
5091 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 350/PFMS | 26/11/2024 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.45 | 0 | 0 | 0
5092 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. | 328/PFMS | 05/10/2024 | 0 | BARA ANDULIA MAHILA SAMITY | 0.63 | 0 | 0 | 0
5093 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19066 | Support-WQMSP | Continuation for Payment of remuneration for engagement of 27 Nos personnel (Sub-District Chemist, Sub- District Bacteriologest, Sub-District Lab-Assistant, Sub-District Sampling Assistant, Sub- District Lab attendant and District Chemist, District Bacteriologest, District Lab-Assistant, District Sampling Assistant, District Lab attendant ) at 04 Nos Sub-District Laboratories & 01 District Laboratory under Nadia Division, PHE Dte. on contractual basis with effecct from 01-10-2025 to 30-11-2025. | 3783/ND | 12/08/2025 | 60 | TARUN KUMAR BHATTACHARYA | 8.74 | 0 | 0 | 0
5094 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order Of 1 No Microtek 650va Ups, 1 no Formujet TN 2365 Toner Cartidge , 1 No Formujet F 2612a Toner Cartidge , | 563/PFMS | 02/03/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5095 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order Of 4 No Formujet TN 2365 Toner Cartidge , 1 No Formujet 12A Toner Cartridge Refill, 1 No Formujet CF 247A Toner Cartridge Refill , 1 No Microtek 650a Ups . | 564/PFMS | 02/03/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5096 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 No of Canon NPG-67 Toner Black under Nadia Division, PHE Dte. | 29/PFMS | 30/04/2024 | 0 | IONET | 0.07 | 0 | 0 | 0
5097 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 No of Canon NPG-67 Toner Magenta under Nadia Division, PHE Dte. | 34/PFMS | 30/04/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5098 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance cum supply order of 2 No Formujet 110A Toner Cartidge With Chip, 2 no formujet Pantum PC208EK Cartidge , | 571/PFMS | 02/03/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5099 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order Of 1 No Formujet TN 2365 Toner Cartidge , 3 No Formujet 110A Toner Cartridge With Chip. | 573/PFMS | 02/03/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5100 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance cum supply order of 1 No Formujet 110A Toner Cartidge With Chip, 3 no Forrmujet Pantum PC208EK Cartidge . | 567/PFMS | 02/03/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5101 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order Of 1 No Formujet 110A Toner Cartidge With Chip, 4 no Formujet TN 2365 Toner Cartidge , 1 No Formujet Pantum PC208EK Cartidge , | 570/PFMS | 02/03/2024 | 0 | IONET | 0.1 | 0 | 0 | 0
5102 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 No Crucial HDD SSD 1TB SATA (BX500), 1 No of Slite Ram Lap D4 4GB 2400 Gold under Nadia Division PHE Dte. | 138/PFMS | 27/07/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5103 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 4 No Formujet F TN-2365 Toner, 2 No of HP Pen Drive 64GB Metal Body V236W Big ( 2.0), 1 Nos of Formujet F HP 110a WITH Chip under Nadia Division PHE Dte. | 140/PFMS | 27/07/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5104 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 no ¿CANON NPGV 67 BLACK CARTRIDGE", under nadia Division P.H.E Dte. | 133/PFMS | 27/07/2024 | 0 | IONET | 0.07 | 0 | 0 | 0
5105 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Canon Multifunction Machines Mfm, On Site OEM Warranty 3 Year under Kalyani Sub-Division-I, Kalyani, PHE Dte, Which will be delivered to Krishnagar sub-division, PHE Dte. Nadia. | 544/PFMS | 17/02/2024 | 0 | EASY DAY ENTERPRISE | 2.3 | 0 | 0 | 0
5106 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 No of Canon NPG-67 Toner Cyan under Nadia Division, PHE Dte | 31/PFMS | 30/04/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5107 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 No of Canon NPG-67 Toner Yellow under Nadia Division, PHE Dte. | 33/PFMS | 30/04/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5108 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Supply of HP Intel core i5 11500 8GB/ 1000 GB HDD/ Windows 10 Professional Details Are Given Bellow: DESKTOP HP 280 G9 (78Y44PA)-I5 @2 Nos (Model No: 1N14094FJ, 1N140904FP) & DESKTOP HP 280 G9 (6X3W3PA#ACJ) @4 Nos (Model No: 4CE336CFJ6,1N140308PQ, 1N140904FQ, 1N140904HC) with HP Monitor P22vb G5 FHD Monitor- 8L1L6A7 @4 Nos ( Model No: 1N24030MM5, 1N24030LVM, 1N24030LVG, 1N24030LVK) Monitor 21.5'' HP LED P22VB G4 FHD ( 3C0E6A7)-HDMI, @2 Nos ( Model No: 1N23221051, 1N23121742) | 142/PFMS | 30/07/2024 | 0 | IONET | 4.97 | 0 | 0 | 0
5109 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 2 No Formujet F DR-2365 Drum Unit, 1 No of Formujet CF247A Toner CARTRIGE, 3 Nos of Formujet F TN-2365 Toner under Nadia Division PHE Dte. | 139/PFMS | 27/07/2024 | 0 | IONET | 0.07 | 0 | 0 | 0
5110 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order Of 1 No Formujet TN 2365 Toner Cartidge , 2 No Formujet 110A Toner Cartridge With Chip , 1 No Formujet DR 2365 Drum Unit , 1 No Adnet Speaker Usb 2.0, 1 No Frontek Spike Buster, | 566/PFMS | 02/03/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5111 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order Of 1 No Mictotek 650va Ups , 1 No Formujet 110a Toner Cartridge With Chip, 2 No Formujet DR 2365 Drum Unit , 1 No Formujet TN 2365 Toner Cartidge , | 568/PFMS | 02/03/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5112 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Brother Multifunction Machines Mfm, On Site OEM Warranty 1 Year, Brand: Brother, Model: MFC-L2701DW, HSN Code: 84433100 Gem Invoice No: GEM-42851152, GeM invoice Date: 06/04/2024, Order No: GEMC-511687761970101, Order Date: 05/04/2024 | 28/PFMS | 30/04/2024 | 0 | IONET | 0.25 | 0 | 0 | 0
5113 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 No Formujet F Hp 110A With Chip, 1 No of Formujet F 88A, 2 Nos of HDD Casing Transparent 3.0 under Nadia Division PHE Dte. | 136/PFMS | 27/07/2024 | 0 | IONET | 0.05 | 0 | 0 | 0
5114 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 No Microtek Ups 650VA, 1 No of Formujet F 2312A Toner, 1 Nos of Quick Heal Total Security 1 User for 3 Years under Nadia Division PHE Dte. | 132/PFMS | 27/07/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5115 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Supply of Desktop Computer HP Intel Core i5 12500 8 GB/ 1000 GB HDD/ Windows 11 Professional with 3 years warranty as per GeM. | 533/PFMS | 10/02/2024 | 0 | EASY DAY ENTERPRISE | 4.9 | 0 | 0 | 0
5116 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Canon Multifunction Machines mfm, on site OEM Warranty 3 years under Kalyani sub-division-I, Kalyani, PHE Dte. | 534/PFMS | 10/02/2024 | 0 | EASY DAY ENTERPRISE | 2.3 | 0 | 0 | 0
5117 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order Of 2 No Formujet Pantum PC208EK Cartidge , 2 No Formujet 110a Toner Cartridge With Chip. | 572/PFMS | 02/03/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5118 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order Of 3 No Formujet F 2612A Toner Cartidge, 3 No Formujet TN 2365 Toner Cartidge, 1 No Formujet 110A Toner Cartridge With Chip | 565/PFMS | 02/03/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5119 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 No of Canon NPG-67 Toner Yellow under Nadia Division, PHE Dte. | 35/PFMS | 30/04/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5120 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 No Canon NPG 67 Black Cartridge, 1 No Formujet TN 3448 Toner Cartridge. | 592/PFMS | 14/03/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5121 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 No of Canon NPG-67 Toner Black under Nadia Division, PHE Dte. | 30/PFMS | 30/04/2024 | 0 | IONET | 0.07 | 0 | 0 | 0
5122 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 No of Canon NPG-67 Toner Black under Nadia Division, PHE Dte. | 37/PFMS | 30/04/2024 | 0 | IONET | 0.07 | 0 | 0 | 0
5123 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order Of 3 No Formujet 110A Toner Cartidge With Chip , 1 No Formujet TN 2365 Toner Cartidge, | 569/PFMS | 02/03/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5124 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order Of 2 No Formujet 110A Toner Cartidge With Chip, 2 No Formujet DR 2365 Drum Unit, 1 No Logitech K120 Keyboard, | 561/PFMS | 02/03/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5125 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order Of 1 No Formujet Pantum PC208EK Cartidge ,6 No Formujet DR 2365 Drum Unit , | 562/PFMS | 02/03/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5126 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 no ¿VOLT IT SMART PRO EXTENSION BOARD 5 mtr, 1 no of Scuda SSD 256 GB sata¿, under nadia Division P.H.E Dte. | 135/PFMS | 27/07/2024 | 0 | IONET | 0.04 | 0 | 0 | 0
5127 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 No Logitech Wbcam C270 HD , 1 No Formujet Pantum P208EK Cartidge, 1 No Frontech Spike 1.5m 3512. | 591/PFMS | 14/03/2024 | 0 | IONET | 0.05 | 0 | 0 | 0
5128 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 No of Canon NPG-67 Toner Black under Nadia Division, PHE Dte. | 36/PFMS | 30/04/2024 | 0 | IONET | 0.07 | 0 | 0 | 0
5129 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 No of Canon NPG-67 Toner Cyan under Nadia Division, PHE Dte. | 32/PFMS | 30/04/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5130 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 No of Canon NPG-67 Toner Magenta under Nadia Division, PHE Dte. | 38/PFMS | 30/04/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5131 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Supply of Brother Multifunction Machines Mfm, On Site OEM Warranty 3 Years, Order Quantity: 12 Nos. under Nadia Division, PHE Dte. Kalyani, Nadia. Contract No: GEMC-511687729441332, Generated Date: 21-Jun-2024. GeM Invoice No: GEM-45291385, GeM Invoice Date: 12-Jul-2024. Model: MFC-L2701DW, HSN Code: 8443, MC. SL. NO: E73804E3N746424, E73804B4N966312, E73804A4N946204, E73804B4N96631, E73804A4N946244, E73804BN966300, E73804A4N946238, E73804B4N966302, E73804A4N946192, E73804B4N966313, E73804B4N966315, E80718M2H844754. | 143/PFMS | 30/07/2024 | 0 | IONET | 3.24 | 0 | 0 | 0
5132 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 No D-Link Switch 5 Port, 1 No of TP Link WL LAN USB adaptor 300 Mbps wn 823N, 3 Nos of D-Link Patch cord cat 6 UTP 1 Mtr Yellow, 2 Nos of Scuda SSD 256 GB Sata, 2 Nos of Zebronics HUB Usb 100HB, under Nadia Division PHE Dte. | 137/PFMS | 27/07/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5133 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Supply Order Through GeM of Portable I51 Tower Device System, Brand HP, Model: HP Pro Tower 280 G9 PCI i5 Desktop PC , HSN CODE:84715000, Qty: 3; Advance Portable I52 Tower Device System, Brand HP, Model: HP Pro Tower 280 G9 PCI i5 Desktop PC , HSN CODE:84715000, Qty: 3; System Portable I52 Tower Device System, Brand HP, Model: HP Pro Tower 280 G9 PCI i5 Desktop PC , HSN CODE:84715000, Qty: 1; System Portable I52 Tower Device System, Brand HP, Model: HP Pro Tower 280 G9 PCI i5 Desktop PC ,HSN CODE:84715000 Qty: 2; Portable MF Speed M1 System Device, Brand: Brother, Model Brother Printer MFC L2701DW, HSN CODE:84433100 Qty: 1. GeM Invoice No: GEM-42879860,Dt:09/04/2024, Order No: GEMC-511687736666801, Dt: 05/04/2024 | 27/PFMS | 30/04/2024 | 0 | IONET | 8.2 | 0 | 0 | 0
5134 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Acceptance Cum Supply Order of 1 no Microtek MTK ups Legend 650, 1 no of Formujet F 2612A Toner, 2 no of Formujet F HP 110A with chip¿, under nadia Division P.H.E Dte. | 134/PFMS | 27/07/2024 | 0 | IONET | 0.09 | 0 | 0 | 0
5135 | NADIA | Nadia Division | Supply, Delivery and Installation of Computer & peripherals (Phase-II) for the official use under office of the Executive Engineer Nadia Division, under Nadia Division, P.H.E. Dte. , SM/19064 | Support-MIS | Supply of HP Multifunction Machines MFM, On Site OEM WARRANTY 5 YEAR, Brand : HP, Category Name & Quadrant : Multifunction Machine MFM (Q2), Model: HP Laser jet Pro MFP MFP 4104 fdw, HSN Code: 8443 Contact No: GEMC-511687762807386, Generated Date: 29-July-2024, GeM Invoice No: GEM-46182376, GeM Invoice Date: 02-Aug-2024 | 215/PFMS | 05/09/2024 | 0 | IONET | 0.5 | 0 | 0 | 0
5136 | NADIA | Nadia Arsenic Division I | Regular Upkeepment & Upgradation of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance Programme Related to Jal Jeevan Mission. , SM/19279 | Support-WQMSP | Regular Upkeepment of Mobile Laboratory Van (MLV) complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with instruments, devices, consumables, reagents. accessories and safety gear for resource personnel for water quality testing in remote areas including extemal designing and painting for IEC propaganda complete with IEC audio visual aids as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. | 1190/NAD-I | 31/07/2024 | 365 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 36.47 | 0 | 0 | 66
5137 | NADIA | Nadia Division | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues Under Jal Jeevan Mission (JJM) Support Activities , SM/12848 | Support-IEC | Making of Documentary film on "Jal Swapno Project" achievements in Nadia District. | 3299/ND | 27/07/2022 | 30 | SPAN COMMUNICATIONS | 8.5 | 8.5 | 100 | 0
5138 | NADIA | Nadia Division | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues Under Jal Jeevan Mission (JJM) Support Activities , SM/12848 | Support-IEC | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues Under Jal Jeevan Mission (JJM) Support Activities | 3272/ND | 31/07/2023 | 184 | IMAGIN | 54.33 | 54.33 | 100 | 91
5139 | NADIA | Nadia Division | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues Under Jal Jeevan Mission (JJM) Support Activities , SM/12848 | Support-IEC | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues Under Jal Jeevan Mission (JJM) Support Activities. [Phase-II] | 6161/ND | 26/12/2023 | 183 | IMAGIN | 74.48 | 62.57 | 100 | 100
5140 | NADIA | Nadia Arsenic Division I | Procurement of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance Programme related to Jal Jeevan Mission under Nadia Arsenic Division-I, P.H.E. Dte. , SM/12742 | Support-WQMSP | Procurement of 1 no. of Mobile Laboratory Van(MLV) complete with internal fabrication,refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with OMAS instruments, devices, consum ables,reagents, smart phone with preloaded waterquality app synchronized with PHED water quality dashboard and safety gear for resource personnel for water quality testing in remote areas including external designing and painting for IECpropaganda complete with IEC audio visual aids as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. (sl.01) | 206/NAD-I | 15/02/2023 | 365 | SAKTI ENTERPRISE | 75.46 | 60.37 | 80 | 82
5141 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Bill for PHED New service connection at BALIADANGA under Gangnapur CCC. | 100/QUT | 24/08/2021 | 0 | WBSEDCL | 10.37 | 0 | 0 | 0
5142 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Route Survey, Distribution Design and Preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Parniamatpur Water Supply Scheme in Ranaghat-I Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. (Sl No.-08) Tender No.-271/NAD-I/2020-2021. | 65/AE-I/NAD-I | 24/02/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 4.8 | 1.18 | 100 | 0
5143 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Route Survey and Distribution Design for preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Gayeshpur Zone - II Water Supply Scheme in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. (Sl No.-01) Tender No.-272/NAD-I/2020-2021. | 58/AE-I/NAD-I | 24/02/2021 | 30 | UMWELT ENGINEER PVT. LTD. | 2.92 | 1.18 | 100 | 0
5144 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Route Survey for preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Chupria Zone - I Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. (Sl No. -11) Tender No. 279/NAD-I/2020-2021. | 72/AE-II/NAD-I | 24/02/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 4.11 | 0 | 0 | 0
5145 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Distribution Design and Preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Nrisinghapur Water Supply Scheme in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. (Sl No.-07) Tender No. 273/NAD-I/2020-2021. | 64/AE-I/NAD-I | 24/02/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 4.8 | 1.18 | 100 | 0
5146 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Distribution Design and Preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Gobindapur Zone - I Water Supply Scheme in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | 60/AE-I/NAD-I | 24/02/2021 | 30 | UMWELT ENGINEER PVT. LTD. | 3.49 | 3.49 | 100 | 0
5147 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Distribution Design and Preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Gobindapur Zone - II Water Supply Scheme in Santipur Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | 62/AE-I/NAD-I | 24/02/2021 | 30 | UMWELT ENGINEER PVT. LTD. | 3.74 | 2.79 | 100 | 0
5148 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Distribution Design for preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Chupria Zone - I Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | 73 /AE-II/NAD-I | 24/02/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 3.38 | 1.2 | 100 | 0
5149 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Distribution Design and Preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Matikumra Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. (Sl No. 10) Tender No.-282/NAD-I/2020-2021. | 67/AE-I/NAD-I | 24/02/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 4.25 | 1.18 | 100 | 0
5150 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Collection of House Hold Details at Prescribed Format through Mobile App/ Hard Copy including Geo- Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for Nagarukhra-II, G.P. & Mollabelia G.P. under Haringhata Block under Surface Water Based Water Supply Scheme under Haringhata and Chakdah (Part) Block under Nadia Arsenic Division-I, P.H.E. Dte. Against Tender No. 195/NAD-I/2020-2021. | 314/AE-I/NAD-I | 28/12/2020 | 30 | HORIZEN | 4.23 | 8.06 | 200 | 0
5151 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Collection of House Hold Details at Prescribed Format through Mobile App/ Hard Copy including Geo- Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for Berohi-I G.P., Berohi-II G.P. and Nagarukhra-I G.P. under Haringhata Block under Surface Water Based Water Supply Scheme under Haringhata and Chakdah (Part) Block under Office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. Against Tender No.- 194/NAD-I/2020-2021. | 313/AE-I/NAD-I | 28/12/2020 | 30 | TECH VISION | 4.38 | 8.72 | 200 | 0
5152 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Collection of House Hold Details at Prescribed Format through Mobile App/ Hard Copy including Geo- Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for different Ground Water Based Water Supply Schemes such as Birnagar under Ranaghat-I Block, Muragachha Zone-I and Muragachha Zone-II under Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte.(Sl No. 04) Tender No.- 241/NAD-I/2020-2021. | 11/AE-I/NAD-I | 08/01/2021 | 30 | M/S R. DUTTA & CO. | 2.64 | 3.98 | 200 | 0
5153 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Collection of House Hold Details at Prescribed Format through Mobile App/ Hard Copy including Geo- Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for different Ground Water Based Water Supply Schemes such as Boalia under Santipur Block, Bhayna Zone-I and Bhayna Zone-II under Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl No. 03) Tender No.-244/NAD-I/2020-2021. | 10/AE-I/NAD-I | 08/01/2021 | 30 | LEMNISCATE | 3.29 | 5.92 | 200 | 0
5154 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Collection of House Hold Details at Prescribed Format through Mobile App/ Hard Copy including Geo- Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for Haringhata-II G.P. under Haringhata Block and Kanchrapara G.P. under Chakdah Block under Surface Water Based Water Supply Scheme under Haringhata and Chakdah (Part) Block under Nadia Arsenic Division-I, P.H.E. Dte.(Sl No. 06) Tender No. 255/NAD-I/2020-2021. | 318/AE-I/NAD-I | 28/12/2020 | 30 | TECH VISION | 3.7 | 4.29 | 200 | 0
5155 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Collection of House Hold Details at Prescribed Format through Mobile App/ Hard Copy including Geo- Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for different Ground Water Based Water Supply Schemes such as Halalpur-Krishnapur Zone-II under Ranaghat-II Block, Beharia, Goalpur Zone-I, Goalpur Zone-II and Nabla under Santipur Block under Nadia Arsenic Division-I, P.H.E. Dte. | 09/AE-I/NAD-I | 08/01/2021 | 30 | M/S R. DUTTA & CO. | 2.67 | 4.69 | 200 | 0
5156 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Collection of House Hold Details at Prescribed Format through Mobile App/ Hard Copy including Geo- Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for Tatla - I G.P. and Tatla - II G.P under Chakdaha Block under Surface Water Based Water Supply Scheme under Chakdah (Part) Block under Nadia Arsenic Division-I, P.H.E. Dte. | 190/AE-II/NAD-I | 28/12/2020 | 15 | HORIZEN | 3.89 | 7.79 | 200 | 0
5157 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Collection of House Hold Details at Prescribed Format through Mobile App/ Hard Copy including Geo- Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for the Ground Based PWSS for Joypur, Itaberia, Garapota and Gobindapur PWSS under Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. (SL On.-03) Tender No.- 261/NAD-I/2020-2021. | 04/AE-II/NAD-I | 08/01/2021 | 15 | ROY CHOWDHURY ASSOCIATES | 4.01 | 7.11 | 200 | 0
5158 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Collection of House Hold Details at Prescribed Format through Mobile App/ Hard Copy including Geo- Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for the Ground Based PWSS for Dhantala, Sabdalpur and Aranghata Narayanpur Zone - I PWSS under Ranaghat -II Block under Nadia Arsenic Division-I, P.H.E. Dte. Tender No.259/NAD-I/2020-2021.(Sl No.- 06) | 07/AE-II/NAD-I | 08/01/2021 | 15 | ROY CHOWDHURY ASSOCIATES | 4.59 | 8.62 | 200 | 0
5159 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Collection of House Hold Details at Prescribed Format through Mobile App/ Hard Copy including Geo- Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for the Ground Based PWSS for Saguna PWSS under Santipur Block, Paschim Noapara Ukilnara Zone - I, Ukilnara Zone - II PWSS under Ranaghat - I Block and Betna PWSS under Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. Tender No.- 257/NAD-I/2020-2021. (Sl No.-05) | 06/AE-II/NAD-I | 08/01/2021 | 15 | ROY CHOWDHURY ASSOCIATES | 3.65 | 6.15 | 200 | 0
5160 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Collection of House Hold Details at Prescribed Format through Mobile App/ Hard Copy including Geo- Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for the Ground Based PWSS for Duttaphulia Zone - I & Duttaphulia Zone - II under Ranaghat -I I Block under Nadia Arsenic Division-I, P.H.E. Dte. Tender No.- 242/NAD-I/2020-2021. (Sl No. -01) | 02/AE-II/NAD-I | 08/01/2021 | 15 | ROY CHOWDHURY ASSOCIATES | 4.13 | 6.66 | 200 | 0
5161 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Collection of House Hold Details at Prescribed Format through Mobile App/ Hard Copy including Geo- Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for Fatepur G.P.under Haringhata Block, Sarati G.P. under Chakdah Block and Kastodanga-I G.P. under Haringhata Block under Surface Water Based Water Supply Scheme under Haringhata and Chakdah (Part) Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl No. -03) Tender No.- 232/NAD-I/2020-2021. | 315/AE-I/NAD-I | 28/12/2020 | 30 | HORIZEN | 4.71 | 8.11 | 200 | 0
5162 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Collection of House Hold Details at Prescribed Format through Mobile App/ Hard Copy including Geo- Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for Kastodanga-II G.P.under Haringhata Block, Simurali G.P., Madanpur-I G.P. and Madanpur-II G.P. under Chakdah Block under Surface Water Based Water Supply Scheme under Haringhata and Chakdah (Part) Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl No.-04) Tender No. - 231/NAD-I/2020-2021. | 316/AE-I/NAD-I | 28/12/2020 | 30 | TECH VISION | 4.77 | 5.5 | 200 | 0
5163 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Collection of House Hold Details at Prescribed Format through Mobile App/ Hard Copy including Geo- Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for DEWLI G.P. and DUBRA G.P under Chakdaha Block under Surface Water Based Water Supply Scheme under Chakdah (Part) Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl No.- 03) Tender No.-252/NAD-I/2020-2021. | 189/AE-II/NAD-I | 28/12/2020 | 15 | HORIZEN | 4.66 | 8.69 | 200 | 0
5164 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Collection of House Hold Details at Prescribed Format through Mobile App/ Hard Copy including Geo- Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for Silinda- I G.P., Silinda -II G.P. and Hingnara G.P under Chakdaha Block under Surface Water Based Water Supply Scheme under Chakdah (Part) Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl No.- 01) Tender No.- 256/NAD-I/2020-2021. | 186/AE-II/NAD-I | 28/12/2020 | 15 | TECH VISION | 4.31 | 8.49 | 200 | 0
5165 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Collection of House Hold Details at Prescribed Format through Mobile App/ Hard Copy including Geo- Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for different Ground Water Based Water Supply Schemes such as Tarapur, Kalaighata, Radhakantapur and Par Niamatpur under Ranaghat-I Block, Gayeshpur Zone-I and Gayeshpur Zone-II under Santipur Block under Nadia Arsenic Division-I, P.H.E. Dte. Tender No.- 243/NAD-I/2020-2021. (Sl No- 01) | 08/AE-I/NAD-I | 08/01/2021 | 30 | LEMNISCATE | 3.72 | 6.66 | 200 | 0
5166 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Water Supply to Uncovered Habiatations by relaying/extention of pipe line at Rautari, Enayetpur Tetultala under Chakdah surface Zone-X (Simurali) Water Supply Scheme under Nadia Arsenic Division-I,P.H.E Dte. Tender No.- 07/NAD-I/2021-2022. | 103/NAD-I | 14/01/2021 | 30 | M/S DIPAK ENTERPRISE | 7.25 | 12.82 | 200 | 0
5167 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Conducting detailed area survey of Haringhata W.T.P. area under Nadia Arsenic Division - I, P.H.E. Dte. Tender No. 15/NAD-I/2021-2022. | 90/AE-I/NAD-I | 05/05/2021 | 30 | M/S R. DUTTA & CO. | 0.87 | 1.74 | 200 | 0
5168 | NADIA | Nadia Arsenic Division I | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Haringhata, chakdaha, ranaghat I/II Santipur and Hanskhali Blocks , SM/07013 | Support-M&E | Preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna/jhaldhara programme covering Masunda village by retrofitting of Paschim Noapara Water Supply Scheme in Ranaghat-I Block of Nadia District under Office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. Tender No- 284/NAD-I/2020-2021. | 76/AE-II/NAD-I | 24/02/2021 | 30 | LEMNISCATE | 2.18 | 4.2 | 200 | 0
5169 | NADIA | Nadia Division | Field Level Survey of different Schools and AWC by GPs enable Mobile App for uploading this data at IMIS Website in Nadia District. , SM/08971 | Support-M&E | Field Level Survey of different Schools and AWC by GPs enable Mobile App for uploading this data at IMIS Website in Nadia District. | 336/PFMS | 23/11/2021 | 0 | HORIZEN | 12.78 | 0 | 0 | 0
5170 | NADIA | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19079 | Support-WQMSP | Continuation work for 6(Six) months maintenance contract (only service & preventative maintenance along with software support) after expiry of one year performance warranty of the offered system at Haringhata water Treatment Plant Laboratory in Nadia District under The Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. Government of West Bengal. (Period from 1/07/2024 to 31/12/2024) | 203/AE-I/NAD-I | 28/06/2024 | 183 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.1 | 0 | 0 | 100
5171 | NADIA | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19079 | Support-WQMSP | Continuation work for "Operation, Analysis, Application support & Training for Triple Quadrupole GC-MS/MS system by engaging Resource Person/s for Pesticide Residue Analysis of Water at Haringhata Water Treatment Plant Laboratory in Nadia District under The Executive Engineer, Nadia Arsenic Division-I, PHE Dte, Government of West Bengal for a period of six (4) months. (w.e.f. 03/09/2024 to 31/12/2024)" | 241/AE-I/NAD-I | 02/09/2024 | 122 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.25 | 0 | 0 | 0
5172 | NADIA | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19079 | Support-WQMSP | Supply of glassware and consumable at water testing laboratory at Haringhata WTP under Nadia Arsenic Division-I, PHE Dte. | 536/AE-I/NAD-I | 11/12/2023 | 30 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.95 | 0.95 | 100 | 100
5173 | NADIA | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19079 | Support-WQMSP | Supply of Chemical and reagents at water testing laboratory at Haringhata WTP under Nadia Arsenic Division-I, PHE Dte | 538/AE-I/NAD-I | 11/12/2023 | 30 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
5174 | NADIA | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19079 | Support-WQMSP | Continuation work for 6(Six) months maintenance contract (only service & preventative maintenance along with software support) after expiry of one year performance warranty of the offered system at Haringhata water Treatment Plant Laboratory in Nadia District under The Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. Government of West Bengal. (Period from 1/1/2024 to 30/06/2024) | 551/AE-I/NAD-I | 27/12/2023 | 183 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 2.1 | 2.1 | 100 | 100
5175 | NADIA | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19079 | Support-WQMSP | Supply of different chemical and accessories for Haringhata WTP Water Testing Laboratory (Prandhara) under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 03) | 29/AE-I/NAD-I | 19/01/2024 | 15 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.97 | 0.97 | 100 | 100
5176 | NADIA | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19079 | Support-WQMSP | Supply and installation of LED Sign Board along with other allied electrical works at Kalyani State Referral Laboratory under Nadia Arsenic Division-I, PHE Dte | 91/AE-I/NAD-I | 22/02/2024 | 30 | TARUN KUMAR BHATTACHARYA | 4.83 | 4.82 | 100 | 100
5177 | NADIA | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19079 | Support-WQMSP | Supply of Chemical & Certified Reference Materials at Kalyani State Laboratory under Nadua Arsenic Division-I, PHE Dte. | 193/AE-I/NAD-I | 21/06/2024 | 15 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.95 | 0.95 | 100 | 100
5178 | NADIA | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19079 | Support-WQMSP | Renovation of existing laboratory room for installation of ICPMS & IC including sample preparation room and Gas cylinder storage room & UPS room along with allied electrical and sanitary works at Kalyani State Referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | 168/NAD-I | 07/02/2024 | 15 | TARUN KUMAR BHATTACHARYA | 10.43 | 10.17 | 100 | 100
5179 | NADIA | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19079 | Support-WQMSP | Supply of Argan (XL) Cylinder for running ICP-MS & IC at Kalyani State Referral Laboratory under Nadia Arsenic Division-I, PHE Dte. | 191/AE-I/NAD-I | 21/06/2024 | 15 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.98 | 0.98 | 100 | 100
5180 | NADIA | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19079 | Support-WQMSP | Continuation work for "Operation, Analysis, Application support & Training for Triple Quadrupole GC-MS/MS system by engaging Resource Person/s for Pesticide Residue Analysis of Water at Haringhata Water Treatment Plant Laboratory in Nadia District under The Executive Engineer, Nadia Arsenic Division-I, PHE Dte, Government of West Bengal for a period of six (6) months. (w.e.f. 03/03/2024 to 02/09/2024)" | 103/AE-I/NAD-I | 01/03/2024 | 184 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 3.46 | 3.46 | 100 | 100
5181 | NADIA | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19079 | Support-WQMSP | Operation , analysis , Application support, training and maintenance and service of GC- MS/MS System including engagement of resource personnel at Kalyani State Referral Laboratory under Nadia Arsenic Division-I, PHE Dte (WEF- 01/01/2025 to 31/12/2025) | 2270/NAD-I | 06/01/2025 | 365 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 11.38 | 0 | 0 | 0
5182 | NADIA | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19079 | Support-WQMSP | Continuation Work Order for Deployment of Laboratory Personal at the laboratory under Haringhata WTP (Sub-district laboratory for Prandhara) at Kalyani, Nadia. (Period from 01.04.2025 to 30.09.2025) | 54/AE-I/NAD-I | 24/03/2025 | 183 | DULAL MAJUMDER | 3.83 | 0 | 0 | 100
5183 | NADIA | Nadia Arsenic Division I | Operational charges of Kalyani State Referral Laboratory under Nadia Arsenic Division-I , PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19079 | Support-WQMSP | Continuous monitoring and testing of water samples by supply of Chemical References and Consumable Gases (As and When Required) for analysing of water samples by ICPMS & GCMS at Kalyani State Referral Laboratory under Nadia Arsenic Division-I,PHE Dte for period of 1 Year. (Sl. NO. 01) | 1200/NAD-I | 18/11/2025 | 365 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 16.15 | 0 | 0 | 0
5184 | NADIA | Nadia Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. , SM/09024 | Support-WQMSP | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. | 72/PFMS | 05/07/2022 | 0 | OTHERS | 13.8 | 0 | 0 | 0
5185 | NADIA | Nadia Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. , SM/09024 | Support-WQMSP | Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. | 339/Kly SD-I | 18/04/2022 | 3 | RAJAT ENTERPRISE | 1.69 | 1.7 | 100 | 0
5186 | NADIA | Nadia Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. , SM/09024 | Support-WQMSP | Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. | 218/Kly SD-I | 22/02/2023 | 90 | CONSTRUCTURE | 0.95 | 0.95 | 100 | 0
5187 | NADIA | Nadia Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. , SM/09024 | Support-WQMSP | Continuation for Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. | 578/ Kly SD-I | 02/05/2023 | 90 | CONSTRUCTURE | 0.95 | 0.95 | 100 | 0
5188 | NADIA | Nadia Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. , SM/09024 | Support-WQMSP | PLACEMENT OF FUND FOR ASHA INCENTIVE OF WATER SAMPLE TESTING BY FTK AT DIFFERENT BLOCKS IN THE DISTRICT OF NADIA | 492/PFMS | 27/03/2023 | 0 | DISTRICT HEALTH & FAMILY WELFARE SAMITI | 7.7 | 0 | 0 | 0
5189 | NADIA | Nadia Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. , SM/09024 | Support-WQMSP | Continuation work order for Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. for the period from 01.08.2023 to 31.10.2023 | 791/KLYSD-I | 27/07/2023 | 92 | CONSTRUCTURE | 0.95 | 0.9 | 100 | 100
5190 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | Providing service by assigning technical resource team for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Krishnaganj Sub-District Water Testing Laboratory under Nadia Division, PHE Dte. | 215/KLYSD1 | 22/07/2021 | 92 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 4.83 | 0 | 0 | 0
5191 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | SUPPLY OF CHEMICAL , GLASSWARE, AND INSTRUMENT .... NADIA LABORATORY, KALYANI, NADIA | 338/DW | 11/01/2021 | 0 | LAXMI ENTERPRISE | 26.1 | 0 | 0 | 0
5192 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | URGENT SUPPLY SILVER - DIETHYL-DITHIO-CARBONATE AND MTC OF WATER QUALITY ..................TESTING LAB | 148/LAB | 10/09/2021 | 0 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.97 | 0 | 0 | 0
5193 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | SUPPLY OF CHEMICALS AND COSUMABLE FOR OP & MTC OF WATER QUALITY ANALYSIS AT DIFFERENT WATER TESTING LABORATORIES IN NADIA DISTRICT UNDER NADIA DIVISION , PHE , DTE. | 311/DW | 02/11/2021 | 0 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 4.98 | 0 | 0 | 0
5194 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | PROVIDING SERVICE BY TECHNICAL RESOURCE ....... KRISHNAGAR SUB. DIST. LABORATORY | 311/DW | 02/11/2021 | 0 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 3.66 | 0 | 0 | 0
5195 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | PROVIDING SERVICE BY TECHNICAL RESOURCE ....... HABIBPUR SUB. DIST. LABORATORY | 311/DW | 02/11/2021 | 0 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 3.66 | 0 | 0 | 0
5196 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | PROVIDING SERVICE BY TECHNICAL RESOURCE ....... TEHATTA SUB. DIST. LABORATORY | 311/DW | 02/11/2021 | 0 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 3.66 | 0 | 0 | 0
5197 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | URGENT SUPPLY SILVER - DIETHYL-DITHIO-CARBONATE AND MTC OF WATER QUALITY ..................TESTING LAB | 148/LAB | 10/09/2021 | 0 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.96 | 0 | 0 | 0
5198 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | PROCUREMENT OF CONSUMABLE FOR OMAS ( ON SITE MOBILE ANALYSIS SYSTEM ) AS DIRECTED LAY EIC UNDER NADIA DIVISION, PHE, DTE. | 141/LAB | 17/08/2021 | 0 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 4.29 | 0 | 0 | 0
5199 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | ANNUAL SERVISES CONTRACT FOR DOUBLE BEAM .......AT BELPUKUR WTP SITE , NADIA | 203/DW | 22/09/2021 | 0 | TARUN KUMAR BHATTACHARYA | 3.85 | 0 | 0 | 0
5200 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | SUPPLY , INSTALLATION , AND COMMISSIONING OF 15KVA UPS BATTERY ETC IN THE DISTRICT LABORATORY | 414/UPS | 08/03/2021 | 0 | OTHERS | 8.45 | 0 | 0 | 0
5201 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | COMPUTER PURCHASED THROUGH GEMS | 167/GEM | 09/09/2021 | 0 | IONET | 3.82 | 0 | 0 | 0
5202 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | ANNUAL SERVICE CONTRACT FOR DOUBLE BEAM ATOMIC ABSOPTION SPECTROMETER AA53300........SPARS PARTS . | 148/LAB | 10/09/2021 | 0 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 4.56 | 0 | 0 | 0
5203 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | MTC FOR COMPUTERS .... NADIA DIST. LAB. | 168/LAB | 13/09/2021 | 0 | IONET | 0.92 | 0 | 0 | 0
5204 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | INRACSTRUCTURE DEVELOPMENT REGARDING NABL .... NADIA DIVISION, PHE, DTE | 203/DW | 22/09/2021 | 0 | SUMAN CHAKRABORTY | 1.98 | 0 | 0 | 0
5205 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | CONSTRUCTION OF SAMPLE COLLECTION .... TESTING LABORATORY | 203/DW | 22/09/2021 | 0 | B.P. ENTERPRISE | 1 | 0 | 0 | 0
5206 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | WATER SAMPLE COLLECTION FROM STREET STAND POST ... NADIA DISTRICT | 148/LAB | 10/09/2021 | 0 | LOKNATH ENTERPRISE | 4.25 | 0 | 0 | 0
5207 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | PROVIDING SERVICE BY TECHNICAL RESOURCE .......BAGULA SUB. DIST. LABORATORY | 311/DW | 02/11/2021 | 0 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 3.66 | 0 | 0 | 0
5208 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | PROVIDING CONSULTANCY SERVISES INCLUDING SUPPLY WATER TESTING LABORATORY | 203/DW | 22/09/2021 | 0 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 2.31 | 0 | 0 | 0
5209 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | Supply and installation of Sign-Board for NABL Accredited/Recognized drinking Water Testing Laboratories under Nadia Division PHE Dte. | 1021/Kly SD-1 | 10/11/2022 | 15 | MANISHIKA CONSTRUCTION | 0.45 | 0.45 | 100 | 0
5210 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | SUPPLY OF LABORATORY CHEMICAL .........NADIA DIVISION, PHE, DTE | 400/DW | 17/12/2021 | 0 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 3.38 | 0 | 0 | 0
5211 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | Annual Service contract for Double beam Atomic Absorption Spectrometer AAS3300 including supply of necessary spare parts and consumables (As and when required) installed at Nadia District Water Testing Laboratory At Haringhata WTP Site, Nadia, under Nadia Division, PHE Dte.(W.E.F-01.08.2021 to 31.07.2022) | 229/Kly SD-1 | 27/07/2021 | 365 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 4.06 | 0 | 0 | 0
5212 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | Supply of Containers for chemical and bacteriological testing at Different Water Testing Laboratories under Nadia Division, PHE Dte. | 1161/Kly SD-I | 16/12/2022 | 15 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.99 | 0.99 | 100 | 0
5213 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | Supply of Chemicals & Consumables at Different Water Testing Laboratories and Calibration of Instruments & Glassware at Nadia District Water Testing Laboratory under Nadia Division, PHE Dte. | 1020/Kly SD-1 | 10/11/2022 | 15 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.99 | 0.99 | 100 | 0
5214 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | Supply and installation of Fire Extinguisher at Nadia District Water Testing Laboratory and PHE Complex, Bhander under Nadia Division, PHE Dte | 184/Kly SD-I | 13/02/2023 | 15 | MRINAL DASGUPTA | 0.94 | 0.94 | 100 | 0
5215 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | SUPPLY OF SCANDISK PEN DRIVE WITH 256 GB STORAGE CAPACITY AND 1 YEAR WARRANTY. SCUDA SSD SATA 256 GB (SSCS 256 GB SATA SSD) WITH CASING 9 NOS. | 428/PFMS | 22/02/2023 | 0 | EASY DAY ENTERPRISE | 0.24 | 0 | 0 | 0
5216 | NADIA | Nadia Division | Annual Procurement of Chemical, Consumables, Glassware & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of different water testing laboratories under Nadia Division PHE Dte. , SM/06631 | Support-WQMSP | Supply of Microtek Line Interactive UPS LEGEND 650VA UPS of Office of the Executive Engineer, Nadia Division, P.H. Engineering Dte. | 414/PFMS | 08/02/2023 | 0 | IONET | 0.34 | 0 | 0 | 0
5217 | NADIA | Nadia Division | Upgradation and Maintenance of Integrated Water Quality Management Information System (IWQ-MIS) for District Specific Dashboard of Nadia in collaboration with Maintaining of a technology-based Management Information System for Water Quality testing of pot , SM/19256 | Support-MIS | Upgradation and Maintenance of Integrated Water Quality Management Information System (IWQ-MIS) for District Specific Dashboard of Nadia in collaboration with Maintaining of a technology-based Management Information System for Water Quality testing of potable water supplied through Functional Household Tap Connections (FHTCs) by means of pre-assigned multifarious sample collection criteria in WebGIS view and upload the water quality test results for flawless functioning of the system.Period from 01.11.2024 to 31.10.2025 | 6709/ND | 29/10/2024 | 365 | HORIZEN | 75.89 | 44.09 | 58.1 | 30
5218 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Maintenance of Nadia District Laboratory under Kalyani Sub Division-I under Nadia Division PHE Dte. w.e.f 01/09/2021 to 31/08/2022 | 328 / KlY SD-I | 31/08/2021 | 365 | MANISHIKA CONSTRUCTION | 1.57 | 1.57 | 100 | 0
5219 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Engagement of 01 no of lab assistant for operation and maintenance of physic-chemical testing unit and bacteriological testing unit of Nadia Divisional Laboratory at W.T.P, Haringhata under Kalyani Sub-Division-1 PHEngineering Dte in the district of Nadia. WEF: 01/02/2022 to 31/05/2022 (Four Months) | 66/KlySD-I | 25/01/2022 | 120 | M/S S.K. ENTERPRISE | 0.4 | 0.4 | 100 | 0
5220 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Monthly remuneration of one no of Lab attendant and one no sampling assistant through agency at Habibpur SD lab & Nadia District Laboratory under Nadia Division, PHE Dte. WEF 01/01/2022 to 31/05/2022 (Five months) | 648/Kly SD-I | 27/12/2021 | 151 | M/S S.K. ENTERPRISE | 0.94 | 0.88 | 100 | 0
5221 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation of engagement of 01 no of Chemist /Analyst for operation and maintenance of physico-Chemical testing unit of Nadia Divisional Laboratory at W.T.P, Haringhata Under Kalyani SD-1, PHE Dte in the district of Nadia. WEF: 01/06/2022 to 31/08/2022 (Three months) | 452/Kly SD-I | 30/05/2022 | 92 | JOYDEV JANA | 0.5 | 0.17 | 100 | 0
5222 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation of engagement of 01 no of Bacteriologist /Analyst for operation and maintenance of Bacteriological testing unit of Nadia Divisional Laboratory Under Kalyani SD-1, P.H.Engineering Dte WEF: 01/06/2022 to 31/08/2022 | 453/Kly SD-I | 30/05/2022 | 92 | GOUTAM DAM | 0.5 | 0.17 | 100 | 0
5223 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation of Engagement of 01 no of Sampling assistant for operation and maintenance of physic-chemical testing unit and bacteriological testing unit of Nadia Water Testing Laboratory under PHE Dte.. WEF: 01/06/2022 to 31/08/2022 (Three Months) | 454/Kly SD-I | 30/05/2022 | 92 | SUCHITRA GHOSH | 0.23 | 0.08 | 100 | 0
5224 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation of Monthly remuneration of one no of Lab attendant and one no sampling assistant through agency at Habibpur SD lab & Nadia District Laboratory under Nadia Division, PHE Dte. WEF 01/06/2022 to 31/08/2022 (Three months) | 456/Kly SD-I | 30/05/2022 | 92 | M/S S.K. ENTERPRISE | 0.56 | 0.53 | 100 | 0
5225 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment of Ad-hoc Bonus to 06 Nos Laboratory Personnel under Nadia Division PHE dte. for the accounting year 2021-2022. | 882/Kly SD-I | 21/09/2022 | 7 | M/S DIPAK ENTERPRISE | 0.39 | 0.39 | 100 | 0
5226 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Monthly remuneration of one(01) no of lab assistant, one(01) no of Lab attendant and one(01) no sampling assistant through agency at Habibpur SD lab & Nadia District Laboratory under Nadia Division, PHE Dte. W.e.f. 01/09/2022 to 30/11/2022 (Three months). | 790/Kly SD-I | 01/09/2022 | 91 | M/S S.K. ENTERPRISE | 0.92 | 0.88 | 100 | 0
5227 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation of Monthly remuneration of one(01) no of lab assistant, one(01) no of Lab attendant and one(01) no sampling assistant through agency at Habibpur SD lab & Nadia District Laboratory under Nadia Division, PHE Dte. W.e.f. 01/12/2022 to 28/02/2023 (Three months). | 1077/Kly SD-1 | 30/11/2022 | 120 | M/S S.K. ENTERPRISE | 0.92 | 0.88 | 100 | 0
5228 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Operation & Mtc of NGO Managed Water Testing Lab (Binay Badal Club 2nd Installment). | 102/PFMS | 03/08/2022 | 0 | BINAY BADAL DINESH CLUB | 0.35 | 0 | 0 | 0
5229 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL OF HARANAGRA SKUS LTD. | 136/PFMS | 05/09/2022 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5230 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ATTENDED NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED NGO MANAGED LABORATORY FOR THE MONTH OF SEPTEMBER-2022. | 292/PFMS | 17/11/2022 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5231 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Monthly Remuneration of 01 No. Chemist, 01 No. Bacteriologist and 01 No. Lab Assistant of WBCADC Ranaghat -II Project NGO Managed Laboratory for the Month of August'2022. | 266/PFMS | 20/10/2022 | 0 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
5232 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Monthly Remuneration of 01 No. Chemist, 01 No. Bacteriologist and 01 No. Lab Assistant of Haranagar Samabay Krishi Unnayan Samity LTD NGO Managed Laboratory for the Month of August'2022. | 267/PFMS | 20/10/2022 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5233 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Monthly Remuneration of 01 No. Chemist, 01 No. Bacteriologist and 01 No. Lab Assistant of Binoy Badal Dinesh Club NGO Managed Laboratory for the Month of August'2022. | 270/PFMS | 20/10/2022 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5234 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL FOR 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR THE MONTH OF OCTOBER'2022 |  | 10/11/2022 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5235 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL OF NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY. | 170/PFMS | 22/09/2022 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5236 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL OF HARANAGRA SKUS LTD. | 169/PFMS | 22/09/2022 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5237 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for Haranagar SKUS Ltd Project for the Month of June'2022 | 94/PFMS | 03/08/2022 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5238 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB BARA ANDULIA MAHILA SAMITY. | 138/PFMS | 05/09/2022 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5239 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | AD-HOC BONUS BILL FOR NGO LAB PERSONNEL (01 NO. CHEMIST, 01 NO. BACTERIOLOGIST AND 01 NOS LAB ATTENDANT) FOR THE YEAR 2021-2022. | 242/PFMS | 18/10/2022 | 0 | BINAY BADAL DINESH CLUB | 0.14 | 0 | 0 | 0
5240 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | OPERATION AND MAINTENANCE OF NGO MANAGED WATER TESTING LABORATORIES [ BARA ANDULIA MAHILA SAMITY] AT NADIA DISTRICT. |  | 10/11/2022 | 0 | BARA ANDULIA MAHILA SAMITY | 0.4 | 0 | 0 | 0
5241 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | OPERATION AND MAINTENANCE OF NGO MANAGED WATER TESTING LABORATORIES [HARANAGAR SKUS LTD] AT NADIA DISTRICT. | 302/PFMS | 17/11/2022 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.35 | 0 | 0 | 0
5242 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB BARA ANDULIA MAHILA SAMITY. | 171/PFMS | 22/09/2022 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5243 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for WBCADC Ranaghat-II Project for the Month of June'2022 | 92/PFMS | 03/08/2022 | 0 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
5244 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL OF NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY. | 137/PFMS | 05/09/2022 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5245 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | AD-HOC BONUS BILL FOR NGO LAB PERSONNEL (01 NO. CHEMIST, 01 NO. BACTERIOLOGIST AND 01 NOS LAB ATTENDANT) FOR THE YEAR 2021-2022. | 238/PFMS | 18/10/2022 | 0 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.14 | 0 | 0 | 0
5246 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL FOR 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR THE MONTH OF OCTOBER'2022 |  | 10/11/2022 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5247 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | AD-HOC BONUS BILL FOR NGO LAB PERSONNEL (01 NO. CHEMIST, 01 NO. BACTERIOLOGIST AND 01 NOS LAB ATTENDANT) FOR THE YEAR 2021-2022. | 239/PFMS | 18/10/2022 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.14 | 0 | 0 | 0
5248 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL FOR 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR THE MONTH OF OCTOBER'2022 |  | 10/11/2022 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5249 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL OF WBCADC RANAGHAT-II PROJECT. | 168/PFMS | 22/09/2022 | 0 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
5250 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for Binoy Badal Dinesh Club for the Month of June'2022 | 95/PFMS | 03/08/2022 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5251 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for Bara Andulia Mohila Samity for the Month of June'2022 | 93/PFMS | 03/08/2022 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5252 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for WBCADC Ranaghat-II Project for the Month of May'2022. | 101/PFMS | 03/08/2022 | 0 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
5253 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ATTENDED WBCADC RANAGHAT-II PROJECT NGO MANAGED LABORATORY FOR THE MONTH OF SEPTEMBER-2022. |  | 18/10/2022 | 0 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
5254 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL OF WBCADC RANAGHAT-II PROJECT. | 290/PFMS | 17/11/2022 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.33 | 0 | 0 | 0
5255 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Monthly Remuneration of 01 No. Chemist, 01 No. Bacteriologist and 01 No. Lab Assistant of Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO Managed Laboratory for the Month of August'2022. | 268/PFMS | 20/10/2022 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5256 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Monthly Remuneration of 01 No. Chemist, 01 No. Bacteriologist and 01 No. Lab Assistant of Bara Andulia Mahila Samity NGO Managed Laboratory for the Month of August'2022. | 269/PFMS | 20/10/2022 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5257 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | AD-HOC BONUS BILL FOR NGO LAB PERSONNEL (01 NO. CHEMIST, 01 NO. BACTERIOLOGIST AND 01 NOS LAB ATTENDANT) FOR THE YEAR 2021-2022. | 240/PFMS | 18/10/2022 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.14 | 0 | 0 | 0
5258 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | AD-HOC BONUS BILL FOR NGO LAB PERSONNEL (01 NO. CHEMIST, 01 NO. BACTERIOLOGIST AND 01 NOS LAB ATTENDANT) FOR THE YEAR 2021-2022. | 241/PFMS | 18/10/2022 | 0 | BARA ANDULIA MAHILA SAMITY | 0.14 | 0 | 0 | 0
5259 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL FOR 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR THE MONTH OF OCTOBER'2022. |  | 10/11/2022 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5260 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL FOR 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR THE MONTH OF OCTOBER'2022 | 295/PFMS | 17/11/2022 | 0 | BARA ANDULIA MAHILA SAMITY | 0.4 | 0 | 0 | 0
5261 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for Bara Andulia Mohila Samity for the Month of May'2022. | 97/PFMS | 03/08/2022 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5262 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ATTENDED BARA ANDULIA MAHILA SAMITY NGO MANAGED LABORATORY FOR THE MONTH OF SEPTEMBER-2022. | 293/PFMS | 17/11/2022 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5263 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for Binoy Badal Dinesh Club for the Month of June'2022 | 96/PFMS | 03/08/2022 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5264 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED for the Month of May'2022 | 99/PFMS | 03/08/2022 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5265 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for BINAY BADAL DINESH CLUB for the Month of May'2022 | 100/PFMS | 03/08/2022 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5266 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ATTENDED HARANAGAR SKUS NGO MANAGED LABORATORY FOR THE MONTH OF SEPTEMBER-2022. | 291/PFMS | 17/11/2022 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5267 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ATTENDED BINOY BADAL DINESH CLUB NGO MANAGED LABORATORY FOR THE MONTH OF SEPTEMBER-2022. | 294/PFMS | 17/11/2022 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5268 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL FOR BINOY BADAL DINESH CLUB. | 172/PFMS | 22/09/2022 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5269 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for Haranagar SKUS LTD for the Month of May'2022. | 98/PFMS | 03/08/2022 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5270 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Operation & Mtc fo NGO Managed Lab for Haranagar SKUS Ltd. (1st Installment). | 103/PFMS | 03/08/2022 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.4 | 0 | 0 | 0
5271 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL FOR BINOY BADAL DINESH CLUB. | 139/PFMS | 05/09/2022 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5272 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL OF WBCADC RANAGHAT-II PROJECT. | 135/PFMS | 05/09/2022 | 0 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
5273 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL FOR 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR THE MONTH OF OCTOBER'2022 |  | 10/11/2022 | 0 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
5274 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Engagement of 01 no of Chemist /Analyst for operation and maintenance of physicoChemical testing unit of Nadia Divisional Laboratory at W.T.P, Haringhata Under Kalyani SD-1, PHE Dte in the district of Nadia. WEF: 01/09/2022 to 28/02/2023 (Six months) | 787/Kly SD-I | 01/09/2022 | 181 | JOYDEV JANA | 0.99 | 0.99 | 100 | 0
5275 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Engagement of 01 no of Sampling assistant for operation and maintenance of physic-chemical testing unit and bacteriological testing unit of Nadia Water Testing Laboratory under PHE Dte. WEF: 01/09/2022 to 28/02/2023 (Six months) | 788/Kly SD-I | 01/09/2022 | 181 | SUCHITRA GHOSH | 0.46 | 0.46 | 100 | 0
5276 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Engagement of 01 no of Bacteriologist /Analyst for operation and maintenance of Bacteriological testing unit of Nadia Divisional Laboratory Under Kalyani SD-1, P.H.Engineering Dte WEF: 01/09/2022 to 28/02/2023 (Six months) | 789/Kly SD-I | 01/09/2022 | 181 | GOUTAM DAM | 0.99 | 0.99 | 100 | 0
5277 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation for Payment of remuneration for engagement of 10 nos. personnel (One Chemist / Bacteriologist and one Lab Assistant) at 5 Nos. Sub-District Laboratories under Nadia Division, P.H.E. Dte. on contractual basis w.e.f. 01.01.2023 to 28.02.2023 (Two Month). | 5454/ND | 29/12/2022 | 61 | CLIFFORD FACILITY SERVICES PVT. LTD | 2.73 | 2.73 | 100 | 0
5278 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation for Engagement of 01 no of Chemist /Analyst for operation and maintenance of physico-Chemical testing unit of Nadia Divisional Laboratory at W.T.P, Haringhata Under Kalyani SD-1, PHE Dte in the district of Nadia. WEF: 01/03/2023 to 31/05/2023 (Three months) | 273/Kly SD-I | 28/02/2023 | 92 | JOYDEV JANA | 0.5 | 0.5 | 100 | 0
5279 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation for Engagement of 01 no of Bacteriologist /Analyst for operation and maintenance of Bacteriological testing unit of Nadia Divisional Laboratory Under Kalyani SD-1, P.H.Engineering Dte WEF: 01/03/2023 to 31/05/2023 (Three months) | 274/Kly SD-I | 28/02/2023 | 92 | GOUTAM DAM | 0.5 | 0.5 | 100 | 0
5280 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation for Engagement of 01 no of Sampling assistant for operation and maintenance of physic-chemical testing unit and bacteriological testing unit of Nadia Water Testing Laboratory under PHE Dte. WEF: 01/03/2023 to 31/05/2023 (Three months) | 275/Kly SD-I | 28/02/2023 | 92 | SUCHITRA GHOSH | 0.23 | 0.23 | 100 | 0
5281 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation of Monthly remuneration of one(01) no of lab assistant, one(01) no of Lab attendant and one(01) no sampling assistant through agency at Habibpur SD lab & Nadia District Laboratory under Nadia Division, PHE Dte. W.e.f. 01/03/2023 to 31/05/2023 (Three months) | 276/ Kly SD-I | 28/02/2023 | 92 | M/S S.K. ENTERPRISE | 0.92 | 0.92 | 100 | 0
5282 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation for Engagement of 01 no of Chemist cum Operator of Atomic Absorption Spectrophotometer (AAS) at Nadia District Water Testing Laboratory under Nadia Division, P.H.E Dte WEF: 01/04/2023 to 30/06/2023 (Three months). | 461/ Kly SD-1 | 31/03/2023 | 91 | M/S S.K. ENTERPRISE | 0.8 | 0.8 | 100 | 0
5283 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation for Engagement of 01 no of Chemist cum Operator of Atomic Absorption Spectrophotometer (AAS) at Nadia District Water Testing Laboratory under Nadia Division, P.H.E Dte WEF: 01/07/2023 to 30/09/2023 (Three months). | 734/KLYSD-I | 27/06/2023 | 92 | M/S S.K. ENTERPRISE | 0.8 | 0 | 0 | 0
5284 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation of Maintenance of Nadia District Water Testing Laboratory under Kalyani Sub Division-I under Nadia Division, PHE Dte. W.E.F- 01/09/2022 to 28/02/2023 | 765/Kly SD-I | 29/08/2022 | 181 | MANISHIKA CONSTRUCTION | 0.79 | 1.31 | 100 | 0
5285 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation for Payment of remuneration for engagement of 10 nos. personnel (One Chemist / Bacteriologist and one Lab Assistant) at 5 Nos. Sub-District Laboratories under Nadia Division, P.H.E. Dte. on contractual basis w.e.f. 01.03.2023 to 30.04.2023 (Two Month). | 854/ND | 28/02/2023 | 61 | CLIFFORD FACILITY SERVICES PVT. LTD | 2.73 | 2.68 | 100 | 0
5286 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation work order for Engagement of 01 no of Sampling assistant for operation and maintenance of physic-chemical testing unit and bacteriological testing unit of Nadia Water Testing Laboratory under PHE Dte. WEF: 01/06/2023 to 31/08/2023 (Three months) | 658/KLYSD-I | 24/05/2023 | 92 | SUCHITRA GHOSH | 0.23 | 0.15 | 100 | 70
5287 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation work order for Engagement of 01 no of Chemist /Analyst for operation and maintenance of physico-Chemical testing unit of Nadia Divisional Laboratory at W.T.P, Haringhata Under Kalyani SD-1, PHE Dte in the district of Nadia. WEF: 01/06/2023 to 31/08/2023 (Three months) | 656/KLYSD-I | 24/05/2023 | 92 | JOYDEV JANA | 0.5 | 0.33 | 100 | 70
5288 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation for Payment of remuneration for engagement of 10 nos. personnel (One Chemist / Bacteriologist and one Lab Assistant) at 5 Nos. Sub-District Laboratories under Nadia Division, P.H.E. Dte. on contractual basis w.e.f. 01.05.2023 to 30.06.2023 (Two Month). | 1939/ND | 28/04/2023 | 61 | CLIFFORD FACILITY SERVICES PVT. LTD | 2.73 | 1.36 | 100 | 50
5289 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation of Monthly remuneration of one(01) no of lab assistant, one(01) no of Lab attendant and one(01) no sampling assistant through agency at Habibpur SD lab & Nadia District Laboratory under Nadia Division, PHE Dte. W.e.f. 01/06/2023 to 31/08/2023 (Three months) | 670/KLYSD-I | 29/05/2023 | 92 | M/S S.K. ENTERPRISE | 0.92 | 0.92 | 100 | 100
5290 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Continuation work order for Engagement of 01 no of Bacteriologist /Analyst for operation and maintenance of Bacteriological testing unit of Nadia Divisional Laboratory Under Kalyani SD-1, P.H.Engineering Dte WEF: 01/06/2023 to 31/08/2023 (Three months) | 657/KlySD-I | 24/05/2023 | 92 | GOUTAM DAM | 0.5 | 0.33 | 100 | 70
5291 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment of remuneration for engagement of 10 nos. personnel (One Chemist / Bacteriologist and one Lab Assistant) at 5 Nos. Sub-District Laboratories under Nadia Division, P.H.E. Dte. on contractual basis w.e.f. 01.01.2022 to 31.12.2022 (One Year). | 7541/ND | 30/12/2021 | 365 | CLIFFORD FACILITY SERVICES PVT. LTD | 16.94 | 16.67 | 100 | 100
5292 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED) under Nadia Divn. PHE Dte. for the month of Jan'2023. | 447/PFMS | 06/03/2023 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5293 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( Haranagar S.K.U.S LTD) under Nadia Divn. PHE Dte. for the month of Feb'2023. | 513/PFMS | 28/03/2023 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5294 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR HARANAGAR SKUS NGO LAB FORTHE MONTH OF APRIL-23. | 43/PFMS | 02/06/2023 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5295 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR WBCADC RANAGHAT-II PROJECT NGO LAB FOR THE MONTH OF APRIL-23. | 42/PFMS | 02/06/2023 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.33 | 0 | 0 | 0
5296 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR HARANAGAR SKUS NGO LAB FOR THE MONTH OF JULY-23. | 223/PFMS | 11/08/2023 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5297 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA WBCADC RANAGHAT-II NGO LAB FOR THE MONTH OF JULY-23. | 222/PFMS | 11/08/2023 | 0 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
5298 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED NGO LAB FOR THE MONTH OF AUGUST-23. | 263/PFMS | 13/09/2023 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5299 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( Secretary Bara Andulia Mahila Samity) under Nadia Divn. PHE Dte. for the month of Jan'2023. | 448/PFMS | 06/03/2023 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5300 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Monthly remuneration of NGO Lab personnel for the Month of Feb'2023 for BARA ANDULIA MAHILA SAMITY. |  | 25/03/2023 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5301 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Monthly remuneration of NGO Lab personnel for the Month of Feb'2023 for W.B.C.A.D.C. RANAGHAT-II |  | 25/03/2023 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.33 | 0 | 0 | 0
5302 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Monthly remuneration of NGO Lab personnel for the Month of Feb'2023 for BINAY BADAL DINESH CLUB |  | 25/03/2023 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5303 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( BINAY BADAL DINESH CLUB) under Nadia Divn. PHE Dte. for the month of Feb'2023. | 516/PFMS | 28/03/2023 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5304 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | BILL FOR LABORATORY ANNUAL MAINTENANCE CHARGE 2ND INSTALLMENT FOR FY 2021-2022 FOR BARA ANDULIA MAHILA SAMITY NGO LAB. | 125/PFMS | 26/06/2023 | 0 | BARA ANDULIA MAHILA SAMITY | 0.35 | 0 | 0 | 0
5305 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR HARANAGAR SKUS LTD NGO LAB FOR THE MONTH OF JUNE-23. | 190/PFMS | 20/07/2023 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5306 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment of honorarium for Nadia Zill M0hila Samabay Rindan Samity Limited NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of November¿ 2022. | 331/PFMS | 23/12/2022 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5307 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment of honorarium for Binoy Bdal Dinesh Club NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of December¿ 2022. | 393/PFMS | 30/01/2023 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5308 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( Officer in charge WBCADC Ranaghat -II project) under Nadia Divn. PHE Dte. for the month of Jan'2023. | 445/PFMS | 06/03/2023 | 0 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
5309 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment of honorarium for WBCADC Ranaghat-II Project NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of December¿ 2022. | 389/PFMS | 30/01/2023 | 0 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
5310 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( NADIA ZILLA GANATANTRIK) under Nadia Divn. PHE Dte. for the month of Jan'2023. | 514/PFMS | 28/03/2023 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5311 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BARA ANDULIA MOHILA SAMITY NGO LAB FOR THE MONTH OF MAY-23. | 101/PFMS | 13/06/2023 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5312 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BARA ANDULIA MOHILA SAMITY NGO LAB FOR THE MONTH OF APRIL-23. | 45/PFMS | 02/06/2023 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5313 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | OPERATION AND MAINTENANCE OF NGO MANAGED WATER TESTING LABORATORY AT NADIA DISTRICT. |  | 18/08/2023 | 0 | BINAY BADAL DINESH CLUB | 0.4 | 0 | 0 | 0
5314 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA ZILLA GANATANTRIC MOHILA SAMABAR RINDAN SAMITY LIMITED NGO LAB FOR THE MONTH OF JULY-23. | 224/PFMS | 11/08/2023 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5315 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment of honorarium for Binoy Badal Dinesh Club NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of November¿ 2022. | 333/PFMS | 23/12/2022 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5316 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment of honorarium for Bara Andulia Mahila Samity, NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of November¿ 2022. | 332/PFMS | 23/12/2022 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5317 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( Haranagar S.K.U.S LTD) under Nadia Divn. PHE Dte. for the month of Jan'2023. | 446/PFMS | 06/03/2023 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5318 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO. CHEMIST, 01 NO. BACTERIOLOGIST, 01 NO. LAB ASSISTANT FOR HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD NGO LABORATORY FOR THE MONTH OF MARCH'2023. | 27/PFMS | 12/05/2023 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5319 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO. CHEMIST, 01 NO. BACTERIOLOGIST, 01 NO. LAB ASSISTANT FOR BARA ANDULIA MAHILA SAMITY NGO LABORATORY FOR THE MONTH OF MARCH'2023. | 29/PFMS | 12/05/2023 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5320 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BINAY BADA DINESH CLUB NGO LAB FOR THE MONTH OF MAY-23. | 102/PFMS | 13/06/2023 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5321 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA ZILLA GANATANTRIC MOHILA SAMITY NGO LAB FOR THE MONTH OF JUNE-23. | 191/PFMS | 20/07/2023 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5322 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR WBCADC RANAGHAT-II PROJECT NGO LAB FOR THE MONTH OF JUNE-23. | 189/PFMS | 20/07/2023 | 0 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
5323 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment of honorarium for WBCADC Ranaghat-II Project NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of November¿ 2022. | 329/PFMS | 23/12/2022 | 0 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
5324 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment of honorarium for Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of December¿ 2022. | 391/PFMS | 30/01/2023 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5325 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( B.B.D CLUB) under Nadia Divn. PHE Dte. for the month of Feb'23. | 512/PFMS | 28/03/2023 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.33 | 0 | 0 | 0
5326 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Monthly remuneration of NGO Lab personnel for the Month of Feb'2023 for Haranagar SKUS. |  | 25/03/2023 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5327 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO. CHEMIST, 01 NO. BACTERIOLOGIST, 01 NO. LAB ASSISTANT FOR W.B.C.A.D.C. RANAGHAT-II PROJECT NGO LABORATORY FOR THE MONTH OF MARCH'2023. | 26/PFMS | 12/05/2023 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.33 | 0 | 0 | 0
5328 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR WBCADC RANAGHAT-II NGO LAB FORTHE MONTH OF MAY-23. | 98/PFMS | 13/06/2023 | 0 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
5329 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | OPERATION AND MAINTENANCE CHARGE OF HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD NGO LABORATORY ( FIRST INSTALLMENT FOR THE YEAR 2022-2023). | 25/PFMS | 12/05/2023 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.4 | 0 | 0 | 0
5330 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BINAY BADAL DINESH CLUB NGO LAB FOR THE MONTH OF APRIL-23. | 46/PFMS | 02/06/2023 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5331 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BINAY BADAL DINESH CLUB NGO LAB FOR THE MONTH OF JUNE-23. | 193/PFMS | 20/07/2023 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5332 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA BINAY BADAL DINESH CLUB NGO LAB FOR THE MONTH OF JULY-23. | 226/PFMS | 11/08/2023 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5333 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( B.B.D CLUB) under Nadia Divn. PHE Dte. for the month of Jan'23. | 449/PFMS | 06/03/2023 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5334 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR HARANAGAR SKUS NGO LAB FOR THE MONTH OF MAY-23. | 99/PFMS | 13/06/2023 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5335 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BINAY BADAL CLUB NGO LAB FOR THE MONTH OF AUGUST-23. | 264/PFMS | 13/09/2023 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5336 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment of honorarium for Haranagar Samabay Krishi Unnayan Samity Ltd NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of November¿ 2022. | 330/PFMS | 23/12/2022 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5337 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment of honorarium for Haranagar Samabay Krishi Unnayan Samity Ltd NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of December- 2022. | 390/PFMS | 30/01/2023 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5338 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment of honorarium for Bara Andulia Mahila Samity NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of November¿ 2022. | 392/PFMS | 30/01/2023 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5339 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( BARA ANDULIA MAHILA SAMITY) under Nadia Divn. PHE Dte. for the month of Jan'2023. | 515/PFMS | 28/03/2023 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5340 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BARA ANDULIA MOHILA SAMITY NGO LAB FOR THE MONTH OF JULY-23. | 226/PFMS | 11/08/2023 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5341 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR WBCADC RANAGHAT-II PROJECT NGO LAB FOR THE MONTH OF AUGUST-23. | 261/PFMS | 13/09/2023 | 0 | W.B.C.A.D.C. RANAGHAT-II | 0.33 | 0 | 0 | 0
5342 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BARA ANDULIA MAHILA SAMITY NGO LAB FOR THE MONTH OF AUGUST-23. | 264/PFMS | 13/09/2023 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5343 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR HARANAGAR NGO LAB FOR THE MONTH OF AUGUST-23. | 262/PFMS | 13/09/2023 | 0 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
5344 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | Monthly remuneration of NGO Lab personnel for the Month of Feb'2023 for NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED |  | 25/03/2023 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5345 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO. CHEMIST, 01 NO. BACTERIOLOGIST, 01 NO. LAB ASSISTANT FOR NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED NGO LABORATORY FOR THE MONTH OF MARCH'2023. | 28/PFMS | 12/05/2023 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5346 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO. CHEMIST, 01 NO. BACTERIOLOGIST, 01 NO. LAB ASSISTANT FOR BINAY BADAL DINESH CLUB NGO LABORATORY FOR THE MONTH OF MARCH'2023. | 30/PFMS | 12/05/2023 | 0 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
5347 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA ZILLA GANATANTRICT MOHILA SAMITY NGO LAB FOR THE MONTH OF MAY-23. | 100/PFMS | 13/06/2023 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5348 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BARA ANDULIA MOHILA SAMITY NGO LAB FOR THE MONTH OF JUNE-23. | 192/PFMS | 20/07/2023 | 0 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
5349 | NADIA | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. , SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA ZILLA GANATANTRIC MOHILA SAMITY NGO LAB FOR THE MONTH OF APRIL-23. | 44/PFMS | 02/06/2023 | 0 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
5350 | NADIA | Nadia Division | Upgradation and Maintenance of Integrated WQMIS for District Specific Dashboard of Nadia in collaboration with Designing & Development of a technology-based Management Information System for WQ testing of potable water supplied through FHTCs by means of p , SM/11400 | Support-MIS | Upgradation and Maintenance of Integrated Water Quality Management Information System (IWQ-MIS) for District Specific Dashboard of Nadia in collaboration with Designing & Development of a technology-based Management Information System for Water Quality testing of potable water supplied through Functional Household Tap Connections (FHTCs) by means of pre-assigned multifarious sample collection criteria in WebGIS view and upload the water quality test results along with upgradation, modification, maintenance & Technical skill enhancement of the end-user for flawless functioning of the system. (Period from 01.10.2022 to 30.09.2023) | 4260/ND | 29/09/2022 | 365 | HORIZEN | 74.02 | 68.23 | 100 | 93
5351 | NADIA | Nadia Division | Upgradation and Maintenance of Integrated WQMIS for District Specific Dashboard of Nadia in collaboration with Designing & Development of a technology-based Management Information System for WQ testing of potable water supplied through FHTCs by means of p , SM/11400 | Support-MIS | Continuation Work order for Upgradation and Maintenance of Integrated Water Quality Management Information System (IWQ-MIS) for District Specific Dashboard of Nadia in collaboration with Designing & Development of a technology-based Management Information System for Water Quality testing of potable water supplied through Functional Household Tap Connections (FHTCs) by means of pre-assigned multifarious sample collection criteria in WebGIS view and upload the water quality test results along with upgradation, modification, maintenance & Technical skill enhancement of the end-user for flawless functioning of the system. (Period from 01.10.2023 to 31.10.2023) | 4438/ND | 29/09/2023 | 31 | HORIZEN | 5.37 | 5.37 | 100 | 100
5352 | NADIA | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission , SM/18273 | Support-WQMSP | Fund Requisition for ASHA incentive for Water Sample testing by FTK Phase-II Jan-23 to April-23. | 165/PFMS | 11/07/2023 | 0 | DISTRICT HEALTH & FAMILY WELFARE SAMITI | 37.28 | 0 | 0 | 0
5353 | NADIA | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission , SM/18273 | Support-WQMSP | Fund Requisition for ASHA Incentive for Water Sample Testing by FTK Phase-II for the period from 01/05/2023 to 30/09/2023. | 383/PFMS | 04/11/2023 | 0 | DISTRICT HEALTH & FAMILY WELFARE SAMITI | 31.9 | 0 | 0 | 0
5354 | NADIA | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission , SM/18273 | Support-WQMSP | Continuation work order for Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. for the period from 01.08.2023 to 31.10.2023 | 791/KLYSD-I | 27/07/2023 | 92 | CONSTRUCTURE | 0.95 | 0.05 | 100 | 100
5355 | NADIA | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission , SM/18273 | Support-WQMSP | Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. W.e.f. 01-11-2023 to 31-01-2024 | 1207/KLYSD-I | 17/11/2023 | 92 | CONSTRUCTURE | 4.76 | 4.76 | 100 | 100
5356 | NADIA | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission , SM/18273 | Support-WQMSP | Continuation of Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. W.e.f. 01-08-2024 to 31-10-2024 | 1159/KlySD-I | 31/07/2024 | 92 | CONSTRUCTURE | 4.76 | 1.92 | 100 | 48
5357 | NADIA | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission , SM/18273 | Support-WQMSP | Continuation of Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. W.e.f. 01-02-2024 to 30-04-2024 | 77/KLYSD-I | 22/01/2024 | 91 | CONSTRUCTURE | 4.76 | 3.26 | 100 | 60
5358 | NADIA | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission , SM/18273 | Support-WQMSP | Continuation of Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. W.e.f. 01-05-2024 to 31-07-2024 | 788/KlySD-I | 30/04/2024 | 92 | CONSTRUCTURE | 4.76 | 3.07 | 100 | 100
5359 | NADIA | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission , SM/18273 | Support-WQMSP | Fund requirement for ASHA incentive for Water Sample testing by FTK Phase-II ( Oct-23 to Nov-23) | 117/PFMS | 17/07/2024 | 0 | DISTRICT HEALTH & FAMILY WELFARE SAMITI | 3.25 | 0 | 0 | 0
5360 | NADIA | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission , SM/18273 | Support-WQMSP | Bill for Requisition of ASHA incentive for Water Sample Testing by FTK Phase-III( January 2024 to August 2024 ), Name of the Account - District Health & Family Welfare Samity, Nadia Bank & Branch Name - PNB, Krishnagar Account Number - 0215010438529 IFSC Code - PUNB0021520 | 324/PFMS | 05/10/2024 | 0 | DISTRICT HEALTH & FAMILY WELFARE SAMITI | 22.57 | 0 | 0 | 0
5361 | NADIA | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission , SM/18273 | Support-WQMSP | Continuation of Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. W.e.f. 01-08-2025 to 31-10-2025. | 1522/KlySD-I | 01/08/2025 | 92 | CONSTRUCTURE | 4.76 | 0 | 0 | 0
5362 | NADIA | Nadia Division | Collection of household details as prescribed format through mobile app/hard copy including Geo-reference at different Ground Water Based Piped W/S Scheme under Krishnagar Sub-Division and Tehatta Sub-Division , SM/07011 | Support-M&E | COLLECTION OF HOUSE HOLD DETAILS THROUGH MOBILE APP/ HARD COPY ....AT DIFFERENT WATER BASED W/S SCHEME UNDER KSD, KRISHNAGAR-1, CHAPRA, NABADWIP, KRISHNAGANJ | 201/DW | 22/09/2021 | 0 | RADIANT | 34.29 | 0 | 0 | 0
5363 | NADIA | Nadia Division | Collection of household details as prescribed format through mobile app/hard copy including Geo-reference at different Ground Water Based Piped W/S Scheme under Krishnagar Sub-Division and Tehatta Sub-Division , SM/07011 | Support-M&E | COLLECTION FOR HOUSE DETAINS AT DIFFERENT GROUND WATER SURFACED W/S UNDER KSD, PHE , DTE | 401/FHTC | 10/03/2021 | 0 | RADIANT | 6.03 | 0 | 0 | 0
5364 | NADIA | Nadia Division | Collection of household details as prescribed format through mobile app/hard copy including Geo-reference at different Ground Water Based Piped W/S Scheme under Krishnagar Sub-Division and Tehatta Sub-Division , SM/07011 | Support-M&E | PROVIDING FHTC AT SURFACE BASED W/S SCHEME (PART-1, ZONE-5) KALIGANJ BLOCK | 401/FHTC | 10/03/2021 | 0 | TECHVISION | 1.96 | 0 | 0 | 0
5365 | NADIA | Nadia Division | Collection of household details as prescribed format through mobile app/hard copy including Geo-reference at different Ground Water Based Piped W/S Scheme under Krishnagar Sub-Division and Tehatta Sub-Division , SM/07011 | Support-M&E | PREPARATION OF DETAIL PROJECT REPORT FOR PROVIDING FHTC | 203/DW | 22/09/2021 | 0 | M/S R. DUTTA & CO. | 0.55 | 0 | 0 | 0
5366 | NADIA | Nadia Division | Collection of household details as prescribed format through mobile app/hard copy including Geo-reference at different Ground Water Based Piped W/S Scheme under Krishnagar Sub-Division and Tehatta Sub-Division , SM/07011 | Support-M&E | PROVIDING HOUSE CONNECTION INCLUDING SUPPLY OF 15MM DIA G.I/UPVC PIPE OF AVERAGE LENGTH OF 15 MTR. 10MM DIA GUN-METAL FERRULE, SADDLE PICE (AS REQUIRED SIZE), 15MM DIA BIB COCK ETC ALL COMPLETE AT PASCHIM BHATJUNGLA (ZONE-I) W/S SCHEME UNDER NADIA DIVISION, PHE DTE (PART-A) | 402/FHTC | 01/03/2021 | 0 | RADIANT | 16.33 | 0 | 0 | 0
5367 | NADIA | Nadia Division | Collection of household details as prescribed format through mobile app/hard copy including Geo-reference at different Ground Water Based Piped W/S Scheme under Krishnagar Sub-Division and Tehatta Sub-Division , SM/07011 | Support-M&E | COLLECTION OF HOUSE HOLD DETAILS AT PRESCRIBED FORMAT THROUGH MOBILE/APP/HARD COPY ......GEO-REFERENCE AT GROUND WATER BASED W/S SCHEME | 162/DW | 07/09/2021 | 0 | RADIANT | 28.66 | 0 | 0 | 0
5368 | NADIA | Nadia Division | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Ranaghat Sub-Division , SM/07012 | Support-M&E | COLLECTION OF HOUSE HOLD DETAILS AT PRESCRIBED FORMAT THROUGH MOBILE APP/HARD COPY INCLUDING GEO-REFERENCE AS DIRECTED BY EIC AND SUB-MISSION OF THE SAME TO PHE DTE. IN SOFT COPY AT DIFFERENT GROUND WATER BASED W/S SCHEME UNDER RANAGHAT SUB-DIVISION, PHE, DTE | 411/FHTC | 05/03/2021 | 0 | LEMNISCATE | 6.85 | 0 | 0 | 0
5369 | NADIA | Nadia Division | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Ranaghat Sub-Division , SM/07012 | Support-M&E | BILL FOR ADVERTISEMENT | 339/ADV | 14/01/2021 | 0 | OTHERS | 0.46 | 0 | 0 | 0
5370 | NADIA | Nadia Division | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Ranaghat Sub-Division , SM/07012 | Support-M&E | PREPARATION OF GEO-REFERENCED GIS MAPPING AT BABLARY, DEWANGANJ, BHANDERKHOLA, SONDA-1&2, KULGACHI, ITLA, DAFORPOTA, PASILA, BHANKAR, DHOPADI W/S SCHEME. | 401/FHTC | 10/03/2021 | 0 | TECHVISION | 4.98 | 0 | 0 | 0
5371 | NADIA | Nadia Division | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Ranaghat Sub-Division , SM/07012 | Support-M&E | COLLECTION OF HOUSEHOLD FORMAT MOBILE APP/HARD COPY IN KRISHNAGAR -II & KALIGANJ BLOCK UNDER SURFACE WATER BASED W/S SCHEME N.SECTOR (PART-II) | 337/DW | 11/01/2021 | 0 | ROY CHOWDHURY ASSOCIATES | 28.37 | 0 | 0 | 0
5372 | NADIA | Nadia Division | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Ranaghat Sub-Division , SM/07012 | Support-M&E | preparation of detail project report for providing FHTC | 203/DW | 22/09/2021 | 0 | INDRANIL DUTTA & ASSOCIATES | 0.4 | 0 | 0 | 0
5373 | NADIA | Nadia Division | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Ranaghat Sub-Division , SM/07012 | Support-M&E | PREPARATION OF GEO-REFERENCE GIS MAPPING WITH INTEGRATED SOFTWARE SHOWING GEO-REFERENCE LOCATION OF HOUSEHOLD PIPED W/S SCHEME AND DISTRIBUTION | 21/DW | 30/04/2021 | 0 | TECHVISION | 3.52 | 0 | 0 | 0
5374 | NADIA | Nadia Division | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Ranaghat Sub-Division , SM/07012 | Support-M&E | EXTENSION OF PIPE LINE ALONG WITH CONSTRUCTION OF STAND POST Z-IX OF SURFACE BASED W/S SCHEME PART-II NORTHERN SECTOR | 335/DW | 11/01/2021 | 0 | SOMNATH CHATTERJEE | 6.51 | 0 | 0 | 0
5375 | NADIA | Nadia Division | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Ranaghat Sub-Division , SM/07012 | Support-M&E | COLLECTION OF HOUSEHOLD FORMAT MOBILE APP/HARD COPY IN KRISHNAGAR -II & KALIGANJ BLOCK UNDER SURFACE WATER BASED W/S SCHEME N.SECTOR (PART-II) | 337/DW | 11/01/2021 | 0 | M/S R. DUTTA & CO. | 25.3 | 0 | 0 | 0
5376 | NADIA | Nadia Division | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Ranaghat Sub-Division , SM/07012 | Support-M&E | PREPARATION OF GEO-REFERENCED GIS MAPPING WITH INTEGRATED SOFTWARE GEO-REFERENCED LOCATION OF HOUSEHOLD PIPE WATER SCHEME AT DIFFERENT SCHEME | 347/DW | 14/01/2021 | 0 | TECHVISION | 4.99 | 0 | 0 | 0
5377 | NADIA | Nadia Division | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Ranaghat Sub-Division , SM/07012 | Support-M&E | COLLECTION OF HOUSEHOLD FORMAT MOBILE APP/HARD COPY IN KRISHNAGAR -II & NABADWIP BLOCK UNDER SURFACE WATER BASED W/S SCHEME N.SECTOR (PART-II) | 337/DW | 11/01/2021 | 0 | INDRANIL DUTTA & ASSOCIATES | 13.17 | 0 | 0 | 0
5378 | NADIA | Nadia Division | Collection of household details through Mobile App/hard copy including Geo-Reference at Nadia Northern Sector(P-1,2&3) and different Ground Water Based Piped W/S Scheme under Ranaghat Sub-Division , SM/07012 | Support-M&E | PREPARATION OF GEO-REFERENCED GIS MAPPING WITH INTEGRATED SOFTWARE GEO-REFERENCED LOCATION OF HOUSEHOLD PIPED W/S SCHEME AT DIFFERENT SCHEME | 347/DW | 14/01/2021 | 0 | TECHVISION | 4.89 | 0 | 0 | 0
5379 | NADIA | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. , SM/10401 | Support-WQMSP | Continuation of Maintenance for computers and related accessories for Nadia District Water Testing Laboratory, 05(Five) nos of Sub-District Water Testing Laboratory and 05 (Five) nos of NGO managed water testing laboratories under Nadia Division, PHE Dte. (W.E.F 01/02/2022 to 31/07/2022) | 78/Kly SD-I | 31/01/2022 | 181 | IONET | 0.92 | 0.92 | 100 | 0
5380 | NADIA | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. , SM/10401 | Support-WQMSP | Procurement of consumables for OMAS (On-site Mobile Analysis System) at Krishnagar Sub-District Laboratory as directed by EIC under Nadia Division, Public Health Engineering Dte. | 563/ Kly SD-I | 24/06/2022 | 15 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 4.29 | 4.29 | 100 | 0
5381 | NADIA | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. , SM/10401 | Support-WQMSP | Supply and installation of Sign-Board for NABL recognition for NGO managed laboratories and other allied works at Nadia District Water Testing Laboratory under Nadia Division PHE Dte. | 689/Kly SD-I | 01/08/2022 | 15 | MANISHIKA CONSTRUCTION | 0.78 | 0.77 | 50 | 0
5382 | NADIA | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. , SM/10401 | Support-WQMSP | Continuation of Annual Service contract for Double beam Atomic Absorption Spectrophotometer AAS3300 including supply of necessary spare parts and consumables (As and when required) installed at Belpukur Water Testing Laboratory At Belpukur WTP Site, Nadia, under Nadia Division, PHE Dte.(W.E.F-01.08.2022 to 31.01.2023) | 675/Kly SD-I | 26/07/2022 | 184 | TARUN KUMAR BHATTACHARYA | 1.56 | 1.56 | 100 | 0
5383 | NADIA | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. , SM/10401 | Support-WQMSP | Continuation of Maintenance for computers and related accessories for Nadia District Water Testing Laboratory, 05(Five) nos of Sub-District Water Testing Laboratory and 05 (Five) nos of NGO managed water testing laboratories under Nadia Division, PHE Dte. (W.E.F 01/08/2022 to 31/01/2023) | 673/Kly SD-I | 26/07/2022 | 184 | IONET | 0.92 | 0.92 | 100 | 0
5384 | NADIA | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. , SM/10401 | Support-WQMSP | Continuation of Annual Service contract for Double beam Atomic Absorption Spectrometer AAS3300 including supply of necessary spare parts and consumables (As and when required) installed at Nadia District Water Testing Laboratory At Haringhata WTP Site, Nadia, under Nadia Division, PHE Dte.(W.E.F-01.08.2022 to 31.01.2023) | 674/Kly SD-I | 26/07/2022 | 184 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 2.03 | 2.06 | 100 | 0
5385 | NADIA | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. , SM/10401 | Support-WQMSP | Annual Service contract for Double beam Atomic Absorption Spectrometer AAS3300 including supply of necessary spare parts and consumables (As and when required) installed at Nadia District Water Testing Laboratory At Haringhata WTP Site, Nadia, under Nadia Division, PHE Dte.(W.E.F-01.08.2021 to 31.07.2022) | 229/Kly SD-1 | 27/07/2021 | 365 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 4.06 | 3.98 | 100 | 0
5386 | NADIA | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. , SM/10401 | Support-WQMSP | Annual Service contract for Double beam Atomic Absorption Spectrophotometer AAS3300 including supply of necessary spare parts and consumables (As and when required) installed at Belpukur Water Testing Laboratory At Belpukur WTP Site, Nadia, under Nadia Division, PHE Dte.(W.E.F-01.08.2021 to 31.07.2022) | 230/Kly SD-1 | 27/07/2021 | 365 | TARUN KUMAR BHATTACHARYA | 3.12 | 3.13 | 100 | 0
5387 | NADIA | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. , SM/10401 | Support-WQMSP | Supply of Chemical, Certified Reference Material, Glassware and instrument for Different Water Testing Laboratories under Nadia Division, PHE Dte. | 1800/ND | 19/04/2022 | 30 | M/S MANDAL SCIENTIFIC AND WATER ANALYSIS | 27.61 | 27.61 | 100 | 0
5388 | NADIA | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. , SM/10401 | Support-WQMSP | Supply of different laboratory instruments, refrigerator etc for maintaining NABL standard of Nadia District Water Testing Laboratory under Nadia Division, PHE Dte. | 922/Kly SD-I | 29/09/2022 | 15 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 0.9 | 0.9 | 100 | 0
5389 | NADIA | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. , SM/10401 | Support-WQMSP | Providing consultancy services for NABL Accreditation of Nadia District Water Testing Laboratory as per ISO/IEC 17025: 2017 including supply of required materials under Nadia Division, PHE Dte. | 542/ Kly SD-I | 24/04/2023 | 183 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 3.95 | 3.95 | 100 | 100
5390 | NADIA | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. , SM/10401 | Support-WQMSP | Water Supply connection including installation of AC at Nadia District Water Testing Laboratory under Nadia Division, PHE Dte. | 661/KlySD-I | 25/05/2023 | 15 | MANISHIKA CONSTRUCTION | 1 | 1 | 100 | 100
5391 | NADIA | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. , SM/10401 | Support-WQMSP | SUPPLY AND INSTALLATION OF 01 NO LCD MONITOR 19 AT NADIA DISTRICT WATER TESTING LABORATORY UNDER NADIA DIVISION, PHE,DTE | 79/PFMS | 02/06/2023 | 0 | IONET | 0.09 | 0 | 0 | 0
5392 | NADIA | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. , SM/10401 | Support-WQMSP | SUPPLY AND INSTALLATION OF 01 NO CCTV CAMERA AND ACCESSORIES AT NADIA DISTRICT WATER TESTING LABORATORY UNDER NADIA DIVISION, PHE,DTE | 80/PFMS | 02/06/2023 | 0 | IONET | 0.1 | 0 | 0 | 0
5393 | NADIA | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. , SM/10401 | Support-WQMSP | SUPPLY OF CHEMICAL REGENT AT DIFFERENT WATER TESTING LABORATORIES UNDER NADIA DIVISION PHE DTE. | 54/PFMS | 02/06/2023 | 0 | BHARATI CHEMICALS & SCIENTIFIC WORKS. | 4.95 | 0 | 0 | 0
5394 | NADIA | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. , SM/10401 | Support-WQMSP | SUPPLY OF FOLLOWING ITEMS AT THE OFFICE OF THE ASSISTANT ENGINEER, KALYANI SUB-DIVISION, PHE,DTE | 82/PFMS | 02/06/2023 | 0 | IONET | 0.09 | 0 | 0 | 0
5395 | NADIA | Nadia Division | Annual Procurement of Chemicals, Consumables, Glassware, Instruments & AMC of Computers, Printers, UPS, Atomic Absorption Spectrophotometer of Different Water Testing Laboratories under Nadia Division, PHE Dte. , SM/10401 | Support-WQMSP | SUPPLY OF FOLLOWING ITEMS AT THE OFFICE OF THE ASSISTANT ENGINEER, KALYANI SUB-DIVISION, PHE,DTE | 81/PFMS | 02/06/2023 | 0 | IONET | 0.1 | 0 | 0 | 0
5396 | NADIA | Nadia Division | Development of IT Network of Active Devices for LAN & WLAN along with EPABX System, CCTV Surveillance System, Conference Room Audio System for Nadia Division, Public Health Engineering Directorate, Govt. of West Bengal , SM/10614 | Support-MIS | Development of IT Network of Active Devices for LAN & WLAN along with EPABX System, CCTV Surveillance System, Conference Room Audio System for Nadia Division, Public Health Engineering Directorate, Govt. of West Bengal | 219/PFMS | 28/09/2022 | 0 | ALTAVISTA TECH SOLUTIONS | 70.92 | 0 | 0 | 0
5397 | NADIA | Nadia Division | Development of IT Network of Active Devices for LAN & WLAN along with EPABX System, CCTV Surveillance System, Conference Room Audio System for Nadia Division, Public Health Engineering Directorate, Govt. of West Bengal , SM/10614 | Support-MIS | Development of IT Network of Active Devices for LAN & WLAN along with EPABX System, CCTV Surveillance System, Conference Room Audio System for Nadia Division, Public Health Engineering Directorate, Govt. of West Bengal. | 2125/ND | 13/05/2022 | 92 | ALTAVISTA TECH SOLUTIONS | 76.41 | 5.48 | 7.18 | 0
5398 | NADIA | Nadia Arsenic Division I | Supply, Delivery and Installation of Computer & peripherals for official use under office of the Executive Engineer, Nadia Arsenic Division-I, under Nadia Arsenic Division-I, P.H.E.Dte. , SM/10738 | Support-MIS | Bill for Canon Multifunction Machines Mfm on site OEM warranty 3 (Three) year, 1 (One) quantity for office of the Executive Engineer NADIA ARSENIC DIVISION-I, PHE,DTE. | 220/PFMS | 14/09/2022 | 0 | IONET | 5.02 | 0 | 0 | 0
5399 | NADIA | Nadia Arsenic Division I | Supply, Delivery and Installation of Computer & peripherals for official use under office of the Executive Engineer, Nadia Arsenic Division-I, under Nadia Arsenic Division-I, P.H.E.Dte. , SM/10738 | Support-MIS | Bill for HP All-in One PC 8 (Eight) Pieces for office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 372/PFMS | 21/12/2022 | 0 | IONET | 7.37 | 0 | 0 | 0
5400 | NADIA | Nadia Arsenic Division I | Supply, Delivery and Installation of Computer & peripherals for official use under office of the Executive Engineer, Nadia Arsenic Division-I, under Nadia Arsenic Division-I, P.H.E.Dte. , SM/10738 | Support-MIS | Bill for HP Desktop PC 4 (four) quantity for office of the Executive Engineer NADIA ARSENIC DIVISION-I, PHE,DTE. | 219/PFMS | 14/09/2022 | 0 | IONET | 3.78 | 0 | 0 | 0
5401 | NADIA | Nadia Arsenic Division I | Supply, Delivery and Installation of Computer & peripherals for official use under office of the Executive Engineer, Nadia Arsenic Division-I, under Nadia Arsenic Division-I, P.H.E.Dte. , SM/10738 | Support-MIS | Bill for HP Desktop PC 8 (Eight) quantity for office of the Executive Engineer NADIA ARSENIC DIVISION-I, PHE,DTE. | 221/PFMS | 14/09/2022 | 0 | IONET | 5.53 | 0 | 0 | 0
5402 | NADIA | Nadia Arsenic Division I | Supply, Delivery and Installation of Computer & peripherals for official use under office of the Executive Engineer, Nadia Arsenic Division-I, under Nadia Arsenic Division-I, P.H.E.Dte. , SM/10738 | Support-MIS | Bill for Epson Plotter 1 (One) Pieces for office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 371/PFMS | 21/12/2022 | 0 | IONET | 3.14 | 0 | 0 | 0
5403 | NADIA | Nadia Arsenic Division I | Supply, Delivery and Installation of Computer & peripherals for official use under office of the Executive Engineer, Nadia Arsenic Division-I, under Nadia Arsenic Division-I, P.H.E.Dte. , SM/10738 | Support-MIS | Bill for single function printer with Automatic 2 sided printing & wireless connectivity 26 (Twenty-Six) quantity for office of the Executive Engineer NADIA ARSENIC DIVISION-I, PHE,DTE. | 218/PFMS | 14/09/2022 | 0 | IONET | 7.12 | 0 | 0 | 0
5404 | NADIA | Nadia Arsenic Division I | Supply, Delivery and Installation of Computer & peripherals for official use under office of the Executive Engineer, Nadia Arsenic Division-I, under Nadia Arsenic Division-I, P.H.E.Dte. , SM/10738 | Support-MIS | Replacement of Cables of CCTV Camera at kalyani state referral Laboratory under NAD-I, PHE Dte. | 169/PFMS | 26/07/2023 | 0 | IONET | 0.1 | 0 | 0 | 0
5405 | NADIA | Nadia Arsenic Division I | Supply, Delivery and Installation of Computer & peripherals for official use under office of the Executive Engineer, Nadia Arsenic Division-I, under Nadia Arsenic Division-I, P.H.E.Dte. , SM/10738 | Support-MIS | Bill for HP 200 Pro G4 22 Inch AIO IPS Panel HP 21.5 Inch IPS Panel under Office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 343/PFMS | 18/11/2023 | 0 | IONET | 0.1 | 0 | 0 | 0
5406 | NADIA | Nadia Arsenic Division I | Supply, Delivery and Installation of Computer & peripherals for official use under office of the Executive Engineer, Nadia Arsenic Division-I, under Nadia Arsenic Division-I, P.H.E.Dte. , SM/10738 | Support-MIS | Bill for HP 200 Pro G4 22 Inch AIO Power Supply, SCUDA 256 GB SATA SSD & Volt IT 2365 Toner Cartridge for Brother under Office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | 344/PFMS | 18/11/2023 | 0 | IONET | 0.1 | 0 | 0 | 0
5407 | NADIA | Nadia Arsenic Division I | Supply, Delivery and Installation of Computer & peripherals for official use under office of the Executive Engineer, Nadia Arsenic Division-I, under Nadia Arsenic Division-I, P.H.E.Dte. , SM/10738 | Support-MIS | Supply and installation of CCTV Camera at kalyani state referral Laboratory under NAD-I, PHE Dte. | 168/PFMS | 26/07/2023 | 0 | IONET | 0.1 | 0 | 0 | 0
5408 | NADIA | Nadia Arsenic Division I | Supply, Delivery and Installation of Computer & peripherals for official use under office of the Executive Engineer, Nadia Arsenic Division-I, under Nadia Arsenic Division-I, P.H.E.Dte. , SM/10738 | Support-MIS | SUPPLY OF HP INTEL CORE i7 12700 8GB/0GB HDD/WINDOWS 11 PROFESSIONAL TO THE OFFICE OF THE EXECUTIVE ENGINEER,NADIA ARSENIC DIVISION-i,P.H.E DTE | 101/PFMS | 11/07/2024 | 0 | IONET | 1.89 | 0 | 0 | 0
5409 | NADIA | Nadia Arsenic Division I | Supply, Delivery and Installation of Computer & peripherals for official use under office of the Executive Engineer, Nadia Arsenic Division-I, under Nadia Arsenic Division-I, P.H.E.Dte. , SM/10738 | Support-MIS | Bill for Supply of HSN Code 84433100 Canon MF 643cdw Multifunction Machines SL No. 2FT74200 | 480/PFMS | 17/02/2024 | 0 | IONET | 0.58 | 0 | 0 | 0
5410 | NADIA | Nadia Division | SUPPLY, COMMISSIONING & MONITORING OF INTELLIGENT DISINFECTION SYSTEMS FOR FREE COMPLETE DISINFECTION OF DRINKING WATER SUPPLIED THROUGH PIPED WATER SUPPLY SCHEMES WITH MONITORING OF DOSAGE STRENGTH AT BARAKULTA WATER SUPPLY SCHEME UNDER NADIA DIVISION, P , SM/12844 | Support-WQMSP | Supply , Commissioning & Monitoring of Intelligent Disinfection systems for free complete disinfection of drinking water supplied through piped water supply schemes with monitoring of dosage strength for 5 nos at Barakulta water supply scheme under Nadia Division ,P.H.Engineering Dte. | 66/ND | 05/01/2023 | 90 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 12.58 | 2.46 | 97.66 | 70
5411 | NADIA | Nadia Division | Upgradation and Maintenance of Integrated Water Quality Management Information System (IWQ-MIS) for District Specific Dashboard of Nadia in collaboration with Maintaining of a technology-based Management Information System for Water Quality testing of pot , SM/19027 | Support-MIS | Upgradation and Maintenance of Integrated Water Quality Management Information System (IWQ-MIS) for District Specific Dashboard of Nadia in collaboration with Maintaining of a technology-based Management Information System for Water Quality testing of potable water supplied through Functional Household Tap Connections (FHTCs) by means of pre-assigned multifarious sample collection criteria in WebGIS view and upload the water quality test results for flawless functioning of the system. Period from 01.11.2023 to 31.10.2024. | 4867/ND | 31/10/2023 | 366 | HORIZEN | 75.36 | 74.18 | 100 | 55
Total | [9 empty] | 1655910.58 | 123849.8 | 7.48