## List of issued work order (Rs.
List of issued work order (Rs. in Lakh)
Sl No. | District | Division | Scheme | Scheme Category | Work Name | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Parmadan Water Supply Scheme at Bagdah Block (Phase-II). , SM/08041 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Parmadan Water Supply Scheme at Bagdah Block under North 24 Parganas water supply Division - I, PHE Dte. (Phase-II) | 420/NWSD-I | 31/05/2021 | 90 | DEBA PRASAD MONDAL | 86.58 | 82.66 | 54.64 | 1
2 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Parmadan Water Supply Scheme at Bagdah Block (Phase-II). , SM/08041 | Retrofitting | Survey, Design and preparation of Retrofitting DPR in connection with " Providing functional household tap connection to every Household under Parmadan W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte. | 218/NWSD - I | 21/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.23 | 3.23 | 100 | 1
3 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Parmadan Water Supply Scheme at Bagdah Block (Phase-II). , SM/08041 | Retrofitting | Hiring of 1(one) No. Motor Cab / Maxi Cab with contract carriage Permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer, North 24 Parganas Water Supply Sub-Divn-I, PHE Dte. for 6(Six) months w.e.f.01.10.2022. | 1080 / NWSD-I | 29/09/2022 | 6 | SOMNATH KAIPUTRA | 0.86 | 2 | 100 | 100
4 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Parmadan Water Supply Scheme at Bagdah Block (Phase-II). , SM/08041 | Retrofitting | Continuation for the work of Hiring of 1 (one) no Motor Cab / Maxi Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer, North 24 Parganas W/S Sub Division-I, P.H.E. Dte. for 1 (one) Month w.e.f 01/04/2023 to 30/04/2023. | 358/NWSD-I | 29/03/2023 | 31 | SOMNATH KAIPUTRA | 0.14 | 0.16 | 100 | 100
5 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Parmadan Water Supply Scheme at Bagdah Block (Phase-II). , SM/08041 | Retrofitting | Hiring of Diesel Ambassador Car / Cab having licensed carriage contract permit from Regional Transport Authority for the office of the Executive Engineer, North 24- Pgs. W/S Division-I, P.H.E. Dte. at Barrackpore under the control of Assistant Engineer (HQ-II), North 24-Pgs. W/S Division-I, P.H.E. Dte. for 181 (One Hundred Eighty One) days w.e.f. 01.1.2023 to 30.06.2023. | 1451/NWSD- I | 22/12/2022 | 181 | BADAL GHOSH | 0.85 | 0.28 | 100 | 51
6 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Parmadan Water Supply Scheme at Bagdah Block (Phase-II). , SM/08041 | Retrofitting | Hiring of Diesel ambassador Car / Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer (HQ-I), North 24 Parganas W/S Division-I, P.H.E. Dte. [w.e.f. 01.06.2023 to 30.11.2023.(183 days)].(Car No.WB25J7778.) | 632/NWSD-I | 25/05/2023 | 183 | GITA DAS | 0.87 | 0.09 | 100 | 20
7 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Chandpur Water Supply Scheme at Bagdah Block under (Phase-I) , SM/08042 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of CHANDPUR Water Supply Scheme at BAGDAH Block under North 24 Parganas Water Supply Division - I, P.H.E. Dte. (Phase-I). | 504 / NWSD-I | 29/06/2021 | 60 | A.K.C. SUPPLY & CONSTRUCTION | 72.47 | 70.66 | 59.55 | 1
8 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-VIII) at Kanchiara OHR site under (Phase-I) for Arsenic affected areas of N , SM/08045 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of surface water based water supply scheme ( Zone VIII) at Kanchiara OHR site under Phase-I for Arsenic affected areas of North 24 Parganas water supply Division - I, PHE Dte. of Amdanga Block at mouza Kancharia J.L. No-16, Urla J.L.No-17 and Kaipukuria, J.L. No 19 under Adhata Gram Panchayat. | 412/NWSD - 1 | 27/05/2021 | 90 | TIRUPATI ENTERPRISES | 91 | 68.34 | 75.11 | 100
9 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-VIII) at Kanchiara OHR site under (Phase-I) for Arsenic affected areas of N , SM/08045 | Retrofitting | Continuation order for the work of Hiring of 1 (one) no. Motor Cab / Maxi Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed it on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer, North 24 Parganas W/S Sub-Division-I, P.H.E. Dte. for 6(Six) months, i.e. 184 days. [w.e.f. 01.05.2024 to 31.10.2024] (Car No.WB25K0619) | 652/NWSD-I | 16/04/2024 | 184 | M/S. SHUBHA ENTERPRISE | 0.87 | 1.89 | 215.94 | 0
10 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dobila Water Supply Scheme at Swarupnagar Block (Phase-I) , SM/07854 | Retrofitting | Material Requisition To Resource Division | 2864/BD | 21/09/2022 | 0 | Resource Division | 2.16 | 0 | 0 | 0
11 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Malidah Water Supply Scheme at Bagdah Block (Phase-II) , SM/07616 | Retrofitting | providing of Functional House hold Tap connection (FHTC) in connection with JJM under command area of Malidah Water Supply Scheme. | 276/BD. | 05/02/2021 | 7 | ORIENT CONSTRUCTION. | 11 | 11 | 100 | 1
12 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Malidah Water Supply Scheme at Bagdah Block (Phase-II) , SM/07616 | Retrofitting | Material Requisition To Resource Division | 2858/BD | 21/09/2022 | 0 | Resource Division | 1.85 | 0 | 0 | 0
13 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kulia Water Supply Scheme at Baduria Block, Dist.-North 24 Parganas (Phase-I) , SM/07843 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for KULIA Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 374/BHTSD | 16/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.77 | 2.77 | 100 | 1
14 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Hingalganj w/s scheme (Zone-II), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | 1858/HSD. | 17/11/2021 | 15 | M/S NIRMAN CONSTRUCTION. | 2.96 | 2.96 | 50 | 1
15 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in Bankra mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj Water Supply Scheme (Zone-II), at Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 1295/ BD | 05/04/2022 | 60 | MONDAL PRECISION PVT.LTD | 112.27 | 0 | 0 | 1
16 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration of existing pilling works to sustain the protection of UPVC distribution pipe line at different places within Bermajur w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 417/HSD | 04/03/2022 | 10 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 3.87 | 0 | 0 | 1
17 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration of 150mm dia. DI rising main from near Kathabari more to CWR i/c CWR connection within Hingalganj w/s scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | 620/HSD | 07/04/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 3.28 | 3.28 | 99.98 | 1
18 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places due to laying of new DI/UPVC pipe line within Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 622/HSD | 07/04/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 2.34 | 2.34 | 100 | 1
19 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Work Order for " Providing Functional Household Tap Connection (FHTC) in Sandlerbil Mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj W/S/Scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, P.H.E.Dte." | 49/BD | 13/01/2021 | 90 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 155.31 | 29.14 | 100 | 1
20 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for for protection works for newly laid different dia. UPVC/DI pipe line at different. places in khosbas, Singherkati mouza & Kanaknagar Mouza for Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 237/BD | 25/01/2022 | 30 | M/S PROGATI ENTERPRISE. | 31.04 | 31.03 | 100 | 1
21 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for Protection of different dia. UPVC pipe line by UC Bullah pile at different places in Paschim Sandelerbill Uttarpara within Hingalganj W/S/Scheme(Z-II). Hingalganj Block under Hasnabad Sub -Division P.H.E. Dte. | 1470/BD. | 13/08/2021 | 15 | M/S B.K.ENTERPRISE. | 15.23 | 2.57 | 100 | 1
22 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at different places for Rejuvenation of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 420/HSD | 04/03/2022 | 10 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.82 | 0 | 0 | 1
23 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for Protection works for newly laid different dia. UPVC/DI pipe line at different places in Sandelerbill mouza within Hingalganj W/S/Scheme(Z-II). Hingalganj Block under Hasnabad Sub -Division P.H.E. Dte | 1463/BD. | 13/08/2021 | 15 | M/S PROGATI ENTERPRISE. | 15.81 | 2.48 | 100 | 1
24 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in Bankra mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj Water Supply Scheme (Zone-II), at Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 1295/BD. | 26/07/2021 | 60 | MONDAL PRECISION PVT.LTD | 115.98 | 100.18 | 100 | 1
25 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration of existing household tap connection at different places due to widening of PWD road from Bankra Bazar to Rupamari more in connection with retrofitting of Hingalganj w/s Scheme (Zone-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 1356/HSD | 03/08/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 2.9 | 2.9 | 50 | 1
26 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration by laying of 140/110/90/75 mm dia. HDPE distribution pipe line from Bankra Bazar to Rupamari more due to widening & strengthening of PWD road in connection with retrofitting of Hingalganj w/s scheme (Z-II), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | 1337/HSD | 02/08/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 4.29 | 4.29 | 50 | 1
27 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration of existing pilling works to sustain the protection of UPVC distribution pipe line at different places within Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 406/HSD | 04/03/2022 | 10 | S.K.ENTERPRISE. | 3.98 | 3.97 | 100 | 1
28 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in Bankra Dobar mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 491/BD. | 26/02/2021 | 30 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 3.45 | 3.45 | 100 | 1
29 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for Protection works for protection of DI rising main at near PH No- 3 (Old LS) within Hingalganj w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 1156/HSD | 12/07/2022 | 10 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 2.53 | 2.53 | 50 | 1
30 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration of 160 mm dia. HDPE pipe line from PH No- 4 to near Kathabari more due to widening & strengthening of PWD road in connection with retrofitting of Hingalganj w/s scheme (Z-II), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | 583/HSD | 28/03/2022 | 15 | SARKAR ENTERPRISE | 4.94 | 4.94 | 100 | 1
31 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the different mouza into Swajal Gram i/c laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 2922/BD | 26/09/2022 | 30 | M/S RAJPATH CONSTRUCTION. | 11.95 | 11.94 | 100 | 1
32 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration by laying of 200/180/160 mm dia. HDPE distribution pipe line from Kathabari more to Rupamari more due to widening & strengthening of PWD road in connection with retrofitting of Hingalganj w/s scheme (Z-II), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | 1341/HSD | 02/08/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 4.66 | 4.66 | 50 | 1
33 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line for damage portion at different places due widening of PWD road of Hingalganj w/s Scheme (Zone-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 1358/HSD | 03/08/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 4.9 | 4.9 | 50 | 1
34 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for Protection works for newly laid different dia.UPVC/DI pipe line at different places in Bankra & Bankra Dobar mouza within Hingalganj W/S/Scheme(Z-II). Hingalganj Block under Hasnabad Sub-Division P.H.E.Dte | 1464/BD. | 13/08/2021 | 30 | MONDAL & CO. (BASIRHAT). | 31.68 | 5.28 | 100 | 1
35 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for Emergent restoration of different dia. UPVC pipe line at different places in Bankra & Bankra Dobar Mouza due to widening & strengthing of PWD road for damage portion within Hingalganj W/S Scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 594/HSD | 29/03/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 4.49 | 4.49 | 100 | 1
36 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Acceptance cum work order for Construction of boundary wall at OHR site & CWR site (PH No.-3) within Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 527/BD | 23/02/2022 | 30 | ABDUL HAMID GAZI. | 22.43 | 20.86 | 100 | 1
37 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Material Requisition To Resource Division | 941/BD | 28/03/2022 | 0 | Resource Division | 150.53 | 0 | 0 | 0
38 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Material Requisition To Resource Division | 1438/BD | 23/05/2022 | 0 | Resource Division | 9.71 | 0 | 0 | 0
39 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Material Requisition To Resource Division | 961/BD | 29/03/2022 | 0 | Resource Division | 115.45 | 0 | 0 | 0
40 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -II), Hingalganj Block , SM/09225 | Retrofitting | Material Requisition To Resource Division | 1815/BD | 19/06/2023 | 0 | Resource Division | 18.48 | 0 | 0 | 0
41 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chikanpara Piped Water Supply Scheme, Gaighata Block (Phase-I) , SM/08269 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Chikanpara Water Supply Scheme in Gaighata Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 147/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.37 | 4.37 | 100 | 1
42 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chikanpara Piped Water Supply Scheme, Gaighata Block (Phase-I) , SM/08269 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of CHIKANPARA Water Supply Scheme at GAIGHATA Block under Barasat Division, PHE Dte. (Phase-I) | 259/BD | 28/01/2022 | 90 | SUPER SKILL. | 195.19 | 194.56 | 100 | 1
43 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chikanpara Piped Water Supply Scheme, Gaighata Block (Phase-I) , SM/08269 | Retrofitting | Material Requisition To Resource Division | 3658/BD | 13/12/2022 | 0 | Resource Division | 15.09 | 0 | 0 | 0
44 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Parmadan Water Supply Scheme atBagdah Block (Phase-I). , SM/08234 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PARMADAN Water Supply Scheme at BAGDAH Block under North 24 Parganas water supply Division - I, PHE Dte. (PHASE-I) | 865/NWSD-I | 08/10/2021 | 60 | M/S - SUKANTA ENTERPRISE | 49.19 | 50.37 | 54.58 | 1
45 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Parmadan Water Supply Scheme atBagdah Block (Phase-I). , SM/08234 | Retrofitting | Continuation order for the work of Hiring of Diesel Ambassador Car / Cab having licensed carriage contract permit from Regional Transport Authority for the office of the Executive Engineer, North 24- Pgs. W/S Division-I, P.H.E. Dte. at Barrackpore under the control of Assistant Engineer (HQ-II), North 24-Pgs. W/S Division-I, P.H.E. Dte. for 184 (One Hundred Eighty Four) days w.e.f. 01.07.2023 to 31.12.2023. | 787/NWSD-I | 23/06/2023 | 184 | BADAL GHOSH | 0.86 | 1.67 | 100 | 20
46 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-III Algoria OHR) at Barasat-I Block , SM/08243 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within command area of surface water based water supply scheme ( Zone III) at Algoria OHR site at Barasat-I Block for Arsenic affected areas of North 24 Parganas water supply Division - I, PHE Dte. (2nd Call) | 1130/NWSD-I | 22/12/2021 | 60 | ALOK ENTERPRISE, A UNIT OF SAKET TREXIM PVT. LTD. | 84.33 | 65.28 | 100 | 100
47 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-III Algoria OHR) at Barasat-I Block , SM/08243 | Retrofitting | Material Requisition To Resource Division | 02/NWSD-I | 03/01/2022 | 0 | Resource Division | 8.77 | 0 | 0 | 0
48 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-III Algoria OHR) at Barasat-I Block , SM/08243 | Retrofitting | Hiring of 1no. Diesel Motor Cab / Maxi Cab with contract carriage permit of R.T.A. in good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Executive Engineer, North 24 Parganas Water Supply Division-I, P.H.E. Dte. for 182 (One Hundred Eighty Two) w.e.f. 01.01.2024 to 30.06.2024. [Vehicle No.WB 25L4241] | 2201/NWSD-I | 29/12/2023 | 182 | M/S. SHUBHA ENTERPRISE | 0.86 | 1.95 | 225.07 | 0
49 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Akipur mouza (rest part after Phase-I) & Bakpukhuria mouza of Akipur Piped Water Supply Scheme, Basirhat-II Block under B , SM/08771 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Akipur Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase II) | 1956/BD | 08/10/2021 | 30 | BANERJEE CONSTRUCTION. | 58.26 | 53.25 | 100 | 1
50 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Construction of RCC stand post at different places & other allied works for damage portion due to cyclone 'YAAS' within Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 631/HSD(CAMP) | 29/06/2021 | 7 | M/S NIRMAN CONSTRUCTION. | 4.3 | 4.3 | 100 | 0
51 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Milon Mondal at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-F) | 592/HSD(Camp) | 29/06/2021 | 7 | DEB PRASAD GHOSH. | 4.26 | 4.22 | 99.04 | 0
52 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Asarani Das at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-G) | 593/HSD(Camp) | 29/06/2021 | 7 | M/S GHOSH CONSTRUCTION. | 4.12 | 4.09 | 99.13 | 0
53 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at near pond of Roti Howly, Probodh Mondal, & Ramen Mondal to Balaram Mondal due to cyclone "YAAS" for Bhabanipur- I GP within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | 599/HSD(Camp) | 29/06/2021 | 7 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 3.98 | 3.96 | 99.68 | 0
54 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Bouthakurani w/s Scheme (Z-I to V), Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 640/HSD (Camp) | 30/06/2021 | 7 | SARKAR ENTERPRISE & CO. | 4.53 | 4.51 | 99.54 | 0
55 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Bouthakurani w/s Scheme (Zone-I to V), Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 642/HSD (Camp) | 30/06/2021 | 7 | R.K.MANDAL AND CO. | 4.81 | 4.81 | 100 | 0
56 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Hingalganj w/s Scheme (Old), Hingalganj Block under Hasnasbad Sub-Division, P.H.E.Dte. | 604/HSD(Camp) | 29/06/2021 | 7 | MONDAL & CO. (BASIRHAT). | 1.93 | 1.93 | 99.58 | 0
57 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC/HDPE pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Rupmari w/s Scheme (Zone-IV to VI), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 659/HSD(Camp) | 30/06/2021 | 7 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.38 | 4.37 | 99.67 | 0
58 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Sandeshkhali w/s Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 660/HSD(Camp) | 30/06/2021 | 7 | MONDAL & CO. (BASIRHAT). | 4.53 | 4.53 | 100 | 0
59 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Laying of 110 mm dia HDPE waste water disposal pipe line for damage portion due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-3), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. (Part-A) | 615/HSD(Camp) | 29/06/2021 | 7 | M/S RAJPATH CONSTRUCTION. | 4.83 | 0 | 0 | 0
60 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 90mm dia. UPVC pipe for the damage portion of AC/UPVC pipeline due to cyclone "YAAS" within Taki Municipal w/s scheme (Zone-II), Taki Municipality under Hasnasbad Sub-Division, P.H.E.Dte. | 608/HSD(Camp) | 29/06/2021 | 7 | M/S RAJPATH CONSTRUCTION. | 3.5 | 3.49 | 99.9 | 0
61 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Laying of different dia PVC distribution pipe line for damage portion due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-16, 19 & 23), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 609/HSD(Camp) | 29/06/2021 | 7 | M/S RAJPATH CONSTRUCTION. | 4.79 | 3.35 | 69.91 | 0
62 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Kartick Mondal at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-H) | 594/HSD(Camp) | 29/06/2021 | 7 | GOBINDA DAS. | 3.95 | 3.93 | 99.4 | 0
63 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Laying of 110 mm dia HDPE waste water disposal pipe line for damage portion due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-3), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. (Part-B) | 616/HSD(Camp) | 29/06/2021 | 7 | M/S RAJPATH CONSTRUCTION. | 3.35 | 3.35 | 100 | 0
64 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of different dia. HDPE distribution pipe line from CWR to Jagananda Ashram for damage portion due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. (Part-B) | 620/HSD(Camp) | 29/06/2021 | 7 | M/S B.K.ENTERPRISE. | 4.39 | 4.39 | 100 | 0
65 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC/HDPE pipe line at different places due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 622/HSD(Camp) | 29/06/2021 | 7 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.55 | 4.55 | 100 | 0
66 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 90 mm dia. UPVC distribution pipe line from near N/H/O Tapas Mallick to near Khargeshwar Adibasi FP School at Mithhakhali for damage portion due to cyclone 'YAAS' within Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. (Part-A) | 629/HSD(Camp) | 29/06/2021 | 7 | R.K.MANDAL AND CO. | 4.67 | 4.67 | 100 | 0
67 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 90 mm dia. UPVC distribution pipe line from near Monipur Bazar to N/H/O Dinabandhu Mondal & Chimta Hatkhola to N/H/O Chittaranjan Das for damage portion due to cyclone 'YAAS' within Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 630/HSD(Camp) | 29/06/2021 | 7 | R.K.MANDAL AND CO. | 4.77 | 4.77 | 100 | 0
68 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Construction of RCC stand post at different places & other allied works for damage portion due to cyclone 'YAAS' within Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 631/HSD(CAMP) | 29/06/2021 | 7 | M/S NIRMAN CONSTRUCTION. | 4.3 | 0 | 0 | 0
69 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Kartick Mondal at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-H) | 594/HSD(Camp) | 29/06/2021 | 7 | GOBINDA DAS. | 3.95 | 0 | 0 | 0
70 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Chotto Sehara w/s Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 645/HSD (Camp) | 30/06/2021 | 7 | MONDAL & CO. (BASIRHAT). | 4.8 | 4.8 | 100 | 0
71 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Baunia Abad w/s Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 646/HSD (Camp) | 30/06/2021 | 7 | M/S PROGATI ENTERPRISE. | 4.53 | 4.53 | 100 | 0
72 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of diff. dia. UPVC distribution pipe line from near Avijan Sangha to Kachari Bari & from near Radharani High School to N/H/O Shyam Singh for damage portion due to cyclone 'YAAS' within Sandeshkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 650/HSD(Camp) | 30/06/2021 | 7 | FIDERE MARINE SERVICES PVT. LLTD. | 4.88 | 4.88 | 100 | 0
73 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Sandeshkhali w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-A) | 651/HSD(Camp) | 30/06/2021 | 7 | RAM CHANDRA HAZRA. | 4.57 | 4.56 | 99.84 | 0
74 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Restoration of pipeline by Laying of diff. dia. HDPE distribution pipe line due to cyclone YAAS in different Mouza within Hasnabad w/s scheme, Hasnabad Block under Hasnabad Sub- Division P.H.E. Dte. | 665/HSD(Camp) | 30/06/2021 | 7 | ROY CHOWDHURY CONSTRUCTION. | 4.49 | 4.49 | 100 | 0
75 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Sandeshkhali w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-B) | 652/HSD(Camp) | 30/06/2021 | 7 | ABDUL HAMID GAZI. | 4.52 | 4.53 | 100 | 0
76 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of diff. dia UPVC pipe line at different places for damaged portion due to cyclone 'YAAS' within Gabberia w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 653/HSD(Camp) | 30/06/2021 | 7 | MONDAL & CO. (BASIRHAT). | 4.59 | 4.59 | 100 | 0
77 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Rupmari w/s Scheme (Zone-IV to VI), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 656/HSD(Camp) | 30/06/2021 | 7 | R.K.MANDAL AND CO. | 4.71 | 4.71 | 100 | 0
78 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Laying of 110 mm dia HDPE waste water disposal pipe line for damage portion due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-3), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. (Part-A) | 615/HSD(Camp) | 29/06/2021 | 7 | M/S RAJPATH CONSTRUCTION. | 4.83 | 0 | 0 | 0
79 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Mukul Mondal at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-A) | 587/HSD(Camp) | 29/06/2021 | 7 | M/S GHOSH CONSTRUCTION. | 4.06 | 4.05 | 99.53 | 0
80 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Sasanka Mondal at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-J) | 596/HSD(Camp) | 29/06/2021 | 7 | NIKHIL SAMADDAR | 3.97 | 3.95 | 99.67 | 0
81 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling near pond of Dr. Pronab Roy, Shambhu Dolui, Md. Rahamat & Firoj Molla due to cyclone "YAAS" for Bhabanipur-I GP within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | 597/HSD(Camp) | 29/06/2021 | 7 | NIKHIL SAMADDAR | 4.09 | 4.03 | 98.6 | 0
82 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at near pond of Jagadish Mondal, Baidyanath Mondal, Madhu Mondal, Santosh Sau & Bablu Roy due to cyclone "YAAS" for Bhabanipur-II GP within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | 598/HSD(Camp) | 29/06/2021 | 7 | ABDUL ALIM MONDAL. | 4.05 | 4.04 | 99.86 | 0
83 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Hingalganj w/s Scheme (Zone-I), Hingalganj Block under Hasnasbad Sub-Division, P.H.E.Dte. | 605/HSD(Camp) | 29/06/2021 | 7 | MONDAL & CO. (BASIRHAT). | 3.94 | 3.93 | 99.75 | 0
84 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order forProtection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Goutam Mondal at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-B) | 588/HSD(Camp) | 29/06/2021 | 7 | GOBINDA DAS. | 3.94 | 3.91 | 99.2 | 0
85 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Tushar Mondal at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-C) | 589/HSD(Camp) | 29/06/2021 | 7 | MD.SALIM GAZI. | 4.11 | 4.06 | 98.98 | 0
86 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by bamboo pilling at different places due to cyclone "YAAS" within Taki Municipal w/s scheme (Zone-II), Taki Municipality under Hasnasbad Sub-Division, P.H.E.Dte. | 606/HSD(Camp) | 29/06/2021 | 7 | R.K.MANDAL AND CO. | 4.75 | 4.74 | 99.7 | 0
87 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Laying of 110 mm dia HDPE waste water disposal pipe line for damage portion due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-3), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. (Part-A) | 615/HSD(Camp) | 29/06/2021 | 7 | M/S RAJPATH CONSTRUCTION. | 4.83 | 4.83 | 100 | 0
88 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at different places due to cyclone "YAAS" within Taki Municipal w/s scheme (Zone-II), Taki Municipality under Hasnasbad Sub-Division, P.H.E.Dte. | 607/HSD(Camp) | 29/06/2021 | 7 | R.K.MANDAL AND CO. | 4.85 | 4.83 | 99.66 | 0
89 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Bermajur w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 611/HSD(Camp) | 29/06/2021 | 7 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.81 | 4.81 | 100 | 0
90 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC distribution pipeline by Bamboo pilling at different places due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 613/HSD(Camp) | 29/06/2021 | 7 | M/S NIRMAN CONSTRUCTION. | 4.77 | 4.76 | 99.92 | 0
91 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new different dia. UPVC pipe for the damage portion of AC/UPVC pipeline due to cyclone "YAAS" within Taki Municipal w/s scheme (Zone-II), Taki Municipality under Hasnasbad Sub-Division, P.H.E.Dte. | 614/HSD(Camp) | 29/06/2021 | 7 | M/S RAJPATH CONSTRUCTION. | 3.45 | 3.45 | 99.76 | 0
92 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Baunia Abad w/s Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 647/HSD (Camp) | 30/06/2021 | 7 | P & S ASSOCIATES. | 4.52 | 4.52 | 99.87 | 0
93 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Durgamandop w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 648/HSD (Camp) | 30/06/2021 | 7 | ABDUL ALIM MONDAL. | 4.52 | 4.51 | 99.73 | 0
94 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Rupmari w/s Scheme (Zone-I to III), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 657/HSD(Camp) | 30/06/2021 | 7 | R.K.MANDAL AND CO. | 4.79 | 4.79 | 100 | 0
95 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC/HDPE pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Rupmari w/s Scheme (Zone-I to III), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 658/HSD(Camp) | 30/06/2021 | 7 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.38 | 4.37 | 99.75 | 0
96 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 75 mm dia. HDPE distribution pipe line from near Sitalia FP School to N/H/O Mrityunjoy Baulia & N/H/O Sudhansu Biswas for damage portion due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 617/HSD(Camp) | 29/06/2021 | 7 | CHITTA RANJAN MONDAL. | 4.79 | 4.79 | 100 | 0
97 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 160mm dia. HDPE distribution pipe line from CWR to Jagananda Ashram for damage portion due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. (Part-A) | 621/HSD(Camp) | 29/06/2021 | 7 | M/S B.K.ENTERPRISE. | 4.91 | 4.91 | 100 | 0
98 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC distribution pipeline by UC bullah pile at N/H/O Nemai Sardar, near Monipur Bazar & other different places due to cyclone 'YAAS' within Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 633/HSD(Camp) | 29/06/2021 | 7 | M/S PROGATI ENTERPRISE. | 4.24 | 4.25 | 100 | 0
99 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Durgamandop w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 648/HSD (Camp) | 30/06/2021 | 7 | ABDUL ALIM MONDAL. | 4.52 | 0 | 0 | 0
100 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Ashu Das at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-D) | 590/HSD(Camp) | 29/06/2021 | 7 | PRITAM MUKHOPADHYAY. | 4.17 | 4.1 | 98.21 | 0
101 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Bhuban Mondal at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-E) | 591/HSD(Camp) | 29/06/2021 | 7 | TAKI ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 4.02 | 3.99 | 99.26 | 0
102 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of diff. dia UPVC pipe line at different places for damaged portion due to cyclone 'YAAS' within Bouthakurani w/s Scheme (Zone-I to V), Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 641/HSD (Camp) | 30/06/2021 | 7 | R.K.MANDAL AND CO. | 4.69 | 4.69 | 100 | 0
103 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection work of UPVC Distribution pipe line by UC bullah pilling at Gabtala Majher para N/H/O Protim Mondal at Bhabanipur-I GP due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-I) | 595/HSD(Camp) | 29/06/2021 | 7 | MD.SALIM GAZI. | 4.08 | 4.03 | 98.86 | 0
104 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line at different places due to cyclone 'YAAS' within Hingalganj w/s Scheme (Zone-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 610/HSD(Camp) | 29/06/2021 | 7 | M/S NIRMAN CONSTRUCTION. | 4.81 | 4.81 | 100 | 0
105 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 90 mm dia. UPVC distribution pipe line from near N/H/O Tapas Mallick to near Khargeshwar Adibasi FP School at Mithhakhali for damage portion due to cyclone 'YAAS' within Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. (Part-B) | 628/HSD(Camp) | 29/06/2021 | 7 | R.K.MANDAL AND CO. | 4.77 | 4.77 | 100 | 0
106 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of diff. dia UPVC pipe line at different places for damaged portion due to cyclone 'YAAS' within Bouthakurani w/s Scheme (Zone-I to V), Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | R.K.MANDAL AND CO | 30/06/2021 | 7 | R.K.MANDAL AND CO. | 4.69 | 0 | 0 | 0
107 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Protection of UPVC distribution pipeline by UC bullah pile at near PH No-1 & N/H/O Ramkrishna Bhuiya due to cyclone 'YAAS' within Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 632/HSD(Camp) | 29/06/2021 | 7 | M/S DATTA ENTERPRISE. | 4.24 | 4.23 | 99.81 | 0
108 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of UPVC pipe line at different places for damaged portion due to cyclone 'YAAS' within Chotto Sehara w/s Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. (Part -B) | 644/HSD (Camp) | 30/06/2021 | 7 | MONDAL & CO. (BASIRHAT). | 4.86 | 4.86 | 50 | 0
109 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of UPVC pipe line at different places for damaged portion due to cyclone 'YAAS' within Chotto Sehara w/s Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. (Part -A) | 643/HSD (Camp) | 30/06/2021 | 7 | MONDAL & CO. (BASIRHAT). | 4.56 | 4.56 | 50 | 0
110 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of different dia. HDPE distribution pipe line from N/H/O Shambhu Mondal to near Khulna Bachar para more for damage portion due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-I), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. (Part B) | 624/HSD(Camp) | 29/06/2021 | 7 | M/S B.K.ENTERPRISE. | 4.89 | 4.89 | 50 | 0
111 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 110 mm dia. UPVC distribution pipe line from near N/H/O Amar Bera at Mithakhali to near Chimta Chowmatha for damage portion due to cyclone 'YAAS' within Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. (Part-B) | 626/HSD(Camp) | 29/06/2021 | 7 | R.K.MANDAL AND CO. | 4.81 | 4.81 | 50 | 0
112 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 110 mm dia. UPVC distribution pipe line from near N/H/O Amar Bera at Mithakhali to near Chimta Chowmatha for damage portion due to cyclone 'YAAS' within Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. (Part-A) | 627/HSD(Camp) | 29/06/2021 | 7 | R.K.MANDAL AND CO. | 4.67 | 4.67 | 50 | 0
113 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 75mm dia UPVC pipe from Sulkuni Jogendra Maity School to Sulkuni Howly para for the damage portion of AC/UPVC pipeline due to cyclone "YAAS" for Bhabanipur-I GP within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | 600/HSD(Camp) | 29/06/2021 | 7 | ABDUL ALIM MONDAL. | 4.81 | 4.8 | 50 | 0
114 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of diff. dia UPVC pipe line at different places for damaged portion due to cyclone 'YAAS' within Rupmari w/s Scheme (Zone-III to IV), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 661/HSD(Camp) | 30/06/2021 | 7 | M/S DATTA ENTERPRISE. | 4.68 | 4.68 | 50 | 0
115 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of diff. dia UPVC pipe line at different places for damaged portion due to cyclone 'YAAS' within Rupmari w/s Scheme (Zone-I to II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 662/HSD(Camp) | 30/06/2021 | 7 | M/S PROGATI ENTERPRISE. | 4.55 | 4.55 | 50 | 0
116 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 90 mm dia. HDPE distribution pipe line from N/H/O Hemanta Sarkar to N/H/O Khokan Mondal at Dk. Hatgacha for damage portion due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 618/HSD(Camp) | 29/06/2021 | 7 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.89 | 4.89 | 50 | 0
117 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 110mm dia. HDPE distribution pipe line from Hatgacha Sarkar para more to N/H/O Hemanta Sarkar for damage portion due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 619/HSD(Camp) | 29/06/2021 | 7 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.84 | 4.84 | 50 | 0
118 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration by laying of 110 mm dia. HDPE distribution pipe line from N/H/O Shambhu Mondal to near Khulna Bachar para more for damage portion due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-I), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. (Part A) | 623/HSD(Camp) | 29/06/2021 | 7 | M/S B.K.ENTERPRISE. | 4.83 | 4.83 | 50 | 0
119 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 90mm dia UPVC pipe from N/H/O Santosh Sau to Roti Howly for the damage portion of AC/UPVC pipeline due to cyclone "YAAS" for Bhabanipur- I GP within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | 602/HSD(Camp) | 29/06/2021 | 7 | BADAL GHOSH. | 4.15 | 4.14 | 100 | 0
120 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 90mm & 75mm dia UPVC pipe at different places for the damage portion of AC/UPVC pipeline due to cyclone "YAAS" for Bhabanipur-I & II GP within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | 601/HSD(Camp) | 29/06/2021 | 7 | M/S K.B.ENTERPRISE. | 3.72 | 3.7 | 100 | 0
121 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of existing household tap connection at different places due to cyclone 'YAAS' within Rupmari w/s Scheme (Zone-III to IV), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 664/HSD(Camp) | 30/06/2021 | 7 | M/S PROGATI ENTERPRISE. | 4.84 | 4.84 | 50 | 0
122 | NORTH 24 PARGANAS | Barasat Division | Restoration of different piped water supply scheme in Sundarban island area of north 24 parganas district duly affected by cyclonic storm YAAS. , SM/09004 | Disaster | Acceptance cum work order for Emergent restoration of existing household tap connection at different places due to cyclone 'YAAS' within Rupmari w/s Scheme (Zone-I to II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 663/HSD(Camp) | 30/06/2021 | 7 | M/S DATTA ENTERPRISE. | 4.84 | 4.84 | 50 | 0
123 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of PIFA W/S Scheme at Basirhat -I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). , SM/08789 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Pifa Water Supply Scheme at Basirhat - I Block under Barasat Division, PHE Dte. (Phase - I) | 221/BD | 24/01/2022 | 45 | M/S ANUBHAB CONSTRUCTION. | 68.51 | 67.86 | 99.05 | 1
124 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of PIFA W/S Scheme at Basirhat -I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). , SM/08789 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for PIFA Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | 190/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.73 | 3.65 | 100 | 1
125 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of PIFA W/S Scheme at Basirhat -I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). , SM/08789 | Retrofitting | Material Requisition To Resource Division | 2985/BD | 29/09/2022 | 0 | Resource Division | 7.39 | 0 | 0 | 0
126 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gangrapota Piped Water Supply Scheme, Bongaon Block (Phase-I) , SM/08264 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Gangrapota Water Supply Scheme at Bongaon Block under Barasat Division, PHE Dte. (Phase-I). | 2175/BD | 18/11/2021 | 90 | AMIT KUMAR BOSE. | 167.22 | 159.23 | 100 | 1
127 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gangrapota Piped Water Supply Scheme, Bongaon Block (Phase-I) , SM/08264 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Gangrapota Water Supply Scheme under Bongaon Sub-Division, under Barasat Division, PHE.Dte. | 611/Bon | 31/12/2021 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.12 | 4.1 | 100 | 1
128 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gangrapota Piped Water Supply Scheme, Bongaon Block (Phase-I) , SM/08264 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Kamarpur & Adj. Mouzas W/S Scheme within the jurisdiction of the Habra Sub-Division under Barasat Division, PHE Dte. | 558/HAB | 20/12/2021 | 10 | UMWELT ENGINEER PVT.LTD. | 3.42 | 3.41 | 100 | 1
129 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gangrapota Piped Water Supply Scheme, Bongaon Block (Phase-I) , SM/08264 | Retrofitting | Construction of Boundary wall at 2nd Pump House site for Augmentation of Gangrapota Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 614/Bon | 08/08/2023 | 21 | A.D.ENTERPRISE. | 3.66 | 0 | 0 | 0
130 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gangrapota Piped Water Supply Scheme, Bongaon Block (Phase-I) , SM/08264 | Retrofitting | Construction of Approach Road Head Work at site for Augmentation of Gangrapota Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 619/BON | 08/08/2023 | 20 | MA CONSTRUCTION. | 3.98 | 3.95 | 100 | 100
131 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gangrapota Piped Water Supply Scheme, Bongaon Block (Phase-I) , SM/08264 | Retrofitting | Material Requisition To Resource Division | 2238/BD | 24/11/2021 | 0 | Resource Division | 10.26 | 0 | 0 | 0
132 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency Hiring charges of 1 no. 30 KVA mobile silent type DG set in the situation of cyclone Amphan 2020 at under Matigacha W/S Scheme | 981A/EMSD-I | 22/05/2020 | 8 | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0 | 0 | 0
133 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency Hiring charges of mobile silent type DG set in the situation of cyclone YAAS 2021 at under Atapur W/S Scheme | 1264/EMSD-I | 24/05/2021 | 1 | DIPALI CONSTRUCTION | 0.2 | 0 | 0 | 0
134 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency hiring charges of 1 no.45 KVA mobile silent DG set on the situation of cylone YASS 2021 at P.H.-H/L Z-II under Hingal ganj Aug. W/S Scheme | 1235/EMSD-I | 21/05/2021 | 31 | BISALAXMI ENTERPRISE | 0.91 | 0 | 0 | 0
135 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency hiring charges of 1 no.30 KVA mobile silent DG set on the situation of cylone Amphan 2020 at P.H.-I Z-III under Bongaon Municipal W/S Scheme | 995C/EMSD-I | 28/05/2020 | 31 | ESENCE ENGINEERING CONCERN | 0.96 | 0 | 0 | 0
136 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency hiring charges of 1 no.30 KVA mobile silent DG set on the situation of cylone Amphan 2020 at P.H.-I under Kaniara W/S Scheme | 991E/EMSD-I | 28/05/2020 | 31 | ESENCE ENGINEERING CONCERN | 0.96 | 0 | 0 | 0
137 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency hiring charges of 1 no.30 KVA mobile silent DG set on the situation of cylone Amphan 2020 at P.H.-I under Mollahati W/S Scheme | 993E/EMSD-I | 28/05/2020 | 31 | ESENCE ENGINEERING CONCERN | 0.96 | 0 | 0 | 0
138 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency hiring charges of 1 no.30 KVA mobile silent DG set on the situation of cylone Amphan 2020 at P.H.-H/L Z-II under Hingalganj Aug W/S Scheme | 1381/EMSD-I | 03/06/2021 | 5 | BISALAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
139 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency Hiring charges of 1 no. 30 KVA mobile silent type DG set in the situation of cyclone YAAS 2021 at P.H.-I under Barunhat W/S Scheme | 1242/EMSD-I | 21/05/2021 | 31 | AVINABA ENGINEERING CONCERN | 0.96 | 0 | 0 | 0
140 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency Hiring charges of mobile silent type DG set in the situation of cyclone YAAS 2021 at under HingalGanj W/S Scheme | 1308/EMSD-I | 27/05/2021 | 4 | INDTECH ASSOCIATES | 0.73 | 0 | 0 | 0
141 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency Hiring charges of 1 no. 30 KVA mobile silent type DG set in the situation of cyclone Amphan 2020 at P.H.-I under Ashudi W/S Scheme | 980B/EMSD-I | 22/05/2020 | 8 | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0 | 0 | 0
142 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency Hiring charges of mobile silent type DG set in the situation of cyclone YAAS 2021 at under hingalganj W/S Scheme | 1263/EMSD-I | 24/05/2021 | 4 | INDTECH ASSOCIATES | 0.82 | 0 | 0 | 0
143 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency Hiring charges of 1 no. 30 KVA mobile silent type DG set in the situation of cyclone Amphan 2020 at under Diara W/S Scheme | 983B/EMSD-I | 22/05/2020 | 8 | BISALAXMI ENTERPRISE | 0.96 | 0 | 0 | 0
144 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Supply & delivery of calcium hypochlorite Caocl2 tablets at diffrnt. P.H. for disinfection of drinking water at cyclone storm Amphan effected under EMSD-I under Gobindapur (Block-Bagdah, Dhanyakuria W/S Scheme. | 1007A/ EMSD-I | 28/05/2020 | 31 | BIJAN ENTERPRISE | 0.85 | 0 | 0 | 0
145 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Supply and delivery of Caocl2 of kanaikathikanthaberia W/S for disinfecting of drinking water on situation YAAS. | 1327/ EMSD-I | 28/05/2021 | 31 | KASHINATH PAL & CO. | 0.94 | 0 | 0 | 0
146 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring charges of mobile silent type DG set open type DG set on emergency basis for the himgalganj W/S on the impending cyclonic storm YAAS under EMD | 1401/ EMSD-I | 04/06/2021 | 5 | INDTECH ASSOCIATES | 0.73 | 0 | 0 | 0
147 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Restoration of external Illumination arrabgement after Amphan cyclone in diffrnt. PWSS under EMSD-II | 572/ EMSD-II | 14/09/2020 | 11 | ABHISEK ENGINEERING CONCERN | 2.25 | 0 | 0 | 0
148 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile siletn type DG set on emergency basis under Hingalganj W/S scheme | 1343/ EMSD-I | 31/05/2021 | 30 | INDTECH ASSOCIATES | 0.73 | 0 | 0 | 0
149 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency hiring charges of 1 no.30 KVA mobile silent DG set on the situation of cylone Amphan 2020 at P.H.-I under Kaniara W/S Scheme | 998C/EMSD-I | 28/05/2020 | 31 | ESENCE ENGINEERING CONCERN | 0.96 | 0 | 0 | 0
150 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency hiring charges of 1 no.30 KVA mobile silent DG set on the situation of cylone Amphan 2020 at P.H.-I under Dhalani W/S Scheme | 997C/EMSD-I | 28/05/2020 | 31 | ESENCE ENGINEERING CONCERN | 0.96 | 0 | 0 | 0
151 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency hiring charges of 1 no.30 KVA mobile silent DG set on the situation of cylone Amphan 2020 at P.H.-I under Dighari W/S Scheme | 994E/EMSD-I | 28/05/2020 | 31 | ESENCE ENGINEERING CONCERN | 0.96 | 0 | 0 | 0
152 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency Hiring charges of 1 no. 45 KVA mobile silent type DG set in the situation of cyclone YAAS 2021 at P.H.-H/L Z-II under HingalGanj Aug. W/S Scheme | 1304/EMSD-I | 27/05/2021 | 3 | BISALAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
153 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency Hiring charges of 1 no. 45 KVA mobile silent type DG set in the situation of cyclone YAAS 2021 at P.H.-H/L Z-II under HingalGanj Aug. W/S Scheme | 1342/EMSD-I | 31/05/2021 | 3 | BISALAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
154 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-i under Deara W/S scheme on Amphan, T.No.542/EMSD-I, W.O-983B/EMSD-I | 983B/ SD I | 22/05/2020 | 365 | BISALAXMI ENTERPRISE | 0.96 | 0.96 | 100 | 0
155 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-I under Ashudi W/S scheme on Amphan, T.No.440/EMSD-I, W.O-980B/EMSD-I | 980B/ SD I | 22/05/2020 | 365 | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0.96 | 100 | 0
156 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Supply delivery of Calcium Hypochlorite tablet at Gobindapur W/S Scheme, T.No.397/EMD, W.O-1007A/EMD | 1007A/ SD I | 28/05/2020 | 365 | BIJAN ENTERPRISE | 0.85 | 0.85 | 100 | 0
157 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency hiring of 30 KVA Mobile silent DG Set on Amphan at PH-I under Kola W/S scheme, T.No.556/EMSD-I, W.O-1018B/EMSD-I | 1018B/ SD I | 29/05/2020 | 365 | M/S DAS ENTERPRISE | 0.96 | 0.96 | 100 | 0
158 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-i Z-III under Bongaon Municipal W/S scheme on Amphan, T.No.579/EMSD-I, W.O-995C/EMSD-I | 995C/ SD I | 28/05/2020 | 365 | ESENCE ENGINEERING CONCERN | 0.96 | 0.96 | 100 | 0
159 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-I under Kaniara W/S scheme on Amphan, T.No.598/EMSD-I, W.O-998C/EMSD-I | 998C/ SD I | 28/05/2020 | 365 | ESENCE ENGINEERING CONCERN | 0.96 | 0.96 | 100 | 0
160 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-I Z-II under Ihhlampur W/S scheme on Amphan, T.No.577/EMSD-I, W.O-991E/EMSD-I | 991E/ SD I | 28/05/2020 | 365 | ESENCE ENGINEERING CONCERN | 0.96 | 0.96 | 100 | 0
161 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-I under Mollahati W/S scheme on Amphan, T.No.578/EMSD-I, W.O-993E/EMSD-I | 993E/ SD I | 28/05/2020 | 365 | ESENCE ENGINEERING CONCERN | 0.96 | 0.96 | 100 | 0
162 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-I under Dhalani W/S scheme on Amphan, T.No.580/EMSD-I, W.O-997C/EMSD-I | 997C/ SD I | 28/05/2020 | 365 | ESENCE ENGINEERING CONCERN | 0.96 | 0.96 | 100 | 0
163 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-I under Dighari W/S scheme on Amphan, T.No.596/EMSD-I, W.O-994E/EMSD-I | 994E/ SD I | 28/05/2020 | 365 | ESENCE ENGINEERING CONCERN | 0.96 | 0.96 | 100 | 0
164 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH- under Hingalganj Aug W/S scheme on Amphan, T.No.436/EMSD-I, W.O-981A/EMSD-I | 981A/ SD I | 22/05/2020 | 365 | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0.96 | 100 | 0
165 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency Hiring of Mobile Silent DG Set on emergency basis On the Situation of YAAS at Different W/S Scheme under EMD | 103/EMSD-I | 26/05/2020 | 365 | ESENCE ENGINEERING CONCERN | 11.57 | 0 | 0 | 0
166 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency Hiring of Mobile Silent DG Set on emergency basis On the Situation of Amphan at Different W/S Scheme under EMD | 102/EMSD-I | 19/05/2020 | 365 | BISALAXMI ENTERPRISE | 9.67 | 0 | 0 | 0
167 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency Hiring of Mobile Silent DG Set on emergency basis On the Situation of Amphan at Different W/S Scheme under EMD | 110/EMSD-I | 21/05/2020 | 365 | ESENCE ENGINEERING CONCERN | 11.57 | 0 | 0 | 0
168 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency hiring charges of 1 no. 30 KVA mobile siletn type DG set on the situation of Amphan 2020 at P.H.-I under Kola W/S scheme | 1018B/ EMSD-I | 29/05/2020 | 31 | M/S DAS ENTERPRISE | 0.96 | 0 | 0 | 0
169 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Emergency hiring of generator for Yass | 1231/EMSD I | 21/05/2021 | 365 | BISALAXMI ENTERPRISE | 0.81 | 0.81 | 100 | 0
170 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH- under HINGALGANJ W/S scheme on yaas, T.No.679/EMSD-I, W.O-1263/EMSD-I | 1263/ SD I | 24/05/2021 | 365 | INDTECH ASSOCIATES | 0.82 | 0.82 | 100 | 0
171 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Restoration of external Illumination on Amphan in different W/S Scheme, T.No49/EMSD-I, W.O-572/EMSD-II | 572/ SD II | 14/09/2020 | 365 | ABHISEK ENGINEERING CONCERN | 2.25 | 2.25 | 100 | 0
172 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Supply delivery of Cacocl tablet at Kanaikathikantaberia W/S scheme, T.No.828/EMSD-I, W.O-1327/EMSD-I | 1327/Sd I | 28/05/2021 | 365 | KASHINATH PAL & CO. | 0.94 | 0.94 | 100 | 0
173 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis Hingalganj W/S scheme on YASS, T.No.10/EMSD-I, W.O1401/EMSD-I | 1401/ SD I | 04/06/2021 | 365 | INDTECH ASSOCIATES | 0.73 | 0.73 | 100 | 0
174 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-H/L under Hingalganj W/S scheme on YASS, T.No.211/EMSD-I, W.O1235/EMSD-I | 1235/ SD I | 21/05/2021 | 365 | BISALAXMI ENTERPRISE | 0.91 | 0.91 | 100 | 0
175 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring charges of mobile Silent type DG set on emergency basis at Hingalganj W/S Scheme on YAAS, T.No.1061/EMD, W.O-1343/EMSD-I | 1343/ SD I | 31/05/2021 | 365 | INDTECH ASSOCIATES | 0.73 | 0.73 | 100 | 0
176 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-H/L under Hingalganj Aug. W/S scheme on YAAS, T.No.869/EMSD-I, W.O-1381/EMSD-I | 1381/ SD I | 03/06/2021 | 365 | BISALAXMI ENTERPRISE | 0.82 | 0.82 | 100 | 0
177 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-I under Barunhat W/S scheme on YAAS, T.No.377/EMSD-I, W.O-1242/EMSD-I | 1242/ SD I | 21/05/2021 | 365 | AVINABA ENGINEERING CONCERN | 0.96 | 0.96 | 100 | 0
178 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-H/L Z-II under Hingalganj W/S scheme on YAAS, T.No.617/EMSD-I, W.O-1304/EMSD-I | 1304/ SD I | 27/05/2021 | 365 | BISALAXMI ENTERPRISE | 0.82 | 0.82 | 100 | 0
179 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-H/L Z-II under Hingalganj Aug W/S scheme on YAAS, T.No.641/EMSD-I, W.O-1342/EMSD-I | 1342/ SD I | 31/05/2022 | 365 | BISALAXMI ENTERPRISE | 0.82 | 0.82 | 100 | 0
180 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH- under Hingalganj Aug W/S scheme on YAAS, T.No.952/EMSD-I, W.O-1308/EMSD-I | 1308/ SD I | 27/05/2021 | 365 | INDTECH ASSOCIATES | 0.73 | 0.73 | 100 | 0
181 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH- under Atapur W/S scheme on yaas, T.No.833/EMSD-I, W.O-1264/EMSD-I | 1264/ SD I | 24/05/2021 | 365 | DIPALI CONSTRUCTION | 0.2 | 0.2 | 100 | 0
182 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set for Amphan at Icchlampur | PFMS-Feb-22 | 23/02/2022 | 0 | INDTECH ASSOCIATES | 0.96 | 0 | 0 | 0
183 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Operation & guarding DG set for Yaas | PFMS-Feb-22 | 09/02/2022 | 0 | BISALAXMI ENTERPRISE | 0.02 | 0 | 0 | 0
184 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Carrying at Haringhata Bottling plant | PFMS-Feb-22 | 09/02/2022 | 0 | ABHISEK ENGINEERING CONCERN | 0.74 | 0 | 0 | 0
185 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Operation & guarding DG set for Yaas | PFMS-Feb-22 | 09/02/2022 | 0 | M/S G.P. ENTERPRISE | 0.43 | 0 | 0 | 0
186 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Operation & guarding DG set for Yaas | PFMS-Feb-22 | 09/02/2022 | 0 | DAS ENTERPRISE (BARANAGAR) | 0.73 | 0 | 0 | 0
187 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at Kuruli | PFMS-Feb-22 | 23/02/2022 | 0 | BISALAXMI ENTERPRISE | 0.96 | 0 | 0 | 0
188 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Supply & delivery at Cyclonic Storm Amphan affected areas |  | 11/02/2022 | 0 | D.K. ELECTRIC | 6.14 | 0 | 0 | 0
189 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Supply & delivery at Cyclonic Storm Amphan affected areas |  | 11/02/2022 | 0 | INDTECH ASSOCIATES | 7.46 | 0 | 0 | 0
190 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Operation & guarding DG set for Amphan | PFMS-Feb-22 | 09/02/2022 | 0 | INDTECH ASSOCIATES | 0.84 | 0 | 0 | 0
191 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at Paschim panchberia | PFMS-Feb-22 | 23/02/2022 | 0 | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0 | 0 | 0
192 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Operation & guarding DG set for Yaas | PFMS-Feb-22 | 09/02/2022 | 0 | BISALAXMI ENTERPRISE | 0.86 | 0 | 0 | 0
193 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at Boyra | PFMS-Feb-22 | 23/02/2022 | 0 | BISALAXMI ENTERPRISE | 0.96 | 0 | 0 | 0
194 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Supply & delivery at Cyclonic Storm Amphan affected areas |  | 11/02/2022 | 0 | GHOSH AND GHOSH | 1.07 | 0 | 0 | 0
195 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Supply & delivery at Cyclonic Storm Amphan affected areas |  | 11/02/2022 | 0 | M/S DAS ENTERPRISE | 4.81 | 0 | 0 | 0
196 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Supply & delivery at Cyclonic Storm Amphan affected areas |  | 11/02/2022 | 0 | MAA KALI ENTERPRISE | 0.84 | 0 | 0 | 0
197 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Supply & delivery at Cyclonic Storm Amphan affected areas |  | 11/02/2022 | 0 | H.K. DAS & CO. | 2.85 | 0 | 0 | 0
198 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set for Amphan at Hingalganj | PFMS-Feb-22 | 23/02/2022 | 0 | INDTECH ASSOCIATES | 0.8 | 0 | 0 | 0
199 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set for Amphan at Hariharpur | PFMS-Feb-22 | 23/02/2022 | 0 | M/S DAS ENTERPRISE | 0.96 | 0 | 0 | 0
200 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at Panchita | PFMS-Feb-22 | 23/02/2022 | 0 | D.K. ELECTRIC | 0.96 | 0 | 0 | 0
201 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set for Amphan at Bagda | PFMS-Feb-22 | 23/02/2022 | 0 | M/S DAS ENTERPRISE | 0.96 | 0 | 0 | 0
202 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Operation & guarding DG set for Yaas | PFMS-Feb-22 | 09/02/2022 | 0 | BISALAXMI ENTERPRISE | 0.7 | 0 | 0 | 0
203 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set for Amphan | PFMS-Feb-22 | 09/02/2022 | 0 | AVINABA ENGINEERING CONCERN | 0.73 | 0 | 0 | 0
204 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Supply & delivery at Cyclonic Storm Amphan affected areas |  | 11/02/2022 | 0 | STANDARD ENGINEERING | 0.94 | 0 | 0 | 0
205 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Operation & guarding DG set for Yaas | PFMS-Feb-22 | 09/02/2022 | 0 | H.K. DAS & CO. | 0.65 | 0 | 0 | 0
206 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Operation & guarding DG set for Yaas | PFMS-Feb-22 | 09/02/2022 | 0 | BISALAXMI ENTERPRISE | 0.89 | 0 | 0 | 0
207 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Operation & guarding DG set for Yaas | PFMS-Feb-22 | 09/02/2022 | 0 | DAS ENTERPRISE (BARANAGAR) | 0.49 | 0 | 0 | 0
208 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Operation & guarding DG set for Yaas | PFMS-Feb-22 | 09/02/2022 | 0 | DAS ENTERPRISE (BARANAGAR) | 0.93 | 0 | 0 | 0
209 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set for Amphan at kamarkella | PFMS-Feb-22 | 23/02/2022 | 0 | INDTECH ASSOCIATES | 0.96 | 0 | 0 | 0
210 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at Rupmari | PFMS-Feb-22 | 23/02/2022 | 0 | BISALAXMI ENTERPRISE | 0.7 | 0 | 0 | 0
211 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at Bagangram | PFMS-Feb-22 | 23/02/2022 | 0 | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0 | 0 | 0
212 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Operation & guarding DG set for Yaas | PFMS-Feb-22 | 09/02/2022 | 0 | BISALAXMI ENTERPRISE | 0.79 | 0 | 0 | 0
213 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at Chandpur | PFMS-Feb-22 | 23/02/2022 | 0 | BISALAXMI ENTERPRISE | 0.96 | 0 | 0 | 0
214 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at Gainpur | PFMS-Feb-22 | 23/02/2022 | 0 | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0 | 0 | 0
215 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Carrying at Haringhata | PFMS-Feb-22 | 09/02/2022 | 0 | ABHISEK ENGINEERING CONCERN | 0.74 | 0 | 0 | 0
216 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at Paikpara | PFMS-Feb-22 | 23/02/2022 | 0 | BISALAXMI ENTERPRISE | 0.96 | 0 | 0 | 0
217 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set for Amphan at Barrackpore | PFMS-Feb-22 | 23/02/2022 | 0 | H.K. DAS & CO. | 0.96 | 0 | 0 | 0
218 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Operation & guarding DG set for Yaas | PFMS-Feb-22 | 09/02/2022 | 0 | BISALAXMI ENTERPRISE | 0.83 | 0 | 0 | 0
219 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Operation & guarding DG set for Yaas | PFMS-Feb-22 | 09/02/2022 | 0 | BISALAXMI ENTERPRISE | 0.8 | 0 | 0 | 0
220 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set for Amphan at Santoshpur | PFMS-Feb-22 | 23/02/2022 | 0 | INDTECH ASSOCIATES | 0.96 | 0 | 0 | 0
221 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set for Amphan at santoshpur | PFMS-Feb-22 | 23/02/2022 | 0 | INDTECH ASSOCIATES | 0.96 | 0 | 0 | 0
222 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set for Amphan at kaniara | PFMS-Feb-22 | 23/02/2022 | 0 | M/S DAS ENTERPRISE | 0.96 | 0 | 0 | 0
223 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at Sindrani | PFMS-Feb-22 | 23/02/2022 | 0 | D.K. ELECTRIC | 0.96 | 0 | 0 | 0
224 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Carrying at Haringhata | PFMS-Feb-22 | 09/02/2022 | 0 | ABHISEK ENGINEERING CONCERN | 0.83 | 0 | 0 | 0
225 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at ganrapota | PFMS-Feb-22 | 23/02/2022 | 0 | D.K. ELECTRIC | 0.96 | 0 | 0 | 0
226 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set for Amphan at Chowberia | PFMS-Feb-22 | 23/02/2022 | 0 | H.K. DAS & CO. | 0.96 | 0 | 0 | 0
227 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set for Amphan at Helenchi | PFMS-Feb-22 | 23/02/2022 | 0 | M/S DAS ENTERPRISE | 0.96 | 0 | 0 | 0
228 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Generator hiring for Amphan | PFMS-Feb-22 | 09/02/2022 | 0 | AVINABA ENGINEERING CONCERN | 0.73 | 0 | 0 | 0
229 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Operation & guarding DG set for Yaas | PFMS-Feb-22 | 09/02/2022 | 0 | DAS ENTERPRISE (BARANAGAR) | 0.8 | 0 | 0 | 0
230 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set for Amphan at Barrackpore | PFMS-Feb-22 | 23/02/2022 | 0 | INDTECH ASSOCIATES | 0.96 | 0 | 0 | 0
231 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set for Amphan at Ghatpatila | PFMS-Feb-22 | 23/02/2022 | 0 | M/S DAS ENTERPRISE | 0.96 | 0 | 0 | 0
232 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at Bagangram | PFMS-Feb-22 | 23/02/2022 | 0 | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0 | 0 | 0
233 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Operation & guarding DG set for Yaas | PFMS-Feb-22 | 09/02/2022 | 0 | H.K. DAS & CO. | 0.98 | 0 | 0 | 0
234 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Operation & guarding DG set for Yaas | PFMS-Feb-22 | 09/02/2022 | 0 | DAS ENTERPRISE (BARANAGAR) | 0.81 | 0 | 0 | 0
235 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at Sindrani | PFMS-Feb-22 | 23/02/2022 | 0 | D.K. ELECTRIC | 0.96 | 0 | 0 | 0
236 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Supply & delivery at Cyclonic Storm Amphan affected areas |  | 11/02/2022 | 0 | BISALAXMI ENTERPRISE | 6.48 | 0 | 0 | 0
237 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Supply & delivery at Cyclonic Storm Amphan affected areas |  | 11/02/2022 | 0 | DAS ENTERPRISE (BARANAGAR) | 5.77 | 0 | 0 | 0
238 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set for Amphan at Palla | PFMS-Feb-22 | 23/02/2022 | 0 | INDTECH ASSOCIATES | 0.96 | 0 | 0 | 0
239 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Operation & guarding DG set for Yaas | PFMS-Feb-22 | 09/02/2022 | 0 | BISALAXMI ENTERPRISE | 0.73 | 0 | 0 | 0
240 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at Bharatpur | PFMS-Feb-22 | 23/02/2022 | 0 | D.K. ELECTRIC | 0.61 | 0 | 0 | 0
241 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at Kurulia | PFMS-Feb-22 | 23/02/2022 | 0 | BISALAXMI ENTERPRISE | 0.96 | 0 | 0 | 0
242 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at Auldanga | PFMS-Feb-22 | 23/02/2022 | 0 | BISALAXMI ENTERPRISE | 0.96 | 0 | 0 | 0
243 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at parmadan | PFMS-Feb-22 | 23/02/2022 | 0 | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0 | 0 | 0
244 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at Krisnachandrapur | PFMS-Feb-22 | 23/02/2022 | 0 | D.K. ELECTRIC | 0.96 | 0 | 0 | 0
245 | NORTH 24 PARGANAS | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. , SM/08994 | Disaster | Hiring DG set at Paschim panchberia | PFMS-Feb-22 | 23/02/2022 | 0 | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0 | 0 | 0
246 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jhupkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10505 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 1617/BD | 07/06/2022 | 90 | RADIANT | 124.77 | 123.97 | 99.36 | 0
247 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jhupkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10505 | Retrofitting | Formal work order for Protection work in different places of Jhupkhali Mouza in connection with retrofitting of Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1324/BD | 28/04/2023 | 30 | RADIANT | 112.53 | 112.39 | 100 | 0
248 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jhupkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10505 | Retrofitting | Acceptance cum work order for Providing Functional tap connection at Dhulia Jhupkhali FP School, Dhulia Jhupkhali Jr. High School & Jhupkhali FP School within the command area of Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1052/HSD | 31/08/2023 | 7 | M/S RAJPATH CONSTRUCTION. | 0.53 | 0.53 | 100 | 100
249 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jhupkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10505 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Jhupkhali mouza due to erosion of soil for heavy rain fall during monsoon season within Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 1064/HSD | 31/08/2023 | 10 | JESMINE ENTERPRISE. | 0.98 | 0.98 | 100 | 100
250 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jhupkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10505 | Retrofitting | Acceptance cum work order for Protection works in different places for protection of different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile in Laukhali and Jhupkhali w/s scheme, Sandeshkhali-I & II block respectively under Hasnabad Sub-Division P.H.E. Dte. | 2681/BD | 04/09/2023 | 30 | SURYA ENTERPRISE. | 67.91 | 67.4 | 100 | 99
251 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jhupkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10505 | Retrofitting | Acceptance cum work order for Construction of boundary wall with RCC column structure at Head Work site (TW No-1) within Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 4377/BD | 10/11/2023 | 90 | JESMINE ENTERPRISE. | 21.09 | 20.58 | 100 | 100
252 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jhupkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10505 | Retrofitting | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site at PH No.-1 within Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 355/BD | 31/01/2025 | 45 | B.S.ENTERPRISE. (BASIRHAT) | 27.86 | 0 | 0 | 0
253 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jhupkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10505 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) for left out house holds under the command area of Jhupkhali water supply scheme in order to provide Har Ghar Jal Certification, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | 371/BD | 06/02/2024 | 208 | ROHAN MONDAL. | 39.12 | 34.67 | 88.63 | 100
254 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10506 | Retrofitting | Acceptance cum work order forProtection of newly laid UPVC pipe line by bamboo pilling at different places at Agarhati mouza in connection with retrofitting of Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 1334/HSD | 02/08/2022 | 10 | K.T.ENGINEERING & CO. | 4.47 | 4.46 | 100 | 1
255 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10506 | Retrofitting | Acceptance cum work order for Additional emergent resting of 100/150 mm dia DI pipeline by concrete block at different places within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 359/HSD | 23/02/2022 | 15 | MD.SALIM GAZI. | 4.19 | 4.15 | 50 | 1
256 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10506 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC pipe line at different places at Agarhati Mouza within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 361/HSD | 23/02/2022 | 15 | MD.SALIM GAZI. | 4.76 | 4.76 | 50 | 1
257 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10506 | Retrofitting | Acceptance cum work order for Emergent casing of UPVC pipe line at different locations over Khal, channel, culverts, roads within Laukhali W/S Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 358/HSD | 23/02/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.39 | 4.49 | 50 | 1
258 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10506 | Retrofitting | Acceptance cum work order for Additional emergent resting of 200/250/300 mm dia DI pipeline by concrete block at different places within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 360/HSD | 23/02/2022 | 15 | SARKAR ENTERPRISE | 4.31 | 4.26 | 50 | 1
259 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10506 | Retrofitting | Acceptance cum work order for Additional emergent restoration of road for damage portion due to newly laid different dia DI/UPVC pipe line at different places at Agarhati Mouza within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 362/HSD | 23/02/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.76 | 4.76 | 50 | 1
260 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10506 | Retrofitting | Acceptance cum work order for Additional emergent restoration of road for damage portion due to newly laid different dia DI/UPVC pipe line at different places at Patharghata Laukhali Mouza within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 363/HSD | 23/02/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.76 | 4.76 | 50 | 1
261 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10506 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling near Baba Loknath Mandir, N/H/O Kalu Singh, Subrata Mondal at Rajbari Sundariakhali and other different places at Laukhali village in connection with retrofitting of Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 1336/HSD | 02/08/2022 | 10 | NIKHIL SAMADDAR | 4.52 | 4.51 | 99.73 | 1
262 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10506 | Retrofitting | Acceptance cum work order for Construction of anchor block for resting of 100/150 mm dia DI pipeline at different places within Laukhali Patharghata w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 1147/HSD | 12/07/2022 | 15 | PRITAM MUKHOPADHYAY. | 4.06 | 3.97 | 97.84 | 0
263 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10506 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at different places at Laukhali Patharghata mouza in connection with retrofitting of Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 1335/HSD | 02/08/2022 | 10 | NIKHIL SAMADDAR | 4.5 | 4.48 | 99.51 | 1
264 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10506 | Retrofitting | Formal work order for Laying of DI rising main and DI/UPVC distribution pipe line and Construction of 700 cum capacity 20mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Laukhali water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | 536/BD | 23/02/2022 | 365 | M/S S.S.ENTERPRISE. (SOUTH) | 452.05 | 156.2 | 100 | 100
265 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10506 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Laukhali W/s scheme Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 1569/BD | 01/06/2022 | 90 | M/S S.S.ENTERPRISE. (SOUTH) | 250.04 | 186.86 | 100 | 100
266 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10506 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at different places of Laukhali Mouza within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1169/HSD | 12/07/2022 | 15 | M/S S.S.ENTERPRISE. (SOUTH) | 4.81 | 4.8 | 100 | 1
267 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10506 | Retrofitting | Material Requisition To Resource Division | 156/BD | 18/01/2023 | 0 | Resource Division | 35.12 | 0 | 0 | 0
268 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10506 | Retrofitting | Acceptance cum work order for Construction of 100 cum/hr Iron Removal Plant with blower room & other allied works within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 2024/BD | 18/06/2025 | 150 | FIDERE MARINE SERVICES PVT. LTD. | 38.3 | 0 | 0 | 0
269 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Laukhali Patharghata W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10506 | Retrofitting | Acceptance cum work order for Construction of boundary wall with brick masonry structure at Head Work site (Ph No-1) within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 4433/BD | 10/11/2023 | 90 | MATRI ENTERPRISE | 16.97 | 0 | 0 | 100
270 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10508 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) within command area of Kalinagar (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Hasnabad Sub-Division, PHE. Dte. | 1506/BD | 26/05/2022 | 90 | UMWELT ENGINEER PVT.LTD. | 208.93 | 199.91 | 95.68 | 47
271 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10508 | Retrofitting | Formal work order for Protection work for newly laid UPVC pipe line at different places of Gajalia, Putimari & Ghatihara Mouza in connection with retrofitting of Kalinagar w/s scheme (Z-II), Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1359/BD | 04/05/2023 | 30 | UMWELT ENGINEER PVT.LTD. | 138.59 | 138.51 | 100 | 59
272 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10508 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Ghatihara mouza due to erosion of soil for heavy rain fall during monsoon season within Kalinagar w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 1057/HSD | 31/08/2023 | 10 | M/S RAJPATH CONSTRUCTION. | 0.98 | 0.98 | 100 | 100
273 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10508 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Putimari mouza due to erosion of soil for heavy rain fall during monsoon season within Kalinagar w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 1058/HSD | 31/08/2023 | 10 | M/S RAJPATH CONSTRUCTION. | 0.95 | 0.94 | 100 | 100
274 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10508 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Gazalia mouza due to erosion of soil for heavy rain fall during monsoon season within Kalinagar w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 1059/HSD | 31/08/2023 | 10 | M/S RAJPATH CONSTRUCTION. | 0.95 | 0.95 | 100 | 100
275 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10508 | Retrofitting | Acceptance cum work order for Construction of boundary wall with brick masonry structure at Head Work site (PH No-1) within Kalinagar w/s scheme (Z-II), Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 4436/BD | 10/11/2023 | 90 | M/S SANJAY ADHIKARI | 16.63 | 16.49 | 100 | 81
276 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10508 | Retrofitting | Enhancement of GST for the work providing FHTC for Augmentation of Kalinagar (Zone-II) W/S Scheme | BP-2024-25-78 | 10/07/2024 | 0 | UMWELT ENGINEER PVT.LTD. | 6.76 | 0 | 0 | 0
277 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10508 | Retrofitting | Acceptance Cum work order for Providing Functional Household Tap Connection (FHTC) for left out house holds under the command area of Kalinagar (Z-II) Water Supply Scheme in order to provide Har Ghar Jal Certification, Sandeshkhalli -I Block under Hasnabad Sub-Division, P.H.E.Dte. | 427/BD | 09/02/2024 | 300 | ABDUL ALIM MONDAL. | 55.66 | 36.73 | 88.44 | 90
278 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase , SM/10508 | Retrofitting | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in connection with augmentation of Kalinagar w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 165/HSD | 27/01/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.97 | 0 | 0 | 100
279 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10105 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Bilkanda (Zone-I) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | 1183/NWSD-I | 31/12/2021 | 15 | UMWELT ENGINEER PRIVATE LIMITED | 4.87 | 4.87 | 100 | 1
280 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10105 | Augmentation | Material Requisition To Resource Division | 739/NWSD-I | 13/06/2022 | 0 | Resource Division | 13.93 | 0 | 0 | 0
281 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10105 | Augmentation | Material Requisition To Resource Division | 750/NWSD-I | 14/06/2022 | 0 | Resource Division | 52.13 | 0 | 0 | 0
282 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10105 | Augmentation | Material Requisition To Resource Division | 641/NWSD-I | 20/05/2022 | 0 | Resource Division | 52.13 | 0 | 0 | 0
283 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10105 | Augmentation | Repair and renovation works for 1000 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir, Boundary wall, Pump House at H/W site and PH-II with other allied works at Bilkanda (Z-I) W/S Scheme under North 24 Pgs Water Supply Division- I, P.H.E. Dte. | 1400/NWSD-I | 05/09/2023 | 60 | SUDHAMAY MAJUMDAR | 47.57 | 47.11 | 100 | 100
284 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10105 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House Hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC , Schedule 80/20 mm OD HDPE (PE 100, PN16) pipe with all necessary works within command area of Bilkanda Zone-I Water Supply Scheme under district North 24 Parganas Water Supply Division-I PHE Dte. | 706/ NWSD-I | 07/06/2022 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 679.28 | 676.84 | 100 | 100
285 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10105 | Augmentation | Supply and installation of Display Board to be placeed at BILKANDA ZONE-I, BANDIPUR, BILKANDA ZONE-II, PATULIA and MOHANPUR, Zone-I-B (Telinipara), Zone-IA-II (Chak Kanthalia) pipe water supply scheme for Barrackpore-II Block under North 24 Pgs. Water Supply Division-I, PHE. Dte. | 70/NWSD-I | 10/01/2024 | 30 | BIBHAS PAL | 4.94 | 1.09 | 100 | 100
286 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10105 | Augmentation | Reimbursement of additional GST due to enhancement of rate from 12% to 18% vide Notification No. 03/2022 Central tax rate dt.13/07/2022 for the work of "Laying of distribution pipeline including providing FHTC at Bilkanda Zone-I W/S Scheme under NWSD-I, P.H.E. Dte. Tender No.28/eT/NWSD-I of 2022-23, Work Order No.706/NWSD-I dt.07/06/2022, Enhancement GST Sanction No. PHE/IV/3260/W-698/23 dt.19/10/2023. | 181/PFMS/24-25 | 03/09/2024 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 31.18 | 0 | 0 | 0
287 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10105 | Augmentation | Road restoration due to laying of pipeline of Augmention work at Bilkanda (Zone-I) W/S Scheme in Barrackpore-II Block under Northn24 Pgs W/S Div-I, P.H.E, Dte. | 849/NWSD-I | 03/06/2025 | 30 | A. S. ENTERPRISE | 8.63 | 0 | 0 | 0
288 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10105 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1431/NWSD-I | 18/09/2024 | 7 | IMAGIN | 4.59 | 0 | 0 | 95
289 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10105 | Augmentation | Construction of Godown at Head Work site for Augmentation of Bilkanda (Zone-I) Water Supply Scheme in Bbarrackpore-II Block of North 24 Parganas District within the jurisdiction of N24Pgs. W/S Division-I, P.H.E. Dte. | 104/NWSD-I | 17/01/2025 | 15 | M/S. PHOENIX INFRASTRUCTURE | 7.43 | 7.4 | 100 | 100
290 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda Zone-I Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10105 | Augmentation | Construction of Latrine at Pump House-II and Road Restoration due to laying of pipeline under Augmentation work at Bilkanda-I W/S Scheme in Barrackpore-II Block under North 24 Pgs W/S Division-I, P.H.E. Dte. | 392/NWSD-I | 12/03/2025 | 30 | B. S. ENTERPRISE | 11.73 | 0 | 0 | 100
291 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10109 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Bandipur Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | 1180/NWSD-I | 31/12/2021 | 15 | UMWELT ENGINEER PRIVATE LIMITED | 4.72 | 4.72 | 100 | 1
292 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10109 | Augmentation | Surging of 5 (five) nos existing big dia Tube well for Bandipur W/S Scheme at Barrackpore -II Block under North 24 Pgs.W/S Division-I, P.H.E. Dte. | 891/NWSD-I | 26/07/2022 | 15 | AQUATECH ENGINEER | 3.34 | 2.28 | 100 | 1
293 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10109 | Augmentation | Material Requisition To Resource Division | 1406/NWSD-I | 13/12/2022 | 0 | Resource Division | 15.16 | 0 | 0 | 0
294 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10109 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House Hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC , Schedule 80/20 mm OD HDPE (PE 100, PN16) pipe with all necessary works including proposed Rising Main system within command area of Bandipur Water Supply Scheme under district North 24 Parganas Water Supply Division-I PHE Dte. | 654/NWSD-I | 24/05/2022 | 90 | UMWELT ENGINEER PRIVATE LIMITED | 548.41 | 546.29 | 100 | 70
295 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10109 | Augmentation | Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep tubewell by D.R. Rig method at Bandipur Water Supply Scheme ( H/W site ) within the jurisdiction of North 24 Pgs Water Supply Division- I, P.H.E. Dte. | 876/NWSD-I | 12/07/2023 | 30 | AUXILIARY TUBEWELL DRILLER | 21.83 | 12.81 | 100 | 100
296 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10109 | Augmentation | Material Requisition To Resource Division | 610/NWSD-I | 17/05/2022 | 0 | Resource Division | 35.68 | 0 | 0 | 0
297 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10109 | Augmentation | Material Requisition To Resource Division | 53/NWSD-I | 13/01/2023 | 0 | Resource Division | 15.16 | 0 | 0 | 0
298 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10109 | Augmentation | Repair and renovation works for 700 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir, Boundary wall, Pump House at H/W site and PH-II, III, IV, V with other allied works at Bandipur W/S Scheme under North 24 Pgs Water Supply Division- I, | 1683/NWSD-I | 30/10/2023 | 60 | B. S. ENTERPRISE | 45.68 | 44.68 | 100 | 100
299 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10109 | Augmentation | Supply and installation of Display Board to be placeed at BILKANDA ZONE-I, BANDIPUR, BILKANDA ZONE-II, PATULIA and MOHANPUR, Zone-I-B (Telinipara), Zone-IA-II (Chak Kanthalia) pipe water supply scheme for Barrackpore-II Block under North 24 Pgs. Water Supply Division-I, PHE. Dte. | 70/NWSD-I | 10/01/2024 | 30 | BIBHAS PAL | 4.94 | 0.7 | 100 | 100
300 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10109 | Augmentation | Restoration works of concrete road and others road under Augmentation Scheme of Bandipur W/S Scheme within the jurisdiction of N24Pgs. W/S Division-I, P.H.E. Dte. | 1632/NWSD-I | 12/11/2024 | 15 | BANERJEE ENTERPRISE | 8.76 | 2.24 | 20.94 | 100
301 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10109 | Augmentation | Shinking of 1 no. Tube well 300mm X 200mm Big Dia.Tube well 300 Mtr. Deep by Direct Rotary Rig method using PVC pipe & UPVC deep well screen pipes with ribs etc. Including cost of Materials under command area of Bandipur Water Supply Scheme at Barrackpore-II Block under North 24 Parganas wate supply Division-I, P.H.E. Dte. | 433/NWSD-I | 19/03/2025 | 30 | AUXILIARY TUBEWELL DRILLER | 22.7 | 0 | 0 | 0
302 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10109 | Augmentation | Inter connection with new Tube well at H/W site under Augmentation Scheme of Bandipur within the jurisdiction of N 24 Pgs. W/S Division-I, P.H.E. Dte. | 1631/NWSD-I | 12/11/2024 | 7 | ARUP CONSTRUCTION | 0.37 | 0.37 | 100 | 100
303 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate , SM/10693 | Augmentation | Repairing & renovation of Pump House No. - 1 & 2 of Talsa W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 498/HAB | 02/12/2021 | 30 | TALUKDER & CO. | 2.16 | 0 | 0 | 1
304 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate , SM/10693 | Augmentation | Material Requisition To Resource Division | 3791/BD | 22/12/2022 | 0 | Resource Division | 10.96 | 0 | 0 | 0
305 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate , SM/10693 | Augmentation | Material Requisition To Resource Division | 2516/BD | 25/08/2022 | 0 | Resource Division | 7.71 | 0 | 0 | 0
306 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate , SM/10693 | Augmentation | Special repair & renovation of pump house and other Allied Works for Pump House No - 1 of Talsa W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 926/HAB | 05/11/2024 | 20 | JP CONSTRUCTION & SUPPLIERS. | 2.66 | 0 | 0 | 0
307 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate , SM/10693 | Augmentation | Special repair & renovation of pump house and other Allied Works for Pump House No - 2 of Talsa W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 931/HAB | 05/11/2024 | 20 | M/S SUKANTA ENTERPRISE. | 2.6 | 0 | 0 | 0
308 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate , SM/10693 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Talsa Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 2312/BD | 03/08/2022 | 90 | DEBAPRASAD MONDAL. | 295.79 | 217.73 | 100 | 100
309 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate , SM/10693 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Rep.) under Talsa and adj. mouzas W/S Scheme and Talsa W/S Scheme with Pump House No-I under Chandpur (Block-Hasnabad) W/S Scheme District of 24 Pgs. (N) | 4803/EMD | 09/08/2023 | 30 | M/S S.R. ENTERPRISE | 60.76 | 24.67 | 100 | 80
310 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate , SM/10693 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 250 mm. x 150 mm. dia. 270 mtr deep tube well by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 for Augmentation of Talsa water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | 2781/BD | 11/09/2023 | 60 | M/S K.P.PAL. | 28.99 | 24.49 | 100 | 100
311 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate , SM/10693 | Augmentation | Construction of Service Road (35 Mtr. Length X 2 Mtr. Width) for Pump House No:1 of Talsa Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 698/HAB | 26/07/2024 | 10 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 2.14 | 0 | 0 | 100
312 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate , SM/10693 | Augmentation | Construction of Service Road (20 Mtr. Length X 2 Mtr. Width) for Pump House No:2 of Talsa Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 701/HAB | 29/07/2024 | 10 | DEBANJAN GHOSH. | 1.22 | 0 | 0 | 100
313 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate , SM/10693 | Augmentation | Acceptance cum work order for Repairing of Boundary Wall for Pump House No - 1 of Talsa water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | 3062/BD | 25/10/2024 | 30 | M/S SANKAR ENTERPRISE. | 6.62 | 0 | 0 | 100
314 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate , SM/10693 | Augmentation | Acceptance cum work order for Relaying of UPVC, pipe,re- fitting of FHTC, along with allied work at Dakshin Talsa of Talsa mouja water supply scheme under JJM programme due to damage of pipe line for construction of bituminious road and concrete drain within the Jurisdiction of Habra Sub-Division under Barasat Division,PHE Dte. | 398/BD | 05/02/2025 | 30 | TALUKDER & CO. | 7.98 | 0 | 0 | 100
315 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC , SM/10587 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Chandpara Water Supply Scheme in Gaighata Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 144/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.05 | 0 | 0 | 1
316 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC , SM/10587 | Augmentation | Repairing & Renovation 2(Two) nos of Pump House and allied works of Chandpara water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 537/Bon | 03/11/2021 | 21 | SAMBHU RAY CHOWDHURY. | 2.52 | 2.47 | 98.01 | 1
317 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC , SM/10587 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Chandapara Water Supply Scheme in Gaighata Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 143/BON | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.05 | 4.04 | 100 | 1
318 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC , SM/10587 | Augmentation | Repairing & Renovation of 01No. Pump House and allied works at Chandpara water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 634/BON | 31/12/2021 | 21 | SAMBHU RAY CHOWDHURY. | 1.26 | 1.14 | 100 | 1
319 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC , SM/10587 | Augmentation | Material Requisition To Resource Division | 3657/BD | 13/12/2022 | 0 | Resource Division | 31.17 | 0 | 0 | 0
320 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC , SM/10587 | Augmentation | Material Requisition To Resource Division | 1360/BD | 13/05/2022 | 0 | Resource Division | 11.96 | 0 | 0 | 0
321 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC , SM/10587 | Augmentation | Renovation and repairing of Boundary wall and Construction of Approach Road at 2nd Tube Well site under Augmentation of Chandpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 841/Bon | 01/11/2023 | 23 | M/S SAYAN ENTERPRISE. | 4.59 | 0 | 0 | 0
322 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC , SM/10587 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chandpara water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte | 2699/BD | 04/09/2023 | 30 | NADIA TUBEWELLS | 16.16 | 10.6 | 100 | 100
323 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC , SM/10587 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chandpara Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | 2937/BD | 27/09/2023 | 30 | JOY GURU ENTERPRISE | 16.12 | 14.88 | 100 | 100
324 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC , SM/10587 | Augmentation | Acceptance cum work order for Renovation & repairing of Boundary wall at Head work site for Augmentation of Chandpara water Supply scheme, Gaighata Block within jurisdiction of Bongaon Sub-Division, P.H.E. Dte. | 4412/BD | 10/11/2023 | 60 | BHABANI ENTERPRISE. | 13.44 | 13.36 | 100 | 100
325 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC , SM/10587 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at 3rd Tube Well site and Construction of Approach Road at 3rd Tube Well site and Head work site under Augmentation of Chandpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 41/BD | 04/01/2024 | 23 | ROY ENGINEERS. | 7.4 | 1.96 | 20.94 | 100
326 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC , SM/10587 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Chandpara Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 3629/BD | 12/12/2022 | 1170 | MAHAVIR PUMPS MANUFACTURING PVT.LTD. | 525.18 | 421.34 | 80.23 | 92
327 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC , SM/10587 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Rep) under Chikanpara W/S Scheme and Pump House No.I, II and III under Chandpara W/S Scheme District of 24 Pgs. (N) | 4795/EMD | 09/08/2023 | 754 | DAS ENTERPRISE (M) | 78.21 | 7.75 | 19.81 | 60
328 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC , SM/10587 | Augmentation | Formal work order for Dismantling and Cement Concreting of existing Cement Concrete Road for laying rest part of UPVC pipes within command area and Drum Sheet Walling for supporting other UPVC Pipes along the NH 35 for Augmentation work at Chandpara W/S Scheme under Gaighata block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 808/BD | 12/03/2024 | 720 | MAHAVIR PUMPS MANUFACTURING PVT.LTD. | 112.22 | 22.51 | 20.06 | 60
329 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC , SM/10587 | Augmentation | Acceptance cum work order for Improvement of Iron Elimination Plant and other related allied works and Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Chandpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 63/BD | 05/01/2024 | 390 | SAMBHU RAY CHOWDHURY. | 6.02 | 6 | 100 | 100
330 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC , SM/10587 | Augmentation | Acceptance cum work order for MS Pipeline Crossing by adopting Mini HDD for Road Crossing near Chandpara Bazar on NH-35 Road including the cost of carrier pipe, all labours, materials tools and cleaning of site etc. complete in all respect for Augmentation of Chandpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 3184/BD | 18/11/2024 | 210 | ATINDRA CONSTRUCTION PRIVATE LIMITED | 14.03 | 0 | 0 | 100
331 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC , SM/10587 | Augmentation | Acceptance cum work order for MS Pipeline Crossing by adopting Mini HDD for Road Crossing near Chandpara Bazar on Chandpara-Thakurnagar Road including the cost of carrier pipe, all labours, materials tools and cleaning of site etc. complete in all respect for Augmentation of Chandpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 3183/BD | 18/11/2024 | 210 | ATINDRA CONSTRUCTION PRIVATE LIMITED | 11.91 | 0 | 0 | 100
332 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC , SM/10587 | Augmentation | Repairing and renovation of High Lift Pump House under Augmentation of Chandpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1395/Bon | 27/11/2024 | 20 | SAMBHU RAY CHOWDHURY. | 1.66 | 1.64 | 100 | 100
333 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) , SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Bilkanda Zone-I Water Supply Scheme of Barrackpur-II Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Bilkanda Zone-I W/S Scheme. | 451/NWSD-I | 10/06/2020 | 3 | RAKESH ENTERPRISE | 0.97 | 0.95 | 98.21 | 100
334 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) , SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMHPAN on 20.05.2020 of Auldanga Water Supply Scheme of Bagdah Block under North 24 Parganas Water Supply Division-I P.H.E. Dte. Location : Within Auldanga W/S Scheme. | 438/NWSD-I | 08/06/2020 | 3 | ONKAR ENTERPRISE | 4.78 | 4.78 | 100 | 100
335 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) , SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMHPAN on 20.05.2020 of Ichhlampur Zone-I Water Supply Scheme of Bongaon Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location : Within Ichhlampur Zone-I W/S Scheme. | 406/NWSD-I | 27/05/2020 | 3 | OM CONSTRUCTION | 2.77 | 2.76 | 99.56 | 100
336 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) , SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Palla Water Supply Scheme of Bongaon Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Palla W/S Scheme. | 427/NWSD-I | 05/06/2020 | 3 | M/S. R. M. CONSTRUCTION | 3.13 | 3.13 | 100 | 100
337 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) , SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Bilkanda Zone-II Water Supply Scheme of Barrackpur-II Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Bilkanda Zone-II W/S Scheme. | 441/NWSD-I | 08/06/2020 | 3 | B. S. ENTERPRISE | 1.97 | 1.97 | 99.89 | 100
338 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) , SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Barakpur Water Supply Scheme of Bongaon Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Barakpur W/S Scheme. | 440/NWSD-I | 08/06/2020 | 3 | OM CONSTRUCTION | 3.06 | 3.05 | 99.75 | 100
339 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) , SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Ichhlampur Zone-II Water Supply Scheme of Bongaon Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Ichhlampur Zone-II W/S Scheme. | 402/NWSD-I | 27/05/2020 | 3 | OM CONSTRUCTION | 3.12 | 3.1 | 99.62 | 100
340 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) , SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Paikpara Water Supply Scheme of Bongaon Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Paikpara W/S Scheme. | 405/NWSD-I | 27/05/2020 | 3 | SHAMALI ENTERPRISE | 1.82 | 1.82 | 100 | 100
341 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) , SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMHPAN on 20.05.2020 of Bagangram Zone-I Water Supply Scheme of Bongaon Block under North 24 Parganas Water Supply Division-I P.H.E. Dte. | 428/ NWSD-I | 06/06/2020 | 3 | GHOSH CONSTRUCTION | 2.9 | 2.9 | 100 | 100
342 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) , SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Santoshpur Zone-II Water Supply Scheme of Bongaon Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Santoshpur Zone-II W/S Scheme. | 404/NWSD-I | 27/05/2020 | 3 | B. S. ENTERPRISE | 2.25 | 2.25 | 99.83 | 100
343 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) , SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Boyra Water Supply Scheme of Bagdah Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Boyra W/S Scheme. | 437/NWSD-I | 08/06/2020 | 3 | B. S. ENTERPRISE | 1.78 | 1.78 | 100 | 100
344 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) , SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Khamarkalla Water Supply Scheme of Bongaon Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Khamarkalla W/S Scheme. | 413/NWSD-I | 29/05/2020 | 3 | B. S. ENTERPRISE | 3.01 | 3.01 | 100 | 100
345 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) , SM/10757 | Disaster | Suppply of drinking water by TATA 107/207/Mechanized van with tank from nearest source to different places of Khejurdanga, Keyadanga, Ajijnagore, Alipur & Uttar Kolsur under Deganga block from 22/05/2020 to 29/05/2020 due to 'AMPHAN' under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Deganga Block | 397/NWSD-.I | 27/05/2020 | 3 | SHAMALI ENTERPRISE | 1.79 | 1.78 | 99.72 | 100
346 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) , SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Bandipur Water Supply Scheme of Barrackpur-II Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. | 450/NWSD-I | 10/06/2020 | 3 | M/S SAIN ENTERPRISE | 2.25 | 2.24 | 99.85 | 100
347 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) , SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Teghari Water Supply Scheme of Barrackpur-II Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Teghari W/S Scheme. | 442/NWSD-1 | 08/06/2020 | 3 | A.K.C. SUPPLY & CONSTRUCTION | 2 | 1.98 | 99.14 | 100
348 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) , SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Bandipur- Patulia (Rej) Water Supply Scheme of Barrackpur-II Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Bandipur- Patulia (Rej) W/S Scheme. | 463/NWSD-1 | 15/06/2020 | 3 | A.K.C. SUPPLY & CONSTRUCTION | 2.05 | 2.04 | 99.52 | 100
349 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC , SM/10565 | Augmentation | Work order for repairing & renovation of Pump House and allied works of Ichhapur Water Supply Scheme. | 540/ BON | 03/11/2021 | 21 | ROY ENGINEERS. | 2.52 | 2.48 | 100 | 1
350 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC , SM/10565 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Ichhapur water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | 2698/BD | 04/09/2023 | 30 | NADIA TUBEWELLS | 16.16 | 13.1 | 100 | 100
351 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC , SM/10565 | Augmentation | Laying of badly damaged distribution pipe line and others allied works for making Panchayet Drain at Ichhapur water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 329/Bon | 03/05/2023 | 12 | ROY ENGINEERS. | 0.51 | 0.51 | 100 | 100
352 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC , SM/10565 | Augmentation | Material Requisition To Resource Division | 1363/BD | 13/05/2022 | 0 | Resource Division | 10.74 | 0 | 0 | 0
353 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC , SM/10565 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Rep) under Shimulpur W/S Scheme and Pump House No-I and II (Rep.) under Ichapur W/S Scheme and Kalupur W/S Scheme District of 24 Pgs. (N) | 4798/EMD | 09/08/2023 | 30 | ORIENTAL ENGINEERING CO. | 91.05 | 19.75 | 75.93 | 80
354 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC , SM/10565 | Augmentation | Renovation and repairing of Boundary wall and Construction of Approach Road at 2nd Tube Well site under Augmentation of Ichhapur Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 978/Bon | 27/12/2023 | 30 | SAMBHU RAY CHOWDHURY. | 3.63 | 0 | 0 | 0
355 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC , SM/10565 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Ichhapur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 3768/BD | 20/12/2022 | 90 | BALAJI UDDYOG | 468.29 | 467.86 | 100 | 100
356 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC , SM/10565 | Augmentation | Acceptance cum work order for Laying of badly damaged UPVC Distribution Pipe Lines due to laying of Secondary Rising Main of Habra-Gaighata Project from Amkola More to Kulipara More along with Road Restoration and other allied works at ICCHAPUR Water Supply Scheme within the jurisdiction of Bongaon SubDivision, under Barasat Division P.H.E.Dte. | 85/BD | 08/01/2024 | 30 | NEW MILLENNIUM ENGG'S CO-OP-SO-LTD. | 19.15 | 19.14 | 100 | 100
357 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC , SM/10565 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Head Work site for Augmentation of Ichhapur Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | 1770/BD | 29/05/2025 | 240 | SONALI CONSTRUCTION | 21.51 | 0 | 0 | 0
358 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC , SM/10565 | Augmentation | Acceptance cum work order for Special Repairing work in connection with augmentation work at total command area of Ichhapur Water Supply Scheme, to repair the damaged pipeline due to road widening and drain construction and also to convert the mouzas into Swajal Gram within Bongaon Sub Division, under Barasat Division, P.H.E.Dte. | 1905/BD | 05/06/2025 | 120 | ROY ENGINEERS. | 16.43 | 0 | 0 | 0
359 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC , SM/10565 | Augmentation | Construction of Latrine at 2nd Pump House site and Renovation of PH No - 1 & 2 for Ichhapur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 653/Bon | 22/05/2025 | 45 | ROY ENGINEERS. | 3.3 | 0 | 0 | 0
360 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC , SM/10565 | Augmentation | Acceptance cum work order for Special Repair & Maintenance work inconnection with augmentation work at Ichhapur W/S Scheme under Gaighata block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | 2596/BD | 06/09/2024 | 12 | ROY ENGINEERS. | 13.24 | 3.5 | 20.94 | 100
361 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC , SM/10565 | Augmentation | Additional laying of UPVC pipe to connect every house hold connection with Augmentation work at Ichhapur W/S Scheme under Gaighata block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. (Part-A) | 1322/Bon | 12/11/2024 | 100 | UPWARDS ENGINEERING PRIVATE LIMITED. | 4.97 | 4.96 | 100 | 100
362 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ichhapur to accommodate FHTC , SM/10565 | Augmentation | Additional laying of UPVC pipe to connect every house hold connection with Augmentation work at Ichhapur W/S Scheme under Gaighata block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. (Part-B) | 1385/Bon | 26/11/2024 | 100 | RAJ ENTERPRISE. | 4.6 | 0 | 0 | 100
363 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC , SM/10584 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Champali water supply scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 2400/BD | 17/08/2022 | 90 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 129.78 | 128.23 | 54.6 | 1
364 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC , SM/10584 | Augmentation | Material Requisition To Resource Division | 2474/BD | 24/08/2022 | 0 | Resource Division | 2.46 | 0 | 0 | 0
365 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC , SM/10584 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Champali W/S Scheme and Nurpur W/S SchemeDistrict of 24 Pgs. (N) NIET No.- 32 of EE/EMD of 2022-23 (Sl. No.- 04) | 1004/EMD | 09/03/2023 | 30 | PADMA ENGINEERING CO. | 53 | 26.52 | 100.07 | 60
366 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC , SM/10584 | Augmentation | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Champali water supply scheme, Minakhan Block under hasnabad Sub-Division, P.H.E. Dte. | 4179/BD | 30/10/2023 | 365 | M/S BISWAS BROTHERS. | 114.29 | 0 | 0 | 0
367 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC , SM/10584 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Champali w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 2436/BD | 22/08/2022 | 30 | AUXILIARY TUBE WELL DRILLERS. | 44.41 | 37.78 | 100 | 100
368 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC , SM/10584 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation for Champali water supply scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 279/HSD | 06/03/2024 | 10 | SARKAR ENTERPRISE | 0.6 | 0 | 0 | 100
369 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC , SM/10584 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Champali w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 237/HSD | 30/01/2025 | 10 | SARKAR ENTERPRISE | 0.81 | 0 | 0 | 100
370 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC , SM/10584 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation of Champali water supply scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 476/HSD | 28/02/2025 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 0.72 | 0 | 0 | 100
371 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC , SM/10584 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection with Augmentation of Champali water supply scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 313/HSD | 04/02/2025 | 10 | SARKAR ENTERPRISE | 0.72 | 0 | 0 | 100
372 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC , SM/10392 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Fakiratakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 2236/BD | 28/07/2022 | 30 | M/S K.P.PAL. | 44.41 | 15.19 | 34.21 | 1
373 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC , SM/10392 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Fakirtakia W/S Scheme District of North 24 Pgs. NIET No.- 12 of EE/EMD of 2022-23 (Sl No.-02) | 5089/EMD | 04/11/2022 | 30 | INDIA ENTERPRISE | 11.29 | 7.97 | 70.57 | 0
374 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC , SM/10392 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 150 mm dia DI distribution main pipeline over existing concrete wall beside Basanti Highway at near Chotto Ajgora in connection with Augmentation of Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 783/HSD | 13/07/2023 | 10 | NEW LIFE CONSTRUCTION. | 0.94 | 0.94 | 100 | 29
375 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC , SM/10392 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 100 mm dia DI distribution main pipeline over existing concrete wall beside Basanti Highway at near Baro Ajgora in connection with Augmentation of Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 778/HSD | 13/07/2023 | 10 | NEW LIFE CONSTRUCTION. | 0.89 | 0.89 | 100 | 29
376 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC , SM/10392 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Fakirtakia water supply scheme, Sandeshkhali-I Block within Hasnabad Sub-Division, under Barasat Division, PHE Dte. | 2674/BD | 08/09/2022 | 90 | PROJECT INDIA | 228.86 | 223.88 | 100 | 1
377 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC , SM/10392 | Augmentation | Acceptance cum work order for Supply, fitting & fixing of sluice valve with valve chember at HW & 2nd TW site in connection with augmentation of Fakitakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1414/HSD | 06/11/2023 | 7 | BADAL GHOSH. | 0.79 | 0.79 | 100 | 100
378 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC , SM/10392 | Augmentation | Material Requisition To Resource Division | 2578/BD | 31/08/2022 | 0 | Resource Division | 6.15 | 0 | 0 | 0
379 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC , SM/10392 | Augmentation | Material Requisition To Resource Division | 520/BD | 20/02/2023 | 0 | Resource Division | 14.66 | 0 | 0 | 0
380 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC , SM/10392 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 150 mm dia DI distribution main pipeline over existing concrete wall beside Basanti Highway at near Bitpole in connection with Augmentation of Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 775/HSD | 13/07/2023 | 10 | NEW LIFE CONSTRUCTION. | 0.94 | 0.94 | 100 | 100
381 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC , SM/10392 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation for Fakirtakia water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 257/HSD | 06/03/2024 | 10 | BADAL GHOSH. | 0.59 | 0.59 | 100 | 100
382 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC , SM/10392 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 100 mm dia DI distribution main pipeline over existing concrete wall beside Basanti Highway at near PH No- 1 in connection with Augmentation of Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 789/HSD | 13/07/2023 | 10 | NEW LIFE CONSTRUCTION. | 0.98 | 0.98 | 100 | 31
383 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC , SM/10392 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection for Augmentation of Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 1604/BD | 19/05/2025 | 30 | M/S SAIN ENTERPRISE. | 10.62 | 0 | 0 | 0
384 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC , SM/10392 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I under Fakirtakia W/S Scheme District of North 24 Pgs. . NIT No.-12 of EE/EMD of 2022-23 (Sl. No.-01) | 5088/EMD | 04/11/2022 | 879 | ESENCE ENGINEERING CONCERN | 11.28 | 9.28 | 82.23 | 70
385 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC , SM/10392 | Augmentation | Formal work order for construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Fakirtakia water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | 1722/BD | 08/06/2023 | 365 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 153.55 | 153.53 | 100 | 72
386 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC , SM/10392 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) for left out house holds under the command area of Fakirtakia water supply scheme in order to provide Har Ghar Jal Certification, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 372/BD | 06/02/2024 | 329 | SARKAR ENTERPRISE & CO. | 47.73 | 38.36 | 86.06 | 100
387 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC , SM/10392 | Augmentation | Acceptance cum work order for Additional Laying of UPVC distribution pipe line, Repairing of existing FHTC & other allied works in connection with Augmentation of Fakirtakia w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 390/BD | 05/02/2025 | 60 | SARKAR ENTERPRISE & CO. | 29.16 | 0 | 0 | 100
388 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Fakirtakia to accommodate FHTC , SM/10392 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in connection with augmentation of Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 482/HSD | 28/02/2025 | 10 | BADAL GHOSH. | 0.96 | 0 | 0 | 100
389 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Patua to accommodate FHTC , SM/11656 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Patua Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 444/ BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.16 | 4.16 | 50 | 1
390 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Patua to accommodate FHTC , SM/11656 | Augmentation | Material Requisition To Resource Division | 601/BD | 23/02/2023 | 0 | Resource Division | 6.94 | 0 | 0 | 0
391 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Patua to accommodate FHTC , SM/11656 | Augmentation | Material Requisition To Resource Division | 859/BD | 20/03/2023 | 0 | Resource Division | 48.85 | 0 | 0 | 0
392 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Patua to accommodate FHTC , SM/11656 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Replacement) under Bharatpur W/S Scheme, Patua W/S Scheme (P/H-I & II) & Chaital W/S Scheme (P/H -I & II) District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 04) | 31/EMD | 03/01/2023 | 819 | M/S P.P. ELECTRICALS | 74.67 | 15.43 | 59.2 | 73
393 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Patua to accommodate FHTC , SM/11656 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Patua Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, PHE Dte. | 3549/BD | 06/12/2022 | 1054 | SUBHASH BOSE. | 326.66 | 224.76 | 68.8 | 27
394 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Patua to accommodate FHTC , SM/11656 | Augmentation | Providing outdoor illumination arrangement at P.H. No. I under Patua W/S Scheme under EMSD-I, P.H.E.Dte. Dist.- 24PGS(N). | 456/EMSD-I | 08/04/2025 | 53 | C.N. ENTERPRISE | 1.36 | 0 | 0 | 100
395 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance Cum Work Order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 1096/BD | 06/04/2023 | 30 | MONDAL & CO. (BASIRHAT). | 62.05 | 47.57 | 76.66 | 0
396 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for Providing Functional tap connection at Dk Durgamandop FP School, DTD Sahid Smriti Bidyalaya & Durgamandop Sardar para High School within the command area of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1053/HSD | 31/08/2023 | 7 | M/S RAJPATH CONSTRUCTION. | 0.69 | 0 | 0 | 0
397 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Durgamandop water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | 2401/BD | 17/08/2022 | 90 | MONDAL & CO. (BASIRHAT). | 287.51 | 266.78 | 100 | 1
398 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (replacement) under Durga-Mandap W/S Scheme District of North 24 Pgs. Tender No.- 08 (Sl. No.-02) of EE/EMD of 2022-23 | 3383 /EMD | 14/08/2022 | 30 | C.M.S. ENGINEERING CONCERN. | 11.34 | 10.36 | 100 | 45
399 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 1044/HSD | 31/08/2023 | 10 | ANKUSH CONSTRUCTION & CO. | 0.93 | 0.93 | 100 | 100
400 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 1043/HSD | 31/08/2023 | 10 | ANKUSH CONSTRUCTION & CO. | 0.9 | 0.9 | 100 | 100
401 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for Protection works in different places for protection of different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile for Augmention of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 2652/BD | 01/09/2023 | 30 | MONDAL & CO. (BASIRHAT). | 56.83 | 56.73 | 100 | 84
402 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for Supply, fitting & fixing of sluice valve with valve chember at HW & 2nd TW site in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1415/HSD | 06/11/2023 | 7 | SARKAR ENTERPRISE | 0.83 | 0.83 | 100 | 100
403 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Material Requisition To Resource Division | 2471/BD | 24/08/2022 | 0 | Resource Division | 7.56 | 0 | 0 | 0
404 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (replacement) under Durga-Mandap W/S Scheme District of North 24 Pgs. Tender No.- 08 (Sl. No.-01) of EE/EMD of 2022-23 | 3382EMD | 09/09/2022 | 30 | BOSE & CHATTERJEE INDUSTRIES | 11.36 | 10.35 | 91.07 | 70
405 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Durgamandop water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 276/HSD | 06/03/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.97 | 0.97 | 100 | 83
406 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Durgamandop Mouza within Durgamandop w/s scheme , Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 888/HSD | 07/08/2024 | 10 | SARKAR ENTERPRISE & CO. | 0.94 | 0.93 | 100 | 100
407 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Formal work order for construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Durgamandop water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, P.H.E. Dte. | 4182/BD | 30/10/2023 | 732 | DEBASIS SAMADDAR | 150.76 | 83.99 | 55.71 | 60
408 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for construction of additional 1 no. switch room cum chlorine room (5.40x3.60) with sanitary and water supply arrangement including plinth protection for augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 110/BD | 09/01/2025 | 75 | MD.SALIM GAZI. | 11.68 | 0 | 0 | 0
409 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Durgamandop w/s scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | 1753/BD | 28/05/2025 | 60 | MONDAL & CO. (BASIRHAT). | 251.97 | 0 | 0 | 0
410 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Ghat para in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte | 307/HSD | 04/02/2025 | 10 | SARKAR ENTERPRISE & CO. | 0.98 | 0 | 0 | 100
411 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places at near Bairagi para at Durgamandop mouza in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 338/HSD | 06/02/2025 | 10 | RATAN SARKAR. | 0.96 | 0 | 0 | 100
412 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places at near Ghat para at Durgamandop mouza in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 247/HSD | 30/01/2025 | 10 | SARKAR ENTERPRISE & CO. | 0.97 | 0 | 0 | 100
413 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for Repairing FHTC with pipeline at Sluice gate para with laying of 63 mm dia UPVC pipe line in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 941/HSD | 29/05/2025 | 10 | SARKAR ENTERPRISE & CO. | 0.96 | 0 | 0 | 100
414 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Char para in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte | 256/HSD | 30/01/2025 | 10 | SARKAR ENTERPRISE & CO. | 0.96 | 0 | 0 | 100
415 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for Repairing FHTC with pipeline at Halder para with laying of 63 mm dia UPVC pipe line in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 1007/HSD | 04/06/2025 | 10 | SARKAR ENTERPRISE & CO. | 0.96 | 0 | 0 | 100
416 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Singh para in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte | 380/HSD | 10/02/2025 | 10 | SARKAR ENTERPRISE & CO. | 0.96 | 0 | 0 | 100
417 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places at near Adhikary para at Durgamandop mouza in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 246/HSD | 30/01/2025 | 10 | SARKAR ENTERPRISE & CO. | 0.96 | 0 | 0 | 100
418 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Colony para in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 182/HSD | 27/01/2025 | 10 | SARKAR ENTERPRISE & CO. | 0.94 | 0 | 0 | 100
419 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Parul para in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte | 306/HSD | 04/02/2025 | 10 | SARKAR ENTERPRISE & CO. | 0.98 | 0 | 0 | 100
420 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgamandap , SM/10370 | Augmentation | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places at near Char para at Durgamandop mouza in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte | 1483/HSD | 14/07/2025 | 10 | SARKAR ENTERPRISE & CO. | 0.97 | 0 | 0 | 100
421 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Debipur to accommodate FHTC , SM/11703 | Augmentation | Construction of pathway & Land development at H/W site of Dakshin Debipur Water Supply Scheme under Basirhat-Il Block under Basirhat Sub-Division, P.H.E. Dte. | 380/BHTSD | 17/03/2022 | 20 | M/S MITRA CONSTRUCTION. | 3.27 | 3.17 | 50 | 1
422 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Debipur to accommodate FHTC , SM/11703 | Augmentation | Route Survey, Design Drawing & DPR Preparation for DAKSHIN DEBIPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 312/ BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.87 | 2.87 | 50 | 1
423 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Debipur to accommodate FHTC , SM/11703 | Augmentation | Material Requisition To Resource Division | 3815/BD | 23/12/2022 | 0 | Resource Division | 2.38 | 0 | 0 | 0
424 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Debipur to accommodate FHTC , SM/11703 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Dakshin Debipur water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | 3373/BD | 18/11/2022 | 90 | CHANCHAL ENTERPRISE & CO. | 212.57 | 212.53 | 100 | 85
425 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Debipur to accommodate FHTC , SM/11703 | Augmentation | Material Requisition To Resource Division | 2306/BD | 03/08/2022 | 0 | Resource Division | 2.3 | 0 | 0 | 0
426 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dakshin Debipur to accommodate FHTC , SM/11703 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Replacement) under Dakshin Debipur W/S Scheme District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 06) | 33/EMD | 03/01/2023 | 30 | JAL PRAVAHIKA PVT. LTD. | 26.07 | 0 | 0 | 60
427 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Debipur to accommodate FHTC , SM/11703 | Augmentation | Acceptance cum work order for Providing new FHTC (Functional Household Tap Connection) by Augmentation and relaying of rising main, distribution UPVC pipe line and repairing of existing FHTC connection which damaged due to construction of drain by local Panchayet from Pump house I to Pump house II of Dakshin Debipur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | 3294/BD | 26/11/2024 | 210 | ROHAN MONDAL. | 57.65 | 0 | 0 | 80
428 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-C (Pasardanga) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11971 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-VIII/C (Pasardanga) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 430/NWSD-I | 01/04/2022 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.17 | 4.17 | 100 | 1
429 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-C (Pasardanga) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11971 | Augmentation | Material Requisition To Resource Division | 482/NWSD-I | 26/04/2023 | 0 | Resource Division | 45.06 | 0 | 0 | 0
430 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-C (Pasardanga) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11971 | Augmentation | Material Requisition To Resource Division | 1714/NWSD-I | 26/11/2024 | 0 | Resource Division | 10.47 | 0 | 0 | 0
431 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-C (Pasardanga) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11971 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 217.23 | 30.76 | 2
432 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC , SM/11605 | Augmentation | Acceptance cum work order for construction of CWR at Sangrampur W/S scheme under Basirhat Sub-Division, P.H.E. Dte. under Barasat Division, PHE Dte. | 333/BD | 02/02/2022 | 45 | MD AMIRUL MOLLA. | 5.2 | 4.49 | 100 | 1
433 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC , SM/11605 | Augmentation | Route Survey, Design Drawing & DPR Preparation for SANGRAMPUR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | 195/BHT SD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 100 | 1
434 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC , SM/11605 | Augmentation | Material Requisition To Resource Division | 3811/BD | 23/12/2022 | 0 | Resource Division | 83.52 | 0 | 0 | 0
435 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC , SM/11605 | Augmentation | New Service Connectio for Sangrampur W/S Scheme | 96/EMD | 29/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.46 | 0 | 0 | 0
436 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC , SM/11605 | Augmentation | New service connection charge for Sangrampur |  | 14/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.46 | 0 | 0 | 0
437 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC , SM/11605 | Augmentation | Supply & Installation of Automatically Controlled Diaphragm type Chlorinator at PH-H/L under Sangrampur (AIRP) W/S Scheme under Eastern Mechanical Sub-Division-I, PHE Dte. Dist. 24 Pgs. (N). | 1329/EMSD-I | 31/05/2023 | 20 | T.N. BANERJEE | 2.99 | 0 | 0 | 0
438 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC , SM/11605 | Augmentation | Providing outdoor Illumination arrangement at P.H. - High Lift under Sangrampur W/S Scheme, Dist 24pgs(N). | 1328/EMSD-I | 31/05/2023 | 15 | DAS ENTERPRISE (BARANAGAR) | 2.21 | 2.18 | 100 | 100
439 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC , SM/11605 | Augmentation | Material Requisition To Resource Division | 1101/BD | 06/04/2023 | 0 | Resource Division | 92.65 | 0 | 0 | 0
440 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC , SM/11605 | Augmentation | Material Requisition To Resource Division | 1659/BD | 05/06/2023 | 0 | Resource Division | 10.04 | 0 | 0 | 0
441 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC , SM/11605 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejuvenation Tube Well in connection to Accommodate FHTC at Pump House No.-II under Sangrampur ground water based water supply scheme under Block_ Basirhat-I Dist. - 24 PARAGANAS (N) under EMD, PHE Dte. (SM/11605) | 2691/EMD | 20/11/2024 | 30 | D.S. ENTERPRISE | 10.54 | 0 | 0 | 0
442 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC , SM/11605 | Augmentation | Formal work order for Laying of DI/UPVC distribution system pipeline and Providing FHTC (Functional Household Tap Connection)for augmentation of Sangrampur water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | 3196/BD | 01/11/2022 | 90 | H.I.ENTERPRISE. | 654.07 | 647.44 | 100 | 83
443 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC , SM/11605 | Augmentation | Enhancement of GST for providing Functional Household Tap Connection (FHTC) in connection with JJM and Jal Swapna Programme within command area of Sangrampur WS Scheme | BP-02024-25-262 | 12/09/2024 | 0 | H.I.ENTERPRISE. | 34.82 | 0 | 0 | 0
444 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC , SM/11605 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Sangrampur Water Supply Scheme in Basirhat - I Block of Basirhat Sub- Division under Barasat Division, PHE Dte. 2nd Call. | 195/BD | 16/01/2025 | 30 | JESMINE ENTERPRISE. | 21.72 | 0 | 0 | 0
445 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC , SM/11605 | Augmentation | Acceptance cum work order for Construction of Boundary Wall at the Head Work site of Sangrampur Water Supply Scheme under Basirhat Sub-Division within Barasat Division, P.H.E. Dte. | 59/BD | 07/01/2025 | 210 | IKBAL HOSSAIN | 18.27 | 0 | 0 | 40
446 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC , SM/11605 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Basirhat-I Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - B) | 147/BHTSD | 29/01/2025 | 20 | S.M.TRADERS. | 0.88 | 0 | 0 | 90
447 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC , SM/11530 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Mathurapur W/S Scheme District of 24 Pgs. (N). (SM/11530) NIET No. 19 of EE/EMD of 2022-23 (Sl. No. - 13) | 6442/EMD | 25/11/2022 | 30 | TRIO CONCERN | 13.02 | 11.73 | 90.15 | 0
448 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC , SM/11530 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Replacement) under Mathurapur W/S Scheme District of 24 Pgs. (N). (SM/11530) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 14) | 6388/EMD | 24/11/2022 | 30 | POLYCON ENGINEERS | 13.04 | 11.63 | 89.18 | 0
449 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC , SM/11530 | Augmentation | Supply & delivery of Change over Switch at different pump houses (Atapur P.H. No. II, Mathurapur P.H. No. I & II, Pipha P.H. No. I, Rejendrapur P.H. No. I, Fakirtakia P.H. No. I and Paltadanga P.H. No. I) related to JJM Work, Dist. 24 Pgs. (N). | 1508/EMSD-I | 21/06/2023 | 10 | BISALAXMI ENTERPRISE | 1.33 | 0 | 0 | 0
450 | NORTH 24 PARGANAS | Central Drilling | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC , SM/11530 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Mathurapur W/S Scheme (TW-I), Barasat-II Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | 1650/CDD | 17/10/2023 | 30 | DEV AND COMPANY | 22.01 | 0 | 0 | 0
451 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC , SM/11530 | Augmentation | Material Requisition To Resource Division | 496/BD | 17/02/2023 | 0 | Resource Division | 29.48 | 0 | 0 | 0
452 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC , SM/11530 | Augmentation | Material Requisition To Resource Division | 4419/BD | 10/11/2023 | 0 | Resource Division | 9.24 | 0 | 0 | 0
453 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC , SM/11530 | Augmentation | Special repairing of rising mains pipe lines at Mathurapur water supply scheme under Basirhat Sub-Division under Barasat Division PHE Dte. | 1030/BHTSD | 28/06/2024 | 7 | ANKUSH CONSTRUCTION & CO. | 0.9 | 0 | 0 | 0
454 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mathurapur to accommodate FHTC , SM/11530 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Mathurapur Water Supply Scheme in Basirhat-II Block of North 24 Parganas District under Barasat Division, PHE Dte. | 3490/BD | 02/12/2022 | 90 | M/S DATTA ENTERPRISE. | 325.16 | 285.78 | 100 | 76
455 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC , SM/11628 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Replacement) under Raghunathpur W/S Scheme District of 24 Pgs. (N). NIET No. 19 of EE/EMD of 2022-2023 (Sl. No. 19) | 6771/EMD | 29/11/2023 | 30 | H.K. DAS & CO. | 13 | 0 | 0 | 0
456 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC , SM/11628 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Raghunathpur W/S Scheme District of 24 Pgs. (N). (SM/11628) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 18) | 6392/EMD | 24/11/2022 | 30 | DAS ENTERPRISE | 13.02 | 11.34 | 87.14 | 1
457 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC , SM/11628 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Replacement) under Raghunathpur W/S Scheme District of 24 Pgs. (N). (SM/11628) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 19) | 6393/EMD | 24/11/2022 | 30 | H.K. DAS & CO. | 13 | 11.4 | 87.69 | 0
458 | NORTH 24 PARGANAS | Central Drilling | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC , SM/11628 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Raghunathpur W/S Scheme (T/W-I) , Basirhat-II Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | 547/CDD | 02/06/2023 | 30 | UTTAM KUMAR CHATTERJEE | 21.56 | 0 | 0 | 0
459 | NORTH 24 PARGANAS | Central Drilling | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC , SM/11628 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Raghunathpur W/S Scheme (TW-II) , Barasat-II Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | 1649/CDD | 17/10/2023 | 30 | DEV AND COMPANY | 22.01 | 0 | 0 | 0
460 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC , SM/11628 | Augmentation | Material Requisition To Resource Division | 493/BD | 17/02/2023 | 0 | Resource Division | 10.73 | 0 | 0 | 0
461 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC , SM/11628 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Raghunathpur water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | 3344/BD | 16/11/2022 | 90 | UTPAL CONSTRUCTION & CO. | 180.46 | 155.48 | 88.21 | 88
462 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC , SM/11628 | Augmentation | Relaying of 75mm dia UPVC Parallel line for repairing of FHTC connections which damaged due to construction of drain from local Panchayet at SriKrishnapur Mouza (Node no. 300 to 307 to 314 to 320) of Raghunathpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | 1028/BHTSD | 28/06/2024 | 7 | M/S MAA TARA ENTERPRISE | 0.73 | 0 | 0 | 100
463 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC , SM/11628 | Augmentation | Relaying of 110mmdia UPVC pipe line damaged due to construction of drain from local Panchayet at SriKrishnapur Mouza (Node no. 300 to 307 to 314 to 320) of Raghunathpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | 1029/BHTSD | 28/06/2024 | 7 | M/S. WAY CON. | 0.91 | 0 | 0 | 100
464 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Debhog to accommodate FHTC , SM/11753 | Augmentation | Material Requisition To Resource Division | 1250/BD | 25/04/2023 | 0 | Resource Division | 17.73 | 0 | 0 | 0
465 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Debhog to accommodate FHTC , SM/11753 | Augmentation | Formal work order for Laying of UPVC Distribution system pipe line and Providing FHTC (Functional Household Tap Connection ) by augmentation for Debhog water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | 518/BD | 20/02/2023 | 773 | UTPAL CONSTRUCTION & CO. | 301.59 | 202.41 | 67.12 | 80
466 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Debhog to accommodate FHTC , SM/11753 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Debhog Water Supply Scheme in Basirhat - I Block of Basirhat Sub- Division under Barasat Division, P.H.E Dte. | 3254/BD | 25/11/2024 | 30 | ROHAN MONDAL. | 21.41 | 0 | 0 | 0
467 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Debhog to accommodate FHTC , SM/11753 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Sankarpur and P/H-II under Debhog W/S Scheme with Pump House No-I under Gachharhati W/S Scheme District of 24 Pgs. (N). | 1483/EMD | 03/06/2024 | 298 | EASTERN INDIA SALES & SERVICE | 52.16 | 0 | 0 | 25
468 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa , SM/13531 | Retrofitting | Formal work order for Laying of Distribution system, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works and Providing FHTC within the jurisdiction of (Zone-XII) under Habra-Gaighata surface based PWSS of Habra-I Block under Barasat Division, P.H.E. Dte. | 2957/BD | 29/09/2023 | 810 | AMAL DUTTA ROY | 1929.73 | 190.93 | 28.16 | 22
469 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Krishnachandrapur Piped Water Supply Scheme, Bongaon Block (Phase-I) , SM/08265 | Retrofitting | Hiring of 1(one) no Luxury Car (Diesel/Driven) for the office use of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Barasat Division P.H.E. Dte. (Period from:-01/02/2022 to 31/01/2023). | 45/Bon | 31/01/2022 | 1 | ROY ENGINEERS. | 1.73 | 1.68 | 97.1 | 1
470 | NORTH 24 PARGANAS | Barasat Division | Sankardaha Piped water supply scheme , SM/13518 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (SANKARDAHA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 308/HSD | 15/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 0
471 | NORTH 24 PARGANAS | Barasat Division | Sankardaha Piped water supply scheme , SM/13518 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (SANKARDAHA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | 309/HSD | 15/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.06 | 2.06 | 100 | 0
472 | NORTH 24 PARGANAS | Barasat Division | Sankardaha Piped water supply scheme , SM/13518 | New | Acceptance cum work order for Strengthing of Brick pavement road for movement of rig machineries for sinking of big dia Tube well at PH No-2 within Sankardaha w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | 1129/HSD | 05/09/2023 | 7 | RUDRA DAS. | 3.55 | 3.51 | 100 | 100
473 | NORTH 24 PARGANAS | Barasat Division | Sankardaha Piped water supply scheme , SM/13518 | New | Material Requisition To Resource Division | 884/BD | 22/03/2023 | 0 | Resource Division | 17.11 | 0 | 0 | 0
474 | NORTH 24 PARGANAS | Eastern Mechanical | Sankardaha Piped water supply scheme , SM/13518 | New | New service connection for Sankardaha PH-I Sankardaha Minakhan | BP-254-23-24 | 20/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.58 | 0 | 0 | 0
475 | NORTH 24 PARGANAS | Eastern Mechanical | Sankardaha Piped water supply scheme , SM/13518 | New | New service connection for Sankardaha PH-II Sankardaha Minakhan | BP-255-23-24 | 20/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.58 | 0 | 0 | 0
476 | NORTH 24 PARGANAS | Barasat Division | Sankardaha Piped water supply scheme , SM/13518 | New | Acceptance cum work order for Strengthing of existing concrete & Brick pavement road for movement of rig machineries for sinking of big dia Tube well at PH No-1 within Sankardaha w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | 2717/BD | 05/09/2023 | 7 | ARBINA ENTERPRISE. | 5.56 | 5.55 | 100 | 100
477 | NORTH 24 PARGANAS | Barasat Division | Sankardaha Piped water supply scheme , SM/13518 | New | Acceptance cum work order for Emergent restoration of road for damage portion at different places in connection with retrofitting of Khas Sankardaha & Sankardaha Abad within Mathbari Abad (Scheme code-SM/15825) w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 995/HSD | 29/08/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.93 | 0.93 | 100 | 100
478 | NORTH 24 PARGANAS | Barasat Division | Sankardaha Piped water supply scheme , SM/13518 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 250 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Sankardaha W/S scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1699/BD | 08/06/2023 | 732 | M/S DATTA ENTERPRISE. | 405.52 | 253.01 | 66.9 | 100
479 | NORTH 24 PARGANAS | Barasat Division | Sankardaha Piped water supply scheme , SM/13518 | New | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection within Sankardaha water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte | 345/HSD | 06/02/2025 | 10 | M/S DATTA ENTERPRISE. | 0.72 | 0 | 0 | 100
480 | NORTH 24 PARGANAS | Barasat Division | Sankardaha Piped water supply scheme , SM/13518 | New | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection within Sankardaha water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte | 527/HSD | 10/03/2025 | 10 | M/S PROGATI ENTERPRISE. | 0.72 | 0 | 0 | 100
481 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District , SM/13537 | Retrofitting | Formal work order for Laying Distribution system, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works and Providing FHTC at Zonal Head Work Site Zone-VI within the jurisdiction of (Zone-VI) under Habra-Gaighata surface based PWSS of Deganga Block under Barasat Division, P.H.E. Dte. | 3008/BD | 05/10/2023 | 90 | PATHIK PABAN NANDI | 697.92 | 0 | 0 | 0
482 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District , SM/13537 | Retrofitting | Material Requisition To Resource Division | 4025/BD | 12/10/2023 | 0 | Resource Division | 78.14 | 0 | 0 | 0
483 | NORTH 24 PARGANAS | Barasat Division | Phulbari Abad Piped Water Supply Scheme. , SM/12717 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (PHULBARI ABAD Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 306/HSD | 15/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 4.82 | 100 | 1
484 | NORTH 24 PARGANAS | Barasat Division | Phulbari Abad Piped Water Supply Scheme. , SM/12717 | New | Material Requisition To Resource Division | 886/BD | 22/03/2023 | 0 | Resource Division | 11.94 | 0 | 0 | 0
485 | NORTH 24 PARGANAS | Barasat Division | Phulbari Abad Piped Water Supply Scheme. , SM/12717 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 150 cum capacity CWR , pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Phulbari Abad w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1691/BD | 07/06/2023 | 366 | M/S B.K.ENTERPRISE. | 252.21 | 220.08 | 87.26 | 80
486 | NORTH 24 PARGANAS | Eastern Mechanical | Phulbari Abad Piped Water Supply Scheme. , SM/12717 | New | Quotation for Service Connection Charges for PH- I under Fulbari Abad W/S Scheme in the district of North 24 Pgs. | BP-326-23-24 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.66 | 0 | 0 | 0
487 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. , SM/13446 | Augmentation | Repairing & Renovation of 1 No. Pump House (Size- 5.20 x 7.20) of Head Work Site and allied works at Matiagachha Water Supply Scheme under Barasat Sub-Division, P.H.E.Dte. | 833/BSD | 16/12/2021 | 30 | M.ENTERPRISE. | 1.85 | 1.75 | 94.66 | 1
488 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. , SM/13446 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Matigacha (Block:-Barasat-II) W/S Scheme District of 24 Pgs. (N) | 4742/EMD | 07/08/2023 | 30 | M.D. ENTERPRISE | 21.37 | 0 | 0 | 0
489 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. , SM/13446 | Augmentation | Repairing & Renovation of 1 No. Pump House (P.H. No-II) and allied works at Matiagachha Supply Scheme under Barasat Sub-Division, P.H.E.Dte. | 837/BSD | 20/12/2021 | 30 | K.D ENTERPRISE. | 1.25 | 0 | 0 | 100
490 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. , SM/13446 | Augmentation | Material Requisition To Resource Division | 1285/BD | 25/04/2023 | 0 | Resource Division | 46.16 | 0 | 0 | 0
491 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. , SM/13446 | Augmentation | Material Requisition To Resource Division | 1673/BD | 06/06/2023 | 0 | Resource Division | 46.16 | 0 | 0 | 0
492 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. , SM/13446 | Augmentation | Material Requisition To Resource Division | 1676/BD | 06/06/2023 | 0 | Resource Division | 11.83 | 0 | 0 | 0
493 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. , SM/13446 | Augmentation | Material Requisition To Resource Division | 4375/BD | 10/11/2023 | 0 | Resource Division | 12.98 | 0 | 0 | 0
494 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. , SM/13446 | Augmentation | Acceptance cum work order for Construction of Boundary Wall at Matiagacha Water Supply Scheme under Barasat-II Block, under Barasat Sub-Division, P.H.E.Dte. | 3080/BD | 29/10/2024 | 30 | SANTU GHOSH. | 25.1 | 0 | 0 | 0
495 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. , SM/13446 | Augmentation | Preparation of DPR in connection of augumentation of Matiagachha Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. Sl. No.-20 | 567/BSD | 29/06/2022 | 30 | RADIANT | 3.27 | 2.76 | 100 | 100
496 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. , SM/13446 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Matiagacha Water Supply Scheme (2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | 2942/BD | 27/09/2023 | 30 | JOY GURU ENTERPRISE | 16.12 | 11.91 | 100 | 100
497 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. , SM/13446 | Augmentation | Acceptance cum work order for Improvement of existing IEP & other related allied works and including adding 1 no. Polishing unit and Repairing and renovation of Compressor Room for Iron Elimination Plant under Augmentation of Matiagachha Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 627/BD | 28/02/2024 | 45 | R.K.MANDAL & CO. | 23.11 | 23.03 | 100 | 100
498 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. , SM/13446 | Augmentation | Formal work order for Construction of 300 cum capacity 20 mtr. height R.C.C. Over Head Reservoir as per Deptt. design, drawing & specification including bored pile & pile cap, laying of DI rising main & distribution pipe line by DI/UPVC and Providing FHTC for Augmentaion of Matiagachha water supply scheme under Barasat Sub-Division, P.H.E. Dte. | 1715/BD | 08/06/2023 | 366 | MITRA CONSTRUCTION. | 378.68 | 141.81 | 37.45 | 39
499 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. , SM/13446 | Augmentation | Acceptance cum work order for Renovation of Iron Elimination Plant at Matiagachha Water Supply Scheme within Barasat-II Block under Barasat Sub Division, P.H.E.Dte. | 98/BD | 09/01/2025 | 40 | AMIT KUMAR BOSE. | 9.19 | 0 | 0 | 0
500 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. , SM/13446 | Augmentation | Construction of Pump House with latrine at Matiagachha water Supply Scheme under Barasat-II Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | 1022/BSD | 03/01/2025 | 40 | BUSTER CONSTRUCTION | 4.87 | 0 | 0 | 0
501 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. , SM/13446 | Augmentation | Acceptance cum work order for Additional Laying of UPVC pipe line and allied work in connection with Augmentation Matiagachha Water Supply Scheme within Barasat Sub Division, P.H.E.Dte. | 57/BD | 07/01/2025 | 30 | MITRA CONSTRUCTION | 37.61 | 0 | 0 | 0
502 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC. , SM/13446 | Augmentation | Acceptance cum work order for Repair & Renovation work at Different site in connection with Augmentation of Matiagacha Water Supply Scheme under Barasat Sub Division, P.H.E.Dte. | 930/BD | 24/03/2025 | 45 | AREOCON. | 9.03 | 0 | 0 | 100
503 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Supply, delivery & installation of 30HP Centrifugal pump motor set at High Lift of Padmapukuria W/S scheme under Eastern Mechanical Division, P.H.E, Dte. Dist. 24 Pgs. (N). NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.- 16) | 6153/EMD | 11/11/2022 | 30 | D.K. ELECTRIC | 7.88 | 7.88 | 100 | 0
504 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at N/H/O Rahaman Molla, Motaleb Molla at Maliari Sekh para & Other places for Augmentation of Padmapukuria w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | 1196/HSD | 13/07/2022 | 10 | M/S ATRI BISWAS | 2.05 | 2.05 | 100 | 1
505 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Padmapukuria water supply scheme (Zone-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 127/BD | 16/01/2023 | 90 | MONDAL & CO. (BASIRHAT). | 416.99 | 369.68 | 100 | 1
506 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Material Requisition To Resource Division | 518/BD | 20/02/2023 | 0 | Resource Division | 124.37 | 0 | 0 | 0
507 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Material Requisition To Resource Division | 913/BD | 22/03/2023 | 0 | Resource Division | 48.74 | 0 | 0 | 0
508 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Padmapukuria water supply scheme (Zone-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 171/BD | 19/01/2023 | 90 | M/S B.K.ENTERPRISE. | 446.28 | 357.95 | 80.21 | 75
509 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 150 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Padmapukuria w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 1205/BD | 20/04/2023 | 30 | ABDUL ALIM MONDAL. | 25.87 | 23.75 | 100 | 63
510 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Construction of protection wall for protection of UPVC pipe line at Maliari Masjid pond for Augmentation of Padmapukuria w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1494/HSD | 01/12/2023 | 15 | BABUSONA CONSTRUCTION. | 4.41 | 4.41 | 100 | 68
511 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Construction of protection wall for protection of UPVC pipe line at N/H/O Hasmat Molla at Maliari for Augmentation of Padmapukuria w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1495/HSD | 01/12/2023 | 15 | GAZI ENTERPRISE | 4.03 | 3.94 | 100 | 70
512 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Padmapukuria W/S scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1141/HSD | 24/09/2024 | 10 | TRISHA ENTERPRISE & CO. | 0.87 | 0.87 | 100 | 100
513 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Padmapukuria W/S scheme (Z-II), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1143/HSD | 24/09/2024 | 10 | M/S R.B.S.ENTERPRISE. | 0.87 | 0 | 0 | 100
514 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | New Service Connection at PH-II under Minakhan W/S Scheme | BP-260-23-24 | 02/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.25 | 0 | 0 | 0
515 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Formal work order for construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per Deptt. design, drawing and specification including bored pile with pile cap for Augmentaion of Padmapukuria water supply scheme (Zone - II), Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | 1739/BD | 08/06/2023 | 724 | M/S B.K.ENTERPRISE. | 121.96 | 0 | 0 | 100
516 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Construction of boundary wall with column structure at OHR site, PH No-2 & 3 in connection with augmentation of Padmapukuria w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1030/BD | 28/03/2025 | 90 | JESMINE ENTERPRISE. | 28.96 | 0 | 0 | 0
517 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Padmapukuria w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 409/BD | 06/02/2025 | 300 | M/S RAJPATH CONSTRUCTION. | 51.15 | 0 | 0 | 96
518 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at P.H. No.-I, II III (Replacement) under Padmapukuria W/S scheme (Zone-I) under Block_ Minakhan Dist. - 24Pgs(N) under EMD, PHE Dte. [SM/13314] | 696/EMD | 04/04/2025 | 30 | GLACIER ENGINEERING CO. | 41.96 | 0 | 0 | 0
519 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Construction of boundary wall with column structure at OHR site in connection with augmentation of Padmapukuria w/s scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1029/BD | 28/03/2025 | 90 | M/S B.K.ENTERPRISE. | 18.14 | 0 | 0 | 0
520 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Formal work order for Construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Padmapukuria water supply scheme (Zone - I), Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | 1723/BD | 08/06/2023 | 725 | MONDAL & CO. (BASIRHAT). | 152.66 | 126.14 | 90.49 | 99
521 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Protection works for protection of UPVC distribution pipe line at N/H/O Murshid Molla in connection with Augmentation of Padmapukuria w/s scheme (Zone-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 2097/BD | 26/07/2024 | 151 | JESMINE ENTERPRISE. | 7.53 | 1.97 | 20.94 | 100
522 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 200 mm dia DI pipeline at different places in connection with Augmentation of Padmapukuria w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 260/HSD | 30/01/2025 | 10 | ABDUL ALIM MONDAL. | 0.95 | 0 | 0 | 100
523 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Padmapukuria mouza in connection with augmentation of Padmapukuria w/s scheme (Z-I), Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | 170/HSD | 27/01/2025 | 10 | ABDUL ALIM MONDAL. | 0.96 | 0 | 0 | 100
524 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Construction of Office cum Godown with sanitary & water supply arrangement i/c plinth protection at OHR site (Size-5.40x3.60 mtr.) for Augmentation of Padmapukuria w/s scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 2962/BD | 04/10/2024 | 120 | JESMINE ENTERPRISE. | 13.54 | 0.7 | 5.03 | 60
525 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Construction of Office cum Godown with sanitary & water supply arrangement i/c plinth protection at OHR site (Size-5.40x3.60 mtr.) for Augmentation of Padmapukuria w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 2966/BD | 04/10/2024 | 120 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 13.5 | 5.22 | 41.21 | 60
526 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Maliari mouza in connection with augmentation of Padmapukuria w/s scheme (Z-I), Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | 172/HSD | 27/01/2025 | 10 | ABDUL ALIM MONDAL. | 0.96 | 0 | 0 | 100
527 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 100 mm dia DI pipeline at different places in connection with Augmentation of Padmapukuria w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 939/HSD | 29/05/2025 | 10 | ABDUL ALIM MONDAL. | 0.95 | 0 | 0 | 100
528 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 200 mm dia DI pipeline at different places in connection with Augmentation of Padmapukuria w/s scheme (Z-II), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 317/HSD | 04/02/2025 | 10 | ABDUL ALIM MONDAL. | 0.95 | 0 | 0 | 100
529 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Land development at Over Head Reservoir site for Augmentation of Padmapukuria water supply scheme (Zone-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | 93/BD | 08/01/2025 | 14 | MONDAL & CO. (BASIRHAT). | 12.06 | 0 | 0 | 100
530 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Bairagi para in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 173/HSD | 27/01/2025 | 10 | SARKAR ENTERPRISE & CO. | 0.94 | 0 | 0 | 100
531 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Supply and installation of 150 mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Padmapukuria water supply scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 318/HSD | 04/02/2025 | 10 | ABDUL ALIM MONDAL. | 0.79 | 0 | 0 | 100
532 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places of Padmapukuria mouza within Padmapukuria w/s scheme (Z-I), Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | 383/HSD | 10/02/2025 | 10 | ABDUL ALIM MONDAL. | 0.96 | 0 | 0 | 100
533 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places of Maliari mouza within Padmapukuria w/s scheme (Z-I), Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | 315/HSD | 04/02/2025 | 10 | ABDUL ALIM MONDAL. | 0.96 | 0 | 0 | 100
534 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Padmapukuria to accommodate FHTC , SM/13314 | Augmentation | Acceptance cum work order for Protection works for newly laid different dia. UPVC pipe line at near Kadihati Jame Masjid, N/H/O Jibon Ali Molla, Maliari in connection with Augmentation of Padmapukuria w/s scheme (Zone-II), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1529/BD | 14/05/2025 | 21 | JESMINE ENTERPRISE. | 9.35 | 0 | 0 | 100
535 | NORTH 24 PARGANAS | Barasat Arsenic Division | SULANGGARI Piped Water Supply Scheme , SM/14634 | New | Sulanggari Piped Water Supply Scheme with Rising Main, LDS, FHTC & construction of 550 cum capacity Overhead Reservoir (OHR) including Soil investigation and foundation design at Sulanggari under Rajarhat block, Dist.- North 24 Parganas. | 1341/B.Ar.D. | 07/06/2023 | 366 | BARMAN ASSOCIATES | 580.02 | 0 | 0 | 5
536 | NORTH 24 PARGANAS | Barasat Arsenic Division | SULANGGARI Piped Water Supply Scheme , SM/14634 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 3rd Pump House site of Sulanggari Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1666/B.Ar.D. | 18/07/2023 | 45 | POWER TOOLS AND ENGINEERING | 18.18 | 0 | 0 | 0
537 | NORTH 24 PARGANAS | Barasat Arsenic Division | SULANGGARI Piped Water Supply Scheme , SM/14634 | New | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 3rd Tube Well Site of SULANGURI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1698/B.Ar.D. | 20/07/2023 | 60 | CHOWDHURY CONSTRUCTION | 6.24 | 0 | 0 | 0
538 | NORTH 24 PARGANAS | Barasat Arsenic Division | SULANGGARI Piped Water Supply Scheme , SM/14634 | New | Construction of 4.88 mtr. x 3.60 mtr. size new Pump House at Head Work Site of SULANGURI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1696/B.Ar.D. | 20/07/2023 | 60 | BARMAN ASSOCIATES | 7.03 | 0 | 0 | 0
539 | NORTH 24 PARGANAS | Barasat Arsenic Division | SULANGGARI Piped Water Supply Scheme , SM/14634 | New | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 2nd Tube Well Site of SULANGURI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1697/B.Ar.D. | 20/07/2023 | 60 | PRAGATI CONSTRUCTION & CO | 6.2 | 0 | 0 | 0
540 | NORTH 24 PARGANAS | Barasat Arsenic Division | SULANGGARI Piped Water Supply Scheme , SM/14634 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 2nd Pump House site of Sulanggari Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1665/B.Ar.D. | 18/07/2023 | 45 | SAHA CONSTRUCTION AND CO | 18.26 | 0 | 0 | 0
541 | NORTH 24 PARGANAS | NTK Mechanical | SULANGGARI Piped Water Supply Scheme , SM/14634 | New | Supply & Installation of pumping machineries & other electro-mechanical accessories in Sulanggari piped W/S scheme under New Town Kolkata Mechanical Division, P.H.E. Dte. | 2133/NTKMD | 11/08/2023 | 180 | GLACIER ENGINEERING CO. | 65.81 | 0 | 0 | 0
542 | NORTH 24 PARGANAS | Barasat Arsenic Division | SULANGGARI Piped Water Supply Scheme , SM/14634 | New | Survey, Design Drawing & DPR Preparation for NEW PWSS (SULANGGARI Water Supply Scheme) in RAJARHAT BLOCK under Barasat Arsenic Division, PHE Dte. | 984/B.Ar.D. | 20/04/2023 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 9.68 | 9.68 | 100 | 100
543 | NORTH 24 PARGANAS | Barasat Arsenic Division | SULANGGARI Piped Water Supply Scheme , SM/14634 | New | Material Requisition To Resource Division | 78/B.Ar.D | 11/01/2024 | 0 | Resource Division | 23.32 | 0 | 0 | 0
544 | NORTH 24 PARGANAS | Barasat Arsenic Division | SULANGGARI Piped Water Supply Scheme , SM/14634 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at Head Work site of Sulanggari Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1664/B.Ar.D. | 18/07/2023 | 720 | SAHA CONSTRUCTION AND CO | 18.26 | 0 | 0 | 100
545 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 1203/BD | 20/04/2023 | 30 | ANJALI ENTERPRISE. | 21.52 | 18.03 | 83.79 | 0
546 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Hingalganj Zone - I Piped Water Supply Scheme under Barasat Division, PHE Dte. | 635/HSD | 08/04/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 0
547 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Material Requisition To Resource Division | 929/BD | 22/03/2023 | 0 | Resource Division | 50.77 | 0 | 0 | 0
548 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 2 & 3(at defunct T/W site) with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Hingalganj W/S(old) scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 2242/BD | 22/08/2022 | 30 | ACME CONSTRUCTION | 44.4 | 16.89 | 38.04 | 55
549 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Additional Construction of 2 nos. switch room cum chlorine room (Size-5.40x3.60 mtr.) for Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 3025/BD | 22/10/2024 | 90 | M/S ANUBHAB CONSTRUCTION. | 15.83 | 0 | 0 | 0
550 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at N/H/O Ajay Manna & Bijon Manna at Mamudpur in connection with Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 3498/BD | 11/12/2024 | 30 | NURJAHAN ENTERPRISE. | 7.55 | 0 | 0 | 0
551 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Formal work order for Laying of Di rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Hingalganj water supply scheme (Z-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 697/BD | 03/03/2023 | 90 | M/S PROGATI ENTERPRISE. | 296.42 | 288.69 | 100 | 53
552 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 2480/BD | 18/08/2023 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 51.64 | 38.28 | 100 | 100
553 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-4 & 5 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 2482/BD | 18/08/2023 | 30 | MONDAL & CO. (BASIRHAT). | 51.6 | 38.01 | 100 | 100
554 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Mamudpur mouza within Hingalganj w/s scheme(Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 220/HSD | 29/02/2024 | 10 | TRISHA ENTERPRISE & CO. | 0.94 | 0.93 | 100 | 100
555 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Hingalganj mouza within Hingalganj w/s scheme(Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 219/HSD | 29/02/2024 | 10 | MONDAL & CO. (BASIRHAT). | 0.97 | 0.97 | 100 | 100
556 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Additional Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 2902/BD | 03/10/2024 | 60 | ANJALI ENTERPRISE. | 51.76 | 0 | 0 | 0
557 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Construction of Pressure sand filter of capacity 120 cum/hr at Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 2023/BD | 18/06/2025 | 150 | FIDERE MARINE SERVICES PVT. LTD. | 38.29 | 0 | 0 | 0
558 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I,II,II,IV and V (Zone-I) under Hingalganj Aug. W/S Scheme, Block-Hingalganj in District of 24 Pgs. (N) NIET No. 38 of EE/EMD of 2022-23 (Sl. No.- 04) | 1232/EMD | 24/03/2023 | 739 | H.K. DAS & CO. | 53.44 | 41.39 | 84.65 | 77
559 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line and other allied works in connection with retrofitting work at different places in connection with augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 94/BD | 08/01/2025 | 14 | MONDAL & CO. (BASIRHAT). | 13.34 | 0 | 0 | 100
560 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejuvenation Tube Well in connection to Accommodate FHTC at Pump House No.-II under Hingalganj Old ground water based water supply scheme under Block_ Hingalganj Dist. - 24 Pgs. (N) under EMD, PHE Dte. (SM/14512) | 2683/EMD | 20/11/2024 | 162 | H.K. DAS & CO. | 10.61 | 0 | 0 | 100
561 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at N/H/O Tapan Shit & Shyamal Samanta at Hingalganj in connection with Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E.Dte. | 3497/BD | 11/12/2024 | 150 | MD.SALIM GAZI. | 7.72 | 0 | 0 | 100
562 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation of Hingalganj water supply scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 175/HSD | 27/01/2025 | 10 | MD.SALIM GAZI. | 0.55 | 0.55 | 100 | 100
563 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Emergent providing of 2 nos. FHTC at Hingalganj Krishimandi with laying of 63 mm dia UPVC pipe line in connection with augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 177/HSD | 27/01/2025 | 10 | MD.SALIM GAZI. | 0.51 | 0.51 | 100 | 100
564 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Emergent laying of 90 mm dia UPVC pipe line for damage portion at N/H/O Ex Sabhapati Sudip Mondal, Hingalganj with retrofitting work in connection with augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 1000/HSD | 04/06/2025 | 10 | TRISHA ENTERPRISE & CO. | 0.87 | 0 | 0 | 100
565 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Construction of protection wall at OHR site, construction of approach road at OHR & CWR site & other allied works within within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 2105/BD | 29/07/2024 | 183 | SARKAR ENTERPRISE & CO. | 12.93 | 0 | 0 | 100
566 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Emergent protection of pipeline with UC Bullah pilling at N/H/O Prodip Mondal at 11 no Sandelerbill within Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 937/HSD | 29/05/2025 | 10 | TRISHA ENTERPRISE & CO. | 0.96 | 0 | 0 | 100
567 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Emergent protection of pipeline with UC Bullah pilling at near primary school at 11 no Sandelerbill within Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte | 991/HSD | 04/06/2025 | 10 | TRISHA ENTERPRISE & CO. | 0.96 | 0 | 0 | 100
568 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Emergent protection of pipeline with UC Bullah pilling at N/H/O Ration Dealer at 11 no Sandelerbill within Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 994/HSD | 04/06/2025 | 10 | MONDAL & CO. (BASIRHAT). | 0.96 | 0 | 0 | 100
569 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Emergent protection of pipeline with UC Bullah pilling at near PH No-3 within Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 538/HSD | 10/03/2025 | 10 | TRISHA ENTERPRISE & CO. | 0.96 | 0 | 0 | 100
570 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Emergent protection of pipeline with UC Bullah pilling at near ICDS at 11 no Sandelerbill within Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 1002/HSD | 04/06/2025 | 10 | TRISHA ENTERPRISE & CO. | 0.96 | 0 | 0 | 100
571 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Providing Functional household tap connection at 8 no Khatuapara SSK, Keorakhali FP School and Sahapur FP School within the command area of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 1482/HSD | 14/07/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.64 | 0 | 0 | 100
572 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-I , SM/14512 | Augmentation | Acceptance cum work order for Supply and installation of 100 mm dia sluice valve at different washout point in distribution pipe line for smooth supply of water in connection with augmentation of Hingalganj water supply scheme Z-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 2331/BD | 07/07/2025 | 30 | MONDAL & CO. (BASIRHAT). | 5.91 | 0 | 0 | 100
573 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District , SM/14540 | Retrofitting | Formal work order for Laying of Distribution system, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works and Providing FHTC within the jurisdiction of (Zone-XXIII) under Habra-Gaighata surface based PWSS of Gaighata Block under Barasat Division, P.H.E. Dte. | 2956/BD | 29/09/2023 | 900 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 2089.66 | 260.09 | 24.75 | 20
574 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15820 | Augmentation | Detail route survey, design of distribution network and preparation of estimate drawing & DPR for providing FHTC in the scheme of Zone-V(Matikumra) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | 257/NWSD-I | 10/03/2023 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.55 | 4.54 | 100 | 0
575 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15820 | Augmentation | Material Requisition To Resource Division | 465/NWSD-I | 26/04/2023 | 0 | Resource Division | 108.47 | 0 | 0 | 0
576 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15820 | Augmentation | Material Requisition To Resource Division | 943/NWSD-I | 18/07/2023 | 0 | Resource Division | 137.22 | 0 | 0 | 0
577 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15820 | Augmentation | Material Requisition To Resource Division | 1104/NWSD-I | 01/08/2023 | 0 | Resource Division | 28.75 | 0 | 0 | 0
578 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15820 | Augmentation | Order for the work of " Providing FHTC, Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of Zone- V (Matikumra) in Deganga Block of North 24 Parganas (s) District under North 24 Pgs W/S Div-I, PHE Dte". | 678/NWSD-I | 01/06/2023 | 1218 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 788.45 | 608.39 | 77.16 | 75
579 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15820 | Augmentation | New service connection at OHR Site , Zone-V of Matikumra water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). | BP-342-23-24 | 11/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.53 | 0 | 0 | 0
580 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15820 | Augmentation | Laying of pipe line & special measure for protection of road and other allied works at different location under Augmentation work at Matikumra W/S. Scheme in Deganga Block under North 24Pgs. W/S Division-I, P.H.E. Dte. | 23/NWSD-I | 06/01/2025 | 15 | RAJ ENTERPRISE | 4.94 | 0 | 0 | 0
581 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15822 | Augmentation | Detail route survey, design of distribution network and preparation of estimate drawing & DPR for providing FHTC in the scheme of Zone-II (Uttar Kalsur) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | 210/NWSD-I | 23/02/2023 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.36 | 4.36 | 100 | 0
582 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15822 | Augmentation | Material Requisition To Resource Division | 467/NWSD-I | 26/04/2023 | 0 | Resource Division | 219.63 | 0 | 0 | 0
583 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15822 | Augmentation | Material Requisition To Resource Division | 1103/NWSD-I | 01/08/2023 | 0 | Resource Division | 30.14 | 0 | 0 | 0
584 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15822 | Augmentation | Material Requisition To Resource Division | 944/NWSD-I | 18/07/2023 | 0 | Resource Division | 249.77 | 0 | 0 | 0
585 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15822 | Augmentation | New service connection at OHR site of Uttar Kalsur water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). Type : | BP-341-23-24 | 11/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.36 | 0 | 0 | 0
586 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15822 | Augmentation | Providing FHTC, Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | 694/NWSD-I | 05/06/2023 | 366 | M/S. TARAK CHANDRA PAUL | 751.17 | 519.96 | 69.22 | 85
587 | NORTH 24 PARGANAS | Barasat Division | Khariat Abad Piped Water Supply Scheme , SM/15829 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KHARIAT ABAD Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-A) | 337/HSD | 21/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.83 | 4.83 | 100 | 1
588 | NORTH 24 PARGANAS | Barasat Division | Khariat Abad Piped Water Supply Scheme , SM/15829 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KHARIAT ABAD Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-B) | 338/HSD | 21/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
589 | NORTH 24 PARGANAS | Barasat Division | Khariat Abad Piped Water Supply Scheme , SM/15829 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KHARIAT ABAD Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-C) | 347/HSD | 21/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.72 | 1.72 | 100 | 1
590 | NORTH 24 PARGANAS | Barasat Division | Khariat Abad Piped Water Supply Scheme , SM/15829 | New | Material Requisition To Resource Division | 870/BD | 22/03/2023 | 0 | Resource Division | 51.83 | 0 | 0 | 0
591 | NORTH 24 PARGANAS | Eastern Mechanical | Khariat Abad Piped Water Supply Scheme , SM/15829 | New | Service connection charges at PH-I under Khariat W/S Scheme | BP-291-23-24 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.04 | 0 | 0 | 0
592 | NORTH 24 PARGANAS | Eastern Mechanical | Khariat Abad Piped Water Supply Scheme , SM/15829 | New | Quotation for Service Connection Charges for PH- II under Khariat Abad W/S Scheme in the district of North 24 Pgs. | BP-366-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.11 | 0 | 0 | 0
593 | NORTH 24 PARGANAS | Eastern Mechanical | Khariat Abad Piped Water Supply Scheme , SM/15829 | New | Quotation for Service Connection Charges for PH- III under Khariat Abad W/S Scheme in the district of North 24 Pgs. | BP-367-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.04 | 0 | 0 | 0
594 | NORTH 24 PARGANAS | Barasat Division | Khariat Abad Piped Water Supply Scheme , SM/15829 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile, Construction of 250 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap within Khariat Abad W/S Scheme, Sandeshkhali block under Hasnabad Sub-Division, P.H.E. Dte. | 4027/BD | 12/10/2023 | 730 | MAHAVIR PUMPS MANUFACTURING PVT.LTD. | 618.97 | 62.02 | 10.02 | 50
595 | NORTH 24 PARGANAS | Barasat Division | Khariat Abad Piped Water Supply Scheme , SM/15829 | New | Formal work order for Withdrawing, relaying and laying of different dia. UPVC/DI pipe line at Bangali para, near cyclone centre, Sahaji para, shayam molla para, Barik para, Ghorami para etc of Jhupkhali and Nazat BDO office, Metekhali, Parsemari & other tail end areas of Boyermari Abad to improve functionality under Khariat Abad w/s scheme under Hasnabad Sub-Division, P.H.E.Dte. | 1749/BD | 28/05/2025 | 180 | CHANCHAL ENTERPRISE & CO. | 177.38 | 0 | 0 | 0
596 | NORTH 24 PARGANAS | Barasat Division | Ketarchak Piped Water Supply Scheme , SM/15833 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KETARCHAK Water Supply Scheme) in HINGALGANJ BLOCK under Barasat Division, PHE Dte. (PART-A) | 237/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 4.82 | 100 | 1
597 | NORTH 24 PARGANAS | Barasat Division | Ketarchak Piped Water Supply Scheme , SM/15833 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KETARCHAK Water Supply Scheme) in HINGALGANJ BLOCK under Barasat Division, PHE Dte. (PART-B) | 238/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
598 | NORTH 24 PARGANAS | Barasat Division | Ketarchak Piped Water Supply Scheme , SM/15833 | New | Material Requisition To Resource Division | 878/BD | 22/03/2023 | 0 | Resource Division | 42.93 | 0 | 0 | 0
599 | NORTH 24 PARGANAS | Barasat Division | Ketarchak Piped Water Supply Scheme , SM/15833 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 cum capacity 20 mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Ketarchak water supply scheme, Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. under Barasat Division, P.H.E. Dte. | 2615/BD | 29/08/2023 | 366 | MONDAL PRECISION PVT.LTD | 507.61 | 75.88 | 14.95 | 30
600 | NORTH 24 PARGANAS | Barasat Division | Ketarchak Piped Water Supply Scheme , SM/15833 | New | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at OHR site (Size-5.40x3.60 mtr.) & PH No-1 (Size-3.60x3.00 mtr.) for Kalitala w/s scheme (Z-I), Hingalganj Block under Ketarchak Piped Water Supply Scheme within Hasnabad Sub-Division, P.H.E. Dte. | 2959/BD | 04/10/2024 | 60 | MD.SALIM GAZI. | 21.3 | 0 | 0 | 0
601 | NORTH 24 PARGANAS | Barasat Division | Ketarchak Piped Water Supply Scheme , SM/15833 | New | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Ph No- 1, 2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Ketarchak w/s scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 634/BD | 28/02/2025 | 60 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 77.48 | 0 | 0 | 0
602 | NORTH 24 PARGANAS | Barasat Division | Ketarchak Piped Water Supply Scheme , SM/15833 | New | Acceptance cum work order for Sinking of 1 No. 400.00 mtr. Deep 100 X 50 mm. dia. Trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe and strainers at T/W site-1 for Ketarchak w/s scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 844/HSD | 19/05/2025 | 10 | M/S GHOSH CONSTRUCTION. | 3.39 | 0 | 0 | 0
603 | NORTH 24 PARGANAS | Eastern Mechanical | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Habra - I and Sandeshkhali - I & II Blocks in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. , SM/15760 | Solarisation | Solarisation of WBSEDCL Energised Electrical installation including net metering at different Pipe Water Supply Scheme at Habra-I and Sandeshkhali-I & II Block in North 24 Parganas District under E.M.D. P.H.E. Dte. | 6350/EMD | 16/10/2023 | 183 | BALAJI UDDYOG | 619.68 | 0 | 0 | 0
604 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18260 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Zone-XVI (Kalijug Biswanathpur) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | 894/NWSD-I | 12/07/2023 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.79 | 3.78 | 100 | 100
605 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18260 | Augmentation | Material Requisition To Resource Division | 1371/NWSD-I | 04/09/2023 | 0 | Resource Division | 129.72 | 0 | 0 | 0
606 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18260 | Augmentation | Supply and installation of Sign Board (900mm X 600mm) determination of Land i.e." This land belongs to PHE. Dte. Govt. of West Bengal" under Surface Water based Pipe Water supply Scheme under North 24 Pgs. Water Supply Division-I, PHE. Dte. | 1432/NWSD-I | 18/09/2024 | 14 | S M TRADERS | 2.17 | 0 | 0 | 100
607 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18260 | Augmentation | Development of approach Road at Head Work Site Kalijug Biswanathpur (Zone-XVI) W/S Scheme in Deganga Block under North 24 Pgs W/S Division-I, PHE. Dte. | 904/NWSD-I | 19/06/2024 | 14 | RAKESH ENTERPRISE | 13.36 | 13.29 | 100 | 100
608 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18260 | Augmentation | Material Requisition To Resource Division | 230/NWSD-I | 06/02/2024 | 0 | Resource Division | 21.71 | 0 | 0 | 0
609 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18260 | Augmentation | New service connection at Kalijug Biswanathpur P.H.No- I Zone- XVI water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). | BP-333-23-24 | 11/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.73 | 0 | 0 | 0
610 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18260 | Augmentation | Providing FHTC, Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of Zone- XVI (KALIJUG BISWANATHPUR) in Deganga Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | 1009/NWSD-I | 25/07/2023 | 1102 | H. I. ENTERPRISE | 762.31 | 501.32 | 65.76 | 82
611 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18260 | Augmentation | Laying of pipeline & other allied work at different location under Augmentation work at Kalijug-Biswanathpur W/S. Scheme in Deganga Block under North 24 Pgs W/S Division-I, P.H.E. Dte. | 725/NWSD-I | 19/05/2025 | 210 | H. I. ENTERPRISE | 76.14 | 0 | 0 | 65
612 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VI (Bashbaruni) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18265 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Zone-VI (Bashbaruni) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | 889/NWSD-I | 12/07/2023 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.73 | 3.72 | 100 | 100
613 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VI (Bashbaruni) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18265 | Augmentation | Material Requisition To Resource Division | 1834/NWSD-I | 10/11/2023 | 0 | Resource Division | 3 | 0 | 0 | 0
614 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VI (Bashbaruni) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18265 | Augmentation | Supply and installation of Sign Board (900mm X 600mm) determination of Land i.e." This land belongs to PHE. Dte. Govt. of West Bengal" under Surface Water based Pipe Water supply Scheme under North 24 Pgs. Water Supply Division-I, PHE. Dte. | 1432/NWSD-I | 18/09/2024 | 14 | S M TRADERS | 2.17 | 0 | 0 | 100
615 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VI (Bashbaruni) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18265 | Augmentation | Material Requisition To Resource Division | 40/NWSD-I | 05/01/2024 | 0 | Resource Division | 19.73 | 0 | 0 | 0
616 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VI (Bashbaruni) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18265 | Augmentation | New service connection at P.H.No- OHR ,Zone- VI of Byasbaruni water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). | BP-129-24-25 | 01/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.1 | 0 | 0 | 0
617 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VI (Bashbaruni) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18265 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure, Proposed Rising Main System, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction of 500 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation (600 mm dia, 22 mtrs. deep and one pile cap adjoning 3 nos of piles) , pipe connection and cost of pipes, specials., Soil Investigation for the work of construction of OHR with staging height 20 mtr, Construction Of Pump House (4.88m X 3.66m) Including Sanitary Arrangement, Boundary Wall, Service Road for 60 M length, Improvement Of Land for Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of ZONE-VI BASHBARUNI in Deganga Block of North 24 Pargana(s) District under North 24 Pgs. W/S Div-I, PHE Dte. | 1673/NWSD-I | 30/10/2023 | 884 | SINGHA ROY AND CO | 733.49 | 0 | 0 | 20
618 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-II to Accommodate FHTC. , SM/18712 | Augmentation | Material Requisition To Resource Division | 3091/BD | 10/10/2023 | 0 | Resource Division | 11.72 | 0 | 0 | 0
619 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-II to Accommodate FHTC. , SM/18712 | Augmentation | Material Requisition To Resource Division | 4369/BD | 10/11/2023 | 0 | Resource Division | 1.35 | 0 | 0 | 0
620 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-II to Accommodate FHTC. , SM/18712 | Augmentation | Preparation of DPR in connection of augumentation of Sohai Swetpur Water Supply Scheme Zone-II under Barasat Sub Division, P.H.E. Dte. | 455/BSD | 20/05/2022 | 30 | RADIANT | 3.38 | 3.3 | 100 | 100
621 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-II to Accommodate FHTC. , SM/18712 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-B | 1117./1/BSD | 09/02/2024 | 4 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
622 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-II to Accommodate FHTC. , SM/18712 | Augmentation | Formal work order for construction of 600 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentaion of Swetpur (Zone-II) water supply scheme under Barasat Sub-Division, P.H.E. Dte. | 2594/BD | 28/08/2023 | 731 | SINGHA ROY & CO. | 523.5 | 87.9 | 16.79 | 8
623 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-II to Accommodate FHTC. , SM/18712 | Augmentation | Formal work order for Additional pipeline and other allied works as per revised LDS in connection with Augmentation of Swetpur-II Water Supply Scheme under JJM programme in Deganga block within Barasat Sub Division, P.H.E.Dte. | 524/BD | 17/02/2025 | 90 | A.P POWER & CONCRETE | 192.44 | 0 | 0 | 0
624 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC , SM/11606 | Augmentation | Route Survey, Design Drawing & DPR Preparation for PASCHIM MADHYAMPUR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | 197/ BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.24 | 3.95 | 50 | 1
625 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC , SM/11606 | Augmentation | Material Requisition To Resource Division | 853/BD | 20/03/2023 | 0 | Resource Division | 51.49 | 0 | 0 | 0
626 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC , SM/11606 | Augmentation | Material Requisition To Resource Division | 611/BD | 23/02/2023 | 0 | Resource Division | 10.1 | 0 | 0 | 0
627 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC , SM/11606 | Augmentation | Material Requisition To Resource Division | 4426/BD | 10/11/2023 | 0 | Resource Division | 13.34 | 0 | 0 | 0
628 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC , SM/11606 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) by augmentation for Paschim Madhyampur water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | 1040/BD | 31/03/2023 | 702 | UTPAL CONSTRUCTION & CO. | 487.91 | 414.23 | 84.9 | 68
629 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC , SM/11606 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Rep.) under Sankchura W/S Scheme and Paschim Madhyampur W/s Scheme District of 24 Pgs. (N) | 4815/EMD | 09/08/2023 | 30 | CONCORD ENGINEERING | 79.5 | 0 | 0 | 0
630 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC , SM/11606 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Basirhat-I Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - C) | 148/BHTSD | 29/01/2025 | 20 | M.R.CONSTRUCTION. | 0.88 | 0 | 0 | 90
631 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC , SM/11606 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Paschim Madhyampur Water Supply Scheme in Basirhat - I Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | 2051/BD | 20/06/2025 | 60 | M/S K.P.PAL. | 21.76 | 0 | 0 | 100
632 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC , SM/11666 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Ghatpatila (Zone-II) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 131/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.89 | 3.89 | 50 | 1
633 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC , SM/11666 | Augmentation | Material Requisition To Resource Division | 1257/BD | 25/04/2023 | 0 | Resource Division | 64.8 | 0 | 0 | 0
634 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC , SM/11666 | Augmentation | Material Requisition To Resource Division | 1861/BD | 23/06/2023 | 0 | Resource Division | 15.65 | 0 | 0 | 0
635 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC , SM/11666 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for augmentation of Ghatpatila (Zone-II) Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 1354/BD | 04/05/2023 | 810 | PATHIK PABAN NANDI | 403.71 | 370.5 | 91.77 | 95
636 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC , SM/11666 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Zone-II) (Replacement) under Ghatpatila W/S Scheme District of 24 Pgs. (N). | 6755/EMD | 28/11/2023 | 30 | GOENKA ENTERPRISE | 22.16 | 7.28 | 32.88 | 80
637 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC , SM/11666 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Ghatpatila (Zone-II) water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | 2688/BD | 04/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.13 | 13.46 | 100 | 100
638 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC , SM/11666 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Ghatpatila (Zone-II) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 4409/BD | 10/11/2023 | 60 | ROY CHOWDHURY CONSTRUCTION. | 15.27 | 15.23 | 100 | 100
639 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC , SM/11666 | Augmentation | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Ghatpatila (Zone-II) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division P.H.E. Dte. | 4463/BD | 21/11/2023 | 414 | ROY ENGINEERS. | 9.57 | 0 | 0 | 0
640 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ghatpatila Zone-II to Accommodate FHTC , SM/11666 | Augmentation | Formal work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe line under Augmentation work at Ghatpatila (Zone - II) W/S Scheme Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 3736/BD | 27/12/2024 | 360 | PATHIK PABAN NANDI | 120.24 | 0 | 0 | 80
641 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Noorpur Piped Water Supply Scheme, Minakhan Block (Phase-I) , SM/08259 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in diff. mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Noorpur w/s scheme, Minakhan block under Hasnabad Sub-Division, PHE Dte. (Phase-I) | 1672/BD | 08/09/2021 | 45 | MONDAL & CO. (BASIRHAT). | 84.12 | 82.46 | 50 | 1
642 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Noorpur Piped Water Supply Scheme, Minakhan Block (Phase-I) , SM/08259 | Retrofitting | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places for providing FHTC in Noorpur/Bokchara mouza within Noorpur w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1989/HSD | 02/12/2021 | 7 | MONDAL & CO. (BASIRHAT). | 1.63 | 1.63 | 50 | 1
643 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Noorpur Piped Water Supply Scheme, Minakhan Block (Phase-I) , SM/08259 | Retrofitting | Material Requisition To Resource Division | 1809/BD | 19/06/2023 | 0 | Resource Division | 14.78 | 0 | 0 | 0
644 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC , SM/18582 | Augmentation | Additional Survey work for DPR Preparation for CHANDIPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 358/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.31 | 0.28 | 100 | 100
645 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC , SM/18582 | Augmentation | Route Survey, Design Drawing & DPR Preparation for CHANDIPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 357/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 4.95 | 100 | 100
646 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC , SM/18582 | Augmentation | Material Requisition To Resource Division | 1251/BD | 25/04/2023 | 0 | Resource Division | 139.05 | 0 | 0 | 0
647 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC , SM/18582 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery along with allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Magurali and P.H. No.- II under Chandipur W/S Scheme District of 24 Pgs. (N) | 4935/EMD | 18/08/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 39.08 | 0 | 0 | 0
648 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC , SM/18582 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Chandipur water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | 2418/BD | 11/08/2023 | 684 | H.I.ENTERPRISE. | 813.8 | 763.96 | 93.88 | 85
649 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Chandipur to accommodate FHTC , SM/18582 | Augmentation | Acceptance cum work order for Restoration of UPVC pipe line and FHTC due to damage of Pipeline and House Connection by WBSEDCL for laying Electric cable at Chandipur Taltala More towards Ghoragacha of Chandipur water Supply Scheme within Basirhat - I Block within Basirhat Sub-Division PHE Dte. under Barasat Division PHE.Dte. | 05/BHTSD | 02/01/2025 | 120 | RAKESH ENTERPRISE. | 2.97 | 0 | 0 | 100
650 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kola Water Supply Scheme at Bagdah Block (Phase-I) , SM/08069 | Retrofitting | Material Requisition To Resource Division | 2861/BD | 21/09/2022 | 0 | Resource Division | 0 | 0 | 0 | 0
651 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC , SM/10574 | Augmentation | Material Requisition To Resource Division | 3363/BD | 17/11/2022 | 0 | Resource Division | 3.53 | 0 | 0 | 0
652 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC , SM/10574 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Malancha w/s scheme (Zone-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 2240/BD | 28/07/2022 | 30 | M/S K.P.PAL. | 44.4 | 35.8 | 100 | 1
653 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC , SM/10574 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Malancha water supply scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | 2449/BD | 23/08/2022 | 90 | MONDAL & CO. (BASIRHAT). | 297.24 | 283.96 | 53.68 | 1
654 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC , SM/10574 | Augmentation | Material Requisition To Resource Division | 2577/BD | 31/08/2022 | 0 | Resource Division | 21.53 | 0 | 0 | 0
655 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC , SM/10574 | Augmentation | Material Requisition To Resource Division | 915/BD | 22/03/2023 | 0 | Resource Division | 22.12 | 0 | 0 | 0
656 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC , SM/10574 | Augmentation | Acceptance cum work order for Protection works in different places for protection of different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile for Augmention of Malancha w/s scheme (Z-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 2655/BD | 01/09/2023 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 50.24 | 50.08 | 100 | 37
657 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC , SM/10574 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II(Rep.) and III(New) (Zone-I) and Pump House No-I and II (Zone-II)(Rep.) under Malancha W/S Scheme District of 24 Pgs. (N) NIET NO. 32 OF EE/EMD OF 2022-23 (SL. NO. -15) | 1013/EMD | 09/03/2023 | 816 | MAHADEV ENTERPRISE | 66.24 | 0 | 0 | 40
658 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC , SM/10574 | Augmentation | Formal work order for Construction of 350 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Malancha water supply scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | 2863/BD | 20/09/2023 | 365 | M/S B.K.ENTERPRISE. | 152.47 | 48.24 | 31.64 | 75
659 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC , SM/10574 | Augmentation | Acceptance cum work order for Sand filling at ditch area for construction of temporary approach road for movement of winch machine and other allied machineries at OHR site within Malancha W/S scheme (Z-II), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 936/HSD | 29/05/2025 | 10 | M/S R.B.S.ENTERPRISE. | 0.96 | 0 | 0 | 0
660 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC , SM/10574 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Mouli mouza within Malancha w/s scheme (Z-II), Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | 999/HSD | 04/06/2025 | 10 | M/S R.B.S.ENTERPRISE. | 0.96 | 0 | 0 | 0
661 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC , SM/10574 | Augmentation | Acceptance cum work order for Withdrawing and relaying of different dia. UPVC pipe line at Mouli mouza in connection with augmentation of Malancha W/S scheme (Z-II), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 389/BD | 05/02/2025 | 60 | JESMINE ENTERPRISE. | 11.03 | 0 | 0 | 100
662 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC , SM/10574 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at OHR site within Malancha W/S scheme (Z-II), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 529/HSD | 10/03/2025 | 10 | M/S R.B.S.ENTERPRISE. | 0.95 | 0 | 0 | 100
663 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC , SM/10574 | Augmentation | Acceptance cum work order for Retrofitting work at Mouli Mouza in connection with Augmentation of Malancha w/s scheme (Z-II), Minkhan Block under Hasnabad Sub-Division, PHE Dte. | 896/BD | 20/03/2025 | 10 | JESMINE ENTERPRISE. | 8.3 | 0 | 0 | 100
664 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC , SM/10574 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Malancha Abad mouza within Malancha w/s scheme (Z-II), Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | 1487/HSD | 14/07/2025 | 10 | JESMINE ENTERPRISE. | 0.96 | 0 | 0 | 100
665 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12372 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-VI/B (Tapanpur) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 334/NWSD-I | 24/03/2022 | 31 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.33 | 4.21 | 100 | 1
666 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12372 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI, B (Tapanpur) in Amdanga Block of North 24 Parganas District. | 4032/ED | 17/10/2023 | 183 | ALPHA ENTERPRISE | 58.67 | 0 | 0 | 0
667 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12372 | Augmentation | Material Requisition To Resource Division | 487/NWSD-I | 26/04/2023 | 0 | Resource Division | 163.65 | 0 | 0 | 0
668 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12372 | Augmentation | Material Requisition To Resource Division | 1716/NWSD-I | 26/11/2024 | 0 | Resource Division | 14.78 | 0 | 0 | 0
669 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12372 | Augmentation | Shifting of HTOH Pole at Tapanpur , Amdanga Block . | 132/PFMS/24-25 | 30/07/2024 | 0 | WBSEDCL | 0.63 | 0 | 0 | 0
670 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12372 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 89.36 | 9.49 | 2
671 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12372 | Augmentation | Road restoration along flank portion of Rafipur Padmanavpur Kakinara PWD road, Sani Mandir (Node 481 ) to Tapanpur F.P School (Node - 30) due to laying of pipeline under Augmentation work at Tapanpur (Zone- VI B) W/S Scheme in Amdanga Block under North 24Pgs. W/S Division-I, P.H.E. Dte. | 776/NWSD-I | 23/05/2025 | 45 | SAHA CONSTRUCTION & CO. | 44.17 | 0 | 0 | 0
672 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kamlabas Water Supply Scheme at Bagdah Block (Phase-I) , SM/07849 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Kamlabas Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 135/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.26 | 3.26 | 100 | 1
673 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon , SM/10308 | Augmentation | Repairing & Renovation of 01No. Pump House and allied works at Krishnachandrapur water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 636/BON | 31/12/2021 | 21 | ACHINTA KUMAR HALDER. | 1.26 | 1.14 | 100 | 1
674 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon , SM/10308 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Krishnachandrapur Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation) | 1174/BD | 19/04/2022 | 90 | SUPRITI ENTERPRISE. | 392.59 | 260.82 | 100 | 1
675 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon , SM/10308 | Augmentation | Acceptance cum work order for Repair and renovation works of R.C.C. Elevated Reservoir of 456 cum for Krishnachandrapur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 189/BD | 20/01/2023 | 30 | TRISHA ENTERPRISE & CO. | 19.03 | 18.97 | 100 | 100
676 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon , SM/10308 | Augmentation | Material Requisition To Resource Division | 1362/BD | 13/05/2022 | 0 | Resource Division | 20.47 | 0 | 0 | 0
677 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon , SM/10308 | Augmentation | Material Requisition To Resource Division | 1674/BD | 13/06/2022 | 0 | Resource Division | 20.09 | 0 | 0 | 0
678 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon , SM/10308 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep) under Krishnachandrapur W/S Scheme and Chowberia W/S Scheme District of 24 Pgs. (N) | 4801/EMD | 09/08/2023 | 511 | A.G ENTERPRISE. | 52.15 | 24.13 | 100 | 100
679 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon , SM/10308 | Augmentation | Construction of Approach Road Head Work at site for Augmentation of Krishnacandrapur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 623/Bon | 08/08/2023 | 25 | ROY CHOWDHURY CONSTRUCTION. | 4.73 | 4.72 | 100 | 100
680 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon , SM/10308 | Augmentation | Acceptance cum work order for Sinking of 2 (two) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Krishnachandrapur Water Supply Scheme (H/W Site & 2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | 2945/BD | 27/09/2023 | 60 | JOY GURU ENTERPRISE | 32.24 | 28 | 100 | 100
681 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon , SM/10308 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Krishnachandrapur Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 535/BD | 21/02/2024 | 45 | ANKUSH CONSTRUCTION & CO. | 17.78 | 17.76 | 100 | 100
682 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon , SM/10308 | Augmentation | Providing boundary illumination arrangement and allied works at P/H No.I (OHR Site) of Krishnachandrapur ground water based W/S scheme under EMSD-I, PHE Dte. in 24Pgs(N). | 225/EMSD-I | 07/02/2025 | 45 | R.K. ENTERPRISES | 4.76 | 0 | 0 | 0
683 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon , SM/10308 | Augmentation | Formal Work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household and laying of UPVC Dedicated Main Pipe Line towards different mouza for better supply of drinking water along with pipe protection and Road Restoration work under Augmentation work at Krishnachandrapur W/S Scheme at Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 887/BD | 14/03/2024 | 711 | SAHA CONSTRUCTION & CO | 108.9 | 84.75 | 77.83 | 90
684 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon , SM/10308 | Augmentation | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site under Augmentation work at Krishnachandrapur W/S Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1542/BD | 15/05/2025 | 120 | B.S.ENTERPRISE. (BASIRHAT) | 51.11 | 0 | 0 | 0
685 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Krishnachandrapur to accommodate FHTC, Block - Bongaon , SM/10308 | Augmentation | Supply delivery & laying of cable with allied works at P.H. No. I and II of Krishnachandrapur Ground water based W/S Scheme under EMSD-I ,PHE Dte.in 24Pgs(N). | 226/EMSD-I | 07/02/2025 | 20 | A.G ENTERPRISE. | 4.31 | 0 | 0 | 100
686 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) , SM/08072 | Retrofitting | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places for providing FHTC within Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 1994/HSD | 02/12/2021 | 7 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 2 | 2 | 100 | 1
687 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) , SM/08072 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in Dholkhali & Tongtala mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 1670/BD | 08/09/2021 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 49.88 | 17.52 | 50 | 1
688 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) , SM/08072 | Retrofitting | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Dholkhali Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-A) | 22/HSD | 04/01/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.9 | 4.9 | 50 | 1
689 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) , SM/08072 | Retrofitting | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Tongtala Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-A) | 14/HSD | 04/01/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.91 | 4.91 | 50 | 1
690 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) , SM/08072 | Retrofitting | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Bouthakurani Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-A) | 18/HSD | 04/01/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.9 | 4.9 | 50 | 1
691 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) , SM/08072 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia. UPVC distribution pipeline for providing FHTC by UC bullah pile at different places within Bouthakurani w/s scheme (Zone-I to III), Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 421/HSD | 04/03/2022 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.73 | 4.78 | 100 | 1
692 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) , SM/08072 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia. UPVC distribution pipeline for providing FHTC by UC bullah pile at different places within Bouthakurani w/s scheme (Zone-IV to V), Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 422/HSD | 04/03/2022 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.73 | 4.73 | 100 | 1
693 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) , SM/08072 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line for providing FHTC by bamboo pilling at different places within Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 465/HSD | 10/03/2022 | 10 | R.K.MANDAL AND CO. | 4.85 | 4.85 | 50 | 1
694 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) , SM/08072 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Bouthakurani w/s scheme, Sandeshkhali-II Block under Hasnabad Sub- Division P.H.E. Dte. | 464/HSD | 10/03/2022 | 10 | R.K.MANDAL AND CO. | 3.39 | 3.39 | 50 | 1
695 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) , SM/08072 | Retrofitting | Material Requisition To Resource Division | 1818/BD | 19/06/2023 | 0 | Resource Division | 16.39 | 0 | 0 | 0
696 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Joypur Gopmahal Water Supply Scheme at Basirhat-II Block (Phase-I) , SM/07853 | Retrofitting | Acceptance cum Work Order for Sinking of 1 no. 300 mm. x 200 mm. dia. 214 mtr deep tube well by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Ward No.- 6 under Ashokenagar-Kalyangar Municipality within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 2452/BD | 17/12/2021 | 30 | NADIA TUBEWELLS | 2.89 | 2.89 | 100 | 1
697 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DIGHARI Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07599 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DIGHARI Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (PHASE-I). | 24/NWSD-I | 08/01/2021 | 90 | MONDAL ENTERPRISE | 68.79 | 114.76 | 86.36 | 1
698 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DIGHARI Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07599 | Retrofitting | Hiring of Diesel ambassador Car / Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer (HQ-I), North 24 Parganas W/S Division-I, P.H.E. Dte. [w.e.f. 01.06.2023 to 30.11.2023.(183 days)].(Car No.WB25J7778.) | 632/NWSD-I | 25/05/2023 | 183 | GITA DAS | 0.87 | 0.68 | 100 | 20
699 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DIGHARI Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07599 | Retrofitting | Continuation order for the work of Hiring of Diesel ambassador Car / Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer (HQ-I), North 24 Parganas W/S Division-I, P.H.E. Dte. [w.e.f. 01.12.2023 to 31.05.2024.(183 days)].(Car No.WB25J7778.) | 1920/NWSD-I | 29/11/2023 | 183 | GITA DAS | 0.87 | 1.39 | 320.02 | 16
700 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-II Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07604 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-II Water Supply Scheme at BONGAON Block under North 24 Parganas Water Supply Division - I, PHE Dte. (Phase-I) | 103/NWSD-I | 01/02/2021 | 90 | A.K.C. SUPPLY & CONSTRUCTION | 55.16 | 86.74 | 79.93 | 1
701 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-II Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07604 | Retrofitting | Continuation order for the work of Hiring of 1 (one) no Motor Cab / Maxi Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Executive Engineer, North 24 Parganas W/S Division-I, P.H.E. Dte. for 184 (one hundred eighty four) days w.e.f 01/03/2023 to 31/08/2023.[Car No.WB 25L 4241]. | 168/NWSD-I | 16/02/2023 | 184 | M/S. SHUBHA ENTERPRISE | 0.87 | 1.02 | 100 | 65
702 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AULDANGA Water Supply Scheme at BAGDAH Block (PHASE-I) , SM/07605 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AULDANGA Water Supply Scheme at BAGDAH Block under North 24 Parganas water supply Division - I, PHE Dte. (PHASE-I). | 74/NWSD-I | 20/01/2021 | 90 | A.K.C. SUPPLY & CONSTRUCTION | 71.32 | 112.91 | 80.77 | 1
703 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AULDANGA Water Supply Scheme at BAGDAH Block (PHASE-I) , SM/07605 | Retrofitting | Hiring of Diesel ambassador Car / Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer (HQ-I), North 24 Parganas W/S Division-I, P.H.E. Dte. [w.e.f. 01.06.2023 to 30.11.2023.(183 days)].(Car No.WB25J7778.) | 632/NWSD-I | 25/05/2023 | 183 | GITA DAS | 0.87 | 1.15 | 100 | 20
704 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AULDANGA Water Supply Scheme at BAGDAH Block (PHASE-I) , SM/07605 | Retrofitting | Continuation order for the work of Hiring of Diesel ambassador Car / Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer (HQ-I), North 24 Parganas W/S Division-I, P.H.E. Dte. [w.e.f. 01.12.2023 to 31.05.2024.(183 days)].(Car No.WB25J7778.) | 1920/NWSD-I | 29/11/2023 | 183 | GITA DAS | 0.87 | 0.74 | 169.4 | 16
705 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Deora Water Supply Scheme at Swarupnagar Block (Phase-II) , SM/07618 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Deora W/S Scheme in Swarupnagar Block under Barasat Division, P.H.E. Dte. | 126/HAB | 16/03/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.23 | 3.19 | 100 | 1
706 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dhalani Water Supply Scheme at Bagdah Block (Phase-I) , SM/07846 | Retrofitting | - Hiring of Luxury Car (Diesel) for the office use of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Bongaon Sub-Division P.H.E. Dte. (Period from 01.02.2021 to 31.01.2022.) | 77/Bon | 29/01/2021 | 365 | ROY ENGINEERS. | 1.73 | 0 | 0 | 1
707 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dhalani Water Supply Scheme at Bagdah Block (Phase-I) , SM/07846 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAGDAH Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-I) | 990/BD. | 27/05/2021 | 45 | UMWELT ENGINEER PVT.LTD. | 89.35 | 11.75 | 41.9 | 1
708 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chowlpur and Its Adjoining mouzas water Supply Scheme for providing Functional House Tap Connection under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08728 | Retrofitting | Providing Functional School, Anganwadi and Health Center Tap Connection and allied works of Command area at Chowlpur & others Ground Water Supply Scheme under Barasat-II Block Under '' JAL SWAPNA'' programme under Barasat Arsenic Division, PHE Dte. | 364/B.Ar.D | 03/03/2022 | 15 | SANTU GHOSH | 3.91 | 3.9 | 50 | 1
709 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chowlpur and Its Adjoining mouzas water Supply Scheme for providing Functional House Tap Connection under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08728 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and allied works Malrameswarpur, Kharigacchi, Chaturbhujpur and Kalikapur mouza of Barasat-II Block from Chowlpur & Its Adjoining Mouzas Ground Water Supply Scheme Under "JAL SWAPNA" programme under Barasat Arsenic Division, PHE Dte. Phase-II | 2077/B.Ar.D. | 02/12/2021 | 90 | BANERJEE CONSTRUCTION | 99.13 | 98.52 | 99.38 | 100
710 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chowlpur and Its Adjoining mouzas water Supply Scheme for providing Functional House Tap Connection under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08728 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling (approx. 48 mtr length) for protection of different dia UPVC/HDPE Pipeline near pond of Sardarhati opposite Sardarhati Hari Mandir under Chowlpur W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | 265/B.Ar.D | 18/02/2022 | 20 | M/S DAS & CO | 4.71 | 0 | 0 | 0
711 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chowlpur and Its Adjoining mouzas water Supply Scheme for providing Functional House Tap Connection under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08728 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling (approx. 50 mtr length) for protection of different dia UPVC/HDPE Pipeline near two ponds at Ghoradaria opposite Ranjit Mandal house and at Malrameswarpur Sardarhati opposite Pradip Sarkar house under Chowlpur W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | 563/B.Ar.D | 23/03/2022 | 15 | NANDY UDYOG | 4.66 | 0 | 0 | 0
712 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chowlpur and Its Adjoining mouzas water Supply Scheme for providing Functional House Tap Connection under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08728 | Retrofitting | Road restoration due to laying of various dia UPVC/HDPE Pipe distribution line at Kalikapur of Chowlpur W/S Scheme under Barasat -II block under Barasat Arsenic Division, PHE Dte. | 36/B.Ar.D | 05/01/2023 | 21 | P. & S. ASSOCIATES | 0.95 | 0.93 | 100 | 1
713 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Khulna Bhanderkhali Piped Water Supply Scheme (Zone-I), Sandeshkhali-II Block (Phase-I) , SM/08762 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in different mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Khulna Bhandarkhali (Zone-I) Water Supply scheme Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte.(Phase-I) | 1740/BD | 14/09/2021 | 45 | M/S B.K.ENTERPRISE. | 76.95 | 76.79 | 99.79 | 1
714 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Khulna Bhanderkhali Piped Water Supply Scheme (Zone-I), Sandeshkhali-II Block (Phase-I) , SM/08762 | Retrofitting | Acceptance cum work order for Emergent restoration of existing pilling works to sustain the protection of UPVC distribution pipe line at different places within Khulna Bhanderkhali w/s scheme (Zone-I), Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1981/HSD | 02/12/2021 | 10 | M/S NIRMAN CONSTRUCTION. | 3.54 | 3.54 | 100 | 1
715 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Paschim Panchberia Zone-I WaterSupply Scheme at Bongaon Block (Phase-II). , SM/08236 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PASCHIM PANCHBERIA ZONE-I Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (PHASE-II). | 850/NWSD-I | 07/10/2021 | 60 | B. S. ENTERPRISE | 68.7 | 70.56 | 53.93 | 1
716 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Santoshpur Zone-II Water SupplyScheme at Bongaon Block (Phase-II). , SM/08238 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-II Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (PHASE-II). | 848/NWSD-I | 07/10/2021 | 60 | M/S. R. M. CONSTRUCTION | 62.2 | 61.73 | 54.65 | 1
717 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Jashaikati Zone I & Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- I) . , SM/08245 | Retrofitting | Route survey, distribution design & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Jasaikhati Zone - I & its adjoining mouza Water Supply Scheme in Baduria Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | 1441/B.Ar.D | 31/08/2021 | 15 | SIRCON ENGINEERING SERVICES | 4.7 | 4.7 | 50 | 1
718 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Jashaikati Zone I & Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- I) . , SM/08245 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Mulluk Chand at danga uttarpara and Sumon Mondal at uttar chowdhury para under Jasaikathi - I W/S Scheme at Baduria block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | 482/B.Ar.D | 16/03/2022 | 15 | TEN STAR ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.58 | 4.58 | 50 | 1
719 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Jashaikati Zone I & Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- I) . , SM/08245 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at kankrasuti mouza of Baduria Block from Jashaikati Zone -I & Its Adjoining Mouzas Ground Water Supply Scheme Under '' JAL SWAPNA'' programme under Barasat Arsenic Division PHE, Dte. (Phase-I). | 1035/B.Ar.D. | 07/06/2021 | 90 | UTPAL CONSTRUCTION AND CO | 96.04 | 28.31 | 29.47 | 100
720 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Jashaikati Zone I & Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- I) . , SM/08245 | Retrofitting | Bullah Pilling for protection of Pipeline ( Approx 60 m) near pond of Sumon Haldar at Jasaikathi (Z-I) W/S Scheme at Baduria Block under Jal Swapna Programme under Barasat Arsenic Division, P.H.E. Dte. | 2232/B.Ar.D | 28/12/2021 | 30 | M/S DATTA ENTERPRISE | 4.45 | 4.44 | 99.78 | 100
721 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Jashaikati Zone II & Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- I) . , SM/08246 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Ramchandrapur mouza of Baduria Block from Jashaikati Zone -II & Its Adjoining Mouzas Ground Water Supply Scheme Under '' JAL SWAPNA'' programme under Barasat Arsenic Division PHE, Dte. (Phase-I) | 1036/B.Ar.D. | 07/06/2021 | 90 | M/S. S. S. ENTERPRISE | 91.6 | 80.27 | 60.86 | 1
722 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dobila Piped Water Supply Scheme, Swarupnagar Block under Barasat Division, P.H.E.Dte. (Phase-II) , SM/08769 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Dobila Piped Water Supply Scheme at Swarupnagar Block under Barasat Division, PHE Dte. (Phase II) | 1954/BD | 08/10/2021 | 15 | M/S SUKANTA ENTERPRISE. | 14.73 | 13.84 | 93.96 | 1
723 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dobila Piped Water Supply Scheme, Swarupnagar Block under Barasat Division, P.H.E.Dte. (Phase-II) , SM/08769 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Matiagacha W/S Scheme in Habra - II Block under Barasat Division, P.H.E. Dte. | 128/HAB | 16/03/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.35 | 0 | 0 | 1
724 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dobila Piped Water Supply Scheme, Swarupnagar Block under Barasat Division, P.H.E.Dte. (Phase-II) , SM/08769 | Retrofitting | Material Requisition To Resource Division | 2863/BD | 21/09/2022 | 0 | Resource Division | 3.08 | 0 | 0 | 0
725 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Joypur Gopmahal Piped Water Supply Scheme, Basirhat-II Block under Barasat Division, P.H.E.Dte. (Phase-II) , SM/08772 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Joypur Gopmahal Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase II) | 1951/BD | 08/10/2021 | 15 | SHIBU BISWAS. | 21.73 | 20.05 | 50 | 1
726 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Joypur Gopmahal Piped Water Supply Scheme, Basirhat-II Block under Barasat Division, P.H.E.Dte. (Phase-II) , SM/08772 | Retrofitting | Sinking of 300 Mtr.Deep 100X40 mm dia Trial- cum-production Tube-Well fitting with PVC Pipes and strainer with Indian Mark-II at Joypur Gopmahal of Basirhat-II Block under Barasat Division PHE Dte. | 1111/ BHT SD | 27/08/2021 | 20 | M/S MAA TARA ENTERPRISE | 2.34 | 1.95 | 50 | 1
727 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area DHOPABERIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08638 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Dhopaberia Water Supply Scheme at Basirhat-II Block under Barasat Division, PHE Dte. (Phase-I). | 1652/BD | 07/09/2021 | 30 | UTPAL CONSTRUCTION & CO. | 53.77 | 52.68 | 100 | 1
728 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area DHOPABERIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08638 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for DHOPABERIA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 310/BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.6 | 3.6 | 100 | 1
729 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area DHOPABERIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08638 | Retrofitting | Material Requisition To Resource Division | 2242/BD | 24/11/2021 | 0 | Resource Division | 10.26 | 0 | 0 | 0
730 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Mirzanagar Piped Water Supply Scheme at Basirhat-II Block (Phase-I) , SM/08639 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for MIRZANAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 307/BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.78 | 3.69 | 100 | 1
731 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Mirzanagar Piped Water Supply Scheme at Basirhat-II Block (Phase-I) , SM/08639 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Mirzanagar Water Supply Scheme at Basirhat-II Block under Barasat Division, PHE Dte.(Phase-I). | 1656/BD | 07/09/2021 | 45 | CHANCHAL ENTERPRISE & CO. | 85.87 | 83.5 | 100 | 1
732 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Jadavpur, Khanpur, Odhanpur, Kumarpur, Fazilpur, Rampur & Sohai mouzas (Part) within Sohai Swetpur Zone-II Piped Water Sup , SM/08652 | Retrofitting | Repairing & Renovation of 1 No. Pump House (Size- 5.20 x 7.20) of Head Work Site and allied works at Sohai Swetpur Water Supply Scheme Zone-II under Barasat Sub-Division, P.H.E.Dte. | 818/BSD | 10/12/2021 | 30 | BHABANI ENTERPRISE. | 1.84 | 1.75 | 94.67 | 0
733 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kachua Swarupnagar Piped Water Supply Scheme at Basirhat-II Block (Phase-I) , SM/08660 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Kachua Swarupnagar Water Supply Scheme at Basirhat-II Block under Barasat Division, PHE Dte.(Phase-I). | 1654/BD | 07/09/2021 | 45 | UTPAL CONSTRUCTION & CO. | 86.71 | 85.64 | 100 | 1
734 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kachua Swarupnagar Piped Water Supply Scheme at Basirhat-II Block (Phase-I) , SM/08660 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for KACHUA SWARUPNAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 308/BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.29 | 4.07 | 100 | 1
735 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Additional survey work for DPR Preparation for SIMLA DURGAPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 377/BHTSD | 16/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.66 | 0 | 0 | 1
736 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for RAJENDRAPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 311/BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.19 | 0 | 0 | 1
737 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for RAJNAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 208/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.72 | 0 | 0 | 1
738 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for GOBINDAPUR DHOKRA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 205/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.86 | 0 | 0 | 1
739 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Ghatpatila (Zone-II) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 131/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.89 | 0 | 0 | 1
740 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Kola Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 136/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.64 | 0 | 0 | 1
741 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Kurulia (Zone-I) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 138/Bon | 18/02/2022 | 15 | UMWELT ENGINEER PVT.LTD. | 4.05 | 0 | 0 | 1
742 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Chhaygharia (Zone-I) Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 123/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.45 | 0 | 0 | 1
743 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Chhaygharia (Zone-III) Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 125/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.42 | 0 | 0 | 1
744 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Chowberia Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 127/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.45 | 0 | 0 | 1
745 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Gadpukuria (Zone-II) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 129/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.73 | 0 | 0 | 1
746 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Malidah Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 140/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.74 | 0 | 0 | 1
747 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Kapileswarpur Water Supply Scheme at Swarupnagar Block under Barasat Division, PHE Dte. (Phase - I) | 940/BD | 28/03/2022 | 90 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 164.9 | 108.96 | 100 | 1
748 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for PASCHIM MADHYAMPUR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | 197/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.24 | 0 | 0 | 1
749 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for GACHHARATI Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | 199/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.69 | 0 | 0 | 1
750 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for NALKORA Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | 202/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.79 | 0 | 0 | 1
751 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for SADIKNAGAR-I Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 206/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.15 | 0 | 0 | 1
752 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for DAKSHIN DEBIPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 312/BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.87 | 0 | 0 | 1
753 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Bansghata Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 142/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 0 | 0 | 1
754 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for SRINAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 342/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.1 | 0 | 0 | 1
755 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Chhaygharia (Zone-II) Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 124/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.98 | 0 | 0 | 1
756 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Kapileswarpur W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09735 | Retrofitting | Material Requisition To Resource Division | 2866/BD | 21/09/2022 | 0 | Resource Division | 0.1 | 0 | 0 | 0
757 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Janaphul Piped Water Supply Scheme at Habra-I Block (Phase-I) , SM/08780 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Janaphul Water Supply Scheme at Habra-I Block within the jurisdiction of Habra Sub-Division, under Barasat Division, PHE Dte. (Phase-I). | 2389/BD | 09/12/2021 | 45 | ORIENT CONSTRUCTION. | 72.42 | 67.56 | 100 | 1
758 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Janaphul Piped Water Supply Scheme at Habra-I Block (Phase-I) , SM/08780 | Retrofitting | Acceptance cum work order for Supply of Mechanized boat on hire basis with providing driver, helper and other requirement as per terms condition and specification as per direction of the EIC under Hasnabad Sub-Division, P.H.E. Dte. Period : 01.08.2022 to 31.07.2023 = 365 days. | 1118/HSD | 08/07/2022 | 1 | RANJIT KUMAR MANDAL. | 3.23 | 11.93 | 100 | 100
759 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Janaphul Piped Water Supply Scheme at Habra-I Block (Phase-I) , SM/08780 | Retrofitting | Acceptance cum Work Order for Hiring of 1(one) number vehicle of Category Motor Cab/Maruti Omni(standard)(Non Air-Conditioned)/LPG/CNG Engine including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub-Division, P.H.E. Dte. at Barrackpore, Kolkata-700122, District- North 24Pgns, W.B. | 253/BKP | 31/07/2023 | 184 | GOPAL SINGHA. | 0.87 | 0.67 | 100 | 40
760 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Magurali Piped Water Supply Scheme at Baduria Block (Phase-I) , SM/08785 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area under Magurali Water Supply Scheme at Baduria Block, District- North 24 Parganas under Barasat Division, PHE Dte.(Phase-I). | 2439/BD | 13/12/2021 | 90 | UTPAL CONSTRUCTION & CO. | 232.79 | 205.13 | 100 | 1
761 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Magurali Piped Water Supply Scheme at Baduria Block (Phase-I) , SM/08785 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for MAGURALI Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 350/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.96 | 4.96 | 100 | 1
762 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Itinda Panitor Piped Water Supply Scheme at Basirhat-I Block (Phase-I) , SM/08786 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Itinda Panitar Water Supply Scheme at Basirhat - I Block under Barasat Division, PHE Dte. (Phase - I) | 2622/BD | 27/12/2021 | 90 | SUBHASH BOSE. | 171.59 | 164.59 | 100 | 1
763 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Itinda Panitor Piped Water Supply Scheme at Basirhat-I Block (Phase-I) , SM/08786 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for ITINDA PANITOR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | 189/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 100 | 1
764 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Itinda Panitor Piped Water Supply Scheme at Basirhat-I Block (Phase-I) , SM/08786 | Retrofitting | Material Requisition To Resource Division | 598/BD | 23/02/2023 | 0 | Resource Division | 22.18 | 0 | 0 | 0
765 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of ARSULA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/08787 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for ARSULA Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 359/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.34 | 3.34 | 100 | 1
766 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of ARSULA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/08787 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Arsula Water Supply Scheme at Baduria Block under Barasat Division, PHE Dte.(Phase-I) | 2437/BD | 13/12/2021 | 90 | M/S S.S.ENTERPRISE. (SOUTH) | 194.62 | 160.59 | 100 | 1
767 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of ARSULA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/08787 | Retrofitting | Material Requisition To Resource Division | 2340/BD | 26/09/2022 | 0 | Resource Division | 18.3 | 0 | 0 | 0
768 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate , SM/10533 | Augmentation | Repairing & renovation of Pump House No. - 1 & 2 of Maslandapur W/S scheme (Zone - II) within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 490/HAB | 30/11/2021 | 30 | ANJALI CONSTRUCTION. | 2.18 | 2.17 | 100 | 1
769 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate , SM/10533 | Augmentation | Material Requisition To Resource Division | 3790/BD | 22/12/2022 | 0 | Resource Division | 34.22 | 0 | 0 | 0
770 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate , SM/10533 | Augmentation | Material Requisition To Resource Division | 2515/BD | 25/08/2022 | 0 | Resource Division | 22.72 | 0 | 0 | 0
771 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate , SM/10533 | Augmentation | Material Requisition To Resource Division | 1558/BD | 23/05/2023 | 0 | Resource Division | 1.85 | 0 | 0 | 0
772 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate , SM/10533 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II & III (Zone-II) under Maslandapur W/S Scheme (Rep.) District of 24 Pgs. (N) NIET No.- 29 of EE/EMD of 2022-23 (Sl. No.- 27) | 1321/EMD | 29/03/2023 | 30 | A.K. ENTERPRISE | 31.79 | 26.94 | 84.74 | 80
773 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate , SM/10533 | Augmentation | construction of the Service Road 35.00 Mtr. Length and 3.00 Mtr. Wide while 1.00 Mtr. wide road already existing in Head Work Site of Maslandapur- II Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 916/HAB | 30/10/2024 | 10 | M/S GUHA CONSTRUCTION. | 2.26 | 0 | 0 | 0
774 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate , SM/10533 | Augmentation | Acceptance cum work order for Construction of the Boundary wall in Pump House No. 2 of Maslandapur- II Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 2410/BD | 22/08/2024 | 35 | M/S MITRA CONSTRUCTION | 5.71 | 0 | 0 | 0
775 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate , SM/10533 | Augmentation | Acceptance cum work order for Sinking of 1 no. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Head Work Site of Maslandapur water supply scheme (Zone - II) within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | 1406/BD | 08/05/2023 | 30 | ARUN TRADERS | 14.49 | 13.43 | 100 | 100
776 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate , SM/10533 | Augmentation | Improvement of Iron Elimination Plant at Maslandapur Zone II WS Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 671/HAB | 30/10/2023 | 30 | S.G. ENTERPRISE | 4.47 | 4.42 | 100 | 100
777 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate , SM/10533 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 300 mm. dia. 36 mtr. long housing pipe & 200 mm. dia. 30 mtr. long Filter at Pump House No. - 2 of Maslandapur(Zone - II) water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | 07/BD | 02/01/2024 | 30 | M/S B.K.ENTERPRISE. | 19.45 | 16.71 | 100 | 100
778 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate , SM/10533 | Augmentation | Construction of Service Road (10 Mtr. Length & 2 Mtr. Wide while 1.00 Mtr existing Road ) for Pump House No:2 of Maslandapur II Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 134/HAB | 05/02/2024 | 15 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 0.75 | 0.73 | 100 | 100
779 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate , SM/10533 | Augmentation | Formal Work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Maslandapur Water Supply Scheme (Zone - II) within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 2448/BD | 23/08/2022 | 900 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 526.45 | 381.78 | 72.52 | 1
780 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate , SM/10533 | Augmentation | Acceptance cum work order for Construction of the Boundary wall in Pump House No. 3 of Maslandapur- II Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 2409/BD | 22/08/2024 | 45 | JOY ENTERPRISE | 6.1 | 6.04 | 100 | 100
781 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate , SM/10533 | Augmentation | Acceptance cum work order for Construction of boundary wall for raising height, drain and repairing of existing boundary wall for the Head Work site of Maslandapur II Piped water supply scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 3160/BD | 14/11/2024 | 40 | S.G. ENTERPRISE | 5.12 | 0 | 0 | 100
782 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate , SM/10533 | Augmentation | Construction of Service Road (10 Mtr. Length & 2 Mtr. Width) for Pump House No:3 of Maslandapur II Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 135/HAB | 05/02/2024 | 15 | JOY ENTERPRISE | 0.6 | 0.6 | 100 | 100
783 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-II to accommodate , SM/10533 | Augmentation | Repair and renovation of High Lift Pump House, Clorine Room and CWR in the Head Work site of Maslandapur II Piped water supply scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 935/HAB | 06/11/2024 | 40 | ANJALI CONSTRUCTION. | 3.86 | 0 | 0 | 100
784 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10556 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with retrofitting of Kanmari w/s scheme (Zone-I), Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 99/BD | 11/01/2023 | 90 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 282.73 | 277.6 | 98.19 | 1
785 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10556 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Kanmari mouza due to erosion of soil for heavy rain fall during monsoon season within Kanmari w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 1082/HSD | 31/08/2023 | 10 | SARKAR ENTERPRISE | 0.93 | 0.92 | 100 | 100
786 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10556 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Nalkora mouza due to erosion of soil for heavy rain fall during monsoon season within Kanmari w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 1083/HSD | 31/08/2023 | 10 | SARKAR ENTERPRISE | 0.92 | 0.92 | 100 | 100
787 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10556 | Retrofitting | Material Requisition To Resource Division | 1828/BD | 29/06/2022 | 0 | Resource Division | 195.63 | 0 | 0 | 0
788 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10556 | Retrofitting | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Kanmari water supply scheme (Zone-I), Sandeshkhali-I Block of Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | 4180/BD | 30/10/2023 | 1087 | TRISHA ENTERPRISE & CO. | 113.9 | 72.36 | 63.53 | 70
789 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10556 | Retrofitting | Acceptance cum work order for Construction of boundary wall with RCC column structure at PH No-1 & 2 within Kanmari w/s scheme (Z-I), Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 4406/BD | 10/11/2023 | 90 | NIKHIL SAMADDAR | 26.72 | 10.03 | 37.55 | 70
790 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Bhangatushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10510 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Bhangatushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 1668/BD | 13/06/2022 | 90 | S. GHOSH & ASSOCIATES PVT. LTD. | 168.43 | 167.55 | 100 | 1
791 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Bhangatushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10510 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC pipe line at different places at Bhanga Tushkhali mouza within Bhanga Tushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 536/HSD | 16/03/2022 | 15 | MD.SALIM GAZI. | 4.75 | 4.68 | 100 | 1
792 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Bhangatushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10510 | Retrofitting | Acceptance cum work order for Sinking of Additional 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tube well by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Bhangatushkhali W/s Scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 3311/BD | 27/11/2024 | 30 | SUBHAJIT SAHA | 31.69 | 0 | 0 | 0
793 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Bhangatushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10510 | Retrofitting | Formal work order for Protection work in different places of Bhangatushkhali Mouza in connection with retrofitting of Bhangatushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1697/BD | 08/06/2023 | 30 | AMAL DUTTA ROY | 167.81 | 150.24 | 100 | 100
794 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Bhangatushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10510 | Retrofitting | Acceptance cum work order for Construction of additional 1 no. switch room cum chlorine room (5.40x3.60) with sanitary and water supply arrangement including plinth protection within Bhangatushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 143/BD | 13/01/2025 | 75 | PRITAM MUKHOPADHYAY. | 8.88 | 0 | 0 | 0
795 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC , SM/10706 | Augmentation | Repairing & renovation of Pump House No. ¿ 1 & 2 of Talsa& adj. mouzas W/S scheme within the jurisdiction of Habra Sub-Division under BarasatDivision, P.H.E. Dte. | 515/HAB | 10/12/2021 | 30 | DAS & CO. | 1.55 | 1.51 | 100 | 1
796 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC , SM/10706 | Augmentation | Material Requisition To Resource Division | 3792/BD | 22/12/2022 | 0 | Resource Division | 14.47 | 0 | 0 | 0
797 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC , SM/10706 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Talsa & Adj. Mouzas Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 2313/BD | 03/08/2022 | 90 | M/S B.K.ENTERPRISE. | 230.62 | 208.82 | 100 | 1
798 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC , SM/10706 | Augmentation | Acceptance cum work order for Construction of Service Road(10 Mtr. Length X 2 Mtr. Width) for Pump House No:2 of Talsa & Adj Mouzas Water Supply Scheme in connection with Augmentation work undeer JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 172/HAB | 19/02/2024 | 15 | M/S LATIKA CONSTRUCTION. | 0.61 | 0 | 0 | 0
799 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC , SM/10706 | Augmentation | Acceptance cum work order for Construction of Boundary Wall for Pump House No - 2 of Talsa & Adj Mouzas water Supply Scheme in connection with Augmentation work under JJM project with in the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | 3065/BD | 25/10/2024 | 40 | PUSPA CONSTRUCTION. | 5.62 | 0 | 0 | 0
800 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC , SM/10706 | Augmentation | Special repair and renovation of pump house and other Allied Works for Pump House No - 2 of Talsa and Adj Mouzas W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 932/HAB | 05/11/2024 | 20 | M/S SANKAR ENTERPRISE. | 2.58 | 0 | 0 | 0
801 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC , SM/10706 | Augmentation | Special repair and renovation of pump house and other Allied Works of Pump House No - 1 under Talsa and Adj Mouzas WS scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 936/HAB | 06/11/2024 | 20 | TALUKDER & CO. | 2.66 | 0 | 0 | 0
802 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC , SM/10706 | Augmentation | Acceptance cum work order for Construction of Boundary Wall (90 m Length) for Pump House no 1 of Talsa & Adj Mouzas water Supply Scheme in connection with Augmentation work under JJM project with in the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | 2583/BD | 05/09/2024 | 45 | BRIGHT STAR CO-OP LABOUR CONTRACTOR & CONSTRUCTION SOCIETY LTD. | 14.76 | 0 | 0 | 0
803 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC , SM/10706 | Augmentation | Construction of Service Road 40 Mtr. Length X 2 Mtr. Width for Pump House No 1 of Talsa and Adj Mouzas Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 920/HAB | 30/10/2024 | 10 | TALUKDER & CO. | 2.44 | 0 | 0 | 0
804 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC , SM/10706 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Rep.) under Talsa and adj. mouzas W/S Scheme and Talsa W/S Scheme with Pump House No-I under Chandpur (Block-Hasnabad) W/S Scheme District of 24 Pgs. (N) | 4803/EMD | 09/08/2023 | 30 | M/S S.R. ENTERPRISE | 60.76 | 21.88 | 100 | 80
805 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC , SM/10706 | Augmentation | Acceptance cum work order for Sinking of 2 no. 300 mm. x 200 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 300 mm. dia. 36 mtr. long housing pipe & 200 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 for Augmentation of Talsa & Adj Mouzas water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | 2779/BD | 11/09/2023 | 60 | M/S SUKANTA ENTERPRISE. | 39.1 | 30.09 | 100 | 100
806 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Talsa & Adjoining mouzas to accommodate FHTC , SM/10706 | Augmentation | Improvement of Iron Elimination Plant at Talsa & Adj. Mouzas W/S Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 672/HAB | 30/10/2023 | 30 | M/S SANKAR ENTERPRISE. | 3.29 | 3.23 | 100 | 100
807 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. , SM/10607 | Augmentation | Survey, Design and preparation of Augmentation DPR in connection with Providing functional household tap connection to every Household under Palla Zone-II W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte. | 1174/NWSD-I | 31/12/2021 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.65 | 4.65 | 100 | 1
808 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. , SM/10607 | Augmentation | Material Requisition To Resource Division | 1210/NWSD-I | 13/10/2022 | 0 | Resource Division | 0.04 | 0 | 0 | 0
809 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. , SM/10607 | Augmentation | Material Requisition To Resource Division | 458/NWSD-I | 26/04/2023 | 0 | Resource Division | 229.11 | 0 | 0 | 0
810 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. , SM/10607 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1430/NWSD-I | 18/09/2024 | 7 | BIBHAS PAL | 5.27 | 0.35 | 50 | 100
811 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. , SM/10607 | Augmentation | New service connection at P.H.No- I ,Zone - II of Palla water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). | BP-386-23-24 | 28/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.63 | 0 | 0 | 0
812 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. , SM/10607 | Augmentation | Construction of approach road by jhama metal with allied works in front of Palla zone-II OHR site & Road Restoration within the command area under Palla Zone-II at Bongaon Block in the District of North 24 Pgs under North 24 Pgs W/S Division-I, P.H.E. Dte. | 798/NWSD-I | 28/05/2025 | 240 | M/S. TARAK CHANDRA PAUL | 15.46 | 0 | 0 | 75
813 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Talsa and Adjoining mouzas Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-I) , SM/07615 | Retrofitting | Continuation work order for the work of Hiring Diesel Luxury Car on daily basis ( from 01-01-2022 to 30-06-2022) for the Office use of the Dy. Superintending Engineer-I, Monitoring Cell, PHE Dte | 2688/ BD | 31/12/2021 | 181 | DIPANKAR NASKAR. | 0.86 | 0 | 0 | 1
814 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Talsa and Adjoining mouzas Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-I) , SM/07615 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Kurulia (Zone-II) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 139/Bon | 18/02/2022 | 15 | UMWELT ENGINEER PVT.LTD. | 3.86 | 3.86 | 100 | 1
815 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-V/A (Kharki) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12563 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-V/A (Kharki) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 419/NWSD-I | 01/04/2022 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.9 | 4.9 | 100 | 1
816 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-V/A (Kharki) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12563 | Augmentation | Material Requisition To Resource Division | 477/NWSD-I | 26/04/2023 | 0 | Resource Division | 210.38 | 0 | 0 | 0
817 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-V/A (Kharki) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12563 | Augmentation | Material Requisition To Resource Division | 1712/NWSD-I | 26/11/2024 | 0 | Resource Division | 17.86 | 0 | 0 | 0
818 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-V/A (Kharki) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12563 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 109.71 | 14.65 | 2
819 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-V/A (Kharki) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12563 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1431/NWSD-I | 18/09/2024 | 7 | IMAGIN | 4.59 | 0 | 0 | 95
820 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bara Bankra to accommodate FHTC , SM/11704 | Augmentation | Material Requisition To Resource Division | 1271/BD | 25/04/2023 | 0 | Resource Division | 149.36 | 0 | 0 | 0
821 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bara Bankra to accommodate FHTC , SM/11704 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Baro Bankra water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | 1720/BD | 08/06/2023 | 642 | MADE & TRADE CO. | 433.09 | 343.7 | 79.36 | 58
822 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bara Bankra to accommodate FHTC , SM/11704 | Augmentation | Regarding Restoration charges for road damages. | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 31.71 | 0 | 0 | 0
823 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bara Bankra to accommodate FHTC , SM/11704 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II, III and IV (Rep.) under Nalabara W/S Scheme and Pump House No-I and II under Barabankra W/S Scheme District of 24 Pgs. (N) | 4811/EMD | 09/08/2023 | 662 | M/S. SAJAHAN CHOWDHURY | 78.21 | 3.67 | 14.08 | 46
824 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bara Bankra to accommodate FHTC , SM/11704 | Augmentation | Acceptance cum work order for special repair renovation of existing structures like Pump house, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Akhipur, Baro Bankra, Bithari Z-I, Bithari Z-II water supply scheme of different block under Basirhat Sub-Division, PHE Dte. | 2381/BD | 10/07/2025 | 150 | JP CONSTRUCTION & SUPPLIERS. | 81.91 | 0 | 0 | 0
825 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bara Bankra to accommodate FHTC , SM/11704 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method at pump house 1 using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Boro Bankra Water Supply Scheme in Swarupnagar Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | 3265/BD | 25/11/2024 | 120 | JOY GURU ENTERPRISE | 21.74 | 0 | 0 | 100
826 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC , SM/11585 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Jafarpur water supply scheme in Basirhat-II Block under Barasat Division, P.H.E Dte. | 3763/BD | 20/12/2022 | 90 | H.I.ENTERPRISE. | 438.55 | 438.38 | 100 | 82
827 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC , SM/11585 | Augmentation | Material Requisition To Resource Division | 489/BD | 17/02/2023 | 0 | Resource Division | 28.3 | 0 | 0 | 0
828 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC , SM/11585 | Augmentation | Relaying of 90mm, 110mm, 125mm, 160mm dia UPVC pipe line which damaged due to strengthening and culvert construction in Gopalpur Haroa road by PWD (Roads) Department at Node no. 429/465 & 543 to 563 of Zafarpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | 1023/BHTSD | 28/06/2024 | 7 | RAKESH ENTERPRISE. | 0.99 | 0.99 | 100 | 100
829 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC , SM/11585 | Augmentation | Relaying of 90mm, 110mm dia UPVC pipe line and repairing of FHTC connection which damaged due to construction of drain from local Panchayet at Node no. 103 to 137 of Zafarpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | 1022/BHTSD | 28/06/2024 | 7 | RAKESH ENTERPRISE. | 0.89 | 0.27 | 23.5 | 100
830 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC , SM/11585 | Augmentation | Repairing of damaged concrete road due to laying of Pipe Line in various place of zafarpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. [SM/11585] | 916/BHTSD | 24/05/2024 | 7 | RAKESH ENTERPRISE. | 0.96 | 0 | 0 | 100
831 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC , SM/11585 | Augmentation | Relaying of 160mm dia UPVC pipe line and repairing of FHTC connection which damaged due to strengthening and culvert construction in Gopalpur Haroa road by PWD (Roads) Department at Node no. 190 to 57 of Zafarpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | 1025/BHTSD | 28/06/2024 | 7 | RAKESH ENTERPRISE. | 0.96 | 0 | 0 | 100
832 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC , SM/11585 | Augmentation | Relaying of 75mm, 90mm, 110mm, 160mm dia UPVC pipe line which damaged due to strengthening and culvert construction in Gopalpur Haroa road by PWD (Roads) Department at Node no. 402 to 190 to 57 of Zafarpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | 1024/BHTSD | 28/06/2024 | 7 | RAKESH ENTERPRISE. | 0.99 | 0 | 0 | 100
833 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC , SM/11585 | Augmentation | Enhancement of GST for providing Functional Household Tap Connection (FHTC) in connection with JJM and Jal Swapna Programme within command area of Jafarpur WS Scheme | BP-2024-25-262 | 12/09/2024 | 0 | H.I.ENTERPRISE. | 23.64 | 0 | 0 | 0
834 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC , SM/11585 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method at Pump House 1 using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Jafarpur Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | 3256/BD | 25/11/2024 | 90 | GHOSH CONSTRUCTION. | 21.75 | 0 | 0 | 0
835 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11557 | Augmentation | Preparation of Augmentation DPR for Rohanda Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | 1951/B.Ar.D | 26/09/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0.99 | 100 | 1
836 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11557 | Augmentation | Material Requisition To Resource Division | 2211/B.Ar.D. | 22/11/2022 | 0 | Resource Division | 16.29 | 0 | 0 | 0
837 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11557 | Augmentation | Sinking of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation of Rohanda w/s scheme of Barasat-II block under Barasat Arsenic Division, P.H.E. Dte. | 1221/B.Ar.D. | 05/07/2022 | 45 | ACME CONSTRUCTION | 14.82 | 13.66 | 100 | 1
838 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11557 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir & other existing civil component of Capacity 450 Cu.m. at Rohanda W/S Scheme uder Barasat-II Block under Barasat Arsenic Division, PHE Dte. (SM/11557) | 2469/B.Ar.D. | 21/12/2022 | 60 | M.R.CONSTRUCTION | 14.74 | 14.05 | 100 | 1
839 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11557 | Augmentation | Construction of 3.6 mtr. x 3.0 mtr. size new Pump House ( Pump House-III ) with sanitary arrangement, construction of boundary wall and Allied Works for ROHANDA W/S Scheme Under Barasat Arsenic Division, PHE Dte. | 469/B.Ar.D. | 27/02/2023 | 60 | PRAGATI CONSTRUCTION & CO | 11.55 | 7.52 | 100 | 90
840 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11557 | Augmentation | Material Requisition To Resource Division | 30/B.Ar.D. | 05/01/2023 | 0 | Resource Division | 16.27 | 0 | 0 | 0
841 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11557 | Augmentation | New Service Connection of WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. for the month of April under Rohanda W/S Scheme. | 39/PFMS/EMD | 18/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.97 | 0 | 0 | 0
842 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11557 | Augmentation | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Rohanda under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 1711/B.Ar.D. | 02/09/2022 | 90 | GARGO TRADERS | 406.42 | 395.87 | 97.4 | 94
843 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11557 | Augmentation | Hiring of one (1) no. Diesel operated AC motor cab / maxi cab (Car No. WB-25F-6815) with engine capacity less than or equal to 2000 C.C. with driver for official use of the Chief Engineer (Head Quarters), Office, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 01.12.2023 to 07.06.2024. | 2696/B.Ar.D | 23/11/2023 | 190 | TOJO ENTERPRISE | 0.99 | 2.49 | 251.94 | 64
844 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11557 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated AC motor cab / maxi cab (Car No. WB-25F-6815) with engine capacity less than or equal to 2000 C.C. with driver for official use of the Chief Engineer (Head Quarters), Office, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 08.06.2024 to 30.06.2024". | 944/B.Ar.D | 06/06/2024 | 23 | TOJO ENTERPRISE | 0.12 | 0.3 | 248.04 | 0
845 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11557 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Rep.) under Rohanda W/S Scheme with Pump House No-I under Choumuha W/S scheme District of 24 Pgs. (N) | 4533-EMD | 19/07/2023 | 471 | M/S. S.G. ENTERPRISE | 31.91 | 12.48 | 53.63 | 100
846 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11557 | Augmentation | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within Kachua, Noapara and Singhpara area for Augmentation of Ground Based Water Supply Scheme at Rohanda under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 536/B.Ar.D. | 13/03/2024 | 30 | TOJO ENTERPRISE | 24.34 | 24.04 | 100 | 5
847 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11557 | Augmentation | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area of Barpol, Palitpara, Rohanda for Augmentation of Ground Based Water Supply Scheme at Rohanda under Barasat-II Block under Barasat Arsenic Division, PHE Dte. | 1851/B.Ar.D. | 21/11/2024 | 30 | DEL DELTA CONSTRUCTION | 8.61 | 0 | 0 | 60
848 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11557 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Rohanda Water Supply Scheme under Barasat-II Block under Barasat Arsenic Division, PHE Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Rohanda Water Supply Scheme under Barasat-II Block by Augmentation of Ground Water based PWSS for Rohanda Water Supply Scheme under Barasat-II Block under Barasat Arsenic Division, PHE Dte. | 245/B.Ar.D | 07/02/2025 | 135 | UMA CONSTRUCTION | 18.12 | 0 | 0 | 100
849 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Rohanda & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11557 | Augmentation | Additional electrical work at P/H No: I (replacement tube well) under Rohanda w/s Scheme, Block: Barasat -II Dist.-24Pgs (N). | 449/EMSD-I | 08/04/2025 | 7 | M/S. S.G. ENTERPRISE | 1.63 | 0 | 0 | 100
850 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC , SM/11756 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bajitpur Zone-I B water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | 1124/BD | 11/04/2023 | 90 | SHIBU BISWAS. | 209.36 | 170.05 | 81.22 | 82
851 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC , SM/11756 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. big dia. 300 mtr deep tubewell by D.R. Rig method using PVC pipe & strainer having 300 mm dia. 36 mtr. long filter for Augmentation of Bajitpur Zone-IB water supply scheme in Baduria Block of Basirhat Sub-Division, under Barasat Division, P.H.E. Dte. | 2802/BD | 12/09/2023 | 30 | DHELA BABA ENTERPRISE | 21.53 | 0 | 0 | 0
852 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC , SM/11756 | Augmentation | Material Requisition To Resource Division | 1242/BD | 25/04/2023 | 0 | Resource Division | 95.52 | 0 | 0 | 0
853 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC , SM/11756 | Augmentation | Material Requisition To Resource Division | 1625/BD | 01/06/2023 | 0 | Resource Division | 9.22 | 0 | 0 | 0
854 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC , SM/11756 | Augmentation | New connection charges for P.H. No.-I under Bajitpur Uttarpara | 121/EMD | 30/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.73 | 0 | 0 | 0
855 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC , SM/11756 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) (Replacement) under Bajitpur W/S Scheme & Bamangachi W/S Scheme (P/H-I, II, III & IV) District of 24 Pgs. (N). NIET No.- 24 of EE/EMD of 2022-23 (Sl. No. -01) | 29/EMD | 03/01/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 67.59 | 27.2 | 80.47 | 100
856 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC , SM/11756 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of (Bajitpur Zone-I A) water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | 1709/BD | 08/06/2023 | 630 | UTPAL CONSTRUCTION & CO. | 356.76 | 117.56 | 32.95 | 42
857 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC , SM/11756 | Augmentation | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Bazitpur zone - I W/S Scheme including increasing the height of back wash water tank at Baduria Block under Basirhat Sub Division, PHE Dte. Capacity- 91.50 Cum/hr. | 928/BD | 15/03/2024 | 360 | RITE WATER SOLUTIONS (I) PVT.LTD. | 21.65 | 0 | 0 | 80
858 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokulpur to accommodate FHTC , SM/11759 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Gokulpur Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 448/ BHTSD | 23/03/2022 | 150 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.32 | 4.32 | 50 | 1
859 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokulpur to accommodate FHTC , SM/11759 | Augmentation | Material Requisition To Resource Division | 605/BD | 23/02/2023 | 0 | Resource Division | 20.7 | 0 | 0 | 0
860 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokulpur to accommodate FHTC , SM/11759 | Augmentation | Material Requisition To Resource Division | 1243/BD | 25/04/2023 | 0 | Resource Division | 15.85 | 0 | 0 | 0
861 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Gokulpur to accommodate FHTC , SM/11759 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Replacement) under Daora, Diara & Gokulpur W/S Scheme, District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 07) | 34/EMD | 03/01/2023 | 30 | AHALYA ENGINEERING WORKS | 70.02 | 15.3 | 54.64 | 76
862 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokulpur to accommodate FHTC , SM/11759 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) by augmentation for Gokulpur water supply scheme in Swarupnagar block under Barasat Division, PHE Dte. | 1039/BD | 31/03/2023 | 730 | UTPAL CONSTRUCTION & CO. | 411.53 | 360.52 | 87.61 | 70
863 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokulpur to accommodate FHTC , SM/11759 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Swarupnagar and Baduria Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - D) | 155/BHTSD | 29/01/2025 | 20 | BIBHAS PAL. | 0.53 | 0 | 0 | 100
864 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-A (Kanchiyara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11922 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-VIII/A (Kanchiyara) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 428/NWSD-I | 01/04/2022 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.46 | 4.46 | 100 | 1
865 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-A (Kanchiyara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11922 | Augmentation | Material Requisition To Resource Division | 476/NWSD-I | 26/04/2023 | 0 | Resource Division | 0.33 | 0 | 0 | 0
866 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-A (Kanchiyara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11922 | Augmentation | Material Requisition To Resource Division | 1711/NWSD-I | 26/11/2024 | 0 | Resource Division | 8.93 | 0 | 0 | 0
867 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-A (Kanchiyara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11922 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 157.53 | 26.29 | 2
868 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. , SM/13469 | Augmentation | Material Requisition To Resource Division | 4021/BD | 12/10/2023 | 0 | Resource Division | 24.5 | 0 | 0 | 0
869 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. , SM/13469 | Augmentation | Material Requisition To Resource Division | 1281/BD | 25/04/2023 | 0 | Resource Division | 86.51 | 0 | 0 | 0
870 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. , SM/13469 | Augmentation | Formal work order for Additional pipeline and other allied works as per revised LDS in connection with Augmentation of Nebhadui Duttapukur Z-II Water Supply Scheme under JJM programme in Barasat-I block within Barasat Sub Division, P.H.E.Dte. | 3737/BD | 27/12/2024 | 90 | M/S B.K.ENTERPRISE. | 100.4 | 0 | 0 | 0
871 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. , SM/13469 | Augmentation | Preparation of DPR in connection of augumentation of Nebadhui Duttapukur Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | 457/BSD | 20/05/2022 | 30 | RADIANT | 3.7 | 3.34 | 100 | 100
872 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. , SM/13469 | Augmentation | Repair and Renovation Work of Pump House at 2nd Tubewell site and allied works at Nebadhui Duttapukur Zone-II Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | 582/BSD | 10/09/2024 | 82 | M/S S.HAQUE & CO. | 2.55 | 1.25 | 100 | 100
873 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. , SM/13469 | Augmentation | Formal work order for Construction of 550 cum capacity 20Mtr. Height R.C.C. Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for augmentation of Nebadhui Duttapukur Zone-II Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | 4122/BD | 17/10/2023 | 623 | M/S B.K.ENTERPRISE. | 598.56 | 105.24 | 17.58 | 35
874 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. , SM/13469 | Augmentation | Different works in connection with Augmentation Nebadhui Duttapukur Zone-II PWSS (1st Tubewell - Pump House). | 1005/BSD | 02/01/2025 | 20 | ROMI TREDERS. | 3.89 | 0 | 0 | 0
875 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. , SM/13469 | Augmentation | Different works in connection with Augmentation Nebadhui Duttapukur Zone-II PWSS (3rd Tubewell - Boundary Wall & Service Road). | 585/BSD | 10/09/2024 | 20 | MANGES INDUSTRIAL CORPORATION. | 2.82 | 0 | 0 | 100
876 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. , SM/13469 | Augmentation | Repair and Renovation Work of Pump House at 3rd Tubewell site and allied works at Nebadhui Duttapukur Zone-II Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | 584/BSD | 10/09/2024 | 20 | MANGES INDUSTRIAL CORPORATION. | 2.51 | 0 | 0 | 100
877 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-II PWSS to Accommodate FHTC. , SM/13469 | Augmentation | Different works in connection with Augmentation Nebadhui Duttapukur Zone-II PWSS (2nd Tubewell - Boundary Wall & Service Road). | 583/BSD | 10/09/2024 | 20 | NEW MA TARA ENTERPRISE. | 2.47 | 0 | 0 | 100
878 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme , SM/13510 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (ATPUKUR Z-II Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 241/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.63 | 4.63 | 100 | 1
879 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme , SM/13510 | New | Material Requisition To Resource Division | 874/BD | 22/03/2023 | 0 | Resource Division | 15.62 | 0 | 0 | 0
880 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme , SM/13510 | New | Acceptance cum work order for Sinking of 1 Nos. 300.00 mtr. Deep 100 X 50 mm. dia. Trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe & strainers at T/W site-1 for Atpukur w/s scheme (Zone-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 1132/HSD | 05/09/2023 | 30 | SARKAR ENTERPRISE & CO. | 2.63 | 2 | 100 | 100
881 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme , SM/13510 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-A). | 280/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.87 | 0.87 | 100 | 100
882 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme , SM/13510 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-B). | 281/HSD | 06/03/2024 | 10 | S.M.TRADERS. | 0.88 | 0 | 0 | 100
883 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme , SM/13510 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-D). | 284/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
884 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme , SM/13510 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-J). | 292/HSD | 06/03/2024 | 10 | M.R.CONSTRUCTION. | 0.88 | 0 | 0 | 100
885 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme , SM/13510 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-E). | 286/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
886 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme , SM/13510 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-C). | 260/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
887 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme , SM/13510 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-H). | 290/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.87 | 0.87 | 100 | 100
888 | NORTH 24 PARGANAS | Eastern Mechanical | Atpukur Zone-II Piped Water Supply Scheme , SM/13510 | New | Quotation for Service Connection Charges for PH- III, Zone-II under Atpukur W/S Scheme in the district of North 24 Pgs. | BP-355-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.56 | 0 | 0 | 0
889 | NORTH 24 PARGANAS | Eastern Mechanical | Atpukur Zone-II Piped Water Supply Scheme , SM/13510 | New | Quotation for Service Connection Charges for PH- I, Zone-II under Atpukur W/S Scheme in the district of North 24 Pgs. | BP-354-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.09 | 0 | 0 | 0
890 | NORTH 24 PARGANAS | Eastern Mechanical | Atpukur Zone-II Piped Water Supply Scheme , SM/13510 | New | Quotation for Service Connection Charges for PH- II, Zone-II under Atpukur W/S Scheme in the district of North 24 Pgs. | BP-356-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.5 | 0 | 0 | 0
891 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme , SM/13510 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 100 cum capacity CWR, pipe connection and cost of pipes, specials and Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Atpukur w/s scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1550/BD | 22/05/2023 | 669 | SARKAR ENTERPRISE & CO. | 210.66 | 200.54 | 91.63 | 95
892 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme , SM/13510 | New | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection within Atpukur water supply scheme (Z-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 341/HSD | 06/02/2025 | 10 | RATAN SARKAR. | 0.72 | 0 | 0 | 100
893 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-II Piped Water Supply Scheme , SM/13510 | New | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection within Atpukur water supply scheme (Z-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 343/HSD | 06/02/2025 | 10 | RATAN SARKAR. | 0.72 | 0 | 0 | 100
894 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District , SM/13521 | Retrofitting | Formal work order for Construction of 2 nos. (1250 CuM & 600 CuM) capacity OHR, Land development, Construction of Office cum Guard room and Switch cum Chlorine Room, Boundary wall, Surface drain and related allied works at Zone-X and XI Head work sites including Laying Distribution System and FHTC of Habra-Gaighata surface water based water supply scheme under Barasat Division, P.H.E. Dte. | 4072/BD | 16/10/2023 | 1095 | GARGO TRADERS | 3804.4 | 390.88 | 40.65 | 44
895 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District , SM/13532 | Retrofitting | Formal work order for Laying of Distribution system, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works and Providing FHTC within the jurisdiction of (Zone-XXVI) under Habra-Gaighata surface based PWSS of Gaighata Block under Barasat Division, P.H.E. Dte. | 2955/BD | 29/09/2023 | 900 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 1603.84 | 151.25 | 22.13 | 75
896 | NORTH 24 PARGANAS | Barasat Division | Niruli Abad Piped Water Supply Scheme. , SM/12716 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (NIRULI ABAD Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. | 292/HSD | 10/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.68 | 3.68 | 100 | 1
897 | NORTH 24 PARGANAS | Barasat Division | Niruli Abad Piped Water Supply Scheme. , SM/12716 | New | Material Requisition To Resource Division | 889/BD | 22/03/2023 | 0 | Resource Division | 12.1 | 0 | 0 | 0
898 | NORTH 24 PARGANAS | Eastern Mechanical | Niruli Abad Piped Water Supply Scheme. , SM/12716 | New | Quotation for Service Connection Charges for PH- II under Neruli Abad W/S Scheme in the district of North 24 Pgs. | BP-29-24-25 | 24/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 19.19 | 0 | 0 | 0
899 | NORTH 24 PARGANAS | Eastern Mechanical | Niruli Abad Piped Water Supply Scheme. , SM/12716 | New | Quotation for Service Connection Charges for PH- I under Neruli Abad W/S Scheme in the district of North 24 Pgs. | BP-325-23-24 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.92 | 0 | 0 | 0
900 | NORTH 24 PARGANAS | Barasat Division | Niruli Abad Piped Water Supply Scheme. , SM/12716 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 100 cum capacity CWR, pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Niruli Abad w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1692/BD | 07/06/2023 | 1092 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 188.07 | 118.53 | 63.03 | 58
901 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District proje , SM/13533 | Retrofitting | Formal work order for Construction of 1150 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at (Zone- XXV) i.e. Jhikra & Laying of Distribution System, Providing FHTC, Construction Land development, Construction of Office cum Guard room and Switch cum Chlorine Room, Boundary wall, Surface drain and other allied works within the jurisdiction of (Zone-XXV) under Surface Water based Water Supply Scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoining Mouzas under North 24 Parganas District project¿ under Barasat Division, P.H.E. Dte. Gaighata Block, PART-G. | 4081/BD | 16/10/2023 | 747 | GBC INFRASTRUCTURE PRIVATE LIMITED | 1699.27 | 262.06 | 40.09 | 45
902 | NORTH 24 PARGANAS | Barasat Division | Kachurhula Zone-II Piped Water Supply Scheme , SM/13445 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KACHURHULA Z-II Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. | 281/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.09 | 3.09 | 100 | 1
903 | NORTH 24 PARGANAS | Barasat Division | Kachurhula Zone-II Piped Water Supply Scheme , SM/13445 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KACHURHULA Z-II Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. | 281/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.09 | 0 | 0 | 1
904 | NORTH 24 PARGANAS | Barasat Division | Kachurhula Zone-II Piped Water Supply Scheme , SM/13445 | New | Material Requisition To Resource Division | 885/BD | 22/03/2023 | 0 | Resource Division | 14.83 | 0 | 0 | 0
905 | NORTH 24 PARGANAS | Barasat Division | Kachurhula Zone-II Piped Water Supply Scheme , SM/13445 | New | Acceptance cum work order for Protection works in different places for protection of different dia DI-UPVC rising/distribution pipe line by UC bullah/bamboo pile for Kachurhula Zone-II w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | 1610/BD | 19/05/2025 | 30 | SARKAR ENTERPRISE & CO. | 15.55 | 0 | 0 | 0
906 | NORTH 24 PARGANAS | Barasat Division | Kachurhula Zone-II Piped Water Supply Scheme , SM/13445 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line,Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 100 cum capacity CWR , pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Kachurhula w/s scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1524/BD | 19/05/2023 | 958 | ROY CHOWDHURY CONSTRUCTION. | 147.05 | 135.53 | 94.68 | 96
907 | NORTH 24 PARGANAS | Central Drilling | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC , SM/13468 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Bamanghachhi W/S Scheme (T/W-I&II), Barasat-I Block under North 24 Pgs District, Central Drilling Division, P.H.E. Dte. | 900/CDD | 18/07/2023 | 30 | UNIVERSAL ENTERPRISES | 33.24 | 11.99 | 36.08 | 37
908 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC , SM/13468 | Augmentation | Material Requisition To Resource Division | 4368/BD | 10/11/2023 | 0 | Resource Division | 21.03 | 0 | 0 | 0
909 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC , SM/13468 | Augmentation | Material Requisition To Resource Division | 3092/BD | 10/10/2023 | 0 | Resource Division | 12.26 | 0 | 0 | 0
910 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC , SM/13468 | Augmentation | Material Requisition To Resource Division | 1287/BD | 25/04/2023 | 0 | Resource Division | 73.47 | 0 | 0 | 0
911 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC , SM/13468 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) (Replacement) under Bajitpur W/S Scheme & Bamangachi W/S Scheme (P/H-I, II, III & IV) District of 24 Pgs. (N). NIET No.- 24 of EE/EMD of 2022-23 (Sl. No. -01) | 29/EMD | 03/01/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 67.59 | 27.2 | 80.47 | 100
912 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC , SM/13468 | Augmentation | Preparation of DPR in connection of augumentation of Bamangachhi Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. Sl. No.-02 | 657/BSD | 18/08/2022 | 30 | RADIANT | 3 | 2.72 | 100 | 100
913 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC , SM/13468 | Augmentation | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentaion of Bamangachhi water supply scheme under Barasat Sub-Division, P.H.E. Dte. | 2650/BD | 01/09/2023 | 366 | S.S.ENTERPRISE. (BAMANGACHI) | 538.69 | 528.74 | 100 | 100
914 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC , SM/13468 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 250 mm. x 150 mm. big dia. 210 mtr deep Tubewell by D.R. Rig method having 250 mm dia 42.0 mtr. long PVC housing pipe & 150 mm dia 30.0 mtr. long filter for Augmentation Bamangachhi Water Supply Scheme (2nd T/W Site) of Barasat Sub-Division under Barasat Division, PHE Dte. | 588/BD | 23/02/2024 | 30 | SUBHAJIT SAHA | 11.22 | 10.88 | 100 | 100
915 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC , SM/13468 | Augmentation | Different works in connection with Augmentation Bamangachi PWSS (1st Tubewell - Pump House, Boundary Wall & Service Road). | 559/BSD | 09/09/2024 | 20 | SANTU GHOSH. | 4.87 | 3.6 | 100 | 100
916 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC , SM/13468 | Augmentation | Renovation of Iron Elimination Plant at Bamangachhi Water Supply Scheme at Pump House - I (46m3/hr.) within Barasat-I Block under Barasat Sub Division, P.H.E.Dte. | 852/BSD | 28/11/2024 | 30 | MANGES INDUSTRIAL CORPORATION. | 4.35 | 0 | 0 | 100
917 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC , SM/13468 | Augmentation | Renovation of Iron Elimination Plant at Bamangachhi Water Supply Scheme at Pump House - IV (46m3/hr.) within Barasat-I Block under Barasat Sub Division, P.H.E.Dte. | 853/BSD | 28/11/2024 | 30 | MANGES INDUSTRIAL CORPORATION. | 4.35 | 0 | 0 | 0
918 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC , SM/13468 | Augmentation | Different works in connection with Augmentation Bamangachi PWSS (2nd Tubewell - Pump House, Boundary Wall & Service Road). | 560/BSD | 09/09/2024 | 20 | TALUKDER & CO. | 4.64 | 0 | 0 | 100
919 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC , SM/13468 | Augmentation | Different works in connection with Augmentation Bamangachhi PWSS (4th Tubewell - Pump House). | 1009/BSD | 02/01/2025 | 20 | M.ENTERPRISE. | 2.74 | 0 | 0 | 100
920 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC , SM/13468 | Augmentation | Different works in connection with Augmentation Bamangachhi PWSS (4th Tubewell - Boundary Wall & Service Road). | 1010/BSD | 02/01/2025 | 20 | BHABANI ENTERPRISE. | 2.22 | 0 | 0 | 100
921 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC , SM/13468 | Augmentation | Differents works in connection with Augmentation Bamangachhi PWSS (3rd Tubewell - Pump House & Service Road) | 1004/BSD | 02/01/2025 | 20 | A D ENTERPRISE (BARASAT) | 1.89 | 0 | 0 | 100
922 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC , SM/13468 | Augmentation | Continution of "Installation of Har Ghar Jal (HGJ) Display Board at different villages of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. " | 1139/BSD | 16/02/2024 | 16 | M.R.CONSTRUCTION. | 0.53 | 0 | 0 | 100
923 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC , SM/13468 | Augmentation | Road restoration work damaged during pipe laying work at Bamangachhi Pathasree road under JJM in Bamangachhi water supply Scheme under Barasat -I Block. | 105/BSD | 07/05/2025 | 15 | DEBANJAN GHOSH. | 2.79 | 0 | 0 | 100
924 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Rajbari Piped water supply scheme , SM/14515 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. I and II (Rep.) under Rajbari W/S Scheme, Block-Sandeshkhali-I in District of 24 Pgs. (N) NIET No. 38 of EE/EMD of 2022-23 (Sl. No.- 07) | 1014/EMD | 09/03/2023 | 30 | BARISAL TRADING CO. | 21.23 | 19.49 | 91.82 | 0
925 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Rajbari Piped water supply scheme , SM/14515 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Rajbari Piped Water Supply Scheme under Barasat Division, PHE Dte. | 633/HSD | 08/04/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.72 | 3.72 | 100 | 1
926 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Rajbari Piped water supply scheme , SM/14515 | Augmentation | Acceptance cum work order for Repairing of Pump House at PH No- 2 for Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 796/HSD | 13/07/2023 | 7 | SAGAR DAS. | 0.62 | 0.56 | 100 | 100
927 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Rajbari Piped water supply scheme , SM/14515 | Augmentation | Material Requisition To Resource Division | 940/BD | 22/03/2023 | 0 | Resource Division | 25.03 | 0 | 0 | 0
928 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Rajbari Piped water supply scheme , SM/14515 | Augmentation | Formal work order for for Laying of UPVC/DI distribution pipe line and providing Functional Household Tap Connection for Augmentation of Rajbari water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 829/BD | 15/03/2023 | 90 | M/S DATTA ENTERPRISE. | 279.81 | 277.17 | 100 | 100
929 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Rajbari Piped water supply scheme , SM/14515 | Augmentation | Acceptance cum work order for Repairing of Pump house and Dismantling, Re-construction of boundary wall and approach road for movement of rig & other machineries for sinking of big dia. TW at PH no- 1 in connection with Augmentation of Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 2718/BD | 05/09/2023 | 21 | M/S ANUBHAB CONSTRUCTION. | 5.06 | 4.45 | 100 | 100
930 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Rajbari Piped water supply scheme , SM/14515 | Augmentation | Acceptance cum work order for Providing Functional household tap connection at Rajbari Purbapara SSK & Paschim Laukhali Sobahan Molla Smriti FP School, within the command area of Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 545/HSD | 10/03/2025 | 10 | SARKAR ENTERPRISE | 0.5 | 0 | 0 | 0
931 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Rajbari Piped water supply scheme , SM/14515 | Augmentation | Acceptance cum work order for Additional Laying of UPVC distribution pipe line and Providing Functional Household Tap Connection for the leftout portion in connection with Augmentation of Rajbari water supply scheme (Z-I), Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 3182/BD | 18/11/2024 | 60 | M/S K.B.ENTERPRISE. | 60.6 | 0 | 0 | 100
932 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Rajbari Piped water supply scheme , SM/14515 | Augmentation | Acceptance cum work order for Protection of different dia. UPVC pipeline by UC bullah pile near PH No- 1 in connection with augmentation of Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 843/HSD | 15/05/2025 | 10 | M/S ANUBHAB CONSTRUCTION. | 1.33 | 0 | 0 | 100
933 | NORTH 24 PARGANAS | Barasat Division | Electrocoagulation based package Surface water based water supply scheme (Solar Power) in Minakhan Block , SM/14625 | New | Acceptance cum work order for Electrocoagulation Based Package Surface Water based Water Supply Scheme (Solar Power) in Minakhan Block, North 24 Parganas District of Barasat Division, P.H.E. Dte. | 407/BD | 09/02/2023 | 30 | CARBON SERVICES INDIA | 45.12 | 35.83 | 79.42 | 0
934 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Acceptance cum work order for Providing Functional tap connection at Radharani High School at Sandeshkhali in connection with augmentation of Sandeshkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1054/HSD | 31/08/2023 | 7 | M/S RAJPATH CONSTRUCTION. | 0.9 | 0 | 0 | 0
935 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Material Requisition To Resource Division | 937/BD | 22/03/2023 | 0 | Resource Division | 50.86 | 0 | 0 | 0
936 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Material Requisition To Resource Division | 4174/BD | 30/10/2023 | 0 | Resource Division | 10.35 | 0 | 0 | 0
937 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Dhamakhali mouza with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 3583/BD | 18/12/2024 | 30 | TITUMIR INTERNATIONAL | 25.86 | 0 | 0 | 0
938 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Gabberia w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 34/HSD | 09/01/2024 | 10 | M/S RAJPATH CONSTRUCTION. | 0.92 | 0 | 0 | 100
939 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Continuation order for one motor launch (M.V. JOYMAKALI) on daily hire basis for use of Hasnabad Sub-Division, P.H.E. Dte. Period : 01.09.23 to 31.10.23 = 61 days. | 1030/HSD | 29/08/2023 | 61 | SUSMITA MANDAL. | 0.91 | 2.66 | 100 | 5
940 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Work order for Supply of Mechanized boat on hire basis with providing driver, helper and other requirement as per terms condition and specification as per direction of the EIC under Hasnabad Sub-Division, P.H.E. Dte. Period : 01.11.23 to 30.04.24 | 1396/HSD | 31/10/2023 | 182 | RANJIT KUMAR MANDAL | 1.61 | 5.42 | 100 | 5
941 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Work order for Supply of one motor launch on daily hire basis for use of Hasnabad Sub-Division, P.H.E. Dte. Period : 01.11.23 to 31.03.24 = 152 days. | 1362/HSD | 31/10/2023 | 152 | SUSMITA MANDAL. | 2.26 | 7.48 | 100 | 10
942 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Acceptance cum work order for Arrangement Of Block Level Orientation programe involving stakeholders of PRI bodies including refreshments, training materials and related activities for 2 nos Blocks ( Sandeshkhali- I & II ) in North 24 Parganas under Barasat Division, P.H.E Dte. | 755/HSD | 19/07/2024 | 10 | IMAGIN | 0.98 | 0.98 | 100 | 100
943 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Gabberia w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 33/HSD | 09/01/2024 | 10 | M/S RAJPATH CONSTRUCTION. | 0.92 | 0 | 0 | 100
944 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line & providing Functional Household Tap Connection with other allied works for Augmentation of Sandeshkhali water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | 1300/BD | 26/04/2023 | 901 | KINGS & CO. | 356.31 | 144.22 | 40.48 | 45
945 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Sandeshkhali W/S Scheme , District of 24 Pgs. (N) | 4932/EMD | 18/08/2023 | 683 | SWAPAN ENTERPRISE | 22.26 | 0 | 0 | 70
946 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 865/BD | 19/03/2025 | 450 | M/S K.B.ENTERPRISE. | 102.2 | 0 | 0 | 30
947 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Acceptance cum work order for Additional Construction of switch room cum chlorine room (3.60x3.00) with sanitary and water supply arrangement including plinth protection at Dhamakhali mouza within Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 864/BD | 19/03/2025 | 225 | RUDRA DAS. | 10.58 | 0 | 0 | 90
948 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Acceptance cum work order for Construction of 200 cum capacity CWR , pipe connection and cost of pipes, specials for Augmentation of Sandeshkhali water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | 1499/BD | 13/05/2025 | 180 | SUFIA ENTERPRISE | 53.52 | 0 | 0 | 0
949 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Sandeshkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 2478/BD | 18/08/2023 | 540 | M/S SUKANTA ENTERPRISE. | 31.71 | 0 | 0 | 100
950 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Acceptance cum work order for Additional Construction of switch room cum chlorine room (3.60x3.00) with sanitary and water supply arrangement including plinth protection at Rampur & Jhupkhali adjoining mouza within Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E.Dte. | 863/BD | 19/03/2025 | 75 | ABUL KALAM GAZI | 10.6 | 0 | 0 | 100
951 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tube well by D.R. Rig method at PH No.-I with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Sandeshkhali W/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E.Dte. | 3581/BD | 18/12/2024 | 70 | M/S SUKANTA ENTERPRISE. | 31.67 | 0 | 0 | 100
952 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-I with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Jeliakhali Purbakhanda w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 3578/BD | 18/12/2024 | 120 | M/S RAJPATH CONSTRUCTION. | 31.66 | 0 | 0 | 100
953 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sandeshkhali , SM/14152 | Augmentation | Acceptance cum work order for Providing Functional tap household connection at Sumitrabala FP School, Rajbari Vidyasagar Smriti FP School and Phulmani Adarsha Vidyamandir (HS)` within the command area of Sandeshkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte | 946/HSD | 29/05/2025 | 10 | SARKAR ENTERPRISE | 0.69 | 0 | 0 | 100
954 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC , SM/14162 | Augmentation | Material Requisition To Resource Division | 3095/BD | 10/10/2023 | 0 | Resource Division | 21.72 | 0 | 0 | 0
955 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC , SM/14162 | Augmentation | Material Requisition To Resource Division | 1266/BD | 25/04/2023 | 0 | Resource Division | 158.32 | 0 | 0 | 0
956 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC , SM/14162 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.IV (Zone-II) (New) under Bodai W/S Scheme District of 24 Pgs. (N) | 4752/EMD | 07/08/2023 | 30 | SMILE | 13.14 | 0 | 0 | 0
957 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC , SM/14162 | Augmentation | Formal work order for construction of 750 cum capacity 20 mtr. height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentaion of Bodai (Zone-II) water supply scheme under Barsasat Sub-Division, P.H.E. Dte. | 2617/BD | 29/08/2023 | 1096 | SUPRITI ENTERPRISE. | 874.9 | 144.08 | 16.47 | 20
958 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC , SM/14162 | Augmentation | Preparation of DPR in connection of augumentation of Bodai Water Supply Scheme Zone-II under Barasat Sub Division, P.H.E. Dte. Sl. No.-02 | 549/BSD | 29/06/2022 | 30 | RADIANT | 3.41 | 3.39 | 100 | 100
959 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC , SM/14162 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Amdanga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-C | 1116A/BSD | 09/02/2024 | 4 | M.R.CONSTRUCTION. | 0.88 | 0.88 | 100 | 100
960 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC , SM/14162 | Augmentation | Formal work order for Additional pipeline and other allied works as per revised LDS in connection with Augmentation of Bodai-II Water Supply Scheme under JJM programme in Amdanga block within Barasat Sub Division, P.H.E.Dte. | 2229/BD | 07/08/2024 | 450 | CHANDA CONSTRUCTION. | 433.82 | 0 | 0 | 25
961 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC , SM/14162 | Augmentation | Different works in connection with Augmentation Bodai Zone-II PWSS (1st Tubewell - Pump House). | 1002/BSD | 02/01/2025 | 20 | M/S DAS & CO. | 3.93 | 0 | 0 | 0
962 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC , SM/14162 | Augmentation | Acceptance cum work order for for Construction of Pump House with latrine at Bodai Zone-II water Supply Scheme under Amdanga Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | 932/BD | 15/03/2024 | 91 | M/S DAS & CO. | 5.09 | 4.9 | 100 | 100
963 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC , SM/14162 | Augmentation | Acceptance cum work order for Sinking of 1 no. 250mm. X 150mm.dia. 220.00mtr. deep tubewell by direct rotary rig method, having 250mm.dia. 42.0mtr. long UPVC housing pipe & 150mm.dia. 30.0mtr. long filter for Augmentation of Bodai Zone-II Water Supply Scheme at 2nd Tubewell Site under Barasat Sub-Division, P.H.E. Dte. | 3586/BD | 18/12/2024 | 90 | M/S K.P.PAL. | 11.56 | 0 | 0 | 100
964 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC , SM/14162 | Augmentation | Different works in connection with Augmentation Bodai Zone-II PWSS (2nd Tubewell - Pump House, Boundary Wall & Service Road) | 1007/BSD | 02/01/2025 | 20 | PURBA SERVICES | 1.93 | 0 | 0 | 100
965 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC , SM/14162 | Augmentation | Differents works in connection with Augmentation Bodai Zone-II PWSS (3rd Tubewell - Pump House, Boundary Wall & Service Road) | 1008/BSD | 02/01/2025 | 20 | M/S SOURAV DAS | 2.64 | 0 | 0 | 100
966 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Sultanpur Piped water supply scheme , SM/14510 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Sultanpur Piped Water Supply Scheme under Barasat Division, PHE Dte. | 632/HSD | 08/04/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3 | 3 | 100 | 1
967 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Sultanpur Piped water supply scheme , SM/14510 | Augmentation | Formal work order for Laying of UPVC/DI distribution pipe line and providing Functional Household Tap Connection for Augmentation of Sultanpur water supply scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 698/BD | 03/03/2023 | 90 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 239.69 | 210.08 | 100 | 92
968 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Sultanpur Piped water supply scheme , SM/14510 | Augmentation | Acceptance cum work order for Construction of approach road with cement concrete at PH No.-1 within Sultanpur w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1130/HSD | 05/09/2023 | 7 | ANKUSH CONSTRUCTION & CO. | 1.83 | 1.64 | 100 | 100
969 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Sultanpur Piped water supply scheme , SM/14510 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Sultanpur w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 917/BD | 15/03/2024 | 45 | M/S B.K.ENTERPRISE. | 50.73 | 45.65 | 100 | 100
970 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Sultanpur Piped water supply scheme , SM/14510 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep) under Sultanpur W/S Scheme, Block-Hasnabad in District of 24 Pgs. (N) | 6757/EMD | 28/11/2023 | 551 | DIPALI CONSTRUCTION | 26.48 | 19.39 | 73.27 | 70
971 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Sultanpur Piped water supply scheme , SM/14510 | Augmentation | Acceptance cum work order for Additional Laying of UPVC distribution pipe line & Providing FHTC for the leftout portion in connection with Augmentation of Sultanpur w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 261/HSD | 30/01/2025 | 10 | M/S TAMAL CHAKRABORTY. | 0.97 | 0 | 0 | 100
972 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Sultanpur Piped water supply scheme , SM/14510 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation of Sultanpur water supply scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 312/HSD | 04/02/2025 | 10 | SARKAR ENTERPRISE | 0.72 | 0 | 0 | 100
973 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme , SM/15323 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Berachampa Water Supply Scheme Zone-IV under Barasat Sub Division, P.H.E. Dte. | 671/BSD | 29/08/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.95 | 3.95 | 100 | 1
974 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme , SM/15323 | Augmentation | Material Requisition To Resource Division | 4371/BD | 10/11/2023 | 0 | Resource Division | 94.42 | 0 | 0 | 0
975 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme , SM/15323 | Augmentation | Material Requisition To Resource Division | 3086/BD | 10/10/2023 | 0 | Resource Division | 28.89 | 0 | 0 | 0
976 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme , SM/15323 | Augmentation | Material Requisition To Resource Division | 1278/BD | 25/04/2023 | 0 | Resource Division | 197.95 | 0 | 0 | 0
977 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme , SM/15323 | Augmentation | Acceptance cum work order for Construction of Boundary Wall at Nandipara Kuchemora Under Berachampa Zone-IV Water Supply Scheme under Deganga Block, under Barasat Sub-Division, P.H.E.Dte. | 3476/BD | 10/12/2024 | 30 | JP CONSTRUCTION & SUPPLIERS. | 32.77 | 0 | 0 | 0
978 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme , SM/15323 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different villages of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-F | 1120./1/BSD | 09/02/2024 | 4 | S.M.TRADERS. | 0.87 | 0.87 | 100 | 100
979 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme , SM/15323 | Augmentation | Construction of Pump House with latrine at Berachampa Zone-IV water Supply Scheme under Deganga Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | 1244/BSD | 15/03/2024 | 31 | M/S S.HAQUE & CO. | 4.88 | 4.87 | 100 | 100
980 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme , SM/15323 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. X 200mm.dia. 190.00mtr. deep tubewell by direct rotary rig method, having 300mm.dia. 42.0mtr. long PVC housing pipe & 200mm.dia. 30.0mtr. long filter for Augumentation of Berachampa Zone-IV Water Supply Scheme at OHR Site under Barasat Sub-Division, P.H.E. Dte. | 2193/BD | 05/08/2024 | 30 | ANJALI ENTERPRISE. | 13.3 | 3.48 | 20.94 | 100
981 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme , SM/15323 | Augmentation | New service connection at P.H.No- I Zone-IV of Berachampa water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). | BP-307-23-24 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.05 | 0 | 0 | 0
982 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme , SM/15323 | Augmentation | Formal work order for Construction of 700 cum capacity 20mtr staging height RCC Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentation of Berachampa Zone-IV Water Supply scheme under Barasat Sub-Division, P.H.E.Dte | 4018/BD | 12/10/2023 | 730 | A.P POWER & CONCRETE | 877.47 | 197.2 | 22.47 | 30
983 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC , SM/15324 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. III (New) under Joypul W/S Scheme, District of 24 Pgs. (N). | 4747/EMD | 07/08/2023 | 30 | T.S.CONSTRUCTION | 10.59 | 0 | 0 | 0
984 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC , SM/15324 | Augmentation | Material Requisition To Resource Division | 4023/BD | 12/10/2023 | 0 | Resource Division | 25.78 | 0 | 0 | 0
985 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC , SM/15324 | Augmentation | Material Requisition To Resource Division | 1289/BD | 25/04/2023 | 0 | Resource Division | 76.38 | 0 | 0 | 0
986 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC , SM/15324 | Augmentation | Continuation work order for Hiring 1(one) no. Diesel Luxary Car on daily basis (for 01.05.2023 to 31.08.2023) for office use of the Assistant Engineer, R.W.S Barasat Sub-Division, P.H.E. Dte | 382/BST | 27/04/2023 | 123 | DEBAPRASAD MONDAL. | 0.58 | 1.03 | 177.1 | 0
987 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC , SM/15324 | Augmentation | Hiring 1(one) no. Diesel Luxary Car on daily basis (for 01.09.2023 to 29.02.2024) for office use of the Assistant Engineer, R.W.S, Barasat Sub- Division, P.H.E. Dte. | 783/BST | 29/08/2023 | 182 | DEBAPRASAD MONDAL. | 0.86 | 1.44 | 166.08 | 0
988 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC , SM/15324 | Augmentation | Hiring 1(One) No. Diesel Luxury Car on Daily basis. (for six months w.e.f. 08.09.2023) for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. | 663/BSD | 07/09/2023 | 182 | ANJALI ENTERPRISE. | 0.86 | 1.5 | 173.16 | 2
989 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC , SM/15324 | Augmentation | Hiring 1(One) No. Diesel Luxury Car on Daily basis for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. (For the Period from 08/03/2024 to 31/08/2024) | 1215/BSD | 07/03/2024 | 176 | ANJALI ENTERPRISE. | 0.84 | 1.45 | 172.87 | 0
990 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC , SM/15324 | Augmentation | Preparation of DPR in connection of augumentation of Joypul Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. Sl. No.-01 | 656/BSD | 18/08/2022 | 30 | RADIANT | 3.73 | 3.04 | 100 | 100
991 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC , SM/15324 | Augmentation | Laying of partly damaged UPVC pipe line at Nabajibonpally under Joypul Water Supply Scheme within Barasat Sub Division, P.H.E.Dte. | 1133/BSD | 12/02/2024 | 7 | TALUKDER & CO. | 0.87 | 0.73 | 100 | 100
992 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC , SM/15324 | Augmentation | Different works in connection with Augmentation Joypul PWSS (2nd Tubewell - Pump House, Boundary Wall & Service Road). | 573/BSD | 10/09/2024 | 82 | SANTU GHOSH. | 3.09 | 0.98 | 100 | 100
993 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC , SM/15324 | Augmentation | Formal work order for Construction of 550cum capacity 20mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and laying of Rising main & distribution pipe line by DI & UPVC and Providing FHTC for Augmentation of Joypul water supply Scheme under Barasat Sub-Division PHE Dte. | 2549/BD | 23/08/2023 | 1096 | MONDAL ENTERPRISE. (BARASAT) | 650.34 | 254.43 | 39.12 | 60
994 | NORTH 24 PARGANAS | Central Drilling | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC , SM/15324 | Augmentation | Hiring of Diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Calcutta Mechanical Sub-Divn-I(D), CDD P.H.E. Dte. | 330/CMSD-I | 04/10/2024 | 182 | SULEKHA PAUL | 0.86 | 0.9 | 104.04 | 0
995 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC , SM/15324 | Augmentation | Continuation work order for Hiring 1(One) No. Diesel Luxury Car on Daily basis for 6 (six) months for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. @ Rs. 475.00 (Rupees four hundred and seventy five only) per day excluding fuel. (Period from 01/09/2024 to 28/02/2024) | 504/BSD | 29/08/2024 | 183 | ANJALI ENTERPRISE. | 0.86 | 0.47 | 54.63 | 0
996 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC , SM/15324 | Augmentation | Continuation work order for Hiring 1(One) No. Diesel Luxury Car on Daily basis for 6 (six) months for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. @ Rs. 475.00 (Rupees four hundred and seventy five only) per day excluding fuel. (Period from 01/03/2025 to 31/08/2025) | 1194/BSD | 24/02/2025 | 184 | ANJALI ENTERPRISE. | 0.87 | 0.67 | 76.98 | 0
997 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC , SM/15324 | Augmentation | Acceptance cum work order for Construction of Pump House with latrine at Joypul water Supply Scheme under Barasat-I Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | 1922/BD | 09/07/2024 | 184 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 5.09 | 0 | 0 | 100
998 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC , SM/15324 | Augmentation | Different works in connection with Augmentation Joypul PWSS (1st Tubewell - Pump House). | 568/BSD | 09/09/2024 | 20 | NEW MA TARA ENTERPRISE. | 2.95 | 0 | 0 | 100
999 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC , SM/15324 | Augmentation | Different works in connection with Augmentation Joypul PWSS (1st Tubewell - Boundary Wall & Service Road). | 567/BSD | 09/09/2024 | 20 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 3.12 | 0 | 0 | 100
1000 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District , SM/15824 | Retrofitting | Formal work order for Construction of 2 nos. (1250 CuM & 600 CuM) capacity OHR, Land development, Construction of Office cum Guard room and Switch cum Chlorine Room, Boundary wall, Surface drain and related allied works at Zone-X and XI Head work sites including Laying Distribution System and FHTC of Habra-Gaighata surface water based water supply scheme under Barasat Division, P.H.E. Dte. | 4072/BD | 16/10/2023 | 1095 | GARGO TRADERS | 3804.4 | 0 | 0 | 44
1001 | NORTH 24 PARGANAS | Barasat Division | Ambaria Piped Water Supply Scheme , SM/15831 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (AMBARIA Water Supply Scheme) in HINGALGANJ BLOCK under Barasat Division, PHE Dte. (PART-A) | 233/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
1002 | NORTH 24 PARGANAS | Barasat Division | Ambaria Piped Water Supply Scheme , SM/15831 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (AMBARIA Water Supply Scheme) in HINGALGANJ BLOCK under Barasat Division, PHE Dte. (PART-B) | 234/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.29 | 4.29 | 100 | 1
1003 | NORTH 24 PARGANAS | Barasat Division | Ambaria Piped Water Supply Scheme , SM/15831 | New | Material Requisition To Resource Division | 881/BD | 22/03/2023 | 0 | Resource Division | 24.21 | 0 | 0 | 0
1004 | NORTH 24 PARGANAS | Eastern Mechanical | Ambaria Piped Water Supply Scheme , SM/15831 | New | Quotation for Service Connection Charges for PH- I under Amberia W/S Scheme in the district of North 24 Pgs. JL No- 94, Plot No. 339 | BP-329-23-24 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.19 | 0 | 0 | 0
1005 | NORTH 24 PARGANAS | Eastern Mechanical | Ambaria Piped Water Supply Scheme , SM/15831 | New | Quotation for Service Connection Charges for PH- II under Amberia W/S Scheme in the district of North 24 Pgs. J.L. No.-94, Plot No- 319 | BP-330-23-24 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.21 | 0 | 0 | 0
1006 | NORTH 24 PARGANAS | Barasat Division | Ambaria Piped Water Supply Scheme , SM/15831 | New | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, leftout work of 500 cum reservoir in connection with Augmentation of Chandpur w/s scheme (Z-II), Hasnabad Block, Construction of Protection wall for protection of UPVC distribution pipe line, Construction of approach road Zone-5 of Surfaced based w/s scheme Hasnabad, Protection works in different location of Amberia and Ghuni mouza, 2 nos. pump connection at PH No.-1 & 2 with CWR in connection within Amberia water supply scheme, Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 1748/BD | 28/05/2025 | 60 | M/S DATTA ENTERPRISE. | 102.67 | 0 | 0 | 80
1007 | NORTH 24 PARGANAS | Barasat Division | Ambaria Piped Water Supply Scheme , SM/15831 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 150 cum capacity CWR, pipe connection and cost of pipes specials for Amberia W/S Scheme, Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | 1737/BD | 08/06/2023 | 731 | MONDAL & CO. (BASIRHAT). | 411.21 | 339.67 | 87.99 | 96
1008 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su , SM/08773 | Retrofitting | Acceptance cum Work Order for Hiring of 1(one) number vehicle of category Motor Cab/Maruti Omni(standard)(Non Air-conditioned) with Diesel/LPG/CNG Engine)[not more than 5 (five) years old] including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub-Division, P.H.E. Dte. at Barrackpore, Kolkata-700120, district- North 24Pgns, W.B. | 432/BKP | 27/07/2021 | 12 | GOPAL SINGHA. | 1.49 | 0.65 | 43.53 | 1
1009 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su , SM/08773 | Retrofitting | Hiring of 1 no. of Diesel Luxury Car (Euro - IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer,Habra Sub-Division, P.H.E. Dte. (For the period from: 01.12.2021 to 30.11.2022) | 488/HAB | 30/11/2021 | 1 | M/S LATIKA CONSTRUCTION. | 1.73 | 3.52 | 202.9 | 1
1010 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su , SM/08773 | Retrofitting | Continuation work order for the work of Hiring Diesel Luxury Car on daily basis (for 6months from 01-04-2022 to 30-09-2022) for the Office of the Executive Engineer, Barasat Division, PHE Dte. | 962/BD | 29/03/2022 | 6 | MADHAB CHANDRA DAS | 0.9 | 1.32 | 147.18 | 1
1011 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su , SM/08773 | Retrofitting | Repairing & Renovation of 02 Nos. Pump House (P.H. No.-IV & V) and allied works at Bodai Water Supply Scheme Zone-I under Barasat Sub-Division, P.H.E.Dte. | 810/BSD | 09/12/2021 | 30 | SUN ENTERPRISE. | 2.52 | 2.32 | 92.01 | 0
1012 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su , SM/08773 | Retrofitting | Repairing & Renovation of 02 Nos. Pump House (P.H. No.-II & III) and allied works at Bodai Water Supply Scheme Zone-I under Barasat Sub-Division, P.H.E.Dte. | 809/BSD | 08/12/2021 | 30 | MONDAL ENTERPRISE. (BARASAT) | 2.52 | 2.33 | 92.62 | 0
1013 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su , SM/08773 | Retrofitting | Hiring 1(One) No. Diesel Luxury Car on Daily basis. (for six months from w.e.f. 01.12.2022) for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. | 804/BSD | 30/11/2022 | 182 | MADHAB CHANDRA DAS | 0.86 | 0.26 | 29.99 | 1
1014 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su , SM/08773 | Retrofitting | Hiring 1(One) No. Diesel Luxury Car on Daily basis. (for 12 months from 01.03.2022 to 28.02.2023 w.e.f. 01.12.2022) for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. | 193/BSD | 25/02/2022 | 365 | MADHAB CHANDRA DAS | 1.25 | 0.76 | 60.68 | 0
1015 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su , SM/08773 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas (Part) within Bodai Zone-I Water Supply Scheme at Amdanga Block under Barasat Division, PHE Dte. Part-A Phase-I | 2145/BD | 12/11/2021 | 90 | UMWELT ENGINEER PVT.LTD. | 222.53 | 201.49 | 100 | 1
1016 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su , SM/08773 | Retrofitting | Repairing & Renovation of 1 No. Pump House (Size- 5.20 x 7.20) of Head Work Site and allied works at Bodai Water Supply Scheme Zone-I under Barasat Sub-Division, P.H.E.Dte. Sl. No.-1 | 805/BSD | 06/12/2021 | 30 | PURBA SERVICES | 1.84 | 1.75 | 100 | 0
1017 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su , SM/08773 | Retrofitting | Acceptance cum Work Order for Hiring of 1(one) number vehicle of category Motor Cab/Maruti Omni(standard)(Non Air-conditioned) with Diesel/LPG/CNG Engine)[not more than 5 (five) years old] including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub-Division, P.H.E. Dte. at Barrackpore, Kolkata-700122, district- North 24Pgns, W.B. | 158/BKP | 29/07/2022 | 365 | GOPAL SINGHA. | 1.73 | 3.93 | 100 | 1
1018 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su , SM/08773 | Retrofitting | Material Requisition To Resource Division | 2240/BD | 24/11/2021 | 0 | Resource Division | 10.26 | 0 | 0 | 0
1019 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su , SM/08773 | Retrofitting | Acceptance cum Work Order for Hiring of 1(one) number vehicle of Category Motor Cab/Maruti Omni(standard)(Non Air-Conditioned)/LPG/CNG Engine including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub-Division, P.H.E. Dte. at Barrackpore, Kolkata-700122, District- North 24Pgns, W.B.(From 01.10.2023 to 31.03.2024) | 333/BKP | 29/09/2023 | 182 | GOPAL SINGHA. | 0.87 | 1.57 | 180.69 | 80
1020 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su , SM/08773 | Retrofitting | Continuation Work Order for Hiring of 1(one) number vehicle of Category Motor Cab/Maruti Omni(standard)(Non Air-Conditioned)/LPG/CNG Engine including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub-Division, P.H.E. Dte. at Barrackpore, Kolkata-700122, District- North 24Pgns, W.B.(Period from 01.02. 2024 to 31.07.2024) | 43/BKP | 22/01/2024 | 182 | GOPAL SINGHA. | 0.86 | 1.95 | 225.86 | 100
1021 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su , SM/08773 | Retrofitting | Continuation Work Order for Hiring of 1(one) number vehicle of Category Motor Cab/Maruti Omni(standard)(Non Air-Conditioned)/LPG/CNG Engine including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub- Division, P.H.E. Dte. at Barrackpore, Kolkata-700122, District- North 24Pgns, W.B. | 107/BKP | 06/03/2024 | 184 | GOPAL SINGHA. | 0.87 | 2.05 | 235.62 | 100
1022 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su , SM/08773 | Retrofitting | Hiring of 1 no. of Diesel Luxury Car (Euro ¿ IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer, Habra Sub-Division, P.H.E. Dte. (For the period from : 01.12.2022 to 30.11.2023) | 660/HAB | 30/11/2022 | 365 | M/S LATIKA CONSTRUCTION. | 1.73 | 4.4 | 100 | 40
1023 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su , SM/08773 | Retrofitting | Continuation Work Order for Hiring of 1(one) number vehicle of Category Motor Cab/Maruti Omni(standard)(Non Air-Conditioned)/LPG/CNG Engine including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub-Division, P.H.E. Dte. at Barrackpore, Kolkata-700122, District- North 24Pgns, W.B.(period from 01.08.2024 to 31.01.2025) | 461/BKP | 12/07/2024 | 184 | GOPAL SINGHA. | 0.87 | 2.01 | 230.06 | 0
1024 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su , SM/08773 | Retrofitting | Work Order for Hiring of 1(one) number vehicle of Category Motor Cab/Maruti Omni(standard)(Non Air-Conditioned)/LPG/CNG Engine including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub-Division, P.H.E. Dte. at Barrackpore, Kolkata-700122, District- North 24Pgns, W.B.(period from 01.10.2024 to 31.03.2025) | 528/BKP | 30/09/2024 | 182 | GOPAL SINGHA. | 0.86 | 2.06 | 238.31 | 0
1025 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas within Bodai Zone-I Piped Water Su , SM/08773 | Retrofitting | Continuation Work Order for Hiring of 1(one) number vehicle of Category Motor Cab/Maruti Omni(standard)(Non Air-Conditioned)/LPG/CNG Engine including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub-Division, P.H.E. Dte. at Barrackpore, Kolkata-700122, District- North 24Pgns, W.B.(period from 01.02.2025 to 31.07.2025) | 21/BKP | 30/01/2025 | 181 | GOPAL SINGHA. | 0.86 | 1.37 | 158.92 | 0
1026 | NORTH 24 PARGANAS | Eastern Mechanical | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Bongaon Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. , SM/15765 | Solarisation | Solarisation of WBSEDCL Energised Electrical installation including net metering at different Pipe Water Supply Scheme at Bongaon Block in North 24 Parganas District under E.M.D. P.H.E. Dte. | 6358/EMD | 16/10/2023 | 183 | EQUIPMENTS AND SPARES AGENCIES | 380.65 | 0 | 0 | 0
1027 | NORTH 24 PARGANAS | Eastern Mechanical | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Bagda Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. , SM/15769 | Solarisation | Solarisation of WBSEDCL Energised Electrical installation including net metering at different Pipe Water Supply Scheme at Bagda Block in North 24 Parganas District under E.M.D. P.H.E. Dte. | 6457/EMD | 02/11/2023 | 730 | SWITCHING AVO ELECTRO POWER LTD. | 249.48 | 0 | 0 | 26
1028 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-X (Basna Benapur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18263 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Zone-X (Basna Benapur) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | 892/NWSD-I | 12/07/2023 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.89 | 3.87 | 100 | 100
1029 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-X (Basna Benapur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18263 | Augmentation | Supply and installation of Sign Board (900mm X 600mm) determination of Land i.e." This land belongs to PHE. Dte. Govt. of West Bengal" under Surface Water based Pipe Water supply Scheme under North 24 Pgs. Water Supply Division-I, PHE. Dte. | 1432/NWSD-I | 18/09/2024 | 14 | S M TRADERS | 2.17 | 0 | 0 | 100
1030 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-X (Basna Benapur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18263 | Augmentation | Material Requisition To Resource Division | 1314/NWSD-I | 30/08/2024 | 0 | Resource Division | 20.01 | 0 | 0 | 0
1031 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-X (Basna Benapur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18263 | Augmentation | Material Requisition To Resource Division | 1872/NWSD-I | 20/12/2024 | 0 | Resource Division | 140.39 | 0 | 0 | 0
1032 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-X (Basna Benapur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18263 | Augmentation | New service connection at Basna Benapur P.H.No- I Zone-X water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). | BP-334-23-24 | 11/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.86 | 0 | 0 | 0
1033 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-X (Basna Benapur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18263 | Augmentation | Providing FHTC, Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of Zone-X (Basna Benapur) in Deganga Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | 1682/NWSD-I | 30/10/2023 | 519 | DIVINE | 735.78 | 0 | 0 | 5
1034 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-X (Basna Benapur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18263 | Augmentation | Shinking of 1 no. Tube well 300mm X 200mm Big Dia.Tube well 300 Mtr. Deep by Direct Rotary Rig method using PVC pipe & UPVC deep well screen pipes with ribs etc. Including cost of Materials for Basna Benapur Zone-X Water Supply Scheme (H/W site) under North 24 Parganas wate supply Division-I, P.H.E. Dte. | 435/NWSD-I | 19/03/2025 | 30 | ACME CONSTRUCTION | 22.68 | 0 | 0 | 0
1035 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VII (Amulia) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18264 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure, Proposed Rising Main System, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction of 550 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation (600 mm dia, 22 mtrs. deep and one pile cap adjoning 3 nos of pipes), pipe connection and cost of pipes, specials, soil investigation for the work of construction of OHR with staging height 20 mtr, Construction Of Pump House (4.88m X 3.66m) Including Sanitary Arrangement, Boundary Wall, Service Road for 60 Mtr. Length, Improvement of Land for Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of ZONE - VII AMULIA in Deganga Block of North 24 Pargana(s) District under N24 Pgs W/S Div-I, PHE Dte. | 1674/NWSD-I | 30/10/2023 | 365 | MANGES INDUSTRIAL CORPORATION | 817.79 | 0 | 0 | 1
1036 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VII (Amulia) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18264 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Zone-VII (Amulia) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | 890/NWSD-I | 12/07/2023 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.27 | 4.29 | 100 | 100
1037 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VII (Amulia) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18264 | Augmentation | Supply and installation of Sign Board (900mm X 600mm) determination of Land i.e." This land belongs to PHE. Dte. Govt. of West Bengal" under Surface Water based Pipe Water supply Scheme under North 24 Pgs. Water Supply Division-I, PHE. Dte. | 1432/NWSD-I | 18/09/2024 | 14 | S M TRADERS | 2.17 | 0 | 0 | 100
1038 | NORTH 24 PARGANAS | Barasat Division | Augmentation of TYANTRA NEORA (POND) WATER SUPPLY SCHEME , SM/17680 | Augmentation | Route Survey, Design Drawing & DPR Preparation for TYANTRA NEORA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 204/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.94 | 2.51 | 100 | 0
1039 | NORTH 24 PARGANAS | Barasat Division | Augmentation of TYANTRA NEORA (POND) WATER SUPPLY SCHEME , SM/17680 | Augmentation | Formal work order for Providing FHTC including laying of Pipe Line, Renovation of Filter Media, Repairing of Wooden Jetty and Electro Mechanical Work for Augmentation at Tyantra Neora pond based water supply scheme in Basirhat - II Block of North 24 Parganas District under Barasat Division, P.H.E. Dte. | 1738/BD | 08/06/2023 | 90 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 88.36 | 49.8 | 56.36 | 30
1040 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of TYANTRA NEORA (POND) WATER SUPPLY SCHEME , SM/17680 | Augmentation | Providing And Installation of Electro Mechanical Equipment and Allied Works at TYANTRA NEORA (POND) Based Water Supply Scheme Dist. - North 24 Pgs under EMD, PHE Dte. (SM/17680) | 1170/EMD | 04/06/2025 | 150 | M/S SAJAHAN CHOWDHURY | 43.71 | 0 | 0 | 80
1041 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC , SM/11535 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Chhaygharia (Zone-II) Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 124/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.98 | 2.98 | 50 | 1
1042 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC , SM/11535 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Chhayagharia Zone- II water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 534/BON | 03/11/2021 | 21 | PRABIR KUMAR MONDAL. | 2.52 | 2.49 | 100 | 1
1043 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC , SM/11535 | Augmentation | Material Requisition To Resource Division | 3696/BD | 14/12/2022 | 0 | Resource Division | 51.36 | 0 | 0 | 0
1044 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC , SM/11535 | Augmentation | Material Requisition To Resource Division | 3661/BD | 13/12/2022 | 0 | Resource Division | 8.27 | 0 | 0 | 0
1045 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC , SM/11535 | Augmentation | Laying of badly damaged distribution pipe line and others allied for widening Panchayet Road from Chhaygharia Ajay Mondal's House to Khedapara F.P School to Trimonipara at Chhaygharia (Zone-II) water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 411/Bon | 23/08/2022 | 15 | PRABIR KUMAR MONDAL. | 4.55 | 3.39 | 100 | 1
1046 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC , SM/11535 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Chhayagharia(Zone-II) Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 3601/BD | 09/12/2022 | 90 | M/S B.N ENTERPRISE | 152.03 | 151.24 | 100 | 100
1047 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC , SM/11535 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Zone-II) (Replacement) under Chhaigharia W/S Scheme, District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 05) | 32/EMD | 03/01/2023 | 30 | M/S. MANABESH ROY | 22.15 | 16.02 | 72.31 | 1
1048 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC , SM/11535 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer at Chhaighoria (Zone-II) water supply scheme (2nd T/W Site) under Bongaon Sub-Division P.H.E.Dte. | 1545/BD | 19/05/2023 | 30 | NEW MA TARA ENTERPRISE. | 15.85 | 13.47 | 100 | 100
1049 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC , SM/11535 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at 1st Tube Well & 2nd Tube Well site and Construction of Approach Road at 1st Tube Well & 2nd Tube Well site under Augmentation of Chhaygharia (Zone-II) Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte | 38/BD | 04/01/2024 | 23 | M/S SANJAY ADHIKARI | 12 | 11.94 | 100 | 100
1050 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC , SM/11535 | Augmentation | Acceptance cum work order for Construction of Boundary wall, Approach Road, Earth Filling and Construction of 3.60 mtr. X 3.00 mtr. size Guard Room with sanitary and water supply arrangement incl. plinth protection at OHR site of Chhaygharia (Zone-II) Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 2357/BD | 20/08/2024 | 405 | B.S.ENTERPRISE. (BASIRHAT) | 45.95 | 4.58 | 9.97 | 15
1051 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC , SM/11535 | Augmentation | Installation of CCTV Camera Connection at Pump house no 1 & 2 for Chhaygharia (Zone-II) w/s scheme, Bongaon Block under Bongaon Sub-Division, PHE Dte. | 538/Bon | 23/04/2025 | 7 | ELDORADO | 0.55 | 0 | 0 | 0
1052 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC , SM/11535 | Augmentation | Acceptance cum work order for Construction of 150 cum. capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile, pile cap & Soil Investigation within command area for Augmentation of Chhaygharia Zone-II Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 2797/BD | 12/09/2023 | 730 | JOY HIND TUBEWELLS. | 91.85 | 23.41 | 25.1 | 60
1053 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC , SM/11535 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe under Augmentation work at Chhaygharia (Zone-II) W/S Scheme Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 3169/BD | 18/11/2024 | 180 | PRABIR KUMAR MONDAL. | 24.89 | 0 | 0 | 100
1054 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC , SM/11535 | Augmentation | Additional laying of UPVC pipe to connect every house hold FHTC with Augmentation work at Chhaygharia (Zone-II) W/S Scheme under Bongaon block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. (Part-A) | 1505/Bon | 30/12/2024 | 30 | R.A. ENTERPRISE. | 4.6 | 0 | 0 | 100
1055 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Chandpur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 793/BD | 13/03/2023 | 30 | M/S RAJPATH CONSTRUCTION. | 42.88 | 21.67 | 100 | 100
1056 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Material Requisition To Resource Division | 928/BD | 22/03/2023 | 0 | Resource Division | 55.9 | 0 | 0 | 0
1057 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Material Requisition To Resource Division | 4511/BD | 28/11/2023 | 0 | Resource Division | 26.12 | 0 | 0 | 0
1058 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Chandpur water supply scheme (Zone-I), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | 1150/BD | 13/04/2023 | 90 | M/S NIRMAN CONSTRUCTION. | 318.37 | 162.88 | 51.16 | 36
1059 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Formal work order for Construction of 150 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap in connection with Augmentation of Chandpur water supply scheme (Zone-I), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | 2329/BD | 16/08/2024 | 365 | GOPINATH ENTERPRISES | 100.59 | 0 | 0 | 0
1060 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing Functional Household Tap Connection in Connection with Augmentation of Chandpur water supply scheme (Zone-II), Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | 402/BD | 09/02/2023 | 90 | MONDAL & CO. (BASIRHAT). | 318.72 | 300.51 | 100 | 60
1061 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 (Size-3.60x3.00 mtr.) for Augmentation of Chandpur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 1429/BD | 11/05/2023 | 60 | PRITAM MUKHOPADHYAY. | 17.32 | 17.14 | 100 | 85
1062 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Rep.) under Talsa and adj. mouzas W/S Scheme and Talsa W/S Scheme with Pump House No-I under Chandpur (Block-Hasnabad) W/S Scheme District of 24 Pgs. (N) | 4803/EMD | 09/08/2023 | 30 | M/S S.R. ENTERPRISE | 60.76 | 9.86 | 100 | 80
1063 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Formal work order for Construction of 500 cum capacity 20 mtr staging height R.C.C Over Head Reservoir as per Deptt. design, drawing & specification including bored pile with pile cap in connection with Augmentation of Chandpur water supply scheme (Zone-II), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | 2866/BD | 20/09/2023 | 365 | MONDAL & CO. (BASIRHAT). | 202.58 | 192.31 | 85.53 | 75
1064 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Chandpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 294/BD | 30/01/2024 | 45 | M/S K.P.PAL. | 51.76 | 23.03 | 100 | 100
1065 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Quotation for Service Connection Charges for PH- I, Zone-II under Chandpur W/S Scheme in the district of North 24 Pgs. | BP-287-23-24 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.55 | 0 | 0 | 0
1066 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Quotation for Service Connection Charges for PH- II, Zone-II under Chandpur W/S Scheme in the district of North 24 Pgs. | BP-288-23-24 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.58 | 0 | 0 | 0
1067 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I , II Zone-II under Chandpur ground water based water supply scheme under Block_ Hasnabad Dist. - North 24 Parganas under EMD, PHE Dte. | 805/EMD | 11/03/2024 | 30 | UNIVERSAL ENTERPRISES | 24.76 | 21.56 | 87.06 | 90
1068 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at P.H. No.-I (New) under Chandpur W/S scheme, Zone-I under Block_ Hasnabad Dist. - 24Pgs(N) under EMD, PHE Dte. [SM/13313] | 1129/EMD | 04/06/2025 | 90 | GANAPATI ENTERPRISE | 14.06 | 0 | 0 | 0
1069 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, leftout work of 500 cum reservoir in connection with Augmentation of Chandpur w/s scheme (Z-II), Hasnabad Block, Construction of Protection wall for protection of UPVC distribution pipe line, Construction of approach road Zone-5 of Surfaced based w/s scheme Hasnabad, Protection works in different location of Amberia and Ghuni mouza, 2 nos. pump connection at PH No.-1 & 2 with CWR in connection within Amberia water supply scheme, Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 1748/BD | 28/05/2025 | 60 | M/S DATTA ENTERPRISE. | 102.67 | 0 | 0 | 80
1070 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Chandpur water supply scheme (Z-II) , Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 147/HSD | 27/01/2025 | 10 | ANKUSH CONSTRUCTION & CO. | 0.84 | 0 | 0 | 100
1071 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) for Augmentation of Chandpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 2973/BD | 04/10/2024 | 180 | SONALI CONSTRUCTION | 10.52 | 0 | 0 | 100
1072 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Acceptance cum work order for Strengthing of approach road for movement of rig machineries by UC bullah pile at Head Work site in connection with augmentation of Chandpur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub- Division P.H.E. Dte. | 347/HSD | 06/02/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.92 | 0 | 0 | 100
1073 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places in connection with Augmentation of Chandpur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 1527/BD | 14/05/2025 | 10 | ARBINA ENTERPRISE. | 9.5 | 0 | 0 | 100
1074 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Acceptance cum work order for Protection of IEP by UC bullah pile at PH No- 2 in connection with augmentation of Chandpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub- Division P.H.E. Dte. | 550/HSD | 10/03/2025 | 10 | M/S GHOSH CONSTRUCTION. | 0.92 | 0 | 0 | 100
1075 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection with augmentation of Chaimalpur water supply scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 152/HSD | 27/01/2025 | 10 | SARKAR ENTERPRISE | 0.47 | 0 | 0 | 100
1076 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with augmentation of Chaimalpur water supply scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 153/HSD | 27/01/2025 | 10 | SARKAR ENTERPRISE | 0.45 | 0 | 0 | 100
1077 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at different places in connection with Augmentation of Chandpur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 1481/HSD | 14/07/2025 | 10 | ARBINA ENTERPRISE. | 0.96 | 0 | 0 | 100
1078 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. , SM/13313 | Augmentation | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places in connection with Augmentation of Chandpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 1526/BD | 14/05/2025 | 10 | ARBINA ENTERPRISE. | 9.88 | 0 | 0 | 100
1079 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC , SM/11764 | Augmentation | Route Survey, Design Drawing & DPR Preparation for GOBINDAPUR Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 443 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.76 | 4.76 | 100 | 1
1080 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC , SM/11764 | Augmentation | Material Requisition To Resource Division | 3699/BD | 14/12/2022 | 0 | Resource Division | 26.46 | 0 | 0 | 0
1081 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC , SM/11764 | Augmentation | Material Requisition To Resource Division | 600/BD | 23/02/2023 | 0 | Resource Division | 9.36 | 0 | 0 | 0
1082 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC , SM/11764 | Augmentation | Material Requisition To Resource Division | 1244/BD | 25/04/2023 | 0 | Resource Division | 158.92 | 0 | 0 | 0
1083 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC , SM/11764 | Augmentation | Material Requisition To Resource Division | 1628/BD | 01/06/2023 | 0 | Resource Division | 9.42 | 0 | 0 | 0
1084 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC , SM/11764 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Gobindapur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 3488/BD | 02/12/2022 | 90 | M/S NIRMAN CONSTRUCTION. | 341.88 | 30.04 | 100 | 99
1085 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC , SM/11764 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Gabindapur Water Supply Scheme (H/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | 2921/BD | 26/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.13 | 13.5 | 100 | 29
1086 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC , SM/11764 | Augmentation | Regarding Restoration charges for road damages. | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 13.3 | 0 | 0 | 0
1087 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC , SM/11764 | Augmentation | Regarding Restoration charges for road damages. | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 8.79 | 0 | 0 | 0
1088 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC , SM/11764 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gobindapur water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | 170/BD | 19/01/2023 | 858 | KINGS & CO. | 437.87 | 122.72 | 62 | 66
1089 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC , SM/11764 | Augmentation | Acceptance cum work order for Construction of Boundary Wall at the site of Pump House -III of Gobindapur Water Supply Scheme under Basirhat Sub-Division within Barasat Division, P.H.E. Dte. | 58/BD | 07/01/2025 | 120 | IKBAL HOSSAIN | 14.35 | 0 | 0 | 60
1090 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC , SM/11764 | Augmentation | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site under Augmentation work at Gobindapur W/S Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1697/BD | 23/05/2025 | 120 | M/S B.K.ENTERPRISE. | 20.9 | 0 | 0 | 0
1091 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur to accommodate FHTC , SM/11764 | Augmentation | Acceptance cum work order for Construction of Boundary wall, Approach Road and plinth protection of Pump House at Head Work site of Gobindapur Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1769/BD | 29/05/2025 | 120 | RAKESH ENTERPRISE. | 24.5 | 0 | 0 | 0
1092 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Diara Water Supply Scheme at Bagdah Block (Phase-I) , SM/08070 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Diara Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 141/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.08 | 4.07 | 100 | 1
1093 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Diara Water Supply Scheme at Bagdah Block (Phase-I) , SM/08070 | Retrofitting | Repairing & Renovation 2(Two) nos of Pump House and allied works of Diara water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 516/Bon | 27/10/2021 | 21 | ROY ENGINEERS. | 2.52 | 2.47 | 100 | 0
1094 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Dighari Water Supply Scheme at Bongaon Block (Phase-II). , SM/08048 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DIGHARI Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (Phase-II) | 417/NWSD-I | 31/05/2021 | 60 | SUDHAMAY MAJUMDAR | 60.62 | 60 | 55.94 | 1
1095 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme for Arsenic affected areas at Deganga Block of North 24 Parganas , SM/08049 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of surface water based W/S scheme for Arsenic affected areas of Deganga Block under North 24 Parganas water supply Division - I, PHE Dte. | 205/NWSD-I | 26/02/2021 | 90 | PUSPA ENTERPRISE | 96.34 | 83.55 | 58.04 | 1
1096 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHAMARKALLA Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07600 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHAMARKALLA Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (PHASE-I). | 23/NWSD-I | 08/01/2021 | 90 | MONDAL ENTERPRISE | 89.99 | 138.87 | 63.43 | 1
1097 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHAMARKALLA Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07600 | Retrofitting | Hiring of Diesel Ambassador Car / Cab having licensed carriage contract permit from Regional Transport Authority for the office of the Executive Engineer, North 24- Pgs. W/S Division-I, P.H.E. Dte. at Barrackpore under the control of Assistant Engineer (HQ-II), North 24-Pgs. W/S Division-I, P.H.E. Dte. for 1 (One) year w.e.f. 01.1.2022. | 1088/NWSD-I | 16/12/2021 | 365 | BADAL GHOSH | 1.72 | 0.36 | 35.87 | 50
1098 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHAMARKALLA Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07600 | Retrofitting | Hiring of Diesel Ambassador Car / Cab having licensed carriage contract permit from Regional Transport Authority for the office of the Executive Engineer, North 24- Pgs. W/S Division-I, P.H.E. Dte. at Barrackpore under the control of Assistant Engineer (HQ-II), North 24-Pgs. W/S Division-I, P.H.E. Dte. for 1 (One) year w.e.f. 01.1.2022. | 1088/NWSD- I | 16/12/2021 | 1 | BADAL GHOSH | 1.72 | 0.51 | 51.04 | 100
1099 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadiknagar Zone-II Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) , SM/07617 | Retrofitting | Formal work order for "Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area Malatipur & Chaita (Part) Mouzas under Sadiknagar Zone - II Water Supply Scheme at Basirhat - II Block Under Barasat Division, PHE Dte. | 495/BD. | 26/02/2021 | 90 | ORIENT CONSTRUCTION. | 97.09 | 56.62 | 58.32 | 1
1100 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadiknagar Zone-II Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) , SM/07617 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for SADIKNAGAR-II Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 207/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.51 | 3.5 | 100 | 1
1101 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadiknagar Zone-II Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) , SM/07617 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Khulna Bhandarkhali Zone-I Water Supply Scheme under Barasat Division, PHE Dte. | 2177/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.92 | 3.93 | 100 | 1
1102 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadiknagar Zone-II Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) , SM/07617 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Krishnachandrapur Water Supply Scheme under Bongaon Sub-Division, under Barasat Division, PHE.Dte. | 612/Bon | 31/12/2021 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.09 | 4.07 | 100 | 1
1103 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadiknagar Zone-II Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) , SM/07617 | Retrofitting | Material Requisition To Resource Division | 2988/BD | 29/09/2022 | 0 | Resource Division | 0.01 | 0 | 0 | 0
1104 | NORTH 24 PARGANAS | Barasat Arsenic Division | Rejuvination of Magurati Srirampur water supply scheme under Baduria Block for providing Functional House Tap Conection , SM/07021 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Magurati Srirampur Mouza of Baduria Block from Magurati Srirampur Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. | 1886/B.Ar.D. | 18/12/2020 | 90 | UMA CONSTRUCTION | 39.19 | 55.48 | 168.66 | 1
1105 | NORTH 24 PARGANAS | Barasat Arsenic Division | Rejuvination of Magurati Srirampur water supply scheme under Baduria Block for providing Functional House Tap Conection , SM/07021 | Retrofitting | Protection of UPVC Pipeline ( approx 50 m.) near Pond of Ajarul Gazi, Safikul Islam and near Ramkrishna Brick Field under Command area of Magurati Srirampur W/S Scheme of Baduria Block in Connection of Retrofiting work for providing FHTC under Barasat Arsenic Division, P.H.E. Dte. | 300/B.Ar.D | 03/02/2021 | 20 | NEW BRIGHT CONSTRUCTION | 3.99 | 0 | 0 | 1
1106 | NORTH 24 PARGANAS | Barasat Arsenic Division | Rejuvination of Magurati Srirampur water supply scheme under Baduria Block for providing Functional House Tap Conection , SM/07021 | Retrofitting | Repairing and Renovation of 02 ( two) nos Pump House and allied works at the site of Magurati Srirampur W/S Scheme at Baduria block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | 282/B.Ar.D | 22/02/2022 | 20 | NIKHIL SAMADDAR | 4.62 | 0 | 0 | 1
1107 | NORTH 24 PARGANAS | Barasat Arsenic Division | Rejuvination of Magurati Srirampur water supply scheme under Baduria Block for providing Functional House Tap Conection , SM/07021 | Retrofitting | Surrender and transfer of unspent JJM fund. | 518 | 11/02/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW ACCOUNT | 259.1 | 0 | 0 | 0
1108 | NORTH 24 PARGANAS | Barasat Arsenic Division | Rejuvination of Magurati Srirampur water supply scheme under Baduria Block for providing Functional House Tap Conection , SM/07021 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Srikrishna Sarkar at purbapara under Magurati Srirampur W/S Scheme at Baduria block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | 560/B.Ar.D | 23/03/2022 | 15 | A 8T CONSTRUCTION | 4.11 | 4.11 | 99.92 | 100
1109 | NORTH 24 PARGANAS | Barasat Arsenic Division | Rejuvenation of Krishnapara Water Supply scheme under Hasnabad Block for providing Functional House Tap Connection , SM/07024 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Muragachha, Harikati and Krishnapara Mouzas of Hasnabad Block from Krishnapara Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. ( Phase-I ) | 1884/B.Ar.D. | 18/12/2020 | 90 | UTPAL CONSTRUCTION AND CO | 83.3 | 132.04 | 142.8 | 1
1110 | NORTH 24 PARGANAS | Barasat Arsenic Division | Rejuvenation of Krishnapara Water Supply scheme under Hasnabad Block for providing Functional House Tap Connection , SM/07024 | Retrofitting | Route survey, Distribution design & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Krishnapara & its adjoining mouza Water Supply Scheme in Hasnabad Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte | 1444/B.Ar.D | 31/08/2021 | 15 | RISHAN ENGINEERING CONSULTANCY | 2.49 | 2.49 | 50 | 1
1111 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Korakati Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) , SM/08761 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in different mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Korakati Water Supply scheme Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte.(Phase-I) | 1741/BD | 14/09/2021 | 45 | R.K.MANDAL AND CO. | 76.55 | 76.55 | 100 | 1
1112 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Korakati Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) , SM/08761 | Retrofitting | Acceptance cum work order for Additional Survey Work For DPR Preparation of Dakshin Bhebia Zone-II Water Supply Scheme under Barasat Division, PHE Dte. | 2182/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.99 | 1.99 | 100 | 1
1113 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Baunia Abad Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) , SM/08763 | Retrofitting | Acceptance cum work Order for Providing Functional Household Tap Connection (FHTC) in Baunia Abad mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. (Phase-I) | 93/BD | 17/01/2022 | 45 | M/S PROGATI ENTERPRISE. | 77.75 | 77.77 | 100 | 1
1114 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Baunia Abad Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) , SM/08763 | Retrofitting | Acceptance cum work order for Construction of Anchor block for resting of different dia DI Rising/Distribution main for low areas at different places for Rejuvenation of Baunia Abad w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division P.H.E. Dte. (Part-A) | 415/HSD | 04/03/2022 | 15 | M/S PROGATI ENTERPRISE. | 4.71 | 4.71 | 100 | 1
1115 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Baunia Abad Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) , SM/08763 | Retrofitting | Acceptance cum work order for Construction of Anchor block for resting of different dia DI Rising/Distribution main for low areas at different places for Rejuvenation of Baunia Abad w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division P.H.E. Dte. (Part-B) | 416/HSD | 04/03/2022 | 15 | M/S DATTA ENTERPRISE. | 4.04 | 4.04 | 100 | 1
1116 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Baunia Abad Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) , SM/08763 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Chandpur Water Supply Scheme under Barasat Division, PHE Dte. | 2166/HSD | 28/12/2021 | 21 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.5 | 4.46 | 100 | 1
1117 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Baunia Abad Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) , SM/08763 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line for providing FHTC by bamboo pilling at different places of Bashberia within Baunia Abad w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 785/HSD | 13/05/2022 | 10 | M/S DATTA ENTERPRISE. | 4.85 | 4.83 | 100 | 1
1118 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Baunia Abad Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) , SM/08763 | Retrofitting | Material Requisition To Resource Division | 1811/BD | 19/06/2023 | 0 | Resource Division | 3.15 | 0 | 0 | 0
1119 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Material Requisition To Resource Division | 2241/BD | 24/11/2021 | 0 | Resource Division | 10.26 | 0 | 0 | 0
1120 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Minakhan GP from 27.05.21 to 03.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | 405/HSD(Camp) | 27/05/2021 | 8 | MONDAL & CO. (BASIRHAT). | 4.58 | 4.58 | 100 | 0
1121 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Mohanpur GP from 27.05.21 to 30.05.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | 407/HSD(Camp) | 27/05/2021 | 4 | TRISHA ENTERPRISE & CO. | 4.77 | 4.77 | 100 | 0
1122 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Mohanpur GP from 31.05.21 to 06.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | 408/HSD(Camp) | 27/05/2021 | 7 | MONDAL & CO. (BASIRHAT). | 4.51 | 4.51 | 100 | 0
1123 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Atpukur GP from 31.05.21 to 06.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | 410/HSD(Camp) | 27/05/2021 | 7 | MONDAL & CO. (BASIRHAT). | 4.55 | 4.55 | 100 | 0
1124 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Khulna GP from 27.05.21 to 29.05.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 429/HSD(Camp) | 27/05/2021 | 3 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.49 | 4.49 | 100 | 0
1125 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Dulduli GP from 21.06.21 to 27.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 571/HSD(Camp) | 14/06/2021 | 7 | M/S DATTA ENTERPRISE. | 4.68 | 4.68 | 100 | 0
1126 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Monipur GP from 04.06.21 to 09.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 470/HSD(Camp) | 03/06/2021 | 6 | M/S NIRMAN CONSTRUCTION. | 4.85 | 4.85 | 100 | 0
1127 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Monipur GP from 10.06.21 to 15.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 471/HSD(Camp) | 03/06/2021 | 6 | M/S NIRMAN CONSTRUCTION. | 4.85 | 4.85 | 100 | 0
1128 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Rupamari GP from 05.06.21.21 to 08.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 496/HSD(Camp) | 03/06/2021 | 4 | MONDAL & CO. (BASIRHAT). | 4.74 | 4.74 | 100 | 0
1129 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Dulduli GP from 07.06.21 to 13.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte | 499/HSD(Camp) | 03/06/2021 | 7 | M/S DATTA ENTERPRISE. | 4.68 | 4.68 | 100 | 0
1130 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sahebkhali GP from 07.06.21 to 13.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 500/HSD(Camp) | 03/06/2021 | 7 | M/S DATTA ENTERPRISE. | 4.69 | 4.69 | 100 | 0
1131 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Monipur GP from 27.05.21 to 28.05.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 423/HSD(Camp) | 27/05/2021 | 2 | M/S NIRMAN CONSTRUCTION. | 4.94 | 4.94 | 100 | 0
1132 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Monipur GP from 29.05.21 to 03.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 424/HSD(Camp) | 27/05/2021 | 6 | M/S NIRMAN CONSTRUCTION. | 4.85 | 4.85 | 100 | 0
1133 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bamanpukur GP from 27.05.21 to 03.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | 406/HSD(Camp) | 27/05/2021 | 8 | MONDAL & CO. (BASIRHAT). | 4.8 | 4.8 | 100 | 0
1134 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Khulna GP from 30.05.21 to 06.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 430/HSD(Camp) | 27/05/2021 | 8 | S.K.ENTERPRISE. | 4.76 | 4.76 | 100 | 0
1135 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Rupamari GP on 27.05.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 436/HSD(Camp) | 27/05/2021 | 1 | MONDAL & CO. (BASIRHAT). | 4.78 | 4.78 | 100 | 0
1136 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sahebkhali GP from 27.05.21 to 30.05.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 438/HSD(Camp) | 27/05/2021 | 4 | M/S PROGATI ENTERPRISE. | 4.7 | 4.7 | 100 | 0
1137 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Rupamari GP from 01.06.21 to 04.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 451/HSD(Camp) | 27/05/2021 | 4 | MONDAL & CO. (BASIRHAT). | 4.73 | 4.73 | 100 | 0
1138 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Khulna GP from 07.06.21 to 14.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 475/HSD(Camp) | 03/06/2021 | 8 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.76 | 4.76 | 100 | 0
1139 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Rupamari GP from 28.05.21 to 31.05.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 446/HSD(Camp) | 27/05/2021 | 4 | MONDAL & CO. (BASIRHAT). | 4.74 | 4.74 | 100 | 0
1140 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Minakhan GP from 04.06.21 to 15.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | 489/HSD(Camp) | 03/06/2021 | 12 | MONDAL & CO. (BASIRHAT). | 4.85 | 4.85 | 100 | 0
1141 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Dulduli GP from 31.05.21 to 06.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 450/HSD(Camp) | 27/05/2021 | 7 | M/S DATTA ENTERPRISE. | 4.69 | 4.69 | 100 | 0
1142 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Minakhan GP from 16.06.21 to 27.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | 522/HSD(Camp) | 14/06/2021 | 12 | MONDAL & CO. (BASIRHAT). | 4.85 | 4.85 | 100 | 0
1143 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bamanpukur GP from 16.06.21 to 27.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | 523/HSD(Camp) | 14/06/2021 | 12 | TRISHA ENTERPRISE & CO. | 4.85 | 4.85 | 100 | 0
1144 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bamanpukur GP from 28.06.21 to 03.07.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | 524/HSD(Camp) | 14/06/2021 | 6 | MONDAL & CO. (BASIRHAT). | 1.82 | 1.82 | 100 | 0
1145 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Mohanpur GP from 14.06.21 to 20.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | 525/HSD(Camp) | 14/06/2021 | 7 | TRISHA ENTERPRISE & CO. | 4.53 | 4.53 | 100 | 0
1146 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Mohanpur GP from 21.06.21 to 28.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | 526/HSD(Camp) | 14/06/2021 | 8 | MONDAL & CO. (BASIRHAT). | 4.86 | 4.86 | 100 | 0
1147 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Atpukur GP from 14.06.21 to 20.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | 527/HSD(Camp) | 14/06/2021 | 7 | MONDAL & CO. (BASIRHAT). | 4.53 | 4.53 | 100 | 0
1148 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Atpukur GP from 21.06.21 to 28.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | 528/HSD(Camp) | 14/06/2021 | 8 | MONDAL & CO. (BASIRHAT). | 4.86 | 4.86 | 100 | 0
1149 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Disinfection & repairing of tube wells at different places in different GPs within Minakhan block due to cyclone 'YAAS' under Hasnabad Sub-Division, PHE Dte. | 529/HSD(Camp) | 14/06/2021 | 7 | TRISHA ENTERPRISE & CO. | 3.71 | 3.71 | 100 | 0
1150 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bamanpukur GP from 04.06.21 to 15.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | 490/HSD(Camp) | 03/06/2021 | 12 | MONDAL & CO. (BASIRHAT). | 4.85 | 4.85 | 100 | 0
1151 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Mohanpur GP from 07.06.21 to 13.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | 491/HSD(Camp) | 03/06/2021 | 7 | TRISHA ENTERPRISE & CO. | 4.53 | 4.53 | 100 | 0
1152 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Atpukur GP from 07.06.21 to 13.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | 492/HSD(Camp) | 03/06/2021 | 7 | MONDAL & CO. (BASIRHAT). | 4.53 | 4.53 | 100 | 0
1153 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bhabanipur GP from 06.06.21 to 11.06.21 due to cyclone 'YAAS', Hasnabad block under Hasnabad Sub-Division, PHE Dte. | 498/HSD(Camp) | 03/06/2021 | 6 | M/S K.B.ENTERPRISE. | 3.07 | 3.07 | 100 | 0
1154 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Rupamari GP from 09.06.21.21 to 12.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 501/HSD(Camp) | 03/06/2021 | 4 | MONDAL & CO. (BASIRHAT). | 4.74 | 4.74 | 100 | 0
1155 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Durgamandop GP from 26.06.21 to 29.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 546/HSD(Camp) | 14/06/2021 | 4 | M/S NIRMAN CONSTRUCTION. | 2.77 | 2.77 | 100 | 0
1156 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Korakati GP from 27.06.21 to 29.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 549/HSD(Camp) | 14/06/2021 | 3 | M/S NIRMAN CONSTRUCTION. | 1.78 | 1.78 | 100 | 0
1157 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Khulna GP from 15.06.21 to 20.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 550/HSD(Camp) | 14/06/2021 | 6 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.75 | 4.75 | 100 | 0
1158 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Khulna GP from 21.06.21 to 26.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 551/HSD(Camp) | 14/06/2021 | 6 | S.K.ENTERPRISE. | 4.76 | 4.76 | 100 | 0
1159 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Khulna GP from 27.06.21 to 29.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 552/HSD(Camp) | 14/06/2021 | 3 | M/S NIRMAN CONSTRUCTION. | 1.78 | 1.78 | 100 | 0
1160 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sahebkhali GP from 14.06.21 to 20.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 560/HSD(Camp) | 14/06/2021 | 7 | M/S DATTA ENTERPRISE. | 4.68 | 4.68 | 100 | 0
1161 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Dulduli GP from 14.06.21 to 20.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte | 561/HSD(Camp) | 14/06/2021 | 7 | M/S PROGATI ENTERPRISE. | 4.68 | 4.68 | 100 | 0
1162 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Rupamari GP from 21.06.21.21 to 24.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 569/HSD(Camp) | 14/06/2021 | 4 | MONDAL & CO. (BASIRHAT). | 4.73 | 4.73 | 100 | 0
1163 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Atpukur GP from 27.05.21 to 30.05.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | 409/HSD(Camp) | 27/05/2021 | 4 | TRISHA ENTERPRISE & CO. | 4.81 | 4.81 | 100 | 0
1164 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. , SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sahebkhali GP from 31.05.21 to 06.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 449/HSD(Camp) | 27/05/2021 | 7 | M/S PROGATI ENTERPRISE. | 4.69 | 4.69 | 100 | 0
1165 | NORTH 24 PARGANAS | Barasat Arsenic Division | Extension of Piped Water Supply (PWS) to Anganwadi Centre (AWCs 56 Nos.) located within the command area of PWS schemes under Barasat Arsenic Division, PHE Dte , SM/09039 | Anganwadi | Arrangement of Drinking Water for Anganwadi Center having Electrical Power connection and located within Command area of Piped Water supply scheme (PWSS) for Sandeshkhali -II Block of North 24 Pgs district under Barasat Arsenic Division, PHE Dte. (Type -IA Electrical Power Operated) | 1935/B.Ar.D. | 18/11/2021 | 30 | MONDAL ENTERPRISE | 13.96 | 13.96 | 50 | 0
1166 | NORTH 24 PARGANAS | Barasat Arsenic Division | Extension of Piped Water Supply (PWS) to Anganwadi Centre (AWCs 56 Nos.) located within the command area of PWS schemes under Barasat Arsenic Division, PHE Dte , SM/09039 | Anganwadi | Arrangement of Drinking Water for Anganwadi Center having Electrical Power connection and located within Command area of Piped Water supply scheme (PWSS) for Baduria, Hasnabad of North 24 Pgs district under Barasat Arsenic Division, PHE Dte. (Type -IA Electrical Power Operated) | 1936/B.Ar.D. | 18/11/2021 | 30 | MAHALAXMI CONSTRUCTION | 13.25 | 13.24 | 36.56 | 0
1167 | NORTH 24 PARGANAS | Barasat Arsenic Division | Extension of Piped Water Supply (PWS) to Anganwadi Centre (AWCs 56 Nos.) located within the command area of PWS schemes under Barasat Arsenic Division, PHE Dte , SM/09039 | Anganwadi | Arrangement of Drinking Water for Anganwadi Center having Electrical Power connection and located within Command area of Piped Water supply scheme (PWSS) for Rajarhat Block of North 24 Pgs district under Barasat Arsenic Division, PHE Dte. (Type -IA Electrical Power Operated). | 1937/B.Ar.D. | 18/11/2021 | 45 | N. H. ENTERPRISE | 21.11 | 19.55 | 50 | 0
1168 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Boyermari Abad Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) , SM/08766 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in different mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Boyermari Abad Water Supply scheme Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte.(Phase-I) | 1738/BD | 14/09/2021 | 45 | DEBAPRASAD MONDAL. | 81.09 | 78.93 | 100 | 1
1169 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Boyermari Abad Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) , SM/08766 | Retrofitting | Material Requisition To Resource Division | 1812/BD | 19/06/2023 | 0 | Resource Division | 16.51 | 0 | 0 | 0
1170 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Patua W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). , SM/09730 | Retrofitting | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area under Patua Water Supply Scheme at SWARUPNAGAR Block, Dist.- North 24 Parganas under Barasat Division. PHE. Dte. (PHASE-I) | 1177/BD | 19/04/2022 | 90 | KINGS & CO. | 193.55 | 172.97 | 73.95 | 1
1171 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Patua W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). , SM/09730 | Retrofitting | Material Requisition To Resource Division | 2342/BD | 26/09/2022 | 0 | Resource Division | 24.12 | 0 | 0 | 0
1172 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of BANGLANI W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08640 | Retrofitting | Formal work order for for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Banglani Water Supply Scheme at Swarupnagar Block under Barasat Division, PHE Dte. (Phase - I) | 217/BD | 24/01/2022 | 90 | JAL PRAVAHIKA PVT. LTD. | 221.85 | 168.02 | 75.73 | 1
1173 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of BANGLANI W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08640 | Retrofitting | Hiring 1(one) no. Diesel Luxary Car on daily basis (for 01.09.2021 to 31.08.2022) for office use of the Assistant Engineer, R.W.S, Barasat Sub- Division, P.H.E. Dte. | 447/BST | 25/08/2021 | 365 | DEBAPRASAD MONDAL. | 1.72 | 1.31 | 76.18 | 1
1174 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of BANGLANI W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08640 | Retrofitting | Continuation work order for Hiring 1(one) no. Diesel Luxary Car on daily basis (for 01.09.2022 to 31.12.2022) for office use of the Assistant Engineer, R.W.S Barasat Sub-Division, P.H.E. Dte. | 641/BST | 31/08/2022 | 122 | DEBAPRASAD MONDAL. | 0.58 | 0.93 | 100 | 1
1175 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of BANGLANI W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08640 | Retrofitting | Continuation work order for the work of Hiring Diesel Luxury Car on daily basis for the Office of the Dy. Superintending Engineer-I, Monitoring Cell, PHE Dte. (Period from 01-07-2022 to 31-12-2022). | 1819/BD | 27/06/2022 | 184 | DIPANKAR NASKAR. | 0.87 | 1.77 | 202.68 | 1
1176 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of BANGLANI W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08640 | Retrofitting | Continuation work order for Hiring 1(one) no. Diesel Luxary Car on daily basis (for 01.01.2023 to 30.04.2023) for office use of the Assistant Engineer, R.W.S Barasat Sub-Division, P.H.E. Dte. | 883/BST | 28/12/2022 | 120 | DEBAPRASAD MONDAL. | 0.57 | 0.95 | 100 | 1
1177 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of BANGLANI W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08640 | Retrofitting | Material Requisition To Resource Division | 2338/BD | 26/09/2022 | 0 | Resource Division | 61.5 | 0 | 0 | 0
1178 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of MATHURAPUR W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08656 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Mathurapur Water Supply Scheme at Basirhat-II Block under Barasat Division, PHE Dte.(Phase-I). | 1655/BD | 07/09/2021 | 45 | CHANCHAL ENTERPRISE & CO. | 85.87 | 83.61 | 100 | 1
1179 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of MATHURAPUR W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08656 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for MATHURAPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 341/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.5 | 3.5 | 100 | 1
1180 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of MATHURAPUR W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08656 | Retrofitting | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Basirhat-II Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - A) | 149/BHTSD | 29/01/2025 | 20 | BIBHAS PAL. | 0.88 | 0 | 0 | 90
1181 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gabberia Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) , SM/08256 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in different mouza including laying of UPVC/PVC pipe line and necessary fittings within Gabberia Water Supply Scheme at Sandeshkhali-II Block under Hsnabad Sub-Division, PHE Dte.(Phase-I) | 435/BD. | 22/02/2021 | 30 | DEBAPRASAD MONDAL. | 77.8 | 32.86 | 42.23 | 1
1182 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gabberia Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) , SM/08256 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Durgapur Baylani Zone I Water Supply Scheme under Barasat Division, PHE Dte. | 2158/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.18 | 4.13 | 100 | 1
1183 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gabberia Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) , SM/08256 | Retrofitting | Material Requisition To Resource Division | 1819/BD | 19/06/2023 | 0 | Resource Division | 21.78 | 0 | 0 | 0
1184 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bajitpur (Zone-I) Piped Water Supply Scheme at Baduria Block (Phase-I) , SM/08644 | Retrofitting | Additional Survey work for DPR Preparation for BAJITPUR ZONE -1 Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 354/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.63 | 0.61 | 100 | 1
1185 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bajitpur (Zone-I) Piped Water Supply Scheme at Baduria Block (Phase-I) , SM/08644 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for BAJITPUR ZONE 1 Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 353/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.97 | 4.97 | 100 | 1
1186 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bajitpur (Zone-I) Piped Water Supply Scheme at Baduria Block (Phase-I) , SM/08644 | Retrofitting | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area under BAJITPUR ZONE-I Water Supply Scheme at Baduria Block, District- North 24 Parganas under Barasat Division,PHE Dte. (Phase-I) | 141/BD | 18/01/2022 | 90 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 266.04 | 179.15 | 64.61 | 1
1187 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bajitpur (Zone-I) Piped Water Supply Scheme at Baduria Block (Phase-I) , SM/08644 | Retrofitting | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Baduria Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - C) | 145/BHTSD | 29/01/2025 | 20 | M.R.CONSTRUCTION. | 0.88 | 0 | 0 | 90
1188 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of DHANYAKURIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/08788 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Dhanyakuria water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase - I) | 404/BD | 10/02/2022 | 45 | UTPAL CONSTRUCTION & CO. | 82.7 | 73.58 | 88.97 | 1
1189 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of DHANYAKURIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/08788 | Retrofitting | Additional Route Survey work for DPR Preparation for DHANYAKURIA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 347/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.25 | 1.25 | 100 | 1
1190 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of DHANYAKURIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/08788 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for DHANYAKURIA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 346/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.79 | 4.79 | 100 | 1
1191 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of DHANYAKURIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/08788 | Retrofitting | Material Requisition To Resource Division | 2989/BD | 29/09/2022 | 0 | Resource Division | 7.39 | 0 | 0 | 0
1192 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. , SM/10374 | Augmentation | Material Requisition To Resource Division | 939/BD | 22/03/2023 | 0 | Resource Division | 9.92 | 0 | 0 | 0
1193 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. , SM/10374 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Baunia Abad water supply scheme, Sandeshkhali-I Block within Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | 2721/BD | 14/09/2022 | 90 | KINGS & CO. | 452.15 | 393.02 | 100 | 1
1194 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. , SM/10374 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 1201/BD | 20/04/2023 | 30 | M/S NIRMAN CONSTRUCTION. | 62.06 | 43.71 | 100 | 56
1195 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. , SM/10374 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site in connectin with Augmentation of Baunia Abad W/S scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 288/HSD | 06/03/2024 | 10 | DEBAPRASAD MONDAL. | 0.84 | 0.84 | 100 | 100
1196 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. , SM/10374 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 350/BD | 31/01/2025 | 90 | M/S DATTA ENTERPRISE. | 223.88 | 0 | 0 | 0
1197 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. , SM/10374 | Augmentation | Acceptance cum work order for Sinking of Additional 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 3303/BD | 27/11/2024 | 270 | JOY GURU ENTERPRISE | 63.39 | 0 | 0 | 0
1198 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. , SM/10374 | Augmentation | Acceptance cum work order for additional Construction of 2 nos. switch room cum chlorine room (5.40x3.60) for augmentation of Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 1633/BD | 20/05/2025 | 60 | JAGANNATH CONSTRUCTION. | 18.2 | 0 | 0 | 0
1199 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. , SM/10374 | Augmentation | Formal work order for construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Baunia Abad water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | 1724/BD | 08/06/2023 | 662 | DEBAPRASAD MONDAL. | 187.27 | 151.07 | 90.5 | 100
1200 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. , SM/10374 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (replacement) under Baunia Abad W/S Scheme District of North 24 Pgs. Tender No.- 08(Sl. No.-06) of EE/EMD of 2022-23 | 3387EMD | 09/09/2022 | 935 | GOENKA ENTERPRISE | 11.36 | 10.21 | 94.51 | 10
1201 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. , SM/10374 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (replacement) under Baunia Abad W/S Scheme District of North 24 Pgs. | 3388EMD | 09/09/2022 | 935 | POLYCON ENGINEERS | 11.36 | 10.55 | 100 | 10
1202 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. , SM/10374 | Augmentation | Additional work i.c.w. Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No- I (Replacement) under Bounia Abad W/S Scheme, Dist. 24 Pgs (N) | 952/EMSD-I | 12/08/2024 | 10 | GOENKA ENTERPRISE | 0.42 | 0 | 0 | 100
1203 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. , SM/10374 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection with Augmentation of Baunia Abad water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 335/HSD | 06/02/2025 | 10 | M/S PROGATI ENTERPRISE. | 0.88 | 0 | 0 | 100
1204 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. , SM/10374 | Augmentation | Additional work icw Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug.work related to FHTC) at Pump House No.II (replacement) under Boania Abad W/S Scheme, District of 24 Pgs.(N). | 957/EMSD-I | 12/08/2024 | 10 | POLYCON ENGINEERS | 0.42 | 0.39 | 100 | 100
1205 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. , SM/10374 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation of Baunia Abad water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 339/HSD | 06/02/2025 | 10 | M/S PROGATI ENTERPRISE. | 0.88 | 0 | 0 | 100
1206 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. , SM/10374 | Augmentation | Acceptance cum work order for Providing Functional household tap connection at Madhya Baunia Jatindra Adarsha Jr. High School, Baunia 24 no Sabkhali para SSK, Baunia 25 no Booth SSK and Chotto Sehara Thakurmoni FP School within the command area of Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 546/HSD | 10/03/2025 | 10 | SARKAR ENTERPRISE | 0.96 | 0 | 0 | 100
1207 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bounia Abad to accommodate FHTC Block Sandeshkhali-I. , SM/10374 | Augmentation | Acceptance cum work order for Temporary approach road for movement of rig machine and other allied machineries at PH No-2 within Baunia Abad w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 231/HSD | 30/01/2025 | 10 | M/S NIRMAN CONSTRUCTION. | 0.89 | 0 | 0 | 100
1208 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jeliakhali Purba Khanda W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (P , SM/10504 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Jeliakhali Purba Khanda W/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 1605/BD | 07/06/2022 | 90 | SUBHASH BOSE. | 126.81 | 120.92 | 100 | 1
1209 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jeliakhali Purba Khanda W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (P , SM/10504 | Retrofitting | Acceptance cum work order Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC pipe line at different places at Jeliakhali Purba mouza within Jeliakhali Purbakhanda w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 533/HSD | 15/03/2022 | 15 | PRITAM MUKHOPADHYAY. | 4.77 | 4.71 | 100 | 1
1210 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jeliakhali Purba Khanda W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (P , SM/10504 | Retrofitting | Acceptance cum work order for Sinking of Additional 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Jeliakhali Purbakhanda w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 3314/BD | 27/11/2024 | 30 | JOY GURU ENTERPRISE | 31.69 | 0 | 0 | 0
1211 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jeliakhali Purba Khanda W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (P , SM/10504 | Retrofitting | Formal work order for Protection work in different places of Jeliakhali Mouza in connection with retrofitting of Jeliakhali Purba Khanda w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1496/BD | 17/05/2023 | 30 | SUBHASH BOSE. | 137.02 | 135.82 | 100 | 100
1212 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Jeliakhali Purba Khanda W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (P , SM/10504 | Retrofitting | Acceptance cum work order for Construction of boundary wall with brick masonry structure at Head Work site within Jeliakhali Purbakhanda w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 4382/BD | 10/11/2023 | 90 | MD.SALIM GAZI. | 28.33 | 26.22 | 100 | 68
1213 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. , SM/10415 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under Bayra W/S Scheme District of 24 Pgs. (N) | 6150 / EMD | 14/08/2022 | 30 | TAMAL ENTERPRISE | 13.22 | 10.93 | 82.7 | 1
1214 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. , SM/10415 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I under Bayra W/S Scheme District of 24 Pgs. (N), | 6149/-EMD | 14/08/2022 | 30 | DEY ENTERPRISE | 13.22 | 10.93 | 82.7 | 1
1215 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. , SM/10415 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system & Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of Bayra Water Supply Scheme in Bagdah Block under district North 24 Parganas Water Supply Division-I, PHE. Dte. | 867/NWSD-I | 21/07/2022 | 90 | H. I. ENTERPRISE | 306.66 | 313.23 | 100 | 98
1216 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. , SM/10415 | Augmentation | Material Requisition To Resource Division | 877/NWSD-I | 22/07/2022 | 0 | Resource Division | 26.15 | 0 | 0 | 0
1217 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. , SM/10415 | Augmentation | Sinking of 1 no. 300 mm. x 200 mm. dia. 250 mtr. Deep tube well by D.R. Rig method at Head Work Site at Boyra Water Supply Scheme under Bagdah Block within the jurisdiction of North 24 Pgs Water Supply Division- I, P.H.E. Dte. | 2028/NWSD-I | 13/12/2023 | 30 | ACME CONSTRUCTION | 19.35 | 15.97 | 100 | 100
1218 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. , SM/10415 | Augmentation | Construction of 250 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials, Construction Boundary Wall & Service Road at Pump House and head work site, Augmentation of Bayra Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. | 640/NWSD-I | 26/05/2023 | 1224 | M/S. BUILDWELL | 156.3 | 24.81 | 15.87 | 35
1219 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. , SM/10415 | Augmentation | Inter connection with new Tube well at H/W site under Augmentation Scheme of Bayra within the jurisdiction of N24Pgs. W/S Division-I, P.H.E. Dte. | 52/NWSD-I | 09/01/2025 | 7 | ARUP CONSTRUCTION | 0.93 | 0 | 0 | 100
1220 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Ground Water Based Piped Water Supply Scheme for Bayra in Bagdah Block of North 24 Parganas District under North 24 Pgs Water Supply Division-I, P.H.E. Dte. , SM/10415 | Augmentation | Repairing and renovation of boundary illumination arrangement and allied works at P.H. No. I (OHR site) under Bayra W/S Scheme under EMSD-I, P.H.E.Dte. Dist.- 24PGS(N). | 453/EMSD-I | 08/04/2025 | 30 | ANJAN ENTERPRISE | 2.52 | 0 | 0 | 100
1221 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | Preparation of Augmentation DPR for Paltadanga Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | 1957/B.Ar.D | 26/09/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0.98 | 100 | 1
1222 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | Material Requisition To Resource Division | 2291/B.Ar.D | 02/12/2022 | 0 | Resource Division | 146.5 | 0 | 0 | 0
1223 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I under Paltadanga W/S Scheme District of North 24 Pgs. NIET No.- 12 of EE/EMD of 2022-23 (Sl. No.- 03) | 5090/EMD | 04/11/2022 | 30 | KASHINATH PAL & CO. | 11.29 | 8.78 | 77.75 | 78
1224 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | Hiring of one (1) no. Diesel operated AC motor cab / maxi cab (Car No. - WB-08C-5757) with engine capacity less than or equal to 2000 C.C. with driver for official use of the Chief Engineer (Head Quarters), PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for six months (w.e.f. 02.01.2023 to 02.07.2023). | 2550/B.Ar.D | 29/12/2022 | 182 | RANA PAUL | 0.95 | 2.39 | 100 | 0
1225 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | Hiring of one (1) no. Diesel operated motor cab (WB-07J-7190) with driver for official use for Deputy Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for six months (w.e.f. 09.01.2023 to 09.07.2023). | 2512/B.Ar.D | 23/12/2022 | 182 | PRIYANKI SADHUKHAN | 0.86 | 1.34 | 100 | 100
1226 | NORTH 24 PARGANAS | Central Drilling | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Paltadanga W/S Scheme (TW-I), Barasat-II Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | 1647/CDD | 17/10/2023 | 30 | SUBHRA ENTERPRISE | 21.79 | 0 | 0 | 0
1227 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | Repair and Renovation works of R.C.C. Elevated Reservoir of Capacity 550 CUM at Paltadanga W/S Scheme of Barasat - II block under Barasat Arsenic Division PHE Dte. | 466/B.Ar.D. | 27/02/2023 | 60 | G. S. CONSTRUCTION & CO. | 19.14 | 18.21 | 100 | 100
1228 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | Hiring of one (1) no. Diesel operated motor cab (Car No.- WB-20BP-9500) with driver for official use for Deputy Superintending Engineer, Eastern Circle, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for six months (w.e.f. 01.01.2023 to 01.07.2023). | 2549/B.Ar.D | 29/12/2022 | 182 | RAJ ENTERPRISE | 0.86 | 2.15 | 100 | 1
1229 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | Material Requisition To Resource Division | 2105/B.Ar.D. | 02/11/2022 | 0 | Resource Division | 12.6 | 0 | 0 | 0
1230 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | Wayleave facility charges from Stn. Sondalia to Beliaghata Road Halt | 237 | 16/08/2023 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS) | 15.24 | 0 | 0 | 0
1231 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | Wayleave plan & survey charges | 180 | 24/07/2023 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS) | 0.21 | 0 | 0 | 0
1232 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Paltadanga W/S Scheme District of North 24 Pgs. NIET No.- 12 of EE/EMD of 2022-23 (Sl. No.-04) | 5091/EMD | 04/11/2022 | 30 | MAHAMAYA ENTERPRISE. | 11.17 | 6.66 | 59.66 | 60
1233 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (Car No.- WB-20BP-9500) with driver for official use for Deputy Superintending Engineer, Eastern Circle, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for six months (w.e.f. 02.07.2023 to 30.12.2023)". | 1535/B.Ar.D | 30/06/2023 | 182 | RAJ ENTERPRISE | 0.86 | 2.26 | 100 | 100
1234 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | Road Restoration of Aminpur - Boalghata road due to Laying of different dia UPVC pipe line under Paltadanga W/S Scheme at Barasat-II Block under Barasat Arsenic Division, PHE Dte. | 1848/B.Ar.D | 21/11/2024 | 21 | P & S ASSOCIATES | 0.94 | 0 | 0 | 100
1235 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | Laying of distribution System including specials , valves all complete Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Paltadanga under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 1708/B.Ar.D. | 02/09/2022 | 1185 | M/S. S. S. ENTERPRISE | 344.61 | 311.65 | 91.71 | 98
1236 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | Supplying, Laying, fitting and fixing of DI pipe and Repairing, Renovation and protection of boundary wall, Fencing work etc. and other allied works at Head work site of Paltadanga Ground Water Based Piped W/S Scheme under Barasat-II Block under Barasat Arsenic Division PHE Dte. | 389/B.Ar.D | 21/02/2024 | 246 | NIKHIL SAMADDAR | 19.27 | 16.06 | 83.53 | 70
1237 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | Recycling of IEP Back Wash with its ancillaries works at the site of Paltadanga W/S Scheme under augmentation Scheme at Barasat-II Block North 24 pgs. District under Barasat Arsenic Division, P.H.E. Dte. | 384/B.Ar.D. | 21/02/2024 | 360 | M/S B. B. ENGINEERING | 11.16 | 0 | 0 | 100
1238 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | Restoration due to laying of various dia UPVC/HDPE Pipe for distribution line at Bharpara Baramallika mouza of Paltadanga W/S Scheme under Barasat -II block under Barasat Arsenic Division, PHE Dte. | 1849/B.Ar.D | 21/11/2024 | 30 | BALAJEE ENTERPRISES | 0.92 | 0 | 0 | 100
1239 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PALTADANGA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10549 | Augmentation | Supplying, Laying, Fitting, fixing and jointing of different dia UPVC pipe line for distribution network and other allied works at Head work site of Paltadanga W/S Scheme under Barasat Arsenic Division PHE Dte. (SM/10549) | 295/B.Ar.D. | 18/02/2025 | 275 | N. H. ENTERPRISE | 17.94 | 0 | 0 | 100
1240 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Tushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10550 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Tushkhali W/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 1604/BD | 07/06/2022 | 90 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 183.73 | 164.74 | 100 | 0
1241 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Tushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10550 | Retrofitting | Acceptance cum work order for Sinking of Additional 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Tushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 3334/BD | 28/11/2024 | 30 | UTPAL CONSTRUCTION & CO. | 31.69 | 0 | 0 | 0
1242 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Tushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10550 | Retrofitting | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter at Joygopalpur tail end within Tushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 3378/BD | 02/12/2024 | 30 | CHANCHAL ENTERPRISE & CO. | 31.47 | 0 | 0 | 0
1243 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Tushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10550 | Retrofitting | Acceptance cum Work order for Construction of boundary wall with RCC column structure at Head Work site within Tushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 4379/BD | 10/11/2023 | 90 | R. B. ENTERPRISE | 21.29 | 18.48 | 100 | 100
1244 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Tushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10550 | Retrofitting | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site at PH No.-1 within Tushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 259/BD | 22/01/2025 | 45 | B.S.ENTERPRISE. (BASIRHAT) | 34.32 | 0 | 0 | 0
1245 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Tushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10550 | Retrofitting | Acceptance cum work order for Construction of additional 1 no. switch room cum chlorine room (5.40x3.60) with sanitary and water supply arrangement including plinth protection at Joygopalpur tail end within Tushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 951/BD | 25/03/2025 | 75 | SABIR ALI GAZI | 8.92 | 0 | 0 | 0
1246 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Tushkhali W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10550 | Retrofitting | Acceptance cum work order for Emergent withdrawing, relaying and laying of different dia. UPVC/DI pipe line at Tushkhali water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E.Dte | 391/BD | 05/02/2025 | 60 | ANKUSH CONSTRUCTION & CO. | 36.68 | 0 | 0 | 100
1247 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah , SM/10298 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Kurulia (Zone-I) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 138/BON | 18/02/2022 | 15 | UMWELT ENGINEER PVT.LTD. | 4.05 | 4.03 | 50 | 1
1248 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah , SM/10298 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I(Z-I) under Kurulia W/S Scheme District of 24 Pgs. (N) (Block- Baduria). NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.- 05) | 6142/EMD | 11/11/2022 | 30 | SWAPAN ENTERPRISE | 12.83 | 11.66 | 90.85 | 0
1249 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah , SM/10298 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II(Z-I) under Kurulia W/S Scheme District of 24 Pgs. (N) (Block- Baduria). NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.-06) | 6143/EMD | 11/11/2022 | 30 | PADMA ENGINEERING CO. | 12.76 | 11.88 | 93.05 | 0
1250 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah , SM/10298 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KURULIA (Zone-II) Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-I) | 490/BD. | 26/02/2021 | 45 | ORIENT CONSTRUCTION. | 67.42 | 0 | 0 | 1
1251 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah , SM/10298 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Kurulia (Zone-I) water supply scheme (2nd T/W site) under Bongaon Sub-Division P.H.E.Dte. | 3589/BD | 08/12/2022 | 15 | M/S SUKANTA ENTERPRISE. | 15.04 | 14.07 | 100 | 0
1252 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah , SM/10298 | Augmentation | Renovation and repairing of Boundary wall at 2nd T/W site for Augmentation of Kurulia (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 612/Bon | 08/08/2023 | 21 | ROY CHOWDHURY CONSTRUCTION. | 2.76 | 2.72 | 100 | 100
1253 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah , SM/10298 | Augmentation | Supply, delivery and fitting fixing of change over switch, cable etc. at pump house no. I (Z-I), under Kurulia W/S Scheme in connection with FHTC. | 1774/EMSD-I | 10/08/2023 | 10 | SWAPAN ENTERPRISE | 1.23 | 0 | 0 | 100
1254 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah , SM/10298 | Augmentation | Construction of Approach Road Head Work at site for Augmentation of Kurulia (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 620/Bon | 08/08/2023 | 15 | ONKAR ENTERPRISE. | 2.4 | 2.35 | 100 | 100
1255 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah , SM/10298 | Augmentation | Material Requisition To Resource Division | 1366/BD | 13/05/2022 | 0 | Resource Division | 8.83 | 0 | 0 | 0
1256 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah , SM/10298 | Augmentation | Material Requisition To Resource Division | 1671/BD | 13/06/2022 | 0 | Resource Division | 8.71 | 0 | 0 | 0
1257 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah , SM/10298 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system with in command area at Kurulia (Zone-I) Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation). | 1243/BD | 26/04/2022 | 90 | M/S NANDY ENTERPRISE | 470.6 | 317.22 | 100 | 100
1258 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah , SM/10298 | Augmentation | Construction of Latrine at Head Work site and Renovation of PH No - 1 & 2 and allied works for Augmentation of Kurulia (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 662/Bon | 23/05/2025 | 45 | M/S SAYAN ENTERPRISE. | 3.51 | 0 | 0 | 0
1259 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kurulia (Zone-I) to accommodate FHTC, Block - Bagdah , SM/10298 | Augmentation | Acceptance cum work order for Repairing and renovation works for 225 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir for Augmentation of Kurulia (Zone-I) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 3039/BD | 22/10/2024 | 135 | GHOSH CONSTRUCTION. | 13.22 | 13.2 | 100 | 100
1260 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Auldanga Water Supply Scheme at Bagdah Block (Phase-II) , SM/08039 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AULDANGA Water Supply Scheme at BAGDAH Block under North 24 Pgs. Water Supply Division-I, PHE Dte. ( Phase-II). | 385/NWSD-I | 12/05/2021 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 237.57 | 427.71 | 185.63 | 1
1261 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Auldanga Water Supply Scheme at Bagdah Block (Phase-II) , SM/08039 | Retrofitting | Continuation order for the work of Hiring of 1no. Diesel Motor Cab / Maxi Cab with contract carriage permit of R.T.A. in good running condition on daily rental basis for JJM works under Office of the Executive Engineer, North 24 Parganas Water Supply Division-I, P.H.E. Dte. for 184 (One Hundred Eighty Four) w.e.f. 01.07.2024 to 31.12.2024. [Vehicle No.WB 23C 5335] | 963/NWSD-I | 26/06/2024 | 184 | M/S. SHUBHA ENTERPRISE | 0.86 | 2.31 | 267.03 | 100
1262 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC , SM/10310 | Augmentation | Making suitable foundation at the out side of the pump house for installation of 1000Lt PVC tank for feeding chlorine solution by automatic chlorinator & other works at Ph I under Bagdah w/s scheme 24 Pgs(N) | 1035/EMSD I | 04/05/2021 | 17 | TALUKDER & CO. | 0.92 | 0.92 | 100 | 1
1263 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC , SM/10310 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under Bagda W/S Scheme District of 24 Pgs. (N) (Block- Baduria). NIET No. 15 of EE/EMD of 2022-23 (Sl. No.- 02) | 6139/ EMD | 14/08/2022 | 30 | GOENKA ENTERPRISE | 12.87 | 8 | 62.14 | 0
1264 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC , SM/10310 | Augmentation | Construction of Approach Road Head Work at site for Augmentation of Bagdah Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 624/Bon | 08/08/2023 | 15 | TAPAN GHOSH. | 2.39 | 2.38 | 100 | 100
1265 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC , SM/10310 | Augmentation | Material Requisition To Resource Division | 1361/BD | 13/05/2022 | 0 | Resource Division | 23.36 | 0 | 0 | 0
1266 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC , SM/10310 | Augmentation | Material Requisition To Resource Division | 1670/BD | 13/06/2022 | 0 | Resource Division | 21.96 | 0 | 0 | 0
1267 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC , SM/10310 | Augmentation | Construction and Repairing works of damaged part of Boundary wall, Main Gate, Drain, Valve Chamber and allied works due to DI Pipe stacking and shifting at Bagdah High School play ground for Bongaon-Bagdah surface water based PWSS within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1393/Bon | 27/11/2024 | 25 | VAI ENTERPRISE. | 4.73 | 0 | 0 | 0
1268 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC , SM/10310 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Bagdah Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | 2927/BD | 26/09/2023 | 30 | DHELA BABA ENTERPRISE | 16.1 | 12.71 | 100 | 100
1269 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC , SM/10310 | Augmentation | Health assessment of existing OHR of Bagdah PWSS (341 cum) and ancillary structures, Bagdah Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 687/Bon | 07/06/2024 | 15 | SIRCON ENGINEERING SERVICES | 4.74 | 4.74 | 100 | 100
1270 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC , SM/10310 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system with in command area at Bagdah Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation). | 1002/BD | 04/04/2022 | 1440 | MAHAVIR PUMPS MANUFACTURING PVT.LTD. | 450.95 | 309.82 | 68.7 | 80
1271 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC , SM/10310 | Augmentation | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site under Augmentation work at Bagdah W/S Scheme Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1544/BD | 15/05/2025 | 120 | N.H. ENTERPRISE | 40.13 | 0 | 0 | 0
1272 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bagdah to accommodate FHTC , SM/10310 | Augmentation | Acceptance cum work order for Hire and labour charges for staging and scaffolding, bamboo baricading and removal of rubbish for dismantling of existing OHR at Head work Site of Bagdah Water Supply Scheme Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 705/BD | 06/03/2025 | 60 | TAPAN GHOSH. | 11.39 | 0 | 0 | 0
1273 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. , SM/10639 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with Providing functional household tap connection to every Household with in Khamarkalla (Zone-I) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte. | 1188/NWSD-I | 31/12/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.88 | 4.88 | 100 | 1
1274 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. , SM/10639 | Augmentation | Material Requisition To Resource Division | 434/NWSD-I | 24/04/2023 | 0 | Resource Division | 146.23 | 0 | 0 | 0
1275 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. , SM/10639 | Augmentation | Material Requisition To Resource Division | 1838/NWSD-I | 10/11/2023 | 0 | Resource Division | 3.08 | 0 | 0 | 0
1276 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. , SM/10639 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) (Rep) under Khamarkalla W/S Scheme District of 24 Pgs. (N) | 4745/EMD | 07/08/2023 | 30 | ALAK KUMAR CHAKRABORTY | 26.5 | 15.53 | 58.58 | 65
1277 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. , SM/10639 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.III and IV (Zone-I) (Rep) under Khamarkalla W/S Scheme District of 24 Pgs. (N) NIET No. 27 of EE/EMD of 2022-2023 (Sl. No. 25) | 6772/EMD | 29/11/2023 | 30 | BOSE & CHATTERJEE INDUSTRIES | 26.47 | 0 | 0 | 0
1278 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. , SM/10639 | Augmentation | Repair and renovation works for 1000 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir , Boundary wall, Pump House at H/W site and PH-II , III & IV with other allied works at Khamarkhalla (Z-I) W/S Scheme under North 24 Pgs Water Supply Division- I, P.H.E. Dte. | 1263/NWSD-I | 21/08/2023 | 60 | M/S. TARAK CHANDRA PAUL | 66.2 | 65.42 | 100 | 100
1279 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. , SM/10639 | Augmentation | Laying of Distribution pipe line and Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe including all necessary works at distribution system within command area of Khamarkalla Zone-I Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE. Dte. | 1289/NWSD-I | 07/11/2022 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 527.02 | 523.24 | 100 | 100
1280 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. , SM/10639 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1430/NWSD-I | 18/09/2024 | 7 | BIBHAS PAL | 5.27 | 0.35 | 50 | 100
1281 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. , SM/10639 | Augmentation | Material Requisition To Resource Division | 1305/NWSD-I | 30/08/2024 | 0 | Resource Division | 3.08 | 0 | 0 | 0
1282 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. , SM/10639 | Augmentation | Laying of pipe line & special measure for protection of road and other allied works at different location under Augmentation work at Khamarkalla W/S. Scheme (Zone-I) in Bongaon Block under North 24 Pgs. W/S. Division-I, PHE. Dte. | 47/NWSD-I | 09/01/2025 | 15 | AMBALIKA ENTERPRISE | 4.84 | 0 | 0 | 100
1283 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas , SM/10102 | Augmentation | Survey, Design and preparation of Retrofitting DPR in connection with " Providing functional household tap connection to every Household under Bagangram Zone-II W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte. | 236/NWSD - I | 24/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.52 | 4.52 | 100 | 1
1284 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas , SM/10102 | Augmentation | Special Repair and renovation of Pump House & Allied Works for Head Works site & 2nd Tube Well site at Bagangram Zone-II Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 379/NWSD-I. | 05/04/2023 | 45 | GHOSH CONSTRUCTION | 5.25 | 0 | 0 | 28
1285 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas , SM/10102 | Augmentation | Special Repair and Renovation of Pump House & Allied Works for Head Works site & 2nd Tube Well Site at BAGANGRAM ZONE-II Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 379/NWSD-I | 05/04/2023 | 45 | GHOSH CONSTRUCTION | 5.25 | 4.01 | 76.48 | 28
1286 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas , SM/10102 | Augmentation | Material Requisition To Resource Division | 612/NWSD-I | 17/05/2022 | 0 | Resource Division | 14.93 | 0 | 0 | 0
1287 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas , SM/10102 | Augmentation | Material Requisition To Resource Division | 649/NWSD-I | 23/05/2022 | 0 | Resource Division | 16.66 | 0 | 0 | 0
1288 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas , SM/10102 | Augmentation | Repair and renovation works for 350 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir , Boundary wall at H/W site and PH-II with other allied works at Bagangram (Z-II) W/S Scheme under North 24 Pgs Water Supply Division- I, P.H.E. Dte. | 1262/NWSD-I | 21/08/2023 | 60 | GHOSH CONSTRUCTION | 32.24 | 31.81 | 100 | 100
1289 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bagangram Zone-II Block : Bongaon, District: North 24 Parganas , SM/10102 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1430/NWSD-I | 18/09/2024 | 7 | BIBHAS PAL | 5.27 | 0.18 | 50 | 100
1290 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/10583 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Barakpur (Zone-I) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | 1181/NWSD-I | 31/12/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.59 | 4.59 | 100 | 1
1291 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/10583 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) (Rep) under Barakpur W/S Scheme District of 24 Pgs. (N) | 4756/EMD | 07/08/2023 | 30 | SWAPAN KUMAR BHANJA | 26.67 | 15.8 | 59.26 | 80
1292 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/10583 | Augmentation | Laying of Distribution pipe line and Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system at distribution system within command area of Barakpur Zone-I Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE. Dte. | 1354/NWSD-I | 28/11/2022 | 90 | JOY HIND TUBEWELLS | 394.47 | 397.89 | 100 | 25
1293 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/10583 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 50 m Length & Service Road (25 Mtr. Length X 2 Mtr. Width) at 2nd pump house site at BARAKPUR ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 446/NWSD-I | 25/04/2023 | 45 | MONDAL ENTERPRISE | 7.28 | 5.9 | 100 | 100
1294 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/10583 | Augmentation | Material Requisition To Resource Division | 469/NWSD-I | 26/04/2023 | 0 | Resource Division | 54.61 | 0 | 0 | 0
1295 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/10583 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-III & IV Zone-I under Barrakpur ground water based water supply scheme under Block_ Bongaon Dist. - North 24PGS under EMD, PHE Dte. | 1309/EMD | 09/05/2024 | 30 | A.S. ENTERPRISE | 26.08 | 0 | 0 | 0
1296 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/10583 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir of 900 Cum capacity at Head work site & other allied works of Barakpur (Zone-I) water supply scheme and other ancillary works under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | 1393/NWSD-I | 05/09/2023 | 60 | A.K.C. SUPPLY & CONSTRUCTION | 30.29 | 27.07 | 100 | 100
1297 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/10583 | Augmentation | Special Repair and renovation works of Pump House, Boundary Wall & other allied works of Barakpur ( Zone-I) water supply scheme and other ancillary works under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | 1392/NWSD-I | 05/09/2023 | 60 | OM CONSTRUCTION | 20.63 | 17.14 | 100 | 100
1298 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/10583 | Augmentation | Repairing of GI Roofing, Structural works including finishing and other allied works at Sripally Barrackpore Store under North 24Pgs. W/S Division-I, P.H.E. Dte. | 462/NWSD-I | 13/03/2024 | 14 | OM CONSTRUCTION | 5.19 | 5.13 | 100 | 100
1299 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/10583 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1430/NWSD-I | 18/09/2024 | 7 | BIBHAS PAL | 5.27 | 0.35 | 50 | 100
1300 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/10583 | Augmentation | Material Requisition To Resource Division | 1306/NWSD-I | 30/08/2024 | 0 | Resource Division | 6.16 | 0 | 0 | 0
1301 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/10583 | Augmentation | Construction of Arsenic cum Iron removal Plants (AIRP) of capacity 168 cum/hr at Head work site of Barakpur (Zone-1) Water Supply Scheme within the Bongaon Block and other ancillary work under North 24 Pgs. w/s Division-l, P.H.E. Dte. | 489/NWSD-I | 15/03/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS(P) LTD. | 371.87 | 0 | 0 | 25
1302 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) augmentation for Barakpur Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/10583 | Augmentation | Laying of UPVC pipes at demage portion due to drain construction & protection work by Bullah pilling N/H of Jayanta Sandhu to Ranjit Chakraborty under Augmentation work of Barrakpur (Zone - I) W/S Scheme, Bongaon Block of North 24 Parganas District within the jurisdiction of N24Pgs. W/S Division-I, P.H.E. Dte. | 775/NWSD-I | 23/05/2025 | 45 | OM CONSTRUCTION | 22.32 | 0 | 0 | 0
1303 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC , SM/12568 | Augmentation | Additional Survey work for DPR Preparation for DAKSHIN CHATRA ZONE -1 Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 352/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.38 | 1.36 | 100 | 1
1304 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC , SM/12568 | Augmentation | Route Survey, Design Drawing & DPR Preparation for DAKSHIN CHATRA ZONE -1 Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 351/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 4.95 | 100 | 1
1305 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC , SM/12568 | Augmentation | Hiring Diesel Luxury Car on daily basis (for 06 months from 01.01.2023 to 30.06.2023) for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. | 1420 /BHTSD | 30/12/2022 | 181 | OM ENTERPRISE | 0.86 | 2.33 | 100 | 100
1306 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC , SM/12568 | Augmentation | Material Requisition To Resource Division | 1254/BD | 25/04/2023 | 0 | Resource Division | 260.28 | 0 | 0 | 0
1307 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC , SM/12568 | Augmentation | Material Requisition To Resource Division | 1632/BD | 01/06/2023 | 0 | Resource Division | 48.44 | 0 | 0 | 0
1308 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC , SM/12568 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No II (Rep.) (Zone-I and II) under Dakshin Chatra W/S Scheme District of 24 Pgs. (N) | 6734/EMD | 29/11/2023 | 30 | CONCORD ENGINEERING | 26.08 | 0 | 0 | 0
1309 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC , SM/12568 | Augmentation | Continuation Work for Hiring Diesel Luxury Car on daily basis for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. (Period: 01.01.2024 to 30.06.2024 for Six Month) | 1290/BHTSD | 29/12/2023 | 182 | DEB KUMAR DAS. | 0.86 | 1.51 | 174.74 | 100
1310 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC , SM/12568 | Augmentation | Laying of HDPE pipe line and Repairing of DI pipelines including supply of Sluice valve (200 mm) for interconnection of AIRP under Augmentation work of Dakshin Chatra Zone-I Water Supply Scheme under Basirhat Sub Division , P.H.E. Dte. under Barasat Division, P.H.E. Dte. | 929/BHTSD | 24/05/2024 | 7 | S.R.M. ENTERPRISE. | 1 | 1 | 100 | 100
1311 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC , SM/12568 | Augmentation | Supply of Sluice valve (200 mm) including construction of Sluice valve chamber for Augmentation of Dakshin Chatra Zone-I Water Supply Scheme under Basirhat Sub Division , P.H.E. Dte. under Barasat Division, P.H.E. Dte. | 928/BHTSD | 24/05/2024 | 7 | ROHAN MONDAL. | 0.97 | 0.97 | 100 | 100
1312 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC , SM/12568 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Dakshin Chatra Zone-I water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | 1210/BD | 20/04/2023 | 1041 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 971.71 | 571.4 | 58.8 | 38
1313 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC , SM/12377 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Nalabara Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 454/ BHTSD | 23/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.97 | 4.97 | 50 | 1
1314 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC , SM/12377 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Nalabara Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 455/ BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.61 | 3.61 | 50 | 1
1315 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC , SM/12377 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. big dia. 300 mtr deep tubewell by D.R. Rig method using PVC pipe & strainer having 300 mm dia. 36 mtr. long filter for Augmentation of Nalabara Zone-II water supply scheme in Swarupnagar Block of Basirhat Sub-Division, under Barasat Division, P.H.E. Dte. | 2800/BD | 12/09/2023 | 30 | DHELA BABA ENTERPRISE | 21.53 | 0 | 0 | 0
1316 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC , SM/12377 | Augmentation | Material Requisition To Resource Division | 1260/BD | 25/04/2023 | 0 | Resource Division | 381.58 | 0 | 0 | 0
1317 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC , SM/12377 | Augmentation | Material Requisition To Resource Division | 1629/BD | 01/06/2023 | 0 | Resource Division | 71.08 | 0 | 0 | 0
1318 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC , SM/12377 | Augmentation | Formal work order for Laying of DI / UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection) by Augmentation of Nalabara (Zone-I) Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E. Dte. | 2713/BD | 05/09/2023 | 546 | GARGO TRADERS | 559.43 | 403.19 | 72.07 | 72
1319 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC , SM/12377 | Augmentation | Regarding Restoration charges for road damages. | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 49.56 | 0 | 0 | 0
1320 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC , SM/12377 | Augmentation | Regarding Restoration charges for road damages. | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 32.73 | 0 | 0 | 0
1321 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC , SM/12377 | Augmentation | New service connection at P.H.No- II of Nalabora water supply scheme under EMSD-I ,PHE Dte .im24Pgs(N). | BP-322-23-24 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 16.96 | 0 | 0 | 0
1322 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC , SM/12377 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II, III and IV (Rep.) under Nalabara W/S Scheme and Pump House No-I and II under Barabankra W/S Scheme District of 24 Pgs. (N) | 4811/EMD | 09/08/2023 | 662 | M/S. SAJAHAN CHOWDHURY | 78.21 | 14.77 | 28.32 | 46
1323 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC , SM/12377 | Augmentation | Acceptance cum work order for Balance Work of Laying of UPVC Distribution pipe line and providing FHTC for augmentation of Nalabara Z-II water Supply Scheme within Swarupnagar Block under Basirhat Sub Division PHE Dte. | 399/BD | 05/02/2025 | 360 | H.I.ENTERPRISE. | 75.98 | 0 | 0 | 65
1324 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC , SM/12377 | Augmentation | Formal work order for Laying of UPVC distribution pipeline and Providing FHTC (Functional Household Tap Connection) for Augmentation of Nalabara Zone-II Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, PHE Dte. | 1125/BD | 11/04/2023 | 811 | H.I.ENTERPRISE. | 634.74 | 613.98 | 97.2 | 60
1325 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalabara to accommodate FHTC , SM/12377 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Swarupnagar Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - B) | 153/BHTSD | 29/01/2025 | 20 | S.M.TRADERS. | 0.87 | 0 | 0 | 100
1326 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC , SM/12273 | Augmentation | Route Survey, Design Drawing & DPR Preparation for PAIKARDANGA Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | 194/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 100 | 1
1327 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC , SM/12273 | Augmentation | Material Requisition To Resource Division | 854/BD | 20/03/2023 | 0 | Resource Division | 377.63 | 0 | 0 | 0
1328 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC , SM/12273 | Augmentation | Material Requisition To Resource Division | 602/BD | 23/02/2023 | 0 | Resource Division | 31.31 | 0 | 0 | 0
1329 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC , SM/12273 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II and III (Rep.) under Paikardanga W/S Scheme District of 24 Pgs. (N) | 4720/EMD | 04/08/2023 | 30 | ASHUTOSH DAS & CO. | 26.49 | 0 | 0 | 0
1330 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC , SM/12273 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Paikardanga water supply scheme in Basirhat-I Block under Barasat Division, P.H.E Dte. | 173/BD | 19/01/2023 | 1074 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 707.21 | 262.57 | 37.13 | 38
1331 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC , SM/12273 | Augmentation | Acceptance cum work order for Restoration of roads under different water supply schemes of Basirhat I Block under Barasat Division P.H.E.Dte. | 3626/BD | 20/12/2024 | 180 | NISHITH BANERJEE | 45.36 | 0 | 0 | 100
1332 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Paikardanga to accommodate FHTC , SM/12273 | Augmentation | Acceptance cum work order for Special repair and renovation of existing structures like Pump House, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Itinda Panitor, Joypur Gopmahal, Kachua Swarupnagar, Mathurapur, Mirzanagar, Nalkora, Paikardanga, Pifa and Gobindapur Water Supply Scheme of different block under Basirhat Sub-Division within Barasat Division, P.H.E Dte. | 2474/BD | 17/07/2025 | 150 | SAHA CONSTRUCTION & CO | 91.3 | 0 | 0 | 0
1333 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC , SM/12275 | Augmentation | Material Requisition To Resource Division | 933/BD | 22/03/2023 | 0 | Resource Division | 120.6 | 0 | 0 | 0
1334 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC , SM/12275 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line and Providing Functional Household Tap Connection for the leftout portion with protection work in connection with Augmentation of Durgapur Baylani water supply scheme (Z-I & II), Hingalganj Block of Hasnabad Sub-Division under Barasat Division, PHE Dte. | 2401/BD | 22/08/2024 | 360 | M/S S.C. CIVIL ENTERPRISES | 116 | 0 | 0 | 0
1335 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC , SM/12275 | Augmentation | Acceptance cum work order for Land development at OHR site in connection with augmentation of Durgapur Baylani w/s scheme (Z-I), Hingalganj under Hasnabad Sub-Division P.H.E. Dte. | 2334/BD | 07/07/2025 | 60 | BABUSONA CONSTRUCTION. | 7.13 | 0 | 0 | 0
1336 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC , SM/12275 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Durgapur Baylani Z-I w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte.Part-C | 342/HSD | 06/02/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.85 | 0 | 0 | 100
1337 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC , SM/12275 | Augmentation | Acceptance cum work order for Laying of 140 mm(Near Asharia Paschim) ,180 mm(Near OHR) dia UPVC distribution pipe line in connection with Augmentation of Durgapur Baylani water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 389/HSD | 10/02/2025 | 10 | M/S K.B.ENTERPRISE. | 0.86 | 0 | 0 | 100
1338 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC , SM/12275 | Augmentation | Acceptance cum work order for Protection of Different dia UPVC pipe line by bamboo pilling at different places of in connection with augmentation of Durgapur Baylani w/s scheme(Z-I), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 321/HSD | 04/02/2025 | 10 | M/S K.B.ENTERPRISE. | 0.94 | 0 | 0 | 100
1339 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC , SM/12275 | Augmentation | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places in connection with augmentation of Durgapur Baylani W/S Scheme(Z-I), Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Phase-III) | 1004/HSD | 04/06/2025 | 10 | M/S K.B.ENTERPRISE. | 0.94 | 0 | 0 | 100
1340 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC , SM/12275 | Augmentation | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places in connection with augmentation of Durgapur Baylani W/S Scheme(Z-I), Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Phase-I) | 470/HSD | 28/02/2025 | 10 | M/S K.B.ENTERPRISE. | 0.93 | 0 | 0 | 100
1341 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC , SM/12275 | Augmentation | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places in connection with augmentation of Durgapur Baylani W/S Scheme(Z-I), Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Phase-II) | 531/HSD | 10/03/2025 | 10 | M/S K.B.ENTERPRISE. | 0.95 | 0 | 0 | 100
1342 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC , SM/12275 | Augmentation | Acceptance cum work order for Special repair & maintenance of different dia UPVC pipe line at different places in connection with augmentation of Durgapur Baylani w/s Scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 893/BD | 20/03/2025 | 10 | ABDUL ALIM MONDAL. | 6.06 | 0 | 0 | 100
1343 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC , SM/12275 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Durgapur Baylani water supply scheme (Z-I) , Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 149/HSD | 27/01/2025 | 10 | ABDUL ALIM MONDAL. | 0.84 | 0 | 0 | 100
1344 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda ZOne-II Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10153 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Bilkanda (Zone-II) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | 1184/NWSD-I | 31/12/2021 | 15 | UMWELT ENGINEER PRIVATE LIMITED | 4.68 | 4.68 | 100 | 1
1345 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda ZOne-II Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10153 | Augmentation | Material Requisition To Resource Division | 749/NWSD-I | 14/06/2022 | 0 | Resource Division | 54.66 | 0 | 0 | 0
1346 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda ZOne-II Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10153 | Augmentation | Material Requisition To Resource Division | 738/NWSD-I | 13/06/2022 | 0 | Resource Division | 39.84 | 0 | 0 | 0
1347 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda ZOne-II Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10153 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House Hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC , Schedule 80/20 mm OD HDPE (PE 100, PN16) pipe with all necessary works within command area of Bilkanda Zone-II Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE Dte. | 705/ NWSD-I | 07/06/2022 | 90 | ALOK ENTERPRISE, A UNIT OF SAKET TREXIM PVT. LTD. | 726.86 | 459.6 | 63.23 | 54
1348 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda ZOne-II Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10153 | Augmentation | Repair and renovation works for 1250 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir , Boundary wall, Pump House at H/W site and PH-II with other allied works at Bilkanda (Z-II) W/S Scheme under North 24 Pgs Water Supply Division- I, P.H.E. Dte. | 1399/NWSD-I | 05/09/2023 | 60 | H. I. ENTERPRISE | 52.34 | 51.36 | 100 | 100
1349 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda ZOne-II Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10153 | Augmentation | Sinking of 1 no. 300 mm. x 200 mm. dia. 250 mtr deep tube well by D.R. Rig method at Head Work Site at Bilkanda-II Water Supply Scheme under Barrackpore-II Block within the jurisdiction of North 24 Pgs Water Supply Division- I, P.H.E. Dte. | 2027/NWSD-I | 13/12/2023 | 30 | ACME CONSTRUCTION | 19.35 | 16.62 | 100 | 100
1350 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda ZOne-II Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10153 | Augmentation | Supply and installation of Display Board to be placeed at BILKANDA ZONE-I, BANDIPUR, BILKANDA ZONE-II, PATULIA and MOHANPUR, Zone-I-B (Telinipara), Zone-IA-II (Chak Kanthalia) pipe water supply scheme for Barrackpore-II Block under North 24 Pgs. Water Supply Division-I, PHE. Dte. | 70/NWSD-I | 10/01/2024 | 30 | BIBHAS PAL | 4.94 | 0.88 | 100 | 100
1351 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda ZOne-II Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10153 | Augmentation | Shinking of 1 no. Tube well 300mm X 200mm Big Dia.Tube well 300 Mtr. Deep by Direct Rotary Rig method using PVC pipe & UPVC deep well screen pipes with ribs etc. Including cost of Materials at Talbanda Mouza under command area of Bilkanda (Zone-I & II) Water Supply Scheme at Barrackpore-II Block under North 24 Parganas wate supply Division-I, P.H.E. Dte. | 434/NWSD-I | 19/03/2025 | 30 | AUXILIARY TUBEWELL DRILLER | 22.7 | 0 | 0 | 0
1352 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda ZOne-II Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10153 | Augmentation | Inter connection with new Tube well at H/W site under Augmentation Scheme of Bilkanda-II W/S Scheme within the jurisdiction of N 24 Pgs. W/S Division-I, P.H.E. Dte. | 1633/NWSD-I | 12/11/2024 | 7 | ARUP CONSTRUCTION | 1.56 | 0 | 0 | 100
1353 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation under Jal Swapna for Bilkanda ZOne-II Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District. , SM/10153 | Augmentation | Road restoration due to laying of pipeline of Augmention work at Bilkanda-II W/S Scheme in Barrackpore-II Block under Northn24 Pgs W/S Div-I, P.H.E, Dte. | 773/NWSD-I | 23/05/2025 | 30 | JOY ENTERPRISE | 8.54 | 0 | 0 | 100
1354 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Joy Gaopalpur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10501 | Retrofitting | Formal work order for Protection work for newly laid UPVC pipe line at different places of Dhuchnikhali Mouza, Korakati Mouza, & Monipur Mouza in connection with retrofitting of Joygopalpur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1360/BD | 04/05/2023 | 30 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 117.2 | 0 | 0 | 0
1355 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Joy Gaopalpur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10501 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Joygopalpur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 1746/BD | 20/06/2022 | 90 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 278.19 | 213.07 | 100 | 1
1356 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Joy Gaopalpur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10501 | Retrofitting | Acceptance cum work order for Sinking of Additional 1 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Joygopalpur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 3579/BD | 18/12/2024 | 30 | M/S RAJPATH CONSTRUCTION. | 31.66 | 7.22 | 20.94 | 100
1357 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Sukhdoani W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10502 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Sukhdaoni w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 1660/BD | 10/06/2022 | 90 | SUPRITI ENTERPRISE. | 113.4 | 102.01 | 89.96 | 1
1358 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Sukhdoani W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10502 | Retrofitting | Acceptance cum work order for Hiring Diesel Luxury Car on Daily basis (for 6 months from 01.10.2022 to 31.03.2023) for the office use of the Executive Engineer, Barasat Division, PHE Dte. | 2826/BD | 29/09/2022 | 181 | MADHAB CHANDRA DAS | 0.89 | 1.56 | 100 | 0
1359 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Sukhdoani W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10502 | Retrofitting | Formal work order for Protection work for newly laid UPVC pipe line at different places of Sukhdoani Mouza in connection with retrofitting of Sukhdoani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1165/BD | 13/04/2023 | 30 | SUPRITI ENTERPRISE. | 68.84 | 68.78 | 99.91 | 0
1360 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Sukhdoani W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10502 | Retrofitting | Acceptance cum work order for Providing Functional tap connection at Sukhdoani (SPL) FP School, Dk. Sukhdoani FP School & Sukhdoani Dwarikanath FP School within the command area of Sukhdoani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1056/HSD | 31/08/2023 | 7 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 0.6 | 0.6 | 100 | 100
1361 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Sukhdoani W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10502 | Retrofitting | Acceptance cum work order for Construction of boundary wall with RCC column structure at Head Work site (Ph No-1) within Sukhdoani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 4381/BD | 10/11/2023 | 90 | ABDUL ALIM MONDAL. | 24.32 | 24.25 | 100 | 100
1362 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Sukhdoani W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10502 | Retrofitting | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Sukhdoani Mouza within Sukhdoani w/s scheme , Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 885/HSD | 07/08/2024 | 10 | NEW LIFE CONSTRUCTION. | 0.96 | 0.96 | 100 | 100
1363 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Sukhdoani W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10502 | Retrofitting | Acceptance cum work order for Restoration of UPVC pipeline, repairing of FHTC within Sukhdoani w/s scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | 448/BD | 10/02/2025 | 60 | NEW LIFE CONSTRUCTION. | 10.96 | 0 | 0 | 100
1364 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC , SM/11538 | Augmentation | Repairing & Renovation 2(Two) nos of Pump House and allied works of Kola water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 527/Bon | 01/11/2021 | 21 | ACHINTA KUMAR HALDER. | 2.52 | 2.47 | 98.19 | 1
1365 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC , SM/11538 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Kola Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 136/BON | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.64 | 3.62 | 50 | 1
1366 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC , SM/11538 | Augmentation | Material Requisition To Resource Division | 3694/BD | 14/12/2022 | 0 | Resource Division | 26.68 | 0 | 0 | 0
1367 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC , SM/11538 | Augmentation | Material Requisition To Resource Division | 3713/BD | 15/12/2022 | 0 | Resource Division | 11.89 | 0 | 0 | 0
1368 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC , SM/11538 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (New) under Kola W/S Scheme, Block-Barasat-II, District of 24 Pgs. (N). | 4933/EMD | 18/08/2023 | 30 | BARISAL TRADING CO. | 22.15 | 0 | 0 | 0
1369 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC , SM/11538 | Augmentation | Emergency laying of wash out pipe line and others allied works from Kola Pump House No-I to nearest Baor at Adibasi Para at Kola water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 383/Bon | 05/08/2022 | 12 | ACHINTA KUMAR HALDER. | 1.1 | 1.08 | 100 | 1
1370 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC , SM/11538 | Augmentation | Supply fitting fixing of change over switch at P.H.No-I & II ,Zone-I of Ghatpatila and P.H.No- I & II of Kola W/S Scheme under EMSD-I, P.H.E. Dte. Dist.-24Pgs(N). | 1814/EMSD-I | 18/08/2023 | 15 | SUNRISE ENGINEERING CORPORATION | 0.86 | 0 | 0 | 100
1371 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC , SM/11538 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Head Work site for Augmentation of Kola Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 524/BD | 20/02/2024 | 30 | DEL DELTA CONSTRUCTION | 13.55 | 10.71 | 79.09 | 85
1372 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC , SM/11538 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Kola Water Supply Scheme, under Bongaon Sub-Division, PHE Dte. | 264/BD | 01/02/2023 | 90 | MONDAL PRECISION PVT.LTD | 330.92 | 326.52 | 100 | 100
1373 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC , SM/11538 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tube well by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kola Water Supply Scheme (H/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E.Dte. | 2938/BD | 27/09/2023 | 30 | JOY GURU ENTERPRISE | 16.12 | 15.11 | 100 | 100
1374 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC , SM/11538 | Augmentation | Acceptance cum work order for Renovation of 34 Cum/hr of capacity AIRP and allied works at Head work site for Augmentation of Kola water Supply Scheme under Bongaon Sub-Division, Barasat Division P.H.E. Dte. | 12/BD | 02/01/2024 | 60 | PUSPA ENTERPRISE. | 38.78 | 31.28 | 100 | 100
1375 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC , SM/11538 | Augmentation | Acceptance cum work order for Repairing and renovation of Compressor Room for AIRP, Construction of Boundary wall at 2nd T/W site and Construction of Approach Road at Head work site and 2nd T/W site under Augmentation of Kola Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 624/BD | 28/02/2024 | 360 | ONKAR ENTERPRISE. | 11.17 | 0 | 0 | 100
1376 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC , SM/11594 | Augmentation | Repairing & Renovation 2(Two) nos of Pump House and allied works of Chhaygharia (Zone-III) water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 535/Bon | 03/11/2021 | 21 | VAI ENTERPIRSE. | 2.52 | 2.47 | 98.09 | 1
1377 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC , SM/11594 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Chhaygharia (Zone-III) Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 125/BON | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.42 | 3.4 | 50 | 1
1378 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC , SM/11594 | Augmentation | Material Requisition To Resource Division | 3653/BD | 13/12/2022 | 0 | Resource Division | 15.03 | 0 | 0 | 0
1379 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC , SM/11594 | Augmentation | Material Requisition To Resource Division | 3695/BD | 14/12/2022 | 0 | Resource Division | 110.28 | 0 | 0 | 0
1380 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC , SM/11594 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Chhayagharia (Zone-III) Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 3491/BD | 02/12/2022 | 90 | M/S PROGATI ENTERPRISE. | 296.33 | 296.19 | 100 | 100
1381 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC , SM/11594 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer at Chhaighoria (Zone-III) water supply scheme (2nd T/W Site) under Bongaon Sub-Division P.H.E.Dte. | 1546/BD | 22/05/2023 | 30 | NEW MA TARA ENTERPRISE. | 15.81 | 10.08 | 100 | 100
1382 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC , SM/11594 | Augmentation | Acceptance cum work order for Construction of Boundary wall, Approach Road, Earth Filling and Construction of 3.60 mtr. X 3.00 mtr. size Guard Room with sanitary and water supply arrangement incl. plinth protection at OHR site of Chhaygharia (Zone-III) Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 2419/BD | 23/08/2024 | 60 | ONKAR ENTERPRISE. | 42.48 | 0 | 0 | 0
1383 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC , SM/11594 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at 1st Tube Well & 2nd Tube Well site and Construction of Approach Road at 1st Tube Well & 2nd Tube Well site under Augmentation of Chhaygharia (Zone-III) Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 561/BD | 22/02/2024 | 45 | ROY ENGINEERS. | 10.23 | 9.86 | 100 | 100
1384 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC , SM/11594 | Augmentation | Installation of CCTV Camera Connection at Pump house no 1 & 2 for Chhaygharia (Zone-III) w/s scheme, Bongaon Block under Bongaon Sub-Division, PHE Dte. | 539/Bon | 23/04/2025 | 7 | ELDORADO | 0.55 | 0 | 0 | 0
1385 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC , SM/11594 | Augmentation | Acceptance cum work order for Restoration of damaged pipe line due to Construction of Pucca Drain by laying of UPVC pipe at different places under Chhaigharia Gram Panchayet, Bongaon Block of Chhaigharia (Zone - III) W/S Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 2053/BD | 20/06/2025 | 90 | VAI ENTERPRISE. | 23.12 | 0 | 0 | 0
1386 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC , SM/11594 | Augmentation | Acceptance cum work order Providing Functional Household Tap Connection (FHTC) to the uncovered household at Jayantipur mouza including laying of UPVC pipe and allied works under Augmentation work at Chhaigharia (Zone-III) W/S Scheme under Chhaigharia G.P., Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1649/BD | 21/05/2025 | 90 | SUJAN KUMAR MISTRY | 25.23 | 0 | 0 | 0
1387 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC , SM/11594 | Augmentation | Laying of UPVC pipe line at different damaged portions under Augmentation work at Chhaygharia (Zone-III) W/S Scheme Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1384/Bon | 26/11/2024 | 86 | JOY GURU ENTERPRISE | 4.96 | 1.31 | 20.94 | 100
1388 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC , SM/11594 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I , II Zone-III under Chhaygharia ground water based water supply scheme under Block_ Bongaon Dist. - North 24PGS under EMD, PHE Dte. | 806/EMD | 11/03/2024 | 355 | INDIA ENTERPRISE | 25.79 | 14.56 | 55.56 | 100
1389 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC , SM/11594 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe under Augmentation work at Chhaygharia (Zone-III) W/S Scheme Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (Part-A). | 3385/BD | 03/12/2024 | 150 | VAI ENTERPRISE. | 12.02 | 0 | 0 | 100
1390 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 790/BD | 13/03/2023 | 30 | ABDUL ALIM MONDAL. | 21.44 | 17.49 | 100 | 100
1391 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Malancha water supply scheme (Zone-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1189/BD | 19/04/2023 | 90 | S.S.ENTERPRISE. (BAMANGACHI) | 417.27 | 415.63 | 100 | 88
1392 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Material Requisition To Resource Division | 922/BD | 22/03/2023 | 0 | Resource Division | 22.12 | 0 | 0 | 0
1393 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Acceptance cum work order for Emergent resting of 100 mm dia DI pipeline by concrete block at different places in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 32-HSD.. | 09/01/2024 | 10 | NEW MANGES INDUSTRIAL CORPORATION | 0.91 | 0 | 0 | 0
1394 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Acceptance cum work order for Protection works for newly laid different dia. UPVC/DI pipe line at Joygram Molla para N/H/O Emdadul Haque in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 3461/BD | 09/12/2024 | 30 | M/S ANUBHAB CONSTRUCTION. | 8.77 | 0 | 0 | 0
1395 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 2493/BD | 18/08/2023 | 30 | M/S RAJPATH CONSTRUCTION. | 43.9 | 34.01 | 100 | 80
1396 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Formal work order for Construction of 350 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Malancha water supply scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | 2886/BD | 20/09/2023 | 365 | S.S.ENTERPRISE. (BAMANGACHI) | 152.49 | 141.63 | 100 | 100
1397 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Acceptance cum work order for Emergent resting of 200 mm dia DI pipeline by concrete block at different places in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 30/HSD | 09/01/2024 | 10 | NEW MANGES INDUSTRIAL CORPORATION | 0.94 | 0.95 | 100 | 80
1398 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Acceptance cum work order for Emergent resting of 150 mm dia DI pipeline by concrete block at different places in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 31/HSD | 09/01/2024 | 10 | NEW MANGES INDUSTRIAL CORPORATION | 0.94 | 0.95 | 100 | 82
1399 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Ph No- 2 within Malancha W/S scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 993/HSD | 29/08/2024 | 10 | M/S RAJPATH CONSTRUCTION. | 0.87 | 0 | 0 | 100
1400 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Acceptance cum work order for Emergent resting of 100 mm dia DI pipeline by concrete block at different places in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 32/HSD | 09/01/2024 | 10 | NEW MANGES INDUSTRIAL CORPORATION | 0.91 | 0.92 | 100 | 62
1401 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II(Rep.) and III(New) (Zone-I) and Pump House No-I and II (Zone-II)(Rep.) under Malancha W/S Scheme District of 24 Pgs. (N) NIET NO. 32 OF EE/EMD OF 2022-23 (SL. NO. -15) | 1013/EMD | 09/03/2023 | 816 | MAHADEV ENTERPRISE | 66.24 | 34.24 | 86.14 | 40
1402 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) for Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 1606/BD | 19/05/2025 | 30 | M/S RAJPATH CONSTRUCTION. | 5.91 | 0 | 0 | 0
1403 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Acceptance cum work order for Protection works for newly laid different dia. UPVC/DI pipe line at Joygram Molla para N/H/O Salauddin Molla in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1528/BD | 14/05/2025 | 21 | MD.SALIM GAZI. | 10.2 | 0 | 0 | 0
1404 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 2865/BD | 30/09/2024 | 90 | S.S.ENTERPRISE. (BAMANGACHI) | 151.25 | 71.11 | 47.03 | 100
1405 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Acceptance cum work order for Protection works for newly laid different dia. UPVC/DI pipe line at Joygram Molla para N/H/O Ajibar Molla in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 3460/BD | 09/12/2024 | 150 | BARNALI DUTTA | 9.41 | 0 | 0 | 100
1406 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 2 in connection with augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 472/HSD | 28/02/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.75 | 0 | 0 | 100
1407 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line and other allied works in connection with retrofitting work at different places in connection with augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | 1632/BD | 20/05/2025 | 15 | NEW MANGES INDUSTRIAL CORPORATION | 11.78 | 0 | 0 | 100
1408 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. , SM/11596 | Augmentation | Acceptance cum work order for Laying of UPVC distribution pipe line for damaged portion due to construction of SRDA road from shop of Saidul Molla to N/H/O Monirul Molla and other allied works in connection with Augmentation of Malancha water supply scheme (Zone-I), Minakhan Block under Hasnabad Sub-Division P.H.E.Dte. | 407/BD | 06/02/2025 | 30 | S.S.ENTERPRISE. (BAMANGACHI) | 14.19 | 3.76 | 20.94 | 100
1409 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte , SM/11661 | Augmentation | Preparation of Augmentation DPR for Konanagar Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | 1837/B.Ar.D | 19/09/2022 | 20 | SIRCON ENGINEERING SERVICES | 0.99 | 0.98 | 100 | 1
1410 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte , SM/11661 | Augmentation | Material Requisition To Resource Division | 2210/B.Ar.D. | 22/11/2022 | 0 | Resource Division | 6.92 | 0 | 0 | 0
1411 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte , SM/11661 | Augmentation | Material Requisition To Resource Division | 2296/B.Ar.D | 02/12/2022 | 0 | Resource Division | 10.09 | 0 | 0 | 0
1412 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte , SM/11661 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep) under Hasnabad W/S Scheme District of 24 Pgs. (N) | 4724/EMD | 04/08/2023 | 30 | P.K. ENGINEERING | 26.5 | 0 | 0 | 0
1413 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte , SM/11661 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir of Capacity 250 Cu.m. at Konanagar W/S Scheme of Hasnababad Block under Barasat Arsenic Division, PHE Dte. | 375/B.Ar.D. | 17/02/2023 | 60 | NIKHIL SAMADDAR | 13.23 | 12.98 | 100 | 0
1414 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte , SM/11661 | Augmentation | Laying of distribution System Including specials all Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Konanagar at Hasnabad Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | 1571/B.Ar.D. | 25/08/2022 | 810 | M/S R. K. ENTERPRISE | 190.29 | 157.32 | 89.66 | 70
1415 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte , SM/11661 | Augmentation | Hiring of one (1) no. Diesel operated motor cab (Car No. WB 07J - 1216) with driver for official use of Assistant Engineer (Sub-Division), Barasat Arsenic Sub ¿ Division under B.Ar.D, PHE Dte. for different works under JJM Schemes with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil w.e.f. 01.03.2024 to 29.08.2024. | 430/B.Ar.D | 28/02/2024 | 182 | OM ENTERPRISE | 0.86 | 2.11 | 244.37 | 0
1416 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KONANAGAR to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte , SM/11661 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (Car No. WB07J - 1216) with driver for official use of Assistant Engineer (Sub-Division), Barasat Arsenic Sub Division under B.Ar.D, PHE Dte. for different works under JJM Schemes with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil w.e.f. 30.08.2024 to 31.10.2024". | 1414/B.Ar.D | 29/08/2024 | 63 | OM ENTERPRISE | 0.3 | 0.67 | 224.68 | 0
1417 | NORTH 24 PARGANAS | Barasat Arsenic Division | SURFACE BASED PWSS FOR BARASAT-II BLOCK , SM/19040 | Augmentation | Survey, Design Drawing & DPR Preparation for Surface Based PWSS for Barasat-II Block under Barasat Arsenic Division, P.H.E. Dte. | 539/B.Ar.D. | 13/03/2024 | 21 | UMWELT ENGINEER PVT. LTD. | 66.14 | 66.14 | 100 | 100
1418 | NORTH 24 PARGANAS | Barasat Arsenic Division | SURFACE BASED PWSS FOR BARASAT-II BLOCK , SM/19040 | Augmentation | Material Requisition To Resource Division | 244/B.Ar.D. | 06/02/2024 | 0 | Resource Division | 4012.31 | 0 | 0 | 0
1419 | NORTH 24 PARGANAS | Barasat Arsenic Division | SURFACE BASED PWSS FOR BARASAT-II BLOCK , SM/19040 | Augmentation | Laying, fitting, fixing, jointing etc of Primary & Secondary Rising Main and Construction of Ground Level Reservoir (GLR) Capacity 1100 CUM with all allied works of Barasat-II Block for Surface Based PWSS for Barasat-II Block in the district of North 24 Parganas under Barasat Arsenic Division, PHE Dte. | 159/B.Ar.D. | 25/01/2024 | 730 | SUPRITI ENTERPRISE | 2710.36 | 0 | 0 | 10
1420 | NORTH 24 PARGANAS | Eastern Mechanical | SURFACE BASED PWSS FOR BARASAT-II BLOCK , SM/19040 | Augmentation | Providing Mechanical / Electrical Equipment for 11/0.433 KV Sub-station along with pumping station and disinfection arrangement Integrated Surface Water Based PWSS for Barasat-II Blocks in the District of North-24-Parganas. 1) Acceptance Order No. 211/MC-III dt. 01.03.2024 2) Administrative Approval No. 3497/PHE-28011/135/2023-SCHM CELL - of PHE Dept. dt. 17.11.2023 3) NIET No.-27/SEMCIII/WBPHED OF 2023-2024 (vide memo.no. 66/MC-III, Dated 13.01.2024) | 757/EMD | 06/03/2024 | 756 | B.T. PROJECTS PVT. LTD | 780 | 0 | 0 | 25
1421 | NORTH 24 PARGANAS | Barasat Arsenic Division | SURFACE BASED PWSS FOR BARASAT-II BLOCK , SM/19040 | Augmentation | Restoration of damaged UPVC pipeline and withdrawing relaying of DI/HDPE pipe distribution System including specials all complete and necessary road restoration work for the scheme of "Surface Based PWSS for Barasat-II Block in the district of North 24 Parganas under Barasat Arsenic Division, PHE Dte". | 593/B.Ar.D. | 26/03/2025 | 180 | SUPRITI ENTERPRISE | 380.56 | 0 | 0 | 20
1422 | NORTH 24 PARGANAS | Barasat Arsenic Division | SURFACE BASED PWSS FOR BARASAT-II BLOCK , SM/19040 | Augmentation | Wall writing on smooth wall surface (Preferably on Govt. premises / Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and two coat best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo picture etc. of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the blocks of Hasnabad (Part), Sandeshkhali-II (Part), Baduria (Part), Haroa, Rajarhat and Barasat-II (Part) all completed as per direction of EIC. (Rate inclusive 18% GST & 1% CESS) | 53/B.Ar.D. | 08/01/2025 | 45 | IMAGIN | 12.33 | 0 | 0 | 80
1423 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC , SM/12111 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Durgapur Baylani w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 1208/BD | 20/04/2023 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 21.47 | 17.1 | 79.66 | 91
1424 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC , SM/12111 | Augmentation | Formal work order for the work of Laying of Di/UPVC distribution pipe line, construction of 500cum capacity 20mtr staging height R.C.C over Head Reservoir as per Deptt. design, drawing & specification including bored pile with pile cap and providing Functional Household Tap Connection in connection with Augmentation of Durgapur Baylani Water Supply Scheme(Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 2458/BD | 17/08/2023 | 1096 | APURBA MANDAL | 844.5 | 542.92 | 64.29 | 71
1425 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC , SM/12111 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Durgapur Baylani w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 2492/BD | 18/08/2023 | 30 | M/S RAJPATH CONSTRUCTION. | 21.95 | 20.25 | 100 | 66
1426 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC , SM/12111 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I)(Rep) under Durgapur- Baylani W/S Scheme District of 24 Pgs. (N) NIET No. 26 of EE/EMD of 2022-23 (Sl. No.-23) | 1169/EMD | 21/03/2023 | 772 | ABHISEK ENGINEERING CONCERN | 26.35 | 18.16 | 76.07 | 80
1427 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC , SM/12111 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Durgapur Baylani Z-I w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. (Part-A) | 244/HSD | 30/01/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.63 | 0 | 0 | 100
1428 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC , SM/12111 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Durgapur Baylani Z-I w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte.Part-B | 243/HSD | 30/01/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.73 | 0 | 0 | 100
1429 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Itinda Panitor to accommodate FHTC , SM/11626 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under Itindapanitor W/S Scheme District of 24 Pgs. (N) | 6387 / EMD | 14/08/2022 | 30 | RAJLAXMI ELECTRICAL WORKS | 13.04 | 9.48 | 72.72 | 1
1430 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Itinda Panitor to accommodate FHTC , SM/11626 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Itinda-Panitor W/S Scheme District of 24 Pgs. (N). (SM/11626) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 11) | 6386/ EMD | 14/08/2022 | 30 | GLACIER ENGINEERING CO. | 13.04 | 8.22 | 63.06 | 1
1431 | NORTH 24 PARGANAS | Central Drilling | Augmentation of ground water based piped water supply scheme for Itinda Panitor to accommodate FHTC , SM/11626 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 270 Mtrs. Depth) by utilising Departmental Machineries for Itinda Panitar W/S Scheme (T/W-I) , Basirhat-I Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | 117/CDD | 17/04/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 19.94 | 0 | 0 | 0
1432 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Itinda Panitor to accommodate FHTC , SM/11626 | Augmentation | Material Requisition To Resource Division | 857/BD | 20/03/2023 | 0 | Resource Division | 190.23 | 0 | 0 | 0
1433 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Itinda Panitor to accommodate FHTC , SM/11626 | Augmentation | Material Requisition To Resource Division | 4414/BD | 10/11/2023 | 0 | Resource Division | 18.48 | 0 | 0 | 0
1434 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Itinda Panitor to accommodate FHTC , SM/11626 | Augmentation | Material Requisition To Resource Division | 3479/BD | 10/12/2024 | 0 | Resource Division | 77.88 | 0 | 0 | 0
1435 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Itinda Panitor to accommodate FHTC , SM/11626 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Itinda Panitor water supply scheme in Basirhat-I Block under Barasat Division, P.H.E Dte. | 429/BD | 13/02/2023 | 1049 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 662.31 | 182.01 | 27.48 | 24
1436 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Preparation of Augmentation DPR for Bagband Saiberia Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | 1958/B.Ar.D | 26/09/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0.98 | 100 | 1
1437 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Material Requisition To Resource Division | 2212/B.Ar.D. | 22/11/2022 | 0 | Resource Division | 20.91 | 0 | 0 | 0
1438 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir & other existing civil component of Capacity 800 Cu.m. at Bagband Saiberia W/S Scheme uder Barasat-II Block under Barasat Arsenic Division, PHE Dte. (SM/11558) | 2468/B.Ar.D. | 21/12/2022 | 60 | SAHA ENTERPRISE | 16.6 | 15.13 | 91.13 | 60
1439 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Sinking of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation of Bagband Saiberia w/s Scheme at Nababpur Mouza of Barasat-II block under Barasat Arsenic Division, P.H.E. Dte. | 468/B.Ar.D. | 27/02/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 15.62 | 11.81 | 100 | 100
1440 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Sinking of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation of Bagband Saiberia w/s Scheme at Kayemba Mouza of Barasat-II block under Barasat Arsenic Division, P.H.E. Dte. | 920/B.Ar.D. | 11/04/2023 | 45 | ACME CONSTRUCTION | 15.62 | 12.77 | 100 | 100
1441 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (AC) (Car No. WB-25F-6815) with driver for official use for Chief Engineer (Head Quarters) in place of Director, WSSO, PHE Department. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 01.06.2023 to 31.08.2023." | 1281/B.Ar.D | 30/05/2023 | 92 | NASIRUDDIN BISWAS | 0.48 | 1.19 | 100 | 100
1442 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Yard lighting arrangement at the premises of P.H No.-I (Head works site) under Bagband Saiberia W/S Scheme, Dist-24Pgs (N). | 748/EMSD-I | 14/03/2023 | 20 | PURUSHOTTAM ENTERPRISE | 3.02 | 2.81 | 100 | 90
1443 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Material Requisition To Resource Division | 31/B.Ar.D. | 05/01/2023 | 0 | Resource Division | 20.91 | 0 | 0 | 0
1444 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Deposit work other than new Service connection at PH-V bagbanda Saiberia Khamarpara W/S Scheme | BP-227-23-24 | 21/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.54 | 0 | 0 | 0
1445 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | New Service connection at PH-V bagbanda Saiberia Kemia Khamarpara W/S Scheme | BP-228-23-24 | 21/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.97 | 0 | 0 | 0
1446 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Bagband Saiberia under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 1721/B.Ar.D. | 05/09/2022 | 630 | PUSPA ENTERPRISE | 442.01 | 261.38 | 59.14 | 86
1447 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (Car No. WB-25L-0302) with driver for official use for Executive Engineer, Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 01.04.2023 to 30.04.2023." | 827/B.Ar.D | 30/03/2023 | 30 | RANJIT KUMAR MONDAL | 0.14 | 0.36 | 251.39 | 0
1448 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Hiring of one (1) no. Diesel operated motor cab (Car No.- WB25K-2915) with driver for official use for Assistant Engineer (HQ-II), Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil w.e.f. 01.05.2023 to 16.11.2023. | 1007/B.Ar.D | 26/04/2023 | 200 | PREMANANDA ROY BISWAS | 0.95 | 2.58 | 216.03 | 40
1449 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (Car No.- WB-25K-2915) with driver for official use for Assistant Engineer (HQ - II), under Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil w.e.f. 17.11.2023 to 30.11.2023". | 2660/B.Ar.D | 09/11/2023 | 14 | PREMANANDA ROY BISWAS | 0.07 | 0.19 | 279.95 | 0
1450 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Construction of 01 (one) no. pump house (4.88 X 3.66 mtr.) at the site Nababpur of Baghband Saiberia W/S Scheme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | 2488/B.Ar.D. | 11/10/2023 | 45 | AT CONSTRUCTION | 7.51 | 6.69 | 100 | 50
1451 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Construction of 01 (one) no. pump house (4.88 X 3.66 mtr.) at the site Kayemba of Baghband Saiberia W/S Scheme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | 2354/B.Ar.D. | 22/09/2023 | 45 | SUJAN KUMAR MISTRI | 5.97 | 5.39 | 100 | 80
1452 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Laying of Pipeine for Pump Connection with necessarey inter connection arrangement for Two (02) nos Pump House at Kayemba and Nababpur at Baghband Saiberia Water Supply Scheme under Barasat-II Block under Barasat Arsenic Division, PHE Dte. | 1581/B.Ar.D. | 23/09/2024 | 30 | SAHA ENTERPRISE | 13.53 | 13.51 | 100 | 100
1453 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Payment of quotation amount for new service connection at P/H No: IV , Nababpur under Bagband Saiberia scheme. | BP-302-23-24 | 04/03/2024 | 0 | W.B.S.E.D.C.L. (GANGANAGAR C.C.C.) | 7.47 | 0 | 0 | 0
1454 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I/ II (Replacement) and III and IV (New) under Bagband-Saiberia W/S Scheme District of 24 Pgs. (N). | 4937/EMD | 18/08/2023 | 30 | GOENKA ENTERPRISE | 33.23 | 20.32 | 61.13 | 66
1455 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No.- WB-25J-3845) with driver for official use for Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 01.07.2024 to 31.12.2024. | 1051/B.Ar.D | 28/06/2024 | 184 | OM ENTERPRISE | 0.87 | 2.2 | 252.17 | 0
1456 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Restoration of damaged existing pipeline and Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within leftout zone of Krisnamati, Bagberia, Kayemba, Andulia and Kirtipur area for Augmentation of Ground Based Water Supply Scheme at Baghband Saiberia under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 234/B.Ar.D | 06/02/2025 | 315 | N. H. ENTERPRISE | 34.02 | 0 | 0 | 50
1457 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Restoration of damaged existing pipeline and Laying of distribution Main (DI Pipe) System including specials all complete from existing and new proposed distribution system along Badu Road and Madanpur Krishnapur area for Augmentation of Ground Based Water Supply Scheme at Baghband Saiberia under Barasat - II Block under Barasat Arsenic Division, PHE Dte. (SM/11558) | 794/B.Ar.D. | 30/04/2025 | 180 | TOJO ENTERPRISE | 14.87 | 0 | 0 | 80
1458 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Bagband Saiberia & Its Adjoining Mouzas water supply scheme for providing Functional House Tap Connection under Barasat Arsenic Division, P.H.E. Dte. , SM/11558 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Baghband Saiberia Water Supply Scheme under Barasat-II Block under Barasat Arsenic Division, PHE Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Baghband Saiberia Water Supply Scheme under Barasat-II Block by Augmentation of Ground Water based PWSS for Baghband Saiberia Water Supply Scheme under Barasat-II Block under Barasat Arsenic Division, PHE Dte. | 244/B.Ar.D | 07/02/2025 | 90 | ROY BISWAS CONSTRUCTION | 20.78 | 0 | 0 | 100
1459 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC , SM/11529 | Augmentation | ¿¿k¿ vghgyvuuu gb hv hv hv hv hvv vhyv vh vhcv v hvh |  | 15/12/2023 | 3 | JOY ENGINEERING CO. | 0 | 0 | 0 | 0
1460 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC , SM/11529 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300mm. x 200 mm. big dia 270 mtr deep Tube well by Direct Rotary Rig method using PVC pipe & strainer having 300 mm Dia 36 mtr. long Housing Pipe and 200 mm Dia 30 mtr. long filter for Augmentation of Joypur Gopmahal Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | 206/BD | 24/01/2023 | 30 | MONDAL & CO. (BASIRHAT). | 39.55 | 38.28 | 100 | 100
1461 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC , SM/11529 | Augmentation | Material Requisition To Resource Division | 483/BD | 17/02/2023 | 0 | Resource Division | 0.55 | 0 | 0 | 0
1462 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC , SM/11529 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I and II under Joypur Gopmahal ground water based water supply scheme under Block_ Bashirhat Dist. - 24Pgs(N) under EMD, PHE Dte. | 6969/EMD | 15/12/2023 | 91 | M/S DILIP MITRA | 20.49 | 19.99 | 100 | 57
1463 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC , SM/11529 | Augmentation | Acceptance cum work order for Special repair and renovation of existing structures like Pump House, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Itinda Panitor, Joypur Gopmahal, Kachua Swarupnagar, Mathurapur, Mirzanagar, Nalkora, Paikardanga, Pifa and Gobindapur Water Supply Scheme of different block under Basirhat Sub-Division within Barasat Division, P.H.E Dte. | 2474/BD | 17/07/2025 | 150 | SAHA CONSTRUCTION & CO | 91.3 | 0 | 0 | 0
1464 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Joypur Gopmahal to accommodate FHTC , SM/11529 | Augmentation | Acceptance cum work order for Laying of UPVC distribution main and Providing FHTC (Functional Household Tap Connection ) by augmentation for Joypur Gopmahal water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | 3585/BD | 08/12/2022 | 744 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 37.54 | 18.81 | 50.14 | 100
1465 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Goknashri Gobindapur to accommodate FHTC , SM/11604 | Augmentation | Route Survey, Design Drawing & DPR Preparation for GOKNASREE GOBINDAPUR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | 193/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.73 | 3.63 | 100 | 1
1466 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Goknashri Gobindapur to accommodate FHTC , SM/11604 | Augmentation | Material Requisition To Resource Division | 1245/BD | 25/04/2023 | 0 | Resource Division | 5.09 | 0 | 0 | 0
1467 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Goknashri Gobindapur to accommodate FHTC , SM/11604 | Augmentation | Material Requisition To Resource Division | 4412/BD | 10/11/2023 | 0 | Resource Division | 16.02 | 0 | 0 | 0
1468 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Goknashri Gobindapur to accommodate FHTC , SM/11604 | Augmentation | Formal work order for laying of UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) by augmentation for Goknashri Gobindapur water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | 1042/BD | 31/03/2023 | 739 | UTPAL CONSTRUCTION & CO. | 383.12 | 333.4 | 87.02 | 64
1469 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Goknashri Gobindapur to accommodate FHTC , SM/11604 | Augmentation | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Goknasree Gobindapur W/S Scheme including increasing the height of back wash tank at Basirhat - I Block under Basirhat Sub Division, PHE Dte. Capacity- 60.00 Cum/hr. | 923/BD | 15/03/2024 | 60 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 33.01 | 27.58 | 83.54 | 50
1470 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Goknashri Gobindapur to accommodate FHTC , SM/11604 | Augmentation | Acceptance cum work order for special repair and renovation of existing structure like Pump House, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Dobila, Eojnogar, Gobindapur Dhokra, Goknasree Gobindapur, Gotra, Sankchura and Mominpur Water Supply Scheme of different block within Basirhat Sub-Division under Barasat Division P.H.E. Dte. | 2464/BD | 16/07/2025 | 150 | M/S TARAFDAR CONSTRUCTION | 81.09 | 0 | 0 | 0
1471 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC , SM/13737 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Bithari Zone-I Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 450/BHT | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 4.95 | 100 | 1
1472 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC , SM/13737 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Bithari Zone-I Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 451/BHT | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.22 | 1.22 | 100 | 0
1473 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC , SM/13737 | Augmentation | Additional Survey work for DPR Preparation for BITHARI ZONE -1 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 451 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.22 | 0 | 0 | 1
1474 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC , SM/13737 | Augmentation | Material Requisition To Resource Division | 1241/BD | 25/04/2023 | 0 | Resource Division | 145.39 | 0 | 0 | 0
1475 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC , SM/13737 | Augmentation | Material Requisition To Resource Division | 1631/BD | 01/06/2023 | 0 | Resource Division | 43.69 | 0 | 0 | 0
1476 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC , SM/13737 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bithari Zone-I water supply scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E Dte. | 1357/BD | 04/05/2023 | 785 | MAHAVIR PUMPS MANUFACTURING PVT.LTD. | 723.95 | 376.45 | 52 | 48
1477 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC , SM/13737 | Augmentation | Regarding Restoration charges for road damages. | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 39.73 | 0 | 0 | 0
1478 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC , SM/13737 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II, III and IV (Rep.) under Bithari (Zone-I) W/S Scheme and Pump House No-I under Taranipur (Zone-I) W/S Scheme District of 24 Pgs. (N) | 6752/EMD | 28/11/2023 | 490 | M.S. ENTERPRISE | 65.12 | 0 | 0 | 60
1479 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC , SM/13737 | Augmentation | Acceptance cum work order for special repair renovation of existing structures like Pump house, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Akhipur, Baro Bankra, Bithari Z-I, Bithari Z-II water supply scheme of different block under Basirhat Sub-Division, PHE Dte. | 2381/BD | 10/07/2025 | 150 | JP CONSTRUCTION & SUPPLIERS. | 81.91 | 0 | 0 | 0
1480 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-I to accommodate FHTC , SM/13737 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Swarupnagar Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - A) | 152/BHTSD | 29/01/2025 | 20 | BIBHAS PAL. | 0.88 | 0 | 0 | 90
1481 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kulia to accommodate FHTC , SM/11755 | Augmentation | Acceptance cum work order for Laying of UPVC distribution main and Providing FHTC (Functional Household Tap Connection ) by augmentation for Kulia water supply scheme in Baduria block under Barasat Division, PHE Dte. | 3586/BD | 08/12/2022 | 30 | PREMANANDA ROY BISWAS. | 73.89 | 72.44 | 100 | 100
1482 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kulia to accommodate FHTC , SM/11755 | Augmentation | Material Requisition To Resource Division | 494/BD | 17/02/2023 | 0 | Resource Division | 2.75 | 0 | 0 | 0
1483 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Taranipur Zone I to accommodate FHTC , SM/11757 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Taranipur Zone I Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 446/ BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.69 | 3.69 | 50 | 1
1484 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Taranipur Zone I to accommodate FHTC , SM/11757 | Augmentation | Material Requisition To Resource Division | 1272/BD | 25/04/2023 | 0 | Resource Division | 5.86 | 0 | 0 | 0
1485 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Taranipur Zone I to accommodate FHTC , SM/11757 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection) for Augmentation of Taranipur Zone-I Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E. Dte. | 1734/BD | 08/06/2023 | 630 | DIVINE | 307.75 | 266.66 | 86.65 | 75
1486 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Taranipur Zone I to accommodate FHTC , SM/11757 | Augmentation | Shifting of One DTR DP structure includuing 63 KVA DTR and one T-Off 9 mtr PCC Pole to the adjucent location on request. | BP-166-24-25 | 25/11/2024 | 0 | W.B.S.E.D.C.L (TEHATTA CCC) | 0.93 | 0 | 0 | 0
1487 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Taranipur Zone I to accommodate FHTC , SM/11757 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II, III and IV (Rep.) under Bithari (Zone-I) W/S Scheme and Pump House No-I under Taranipur (Zone-I) W/S Scheme District of 24 Pgs. (N) | 6752/EMD | 28/11/2023 | 490 | M.S. ENTERPRISE | 65.12 | 0 | 0 | 60
1488 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Taranipur Zone I to accommodate FHTC , SM/11757 | Augmentation | Providing outdoor illumination arrangement at P.H. No.- I, Zone-I under Taranipur W/S Scheme under EMSD-I, P.H.E. Dte. Dist.- 24PGS(N). | 455/EMSD-I | 08/04/2025 | 25 | AMIT DAS | 1.36 | 0 | 0 | 0
1489 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. , SM/11987 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 180 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Barunhat Patlikhanpur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 1218/BD | 20/04/2023 | 30 | ANJALI ENTERPRISE. | 25.41 | 17.83 | 70.18 | 0
1490 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. , SM/11987 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 180 mtr deep Tubewell by D.R. Rig method at PH No.- 1 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Barunhat Patlikhanpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 1219/BD | 20/04/2023 | 30 | ANJALI ENTERPRISE. | 12.7 | 9.5 | 74.81 | 0
1491 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. , SM/11987 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Barunhat Patlikhanpur water supply scheme (Z-I), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | 699/BD | 03/03/2023 | 90 | MONDAL & CO. (BASIRHAT). | 417.62 | 406.32 | 100 | 48
1492 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. , SM/11987 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 (Size-3.60x3.00 mtr.) for Augmentation of Barunhat Patlikhanpur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 1428/BD | 11/05/2023 | 60 | JESMINE ENTERPRISE. | 17.34 | 17.15 | 100 | 100
1493 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. , SM/11987 | Augmentation | Acceptance cum work order for Repairing of pump house with boundary wall & other allied works at PH No.-1 of Barunhat Patlikhanpur w/s scheme, Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | 2117/BD | 19/07/2023 | 21 | M/S K.B.ENTERPRISE. | 7.39 | 7.32 | 100 | 100
1494 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. , SM/11987 | Augmentation | Acceptance cum work order for Construction of new stand post for Barunhat patlikhanpur w/s Scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte | 829/HSD | 14/07/2023 | 10 | PRASANTA MITRA. | 2.89 | 2.89 | 100 | 100
1495 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. , SM/11987 | Augmentation | Material Requisition To Resource Division | 935/BD | 22/03/2023 | 0 | Resource Division | 80.45 | 0 | 0 | 0
1496 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. , SM/11987 | Augmentation | New service connection under AE-I Barunhat Siristala | BP-122-23-24 | 07/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.47 | 0 | 0 | 0
1497 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. , SM/11987 | Augmentation | New Service Connection under AE-I Barunhat | BP-123-23-24 | 07/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 16.13 | 0 | 0 | 0
1498 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. , SM/11987 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Barunhat Patlikhanpur water supply scheme (Zone-II), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | 87/BD | 11/01/2023 | 90 | R.K.MANDAL & CO. | 317.9 | 310.72 | 100 | 80
1499 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. , SM/11987 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II (Rep.) and III and IV (New) under Barunhat-Patlikhanpur W/S Scheme District of 24 Pgs. (N) NIET No.- 29 of EE/EMD of 2022-23 (Sl. No.- 06) | 1287/EMD | 28/03/2023 | 30 | S.G. ENTERPRISE | 52.98 | 49.17 | 70.13 | 45
1500 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. , SM/11987 | Augmentation | Formal work order for Construction of 500cum capacity 20mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Barunhat Patlikhanpur water supply Scheme(Z-I), Hasnabad Block under Hasnabad Sub-Division PHE Dte. | 2611/BD | 29/08/2023 | 365 | MONDAL & CO. (BASIRHAT). | 203.7 | 185.49 | 100 | 100
1501 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. , SM/11987 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no-1 in connection with Augmentation of Barunhat Patlikhanpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 38/HSD | 09/01/2024 | 10 | SHYAM SUNDAR DAS. | 0.93 | 0.88 | 100 | 100
1502 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. , SM/11987 | Augmentation | Formal work order for Additional Laying of DI/UPVC distribution pipe line and Providing Functional Household Tap Connection for the left out portion in connection with Augmentation of Baruhat Patlikhanpur water supply scheme (Z-I), Hasnabad Block of Hasnabad Sub-Division, P.H.E Dte. | 1735/BD | 27/06/2024 | 90 | MONDAL & CO. (BASIRHAT). | 107.74 | 69.79 | 65.89 | 70
1503 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. , SM/11987 | Augmentation | Acceptance cum work order for Emergent resting of old rising main pipeline with UC Bullah pilling at OHR site in connection with augmentation io Barunhat Patlikhanpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub- Division P.H.E. Dte. | 326/HSD | 04/02/2025 | 10 | MONDAL & CO. (BASIRHAT). | 0.98 | 0 | 0 | 0
1504 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. , SM/11987 | Augmentation | Formal work order for Construction of 350 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Barunhat Patlikhanpur water supply scheme (Z-II), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | 2867/BD | 20/09/2023 | 528 | R.K.MANDAL & CO. | 152.42 | 74.03 | 55.77 | 100
1505 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. , SM/11987 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with augmentation of Barunhat Patlikhanpur water supply scheme (Z-I), Hasnabd block under Hasnabad Sub-Division, P.H.E. Dte. | 265/HSD | 30/01/2025 | 10 | STAR CONSTRUCTION. | 0.55 | 0 | 0 | 100
1506 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC. , SM/11987 | Augmentation | Acceptance cum work order for Special Repair & Maintenance of Rising main & Distribution system (CI/DI/UPVC) with construction of new stand post for Barunhat Patlikhanpur w/s Scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 577/HSD | 17/03/2025 | 10 | STAR CONSTRUCTION. | 2.15 | 0 | 0 | 100
1507 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sonpur to accommodate FHTC , SM/11758 | Augmentation | Route Survey, Design Drawing & DPR Preparation for SONPUR Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 458 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.87 | 2.87 | 100 | 1
1508 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sonpur to accommodate FHTC , SM/11758 | Augmentation | Material Requisition To Resource Division | 3809/BD | 23/12/2022 | 0 | Resource Division | 0.41 | 0 | 0 | 0
1509 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sonpur to accommodate FHTC , SM/11758 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Sonpur water supply scheme in Swarupnagar block under Barasat Division, PHE Dte. | 3401/BD | 21/11/2022 | 90 | M/S ANUBHAB CONSTRUCTION. | 133.98 | 127.7 | 100 | 95
1510 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sonpur to accommodate FHTC , SM/11758 | Augmentation | Providing voltage correction arrangement with allied works at PH-I of Sonpur GRW W/S Scheme under EMSD-I. | 1780EMSD-I | 10/08/2023 | 30 | P.K. ENTERPRISE | 3.15 | 3.12 | 100 | 100
1511 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sonpur to accommodate FHTC , SM/11758 | Augmentation | Material Requisition To Resource Division | 4413/BD | 10/11/2023 | 0 | Resource Division | 6.16 | 0 | 0 | 0
1512 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sonpur to accommodate FHTC , SM/11758 | Augmentation | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Sonepur W/S Scheme including increasing the height of back wash water tank at Swarupnagara Block under Basirhat Sub Division, PHE Dte. Capacity-10.00Cum/hr. | 924/BD | 15/03/2024 | 360 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 23.32 | 0 | 0 | 75
1513 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC , SM/11699 | Augmentation | Material Requisition To Resource Division | 3421/BD | 23/11/2022 | 0 | Resource Division | 62.56 | 0 | 0 | 0
1514 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC , SM/11699 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Khulna Bhanderkhali W/S scheme (Zone-II), Sandeshkhali-II Block within Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | 2722/BD | 14/09/2022 | 90 | S.S.ENTERPRISE. (BAMANGACHI) | 345.34 | 320.2 | 92.72 | 1
1515 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC , SM/11699 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Zone-II) (Replacement) under Kulna-Bhanderkhali W/S Scheme District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 09) | 36/EMD | 03/01/2023 | 30 | JAL PRAVAHIKA PVT. LTD. | 26.49 | 24.17 | 100 | 100
1516 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC , SM/11699 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.III (Zone-II) (Replacement) under Khulna-Bhanderkhali W/S Scheme District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 10) | 37/EMD | 03/01/2023 | 30 | D.K. ELECTRIC | 13.24 | 12.36 | 100 | 100
1517 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC , SM/11699 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Khulna Bhanderkhali w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 785/BD | 13/03/2023 | 30 | M/S NIRMAN CONSTRUCTION. | 47.08 | 36.84 | 100 | 100
1518 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC , SM/11699 | Augmentation | Acceptance cum work order for Construction of boundary wall at pond site for damaged portion & repairing of existing boundary wall at CWR site within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II Block under Hasnabad Sub-Division, P.H.E. Dte. | 2113/BD | 19/07/2023 | 21 | ANKUSH CONSTRUCTION & CO. | 6.14 | 6.14 | 100 | 55
1519 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC , SM/11699 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Khulna Bhanderkhali w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 2491/BD | 18/08/2023 | 30 | M/S PROGATI ENTERPRISE. | 26.89 | 20.57 | 100 | 100
1520 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC , SM/11699 | Augmentation | Material Requisition To Resource Division | 941/BD | 22/03/2023 | 0 | Resource Division | 9.14 | 0 | 0 | 0
1521 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC , SM/11699 | Augmentation | Acceptance cum work order for Protection works in different places for protection of different dia DI/UPVC rising/distribution pipe line by UC bullah/Bamboo pile for Augmentation of Khulna Bhandarkhali Zone-II w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 2656/BD | 01/09/2023 | 30 | M/S DATTA ENTERPRISE. | 58.87 | 58.07 | 100 | 85
1522 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC , SM/11699 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Khulna Bhanderkhali water supply scheme (Z-II) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 1419/HSD | 06/11/2023 | 7 | DEB PRASAD GHOSH. | 0.96 | 0.96 | 100 | 100
1523 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC , SM/11699 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-3 in connection with Augmentation for Khulna Bhanderkhali water supply scheme (Z-II) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 1418/HSD | 06/11/2023 | 7 | DEB PRASAD GHOSH. | 0.93 | 0.93 | 100 | 100
1524 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC , SM/11699 | Augmentation | Quotation for Service Connection Charges for PH- III under Bhanderkhali W/S Scheme in the district of North 24 Pgs. JL No. 92, Plot No-112. | BP-321-23-24 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.02 | 0 | 0 | 0
1525 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC , SM/11699 | Augmentation | Quotation for Service Connection Charges for PH- I under Bhanderkhali W/S Scheme in the district of North 24 Pgs. JL No- 92, Plot No-1 & 65/264 |  | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.55 | 0 | 0 | 0
1526 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC , SM/11699 | Augmentation | Formal work order for Construction of 150 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Khulna Bhanderkhali (Zone-II) under Surface Based Water Supply Scheme Hasnabad under Hasnabad Sub-Division, PHE Dte. | 2261/BD | 12/08/2024 | 365 | B.S.ENTERPRISE. (BASIRHAT) | 115.79 | 0 | 0 | 0
1527 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC , SM/11699 | Augmentation | Acceptance cum work order for Providing Functional tap connection at Sitalia Khaitala SSK, ICDS Centre no-77, Dakshin Sitalia FP School, South Hatgacha Jr. Basic School and Hatgacha Goramari FP Schoolwithin the command area of Khulna Bhanderkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 997/HSD | 04/06/2025 | 10 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 0.96 | 0 | 0 | 0
1528 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC , SM/11699 | Augmentation | Acceptance cum work order for Repairing of Pump House at PH No- 1, 2 & 3 in connection with augmentation of Khulna Bhandarkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 895/BD | 20/03/2025 | 75 | GAZI ENTERPRISE | 5.52 | 0 | 0 | 0
1529 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC , SM/11699 | Augmentation | Acceptance cum work order for Protection of pipe line by bamboo pilling near Ph no- 3 in connection with augmentation of Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 371/HSD | 10/02/2025 | 10 | M/S NIRMAN CONSTRUCTION. | 0.85 | 0 | 0 | 100
1530 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped W/S Scheme for Gainpur in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. , SM/11940 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1430/NWSD-I | 18/09/2024 | 7 | BIBHAS PAL | 5.27 | 0.53 | 50 | 100
1531 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped W/S Scheme for Gainpur in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. , SM/11940 | Augmentation | Construction of 100 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation, Soil Test), pipe connection and cost of pipes, specials, Construction Boundary wall at Pump House, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc., Augmentation of Gainpur Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. | 552/NWSD-I | 08/05/2023 | 366 | SUDHAMAY MAJUMDAR | 166.79 | 59.45 | 35.64 | 26
1532 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped W/S Scheme for Gainpur in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. , SM/11940 | Augmentation | Laying of distribution system & related works at Gainpur W/S scheme in the District of North 24 Parganas under North 24 Parganas water Supply Division-I, PHE Dte. | 483/NWSD-I | 28/03/2025 | 15 | SUDHAMAY MAJUMDAR | 15.22 | 0 | 0 | 55
1533 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Chhaimalpur , SM/13767 | Augmentation | Material Requisition To Resource Division | 926/BD | 22/03/2023 | 0 | Resource Division | 4.71 | 0 | 0 | 0
1534 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Chhaimalpur , SM/13767 | Augmentation | Formal work order for Construction of 100 cum capacity CWR, pipe connection and cost of pipes, specials and Laying of DI rising main, DI/UPVC distribution pipe line, providing Functional Household Tap Connection in connection with Augmentation of Chaimalpur water supply scheme, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | 1221/BD | 20/04/2023 | 366 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 215.47 | 205.22 | 100 | 65
1535 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Chhaimalpur , SM/13767 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 180 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300 mm dia 48 mtr. long housing pipe & 200 mm dia 30 mtr. long filter for Augmentation of Chaimalpur w/s scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 2496/BD | 21/08/2023 | 30 | ANJALI ENTERPRISE. | 26.02 | 18.61 | 100 | 69
1536 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Chhaimalpur , SM/13767 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Chhaimalpur W/S Scheme and Pump House No.I & II under Asharia-Narayanpur W/S Scheme , District of 24 Pgs. (N) NIET No.- 29 of EE/EMD of 2022-23 (Sl. No.-07) | 1003/EMD | 09/03/2023 | 695 | SWAPAN KUMAR BHANJA | 42.29 | 35.1 | 100 | 100
1537 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Chhaimalpur , SM/13767 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Nandanpur mouza within Chaimalpur w/s scheme, Hasnabad block under Hasnasbad Sub-Division, P.H.E.Dte. | 239/HSD | 30/01/2025 | 10 | ABDUL HAMID GAZI. | 0.89 | 0 | 0 | 100
1538 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Chhaimalpur , SM/13767 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Sirajpur mouza within Chaimalpur w/s scheme, Hasnabad block under Hasnasbad Sub-Division, P.H.E.Dte. | 536/HSD | 10/03/2025 | 10 | SARKAR ENTERPRISE | 0.97 | 0 | 0 | 100
1539 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Chhaimalpur , SM/13767 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no-1 in connection with Augmentation of Chaimalpur w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 949/HSD | 29/05/2025 | 10 | SARKAR ENTERPRISE | 0.93 | 0 | 0 | 100
1540 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. , SM/12735 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Khulna Bhanderkhali w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 786/BD | 13/03/2023 | 30 | MONDAL & CO. (BASIRHAT). | 47.09 | 37.47 | 100 | 0
1541 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. , SM/12735 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.-2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Khulna Bhanderkhali w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 2490/BD | 18/08/2023 | 30 | M/S DATTA ENTERPRISE. | 26.91 | 21.67 | 100 | 100
1542 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. , SM/12735 | Augmentation | Material Requisition To Resource Division | 923/BD | 22/03/2023 | 0 | Resource Division | 94.23 | 0 | 0 | 0
1543 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. , SM/12735 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Khulna Bhanderkhali W/S scheme (Zone-I), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | 3182/BD | 01/11/2022 | 90 | UMWELT ENGINEER PVT.LTD. | 497.55 | 365.15 | 100 | 100
1544 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. , SM/12735 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Zone-I)(Rep.) under Khulna-Bhanderkhali W/S Scheme District of 24 Pgs. (N) NIET No.- 26 of EE/EMD of 2022-23 (Sl. No.- 29) | 1170/EMD | 21/03/2023 | 30 | M.S. ENTERPRISE | 39.16 | 35.99 | 100 | 90
1545 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. , SM/12735 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no-1 in connection with Augmentation of Khulna Bhandarkhali w/s scheme (Z-I), Sandeshkhali -II block under Hasnabad Sub-Division P.H.E. Dte. | 799/HSD | 13/07/2023 | 10 | JESMINE ENTERPRISE. | 0.9 | 0.88 | 100 | 100
1546 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. , SM/12735 | Augmentation | Acceptance cum work order for Construction of approach road with cement concrete at Pump house No-1 within Khulna Bhanderkhali w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte | 801/HSD | 13/07/2023 | 7 | JESMINE ENTERPRISE. | 0.57 | 0.51 | 100 | 100
1547 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. , SM/12735 | Augmentation | Acceptance cum work order for Repairing of Pump House at PH No- 1, 2 & 3 for Khulna Bhandarkhali w/s scheme (Zone-I), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 2719/BD | 05/09/2023 | 21 | LAHIRI CONSTRUCTION. | 6.11 | 6.01 | 100 | 80
1548 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. , SM/12735 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Khulna Bhanderkhali water supply scheme (Z-I) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 1417/HSD | 06/11/2023 | 7 | ANKUSH CONSTRUCTION & CO. | 0.98 | 0.96 | 100 | 100
1549 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. , SM/12735 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-3 in connection with Augmentation for Khulna Bhanderkhali water supply scheme (Z-I) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 285/HSD | 06/03/2024 | 10 | DEB PRASAD GHOSH. | 0.67 | 0.67 | 100 | 100
1550 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. , SM/12735 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no-3 in connection with Augmentation of Khulna Bhandarkhali w/s scheme (Z-I), Sandeshkhali -II block under Hasnabad Sub-Division P.H.E. Dte. | 800/HSD | 24/05/2023 | 10 | JESMINE ENTERPRISE. | 0.84 | 0.8 | 100 | 100
1551 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. , SM/12735 | Augmentation | Quotation for Service Connection Charges for PH- I under Bhanderkhali W/S Scheme in the district of North 24 Pgs. JL No- 92, Plot No-1 & 65/264 | BP-320-23-24 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.55 | 0 | 0 | 0
1552 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. , SM/12735 | Augmentation | Quotation for Service Connection Charges for PH- III under Bhanderkhali W/S Scheme in the district of North 24 Pgs. JL No. 92, Plot No-112. |  | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.02 | 0 | 0 | 0
1553 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. , SM/12735 | Augmentation | Quotation for Service Connection Charges for PH- II under Bhanderkhali W/S Scheme in the district of North 24 Pgs. JL No- 92, Plot No- 63 | BP-327-23-24 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 18.31 | 0 | 0 | 0
1554 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. , SM/12735 | Augmentation | Enhancement of GST for the work providing FHTC for augmentation of Khulna Bhanderkhali (Zone-I) | BP-2024-25-78 | 10/07/2024 | 0 | UMWELT ENGINEER PVT.LTD. | 25.4 | 0 | 0 | 0
1555 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. , SM/12735 | Augmentation | Formal work order for construction of 450 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Khulna Bhanderkhali water supply scheme (Zone - I), Sandeshkhali-II Block under Hasnabad Sub-Division, P.H.E. Dte. | 2610/BD | 29/08/2023 | 1095 | M/S PROGATI ENTERPRISE. | 194.78 | 0 | 0 | 0
1556 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. , SM/12735 | Augmentation | Acceptance cum work order for Providing Functional Household tap connection at Sitalia FP School, South Hatgacha Jr. High School, Dakshin Hatgacha Adibasi SSK and Uttar Hatgacha SSK within the command area of Khulna Bhanderkhaliw/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 543/HSD | 10/03/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.83 | 0 | 0 | 0
1557 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Khulna Bhanderkhali Zone-I to accommodate FHTC. , SM/12735 | Augmentation | Acceptance cum work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Khulna Bhanderkhali w/s scheme (Z-I), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | 392/BD | 05/02/2025 | 60 | ANKUSH CONSTRUCTION & CO. | 12.47 | 0 | 0 | 100
1558 | NORTH 24 PARGANAS | Barasat Division | Hatbhanga Piped Water Supply Scheme , SM/13525 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (HATBHANGA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | 277/HSD | 09/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 0.8 | 0.8 | 100 | 1
1559 | NORTH 24 PARGANAS | Barasat Division | Hatbhanga Piped Water Supply Scheme , SM/13525 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (HATBHANGA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 276/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
1560 | NORTH 24 PARGANAS | Barasat Division | Hatbhanga Piped Water Supply Scheme , SM/13525 | New | Material Requisition To Resource Division | 880/BD | 22/03/2023 | 0 | Resource Division | 16.26 | 0 | 0 | 0
1561 | NORTH 24 PARGANAS | Eastern Mechanical | Hatbhanga Piped Water Supply Scheme , SM/13525 | New | New service connection for Hatbhanga PH-II, Hatbhanga minakhan | BP-252-23-24 | 20/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.76 | 0 | 0 | 0
1562 | NORTH 24 PARGANAS | Barasat Division | Hatbhanga Piped Water Supply Scheme , SM/13525 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 150 cum capacity CWR, pipe connection and cost of pipes specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at P.H. No.-1 (Size - 5.40 x 3.60 mtr.) & P.H. No-2 (Size - 3.60 x 3.00 mtr.) for Hatbhanga W/S Scheme, Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | 1714/BD | 08/06/2023 | 366 | POWER TOOLS & ENGINEERING | 268.27 | 113.97 | 42.48 | 65
1563 | NORTH 24 PARGANAS | Eastern Mechanical | Hatbhanga Piped Water Supply Scheme , SM/13525 | New | Quotation for Service Connection Charges for PH- I under Hathbhanga W/S Scheme in the district of North 24 Pgs. | BP-357-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.74 | 0 | 0 | 0
1564 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa , SM/13527 | Retrofitting | Formal work order for Laying Distribution system, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works and Providing FHTC at Zonal Head work site - XVII i.e. Betpuli within the jurisdiction of (Zone-XVII) under Habra-Gaighata surface based PWSS of Habra-I Block PART-F under Barasat Division, P.H.E. Dte. | 3020/BD | 05/10/2023 | 900 | BALAJI UDDYOG | 991.27 | 117.84 | 18.24 | 65
1565 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Donnagar PWSS to Accommodate FHTC. , SM/14127 | Augmentation | Material Requisition To Resource Division | 1274/BD | 25/04/2023 | 0 | Resource Division | 23.58 | 0 | 0 | 0
1566 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Donnagar PWSS to Accommodate FHTC. , SM/14127 | Augmentation | Material Requisition To Resource Division | 1675/BD | 06/06/2023 | 0 | Resource Division | 7.07 | 0 | 0 | 0
1567 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Donnagar PWSS to Accommodate FHTC. , SM/14127 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Donnagar W/S Scheme District of 24 Pgs. (N). | 4749/EMD | 07/08/2023 | 30 | BARISAL TRADING CO. | 20.19 | 17.05 | 84.48 | 85
1568 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Donnagar PWSS to Accommodate FHTC. , SM/14127 | Augmentation | Acceptance cum work order for Sinking of 250mm. X 150mm.dia. 300.00mtr. deep tubewell by direct rotary rig method, having 250mm.dia. 30.0mtr. long PVC housing pipe & 150mm.dia. 30.0mtr. long pre-packed resin bonded filter at Head Work Site of Donnagar Water Supply Scheme under Barasat Sub-Division, P.H.E. Dte. | 523/BD | 20/02/2023 | 15 | M/S SUKANTA ENTERPRISE. | 14.69 | 12.12 | 100 | 32
1569 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Donnagar PWSS to Accommodate FHTC. , SM/14127 | Augmentation | Preparation of DPR in connection of augumentation of Donnagar Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. Sl. No.-15 | 562/BSD | 29/06/2022 | 30 | RADIANT | 2.6 | 2.46 | 100 | 100
1570 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Donnagar PWSS to Accommodate FHTC. , SM/14127 | Augmentation | Formal work order for Laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for augmentation of Donnagar Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | 1531/BD | 19/05/2023 | 681 | M/S S. & P CONSTRUCTION | 147.04 | 76.92 | 52.31 | 20
1571 | NORTH 24 PARGANAS | Barasat Division | Purana Bongaon Piped water supply scheme , SM/13896 | New | Survey, Design, Drawing & DPR preparation for new PWSS at Puratan Bongaon water supply scheme in the Bongaon Block under Bongaon Sub-Division, under Barasat Division P.H.E.Dte. (Part-A) | 344/Bon | 07/07/2022 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 100 | 1
1572 | NORTH 24 PARGANAS | Barasat Division | Purana Bongaon Piped water supply scheme , SM/13896 | New | Survey, Design, Drawing & DPR preparation for new PWSS at Puratan Bongaon water supply scheme in the Bongaon Block under Bongaon Sub-Division, under Barasat Division P.H.E.Dte. (Part-B) | 345/Bon | 07/07/2022 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.16 | 2.16 | 100 | 1
1573 | NORTH 24 PARGANAS | Barasat Division | Purana Bongaon Piped water supply scheme , SM/13896 | New | Material Requisition To Resource Division | 1863/BD | 23/06/2023 | 0 | Resource Division | 14.21 | 0 | 0 | 0
1574 | NORTH 24 PARGANAS | Barasat Division | Purana Bongaon Piped water supply scheme , SM/13896 | New | Formal work order for Construction of 350 cum. capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile, pile cap & Soil Investigation and laying of Rising Main, Distribution Main with Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Purana Bongaon Water Supply Scheme under Bongaon Sub-Division, PHE Dte. (New Scheme). | 2033/BD | 13/07/2023 | 366 | M/S B.K.ENTERPRISE. | 431.33 | 218.89 | 50.75 | 55
1575 | NORTH 24 PARGANAS | Eastern Mechanical | Purana Bongaon Piped water supply scheme , SM/13896 | New | New service connection at P.H.No- I of Puraton Bongaon water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). | BP-362-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.89 | 0 | 0 | 0
1576 | NORTH 24 PARGANAS | Barasat Division | Purana Bongaon Piped water supply scheme , SM/13896 | New | Acceptance cum work order for Construction of Boundary wall, Approach Road and Land development at Head Work site of Purana Bongaon Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. 2nd Call. | 228/BD | 20/01/2025 | 300 | SARKAR ENTERPRISE & CO. | 33.13 | 0 | 0 | 50
1577 | NORTH 24 PARGANAS | Barasat Division | Purana Bongaon Piped water supply scheme , SM/13896 | New | Acceptance cum work order for Sinking of 1 (one) no. new 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Purana Bongaon Piped Water Supply Scheme at H/W Site under Bongaon Sub-Division, P.H.E. Dte. | 2834/BD | 15/09/2023 | 510 | NADIA TUBEWELLS | 21.56 | 16.45 | 100 | 100
1578 | NORTH 24 PARGANAS | Barasat Division | Purana Bongaon Piped water supply scheme , SM/13896 | New | Acceptance cum work order for Construction of 5.40 mtr. X 3.60mtr. size Switch room with sanitary and water supply arrangement incl. plinth protection at Head Work site at Purana Bongaon w/s scheme Bongaon Block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | 606/BD | 23/02/2024 | 405 | KAMAL HALDER. | 5.6 | 0 | 0 | 100
1579 | NORTH 24 PARGANAS | Barasat Division | Garibpur Piped water supply scheme , SM/13897 | New | Survey, Design, Drawing & DPR preparation for new PWSS at Garibpur water supply scheme in the Bongaon Block under Bongaon Sub-Division, under Barasat Division P.H.E. Dte. | 348/Bon | 07/07/2022 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.45 | 4.45 | 100 | 1
1580 | NORTH 24 PARGANAS | Barasat Division | Garibpur Piped water supply scheme , SM/13897 | New | Material Requisition To Resource Division | 1866/BD | 23/06/2023 | 0 | Resource Division | 4.65 | 0 | 0 | 0
1581 | NORTH 24 PARGANAS | Barasat Division | Garibpur Piped water supply scheme , SM/13897 | New | Acceptance cum work order for Construction of Boundary wall, Approach Road and Land development at Head Work site of Garibpur Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 3157/BD | 14/11/2024 | 30 | AMIT KUMAR BOSE. | 34.19 | 0 | 0 | 0
1582 | NORTH 24 PARGANAS | Barasat Division | Garibpur Piped water supply scheme , SM/13897 | New | Acceptance cum work order for Sinking of 1 (one) no. new 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Garibpur Piped Water Supply Scheme at H/W Site under Bongaon Sub-Division, P.H.E. Dte. | 2832/BD | 15/09/2023 | 30 | NADIA TUBEWELLS | 21.56 | 15.59 | 100 | 100
1583 | NORTH 24 PARGANAS | Barasat Division | Garibpur Piped water supply scheme , SM/13897 | New | Acceptance cum work order for Construction of 5.40 mtr. X 3.60mtr. size Switch room with sanitary and water supply arrangement incl. plinth protection at Head Work site at Garibpur w/s scheme Bongaon Block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | 607/BD | 23/02/2024 | 307 | TAPAN GHOSH. | 5.61 | 1.49 | 20.94 | 100
1584 | NORTH 24 PARGANAS | Eastern Mechanical | Garibpur Piped water supply scheme , SM/13897 | New | New service connection at P.H.No- I of Garibpur water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). | BP-328-23-24 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.5 | 0 | 0 | 0
1585 | NORTH 24 PARGANAS | Barasat Division | Garibpur Piped water supply scheme , SM/13897 | New | Formal Work order for Construction of 100 cum. capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile, pile cap & Soil Investigation and laying of Rising Main, Distribution Main with Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Garibpur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. (New Scheme) | 2057/BD | 14/07/2023 | 731 | AMIT KUMAR BOSE. | 223.93 | 116.43 | 51.99 | 54
1586 | NORTH 24 PARGANAS | Eastern Mechanical | Garibpur Piped water supply scheme , SM/13897 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. Garibpur W/S Scheme (P/H -I) District of 24 Pgs. (N). N.I.E.T No. 29 of EE / EMD of 2022-2023 (2022_PHED_434059_36) | 6732/EMD | 28/11/2023 | 581 | A.G ENTERPRISE. | 10.11 | 0 | 0 | 90
1587 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas D , SM/13534 | Retrofitting | Formal work order for Laying of Distribution system, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works and Providing FHTC within the jurisdiction of (Zone-XXIV) under Habra-Gaighata surface based PWSS of Gaighata Block under Barasat Division, P.H.E. Dte. | 2959/BD | 29/09/2023 | 810 | M/S S.S.ENTERPRISE. (SOUTH) | 1776.28 | 113.88 | 18.33 | 33
1588 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District , SM/14541 | Retrofitting | Material Requisition To Resource Division | 1995/BD | 10/07/2023 | 0 | Resource Division | 126.15 | 0 | 0 | 0
1589 | NORTH 24 PARGANAS | Eastern Mechanical | Katakhali Piped Water Supply Scheme , SM/15826 | New | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No. I and II under Katakhali WS Scheme Block-Hasnabad New District of 24 Pgs. N | 4887/EMD | 14/08/2023 | 30 | CINZANO | 21.42 | 0 | 0 | 0
1590 | NORTH 24 PARGANAS | Barasat Division | Katakhali Piped Water Supply Scheme , SM/15826 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KATAKHALI Water Supply Scheme) in HASNABAD BLOCK under Barasat Division, PHE Dte. (PART-A) | 231/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
1591 | NORTH 24 PARGANAS | Barasat Division | Katakhali Piped Water Supply Scheme , SM/15826 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KATAKHALI Water Supply Scheme) in HASNABAD BLOCK under Barasat Division, PHE Dte. (PART-B) | 232/HSD | 02/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.01 | 4.01 | 100 | 1
1592 | NORTH 24 PARGANAS | Barasat Division | Katakhali Piped Water Supply Scheme , SM/15826 | New | Material Requisition To Resource Division | 871/BD | 22/03/2023 | 0 | Resource Division | 249.11 | 0 | 0 | 0
1593 | NORTH 24 PARGANAS | Barasat Division | Katakhali Piped Water Supply Scheme , SM/15826 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2, 3 & 4 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 cum capacity 20 mtr.staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Katakhali water supply scheme, Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte | 1729/BD | 08/06/2023 | 1028 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 389.24 | 273.03 | 70.14 | 100
1594 | NORTH 24 PARGANAS | Barasat Division | Katakhali Piped Water Supply Scheme , SM/15826 | New | Formal work order for Additional Laying of DI Rising main & UPVC distribution pipe line, protection works & other allied works within Katakhali w/s scheme, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | 2738/BD | 20/09/2024 | 240 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 211.44 | 56.21 | 26.58 | 75
1595 | NORTH 24 PARGANAS | Eastern Mechanical | Katakhali Piped Water Supply Scheme , SM/15826 | New | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No. III under Katakhali WS Scheme Block-Hasnabad New District of 24 Pgs. North | 4875/EMD | 14/08/2023 | 30 | GANAPATI ENTERPRISE | 10.61 | 0 | 0 | 90
1596 | NORTH 24 PARGANAS | Barasat Division | Katakhali Piped Water Supply Scheme , SM/15826 | New | Acceptance cum work order for Construction of boundary wall with column structure at PH No-- 2, 3 & 4 within Katakhali w/s scheme, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | 1028/BD | 28/03/2025 | 90 | R B ENTERPRISE | 25.44 | 0 | 0 | 0
1597 | NORTH 24 PARGANAS | Barasat Division | Katakhali Piped Water Supply Scheme , SM/15826 | New | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1,2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Katakhali w/s scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 3371/BD | 02/12/2024 | 90 | SHIBU BISWAS. | 77.65 | 0 | 0 | 100
1598 | NORTH 24 PARGANAS | Barasat Division | Kusangra Piped Water Supply Scheme , SM/15832 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KUSANGRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 284/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 0
1599 | NORTH 24 PARGANAS | Barasat Division | Kusangra Piped Water Supply Scheme , SM/15832 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KUSANGRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | 287/HSD | 10/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.44 | 3.44 | 100 | 0
1600 | NORTH 24 PARGANAS | Barasat Division | Kusangra Piped Water Supply Scheme , SM/15832 | New | Material Requisition To Resource Division | 893/BD | 22/03/2023 | 0 | Resource Division | 45.01 | 0 | 0 | 0
1601 | NORTH 24 PARGANAS | Barasat Division | Kusangra Piped Water Supply Scheme , SM/15832 | New | Material Requisition To Resource Division | 3477/BD | 10/12/2024 | 0 | Resource Division | 25.32 | 0 | 0 | 0
1602 | NORTH 24 PARGANAS | Eastern Mechanical | Kusangra Piped Water Supply Scheme , SM/15832 | New | Quotation for Service Connection Charges for PH- II under Kusangra W/S Scheme in the district of North 24 Pgs. | BP-369-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.5 | 0 | 0 | 0
1603 | NORTH 24 PARGANAS | Eastern Mechanical | Kusangra Piped Water Supply Scheme , SM/15832 | New | Supplementary Quotation for Location Changes for PH- III under Kusangra W/S Scheme in the district of North 24 Pgs. | BP-368-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.99 | 0 | 0 | 0
1604 | NORTH 24 PARGANAS | Eastern Mechanical | Kusangra Piped Water Supply Scheme , SM/15832 | New | New Service Connection at PH-III under Kusangra W/S Scheme. | BP-261-23-24 | 02/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.6 | 0 | 0 | 0
1605 | NORTH 24 PARGANAS | Barasat Division | Kusangra Piped Water Supply Scheme , SM/15832 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile, Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap within Kusangra W/S Scheme, Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | 2703/BD | 04/09/2023 | 1096 | M/S PROGATI ENTERPRISE. | 439.52 | 167.09 | 38.02 | 20
1606 | NORTH 24 PARGANAS | Barasat Division | Kusangra Piped Water Supply Scheme , SM/15832 | New | Acceptance cum work order for Construction of RCC culvert, cut-off wall, approach road and other allied works at Over Head Reservoir site (HW site) for Kusangra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 676/BD | 01/03/2024 | 280 | M/S GHOSH CONSTRUCTION. | 8.58 | 7.78 | 90.6 | 90
1607 | NORTH 24 PARGANAS | Barasat Division | Kusangra Piped Water Supply Scheme , SM/15832 | New | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Ph No- 1, 2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Kusangra w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 632/BD | 28/02/2025 | 60 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 77.49 | 0 | 0 | 0
1608 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chaumuha Water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08729 | Retrofitting | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Chowmuha & its adjoining mouza water supply scheme in Barasat -II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | 1699/B.Ar.D | 30/09/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.38 | 3.35 | 50 | 1
1609 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chaumuha Water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08729 | Retrofitting | Providing Functional House Hod Connection and Allied workas at Dhokra and Khamar Nowabad Mouzas of Barasat II Block from Chaumuha & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | 1724/B.Ar.D. | 01/10/2021 | 90 | BALAJEE ENTERPRISES | 72.05 | 71.9 | 50 | 1
1610 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chaumuha Water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08729 | Retrofitting | Emergent protection of UPVC distribution pipe line at Choumuh more of Choumah W/S scheme at Barasat II under Barasat Arsenic Division, P.H.E. Dte. (Length - 70 mtr. Approx) | 1830/B.Ar.D | 01/11/2021 | 30 | IDEAL CONSTRUCTION | 4.79 | 4.79 | 100 | 1
1611 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chaumuha Water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08729 | Retrofitting | Emergent protection of UPVC distribution pipe line near dhokra (In between Node 44-45) of Chaumuha W/S scheme related to the work FHTCat Barasat - II under Barasat Arsenic Division, P.H.E. Dte. (Approx. Length = 70 mtr). | 363/B.Ar.D | 03/03/2022 | 15 | AT CONSTRUCTION | 4.79 | 4.79 | 50 | 1
1612 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chaumuha Water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08729 | Retrofitting | Repairing & Renovation of damaged Ladder of OHR & Allied works of Chowmuha Water Supply Scheme under Barasat -II block under Barasat Arsenic Division, P.H.E. Dte. | 338/B.Ar.D | 28/02/2022 | 15 | BALAJEE ENTERPRISES | 4.64 | 4.62 | 50 | 1
1613 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chaumuha Water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08729 | Retrofitting | Balance portion work of repairing and renovation of 02 (two) nos pump house and 01 (one) no I.E.P room and allied works at the site of Chowma W/S Scheme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | 468/B.Ar.D | 16/03/2022 | 15 | SANTU GHOSH | 4.78 | 4.77 | 50 | 1
1614 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chaumuha Water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08729 | Retrofitting | Emergent protection work of UPVC distribution pipe line near Chaumuha Chotopol (between Node 2-21) releted to the work of FHTC" of Chaumuha W/S scheme at Barasat - II under JALSWAPNA Programme under Barasat Arsenic Division, P.H.E. Dte. (Approx Lenth 70 mtr) | 2234/B.Ar.D | 28/12/2021 | 30 | A. K. DUTTA & CO. | 4.79 | 0 | 0 | 0
1615 | NORTH 24 PARGANAS | Eastern Mechanical | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Minakhan, Hingalganj and Amdanga Blocks in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. , SM/15764 | Solarisation | Solarisation of WBSEDCL Energised Electrical installation including net metering at different Pipe Water Supply Scheme at Minkhan, Hingalganj & Amdanga Blocks in North 24 Parganas District under E.M.D. P.H.E. Dte. | 6455/EMD | 02/11/2023 | 182 | A.K. INDUSTRIES | 408.07 | 0 | 0 | 0
1616 | NORTH 24 PARGANAS | Eastern Mechanical | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Basirhat- II Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. , SM/15761 | Solarisation | Solarisation of WBSEDCL Energised Electrical installation including net metering at different Pipe Water Supply Scheme at Basirhat- II Block in North 24 Parganas District under E.M.D. P.H.E. Dte. | 6357/EMD | 16/10/2023 | 183 | BINGAS ELECTRICAL ELECTRONICS & SOLAR SYSTEM | 287.12 | 0 | 0 | 0
1617 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Parmadan Water Supply Scheme in Bagdah Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, P.H.E. Dte. , SM/10608 | Augmentation | Material Requisition To Resource Division | 878/NWSD-I | 22/07/2022 | 0 | Resource Division | 4.08 | 0 | 0 | 0
1618 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Parmadan Water Supply Scheme in Bagdah Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, P.H.E. Dte. , SM/10608 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep) under Parmadan W/S Scheme District of 24 Pgs. (N). WBPHED/EE/EMD/NIeT-27 of 2023-24 | 4737../EMD | 07/08/2023 | 30 | BISALAXMI ENTERPRISE | 26.49 | 15.46 | 58.37 | 60
1619 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Parmadan Water Supply Scheme in Bagdah Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, P.H.E. Dte. , SM/10608 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House Hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC , Schedule 80/20 mm OD HDPE (PE 100, PN16) pipe with all necessary works within command area of PARMADAN Water Supply Scheme under North 24 Parganas Water Supply Division-I, PHE Dte. | 868/NWSD-I | 21/07/2022 | 90 | A.K.C. SUPPLY & CONSTRUCTION | 149.1 | 148.97 | 100 | 85
1620 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Parmadan Water Supply Scheme in Bagdah Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, P.H.E. Dte. , SM/10608 | Augmentation | Repair and renovation works of 250 m3 RCC Elevated Reservoir, Boundary Wall, Pump House, Service roads etc. at Head Works Site and other tube well Sites under Parmadan Zone-I Water Supply scheme in Bagdah Block under North 24 Parganas water Supply Division-I, PHE Dte. | 236/NWSD-I | 02/03/2023 | 60 | DEBA PRASAD MONDAL | 42.93 | 33.03 | 100 | 100
1621 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Parmadan Water Supply Scheme in Bagdah Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, P.H.E. Dte. , SM/10608 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1430/NWSD-I | 18/09/2024 | 7 | BIBHAS PAL | 5.27 | 0.53 | 50 | 100
1622 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Parmadan Water Supply Scheme in Bagdah Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, P.H.E. Dte. , SM/10608 | Augmentation | Material Requisition To Resource Division | 1315/NWSD-I | 30/08/2024 | 0 | Resource Division | 1.23 | 0 | 0 | 0
1623 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Parmadan Water Supply Scheme in Bagdah Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, P.H.E. Dte. , SM/10608 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1431/NWSD-I | 18/09/2024 | 7 | IMAGIN | 4.59 | 0 | 0 | 95
1624 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC , SM/11600 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Koniara water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 552/ BON | 03/11/2021 | 21 | K. ENTERPRISE | 2.52 | 2.49 | 100 | 1
1625 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC , SM/11600 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Koniara Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 137/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.73 | 3.73 | 100 | 1
1626 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC , SM/11600 | Augmentation | Material Requisition To Resource Division | 3656/BD | 13/12/2022 | 0 | Resource Division | 12.62 | 0 | 0 | 0
1627 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC , SM/11600 | Augmentation | Material Requisition To Resource Division | 3693/BD | 14/12/2022 | 0 | Resource Division | 30.39 | 0 | 0 | 0
1628 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC , SM/11600 | Augmentation | Continuation order for one motor launch (M.V. JOYMAKALI) on daily hire basis for use of Hasnabad Sub-Division, P.H.E. Dte. Period : 01.09.22 to 28.02.23=181 days. | 1484/HSD | 29/08/2022 | 183 | SUSMITA MANDAL. | 2.7 | 9.29 | 100 | 100
1629 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC , SM/11600 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Kaniara Water Supply Scheme, Bagdah Block under Bongaon Sub-Division, PHE Dte. | 3764/BD | 20/12/2022 | 90 | SUPER SKILL. | 341.46 | 338.45 | 100 | 100
1630 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC , SM/11600 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kaniara water supply scheme at Head Work Site under Bongaon Sub-Division P.H.E.Dte. | 2689/BD | 04/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.12 | 13.83 | 100 | 100
1631 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC , SM/11600 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kaniara water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | 2687/BD | 04/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.12 | 13.64 | 100 | 100
1632 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC , SM/11600 | Augmentation | Acceptance cum work order for Renovation of 32 Cum/hr of capacity AIRP and allied works at Head work site for Augmentation of Koniara water Supply Scheme under Bongaon Sub-Division, Barasat Division P.H.E. Dte. | 14/BD | 02/01/2024 | 60 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 36.22 | 28.24 | 100 | 100
1633 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC , SM/11600 | Augmentation | Acceptance cum work order for Additional laying of UPVC pipe line under Augmentation of Koniara Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1385/BD | 30/04/2025 | 60 | UPWARDS ENGINEERING PRIVATE LIMITED. | 11.42 | 0 | 0 | 0
1634 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC , SM/11600 | Augmentation | Acceptance cum work order for Additional laying of UPVC pipe line under Augmentation of Koniara Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (Part - B) | 2860/BD | 14/08/2025 | 45 | HAQUE ENTERPRISE | 6.12 | 0 | 0 | 0
1635 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC , SM/11600 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram with laying of UPVC pipe line and Repairing and Renovation of AIRP Compressor Room under Augmentation of Koniara Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1403/Bon | 28/11/2024 | 120 | HAQUE ENTERPRISE | 4.83 | 0 | 0 | 100
1636 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Bahira & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) , SM/08178 | Retrofitting | Providing Functional House Hold Connection and Allied workas at Bahira and BhagyantpurMouzas of Barasat II Block from Bahira & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | 467/B.Ar.D. | 19/02/2021 | 90 | M/S JHARNA ENTERPRISE | 80.88 | 160.1 | 197.95 | 1
1637 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Bahira & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) , SM/08178 | Retrofitting | Construction of pathway and allied works at the site of Bahira W/S Scheme under Jal Swapna Programme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | 277/B.Ar.D | 21/02/2022 | 20 | S. S. CONSULTANCY & CONSTRUCTION | 4.59 | 4.58 | 99.84 | 1
1638 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Bahira & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) , SM/08178 | Retrofitting | Repairing and Renovation of 02 (two) nos pump house and 01 (one) No I.E.P room, and allied works at the site of Bahira W/S Scheme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | 1829/B.Ar.D | 01/11/2021 | 30 | S. S. CONSULTANCY & CONSTRUCTION | 4.79 | 4.79 | 99.93 | 70
1639 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Bahira & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) , SM/08178 | Retrofitting | Specials Repairing of Rising Main & Interconnection of 168.3 mm dia Ms pipe 250mm dia & 150 mm dia DI pipe at Bahira H/W Site under Bahira W/S Scheme at Barasat-II block under Barasat Arsenic Division, PHE Dte. under JAL SWAPNA Programme. | 339/B.Ar.D | 28/02/2022 | 15 | BANI ENGINEERING CO | 4.6 | 0 | 0 | 0
1640 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11662 | Augmentation | Laying of UPVC Pipe at damaged portion from npde 33-34, 33a-33,44a-47-470 of Jeliakhali Paschim Khanda W/S scheme of Sandeshkhali Block II for providing FHTC under Jalaswapna Programme under Barasat Arsenic Division, PHE Dte. | 2253/B.Ar.D. | 30/12/2021 | 45 | BALAJEE ENTERPRISES | 28.09 | 28.09 | 100 | 1
1641 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11662 | Augmentation | Preparation of Augmentation DPR for Jeliakhali Paschim Khanda Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | 1840/B.Ar.D | 19/09/2022 | 20 | RISHAN ENGINEERING CONSULTANCY | 0.98 | 0.98 | 100 | 1
1642 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11662 | Augmentation | Material Requisition To Resource Division | 2289/B.Ar.D | 02/12/2022 | 0 | Resource Division | 10.97 | 0 | 0 | 0
1643 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11662 | Augmentation | Repair & Renovation of Iron Elementation Plant of 58 M3 including Media Change of Jeliakhali Paschim Khanda Water Supply Scheme under Sandeshkhali-II Block Under Barasat Arsenic Division, PHE Dte. | 476/B.Ar.D. | 27/02/2023 | 30 | IDEAL CONSTRUCTION | 4.83 | 4.53 | 93.85 | 100
1644 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11662 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir & other existing civil component of Capacity 250 Cu.m. at Jeliakhali Paschim Khanda W/S Scheme under Sandeshkhali-II Block under Barasat Arsenic Division, PHE Dte. (SM/11662) | 2471/B.Ar.D. | 21/12/2022 | 60 | MAHALAXMI CONSTRUCTION | 15.65 | 14.36 | 100 | 1
1645 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11662 | Augmentation | Bullah piling for Protection of UPVC distribution pipe line at Jeliakhali Paschim Khanda Jhil para of Jeliakhali Paschim khanda W/S Scheme under Sandeshkhali- II Block under Barasat Arsenic Division, P.H.E. Dte. | 474/B.Ar.D. | 27/02/2023 | 25 | CHAKRABORTY SUPPLIERS & CONSTRUCTION | 9.87 | 9.85 | 100 | 1
1646 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11662 | Augmentation | Laying of distribution System including specials all complete at Pipre khali, 52 Para, Jeliakhali 6 no, adibashi Para for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at JELIAKHALI PASCHIM KHANDA under Sandeshkhali - II Block under Barasat Arsenic Division, PHE Dte. | 919/B.Ar.D. | 11/04/2023 | 45 | TRISHA ENTERPRISE AND CO. | 44.17 | 44.02 | 100 | 95
1647 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11662 | Augmentation | Bullah piling for protection of UPVC distribution pipe line at Jeliakhali Paschim Khanda 3 no Para of Jeliakhali Paschim Khanda W/S Scheme under Sandeshkhali- II Block under Barasat Arsenic Division, P.H.E. Dte. | 1167/B.Ar.D. | 16/05/2023 | 30 | ABDUL ALIM MONDAL | 7.52 | 7.43 | 100 | 100
1648 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11662 | Augmentation | Supply, delivery and installation of submersible pump moter set including other allied works at P H No. I & II of Jeliakhali Purbakhand water supply scheme under Eastern Mechanical Sub Division-I, PHE Dte. Dist- 24 Pgs(N) | 1501/EMSD-I | 21/06/2023 | 15 | M/S DILIP MITRA | 3.19 | 3 | 100 | 100
1649 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11662 | Augmentation | Material Requisition To Resource Division | 2109/B.Ar.D. | 02/11/2022 | 0 | Resource Division | 2.41 | 0 | 0 | 0
1650 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11662 | Augmentation | Laying of Pipeine for Pump Connection and Construction of 4.88 mtr. x 3.60 mtr. size new Pump House with at Jekiakhali Paschimkhanda Water Supply Scheme under Sandeshkhali-II Block under Barasat Arsenic Division, PHE Dte. | 1850/B.Ar.D. | 21/11/2024 | 45 | AMIT KUMAR BOSE | 10.45 | 0 | 0 | 0
1651 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11662 | Augmentation | Sal-Bullah Pilling for pipe protection work at Jeliakhali Paschim Khanda under Sandeshkhali-II Block Under Barasat Arsenic Division, PHE Dte. | 992/B.Ar.D. | 19/06/2024 | 45 | OM ENTERPRISE | 14.47 | 14.44 | 100 | 100
1652 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11662 | Augmentation | Continuation Order for "Hiring of Power Driven Mini Launch of office of the Executive Engineer, Barasat Arsenic Division, P.H.E. Dte." for the period of 91 days (i.e. from 01.04.2024 to 30.06.2024)''. | 679/B.Ar.D | 28/03/2024 | 91 | RANJIT KUMAR MANDAL | 1.04 | 1.76 | 100 | 100
1653 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11662 | Augmentation | Hiring of one (1) no. Diesel / Petrol operated motor cab ( Car No.- WB25M 3675) with driver for official use of Assistant Engineer (HQ-I) & Assistant Engineer (HQ-II), B.Ar.D, PHE Dte. for different works under JJM Schemes with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 14.08.2024 to 28.02.2025. | 1330/B.Ar.D | 14/08/2024 | 199 | SUSMITA MANDAL | 0.95 | 2.35 | 248.22 | 0
1654 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11662 | Augmentation | Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No. - WB23F - 6448) with driver for official use for Executive Engineer, Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 01.07.2024 to 31.12.2024. | 1022/B.Ar.D | 21/06/2024 | 184 | RANJIT KUMAR MANDAL | 0.87 | 2.22 | 253.47 | 0
1655 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11662 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (Car No. WB23F - 6448) with driver for official use for Executive Engineer, Barasat Arsenic Division PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 01.01.2025 to 28.02.2025. | 2050/B.Ar.D | 30/12/2024 | 59 | RANJIT KUMAR MANDAL | 0.28 | 0.72 | 255.92 | 0
1656 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JELIAKHALI PASCHIM KHANDA to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11662 | Augmentation | Laying of distribution System, Laying of Rising Main including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at JELIAKHALI PASCHIM KHANDA under Sandeshkhali - II Block under Barasat Arsenic Division, PHE Dte. | 1569/B.Ar.D. | 25/08/2022 | 899 | PIKASU BOSE | 193.42 | 155.74 | 98.23 | 95
1657 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11864 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-II/B (Malikapur) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 331/NWSD-I | 24/03/2022 | 31 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.29 | 3.23 | 100 | 1
1658 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11864 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II, B (Malikapur) in Barasat-I Block of North 24 Parganas District. | 4029/ED | 17/10/2023 | 183 | A.G. ENTERPRISE | 55.55 | 0 | 0 | 0
1659 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11864 | Augmentation | Material Requisition To Resource Division | 480/NWSD-I | 26/04/2023 | 0 | Resource Division | 31.12 | 0 | 0 | 0
1660 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11864 | Augmentation | Payment to WBSEDCL of Malikapur |  | 27/06/2023 | 0 | WBSEDCL | 1.66 | 0 | 0 | 0
1661 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11864 | Augmentation | Quotation for New Connection at Malikapur OHR site. | 609 | 05/12/2024 | 0 | WBSEDCL | 3.95 | 0 | 0 | 0
1662 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11864 | Augmentation | Shifting of HTOH & LTOH line from PHE Land. Application ID: 100000118529 Application Date: 09.09.2024 Quotation Date: 09.09.2024 Quotation due date: 08.12.2024 | 204/PFMS/24-25 | 19/09/2024 | 0 | WBSEDCL | 1.9 | 0 | 0 | 0
1663 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11864 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 158.9 | 24.75 | 2
1664 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC , SM/12278 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Sahebkhali water supply scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 88/BD | 11/01/2023 | 90 | M/S NIRMAN CONSTRUCTION. | 354.45 | 323.2 | 91.18 | 1
1665 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC , SM/12278 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. VI (New) under Sahebkhali W/S Scheme District of 24 Pgs. (N) | 4940/EMD | 18/08/2023 | 30 | KUNDU ELECTRICAL ENTERPRISE | 13.82 | 0 | 0 | 0
1666 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC , SM/12278 | Augmentation | Material Requisition To Resource Division | 920/BD | 22/03/2023 | 0 | Resource Division | 137.48 | 0 | 0 | 0
1667 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC , SM/12278 | Augmentation | Material Requisition To Resource Division | 4175/BD | 30/10/2023 | 0 | Resource Division | 18.56 | 0 | 0 | 0
1668 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC , SM/12278 | Augmentation | Formal work order for construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Sahebkhali water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | 4200/BD | 31/10/2023 | 365 | M/S RAJPATH CONSTRUCTION. | 150.42 | 0 | 0 | 0
1669 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC , SM/12278 | Augmentation | Acceptance cum work order for Sinking of 1 Nos. 330.00 mtr. Deep 100 X 50 mm. dia. Trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe & strainers at T/W site-1 for Sahebkhali w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 629/HSD | 12/06/2024 | 10 | DEB PRASAD GHOSH. | 3.5 | 0 | 0 | 0
1670 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC , SM/12278 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No -I with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Sahebkhali w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 2900/BD | 03/10/2024 | 30 | SUBHAJIT SAHA | 31.68 | 0 | 0 | 0
1671 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC , SM/12278 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Replacement) under Sahebkhali W/S Scheme District of 24 Pgs. (N) | 4938/MD | 18/08/2023 | 30 | KARTICK BAL | 41.4 | 36.57 | 100 | 70
1672 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC , SM/12278 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Sahebkhali w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 526/BD | 20/02/2024 | 45 | UTPAL CONSTRUCTION & CO. | 61.24 | 48.73 | 100 | 100
1673 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC , SM/12278 | Augmentation | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3, 4 & 5 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Sahebkhali w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 915/BD | 15/03/2024 | 60 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 94.87 | 71.18 | 100 | 100
1674 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC , SM/12278 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.IV and V (Replacement) under Sahebkhali W/S Scheme District of 24 Pgs. (N) | 4939/EMD | 18/08/2023 | 622 | ASHOKE ADHIKARY | 27.57 | 0 | 0 | 100
1675 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC , SM/12278 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) for Augmentation of Sahebkhali w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 301/BD | 28/01/2025 | 75 | M/S S.HAQUE & CO. | 12.36 | 0 | 0 | 0
1676 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC , SM/12278 | Augmentation | Formal work order for Additional laying of UPVC distribution pipe line including protection work for DI pipe at N/H/O Provas Halder towards Suvomay Mondal house & other allied work for UPVC pipe laying at different places in connection with Augmentation of Sahebkhali w/s scheme (Z-I), Hingalganj block within Hasnabad Sub-Division under Barasat Division P.H.E. Dte. | 1797/BD | 30/05/2025 | 60 | SAHA CONSTRUCTION & CO | 139.89 | 0 | 0 | 0
1677 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC , SM/12278 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Sahebkhali water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 1304/BD | 26/04/2023 | 777 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 554.49 | 492.32 | 88.8 | 90
1678 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC , SM/12278 | Augmentation | Formal work order for Construction of 250 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Sahebkhali water supply scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | 4110/BD | 17/10/2023 | 791 | ROY CHOWDHURY CONSTRUCTION. | 140.37 | 91.08 | 62.75 | 75
1679 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC , SM/12278 | Augmentation | Formal work order for Laying of DI rising main in connection with Augmentation of Sahebkhali water supply scheme (Z-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 2098/BD | 26/07/2024 | 90 | ABDUL ALIM MONDAL. | 104.06 | 26.65 | 20.94 | 100
1680 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC , SM/12278 | Augmentation | Acceptance cum work order for Land development at Head Work Site in connection with Augmentation of Sahebkhali w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 1609/BD | 19/05/2025 | 15 | SARKAR ENTERPRISE & CO. | 9.64 | 0 | 0 | 100
1681 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC , SM/12278 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Sahebkhali water supply scheme (Z-I) , Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 150/HSD | 27/01/2025 | 10 | M/S DATTA ENTERPRISE. | 0.95 | 0 | 0 | 100
1682 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Paltadanga & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) , SM/08176 | Retrofitting | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Paltadanga & its adjoining mouza water supply scheme in Barasat - II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | 1701/B.Ar.D | 30/09/2021 | 15 | UMWELT ENGINEER PVT. LTD. | 4.7 | 4.7 | 50 | 1
1683 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Paltadanga & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) , SM/08176 | Retrofitting | Providing Functional House Hold Connection and Allied workas at Kismat sonatikari, Sonatikari, Dugdia and Bharparbara Malik Mouzas of Barasat II Block from Paltadanga & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | 465/B.Ar.D. | 19/02/2021 | 90 | BALAJEE ENTERPRISES | 60.68 | 118.18 | 97.63 | 1
1684 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Paltadanga & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) , SM/08176 | Retrofitting | Repairing and Renovation of 02 (two) nos pump house and 01 (one) No I.E.P room, and allied works at the site of Paltadanga W/S Scheme under Jal Swapna Programme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | 2218/B.Ar.D | 24/12/2021 | 30 | KUNDU CONSTRUCTION CO. | 4.79 | 4.78 | 50 | 1
1685 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Puturia & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) , SM/08179 | Retrofitting | Withdrawing and Laying of UPVC Pipe Line in damaged portion of distribution network and protection work of UPVC line at Puturia -Kharbil of Puturia Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | 1833/B.Ar.D | 01/11/2021 | 30 | M/S. BAKSHI ENTERPRISE | 4.78 | 4.73 | 50 | 1
1686 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Puturia & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) , SM/08179 | Retrofitting | Emergent protection of UPVC distribution pipe line near 2nd Pump House at PUTURIA W/S of Barasat II block under retrofitting of Puturia W/S for providing FHTC (Phase-I) under Barasat Arsenic Division, P.H.E. Dte. | 268/B.Ar.D | 18/02/2022 | 21 | BAKSHI ENTERPRISE | 4.47 | 4.48 | 50 | 1
1687 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Puturia & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) , SM/08179 | Retrofitting | Providing Functional House Hold Connection and Allied workas at puturia and Tona Mouzas of Barasat II Block from Puturia & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | 468/B.Ar.D. | 19/02/2021 | 90 | SAKTI ENTERPRISE | 75.31 | 38.28 | 50.82 | 100
1688 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Puturia & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) , SM/08179 | Retrofitting | Laying UPVC Pipeline for Providing Functional Household Tap Connection of Command area at Puturia Ground Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division PHE, Dte. (SM/08179) (Sl No. 4) | 2124/B.Ar.D. | 04/11/2022 | 15 | SAKTI ENTERPRISE | 2.63 | 2.63 | 100 | 1
1689 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARAKPUR Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07602 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARAKPUR Water Supply Scheme at Bongaon Block under North 24 Parganas Water Supply Division-I, PHE Dte. (Phase-I) | 67/NWSD-I | 20/01/2021 | 90 | M/S. TARAK CHANDRA PAUL | 91.43 | 155.83 | 85.81 | 1
1690 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARAKPUR Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07602 | Retrofitting | Hiring of Diesel Ambassador Car / Cab having licensed carriage contract permit from Regional Transport Authority for the office of the Executive Engineer, North 24- Pgs. W/S Division-I, P.H.E. Dte. at Barrackpore under the control of Assistant Engineer (HQ-II), North 24-Pgs. W/S Division-I, P.H.E. Dte. for 1 (One) year w.e.f. 01.1.2022. | 1088/NWSD-I | 16/12/2021 | 365 | BADAL GHOSH | 1.72 | 0 | 0 | 50
1691 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARAKPUR Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07602 | Retrofitting | Hiring of Diesel Ambassador Car / Cab having licensed carriage contract permit from Regional Transport Authority for the office of the Executive Engineer, North 24- Pgs. W/S Division-I, P.H.E. Dte. at Barrackpore under the control of Assistant Engineer (HQ-II), North 24-Pgs. W/S Division-I, P.H.E. Dte. for 1 (One) year w.e.f. 01.1.2022. | 1088/NWSD- I | 16/12/2021 | 1 | BADAL GHOSH | 1.72 | 0.39 | 54.36 | 100
1692 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARAKPUR Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07602 | Retrofitting | Hiring of Diesel Ambassador Car / Cab having licensed carriage contract permit from Regional Transport Authority for the office of the Executive Engineer, North 24- Pgs. W/S Division-I, P.H.E. Dte. at Barrackpore under the control of Assistant Engineer (HQ-II), North 24-Pgs. W/S Division-I, P.H.E. Dte. for 181 (One Hundred Eighty One) days w.e.f. 01.1.2023 to 30.06.2023. | 1451/NWSD- I | 22/12/2022 | 181 | BADAL GHOSH | 0.85 | 1.83 | 100 | 51
1693 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BANGANGRAM ZONE-II Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07609 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BANGANGRAM ZONE-II Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (Phase-I) | 75/NWSD-I | 20/01/2021 | 60 | GHOSH CONSTRUCTION | 52.31 | 91.54 | 100 | 1
1694 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1861/HSD.. | 17/11/2021 | 15 | M/S NIRMAN CONSTRUCTION. | 2.37 | 2.37 | 50 | 0
1695 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1861/HSD. | 17/11/2021 | 15 | M/S NIRMAN CONSTRUCTION. | 2.37 | 0 | 0 | 1
1696 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Acceptance cum work order for Construction of approach road with cement concrete at PH No.-3 within Joygopalpur w/s scheme, Sandehkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 792/HSD | 13/05/2022 | 10 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 0.8 | 0 | 0 | 1
1697 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Acceptance cum work order for Emergent supply, fitting & fixing of Main gate and other allied works at OHR site within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 617/HSD | 07/04/2022 | 15 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 0.6 | 0.6 | 100 | 1
1698 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Acceptance cum work order for Restoration of existing concrete road for damaged portion due to movement of heavy vehicles during construction of OHR at Bermajur H.W. site within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. (Part-A) | 1992/HSD | 02/12/2021 | 15 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.4 | 4.39 | 99.79 | 1
1699 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Acceptance cum work order for Protection of UPVC distribution pipeline by UC bullah pile at different places for protection of different dia UPVC distribution pipe line within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1865/HSD | 17/11/2021 | 15 | M/S NIRMAN CONSTRUCTION. | 4.79 | 4.77 | 99.68 | 1
1700 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Acceptance cum work order for Restoration of existing concrete road for damaged portion due to movement of heavy vehicles during construction of OHR at Bermajur H.W. site within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. (Part-B) | 1993/HSD | 02/12/2021 | 15 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.78 | 4.78 | 100 | 1
1701 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Bhabanipur (Zone-I & Zone-II) Water Supply Scheme under Barasat Division, PHE Dte. | 2156/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.76 | 4.76 | 100 | 1
1702 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Malancha Zone I Water Supply Scheme under Barasat Division, PHE Dte. | 2151/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.43 | 4.4 | 100 | 1
1703 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Malancha Zone II Water Supply Scheme under Barasat Division, PHE Dte. | 2152/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.77 | 3.75 | 100 | 1
1704 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia. UPVC distribution pipeline for providing FHTC by UC bullah pile at different places within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 470/HSD | 10/03/2022 | 10 | ARBINA ENTERPRISE. | 3.89 | 3.88 | 50 | 1
1705 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Acceptance cum work order for Protection works for newly laid different dia.UPVC/DI pipe line at different places in Bermajur Taltala Para, Molla para, Hatkhola Para, Dangal para, Kalyani para, Kachari para & Pol para within Bermajur W/S/Scheme Sandeshkhali-II Block under Hasnabad Sub-Division P.H.E.Dte. | 1465/BD. | 13/08/2021 | 30 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 32.29 | 6.09 | 100 | 1
1706 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Acceptance cum work order for Protection works for protection of UPVC distribution pipe line at N/H/O Laxmikanta Singh within Bermajur w/s Scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 1243/HSD | 20/07/2022 | 15 | M/S ANUBHAB CONSTRUCTION. | 0.56 | 0.57 | 50 | 1
1707 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Acceptance cum work order for Emergent restoration of existing pilling works to sustain the protection of UPVC distribution pipe line at different places within Bermajur w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 417/HSD | 04/03/2022 | 10 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 3.87 | 3.89 | 100 | 1
1708 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Acceptance cum work order for Connection of OHR from rising main and other allied works at Head Work site within Bermajur w/s scheme, Sandeshkhali-II Block under Hasnabad Sub- Division P.H.E. Dte. | 1152/HSD | 12/07/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 4.11 | 4.1 | 50 | 1
1709 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Acceptance cum work order for Additional works for approach road with cement concrete and other allied works at Head Work site within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1153/HSD | 12/07/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 1.55 | 1.55 | 50 | 1
1710 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the Bermajur mouza into Swajal Gram i/c laying of UPVC/PVC pipe & supply of necessary fittings within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 2920/BD | 26/09/2022 | 30 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 24.18 | 24.16 | 50 | 1
1711 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Kalitala Water Supply Scheme under Barasat Division, PHE Dte. | 2179/HSD | 28/12/2021 | 21 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 3.93 | 3.93 | 100 | 1
1712 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Acceptance cum work order for Supply of Mechanized boat on hire basis with providing driver, helper and other requirement as per terms condition and specification as per direction of the EIC under Hasnabad Sub-Division, P.H.E. Dte. Period : 01.07.2021 to 30.06.2022 = 365 days | 1112/HSD | 29/06/2021 | 365 | RANJIT KUMAR MANDAL. | 3.15 | 1.05 | 100 | 1
1713 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Material Requisition To Resource Division | 677/BD | 01/03/2023 | 0 | Resource Division | 61.6 | 0 | 0 | 0
1714 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. , SM/07610 | Retrofitting | Material Requisition To Resource Division | 1820/BD | 19/06/2023 | 0 | Resource Division | 20.33 | 0 | 0 | 0
1715 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Akipur Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) , SM/07613 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Akipur Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase - I) | 402/BD | 10/02/2022 | 30 | SARKAR ENTERPRISE & CO. | 51.46 | 46.89 | 100 | 1
1716 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Akipur Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) , SM/07613 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for AKIPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 304/BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.02 | 2.95 | 100 | 1
1717 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Akipur Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) , SM/07613 | Retrofitting | Material Requisition To Resource Division | 2987/BD | 29/09/2022 | 0 | Resource Division | 0.01 | 0 | 0 | 0
1718 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Tildanga & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07712 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Dakshindiara, Chak Khamarpur, Shrikati, Jagannathpur and Mahespur Mouzas of Baduria Block from Tildanga Ground Water Supply Scheme under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I). | 562/B.Ar.D. | 26/02/2021 | 90 | SANJUKTA ENGINEERS | 82.47 | 101.42 | 83.46 | 1
1719 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Tildanga & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07712 | Retrofitting | Route survey, distribution design & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Magurati Srirampur, Tildanga & its adjoining mouza Water Supply Scheme in Baduria Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | 1445/B.Ar.D | 31/08/2021 | 15 | SIRCON ENGINEERING SERVICES | 4.06 | 4.06 | 50 | 1
1720 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Tildanga & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07712 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Asraf Ali at Srikati Sesher para under Tildanga W/S Scheme at Baduria block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | 473/B.Ar.D | 16/03/2022 | 15 | G. S. CONSTRUCTION & CO. | 4.45 | 4.44 | 50 | 1
1721 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Tildanga & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07712 | Retrofitting | Road restoration due to laying of UPVC/HDPE Pipe line for providing FHTC of Tildanga Water Supply Scheme under Baduria Block under Barasat Arsenic Division, PHE Dte. (SM/07712) (Sl No. 1) | 2086/B.Ar.D. | 28/10/2022 | 15 | BALAJEE ENTERPRISES | 3.95 | 3.94 | 100 | 1
1722 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Tildanga & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07712 | Retrofitting | Withdrawal and Relaying of 160 mm dia. HDPE rising main pipeline along with protection work and other allied works near 2nd Pump House under Tildanga W/S Scheme under Barasat Arsenic Division, PHE Dte. | 1168/B.Ar.D. | 16/05/2023 | 30 | M/S DATTA ENTERPRISE | 4.84 | 4.78 | 100 | 100
1723 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Deora Water Supply Scheme at Swarupnagar Block (Phase-I) , SM/07844 | Retrofitting | Repairing & renovation of Pump House No. - 1 & 2 of Deora W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 389/HAB | 21/07/2022 | 30 | M/S SAMIT CHANDRA DEY. | 2.09 | 2.06 | 98.39 | 0
1724 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Jeliakhali Paschim khanda water supply scheme under sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08726 | Retrofitting | Route survey, distribution design & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Jeliakhali Paschim Khanda Water Supply Scheme in Sandeshkhali - II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | 1442/B.Ar.D | 31/08/2021 | 15 | SIRCON ENGINEERING SERVICES | 4.71 | 4.03 | 50 | 1
1725 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Jeliakhali Paschim khanda water supply scheme under sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08726 | Retrofitting | Providing Functional House Hod Connection and Allied workas at 4 nos habitation of Jelia Khali Paschim Khanda Mouzas of Sandeshkhali II Block from Jeliakhali Paschim Khanda Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | 1725/B.Ar.D. | 01/10/2021 | 90 | BALAJEE ENTERPRISES | 51.57 | 51.54 | 99.94 | 85
1726 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Restoration of pipeline by Laying of diff. dia. HDPE distribution pipe line due to cyclone ¿YAAS¿ in Kalutala Mouza within Hasnabad w/s scheme, Hasnabad Block under Hasnabad Sub- Division P.H.E. Dte. | 669/HSD(Camp) | 30/06/2021 | 7 | ABDUL HAMID GAZI. | 4.45 | 4.45 | 100 | 0
1727 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Gabberia w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 654/HSD(Camp) | 30/06/2021 | 7 | PRITAM MUKHOPADHYAY. | 4.57 | 4.54 | 99.41 | 0
1728 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Restoration of pipeline by Laying of diff. dia. HDPE distribution pipe line due to cyclone YAAS in Purbachak Mouza within Hasnabad w/s scheme, Hasnabad Block under Hasnabad Sub- Division P.H.E. Dte. | 666/HSD(Camp) | 30/06/2021 | 7 | ROY CHOWDHURY CONSTRUCTION. | 4.51 | 4.51 | 100 | 0
1729 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 90mm dia UPVC pipe from N/H/O Santosh Sau to Roti Howly for the damage portion of AC/UPVC pipeline due to cyclone "YAAS" for Bhabanipur- I GP within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | 602/HSD(Camp) | 29/06/2021 | 7 | BADAL GHOSH. | 4.15 | 0 | 0 | 0
1730 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 90mm & 75mm dia UPVC pipe at different places for the damage portion of AC/UPVC pipeline due to cyclone "YAAS" for Bhabanipur-I & II GP within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | 601/HSD(Camp) | 29/06/2021 | 7 | M/S K.B.ENTERPRISE. | 3.72 | 0 | 0 | 0
1731 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Protection of UPVC distribution pipeline by UC bullah pile at different places due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 612/HSD(Camp) | 29/06/2021 | 7 | CHITTA RANJAN MONDAL. | 4.24 | 4.24 | 100 | 0
1732 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Korakati w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 649/HSD (Camp) | 30/06/2021 | 7 | MD.SALIM GAZI. | 4.53 | 4.52 | 99.8 | 0
1733 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Restoration of pipeline by Laying of diff. dia. HDPE distribution pipe line due to cyclone ¿YAAS¿ Monoharpur Mouza within Hasnabad w/s scheme, Hasnabad Block under Hasnabad Sub- Division P.H.E. Dte. | 668/HSD(Camp) | 30/06/2021 | 7 | ABDUL HAMID GAZI. | 4.47 | 4.47 | 100 | 0
1734 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 110mm dia UPVC pipe from N/H/O Balaram Mondal to Bablu Roy for the damage portion of AC/UPVC pipeline due to cyclone "YAAS" for Bhabanipur-I GP within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | 603/HSD(Camp) | 29/06/2021 | 7 | CHANCHAL ENTERPRISE & CO. | 4.41 | 4.41 | 100 | 0
1735 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Protection of UPVC distribution pipeline by UC bullah pile at N/H/O Samir Gayen & other diff. places due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-I), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 625/HSD(Camp) | 29/06/2021 | 7 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 4.24 | 4.19 | 100 | 0
1736 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Bermajur w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-A) | 634/HSD(Camp) | 29/06/2021 | 7 | LAHIRI CONSTRUCTION. | 4.38 | 4.34 | 100 | 0
1737 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Bermajur w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-B) | 635/HSD(Camp) | 29/06/2021 | 7 | PRASANTA MITRA. | 4.38 | 4.34 | 100 | 0
1738 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Emergent supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places due to cyclone 'YAAS' within Abad Kuliadanga Desalination Plant covered area under, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | 670/HSD (Camp) | 30/06/2021 | 13 | M/S RAJPATH CONSTRUCTION. | 4.49 | 4.49 | 100 | 0
1739 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 75mm dia UPVC pipe from N/H/O Palash Sardar to Sluice gate due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | 672/HSD (Camp) | 30/06/2021 | 7 | ABDUL ALIM MONDAL. | 4.94 | 4.93 | 100 | 0
1740 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Restoration of waste water pipeline by laying of new 110mm dia UPVC pipe due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 673/HSD (Camp) | 30/06/2021 | 7 | M/S DATTA ENTERPRISE. | 0.98 | 0.97 | 100 | 0
1741 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Restoration of waste water pipeline by laying of new 110mm dia UPVC pipe due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-IV), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 674/HSD (Camp) | 30/06/2021 | 7 | M/S PROGATI ENTERPRISE. | 4.75 | 4.74 | 100 | 0
1742 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Protection work of UPVC pipe line by Bamboo pilling at different places due to cyclone 'YAAS' within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | 675/HSD (Camp) | 30/06/2021 | 7 | ABDUL ALIM MONDAL. | 3.8 | 3.79 | 100 | 0
1743 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Additional Restoration of waste water pipeline by laying of new 110mm dia UPVC pipe due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-IV), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 678/HSD (Camp) | 30/06/2021 | 7 | M/S PROGATI ENTERPRISE. | 4.46 | 4.45 | 100 | 0
1744 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Restoration of different dia PVC distribution pipe line due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-13, 20 & 21), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 679/HSD (Camp) | 30/06/2021 | 7 | M/S DATTA ENTERPRISE. | 4.85 | 4.85 | 100 | 0
1745 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Restoration of different dia PVC distribution pipe line due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-27, 28 & 29), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 680/HSD (Camp) | 30/06/2021 | 7 | M/S PROGATI ENTERPRISE. | 4.87 | 4.87 | 100 | 0
1746 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 90mm dia UPVC pipe from N/H/O Asim Das to Animesh Makhal due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | 681/HSD (Camp) | 30/06/2021 | 7 | ABDUL ALIM MONDAL. | 4.87 | 4.86 | 100 | 0
1747 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 90 mm & 75mm dia UPVC distribution pipe line from N/H/O Santosh Khara to Arindam Mondal due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | 676/HSD (Camp) | 30/06/2021 | 7 | ABDUL ALIM MONDAL. | 4.83 | 4.83 | 100 | 0
1748 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Kalinagar GP from 30.05.21 to 05.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 414/HSD(Camp) | 27/05/2021 | 7 | M/S PROGATI ENTERPRISE. | 4.69 | 4.69 | 100 | 0
1749 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-I GP from 27.05.21 to 29.05.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 415/HSD(Camp) | 27/05/2021 | 3 | M/S DATTA ENTERPRISE. | 4.49 | 4.49 | 100 | 0
1750 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-I GP from 30.05.21 to 06.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 416/HSD(Camp) | 27/05/2021 | 8 | M/S PROGATI ENTERPRISE. | 4.75 | 4.75 | 100 | 0
1751 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-II GP from 30.05.21 to 06.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 418/HSD(Camp) | 27/05/2021 | 8 | M/S DATTA ENTERPRISE. | 4.86 | 4.86 | 100 | 0
1752 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sandeshkhali GP from 30.05.21 to 06.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 432/HSD(Camp) | 27/05/2021 | 8 | M/S NIRMAN CONSTRUCTION. | 4.91 | 4.91 | 100 | 0
1753 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Kalinagar GP from 27.05.21 to 29.05.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 413/HSD(Camp) | 27/05/2021 | 3 | M/S DATTA ENTERPRISE. | 4.71 | 4.71 | 100 | 0
1754 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-II GP from 27.05.21 to 29.05.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 417/HSD(Camp) | 27/05/2021 | 3 | M/S PROGATI ENTERPRISE. | 4.58 | 4.58 | 100 | 0
1755 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Hingalganj GP from 21.06.21 to 26.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 570/HSD(Camp) | 14/06/2021 | 6 | MONDAL & CO. (BASIRHAT). | 4.89 | 4.89 | 100 | 0
1756 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 11, 12, 14 from 01.06.21 to 11.06.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | 453/HSD(Camp) | 27/05/2021 | 11 | M/S RAJPATH CONSTRUCTION. | 4.76 | 4.76 | 100 | 0
1757 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Durgamandop GP from 12.06.21 to 18.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 473/HSD(Camp) | 03/06/2021 | 7 | M/S NIRMAN CONSTRUCTION. | 4.86 | 4.86 | 100 | 0
1758 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Kalinagar GP from 06.06.21 to 12.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 482/HSD(Camp) | 03/06/2021 | 7 | M/S PROGATI ENTERPRISE. | 4.68 | 4.68 | 100 | 0
1759 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-I GP from 07.06.21 to 14.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 483/HSD(Camp) | 03/06/2021 | 8 | M/S DATTA ENTERPRISE. | 4.76 | 4.76 | 100 | 0
1760 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-II GP from 07.06.21 to 14.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 484/HSD(Camp) | 03/06/2021 | 8 | M/S PROGATI ENTERPRISE. | 4.85 | 4.85 | 100 | 0
1761 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Hingalganj GP from 09.06.21 to 14.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 502/HSD(Camp) | 03/06/2021 | 6 | MONDAL & CO. (BASIRHAT). | 4.9 | 4.9 | 100 | 0
1762 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 11, 12, 14 from 12.06.21 to 22.06.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | 504/HSD(Camp) | 03/06/2021 | 11 | M/S RAJPATH CONSTRUCTION. | 4.76 | 4.76 | 100 | 0
1763 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Hatgachi GP from 27.05.21 to 04.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 421/HSD(Camp) | 27/05/2021 | 9 | M/S DATTA ENTERPRISE. | 4.67 | 4.67 | 100 | 0
1764 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Hingalganj GP on 27.05.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte | 437/HSD(Camp) | 27/05/2021 | 1 | MONDAL & CO. (BASIRHAT). | 4.43 | 4.43 | 100 | 0
1765 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 11, 12, 14 from 27.05.21 to 31.05.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | 440/HSD(Camp) | 27/05/2021 | 5 | M/S RAJPATH CONSTRUCTION. | 4.64 | 4.64 | 100 | 0
1766 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Hingalganj GP from 28.05.21 to 02.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 447/HSD(Camp) | 27/05/2021 | 6 | TRISHA ENTERPRISE & CO. | 4.9 | 4.9 | 100 | 0
1767 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Hatgachi GP from 05.06.21 to 18.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 487/HSD(Camp) | 03/06/2021 | 14 | M/S PROGATI ENTERPRISE. | 4.67 | 4.67 | 100 | 0
1768 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Hingalganj GP from 03.06.21 to 08.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 493/HSD(Camp) | 03/06/2021 | 6 | MONDAL & CO. (BASIRHAT). | 4.89 | 4.89 | 100 | 0
1769 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Kalinagar GP from 20.06.21 to 27.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 532/HSD(Camp) | 14/06/2021 | 8 | M/S PROGATI ENTERPRISE. | 4.9 | 4.9 | 100 | 0
1770 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-I GP from 15.06.21 to 22.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 533/HSD(Camp) | 14/06/2021 | 8 | M/S DATTA ENTERPRISE. | 4.76 | 4.75 | 100 | 0
1771 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-I GP from 23.06.21 to 29.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 534/HSD(Camp) | 14/06/2021 | 7 | M/S DATTA ENTERPRISE. | 4.16 | 4.16 | 100 | 0
1772 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-II GP from 15.06.21 to 22.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 535/HSD(Camp) | 14/06/2021 | 8 | M/S PROGATI ENTERPRISE. | 4.85 | 4.85 | 100 | 0
1773 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Hingalganj GP from 15.06.21 to 20.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 562/HSD(Camp) | 14/06/2021 | 6 | MONDAL & CO. (BASIRHAT). | 4.89 | 4.89 | 100 | 0
1774 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Kalinagar GP from 13.06.21 to 19.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 505/HSD(Camp) | 03/06/2021 | 7 | M/S DATTA ENTERPRISE. | 4.69 | 4.69 | 100 | 0
1775 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Hatgachi GP from 19.06.21 to 29.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 539/HSD(Camp) | 14/06/2021 | 11 | M/S DATTA ENTERPRISE. | 3.67 | 3.67 | 100 | 0
1776 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sandeshkhali GP from 15.06.21 to 22.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 553/HSD(Camp) | 14/06/2021 | 8 | M/S NIRMAN CONSTRUCTION. | 4.91 | 4.91 | 100 | 0
1777 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sandeshkhali GP from 23.06.21 to 28.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 554/HSD(Camp) | 14/06/2021 | 6 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 3.68 | 3.68 | 100 | 0
1778 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 11, 12, 14 from 23.06.21 to 30.06.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | 573/HSD(Camp) | 14/06/2021 | 8 | M/S RAJPATH CONSTRUCTION. | 3.45 | 3.45 | 100 | 0
1779 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sandeshkhali GP from 27.05.21 to 29.05.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 431/HSD(Camp) | 27/05/2021 | 3 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.89 | 4.89 | 100 | 0
1780 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-II GP from 23.06.21 to 29.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 536/HSD(Camp) | 14/06/2021 | 8 | M/S PROGATI ENTERPRISE. | 4.24 | 4.24 | 100 | 0
1781 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm , SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sandeshkhali GP from 07.06.21 to 14.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 476/HSD(Camp) | 03/06/2021 | 8 | M/S NIRMAN CONSTRUCTION. | 4.9 | 4.9 | 100 | 0
1782 | NORTH 24 PARGANAS | Barasat Arsenic Division | Emergent restoration by repairing and renovation of existing pipeline, providing DG set and arrangement of temporary water supply through mechanised van for uninterrupted supply of drinking water to the extensively damaged ground W/S scheme of Baduria, Ha , SM/09030 | Disaster | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Pankoj Bhwomik , Jame Masjid at Maheshpur Majher para under Tildanga W/S Scheme at Baduria block due to Super Cyclone " AMPHAN" under Barasat Arsenic Division, PHE Dte. | 558/B.Ar.D | 23/03/2022 | 7 | R. K. MANDAL & CO. | 4.8 | 0 | 0 | 0
1783 | NORTH 24 PARGANAS | Barasat Arsenic Division | Emergent restoration by repairing and renovation of existing pipeline, providing DG set and arrangement of temporary water supply through mechanised van for uninterrupted supply of drinking water to the extensively damaged ground W/S scheme of Baduria, Ha , SM/09030 | Disaster | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near 2nd Pump House under Dwarir Jungle W/S Scheme at Sandeshkhali - II block due to Super Cyclone "Amphan" under Barasat Arsenic Division, PHE Dte. | 559/B.Ar.D | 23/03/2022 | 7 | R. K. MANDAL & CO. | 4.61 | 0 | 0 | 0
1784 | NORTH 24 PARGANAS | Barasat Arsenic Division | Emergent restoration by repairing and renovation of existing pipeline, providing DG set and arrangement of temporary water supply through mechanised van for uninterrupted supply of drinking water to the extensively damaged ground W/S scheme of Baduria, Ha , SM/09030 | Disaster | Bullah Pilling for protection of Pipeline (Approx 60 m) near pond of Bulbul Fakir at Fakir Para under Konanagar W/S Scheme at Hasnabad Block due to Super Cyclone "AMPHAN" under Barasat Arsenic Division, P.H.E. Dte. | 557/B.Ar.D | 23/03/2022 | 7 | SAFE STEP ENTERPRISE | 3.87 | 0 | 0 | 0
1785 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Nabatkati W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). , SM/09729 | Retrofitting | Material Requisition To Resource Division | 2341/BD | 26/09/2022 | 0 | Resource Division | 2.93 | 0 | 0 | 0
1786 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Nabatkati W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). , SM/09729 | Retrofitting | Material Requisition To Resource Division | 603/BD | 23/02/2023 | 0 | Resource Division | 38.14 | 0 | 0 | 0
1787 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-I) , SM/07851 | Retrofitting | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Tongtala Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-A) | 14/HSD | 04/01/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.91 | 0 | 0 | 1
1788 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-I) , SM/07851 | Retrofitting | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Bouthakurani Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-B) | 20/HSD | 04/01/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.91 | 4.91 | 50 | 1
1789 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-I) , SM/07851 | Retrofitting | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Dholkhali Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-B) | 24/HSD | 04/01/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.91 | 4.91 | 50 | 1
1790 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-I) , SM/07851 | Retrofitting | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Dholkhali Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-C) | 26/HSD | 04/01/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.79 | 4.76 | 100 | 1
1791 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-I) , SM/07851 | Retrofitting | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Tongtala Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-B) | 16/HSD | 04/01/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.91 | 4.91 | 50 | 1
1792 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-I) , SM/07851 | Retrofitting | Material Requisition To Resource Division | 1813/BD | 19/06/2023 | 0 | Resource Division | 2.59 | 0 | 0 | 0
1793 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dakshin Bagundi Piped Water Supply Scheme, Basirhat-I Block under Barasat Division, P.H.E.Dte. (Phase-II) , SM/08768 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Dakshin Bagundi piped Water Supply Scheme at Basirhat -I Block under Barasat Division, PHE Dte. (Phase II) | 1955/BD | 08/10/2021 | 15 | DEY & CO. | 16.5 | 14.77 | 89.55 | 1
1794 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kulia Piped Water Supply Scheme, Baduria Block under Barasat Division, P.H.E.Dte. (Phase-II) , SM/08770 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Kulia Piped water Supply Scheme at Baduria Block under Barasat Division, PHE Dte. (Phase II) | 1953/BD | 08/10/2021 | 15 | B.S.ENTERPRISE. (BASIRHAT) | 21.69 | 21.27 | 98.07 | 1
1795 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Talsa Piped Water Supply Scheme at Habra-II Block (Phase-I) , SM/08776 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALSA Water Supply Scheme at Habra - II Block under Barasat Division, PHE Dte. (Phase - I) | 181/BD | 20/01/2022 | 45 | CHANDA CONSTRUCTION. | 71.19 | 69.88 | 100 | 1
1796 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bajitpur (Zone-II) Piped Water Supply Scheme at Baduria Block (Phase-I) , SM/08654 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Bajitur Zone-II Water Supply Scheme at Baduria Block, Dist- North 24 Parganas under Barasat Division, PHE Dte.(Phase-I) | 2269/BD/BD | 26/11/2021 | 90 | ORIENT CONSTRUCTION. | 128.44 | 114.35 | 100 | 1
1797 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bajitpur (Zone-II) Piped Water Supply Scheme at Baduria Block (Phase-I) , SM/08654 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for BAJITPUR ZONE -2 Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 355/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.74 | 3.72 | 100 | 1
1798 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Raghunathpur Piped Water Supply Scheme at Basirhat-II Block (Phase-I) , SM/08657 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Raghunathpur Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase - I) | 1673/BD | 08/09/2021 | 30 | SHIBU BISWAS. | 48.8 | 48.11 | 100 | 1
1799 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Raghunathpur Piped Water Supply Scheme at Basirhat-II Block (Phase-I) , SM/08657 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for RAGHUNATHPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 345/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.11 | 3.1 | 100 | 1
1800 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Khosdelpur & Its Adjoining mouzas Piped Water Supply Scheme at Habra-II Block (Phase-I) , SM/08784 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Murarisha Water Supply Scheme under Barasat Division, PHE Dte. | 2153/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.05 | 4.05 | 100 | 1
1801 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Khosdelpur & Its Adjoining mouzas Piped Water Supply Scheme at Habra-II Block (Phase-I) , SM/08784 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Gadpukuria (Zone-I) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 128/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.55 | 4.55 | 100 | 1
1802 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Khosdelpur & Its Adjoining mouzas Piped Water Supply Scheme at Habra-II Block (Phase-I) , SM/08784 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Dakshin Bhebia Zone-I Water Supply Scheme under Barasat Division, PHE Dte. | 2183/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.49 | 4.49 | 100 | 1
1803 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Khosdelpur & Its Adjoining mouzas Piped Water Supply Scheme at Habra-II Block (Phase-I) , SM/08784 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHOSDELPUR & ITS ADJ. MOUZAS Water Supply Scheme at Habra - II Block within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. (Phase - I) | 2624/BD | 27/12/2021 | 90 | MAHAVIR PUMPS MANUFACTURING PVT.LTD. | 114.14 | 87.23 | 100 | 1
1804 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BANSJHARI MALLIKPUR W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08650 | Retrofitting | Acceptance cum work order for for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Bansjhari Mallikpur Supply Scheme at Basirhat - I Block under Barasat Division, PHE Dte. (Phase -I). | 400/BD | 10/02/2022 | 30 | SUDHAMAY MAJUMDAR. | 50.02 | 48.28 | 100 | 1
1805 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BANSJHARI MALLIKPUR W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08650 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for BANSJHARI MALLIKPUR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | 198/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.29 | 3.27 | 100 | 1
1806 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BANSJHARI MALLIKPUR W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08650 | Retrofitting | Day to Day repair Operation & maintenance of CI/DI/HDPE/UPVC/AC/GI Rising main & Distribution system for Bansghata water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 622/Bon | 31/12/2021 | 1 | KAMAL HALDAR. | 1.39 | 0 | 0 | 1
1807 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. , SM/10299 | Augmentation | Survey, Design and preparation of Retrofitting DPR in connection with Providing functional household tap connection to every Household under Chandpur W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte. | 1176/NWSD-I | 31/12/2021 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.99 | 3.99 | 100 | 1
1808 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. , SM/10299 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works within command area of Chandpur Water Supply Scheme under North 24 Parganas Water Supply Division-I, PHE. Dte. | 588/NWSD-I | 10/05/2022 | 90 | H. I. ENTERPRISE | 227.12 | 204.13 | 89.87 | 87
1809 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. , SM/10299 | Augmentation | Material Requisition To Resource Division | 648/NWSD-I | 23/05/2022 | 0 | Resource Division | 2.16 | 0 | 0 | 0
1810 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. , SM/10299 | Augmentation | Material Requisition To Resource Division | 609/NWSD-I | 17/05/2022 | 0 | Resource Division | 9.02 | 0 | 0 | 0
1811 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. , SM/10299 | Augmentation | Material Requisition To Resource Division | 1837/NWSD-I | 10/11/2023 | 0 | Resource Division | 3.08 | 0 | 0 | 0
1812 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. , SM/10299 | Augmentation | Repair And Renovation Works Of R.C.C. Elevated Reservoir Of 250 CUM, Pump House At Head Works Site, Special Repair & Renovation Of Boundary Wall At Head Work Site & Other Allied Works At Chandpur W/S Scheme Under Bagdag Block In The District Of North 24 Pargana(S) Under N 24 Pgs W/S Div-I, Phe Dte. | 1433/NWSD-I | 11/09/2023 | 424 | CHANDIMATA CONSTRUCTION | 26.87 | 5.85 | 20.94 | 5
1813 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. , SM/10299 | Augmentation | Material Requisition To Resource Division | 1302/NWSD-I | 30/08/2024 | 0 | Resource Division | 1.85 | 0 | 0 | 0
1814 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. , SM/10299 | Augmentation | Laying of pipeline & special measure for protection of road and other allied works at different location under Augmentation work at Chandpur W/S. Scheme in Bagda Block under North 24 Parganas W/S. Division-I, PHE. Dte. | 169/NWSD-I | 30/01/2025 | 30 | A.K.C. SUPPLY & CONSTRUCTION | 24.42 | 0 | 0 | 0
1815 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. , SM/10299 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1431/NWSD-I | 18/09/2024 | 7 | IMAGIN | 4.59 | 0 | 0 | 95
1816 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to Accommodate FHTC Block- Bagda, Dist-North 24 Parganas. , SM/10299 | Augmentation | CONSTRUCTION OF SERVICE ROAD OF 150 M LENGTH WITH PROTECTION WORK WITHIN THE COMMAND AREA UNDER CHANDPUR W/S SCHEME UNDER BAGDAH BLOCK OF NORTH 24 PARGANA(S) DISTRICT UNDER N 24 PGS W/S DIV-I, PHE DTE. | 444/NWSD-I | 11/03/2024 | 60 | PATHIK PABAN NANDI | 29.73 | 0 | 0 | 100
1817 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gobindapur Water Supply Scheme at Bagdah Block (Phase-II) , SM/07624 | Retrofitting | Material Requisition To Resource Division | 3660/BD | 13/12/2022 | 0 | Resource Division | 3.12 | 0 | 0 | 0
1818 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Champali Piped Water Supply Scheme, Minakhan Block (Phase-I) , SM/08260 | Retrofitting | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places due to laying of new DI/UPVC pipe line in Champali mouza within Champali w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1987/HSD | 02/12/2021 | 7 | S.K.ENTERPRISE. | 2.44 | 2.44 | 100 | 1
1819 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Champali Piped Water Supply Scheme, Minakhan Block (Phase-I) , SM/08260 | Retrofitting | Acceptance cum work order for Protection of newly laid DI/UPVC pipe line by UC bullah pile at different places in Champali mouza within Champali w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | 1991/HSD | 02/12/2021 | 10 | M/S NIRMAN CONSTRUCTION. | 4.38 | 4.38 | 99.99 | 1
1820 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Champali Piped Water Supply Scheme, Minakhan Block (Phase-I) , SM/08260 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in diff. mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Champali w/s scheme, Minakhan block under Hasnabad Sub-Division, PHE Dte. (Phase-I) | 1671/BD | 08/09/2021 | 45 | M/S NIRMAN CONSTRUCTION. | 77.7 | 76.48 | 100 | 1
1821 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Champali Piped Water Supply Scheme, Minakhan Block (Phase-I) , SM/08260 | Retrofitting | Material Requisition To Resource Division | 1810/BD | 19/06/2023 | 0 | Resource Division | 13.49 | 0 | 0 | 0
1822 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PASCHIM PANCHBERIA ZONE-I Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07606 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PASCHIM PANCHBERIA ZONE-I Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (Phase-I) | 68/NWSD-I | 20/01/2021 | 60 | B. S. ENTERPRISE_ | 38.45 | 74.55 | 114.82 | 1
1823 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Refuge para in Rampur Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1352/HSD | 03/08/2022 | 10 | R.K.MANDAL & CO. | 4.33 | 4.29 | 50 | 1
1824 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Arsad Miya Bazaar in Dhamakhali Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1353/HSD | 03/08/2022 | 10 | SARKAR ENTERPRISE & CO. | 4.73 | 4.56 | 50 | 1
1825 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Paschim Dhamakhali pramanik para in Damakhali Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1359/HSD | 03/08/2022 | 10 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 4.02 | 4.01 | 50 | 1
1826 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Purba dhamakhali pramanik para in Dhamakhali Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1360/HSD | 03/08/2022 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.81 | 4.76 | 50 | 1
1827 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of samanta Para in Rampur Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad SubDivision P.H.E. Dte | 1317/HSD | 02/08/2022 | 10 | MUKHERJEE CONSTRUCTION | 4.85 | 4.85 | 50 | 1
1828 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Ghoja para in Damakhali Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1391/HSD | 08/08/2022 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.26 | 4.21 | 50 | 1
1829 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Mistiri para in Damakhali Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1392/HSD | 08/08/2022 | 10 | M/S R.B.S.ENTERPRISE. | 4.13 | 4.12 | 50 | 1
1830 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of 50 Bigha More in Damakhali Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1394/HSD | 08/08/2022 | 10 | M/S B.K.ENTERPRISE. | 4.09 | 4.08 | 50 | 1
1831 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Rampur Haldar para in Rampur Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1347/HSD | 03/08/2022 | 10 | R.K.MANDAL & CO. | 4.88 | 4.85 | 50 | 1
1832 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Rampur notun para in Rampur Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1348/HSD | 03/08/2022 | 10 | SARKAR ENTERPRISE & CO. | 4.17 | 4.16 | 50 | 1
1833 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Rampur Adibasi para in Rampur Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1349/HSD | 03/08/2022 | 10 | R.K.MANDAL & CO. | 4.76 | 4.73 | 50 | 1
1834 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia HDPE/UPVC distribution pipe line From Abu Baktar to Toto stand at Rampur Bazaar in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 1332/HSD | 02/08/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 3.98 | 3.95 | 50 | 1
1835 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia HDPE/UPVC distribution pipe line From Khaja baba Fish arot to Mamoni Builder's at Rampur Bazaar in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 1338/HSD | 02/08/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 4.17 | 4.11 | 50 | 1
1836 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Moilobi Para in Rampur Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1318/HSD | 02/08/2022 | 10 | R.K.MANDAL & CO. | 4.81 | 4.76 | 50 | 1
1837 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Gayen para in Rampur Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1319/HSD | 02/08/2022 | 10 | SARKAR ENTERPRISE & CO. | 3.98 | 3.97 | 50 | 1
1838 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia HDPE/UPVC distribution pipe line From Mamoni Builder's to Molla store at Rampur Bazaar in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 1339/HSD | 02/08/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 2.97 | 2.91 | 50 | 1
1839 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Kachari para in Damakhali Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1321/HSD | 02/09/2022 | 10 | ABDUL HAMID GAZI. | 4.05 | 4.04 | 50 | 1
1840 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Emergent resting of distribution main by concrete block for low areas at Halder Ghery to Pole para in connection with retrofitting of Rampur w/s scheme , Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 568/HSD | 22/03/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 3.97 | 3.92 | 100 | 1
1841 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Additional Emergent resting of distribution main by concrete block for low areas at Halder Ghery to Pole para in connection with retrofitting of Rampur w/s scheme , Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 569/HSD | 22/03/2022 | 15 | NEW MANGES INDUSTRIAL CORPORATION | 4.24 | 4.19 | 100 | 1
1842 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Emergent resting of distribution main by concrete block for low areas at PWD road to Rampur Burning ghat in connection with retrofitting of Rampur w/s scheme , Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 570/HSD | 22/03/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 4.02 | 2.38 | 100 | 1
1843 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia UPVC distribution pipe line at different places of Akunji para,Naskar para,Gajen para & 50 Bigha more in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 590/HSD | 29/03/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 4.75 | 4.6 | 100 | 1
1844 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia UPVC distribution pipe line at different places of Molla para,Colony para,Samanta Para & Bagdi para connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 586/HSD | 28/03/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 4.06 | 3.97 | 100 | 1
1845 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid 125 mm dia HDPE distribution pipe line from Arsad Miya Bazar to Dhamakhali Busstand in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 578/HSD | 28/03/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 4.73 | 3.59 | 100 | 1
1846 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia UPVC distribution pipe line at different places of Bagdipara to rampur bazar road,rampur ferry ghat to anganwadi centre & 972 bus stand in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 598/HSD | 31/03/2022 | 15 | NEW MANGES INDUSTRIAL CORPORATION | 1.39 | 1.31 | 100 | 1
1847 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia UPVC distribution pipe line at different places of Haldar para,Haldar gheri more & pole para in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 582/HSD | 28/03/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 4.17 | 4.11 | 100 | 1
1848 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Protection work for newly laid Distribution main 300 mm dia DI Pipe with UC bullah pile from HW site to PWD Road within Rampur w/s scheme,Sandeskhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 510/HSD | 15/03/2022 | 15 | NEW MANGES INDUSTRIAL CORPORATION | 2.25 | 2.01 | 100 | 1
1849 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Emergent resting of distribution main by concrete block for low areas from Pole para to Rampur bazaar in connection with retrofitting of Rampur w/s scheme , Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 511/HSD | 15/03/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 4.09 | 4.03 | 100 | 1
1850 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Emergent resting of 100/150 mm dia DI distribution main by concrete block for low areas of Rampur w/s scheme in connection with retrofitting, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 512/HSD | 15/03/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 3.05 | 2.94 | 100 | 1
1851 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia HDPE/UPVC distribution pipe line from Molla store to Abu baktar shop at Rampur Bazaar in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 1330/HSD | 02/08/2022 | 10 | S.S.ENTERPRISE. (BAMANGACHI) | 2.6 | 2.59 | 50 | 1
1852 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Rampur Hat khola para in Rampur Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1320/HSD | 02/08/2022 | 10 | BARNALI DUTTA | 3.91 | 3.88 | 100 | 1
1853 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Emergent resting of 200mm dia DI distribution main by concrete block for low areas in connection with retrofitting of Rampur w/s scheme , Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 571/HSD | 22/03/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 4.5 | 3.63 | 80.67 | 0
1854 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Emergent resting of 250mm dia DI distribution main by concrete block for low areas in connection with retrofitting of Rampur w/s scheme , Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 572/HSD | 22/03/2022 | 15 | NEW MANGES INDUSTRIAL CORPORATION | 4.12 | 3.28 | 79.62 | 0
1855 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Continuation order for Hiring of one no. DIESEL MOTOR CAB (BS-IV) on daily hire basis for use of the Assistant Engineer, HASNABAD SUB-DIVISION, PHE DTE. Period from 01.10.21 to 30.09.22. | 1617/HSD | 29/09/2021 | 365 | SUSMITA MANDAL. | 1.72 | 3.75 | 100 | 1
1856 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 1539/BD | 30/05/2022 | 90 | S.S.ENTERPRISE. (BAMANGACHI) | 158.7 | 155.05 | 72.78 | 1
1857 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Construction of boundary wall with RCC column structure at Pump House No.-2 within Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. (Part-A) | 771/HSD | 13/05/2022 | 21 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 4.77 | 4.17 | 100 | 1
1858 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Construction of boundary wall with RCC column structure at Pump House No.-2 within Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. (Part-B) | 772/HSD | 13/05/2022 | 21 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 1.75 | 1.7 | 100 | 1
1859 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Formal work order for Protection work for newly laid UPVC pipe line at different places of Rampur & Dhamakhali Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1670/BD | 06/06/2023 | 30 | S.S.ENTERPRISE. (BAMANGACHI) | 115.27 | 115.23 | 100 | 60
1860 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Rampur mouza due to erosion of soil for heavy rain fall during monsoon season within Rampur w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 1080/HSD | 31/08/2023 | 10 | M/S RAJPATH CONSTRUCTION. | 0.99 | 0.98 | 100 | 100
1861 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Construction of boundary wall with RCC column structure at Head Work (Ph No-1) site within Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 4438/BD | 10/11/2023 | 90 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 22.05 | 20.63 | 100 | 100
1862 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Rampur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10511 | Retrofitting | Acceptance cum work order for Construction of approach road & other allied works at Head Work site (PH No.-1) within Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte | 526/BD | 23/02/2022 | 990 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 31.47 | 13.57 | 51.56 | 100
1863 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10111 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Santoshpur (Zone-I) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | 1195/NWSD-I | 31/12/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.53 | 4.53 | 100 | 1
1864 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10111 | Augmentation | Repair and renovation works of R.C.C. Elevaced Reservoir 350 cum at SANTOSHPUR ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 408/NWSD-I | 11/04/2023 | 45 | RAKESH ENTERPRISE | 13.91 | 13.9 | 100 | 100
1865 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10111 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 40 m Length in 2nd Pump house site at Santoshpur Zone - I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 410/NWSD-I | 11/04/2023 | 45 | P & S ASSOCIATES | 5.17 | 4.33 | 100 | 100
1866 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10111 | Augmentation | Special Repair & Renovation of Pump House at Head Works site & Service Road (60 Mtr. Length X 3 Mtr. Width) at Head Works site at SANTOSHPUR ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 411/NWSD-I | 11/04/2023 | 45 | PRABIR KUMAR MONDAL | 7.22 | 6.8 | 100 | 45
1867 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10111 | Augmentation | Special Repair & Renovation of Pump House at 2nd Pump house site & Service Road (25 Mtr. Length X 2 Mtr. Width) at 2nd Pump house site at SANTOSHPUR ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 412/NWSD-I | 11/04/2023 | 45 | JEET ENTERPRISE | 4.18 | 3.65 | 100 | 35
1868 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10111 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 146 m Length in Head work site at SANTOSHPUR ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 409/NWSD-I | 11/04/2023 | 45 | AYUSH ENTERPRISE | 14.26 | 9.74 | 100 | 5
1869 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10111 | Augmentation | Material Requisition To Resource Division | 748/NWSD-I | 14/06/2022 | 0 | Resource Division | 18.89 | 0 | 0 | 0
1870 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10111 | Augmentation | Material Requisition To Resource Division | 737/NWSD-I | 13/06/2022 | 0 | Resource Division | 130.25 | 0 | 0 | 0
1871 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10111 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works within command area of SANTOSHPUR Zone-I Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE. Dte. | 704/NWSD-I | 07/06/2022 | 90 | SUPRITI ENTERPRISE | 528.09 | 525.48 | 100 | 69
1872 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10111 | Augmentation | Material Requisition To Resource Division | 1311/NWSD-I | 30/08/2024 | 0 | Resource Division | 5.54 | 0 | 0 | 0
1873 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10111 | Augmentation | Renovation of AIRP at Santoshpur-Zone-I Water Supply Scheme of capacity 92 Cu.m/hr of Bongaon Block under North 24 Pgs. W/S Div-I, PHE Dte. | 1670/NWSD-I | 19/11/2024 | 360 | J. D. J. ENTERPRISE, A UNIT OF JDJ TRADERS PRIVATE LIMITED | 80.35 | 0 | 0 | 35
1874 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-I to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10111 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1431/NWSD-I | 18/09/2024 | 7 | IMAGIN | 4.59 | 0 | 0 | 95
1875 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Khamarkalla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, P.H.E Dte. , SM/10758 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Khamarkalla (Zone-II) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | 1189/NWSD-I | 31/12/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.15 | 4.15 | 100 | 0
1876 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Khamarkalla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, P.H.E Dte. , SM/10758 | Augmentation | Material Requisition To Resource Division | 1209/NWSD-I | 13/10/2022 | 0 | Resource Division | 0.04 | 0 | 0 | 0
1877 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Khamarkalla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, P.H.E Dte. , SM/10758 | Augmentation | Material Requisition To Resource Division | 456/NWSD-I | 26/04/2023 | 0 | Resource Division | 23.57 | 0 | 0 | 0
1878 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Khamarkalla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, P.H.E Dte. , SM/10758 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1430/NWSD-I | 18/09/2024 | 7 | BIBHAS PAL | 5.27 | 0.18 | 50 | 100
1879 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Khamarkalla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, P.H.E Dte. , SM/10758 | Augmentation | Material Requisition To Resource Division | 1304/NWSD-I | 30/08/2024 | 0 | Resource Division | 12.32 | 0 | 0 | 0
1880 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Khamarkalla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, P.H.E Dte. , SM/10758 | Augmentation | Laying of Distribution System including specials, valves and pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, Construction of 500 cum capacity 20 Mtr. staging height RCC Over Head Reservoir with pile foundation and pipe connection including cost of pipes & specials with soil investigation, Construction of Pump House (4.88m X 3.66m) including Sanitary Arrangement, Construction of Boundary Wall, Construction of Service Road, Improvement Of Land, Pipe carring structure for a span of 25 Meter for crossing of a Canal / River etc. for Augmentation of Ground Water Based Piped Water Supply Scheme for Khamarkalla Zone-II in Bongaon Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | 1680/NWSD-I | 30/10/2023 | 910 | MITRA CONSTRUCTION | 517.31 | 43.99 | 8.5 | 20
1881 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC , SM/10727 | Augmentation | Repairing & renovation of Pump House No. ? 1 & 2 of Kamarpur& adj. mouzas W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 512/HAB | 10/12/2021 | 30 | M/S LATIKA CONSTRUCTION. | 1.4 | 1.32 | 100 | 1
1882 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC , SM/10727 | Augmentation | Material Requisition To Resource Division | 3800/BD | 22/12/2022 | 0 | Resource Division | 4.41 | 0 | 0 | 0
1883 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC , SM/10727 | Augmentation | Material Requisition To Resource Division | 2517/BD | 25/08/2022 | 0 | Resource Division | 6.75 | 0 | 0 | 0
1884 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC , SM/10727 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II & III (Zone-I) under Maslandapur W/S Scheme and Pump House No-I an II uuder Kamarpur-Tazpur W/S Scheme (Rep.) District of 24 Pgs. (N) NIET No.- 29 of EE/EMD of 2022-23 (Sl. No.- 26) | 1320/EMD | 29/03/2023 | 30 | M/S DILIP MITRA | 53 | 17.61 | 83.09 | 80
1885 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC , SM/10727 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 250 mm. x 150 mm. dia. 270 mtr deep tube well by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 for Augmentation of Kamarpur & Adjoining Mouzas water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | 2776/BD | 11/09/2023 | 60 | ANJALI ENTERPRISE. | 28.99 | 12.33 | 42.53 | 65
1886 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC , SM/10727 | Augmentation | Construction of Service Road 55 Mtr. Length X 2 Mtr. Width for Pump House No1 of kamarpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 934/HAB | 06/11/2024 | 10 | M/S LATIKA CONSTRUCTION. | 3.35 | 0 | 0 | 0
1887 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC , SM/10727 | Augmentation | Special repair and renovation of pump house and other Allied Works for Pump House No - 1 of Kamarpur WS scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 922/HAB | 30/10/2024 | 20 | M/S LATIKA CONSTRUCTION. | 2.66 | 0 | 0 | 0
1888 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC , SM/10727 | Augmentation | Construction of Service Road (55 Mtr. Length X 2 Mtr. Width) for Pump House No:2 of kamarpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 693/HAB | 25/07/2024 | 10 | G.P.ENTERPRISE. | 1.22 | 0 | 0 | 0
1889 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC , SM/10727 | Augmentation | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system for Augmentation of Kamarpur & Adj. Mouzas water supply scheme within jurisdiction of Habra Sub-Division, PHE Dte. under barasat Division, PHE Dte. | 2445/BD | 23/08/2022 | 90 | CHANDA CONSTRUCTION. | 212.3 | 212.2 | 100 | 100
1890 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC , SM/10727 | Augmentation | Improvement of Iron Elimination Plant at Kamarpur & adj. Mouzas W/S Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 689/HAB | 01/11/2023 | 30 | M/S LATIKA CONSTRUCTION. | 2.97 | 2.97 | 100 | 100
1891 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC , SM/10727 | Augmentation | Special repair & renovation of pump house and other Allied Works for Pump House No - 2 of Kamarpur W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 927/HAB | 05/11/2024 | 20 | M/S LATIKA CONSTRUCTION. | 2.6 | 0 | 0 | 100
1892 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC , SM/10727 | Augmentation | Repairing of 65 m Boundary Wall for PH-2 of Kamarpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 914/HAB | 30/10/2024 | 25 | M/S LATIKA CONSTRUCTION. | 3.22 | 0 | 0 | 100
1893 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kamarpur & Adjoining mouzas to accommodate FHTC , SM/10727 | Augmentation | Acceptance cum work order for Interconnection of Tube well rising main & I.E.P at Head work site of Kamarpur & adj moujas water supply scheme and connection of rising main with newly sunk 5 nos big dia tube-well under Bira- Rajibpur,Talsa & kamarpur & adjoining moujas water supply scheme in connection JJM programme within the jurisdiction of Habra Sub-Division under Barasat Division,P.H.E.Dte. | 421/BD | 06/02/2025 | 30 | M/S LATIKA CONSTRUCTION. | 16.49 | 0 | 0 | 100
1894 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate , SM/10577 | Augmentation | Repairing & renovation of Pump House No. - 1 of Sadpur W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 500/HAB | 02/12/2021 | 30 | M/S SUKANTA ENTERPRISE. | 0.74 | 0.7 | 100 | 1
1895 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate , SM/10577 | Augmentation | Material Requisition To Resource Division | 3795/BD | 22/12/2022 | 0 | Resource Division | 0.87 | 0 | 0 | 0
1896 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate , SM/10577 | Augmentation | Material Requisition To Resource Division | 1560/BD | 23/05/2023 | 0 | Resource Division | 1.23 | 0 | 0 | 0
1897 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate , SM/10577 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Sadpur Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 1669/BD | 06/06/2023 | 90 | B.M.ENTERPRISE. | 105.99 | 43.32 | 40.87 | 80
1898 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate , SM/10577 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Bira-Rajibpur W/S Scheme, Khasdelpur W/S Scheme and Kumarjole W/S Scheme with Pump House No-I under Sadpur W/S Scheme District of 24 Pgs. (N) | 4490/EMD | 14/07/2023 | 537 | EASTERN INDIA SALES & SERVICE | 74.22 | 3.39 | 32.02 | 90
1899 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate , SM/10577 | Augmentation | Special repair & renovation of pump house and other allied Works for Pump House No - 1 of Sadpur W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 136/HAB | 05/02/2024 | 15 | JOY ENTERPRISE | 0.45 | 0.44 | 100 | 100
1900 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate , SM/10577 | Augmentation | Construction of Service Road 50 Mtr. Length and 2 Mtr. Width for Pump House No1 of Sadpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 783/HAB | 20/08/2024 | 10 | JOY ENTERPRISE | 2.95 | 2.92 | 100 | 100
1901 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate , SM/10577 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 1 for Augmentation of Sadpur water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | 2772/BD | 11/09/2023 | 674 | NADIA TUBEWELLS | 14.48 | 0 | 0 | 100
1902 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sadpur to accommodate , SM/10577 | Augmentation | Repairing of Boundary Wall for Pump House No - 1 of Sadpur water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | 691/HAB | 24/07/2024 | 35 | JOY ENTERPRISE | 4 | 0 | 0 | 100
1903 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10581 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with Providing functional household tap connection to every Household with in Paschim Panchberia (Zone-I) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte. | 1192/NWSD-I | 31/12/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.75 | 4.75 | 100 | 1
1904 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10581 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system & Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVc, Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of Paschim Panchberia Zone-I Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE. Dte. | 967/NWSD-I | 12/08/2022 | 90 | MADE & TRADE CO. | 412.72 | 415.86 | 100 | 100
1905 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10581 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 44 m Length in 3rd. Pump house site at PASCHIM PANCHBERIA ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 280/NWSD-I | 14/03/2023 | 45 | M/S DAS AND CO | 5.16 | 3.49 | 100 | 100
1906 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10581 | Augmentation | Service Road (60 Mtr. Length X 3 Mtr. Width) at Headwork site at PASCHIM PANCHBERIA ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas Water Supply Division-I, PHE Dte. | 282/NWSD-I | 14/03/2023 | 45 | R K ENTERPRISE | 4.69 | 4.72 | 100 | 100
1907 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10581 | Augmentation | Repair & Renovation for one no. Pump house at 3rd Tube well site and Service Road (25 Mtr. Length X 2 Mtr. Width) at 2nd & 3rd Tube well site at PASCHIM PANCHBERIA ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 283/NWSD-I | 14/03/2023 | 45 | M/S. SUPER CONSTRUCTION | 5.72 | 5.34 | 100 | 100
1908 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10581 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 44 m Length in 2nd Pump house site at PASCHIM PANCHBERIA ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 279/NWSD-I | 14/03/2023 | 45 | A. S. ENTERPRISE | 5.19 | 3.77 | 100 | 100
1909 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10581 | Augmentation | Special Repair & Renovation for two nos. (Head work site and 2nd Tube well site) Pump house and Allied Works as per site at PASCHIM PANCHBERIA ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 281/NWSD-I | 14/03/2023 | 45 | M/S. SANDHYA CONSTRUCTION | 5.25 | 4.69 | 100 | 20
1910 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10581 | Augmentation | Construction of BOUNDARY WALL for 167 m Length at Head work site at PASCHIM PANCHBERIA ZONE-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 492/NWSD-I | 26/04/2023 | 45 | PHOENIX INFRASTRUCTURE | 19.93 | 19.28 | 100 | 15
1911 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10581 | Augmentation | Material Requisition To Resource Division | 970/NWSD-I | 12/08/2022 | 0 | Resource Division | 43.47 | 0 | 0 | 0
1912 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10581 | Augmentation | Renovation of AIRP at Paschim Pachneria Zone-I Water Supply Scheme of capacity 110.81 Cu.m/hr of Bongaon Block under North 24 Pgs. W/S Div-I, PHE Dte. | 1738/NWSD-I | 28/11/2024 | 180 | MONDAL PRECISION PRIVATE LIMITED | 63.45 | 0 | 0 | 0
1913 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10581 | Augmentation | Laying of distribution pipe line at Paschim Pancberia Zone -I W/S Scheme in the District of North 24 Parganas under North 24 Parganas water Supply Division-I, PHE Dte. | 1236/NWSD-I | 18/08/2023 | 60 | A.K.C. SUPPLY & CONSTRUCTION | 63.24 | 62.17 | 100 | 100
1914 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10581 | Augmentation | Repair and renovation works of R.C.C. Elevaced Reservoir of 550 cum at Paschim Panchberia Zone-I" of Bongon Block in the district of North 24 pargana(s) under North 24 Pgs. W/S Div-I, P.H.E. Dte. | 1265/NWSD-I | 21/08/2023 | 60 | SAMBIT NEOGI | 14.05 | 12.78 | 100 | 30
1915 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC(Functional Household Tap Connection) by augmentation for Paschim Panchberia Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10581 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1431/NWSD-I | 18/09/2024 | 7 | IMAGIN | 4.59 | 0 | 0 | 95
1916 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/10638 | Augmentation | Survey, Design and preparation of Augmentation DPR in connection with Providing functional household tap connection to every Household under Paikpara Zone-I W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte. | 1171/NWSD-I | 31/12/2021 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.81 | 4.81 | 100 | 1
1917 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/10638 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.III and IV (Zone-I) (Rep) under Paikpara W/S Scheme District of 24 Pgs. (N) | 4740/EMD | 07/08/2023 | 30 | CINZANO | 26.54 | 0 | 0 | 0
1918 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/10638 | Augmentation | Material Requisition To Resource Division | 1165/NWSD-I | 26/09/2022 | 0 | Resource Division | 0.03 | 0 | 0 | 0
1919 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/10638 | Augmentation | Material Requisition To Resource Division | 1840/NWSD-I | 10/11/2023 | 0 | Resource Division | 3.08 | 0 | 0 | 0
1920 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/10638 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) (Rep) under Paikpara W/S Scheme District of 24 Pgs. (N) | 4741/EMD | 07/08/2023 | 30 | S.P. ENTERPRISE (SILIGURI) | 26.24 | 15.18 | 57.87 | 66
1921 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/10638 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1430/NWSD-I | 18/09/2024 | 7 | BIBHAS PAL | 5.27 | 0.35 | 50 | 100
1922 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/10638 | Augmentation | Material Requisition To Resource Division | 1307/NWSD-I | 30/08/2024 | 0 | Resource Division | 6.16 | 0 | 0 | 0
1923 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/10638 | Augmentation | Construction of Bituminous road from Ghatbour GP office to Kalmegha at Ghatbour GP under Bongaon Block. | 279/PFMS/24-25 | 06/12/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA, NORTH 24 PARGANAS DIVISION | 15.51 | 0 | 0 | 0
1924 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/10638 | Augmentation | Repair and renovation works of 1000 m3 RCC Elevated Reservoir, Boundary Wall, Pump House, Service roads etc. at Head Works Site and other tube well Sites under Paikpara Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 235/NWSD-I | 02/03/2023 | 900 | SUDHAMAY MAJUMDAR | 76.43 | 0 | 0 | 55
1925 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/10638 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1431/NWSD-I | 18/09/2024 | 7 | IMAGIN | 4.59 | 0 | 0 | 95
1926 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, , SM/07852 | Retrofitting | Acceptance cum work order for Construction of boundary wall at East & West side for damaged portion at PH No.-4 for Rejuvenation of Hasnabad w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 393/HSD | 11/02/2021 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 1.87 | 1.8 | 100 | 0
1927 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, , SM/07852 | Retrofitting | Acceptance cum work order for Repairing of Pump House No.-3 for Rejuvenation of Hasnabad w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 385/HSD | 11/02/2021 | 15 | M/S LALTI ENTERPRISE | 1.31 | 1.28 | 100 | 0
1928 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, , SM/07852 | Retrofitting | Acceptance cum work order for Additional Emergent restoration of concrete road for damage portion at different places due to newly laid HDPE/DI pipeline within Hasnabad w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 1658/HSD | 05/10/2021 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 2.86 | 2.86 | 100 | 0
1929 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, , SM/07852 | Retrofitting | Acceptance cum work order for Additional Functional Household Tap Connection (FHTC) in Joykrisnapur mouza including laying of UPVC/PVC pipe & supply of necessary fittings Sultanpur w/s scheme, Minakhan block under Hasnabad Sub-Division, PHE Dte. | 1652/HSD | 05/10/2021 | 15 | MONDAL & CO. (BASIRHAT). | 3.04 | 3.04 | 100 | 0
1930 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, , SM/07852 | Retrofitting | Acceptance cum work order for Restoration of pipeline by withdrawn & relaying of different dia. UPVC pipe line for extra widening of PWD road from Sri Chaitanya Math to Pather Dabi More within Hingalganj W/S Scheme (Zone-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 1654/HSD | 05/10/2021 | 15 | MONDAL & CO. (BASIRHAT). | 4.6 | 4.59 | 100 | 0
1931 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, , SM/07852 | Retrofitting | Acceptance cum work order for Additional Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Bouthakurani water supply scheme (For Bouthakurani & Tongtala Mouza) at Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. | 1655/HSD | 05/10/2021 | 15 | M/S B.K.ENTERPRISE. | 4.35 | 4.35 | 100 | 0
1932 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, , SM/07852 | Retrofitting | Acceptance cum work order for Special Repair & Maintenance of Rising main & Distribution system (CI/DI/HDPE/UPVC) of Hasnabad w/s Scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 1659/HSD | 05/10/2021 | 21 | MONDAL & CO. (BASIRHAT). | 4.4 | 4.4 | 100 | 0
1933 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, , SM/07852 | Retrofitting | Acceptance cum work order for Additional Functional Household Tap Connection (FHTC) in Khosbas & Singerkati mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 1661/HSD | 05/10/2021 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 1.2 | 1.2 | 100 | 0
1934 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, , SM/07852 | Retrofitting | Acceptance cum work order for Special Repair & Maintenance of Rising main & Distribution system (CI/DI/UPVC) for Mamudpur Mouza within Hingalganj w/s Scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 1645/HSD | 05/10/2021 | 15 | TRISHA ENTERPRISE & CO. | 2.54 | 2.53 | 100 | 0
1935 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, , SM/07852 | Retrofitting | Acceptance cum work order for OHR connection with distribution main including Laying of balance laying work of rising main and distribution pipe line within Hingalganj water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | 1646/HSD | 05/10/2021 | 15 | ANKUSH CONSTRUCTION & CO. | 4.51 | 4.48 | 100 | 0
1936 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, , SM/07852 | Retrofitting | Acceptance cum work order for Special Repair & Maintenance of Rising main & Distribution system (CI/DI/UPVC) for Hingalganj Mouza within Hingalganj w/s Scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 1644/HSD | 05/10/2021 | 15 | MONDAL & CO. (BASIRHAT). | 2.59 | 2.58 | 100 | 0
1937 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, , SM/07852 | Retrofitting | Acceptance cum work order for Additional Land development at Pump House No.-1 (New site) within Sultanpur w/s scheme, Minakhan Block under Hasnabad Sub-Division P.H.E. Dte. | 1647/HSD | 05/10/2021 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 1.14 | 1.14 | 100 | 0
1938 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, , SM/07852 | Retrofitting | Acceptance cum work order for Laying of 150 mm dia. DI rising main from Pump House No-2 to Pump House No.-1 (New site) within Sultanpur w/s scheme, Minakhan Block under Hasnabad Sub- Division P.H.E. Dte. | 1648/HSD | 05/10/2021 | 10 | R.K.MANDAL AND CO. | 1.2 | 1.18 | 100 | 0
1939 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, , SM/07852 | Retrofitting | Acceptance cum work order for Additional Functional Household Tap Connection (FHTC) in Paitkelpota & Paitkelpota Abad mouza including laying of UPVC/PVC pipe & supply of necessary fittings Sultanpur w/s scheme, Minakhan block under Hasnabad Sub-Division, PHE Dte. | 1649/HSD | 05/10/2021 | 15 | MONDAL & CO. (BASIRHAT). | 1.9 | 1.9 | 100 | 0
1940 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, , SM/07852 | Retrofitting | Acceptance cum work order for Additional land development at tube well site-3 (CWR site) within Hingalganj w/s scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | 1660/HSD | 05/10/2021 | 10 | TRISHA ENTERPRISE & CO. | 0.92 | 0.92 | 100 | 0
1941 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, , SM/07852 | Retrofitting | Acceptance cum work order for Supply of different dia. Sluice Valve & construction of different dia. Sluice Valve chamber at different places within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | 1663/HSD | 05/10/2021 | 10 | MONDAL & CO. (BASIRHAT). | 4.88 | 4.88 | 100 | 0
1942 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, , SM/07852 | Retrofitting | Acceptance cum work order for Additional Functional Household Tap Connection (FHTC) in Radhanagar mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Chotto Sehara w/s scheme Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 1665/HSD | 05/10/2021 | 10 | TRISHA ENTERPRISE & CO. | 3.56 | 3.56 | 100 | 0
1943 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, , SM/07852 | Retrofitting | Acceptance cum work order for Restoration of pipeline by withdrawn & relaying of different dia. UPVC pipe line for extra widening of PWD road from Ghoshpara More to Sri Chaitanya Math within Hingalganj W/S Scheme (Zone-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 1653/HSD | 05/10/2021 | 15 | MONDAL & CO. (BASIRHAT). | 4.61 | 4.6 | 100 | 0
1944 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC , SM/12274 | Augmentation | Material Requisition To Resource Division | 491/BD | 17/02/2023 | 0 | Resource Division | 184.92 | 0 | 0 | 0
1945 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC , SM/12274 | Augmentation | Material Requisition To Resource Division | 608/BD | 23/02/2023 | 0 | Resource Division | 40.91 | 0 | 0 | 0
1946 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC , SM/12274 | Augmentation | Material Requisition To Resource Division | 4410/BD | 10/11/2023 | 0 | Resource Division | 12.32 | 0 | 0 | 0
1947 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC , SM/12274 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. II and III (Rep.) under Dhanyakuria W/S Scheme District of 24 Pgs. (N) 2022_PHED_426715_22 (N.I.E.T No. 26 of EE / EMD of 2022-2023) | 6726/EMD | 28/11/2023 | 30 | S.S.ENTERPRISES | 26.67 | 0 | 0 | 0
1948 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC , SM/12274 | Augmentation | Special Repairing of DI pipe, Supply of Sluice valve & construction of Sluice valve chamber for Augmentation of Dhanyakuria Water Supply Scheme in Basirhat-II block of North 24 Parganas district under Barasat Division, P.H.E. Dte. | 935/BHTSD | 24/05/2024 | 7 | ANKUSH CONSTRUCTION & CO. | 0.88 | 0 | 0 | 0
1949 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC , SM/12274 | Augmentation | Special Repairing of existing HDPE & UPVC pipelines for Augmentation of Dhanyakuria Water Supply Scheme in Basirhat-II block of North 24 Parganas district under Barasat Division, P.H.E. Dte. | 936/BHTSD | 24/05/2024 | 7 | ANKUSH CONSTRUCTION & CO. | 0.98 | 0 | 0 | 0
1950 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC , SM/12274 | Augmentation | Hiring additional Diesel Luxury Car on daily basis for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. (Period: 01.07.2023 to 31.12.2023) | 605/BHTSD | 28/06/2023 | 184 | OM ENTERPRISE | 0.87 | 1.91 | 218.98 | 0
1951 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC , SM/12274 | Augmentation | Continuation Work for Hiring additional Diesel Luxury Car on daily basis for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. (Period: 01.01.2024 to 30.06.2024) | 1291/BHTSD | 29/12/2023 | 183 | OM ENTERPRISE | 0.86 | 1.71 | 197.28 | 0
1952 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC , SM/12274 | Augmentation | Material Requisition To Resource Division | 3480/BD | 10/12/2024 | 0 | Resource Division | 99.05 | 0 | 0 | 0
1953 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC , SM/12274 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Dhanyakuria water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | 3343/BD | 16/11/2022 | 991 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 888.3 | 529.45 | 59.6 | 36
1954 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC , SM/12274 | Augmentation | Hiring of Diesel Luxury Car is essential for proper supervision of huge number of ground water based Augmentation Scheme at different blocks under Basirhat Sub-Division P.H.E. Dte. (Period 01.07.2024 to 31.12.2024 for Six Month), Sl.No. - 01 | 1017/BHTSD | 28/06/2024 | 184 | OM ENTERPRISE | 0.87 | 2.03 | 231.71 | 0
1955 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC , SM/12274 | Augmentation | Acceptance cum work order for Eucalyptus Bullah Pilling for Emergency protection Work of Pipe line at different places for Augmentation of Dhanyakuria Water Supply Scheme of Basirhat Sub Division under Barasat Division P.H.E. | 542/BD | 19/02/2025 | 30 | SAMIR KUMAR DEY. | 52.24 | 0 | 0 | 0
1956 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhanyakuria to accommodate FHTC , SM/12274 | Augmentation | Special repairing of Rising main and pipe lines at Dhanyakuria water supply scheme under Basirhat Sub-Division under Barasat Division PHE Dt | 1031/BHTSD | 28/06/2024 | 7 | ANKUSH CONSTRUCTION & CO. | 0.89 | 0 | 0 | 100
1957 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Magurali and its adjoining mouzas to accommodate FHTC , SM/11655 | Augmentation | Material Requisition To Resource Division | 3816/BD | 23/12/2022 | 0 | Resource Division | 119.56 | 0 | 0 | 0
1958 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Magurali and its adjoining mouzas to accommodate FHTC , SM/11655 | Augmentation | Material Requisition To Resource Division | 610/BD | 23/02/2023 | 0 | Resource Division | 10.1 | 0 | 0 | 0
1959 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Magurali and its adjoining mouzas to accommodate FHTC , SM/11655 | Augmentation | Material Requisition To Resource Division | 4408/BD | 10/11/2023 | 0 | Resource Division | 6.16 | 0 | 0 | 0
1960 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Magurali and its adjoining mouzas to accommodate FHTC , SM/11655 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Magurali water supply scheme in Baduria block under Barasat Division, PHE Dte. | 3342/BD | 16/11/2022 | 1074 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 567.42 | 400.47 | 70.58 | 71
1961 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Magurali and its adjoining mouzas to accommodate FHTC , SM/11655 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery along with allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Magurali and P.H. No.- II under Chandipur W/S Scheme District of 24 Pgs. (N) | 4935/EMD | 18/08/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 39.08 | 0 | 0 | 0
1962 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Champapukuria to accommodate FHTC , SM/11586 | Augmentation | Material Requisition To Resource Division | 2308/BD | 03/08/2022 | 0 | Resource Division | 2.43 | 0 | 0 | 0
1963 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Champapukuria to accommodate FHTC , SM/11586 | Augmentation | Material Requisition To Resource Division | 4418/BD | 10/11/2023 | 0 | Resource Division | 6.16 | 0 | 0 | 0
1964 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Champapukuria to accommodate FHTC , SM/11586 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method at Pump House 1 using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Champapukuria Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | 3261/BD | 25/11/2024 | 30 | NEW MA TARA ENTERPRISE. | 21.59 | 0 | 0 | 0
1965 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Champapukuria to accommodate FHTC , SM/11586 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipeline and Providing FHTC (Functional Household Tap Connection ) for augmentation of Champapukuria water supply scheme in Basirhat-II block of North 24 Parganas Distruct under Barasat Division, PHE Dte. | 3473/BD | 01/12/2022 | 90 | UTPAL CONSTRUCTION & CO. | 211.02 | 210.11 | 100 | 92
1966 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Champapukuria to accommodate FHTC , SM/11586 | Augmentation | Acceptance cum work order for special repair and renovation of existing structures like Pump House, boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Champapukur, Chandipur, Dakhin Debipur, Dhopaberia, Srinagar and Sangrampur Water Supply Scheme of different block under Basirhat Sub-Division, PHE Dte. | 2424/BD | 14/07/2025 | 150 | DAS ENTERPRISE | 82.86 | 0 | 0 | 0
1967 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC , SM/11593 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Chhaygharia (Zone-I) Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 123/BON | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.45 | 3.45 | 50 | 1
1968 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC , SM/11593 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Chhayageria Zone-I water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 533/BD | 03/11/2021 | 21 | DURGA ENTERPRISE. | 2.52 | 2.48 | 100 | 1
1969 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC , SM/11593 | Augmentation | Material Requisition To Resource Division | 3655/BD | 13/12/2022 | 0 | Resource Division | 20.38 | 0 | 0 | 0
1970 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC , SM/11593 | Augmentation | Material Requisition To Resource Division | 3688/BD | 14/12/2022 | 0 | Resource Division | 35.66 | 0 | 0 | 0
1971 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC , SM/11593 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Chhayagharia(Zone-I) Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 3604/BD | 09/12/2022 | 90 | MONDAL ENTERPRISE. (BARASAT) | 462.8 | 461.39 | 99.7 | 1
1972 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC , SM/11593 | Augmentation | Acceptance cum work order for Construction of Boundary wall, Approach Road, Earth Filling and Construction of 3.60 mtr. X 3.00 mtr. size Guard Room with sanitary and water supply arrangement incl. plinth protection at OHR site of Chhayagharia Water Supply Scheme (Z-I), Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 2420/BD | 23/08/2024 | 60 | ACHINTA KUMAR HALDER. | 28.75 | 0 | 0 | 0
1973 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC , SM/11593 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chhaighoria (Zone-I) water supply scheme at Head Work Site under Bongaon Sub-Division P.H.E.Dte. | 2683/BD | 04/09/2023 | 30 | DHELA BABA ENTERPRISE | 16.17 | 14.45 | 100 | 100
1974 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC , SM/11593 | Augmentation | Installation of CCTV Camera Connection at Pump house no 1 & 2 for Chhaygharia (Zone-I) w/s scheme, Bongaon Block under Bongaon Sub-Division, PHE Dte. | 533/Bon | 22/04/2025 | 7 | ELDORADO | 0.55 | 0 | 0 | 0
1975 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC , SM/11593 | Augmentation | Installation of CCTV Camera Connection at Pump house no 1 & 2 for Bongaon S.D. Hospital w/s scheme, Bongaon Block under Bongaon Sub-Division, PHE Dte. | 532/Bon | 22/04/2025 | 7 | ELDORADO | 0.55 | 0 | 0 | 0
1976 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC , SM/11593 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chhayageria (Zone-I) water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | 2691/BD | 04/09/2023 | 540 | JOY HIND TUBEWELLS. | 16.16 | 0 | 0 | 100
1977 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC , SM/11593 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at 1st Tube Well & 2nd Tube Well site and Construction of Approach Road at 1st Tube Well & 2nd Tube Well site under Augmentation of Chhaygharia (Zone-I) Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 559/BD | 22/02/2024 | 495 | KAMAL HALDER. | 7.2 | 3.15 | 43.82 | 60
1978 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC , SM/11593 | Augmentation | Additional laying of UPVC pipe to connect every house hold FHTC with Augmentation work at Chhaygharia (Zone-I) W/S Scheme under Bongaon block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. (Part-A) | 1504/Bon | 30/12/2024 | 150 | IMPULSE INTERNATIONAL | 4.79 | 0 | 0 | 100
1979 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC , SM/11598 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Shimulpur Water Supply Scheme in Gaighata Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 144/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.34 | 0 | 0 | 1
1980 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC , SM/11598 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Shimulpur Water Supply Scheme in Gaighata Block withinthe Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 144/ BON | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.34 | 4.32 | 100 | 1
1981 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC , SM/11598 | Augmentation | Work order for repairing & renovation of Pump House and allied works of Simulpur Water Supply Scheme. | 587/ BON | 15/12/2021 | 21 | ONKAR ENTERPRISE. | 2.52 | 2.32 | 100 | 1
1982 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC , SM/11598 | Augmentation | Repairing & Renovation of 01No. Pump House and allied works at Shimulur water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 631/ BON | 31/12/2021 | 15 | ONKAR ENTERPRISE. | 1.26 | 1.15 | 100 | 1
1983 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC , SM/11598 | Augmentation | Material Requisition To Resource Division | 3690/BD | 14/12/2022 | 0 | Resource Division | 52.1 | 0 | 0 | 0
1984 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC , SM/11598 | Augmentation | Material Requisition To Resource Division | 3654/BD | 13/12/2022 | 0 | Resource Division | 40.85 | 0 | 0 | 0
1985 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC , SM/11598 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Shimulpur water supply scheme at Head Work Site under Bongaon Sub-Division P.H.E.Dte. | 2697/BD | 04/09/2023 | 30 | NADIA TUBEWELLS | 16.16 | 13.93 | 100 | 100
1986 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC , SM/11598 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Rep) under Shimulpur W/S Scheme and Pump House No-I and II (Rep.) under Ichapur W/S Scheme and Kalupur W/S Scheme District of 24 Pgs. (N) | 4798/EMD | 09/08/2023 | 30 | ORIENTAL ENGINEERING CO. | 91.05 | 27.49 | 70.46 | 80
1987 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC , SM/11598 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Shimulpur Water Supply Scheme (2nd T/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte | 2936/BD | 27/09/2023 | 442 | JOY GURU ENTERPRISE | 16.12 | 5.24 | 30.69 | 100
1988 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC , SM/11598 | Augmentation | Acceptance cum work order for Repairing of Boundary wall and Construction of Approach Road at Head Work site, 2nd Pump House Site & 3rd Pump House Site under Augmentation of Shimulpur Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 564/BD | 22/02/2024 | 45 | M/S SUKANTA ENTERPRISE. | 12.72 | 12.7 | 100 | 100
1989 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC , SM/11598 | Augmentation | Formal work order for Additional laying of UPVC pipe with allied works to connect every house hold connection under Augmentation work at Simulpur W/S Scheme Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 610/BD | 27/02/2024 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 102.67 | 102.66 | 100 | 100
1990 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC , SM/11598 | Augmentation | Acceptance cum work order for Improvement of Iron Elimination Plant and other related allied works and Repairing and renovation of Compressor Room for Iron Elimination Plant under Augmentation of Shimulpur Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 628/BD | 28/02/2024 | 45 | TAPAN GHOSH. | 6.03 | 1.59 | 20.94 | 100
1991 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC , SM/11598 | Augmentation | Construction of Latrine at Head Work site for Augmentation of Shimulpur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 672/Bon | 26/05/2025 | 45 | A.D.ENTERPRISE. | 1.75 | 0 | 0 | 0
1992 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC , SM/11598 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection(FHTC) for Augmentation of Shimulpur water supply scheme under Bongaon Sub-Division, P.H.E Dte. | 1126/BD | 11/04/2023 | 720 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 639.23 | 623.21 | 97.56 | 100
1993 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC , SM/11667 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Matiagacha W/S Scheme in Habra - II Block under Barasat Division, P.H.E. Dte. | 128/HAB | 16/03/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.35 | 3.27 | 50 | 1
1994 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC , SM/11667 | Augmentation | Repairing & Renovation of 01No. Pump House and allied works at Matiagacha water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 530/BON | 03/11/2021 | 21 | KAMAL HALDER. | 2.52 | 2.5 | 100 | 1
1995 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC , SM/11667 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. II under Matigacha (Block:-Barasat-II) W/S Scheme District of 24 Pgs. (N) N.I.E.T No. 27 of EE / EMD of 2022-2023 (2022_PHED_431015_28) | 6731/EMD | 28/11/2023 | 30 | M.D. ENTERPRISE | 10.69 | 0 | 0 | 0
1996 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC , SM/11667 | Augmentation | Material Requisition To Resource Division | 1252/BD | 25/04/2023 | 0 | Resource Division | 8.28 | 0 | 0 | 0
1997 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC , SM/11667 | Augmentation | Acceptance cum work order for Repairing of Boundary wall and Construction of Approach Road at Head Work site & 2nd Pump House site under Augmentation of Matiagachha Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 563/BD | 22/02/2024 | 45 | M/S SANDHYA CONSTRUCTION | 9.88 | 9.87 | 100 | 100
1998 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC , SM/11667 | Augmentation | Acceptance cum work order for Repairing and renovation works of 200 cum. capacity 20mtr. Staging height R.C.C. Over Head water Reservoir for Augmentation of Matiagachha Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1535/BD | 07/06/2024 | 45 | B.S.ENTERPRISE. (BASIRHAT) | 13.15 | 13.11 | 100 | 100
1999 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC , SM/11667 | Augmentation | Payment of invoice bill for new service connection at PH-III under Matiagacha W/S Scheme. | BP-303-23-24 | 04/03/2024 | 0 | W.B.S.E.D.C.L. (GANGANAGAR C.C.C.) | 3.94 | 0 | 0 | 0
2000 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC , SM/11667 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II Matiagacha (Block-Habra II) W/S Scheme and Pump House No.I & II Ashudi W/S scheme District of 24 Pgs. (N) | 6738/EMD | 29/11/2023 | 550 | M/S S.R. ENTERPRISE | 42.55 | 0 | 0 | 50
2001 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC , SM/11667 | Augmentation | Formal work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe under Augmentation work at Matiagachha W/S Scheme at Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (SM/11667) | 3130/BD | 12/11/2024 | 270 | M/S SUKANTA ENTERPRISE. | 115.81 | 0 | 0 | 30
2002 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC , SM/11667 | Augmentation | Formal work order fior Laying of DI rising main, UPVC distribution pipe line and Providing Functional Household Tap Connection for augmentation of Matiagacha Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 1356/BD | 04/05/2023 | 720 | M/S R.K. ENTERPRISE | 231.73 | 130.41 | 87.2 | 80
2003 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC , SM/11667 | Augmentation | Construction of damaged part of Boundary wall due to Sinking of Big dia. T/W, Connection of 2nd T/W with rising main by DI & UPVC pipe line, Construction of Valve Chamber & Inspection pit and allied works for Augmentation of Matiagachha W/S Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1506/Bon | 30/12/2024 | 90 | M/S SANDHYA CONSTRUCTION | 3.68 | 0 | 0 | 100
2004 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Diara to accommodate FHTC , SM/11668 | Augmentation | Material Requisition To Resource Division | 3711/BD | 15/12/2022 | 0 | Resource Division | 14.86 | 0 | 0 | 0
2005 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Diara to accommodate FHTC , SM/11668 | Augmentation | Repairing & Renovation 2(Two) nos of Pump House and allied works of Kola water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 516/Bon | 31/12/2021 | 21 | ROY ENGINEERS. | 2.52 | 0 | 0 | 1
2006 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Diara to accommodate FHTC , SM/11668 | Augmentation | Material Requisition To Resource Division | 78/BD | 10/01/2023 | 0 | Resource Division | 118.89 | 0 | 0 | 0
2007 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Diara to accommodate FHTC , SM/11668 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Replacement) under Daora, Diara & Gokulpur W/S Scheme, District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 07) | 34/EMD | 03/01/2023 | 30 | AHALYA ENGINEERING WORKS | 70.02 | 20.11 | 95.73 | 76
2008 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Diara to accommodate FHTC , SM/11668 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Diara Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 3489/BD | 02/12/2022 | 90 | MONDAL & CO. (BASIRHAT). | 380.98 | 355.91 | 100 | 100
2009 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Diara to accommodate FHTC , SM/11668 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tube well by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Diara Water Supply Scheme (2nd T/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | 2920/BD | 26/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.12 | 13.79 | 100 | 100
2010 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Diara to accommodate FHTC , SM/11668 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Diara water supply scheme at Head Work Site under Bongaon Sub-Division P.H.E.Dte. | 2696/BD | 04/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.1 | 13.54 | 100 | 100
2011 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Diara to accommodate FHTC , SM/11668 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Head work site for Augmentation of Diara water Supply scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division, under Barasat Division P.H.E. Dte. | 4414/BD | 10/11/2023 | 60 | ACHINTA KUMAR HALDER. | 14.5 | 14.5 | 100 | 100
2012 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Diara to accommodate FHTC , SM/11668 | Augmentation | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and Construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Diara Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 39/BD | 04/01/2024 | 391 | J AND T ENTERPRISE | 8.89 | 0 | 0 | 0
2013 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Diara to accommodate FHTC , SM/11668 | Augmentation | Formal work order for Construction of 200 cum capacity CWR with pipe connection, Construction of Boundary wall, Approach Road, Earth Filling, Construction of 5.40 mtr. X 3.60 mtr. size Switch Room with sanitary and water supply arrangement and Laying of DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah pile at different places at Diara (Zone-II) Water Supply Scheme in connection with surface water based water supply scheme of Bongaon-Bagdah in the District of North 24 Parganas under Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 2222/BD | 07/08/2024 | 360 | ROY CHOWDHURY CONSTRUCTION. | 108.24 | 23.3 | 21.53 | 60
2014 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Diara to accommodate FHTC , SM/11668 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 250 mtr deep Tubewell by D.R. Rig method having 300 mm. dia. 36 mtr. long housing pipe & 200 mm. dia. 30 mtr. long ribbed strainer at Head Work site for Augmentation of Diara (Zone-II) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 2042/BD | 20/06/2025 | 60 | JOY GURU ENTERPRISE | 16.37 | 0 | 0 | 0
2015 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Diara to accommodate FHTC , SM/11668 | Augmentation | Acceptance cum work order for Improvement of existing IEP & other related allied works and including adding 1 no. Polishing unit (3.15 m. dia. x 1.50 m. ht.) (including media) under Augmentation of Diara Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 2074/BD | 24/06/2025 | 45 | ONKAR ENTERPRISE. | 21.65 | 0 | 0 | 0
2016 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Diara to accommodate FHTC , SM/11668 | Augmentation | Acceptance cum work order for Special Repairing work in connection with augmentation work at total command area of Diara Water Supply Scheme, to repair the damaged pipeline due to road widening and drain construction and also to convert the 'Kapashati' mouza (JL No. 73) in to Swajal Gram within Bongaon Sub Division, under Barasat Division, P.H.E.Dte. | 2859/BD | 14/08/2025 | 45 | ROY ENGINEERS. | 7.98 | 0 | 0 | 0
2017 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC , SM/11669 | Augmentation | Material Requisition To Resource Division | 921/BD | 22/03/2023 | 0 | Resource Division | 101.89 | 0 | 0 | 0
2018 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC , SM/11669 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Replacement) under Bharatpur W/S Scheme, Patua W/S Scheme (P/H-I & II) & Chaital W/S Scheme (P/H -I & II) District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 04) | 31/EMD | 03/01/2023 | 819 | M/S P.P. ELECTRICALS | 74.67 | 13.02 | 49.2 | 73
2019 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC , SM/11669 | Augmentation | Formal work order for Additional Laying of DI/UPVC distribution pipe line and Providing Functional Household Tap Connection for the leftout portion in connection with Augmentation of Chaital water supply scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 881/BD | 14/03/2024 | 90 | M/S B.K.ENTERPRISE. | 140.08 | 63.01 | 44.98 | 80
2020 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC , SM/11669 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Chaital water supply scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 517/BD | 20/02/2023 | 90 | M/S B.K.ENTERPRISE. | 372.13 | 351.13 | 100 | 100
2021 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC , SM/11669 | Augmentation | Formal work order for construction of 500 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Chaital water supply scheme, Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | 2614/BD | 29/08/2023 | 365 | M/S B.K.ENTERPRISE. | 203.43 | 120.47 | 59.22 | 75
2022 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC , SM/11669 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection with augmentation of Chaital water supply scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 264/HSD | 30/01/2025 | 10 | M/S R.B.S.ENTERPRISE. | 0.62 | 0 | 0 | 100
2023 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC , SM/11669 | Augmentation | Acceptance cum work order for Sand filling at ditch area for construction of temporary approach road for movement of winch machine and other allied machineries at OHR site within Chaital W/S scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte | 324/HSD | 04/02/2025 | 10 | M/S R.B.S.ENTERPRISE. | 0.95 | 0 | 0 | 100
2024 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC , SM/11669 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with augmentation of Chaital water supply scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 478/HSD | 28/02/2025 | 10 | M/S K.B.ENTERPRISE. | 0.61 | 0 | 0 | 100
2025 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Palla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/11212 | Augmentation | Survey, Design and preparation of Augmentation DPR in connection with Providing functional household tap connection to every Household under Palla Zone-I W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte. | 1173/NWSD-I | 31/12/2021 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.81 | 4.81 | 100 | 0
2026 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Palla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/11212 | Augmentation | Material Requisition To Resource Division | 388/NWSD-I | 06/04/2023 | 0 | Resource Division | 245.61 | 0 | 0 | 0
2027 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Palla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/11212 | Augmentation | Material Requisition To Resource Division | 1841/NWSD-I | 10/11/2023 | 0 | Resource Division | 3.08 | 0 | 0 | 0
2028 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Palla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/11212 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) (Rep) under Palla W/S Scheme District of 24 Pgs. (N) | 4739/EMD | 07/08/2023 | 30 | KASHINATH PAL & CO. | 26.51 | 18.76 | 70.76 | 10
2029 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Palla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/11212 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.III and IV (Zone-I) (Rep) under Palla W/S Scheme District of 24 Pgs. (N) | 4738/EMD | 07/08/2023 | 30 | MAA KALI ENTERPRISE | 26.07 | 15.3 | 58.69 | 65
2030 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Palla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/11212 | Augmentation | Repair and renovation works for 900 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir, Boundary wall, Pump House at H/W site and PH-II , III & IV with other allied works at Palla (ZONE-I) W/S Scheme under North 24 Pgs Water Supply Division- I, P.H.E. Dte. | 1238/NWSD-I | 18/08/2023 | 60 | M/S. R. M. CONSTRUCTION | 55.82 | 55.39 | 100 | 100
2031 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Palla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/11212 | Augmentation | WITHDRAWING & STACKING OF DISTRIBUTION 300 MM DIA DI K-7 PIPE FROM BELTA WORK SITE TO DIFFERENT DEPARTMENTAL STORE UNDER NORTH 24 PGS W/S SUB-DIVISION-I, PHE DTE. | 143/NWSD-I | 24/01/2024 | 14 | NIKHIL SAMADDAR | 6.19 | 4.03 | 100 | 80
2032 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Palla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/11212 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1430/NWSD-I | 18/09/2024 | 7 | BIBHAS PAL | 5.27 | 0.35 | 50 | 100
2033 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Palla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/11212 | Augmentation | Material Requisition To Resource Division | 1308/NWSD-I | 30/08/2024 | 0 | Resource Division | 3.08 | 0 | 0 | 0
2034 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Palla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/11212 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system & Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works within command area of PALLA Zone-I Water Supply Scheme under North 24 Parganas Water Supply Division-I, PHE. | 1197/NWSD-I | 12/10/2022 | 90 | ALOK ENTERPRISE, A UNIT OF SAKET TREXIM PVT. LTD. | 663.85 | 457.25 | 68.88 | 55
2035 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Palla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/11212 | Augmentation | Renovation of AIRP at Palla Water Supply Scheme of capacity 175 Cu.m/hr of Bongaon Block under North 24 Pgs. W/S Div-I, PHE Dte. | 1589/NWSD-I | 29/10/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS(P) LTD. | 122.28 | 0 | 0 | 78
2036 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Palla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. , SM/11212 | Augmentation | Construction of Godown at Head Work site for Augmentation of Palla (Zone-I) Water Supply Scheme, Bongaon Block of North 24 Parganas District within the jurisdiction of N24Pgs. W/S Division-I, P.H.E. Dte. | 600/NWSD-I | 22/04/2025 | 15 | M/S. R. M. CONSTRUCTION | 6.94 | 0 | 0 | 0
2037 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-I) to accommodate FHTC , SM/11525 | Augmentation | Route Survey, Design Drawing & DPR Preparation for SADIKNAGAR-I Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 206/ BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.15 | 3.96 | 50 | 1
2038 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-I) to accommodate FHTC , SM/11525 | Augmentation | Material Requisition To Resource Division | 3816/BD | 23/12/2022 | 0 | Resource Division | 17.46 | 0 | 0 | 0
2039 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-I) to accommodate FHTC , SM/11525 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Zone-I) (Replacement) under Sadiknagar W/S Scheme District of 24 Pgs. (N). (SM/11525) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 24) | 6396/EMD | 24/11/2022 | 30 | S.S.ENTERPRISES | 13.04 | 11.5 | 88.18 | 0
2040 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-I) to accommodate FHTC , SM/11525 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Zone-I) (Replacement) under Sadiknagar W/S Scheme District of 24 Pgs. (N). (SM/11525) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 26) | 6397/EMD | 24/11/2022 | 30 | ESENCE ENGINEERING CONCERN | 13.08 | 11.53 | 88.2 | 0
2041 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-I) to accommodate FHTC , SM/11525 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Sadik Nagar Zone-I water supply scheme in Basirhat-II Block under Barasat Division, P.H.E Dte. | 3605/BD | 09/12/2022 | 90 | PUSPA ENTERPRISE. | 406.99 | 395.2 | 100 | 100
2042 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-I) to accommodate FHTC , SM/11525 | Augmentation | Material Requisition To Resource Division | 4404/BD | 10/11/2023 | 0 | Resource Division | 18.48 | 0 | 0 | 0
2043 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-I) to accommodate FHTC , SM/11525 | Augmentation | Enhancement of GST for laying of distribution pipe line and providing FHTC for Augmentation of Sadiknagar Zone -I water supply scheme under Basirhat Sub-Division, P.H.E.Dte. | BP-2024-25-391 | 04/10/2024 | 0 | PUSPA ENTERPRISE. | 13.91 | 0 | 0 | 0
2044 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIII (Aziznagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12413 | Augmentation | Detail route survey, design of distribution network and preparation of estimate drawing & DPR for providing FHTC in the scheme of Zone-XIII (Aziznagar) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | 1065/NWSD-I | 05/09/2022 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.51 | 3.55 | 100 | 0
2045 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIII (Aziznagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12413 | Augmentation | Material Requisition To Resource Division | 460/NWSD-I | 26/04/2023 | 0 | Resource Division | 103.34 | 0 | 0 | 0
2046 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIII (Aziznagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12413 | Augmentation | Material Requisition To Resource Division | 1205/NWSD-I | 14/08/2023 | 0 | Resource Division | 20.13 | 0 | 0 | 0
2047 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIII (Aziznagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12413 | Augmentation | New service connection at OHR Site of Aziznagar water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). Type : | BP-343-23-24 | 11/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.48 | 0 | 0 | 0
2048 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIII (Aziznagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12413 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure, Proposed Rising Main System, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Repair And Renovation Works of R.C.C. Elevated Reservoir 900 Cum, Construction Of Pump House (4.88m X 3.66m) Including Sanitary Arrangement, Repairing of Boundary Wall Construction Of Service Road for 60 Mtr. length, Improvement of land, Special Repair And Renovation Of Chlorine Room and Guard Room for Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of ZONE - XIII AZIZNAGAR in Deganga Block of North 24 Pargana(s) District under N24 Pgs W/S Div-I, PHE Dte. | 1146/NWSD-I | 07/08/2023 | 879 | M/S. S.S. ENTERPRISE | 533.66 | 308.54 | 57.82 | 85
2049 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC , SM/11761 | Augmentation | Material Requisition To Resource Division | 1240/BD | 25/04/2023 | 0 | Resource Division | 13.72 | 0 | 0 | 0
2050 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC , SM/11761 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Gadpukuria (Zone-I) Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | 2926/BD | 26/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.12 | 13.81 | 100 | 100
2051 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC , SM/11761 | Augmentation | Acceptance cum work order for Renovation of 103 Cum/hr of capacity AIRP and allied works at Head work site for Augmentation of Gadpukuria (Zone-I) water Supply Scheme under Bongaon Sub-Division, Barasat Division P.H.E. Dte. | 13/BD | 02/01/2024 | 365 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 77.74 | 70.84 | 99.75 | 100
2052 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC , SM/11761 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Head work site for Augmentation of Gadpukuria (Zone-I) water Supply scheme, Bagdah Block within jurisdiction of Bongaon Sub-Division, P.H.E. Dte. | 4411/BD | 10/11/2023 | 60 | GHOSH CONSTRUCTION. | 19.46 | 19.43 | 100 | 100
2053 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC , SM/11761 | Augmentation | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Gadpukuria (Zone-I) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division P.H.E. Dte. | 4462/BD | 21/11/2023 | 23 | A.D.ENTERPRISE. | 11.48 | 11.45 | 100 | 100
2054 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC , SM/11761 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional Household Tap Connection (FHTC) for augmentation of Gadpukuria (Zone-I) Water Supply Scheme under Bongaon Sub-Division, PHE Dte | 1396/BD | 08/05/2023 | 899 | M/S DIPAK ENTERPRISE | 343.41 | 259.65 | 75.61 | 90
2055 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC , SM/11761 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at P.H. No.-II ,ZONE-I (Replacement TUBE WELL) under Gadpukuria ground water based w/s scheme under Block_ Bagdah Dist. - 24Pgs(N) under EMSD-I, PHE Dte. | 2534/EMD | 28/10/2024 | 30 | BIJAN ENTERPRISE | 11.78 | 0 | 0 | 0
2056 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC , SM/11761 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at P.H. No.-I and II ,ZONE-II (NEW TUBE WELL) under Gadpukuria ground water based w/s scheme under Block_ Bagdah Dist. - 24Pgs(N) under EMSD-I, PHE Dte. | 2535/EMD | 28/10/2024 | 124 | JAGANNATH ENTERPRISE | 23.56 | 0 | 0 | 95
2057 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC , SM/11761 | Augmentation | Acceptance cum work order for Additional laying of UPVC pipe to connect every house hold FHTC with Augmentation work at Gadpukuria (Zone-I) W/S Scheme under Bagdah Block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | 1699/BD | 23/05/2025 | 60 | THE TOWER CONSTRUCTION | 14.88 | 0 | 0 | 0
2058 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC , SM/11761 | Augmentation | Acceptance cum work order for Repairing and repairing work for 500cum capacity 20mtr. staging height R.C.C Over Head Reservoir for Augmentation of Gadpukur (Zone-I) Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division P.H.E. Dte. | 1536/BD | 07/06/2024 | 45 | ONKAR ENTERPRISE. | 20.09 | 0 | 0 | 100
2059 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Gadpukuria Zone-I to Accommodate FHTC , SM/11761 | Augmentation | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site under Augmentation work at Gadpukuria (Zone - I) W/S Scheme Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1543/BD | 15/05/2025 | 120 | H.I.ENTERPRISE. | 34.28 | 0 | 0 | 100
2060 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC , SM/11762 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Gadpukuria (Zone-II) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 129/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.73 | 3.73 | 50 | 1
2061 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC , SM/11762 | Augmentation | Material Requisition To Resource Division | 3686/BD | 14/12/2022 | 0 | Resource Division | 76.22 | 0 | 0 | 0
2062 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC , SM/11762 | Augmentation | Material Requisition To Resource Division | 1860/BD | 23/06/2023 | 0 | Resource Division | 5.56 | 0 | 0 | 0
2063 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC , SM/11762 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Head work site for Augmentation of Gadpukuria (Zone-II) water Supply scheme, Bagdah Block within jurisdiction of Bongaon Sub-Division, P.H.E. Dte. | 4410/BD | 10/11/2023 | 60 | PRABIR KUMAR MONDAL. | 15.9 | 10.04 | 63.16 | 85
2064 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC , SM/11762 | Augmentation | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and Construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Gadpukuria (Zone-II) water Supply scheme, Bagdah Block within jurisdiction of Bongaon Sub-Division, P.H.E. Dte. | 4486/BD | 23/11/2023 | 414 | MA CONSTRUCTION. | 9.25 | 0 | 0 | 45
2065 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC , SM/11762 | Augmentation | Acceptance cum work order for Hiring Diesel Luxury Car on Daily basis ( from 01.01.2024 to 31.03.2024) for the office use of Deputy Superintending Engineer, Planning Circle-I, PHE Dte. | 4876/BD | 29/12/2023 | 91 | M/S B.K.ENTERPRISE. | 0.43 | 1.03 | 237.24 | 100
2066 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC , SM/11762 | Augmentation | Acceptance cum work order for Hiring Diesel Luxury Car on Daily basis for the office use of Deputy Superintending Engineer, Planning Circle-I, PHE Dte.(01-04-2024 to 30-06-2024). | 926/BD | 15/03/2024 | 91 | M/S B.K.ENTERPRISE. | 0.43 | 1.02 | 235.32 | 100
2067 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC , SM/11762 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. Tube well 250 mtr deep by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Gadpukuria (Zone - II) Water Supply Scheme at H/W Site & 2nd T/W Site under Bongaon Sub-Division, P.H.E. Dte. | 2831/BD | 15/09/2023 | 60 | B.M.ENGINEERING. & CONSTRUCTION. | 32.24 | 27.49 | 100 | 100
2068 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC , SM/11762 | Augmentation | Hiring of Luxury Car (Diesel/Driven) for the office use of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Barasat Division P.H.E. Dte. (Period from:- 01/08/2023 to 31/01/ 2024). | 591/Bon | 31/07/2023 | 184 | ROY ENGINEERS. | 0.87 | 1.67 | 100 | 100
2069 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC , SM/11762 | Augmentation | Acceptance cum work order for Withdrawing & relaying of existing UPVC distribution system along the same alignment due to widening and strengthening of Zilla Parishad road from Buzar Bagee Kalitala to Chatar Bagee inconnection with augmentation work at Godpukuria (Zone-II) W/S Scheme under Bagdah block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | 652/BD | 29/02/2024 | 30 | R.K.MANDAL & CO. | 8.92 | 8.81 | 100 | 100
2070 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC , SM/11762 | Augmentation | Acceptance cum work order for Construction of 5.40 mtr. X 3.60mtr. size Switch room with sanitary and water supply arrangement incl. plinth protection at Head Work site at Gadpukuria w/s scheme (Zone-II), Bagdah Block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | 608/BD | 23/02/2024 | 45 | UPWARDS ENGINEERING PRIVATE LIMITED. | 5.57 | 5.57 | 100 | 100
2071 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC , SM/11762 | Augmentation | Construction of 3.60 mtr. X 3.00mtr. size Switch room with sanitary and water supply arrangement incl. plinth protection at 2nd Tube Well site at Gadpukuria w/s scheme (Zone-II), Bagdah block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | 210/Bon | 27/02/2024 | 45 | ONKAR ENTERPRISE. | 4.35 | 4.35 | 100 | 100
2072 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC , SM/11762 | Augmentation | New service connection at P.H.No- I,Zone-II of Gadpukuria water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). | BP-350-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.04 | 0 | 0 | 0
2073 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC , SM/11762 | Augmentation | New service connection at P.H.No- II,Zone-II of Gadpukuria water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). | BP-349-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5 | 0 | 0 | 0
2074 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC , SM/11762 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at P.H. No.-I and II ,ZONE-II (NEW TUBE WELL) under Gadpukuria ground water based w/s scheme under Block_ Bagdah Dist. - 24Pgs(N) under EMSD-I, PHE Dte. | 2535/EMD | 28/10/2024 | 124 | JAGANNATH ENTERPRISE | 23.56 | 0 | 0 | 95
2075 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kapileswarpur to accommodate FHTC , SM/11763 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Kapileswarpur Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 445/ BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.04 | 4.04 | 50 | 1
2076 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kapileswarpur to accommodate FHTC , SM/11763 | Augmentation | Material Requisition To Resource Division | 3810/BD | 23/12/2022 | 0 | Resource Division | 2.38 | 0 | 0 | 0
2077 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kapileswarpur to accommodate FHTC , SM/11763 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Kapileswarpur water supply scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, PHE Dte. | 3305/BD | 10/11/2022 | 90 | KINGS & CO. | 240.31 | 205.3 | 100 | 90
2078 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kapileswarpur to accommodate FHTC , SM/11763 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Kapileswarpur W/S Scheme District of 24 Pgs. (N) | 6756/EMD | 28/11/2023 | 490 | M/S DAS ENTERPRISE | 26.73 | 4.17 | 15.59 | 60
2079 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area Kendua mouza, Jagatpur mouza and Chaita mouza (Rest part after phase-I) of Sadiknagar Zone-II Piped Water Supply Scheme, Basirh , SM/08767 | Retrofitting | Continuation Order for Hiring Diesel Luxury Car on daily basis (for 4 months from 01.03.2022 to 30.06.2022) for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. | 178/BHTSD | 25/02/2022 | 120 | DEB KUMAR DAS. | 0.58 | 1.83 | 272.13 | 1
2080 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area Kendua mouza, Jagatpur mouza and Chaita mouza (Rest part after phase-I) of Sadiknagar Zone-II Piped Water Supply Scheme, Basirh , SM/08767 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Sadiknagar Zone-II Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase II) | 1952/BD | 08/10/2021 | 30 | SUDHAMAY MAJUMDAR. | 58.36 | 53.39 | 100 | 1
2081 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area Kendua mouza, Jagatpur mouza and Chaita mouza (Rest part after phase-I) of Sadiknagar Zone-II Piped Water Supply Scheme, Basirh , SM/08767 | Retrofitting | Hiring Diesel Luxury Car on daily basis (for 12 months from 01.07.2022 to 30.06.2023) for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. | 857/BHT | 27/06/2022 | 365 | DEB KUMAR DAS. | 1.73 | 1.84 | 100 | 0
2082 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area Kendua mouza, Jagatpur mouza and Chaita mouza (Rest part after phase-I) of Sadiknagar Zone-II Piped Water Supply Scheme, Basirh , SM/08767 | Retrofitting | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Basirhat-II Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - C) | 151/BHTSD | 29/01/2025 | 20 | BIBHAS PAL. | 0.88 | 0 | 0 | 90
2083 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-B (Maricha) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12729 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-VIII/B (Maricha) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 429/NWSD-I | 01/04/2022 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.9 | 4.9 | 100 | 1
2084 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-B (Maricha) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12729 | Augmentation | Material Requisition To Resource Division | 481/NWSD-I | 26/04/2023 | 0 | Resource Division | 183.51 | 0 | 0 | 0
2085 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-B (Maricha) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12729 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 307.58 | 31.94 | 2
2086 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-B (Maricha) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12729 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery to be installed at Zone-VII, C (Dariapur) for Augmentation of Zone-VIII, A/B/C in Amdanga Block of North 24 Parganas District. | 4031/ED | 17/10/2023 | 749 | M/S P.P. ELECTRICALS | 109.28 | 0 | 0 | 20
2087 | NORTH 24 PARGANAS | Barasat Division | Pipuldaha Piped Water Supply Scheme. , SM/12721 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (PIPULDAHA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. | 307/HSD | 15/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.26 | 4.26 | 100 | 1
2088 | NORTH 24 PARGANAS | Barasat Division | Pipuldaha Piped Water Supply Scheme. , SM/12721 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (PIPULDAHA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. | 307/HSD | 15/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.26 | 0 | 0 | 1
2089 | NORTH 24 PARGANAS | Barasat Division | Pipuldaha Piped Water Supply Scheme. , SM/12721 | New | Material Requisition To Resource Division | 888/BD | 22/03/2023 | 0 | Resource Division | 168.16 | 0 | 0 | 0
2090 | NORTH 24 PARGANAS | Eastern Mechanical | Pipuldaha Piped Water Supply Scheme. , SM/12721 | New | New service connection for Pipuldaha PH-II P.O.-Chandibari P.S.-minakhan | BP-249-23-24 | 20/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.25 | 0 | 0 | 0
2091 | NORTH 24 PARGANAS | Barasat Division | Pipuldaha Piped Water Supply Scheme. , SM/12721 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 100 cum capacity CWR, pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Pipuldaha w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1684/BD | 07/06/2023 | 366 | GHOSH CONSTRUCTION. | 205.49 | 132.74 | 64.6 | 75
2092 | NORTH 24 PARGANAS | Eastern Mechanical | Pipuldaha Piped Water Supply Scheme. , SM/12721 | New | Quotation for Service Connection Charges for PH- I under Pipuldaha W/S Scheme in the district of North 24 Pgs. | BP-353-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.23 | 0 | 0 | 0
2093 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme , SM/13892 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Berachampa Water Supply Scheme Zone-V under Barasat Sub Division, P.H.E. Dte. | 673/BSD | 31/08/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.61 | 3.61 | 100 | 1
2094 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme , SM/13892 | Augmentation | Material Requisition To Resource Division | 3089/BD | 10/10/2023 | 0 | Resource Division | 21.99 | 0 | 0 | 0
2095 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme , SM/13892 | Augmentation | Material Requisition To Resource Division | 1288/BD | 25/04/2023 | 0 | Resource Division | 48.13 | 0 | 0 | 0
2096 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme , SM/13892 | Augmentation | Material Requisition To Resource Division | 4366/BD | 10/11/2023 | 0 | Resource Division | 38.51 | 0 | 0 | 0
2097 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme , SM/13892 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Berachampa Zone - V 1st Tubewell site at Kaukepara Mouza within Deganga Block under Barasat Sub-Division, PHE Dte. | 3702/BD | 26/12/2024 | 30 | DEBAPRASAD MONDAL. | 27.57 | 0 | 0 | 0
2098 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme , SM/13892 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. big dia. 185 mtr deep Tubewell by D.R. Rig method having 300 mm dia 42.0 mtr. long PVC housing pipe & 200 mm dia 30.0 mtr. long filter for Augmentation Berachampa Zone-V Water Supply Scheme (Head Work Site) of Barasat Sub-Division under Barasat Division, PHE Dte. | 804/BD | 12/03/2024 | 30 | ACME CONSTRUCTION | 13.08 | 12.47 | 100 | 100
2099 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme , SM/13892 | Augmentation | Construction of Pump House with latrine at Berachampa Zone-V water Supply Scheme under Deganga Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | 1245/BSD | 15/03/2024 | 31 | SANTU GHOSH. | 4.91 | 4.9 | 100 | 90
2100 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme , SM/13892 | Augmentation | New service connection at P.H.No- I Zone- V of Berachampa water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). | BP-304-23-24 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.99 | 0 | 0 | 0
2101 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme , SM/13892 | Augmentation | Additional quotation for New service connection at P.H.No- I , Zone- V of Berachampa water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N) | BP-11-24-25 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.2 | 0 | 0 | 0
2102 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme , SM/13892 | Augmentation | Formal work order for Construction of 550 cum capacity 20 Mtr. staging height RCC Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for augmentation of Berachampa Zone-V Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | 4070/BD | 16/10/2023 | 687 | DEBAPRASAD MONDAL. | 567.01 | 187.89 | 33.14 | 45
2103 | NORTH 24 PARGANAS | Barasat Division | Paschim Huda Piped water supply scheme , SM/13895 | New | Survey, Design, Drawing & DPR preparation for new PWSS at Paschim Huda water supply scheme in the Bongaon Block under Bongaon Sub-Division, under Barasat Division, P.H.E.Dte. (Part-A) | 346/Bon | 07/07/2022 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 100 | 1
2104 | NORTH 24 PARGANAS | Barasat Division | Paschim Huda Piped water supply scheme , SM/13895 | New | Survey, Design, Drawing & DPR preparation for new PWSS at Paschim Huda water supply scheme in the Bongaon Block under Bongaon Sub-Division, under Barasat Division P.H.E. Dte. (Part-B) | 347/Bon | 07/07/2022 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.39 | 0.39 | 100 | 1
2105 | NORTH 24 PARGANAS | Barasat Division | Paschim Huda Piped water supply scheme , SM/13895 | New | Material Requisition To Resource Division | 1865/BD | 23/06/2023 | 0 | Resource Division | 7.45 | 0 | 0 | 0
2106 | NORTH 24 PARGANAS | Barasat Division | Paschim Huda Piped water supply scheme , SM/13895 | New | Acceptance cum work order for Sinking of 1 (one) no. new 300 mm. x 200 mm. dia. 300 mtr deep Tube well by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Paschim Huda Piped Water Supply Scheme at H/W Site under Bongaon Sub-Division, P.H.E. Dte. | 2833/BD | 15/09/2023 | 30 | NADIA TUBEWELLS | 21.56 | 15.48 | 100 | 100
2107 | NORTH 24 PARGANAS | Eastern Mechanical | Paschim Huda Piped water supply scheme , SM/13895 | New | New service connection at P.H.No- I of Paschim Huda water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). | BP-06-24-25 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.94 | 0 | 0 | 0
2108 | NORTH 24 PARGANAS | Eastern Mechanical | Paschim Huda Piped water supply scheme , SM/13895 | New | Additional quotation for new service connection at P.H.No- I of Paschim Huda W./S scheme under EMSD-I , PHE Dte in 24Pgs(N). | BP-168-24-25 | 27/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.07 | 0 | 0 | 0
2109 | NORTH 24 PARGANAS | Eastern Mechanical | Paschim Huda Piped water supply scheme , SM/13895 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I under Paschim Huda W/S Scheme, District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 12) | 39/EMD | 03/01/2023 | 819 | SWAPAN KUMAR BHANJA | 10.65 | 8.58 | 80.57 | 100
2110 | NORTH 24 PARGANAS | Barasat Division | Paschim Huda Piped water supply scheme , SM/13895 | New | Formal work order for Construction of 200 cum. capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile, pile cap & Soil Investigation and laying of Rising Main, Distribution Main with Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Paschim Huda Water Supply Scheme under Bongaon Sub-Division, PHE Dte. (New Scheme) | 2056/BD | 14/07/2023 | 627 | R.K.MANDAL & CO. | 323.01 | 246.37 | 74.73 | 100
2111 | NORTH 24 PARGANAS | Barasat Division | Paschim Huda Piped water supply scheme , SM/13895 | New | Acceptance cum work order for Construction of 5.40 mtr. X 3.60mtr. size Switch room with sanitary and water supply arrangement incl. plinth protection at Head Work site at Paschim Huda w/s scheme Bongaon Block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | 605/BD | 23/02/2024 | 360 | VAI ENTERPRISE. | 5.61 | 0 | 0 | 100
2112 | NORTH 24 PARGANAS | Barasat Division | Paschim Huda Piped water supply scheme , SM/13895 | New | Acceptance cum work order for Construction of Boundary wall, Approach Road and Land development at Head Work site of Paschim Huda Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 3086/BD | 29/10/2024 | 120 | R.K.MANDAL & CO. | 26.22 | 0 | 0 | 100
2113 | NORTH 24 PARGANAS | Eastern Mechanical | Paschim Huda Piped water supply scheme , SM/13895 | New | Repairing and renovation of boundary illumination arrangement and allied works at P.H. No. I under Paschim Huda W/S Scheme under EMSD-I, P.H.E.Dte. Dist.- 24PGS(N). | 452/EMSD-I | 08/04/2025 | 94 | SWAPAN KUMAR BHANJA | 4.49 | 0 | 0 | 100
2114 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Hingalganj Zone - II Piped Water Supply Scheme under Barasat Division, PHE Dte. | 636/HSD | 08/04/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.39 | 4.39 | 100 | 0
2115 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-5 & 6 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 2489/BD | 18/08/2023 | 30 | M/S DATTA ENTERPRISE. | 51.63 | 38.75 | 100 | 100
2116 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at pond of Monojit Gayen and near shop of Abdul Alim Gazi in connection with Augmentation of Hingalganj W/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 3500/BD | 11/12/2024 | 30 | S.K.ENTERPRISE. | 8.64 | 0 | 0 | 0
2117 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at N/H/O Abdul Dhali & Anar Dhali in connection with Augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 3499/BD | 11/12/2024 | 912 | SARKAR ENTERPRISE | 8.51 | 0 | 0 | 0
2118 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at N/H/O Rabiul Gazi & Enamul Gazi in connection with Augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 3740/BD | 27/12/2024 | 30 | CHITTARANJAN MONDAL | 8.19 | 0 | 0 | 0
2119 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Formal work order for Laying of UPVC/DI distribution pipe line and providing Functional Household Tap Connection for Augmentation of Hingalganj water supply scheme (Z-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 700/BD | 03/03/2023 | 90 | M/S NIRMAN CONSTRUCTION. | 313.44 | 291.97 | 100 | 40
2120 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for inking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 525/BD | 20/02/2024 | 45 | UTPAL CONSTRUCTION & CO. | 49.99 | 38.62 | 100 | 100
2121 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-5 & 6 in connection with Augmentation for Hingalganj w/s (Z-II) scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 271/HSD | 06/03/2024 | 10 | M/S RAJPATH CONSTRUCTION. | 0.96 | 0.96 | 100 | 100
2122 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Additional Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 2903/BD | 03/10/2024 | 60 | M/S RAJPATH CONSTRUCTION. | 51.59 | 0 | 0 | 0
2123 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room (3.60x3.00) with sanitary and water supply arrangement including plinth protection for Hingalganj w/s scheme (Old), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 145/BD | 13/01/2025 | 75 | ABDUL HAMID GAZI. | 10.59 | 0 | 0 | 0
2124 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Additional Construction of 2 nos. switch room cum chlorine room (Size-5.40x3.60 mtr.) for Augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 1428/BD | 06/05/2025 | 90 | SUPER ENTERPRISE | 14.14 | 0 | 0 | 0
2125 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II, III, IV,V and VI (Zone-II) (Rep.) under Hingalganj Aug. W/S Scheme, Block- Hingalganj in District of 24 Pgs. (N) | 6773/EMD | 29/11/2023 | 550 | M.S. ENTERPRISE | 63 | 18.79 | 33.13 | 32
2126 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 527/BD | 20/02/2024 | 406 | UTPAL CONSTRUCTION & CO. | 49.99 | 11.99 | 23.52 | 100
2127 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in 4 & 8 no Sandelerbill in Sandelerbill mouza in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 381/HSD | 10/02/2025 | 10 | S.K.ENTERPRISE. | 0.96 | 0 | 0 | 100
2128 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Uttar Bankra Dobar in Bankra Dobar mouza in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 474/HSD | 28/02/2025 | 10 | S.K.ENTERPRISE. | 0.96 | 0 | 0 | 100
2129 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line and other allied works in connection with retrofitting work at different places in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 164/BD | 14/01/2025 | 21 | S.K.ENTERPRISE. | 14.45 | 3.82 | 20.94 | 100
2130 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in 14 no Sandelerbill in Sandelerbill mouza in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 174/HSD | 27/01/2025 | 10 | M/S NIRMAN CONSTRUCTION. | 0.96 | 0 | 0 | 100
2131 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in 11 no Sandelerbill in Sandelerbill mouza in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 179/HSD | 27/01/2025 | 10 | M/S NIRMAN CONSTRUCTION. | 0.96 | 0 | 0 | 100
2132 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in 9 no Sandelerbill in Sandelerbill mouza in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 181/HSD | 27/01/2025 | 10 | M/S NIRMAN CONSTRUCTION. | 0.96 | 0 | 0 | 100
2133 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Singherkati mouza in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 234/HSD | 30/01/2025 | 10 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 0.96 | 0 | 0 | 100
2134 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Providing Functional household tap connection at 11 no Sandelerbill FP School, 9 no Purba Sandeslerbill FP School, Dakshin Bankra Sarkarpara SSk, Sandelerbill Jr. High School and Tarinipur SSK within the command area of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 544/HSD | 10/03/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.96 | 0 | 0 | 100
2135 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Bankra mouza in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 382/HSD | 10/02/2025 | 10 | S.K.ENTERPRISE. | 0.96 | 0 | 0 | 100
2136 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Hingalganj Piped water supply scheme Zone-II , SM/14513 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Dakshin Bankra Dobar in Bankra Dobar mouza in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 314/HSD | 04/02/2025 | 10 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 0.96 | 0 | 0 | 100
2137 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District , SM/14539 | Retrofitting | Formal work order for Construction of 1 no. 1250 Cum capacity OHR, Land development, Construction of Office cum Guard room and Switch cum Chlorine Room, Boundary wall, Surface drain and related allied works at Zone-IX Head work site including Laying Distribution System and FHTC of Habra-Gaighata surface water based water supply scheme under Barasat Division, P.H.E. Dte. | 4138/BD | 18/10/2023 | 1095 | S & P ENTERPRISE | 1608.93 | 0 | 0 | 20
2138 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme , SM/14490 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Berachampa Water Supply Scheme Zone-I under Barasat Sub Division, P.H.E. Dte. | 658/BSD | 18/08/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.86 | 3.86 | 100 | 1
2139 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme , SM/14490 | Augmentation | Material Requisition To Resource Division | 1284/BD | 25/04/2023 | 0 | Resource Division | 211.19 | 0 | 0 | 0
2140 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme , SM/14490 | Augmentation | Material Requisition To Resource Division | 3093/BD | 10/10/2023 | 0 | Resource Division | 24.61 | 0 | 0 | 0
2141 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme , SM/14490 | Augmentation | Material Requisition To Resource Division | 4374/BD | 10/11/2023 | 0 | Resource Division | 9.49 | 0 | 0 | 0
2142 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme , SM/14490 | Augmentation | Formal work order for Construction of 700cum capacity 20mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and providing FHTC for Augmentation of Berachampa Zone-I water supply Scheme under Barasat Sub-Division PHE Dte. | 2552/BD | 24/08/2023 | 1096 | MONDAL ENTERPRISE. (BARASAT) | 777.6 | 185.11 | 23.81 | 24
2143 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme , SM/14490 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. X 200mm.dia. 190.00mtr. deep tube well by direct rotary rig method, having 300mm.dia. 42.0mtr. long PVC housing pipe & 200mm.dia. 30.0mtr. long filter for Augmentation of Berachampa Zone-I Water Supply Scheme at 2nd Tube well Site under Barasat Sub-Division, P.H.E. Dte. | 2192/BD | 05/08/2024 | 30 | M/S K.P.PAL. | 13.3 | 12.65 | 100 | 100
2144 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme , SM/14490 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-C | 1119./BSD | 09/02/2024 | 4 | S.M.TRADERS. | 0.88 | 0.88 | 100 | 100
2145 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme , SM/14490 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. big dia. 185 mtr deep Tube well by D.R. Rig method having 300 mm dia 42.0 mtr. long PVC housing pipe & 200 mm dia 30.0 mtr. long filter for Augmentation Berachampa Zone-I Water Supply Scheme (Head Work Site) of Barasat Sub-Division under Barasat Division, PHE Dte. | 802/BD | 15/03/2024 | 30 | ACME CONSTRUCTION | 13.08 | 12.38 | 100 | 80
2146 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme , SM/14490 | Augmentation | Construction of Pump House with latrine at Berachampa Zone-I water Supply Scheme under Deganga Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | 1242/BSD | 15/03/2024 | 31 | ROMI TREDERS. | 4.86 | 4.86 | 100 | 100
2147 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme , SM/14490 | Augmentation | New service connection at P.H.No- I ,Zone-I of Berachampa water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). | BP-306-23-24 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.5 | 0 | 0 | 0
2148 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme , SM/14490 | Augmentation | Acceptance cum work order for Renovation of Iron Elimination Plant at Berachampa Zone-I Water Supply Scheme within Deganga Block under Barasat Sub Division, P.H.E.Dte. | 99/BD | 09/01/2025 | 40 | JAGANNATH CONSTRUCTION. | 9.19 | 0 | 0 | 0
2149 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme , SM/14490 | Augmentation | Formal work order for Road restoration work damaged during pipe laying work under JJM in different water supply scheme under Barasat-II and Deganga block under Barasat Division P.H.E.Dte. | 393/BD | 05/02/2025 | 120 | MONDAL ENTERPRISE. (BARASAT) | 167.48 | 0 | 0 | 0
2150 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme , SM/14490 | Augmentation | Acceptance cum work order for Construction of Boundary Wall in Hosenpur Mouza Water Supply Scheme at Berachampa Zone - I within Deganga Block under Barasat Sub-Division, PHE Dte. | 56/BD | 07/01/2025 | 120 | JIT CONSTRUCTION | 27.29 | 0 | 0 | 40
2151 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme , SM/14490 | Augmentation | Acceptance cum work order for Additional Laying of HDPE pipe line and allied work in connection with Augmentation Berachampa Zone-I Water Supply Scheme within Barasat Sub Division, P.H.E.Dte. | 54/BD | 07/01/2025 | 30 | MONDAL ENTERPRISE. (BARASAT) | 36.88 | 0 | 0 | 0
2152 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme , SM/14490 | Augmentation | Hiring 1 (one) no. Diesel Luxary Car on daily basis (for 01.09.2024 to 28.02.2025) for office use of the Assistant Engineer, R.W.S, Barasat Sub- Division, P.H.E. Dte. | 983/BST | 30/08/2024 | 181 | DEBAPRASAD MONDAL. | 0.86 | 1.47 | 170.68 | 0
2153 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Material Requisition To Resource Division | 925/BD | 22/03/2023 | 0 | Resource Division | 280.28 | 0 | 0 | 0
2154 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Material Requisition To Resource Division | 4509/BD | 28/11/2023 | 0 | Resource Division | 17.23 | 0 | 0 | 0
2155 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-II , III, IV (Zone-II) under Kalitala ground water based water supply scheme under Block_ Hingalganj Dist. - 24Pgs(N) under EMD, PHE Dte. (SM/14153) | 2685/EMD | 20/11/2024 | 30 | R.N.S. TRADING | 36.65 | 0 | 0 | 0
2156 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Kalitala water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 654/BD | 28/02/2023 | 90 | SUPRITI ENTERPRISE. | 610.1 | 591.61 | 100 | 60
2157 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Kalitala water supply scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 1151/BD | 13/04/2023 | 90 | UMWELT ENGINEER PVT.LTD. | 851.89 | 839.63 | 100 | 100
2158 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kalitala w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 2477/BD | 18/08/2023 | 30 | M/S PROGATI ENTERPRISE. | 63.27 | 43.87 | 100 | 71
2159 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 2476/BD | 18/08/2023 | 30 | M/S DATTA ENTERPRISE. | 63.24 | 47.03 | 100 | 98
2160 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kalitala w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 528/BD | 20/02/2024 | 45 | UTPAL CONSTRUCTION & CO. | 61.24 | 45.07 | 100 | 100
2161 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kalitala w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 529/BD | 20/02/2024 | 45 | UTPAL CONSTRUCTION & CO. | 61.24 | 46.06 | 100 | 100
2162 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 100 mm dia DI pipeline at different places in connection with Augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 1005/HSD | 29/08/2024 | 10 | ABDUL ALIM MONDAL. | 0.99 | 0 | 0 | 100
2163 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 200 mm dia DI pipeline at different places from N/H/O Narayan Biswas to Naskar para culvert in connection with Augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 1007/HSD | 29/08/2024 | 10 | ABDUL ALIM MONDAL. | 0.99 | 0.52 | 34.68 | 100
2164 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Formal work order for Construction of 250 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Kalitala (Zone-I) water supply scheme, Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 1731/BD | 08/06/2023 | 1096 | M/S PROGATI ENTERPRISE. | 141.21 | 0 | 0 | 0
2165 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Formal work order for Construction of 300 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Kalitala (Zone-II) water supply scheme, Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 1733/BD | 08/06/2023 | 730 | M/S NIRMAN CONSTRUCTION. | 150.78 | 54.42 | 36.09 | 75
2166 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II, III, IV & V under Kalitala W/S Scheme District of 24 Pgs. (N) | 4799/EMD | 09/08/2023 | 578 | ASHUTOSH DAS & CO. | 54.35 | 0 | 0 | 75
2167 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Emergent resting of old rising main pipeline with UC Bullah pilling at Kalitala Bazar at Kalitala mouza within Kalitala w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 930/HSD | 29/05/2025 | 10 | CHANCHAL ENTERPRISE & CO. | 0.82 | 0 | 0 | 0
2168 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Retrofitting work at Samsernagar river side area in connection with Augmentation of Kalitala w/s scheme, Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 155/HSD | 27/01/2025 | 10 | CHANCHAL ENTERPRISE & CO. | 0.98 | 0 | 0 | 100
2169 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Withdrawing & relaying of 90 mm dia. UPVC pipe line near Paschim Kalitala in connection with Augmentation of Kalitala W/S Scheme, Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 156/HSD | 27/01/2025 | 10 | CHANCHAL ENTERPRISE & CO. | 0.95 | 0 | 0 | 100
2170 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Protection of newly restored UPVC distribution pipeline by Bamboo pilling at Hatkhola area in connection with augmentation of Kalitala w/s scheme, Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 157/HSD | 27/01/2025 | 10 | CHANCHAL ENTERPRISE & CO. | 0.87 | 0 | 0 | 100
2171 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Emergent resting of old rising main pipeline with UC Bullah pilling at Kamalakhali more at Kalitala mouza within Kalitala w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 349/HSD | 06/02/2025 | 10 | CHANCHAL ENTERPRISE & CO. | 0.94 | 0 | 0 | 100
2172 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at Duckbunglow at Kalitala mouza in connection with augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 336/HSD | 06/02/2025 | 10 | ABDUL ALIM MONDAL. | 0.96 | 0 | 0 | 100
2173 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places at near Laskar para at Kalitala mouza in connection with augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 254/HSD | 30/01/2025 | 10 | ABDUL ALIM MONDAL. | 0.97 | 0 | 0 | 100
2174 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Construction of boundary wall at PH No.-8 & 9 for Augmentation of Kalitala w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 1527/BD | 07/06/2024 | 30 | LAHIRI CONSTRUCTION. | 6.27 | 0 | 0 | 100
2175 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at OHR site within Kalitala W/S scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 240/HSD | 30/01/2025 | 10 | S.K.ENTERPRISE. | 0.97 | 0 | 0 | 100
2176 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Protection work for construction of approach road for movement of winch machine and other allied machineries at OHR site within Kalitala w/s scheme (Z-II), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 241/HSD | 30/01/2025 | 10 | M/S NIRMAN CONSTRUCTION. | 0.95 | 0 | 0 | 100
2177 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Emergent resting of old rising main pipeline with UC Bullah pilling at Daspara more at Kalitala mouza within Kalitala w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 530/HSD | 10/03/2025 | 10 | CHANCHAL ENTERPRISE & CO. | 0.94 | 0 | 0 | 100
2178 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places at near Ghosh para at Kalitala mouza in connection with augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 245/HSD | 30/01/2025 | 10 | ABDUL ALIM MONDAL. | 0.97 | 0 | 0 | 100
2179 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas , SM/14153 | Augmentation | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places at near Dakshin para at Parghumti mouza in connection with augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 308/HSD | 04/02/2025 | 10 | ABDUL ALIM MONDAL. | 0.98 | 0 | 0 | 100
2180 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Bermajur Piped water supply scheme , SM/14511 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Bermajur Piped Water Supply Scheme under Barasat Division, PHE Dte. | 634/HSD | 08/04/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.32 | 4.32 | 100 | 0
2181 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Bermajur Piped water supply scheme , SM/14511 | Augmentation | Material Requisition To Resource Division | 914/BD | 22/03/2023 | 0 | Resource Division | 36.68 | 0 | 0 | 0
2182 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Bermajur Piped water supply scheme , SM/14511 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Bermajur w/s scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | 2735/BD | 20/09/2024 | 30 | M/S NIRMAN CONSTRUCTION. | 283.68 | 45.66 | 16.1 | 58
2183 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Bermajur Piped water supply scheme , SM/14511 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bermajur water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | 701/BD | 03/03/2023 | 90 | M/S DATTA ENTERPRISE. | 242.46 | 242.35 | 100 | 38
2184 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Bermajur Piped water supply scheme , SM/14511 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 296/BD | 30/01/2024 | 45 | M/S RAJPATH CONSTRUCTION. | 51.76 | 12.59 | 21.24 | 100
2185 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Bermajur Piped water supply scheme , SM/14511 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 2929/BD | 03/10/2024 | 80 | TITUMIR INTERNATIONAL | 51.66 | 11.65 | 20.94 | 100
2186 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Bermajur Piped water supply scheme , SM/14511 | Augmentation | Acceptance cum work order for Additional Laying of UPVC distribution pipe line with restoration works near Gazikhali Sasan in connection with Augmentation of Bermajur w/s scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | 1525/BD | 14/05/2025 | 30 | PRITAM MUKHOPADHYAY. | 10.77 | 0 | 0 | 0
2187 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Bermajur Piped water supply scheme , SM/14511 | Augmentation | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site at PH No.-1 within Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 355/BD | 31/01/2025 | 45 | B.S.ENTERPRISE. (BASIRHAT) | 27.86 | 0 | 0 | 0
2188 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Bermajur Piped water supply scheme , SM/14511 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. I, II, III and IV under Bermajur W/S Scheme, Block-Sandeshkhali-II in District of 24 Pgs. (N). | 6753/EMD | 28/11/2023 | 431 | M/S DILIP MITRA | 43.15 | 34.96 | 84.63 | 60
2189 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Repair, Renovation of Staff Quarter, Laboratory at Mangal Pandey WTP Premises, and Dariapur (Zone-VII-C) including civil works, supply of furniture, Sanitary arrangement & other allied works under office of The Executive Engineer, North 24 Pags. Water Supply Division-I, PHE. Dte. | 374/NWSD-I | 05/04/2023 | 30 | PHOENIX INFRASTRUCTURE | 10.17 | 10.01 | 98.44 | 20
2190 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I, B (Telinipara) in Barrackpore-II Block of North 24 Parganas District. | 4033/ED | 17/10/2023 | 183 | S.P. CONSTRUCTION | 34.15 | 0 | 0 | 0
2191 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II, B (Malikapur) in Barasat-I Block of North 24 Parganas District. | 4029/ED | 17/10/2023 | 183 | A.G. ENTERPRISE | 55.55 | 0 | 0 | 0
2192 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI, B (Tapanpur) in Amdanga Block of North 24 Parganas District. | 4032/ED | 17/10/2023 | 183 | ALPHA ENTERPRISE | 58.67 | 0 | 0 | 0
2193 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Preparation of Augmentation DPR of Intake, Rising Main, WTP, Boosting Station of Surface Water Based Water Supply Project under North 24 Parganas Water Supply Division-I, PHE. Dte. | 1079/NWSD-I | 29/09/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 19.96 | 19.96 | 100 | 1
2194 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Renovation of Administrative Building , Out House, Chemical House, Laboratory at Water Treatment Plant and 3 (Three) Nos. units of Boosting Station-I at Madhabpur by supplying Furnitures, Air Condition Machines and other allied works under Office of the Executive Engineer, NWSD-I, PHE. Dte. | 352/NWSD-I | 27/03/2023 | 60 | KINGS AND CO. | 133.48 | 123.98 | 100 | 100
2195 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Repairing of damaged boundary wall at Mangal Pandey Water Treatment Plant site and other ancilary works under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | 1391/NWSD-I | 05/09/2023 | 60 | CONCORD ENGINEERING | 14.04 | 13.73 | 100 | 100
2196 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Material Requisition To Resource Division | 490/NWSD-I | 26/04/2023 | 0 | Resource Division | 2047.44 | 0 | 0 | 0
2197 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Feasibility study to select a suitable location for Water Intake (2.5 MGD) Jetty - Augmentation of Intake WTP & Rising Main for Surface Water Based Piped Water Supply Scheme of Mangal Pandey Water Treatment Plant for Arsenic Affected areas of North 24 Parganas under North 24 Pgs. W/S Division-I, P.H.E. Dte., Govt. of West Bengal. | 263/PFMS/23-24 | 03/10/2023 | 0 | SYAMA PRASAD MOOKERJEE PORT, KOLKATA | 53.67 | 0 | 0 | 0
2198 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Supply, Installation & Commissioning of 38 Nos of CCTV Camera for Indoor/Outdoor Purpose at Different area of Mangal Pandey Water Treatment Plant under North 24 Pgs. Water Supply Division-I, PHE. Dte.(2nd Call) | 550/NWSD-I | 29/04/2022 | 60 | KIS MANAGEMENT PRIVATE LIMITED | 18.53 | 0.82 | 13.03 | 100
2199 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I, A-I (Surjapur) in Barrackpore-II & Barasat-I Block of North 24 Parganas District. | 4027/ED | 17/10/2023 | 183 | WEST BENGAL ENGINEERING CO. | 30.05 | 0 | 0 | 10
2200 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI, A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District. | 4028/ED | 17/10/2023 | 183 | WEST BENGAL ENGINEERING CO. | 33.17 | 0 | 0 | 10
2201 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII, A (Kharu) in Amdanga Block of North 24 Parganas District. | 4026/ED | 17/10/2023 | 822 | ORIENTAL ENGINEERING CO. | 29.74 | 0 | 0 | 5
2202 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I, A-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District. | 4889/ED | 27/12/2023 | 183 | BENGAL CONSTRUCTION | 59.48 | 0 | 0 | 0
2203 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Restoration Work by providing sand filling and G.S.B., W.M.M. & B.M. in damage Bituminous Road portion at different location in connection with the laying of rising main within the command area of Malikapur (Zone-IIB) W/S scheme due to cutting of existing black top road by open trench method for JJM/FHTC Project under North 24PGS Water Supply Divn.-I, P.H.E. Dte. | 1406/NWSD-I | 12/09/2024 | 30 | BASHUDEV DUTTA | 59.38 | 0 | 0 | 100
2204 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Quotation Bill for New Service Connection at Kharu OHE Site | 785 | 20/02/2024 | 0 | WBSEDCL | 1.41 | 0 | 0 | 0
2205 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Quotation for Sarberia OHR site Application no: 1007488840 SM 15816 | 852 | 07/03/2024 | 0 | WBSEDCL | 2.05 | 0 | 0 | 0
2206 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Tentulia Existing OHR site quotation received for Load Enhancement Application No. 1007958975 Consumer Id 153161466 SM Code : 15816 | 562 | 11/11/2024 | 0 | WBSEDCL | 0.35 | 0 | 0 | 0
2207 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Quotation Bill for New Service Connection at Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | 592 | 29/12/2023 | 0 | WBSEDCL | 1.08 | 0 | 0 | 0
2208 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Quotation Bill for New Service Connection at Beraberia OHR Site | 786 | 21/02/2024 | 0 | WBSEDCL | 0.97 | 0 | 0 | 0
2209 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Quotation for New Service Connection at Khilkapur OHR site SM Code: 15816 | 634 | 18/12/2024 | 0 | WBSEDCL | 6.96 | 0 | 0 | 0
2210 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Quotation Bill for New Service Connection at Berunanpukuria W/S. Sch. | 620 | 08/01/2024 | 0 | WBSEDCL | 1.21 | 0 | 0 | 0
2211 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Quotation for Load enhancement of Telenipara OHR site for Mangal Pandey Augmentation SM Code: 15816 | 906 | 21/03/2024 | 0 | WBSEDCL | 1.72 | 0 | 0 | 0
2212 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Supplimentory Quotation for Load enhancement of Surjapur OHR site for Mangal Pandey Augmentation SM Code: 15816 | 907 | 21/03/2024 | 0 | WBSEDCL | 2.82 | 0 | 0 | 0
2213 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Supplimentory Quotation for Load enhancement of Telenipara OHR site for Mangal Pandey Augmentation SM Code: 15816 | 905 | 21/03/2024 | 0 | WBSEDCL | 7.17 | 0 | 0 | 0
2214 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Aug of Mangal Pandey Surface based Water Supply Scheme in the District of North 24-Parganas at Kharki OHR site.[SM/15816] | 444 | 05/09/2024 | 0 | WBSEDCL | 0.46 | 0 | 0 | 0
2215 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Surjapur OHR Site Customer ID: 152146528 SM 15816 | 903 | 19/03/2024 | 0 | WBSEDCL | 1.12 | 0 | 0 | 0
2216 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 59.51 | 1.41 | 2
2217 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Augmentation of Centrifugal Pumping Machinery at Boosting Station - I along with disinfection arrangement at different zones under Mangal Pandey Surface based Water Supply Scheme in the District of North 24-Parganas. | 4022/ED | 17/10/2023 | 593 | ORIENTAL ENGINEERING CO. | 323.41 | 115.82 | 35.81 | 5
2218 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery to be installed at Zone-VII, C (Dariapur) for Augmentation of Zone-VIII, A/B/C in Amdanga Block of North 24 Parganas District. | 4031/ED | 17/10/2023 | 749 | M/S P.P. ELECTRICALS | 109.28 | 0 | 0 | 20
2219 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Renovation of High Lift Pumping Machinery, MCC panel, Sub-station equipments along with SCADA system at Water Treatment Plant of Mangal Pandey Surface based Water Supply Scheme in the District of North 24-Parganas. | 4020/ED | 17/10/2023 | 549 | B.T. PROJECT PVT. LTD. | 392.78 | 252.41 | 64.26 | 5
2220 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Providing Electro Mechanical equipments for Augmentation of Intake of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas District. | 4021/ED | 17/10/2023 | 822 | ORIENTAL ENGINEERING CO. | 143.79 | 0 | 0 | 0
2221 | NORTH 24 PARGANAS | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII, B (Rautara) in Amdanga Block of North 24 Parganas District. | 4030/ED | 17/10/2023 | 810 | DEY ENTERPRISE | 57.7 | 0 | 0 | 25
2222 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Engagement of Personnel for Preparation of Environmental Impact Assessment (EIA) /Environmental Management Plant (EMP) study and Collation of Project Legal data, Collection of Project Environmental data as per scope of work, detail assessment report as per guidelines of EIA, 2006 by Govt. of India for Construction of new Intake Jetty at bank of Hooghly river within the Mangal Pandey Water Treatment Plant Campus for drawal of Raw Water from river Hooghly through Intake jetty (2.5 MGD) for the project of "Augmentation of Intake, WTP & Rising Main for Surface Water Based Piped Water Supply Scheme of Mangal Pandey Water Treatment Plant for Arsenic Affected areas of North 24 Parganas" under North 24 Pgs Water Supply Division-I, P.H.E. Dte, Govt. of West Bengal all complete as per direction of EIC. Detailed scope of work is annexed. | 1016/NWSD-I | 08/07/2024 | 146 | RSP GREEN DEVELOPMENT & LABORETORIES PVT LTD | 9.99 | 9.99 | 100 | 100
2223 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di , SM/15816 | Augmentation | Engagement of Personnel for design & analysis & submission of report for Bank protection work for construction of new Intake Jetty within Mangal Pandey Water Treatment Plant for construction of new Intake Jetty at bank of Hooghly river within the Mangal Pandey Water Treatment Plant Campus for drawal of Raw Water from river Hooghly through Intake jetty (2.5 MGD) for the project of "Augmentation of Intake, WTP & Rising Main for Surface Water Based Piped Water Supply Scheme of Mangal Pandey Water Treatment Plant for Arsenic Affected areas of North 24 Parganas" under North 24 Pgs Water Supply Division-I, P.H.E. Dte, Govt. of West Bengal all complete as per direction of EIC. Detailed scope of work is annexed. | 1017/NWSD-I | 08/07/2024 | 216 | CONCORD ENGINEERING | 6.79 | 0 | 0 | 100
2224 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV_A (Ruiya) and Zone-XIV_B (Dangadihila) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15817 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas at Zone- XIV A, (Dangadihila) in Barrackpore-II Block of North 24 Parganas District. | 4023/ED | 17/10/2023 | 183 | R.N.S. TRADING | 57.03 | 0 | 0 | 0
2225 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV_A (Ruiya) and Zone-XIV_B (Dangadihila) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15817 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV, B (Ruiya) in Barrackpore-II Block of North 24 Parganas District. | 4025/ED | 17/10/2023 | 183 | AHALYA ENGINEERING WORKS | 62.2 | 0 | 0 | 0
2226 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV_A (Ruiya) and Zone-XIV_B (Dangadihila) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15817 | Augmentation | Design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme Zone-XIV-A (Ruiya), North 24 Pgs.W/S Division-I, P.H.E. Dte. | 892/NWSD-I | 26/07/2022 | 31 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.62 | 1.62 | 100 | 1
2227 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV_A (Ruiya) and Zone-XIV_B (Dangadihila) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15817 | Augmentation | Material Requisition To Resource Division | 484/NWSD-I | 26/04/2023 | 0 | Resource Division | 10.71 | 0 | 0 | 0
2228 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV_A (Ruiya) and Zone-XIV_B (Dangadihila) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15817 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 0 | 0 | 2
2229 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15819 | Augmentation | Detail route survey, design of distribution network and preparation of estimate drawing & DPR for providing FHTC in the scheme of Zone-III (Raypur) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | 228/NWSD-I | 28/02/2023 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.92 | 3.91 | 100 | 0
2230 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15819 | Augmentation | Material Requisition To Resource Division | 466/NWSD-I | 26/04/2023 | 0 | Resource Division | 151.42 | 0 | 0 | 0
2231 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15819 | Augmentation | Material Requisition To Resource Division | 1259/NWSD-I | 21/08/2023 | 0 | Resource Division | 23.65 | 0 | 0 | 0
2232 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15819 | Augmentation | Providing FHTC, Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | 884/NWSD-I | 12/07/2023 | 366 | S & P ENTERPRISE | 774.61 | 422.94 | 54.6 | 40
2233 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15819 | Augmentation | Additional quotation for New service connection at P.H.No- I of Raypur water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N) | BP-346-23-24 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.07 | 0 | 0 | 0
2234 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15819 | Augmentation | New service connection at P.H.No- I of Raypur water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). | BP-298-23-24 | 28/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.57 | 0 | 0 | 0
2235 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15819 | Augmentation | Shifting of PCC Pole at Raypur OHR Site | 131/PFMS/24-25 | 30/07/2024 | 0 | WBSEDCL | 0.12 | 0 | 0 | 0
2236 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15819 | Augmentation | Restoration of 90mm dia HDPE pipeline at Raypur Ghoshpara, under Raypur Mouza within Deganga Block in the District of North 24 Pgs under North 24 Pgs W/S Division-I, P.H.E. Dte. | 107/NWSD-I | 17/01/2025 | 7 | HAKIM ENTERPRISE | 3.33 | 0 | 0 | 0
2237 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. , SM/18410 | Augmentation | Material Requisition To Resource Division | 3090/BD | 10/10/2023 | 0 | Resource Division | 7.26 | 0 | 0 | 0
2238 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. , SM/18410 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Sohai Swetpur Zone-I within Deganga Block under Barasat Sub-Division, PHE Dte. | 3703/BD | 26/12/2024 | 30 | GIRIDHARI DAS | 12.8 | 0 | 0 | 0
2239 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. , SM/18410 | Augmentation | Preparation of DPR in connection of augumentation of Sohai Swetpur Water Supply Scheme Zone-I under Barasat Sub Division, P.H.E. Dte. | 672/BSD | 30/08/2022 | 30 | RADIANT | 3.28 | 3.01 | 100 | 100
2240 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. , SM/18410 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-A | 1117/BSD | 09/02/2024 | 4 | M.R.CONSTRUCTION. | 0.88 | 0.88 | 100 | 100
2241 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. , SM/18410 | Augmentation | New service connection at P.H.No- III , Zone-I of Swetpur water supply scheme under EMSD-I ,PHE Dte .im24Pgs(N). | BP-331-23-24 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.2 | 0 | 0 | 0
2242 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. , SM/18410 | Augmentation | Formal work order for Construction of 550cum capacity 20Mtr staging Height R.C.C. Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentation of Swetpur Zone-I Water Supply Scheme under Barasat Sub-Division, P.H.E.Dte. | 2382/BD | 10/08/2023 | 732 | M/S BISWAS BROTHERS. | 461.4 | 156.39 | 33.89 | 55
2243 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC. , SM/18410 | Augmentation | Acceptance cum work order for Repair & Renovation work at Different site in connection with Augmentation of Sohai Swetpur, Zone-I Water Supply Scheme under Barasat Sub Division, P.H.E.Dte. | 1026/BD | 28/03/2025 | 45 | M/S S.HAQUE & CO. | 12.75 | 0 | 0 | 100
2244 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) , SM/08074 | Retrofitting | Acceptance cum work order for Construction of Anchor block for resting of 100 mm dia DI Distribution main for low areas at different places within Rupmari w/s scheme, Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | 400/HSD | 04/03/2022 | 15 | M/S PROGATI ENTERPRISE. | 3.86 | 3.86 | 100 | 1
2245 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) , SM/08074 | Retrofitting | Acceptance cum work order for Laying of 100 mm dia. DI distribution main from near PH No-3 towards Halda more for damage portion within Rupmari w/s scheme (Zone-III), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | 402/HSD | 04/03/2022 | 10 | M/S PROGATI ENTERPRISE. | 1.53 | 1.53 | 99.92 | 1
2246 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) , SM/08074 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia. UPVC distribution pipeline for providing FHTC by UC bullah pile at different places within Rupmari w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 404/HSD | 04/03/2022 | 10 | M/S PROGATI ENTERPRISE. | 4.95 | 5 | 100 | 1
2247 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) , SM/08074 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line for providing FHTC by bamboo pilling at different places within Rupmari w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 403/HSD | 04/03/2022 | 10 | M/S DATTA ENTERPRISE. | 4.93 | 4.91 | 99.58 | 1
2248 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) , SM/08074 | Retrofitting | Acceptance cum work Order for Providing Functional Household Tap Connection (FHTC) in Rupmari & Bastali mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Rupmari W/S scheme, Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 95/BD | 17/01/2022 | 45 | M/S DATTA ENTERPRISE. | 96.84 | 96.43 | 100 | 1
2249 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) , SM/08074 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Rupmari w/s scheme (For Zone-IV to VI), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 253/HSD | 07/02/2022 | 10 | M/S DATTA ENTERPRISE. | 4.86 | 3.46 | 100 | 1
2250 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) , SM/08074 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Rupmari w/s scheme (For Zone-I to III), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 256/HSD | 07/02/2022 | 10 | M/S PROGATI ENTERPRISE. | 3.46 | 3.46 | 100 | 1
2251 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) , SM/08074 | Retrofitting | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places for providing FHTC within Rupmari w/s scheme (Zone-III to VI), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 940/HSD | 07/06/2022 | 15 | M/S DATTA ENTERPRISE. | 3.08 | 3.08 | 100 | 1
2252 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) , SM/08074 | Retrofitting | Acceptance cum work order for Withdrawing & relaying of 75 mm dia. HDPE pipe line from near Halda High School towards Kumirmari kheya Ghat for damage portion within Rupmari W/S Scheme (Z-III & IV), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 941/HSD | 07/06/2022 | 10 | M/S PROGATI ENTERPRISE. | 4.92 | 4.92 | 50 | 1
2253 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) , SM/08074 | Retrofitting | Material Requisition To Resource Division | 44/BD | 04/01/2023 | 0 | Resource Division | 61.6 | 0 | 0 | 0
2254 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Chotto Sehara W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). , SM/10554 | Retrofitting | Work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the Sehara Radhanagar mouza into Swajal Gram i/c laying of UPVC/PVC pipe & supply of necessary fittings within Chotto Sehara w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 2921/BD | 26/09/2022 | 30 | TRISHA ENTERPRISE & CO. | 24 | 23.99 | 50 | 1
2255 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Chotto Sehara W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). , SM/10554 | Retrofitting | Acceptance cum work order for Construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Chotto Sehara water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte | 1153/BD. | 12/04/2022 | 240 | S.S.ENTERPRISE. (BAMANGACHI) | 143.13 | 72.69 | 100 | 95
2256 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Chotto Sehara W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). , SM/10554 | Retrofitting | Acceptance cum work order for Construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Chotto Sehara water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 1153/BD | 12/04/2022 | 240 | M/S S.S.ENTERPRISE. (SOUTH) | 146.26 | 49.03 | 100 | 1
2257 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC , SM/10300 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I under panchita W/S Scheme District of 24 Pgs. (N) | 6145 / EMD | 14/08/2022 | 30 | P.K. ENTERPRISE | 12.82 | 10.38 | 80.96 | 1
2258 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC , SM/10300 | Augmentation | Formal Work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system with in command area at Panchita Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation). | 1209/BD | 21/04/2022 | 90 | UMWELT ENGINEER PVT.LTD. | 393.47 | 386.33 | 100 | 0
2259 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC , SM/10300 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under Panchita W/S Scheme District of 24 Pgs. (N) (Block- Baduria). NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.- 09) | 6146/EMD | 11/11/2022 | 30 | S.M. ELECTRICALS | 12.81 | 11.9 | 100 | 100
2260 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC , SM/10300 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Panchita water supply scheme (2nd T/W site) under Bongaon Sub-Division P.H.E.Dte. | 3591/BD | 08/12/2022 | 15 | SAHA CONSTRUCTION & CO | 15.12 | 13.73 | 100 | 0
2261 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC , SM/10300 | Augmentation | Renovation and repairing of Boundary wall at 2nd T/W site for Augmentation of Panchita Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 615/Bon | 08/08/2023 | 21 | PRABIR KUMAR MONDAL. | 4.15 | 4.11 | 100 | 100
2262 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC , SM/10300 | Augmentation | Urgently repairing and laying of badly damaged pipe line and FHTC connection due to construction of Gram Panchayat surface drain at Nakful area of Panchita Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | 625/Bon | 08/08/2023 | 15 | PRABIR KUMAR MONDAL. | 0.71 | 0.7 | 100 | 100
2263 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC , SM/10300 | Augmentation | Material Requisition To Resource Division | 1367/BD | 13/05/2022 | 0 | Resource Division | 19.79 | 0 | 0 | 0
2264 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC , SM/10300 | Augmentation | Material Requisition To Resource Division | 1672/BD | 13/06/2022 | 0 | Resource Division | 19.79 | 0 | 0 | 0
2265 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC , SM/10300 | Augmentation | Acceptance cum work order for Repair and renovation works of 180 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir alongwith rising main connection with 2nd Tube well for Augmentation of Panchita Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 3038/BD | 22/10/2024 | 45 | DEBAPRASAD MONDAL. | 15.61 | 0 | 0 | 0
2266 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC , SM/10300 | Augmentation | Construction of Approach Road Head Work at site for Augmentation of Panchita Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 617/Bon | 08/08/2023 | 17 | KAMAL HALDER. | 2.94 | 2.93 | 100 | 100
2267 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC , SM/10300 | Augmentation | Acceptance cum work order for Repair & renovation of Pump House at 2nd T/W site for Augmentation of Panchita Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 604/Bon | 04/08/2023 | 21 | PRABIR KUMAR MONDAL. | 1.78 | 1.75 | 100 | 100
2268 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC , SM/10300 | Augmentation | Construction of Approach Road at 2ndT/W site for Augmentation of Panchita Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | 559/Bon | 18/07/2023 | 15 | PRABIR KUMAR MONDAL. | 0.87 | 0.87 | 100 | 100
2269 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC , SM/10300 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Panchita Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 536/BD | 21/02/2024 | 45 | PRABIR KUMAR MONDAL. | 14.25 | 0 | 0 | 100
2270 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC , SM/10300 | Augmentation | Health assessment of existing OHR of Panchita PWSS (180 cum) and ancillary structures, Bongaon Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 691/Bon | 07/06/2024 | 15 | SIRCON ENGINEERING SERVICES | 3.53 | 3.53 | 100 | 100
2271 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC , SM/10300 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe under Augmentation work at Panchita W/S Scheme Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (PART-B). | 1769/BD | 01/07/2024 | 284 | A.D.ENTERPRISE. | 24.28 | 0 | 0 | 100
2272 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Panchita to Accommodate FHTC , SM/10300 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe under Augmentation work at Panchita W/S Scheme Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (PART-A). | 1768/BD | 01/07/2024 | 15 | PRABIR KUMAR MONDAL. | 12.13 | 0 | 0 | 100
2273 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC , SM/17679 | Augmentation | Material Requisition To Resource Division | 1267/BD | 25/04/2023 | 0 | Resource Division | 99.41 | 0 | 0 | 0
2274 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC , SM/17679 | Augmentation | Material Requisition To Resource Division | 4020/BD | 12/10/2023 | 0 | Resource Division | 17.25 | 0 | 0 | 0
2275 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC , SM/17679 | Augmentation | Formal work order for Construction of 450cum capacity 20mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and providing FHTC for Augmentation of Deara water supply Scheme under Barasat Sub-Division PHE Dte. | 2561/BD | 24/08/2023 | 366 | SINGHA ROY & CO. | 507.92 | 103.06 | 20.29 | 25
2276 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC , SM/17679 | Augmentation | Acceptance cum work order for Construction of Boundary Wall at Deara Water Supply Scheme under Barasat-II Block, under Barasat Sub-Division, P.H.E.Dte. | 3081/BD | 29/10/2024 | 30 | M/S SANJAY ADHIKARI | 32.14 | 0 | 0 | 0
2277 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC , SM/17679 | Augmentation | Preparation of DPR in connection of augmentation of Deara Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. Sl. No.-21 | 568/BSD | 29/06/2022 | 30 | RADIANT | 2.97 | 2.79 | 100 | 100
2278 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC , SM/17679 | Augmentation | Payment of invoice bill for new service connection at p/h no: III under Deara water supply scheme. | BP-290-23-24 | 27/02/2024 | 0 | W.B.S.E.D.C.L. (GANGANAGAR C.C.C.) | 3.79 | 0 | 0 | 0
2279 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC , SM/17679 | Augmentation | Acceptance cum work order for Additional Laying of UPVC pipe line and allied work in connection with Augmentation Deara Water Supply Scheme within Barasat Sub Division, P.H.E.Dte. | 53/BD | 07/01/2025 | 30 | SINGHA ROY & CO. | 27.35 | 0 | 0 | 0
2280 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC , SM/17679 | Augmentation | Acceptance cum work order for Renovation of Iron Elimination Plant at Deara Water Supply Scheme within Barasat-II Block under Barasat Sub Division, P.H.E.Dte. | 375/BD | 04/02/2025 | 40 | TALUKDER & CO. | 9.19 | 0 | 0 | 0
2281 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC , SM/17679 | Augmentation | Construction of Pump House with latrine at Deara water Supply Scheme under Barasat-II Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | 1021/BSD | 03/01/2025 | 40 | M.ENTERPRISE. | 4.87 | 0 | 0 | 0
2282 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dhalani Water Supply Scheme at Bagdah Block (Phase-II) , SM/08066 | Retrofitting | Hiring of Luxury Car (Diesel) for the office use of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Bongaon Sub-Division P.H.E. Dte. (Period from 01.02.2022 to 31.01.2023.) | 45/Bon | 31/01/2022 | 12 | ROY ENGINEERS. | 1.73 | 0 | 0 | 1
2283 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dhalani Water Supply Scheme at Bagdah Block (Phase-II) , SM/08066 | Retrofitting | Repairing & Renovation of 02No. Pump House and allied works at Dhalani water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 595/BON | 22/12/2021 | 21 | TAPAN GHOSH. | 2.52 | 0 | 0 | 1
2284 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Palla Water Supply Scheme at Bongaon Block (Phase-I) , SM/08047 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PALLA Water Supply Scheme at BONGAON Block under North 24 Parganas Water Supply Division - I, P.H.E. Dte. (Phase-I). | 458 / NWSD-I | 10/06/2021 | 60 | TIRUPATI ENTERPRISES | 70.9 | 69.5 | 63.68 | 1
2285 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ICHHLAMPUR ZONE-II Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07601 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ICHHLAMPUR ZONE-II Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (Phase-I) | 72/NWSD-I | 20/01/2021 | 90 | H. I. ENTERPRISE | 82.89 | 160.93 | 108.16 | 1
2286 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ICHHLAMPUR ZONE-II Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07601 | Retrofitting | Hiring of 1 (one) no. Motor Cab / Maxi Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer, North 24 Parganas W/S Sub-Division-I, P.H.E. Dte. for 6(Six) months, i.e. 184 days. [w.e.f. 01.05.2023 to 31.10.2023] (Car No.WB25K0619) | 502/NWSD-I | 27/04/2023 | 184 | M/S. SHUBHA ENTERPRISE | 0.87 | 0.52 | 100 | 70
2287 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ICHHLAMPUR ZONE-II Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07601 | Retrofitting | Continuation order for the work of Hiring of 1 (one) no. Motor Cab / Maxi Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed it on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer, North 24 Parganas W/S Sub-Division-I, P.H.E. Dte. for 6(Six) months, i.e. 182 days. [w.e.f. 01.11.2023 to 30.04.2024] (Car No.WB25K0619) | 1646/NWSD-I | 16/10/2023 | 182 | M/S. SHUBHA ENTERPRISE | 0.86 | 1.24 | 201.82 | 67
2288 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Matiagacha Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-I) , SM/07621 | Retrofitting | Material Requisition To Resource Division | 2860/BD | 21/09/2022 | 0 | Resource Division | 3.08 | 0 | 0 | 0
2289 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Matiagacha Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-II) , SM/07622 | Retrofitting | Material Requisition To Resource Division | 2865/BD | 21/09/2022 | 0 | Resource Division | 1.23 | 0 | 0 | 0
2290 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chaumuha Water Supply scheme under Barasat - II Block for providing Functional House Tap Connection , SM/07023 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Chaumuha Mouza of Barasat- II Block from Chaumuha Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I) | 1885/B.Ar.D. | 18/12/2020 | 90 | UMWELT ENGINEER PVT. LTD. | 91.5 | 165.64 | 174.23 | 1
2291 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofiting of Jeliakhali Paschim khanda water supply scheme under sandeshkhali- II Block for providing Functional House Tap Conection , SM/07025 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Jeliakhali Pashchim Mouza of Sandeshkhali-II Block from Jeliakhali Pashchim Khanda Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. | 1883/B.Ar.D. | 18/12/2020 | 90 | M/S. S. S. ENTERPRISE | 96.55 | 191.44 | 198.29 | 1
2292 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Konanagar water supply scheme under Hasnabad Block for providing Functional House Tap Conection , SM/07027 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Khorda, Jalsira and Konanagar Mouzas of Hasnabad Block from Konanagar Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. ( Phase-I ). | 1880/B.Ar.D. | 18/12/2020 | 90 | M/S ROY CHOWDHURY & CO. | 82.2 | 146.38 | 155.61 | 1
2293 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Konanagar water supply scheme under Hasnabad Block for providing Functional House Tap Conection , SM/07027 | Retrofitting | Route survey, distribution design & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Konanagar , Rajapura & its adjoining mouza Water Supply Scheme in Hasnabad Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | 1443/B.Ar.D | 31/08/2021 | 15 | SIRCON ENGINEERING SERVICES | 4.74 | 4.39 | 50 | 1
2294 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Konanagar water supply scheme under Hasnabad Block for providing Functional House Tap Conection , SM/07027 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Magurati Srirampur Mouza of Baduria Block from Magurati Srirampur Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. | 1886/B.Ar.D. | 18/12/2020 | 90 | UMA CONSTRUCTION | 39.19 | 14.23 | 100 | 1
2295 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chowlpur & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07713 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Chowlpur, Ghoradaria and Mitpukuria Mouzas of Barasat- II Block from Chowlpur Ground Water Supply Scheme under "Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I) | 561/B.Ar.D. | 26/02/2021 | 90 | SANJUKTA ENGINEERS | 77.59 | 107.62 | 85.22 | 1
2296 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chowlpur & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07713 | Retrofitting | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Chowlpur & its adjoining mouza water supply scheme in Barasat -II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | 1698/B.Ar.D | 30/09/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.04 | 3.04 | 50 | 1
2297 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chowlpur & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07713 | Retrofitting | Repairing and Renovation of 02 (two) nos pump house and 01 (one) No I.E.P room, and allied works at the site of Chowlpur W/S Scheme under Jal Swapna Programme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | 2217/B.Ar.D | 24/12/2021 | 30 | CHOWDHURY CONSTRUCTION | 4.8 | 4.8 | 50 | 1
2298 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chowlpur & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07713 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling (approx. 50 mtr length) for protection of different dia UPVC/HDPE Pipeline near two ponds at Ghoradaria opposite Gour Biswas house and at Malrameswarpur Sardarhati opposite Pranab Sarkar house under Chowlpur W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | 288/B.Ar.D | 23/02/2022 | 20 | CHOWDHURY CONSTRUCTION | 4.8 | 4.26 | 100 | 1
2299 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chowlpur & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07713 | Retrofitting | Renovation of Pathway and Painting of boundary wall and other allied works at Chowlpur Head Work Site under Chowlpur Water Supply scheme of Barasat ll Block under JAL SWAPNA Programme under Barasat Arsenic Division, P.H.E. Dte. | 484/B.Ar.D | 16/03/2022 | 15 | MODERN CONSTRUCTIONS | 4.64 | 0 | 0 | 1
2300 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Dakshin Bagundi Water Supply Scheme at Basirhat-I Block, Dist.-North 24 Parganas (Phase-I) , SM/07845 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for DAKSHIN BAGUNDI Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | 200/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.76 | 2.63 | 100 | 1
2301 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Rupmari w/s scheme (For Zone-I to III), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 256/HSD | 07/02/2022 | 10 | M/S PROGATI ENTERPRISE. | 3.46 | 0 | 0 | 1
2302 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Rupmari w/s scheme (For Zone-IV to VI), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 253/HSD | 07/02/2022 | 10 | M/S DATTA ENTERPRISE. | 3.46 | 0 | 0 | 1
2303 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Construction of boundary wall at OHR site & CWR site with approach road at CWR site within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 528/BD | 23/02/2022 | 30 | PRITAM MUKHOPADHYAY. | 19.65 | 15.84 | 80.62 | 1
2304 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of DI rising main from near culvert to near Sahapur more for damaged portion due to widening & strengthing of PWD road within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | 588/HSD | 28/03/2022 | 15 | TRISHA ENTERPRISE & CO. | 4.85 | 4.8 | 98.97 | 1
2305 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of UPVC pipe line from Hingalganj Kalibari to Hingalganj GP office for damaged portion due to widening & strengthening of PWD road within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 596/HSD | 31/03/2022 | 15 | TRISHA ENTERPRISE & CO. | 4.18 | 4.18 | 100 | 1
2306 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of different dia. UPVC pipe line from near Hingalganj Kalibari to near Sahapur more for damaged portion due to widening & Strengthing of PWD road within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 602/HSD | 31/03/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.26 | 4.26 | 100 | 1
2307 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Emergent withdrawing & relaying of different dia. UPVC pipe line at Hingalganj Bazar area, Hingalganj Hospital, BDO Office, Dk. Hingalganj, Garhpara, Sahapur & other places for damaged portion within Hingalganj W/S Scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 592/HSD | 29/03/2022 | 15 | SARKAR ENTERPRISE | 4.87 | 4.87 | 100 | 1
2308 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places due to laying of new DI/UPVC pipe line within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 629/HSD | 08/04/2022 | 15 | MONDAL & CO. (BASIRHAT). | 2.45 | 2.45 | 100 | 1
2309 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places due to laying of new DI/UPVC pipe line within Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 622/HSD | 07/04/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 2.34 | 0 | 0 | 1
2310 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Protection works for newly laid different dia. UPVC/DI pipe line at different places in Mamudpur mouza within Hingalganj W/S/Scheme(Z-I). Hingalganj Block under Hasnabad Sub -Division P.H.E. Dte. | 1461/BD | 13/08/2021 | 15 | M/S K.B.ENTERPRISE. | 16.06 | 14 | 50 | 1
2311 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for for protection works for newly laid different dia. UPVC/DI pipe line at different. places in Mamudpur mouza for Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 232/BD | 25/01/2022 | 30 | MONDAL & CO. (BASIRHAT). | 31.2 | 31.43 | 100 | 1
2312 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for for protection works for newly laid different dia. UPVC/DI pipe line at different. places in Hingalganj mouza for Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 235/BD | 25/01/2022 | 15 | MONDAL & CO. (BASIRHAT). | 18.36 | 18.36 | 100 | 1
2313 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Protection of HDPE rising main pipe line by bamboo piling from near Krishnapada Smriti More to N/H/O Ramesh Gayen for Rejuvenation of Durgapur Baylani w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 527/HSD | 15/03/2022 | 10 | MONDAL & CO. (BASIRHAT). | 4.47 | 0 | 0 | 1
2314 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Additional Land development at Head Work Site within Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 1664/HSD | 05/10/2021 | 10 | MONDAL & CO. (BASIRHAT). | 4.85 | 4.84 | 100 | 1
2315 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration by laying of 160/110 mm dia. HDPE distribution pipe line from near SBI bank to Bankra Bazar due to widening & strengthening of PWD road in connection with retrofitting of Hingalganj w/s scheme (Z-I), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | 1355/HSD | 03/08/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.74 | 4.74 | 50 | 1
2316 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line for damage portion at different places due widening of PWD road of Hingalganj w/s Scheme (Zone-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 914/HSD | 07/06/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.9 | 4.9 | 50 | 1
2317 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of existing household tap connection at different places due to widening of PWD road from Boltala to Bankra Bazar in connection with retrofitting of Hingalganj w/s Scheme (Zone-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 1357/HSD | 03/08/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.64 | 4.64 | 50 | 1
2318 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Repairing of Pump House No.-2 within Hingalganj w/s scheme (Old), Hingalgan block under Hasnabad Sub-Division P.H.E. Dte. | 1399/HSD | 08/08/2022 | 21 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 3.46 | 3.46 | 100 | 1
2319 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Laying of 90 mm dia. UPVC pipe line from Boltala Kalupara More to near Katakhali Madrasa within Hingalganj W/S Scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 937/HSD | 07/06/2022 | 10 | TRISHA ENTERPRISE & CO. | 3.19 | 3.19 | 50 | 1
2320 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Laying of different dia. UPVC pipe line for damage portion due to construction of concrete road at Mamudpur Purba & Paschim para within Hingalganj W/S Scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 936/HSD | 07/06/2022 | 10 | MONDAL & CO. (BASIRHAT). | 3.37 | 3.37 | 100 | 1
2321 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration by laying of 75 mm dia. HDPE distribution pipe line from PWD road to Hingalganj Police Station, PWD road to Hingalganj BDO office & BDO office to BDO quarter for damage portion in connection with retrofitting of Hingalganj w/s scheme (Z-I), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | 1333/HSD | 02/08/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.83 | 4.83 | 50 | 1
2322 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Construction of boundary wall for damaged portion at PH No-2 within Hingalganj w/s scheme (Old), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 1402/HSD | 08/08/2022 | 21 | M/S RAJPATH CONSTRUCTION. | 3.62 | 3.61 | 100 | 1
2323 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Protection works for newly laid 200mm dia. UPVC pipe line at N/H/O Susanta Ghosh at Hingalganj within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 935/HSD | 07/06/2022 | 10 | MONDAL & CO. (BASIRHAT). | 2.36 | 0 | 0 | 1
2324 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration by laying of 90 mm dia. HDPE distribution pipe line from near Electric power house to Bankra Bazar due to widening & strengthening of PWD road in connection with retrofitting of Hingalganj w/s scheme (Z-I), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | 1340/HSD | 02/08/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.81 | 4.81 | 50 | 1
2325 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Emergent resting of 100/150 mm dia DI pipeline by concrete block at different places within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 584/HSD | 28/03/2022 | 15 | TRISHA ENTERPRISE & CO. | 3.09 | 3.06 | 100 | 1
2326 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of different dia. DI distribution pipe line from near Bankra Bazar to near culvert for damaged portion due to widening & strengthing of PWD road within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | 581/HSD | 28/03/2022 | 15 | MONDAL & CO. (BASIRHAT). | 3.74 | 3.67 | 100 | 1
2327 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Construction of approach road with cement concrete and other allied works at PH No.- 3 within Hingalganj w/s scheme (Old), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 1192/HSD | 13/07/2022 | 15 | PRASANTA MITRA. | 3.44 | 3.08 | 89.41 | 91
2328 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of DI rising main from near Sahapur more to near OHR for damaged portion due to widening & strengthing of PWD road within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | 619/HSD | 07/04/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.81 | 4.67 | 97.13 | 1
2329 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Emergent restoration of UPVC pipe line from near Hingalganj GP office to Dakshin Hingalganj at different places (SI office, Garpara, BDO office, Sahapur) for damaged portion within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 600/HSD | 31/03/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.42 | 4.42 | 100 | 1
2330 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Protection works for newly laid 200mm dia. UPVC pipe line at N/H/O Susanta Ghosh at Hingalganj within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 935/HSD | 07/07/2022 | 10 | MONDAL & CO. (BASIRHAT). | 2.36 | 2.35 | 99.23 | 1
2331 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Laying of 90 mm dia. UPVC pipe line from Boltala Kalupara More to near Katakhali Madrasa within Hingalganj W/S Scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 937/HSD | 07/07/2022 | 10 | TRISHA ENTERPRISE & CO. | 3.19 | 0 | 0 | 1
2332 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Laying of different dia. UPVC pipe line for damage portion due to construction of concrete road at Mamudpur Purba & Paschim para within Hingalganj W/S Scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 936/HSD | 07/06/2022 | 10 | MONDAL & CO. (BASIRHAT). | 3.37 | 0 | 0 | 1
2333 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Protection works for newly laid different dia. UPVC pipe line at different places in Hingalganj mouza within Hingalganj W/S/Scheme(Z-I).Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | 1462/BD | 13/08/2021 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 14.98 | 3.49 | 50 | 1
2334 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in Mamudpur & Hingalganj mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 142/BD | 18/01/2022 | 90 | M/S S.S.ENTERPRISE. (SOUTH) | 390.88 | 350.49 | 80.82 | 1
2335 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Material Requisition To Resource Division | 1814/BD | 19/06/2023 | 0 | Resource Division | 30.8 | 0 | 0 | 0
2336 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hingalganj Piped Water Supply Scheme (Zone -I), Hingalganj Block , SM/09224 | Retrofitting | Acceptance cum work order for Repairing of Pump House No.-3 & 4, construction of boundary wall & approach road at P.H.No.-3 & other allied works within Hingalganj w/s scheme (Old), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | 2112/BD | 19/07/2023 | 21 | GOBINDA DAS. | 9.21 | 9.05 | 100 | 46
2337 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mollahati Water Supply Scheme at Bongaon Block under North 24 Parganas Water Supply Division-I, P.H.E. Dte. (Phase-I). , SM/08731 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MOLLAHATI Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (Phase-I) | 962/NWSD-I | 16/11/2021 | 75 | ONKAR ENTERPRISE | 92.39 | 93.37 | 100 | 1
2338 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ichhapur Piped Water Supply Scheme, Gaighata Block (Phase-I) , SM/08270 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Ichhapur Water Supply Scheme in Gaighata Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 145/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.21 | 4.19 | 100 | 1
2339 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ichhapur Piped Water Supply Scheme, Gaighata Block (Phase-I) , SM/08270 | Retrofitting | Formal Work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ICHHAPUR Water Supply Scheme at Gaighata Block under Barasat Division, PHE Dte. (Phase-I) | 313/BD | 01/02/2022 | 90 | MONDAL & CO. (BASIRHAT). | 123.07 | 121.07 | 100 | 1
2340 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ichhapur Piped Water Supply Scheme, Gaighata Block (Phase-I) , SM/08270 | Retrofitting | Material Requisition To Resource Division | 3659/BD | 13/12/2022 | 0 | Resource Division | 15.1 | 0 | 0 | 0
2341 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Bangangram (Zone-II) Water SupplyScheme at Bongaon Block (Phase-II). , SM/08237 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BANGANGRAM (ZONE-II) Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (PHASE-II) | 944/NWSD-I | 12/11/2021 | 60 | MONDAL ENTERPRISE | 52.24 | 50.74 | 100 | 1
2342 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan mission (JJM and Jal Swapna) under command area of Taranipur W/S Scheme (Zone-II) at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase -I). , SM/09728 | Retrofitting | Material Requisition To Resource Division | 2993/BD | 29/09/2022 | 0 | Resource Division | 0.08 | 0 | 0 | 0
2343 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOTRA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08642 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Gotra Water Supply Scheme at Basirhat - I Block under Barasat Division, PHE Dte. (Phase - I). | 1676/BD | 08/09/2021 | 45 | M/S NIRMAN CONSTRUCTION. | 86.18 | 84.63 | 98.2 | 1
2344 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOTRA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08642 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Talsa W/S Scheme within the jurisdiction of the Habra Sub-Division under Barasat Division, PHE Dte. | 559/HAB | 20/12/2021 | 10 | UMWELT ENGINEER PVT.LTD. | 3.67 | 3.7 | 100 | 1
2345 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOTRA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08642 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Chhaimalpur Water Supply Scheme under Barasat Division, PHE Dte. | 2169/HSD | 28/12/2021 | 21 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 2.79 | 2.79 | 100 | 1
2346 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOTRA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08642 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for GOTRA Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | 196/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.3 | 4.16 | 100 | 1
2347 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOTRA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08642 | Retrofitting | Hiring Diesel Luxury Car on daily basis for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. (Period 01.07.2023 to 31.12.2023 for Six Month) | 604/BHTSD | 28/06/2023 | 184 | DEB KUMAR DAS. | 0.87 | 1.54 | 176.72 | 33
2348 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BARABANKRA W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08659 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Bara Bankra Water Supply Scheme at Swarupnagar Block under Barasat Division, PHE.(Phase-I). | 1974/BD | 26/10/2021 | 90 | PUSPA ENTERPRISE. | 192.09 | 179.4 | 93.39 | 1
2349 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BARABANKRA W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08659 | Retrofitting | Additional Survey work for DPR Preparation for BITHARI ZONE -2 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 453 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.63 | 0 | 0 | 1
2350 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BARABANKRA W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08659 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for BITHARI ZONE -2 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 452 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.75 | 0 | 0 | 1
2351 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BARABANKRA W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08659 | Retrofitting | Route Survey,design drawing & DPR Preparation for PARUI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 460 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 0 | 0 | 1
2352 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BARABANKRA W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08659 | Retrofitting | Acceptance cum work order for Additional Survey Work For DPR Preparation of Khulna Bhandarkhali Zone-I Water Supply Scheme under Barasat Division, PHE Dte. | 2178/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.08 | 2.08 | 100 | 1
2353 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BARABANKRA W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08659 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Gabbaria Water Supply Scheme under Barasat Division, PHE Dte. | 2173/HSD | 28/12/2021 | 21 | UMWELT ENGINEER PVT.LTD. | 3.39 | 3.39 | 100 | 1
2354 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BARABANKRA W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08659 | Retrofitting | Additional Survey work for DPR Preparation for NALABARA Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 455 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.61 | 0 | 0 | 1
2355 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BARABANKRA W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08659 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for NALABARA Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 454 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.97 | 0 | 0 | 1
2356 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BARABANKRA W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08659 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for NABATKATI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 459 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.81 | 0 | 0 | 1
2357 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BARABANKRA W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08659 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for BANGLANI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 456 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 0 | 0 | 1
2358 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BARABANKRA W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08659 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for DAKSHIN CHATRA ZONE -2 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 442 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.04 | 0 | 0 | 1
2359 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BARABANKRA W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08659 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for PATUA Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 444 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.16 | 0 | 0 | 1
2360 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BARABANKRA W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08659 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for BARA BANKRA Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 441 /BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.57 | 4.57 | 50 | 1
2361 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of BARABANKRA W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08659 | Retrofitting | Material Requisition To Resource Division | 2862/BD | 21/09/2022 | 0 | Resource Division | 36.2 | 0 | 0 | 0
2362 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of RAHARHATI W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08646 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Raharhati Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase - I) | 1674/BD | 08/09/2021 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 57.32 | 55.29 | 96.45 | 1
2363 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of RAHARHATI W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08646 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Hasnabad Water Supply Scheme under Barasat Division, PHE Dte. | 2163/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.21 | 4.21 | 100 | 1
2364 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of RAHARHATI W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08646 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for RAHARHATI Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 343/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.34 | 2.97 | 100 | 1
2365 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOKNA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08647 | Retrofitting | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Gokna Water Supply Scheme at Baduria Block under Barasat Division, PHE Dte. (Phase - I) | 315/BD | 01/02/2022 | 90 | KINGS & CO. | 220.6 | 214.18 | 100 | 1
2366 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOKNA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08647 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for GOKNA Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 360/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.96 | 4.96 | 100 | 1
2367 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOKNA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08647 | Retrofitting | Additional Survey work for DPR Preparation for GOKNA Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 361/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.59 | 4.53 | 100 | 1
2368 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GOKNA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08647 | Retrofitting | Material Requisition To Resource Division | 2986/BD | 29/09/2022 | 0 | Resource Division | 0.06 | 0 | 0 | 0
2369 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Rajbari W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). , SM/10553 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by withdrawing & relaying of 90 mm dia. UPVC pipe line at different places of Rajbari W/S Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 621/HSD | 07/04/2022 | 15 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 1.52 | 1.5 | 100 | 1
2370 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Rajbari W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). , SM/10553 | Retrofitting | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep as replacement Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 250mm dia 36 mtr. long housing pipe & 150mm dia 30 mtr. long filter at Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 1893/BD | 05/07/2022 | 30 | BABUSONA CONSTRUCTION. | 43.55 | 37.54 | 86.22 | 0
2371 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Rajbari W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final). , SM/10553 | Retrofitting | Formal Work order for Laying of DI rising main and DI/UPVC distribution pipe line and Construction of 900 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Chunchura & Rajbari water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division,PHE Dte. under Barasat Division, PHE Dte. | 767/Bd | 16/03/2022 | 12 | S. GHOSH & ASSOCIATES PVT. LTD. | 563.09 | 95.49 | 100 | 100
2372 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ashariya Narayanpur to accommodate FHTC , SM/10558 | Augmentation | Formal work order for for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Ashariya Narayanpur water supply scheme, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | 2399/BD | 17/08/2022 | 90 | M/S DATTA ENTERPRISE. | 271.42 | 268.98 | 54.66 | 1
2373 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ashariya Narayanpur to accommodate FHTC , SM/10558 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Ashariya Narayanpur w/s scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 2235/BD | 28/07/2022 | 30 | M/S K.P.PAL. | 44.42 | 18.62 | 100 | 1
2374 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ashariya Narayanpur to accommodate FHTC , SM/10558 | Augmentation | Acceptance cum work order for Repairing of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir & other allied work for Augmentation of Asharia Narayanpur water supply scheme, Hasnabad block under Hasnabad Sub-Division, PHE Dte. | 1430/BD | 11/05/2023 | 45 | B.S.ENTERPRISE. (BASIRHAT) | 27.62 | 26.62 | 100 | 100
2375 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ashariya Narayanpur to accommodate FHTC , SM/10558 | Augmentation | Material Requisition To Resource Division | 2469/BD | 24/08/2022 | 0 | Resource Division | 15.08 | 0 | 0 | 0
2376 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Ashariya Narayanpur to accommodate FHTC , SM/10558 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Chhaimalpur W/S Scheme and Pump House No.I & II under Asharia-Narayanpur W/S Scheme , District of 24 Pgs. (N) NIET No.- 29 of EE/EMD of 2022-23 (Sl. No.-07) | 1003/EMD | 09/03/2023 | 695 | SWAPAN KUMAR BHANJA | 42.29 | 0 | 0 | 100
2377 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Ashariya Narayanpur to accommodate FHTC , SM/10558 | Augmentation | Formal work order for Repairing & renovation of existing AIRP capacity 54m3/hr for Augmentation of Ashariya Narayanpur w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 3713/BD | 26/12/2024 | 180 | WIST WATER SOLUTIONS PVT. LTD. | 57.54 | 0 | 0 | 0
2378 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Magurati Srirampur W/S Scheme for providing FHTC under Barasat Arsenic Division, PHE Dte. (Phase - II) , SM/10559 | Augmentation | Sinking of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation at 2nd T/W site of Magurati Srirampur w/s scheme of Baduria block under Barasat Arsenic Division, P.H.E. Dte. (Sl No. 2) | 1106/B.Ar.D. | 17/06/2022 | 45 | ACME CONSTRUCTION | 14.61 | 10.97 | 100 | 1
2379 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Magurati Srirampur W/S Scheme for providing FHTC under Barasat Arsenic Division, PHE Dte. (Phase - II) , SM/10559 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II underMagurati Srirampur W/S Scheme District of 24 Pgs. (N) (Block- Baduria). NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.- 07) | 6144/EMD | 11/11/2022 | 30 | R.N.S. TRADING | 12.8 | 11.88 | 100 | 100
2380 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Magurati Srirampur W/S Scheme for providing FHTC under Barasat Arsenic Division, PHE Dte. (Phase - II) , SM/10559 | Augmentation | Laying of UPVC pipe line for Providing Functional House Hold Tap Connection under command area of Magurati Srirampur water supply scheme of Baduria Block under JJM Programme under Barasat Arsenic Division, PHE Dte. | 243/B.Ar.D. | 02/02/2023 | 30 | UMA CONSTRUCTION | 13.6 | 13.34 | 100 | 90
2381 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC , SM/10519 | Augmentation | Repairing & renovation of Pump House No. - 1 & 2 of Gaighata W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 494/HAB | 02/12/2021 | 30 | M/S SANKAR ENTERPRISE. | 2.95 | 2.9 | 100 | 1
2382 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC , SM/10519 | Augmentation | Repairing & renovation of Pump House No. ¿ 3 of Gaighata W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 511/HAB | 10/12/2021 | 30 | M/S SANKAR ENTERPRISE. | 1.47 | 1.45 | 100 | 1
2383 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC , SM/10519 | Augmentation | Material Requisition To Resource Division | 3796/BD | 22/12/2022 | 0 | Resource Division | 177.61 | 0 | 0 | 0
2384 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC , SM/10519 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 of Gaighata water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | 1408/BD | 08/05/2023 | 30 | NADIA TUBEWELLS | 28.98 | 25.15 | 100 | 100
2385 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC , SM/10519 | Augmentation | Material Requisition To Resource Division | 3106/BD | 18/10/2022 | 0 | Resource Division | 14.06 | 0 | 0 | 0
2386 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC , SM/10519 | Augmentation | Material Requisition To Resource Division | 1555/BD | 23/05/2023 | 0 | Resource Division | 7.44 | 0 | 0 | 0
2387 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC , SM/10519 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Janapul W/S Scheme and Bergum W/S Scheme with Pump House No-I, II And III under Gaighata W/S Scheme District of 24 Pgs. (N) | 4797/EMD | 09/08/2023 | 570 | MAHADEV ENTERPRISE | 74.15 | 16.05 | 50.52 | 57
2388 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC , SM/10519 | Augmentation | Special repair and renovation of pump house and other Allied Works for Pump House No - 1 of Gaighata WS scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 921/HAB | 30/10/2024 | 20 | DEBASISH SARKAR. | 2.65 | 0 | 0 | 0
2389 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC , SM/10519 | Augmentation | Construction of Service Road 45 Mtr. Length X 2 Mtr. Width for Pump House No 1 of Gaighata Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 917/HAB | 30/10/2024 | 10 | M/S DAS & CO. | 2.75 | 0 | 0 | 0
2390 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC , SM/10519 | Augmentation | Construction of Service Road 17 Mtr. Length X 2 Mtr. Width for Pump House No 2 of Gaighata Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 919/HAB | 30/10/2024 | 10 | DEBANJAN GHOSH. | 1.04 | 0 | 0 | 0
2391 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC , SM/10519 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 3 for Augmentation of Gaighata water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | 2778/BD | 11/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 14.47 | 11.64 | 100 | 100
2392 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC , SM/10519 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of at Gaighata Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 2533/BD | 29/08/2022 | 1260 | SUPRITI ENTERPRISE. | 482.07 | 404.3 | 83.87 | 90
2393 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC , SM/10519 | Augmentation | Acceptance cum work order for Construction of Boundary Wall (110 m Length) for Pump House No - 1 of Gaighata water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | 2283/BD | 13/08/2024 | 160 | PUSPA CONSTRUCTION. | 16.34 | 0 | 0 | 0
2394 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC , SM/10519 | Augmentation | Improvement of Iron Elimination Plant including repairing of drain and other allied works of Gaighata W/S Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 692/HAB | 25/07/2024 | 30 | M/S LATIKA CONSTRUCTION. | 4.07 | 4.06 | 100 | 100
2395 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gaighata to accommodate FHTC , SM/10519 | Augmentation | Acceptance cum work order for Construction of Boundary Wall (70 m Length) for Pump House No - 2 of Gaighata water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | 2285/BD | 13/08/2024 | 20 | VAI ENTERPRISE. | 11.03 | 0 | 0 | 100
2396 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10100 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Patulia Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | 1194/NWSD-I | 31/12/2021 | 15 | UMWELT ENGINEER PRIVATE LIMITED | 4.88 | 4.88 | 100 | 1
2397 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10100 | Augmentation | Repair and renovation works for 900 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir, Boundary wall, Pump House and construction of Godown at H/W site with other allied works at Patulia W/S Scheme under North 24 Pgs Water Supply Division- I, P.H.E. Dte. | 1264/NWSD-I | 21/08/2023 | 60 | M/S. ASOKE GHOSH AND BROTHERS | 55.54 | 0 | 0 | 0
2398 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10100 | Augmentation | CONSTRUCTION OF PUMP HOUSE (4.88M X 3.66M) INCLUDING SANITARY ARRANGEMENT at Ruiya Verir Gate Bazar, Dag no.- 220, Khatian no.- 715, J.L. no- 20 under Patulia Water supply scheme within the jurisdiction of North 24 Pgs Water Supply Division- I, P.H.E. Dte. (Sl. No. 07). | 1510/NWSD-I | 22/09/2023 | 60 | M/S. ASOKE GHOSH AND BROTHERS | 5.57 | 0 | 0 | 0
2399 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10100 | Augmentation | Material Requisition To Resource Division | 675/NWSD-I | 26/05/2022 | 0 | Resource Division | 69.9 | 0 | 0 | 0
2400 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10100 | Augmentation | Material Requisition To Resource Division | 642/NWSD-I | 20/05/2022 | 0 | Resource Division | 58.46 | 0 | 0 | 0
2401 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10100 | Augmentation | Material Requisition To Resource Division | 1842/NWSD-I | 10/11/2023 | 0 | Resource Division | 3.08 | 0 | 0 | 0
2402 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10100 | Augmentation | CONSTRUCTION OF PUMP HOUSE (4.88M X 3.66M) INCLUDING SANITARY ARRANGEMENT at Patulia Girls School Ground ( Bandipur Play Ground ) Dag No. 1552, LR KH No.282 , JL No. 04 under Patulia Water supply scheme within the jurisdiction of North 24 Pgs Water Supply Division- I, P.H.E. Dte. (Sl. No. 08) | 1434/NWSD-I | 11/09/2023 | 60 | A. S. ENTERPRISE | 5.57 | 5.54 | 100 | 100
2403 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10100 | Augmentation | Supply and installation of Display Board to be placeed at BILKANDA ZONE-I, BANDIPUR, BILKANDA ZONE-II, PATULIA and MOHANPUR, Zone-I-B (Telinipara), Zone-IA-II (Chak Kanthalia) pipe water supply scheme for Barrackpore-II Block under North 24 Pgs. Water Supply Division-I, PHE. Dte. | 70/NWSD-I | 10/01/2024 | 30 | BIBHAS PAL | 4.94 | 0.53 | 100 | 100
2404 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Patulia Block- Barrackpur-II, Dist-North 24 Parganas. , SM/10100 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House Hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC , Schedule 80/20 mm OD HDPE (PE 100, PN16) pipe with all necessary works within command area of Patulia Water Supply Scheme under North 24 Parganas Water Supply Division-I, PHE Dte. | 670/ NWSD-I | 26/05/2022 | 90 | CONCORD ENGINEERING | 786.84 | 613.09 | 77.92 | 90
2405 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC , SM/10309 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Gangrapota water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 536/BON | 03/11/2021 | 21 | GHOSH CONSTRUCTION. | 2.52 | 2.48 | 100 | 1
2406 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC , SM/10309 | Augmentation | Repairing & Renovation of 01No. Pump House (PH-III) and allied works at Gangrapota water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 635/ BON | 31/12/2021 | 15 | GHOSH CONSTRUCTION. | 1.26 | 1.15 | 100 | 1
2407 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC , SM/10309 | Augmentation | Making Suitable Foundation at out side of the PUmp House of 1000ltr PV Tank at PH-I Z-II under Kurulia W/S Scheme, W/O-1036/SD-I, T.No.1132/SD-I | 1036/SD I | 04/05/2021 | 30 | TAMAL ENTERPRISE | 0.63 | 0 | 0 | 0
2408 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC , SM/10309 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Gangrapota water supply scheme (2nd T/W site) under Bongaon Sub-Division P.H.E.Dte. | 3621/BD | 12/12/2022 | 15 | DHELA BABA ENTERPRISE | 15.12 | 13.34 | 88.23 | 0
2409 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC , SM/10309 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under Ganrapota W/S Scheme District of 24 Pgs. (N) (Block- Baduria).NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.-04) | 6141 / EMD | 14/08/2022 | 30 | TRIDENT ENTERPRISE | 9.29 | 9.29 | 100 | 1
2410 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC , SM/10309 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I under gangrapota W/S Scheme District of 24 Pgs. (N) | 6140 / EMD | 14/08/2022 | 30 | GHOSH AND GHOSH | 12.82 | 10.58 | 82.56 | 1
2411 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC , SM/10309 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Gangrapota Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation) | 1004/BD | 04/04/2022 | 90 | M/S DIPAK ENTERPRISE | 298.46 | 282.74 | 100 | 1
2412 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC , SM/10309 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under Ganrapota W/S Scheme District of 24 Pgs. (N) (Block- Baduria).NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.-04) | 6141-EMD | 11/11/2022 | 151 | TRIDENT ENTERPRISE | 2.7 | 2.7 | 100 | 0
2413 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC , SM/10309 | Augmentation | Material Requisition To Resource Division | 1369/BD | 13/05/2022 | 0 | Resource Division | 26.76 | 0 | 0 | 0
2414 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC , SM/10309 | Augmentation | Material Requisition To Resource Division | 1675/BD | 13/06/2022 | 0 | Resource Division | 76.64 | 0 | 0 | 0
2415 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC , SM/10309 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Gangrapota Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | 2928/BD | 26/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.13 | 8.27 | 100 | 100
2416 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC , SM/10309 | Augmentation | Construction of Approach Road at 2nd Pump House site for Augmentation of Gangrapota Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 555/Bon | 18/07/2023 | 15 | M/S SAYAN ENTERPRISE. | 0.8 | 0.79 | 100 | 100
2417 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC , SM/10309 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Gangrapota Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 519/BD | 20/02/2024 | 30 | S.D. CONSTRUCTION. | 15.09 | 15.08 | 100 | 100
2418 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC , SM/10309 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household of Chanda, Gangrapota, Gobrapur and Kamalapur mouzas including laying of UPVC pipe with pile work under Augmentation work at Gangrapota W/S Scheme Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | 1387/BD | 30/04/2025 | 90 | ONKAR ENTERPRISE. | 76.95 | 0 | 0 | 0
2419 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gangrapota to Accommodate FHTC , SM/10309 | Augmentation | Laying of DI pipe for inter-connection with newly sunk Replacement Tube Wells and OHR Connection and urgent allied works in distribution system under Augmentation work at Gangrapota W/S Scheme under Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 480/Bon | 07/04/2025 | 30 | GHOSH CONSTRUCTION. | 2.34 | 0 | 0 | 100
2420 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC , SM/10690 | Augmentation | Repairing & Renovation of 01No. Pump House and allied works at Chikonpara water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 632/BON | 31/12/2021 | 21 | MA CONSTRUCTION. | 1.26 | 1.19 | 100 | 1
2421 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC , SM/10690 | Augmentation | Repairing & Renovation of 02No. Pump House and allied works at Chikonpara water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 586/BON | 15/12/2021 | 21 | MA CONSTRUCTION. | 2.52 | 2.34 | 100 | 1
2422 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC , SM/10690 | Augmentation | Material Requisition To Resource Division | 1368/BD | 13/05/2022 | 0 | Resource Division | 46.36 | 0 | 0 | 0
2423 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC , SM/10690 | Augmentation | Renovation and repairing of Boundary wall and Construction of Approach Road at 2nd Tube Well site under Augmentation of Chikanpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 977/Bon | 27/12/2023 | 30 | M/S SAYAN ENTERPRISE. | 4.84 | 0 | 0 | 0
2424 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC , SM/10690 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Chikanpara Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 3762/BD | 20/12/2022 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 481.61 | 481.36 | 100 | 100
2425 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC , SM/10690 | Augmentation | Acceptance cum work order for Renovation & repairing of Boundary wall at Head work site for Augmentation of Chikanpara water Supply scheme, Gaighata Block within jurisdiction of Bongaon Sub-Division, P.H.E. Dte. | 4413/BD | 10/11/2023 | 60 | VAI ENTERPRISE. | 10.85 | 10.76 | 100 | 100
2426 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC , SM/10690 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at 3rd Tube Well site and Construction of Approach Road at 3rd Tube Well site and Head work site under Augmentation of Chikanpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 40/BD | 04/01/2024 | 23 | M/S.RAJESH CONTRUCTION | 8.42 | 8.18 | 100 | 100
2427 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC , SM/10690 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Rep) under Chikanpara W/S Scheme and Pump House No.I, II and III under Chandpara W/S Scheme District of 24 Pgs. (N) | 4795/EMD | 09/08/2023 | 754 | DAS ENTERPRISE (M) | 78.21 | 15.4 | 39.38 | 60
2428 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC , SM/10690 | Augmentation | Acceptance cum work order for Special Repairing work in connection with augmentation work at total command area of Chikanpara Water Supply Scheme, to repair the damaged pipeline due to road widening and drain construction, to extend the Backwash line and also to convert the mouzas into Swajal Gram within Bongaon Sub Division, under Barasat Division, P.H.E.Dte. | 1904/BD | 05/06/2025 | 120 | MA CONSTRUCTION. | 13.57 | 0 | 0 | 0
2429 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC , SM/10690 | Augmentation | Repairing and renovation of 150 Cum C.W.R. for Augmentation of Chikanpara Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 816/Bon | 26/06/2025 | 45 | MA CONSTRUCTION. | 1.8 | 0 | 0 | 0
2430 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC , SM/10690 | Augmentation | Construction of Latrine at Head Work site and Renovation of P/H No-1 for Chikanpara Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 638/Bon | 21/05/2025 | 45 | MA CONSTRUCTION. | 4.31 | 0 | 0 | 0
2431 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC , SM/10690 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chikanpara water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | 2690/BD | 04/09/2023 | 510 | JOY HIND TUBEWELLS. | 16.16 | 14.26 | 100 | 100
2432 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC , SM/10690 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chikanpara water supply scheme at Head Work Site under Bongaon Sub-Division P.H.E.Dte. | 2686/BD | 04/09/2023 | 420 | JOY HIND TUBEWELLS. | 16.16 | 13.56 | 100 | 100
2433 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chikanpara to accommodate FHTC , SM/10690 | Augmentation | Acceptance cum work order for Improvement of Iron Elimination Plant and other related allied works and Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Chikanpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 54/BD | 05/01/2024 | 30 | MONDAL & CO.(BON) | 6.02 | 6.02 | 100 | 100
2434 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC , SM/10782 | Augmentation | Repairing & renovation of Pump House No. - 1 & 2 of BiraRajibpur W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 499/HAB | 02/12/2021 | 30 | B.M.ENTERPRISE. | 2.15 | 2.1 | 100 | 1
2435 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC , SM/10782 | Augmentation | Material Requisition To Resource Division | 3793/BD | 22/12/2022 | 0 | Resource Division | 272.77 | 0 | 0 | 0
2436 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC , SM/10782 | Augmentation | Acceptance cum work order for the work of Hiring Diesel Luxury Car on daily basis for the Office of the Dy. Superintending Engineer-I, Monitoring Cell, PHE Dte. (Period from 01-01-2023 to 30-06-2023). | 3867/BD | 30/12/2022 | 181 | DIPANKAR NASKAR. | 0.86 | 1.85 | 100 | 1
2437 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC , SM/10782 | Augmentation | Acceptance cum work order for Sinking of 2 no. 300 mm. x 200 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 300 mm. dia. 36 mtr. long housing pipe & 200 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 of Bira Rajibpur water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | 1410/BD | 08/05/2023 | 30 | M/S K.P.PAL. | 39.12 | 31.66 | 100 | 100
2438 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC , SM/10782 | Augmentation | Material Requisition To Resource Division | 2518/BD | 25/08/2022 | 0 | Resource Division | 21.54 | 0 | 0 | 0
2439 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC , SM/10782 | Augmentation | Material Requisition To Resource Division | 1554/BD | 23/05/2023 | 0 | Resource Division | 13.55 | 0 | 0 | 0
2440 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC , SM/10782 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Bira-Rajibpur W/S Scheme, Khasdelpur W/S Scheme and Kumarjole W/S Scheme with Pump House No-I under Sadpur W/S Scheme District of 24 Pgs. (N) | 4490/EMD | 14/07/2023 | 537 | EASTERN INDIA SALES & SERVICE | 74.22 | 19.18 | 90.46 | 90
2441 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC , SM/10782 | Augmentation | Formal Work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Bira Rajibpur Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 2447/BD | 23/08/2022 | 1251 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 619.57 | 197.69 | 31.91 | 75
2442 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC , SM/10782 | Augmentation | Hiring of 1 no. of Diesel Luxury Car (Euro - IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer, Habra Sub-Division, under Barasat Division P.H.E. Dte. (For the period from: 01.12.2023 to 30.11.24) | 720/HAB | 23/11/2023 | 366 | M/S LATIKA CONSTRUCTION. | 1.74 | 3.89 | 223.48 | 60
2443 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC , SM/10782 | Augmentation | Continuation work order Hiring of 1 no. of Diesel Luxury Car (Euro ¿ IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer, for supervision of J.J.M. related work, executed within the entire jurisdiction of Habra Sub-Division, under Barasat Division P.H.E. Dte. (For the period from :01.09.24 to 28.02.25) = six months | 780/HAB | 28/08/2024 | 184 | M/S SUKANTA ENTERPRISE. | 0.86 | 1.79 | 208.06 | 100
2444 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC , SM/10782 | Augmentation | Continuation work order for Hiring of 1 no. of Diesel Luxury Car (Euro - IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer, Habra Sub-Division, under Barasat Division P.H.E. Dte. (For the period from : 01.12.24 to 31.05.25) | 993/HAB | 29/11/2024 | 182 | M/S LATIKA CONSTRUCTION. | 0.86 | 1.83 | 212.06 | 0
2445 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC , SM/10782 | Augmentation | Acceptance cum work order for Construction of Boundary Wall (35 m Length) for Pump House No - 1 of Bira-Rajibpur water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | 2282/BD | 13/08/2024 | 30 | M/S LATIKA CONSTRUCTION. | 5.65 | 0 | 0 | 100
2446 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. , SM/10579 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Mohonpur Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | 1190/NWSD-I | 31/12/2021 | 15 | UMWELT ENGINEER PRIVATE LIMITED | 4.88 | 4.88 | 100 | 1
2447 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. , SM/10579 | Augmentation | Sinking of 01 No. Tube well 300 x 200 mm dia, 300 mtr. Depth at 2nd Tube Well site within command area of Mohanpur Water Supply Scheme at Barrackpore-II Block under North 24 Parganas Water Supply Division-I, PHE. Dte. | 1409/NWSD-I | 13/12/2022 | 20 | AUXILIARY TUBEWELL DRILLER | 21.05 | 15 | 100 | 1
2448 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. , SM/10579 | Augmentation | Construction of BOUNDARY WALL for 44 m Length, Special Repair & Renovation one Pump house and Allied Works & Service Road (25 Mtr. Length X 2 Mtr. Width) at 3rd. pump house site at Mohanpur Water Supply scheme in Barrackpur-II Block under North 24 Parganas water Supply Division-I, PHE Dte. | 447/NWSD-I | 25/04/2023 | 45 | BANERJEE ENTERPRISE | 9.93 | 7.92 | 100 | 100
2449 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. , SM/10579 | Augmentation | Material Requisition To Resource Division | 1839/NWSD-I | 10/11/2023 | 0 | Resource Division | 15.4 | 0 | 0 | 0
2450 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. , SM/10579 | Augmentation | Construction of Boundary wall other allied works at proposed head work site at Babanpur (behind Santi Sarabar) of Mohanpur Water supply scheme within the jurisdiction of North 24 Pgs Water Supply Division- I, P.H.E. Dte. | 1396/NWSD-I | 05/09/2023 | 60 | DAS TRADING | 34 | 10.74 | 31.6 | 5
2451 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. , SM/10579 | Augmentation | Restoration & Development of road of proposed H/W Site at Babanpur (behind Santi Sarabar) & protection work of Boundary wall along pond sitde of existing Head Work site under Augmentation work at Mohanpur W/S Scheme within the jurisdiction of N24Pgs. W/S Sub-Division-I, P.H.E. Dte. | 1630/NWSD-I | 12/11/2024 | 30 | A.K.C. SUPPLY & CONSTRUCTION | 26.81 | 0 | 0 | 0
2452 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. , SM/10579 | Augmentation | Sinking of 01 No. Tube well 300 x 200 mm dia, 300 mtr. Depth at Head Works site within command area of Mohanpur Water Supply Scheme at Barrackpore-II Block under North 24 Parganas Water Supply Division-I, PHE. Dte. | 653/NWSD-I | 29/05/2023 | 20 | AUXILIARY TUBEWELL DRILLER | 21.07 | 17.12 | 100 | 100
2453 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. , SM/10579 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir of 250 Cum capacity at Head work site of Mohanpur water supply scheme and other ancilary works under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | 1397/NWSD-I | 05/09/2023 | 60 | DAS TRADING | 14.15 | 14.13 | 100 | 100
2454 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. , SM/10579 | Augmentation | Construction of Pump house (4.88m X 3.66m) including Sanitary arrenagement And strenthing the approach road along with other allied works at proposed head work site at Babanpur (behind Santi Sarabar) of Mohanpur Water supply scheme within the jurisdiction of North 24 Pgs Water Supply Division- I, P.H.E. Dte. | 1395/NWSD-I | 05/09/2023 | 60 | A.K.C. SUPPLY & CONSTRUCTION | 20.92 | 20.89 | 100 | 100
2455 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. , SM/10579 | Augmentation | Supply and installation of Display Board to be placeed at BILKANDA ZONE-I, BANDIPUR, BILKANDA ZONE-II, PATULIA and MOHANPUR, Zone-I-B (Telinipara), Zone-IA-II (Chak Kanthalia) pipe water supply scheme for Barrackpore-II Block under North 24 Pgs. Water Supply Division-I, PHE. Dte. | 70/NWSD-I | 10/01/2024 | 30 | BIBHAS PAL | 4.94 | 0.35 | 100 | 100
2456 | NORTH 24 PARGANAS | Electrical | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. , SM/10579 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MOHANPUR PIPED W/S SCHEME, T.W. No. IV, Block: Barrackpore-II, District - North 24 Pgs. under JJM Program under Electrical Division PHE Dte. | 426/ED | 29/02/2024 | 90 | DEY ENTERPRISE | 10.43 | 10.16 | 97.45 | 100
2457 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. , SM/10579 | Augmentation | Material Requisition To Resource Division | 670/NWSD-I | 18/04/2024 | 0 | Resource Division | 74.34 | 0 | 0 | 0
2458 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. , SM/10579 | Augmentation | Material Requisition To Resource Division | 214/NWSD-I | 02/02/2024 | 0 | Resource Division | 12.32 | 0 | 0 | 0
2459 | NORTH 24 PARGANAS | Electrical | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. , SM/10579 | Augmentation | Quotation for New service connection at Mohanpur PWSS Head Works Site SM/10579 | 822 | 01/03/2024 | 0 | WBSEDCL | 5.43 | 0 | 0 | 0
2460 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte. , SM/10579 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system, Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works, Construction of 500 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including 550 mm dia. pile foundation and pipe connection and Soil investigation for construction of one RCC Over Head Reservoir of staging height 20 Mtr. within command area of Mohanpur Water Supply Scheme in Barrackpore-II Block under district North 24 Parganas Water Supply Division-I, PHE. Dte. | 639/NWSD-I | 26/05/2023 | 1316 | CONCORD ENGINEERING | 716.1 | 261.78 | 36.56 | 60
2461 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. , SM/10580 | Augmentation | Survey, Design and preparation of Retrofitting DPR in connection with " Providing functional household tap connection to every Household under Auldanga Zone-I W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte." | 314/NWSD - I | 21/03/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.3 | 4.3 | 100 | 1
2462 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. , SM/10580 | Augmentation | Repair and renovation works of 700 m3 RCC Elevated Reservoir, Boundary Wall, Pump House, Service roads etc. at Head Works Site and other tube well Sites under AULDANGA ZONE-I Water Supply scheme in Bagdah Block under North 24 Parganas water Supply Division-I, PHE Dte. | 234/NWSD-I | 02/03/2023 | 60 | ONKAR ENTERPRISE | 65.07 | 59.43 | 91.33 | 0
2463 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. , SM/10580 | Augmentation | Laying of distribution pipe line & Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete at Auldanga Zone -I W/S Scheme in the District of North 24 Parganas under North 24 Parganas water Supply Division-I, PHE Dte. | 1511/NWSD-I | 22/09/2023 | 60 | M/S. ASOKE GHOSH AND BROTHERS | 38.23 | 0 | 0 | 2
2464 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. , SM/10580 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system & Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works within command area of Auldanga Zone-1 Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE. Dte. | 875/NWSD-I | 22/07/2022 | 90 | MONDAL ENTERPRISE | 259.06 | 256.45 | 100 | 85
2465 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. , SM/10580 | Augmentation | Material Requisition To Resource Division | 881/NWSD-I | 22/07/2022 | 0 | Resource Division | 79.88 | 0 | 0 | 0
2466 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. , SM/10580 | Augmentation | Material Requisition To Resource Division | 1163/NWSD-I | 26/09/2022 | 0 | Resource Division | 0.01 | 0 | 0 | 0
2467 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. , SM/10580 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I, II and III Zone-I Rep. under Auldanga WS Scheme District of 24 Pgs. North. WBPHED/EE/EMD/NIET-27/2022-2023 [SL.-2] | 4758./EMD | 07/08/2023 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 39.72 | 23.06 | 58.06 | 60
2468 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. , SM/10580 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1430/NWSD-I | 18/09/2024 | 7 | BIBHAS PAL | 5.27 | 0.18 | 50 | 100
2469 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. , SM/10580 | Augmentation | Renovation of AIRP at Auldanga Zone-I Water Supply Scheme of capacity 147.88 Cu.m/hr of Bongaon Block under North 24 Pgs. W/S Div-I, PHE Dte. | 1668/NWSD-I | 19/11/2024 | 360 | J. D. J. ENTERPRISE, A UNIT OF JDJ TRADERS PRIVATE LIMITED | 109.3 | 0 | 0 | 60
2470 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. , SM/10580 | Augmentation | Protection work & land development at H/W Site under Augmentation Scheme of Auldanga W/S Scheme (Zone - II) within the jurisdiction of N24Pgs. W/S Division-I, P.H.E. Dte. | 54/NWSD-I | 09/01/2025 | 30 | MONDAL ENTERPRISE | 45.44 | 0 | 0 | 0
2471 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Auldanga Zone-I Water Supply Scheme in Bagdah Block of North 24 Parganas District under North 24 Pgs. W/S Div-I, P.H.E. Dte. , SM/10580 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1431/NWSD-I | 18/09/2024 | 7 | IMAGIN | 4.59 | 0 | 0 | 95
2472 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12566 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-VI/A (Beraberia) of Surface based Water Supply Scheme for Arsenic affected areas of N 24 Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 333/NWSD-I | 24/03/2022 | 1 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.83 | 4.96 | 100 | 1
2473 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12566 | Augmentation | Material Requisition To Resource Division | 471/NWSD-I | 26/04/2023 | 0 | Resource Division | 157.98 | 0 | 0 | 0
2474 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12566 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI, A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District. | 4028/ED | 17/10/2023 | 183 | WEST BENGAL ENGINEERING CO. | 33.17 | 0 | 0 | 10
2475 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12566 | Augmentation | Material Requisition To Resource Division | 1707/NWSD-I | 26/11/2024 | 0 | Resource Division | 10.16 | 0 | 0 | 0
2476 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12566 | Augmentation | Madhabpur to Harpara Dakshin Package No. WB-01-336 due to laying pipi line. | 218/PFMS/24-25 | 25/09/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA, NORTH 24 PARGANAS DIVISION | 13.5 | 0 | 0 | 0
2477 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12566 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 214.68 | 25.08 | 2
2478 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12566 | Augmentation | Road restoration along flank portion of Rafipur Padmanavpur Kakinara PWD road, Madhavpur High School (Node 563) to Dishari Adarsha Siksha Niketan (Node - 804) due to laying of pipeline under Augmentation work at Beraberia (Zone- VI A) W/S Scheme in Amdanga Block under North 24Pgs. W/S Division-I, P.H.E. Dte. | 777/NWSD-I | 23/05/2025 | 30 | AREOCON | 12.54 | 0 | 0 | 0
2479 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajnagar to accommodate FHTC , SM/11630 | Augmentation | Route Survey, Design Drawing & DPR Preparation for RAJNAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 208/ BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.72 | 2.63 | 50 | 1
2480 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajnagar to accommodate FHTC , SM/11630 | Augmentation | Acceptance cum work order for Laying of UPVC distribution main and Providing FHTC (Functional Household Tap Connection ) by augmentation for Rajnagar water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | 3587/BD | 08/12/2022 | 30 | B.S.ENTERPRISE. (BASIRHAT) | 62.54 | 62.4 | 100 | 100
2481 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajnagar to accommodate FHTC , SM/11630 | Augmentation | Material Requisition To Resource Division | 485/BD | 17/02/2023 | 0 | Resource Division | 0.44 | 0 | 0 | 0
2482 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Rajnagar to accommodate FHTC , SM/11630 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Bansjhari-Mullickpur and Maminpur W/S Scheme with Pump House No-I under Rajnagar W/S Scheme District of 24 Pgs. (N) | 4809./EMD | 09/08/2023 | 30 | S.G. ENTERPRISE | 65.16 | 9.03 | 69.31 | 75
2483 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Rajnagar to accommodate FHTC , SM/11630 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.- II under Rajnagar ground water based water supply scheme under Block_ Basirhat-II Dist. - 24 PARAGANAS (N) under EMD, PHE Dte. [SM/11630] | 2689/EMD | 20/11/2024 | 30 | S M ELECTRICALS | 6.98 | 0 | 0 | 0
2484 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-II to accommodate FHTC , SM/11701 | Augmentation | Material Requisition To Resource Division | 1236/BD | 25/04/2023 | 0 | Resource Division | 4.59 | 0 | 0 | 0
2485 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-II to accommodate FHTC , SM/11701 | Augmentation | Material Requisition To Resource Division | 1633/BD | 01/06/2023 | 0 | Resource Division | 10.1 | 0 | 0 | 0
2486 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-II to accommodate FHTC , SM/11701 | Augmentation | Material Requisition To Resource Division | 1646/BD | 02/06/2023 | 0 | Resource Division | 13.76 | 0 | 0 | 0
2487 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-II to accommodate FHTC , SM/11701 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) with Pump House no-III(New) under Monipur W/S Scheme with Bajitpur (I and II, Zone-II) W/S Scheme in District of 24 Pgs. (N) | 6739/EMD | 29/11/2023 | 580 | GLACIER ENGINEERING CO. | 67.8 | 0 | 0 | 40
2488 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-II to accommodate FHTC , SM/11701 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Bajitpur Zone-II water supply scheme (Zone-II), in Baduria Block under Barasat Division, PHE Dte. | 1190/BD | 19/04/2023 | 738 | DIVINE | 330.08 | 306.72 | 99.71 | 50
2489 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-II to accommodate FHTC , SM/11701 | Augmentation | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Bazitpur, zone - II W/S Scheme including increasing the height of back wash water tank at Baduria Block under Basirhat Sub Division, PHE Dte. Capacity- 90.00 Cum/hr. | 921/BD | 15/03/2024 | 360 | MONDAL PRECISION PVT.LTD | 36.2 | 0 | 0 | 90
2490 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mirjanagar to accommodate FHTC , SM/11702 | Augmentation | Material Requisition To Resource Division | 606/BD | 23/02/2023 | 0 | Resource Division | 10.48 | 0 | 0 | 0
2491 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mirjanagar to accommodate FHTC , SM/11702 | Augmentation | Material Requisition To Resource Division | 856/BD | 20/03/2023 | 0 | Resource Division | 23.33 | 0 | 0 | 0
2492 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mirjanagar to accommodate FHTC , SM/11702 | Augmentation | Acceptance cum work order for Restoration of roads under different water supply schemes of Basirhat II Block within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | 3554/BD | 16/12/2024 | 30 | M/S MAA TARA ENTERPRISE | 29.52 | 0 | 0 | 0
2493 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mirjanagar to accommodate FHTC , SM/11702 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipeline and Providing FHTC (Functional Household Tap Connection ) for augmentation of Mirjanagar water supply scheme in Basirhat-II block of North 24 Parganas District under Barasat Division, PHE Dte. | 3476/BD | 01/12/2022 | 90 | SUPER SKILL. | 288.66 | 287.73 | 100 | 90
2494 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mirjanagar to accommodate FHTC , SM/11702 | Augmentation | Acceptance cum work order for Special repair and renovation of existing structures like Pump House, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Itinda Panitor, Joypur Gopmahal, Kachua Swarupnagar, Mathurapur, Mirzanagar, Nalkora, Paikardanga, Pifa and Gobindapur Water Supply Scheme of different block under Basirhat Sub-Division within Barasat Division, P.H.E Dte. | 2474/BD | 17/07/2025 | 150 | SAHA CONSTRUCTION & CO | 91.3 | 0 | 0 | 0
2495 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mirjanagar to accommodate FHTC , SM/11702 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method at Pump House 2 using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Mirjanagar Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | 3259/BD | 25/11/2024 | 137 | ANJALI ENTERPRISE. | 21.75 | 0 | 0 | 100
2496 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mirjanagar to accommodate FHTC , SM/11702 | Augmentation | Acceptance cum work order for Restoration of roads and emergency protection work under different places of Mirzanagar Water Supply Scheme within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | 1021/BD | 28/03/2025 | 60 | LUCKY CONSTRUCTION. | 5.69 | 0 | 0 | 100
2497 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11544 | Augmentation | Preparation of Augmentation DPR for Bahira Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | 1956/B.Ar.D | 26/09/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0.98 | 100 | 1
2498 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11544 | Augmentation | Laying of distribution System including specials, valves all complete Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Bahira under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 1742/B.Ar.D. | 07/09/2022 | 90 | MADE AND TRADE CO. | 311.1 | 253.32 | 81.43 | 72
2499 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11544 | Augmentation | Sinking of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method near H/W Side with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation of Bahira w/s scheme of Barasat-II block under Barasat Arsenic Division, P.H.E. Dte. (Sl No. 1) | 2055/B.Ar.D. | 19/10/2022 | 45 | UNIFIED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 15.58 | 13.76 | 100 | 70
2500 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11544 | Augmentation | Material Requisition To Resource Division | 205/B.Ar.D. | 30/01/2023 | 0 | Resource Division | 16.41 | 0 | 0 | 0
2501 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11544 | Augmentation | Material Requisition To Resource Division | 28/B.Ar.D. | 05/01/2023 | 0 | Resource Division | 12.26 | 0 | 0 | 0
2502 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11544 | Augmentation | Hiring of one (1) no. Diesel operated motor cab (Car No.- WB25L-3454) with driver for official use for Assistant Engineer (Sub-Division), under Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil w.e.f. 01.05.2023 to 16.11.2023. | 1008/B.Ar.D | 26/04/2023 | 200 | PREMANANDA ROY BISWAS | 0.95 | 2.3 | 128.48 | 70
2503 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11544 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (Car No.- WB-25L-3454) with driver for official use for Assistant Engineer (Sub-Division), under Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil w.e.f. 17.11.2023 to 30.11.2023". | 2661/B.Ar.D | 09/11/2023 | 14 | PREMANANDA ROY BISWAS | 0.07 | 0.16 | 247.8 | 0
2504 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11544 | Augmentation | Sal-Bullah Pilling for pipe protection work at Bahira under Barasat-II Block Under Barasat Arsenic Division, PHE Dte. | 981/B.Ar.D. | 18/06/2024 | 25 | CHAKRABORTY SUPPLIERS & CONSTRUCTION | 5.85 | 5.81 | 100 | 100
2505 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11544 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir & other existing civil component of Capacity 550 Cu.m. at Bahira W/S Scheme under Barasat-II Block under Barasat Arsenic Division, PHE Dte. | 237/B.Ar.D. | 02/02/2023 | 841 | MONDAL ENTERPRISE | 16.32 | 10.13 | 62.09 | 40
2506 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11544 | Augmentation | Inter connection of pump with Existing IEP and other allied works of Bahira W/S Scheme Barasat-II Block under Barasat Arsenic Division, PHE Dte. | 429/B.Ar.D. | 10/03/2025 | 30 | S.B.S. ENTERPRISE | 2.5 | 0 | 0 | 100
2507 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for BAHIRA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11544 | Augmentation | Damage pipeline laying and other allied works of Bahira W/S Scheme Barasat-II Block under Barasat Arsenic Division, PHE Dte. | 427/B.Ar.D. | 10/03/2025 | 30 | S.B.S. ENTERPRISE | 3.93 | 0 | 0 | 100
2508 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11545 | Augmentation | Preparation of Augmentation DPR for Chowmuha Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | 1954/B.Ar.D | 26/09/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0.99 | 100 | 1
2509 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11545 | Augmentation | Material Requisition To Resource Division | 29/B.Ar.D. | 05/01/2023 | 0 | Resource Division | 1.53 | 0 | 0 | 0
2510 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11545 | Augmentation | Emergent Protection of 90 mm dia UPVC Pipeline in between Node 459-460&106-107 related to the work " Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Chaumuha Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte." (60mtr) | 2374/B.Ar.D. | 27/09/2023 | 30 | NEELAM ENTERPRISE | 5.89 | 5.88 | 100 | 100
2511 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11545 | Augmentation | Emergent Protection of 90 mm dia UPVC Pipeline in between Node 459-460 & 106-107 related to the work "Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Chaumuha Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte." (60mtr). | 2658/B.Ar.D. | 09/11/2023 | 30 | MONDAL ENTERPRISE | 5.93 | 5.88 | 100 | 100
2512 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11545 | Augmentation | Emergent Protection of 90 mm dia UPVC Pipeline in between Node 374-376 related to the work " Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Chaumuha Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 3029/B.Ar.D. | 29/12/2023 | 30 | RHINE CONSTRUCTION | 4.63 | 4.61 | 100 | 100
2513 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11545 | Augmentation | Laying of 200 mm dia D.I rising main from 2nd Tubewell to Head work site of Chaumuha W/S scheme at Barasat - II under Barasat Arsenic Division, P.H.E. Dte. | 3007/B.Ar.D | 28/12/2023 | 21 | R. UNIQUE CONSTRUCTION | 0.93 | 0.92 | 100 | 100
2514 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11545 | Augmentation | Repair and Renovation works of 250 Cum OHR and allied water supply component infrastructure under Chaumuha W/S Scheme of Barasat -II Block under Barasat Arsenic Division, PHE Dte. | 3026/B.Ar.D. | 29/12/2023 | 45 | BANERJEE CONSTRUCTION | 19.55 | 19.41 | 100 | 100
2515 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11545 | Augmentation | Increse of Water pressure through by pass Pipeline from Second tubewell to main distribution pipeline and allied repairing works in Chaumuha Water Supply Scheme under Barasat Arsenic Division, P.H.E Dte. | 983/B.Ar.D. | 18/06/2024 | 21 | BANERJEE CONSTRUCTION | 2.53 | 2.35 | 100 | 100
2516 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11545 | Augmentation | Restoration of Road due to Laying of 200 mm dia D.I rising main from 2nd Tubewell to Head work site at Chaumuha Purbapara of Chaumuha W/S scheme at Barasat - II under Barasat Arsenic Division, P.H.E. Dte. | 1847/B.Ar.D | 21/11/2024 | 21 | R. UNIQUE CONSTRUCTION | 0.95 | 0.93 | 100 | 100
2517 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11545 | Augmentation | Payment of quotation for new service connection at P/H - III under Chaumuha water supply scheme. Dist: 24 Pgs (North) | BP-338-23-24 | 11/03/2024 | 0 | W.B.S.E.D.C.L (KADAMBAGACHI C.C.C) | 2.06 | 0 | 0 | 0
2518 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11545 | Augmentation | Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Chaumuha Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 1557/B.Ar.D. | 24/08/2022 | 900 | BANERJEE CONSTRUCTION | 168.13 | 131.79 | 78.39 | 90
2519 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11545 | Augmentation | Outdoor illumination by supplying and installing of 15 watt solar street Light at PH- I under Chaumuha W/S Scheme, Barasat-II Block, Dist.- 24 pgs (N) under Eastern Mechanical Division, P.H.E. Dte. | 341/EMSD-I | 11/03/2025 | 30 | M/S GHOSH ENTERPRISE | 2.72 | 0 | 0 | 0
2520 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for CHAUMUHA to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11545 | Augmentation | Development of road Fron Node 05 To 312 312 [Chaumuha Purba para to Dhokra at Chowmuha W/S Scheme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | 432/B.Ar.D. | 10/03/2025 | 30 | RHINE CONSTRUCTION | 4.84 | 0 | 0 | 100
2521 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Bagband Saiberia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07709 | Retrofitting | Providing Functional School , Anganwadi and Health Center Tap Connection and allied works of Command area at Bagband-Saiberia Ground Water Supply Scheme under Barasat-II Block Under '' JAL SWAPNA'' programme under Barasat Arsenic Division PHE, Dte. | 267/B.Ar.D | 18/02/2022 | 20 | A P POWER AND CONCRETE | 3.9 | 3.88 | 50 | 1
2522 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Bagband Saiberia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07709 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Bagband-Sarberia, Kirttipur and Krishnamati Mouzas of Barasat- II Block from Bagband Saiberia Ground Water Supply Scheme Under "Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I) | 128/B.Ar.D. | 20/01/2021 | 90 | R. K. MANDAL & CO. | 85.38 | 147.61 | 172.9 | 100
2523 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Bagband Saiberia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07709 | Retrofitting | Laying of HDPE Pipe Line in damaged portion of distribution network at Gobindapur under Bagband-Saiberia Water Supply Scheme under under Barasat Arsenic Division, PHE Dte. (SM/07709) (Sl No. 2) | 2087/B.Ar.D. | 28/10/2022 | 21 | BALAJEE ENTERPRISES | 4.2 | 4.2 | 100 | 1
2524 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. , SM/13472 | Augmentation | Material Requisition To Resource Division | 1672/BD | 06/06/2023 | 0 | Resource Division | 15.2 | 0 | 0 | 0
2525 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. , SM/13472 | Augmentation | Material Requisition To Resource Division | 1283/BD | 25/04/2023 | 0 | Resource Division | 36.84 | 0 | 0 | 0
2526 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. , SM/13472 | Augmentation | Preparation of DPR in connection of augumentation of Shibalaya Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | 667/BSD | 25/08/2022 | 30 | RADIANT | 3.07 | 2.79 | 100 | 100
2527 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. , SM/13472 | Augmentation | Different works in connection with Augmentation Shibalaya PWSS (1st Tubewell site - Pump House). | 579/BSD | 10/09/2024 | 20 | RANA ENTERPRISE | 2.66 | 1.69 | 100 | 100
2528 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. , SM/13472 | Augmentation | Arrangement of Block Level Orientation Programe involving stakeholders of PRI bodies including refreshments, training materials and related activities for 2 nos Blocks (Barasat-I & II) in North 24 Parganas under Barasat Division, P.H.E. Dte. | 171/BSD | 10/06/2024 | 7 | IMAGIN | 0.98 | 0.98 | 100 | 100
2529 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. , SM/13472 | Augmentation | Formal work order for Construction of 300 cum capacity 20 mtr. height R.C.C. Over Head Reservoir as per Deptt. design, drawing & specification including bored pile & pile cap, laying of DI rising main & distribution pipe line by DI/UPVC and Providing FHTC for Augmentaion of Shibalaya water supply scheme under Barasat Sub-Division, P.H.E. Dte. | 1713/BD | 08/06/2023 | 731 | DIAMOND ENGINEER'S CO-OP. SOCIETY LTD. | 364.71 | 185.68 | 50.91 | 80
2530 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. , SM/13472 | Augmentation | Different works in connection with Augmentation Shibalaya PWSS (2nd Tubewell site - Boundary Wall & Service Road). | 580/BSD | 10/09/2024 | 20 | B. S. ENTERPRISE (BANAMALIPUR) | 2.77 | 1.41 | 100 | 100
2531 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. , SM/13472 | Augmentation | Different works in connection with Augmentation Shibalaya PWSS (1st Tubewell site - Boundary Wall & Service Road). | 578/BSD | 10/09/2024 | 20 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 3.2 | 0 | 0 | 100
2532 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. , SM/13472 | Augmentation | Different works in connection with Augmentation Shibalaya PWSS (2nd Tubewell site - Pump House). | 581/BSD | 10/09/2024 | 20 | M/S SUKANTA ENTERPRISE. | 2.65 | 0 | 0 | 100
2533 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SHIBALAYA to accommodate FHTC. , SM/13472 | Augmentation | Acceptance cum work order for Renovation of Iron Elimination Plant at Shibalaya W/S Scheme (75.7 m3/hr) within Barasat-I Block under Barasat Sub Division, P.H.E.Dte. | 1924/BD | 09/07/2024 | 135 | M/S SANKAR ENTERPRISE. | 7.44 | 0 | 0 | 100
2534 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nabatkati to accommodate FHTC , SM/11760 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Nabatkati Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 459/ BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.81 | 3.81 | 50 | 1
2535 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nabatkati to accommodate FHTC , SM/11760 | Augmentation | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Nabatkati Water Supply Scheme at Swarupnagar Block under Barasat Division, PHE Dte. | 1135/BD | 12/04/2022 | 90 | UTPAL CONSTRUCTION & CO. | 184.62 | 36.58 | 59.73 | 12
2536 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nabatkati to accommodate FHTC , SM/11760 | Augmentation | Material Requisition To Resource Division | 858/BD | 20/03/2023 | 0 | Resource Division | 0.84 | 0 | 0 | 0
2537 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nabatkati to accommodate FHTC , SM/11760 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Nabatkati water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | 513/BD | 20/02/2023 | 824 | UTPAL CONSTRUCTION & CO. | 285.35 | 208.83 | 73.18 | 60
2538 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Nabatkati to accommodate FHTC , SM/11760 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Dobila W/S Scheme, Nabatkati W/S Scheme and Kurulia (Zone-II) W/S Scheme District of 24 Pgs. (N) | 4813/EMD | 09/08/2023 | 30 | DEBJYOTI BASU | 78.24 | 15.54 | 59.57 | 66
2539 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nabatkati to accommodate FHTC , SM/11760 | Augmentation | Relaying of 75mm dia UPVC pipe line and repairing of FHTC connections due to damaged during construction of road by WBSRDA at Node no. 100 to 175 of Nabatkati water Supply Scheme under Basirhat Sub-Division within Barasat Division, PHE Dte. | 1169/BHTSD | 30/07/2024 | 15 | M/S. WAY CON. | 0.88 | 0.88 | 100 | 50
2540 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-A (Kharu) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11941 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-VII/A (Kharu) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 424/NWSD-I | 01/04/2022 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.39 | 4.39 | 100 | 1
2541 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-A (Kharu) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11941 | Augmentation | Material Requisition To Resource Division | 478/NWSD-I | 26/04/2023 | 0 | Resource Division | 89.12 | 0 | 0 | 0
2542 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-A (Kharu) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11941 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII, A (Kharu) in Amdanga Block of North 24 Parganas District. | 4026/ED | 17/10/2023 | 822 | ORIENTAL ENGINEERING CO. | 29.74 | 10.06 | 34.51 | 5
2543 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-A (Kharu) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11941 | Augmentation | Material Requisition To Resource Division | 1705/NWSD-I | 26/11/2024 | 0 | Resource Division | 6.96 | 0 | 0 | 0
2544 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-A (Kharu) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11941 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 104.26 | 16.24 | 2
2545 | NORTH 24 PARGANAS | Barasat Division | Mallik Gheri Piped Water Supply Scheme. , SM/13813 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (MALLIKGHERI Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | 289/HSD | 10/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.81 | 2.81 | 100 | 0
2546 | NORTH 24 PARGANAS | Barasat Division | Mallik Gheri Piped Water Supply Scheme. , SM/13813 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (MALLIKGHERI Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 288/HSD | 10/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 0
2547 | NORTH 24 PARGANAS | Barasat Division | Mallik Gheri Piped Water Supply Scheme. , SM/13813 | New | Material Requisition To Resource Division | 894/BD | 22/03/2023 | 0 | Resource Division | 33.53 | 0 | 0 | 0
2548 | NORTH 24 PARGANAS | Eastern Mechanical | Mallik Gheri Piped Water Supply Scheme. , SM/13813 | New | Quotation for Service Connection Charges for PH- II under Mallickgheri W/S Scheme in the district of North 24 Pgs. | BP-358-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.54 | 0 | 0 | 0
2549 | NORTH 24 PARGANAS | Eastern Mechanical | Mallik Gheri Piped Water Supply Scheme. , SM/13813 | New | Quotation for Service Connection Charges for PH- III under Mallickgheri W/S Scheme in the district of North 24 Pgs. | BP-359-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.03 | 0 | 0 | 0
2550 | NORTH 24 PARGANAS | Barasat Division | Mallik Gheri Piped Water Supply Scheme. , SM/13813 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Mallick Gheri W/S Scheme, Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | 2579/BD | 25/08/2023 | 1096 | M/S DATTA ENTERPRISE. | 500.78 | 274.68 | 54.85 | 75
2551 | NORTH 24 PARGANAS | Barasat Division | Mallik Gheri Piped Water Supply Scheme. , SM/13813 | New | Acceptance cum work order for 1 no. pump connection at PH No.-3 in connection within Mallickgheri water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 942/HSD | 29/05/2025 | 10 | M/S DATTA ENTERPRISE. | 0.72 | 0 | 0 | 0
2552 | NORTH 24 PARGANAS | Barasat Division | Mallik Gheri Piped Water Supply Scheme. , SM/13813 | New | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection within Mallickgheri water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 998/HSD | 04/06/2025 | 10 | M/S DATTA ENTERPRISE. | 0.72 | 0 | 0 | 0
2553 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I-B (Telinipara) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13902 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-IB (Telinipara) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 332/NWSD-I | 24/03/2022 | 1 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.83 | 4.98 | 100 | 1
2554 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I-B (Telinipara) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13902 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I, B (Telinipara) in Barrackpore-II Block of North 24 Parganas District. | 4033/ED | 17/10/2023 | 183 | S.P. CONSTRUCTION | 34.15 | 0 | 0 | 0
2555 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I-B (Telinipara) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13902 | Augmentation | Material Requisition To Resource Division | 488/NWSD-I | 26/04/2023 | 0 | Resource Division | 85.47 | 0 | 0 | 0
2556 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I-B (Telinipara) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13902 | Augmentation | Supply and installation of Display Board to be placeed at BILKANDA ZONE-I, BANDIPUR, BILKANDA ZONE-II, PATULIA and MOHANPUR, Zone-I-B (Telinipara), Zone-IA-II (Chak Kanthalia) pipe water supply scheme for Barrackpore-II Block under North 24 Pgs. Water Supply Division-I, PHE. Dte. | 70/NWSD-I | 10/01/2024 | 30 | BIBHAS PAL | 4.94 | 0.7 | 100 | 100
2557 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I-B (Telinipara) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13902 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 241.18 | 24.5 | 2
2558 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC , SM/13405 | Augmentation | Material Requisition To Resource Division | 1248/BD | 25/04/2023 | 0 | Resource Division | 520.48 | 0 | 0 | 0
2559 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC , SM/13405 | Augmentation | Material Requisition To Resource Division | 4424/BD | 10/11/2023 | 0 | Resource Division | 47.88 | 0 | 0 | 0
2560 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC , SM/13405 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gokna Zone-I A water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | 1726/BD | 08/06/2023 | 90 | SUJIT KUMAR SAHA | 224.48 | 144.93 | 64.56 | 10
2561 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC , SM/13405 | Augmentation | Regarding Restoration charges for road damages. | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 76.53 | 0 | 0 | 0
2562 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC , SM/13405 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gokna Zone-II water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | 1301/BD | 26/04/2023 | 945 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 766.02 | 329.99 | 43.08 | 29
2563 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC , SM/13405 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gokna Zone-I B water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | 1694/BD | 08/06/2023 | 683 | SUPRITI ENTERPRISE. | 581.97 | 225.8 | 38.8 | 20
2564 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC , SM/13405 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Rep.) and IV (New) under Gokna W/S Scheme and Pump House No- II (Rep) under Arsula W/S Scheme District of 24 Pgs. (N) | 6735/EMD | 29/11/2023 | 489 | M.S. ENTERPRISE | 39.12 | 0 | 0 | 30
2565 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC , SM/13405 | Augmentation | Hiring Diesel Luxury Car on daily basis for the supervision of work and office uses under Basirhat Sub-Division P.H.E. Dte. (Period: 01.07.2024 to 31.12.2024), Sl.No. - 02 | 1018/BHTSD | 28/06/2024 | 184 | DEB KUMAR DAS. | 0.87 | 1.35 | 154.48 | 0
2566 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokna to accommodate FHTC , SM/13405 | Augmentation | Acceptance cum work order for Restoration of roads under different water supply schemes of Baduria Block within Basirhat Sub-Division under Barasat Division P.H.E.Dte | 3553/BD | 16/12/2024 | 390 | PRITAM MUKHOPADHYAY. | 60.15 | 0 | 0 | 0
2567 | NORTH 24 PARGANAS | Barasat Division | Niruli Piped Water Supply Scheme , SM/12714 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (NIRULI Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 290/HSD | 10/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
2568 | NORTH 24 PARGANAS | Barasat Division | Niruli Piped Water Supply Scheme , SM/12714 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (NIRULI Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | 291/HSD | 10/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.05 | 1.05 | 100 | 1
2569 | NORTH 24 PARGANAS | Barasat Division | Niruli Piped Water Supply Scheme , SM/12714 | New | Material Requisition To Resource Division | 882/BD | 22/03/2023 | 0 | Resource Division | 18.22 | 0 | 0 | 0
2570 | NORTH 24 PARGANAS | Eastern Mechanical | Niruli Piped Water Supply Scheme , SM/12714 | New | Quotation for Service Connection Charges for PH- II under Neruli W/S Scheme in the district of North 24 Pgs. | BP-28-24-25 | 24/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.53 | 0 | 0 | 0
2571 | NORTH 24 PARGANAS | Eastern Mechanical | Niruli Piped Water Supply Scheme , SM/12714 | New | Quotation for Service Connection Charges for PH- I under Neruli W/S Scheme in the district of North 24 Pgs. | BP-324-23-24 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.18 | 0 | 0 | 0
2572 | NORTH 24 PARGANAS | Barasat Division | Niruli Piped Water Supply Scheme , SM/12714 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line,Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Niruli w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1544/BD | 22/05/2023 | 863 | DEBAPRASAD MONDAL. | 348.43 | 271.88 | 78.03 | 85
2573 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13435 | Augmentation | Detail route survey, design of distribution network and preparation of estimate drawing & DPR for providing FHTC in the scheme of Zone-XII (Abjannagar) under North 24 Pgs. W/S Division-I, P.H.E. Dte. Sl.No. - 12. | 1298/NWSD-I | 07/11/2022 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.49 | 3.49 | 100 | 0
2574 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13435 | Augmentation | Material Requisition To Resource Division | 459/NWSD-I | 26/04/2023 | 0 | Resource Division | 128.89 | 0 | 0 | 0
2575 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13435 | Augmentation | Providing FHTC, Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of ZONE-XII (ABJANNAGAR) in Deganga Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | 1619/NWSD-I | 12/10/2023 | 720 | A.K.C. SUPPLY & CONSTRUCTION | 567.97 | 116.67 | 20.54 | 45
2576 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13435 | Augmentation | Supply and installation of Sign Board (900mm X 600mm) determination of Land i.e." This land belongs to PHE. Dte. Govt. of West Bengal" under Surface Water based Pipe Water supply Scheme under North 24 Pgs. Water Supply Division-I, PHE. Dte. | 1432/NWSD-I | 18/09/2024 | 14 | S M TRADERS | 2.17 | 0 | 0 | 100
2577 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13435 | Augmentation | Material Requisition To Resource Division | 1316/NWSD-I | 30/08/2024 | 0 | Resource Division | 17.11 | 0 | 0 | 0
2578 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13435 | Augmentation | New service connection at P.H.No- I , Zone- XII of Abjannagar water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). Type : | BP-340-23-24 | 11/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.41 | 0 | 0 | 0
2579 | NORTH 24 PARGANAS | Central Drilling | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13435 | Augmentation | Continuation for Hiring of Diesel Driven Motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Calcutta Mechanical Sub Division-ll (D),CDD, P.H.Enginering Dte. for supervision of JJM Related works. | 24/CMSD-II(D) | 31/01/2025 | 182 | MD NIZAMUDDIN | 0.86 | 1.77 | 205.1 | 0
2580 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13435 | Augmentation | Laying of Pipeline & special measure for protection of road and other allied works at different location under Augmentation work at Abjannagar W/S. Scheme in Deganga Block under North 24 Pgs. W/S. Division-I, P.H.E. Dte. | 726/NWSD-I | 19/05/2025 | 30 | A.K.C. SUPPLY & CONSTRUCTION | 67.06 | 0 | 0 | 0
2581 | NORTH 24 PARGANAS | Central Drilling | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13435 | Augmentation | Continuation for Hiring of Diesel Driven Motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Calcutta Mechanical Sub Division-ll (D),CDD, P.H.Enginering Dte. for supervision of JJM Related works. | 152/CMSD-II(D) | 30/07/2025 | 182 | MD NIZAMUDDIN | 0.86 | 0 | 0 | 0
2582 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme , SM/13894 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Berachampa Water Supply Scheme Zone-III under Barasat Sub Division, P.H.E. Dte. | 668/BSD | 25/08/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.73 | 3.73 | 100 | 1
2583 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme , SM/13894 | Augmentation | Material Requisition To Resource Division | 3088/BD | 10/10/2023 | 0 | Resource Division | 17.77 | 0 | 0 | 0
2584 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme , SM/13894 | Augmentation | Material Requisition To Resource Division | 1270/BD | 25/04/2023 | 0 | Resource Division | 37.17 | 0 | 0 | 0
2585 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme , SM/13894 | Augmentation | Material Requisition To Resource Division | 4370/BD | 10/11/2023 | 0 | Resource Division | 90.94 | 0 | 0 | 0
2586 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme , SM/13894 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. big dia. 185 mtr deep Tube well by D.R. Rig method having 300 mm dia 42.0 mtr. long PVC housing pipe & 200 mm dia 30.0 mtr. long filter for Augmentation Berachampa Zone-III Water Supply Scheme (Head Work Site) of Barasat Sub-Division under Barasat Division, PHE Dte. | 803/BD | 12/03/2024 | 30 | ACME CONSTRUCTION | 13.08 | 12.38 | 100 | 100
2587 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme , SM/13894 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-E | 1120/BSD | 09/02/2024 | 4 | S.M.TRADERS. | 0.87 | 0.87 | 100 | 100
2588 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme , SM/13894 | Augmentation | Construction of Pump House with latrine at Berachampa Zone-III water Supply Scheme under Deganga Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | 1243/BSD | 15/03/2024 | 277 | D.K.CONSTRUCTION | 4.91 | 4.9 | 100 | 80
2589 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme , SM/13894 | Augmentation | New service connection at P.H.No- I ,Zone- III of Berachampa water supply scheme under EMSD-I ,PHE Dte .im24Pgs(N). | BP-305-23-24 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.64 | 0 | 0 | 0
2590 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme , SM/13894 | Augmentation | Acceptance cum work order for Sinking of 3 nos 300mm. X 200mm.dia. 200.00mtr. deep tube well by direct rotary rig method, having 300mm.dia. 42.0mtr. long PVC housing pipe & 200mm.dia. 30.0mtr. long UPVC Medium Well Screen (RMS) Pipes with Ribs at Berachampa Zone-II( H/W site & 2nd T/W site) & Berachampa Zone-III( 2nd T/W site) Water Supply Scheme under Barasat Sub-Division, P.H.E. Dte. | 646/BD | 28/02/2025 | 60 | JOY GURU ENTERPRISE | 42.76 | 0 | 0 | 0
2591 | NORTH 24 PARGANAS | Barasat Division | Uchildaha Piped water supply scheme , SM/13815 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (UCHILDAHA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 312/HSD | 15/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
2592 | NORTH 24 PARGANAS | Barasat Division | Uchildaha Piped water supply scheme , SM/13815 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (UCHILDAHA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | 313/HSD | 15/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 3.89 | 3.89 | 100 | 0
2593 | NORTH 24 PARGANAS | Barasat Division | Uchildaha Piped water supply scheme , SM/13815 | New | Material Requisition To Resource Division | 877/BD | 22/03/2023 | 0 | Resource Division | 30.59 | 0 | 0 | 0
2594 | NORTH 24 PARGANAS | Barasat Division | Uchildaha Piped water supply scheme , SM/13815 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap within Uchildaha W/S Scheme, Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | 2581/BD | 25/08/2023 | 366 | MONDAL & CO. (BASIRHAT). | 488.99 | 384.77 | 78.69 | 75
2595 | NORTH 24 PARGANAS | Eastern Mechanical | Uchildaha Piped water supply scheme , SM/13815 | New | Quotation for Service Connection Charges for PH- I under Uchildaha W/S Scheme in the district of North 24 Pgs. | BP-360-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.22 | 0 | 0 | 0
2596 | NORTH 24 PARGANAS | Eastern Mechanical | Uchildaha Piped water supply scheme , SM/13815 | New | Quotation for Service Connection Charges for PH- II under Uchildaha W/S Scheme in the district of North 24 Pgs. | BP-361-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 16.78 | 0 | 0 | 0
2597 | NORTH 24 PARGANAS | Barasat Division | Uchildaha Piped water supply scheme , SM/13815 | New | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for within Atpukur (Z-I) and Uchildaha w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 633/BD | 28/02/2025 | 45 | SHIBU BISWAS. | 51.76 | 0 | 0 | 0
2598 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District proje , SM/13535 | Retrofitting | Formal work order for Laying of Distribution System, Providing FHTC, Construction of Office cum Guard room, Land development and Switch cum Chlorine Room, Boundary wall, Surface drain and other allied works within the jurisdiction of (Zone-XX) i.e. Matikumra / (Zone-XXII) i.e. Chikanpara under Habra-Gaighata surface based PWSS, of Gaighata Block under Barasat Division, P.H.E. Dte. GAIGHATA BLOCK, PART-B / Gaighata Block, PART-D | 4073/BD | 16/10/2023 | 1095 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2790.09 | 713.16 | 74.25 | 88
2599 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. , SM/15559 | Augmentation | Sinking of 300 mm. x 200 mm. dia. x 330 mtr. deep tube well by direct rotary rig method for 3rd Tubewell at Thakdari of Zone - V, near Thakdari Head Work site under SWBPWSS under Barasat Arsenic Division, PHE Dte. | 1000/B.Ar.D. | 02/06/2022 | 45 | AUXILIARY TUBEWELL DRILLERS | 21.16 | 14.93 | 70.55 | 100
2600 | NORTH 24 PARGANAS | NTK Mechanical | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. , SM/15559 | Augmentation | Supply & Installation of pumping machineries & other electro-mechanical accessories in Thakdari piped W/S scheme under New Town Kolkata Mechanical Division, P.H.E. Dte. | 783 / NTKMD | 26/05/2023 | 180 | DIPALI CONSTRUCTION | 27.24 | 0 | 0 | 85
2601 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. , SM/15559 | Augmentation | Supplying & laying, fitting, fixing, jointing etc. of different dia HDPE pipe line for distribution system and Laying of Rising Main from existing H/W Site to OHR Site and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN6) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete for Thakdari Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | 1775/B.Ar.D. | 27/07/2023 | 366 | SAHA ENTERPRISE | 123.54 | 0 | 0 | 0
2602 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. , SM/15559 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme Thakdari under Barasat Arsenic Division, PHE Dte. | 2334/B.Ar.D. | 21/09/2023 | 21 | UMWELT ENGINEER PVT. LTD. | 3.23 | 3.23 | 100 | 100
2603 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. , SM/15559 | Augmentation | Construction of Boundary Wall at Thakdari OHR site under SWBPWSS for arsenic affected areas of Haroa, Rajarhat & Bhangar-II Block under Barasat Arsenic Division. PHE Dte. | 2941/B.Ar.D. | 22/12/2023 | 70 | AZAD CONSTRUCTION | 20.36 | 15.77 | 77.45 | 85
2604 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. , SM/15559 | Augmentation | Construction of 1 (one) no. (G+1 Storied) switch room cum chlorine room and Scada Room (4.1m x 5.9m) including sanitary arrangement the site of Thakdari W/S scheme under Barasat Arsenic Division. PHE Dte. | 1875/B.Ar.D. | 26/11/2024 | 50 | ROY BISWAS CONSTRUCTION | 15.43 | 0 | 0 | 0
2605 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. , SM/15559 | Augmentation | Supply, delivery, installation & commissioning of 200 mm Dia Electromagnetic Flowmeter, RTU, Sluice valve etc. and other allied works at Thakdari water supply Scheme under Rajarhat Block under SWBPWSS in Rajarhat, Haroa & Bhangar II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | 1936/B.Ar.D. | 14/08/2023 | 723 | MSA INSTRUMENTS | 6.43 | 5.1 | 85.47 | 80
2606 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Thakdari Piped Water Supply Scheme in Rajarhat Block of North 24 Parganas District under Barasat Arsenic Division, P.H.E. Dte. , SM/15559 | Augmentation | Connection of Newly constructed OHR at Thakdari and Other Allied Works under Thakdari Water Supply Scheme under Barasat Arsenic Division. | 79/B.Ar.D | 13/01/2025 | 45 | OM ENTERPRISE | 5.37 | 0 | 0 | 100
2607 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District , SM/14542 | Retrofitting | Material Requisition To Resource Division | 4024/BD | 12/10/2023 | 0 | Resource Division | 123.26 | 0 | 0 | 0
2608 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District , SM/14542 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area & Construction of Office cum Guard room and Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works at Head work site of Zone-I within Amdanga Block of surface based Water Supply Scheme for arsenic affected areas of Habra-Gaighata & adjoining mouzas in the district North 24 Parganas under Barasat Division, P.H.E. Dte. | 3007/BD | 05/10/2023 | 90 | KINGS & CO. | 894.25 | 0 | 0 | 0
2609 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IX (Khejurdanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15821 | Augmentation | Detail route survey, design of distribution network and preparation of estimate drawing & DPR for providing FHTC in the scheme of Zone-IX (Khejurdanga) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | 1062/NWSD-I | 05/09/2022 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.17 | 4.16 | 100 | 0
2610 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IX (Khejurdanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15821 | Augmentation | Material Requisition To Resource Division | 464/NWSD-I | 26/04/2023 | 0 | Resource Division | 87.32 | 0 | 0 | 0
2611 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IX (Khejurdanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15821 | Augmentation | Material Requisition To Resource Division | 942/NWSD-I | 18/07/2023 | 0 | Resource Division | 107.23 | 0 | 0 | 0
2612 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IX (Khejurdanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15821 | Augmentation | Material Requisition To Resource Division | 1102/NWSD-I | 01/08/2023 | 0 | Resource Division | 19.91 | 0 | 0 | 0
2613 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IX (Khejurdanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15821 | Augmentation | New service connection at Khejurdanga (OHR) Zone- IX water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). | BP-336-23-24 | 11/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.66 | 0 | 0 | 0
2614 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IX (Khejurdanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15821 | Augmentation | Providing FHTC, Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of Zone-IX (Khejurdanga) in Deganga Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | 683/NWSD-I | 02/06/2023 | 1389 | S & P ENTERPRISE | 617.14 | 392.39 | 63.58 | 72
2615 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IX (Khejurdanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15821 | Augmentation | Repairing of Jhama metal road from Khejurdanga Dakhinpara Durga Mandir to Khejurdanga Primary School due to lay of pipeline under Khejurdanga W/S scheme in the District of North 24 Parganas under North 24 Parganas water Supply Division-I, PHE Dte. | 108/NWSD-I | 17/01/2025 | 7 | RAKESH ENTERPRISE | 8.37 | 0 | 0 | 95
2616 | NORTH 24 PARGANAS | Eastern Mechanical | Implementation of Affordable IoT- System at Baunia Abad Water Supply Scheme under Sandeshkhali- I Block of 24 Pgs.(N) District in West Bengal. , SM/17096 | IOT | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (replacement) under Baunia Abad W/S Scheme District of North 24 Pgs. | 3387 / EMD | 09/09/2022 | 30 | GOENKA ENTERPRISE | 11.36 | 0 | 0 | 0
2617 | NORTH 24 PARGANAS | Eastern Mechanical | Implementation of Affordable IoT- System at Baunia Abad Water Supply Scheme under Sandeshkhali- I Block of 24 Pgs.(N) District in West Bengal. , SM/17096 | IOT | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (replacement) under Baunia Abad W/S Scheme District of North 24 Pgs. | 3388 / EMD | 09/09/2022 | 30 | POLYCON ENGINEERS | 11.36 | 0 | 0 | 0
2618 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Atapur water supply scheme under sandeshkhali- II Block for providing Functional House Tap Connection in North 24 Pargana District (Phase-I) , SM/07706 | Retrofitting | Route survey, distribution design & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Atapur Water Supply Scheme in Sandeshkhali - II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | 1440/B.Ar.D | 31/08/2021 | 15 | RISHAN ENGINEERING CONSULTANCY | 2.41 | 2.41 | 50 | 0
2619 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Atapur water supply scheme under sandeshkhali- II Block for providing Functional House Tap Connection in North 24 Pargana District (Phase-I) , SM/07706 | Retrofitting | Providing Functional School , Anganwadi and Health Center Tap Connection and allied works of Command area at Atapur, Dwarir Jungle & Jeliakhali Paschim Khanda Ground Water Supply Scheme under Sandeshkhali-II Block Under '' JAL SWAPNA'' programme under Barasat Arsenic Division, PHE Dte. | 341/B.Ar.D | 28/02/2022 | 15 | M/S.KRISHNA MONDAL | 3.97 | 0 | 0 | 0
2620 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Atapur water supply scheme under sandeshkhali- II Block for providing Functional House Tap Connection in North 24 Pargana District (Phase-I) , SM/07706 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Atapur Mouza of Sandeshkhali-II Block from Atapur Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. | 136/B.Ar.D. | 21/01/2021 | 90 | M/S NIRMAN CONSTRUCTION | 60.13 | 75.25 | 125.15 | 80
2621 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Atapur water supply scheme under sandeshkhali- II Block for providing Functional House Tap Connection in North 24 Pargana District (Phase-I) , SM/07706 | Retrofitting | Laying of UPVC Pipe Line from pump house no 1 towards Duchnekhali bazar for Functional House Hold Tap Connection under command area of Atapur water supply scheme of Sandeshkhali - II Block under JJM Programme under Barasat Arsenic Division, PHE Dte. | 470/B.Ar.D. | 27/02/2023 | 30 | P. & S. ASSOCIATES | 11.83 | 11.83 | 100 | 0
2622 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XI (Jhikra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18261 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme in the scheme of Zone-XI (Jhikra) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | 893/NWSD-I | 12/07/2023 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.89 | 3.94 | 100 | 100
2623 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XI (Jhikra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18261 | Augmentation | Material Requisition To Resource Division | 1372/NWSD-I | 04/09/2023 | 0 | Resource Division | 67.02 | 0 | 0 | 0
2624 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XI (Jhikra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18261 | Augmentation | Providing FHTC, Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of Zone-XI (JHIKRA) in Deganga Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | 1136/NWSD-I | 04/08/2023 | 366 | S & P ENTERPRISE | 865.27 | 208.46 | 24.09 | 15
2625 | NORTH 24 PARGANAS | Central Drilling | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XI (Jhikra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18261 | Augmentation | Hiring of Diesel Driven Motor Cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Calcutta Mecha nical Sub Division-I(D), CDD, P.H.Engineering Dte. For Supervision of JJM related works. | 13/CMSD-I(D) | 15/01/2024 | 198 | AJAY KUMAR | 0.94 | 0.6 | 212.43 | 15
2626 | NORTH 24 PARGANAS | Central Drilling | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XI (Jhikra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18261 | Augmentation | Continuation for hiring of Diesel Driven Motor Cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Calcutta Mecha nical Sub Division-I(D), CDD, P.H.Engineering Dte. For Supervision of JJM related works. | 271/CMSD-I | 26/07/2024 | 184 | AJAY KUMAR | 0.87 | 0.66 | 75.52 | 0
2627 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XI (Jhikra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18261 | Augmentation | Supply and installation of Sign Board (900mm X 600mm) determination of Land i.e." This land belongs to PHE. Dte. Govt. of West Bengal" under Surface Water based Pipe Water supply Scheme under North 24 Pgs. Water Supply Division-I, PHE. Dte. | 1432/NWSD-I | 18/09/2024 | 14 | S M TRADERS | 2.17 | 0 | 0 | 100
2628 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XI (Jhikra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18261 | Augmentation | Material Requisition To Resource Division | 1383/NWSD-I | 09/09/2024 | 0 | Resource Division | 10.81 | 0 | 0 | 0
2629 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XI (Jhikra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18261 | Augmentation | New service connection at P.H.No- I of Jhikra water supply scheme under EMSD-I ,PHE Dte .im24Pgs(N). |  | 23/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.53 | 0 | 0 | 0
2630 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Rajapur to accommodate FHTC , SM/17408 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I and II Rep. under Rajapur Block Baduria WS Scheme District of 24 Pgs. N | 4872/EMD | 14/08/2023 | 30 | S.G. TECHNICAL SERVICES | 26.07 | 0 | 0 | 0
2631 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajapur to accommodate FHTC , SM/17408 | Augmentation | Route Survey, Design Drawing & DPR Preparation for RAJAPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 356/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.16 | 4.13 | 100 | 0
2632 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajapur to accommodate FHTC , SM/17408 | Augmentation | Material Requisition To Resource Division | 1279/BD | 25/04/2023 | 0 | Resource Division | 66.17 | 0 | 0 | 0
2633 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Rajapur to accommodate FHTC , SM/17408 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under RAJAPUR W/S Scheme (Block : Tehatta I) Dist.- Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 09) | 1608/EMD | 26/04/2023 | 617 | A.S. ENTERPRISE | 18.91 | 17.92 | 96.93 | 40
2634 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajapur to accommodate FHTC , SM/17408 | Augmentation | Formal work order for Providing FHTC (Functional Household Tap Connection) by Augmentation for Rajapur Water Supply Scheme in Baduria Block under Barasat Division, P.H.E. Dte. | 1735/BD | 08/06/2023 | 838 | DEBAPRASAD MONDAL. | 353.44 | 266.43 | 75.38 | 50
2635 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC , SM/10514 | Augmentation | Repairing & renovation of Pump House No. ? 1 & 2 of Bergum W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 502/HAB | 03/12/2021 | 30 | AREOCON. | 2.07 | 2.06 | 100 | 1
2636 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC , SM/10514 | Augmentation | Material Requisition To Resource Division | 3789/BD | 22/12/2022 | 0 | Resource Division | 26.74 | 0 | 0 | 0
2637 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC , SM/10514 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Bergum Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 2534/BD | 29/08/2022 | 90 | UMWELT ENGINEER PVT.LTD. | 654.34 | 638.03 | 100 | 1
2638 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC , SM/10514 | Augmentation | Material Requisition To Resource Division | 3109/BD | 18/10/2022 | 0 | Resource Division | 17.8 | 0 | 0 | 0
2639 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC , SM/10514 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Janapul W/S Scheme and Bergum W/S Scheme with Pump House No-I, II And III under Gaighata W/S Scheme District of 24 Pgs. (N) | 4797/EMD | 09/08/2023 | 570 | MAHADEV ENTERPRISE | 74.15 | 9.75 | 46.05 | 57
2640 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC , SM/10514 | Augmentation | Construction of Service Road (20 Mtr. Length & 2 Mtr. Width) for Pump House No:3 of Bergum Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 702/HAB | 30/07/2024 | 15 | ANJALI CONSTRUCTION. | 1.11 | 0 | 0 | 0
2641 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC , SM/10514 | Augmentation | Acceptance cum work order for Construction of the Boundary wall in Pump House No. 3 of Bergum Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 3159/BD | 14/11/2024 | 45 | AREOCON. | 8.62 | 0 | 0 | 0
2642 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC , SM/10514 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 300 mm. dia. 36 mtr. long housing pipe & 200 mm. dia. 30 mtr. long Filter at Pump House No. - 1 of Bergum water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | 06/BD | 02/01/2024 | 30 | M/S B.K.ENTERPRISE. | 19.45 | 17.58 | 100 | 100
2643 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC , SM/10514 | Augmentation | Construction of Service Road (10 Mtr. Length & 2 Mtr. Width) for Pump House No:1 of Bergum Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 132/HAB | 05/02/2024 | 15 | DEBASISH SARKAR. | 0.75 | 0.74 | 100 | 100
2644 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC , SM/10514 | Augmentation | Enhancement of GST for the work providing FHTC for augmentation of Bergum water supply scheme | BP-2024-25-54 | 19/06/2024 | 0 | UMWELT ENGINEER PVT.LTD. | 33.93 | 0 | 0 | 0
2645 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC , SM/10514 | Augmentation | Special repair and renovation of boundary wall and other allied Works for Pump House No - 1 of Bergum WS scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 913/HAB | 30/10/2024 | 60 | AREOCON. | 1.91 | 1.86 | 100 | 100
2646 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Kaugachhi Zone-III Piped Water Supply Scheme , SM/14502 | New | Laying of Distribution System, Rising Main including specials, valves and pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir with pile foundation and pipe connection including cost of pipes & specials with soil investigation, Construction of Pump House (4.88m X 3.66m) including Sanitary Arrangement, Construction of Boundary Wall, Construction of Service Road, Improvement Of Land, Pipe carring structure for a span of 25 Meter for crossing of a Canal / River etc. for Augmentation of Ground Water Based Piped Water Supply Scheme for KAUGACHHI ZONE-III in Barrackpur-I Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | 1677/NWSD-I | 30/10/2023 | 365 | NEW INDIA CONSTRUCTION | 391.51 | 0 | 0 | 0
2647 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Kaugachhi Zone-III Piped Water Supply Scheme , SM/14502 | New | Survey, Design Drawing & DPR Preparation for NEW PWSS (KAUGACHHI ZONE-III Water Supply Scheme) in BARRACKPUR-I BLOCK under N 24 Pgs W/S Div-I, PHE Dte. | 121/NWSD-I | 02/02/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.95 | 4.95 | 100 | 1
2648 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Kaugachhi Zone-III Piped Water Supply Scheme , SM/14502 | New | Material Requisition To Resource Division | 453/NWSD-I | 26/04/2023 | 0 | Resource Division | 4.01 | 0 | 0 | 0
2649 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11659 | Augmentation | Preparation of Augmentation DPR for Tildanga Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | 1833/B.Ar.D | 19/09/2022 | 20 | SIRCON ENGINEERING SERVICES | 0.98 | 0.98 | 100 | 1
2650 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11659 | Augmentation | Material Requisition To Resource Division | 2294/B.Ar.D | 02/12/2022 | 0 | Resource Division | 9.3 | 0 | 0 | 0
2651 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11659 | Augmentation | Sinking for 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method near Pump House no.-2 with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter at Tildanga w/s scheme of Baduria block under Barasat Arsenic Division, P.H.E. Dte. (Sl No. 4) | 2058/B.Ar.D. | 19/10/2022 | 45 | TRISHA ENTERPRISE AND CO. | 15.35 | 13.35 | 100 | 1
2652 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11659 | Augmentation | Repair and Renovation works of OHR and allied water supply component infrastructure under Tildanga W/S Scheme of Baduria Block under Barasat Arsenic Division, PHE Dte. | 949/B.Ar.D. | 17/04/2023 | 60 | MONDAL ENTERPRISE | 12.55 | 12.07 | 100 | 100
2653 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11659 | Augmentation | Material Requisition To Resource Division | 2113/B.Ar.D. | 02/11/2022 | 0 | Resource Division | 9.89 | 0 | 0 | 0
2654 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11659 | Augmentation | New service connection at PH-III under Tildanga W/S Scheme. | BP-124-23-24 | 07/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.17 | 0 | 0 | 0
2655 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11659 | Augmentation | Laying of distribution System Including specials all Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Tildanga at Baduria Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | 1572/B.Ar.D. | 25/08/2022 | 900 | AMIT KUMAR BOSE | 249.41 | 168.27 | 67.47 | 81
2656 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11659 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Rep.) under Tildanga W/S Scheme District of 24 Pgs. (N) NIET No.- 27 of EE/EMD of 2022-23 (Sl. No.- 38) | 1439/EMD | 10/04/2023 | 30 | C.M ENTERPRISE | 21.22 | 13.6 | 64.08 | 60
2657 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11659 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at P.H. No.-III under Tildanga ground water based w/s scheme under Block_ Baduria in the District of North 24 Parganas under Eastern Mechanical Division, PHE Dte. | 1909/EMD | 31/07/2024 | 30 | TAMAL ENTERPRISE | 9.15 | 0 | 0 | 0
2658 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11659 | Augmentation | Laying of UPVC/HDPE pipeline and Repairing , Rennovation of Boundary wall, Fencing work etc and other allied works at Head work site of Tildanga W/S Scheme under Baduria Block under Barasat Arsenic Division PHE Dte. | 391/B.Ar.D | 21/02/2024 | 45 | KUNDU CONSTRUCTION CO. | 12.41 | 12.36 | 100 | 100
2659 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11659 | Augmentation | Laying of pipe line & inter connection at PH No.-3 for Tildanga water supply scheme under Baduria Block in the district of North 24 Parganas under Barasat Arsenic Division, PHE Dte. | 433/B.Ar.D. | 10/03/2025 | 30 | CHOWDHURY CONSTRUCTION | 4.68 | 0 | 0 | 0
2660 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TILDANGA to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11659 | Augmentation | Replacement of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method at Pump House no.-2 with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter at Tildanga w/s scheme of Baduria block under Barasat Arsenic Division, P.H.E. Dte. (SM/11659) | 797/B.Ar.D. | 30/04/2025 | 135 | MONDAL & CO | 15.49 | 0 | 0 | 100
2661 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-II) to accommodate FHTC , SM/11523 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Zone-II) (Replacement) under Sadiknagar W/S Scheme District of 24 Pgs. (N). (SM/11523) NIET No. 19 of EE/EMD of 2022-23 (Sl. No. - 25) | 6439/EMD | 25/11/2022 | 30 | MAA KALI ENTERPRISE | 12.99 | 11.38 | 87.6 | 0
2662 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-II) to accommodate FHTC , SM/11523 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Zone-II) (Replacement) under Sadiknagar W/S Scheme District of 24 Pgs. (N). (SM/11523) NIET No. 19 of EE/EMD of 2022-23 (Sl. No. - 27) | 6438/ EMD | 14/08/2022 | 30 | BIDYUT KUMAR MUKHERJEE | 13.05 | 11.38 | 87.25 | 1
2663 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-II) to accommodate FHTC , SM/11523 | Augmentation | Material Requisition To Resource Division | 2305/BD | 03/08/2022 | 0 | Resource Division | 4.84 | 0 | 0 | 0
2664 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-II) to accommodate FHTC , SM/11523 | Augmentation | Material Requisition To Resource Division | 484/BD | 17/02/2023 | 0 | Resource Division | 4.43 | 0 | 0 | 0
2665 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-II) to accommodate FHTC , SM/11523 | Augmentation | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) For Augmentation of Sadiknagar Zone-II Water Supply Scheme in Basirhat-II Block of North 24 Parganas District under Barasat Division, PHE Dte. | 3474/BD | 01/12/2022 | 90 | TIRUPATI ENTERPRISES | 214.95 | 131.82 | 61.33 | 80
2666 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sadiknagar (Zone-II) to accommodate FHTC , SM/11523 | Augmentation | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Sadiknagar zone - II W/S Scheme at Basirhat - II Block under Basirhat Sub Division, PHE Dte. Capacity - 56.25 Cum/hr. | 919/BD | 15/03/2024 | 60 | MONDAL PRECISION PVT.LTD | 29.4 | 29.39 | 100 | 100
2667 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-A (Algaria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13794 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-III (Algaria) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 420/NWSD-I | 01/04/2022 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.93 | 4.93 | 100 | 1
2668 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-A (Algaria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13794 | Augmentation | Material Requisition To Resource Division | 470/NWSD-I | 26/04/2023 | 0 | Resource Division | 154.24 | 0 | 0 | 0
2669 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-A (Algaria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13794 | Augmentation | Laying of 300 mm dia.250 mm dia,200 mm dia D.I. distribution main along NH 34 from Algoria more towards Babpur More (PH-I) under surface water based Water Supply scheme (PH-I) in the District of North 24 Parganas under North 24 Parganas water Supply Division-I, PHE Dte. | 1713/NWSD-I | 31/10/2023 | 30 | M/S. SHUBHA ENTERPRISE | 35.25 | 14.92 | 42.34 | 65
2670 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-A (Algaria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13794 | Augmentation | Material Requisition To Resource Division | 1706/NWSD-I | 26/11/2024 | 0 | Resource Division | 8.93 | 0 | 0 | 0
2671 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-A (Algaria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/13794 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 148.48 | 24.78 | 2
2672 | NORTH 24 PARGANAS | Barasat Arsenic Division | RAIGACHHI Piped Water Supply Scheme. , SM/18599 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at Head Work site of Raigachhi Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1940/B.Ar.D. | 14/08/2023 | 45 | NEW LIFE CONSTRUCTION | 18.18 | 0 | 0 | 0
2673 | NORTH 24 PARGANAS | Barasat Arsenic Division | RAIGACHHI Piped Water Supply Scheme. , SM/18599 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 2nd Pump House site of Raigachhi Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1941/B.Ar.D. | 14/08/2023 | 45 | ABDUL HAMID GAZI | 18.17 | 0 | 0 | 0
2674 | NORTH 24 PARGANAS | NTK Mechanical | RAIGACHHI Piped Water Supply Scheme. , SM/18599 | New | Supply & Installation of pumping machineries & other electro-mechanical accessories in Raigachhi piped W/S scheme under New Town Kolkata Mechanical Division, P.H.E. Dte. | 2131/NTKMD | 11/08/2023 | 180 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 47.44 | 0 | 0 | 0
2675 | NORTH 24 PARGANAS | Barasat Arsenic Division | RAIGACHHI Piped Water Supply Scheme. , SM/18599 | New | Construction of 4.88 mtr. x 3.60 mtr. size new Pump House at Head Work Site of RAIGACHI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1990/B.Ar.D. | 18/08/2023 | 60 | SAFE STEP ENTERPRISE | 7.29 | 0 | 0 | 0
2676 | NORTH 24 PARGANAS | Barasat Arsenic Division | RAIGACHHI Piped Water Supply Scheme. , SM/18599 | New | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 2nd Tube Well Site of RAIGACHI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1991/B.Ar.D. | 18/08/2023 | 60 | B.M.TRADERS | 6.19 | 0 | 0 | 0
2677 | NORTH 24 PARGANAS | Barasat Arsenic Division | RAIGACHHI Piped Water Supply Scheme. , SM/18599 | New | Survey, Design Drawing & DPR Preparation for NEW PWSS (RAIGACHHI Water Supply Scheme) in RAJARHAT BLOCK under Barasat Arsenic Division, PHE Dte. | 1837/B.Ar.D. | 01/08/2023 | 30 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 7.85 | 7.85 | 100 | 100
2678 | NORTH 24 PARGANAS | Barasat Arsenic Division | RAIGACHHI Piped Water Supply Scheme. , SM/18599 | New | Material Requisition To Resource Division | 79/B.Ar.D | 11/01/2024 | 0 | Resource Division | 12.75 | 0 | 0 | 0
2679 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of CHOWLPUR Piped Water Supply Scheme in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/13420 | Augmentation | Providing Functional Household Tap Connection and allied works of Command area at Chowlpur Ground Water Supply Scheme under Barasat-II Block Under '' JAL JIVAN MISSION'' programme under Barasat Arsenic Division PHE, Dte. | 475/B.Ar.D. | 27/02/2023 | 30 | TOJO ENTERPRISE | 6.09 | 5.99 | 100 | 100
2680 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of CHOWLPUR Piped Water Supply Scheme in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/13420 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated AC motor cab / maxi cab (Car No. WB-08C-5757) with engine capacity less than or equal to 2000 C.C. with driver for official use for Chief Engineer (Head Quarters), PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 03.07.2023 to 30.09.2023". | 1533/B.Ar.D | 30/06/2023 | 90 | RANA PAUL | 0.47 | 1.2 | 100 | 100
2681 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of CHOWLPUR Piped Water Supply Scheme in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/13420 | Augmentation | Supplying, Laying, fitting & fixing of different dia UPVC pipe and other allied works at Command area of Chowlpur Ground Water Supply Scheme under Barasat-II Block Under '' JAL JIVAN MISSION'' programme under Barasat Arsenic Division, PHE Dte. | 2376/B.Ar.D. | 27/09/2023 | 30 | CHOWDHURY CONSTRUCTION | 4.81 | 4.8 | 100 | 100
2682 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of CHOWLPUR Piped Water Supply Scheme in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/13420 | Augmentation | Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Chowlpur Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 120/B.Ar.D. | 18/01/2023 | 60 | M.R.CONSTRUCTION | 63.85 | 62.41 | 100 | 100
2683 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of CHOWLPUR Piped Water Supply Scheme in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/13420 | Augmentation | Reconnection and strenthening of existing Functional Household Tap Connection and other allied works at Command area of Chowlpur Ground Water Supply Scheme under Barasat-II Block Under '' JAL JIVAN MISSION'' programme under Barasat Arsenic Division PHE, Dte. | 2375/B.Ar.D. | 27/09/2023 | 30 | PRAGATI CONSTRUCTION & CO | 2.93 | 2.91 | 100 | 100
2684 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of CHOWLPUR Piped Water Supply Scheme in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/13420 | Augmentation | Repair and Renovation works of R.C.C. Elevated Reservoir of Capacity 350 CUM at Chowlpur W/S Scheme of Barasat - II block under Barasat Arsenic Division PHE Dte. | 2655/B.Ar.D. | 09/11/2023 | 45 | B S ENTERPRISE | 13.24 | 13.04 | 100 | 100
2685 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of CHOWLPUR Piped Water Supply Scheme in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/13420 | Augmentation | Providing Functional House Hold Tap Connection (FHTC) for uncovered area and laying UPVC / HDPE pipeline and alied works within command area at Chowlpur Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 383/B.Ar.D. | 21/02/2024 | 30 | P. & S. ASSOCIATES | 68.22 | 68.17 | 100 | 65
2686 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of CHOWLPUR Piped Water Supply Scheme in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/13420 | Augmentation | Material Requisition To Resource Division | 1472/B.Ar.D. | 06/09/2024 | 0 | Resource Division | 49.19 | 0 | 0 | 0
2687 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of CHOWLPUR Piped Water Supply Scheme in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/13420 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. II under Chowlpur W/S Scheme and Pump House No-III (New) under Dwarir Jangle W/S Scheme District of 24 Pgs. (N) | 4805/EMD | 09/08/2023 | 542 | P.K. ENGINEERING | 21.79 | 0 | 0 | 50
2688 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of CHOWLPUR Piped Water Supply Scheme in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/13420 | Augmentation | Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No. - WB25K - 2915) with driver for official use for Assistant Engineer (HQ-II), Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 01.07.2024 to 31.12.2024. | 1024/B.Ar.D | 21/06/2024 | 184 | PREMANANDA ROY BISWAS | 0.87 | 2.3 | 262.73 | 0
2689 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of CHOWLPUR Piped Water Supply Scheme in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/13420 | Augmentation | Supplying, laying , fitting & fixing of different dia DI(K7) and UPVC pipes for distribution network and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Chowlpur Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 233/B.Ar.D | 06/02/2025 | 300 | P & S ASSOCIATES | 54.21 | 0 | 0 | 15
2690 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | supply & installation of LED Sing board P.H. no. I (Zone-I&II) of Rupmari w/s scheme 24Pgs(N) | 1411/EMSD I | 10/07/2020 | 13 | S.P. ENTERPRISE | 0.4 | 0 | 0 | 1
2691 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of RUPMARI Water Supply Scheme under Barasat Division, PHE Dte. | 228/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.81 | 4.81 | 100 | 1
2692 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Additional Survey Work For DPR Preparation of Augmentation of RUPMARI Water Supply Scheme under Barasat Division, PHE Dte. | 229/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.04 | 1.04 | 100 | 1
2693 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Rupmari w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 1207/BD | 20/04/2023 | 30 | M/S PROGATI ENTERPRISE. | 42.94 | 36.11 | 84.08 | 0
2694 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Construction of boundary wall at Pump House No-1, 2 & 5 for damaged portion and repairing of existing boundary wall within Rupmari w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 822/HSD | 14/07/2023 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.38 | 0 | 0 | 0
2695 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Pump connection at PH No-5 & other allied works for Augmentation of Rupmari w/s scheme, Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | 616/HSD | 07/04/2022 | 15 | GOBINDA DAS. | 1.97 | 1.97 | 100 | 1
2696 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Rupmari w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 1204/BD | 20/04/2023 | 30 | M/S DATTA ENTERPRISE. | 42.94 | 37.37 | 100 | 100
2697 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Construction of boundary wall at Pump House No-1, 2 & 5 for damaged portion and repairing of existing boundary wall within Rupmari w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 822/HSD | 14/07/2023 | 15 | ANKUSH CONSTRUCTION & CO. | 4.38 | 4.37 | 100 | 100
2698 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no-5 in connection with Augmentation of Rupmari w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 786/HSD | 13/07/2023 | 10 | SARKAR ENTERPRISE | 0.88 | 0.88 | 100 | 100
2699 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Material Requisition To Resource Division | 519/BD | 20/02/2023 | 0 | Resource Division | 145.86 | 0 | 0 | 0
2700 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Zone-I and II) )(Rep.) under Rupmari W/S Scheme District of 24 Pgs. (N) NIET No.- 32 of EE/EMD of 2022-23 (Sl. No.- 22) | 1012/EMD | 09/03/2023 | 30 | CREATIVE WATER & PROCESS TECHNOLOGIES PVT. LTD. | 79.43 | 66.05 | 83.15 | 85
2701 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Construction of Office cum Godown with sanitary & water supply arrangement i/c plinth protection at OHR site (Size-5.40x3.60 mtr.) for Augmentation of Rupamari w/s scheme (Z-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 2974/BD | 04/10/2024 | 60 | TALUKDER & CO. | 13.56 | 0 | 0 | 0
2702 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Rupmari (Zone-II water supply scheme, Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 405/BD | 09/02/2023 | 90 | M/S NIRMAN CONSTRUCTION. | 345.89 | 343.44 | 100 | 1
2703 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing Functional Household Tap Connection in Connection with Augmentation of Rupmari water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | 403/BD | 09/02/2023 | 90 | M/S DATTA ENTERPRISE. | 348.91 | 342.66 | 100 | 85
2704 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Rupmari w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 2479/BD | 18/08/2023 | 30 | ABDUL ALIM MONDAL. | 25.81 | 19.29 | 100 | 77
2705 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 150 mm dia DI pipeline at different places in connection with Augmentation of Rupmari w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 261/HSD | 06/03/2024 | 10 | M/S NIRMAN CONSTRUCTION. | 0.93 | 0.93 | 100 | 100
2706 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site in connection with Augmentation of Rupmari w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 275/HSD | 06/03/2024 | 10 | SARKAR ENTERPRISE & CO. | 0.83 | 0.83 | 100 | 79
2707 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 150 mm dia DI pipeline at different places in connection with Augmentation of Rupmari w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 262/HSD | 06/03/2024 | 10 | M/S DATTA ENTERPRISE. | 0.93 | 0.93 | 100 | 85
2708 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 100 mm dia DI pipeline at different places in connection with Augmentation of Rupmari w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 264/HSD | 06/03/2024 | 10 | M/S DATTA ENTERPRISE. | 0.93 | 0.93 | 100 | 85
2709 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 100 mm dia DI pipeline at different places in connection with Augmentation of Rupmari w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 881/HSD | 07/08/2024 | 10 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 0.93 | 0.91 | 100 | 100
2710 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Construction of Office cum Godown with sanitary & water supply arrangement i/c plinth protection at OHR site (Size-5.40x3.60 mtr.) for Augmentation of Rupamari w/s scheme (Z-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 3023/BD | 22/10/2024 | 360 | LAHIRI CONSTRUCTION. | 13.58 | 0 | 0 | 50
2711 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Rupmari water supply scheme (Zone - I), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | 2031/BD | 13/07/2023 | 739 | SARKAR ENTERPRISE & CO. | 114.21 | 78.82 | 76.33 | 100
2712 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Rupmari water supply scheme (Zone - II), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | 2032/BD | 13/07/2023 | 626 | DEBAPRASAD MONDAL. | 114.2 | 86.07 | 77.86 | 85
2713 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Formal work order for Protection works for protection of UPVC distribution pipe line at different places and other allied works in connection with Augmentation of Rupmari w/s scheme (Z-I & II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 2866/BD | 30/09/2024 | 120 | UTPAL CONSTRUCTION & CO. | 132.55 | 0 | 0 | 100
2714 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places of Rupamari & Bainara mouza within Rupmari w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 316/HSD | 04/02/2025 | 10 | GOBINDA DAS. | 0.96 | 0 | 0 | 100
2715 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection with Augmentation of Rupmari water supply scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 473/HSD | 28/02/2025 | 10 | GOBINDA DAS. | 0.72 | 0 | 0 | 100
2716 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Providing Functional household tap connection at Rupamari Adibasi Jr. Basic School, Bainara Keorakhali SSK, Uttar Banstali Adibasi FP School within the command area of Rupmari w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 990/HSD | 04/06/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.74 | 0 | 0 | 100
2717 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Emergent protection of pipeline with UC Bullah pilling at N/H/O Shibpada Sardar, Rupmari within Rupmari w/s scheme (Z-I), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 940/HSD | 29/05/2025 | 10 | GOBINDA DAS. | 0.96 | 0 | 0 | 100
2718 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation of Rupmari water supply scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 259/HSD | 30/01/2025 | 10 | GOBINDA DAS. | 0.7 | 0 | 0 | 100
2719 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Rupamari & Bainara mouza in connection with augmentation of Rupmari w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 166/HSD | 27/01/2025 | 10 | GOBINDA DAS. | 0.96 | 0.96 | 100 | 100
2720 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Emergent providing of 1 no. FHTC at Debdas Bar house with laying of 63 mm dia UPVC pipe line for damage portion in connection with augmentation of Rupmari w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 168/HSD | 27/01/2025 | 10 | GOBINDA DAS. | 0.48 | 0.48 | 100 | 100
2721 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Banstala mouza in connection with augmentation of Rupmari w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte | 164/HSD | 27/01/2025 | 10 | GOBINDA DAS. | 0.96 | 0.96 | 100 | 100
2722 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC. , SM/12122 | Augmentation | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places of Banstala mouza within Rupmari w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | 384/HSD | 10/02/2025 | 10 | GOBINDA DAS. | 0.96 | 0 | 0 | 100
2723 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/13761 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir of Capacity 250 Cu.m. at Rajapura W/S Scheme of Hasnababad Block under Barasat Arsenic Division, PHE Dte. | 276/B.Ar.D. | 06/02/2023 | 60 | MONDAL ENTERPRISE | 11.21 | 8.61 | 100 | 1
2724 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/13761 | Augmentation | Preparation of Augmentation DPR for Rajapura Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | 1030/B.Ar.D | 28/04/2023 | 21 | SIRCON ENGINEERING SERVICES | 0.98 | 0.98 | 100 | 100
2725 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/13761 | Augmentation | Material Requisition To Resource Division | 27/B.Ar.D. | 05/01/2023 | 0 | Resource Division | 1.72 | 0 | 0 | 0
2726 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/13761 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I , II Zone-I under Rajapura ground water based water supply scheme under Block_ Sandeshkhali-I Dist. - North 24PGS under EMD, PHE Dte. WBPHED/EE/EMD/NIeT-37 of 2023-24 (Sl no. 12) | 944/EMD | 18/03/2024 | 30 | PADMA ENGINEERING CO. | 25.48 | 0 | 0 | 0
2727 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/13761 | Augmentation | Laying of distribution System Including specials all Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Rajapura at Hasnabad Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | 2326/BArD | 06/12/2022 | 90 | SAKTI ENTERPRISE | 115.75 | 111.84 | 100 | 100
2728 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/13761 | Augmentation | Laying of distribution system including specials all providing Functional House hold Tap Connection (FHTC) from existing and new proposed distribution system system within command area for Augmentation of Ground Based Water Supply Scheme at Rajapura at Hasnabad Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | 1621/B.Ar.D. | 12/07/2023 | 60 | B S ENTERPRISE | 48.59 | 46.95 | 100 | 100
2729 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for RAJAPURA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/13761 | Augmentation | Sal-Bullah Pilling for pipe protection work at Rajapura under Hasnabad Block Under Barasat Arsenic Division, PHE Dte. | 993/B.Ar.D. | 19/06/2024 | 40 | M/S ROY CHOWDHURY & CO. | 14.43 | 14.19 | 100 | 100
2730 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme , SM/13893 | Augmentation | Repairing & Renovation of 1 No. Pump House (P.H. No-IV) and allied works at Berachampa Water Supply Scheme Zone-II under Barasat Sub-Division, P.H.E.Dte. | 832/BSD | 16/12/2021 | 30 | ROMI TREDERS. | 1.25 | 1.18 | 94.55 | 1
2731 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme , SM/13893 | Augmentation | Repairing & Renovation of 1 No. Pump House (Size- 5.20 x 7.20) of Head Work Site and allied works at Berachampa Water Supply Scheme Zone-II under Barasat Sub-Division, P.H.E.Dte. | 830/BSD | 16/12/2021 | 30 | P.ENTERPRISE. | 1.85 | 1.75 | 94.66 | 1
2732 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme , SM/13893 | Augmentation | Repairing & Renovation of 02 Nos. Pump House (P.H. No.-II & III) and allied works at Berachampa Water Supply Scheme Zone-II under Barasat Sub-Division, P.H.E.Dte. | 831/BSD | 16/12/2021 | 30 | KABASI ENTERPRISE. | 2.51 | 2.39 | 95.15 | 1
2733 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme , SM/13893 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Berachampa Water Supply Scheme Zone-II under Barasat Sub Division, P.H.E. Dte. | 659/BSD | 18/08/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.61 | 3.58 | 100 | 1
2734 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme , SM/13893 | Augmentation | Material Requisition To Resource Division | 3087/BD | 10/10/2023 | 0 | Resource Division | 18.46 | 0 | 0 | 0
2735 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme , SM/13893 | Augmentation | Material Requisition To Resource Division | 1269/BD | 25/04/2023 | 0 | Resource Division | 32.07 | 0 | 0 | 0
2736 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme , SM/13893 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-D | 1119/1/BSD | 09/02/2024 | 4 | M.R.CONSTRUCTION. | 0.88 | 0.88 | 100 | 100
2737 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme , SM/13893 | Augmentation | Arrangement of Block Level Orientation Programe involving stakeholders of PRI bodies including refreshments, training materials and related activities for 2 nos Blocks (Amdanga & Deganga) in North 24 Parganas under Barasat Division, P.H.E. Dte. | 172/BSD | 10/06/2024 | 7 | IMAGIN | 0.98 | 0.98 | 100 | 100
2738 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme , SM/13893 | Augmentation | Acceptance cum work order for Renovation of Iron Elimination Plant at Berachampa Zone-II Water Supply Scheme within Deganga Block under Barasat Sub Division, P.H.E.Dte. | 615/BD | 27/02/2025 | 40 | ANJALI ENTERPRISE. | 9.21 | 0 | 0 | 0
2739 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Berachampa Zone-2 Piped Water Supply Scheme , SM/13893 | Augmentation | Acceptance cum work order for Sinking of 3 nos 300mm. X 200mm.dia. 200.00mtr. deep tube well by direct rotary rig method, having 300mm.dia. 42.0mtr. long PVC housing pipe & 200mm.dia. 30.0mtr. long UPVC Medium Well Screen (RMS) Pipes with Ribs at Berachampa Zone-II( H/W site & 2nd T/W site) & Berachampa Zone-III( 2nd T/W site) Water Supply Scheme under Barasat Sub-Division, P.H.E. Dte. | 646/BD | 28/02/2025 | 60 | JOY GURU ENTERPRISE | 42.76 | 0 | 0 | 0
2740 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Gadpukuria Piped Water Supply Scheme at Bagdah Block (Phase-I) , SM/08067 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Gadpukuria Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-I). | 1356/BD. | 03/08/2021 | 90 | ORIENT CONSTRUCTION. | 131.31 | 0 | 0 | 1
2741 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Gadpukuria Piped Water Supply Scheme at Bagdah Block (Phase-II) , SM/08068 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Gadpukuria Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-II). | 423/BD. | 19/02/2021 | 45 | M/S S.S.ENTERPRISE. (SOUTH) | 84.66 | 49.4 | 100 | 1
2742 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Gadpukuria Piped Water Supply Scheme at Bagdah Block (Phase-II) , SM/08068 | Retrofitting | Repairing & Renovation 2(Two) nos of Pump House and allied works of Gadpukuria water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 531/Bon | 03/11/2021 | 21 | MA CONSTRUCTION. | 2.52 | 2.49 | 100 | 1
2743 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Paikpara Water Supply Scheme at Bongaon Block (Phase-II). , SM/08043 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAIKPARA Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (PHASE-II) | 419/NWSD-I | 31/05/2021 | 90 | ORIENT CONSTRUCTION | 96.79 | 79.46 | 82.1 | 100
2744 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Paikpara Water Supply Scheme at Bongaon Block (Phase-II). , SM/08043 | Retrofitting | Continuation order for the work of Hiring of 1 (one) no Motor Cab / Maxi Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Executive Engineer, North 24 Parganas W/S Division-I, P.H.E. Dte. for 122 (One Hundred Twenty Two) days w.e.f 01/09/2023 to 31/12/2023.[Car No.WB 25L 4241]. | 1296/NWSD-I | 24/08/2023 | 122 | M/S. SHUBHA ENTERPRISE | 0.58 | 1.2 | 207.14 | 50
2745 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Malidah Water Supply Scheme at Bagdah Block (Phase-I) , SM/07848 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Malidah Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-I). | 79/BD. | 18/01/2021 | 60 | ORIENT CONSTRUCTION. | 57.85 | 0 | 0 | 0
2746 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Malidah Water Supply Scheme at Bagdah Block (Phase-I) , SM/07848 | Retrofitting | Material Requisition To Resource Division | 2866/BD | 21/09/2022 | 0 | Resource Division | 2.83 | 0 | 0 | 0
2747 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAIKPARA Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07603 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAIKPARA Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (Phase-I) | 73/NWSD-I | 20/01/2021 | 90 | PUSPA ENTERPRISE | 67.26 | 125.45 | 131.37 | 1
2748 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rajbari Water Supply Scheme, Sandeshkhali - I Block. , SM/07611 | Retrofitting | Acceptance cum work order for Construction of boundary wall with RCC column structure at Head Work site (PH No-1) within Chunchura & Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 4376/BD | 10/11/2023 | 90 | MONDAL & CO. (BASIRHAT). | 23.88 | 0 | 0 | 0
2749 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rajbari Water Supply Scheme, Sandeshkhali - I Block. , SM/07611 | Retrofitting | Acceptance cum work order for Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Rajbari water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 1152/BD | 12/04/2022 | 240 | S.S.ENTERPRISE. (BAMANGACHI) | 97.05 | 30.31 | 100 | 1
2750 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rajbari Water Supply Scheme, Sandeshkhali - I Block. , SM/07611 | Retrofitting | Acceptance cum work order for Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Rajbari water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 1152/ BD | 12/04/2022 | 240 | S.S.ENTERPRISE. (BAMANGACHI) | 97.05 | 18.73 | 50 | 0
2751 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rajbari Water Supply Scheme, Sandeshkhali - I Block. , SM/07611 | Retrofitting | Work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the Rajbari mouza into Swajal Gram i/c laying of UPVC/PVC pipe & supply of necessary fittings within Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 2923/BD | 26/09/2022 | 30 | ABDUL HAMID GAZI. | 11.33 | 11.32 | 100 | 1
2752 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Talsa and Adjoining mouzas Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-II) , SM/07612 | Retrofitting | Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Talsa & Adjoining Mouzas Water Supply Scheme at Habra-II Block under Barasat Division, PHE Dte. (Phase-II). | 388/BD. | 18/02/2021 | 90 | PUSPA ENTERPRISE. | 84.95 | 20.23 | 23.81 | 1
2753 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Talsa and Adjoining mouzas Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-II) , SM/07612 | Retrofitting | Acceptance cum work order for Providing Functional House Hold Tap Connection (FHTC) from existing distribution system at Talsa & Adj. Mouzas Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte.( For balance work of Retrofitting). | 3583/ BD | 08/12/2022 | 30 | TRISHA ENTERPRISE & CO. | 42.66 | 42.65 | 100 | 1
2754 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Puturia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07707 | Retrofitting | Route survey, Distribution designe & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Puturia & its adjoining mouza Water Supply Scheme in Barasat -II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | 1563/B.Ar.D. | 15/09/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 6.19 | 6.19 | 50 | 1
2755 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Puturia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07707 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Jiyawal at Bokanda Majher Para under Puturia W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | 475/B.Ar.D | 16/03/2022 | 15 | CHAKRABORTY SUPPLIERS & CONSTRUCTION | 4.68 | 4.67 | 50 | 1
2756 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Puturia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07707 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Simulgachhi, Bonkanda and Baidyapur Mouzas of Barasat- II Block from Puturia Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I). | 127/B.Ar.D. | 20/01/2021 | 90 | BANI ENGINEERING CO | 94.63 | 80.52 | 85.09 | 100
2757 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Puturia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07707 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near Najrul house and Hafijul house at Simulgachi under Puturia W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | 481/B.Ar.D | 16/03/2022 | 15 | M/S.KRISHNA MONDAL | 4.79 | 4.79 | 99.99 | 70
2758 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Puturia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07707 | Retrofitting | Repair & Renovation of Iron Elimination Plant of 161 M3 including Media Change of Puturia Water Supply Scheme under Barasat- II Block Under Barasat Arsenic Division, PHE Dte. | 1165/B.Ar.D. | 16/05/2023 | 30 | GHOSH CONSTRUCTION | 8.71 | 8.32 | 100 | 100
2759 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Humaipur Piped Water Supply Scheme at Barasat-II Block (Phase-I) , SM/07842 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Banspol, Dariala & Birpur mouzas within Humaipur Water Supply Scheme at Barasat-II Block under Barasat Sub Division, PHE Dte. | 2626/BD | 05/09/2022 | 30 | M/S K.B.ENTERPRISE. | 43.06 | 38.98 | 100 | 1
2760 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Humaipur Piped Water Supply Scheme at Barasat-II Block (Phase-I) , SM/07842 | Retrofitting | Acceptance cum work order for Repair & Renovation work at Head work site in connection with Augmentation of Humaipur Water Supply Scheme under Barasat Sub Division, P.H.E.Dte. | 1033/BD | 28/03/2025 | 45 | MUKHERJEE CONSTRUCTION (NADIA) | 19.71 | 0 | 0 | 0
2761 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Humaipur Piped Water Supply Scheme at Barasat-II Block (Phase-I) , SM/07842 | Retrofitting | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at Humaipur OHR site under Humipur Water Supply Scheme within Barasat Sub-Division, PHE Dte. | 1724/BD | 27/05/2025 | 120 | MONDAL ENTERPRISE. (BARASAT) | 31.87 | 0 | 0 | 0
2762 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Jashaikati Zone - II and Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08723 | Retrofitting | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Jashaikati Zone - II & its adjoining mouza water supply scheme in Baduria Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | 1703/B.Ar.D | 30/09/2021 | 15 | SIRCON ENGINEERING SERVICES | 4.7 | 4.7 | 50 | 1
2763 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Jashaikati Zone - II and Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08723 | Retrofitting | Providing Functional House Hod Connection and Allied workas at Ramchandra pur khas pur, Hugle and Keutsa Mouzas of Baduria Block from Jasikhati Zone-II & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | 1709/B.Ar.D. | 01/10/2021 | 90 | UTPAL CONSTRUCTION AND CO | 73.47 | 72.36 | 50 | 1
2764 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Jashaikati Zone - II and Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08723 | Retrofitting | Repairing and Renovation of 02 ( two) nos Pump House and allied works at the site of Jasaikathi ( Zone-II ) W/S Scheme at Baduria block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | 266/B.Ar.D | 18/02/2022 | 20 | NEELAM ENTERPRISE | 4.72 | 4.72 | 50 | 1
2765 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Jashaikati Zone - II and Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08723 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Akbar Biswas and others at Hugle under Jasaikathi - II W/S Scheme at Baduria block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | 483/B.Ar.D | 16/03/2022 | 15 | RHINE CONSTRUCTION | 4.72 | 4.71 | 50 | 1
2766 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Jashaikati Zone - I and Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas under Barasat Arsenic Division PHE Dte (Phase- II) , SM/08724 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Sumon Mondal under Jasaikathi - I W/S Scheme at Baduria block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | 477/B.Ar.D | 16/03/2022 | 15 | M/S DATTA ENTERPRISE | 4.47 | 4.46 | 99.83 | 100
2767 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Jashaikati Zone - I and Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas under Barasat Arsenic Division PHE Dte (Phase- II) , SM/08724 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Jashaikati mouza of Baduria Block from Jashaikati ( Zone-I ) & Its Adjoining Mouzas Ground Water Supply Scheme Under '' JAL SWAPNA'' programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | 2078/B.Ar.D. | 02/12/2021 | 90 | KINGS & CO. | 117.37 | 110.28 | 93.96 | 100
2768 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sindrani (Zone-I) Piped Water Supply Scheme at Bagdah Block (Phase-I) , SM/08266 | Retrofitting | Continuation work order for the work of Hiring Diesel Luxury Car on daily basis (for 6months from 01-07-2022 to 30-09-2022) for the Office of the Assistant Engineer (HQ), Barasat Division, PHE Dte. | 1863/BD | 30/06/2022 | 92 | M/S SAMIT CHANDRA DEY. | 0.44 | 0.71 | 163.18 | 1
2769 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sindrani (Zone-I) Piped Water Supply Scheme at Bagdah Block (Phase-I) , SM/08266 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Sindrani (Zone-I) Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-I). | 2387/BD | 09/12/2021 | 45 | DEBAPRASAD MONDAL. | 73.93 | 73.41 | 100 | 1
2770 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sindrani (Zone-I) Piped Water Supply Scheme at Bagdah Block (Phase-I) , SM/08266 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Sahebkhali (Zone-I & Zone-II) Water Supply Scheme under Barasat Division, PHE Dte. | 2146/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.76 | 4.76 | 100 | 1
2771 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sindrani (Zone-I) Piped Water Supply Scheme at Bagdah Block (Phase-I) , SM/08266 | Retrofitting | Construction of Approach Road at 2ndT/W site for Augmentation of Sindrani (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | 562/Bon | 18/07/2023 | 15 | ONKAR ENTERPRISE. | 0.89 | 0 | 0 | 0
2772 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sindrani (Zone-I) Piped Water Supply Scheme at Bagdah Block (Phase-I) , SM/08266 | Retrofitting | Renovation and repairing of Boundary wall at 2nd T/W site for Augmentation of Sindrani (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 616/Bon | 08/08/2023 | 21 | VAI ENTERPRISE. | 1.86 | 1.83 | 100 | 100
2773 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sindrani (Zone-I) Piped Water Supply Scheme at Bagdah Block (Phase-I) , SM/08266 | Retrofitting | Construction of Approach Road Head Work at site for Augmentation of Sindrani (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 618/Bon | 08/08/2023 | 25 | ROY ENGINEERS. | 4.51 | 4.51 | 100 | 100
2774 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Koniara Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08267 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KONIARA Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-I) | 164/BD | 19/01/2022 | 30 | ROY CHOWDHURY CONSTRUCTION. | 35.78 | 35.74 | 99.88 | 1
2775 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Koniara Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08267 | Retrofitting | Acceptance cum work order for additional Survey Work For DPR Preparation of Sahebkhali (Zone-I & Zone-II) Water Supply Scheme under Barasat Division, PHE Dte. | 2147/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.84 | 2.79 | 98.33 | 1
2776 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Koniara Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08267 | Retrofitting | Laying of distribution pipe line for smoothly water supply all over back site villagers and other allied works at Koniara water supply scheme under Bongaon Sub-Division P.H.E.Dte. | 404/Bon | 23/08/2022 | 15 | ROY CHOWDHURY CONSTRUCTION. | 3.49 | 3.47 | 50 | 1
2777 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Koniara Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08267 | Retrofitting | Material Requisition To Resource Division | 2868/BD | 21/09/2022 | 0 | Resource Division | 2.14 | 0 | 0 | 0
2778 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gaighata Piped Water Supply Scheme at Gaighata Block (Phase-I) , SM/08777 | Retrofitting | Acceptance cum work order for Estimate for Additional Survey Work For DPR Preparation of Bhabanipur (Zone-I & Zone-II) Water Supply Scheme under Barasat Division, PHE Dte. | 2157/HSD | 28/12/2021 | 21 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 3.47 | 3.44 | 100 | 1
2779 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gaighata Piped Water Supply Scheme at Gaighata Block (Phase-I) , SM/08777 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Bagdah Water Supply Scheme under Bongaon Sub-Division, under Barasat Division,PHE.Dte. | 608/Bon | 31/12/2021 | 20 | UMWELT ENGINEER PVT.LTD. | 4.27 | 4.27 | 100 | 1
2780 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gaighata Piped Water Supply Scheme at Gaighata Block (Phase-I) , SM/08777 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Sindrani (Zone-I) Water Supply Scheme under Bongaon Sub-Division, under Barasat Division, PHE Dte. | 609/Bon | 31/12/2021 | 20 | UMWELT ENGINEER PVT.LTD. | 4.14 | 4.14 | 100 | 1
2781 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gaighata Piped Water Supply Scheme at Gaighata Block (Phase-I) , SM/08777 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Gaighata Water Supply Scheme at Gaighata Block within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. (Phase-I). | 2174/BD | 18/11/2021 | 90 | SINGHA ROY & CO. | 133.93 | 129.03 | 100 | 1
2782 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gaighata Piped Water Supply Scheme at Gaighata Block (Phase-I) , SM/08777 | Retrofitting | Material Requisition To Resource Division | 252/BD | 27/01/2022 | 0 | Resource Division | 1.99 | 0 | 0 | 0
2783 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Rohanda & Its adjoining Mouzas Water Supply Scheme under Barasat II Block for providing Functional House Tap Connection in North 24 Pargana District (Phase-I) , SM/08247 | Retrofitting | Route survey, Distribution designe & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Rohanda & its adjoining mouza Water Supply Scheme in Barasat -II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | 1564/B.Ar.D. | 15/09/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5.78 | 5.58 | 50 | 1
2784 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Rohanda & Its adjoining Mouzas Water Supply Scheme under Barasat II Block for providing Functional House Tap Connection in North 24 Pargana District (Phase-I) , SM/08247 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Palitpara, Rohanda, Noapara, Banpol, Singhapra mouza's of Barasat - II Block from Rohanda & Its Adjoining Mouzas Ground Water Supply Scheme Under '' JAL SWAPNA'' programme under Barasat Arsenic Division PHE, Dte. (Phase-I) | 1037/B.Ar.D. | 07/06/2021 | 90 | S. P. CONSTRUCTION | 95.15 | 177.38 | 186.41 | 100
2785 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Maslandapur Piped Water Supply Scheme (Zone-I) at Habra-I Block (Phase-I) , SM/08778 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Sindrani (Zone-II) Water Supply Scheme under Bongaon Sub-Division, under Barasat Division, PHE.Dte. | 610/Bon | 31/12/2021 | 20 | UMWELT ENGINEER PVT.LTD. | 3.48 | 3.48 | 100 | 1
2786 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Maslandapur Piped Water Supply Scheme (Zone-I) at Habra-I Block (Phase-I) , SM/08778 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Maslandapur Water Supply Scheme(Zone-I) at Habra-I Block within the jurisdiction of Habra Sub-Division, under Barasat Division, PHE Dte. (Phase-I). | 2436/BD | 13/12/2021 | 90 | SUPRITI ENTERPRISE. | 113.29 | 109.24 | 100 | 1
2787 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Maslandapur Piped Water Supply Scheme (Zone-I) at Habra-I Block (Phase-I) , SM/08778 | Retrofitting | Material Requisition To Resource Division | 249/BD | 27/01/2022 | 0 | Resource Division | 1.99 | 0 | 0 | 0
2788 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Helencha Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08263 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Helencha Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 134/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 100 | 1
2789 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Helencha Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08263 | Retrofitting | Hiring of 1(one) no Luxury Car (Diesel/Driven) for the office use of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Barasat Division P.H.E. Dte. (Period from:-01/02/2023 to 31/07/2023). | 99/Bon | 31/01/2023 | 181 | ROY ENGINEERS. | 0.86 | 1.26 | 100 | 100
2790 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Helencha Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08263 | Retrofitting | Repairing & Renovation of Head Work Pump House site and allied works at Helencha water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 409/Bon | 23/08/2022 | 12 | KAMAL HALDAR. | 3 | 2.96 | 100 | 1
2791 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Helencha Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08263 | Retrofitting | Hiring of 1(one) no Luxury Car (Diesel/Driven) for the office use of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Barasat Division P.H.E. Dte. (Period from:-01/02/2023 to 31/07/2023). | 99/.BON | 31/01/2023 | 181 | ROY ENGINEERS. | 0.86 | 0.65 | 100 | 100
2792 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate , SM/10529 | Augmentation | Repairing & renovation of Pump House No. ? 1 & 2 of Janaphul W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 503/HAB | 03/12/2021 | 30 | AREOCON. | 1.3 | 1.24 | 100 | 1
2793 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate , SM/10529 | Augmentation | Material Requisition To Resource Division | 3797/BD | 22/12/2022 | 0 | Resource Division | 6.17 | 0 | 0 | 0
2794 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate , SM/10529 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 2 for Augmentation of Janaphul water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | 2777/BD | 11/09/2023 | 30 | M/S K.P.PAL. | 14.5 | 0 | 0 | 0
2795 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate , SM/10529 | Augmentation | Material Requisition To Resource Division | 3106/BD | 18/10/2022 | 0 | Resource Division | 8.11 | 0 | 0 | 0
2796 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate , SM/10529 | Augmentation | Material Requisition To Resource Division | 1556/BD | 23/05/2023 | 0 | Resource Division | 0.92 | 0 | 0 | 0
2797 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate , SM/10529 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Janapul W/S Scheme and Bergum W/S Scheme with Pump House No-I, II And III under Gaighata W/S Scheme District of 24 Pgs. (N) | 4797/EMD | 09/08/2023 | 570 | MAHADEV ENTERPRISE | 74.15 | 0 | 0 | 57
2798 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate , SM/10529 | Augmentation | Acceptance cum work order for construction of the Boundary wall in Pump House No. 2 of Janaphul Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 1799/BD | 01/07/2024 | 45 | AREOCON. | 5.19 | 0 | 0 | 0
2799 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate , SM/10529 | Augmentation | Formal Work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of at Janaphul Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 2461/BD | 23/08/2022 | 90 | UTPAL CONSTRUCTION & CO. | 230.82 | 192.12 | 100 | 100
2800 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate , SM/10529 | Augmentation | Acceptance cum work order for Sinking of 1 no. 250 mm. x 150 mm. dia. 270 mtr deep tube well by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 2 of Janaphul water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | 1407/BD | 08/05/2023 | 30 | M/S K.P.PAL. | 14.5 | 13.16 | 100 | 100
2801 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate , SM/10529 | Augmentation | Improvement of Iron Elimination Plant at Janaphul W/S Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 692/HAB | 02/11/2023 | 30 | GHOSH CONSTRUCTION | 4.51 | 4.5 | 100 | 100
2802 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Janaphul to accommodate , SM/10529 | Augmentation | Special repair & renovation of boundary wall and other allied Works for Pump House No - 1 of Janaphul W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 131/HAB | 05/02/2024 | 20 | DEBANJAN GHOSH. | 0.77 | 0.77 | 100 | 100
2803 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10557 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with retofitting of Kanmari w/s scheme (Zone-II), Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 100/BD | 11/01/2023 | 90 | M/S PROGATI ENTERPRISE. | 297.96 | 291.19 | 100 | 1
2804 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10557 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Nazat mouza due to erosion of soil for heavy rain fall during monsoon season within Kanmari w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 1084/HSD | 31/08/2023 | 10 | M/S PROGATI ENTERPRISE. | 0.95 | 0.95 | 100 | 100
2805 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10557 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Hatgachi mouza due to erosion of soil for heavy rain fall during monsoon season within Kanmari w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 1085/HSD | 31/08/2023 | 10 | M/S PROGATI ENTERPRISE. | 0.94 | 0.94 | 100 | 100
2806 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10557 | Retrofitting | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Kanmari mouza within Kanmari w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 231/HSD | 29/02/2024 | 10 | SARKAR ENTERPRISE | 0.93 | 0.93 | 100 | 100
2807 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10557 | Retrofitting | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Nazat mouza within Kanmari w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 234/HSD | 29/02/2024 | 10 | M/S PROGATI ENTERPRISE. | 0.95 | 0.95 | 100 | 100
2808 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10557 | Retrofitting | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Hatgachi mouza within Kanmari w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 233/HSD | 29/02/2024 | 10 | M/S PROGATI ENTERPRISE. | 0.94 | 0.94 | 100 | 100
2809 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10557 | Retrofitting | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Nalkora mouza within Kanmari w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 232/HSD | 29/02/2024 | 10 | SARKAR ENTERPRISE | 0.93 | 0.93 | 100 | 100
2810 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10557 | Retrofitting | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Kanmari W/S scheme (Z-I), Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 1117/HSD | 19/09/2024 | 10 | TRISHA ENTERPRISE & CO. | 0.9 | 0.9 | 100 | 100
2811 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10557 | Retrofitting | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Hatgachi mouza in connection with augmentation of Kanmari w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 523/HSD | 10/03/2025 | 10 | SARKAR ENTERPRISE | 0.96 | 0 | 0 | 100
2812 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10557 | Retrofitting | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Nalkora mouza in connection with augmentation of Kanmari w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 337/HSD | 06/02/2025 | 10 | M/S PROGATI ENTERPRISE. | 0.96 | 0 | 0 | 100
2813 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10557 | Retrofitting | Acceptance cum work order for Providing Functional tap connection at Uttar Nalkora Nityananda FP School, Chunchura FP School, Nalkora Sarat Chandra Smriti FP School, Hatgachi Bhutnath para SSK, Dk. Akratala kakdanga para SSK and Uttar Kanmari FP School within the command area of Kanmari w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 948/HSD | 29/05/2025 | 10 | SARKAR ENTERPRISE | 0.96 | 0 | 0 | 100
2814 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Khamarkalla Water Supply Scheme at Bongaon Block (Phase-II). , SM/08239 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHAMARKALLA Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (PHASE-II) | 863/NWSD-I | 08/10/2021 | 75 | M/S. TARAK CHANDRA PAUL | 80.93 | 80.92 | 54.11 | 1
2815 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Khamarkalla Water Supply Scheme at Bongaon Block (Phase-II). , SM/08239 | Retrofitting | Continuation order for the work of Hiring of 1 (one) no Motor Cab / Maxi Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Executive Engineer, North 24 Parganas W/S Division-I, P.H.E. Dte. for 181 (one hundred eighty one) days w.e.f 01/09/2022 to 28/02/2023. | 1018/NWSD-I | 24/08/2022 | 181 | M/S. SHUBHA ENTERPRISE | 0.86 | 1.81 | 100 | 100
2816 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Khamarkalla Water Supply Scheme at Bongaon Block (Phase-II). , SM/08239 | Retrofitting | Hiring of Diesel ambassador Car / Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer (HQ-I), North 24 Parganas W/S Division-I, P.H.E. Dte. [w.e.f. 01.06.2023 to 30.11.2023.(183 days)].(Car No.WB25J7778.) | 632/NWSD-I | 25/05/2023 | 183 | GITA DAS | 0.87 | 0.2 | 100 | 20
2817 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Khamarkalla Water Supply Scheme at Bongaon Block (Phase-II). , SM/08239 | Retrofitting | Continuation order for the work of Hiring of Diesel Ambassador Car / Cab having licensed carriage contract permit from Regional Transport Authority for the office of the Executive Engineer, North 24- Pgs. W/S Division-I, P.H.E. Dte. at Barrackpore under the control of Assistant Engineer (HQ-II), North 24-Pgs. W/S Division-I, P.H.E. Dte. for 184 (One Hundred Eighty Four) days w.e.f. 01.07.2023 to 31.12.2023. | 787/NWSD-I | 23/06/2023 | 184 | BADAL GHOSH | 0.86 | 0.64 | 100 | 20
2818 | NORTH 24 PARGANAS | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Acceptance cum work order for Land development at tube well site-1 within Nityabaria w/s scheme, Sandeshkhali-I under Hasnabad Sub-Division P.H.E. Dte. | 13/HSD | 04/01/2022 | 15 | M/S DATTA ENTERPRISE. | 4.93 | 4.87 | 100 | 1
2819 | NORTH 24 PARGANAS | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Acceptance cum work order for Sinking of 1 No. 360.00 mtr. Deep 100 X 40 mm. dia. trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe & strainers at T/W site-2 for Nityabaria w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 27/HSD | 04/01/2022 | 15 | M/S GHOSH CONSTRUCTION. | 3.14 | 2.58 | 100 | 1
2820 | NORTH 24 PARGANAS | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Acceptance cum work order for Sinking of 1 No. 360.00 mtr. Deep 100 X 40 mm. dia. trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe & strainers at T/W site-1 for Nityabaria w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 25/HSD | 04/01/2022 | 15 | GOBINDA DAS. | 3.14 | 2.7 | 100 | 1
2821 | NORTH 24 PARGANAS | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Acceptance cum work order for Land development at tube well site-2 within Nityabaria w/s scheme, Sandeshkhali-I under Hasnabad Sub-Division P.H.E. Dte. | 15/HSD | 04/01/2022 | 10 | M/S PROGATI ENTERPRISE. | 1.59 | 1.59 | 100 | 1
2822 | NORTH 24 PARGANAS | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Acceptance cum work order for Additional land development for connecting road at tube well site-1 (H/W site) within Nityabaria w/s scheme, Sandeshkhali-I under Hasnabad Sub-Division P.H.E. Dte. | 930/HSD | 07/06/2022 | 21 | M/S DATTA ENTERPRISE. | 2.01 | 2.01 | 50 | 1
2823 | NORTH 24 PARGANAS | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Acceptance cum work order for Additional land development at tube well site-1 (H/W site) within Nityabaria w/s scheme, Sandeshkhali-I under Hasnabad Sub-Division P.H.E. Dte. | 931/HSD | 07/06/2022 | 21 | M/S PROGATI ENTERPRISE. | 4.53 | 4.53 | 50 | 1
2824 | NORTH 24 PARGANAS | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Acceptance Cum Work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Nityaberia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 2245/BD | 28/07/2022 | 30 | M/S K.P.PAL. | 54.44 | 36.84 | 67.67 | 0
2825 | NORTH 24 PARGANAS | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Acceptance cum work order for Geotechnical investigation for the construction of proposed OHR (Capacity 400 M3 ) at HW site within Nityaberia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 1380/HSD | 04/08/2022 | 30 | RANJIT MITRA SUPPLIERS | 0.73 | 0.73 | 100 | 0
2826 | NORTH 24 PARGANAS | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 (Size-3.60x3.00 mtr.) within Nityabaria w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 1889/BD | 05/07/2022 | 60 | BABUSONA CONSTRUCTION. | 12.5 | 12.63 | 100 | 10
2827 | NORTH 24 PARGANAS | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Acceptance cum work order for Protection work for protection of 2nd pump house at canal side by UC bullah pilling within Nityaberia w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte | 1046/HSD | 31/08/2023 | 10 | BABUSONA CONSTRUCTION. | 0.95 | 0.95 | 100 | 100
2828 | NORTH 24 PARGANAS | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Acceptance cum work order for Additional height for construction of PH No- 2 & other allied works at located canal side within Nityaberia w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1411/HSD | 06/11/2023 | 10 | BABUSONA CONSTRUCTION. | 0.97 | 0.97 | 100 | 100
2829 | NORTH 24 PARGANAS | Eastern Mechanical | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Deposit Works, other than new service connection (GL:4704001) under AE-I Nityaberia | BP-99-23-24 | 31/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.94 | 0 | 0 | 0
2830 | NORTH 24 PARGANAS | Eastern Mechanical | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | New Service Connection under AE-I Nityaberia | BP-98-23-24 | 31/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.91 | 0 | 0 | 0
2831 | NORTH 24 PARGANAS | Eastern Mechanical | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Deposit works, Other Than new Service Connection under AE-I Nityaberia | BP-97-23-24 | 31/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.95 | 0 | 0 | 0
2832 | NORTH 24 PARGANAS | Eastern Mechanical | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | New Service Connection under AE-I Nityaberia | BP-100-23-24 | 31/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.85 | 0 | 0 | 0
2833 | NORTH 24 PARGANAS | Eastern Mechanical | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (New) under Nityaberia W/S Scheme District of 24 Pgs. (N) NIET No.- 27 of EE/EMD of 2022-23 (Sl. No.- 29) | 1438/EMD | 10/04/2023 | 30 | M/S DAS ENTERPRISE | 26.77 | 24.18 | 90.29 | 90
2834 | NORTH 24 PARGANAS | Eastern Mechanical | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Outdoor illumination by supplying and installing of 15 Watt Solar Street Light at P.H No.I under Nityaberia W/S Scheme, Sandeshkhali-II Block, Dist. 24 pgs (N) under Eastern Mechanical Division, P.H.E.Dte. | 1199/EMSD-I | 27/09/2024 | 30 | RMD TRADING | 1.42 | 0 | 0 | 0
2835 | NORTH 24 PARGANAS | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Material Requisition To Resource Division | 3478/BD | 10/12/2024 | 0 | Resource Division | 34.89 | 0 | 0 | 0
2836 | NORTH 24 PARGANAS | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Formal work order for "Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection & Construction of 400 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Department design, drawing & specification including bored pile & pile cap in connection with Nityaberia water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | 2577/BD | 25/08/2023 | 1096 | KINGS & CO. | 859.85 | 173.69 | 20.2 | 25
2837 | NORTH 24 PARGANAS | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 for Nityaberia water supply scheme, Sandeskhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 387/HSD | 10/02/2025 | 10 | KINGS & CO. | 0.95 | 0 | 0 | 0
2838 | NORTH 24 PARGANAS | Barasat Division | NITYABARIA PIPED WATER SUPPLY SCHEME , SM/10182 | New | Formal work order for Additional Laying of UPVC distribution pipe line and other allied works within Nityaberia water supply scheme Sandeshkhali-I Block and Surface Water Based Piped Water Supply Scheme for Hasnabad, under Hasnabad Sub-Division, PHE Dte. | 3745/BD | 27/12/2024 | 360 | KINGS & CO. | 163.99 | 0 | 0 | 25
2839 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC , SM/11534 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & strainer having 300mm dia 36 mtr. Long housing pipe & 200 mm dia 30 mtr. long filter at Bharatpur water supply scheme under Bongaon Sub-Division P.H.E.Dte. | 2241/BD | 28/07/2022 | 30 | MONDAL ENTERPRISE. (BARASAT) | 14.32 | 12.4 | 86.6 | 1
2840 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC , SM/11534 | Augmentation | Repairing & Renovation of 01No. Pump House and allied works at Bharatpur water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 633/BON | 31/12/2021 | 21 | GHOSH CONSTRUCTION. | 1.26 | 1.2 | 100 | 1
2841 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC , SM/11534 | Augmentation | Material Requisition To Resource Division | 3692/BD | 14/12/2022 | 0 | Resource Division | 0.41 | 0 | 0 | 0
2842 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC , SM/11534 | Augmentation | Material Requisition To Resource Division | 3666/BD | 13/12/2022 | 0 | Resource Division | 7.57 | 0 | 0 | 0
2843 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC , SM/11534 | Augmentation | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Bharatpur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 3470/BD | 01/12/2022 | 90 | ONKAR ENTERPRISE. | 140.49 | 140.43 | 99.95 | 1
2844 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC , SM/11534 | Augmentation | Construction of Boundary wall at 2nd T/W site for Augmentation of Bharatpur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 613/Bon | 08/08/2023 | 21 | ONKAR ENTERPRISE. | 4.08 | 0 | 0 | 0
2845 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC , SM/11534 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Bharatpur Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 126/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.98 | 2.98 | 100 | 1
2846 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC , SM/11534 | Augmentation | Construction of Approach Road at 2ndT/W site for Augmentation of Bharatpur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | 556/Bon | 18/07/2023 | 15 | GHOSH CONSTRUCTION. | 0.92 | 0.92 | 100 | 100
2847 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC , SM/11534 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Replacement) under Bharatpur W/S Scheme, Patua W/S Scheme (P/H-I & II) & Chaital W/S Scheme (P/H -I & II) District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 04) | 31/EMD | 03/01/2023 | 819 | M/S P.P. ELECTRICALS | 74.67 | 14.47 | 65.36 | 73
2848 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC , SM/11534 | Augmentation | Construction of Approach Road Head Work at site for Augmentation of Bharatpur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 622/Bon | 08/08/2023 | 12 | SAMBHU RAY CHOWDHURY. | 1.51 | 1.47 | 100 | 100
2849 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC , SM/11534 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Bharatpur Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 538/BD | 21/02/2024 | 45 | LAXMEE ENTERPRISE | 7.27 | 7.18 | 100 | 100
2850 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC , SM/11534 | Augmentation | Acceptance cum work order for Construction of 150 cum. capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile, pile cap & Soil Investigation within command area for Augmentation of Bharatpur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 2793/BD | 12/09/2023 | 730 | B.M.ENGINEERING. & CONSTRUCTION. | 91.92 | 44.42 | 48.32 | 60
2851 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC , SM/11534 | Augmentation | Carriage of different dia D.I. K-9 pipes with loading & unloading from Hasnabad Rampur to Bongaon Municipality (Zone-II) H/W site under Bongaon Sub-Division, P.H.E.Dte. | 958/Bon | 02/08/2024 | 9 | KAMAL HALDER. | 0.53 | 0 | 0 | 100
2852 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC , SM/11534 | Augmentation | Carriage of 100 mm. dia D.I. K-9 pipes with loading & unloading from Bongaon Municipality (Zone-II) H/W Site to Krishnachandrapur H/W Site under Bongaon Sub-Division, P.H.E.Dte. | 959/Bon | 02/08/2024 | 9 | ROY CHOWDHURY CONSTRUCTION. | 0.47 | 0 | 0 | 100
2853 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of BOUTHAKURANI Water Supply Scheme under Barasat Division, PHE Dte. | 230/HSD | 02/02/2022 | 15 | UMWELT ENGINEER PVT.LTD. | 4.81 | 4.81 | 100 | 1
2854 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Material Requisition To Resource Division | 3365/BD | 17/11/2022 | 0 | Resource Division | 3.05 | 0 | 0 | 0
2855 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bouthakurani water supply scheme (Zone-I), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | 2403/BD | 17/08/2022 | 90 | R.K.MANDAL & CO. | 239.51 | 236.33 | 98.67 | 1
2856 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bouthakurani w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 788/BD | 13/03/2023 | 30 | M/S DATTA ENTERPRISE. | 47.05 | 38.83 | 82.53 | 0
2857 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 789/BD | 13/03/2023 | 30 | M/S DATTA ENTERPRISE. | 47.04 | 37.49 | 79.69 | 1
2858 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Zone-I) and Pump House No-I and II (Zone-II)(Rep.) under Bouthakurani W/S Scheme District of 24 Pgs. (N) NIET No.- 32 of EE/EMD of 2022-23 (Sl. No.- 03) | 1282/EMD | 28/03/2023 | 30 | SINHA ELECTRICALS | 66.26 | 57.89 | 87.36 | 0
2859 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Additional Emergent restoration of approach road for movement of rig machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 780/HSD | 13/07/2023 | 10 | SHYAM SUNDAR DAS. | 0.55 | 0 | 0 | 0
2860 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Formal work order for for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bouthakurani water supply scheme (Zone-II), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | 2402/BD | 17/08/2022 | 90 | M/S PROGATI ENTERPRISE. | 238.52 | 236.38 | 60.98 | 1
2861 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Repairing & construction of boundary wall for movement of rig machineries for sinking of big dia TW at PH no- 3 in connection with Augmentation of Bouthakurani w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 776/HSD | 13/07/2023 | 10 | PRITAM MUKHOPADHYAY. | 0.73 | 0.73 | 100 | 100
2862 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Repairing & construction of boundary wall for movement of rig machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte | 781/HSD | 13/07/2023 | 10 | PRITAM MUKHOPADHYAY. | 0.6 | 0.6 | 100 | 100
2863 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Repairing & construction of boundary wall for movement of rig machineries for sinking of big dia TW at PH no- 4 in connection with Augmentation of Bouthakurani w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 784/HSD | 13/07/2023 | 10 | SHYAM SUNDAR DAS. | 0.71 | 0.7 | 100 | 100
2864 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bouthakurani w/s scheme (Z-I), Sandeshkhali-IIblock under Hasnabad Sub-Division, P.H.E. Dte. | 2472/BD | 18/08/2023 | 30 | M/S DATTA ENTERPRISE. | 26.97 | 21.39 | 100 | 100
2865 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Protection works in different places for protection of different dia DI/UPVC rising/distribution pipe line by UC bullah/Bamboo pile for Augmentation of Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 2657/BD | 01/09/2023 | 30 | R.K.MANDAL & CO. | 80.57 | 80.45 | 100 | 81
2866 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Material Requisition To Resource Division | 2470/BD | 24/08/2022 | 0 | Resource Division | 8.3 | 0 | 0 | 0
2867 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Sinking of Additional 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Sandeshkhali and Bouthakurani (Z-II) w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 3332/BD | 28/11/2024 | 60 | UTPAL CONSTRUCTION & CO. | 63.3 | 0 | 0 | 0
2868 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Emergent restoration of approach road for movement of rig machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte | 779/HSD | 13/07/2023 | 10 | NURJAHAN ENTERPRISE. | 0.79 | 0.79 | 100 | 100
2869 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Repairing & construction of boundary wall for movement of rig machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 782/HSD | 13/07/2023 | 10 | NURJAHAN ENTERPRISE. | 0.93 | 0.92 | 100 | 100
2870 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Bouthakurani water supply scheme (Z-II) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 630/HSD | 12/06/2024 | 10 | PRITAM MUKHOPADHYAY. | 1.02 | 1 | 100 | 100
2871 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-3 & 4 in connection with Augmentation for Bouthakurani water supply scheme (Z-I) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 631/HSD | 12/06/2024 | 10 | PRITAM MUKHOPADHYAY. | 1.02 | 1.01 | 100 | 100
2872 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection for the leftout portion at Dholkhali Mouza in connection with Augmentation of Bouthakurani water supply scheme (Z- I), Sandeskhali-II Block under Hasnabad Sub-Division, PHE Dte. | 386/HSD | 10/02/2025 | 10 | HASAN ENTERPRISE | 0.97 | 0 | 0 | 0
2873 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-5 in connection with Augmentation for Bouthakuranii (Z-I) water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 151/HSD | 27/01/2025 | 10 | PRITAM MUKHOPADHYAY. | 0.73 | 0 | 0 | 100
2874 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Supply and installation of 100 & 150 mm dia sluice valve in distribution pipe line for smooth supply of water at different palces in connection with augmentation of Bouthakurani water supply scheme (Z-II), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. (Part-B) | 344/HSD | 06/02/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.6 | 0 | 0 | 100
2875 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places in connection with augmentation of Bouthakurani W/S Scheme Z-II, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Phase-III) | 390/HSD | 10/02/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.97 | 0 | 0 | 100
2876 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Supply and installation of 100mm dia sluice valve in distribution pipe line for smooth supply of water at different palces in connection with augmentation of Bouthakurani water supply scheme (Z-II), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. (Part-A) | 242/HSD | 30/01/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.84 | 0 | 0 | 100
2877 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places in connection with augmentation of Bouthakurani W/S Scheme Z-II, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Phase-I) | 471/HSD | 28/02/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.95 | 0 | 0 | 100
2878 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Special repair & maintenance of different dia UPVC pipe line at different places in connection with augmentation of Bouthakurani w/s Scheme (Z-II), Sandeskhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. Phase-1 | 320/HSD | 04/02/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.97 | 0 | 0 | 100
2879 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Special repair & maintenance of different dia UPVC pipe line at different places in connection with augmentation of Bouthakurani w/s Scheme (Z-II), Sandeskhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. Phase-2 | 1006/HSD | 04/06/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.92 | 0 | 0 | 100
2880 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Special repair & maintenance of different dia UPVC pipe line at different places in connection with augmentation of Bouthakurani w/s Scheme (Z-II), Sandeskhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. Phase-3 | 532/HSD | 10/03/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.93 | 0 | 0 | 100
2881 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Providing Functional household tap connection at Tushkhali Harasit Smriti MSK, Purba Bouthakurani FP School and Dholkhali Dakshinpara SSK within the command area of Tushkhali and Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte | 952/HSD | 29/05/2025 | 10 | M/S K.B.ENTERPRISE. | 0.91 | 0 | 0 | 100
2882 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places in connection with augmentation of Bouthakurani W/S Scheme Z-II, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Phase-II) | 319/HSD | 04/02/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.95 | 0 | 0 | 100
2883 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Special repair & maintenance of different dia UPVC pipe line at different places in connection with augmentation of Bouthakurani w/s Scheme (Z-II), Sandeskhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. Phase-4 | 1485/HSD | 14/07/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.93 | 0 | 0 | 100
2884 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. , SM/11536 | Augmentation | Acceptance cum work order for Providing Functional tap household connection at Bouthakurani Dakshinpara FP School and Tongtala Adibasi FP School within the command area of Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1492/HSD | 14/07/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.61 | 0 | 0 | 100
2885 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC , SM/12276 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Bansghata Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 142/BON | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 50 | 1
2886 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC , SM/12276 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Replacement) under Bansghata W/S Scheme, District of 24 Pgs. (N). NIET No.- 26 of EE/EMD of 2022-23 (Sl. No.- 02) | 1552/EMD | 20/04/2023 | 30 | TALUKDER & CO. | 21.41 | 0 | 0 | 0
2887 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC , SM/12276 | Augmentation | Material Requisition To Resource Division | 1246/BD | 25/04/2023 | 0 | Resource Division | 113.03 | 0 | 0 | 0
2888 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC , SM/12276 | Augmentation | Material Requisition To Resource Division | 1864/BD | 23/06/2023 | 0 | Resource Division | 31.18 | 0 | 0 | 0
2889 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC , SM/12276 | Augmentation | Formal work order for Laying of Di rising main, DI/UPVC distribution pipe line and Providing (FHTC) for augmentation of Bansghata Water Supply Scheme, Bagdah Block, under Bongaon Sub-Division, PHE Dte. | 760/BD | 10/03/2023 | 90 | UMWELT ENGINEER PVT.LTD. | 747.85 | 747.34 | 100 | 100
2890 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC , SM/12276 | Augmentation | Acceptance cum work order for Construction of Boundary wall, Approach Road, Earth Filling and Construction of 3.60 mtr. X 3.00 mtr. size Guard Room with sanitary and water supply arrangement incl. plinth protection at OHR site of Basghata Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 2358/BD | 20/08/2024 | 420 | MD.SALIM GAZI. | 25.84 | 0 | 0 | 75
2891 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC , SM/12276 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Replacement) under Bansghata W/S Scheme, District of 24 Pgs. (N). | 4725/EMD | 04/08/2023 | 606 | TALUKDER & CO. | 21.41 | 19.5 | 100 | 100
2892 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC , SM/12276 | Augmentation | Acceptance cum work order for Sinking of 2 (two) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer at Augmentation of Bansghata Water Supply Scheme (H/W Site & 2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | 518/BD | 20/02/2024 | 300 | M/S N.K. BUILDERS | 30.51 | 6.1 | 20.94 | 100
2893 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC , SM/12276 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at 1st Tube Well & 2nd Tube Well site and Construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Bansghata water Supply scheme, Bagdah Block within jurisdiction of Bongaon Sub-Division, under Barasat Division P.H.E. Dte. | 4471/BD | 22/11/2023 | 414 | ROY CHOWDHURY CONSTRUCTION. | 12.67 | 9.13 | 72.1 | 73
2894 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gabberia to accommodate FHTC. , SM/10781 | Augmentation | Material Requisition To Resource Division | 938/BD | 22/03/2023 | 0 | Resource Division | 19.76 | 0 | 0 | 0
2895 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gabberia to accommodate FHTC. , SM/10781 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Gabberia w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 2475/BD | 18/08/2023 | 30 | M/S RAJPATH CONSTRUCTION. | 63.23 | 43.58 | 100 | 92
2896 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Gabberia to accommodate FHTC. , SM/10781 | Augmentation | Formal work order for "Laying of DI rising main, DI/UPVC distribution pipe line, Construction of 300 cum capacity 20rntr. staging height R.C.C. Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and providing Functional Household Tap Connection with Augmentaion of Gabberia water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, P.H.E. Dte. | 2526/BD | 23/08/2023 | 707 | BALAJEE ENTERPRISES | 550.99 | 323.7 | 62.78 | 79
2897 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghona to accommodate FHTC , SM/11627 | Augmentation | Material Requisition To Resource Division | 3821/BD | 23/12/2022 | 0 | Resource Division | 27.91 | 0 | 0 | 0
2898 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghona to accommodate FHTC , SM/11627 | Augmentation | Material Requisition To Resource Division | 4405/BD | 10/11/2023 | 0 | Resource Division | 3.08 | 0 | 0 | 0
2899 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghona to accommodate FHTC , SM/11627 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) by augmentation for Ghona water supply scheme in Basirhat-II Block of North 24 Parganas District under Barasat Division, PHE Dte. | 3184/BD | 01/11/2022 | 90 | SHIBU BISWAS. | 179.98 | 130.01 | 100 | 85
2900 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC , SM/11658 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Dakshin Chatra Zone II Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 442/ BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.04 | 4.04 | 50 | 1
2901 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC , SM/11658 | Augmentation | Material Requisition To Resource Division | 1239/BD | 25/04/2023 | 0 | Resource Division | 69.2 | 0 | 0 | 0
2902 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC , SM/11658 | Augmentation | Material Requisition To Resource Division | 1627/BD | 01/06/2023 | 0 | Resource Division | 19.43 | 0 | 0 | 0
2903 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC , SM/11658 | Augmentation | Formal work order for Laying of UPVC distribution pipeline and Providing FHTC (Functional Household Tap Connection) for Augmentation of Dakshin Chatra Zone-II Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, PHE Dte. | 1041/BD | 31/03/2023 | 773 | DIAMOND ENGINEER'S CO-OP. SOCIETY LTD. | 378.49 | 337.54 | 89.18 | 37
2904 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC , SM/11658 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No II (Rep.) (Zone-I and II) under Dakshin Chatra W/S Scheme District of 24 Pgs. (N) | 6734/EMD | 29/11/2023 | 30 | CONCORD ENGINEERING | 26.08 | 0 | 0 | 0
2905 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC , SM/11658 | Augmentation | Dismantling of a dilapidated Room due to construction of Bio Eco Tech Plant at the Head Work site of Dakshin Chatra Zone I Water Supply Scheme under Barasat Division, P.H.E. | 942/BHTSD | 24/05/2024 | 7 | N.R. ENTERPRISE | 0.97 | 0.97 | 100 | 100
2906 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC , SM/11658 | Augmentation | Acceptance cum work order for Restoration of roads under different water supply schemes of Swarupnagar Block within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | 3625/BD | 20/12/2024 | 90 | PUSPA CONSTRUCTION. | 57.26 | 0 | 0 | 0
2907 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone II to accommodate FHTC , SM/11658 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Swarupnagar Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - C) | 154/BHTSD | 29/01/2025 | 20 | M.R.CONSTRUCTION. | 0.88 | 0 | 0 | 100
2908 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11708 | Augmentation | Preparation of Augmentation DPR for Jasaikathi (Zone-II) Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | 1835/B.Ar.D | 19/09/2022 | 20 | RISHAN ENGINEERING CONSULTANCY | 0.98 | 0.97 | 100 | 1
2909 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11708 | Augmentation | Material Requisition To Resource Division | 2293/B.Ar. | 02/12/2022 | 0 | Resource Division | 10.97 | 0 | 0 | 0
2910 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11708 | Augmentation | Sinking for 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method near Pump House no.-2 with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter at Jasaikathi (Z-II) w/s scheme of Baduria block under Barasat Arsenic Division, P.H.E. Dte. (Sl No. 3) | 2057/B.Ar.D. | 19/10/2022 | 45 | M/S RAJPATH CONSTRUCTION | 15.35 | 12.2 | 100 | 1
2911 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11708 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir of Capacity 550 Cu.m. at Jasaikathi (Z-II) W/S Scheme of Baduria Block under Barasat Arsenic Division, PHE Dte. | 238/B.Ar.D. | 02/02/2023 | 60 | M/S DATTA ENTERPRISE | 13.66 | 13.47 | 100 | 1
2912 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11708 | Augmentation | Material Requisition To Resource Division | 2106/B.Ar.D. | 02/11/2022 | 0 | Resource Division | 9.61 | 0 | 0 | 0
2913 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11708 | Augmentation | New Service Connection at PH-III Z-II under Jashaikati W/ Scheme. | BP-167-23-24 | 19/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.86 | 0 | 0 | 0
2914 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11708 | Augmentation | Supply Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I and II Zone II Rep. under Jashaikathi WS Scheme District of 24 Pgs. N. | 4870/EMD | 14/08/2023 | 30 | M/S S.R. ENTERPRISE | 26.07 | 12.17 | 46.66 | 47
2915 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11708 | Augmentation | Hiring of one (1) no. Diesel / Petrol operated AC motor cab / maxi cab (Car No. - WB25F - 6815) with engine capacity less than or equal to 2000 C.C. with driver for official use of the Chief Engineer (Head Quarters), Office, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 01.07.2024 to 31.12.2024. | 1047/F/B.Ar.D | 27/06/2024 | 184 | TOJO ENTERPRISE | 0.96 | 1.59 | 166.45 | 0
2916 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11708 | Augmentation | Construction of 3.6 mtr. x 3.0 mtr. size new Pump House ( Pump House-III ) with sanitary arrangement, construction of boundary wall and Allied Works for Jasaikathi ( Z-II ) W/S Scheme Under Baduria Block under Barasat Arsenic Division, PHE Dte. | 1796/B.Ar.D. | 28/07/2023 | 60 | AFRINA ENTERPRISE | 11.68 | 11.42 | 100 | 100
2917 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11708 | Augmentation | Laying of DI pipe and Repairing, Rennovation and protection of boundary wall, Fencing work etc and other allied works at Head work site of Jasaikathi-(Z-II) W/S Scheme under Baduria Block under Barasat Arsenic Division PHE Dte. | 393/B.Ar.D | 21/02/2024 | 45 | MAHALAXMI CONSTRUCTION | 14.79 | 14.32 | 100 | 100
2918 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11708 | Augmentation | Laying of distribution System Including specials all Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Jasaikathi Zone -II at Baduria Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | 1635/B.Ar.D. | 30/08/2022 | 990 | CHANCHAL ENTERPRISE & CO. | 284.52 | 268.83 | 98.86 | 86
2919 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC. , SM/11595 | Augmentation | Formal Work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Nurpur water supply scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 2398/BD | 17/08/2022 | 90 | M/S NIRMAN CONSTRUCTION. | 183.61 | 179.26 | 100 | 1
2920 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC. , SM/11595 | Augmentation | Material Requisition To Resource Division | 2475/BD | 24/08/2022 | 0 | Resource Division | 4.91 | 0 | 0 | 0
2921 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC. , SM/11595 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Champali W/S Scheme and Nurpur W/S SchemeDistrict of 24 Pgs. (N) NIET No.- 32 of EE/EMD of 2022-23 (Sl. No.- 04) | 1004/EMD | 09/03/2023 | 30 | PADMA ENGINEERING CO. | 53 | 14.37 | 54.22 | 60
2922 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC. , SM/11595 | Augmentation | Formal work order for construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Nurpur water supply scheme, Minakhan Block of Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | 4181/BD | 30/10/2023 | 730 | SARKAR ENTERPRISE & CO. | 122.36 | 55.65 | 53.99 | 100
2923 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC , SM/11602 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Kamlabas water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 592/BON | 22/12/2021 | 21 | MONDAL & CO.(BON) | 2.52 | 2.31 | 100 | 1
2924 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC , SM/11602 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Kamalabas Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 3630/BD | 12/12/2022 | 90 | BANERJEE CONSTRUCTION. ( BARASAT) | 181.45 | 131.1 | 100 | 0
2925 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC , SM/11602 | Augmentation | Material Requisition To Resource Division | 1259/BD | 25/04/2023 | 0 | Resource Division | 17.95 | 0 | 0 | 0
2926 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC , SM/11602 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kamalabas Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | 2944/BD | 27/09/2023 | 30 | JOY GURU ENTERPRISE | 16.12 | 13.3 | 100 | 100
2927 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC , SM/11602 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep replacement T/W by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kamlabas Water Supply Scheme (2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | 2829/BD | 15/09/2023 | 30 | SAHA CONSTRUCTION & CO | 16.14 | 13.46 | 100 | 100
2928 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC , SM/11602 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Head Work site for Augmentation of Kamlabas Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 534/BD | 21/02/2024 | 45 | REAL TIME | 12.89 | 13.25 | 100 | 100
2929 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC , SM/11602 | Augmentation | Construction of 3.60 mtr. X 3.00mtr. size Switch room with sanitary and water supply arrangement incl. plinth protection at 2nd Tube Well site at Kamlabas w/s scheme Bagdah block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | 211/Bon | 27/02/2024 | 45 | MONDAL & CO.(BON) | 4.39 | 4.39 | 100 | 100
2930 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC , SM/11602 | Augmentation | Emergent works for repairing pipe line, FHTC refining, ferrule wash with supply of sluice valve and construction of valve chamber under Augmentation work at Kamlabas W/S Scheme Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 490/Bon | 04/04/2024 | 15 | MONDAL & CO.(BON) | 4.97 | 4.94 | 100 | 100
2931 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC , SM/11602 | Augmentation | New service connection at P.H.No- II of Kamalabas water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). | BP-348-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.9 | 0 | 0 | 0
2932 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC , SM/11602 | Augmentation | Enhancement amount of GST for laying of DI/UPVC distribution pipe line and providing FHTC for Augmentation Kamlanbas wsscheme. | BP-2024-25-416 | 07/10/2024 | 0 | BANERJEE CONSTRUCTION. ( BARASAT) | 7.08 | 0 | 0 | 0
2933 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC , SM/11602 | Augmentation | Acceptance cum work order for Restoration of existing 140 mm dia UPVC pipe line along the main road by UC Ballah pilling due to soil erosion at the bank of Ichhamati river near Holor Ghat (Chalk Jhitkipota) under Augmentation work of Kamalabas W/S Scheme, Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1523/BD | 14/05/2025 | 180 | ANARUL KHAN. | 61.45 | 0 | 0 | 40
2934 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC , SM/11602 | Augmentation | Acceptance cum work order for Improvement of existing IEP & other related allied works and including adding 1 no. Polishing unit and Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Kamalabas Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 2448/BD | 15/07/2025 | 45 | MONDAL ENTERPRISE. (BARASAT) | 23.45 | 0 | 0 | 0
2935 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC , SM/11602 | Augmentation | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and Construction of Approach Road at Head Work & 2nd T/W site under Augmentation of Kamlabas Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 558/BD | 22/02/2024 | 450 | S.S. INFRASTRUCTURE | 10.36 | 0 | 0 | 100
2936 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC , SM/11602 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram with laying of UPVC pipe line, Tube Well connection and pipe protection work under Augmentation work at Kamlabas W/S Scheme Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1397/Bon | 27/11/2024 | 90 | SONALI CONSTRUCTION | 4.8 | 0 | 0 | 100
2937 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. , SM/11214 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Ichhlampur (Zone-I) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | 1186/NWSD-I | 31/12/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.65 | 4.65 | 100 | 1
2938 | NORTH 24 PARGANAS | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. , SM/11214 | Augmentation | Providing And Installation of Electro Mechanical Equipments and Allied Works for Arsenic Removal Plant at Zone I of Ichhlampore Piped Water Supply Scheme, Block Bongaon Dist. North 24 Pgs under EMD, PHE Dte. | 4871/EMD | 14/08/2023 | 30 | DIPALI CONSTRUCTION | 37.15 | 0 | 0 | 0
2939 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. , SM/11214 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system & Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of Ichhlampur Zone-1 Water Supply Scheme under North 24 Parganas Water Supply Division-I, PHE.Dte. | 876/NWSD-I | 22/07/2022 | 90 | M/S. TARAK CHANDRA PAUL | 763.75 | 680.99 | 100 | 62
2940 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. , SM/11214 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 160 m Length in Head work site at Ichhlampur Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 380/NWSD-I | 05/04/2023 | 45 | ROY CHOWDHURY CONSTRUCTION | 16.26 | 8.16 | 100 | 75
2941 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. , SM/11214 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 45 m Length in 3rd Pump house site at Ichhlampur Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 382/NWSD-I | 05/04/2023 | 45 | A K DUTTA & CO | 6.05 | 5.78 | 100 | 100
2942 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. , SM/11214 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 45 m Length in 2nd Pump house site at Ichhlampur Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 381/NWSD-I | 05/04/2023 | 45 | M/S DHELA BABA ENTERPRISE | 6.08 | 4 | 100 | 100
2943 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. , SM/11214 | Augmentation | Special Repair & Renovation two nos. Pump house and Servicer road at 2nd & 3rd Tube well site at Ichhlampur Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 881/NWSD-I | 12/07/2023 | 45 | MAA TARA ENTERPRISE | 8.64 | 6.34 | 100 | 100
2944 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. , SM/11214 | Augmentation | Material Requisition To Resource Division | 880/NWSD-I | 22/07/2022 | 0 | Resource Division | 75.43 | 0 | 0 | 0
2945 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. , SM/11214 | Augmentation | Material Requisition To Resource Division | 879/NWSD-I | 22/07/2022 | 0 | Resource Division | 28.08 | 0 | 0 | 0
2946 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. , SM/11214 | Augmentation | Construction of Arsenic cum Iron removal Plants (AIRP) of capacity 105 cum/hr at Head work site of Ichhlampur (Zone-I) Water Supply Scheme within the Bongaon Block and other anciliary work under North 24 Pgs. W/S Division-I, P.H.E. Dte. | 499/NWSD-I | 15/03/2024 | 365 | HARBAUER INDIA (P) LTD | 267.95 | 0 | 0 | 0
2947 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. , SM/11214 | Augmentation | Repair and renovation works for 550 cum. capacity R.C.C. Over Head water Reservoir and other allied works at Ichhlampur (Zone-I) W/S Scheme under North 24 Pgs Water Supply Division- I, P.H.E. Dte. | 1436/NWSD-I | 11/09/2023 | 60 | ROY CHOWDHURY CONSTRUCTION | 27.71 | 27.03 | 100 | 100
2948 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. , SM/11214 | Augmentation | Material Requisition To Resource Division | 1312/NWSD-I | 30/08/2024 | 0 | Resource Division | 1.85 | 0 | 0 | 0
2949 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. , SM/11214 | Augmentation | Laying of distribution system including specials ,valves, & pipes carrying all complete at Ichhlampur Zone-I Water Supply scheme in the District of North 24 Parganas under North 24 Parganas water Supply Division-I, PHE Dte. | 1628/NWSD-I | 12/11/2024 | 421 | M/S. S.S. ENTERPRISE | 23.57 | 0 | 0 | 0
2950 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. , SM/11214 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1431/NWSD-I | 18/09/2024 | 7 | IMAGIN | 4.59 | 0 | 0 | 95
2951 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11559 | Augmentation | Preparation of Augmentation DPR for Mahisgadi Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | 1952/B.Ar.D | 26/09/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0.99 | 100 | 1
2952 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11559 | Augmentation | Material Requisition To Resource Division | 2297/B.Ar.D | 02/12/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
2953 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11559 | Augmentation | Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Mahisgadi & its adjoining mouza Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 1559/B.Ar.D. | 24/08/2022 | 90 | M/S R. M. CONSTRUCTION | 131.17 | 112.15 | 85.49 | 85
2954 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11559 | Augmentation | Withdrawling and re laying of 250 mm dia upvc pipeline related to the work "Providing Functional House Hold Tap Connection (FHTC) from the existing and new proposed distribution system within Command area at Mahisgadi & its adjoining mouza water supply Scheme under Barasat-II Block Under Barasat Arsenic, PHE Dte. | 2339/B.Ar.D. | 21/09/2023 | 30 | M/S R. M. CONSTRUCTION | 6.45 | 6.41 | 99.4 | 95
2955 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11559 | Augmentation | Material Requisition To Resource Division | 2107/B.Ar.D. | 02/11/2022 | 0 | Resource Division | 0.79 | 0 | 0 | 0
2956 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11559 | Augmentation | Increse of Water pressure through by pass Pipeline from Second tubewell to main distribution pipeline and dedicated pipeline for I.E.P. to haroa khal in Mahisgadi Water Supply Scheme under Barasat Arsenic Division, P.H.E Dte. | 982/B.Ar.D. | 18/06/2024 | 40 | SUJAN KUMAR MISTRI | 4.08 | 0 | 0 | 0
2957 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11559 | Augmentation | Laying of pipeline at damaged portion due to construction of road, drain by panchayet related to the work "Providing Functional House Hold Tap Connection (FHTC) from the existing and new proposed distribution system within Command area at Mahisgadi & its adjoining mouza water supply Scheme under Barasat-II Block Under Barasat Arsenic, PHE Dte. | 1827/B.Ar.D. | 01/08/2023 | 45 | P. & S. ASSOCIATES | 28.23 | 27.73 | 100 | 100
2958 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11559 | Augmentation | Repair and Renovation works of 350 Cum OHR and allied water supply component infrastructure under Mahisgadi W/S Scheme of Barasat -II Block under Barasat Arsenic Division, PHE Dte. | 3027/B.Ar.D. | 29/12/2023 | 45 | UMA CONSTRUCTION | 19.75 | 19.6 | 100 | 100
2959 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11559 | Augmentation | Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No. - WB19J - 2141) with driver for official use for Assistant Engineer (HQ-I), Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 01.07.2024 to 31.12.2024. | 1023/B.Ar.D | 21/06/2024 | 184 | OM ENTERPRISE | 0.87 | 2.23 | 255.38 | 0
2960 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11559 | Augmentation | Repairing of damaged diifferent dia pipeline for increasing the functionality of House hold tap connection within command area of Kamuduni Mouza at Mahisgadi W/S Scheme at Barasat-II Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | 430/B.Ar.D. | 10/03/2025 | 30 | SANTU GHOSH | 4.83 | 0 | 0 | 100
2961 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Based Piped Water Supply Scheme for MAHISHGADI to accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11559 | Augmentation | Repairing of D.I distribution pipeline in the H/W Site of Mahisgadi Water Supply Scheme under Barasat Arsenic Division, P.H.E Dte. | 431/B.Ar.D. | 10/03/2025 | 30 | SAFE STEP ENTERPRISE | 3.41 | 0 | 0 | 100
2962 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Srinagar to accommodate FHTC , SM/11528 | Augmentation | Route Survey, Design Drawing & DPR Preparation for SRINAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte | 342/ BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.1 | 3.92 | 50 | 1
2963 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Srinagar to accommodate FHTC , SM/11528 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Replacement) under Srinagar W/S Scheme District of 24 Pgs. (N). (SM/11528) NIET No. 19 of EE/EMD of 2022-23 (Sl. No. - 29) | 6436/EMD | 25/11/2022 | 30 | AHALYA ENGINEERING WORKS | 13.04 | 7.65 | 58.69 | 0
2964 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Srinagar to accommodate FHTC , SM/11528 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Srinagar W/S Scheme District of 24 Pgs. (N). (SM/11528) NIET No. 19 of EE/EMD of 2022-23 (Sl. No. - 28) | 6437/EMD | 25/11/2022 | 30 | MERCURY ENGINEERING COMPANY | 13.04 | 0 | 0 | 0
2965 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Srinagar to accommodate FHTC , SM/11528 | Augmentation | Material Requisition To Resource Division | 482/BD | 17/02/2023 | 0 | Resource Division | 70.46 | 0 | 0 | 0
2966 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Srinagar to accommodate FHTC , SM/11528 | Augmentation | Material Requisition To Resource Division | 596/BD | 23/02/2023 | 0 | Resource Division | 16.4 | 0 | 0 | 0
2967 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Srinagar to accommodate FHTC , SM/11528 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Srinagar water supply scheme in Basirhat-II Block of North 24 Parganas district under under Barasat Division, PHE Dte. | 92/BD | 11/01/2023 | 90 | CHANDA CONSTRUCTION. | 376.97 | 348.89 | 92.55 | 82
2968 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Srinagar to accommodate FHTC , SM/11528 | Augmentation | Acceptance cum work order for special repair and renovation of existing structures like Pump House, boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Champapukur, Chandipur, Dakhin Debipur, Dhopaberia, Srinagar and Sangrampur Water Supply Scheme of different block under Basirhat Sub-Division, PHE Dte. | 2424/BD | 14/07/2025 | 150 | DAS ENTERPRISE | 82.86 | 0 | 0 | 0
2969 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Raharhati to accommodate FHTC , SM/11531 | Augmentation | Material Requisition To Resource Division | 3818/BD | 23/12/2022 | 0 | Resource Division | 27.79 | 0 | 0 | 0
2970 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Raharhati to accommodate FHTC , SM/11531 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Replacement) under Raharhati W/S Scheme District of 24 Pgs. (N). (SM/11531) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 21) | 6395/EMD | 24/11/2022 | 30 | WIZARDTECH SOLUTION | 13.02 | 11.37 | 87.34 | 0
2971 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Raharhati to accommodate FHTC , SM/11531 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Raharhati W/S Scheme District of 24 Pgs. (N). (SM/11531) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 20) | 6394/EMD | 24/11/2022 | 30 | S.S. ENTERPRISE | 13.02 | 11.42 | 87.73 | 0
2972 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Raharhati to accommodate FHTC , SM/11531 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. big dia. 300 mtr deep Tubewell by D.R. Rig method, with 300 mm dia 36.0 mtr. long PVC having 200mm dia 30 mtr. long filter for Augmentation of Raharati Water Supply Scheme in Basirhat-II Block of Basirhat Sub-Division under Barasat Division, PHE Dte. | 769/BD | 11/03/2024 | 30 | SHEKH ENTERPRISE | 21.75 | 0 | 0 | 0
2973 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Raharhati to accommodate FHTC , SM/11531 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Raharhati water supply scheme in Basirhat-II Block of North 24 Parganas District under Barasat Division, PHE Dte. | 3306/BD | 10/11/2022 | 90 | M/S PRADIP KUMAR PAL | 139.59 | 139.49 | 100 | 99
2974 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC , SM/11632 | Augmentation | Acceptance cum work order for Providing Functional tap connection at Paschim Monipur FP School, East Monipur Khargeswar Adibasi FP School within the command area of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1051/HSD | 31/08/2023 | 7 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 0.48 | 0 | 0 | 0
2975 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC , SM/11632 | Augmentation | Acceptance cum work order for Protection works in different places for protection of different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile for Augmention of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 2654/BD | 01/09/2023 | 30 | M/S K.B.ENTERPRISE. | 27.43 | 27.39 | 99.87 | 85
2976 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC , SM/11632 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Monipur water supply scheme,Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | 2446/BD | 23/08/2022 | 90 | APURBA MANDAL | 278.15 | 252.56 | 68.93 | 1
2977 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC , SM/11632 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 1206/BD | 20/04/2023 | 30 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 31.03 | 24.86 | 100 | 51
2978 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC , SM/11632 | Augmentation | Acceptance cum work order for Supply, fitting & fixing of sluice valve with valve chember at HW & 2nd TW site in connection with augmentation of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 1416/HSD | 06/11/2023 | 7 | BADAL GHOSH. | 0.97 | 0.97 | 100 | 100
2979 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC , SM/11632 | Augmentation | Material Requisition To Resource Division | 2473/BD | 24/08/2022 | 0 | Resource Division | 13.91 | 0 | 0 | 0
2980 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC , SM/11632 | Augmentation | Acceptance cum work order Sinking of 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 2474/BD | 18/08/2023 | 30 | M/S RAJPATH CONSTRUCTION. | 31.64 | 25.14 | 100 | 100
2981 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC , SM/11632 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Monipur water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 1413/HSD | 06/11/2023 | 7 | ANKUSH CONSTRUCTION & CO. | 0.91 | 0.9 | 100 | 100
2982 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC , SM/11632 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) with Pump House no-III(New) under Monipur W/S Scheme with Bajitpur (I and II, Zone-II) W/S Scheme in District of 24 Pgs. (N) | 6739/EMD | 29/11/2023 | 580 | GLACIER ENGINEERING CO. | 67.8 | 15.05 | 36.99 | 40
2983 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC , SM/11632 | Augmentation | Acceptance cum work order for Sinking of Additional 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Korakati and Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 3333/BD | 28/11/2024 | 60 | UTPAL CONSTRUCTION & CO. | 63.34 | 0 | 0 | 0
2984 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC , SM/11632 | Augmentation | Formal work order for Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Monipur water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, P.H.E. Dte. | 1721/BD | 08/06/2023 | 642 | R.K.MANDAL & CO. | 150.42 | 127.83 | 88 | 90
2985 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC , SM/11632 | Augmentation | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places in connection with augmentation of Monipur W/S Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Phase-II) | 542/HSD | 10/03/2025 | 10 | BADAL GHOSH. | 0.95 | 0 | 0 | 100
2986 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC , SM/11632 | Augmentation | Acceptance cum work order for Providing Functional household tap connection at North Monipur FP School, Paschim Monipur FP School and Gabberia FP School within the command area of Monipur & Gabberia w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 548/HSD | 10/03/2025 | 10 | M/S K.B.ENTERPRISE. | 0.76 | 0 | 0 | 100
2987 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC , SM/11632 | Augmentation | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places in connection with augmentation of Monipur W/S Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Phase-I) | 468/HSD | 28/02/2025 | 10 | BADAL GHOSH. | 0.96 | 0 | 0 | 100
2988 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC , SM/11632 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site in connecting with Augmentation of Monipur W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 161/HSD | 27/01/2025 | 10 | R.K.MANDAL & CO. | 0.98 | 0 | 0 | 100
2989 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC , SM/11632 | Augmentation | Acceptance cum work order for Protection of pile cap at canal side by bamboo pilling in connection with Augmentation of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 160/HSD | 27/01/2025 | 10 | R.K.MANDAL & CO. | 0.92 | 0 | 0 | 100
2990 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC , SM/11632 | Augmentation | Acceptance cum work order for Installation of CCTV Camera Connection at Pump house no 1 & 2 for Monipur w/s scheme, Sandeshkhali -II Block under Hasnabad Sub-Division, PHE Dte | 189/HSD | 28/01/2025 | 10 | M/S DATTA ENTERPRISE. | 0.58 | 0 | 0 | 100
2991 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC , SM/11632 | Augmentation | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Dakshin Monipur in connection with augmentation of Monipur w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 947/HSD | 29/05/2025 | 10 | SAGAR DAS. | 0.96 | 0 | 0 | 100
2992 | NORTH 24 PARGANAS | Barasat Division | Bachhra piped Water supply scheme , SM/12712 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BACHHRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 244/HSD | 03/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.8 | 4.8 | 100 | 1
2993 | NORTH 24 PARGANAS | Barasat Division | Bachhra piped Water supply scheme , SM/12712 | New | Material Requisition To Resource Division | 876/BD | 22/03/2023 | 0 | Resource Division | 30.63 | 0 | 0 | 0
2994 | NORTH 24 PARGANAS | Barasat Division | Bachhra piped Water supply scheme , SM/12712 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 100 cum capacity CWR, pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Bachhra w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1690/BD | 07/06/2023 | 366 | R.K.MANDAL & CO. | 267.07 | 223.92 | 83.84 | 85
2995 | NORTH 24 PARGANAS | Eastern Mechanical | Bachhra piped Water supply scheme , SM/12712 | New | Quotation for Service Connection Charges for PH- II under Bachra W/S Scheme in the district of North 24 Pgs. | BP-351-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.14 | 0 | 0 | 0
2996 | NORTH 24 PARGANAS | Barasat Division | Bachhra piped Water supply scheme , SM/12712 | New | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection within Bachra water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 541/HSD | 10/03/2025 | 10 | M/S SOURAV DAS | 0.72 | 0 | 0 | 0
2997 | NORTH 24 PARGANAS | Barasat Division | Bachhra piped Water supply scheme , SM/12712 | New | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection within Bachra water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 1477/HSD | 14/07/2025 | 10 | M/S SOURAV DAS | 0.72 | 0 | 0 | 0
2998 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-I to accommodate FHTC , SM/12123 | Augmentation | Material Requisition To Resource Division | 930/BD | 22/03/2023 | 0 | Resource Division | 86.74 | 0 | 0 | 0
2999 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-I to accommodate FHTC , SM/12123 | Augmentation | Material Requisition To Resource Division | 4508/BD | 28/11/2023 | 0 | Resource Division | 33.88 | 0 | 0 | 0
3000 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-I to accommodate FHTC , SM/12123 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Zone-I)(Rep.) and Pump house no-III (New) under Dakshin Bhebia W/S Scheme with Pump House No-I and II under Ramnagar W/S scheme District of 24 Pgs. (N) | 4808/EMD | 09/08/2023 | 30 | A.G ENTERPRISE. | 53.18 | 0 | 0 | 40
3001 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-I to accommodate FHTC , SM/12123 | Augmentation | Strengthening and improvement of RIDF road | BP-2024-25-220 | 02/09/2024 | 0 | EXECUTIVE ENGINEER (HPIU), WBSRDA ,BARASAT DIVISION | 45.3 | 0 | 0 | 0
3002 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-I to accommodate FHTC , SM/12123 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Construction of 600 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and providing Functional Household Tap Connection in connection with Augmentaion of Dakshin Bhebia water supply scheme (Zone-I), Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | 2593/BD | 28/08/2023 | 1097 | H.I.ENTERPRISE. | 937.45 | 684.96 | 73.07 | 65
3003 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-I to accommodate FHTC , SM/12123 | Augmentation | Acceptance cum work order for Surging and development of Big dia tubewell by Carrying out surging and back blowing of existing tube well including installation of suitable education pipes of adequate diameter upto required depth along with suitable airline pipes for injecting compressed air under pressure at the appropriates depth inside the tube well within Hasnabad Sub-Division PHE Dte. under Barasat Division P.H.E Dte. | 172/BD | 15/01/2025 | 240 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 30.65 | 0 | 0 | 60
3004 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-I to accommodate FHTC , SM/12123 | Augmentation | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Ph No.-1, 2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Dakshin Bhebia w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 3577/BD | 18/12/2024 | 90 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 77.52 | 6.46 | 8.33 | 68
3005 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-I to accommodate FHTC , SM/12123 | Augmentation | Acceptance cum work order for Construction of additional 1 no. switch room cum chlorine room (5.40x3.60) with sanitary and water supply arrangement including plinth protection in connection with augmentation of Dakshin Bhebia W/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 1024/BD | 28/03/2025 | 75 | ABDUR RAHIM GAZI | 7.49 | 0 | 0 | 0
3006 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-I to accommodate FHTC , SM/12123 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-II)(Rep.) under Dakshin Bhebia W/S Scheme District of 24 Pgs. (N) | 4719/EMD | 04/08/2023 | 30 | TRIO CONCERN | 27.16 | 15.54 | 62.64 | 60
3007 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bayra Water Supply Scheme at Bagdah Block under North 24 Pgs. W/S Division-I, P.H.E. Dte. (Phase-I). , SM/08732 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAYRA Water Supply Scheme at BAGDAH Block under North 24 Parganas water supply Division - I, PHE Dte (PHASE-I). | 851/NWSD-I | 07/10/2021 | 75 | A.K.C. SUPPLY & CONSTRUCTION | 82.11 | 82.21 | 100 | 1
3008 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bayra Water Supply Scheme at Bagdah Block under North 24 Pgs. W/S Division-I, P.H.E. Dte. (Phase-I). , SM/08732 | Retrofitting | Survey, Design and preparation of Retrofitting DPR in connection with Providing functional household tap connection to every Household under Bayra W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte. | 1175/NWSD-I | 31/12/2021 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.18 | 4.18 | 100 | 1
3009 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bayra Water Supply Scheme at Bagdah Block under North 24 Pgs. W/S Division-I, P.H.E. Dte. (Phase-I). , SM/08732 | Retrofitting | Continuation for Hiring of 1 (one) no. Motor Cab / Maxi Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer (HQ-I), North 24 Parganas W/S Division-I, P.H.E. Dte. for 61 (Sixty One) days w.e.f. 01.04.2023 to 31.05.2023.(Vehicle No.WB-25J-7778 ) | 364/NWSD-I | 31/03/2023 | 61 | GITA DAS | 0.29 | 0.71 | 100 | 90
3010 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bayra Water Supply Scheme at Bagdah Block under North 24 Pgs. W/S Division-I, P.H.E. Dte. (Phase-I). , SM/08732 | Retrofitting | Hiring of 1 (one) no. Motor Cab / Maxi Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer, North 24 Parganas W/S Sub-Division-I, P.H.E. Dte. for 6(Six) months, i.e. 184 days. [w.e.f. 01.05.2023 to 31.10.2023] (Car No.WB25K0619) | 502/NWSD-I | 27/04/2023 | 184 | M/S. SHUBHA ENTERPRISE | 0.87 | 1.42 | 100 | 70
3011 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bayra Water Supply Scheme at Bagdah Block under North 24 Pgs. W/S Division-I, P.H.E. Dte. (Phase-I). , SM/08732 | Retrofitting | Continuation order for the work of Hiring of 1 (one) no. Motor Cab / Maxi Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed it on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer, North 24 Parganas W/S Sub-Division-I, P.H.E. Dte. for 6(Six) months, i.e. 182 days. [w.e.f. 01.11.2023 to 30.04.2024] (Car No.WB25K0619) | 1646/NWSD-I | 16/10/2023 | 182 | M/S. SHUBHA ENTERPRISE | 0.86 | 0.62 | 249.48 | 67
3012 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Zafarpur Piped Water Supply Scheme at Basirhat-II Block (Phase-I) , SM/08645 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Zafarpur Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase - I) | 2461/BD | 15/12/2021 | 45 | SHIBU BISWAS. | 81.63 | 81.47 | 100 | 1
3013 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Zafarpur Piped Water Supply Scheme at Basirhat-II Block (Phase-I) , SM/08645 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for ZAFARPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 203/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.3 | 4.19 | 100 | 1
3014 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Zafarpur Piped Water Supply Scheme at Basirhat-II Block (Phase-I) , SM/08645 | Retrofitting | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Basirhat-II Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - B) | 150/BHTSD | 29/01/2025 | 20 | BIBHAS PAL. | 0.88 | 0 | 0 | 90
3015 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kshudra Mangalgathi, Mirzzapur, Swetpur, Daibagnapol, Mongal Nagar Noajispur, Bajitnagar, Mobarakpur & Bora Bisweswarpur m , SM/08653 | Retrofitting | Fomal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Kshudra Mangalgathi, Mirzzapur, Swetpur, Daibagnapol, Mongal Nagar, Noajispur, Bajitnagar, Mobarakpur & Bara Bisweswarpur mouzas (Part) within Sohai Swetpur Zone-I Water Supply Scheme at Deganga Block under Barasat Division, PHE Dte. Part-A Phase-I | 1975/BD | 26/10/2021 | 90 | H.I.ENTERPRISE. | 225.34 | 210.13 | 60.77 | 1
3016 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kshudra Mangalgathi, Mirzzapur, Swetpur, Daibagnapol, Mongal Nagar Noajispur, Bajitnagar, Mobarakpur & Bora Bisweswarpur m , SM/08653 | Retrofitting | Laying of UPVC pipe line at village Khudramangalgathi in connection with FHTC work under Sohai Swetpur Zone-I Water Supply Scheme within Barasat Sub Division, P.H.E.Dte. Sl.-1 | 309/BSD | 11/04/2022 | 7 | RAKESH ENTERPRISE. | 4.5 | 4.5 | 100 | 1
3017 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kshudra Mangalgathi, Mirzzapur, Swetpur, Daibagnapol, Mongal Nagar Noajispur, Bajitnagar, Mobarakpur & Bora Bisweswarpur m , SM/08653 | Retrofitting | Road restoration work at Kalitala More to Pump House no.-1 via Swetpur Bazar in connection with laying of distribution system of pipe line with Sohai Swetpur Water Supply Scheme Zone-I under Barasat Sub Division, P.H.E.Dte. Sl. No.-07 | 336/BSD | 12/04/2022 | 7 | SUN ENTERPRISE. | 4.58 | 4.58 | 100 | 1
3018 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kshudra Mangalgathi, Mirzzapur, Swetpur, Daibagnapol, Mongal Nagar Noajispur, Bajitnagar, Mobarakpur & Bora Bisweswarpur m , SM/08653 | Retrofitting | Road restoration work at Pump House no.-1 to Mirjapur High School via Pump House No.-2 in connection with laying of distribution system of pipe line with Sohai Swetpur Water Supply Scheme Zone-I under Barasat Sub Division, P.H.E.Dte. Sl. No.-08 | 337/BSD | 12/04/2022 | 7 | SUN ENTERPRISE. | 4.55 | 4.55 | 100 | 1
3019 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kshudra Mangalgathi, Mirzzapur, Swetpur, Daibagnapol, Mongal Nagar Noajispur, Bajitnagar, Mobarakpur & Bora Bisweswarpur m , SM/08653 | Retrofitting | Laying of UPVC pipe line at Culvert More towards Khudramangalgathi in connection with FHTC work under Sohai Swetpur Zone-I Water Supply Scheme within Barasat Sub Division, P.H.E.Dte. Sl. No.-02 | 310/BSD | 11/04/2022 | 7 | RAKESH ENTERPRISE. | 4.27 | 4.27 | 100 | 1
3020 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kshudra Mangalgathi, Mirzzapur, Swetpur, Daibagnapol, Mongal Nagar Noajispur, Bajitnagar, Mobarakpur & Bora Bisweswarpur m , SM/08653 | Retrofitting | Repairing & Renovation of 1 No. Pump House (P.H. No-II) and allied works at Sohai Swetpur Water Supply Scheme Zone-I under Barasat Sub-Division, P.H.E.Dte. Sl. No.-7 | 817/BSD | 10/12/2021 | 30 | JIBON BOSE. | 1.25 | 1.1 | 100 | 0
3021 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kshudra Mangalgathi, Mirzzapur, Swetpur, Daibagnapol, Mongal Nagar Noajispur, Bajitnagar, Mobarakpur & Bora Bisweswarpur m , SM/08653 | Retrofitting | Repairing & Renovation of 1 No. Pump House (Size- 5.20 x 7.20) of Head Work Site and allied works at Sohai Swetpur Water Supply Scheme Zone-I under Barasat Sub-Division, P.H.E.Dte. Sl. No.-6 | 816/BSD | 10/12/2021 | 30 | M/S S.HAQUE & CO. | 1.84 | 1.74 | 100 | 0
3022 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Rajapura water supply scheme under Hasnabad Block for providing Functional House Tap Connection , SM/07022 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Ghola, Rajapura and Chalitabaria Mouzas of Hasnabad Block from Rajapura Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. | 1881/B.Ar.D. | 18/12/2020 | 90 | UTPAL CONSTRUCTION AND CO | 96.59 | 61.47 | 83.52 | 1
3023 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Rajapura water supply scheme under Hasnabad Block for providing Functional House Tap Connection , SM/07022 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Muragachha, Harikati and Krishnapara Mouzas of Hasnabad Block from Krishnapara Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. ( Phase-I ) | 1884/B.Ar.D. | 18/12/2020 | 90 | UTPAL CONSTRUCTION AND CO | 83.3 | 100 | 200 | 1
3024 | NORTH 24 PARGANAS | Barasat Division | Chutkia Radhanagar Piped Water Supply Scheme , SM/13524 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (CHUTKIA RADHANAGAR Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | 271/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.85 | 0.85 | 100 | 1
3025 | NORTH 24 PARGANAS | Barasat Division | Chutkia Radhanagar Piped Water Supply Scheme , SM/13524 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (CHUTKIA RADHANAGAR Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 249/HSD | 03/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 4.82 | 100 | 0
3026 | NORTH 24 PARGANAS | Barasat Division | Chutkia Radhanagar Piped Water Supply Scheme , SM/13524 | New | Material Requisition To Resource Division | 883/BD | 22/03/2023 | 0 | Resource Division | 28.59 | 0 | 0 | 0
3027 | NORTH 24 PARGANAS | Eastern Mechanical | Chutkia Radhanagar Piped Water Supply Scheme , SM/13524 | New | New service connection for Chutkia PH-I, Chutkia sankardaha | BP-250-23-24 | 20/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.17 | 0 | 0 | 0
3028 | NORTH 24 PARGANAS | Eastern Mechanical | Chutkia Radhanagar Piped Water Supply Scheme , SM/13524 | New | New service connection for Chutkia PH-II, Chutkia Sankardaha | BP-251-23-24 | 20/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.84 | 0 | 0 | 0
3029 | NORTH 24 PARGANAS | Barasat Division | Chutkia Radhanagar Piped Water Supply Scheme , SM/13524 | New | Acceptance cum work order for Strengthing of existing concrete road for movement of rig machineries for sinking of big dia Tube well at PH No- 2 within Chutkia Radhanagar w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | 1128/HSD | 05/09/2023 | 7 | NURJAHAN ENTERPRISE. | 1.69 | 1.51 | 100 | 100
3030 | NORTH 24 PARGANAS | Barasat Division | Chutkia Radhanagar Piped Water Supply Scheme , SM/13524 | New | Acceptance cum work order for Construction of additional 1 no. switch room cum chlorine room (5.40x3.60) with sanitary and water supply arrangement including plinth protection at Chikar more end within Chutkia Radhanagar w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 111/BD | 09/01/2025 | 150 | TARUN KUMAR LAHA | 7.47 | 0 | 0 | 0
3031 | NORTH 24 PARGANAS | Barasat Division | Chutkia Radhanagar Piped Water Supply Scheme , SM/13524 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line,Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 150 cum capacity CWR , pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Chutkia Radhanagar w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1439/BD | 11/05/2023 | 692 | R.K.MANDAL & CO. | 290.05 | 222.19 | 83.14 | 100
3032 | NORTH 24 PARGANAS | Barasat Division | Chutkia Radhanagar Piped Water Supply Scheme , SM/13524 | New | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection within Chutkia Radhanagar water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 525/HSD | 10/03/2025 | 10 | M/S SOURAV DAS | 0.72 | 0 | 0 | 100
3033 | NORTH 24 PARGANAS | Barasat Division | Chutkia Radhanagar Piped Water Supply Scheme , SM/13524 | New | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection within Chutkia Radhanagar water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 1479/HSD | 14/07/2025 | 10 | M/S SOURAV DAS | 0.72 | 0 | 0 | 100
3034 | NORTH 24 PARGANAS | Barasat Division | Kachurhula Zone-I Piped Water Supply Scheme , SM/13522 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KACHURHULA Z-I Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte | 280/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.5 | 4.5 | 100 | 1
3035 | NORTH 24 PARGANAS | Barasat Division | Kachurhula Zone-I Piped Water Supply Scheme , SM/13522 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KACHURHULA Z-I Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte | 280/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.5 | 0 | 0 | 1
3036 | NORTH 24 PARGANAS | Barasat Division | Kachurhula Zone-I Piped Water Supply Scheme , SM/13522 | New | Acceptance cum work order for Sinking of 1 Nos. 300.00 mtr. Deep 100 X 50 mm. dia. Trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe & strainers at T/W site-1 for Kachurhula w/s scheme (Zone-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 1190/HSD | 22/09/2023 | 10 | ROY CHOWDHURY CONSTRUCTION. | 2.63 | 1.76 | 100 | 100
3037 | NORTH 24 PARGANAS | Barasat Division | Kachurhula Zone-I Piped Water Supply Scheme , SM/13522 | New | Material Requisition To Resource Division | 892/BD | 22/03/2023 | 0 | Resource Division | 17.66 | 0 | 0 | 0
3038 | NORTH 24 PARGANAS | Barasat Division | Kachurhula Zone-I Piped Water Supply Scheme , SM/13522 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-H). | 273/HSD | 06/03/2024 | 10 | S.M.TRADERS. | 0.88 | 0.88 | 100 | 100
3039 | NORTH 24 PARGANAS | Barasat Division | Kachurhula Zone-I Piped Water Supply Scheme , SM/13522 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 100 cum capacity CWR, pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Kachurhula w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1693/BD | 07/06/2023 | 731 | TRISHA ENTERPRISE & CO. | 166.1 | 72.97 | 43.93 | 16
3040 | NORTH 24 PARGANAS | Barasat Division | Kachurhula Zone-I Piped Water Supply Scheme , SM/13522 | New | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 250 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Kachurhula w/s scheme (Zone-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 553/BD | 22/02/2024 | 495 | SAHA CONSTRUCTION & CO | 33.41 | 0 | 0 | 50
3041 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa , SM/13547 | Retrofitting | Formal work order for Land development, Construction of Office cum Guard room and Switch cum Chlorine Room, Boundary wall, Surface drain and related allied works at Zonal Head work site - XV i.e. Bergum including Laying Distribution System within the jurisdiction of (Zone-XV) & Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Surface Water based Water Supply Scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoining Mouzas under North 24 Parganas District project under Habra Sub Division within Barasat Division, P.H.E. Dte. Habra-I Block PART-D. | 4046/BD | 13/10/2023 | 1095 | H.I.ENTERPRISE. | 1322.52 | 375 | 43.59 | 92
3042 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Chhota Sehara Piped water supply scheme , SM/14514 | Augmentation | Supply & delivery of submersible pump motor set and installed the same of P/H No. I & II under Chhota Sehara water supply scheme Dist- 24 Pgs(N). T.No. 110/SD I 23.24 Dt. 05.04.23 W.o. dt. 31.05.23 | 1332/SDI | 14/08/2022 | 30 | S.B.ENTERPRISE | 1.72 | 0 | 0 | 30
3043 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Chhota Sehara Piped water supply scheme , SM/14514 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. I & II under Chhoto Sehara W/S Scheme, Block-Sandeshkhali-I in District of 24 Pgs. (N) | 6754/EMD | 28/11/2023 | 30 | P.K. ENGINEERING | 22.29 | 0 | 0 | 0
3044 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Chhota Sehara Piped water supply scheme , SM/14514 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Chhoto Sehara Piped Water Supply Scheme under Barasat Division, PHE Dte. | 631/HSD | 08/04/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 2.78 | 2.78 | 100 | 0
3045 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Chhota Sehara Piped water supply scheme , SM/14514 | Augmentation | Formal work order for Laying of UPVC/DI distribution pipe line and providing Functional Household Tap Connection for Augmentation of Chotto Sehara water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 830/BD | 15/03/2023 | 90 | MONDAL & CO. (BASIRHAT). | 227.81 | 209.69 | 100 | 0
3046 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Chhota Sehara Piped water supply scheme , SM/14514 | Augmentation | Supply & delivery of submersible pump moter set and istalled the same of P/H No. I & II under Chhota Sehara water supply scheme Dist- 24 Pgs(N). | 1332/EMSD-I | 31/05/2023 | 15 | S.B.ENTERPRISE | 1.72 | 1.58 | 92.18 | 100
3047 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Chhota Sehara Piped water supply scheme , SM/14514 | Augmentation | Acceptance cum work order for Construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Chotto Sehara water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte | 1153/BD. | 12/04/2022 | 240 | S.S.ENTERPRISE. (BAMANGACHI) | 143.13 | 21.81 | 100 | 95
3048 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Chhota Sehara Piped water supply scheme , SM/14514 | Augmentation | Additional work in connection with Supply & delivery of submersible pump moter and installed the same at P H No. I & II of Chhota Sehara water supply scheme under Eastern Mechanical Sub Division-I, PHE Dte. Dist- 24 Pgs(N) | 1785/EMSD-I | 10/08/2023 | 7 | S.B.ENTERPRISE | 1.29 | 1.27 | 100 | 100
3049 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Chhota Sehara Piped water supply scheme , SM/14514 | Augmentation | Providing outdoor illumination arrangement at PH-I & II under chhota sehara W/S Scheme. | 744EMD | 14/03/2023 | 30 | M/S. G.P. ENTERPRISE | 2.17 | 2.17 | 50 | 90
3050 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Chhota Sehara Piped water supply scheme , SM/14514 | Augmentation | Material Requisition To Resource Division | 936/BD | 22/03/2023 | 0 | Resource Division | 28.95 | 0 | 0 | 0
3051 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Chhota Sehara Piped water supply scheme , SM/14514 | Augmentation | Acceptance cum work order for Construction of boundary wall with RCC column structure at head Work site (PH No-1 ) within Chotto Sehara w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 4380/BD | 10/11/2023 | 539 | M/S DATTA ENTERPRISE. | 27.13 | 0 | 0 | 100
3052 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Chhota Sehara Piped water supply scheme , SM/14514 | Augmentation | Formal work order for Additional laying of 160 mm dia. HDPE pipe line from old pump house no- 1 & 2 to near Roy para, protection works & other allied works within Kalinagar W/s scheme (Z-I), Sandeshkhali-I Block under Hasnabad Sub-Division P.H.E. Dte. | 3669/BD | 24/12/2024 | 270 | CHANCHAL ENTERPRISE & CO. | 163.96 | 0 | 0 | 60
3053 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Mohanpur w/s scheme (Z-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 794/BD | 13/03/2023 | 30 | M/S RAJPATH CONSTRUCTION. | 42.87 | 33.12 | 77.26 | 0
3054 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing Functional Household Tap Connection in Connection with Augmentation of Mohanpur water supply scheme (Zone-I), Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | 401/BD | 09/02/2023 | 90 | M/S PROGATI ENTERPRISE. | 306.25 | 293.07 | 100 | 1
3055 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing Functional Household Tap Connection in Connection with Augmentation of Mohanpur water supply scheme (Zone-II), Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | 404/BD | 09/02/2023 | 90 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 283.51 | 257.49 | 100 | 1
3056 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Mohanpur w/s scheme (Zone-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 787/BD | 13/03/2023 | 30 | M/S RAJPATH CONSTRUCTION. | 21.45 | 14.51 | 100 | 0
3057 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 250 mtr deep Tubewell by D.R. Rig method at PH No.-2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Mohanpur w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 2473/BD | 18/08/2023 | 30 | ABDUL ALIM MONDAL. | 16.45 | 13.27 | 100 | 100
3058 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Material Requisition To Resource Division | 917/BD | 22/03/2023 | 0 | Resource Division | 2.48 | 0 | 0 | 0
3059 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I)(Rep.) and Pump House No- I and II (New) (Zone-II) under Mohanpur W/S Scheme in the District of 24 Pgs. (N) NIET No. 34 of EE/EMD of 2022-23 (Sl. No. 08) | 1231/EMD | 24/03/2023 | 30 | ASHUTOSH DAS & CO. | 53 | 0 | 0 | 90
3060 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Mohanpur water supply scheme (Zone-I), Minakhan Block of Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | 4193/BD | 30/10/2023 | 365 | M/S RAJPATH CONSTRUCTION. | 114.56 | 0 | 0 | 0
3061 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Formal work order for Construction of 150 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Mohanpur Zone-II in connection with Augmentation of Mohanpur water supply scheme (Zone-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 2275/BD | 12/08/2024 | 365 | M/S B.K.ENTERPRISE. | 100.39 | 0 | 0 | 0
3062 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 (Size-3.60x3.00 mtr.) for Augmentation of Mohanpur w/s scheme (Z-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 1441/BD | 11/05/2023 | 60 | ROYAL CONSTRUCTION | 16.03 | 15.09 | 100 | 62
3063 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Acceptance cum work order for Laying of 150 mm dia. DI rising main from Uttar Kalibari Adhikary House to PH No- 2 within Mohanpur w/s scheme (Z-II), Minakhan Block under Hasnabad Sub- Division P.H.E. Dte. | 806/HSD | 13/07/2023 | 7 | SARKAR ENTERPRISE | 0.9 | 0.9 | 100 | 100
3064 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Acceptance cum work order for 2 no. pump connection at PH No.-1 & 2 in connection with Augmentation for Mohanpur water supply scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 868/HSD | 07/08/2024 | 7 | ANKUSH CONSTRUCTION & CO. | 1.17 | 1.05 | 100 | 100
3065 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Acceptance cum work order for Laying of 150 mm dia. DI rising main from PH No-1 to Uttar Kalibari Adhikary House within Mohanpur w/s scheme (Z-II), Minakhan Block under Hasnabad Sub- Division P.H.E. Dte. | 803/HSD | 13/07/2023 | 7 | SARKAR ENTERPRISE | 0.98 | 0.97 | 100 | 100
3066 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Quotation for Service Connection Charges for PH- I, Zone-II under Mohanpur W/S Scheme in the district of North 24 Pgs. | BP-84-24-25 | 09/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.47 | 0 | 0 | 0
3067 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Quotation for Service Connection Charges for PH- II, Zone-II under Mohanpur W/S Scheme in the district of North 24 Pgs. | BP-363-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.03 | 0 | 0 | 0
3068 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Acceptance cum work order for Protection work by bamboo piling in different places in connection with augmentation of Mohanpur w/s scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 309/HSD | 04/02/2025 | 10 | SARKAR ENTERPRISE | 0.94 | 0 | 0 | 100
3069 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Mohanpur w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 310/HSD | 04/02/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.81 | 0 | 0 | 100
3070 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Kalibari and Tangramari in connection with augmentation of Mohanpur w/s scheme (Z-II), Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | 373/HSD | 10/02/2025 | 10 | SARKAR ENTERPRISE | 0.96 | 0 | 0 | 100
3071 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places in connection with augmentation of Mohanpur w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 374/HSD | 10/02/2025 | 10 | ANKUSH CONSTRUCTION & CO. | 0.32 | 0 | 0 | 100
3072 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Acceptance cum work order for Protection work by bamboo piling in different places of Kalibari in connection with augmentation of Mohanpur w/s scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 375/HSD | 10/02/2025 | 10 | SARKAR ENTERPRISE | 0.94 | 0 | 0 | 100
3073 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Acceptance cum work order for 2 no. pump connection at PH No.-1 & 2 in connection with Augmentation for Mohanpur water supply scheme (Z-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 867/HSD | 07/08/2024 | 7 | SARKAR ENTERPRISE & CO. | 1.17 | 0 | 0 | 100
3074 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Mohanpur , SM/14151 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Mohanpur w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 477/HSD | 28/02/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.81 | 0 | 0 | 100
3075 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. III (Rep.) under Chandrapur W/S Scheme District of 24 Pgs. (N) N.I.E.T No. 27 of EE / EMD of 2022-2023 (2022_PHED_431015_13) | 6729/EMD | 28/11/2023 | 30 | EASTERN INDIA SALES & SERVICE | 13.23 | 0 | 0 | 0
3076 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Material Requisition To Resource Division | 4022/BD | 12/10/2023 | 0 | Resource Division | 55.3 | 0 | 0 | 0
3077 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Material Requisition To Resource Division | 1276/BD | 25/04/2023 | 0 | Resource Division | 208.17 | 0 | 0 | 0
3078 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Different works in connection with Augmentation Chandrapur PWSS (1st Tubewell - Pump House). | 562/BSD | 09/09/2024 | 20 | JIBON BOSE. | 2.95 | 0 | 0 | 0
3079 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Different works in connection with Augmentation Chandrapur PWSS (3rd Tubewell - Boundary Wall & Service Road). | 565/BSD | 09/09/2024 | 20 | SUN ENTERPRISE. | 3.78 | 0 | 0 | 0
3080 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Hiring 1(One) No. Diesel Luxury Car on Daily basis. (for 6 months from w.e.f. 01.12.2023) for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. | 857/BSD | 29/11/2023 | 183 | MADHAB CHANDRA DAS | 0.87 | 1.98 | 227.89 | 0
3081 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Construction of New Pump House (Charkhara Mouza) with latrine at Chandrapur Water Supply Scheme under Barasat-I Block, size of 3.00m x 3.60m with latrine within Barasat Sub Division, P.H.E.Dte. | 1241/BSD | 15/03/2024 | 31 | S.MUKHERJEE. | 4.18 | 0 | 0 | 0
3082 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Different works in connection with Augmentation Chandrapur PWSS (1st Tubewell - Boundary Wall & Service Road). | 561/BSD | 09/09/2024 | 20 | S.MUKHERJEE. | 4.1 | 0 | 0 | 0
3083 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Preparation of DPR in connection of augumentation of Chandrapur Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | 456/BSD | 20/05/2022 | 30 | RADIANT | 4.58 | 0 | 0 | 100
3084 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Construction of Culvert at Pump House - V of Chandrapur W/S Scheme under Barasat Sub. Division, PHE Dte. | 509/BSD | 30/08/2024 | 15 | S.MUKHERJEE. | 0.86 | 0.81 | 100 | 100
3085 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Barasat-I Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-A | 1121/BSD | 09/02/2024 | 4 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
3086 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Construction of New Pump House (Digha Mouza) with latrine at Chandrapur Water Supply Scheme under Barasat-I Block, size of 3.00m x 3.60m with latrine within Barasat Sub Division, P.H.E.Dte. | 166/BSD | 07/06/2024 | 30 | JIBON BOSE. | 4.18 | 3.95 | 100 | 100
3087 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | New service connection at P.H.No- III of Chandrapur water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). | BP-280-23-24 | 07/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.49 | 0 | 0 | 0
3088 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | New service connection at P.H.No- II of Chandrapur water supply scheme under EMSD-I ,PHE Dte .im24Pgs(N). | BP-279-23-24 | 07/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.96 | 0 | 0 | 0
3089 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.IV and V (New) under Chandrapur W/S Scheme District of 24 Pgs. (N) | 4750/EMD | 07/08/2023 | 603 | D.K. ELECTRIC | 26.48 | 4.67 | 17.64 | 40
3090 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Formal work order for Construction of 1200cum capacity 20mtr.Height R.C.C Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and Providing FHTC for Augmentation of Chandrapur Water Supply Scheme under Barasat Sub-Division, P.H.E. Dte. | 3062/BD | 09/10/2023 | 1027 | MONDAL ENTERPRISE. (BARASAT) | 1459.09 | 462.91 | 31.73 | 46
3091 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Formal work order for Additional pipeline and other allied works as per revised LDS in connection with Augmentation of Chandrapur Water Supply Scheme under JJM programme in Barasat-I block within Barasat Sub Division, P.H.E.Dte. | 2004/BD | 18/07/2024 | 630 | KINGS & CO. | 682.84 | 100 | 14.64 | 34
3092 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Formal work order for road restoration work damaged during pipe laying work under JJM in different water supply scheme under Barasat-I and Amdanga Block under Barasat Division P.H.E.Dte. | 1306/BD | 24/04/2025 | 120 | PIYALI CONSTRUCTION & GENERAL ORDER SUPPLIER | 99.64 | 0 | 0 | 0
3093 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Different works in connection with Augmentation Chandrapur PWSS (3rd Tubewell - Pump House). | 566/BSD | 09/09/2024 | 20 | B. S. ENTERPRISE (BANAMALIPUR) | 2.33 | 0 | 0 | 100
3094 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Different works in connection with Augmentation Chandrapur PWSS (2nd Tubewell - Pump House). | 564/BSD | 09/09/2024 | 20 | M/S SANKAR ENTERPRISE. | 2.93 | 0 | 0 | 100
3095 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Different works in connection with Augmentation Chandrapur PWSS (2nd Tubewell - Boundary Wall & Service Road). | 563/BSD | 09/09/2024 | 20 | M/S DAS & CO. | 2.65 | 0 | 0 | 100
3096 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Acceptance cum work order for Sinking of 1 no. 250mm. X 150mm.dia. 220.00mtr. deep tubewell by direct rotary rig method, having 250mm.dia. 42.0mtr. long UPVC housing pipe & 150mm.dia. 30.0mtr. long filter at Digha Mouza for Augmentation of Chandrapur Water Supply Scheme at 5th Tubewell Site under Barasat Sub-Division, P.H.E. Dte. | 2196/BD | 05/08/2024 | 240 | SUBHAJIT SAHA | 11.55 | 0 | 0 | 100
3097 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Acceptance cum work order for Sinking of 1 no. 250mm. X 150mm.dia. 220.00mtr. deep tubewell by direct rotary rig method, having 250mm.dia. 42.0mtr. long UPVC housing pipe & 150mm.dia. 30.0mtr. long filter at Charkhara Mouza for Augmentation of Chandrapur Water Supply Scheme at 4th Tubewell Site under Barasat Sub-Division, P.H.E. Dte. | 2301/BD | 14/08/2024 | 191 | JOY GURU ENTERPRISE | 11.55 | 0 | 0 | 100
3098 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC , SM/14161 | Augmentation | Emergent filling with silver sand at 4th tubewell site of Chandrapur Water Supply Scheme due to collapse during boring of deep tubewell under Barasat Sub Division, P.H.E. Dte. | 1113/BSD | 30/01/2025 | 7 | JOY GURU ENTERPRISE | 0.45 | 0 | 0 | 100
3099 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of CHAMPAPUKURIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08658 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Champapukuria Water Supply Scheme at Basirhat-II Block under Barasat Division, PHE Dte. (Phase-I). | 1651/BD | 07/09/2021 | 45 | UTPAL CONSTRUCTION & CO. | 71.61 | 70.23 | 98.07 | 1
3100 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of CHAMPAPUKURIA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08658 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for CHAMPAPUKURIA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 344/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.43 | 3.42 | 100 | 1
3101 | NORTH 24 PARGANAS | Barasat Division | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota , SM/13984 | Augmentation | Material Requisition To Resource Division | 2093/BD | 18/07/2023 | 0 | Resource Division | 12.63 | 0 | 0 | 0
3102 | NORTH 24 PARGANAS | Barasat Division | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota , SM/13984 | Augmentation | Material Requisition To Resource Division | 1862/BD | 23/06/2023 | 0 | Resource Division | 12.63 | 0 | 0 | 0
3103 | NORTH 24 PARGANAS | Barasat Division | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota , SM/13984 | Augmentation | Hiring of Luxury Car (Diesel) for the office use of the Assistant Engineer Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | 87/Bon | 30/01/2024 | 182 | ROY ENGINEERS. | 0.86 | 1.8 | 208.2 | 0
3104 | NORTH 24 PARGANAS | Barasat Division | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota , SM/13984 | Augmentation | Hiring of an Additional Vehicle (Diesel) for the site inspection of different ongoing schemes under JJM Program at Bongaon Sub-Division, P.H.E.Dte. | 484/Bon | 30/06/2023 | 184 | VAI ENTERPRISE. | 0.87 | 1.78 | 203.61 | 100
3105 | NORTH 24 PARGANAS | Barasat Division | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota , SM/13984 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Gangrapota(Additional) Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 2030/BD | 13/07/2023 | 90 | RAJ KUMAR MONDAL | 175.4 | 174.09 | 100 | 70
3106 | NORTH 24 PARGANAS | Barasat Division | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota , SM/13984 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Gangrapota Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | 2928/BD | 26/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.13 | 5.21 | 100 | 100
3107 | NORTH 24 PARGANAS | Barasat Division | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota , SM/13984 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household of Kundipur, Kundipur Jalkar and Keutipara mouza including laying of UPVC pipe under Augmentation work at additional Gangrapota & Gangrapota W/S Scheme, Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1650/BD | 21/05/2025 | 90 | REAL TIME | 43.26 | 0 | 0 | 0
3108 | NORTH 24 PARGANAS | Barasat Division | Additional detail project report for augmentation of Ground water based PWSS for Gangrapota , SM/13984 | Augmentation | Acceptance cum work order for Repairing and renovation works for 450 cum. capacity 20mtr. Staging height R.C.C. Over Head water Reservoir for Augmentation of Gangrapota Water Supply Scheme,Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1537/BD | 07/06/2024 | 270 | MONDAL ENTERPRISE. (BARASAT) | 18.37 | 0 | 0 | 100
3109 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah , SM/10786 | Augmentation | Material Requisition To Resource Division | 3410/BD | 22/11/2022 | 0 | Resource Division | 7.9 | 0 | 0 | 0
3110 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah , SM/10786 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system with in command area at Sindrani (Zone-II) Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation). | 1649/BD | 09/06/2022 | 90 | MONDAL ENTERPRISE. (BARASAT) | 324.72 | 324.48 | 99.93 | 1
3111 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah , SM/10786 | Augmentation | Acceptance cum wok order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Sindrani (Zone-II) water supply scheme (2nd T/W site) under Bongaon Sub-Division P.H.E.Dte. | 3623/BD | 12/12/2022 | 15 | NADIA TUBEWELLS | 15.07 | 12.82 | 100 | 0
3112 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah , SM/10786 | Augmentation | Continuation order for one motor launch (M.V. JOYMAKALI) on daily hire basis for use of Hasnabad Sub-Division, P.H.E. Dte. Period : 01.03.22 to 31.08.22=184 days. | 386/HSD | 28/02/2022 | 184 | SUSMITA MANDAL. | 2.74 | 8.87 | 100 | 100
3113 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah , SM/10786 | Augmentation | Construction of Approach Road Head Work at site for Augmentation of Sindrani (Zone-II) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 790/Bon | 10/10/2023 | 15 | UPWARDS ENGINEERING PRIVATE LIMITED | 3.53 | 3.53 | 100 | 100
3114 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah , SM/10786 | Augmentation | Material Requisition To Resource Division | 1669/BD | 13/06/2022 | 0 | Resource Division | 14.85 | 0 | 0 | 0
3115 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah , SM/10786 | Augmentation | Hiring of Vehicle for the (Diesel) for the office use as well as sites inspection of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Barasat Division P.H.E. Dte. Period from 01.01.2023 to 31.06.2023. for 6 (six) months. | 676/BON | 30/12/2022 | 182 | VAI ENTERPRISE. | 0.86 | 2.09 | 100 | 100
3116 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah , SM/10786 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Sindrani (Zone - II) Water Supply Scheme (H/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | 2922/BD | 26/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.1 | 14.08 | 100 | 100
3117 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah , SM/10786 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Sindrani (Zone-II) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 522/BD | 20/02/2024 | 30 | A.D.ENTERPRISE. | 16.87 | 16.86 | 100 | 100
3118 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah , SM/10786 | Augmentation | Health assessment of existing OHR of Sindrani (Zone-II) PWSS (135 cum) and ancillary structures, Bagdah Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 686/Bon | 07/06/2024 | 15 | RISHAN ENGINEERING CONSULTANCY | 2.91 | 2.91 | 100 | 100
3119 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah , SM/10786 | Augmentation | Construction of 3.60 mtr. X 3.00mtr. size Switch room with sanitary and water supply arrangement incl. plinth protection at 2nd Tube Well site at Sindrani w/s scheme (Zone-II), Bagdah block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | 209/Bon | 27/02/2024 | 45 | SAMBHU RAY CHOWDHURY. | 4.41 | 4.4 | 100 | 100
3120 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah , SM/10786 | Augmentation | New service connection at P.H.No- II ,Zone -II of Sindrani water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). | BP-95-24-25 | 29/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.06 | 0 | 0 | 0
3121 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sindrani (Zone-II) to accommodate FHTC, Block - Bagdah , SM/10786 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of DI pipe Rising Main, Distribution UPVC pipe line and Tube Well Connection under Augmentation work at Sindrani W/S Scheme (Zone - II) Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1767/BD | 01/07/2024 | 270 | M/S SUKANTA ENTERPRISE. | 18.13 | 0 | 0 | 100
3122 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Mathurabil Zone-III in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. , SM/19110 | Augmentation | Material Requisition To Resource Division | 2181/BD | 02/08/2024 | 0 | Resource Division | 13.02 | 0 | 0 | 0
3123 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Mathurabil Zone-III in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. , SM/19110 | Augmentation | Material Requisition To Resource Division | 2181/BD | 02/08/2024 | 0 | Resource Division | 17.29 | 0 | 0 | 0
3124 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Mathurabil Zone-III in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. , SM/19110 | Augmentation | Acceptance cum Work Order for Restoration of bituminious road from Nagdaha Adibansipara more to Shibtala in Majhipara Palashi G.P within Barrackpore -I Block for repairing of damage of bituminous road in connection with Mathurabil water supply project (Zone I,II,III) of J.J.M. under Barrackpore-I Sub-Division of Barasat Division P.H.E. Dte. | 95/BKP | 24/03/2025 | 15 | CHOWDHURY CONSTRUCTION. | 2.26 | 0 | 0 | 100
3125 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Mathurabil Zone-III in Barrackpore-I Block of North 24 Parganas District under Barasat Division, P.H.E.Dte. , SM/19110 | Augmentation | Acceptance cum Work Order for Restoration of bituminious road from Shibtala to Tarikhana more in Majhipara Palashi G.P. within Barrackpore-1 Dev. Block for repairing of damages in bituminous roads in connection with Mathurabil water supply project (Zone-I,II,III) of J.J.M. under Barrackpore Sub-Division of Barasat Division , P.H.E. Dte. | 96/BKP | 24/03/2025 | 15 | M/S RANA ENTERPRISE. | 4.41 | 0 | 0 | 100
3126 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC , SM/10375 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Sindrani(ZI&II) water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 594/BON | 22/12/2021 | 21 | GHOSH CONSTRUCTION. | 2.52 | 2.34 | 100 | 1
3127 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC , SM/10375 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II(Z-I) under Sindrani W/S Scheme District of 24 Pgs. (N) (Block- Baduria). NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.- 11) | 6148 /EMD | 14/08/2022 | 30 | DIPALI CONSTRUCTION | 15 | 0 | 0 | 0
3128 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC , SM/10375 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under Sindrani W/S Scheme District of 24 Pgs. (N) | 6148 / EMD | 14/08/2022 | 30 | DIPALI CONSTRUCTION | 12.81 | 9.06 | 70.76 | 0
3129 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC , SM/10375 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I Z-I under Sindrani W/S Scheme District of 24 Pgs. (N) | 6147 / EMD | 14/08/2022 | 30 | RAKA ENTERPRISE | 12.85 | 11.96 | 93.06 | 1
3130 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC , SM/10375 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system with in command area at Sindrani (Zone-I) Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation). | 1210/BD | 21/04/2022 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 299.02 | 42.84 | 15.12 | 1
3131 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC , SM/10375 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Sindrani (Zone-I) water supply scheme (Head Works site) under Bongaon Sub-Division P.H.E.Dte. | 3622/BD | 12/12/2022 | 15 | NADIA TUBEWELLS | 15.06 | 12.32 | 100 | 0
3132 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC , SM/10375 | Augmentation | Supply, delivery and fitting fixing of change over switch, cable etc. at pump house no. I (Z-I), under Sindrani W/S Scheme in connection with FHTC. | 1773/EMSD-I | 10/08/2023 | 10 | RAKA ENTERPRISE | 2.39 | 0 | 0 | 100
3133 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC , SM/10375 | Augmentation | Material Requisition To Resource Division | 1364/BD | 13/05/2022 | 0 | Resource Division | 33.31 | 0 | 0 | 0
3134 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC , SM/10375 | Augmentation | Material Requisition To Resource Division | 1675/BD | 13/06/2022 | 0 | Resource Division | 16.72 | 0 | 0 | 0
3135 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC , SM/10375 | Augmentation | Material Requisition To Resource Division | 2374/BD | 12/08/2022 | 0 | Resource Division | 60.89 | 0 | 0 | 0
3136 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC , SM/10375 | Augmentation | Health assessment of existing OHR of Sindrani (Zone-I) PWSS (135 cum) and ancillary structures, Bagdah Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 685/Bon | 07/06/2024 | 15 | RISHAN ENGINEERING CONSULTANCY | 3.12 | 3.12 | 100 | 100
3137 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Sindrani Zone-I to accommodate FHTC , SM/10375 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe and tube well connection under Augmentation work at Sindrani W/S Scheme (Zone - I) Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1766/BD | 01/07/2024 | 15 | ONKAR ENTERPRISE. | 19.03 | 0 | 0 | 100
3138 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate , SM/10530 | Augmentation | Material Requisition To Resource Division | 3799/BD | 22/12/2022 | 0 | Resource Division | 90.58 | 0 | 0 | 0
3139 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate , SM/10530 | Augmentation | Material Requisition To Resource Division | 3107/BD | 18/10/2022 | 0 | Resource Division | 9.23 | 0 | 0 | 0
3140 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate , SM/10530 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) and III(New) (Zone-II) under Durgapur-Baylani W/S Scheme with P/H-I, II and III(any 2 nos) under Kankpul W/S Scheme in District of 24 Pgs. (N) NIET No.- 32 of EE/EMD of 2022-23 (Sl. No.- 09) | 1285/EMD | 28/03/2023 | 30 | BENGAL CONSTRUCTION | 60.96 | 0 | 0 | 40
3141 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate , SM/10530 | Augmentation | Continuation work order Hiring of 1 no. of Diesel Luxury Car (Euro - IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer, For supervision of J.J.M. related work, executed within the entire Jurisdiction of Habra Sub-Division, under Barasat Division P.H.E. Dte.(For the period from: 01.03.2024 to 31.08.24) | 211/HAB | 28/02/2024 | 182 | M/S SUKANTA ENTERPRISE. | 0.87 | 1.97 | 225.63 | 0
3142 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate , SM/10530 | Augmentation | Acceptance cum work order for construction of Service Road(15 Mtr. Length X 2 Mtr. Width) for Pump House No:2 of Kankpul Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 169/HAB | 19/02/2024 | 15 | M/S LATIKA CONSTRUCTION. | 0.92 | 0 | 0 | 0
3143 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate , SM/10530 | Augmentation | Special repair & renovation of pump house and other Allied Works for Pump House No - 2 of Kankpul W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 930/HAB | 05/11/2024 | 20 | VAI ENTERPRISE. | 2.6 | 0 | 0 | 0
3144 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate , SM/10530 | Augmentation | Acceptance cum work order for Construction of Boundary Wall (75 m Length) for Pump House No - 3 of Kankpul water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | 2581/BD | 05/09/2024 | 45 | NEW MA TARA ENTERPRISE. | 11.91 | 0 | 0 | 0
3145 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate , SM/10530 | Augmentation | Construction of Service Road (35 Mtr. Length X 2 Mtr. Width) for Pump House No:3 of kankpul Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 694/HAB | 25/07/2024 | 10 | DEBASISH SARKAR. | 2.14 | 0 | 0 | 0
3146 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate , SM/10530 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Kankpul Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 2678/BD | 08/09/2022 | 90 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 328.95 | 288.55 | 100 | 1
3147 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate , SM/10530 | Augmentation | Acceptance cum work order for Hiring Petrol Luxury Car on Daily basis (from20.08.2024 to 28.02.2025) for the office use of the Assistant Engineer(HQ), Barasat Division, PHE Dte | 2341/BD | 16/08/2024 | 193 | M/S B.K.ENTERPRISE. | 0.92 | 1.97 | 215.08 | 0
3148 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate , SM/10530 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 250 mm. x 150 mm. dia. 270 mtr deep tube well by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 for Augmentation of Kankpul water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | 2775/BD | 11/09/2023 | 583 | B.M.ENGINEERING. & CONSTRUCTION. | 28.92 | 0 | 0 | 100
3149 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate , SM/10530 | Augmentation | Special repair & renovation of pump house and other Allied Works for Pump House No - 1 of Kankpul W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 924/HAB | 05/11/2024 | 20 | VAI ENTERPRISE. | 2.66 | 0 | 0 | 100
3150 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kankpul to accommodate , SM/10530 | Augmentation | Acceptance cum work order for Construction of Boundary Wall for Pump House No - 2 of Kankpul water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | 3064/BD | 25/10/2024 | 40 | SANTU GHOSH. | 6.61 | 0 | 0 | 100
3151 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC , SM/12124 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.III and IV(Rep) under Hasnabad W/S Scheme District of 24 Pgs. (N) | 1972/EMD | 07/06/2023 | 30 | GHOSE ENGINEERING SYNDICATE | 26.5 | 10.61 | 40.02 | 50
3152 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC , SM/12124 | Augmentation | Acceptance cum work order for Providing Functional tap connection at Rameswarpur Union Adarsha Bidyalaya at Rameswarpur in connection with augmentation of Hasnabad w/s scheme, Hasnabad block under Hasnabad Sub- Division P.H.E. Dte. | 1050/HSD | 01/09/2023 | 10 | SARKAR ENTERPRISE | 0.6 | 0 | 0 | 0
3153 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC , SM/12124 | Augmentation | Acceptance cum work order for Construction of boundary wall at North side for damaged portion, construction of approach road & other allied works at PH No-2 within Hasnabad w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 821/HSD | 14/07/2023 | 10 | SARKAR ENTERPRISE | 3.87 | 3.87 | 100 | 100
3154 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC , SM/12124 | Augmentation | Acceptance cum work order for Construction of approach road, North side boundary wall & other allied works at PH no-1 within Hasnabad w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 820/HSD | 14/07/2023 | 21 | ABDUL ALIM MONDAL. | 2.73 | 2.69 | 100 | 100
3155 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC , SM/12124 | Augmentation | Material Requisition To Resource Division | 932/BD | 22/03/2023 | 0 | Resource Division | 221.49 | 0 | 0 | 0
3156 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC , SM/12124 | Augmentation | Acceptance cum work order for Arrangement Of Block Level Orientation programe involving stakeholders of PRI bodies including refreshments, training materials and related activities for 2 nos Blocks ( Hasnabad & Hingalganj) in North 24 Parganas under Barasat Division, P.H.E Dte. | 754/HSD | 19/07/2024 | 10 | IMAGIN | 0.98 | 0.98 | 100 | 100
3157 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC , SM/12124 | Augmentation | Formal work order for "Laying of DI rising main, DI/UPVC distribution pipe line, Construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and providing Functional Household Tap Connection in connection with Augmentaion of Hasnabad water supply scheme, Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | 2601/BD | 28/08/2023 | 582 | M/S S.S.ENTERPRISE. (SOUTH) | 793.69 | 378.08 | 47.64 | 70
3158 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC , SM/12124 | Augmentation | Acceptance cum work order for Withdrawing, relaying of different dia. UPVC pipe line at Chaktangramari para in connection with augmentation of Hasnabad water supply scheme under Hasnabad Sub-Division, P.H.E.Dte. | 1005/HSD | 04/06/2025 | 10 | SARKAR ENTERPRISE | 0.95 | 0 | 0 | 0
3159 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC , SM/12124 | Augmentation | Acceptance cum work order for Withdrawing, relaying of different dia. UPVC pipe line at Pal para in connection with augmentation of Hasnabad water supply scheme under Hasnabad Sub-Division, P.H.E.Dte. | 1486/HSD | 14/07/2025 | 10 | SARKAR ENTERPRISE | 0.96 | 0 | 0 | 100
3160 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC , SM/12124 | Augmentation | Acceptance cum work order for Withdrawing and relaying of 90mm dia. UPVC pipe line at Barajpur in connection with augmentation of Hasnabad W/S scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 950/HSD | 29/05/2025 | 10 | SARKAR ENTERPRISE | 0.94 | 0 | 0 | 100
3161 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC , SM/18416 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. III (Zone-I) (Rep.) under Bodai W/S Scheme District of 24 Pgs. (N) N.I.E.T No. 27 of EE / EMD of 2022-2023 (2022_PHED_431015_9) | 6727/EMD | 28/11/2023 | 30 | S.G. ENTERPRISE | 13.13 | 0 | 0 | 0
3162 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC , SM/18416 | Augmentation | Material Requisition To Resource Division | 3094/BD | 10/10/2023 | 0 | Resource Division | 26.86 | 0 | 0 | 0
3163 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC , SM/18416 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. III (Zone-II) (Rep.) under Bodai W/S Scheme District of 24 Pgs. (N) N.I.E.T No. 27 of EE / EMD of 2022-2023 (2022_PHED_431015_10) | 6728/EMD | 28/11/2023 | 30 | DEY ENTERPRISE | 13.15 | 0 | 0 | 0
3164 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC , SM/18416 | Augmentation | Preparation of DPR in connection of augumentation of Bodai Water Supply Scheme Zone-I under Barasat Sub Division, P.H.E. Dte. Sl. No.-01 | 548/BSD | 29/06/2022 | 30 | RADIANT | 3.7 | 3.32 | 100 | 100
3165 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC , SM/18416 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Amdanga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-B | 1116./1/BSD | 09/02/2024 | 4 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
3166 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC , SM/18416 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Amdanga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-A | 1116/BSD | 09/02/2024 | 4 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 89
3167 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC , SM/18416 | Augmentation | Formal work order for Construction of 900 cum capacity 20mtr Height R.C.C Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentation of Bodai Zone-I Water Supply Scheme under Barasat Sub-Division P.H.E.Dte. | 3080/BD | 10/10/2023 | 722 | PUSPA ENTERPRISE. | 1051.63 | 444.01 | 42.22 | 64
3168 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC , SM/18416 | Augmentation | Hiring 1(One) No. Diesel Luxury Car on Daily basis. (for 6 (six) months from w.e.f. 01.06.2024) for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. @ Rs. 475.00 (Rupees four hundred & seventy five only) per day Excluding fuel. (Period for 01/06/2024 to 30/11/2024) | 140/BSD | 28/05/2024 | 184 | MADHAB CHANDRA DAS | 0.87 | 1.88 | 216.66 | 0
3169 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC , SM/18416 | Augmentation | Formal work order for Additional pipeline and other allied works as per revised LDS in connection with Augmentation of Bodai-I Water Supply Scheme under JJM programme in Amdanga block within Barasat Sub Division, P.H.E.Dte. | 2580/BD | 05/09/2024 | 90 | A.P POWER & CONCRETE | 325.89 | 0 | 0 | 0
3170 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC , SM/18416 | Augmentation | Formal work order for road restoration work damaged during pipe laying work under JJM in different water supply scheme under Barasat-I and Amdanga Block under Barasat Division P.H.E.Dte. | 1306/BD | 24/04/2025 | 120 | PIYALI CONSTRUCTION & GENERAL ORDER SUPPLIER | 99.64 | 0 | 0 | 0
3171 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC , SM/18416 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-IV , V Zone-I under Bodai ground water based water supply scheme under Block_ Amdanga Dist. - North 24PGS under EMD, PHE Dte. | 804/EMD | 11/03/2024 | 508 | ESENCE ENGINEERING CONCERN | 25.37 | 0 | 0 | 100
3172 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC , SM/18416 | Augmentation | Acceptance cum work order for Sinking of 1 no. 250mm. X 150mm.dia. 220.00mtr. deep tubewell by direct rotary rig method, having 250mm.dia. 42.0mtr. long UPVC housing pipe & 150mm.dia. 30.0mtr. long filter for Augmentation of Bodai Zone-I Water Supply Scheme at 3rd Tubewell Site under Barasat Sub-Division, P.H.E. Dte. | 3585/BD | 18/12/2024 | 90 | M/S K.P.PAL. | 11.56 | 0 | 0 | 100
3173 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV/A (Tentulia) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11921 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-IV/A (Tentulia) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 422/NWSD-I | 01/04/2022 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.9 | 4.9 | 100 | 1
3174 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV/A (Tentulia) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11921 | Augmentation | Material Requisition To Resource Division | 489/NWSD-I | 26/04/2023 | 0 | Resource Division | 1.09 | 0 | 0 | 0
3175 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV/A (Tentulia) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11921 | Augmentation | Material Requisition To Resource Division | 1717/NWSD-I | 26/11/2024 | 0 | Resource Division | 11.7 | 0 | 0 | 0
3176 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV/A (Tentulia) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11921 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 186.71 | 30.09 | 2
3177 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV/A (Tentulia) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11921 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1431/NWSD-I | 18/09/2024 | 7 | IMAGIN | 4.59 | 0 | 0 | 95
3178 | NORTH 24 PARGANAS | NTK Mechanical | TARULIA Piped Water Supply Scheme , SM/18598 | New | Supply & Installation of pumping machineries & other electro-mechanical accessories in Tarulia piped W/S scheme under New Town Kolkata Mechanical Division, P.H.E. Dte. | 2134/NTKMD | 11/08/2023 | 180 | AHALYA ENGINEERING WORKS | 73.96 | 0 | 0 | 0
3179 | NORTH 24 PARGANAS | Barasat Arsenic Division | TARULIA Piped Water Supply Scheme , SM/18598 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 3rd Pump House site of Tarulia Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1947/B.Ar.D. | 14/08/2023 | 45 | ACME CONSTRUCTION | 18.27 | 0 | 0 | 0
3180 | NORTH 24 PARGANAS | Barasat Arsenic Division | TARULIA Piped Water Supply Scheme , SM/18598 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at Head Work site of Tarulia Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1945/B.Ar.D. | 14/08/2023 | 45 | ACME CONSTRUCTION | 18.27 | 0 | 0 | 0
3181 | NORTH 24 PARGANAS | Barasat Arsenic Division | TARULIA Piped Water Supply Scheme , SM/18598 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 2nd Pump House site of Tarulia Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1946/B.Ar.D. | 14/08/2023 | 45 | ACME CONSTRUCTION | 18.27 | 0 | 0 | 0
3182 | NORTH 24 PARGANAS | Barasat Arsenic Division | TARULIA Piped Water Supply Scheme , SM/18598 | New | Construction of 4.88 mtr. x 3.60 mtr. size new Pump House at Head Work Site of TARULIA Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1987/B.Ar.D. | 18/08/2023 | 60 | M/S DAS & CO | 7.38 | 0 | 0 | 0
3183 | NORTH 24 PARGANAS | Barasat Arsenic Division | TARULIA Piped Water Supply Scheme , SM/18598 | New | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 2nd Tube Well Site of TARULIA Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1988/B.Ar.D. | 18/08/2023 | 60 | B. S. ENTERPRISE | 6.23 | 0 | 0 | 0
3184 | NORTH 24 PARGANAS | Barasat Arsenic Division | TARULIA Piped Water Supply Scheme , SM/18598 | New | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 3rd Tube Well Site of TARULIA Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1989/B.Ar.D. | 18/08/2023 | 60 | SHIVAM CONSTRUCTION | 6.18 | 0 | 0 | 0
3185 | NORTH 24 PARGANAS | Barasat Arsenic Division | TARULIA Piped Water Supply Scheme , SM/18598 | New | Tarulia Piped Water Supply Scheme with Rising Main, LDS, FHTC & construction of 600 cum capacity Overhead Reservoir (OHR) including Soil investigation and foundation design at Tarulia under Rajarhat block, Dist.- North 24 Parganas. | 2557/B.Ar.D. | 30/10/2023 | 366 | AZAD ENTERPRISE | 663.57 | 0 | 0 | 0
3186 | NORTH 24 PARGANAS | Barasat Arsenic Division | TARULIA Piped Water Supply Scheme , SM/18598 | New | Survey, Design Drawing & DPR Preparation for NEW PWSS (TARULIA Water Supply Scheme) in RAJARHAT BLOCK under Barasat Arsenic Division, PHE Dte. | 1838/B.Ar.D. | 01/08/2023 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 11.11 | 11.11 | 100 | 100
3187 | NORTH 24 PARGANAS | Barasat Arsenic Division | TARULIA Piped Water Supply Scheme , SM/18598 | New | Material Requisition To Resource Division | 76/B.Ar.D | 11/01/2024 | 0 | Resource Division | 26.28 | 0 | 0 | 0
3188 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC , SM/11653 | Augmentation | Material Requisition To Resource Division | 1249/BD | 25/04/2023 | 0 | Resource Division | 114.4 | 0 | 0 | 0
3189 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC , SM/11653 | Augmentation | Material Requisition To Resource Division | 4406/BD | 10/11/2023 | 0 | Resource Division | 15.4 | 0 | 0 | 0
3190 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC , SM/11653 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Rep.) under Sankchura W/S Scheme and Paschim Madhyampur W/s Scheme District of 24 Pgs. (N) | 4815/EMD | 09/08/2023 | 30 | CONCORD ENGINEERING | 79.5 | 0 | 0 | 0
3191 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC , SM/11653 | Augmentation | Special repairing of pipe line at different location of Sankhchura Water Supply Scheme under Basirhat Sub Division, P.H.E. Dte. | 914/BHTSD | 24/05/2024 | 7 | SOUMIT CONSTRUCTION | 0.31 | 0.31 | 100 | 100
3192 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC , SM/11653 | Augmentation | Material Requisition To Resource Division | 385/BD | 07/02/2024 | 0 | Resource Division | 65.63 | 0 | 0 | 0
3193 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC , SM/11653 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Sankchura water supply scheme in Basirhat-I Block under Barasat Division, P.H.E Dte. | 1708/BD | 08/06/2023 | 723 | UTPAL CONSTRUCTION & CO. | 444.98 | 311.93 | 70.1 | 50
3194 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC , SM/11653 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Sankchura Water Supply Scheme in Basirhat - I Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | 3255/BD | 25/11/2024 | 120 | M/S K.P.PAL. | 21.75 | 0 | 0 | 100
3195 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC , SM/11653 | Augmentation | Acceptance cum work order for Restoration of roads from Sankchura Godown more towards Katarati more within Nimderia Kodalia GP under Sankchura Water Supply Scheme of Basirhat-I Block within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | 1023/BD | 28/03/2025 | 60 | SUPER ENTERPRISE | 7.09 | 0 | 0 | 100
3196 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. , SM/13471 | Augmentation | Material Requisition To Resource Division | 1674/BD | 06/06/2023 | 0 | Resource Division | 14.7 | 0 | 0 | 0
3197 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. , SM/13471 | Augmentation | Material Requisition To Resource Division | 4373/BD | 10/11/2023 | 0 | Resource Division | 16.37 | 0 | 0 | 0
3198 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. , SM/13471 | Augmentation | Material Requisition To Resource Division | 1280/BD | 25/04/2023 | 0 | Resource Division | 45.73 | 0 | 0 | 0
3199 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. , SM/13471 | Augmentation | Different works in connection with Augmentation Nebadhui Duttapukur Zone-I PWSS (1st Tubewell - Pump House). | 574/BSD | 10/09/2024 | 20 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 3.24 | 1.2 | 100 | 100
3200 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. , SM/13471 | Augmentation | Formal work order for Construction of 350 cum capacity 20 mtr. height R.C.C. Over Head Reservoir as per Deptt. design, drawing & specification including bored pile & pile cap, laying of DI rising main & distribution pipe line by DI/UPVC and Providing FHTC for Augmentaion of Nebadhui Duttapukur (Zone - I) water supply scheme under Barasat Sub-Division, P.H.E. Dte. | 1712/BD | 08/06/2023 | 731 | DIAMOND ENGINEER'S CO-OP. SOCIETY LTD. | 386.46 | 181.58 | 46.99 | 75
3201 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. , SM/13471 | Augmentation | Different works in connection with Augmentation Nebadhui Duttapukur Zone-I PWSS (3rd Tubewell -Pump House, Boundary Wall & Service Road). | 577/BSD | 10/09/2024 | 20 | ROMI TREDERS. | 3.09 | 0 | 0 | 100
3202 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. , SM/13471 | Augmentation | Different works in connection with Augmentation Nebadhui Duttapukur Zone-I PWSS (1st Tubewell - Boundary Wall & Service Road). | 575/BSD | 10/09/2024 | 20 | M/S DAS & CO. | 3.26 | 0 | 0 | 100
3203 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Nebadhai Duttapukur Zone-I PWSS to Accommodate FHTC. , SM/13471 | Augmentation | Different works in connection with Augmentation Nebadhui Duttapukur Zone-I PWSS (2nd Tubewell - Pump House, Boundary Wall & Service Road). | 576/BSD | 10/09/2024 | 20 | M/S SANKAR ENTERPRISE. | 4.64 | 0 | 0 | 100
3204 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-VII-Khoru OHR) at Amdanga Block , SM/08244 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of surface water based water supply scheme (Zone VII) at Khoru OHR site at Amdanga Block for Arsenic affected areas of North 24 Parganas water supply Division - I, PHE Dte. (2nd. Call) | 1129/NWSD-I | 22/12/2021 | 60 | ALOK ENTERPRISE, A UNIT OF SAKET TREXIM PVT. LTD. | 78.07 | 57.77 | 100 | 100
3205 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-VII-Khoru OHR) at Amdanga Block , SM/08244 | Retrofitting | Material Requisition To Resource Division | 01/NWSD-I | 03/01/2022 | 0 | Resource Division | 7.98 | 0 | 0 | 0
3206 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water SupplyScheme (Zone-VII-Khoru OHR) at Amdanga Block , SM/08244 | Retrofitting | Hiring of 1no. Diesel Motor Cab / Maxi Cab with contract carriage permit of R.T.A. in good running condition on daily rental basis for JJM works under Office of the Executive Engineer, North 24 Parganas Water Supply Division-I, P.H.E. Dte. for 182 (One Hundred Eighty Two) w.e.f. 01.01.2024 to 30.06.2024. [Vehicle No.WB 23C 5335] | 2200/NWSD-I | 29/12/2023 | 182 | M/S. SHUBHA ENTERPRISE | 0.86 | 2.24 | 262.04 | 100
3207 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block , SM/08073 | Retrofitting | Acceptance cum work order for Protection works for newly laid different dia.UPVC/DI pipe line at different places in Radhanagar laskar para, majher para, Singh para & Tati Para within Chhoto Sehara W/S/Scheme, Sandeshkhali-I Block under Hasnabad Sub-Division P.H.E.Dte. | 1467/BD. | 13/08/2021 | 30 | M/S DATTA ENTERPRISE. | 31.6 | 4.63 | 100 | 1
3208 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block , SM/08073 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in Dholkhali & Tongtala mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 1670/BD | 08/09/2021 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 49.88 | 31.41 | 100 | 1
3209 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block , SM/08073 | Retrofitting | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Chotto Sehara mouza within Chotto Sehara w/s scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 1172/HSD | 26/09/2024 | 10 | TRISHA ENTERPRISE & CO. | 0.97 | 0.97 | 100 | 100
3210 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block , SM/08073 | Retrofitting | Acceptance cum work order for Supply and installation of 150mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Chotto Sehara water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 999/HSD | 29/08/2024 | 10 | TRISHA ENTERPRISE & CO. | 0.97 | 0.97 | 100 | 100
3211 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block , SM/08073 | Retrofitting | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Radhanagar mouza within Chotto Sehara w/s scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 994/HSD | 29/08/2024 | 10 | TRISHA ENTERPRISE & CO. | 0.97 | 0.97 | 100 | 100
3212 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block , SM/08073 | Retrofitting | Acceptance cum work order for Supply and installation of 200mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Chotto Sehara water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 1001/HSD | 29/08/2024 | 10 | TRISHA ENTERPRISE & CO. | 0.97 | 0.97 | 100 | 100
3213 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block , SM/08073 | Retrofitting | Acceptance cum work order for Supply and installation of 100mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Chotto Sehara water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 997/HSD | 29/08/2024 | 10 | TRISHA ENTERPRISE & CO. | 0.84 | 0.84 | 100 | 100
3214 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block , SM/08073 | Retrofitting | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places at near Adhikary para at Choto Sehara mouza in connection with augmentation of Choto Sehara w/s scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 467/HSD | 28/02/2025 | 10 | MD.SALIM GAZI. | 0.84 | 0 | 0 | 100
3215 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block , SM/08073 | Retrofitting | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Choto Sehara mouza in connection with augmentation of Choto Sehara w/s scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 377/HSD | 10/02/2025 | 10 | GOBINDA DAS. | 0.61 | 0 | 0 | 100
3216 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block , SM/08073 | Retrofitting | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Sehara Radhanagar mouza in connection with augmentation of Choto Sehara w/s scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 304/HSD | 04/02/2025 | 10 | GOBINDA DAS. | 0.61 | 0 | 0 | 100
3217 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-IV) at Tentulia OHR site under Phase-I for Arsenic affected areas of North , SM/08040 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-IV) at Tentulia OHR site under Phase-I for Arsenic affected areas of North 24 Parganas Water Supply Division-I, P.H.E. Dte. of Barasat-I Block at Mouza Tentulia, J.L. No.114 and Choto Jagulia, J.L. No. 115 under Choto Jagulia Gram Panchayat. | 418/NWSD-I | 31/05/2021 | 90 | MANGES INDUSTRIAL CORPORATION | 80.7 | 71.4 | 64.9 | 1
3218 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-IV) at Tentulia OHR site under Phase-I for Arsenic affected areas of North , SM/08040 | Retrofitting | Hiring of 1 (one) no. Motor Cab / Maxi Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer (HQ-I), North 24 Parganas W/S Division-I, P.H.E. Dte. for 182 (one hundred eighty two) days w.e.f. 01.10.2022 to 31.03.2023. | 1078/NWSD-I | 29/09/2022 | 182 | GITA DAS | 0.86 | 1.98 | 100 | 100
3219 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bangangram (Zone-I) Water Supply Scheme at Bongaon Block (Phase-II) , SM/08044 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAGANGRAM (ZONE-I) Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (Phase-II) | 414/NWSD-I | 27/05/2021 | 60 | GHOSH CONSTRUCTION | 37.92 | 74.81 | 200 | 1
3220 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gobindapur Water Supply Scheme at Bagdah Block (Phase-I) , SM/07850 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Gobindapur Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 132/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.21 | 4.19 | 100 | 1
3221 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BANGANGRAM ZONE-I Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07608 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BANGANGRAM (ZONE-I) Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (Phase-I) | 69/NWSD-I | 20/01/2021 | 75 | TIRUPATI ENTERPRISES | 72.3 | 112.41 | 80.44 | 1
3222 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ashudi Water Supply Scheme (Phase-I) , SM/07623 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Ashudi W/S Scheme in Habra - II Block under Barasat Division, P.H.E. Dte. | 127/HAB | 16/03/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.13 | 3.09 | 100 | 1
3223 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Dwarir Jangle water supply scheme under sandeshkhali- II Block for providing Functional House Tap Conection , SM/07026 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Dwarir Jangle Mouza of Sandeshkhali-II Block from Dwarir Jangle Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. | 1882/B.Ar.D. | 18/12/2020 | 90 | UTPAL CONSTRUCTION AND CO | 96.31 | 167.65 | 128.27 | 1
3224 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of MASIA- NABASTIA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09226 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Masia Nabastia water Supply Scheme at Baduria Block under Barasat Division, PHE Dte. (Phase - I) | 401/BD | 10/02/2022 | 45 | PREMANANDA ROY BISWAS. | 49.45 | 49.25 | 100 | 1
3225 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of MASIA- NABASTIA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09226 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for MASIA-NABASTIA Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 375/BHTSD | 16/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.22 | 3.19 | 100 | 1
3226 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of MASIA- NABASTIA W/S Scheme at Baduria Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/09226 | Retrofitting | Material Requisition To Resource Division | 2992/BD | 29/09/2022 | 0 | Resource Division | 0.02 | 0 | 0 | 0
3227 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Mahisgadi water supply scheme under Barasat- II Block for providing Functional House Tap Connection in North 24Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08727 | Retrofitting | Providing Functional House Hod Connection and Allied workas at Kamduni and Kharibari Mouzas of Barasat II Block from Mahisgadi & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | 1710/B.Ar.D. | 01/10/2021 | 90 | BALAJEE ENTERPRISES | 51.31 | 51.22 | 50 | 1
3228 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Mahisgadi water supply scheme under Barasat- II Block for providing Functional House Tap Connection in North 24Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08727 | Retrofitting | Emergent protection of UPVC distribution pipe line near Haroa Khal from Dilip Mondal House to Kharibari Purba para of Mahisgadi W/S scheme related to the work FHTCat Barasat - II under Barasat Arsenic Division, P.H.E. Dte. (Approx. Length = 70 mtr) | 362/B.Ar.D | 03/03/2022 | 15 | M/S B. B. ENGINEERING | 4.8 | 4.8 | 100 | 1
3229 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Mahisgadi water supply scheme under Barasat- II Block for providing Functional House Tap Connection in North 24Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08727 | Retrofitting | Repairing & Renovation of damaged Ladder of OHR & allied works at Mahishgadi Water Supply Scheme under Barasat -II block under Barasat Arsenic Division, P.H.E. Dte. | 337/B.Ar.D | 28/02/2022 | 15 | BALAJEE ENTERPRISES | 4.63 | 0 | 0 | 1
3230 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Mahisgadi water supply scheme under Barasat- II Block for providing Functional House Tap Connection in North 24Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08727 | Retrofitting | Repairing and renovation of 02 (two) nos pump house and 01 (one) no I.E.P room and allied works at the site of Mahisgadi W/S Scheme at Barasat - II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | 1732/B.Ar.D | 05/10/2021 | 30 | SUN ENTERPRISE | 4.77 | 4.66 | 100 | 100
3231 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Mahisgadi water supply scheme under Barasat- II Block for providing Functional House Tap Connection in North 24Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08727 | Retrofitting | Emergent works of Development of Land, Protection of Pipe line and Road restoration due to laying of UPVC/HDPE Pipe line for providing FHTC of MAHISHGADI Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 1647/B.Ar.D. | 14/07/2023 | 45 | BALAJEE ENTERPRISES | 24.37 | 24.35 | 100 | 100
3232 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Gainpur Water Supply Scheme at Bongaon Block under North 24 Parganas Water Supply Division-I, P.H.E. Dte. , SM/08730 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GAINPUR Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (Phase-I) | 852/NWSD-I | 07/10/2021 | 75 | DAS TRADING | 48.75 | 48.08 | 100 | 1
3233 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ghatpatila (Zone-I) Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08268 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Ghatpatila (Zone-I) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 130/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.11 | 4.11 | 100 | 1
3234 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ghatpatila (Zone-I) Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08268 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Ghatpatila (Zone-I) Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-I) | 314/BD | 01/02/2022 | 90 | M/S NIRMAN CONSTRUCTION. | 113.02 | 112.46 | 100 | 1
3235 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of Paschim Panchberia Zone-II WaterSupply Scheme at Bongaon Block (Phase-I). , SM/08235 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PASCHIM PANCHBERIA ZONE-II Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (PHASE-I). | 849/NWSD-I | 07/10/2021 | 60 | H. I. ENTERPRISE | 58.98 | 58.92 | 52.55 | 1
3236 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of EOJNAGAR W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08655 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Eojnagar Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase - I) | 403/BD | 10/02/2022 | 45 | UTPAL CONSTRUCTION & CO. | 91.51 | 0 | 0 | 1
3237 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of EOJNAGAR W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08655 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for EOJNAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 306/BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.94 | 3.86 | 100 | 1
3238 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of EOJNAGAR W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08655 | Retrofitting | Material Requisition To Resource Division | 2990/BD | 29/09/2022 | 0 | Resource Division | 0.02 | 0 | 0 | 0
3239 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of SANKCHURA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08649 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Sankchura Water Supply Scheme at Basirhat - I Block under Barasat Division, PHE Dte. (Phase - I) | 245/BD | 27/01/2022 | 45 | SHIBU BISWAS. | 78.21 | 77.09 | 98.56 | 1
3240 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of SANKCHURA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08649 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for SANKCHURA Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | 201/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.37 | 4.25 | 100 | 1
3241 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of SANKCHURA W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08649 | Retrofitting | Material Requisition To Resource Division | 2984/BD | 29/09/2022 | 0 | Resource Division | 0.02 | 0 | 0 | 0
3242 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kumarjole Piped Water Supply Scheme, Minakhan Block (Phase-I) , SM/08258 | Retrofitting | Acceptance cum work order for Protection of UPVC rising main by UC bullah pile at Joygram Fisheries for Rejuvenation of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1851/HSD | 17/11/2021 | 15 | ABDUL ALIM MONDAL. | 3.36 | 3.34 | 50 | 1
3243 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kumarjole Piped Water Supply Scheme, Minakhan Block (Phase-I) , SM/08258 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Kumarjole w/s scheme, Minakhan Block under Hasnabad Sub- Division P.H.E. Dte. | 1995/HSD.. | 02/12/2021 | 15 | ABDUL ALIM MONDAL. | 3.5 | 3.5 | 50 | 1
3244 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kumarjole Piped Water Supply Scheme, Minakhan Block (Phase-I) , SM/08258 | Retrofitting | Acceptance cum work order for Protection Emergent restoration of concrete road for damage portion at different places for providing FHTC within Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1984/HSD | 02/12/2021 | 7 | ABDUL ALIM MONDAL. | 2.46 | 2.46 | 50 | 1
3245 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kumarjole Piped Water Supply Scheme, Minakhan Block (Phase-I) , SM/08258 | Retrofitting | Acceptance cum work order for Construction of protection wall for protection of UPVC pipe line at N/H of Majed Gazi at Uttar Kumarjole Purba para for Retrofitting of Kumarjole W/S Scheme, Minakhan Block under Hasnabad Sub-Division P.H.E. Dte. | 2055/BD | 18/09/2020 | 10 | RUDRA DAS. | 3.27 | 3.27 | 99.97 | 0
3246 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kumarjole Piped Water Supply Scheme, Minakhan Block (Phase-I) , SM/08258 | Retrofitting | Material Requisition To Resource Division | 1817/BD | 19/06/2023 | 0 | Resource Division | 52.67 | 0 | 0 | 0
3247 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bira Rajibpur Piped Water Supply Scheme at Habra-II Block (Phase-I) , SM/08782 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Ashari Narayanpur Water Supply Scheme under Barasat Division, PHE Dte. | 2170/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.61 | 3.59 | 100 | 1
3248 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bira Rajibpur Piped Water Supply Scheme at Habra-II Block (Phase-I) , SM/08782 | Retrofitting | Formal Work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BIRA RAJIBPUR Water Supply Scheme at Habra -II Block within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. (Phase - I) | 2623/BD | 27/12/2021 | 90 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 189.09 | 156.26 | 100 | 1
3249 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kankpul Piped Water Supply Scheme at Habra-II Block (Phase-I) , SM/08783 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Kankpul Water Supply Scheme at Habra-II Block within the jurisdiction of Habra Sub-Division, under Barasat Division, PHE Dte. (Phase-I). | 2388/BD | 09/12/2021 | 45 | S.S.ENTERPRISE. (BAMANGACHI) | 82.85 | 71.02 | 85.72 | 1
3250 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kankpul Piped Water Supply Scheme at Habra-II Block (Phase-I) , SM/08783 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Korakati Water Supply Scheme under Barasat Division, PHE Dte. | 2172/HSD | 28/12/2021 | 21 | UMWELT ENGINEER PVT.LTD. | 4.12 | 4.12 | 100 | 1
3251 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kankpul Piped Water Supply Scheme at Habra-II Block (Phase-I) , SM/08783 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Kankpul W/S Scheme within the jurisdiction of the Habra Sub-Division under Barasat Division, PHE Dte. | 567/HAB | 22/12/2021 | 10 | UMWELT ENGINEER PVT.LTD. | 4.02 | 4.02 | 100 | 1
3252 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kurulia Zone-II Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08262 | Retrofitting | Construction of Approach Road Head Work at site for Augmentation of Kurulia (Zone-II) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 621/Bon | 08/08/2023 | 25 | GHOSH CONSTRUCTION. | 4.75 | 4.74 | 100 | 100
3253 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kurulia Zone-II Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08262 | Retrofitting | Construction of Approach Road at 2ndT/W site for Augmentation of Kurulia (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | 558/Bon | 18/07/2023 | 15 | ROY ENGINEERS. | 0.93 | 0.92 | 100 | 100
3254 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kurulia Zone-II Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08262 | Retrofitting | Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Kurulia (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 643/Bon | 14/08/2023 | 21 | M/S SAYAN ENTERPRISE. | 1.59 | 1.57 | 100 | 100
3255 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kurulia Zone-II Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08262 | Retrofitting | Improvement of Iron Elimination Plant and other related allied works at Kurulia (Zone - II) W/S Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 638/Bon | 14/08/2023 | 15 | SAMBHU RAY CHOWDHURY. | 2.49 | 2.41 | 100 | 100
3256 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kurulia Zone-II Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08262 | Retrofitting | Formal work order for Improvement of Iron Elimination Plant and other related allied works at Kurulia (Zone-I) W/S Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 637/Bon | 14/08/2023 | 15 | TAPAN GHOSH. | 2.45 | 0 | 0 | 99
3257 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Acceptance cum work order for Restoration of RCC drain from Joygram Bazar Idgah to near Pintu Molla Garage for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1238/HSD | 20/07/2022 | 21 | JESMINE ENTERPRISE. | 4.76 | 0 | 0 | 1
3258 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Acceptance cum work order for Restoration of RCC drain from N/H/O Sahidul Molla to near Julfikar Molla shop for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1246/HSD | 20/07/2022 | 21 | JESMINE ENTERPRISE. | 4.76 | 0 | 0 | 1
3259 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Acceptance cum work order for Restoration of RCC drain from Pintu Molla Garage to N/H/O Sahidul Molla for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1240/HSD | 20/07/2022 | 21 | JESMINE ENTERPRISE. | 4.76 | 0 | 0 | 1
3260 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Acceptance cum work order for Restoration of RCC drain from Near Julfikar Molla shop to N/H/O Sariful Molla for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1244/HSD | 20/07/2022 | 21 | JESMINE ENTERPRISE. | 3.39 | 0 | 0 | 1
3261 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Acceptance cum work order for Laying of 150 mm dia. DI distribution main from near PH No-1 to N/H/O Prasanta Mondal, N/H/O Sudip Gayen to Chanchal Chatterjee & Sudip Gayen to Santanu Joardar for damage portion within Korakati w/s scheme, Sandeshkhali-II Block under Hasnabad Sub- Division P.H.E. Dte. | 1189/HSD | 13/07/2022 | 15 | R.K.MANDAL & CO. | 4.27 | 4.27 | 50 | 1
3262 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Acceptance cum work order for Laying of 100mm dia. DI distribution main from N/H/O Chanchal Chatterjee to N/H/O Kritanta Mondal & Biswajit Baidya for damage portion within Korakati w/s scheme, Sandeshkhali-II Block under Hasnabad Sub- Division P.H.E. Dte. | 1191/HSD | 13/07/2022 | 10 | R.K.MANDAL & CO. | 2.17 | 2.17 | 50 | 1
3263 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Acceptance cum work order for Laying of 200 mm dia. DI distribution main from PH No- 1 to PH No-2 & PH No- 2 to N/H/O Sudip Gayen for damage portion within Korakati w/s scheme, Sandeshkhali-II Block under Hasnabad Sub- Division P.H.E. Dte. | 1186/HSD | 13/07/2022 | 15 | R.K.MANDAL & CO. | 4.25 | 4.25 | 50 | 1
3264 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator at (inconnection with Aug. work related to FHTC) Pump House No.II (Replacement) under Korakati W/S Scheme District of North 24 Pgs. | 3035/ EMD | 08/08/2022 | 30 | SANKAR PRASAD DUTTA & CO, | 10.14 | 0 | 0 | 1
3265 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 1202/BD | 20/04/2023 | 30 | TRISHA ENTERPRISE & CO. | 31.02 | 23.48 | 75.7 | 0
3266 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 1042-HSD. | 31/08/2023 | 10 | ANKUSH CONSTRUCTION & CO. | 0.9 | 0 | 0 | 0
3267 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Korakati water supply scheme, Sandeshkhali-II Block within Hasnabad Sub-Division, under Barasat Division, PHE Dte. | 2675/BD | 08/09/2022 | 90 | PATHIK PABAN NANDI | 274.1 | 265.59 | 100 | 1
3268 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator at (inconnection with Aug. work related to FHTC) Pump House No.II (Replacement) under Korakati W/S Scheme District of North 24 Pgs. | 3035/EMD | 08/08/2022 | 212 | SANKAR PROSAD DUTTA & CO. | 9.33 | 9.33 | 100 | 0
3269 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (replacement) under Korakati W/S Scheme District of North 24 Pgs. Tender No.- 08 (Sl. No.-03) of EE/EMD of 2022-23 | 3384EMD | 09/09/2022 | 30 | CHATTERJEE BROTHERS | 11.31 | 10.31 | 100 | 70
3270 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 1041/HSD | 31/08/2023 | 10 | ANKUSH CONSTRUCTION & CO. | 0.9 | 0.9 | 100 | 100
3271 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 1042/HSD | 31/08/2023 | 10 | ANKUSH CONSTRUCTION & CO. | 0.9 | 0.9 | 100 | 100
3272 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Korakati water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 1412/HSD | 06/11/2023 | 7 | ANKUSH CONSTRUCTION & CO. | 0.91 | 0.91 | 100 | 59
3273 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Material Requisition To Resource Division | 2576/BD | 31/08/2022 | 0 | Resource Division | 6.15 | 0 | 0 | 0
3274 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Material Requisition To Resource Division | 918/BD | 22/03/2023 | 0 | Resource Division | 10.9 | 0 | 0 | 0
3275 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | illumination by supplying and installing of 15 Watt Solar Street Light at P.H No. I under Korakati W/S Scheme,Sandeshkhali-II Block, Dist. 24 pgs (N) under Eastern Mechanical Division, P.H.E.Dte. | 1197/EMSD-I | 27/09/2024 | 30 | P.K. ENTERPRISE | 1.5 | 0 | 0 | 0
3276 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Acceptance cum work order for Protection works in different places for protection of different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile for Augmention of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 2680/BD | 04/09/2023 | 30 | ANKIT CONSTRUCTION | 66.88 | 66.57 | 100 | 82
3277 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Supply delivery & fixing at site 4 Core, 50 Sq. Mm XLPE Al, Ar. Cable for shifting of service connection cable at Head Work site of Korakati W/S Scheme District of 24Pgs(N). | 295/EMSD-I | 11/03/2024 | 10 | TAKE ME INDIA | 0.55 | 0.55 | 100 | 100
3278 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 865/BD | 19/03/2025 | 450 | M/S K.B.ENTERPRISE. | 102.2 | 0 | 0 | 30
3279 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Korakati water supply scheme, Sandeshkhali-II Block of Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | 4190/BD | 30/10/2023 | 465 | M/S K.B.ENTERPRISE. | 140.14 | 102.12 | 77.2 | 85
3280 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places in connection with augmentation of Korakati W/S Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Phase-II) | 469/HSD | 28/02/2025 | 10 | PRASANTA MITRA. | 0.97 | 0 | 0 | 100
3281 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Acceptance cum work order for Installation of CCTV Camera Connection at Pump house no 1 & 2 for Korakati w/s scheme, Sandeshkhali -II Block under Hasnabad Sub-Division, PHE Dte | 186/HSD | 28/01/2025 | 10 | M/S DATTA ENTERPRISE. | 0.58 | 0 | 0 | 100
3282 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Acceptance cum work order for Supply and installation of 150 mm dia sluice valve in distribution pipe line for smooth supply of water at different palces in connection with augmentation of Korakati water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | 944/HSD | 29/05/2025 | 10 | NEW LIFE CONSTRUCTION. | 0.83 | 0 | 0 | 100
3283 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places in connection with augmentation of Korakati W/S Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Phase-I) | 322/HSD | 04/02/2025 | 10 | PRASANTA MITRA. | 0.96 | 0 | 0 | 100
3284 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Korakati, Block Sandeshkhali-II. , SM/10376 | Augmentation | Acceptance cum work order for Providing Functional tap connection at Uttar Korakati SSK, Korakati Sishu Kalyan Vidyapith and Paschim Monipur Vijoy Das Smriti MSK within the command area of Korakati and Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 992/HSD | 04/06/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.72 | 0 | 0 | 100
3285 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC , SM/10555 | Augmentation | Acceptance cum work order for Withdrawing & relaying of 110 mm dia. UPVC pipe line from PH no- 1 towards Adibasi Sonali Sangha of Murarisha W/S Scheme,Hasnabad block under Hasnasbad Sub-Division, P.H.E.Dte. | 378/HSD | 31/03/2023 | 10 | MD.SALIM GAZI. | 0.9 | 0.9 | 99.74 | 0
3286 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC , SM/10555 | Augmentation | Acceptance cum work order for Withdrawing & relaying of 110 mm dia. UPVC pipe line from PH no- 1 towards Adibasi Sonali Sangha of Murarisha W/S Scheme,Hasnabad block under Hasnasbad Sub-Division, P.H.E.Dte. | 378/HSD | 31/03/2023 | 10 | MD.SALIM GAZI. | 0.9 | 0 | 0 | 0
3287 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC , SM/10555 | Augmentation | Material Requisition To Resource Division | 934/BD | 22/03/2023 | 0 | Resource Division | 27.49 | 0 | 0 | 0
3288 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC , SM/10555 | Augmentation | Material Requisition To Resource Division | 4510/BD | 28/11/2023 | 0 | Resource Division | 18.1 | 0 | 0 | 0
3289 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC , SM/10555 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 200 mm dia DI pipeline at different places in connection with Augmentation of Murarisha w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 274/HSD | 06/03/2024 | 10 | NEW MANGES INDUSTRIAL CORPORATION | 0.95 | 0.94 | 100 | 80
3290 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC , SM/10555 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 150 mm dia DI pipeline at different places in connection with Augmentation of Murarisha w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 268/HSD | 06/03/2024 | 10 | NEW MANGES INDUSTRIAL CORPORATION | 0.92 | 0.91 | 100 | 100
3291 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC , SM/10555 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site in connection with Augmentation of Murarisha W/S scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 259/HSD | 06/03/2024 | 10 | S.S.ENTERPRISE. (BAMANGACHI) | 0.94 | 0.94 | 100 | 37
3292 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC , SM/10555 | Augmentation | Acceptance cum work order for Construction of anchor block for resting of 250 mm dia DI pipeline at different places in connection with Augmentation of Murarisha w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 873/HSD | 07/08/2024 | 10 | NEW MANGES INDUSTRIAL CORPORATION | 0.95 | 0.94 | 100 | 100
3293 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC , SM/10555 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II, III and IV(Rep.) under Murarisha W/S Scheme and Jeliakhali-Paschimkhanda (I or II) W/S Scheme in District of 24 Pgs. (N) NIET-32 of EE/EMD of 2022-23 (Sl. no.19) | 4810/EMD | 09/08/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 63.65 | 0 | 0 | 75
3294 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC , SM/10555 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, construction of 350 cum capacity 20 mtr staging height R.C.C Over Head Reservoir as per Deptt. design, drawing & specification including bored pile with pile cap and providing Functional Household Tap Connection in connection with Augmentation of Murarisha water supply scheme, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | 2591/BD | 28/08/2023 | 581 | S.S.ENTERPRISE. (BAMANGACHI) | 576.34 | 546.09 | 94.83 | 98
3295 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC , SM/10555 | Augmentation | Acceptance cum work order for Land development at Over Head Reservoir site for Augmentation of Murarisha water supply scheme, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | 2457/BD | 27/08/2024 | 15 | BARNALI DUTTA | 5.44 | 5.31 | 100 | 100
3296 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Murarisha to accommodate FHTC , SM/10555 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Murarisha w/s scheme, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | 3640/BD | 23/12/2024 | 180 | S.S.ENTERPRISE. (BAMANGACHI) | 169.89 | 15.36 | 8.49 | 70
3297 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District , SM/10777 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 48 m Length in 3rd. Pump house site at Mollahati Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte | 405/NWSD-I | 11/04/2023 | 45 | SHAMALI ENTERPRISE | 5.9 | 3.55 | 60.24 | 70
3298 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District , SM/10777 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Mollahati Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | 1191/NWSD-I | 31/12/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5 | 5 | 100 | 0
3299 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District , SM/10777 | Augmentation | Special Repairing & Renovation of Pump House at 2nd Pump House site & Service road (25 Mtr. Length X 2 Mtr. Width) at 2nd Pump House site of Mollahati Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte | 407/NWSD-I | 11/04/2023 | 45 | RAHUL ENTERPRISE | 4.13 | 3.6 | 100 | 100
3300 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District , SM/10777 | Augmentation | Special Repairing & Renovation of Pump House at Head Works site & Service road (60 Mtr. Length X 3 Mtr. Width) at Head works site of Mollahati Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte | 406/NWSD-I | 11/04/2023 | 45 | HAKIM ENTERPRISE | 7.29 | 6.93 | 100 | 100
3301 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District , SM/10777 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 51 m Length in 2nd Pump house site at Mollahati Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 413/NWSD-I | 11/04/2023 | 45 | M/S SAIN ENTERPRISE | 6.19 | 4.01 | 100 | 60
3302 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District , SM/10777 | Augmentation | UPVC pipe laying work along with allied works under Mollahati Water Supply Scheme in the district of North 24 PGS under N 24 Pgs W/S Div-I, PHE Dte. | 1087/NWSD-I | 01/08/2023 | 60 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 76.32 | 76.25 | 100 | 100
3303 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District , SM/10777 | Augmentation | Material Requisition To Resource Division | 1164/NWSD-I | 26/09/2022 | 0 | Resource Division | 0.04 | 0 | 0 | 0
3304 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District , SM/10777 | Augmentation | Renovation of AIRP at Mollahati Water Supply Scheme of capacity 110.81 Cu.m/hr of Bongaon Block under North 24 Pgs. W/S Div-I, PHE Dte. | 1644/NWSD-I | 13/11/2024 | 180 | CONCORD ENGINEERING | 71.75 | 0 | 0 | 0
3305 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District , SM/10777 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system & Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of Mollahati Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE. Dte. | 1055/NWSD-I | 01/09/2022 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 681.95 | 678.05 | 100 | 100
3306 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District , SM/10777 | Augmentation | Repair and renovation works for 550 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir , Boundary wall at H/W site and PH-III with other allied works at Mollahati W/S Scheme under North 24 Pgs Water Supply Division- I, P.H.E. Dte. | 1240/NWSD-I | 18/08/2023 | 60 | MONDAL ENTERPRISE | 36.59 | 35.6 | 100 | 100
3307 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District , SM/10777 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1430/NWSD-I | 18/09/2024 | 7 | BIBHAS PAL | 5.27 | 0.35 | 50 | 100
3308 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District , SM/10777 | Augmentation | Reimbursement of additional GST due to enhancement of rate from 12% to 18% vide Notification No. 03/2022 Central tax rate dt.13/07/2022 for the work of "Laying of distribution pipeline including providing FHTC at Mollahati W/S Scheme under NWSD-I, P.H.E. Dte. Tender No.82/eT/NWSD-I of 2022-23, Work Order No.1055/NWSD-I dt.01/09/2022, Enhancement GST Sanction No. PHE/IV/3260/W-698/23 dt.19/10/2023. | 180/PFMS/24-25 | 03/09/2024 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 35.98 | 0 | 0 | 0
3309 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. , SM/10582 | Augmentation | Survey, Design and preparation of Retrofitting DPR in connection with " Providing functional household tap connection to every Household under Auldanga Zone-II W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte." | 315/NWSD - I | 21/03/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.92 | 3.92 | 100 | 1
3310 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. , SM/10582 | Augmentation | Material Requisition To Resource Division | 1211/NWSD-I | 13/10/2022 | 0 | Resource Division | 7.42 | 0 | 0 | 0
3311 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. , SM/10582 | Augmentation | Material Requisition To Resource Division | 454/NWSD-I | 26/04/2023 | 0 | Resource Division | 55.56 | 0 | 0 | 0
3312 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. , SM/10582 | Augmentation | Laying of Distribution System including specials & valves, pipe carrying structure, Providing FHTC including supplying , laying, fitting, fixing of 15 mm NB PVC (Schedule 80) / 20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun meter ferrule, saddle piece etc. all complete, construction works of R.C.C Elevated Reservoir 350m3,Construction of Pump House, Boundary wall, Service Road (25Mtr. Length x 2 Mtr. Width) at Pump House site at Auldanga Zone - II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | 929/NWSD-I | 17/07/2023 | 366 | MONDAL ENTERPRISE | 476.14 | 127.07 | 26.69 | 65
3313 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. , SM/10582 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1430/NWSD-I | 18/09/2024 | 7 | BIBHAS PAL | 5.27 | 0.14 | 44.27 | 100
3314 | NORTH 24 PARGANAS | Eastern Mechanical | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. , SM/10582 | Augmentation | New service connection at P.H.No- I ,Zone-II of Auldanga water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). Type : | BP-339-23-24 | 11/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.11 | 0 | 0 | 0
3315 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. , SM/10582 | Augmentation | Protection work & land development at H/W Site under Augmentation Scheme of Auldanga W/S Scheme (Zone - II) within the jurisdiction of N24Pgs. W/S Division-I, P.H.E. Dte. | 54/NWSD-I | 09/01/2025 | 30 | MONDAL ENTERPRISE | 45.44 | 0 | 0 | 0
3316 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-I (Surjapur) in Barrackpore-II & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11827 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-IA/I (Surjapur) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 328/NWSD-I | 24/03/2022 | 1 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.64 | 4.41 | 100 | 1
3317 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-I (Surjapur) in Barrackpore-II & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11827 | Augmentation | Material Requisition To Resource Division | 486/NWSD-I | 26/04/2023 | 0 | Resource Division | 6.52 | 0 | 0 | 0
3318 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-I (Surjapur) in Barrackpore-II & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11827 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I, A-I (Surjapur) in Barrackpore-II & Barasat-I Block of North 24 Parganas District. | 4027/ED | 17/10/2023 | 183 | WEST BENGAL ENGINEERING CO. | 30.05 | 0 | 0 | 10
3319 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-I (Surjapur) in Barrackpore-II & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11827 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 145.34 | 20.58 | 2
3320 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-I (Surjapur) in Barrackpore-II & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11827 | Augmentation | Road restoration along flank portion of bituminous road of PWD/ PMGSY/ Zilla Parisad/ Panchayet road due to laying of pipeline and reallocation of Rising Main under Augmentation work at Surjapur (Zone-IA-I) W/S Scheme in Barrackpore-II Block under North 24Pgs. W/S Division-I, P.H.E. Dte. | 770/NWSD-I | 23/05/2025 | 45 | DAS TRADING | 29.58 | 0 | 0 | 0
3321 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC , SM/11539 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Malidah water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 526/ BON | 01/11/2021 | 21 | TAPAN GHOSH. | 2.52 | 2.48 | 100 | 1
3322 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC , SM/11539 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Malidah Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 140/BON | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.74 | 3.72 | 50 | 1
3323 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC , SM/11539 | Augmentation | Material Requisition To Resource Division | 3686/BD | 14/12/2022 | 0 | Resource Division | 12.95 | 0 | 0 | 0
3324 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC , SM/11539 | Augmentation | Material Requisition To Resource Division | 3712/BD | 15/12/2022 | 0 | Resource Division | 1.79 | 0 | 0 | 0
3325 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC , SM/11539 | Augmentation | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Malidah Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 3471/BD | 01/12/2022 | 90 | R.K.MANDAL & CO. | 243.9 | 183.97 | 100 | 100
3326 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC , SM/11539 | Augmentation | Acceptance cum work order for Sinking of 2 (two) nos. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tube well by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Malidah Water Supply Scheme (H/W Site & 2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | 2830/BD | 15/09/2023 | 60 | DHELA BABA ENTERPRISE | 32.28 | 27.78 | 100 | 100
3327 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC , SM/11539 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Head Work site for Augmentation of Malidah Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 4407/BD | 10/11/2023 | 60 | BHABANI ENTERPRISE. | 11.49 | 11.47 | 100 | 100
3328 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC , SM/11539 | Augmentation | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Malidah Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division P.H.E. Dte. | 4465/BD | 21/11/2023 | 23 | KAMAL HALDER. | 7.15 | 7.15 | 100 | 100
3329 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC , SM/11539 | Augmentation | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site under Augmentation work at Malidah W/S Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1541/BD | 15/05/2025 | 120 | NISHITH BANERJEE | 31.89 | 0 | 0 | 0
3330 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC , SM/11539 | Augmentation | Acceptance cum work order for Repair and renovation works of 250cum capacity 20mtr. staging height R.C.C. over Head Reservoir for Augmentation of Malidah Water Supply Scheme, Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 3404/BD | 04/12/2024 | 180 | PRABIR KUMAR MONDAL. | 7.9 | 0 | 0 | 100
3331 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC , SM/11539 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying and repair of UPVC pipe and allied works in connection with Augmentation work at Malidah W/S Scheme Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 3386/BD | 03/12/2024 | 90 | VAI ENTERPRISE. | 11.41 | 0 | 0 | 100
3332 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bansjhari Mallickpur to accommodate FHTC , SM/11634 | Augmentation | Material Requisition To Resource Division | 3813/BD | 23/12/2022 | 0 | Resource Division | 98.04 | 0 | 0 | 0
3333 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bansjhari Mallickpur to accommodate FHTC , SM/11634 | Augmentation | Material Requisition To Resource Division | 4415/BD | 10/11/2023 | 0 | Resource Division | 9.24 | 0 | 0 | 0
3334 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bansjhari Mallickpur to accommodate FHTC , SM/11634 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Bansjhari Mallikpur water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | 3341/BD | 16/11/2022 | 867 | UTPAL CONSTRUCTION & CO. | 227.32 | 169.23 | 74.44 | 90
3335 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bansjhari Mallickpur to accommodate FHTC , SM/11634 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Bansjhari-Mullickpur and Maminpur W/S Scheme with Pump House No-I under Rajnagar W/S Scheme District of 24 Pgs. (N) | 4809./EMD | 09/08/2023 | 30 | S.G. ENTERPRISE | 65.16 | 21.9 | 84.04 | 75
3336 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. , SM/12625 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-IV/B (Saraberia) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 423/NWSD-I | 01/04/2022 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.87 | 4.87 | 100 | 1
3337 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. , SM/12625 | Augmentation | Material Requisition To Resource Division | 485/NWSD-I | 26/04/2023 | 0 | Resource Division | 78.35 | 0 | 0 | 0
3338 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. , SM/12625 | Augmentation | Way leave / crossing purpose water supply (JJM) station from Kazipara Halt to Karea Kadambagachhi Halt. (Eastern Railway, Sealdah). KM Mast : 4/35-37 - 4/34-36, Application ID : ER-SDAH-2023-WL-56 | 261/PFMS/23-24 | 03/10/2023 | 0 | EASTERN RAILWAY, SEALDAH | 6.22 | 0 | 0 | 0
3339 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. , SM/12625 | Augmentation | Way leave / crossing purpose water supply (JJM) station from Kazipara Halt to Karea Kadambagachi. (Eastern Railway, Sealdah). KM Mast : 6/02-06 - 6/01-05, Application ID : ER-SDAH-2023-WL-57. | 262/PFMS/23-24 | 03/10/2023 | 0 | EASTERN RAILWAY, SEALDAH | 4.74 | 0 | 0 | 0
3340 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. , SM/12625 | Augmentation | Railway way leave permission between Mast 6/02-06 - 6/01-05 at Station from Kazipara Halt (KZPR)- Karea Kadambagachhi Halt (KBGH) for laying 600 mm. dia. (OD) M.S pipe by Jack Pushing Technique for Augmentaion of Surface Based Piped Water Supply Scheme for Zone- IV-B (Saraberia) in Barasat-I Block under North 24 Pgs W/S Division-I P.H.E. Dte. | 2126/NWSD-I | 28/12/2023 | 31 | M/S. SHUBHA ENTERPRISE | 0.95 | 0.75 | 44.15 | 100
3341 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. , SM/12625 | Augmentation | Material Requisition To Resource Division | 1715/NWSD-I | 26/11/2024 | 0 | Resource Division | 17.86 | 0 | 0 | 0
3342 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. , SM/12625 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 302.58 | 28.86 | 2
3343 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. , SM/12625 | Augmentation | Reapiring and restoration of Black Top metal road under the command area of Saraberia, Kharki, Tentulia Water Supply Scheme within Barasat-I Block under North 24 Pgs W/S Division-I | 754/NWSD-I | 22/05/2025 | 45 | BASHUDEV DUTTA | 45.91 | 0 | 0 | 0
3344 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC , SM/12277 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.III (Chimta)(Rep.) and IV(New) (Zone-II) under Dakshin Bhebia W/S Scheme District of 24 Pgs. (N) | 4941/EMD | 18/08/2023 | 30 | ESENCE ENGINEERING CONCERN | 26.47 | 0 | 0 | 0
3345 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC , SM/12277 | Augmentation | Material Requisition To Resource Division | 912/BD | 22/03/2023 | 0 | Resource Division | 163.73 | 0 | 0 | 0
3346 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC , SM/12277 | Augmentation | Material Requisition To Resource Division | 4173/BD | 30/10/2023 | 0 | Resource Division | 37.95 | 0 | 0 | 0
3347 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC , SM/12277 | Augmentation | Material Requisition To Resource Division | 4559/BD | 01/12/2023 | 0 | Resource Division | 74.49 | 0 | 0 | 0
3348 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC , SM/12277 | Augmentation | Acceptance cum work order for Restoration of 225 mm dia. UPVC pipe line due to construction of drain at Kharampur more within Dakshin Bhebia W/S Scheme (Z-II), Hasnabad block under Hasnasbad Sub-Division, P.H.E.Dte. | 1420/HSD | 06/11/2023 | 523 | SARKAR ENTERPRISE | 0.92 | 0 | 0 | 100
3349 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC , SM/12277 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line and Providing Functional Household Tap Connection for the leftout portion with protection work in connection with Augmentation of Dakshin Bhebia water supply scheme (Z-II), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | 3623/BD | 20/12/2024 | 360 | H.I.ENTERPRISE. | 178.87 | 0 | 0 | 50
3350 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC , SM/12277 | Augmentation | Acceptance cum work order for Surging and development of Big dia tubewell by Carrying out surging and back blowing of existing tube well including installation of suitable education pipes of adequate diameter upto required depth along with suitable airline pipes for injecting compressed air under pressure at the appropriates depth inside the tube well within Hasnabad Sub-Division PHE Dte. under Barasat Division P.H.E Dte. | 172/BD | 15/01/2025 | 240 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 30.65 | 0 | 0 | 60
3351 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC , SM/12277 | Augmentation | Acceptance cum work order for Construction of additional 1 no. switch room cum chlorine room (5.40x3.60) with sanitary and water supply arrangement including plinth protection in connection with augmentation of Dakshin Bhebia w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 894/BD | 20/03/2025 | 75 | ARBINA ENTERPRISE. | 7.47 | 0 | 0 | 100
3352 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-C (Dariapur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12564 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-VII/C (Dariapur) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 427/NWSD-I | 01/04/2022 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.96 | 4.96 | 100 | 1
3353 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-C (Dariapur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12564 | Augmentation | Material Requisition To Resource Division | 474/NWSD-I | 26/04/2023 | 0 | Resource Division | 134.8 | 0 | 0 | 0
3354 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-C (Dariapur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12564 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII, C (Dariapur) in Amdanga Block of North 24 Parganas District. | 4888/ED | 27/12/2023 | 183 | SUNRISE ENGINEERING CORPORATION | 61.12 | 0 | 0 | 0
3355 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-C (Dariapur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12564 | Augmentation | Material Requisition To Resource Division | 1710/NWSD-I | 26/11/2024 | 0 | Resource Division | 47.74 | 0 | 0 | 0
3356 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-C (Dariapur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12564 | Augmentation | Panchpota Dhankal to Nima more PWD Road , Amdanga Block due to laying of PHE pipe line under Dariapur Surface scheme . | 168/PFMS/24-25 | 26/08/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA, NORTH 24 PARGANAS DIVISION | 17.43 | 0 | 0 | 0
3357 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-C (Dariapur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12564 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 174.78 | 14.85 | 2
3358 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-B (Rautara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12565 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-VII/B (Rautara) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 426/NWSD-I | 01/04/2022 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.33 | 4.33 | 100 | 1
3359 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-B (Rautara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12565 | Augmentation | Material Requisition To Resource Division | 483/NWSD-I | 26/04/2023 | 0 | Resource Division | 127.87 | 0 | 0 | 0
3360 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-B (Rautara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12565 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 150.96 | 15.34 | 2
3361 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-B (Rautara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12565 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII, B (Rautara) in Amdanga Block of North 24 Parganas District. | 4030/ED | 17/10/2023 | 810 | DEY ENTERPRISE | 57.7 | 0 | 0 | 25
3362 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-B (Rautara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12565 | Augmentation | Road restoration along flank portion of Madhabpur Kakinara PWD road, Sankarpur more (Node 69) to Tapanpur F.P School (Node - 994) due to laying of pipeline under Augmentation work at Rautara (Zone- VII_B) W/S Scheme in Amdanga Block under North 24Pgs. W/S Division-I, P.H.E. Dte. | 795/NWSD-I | 28/05/2025 | 30 | NIKHIL SAMADDAR | 21.47 | 0 | 0 | 0
3363 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-B (Rautara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12565 | Augmentation | Road restoration along flank portion of Rafipur Padmanavpur Kakinara PWD road, Sankarpur more (Node 69) to Masjid Bilal Rahampulla (Node - 338) due to laying of pipeline under Augmentation work at Rautara (Zone- VII_B) W/S Scheme in Amdanga Block under North 24Pgs. W/S Division-I, P.H.E. Dte. | 800/NWSD-I | 28/05/2025 | 30 | BANERJEE CONSTRUCTION | 31.27 | 0 | 0 | 0
3364 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Arsula to accommodate FHTC , SM/11700 | Augmentation | Material Requisition To Resource Division | 1237/BD | 25/04/2023 | 0 | Resource Division | 141.41 | 0 | 0 | 0
3365 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Arsula to accommodate FHTC , SM/11700 | Augmentation | Material Requisition To Resource Division | 4425/BD | 10/11/2023 | 0 | Resource Division | 17.4 | 0 | 0 | 0
3366 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Arsula to accommodate FHTC , SM/11700 | Augmentation | Regarding Restoration charges for road damages. | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 18.45 | 0 | 0 | 0
3367 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Arsula to accommodate FHTC , SM/11700 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Arsula water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | 1217/BD | 20/04/2023 | 950 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 667.97 | 389.66 | 58.33 | 55
3368 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Arsula to accommodate FHTC , SM/11700 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Rep.) and IV (New) under Gokna W/S Scheme and Pump House No- II (Rep) under Arsula W/S Scheme District of 24 Pgs. (N) | 6735/EMD | 29/11/2023 | 489 | M.S. ENTERPRISE | 39.12 | 0 | 0 | 30
3369 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Arsula to accommodate FHTC , SM/11700 | Augmentation | Acceptance cum work order for Restoration of roads under different water supply schemes of Baduria Block within Basirhat Sub-Division under Barasat Division P.H.E.Dte | 3553/BD | 16/12/2024 | 390 | PRITAM MUKHOPADHYAY. | 60.15 | 0 | 0 | 0
3370 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Arsula to accommodate FHTC , SM/11700 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Baduria Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - A) | 143/BHTSD | 29/01/2025 | 20 | BIBHAS PAL. | 0.88 | 0 | 0 | 90
3371 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11705 | Augmentation | Sinking of 1 no 250 mm. X 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation at 2nd T/W site of Atapur w/s scheme of Sandeshkhali- II block under Barasat Arsenic Division, P.H.E. Dte. | 849/B.Ar.D. | 06/05/2022 | 45 | M/S. S. S. ENTERPRISE | 19.74 | 15.2 | 33.33 | 1
3372 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11705 | Augmentation | Preparation of Augmentation DPR for Atapur Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | 1839/B.Ar.D | 19/09/2022 | 20 | SIRCON ENGINEERING SERVICES | 0.98 | 0.98 | 100 | 1
3373 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11705 | Augmentation | Material Requisition To Resource Division | 2288/B.Ar.D | 02/12/2022 | 0 | Resource Division | 10.97 | 0 | 0 | 0
3374 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11705 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Replacement) under Atapur W/S Scheme, District of 24 Pgs. (N). (SM/11705) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 03) | 6381/EMD | 24/11/2022 | 30 | D.K. ELECTRIC | 10.12 | 10.12 | 100 | 0
3375 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11705 | Augmentation | Sinking of 1 no Replacement 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 250 mm dia 42 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation of Atapur w/s Scheme at PH-I of Sandeshkhali-II block under Barasat Arsenic Division, P.H.E. Dte. | 467/B.Ar.D. | 27/02/2023 | 45 | UNIFIED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.81 | 16.64 | 100 | 1
3376 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11705 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Atapur W/S Scheme, District of 24 Pgs. (N). (SM/11705) | 6381 /EMD | 24/11/2022 | 30 | D.K. ELECTRIC | 10.12 | 0 | 0 | 1
3377 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11705 | Augmentation | Material Requisition To Resource Division | 2112/B.Ar.D. | 02/11/2022 | 0 | Resource Division | 3.53 | 0 | 0 | 0
3378 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11705 | Augmentation | Repair and Renovation of 136 Cum capacity OHR, Construction of 2nd Pump House Boundary Wall at OHR Site, 1st pump house & 2nd pump house pump connection and allied work for Atapur W/S Scheme Under Barasat Arsenic Division, PHE Dte. | 3028/B.Ar.D. | 29/12/2023 | 50 | M/S NIRMAN CONSTRUCTION | 73.1 | 72.48 | 100 | 55
3379 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11705 | Augmentation | Withdrawing and relaying of pipelines and Sal-Bullah Pilling for pipe protection work at Atapur under Sandeshkhali-II Block Under Barasat Arsenic Division, PHE Dte. | 984/B.Ar.D. | 18/06/2024 | 30 | DEL DELTA CONSTRUCTION | 5.88 | 5.78 | 100 | 100
3380 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ATAPUR to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11705 | Augmentation | Laying of distribution System, Laying of Rising Main including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at ATAPUR under Sandeshkhali - II Block under Barasat Arsenic Division, PHE Dte. | 1567/B.Ar.D. | 25/08/2022 | 990 | M/S NIRMAN CONSTRUCTION | 192.73 | 170.34 | 91.34 | 90
3381 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Daudpur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10503 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna programme within command area of Daudpur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 1492/BD | 25/05/2022 | 90 | M/S S.S.ENTERPRISE. (SOUTH) | 164.51 | 125.08 | 55.45 | 1
3382 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Daudpur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10503 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within laukhali mouza due to erosion of soil for heavy rain fall during monsoon season within Daudpur w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | 1055/HSD | 31/08/2023 | 10 | ABDUL ALIM MONDAL. | 0.97 | 0.86 | 100 | 100
3383 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Daudpur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10503 | Retrofitting | Acceptance cum work order for Protection work for newly laid different dia. UPVC/DI distribution pipeline at different places in Daudpur Mouza of Daudpur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 2658/BD | 01/09/2023 | 30 | M/S PROGATI ENTERPRISE. | 34.09 | 33.95 | 100 | 100
3384 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Daudpur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10503 | Retrofitting | Acceptance cum work order for Sinking of Additional 1 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Daudpur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 3580/BD | 18/12/2024 | 30 | SUBHAJIT SAHA | 31.69 | 0 | 0 | 0
3385 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Daudpur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10503 | Retrofitting | Acceptance cum work order for Construction of boundary wall with RCC column structure at head Work site within Daudpur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | 4378/BD | 10/11/2023 | 90 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 23.09 | 21.09 | 100 | 100
3386 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalkora to accommodate FHTC , SM/11524 | Augmentation | Route Survey, Design Drawing & DPR Preparation for NALKORA Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | 202/ BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.79 | 2.61 | 50 | 1
3387 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalkora to accommodate FHTC , SM/11524 | Augmentation | Material Requisition To Resource Division | 3819/BD | 23/12/2022 | 0 | Resource Division | 23.93 | 0 | 0 | 0
3388 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalkora to accommodate FHTC , SM/11524 | Augmentation | Acceptance cum work order for Laying of UPVC distribution main and Providing FHTC (Functional Household Tap Connection ) by augmentation for Nalkora water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | 3588/BD | 08/12/2022 | 30 | SARKAR ENTERPRISE & CO. | 69.53 | 62.47 | 100 | 99
3389 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalkora to accommodate FHTC , SM/11524 | Augmentation | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Nalkora W/S Scheme including increasing the height of back wash tank at Basirhat - I Block under Basirhat Sub Division, PHE Dte. Capacity - 10.81 Cum/hr. | 920/BD | 15/03/2024 | 240 | MONDAL PRECISION PVT.LTD | 23.26 | 16.77 | 72.08 | 60
3390 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC , SM/11540 | Augmentation | Material Requisition To Resource Division | 3687/BD | 14/12/2022 | 0 | Resource Division | 7.03 | 0 | 0 | 0
3391 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC , SM/11540 | Augmentation | Material Requisition To Resource Division | 3710/BD | 15/12/2022 | 0 | Resource Division | 18.47 | 0 | 0 | 0
3392 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC , SM/11540 | Augmentation | Repairing & Renovation 2(Two) nos of Pump House and allied works of Ghatpatila (Zone-I) water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 539/Bon | 03/11/2021 | 21 | ROY CHOWDHURY CONSTRUCTION. | 2.52 | 2.49 | 98.83 | 1
3393 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC , SM/11540 | Augmentation | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) For Augmentation of Ghatpatila Zone-I Water Supply Scheme in Bagdah Block under Bongaon Sub-Division, PHE Dte. | 3469/BD | 01/12/2022 | 90 | H.I.ENTERPRISE. | 471.66 | 413.3 | 100 | 0
3394 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC , SM/11540 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer at Ghatpatila (Zone-I) water supply scheme (Head Work Site) under Bongaon Sub-Division P.H.E.Dte. Part-A | 1548/BD | 22/05/2023 | 30 | SAHA CONSTRUCTION & CO | 16.16 | 13.69 | 100 | 100
3395 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC , SM/11540 | Augmentation | Acceptance cum work order forSinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer at Ghatpatila (Zone-I) water supply scheme (2nd T/W Site) under Bongaon Sub-Division P.H.E.Dte.-- Part- B | 1547/BD | 22/05/2023 | 30 | SAHA CONSTRUCTION & CO | 16.17 | 13.75 | 100 | 100
3396 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC , SM/11540 | Augmentation | Supply fitting fixing of change over switch at P.H.No-I & II ,Zone-I of Ghatpatila and P.H.No- I & II of Kola W/S Scheme under EMSD-I, P.H.E. Dte. Dist.-24Pgs(N). | 1814/EMSD-I | 18/08/2023 | 15 | SUNRISE ENGINEERING CORPORATION | 0.86 | 0 | 0 | 100
3397 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC , SM/11540 | Augmentation | Material Requisition To Resource Division | 1255/BD | 25/04/2023 | 0 | Resource Division | 73.62 | 0 | 0 | 0
3398 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC , SM/11540 | Augmentation | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Ghatpatila (Zone-I) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division P.H.E. Dte. | 4464/BD | 21/11/2023 | 23 | KAMAL HALDER. | 6.86 | 3.43 | 50.09 | 60
3399 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC , SM/11540 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Ghatpatila (Zone-I) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 4408/BD | 10/11/2023 | 60 | ONKAR ENTERPRISE. | 11.79 | 0 | 0 | 100
3400 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC , SM/11540 | Augmentation | Enhancement of GST for providing Functional Household Tap Connection (FHTC) in connection with JJM and Jal Swapna Programme within command area of Ghatpatila Zone-I WS Scheme | BP-02024-25-262 | 12/09/2024 | 0 | H.I.ENTERPRISE. | 22.17 | 0 | 0 | 0
3401 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC , SM/11540 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe and Tube well connection under Augmentation work at Ghatpatila W/S Scheme (Zone - I), Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1770/BD | 01/07/2024 | 315 | ROY CHOWDHURY CONSTRUCTION. | 22.88 | 7.37 | 32.21 | 100
3402 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC , SM/11540 | Augmentation | Repairing of outdoor light & allied work at P.H. no.l , Zone -I of Ghatpatila WS Scheme under EMSD-l, P.H.E. Dte. Dist.-24Pgs(N). | 450/EMSD-I | 08/04/2025 | 84 | GHOSH AND GHOSH | 2.66 | 0 | 0 | 100
3403 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC , SM/11592 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Chowberia Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 127/BON | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.45 | 3.43 | 50 | 1
3404 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC , SM/11592 | Augmentation | Material Requisition To Resource Division | 3689/BD | 14/12/2022 | 0 | Resource Division | 124.58 | 0 | 0 | 0
3405 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC , SM/11592 | Augmentation | Material Requisition To Resource Division | 3662/BD | 13/12/2022 | 0 | Resource Division | 14 | 0 | 0 | 0
3406 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC , SM/11592 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Chowberia Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 3546/BD | 06/12/2022 | 90 | M/S B.K.ENTERPRISE. | 279.32 | 227.89 | 81.59 | 1
3407 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC , SM/11592 | Augmentation | Repairing & Renovation 2(Two) nos of Pump House and allied works of Chowberia water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 532/Bon | 03/11/2021 | 21 | A.D.ENTERPRISE. | 2.52 | 2.51 | 100 | 1
3408 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC , SM/11592 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep) under Krishnachandrapur W/S Scheme and Chowberia W/S Scheme District of 24 Pgs. (N) | 4801/EMD | 09/08/2023 | 511 | A.G ENTERPRISE. | 52.15 | 24.25 | 100 | 100
3409 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC , SM/11592 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chauberia water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | 2695/BD | 04/09/2023 | 30 | DHELA BABA ENTERPRISE | 16.17 | 11.74 | 100 | 100
3410 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC , SM/11592 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chauberia Water Supply Scheme (H/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte | 2923/BD | 26/09/2023 | 30 | SAHA CONSTRUCTION & CO | 16.14 | 13.72 | 100 | 100
3411 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC , SM/11592 | Augmentation | Acceptance cum work order for Construction of Boundary wall aand Construction of Approach Road at 1st T/W site under Augmentation of Chauberia water Supply scheme, Bongaon Block within jurisdiction of Bongaon Sub-Division, under Barasat Division P.H.E. Dte. | 4485/BD | 23/11/2023 | 23 | TAPAN GHOSH. | 5.58 | 5.57 | 100 | 100
3412 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC , SM/11592 | Augmentation | Quotation for New service connection at OHR site of Chowberia water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N) | BP-181 | 13/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.46 | 0 | 0 | 0
3413 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC , SM/11592 | Augmentation | Acceptance cum work order for Improvement of Iron Elimination Plant and other related allied works and Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Chauberia Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte | 53/BD | 05/01/2024 | 420 | TAPAN GHOSH. | 6.03 | 0 | 0 | 100
3414 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC , SM/11592 | Augmentation | Acceptance cum work order for Construction of Boundary wall, Approach Road, Earth Filling and Construction of 3.60 mtr. X 3.00 mtr. size Guard Room with sanitary and water supply arrangement incl. plinth protection at OHR site of Chowberia Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 2418/BD | 23/08/2024 | 420 | M/S B.K.ENTERPRISE. | 35.07 | 0 | 0 | 100
3415 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC , SM/11603 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Ramnagar Water Supply Scheme in Gaighata Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 146/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.98 | 2.98 | 100 | 1
3416 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC , SM/11603 | Augmentation | Repairing & Renovation of 02No. Pump House and allied works at Ramnagar water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 541/BON | 03/11/2021 | 21 | MA CONSTRUCTION. | 2.52 | 2.47 | 100 | 1
3417 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC , SM/11603 | Augmentation | Material Requisition To Resource Division | 3691/BD | 14/12/2022 | 0 | Resource Division | 12.68 | 0 | 0 | 0
3418 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC , SM/11603 | Augmentation | Material Requisition To Resource Division | 3663/BD | 13/12/2022 | 0 | Resource Division | 7.98 | 0 | 0 | 0
3419 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC , SM/11603 | Augmentation | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) For Augmentation of Ramnagar Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 3472/BD | 01/12/2022 | 90 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 200.08 | 199.57 | 100 | 1
3420 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC , SM/11603 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Ramnagar water supply scheme at Head Work Site under Bongaon Sub-Division P.H.E.Dte. | 2685/BD | 04/09/2023 | 30 | SAHA CONSTRUCTION & CO | 16.17 | 11.73 | 100 | 100
3421 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC , SM/11603 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Zone-I)(Rep.) and Pump house no-III (New) under Dakshin Bhebia W/S Scheme with Pump House No-I and II under Ramnagar W/S scheme District of 24 Pgs. (N) | 4808/EMD | 09/08/2023 | 30 | A.G ENTERPRISE. | 53.18 | 19.14 | 89.98 | 40
3422 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC , SM/11603 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Ramnagar water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | 2684/BD | 04/09/2023 | 30 | SAHA CONSTRUCTION & CO | 16.17 | 11.22 | 100 | 100
3423 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC , SM/11603 | Augmentation | Acceptance cum work order for Repairing of Boundary wall at Head Work site, Construction of Boundary wall at 2nd Pump House site and Construction of Approach Road at Head Work site and 2nd T/W Site under Augmentation of Ramnagar Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 565/BD | 22/02/2024 | 45 | JP CONSTRUCTION & SUPPLIERS. | 12.84 | 12.65 | 100 | 100
3424 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC , SM/11603 | Augmentation | Acceptance cum work order for Improvement of Iron Elimination Plant and other related allied works and Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Ramnagar Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 630/BD | 28/02/2024 | 45 | GHOSH CONSTRUCTION | 5.97 | 5.96 | 100 | 100
3425 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC , SM/11603 | Augmentation | Connection of 2 nos. newly sunk Replaced Tube well with rising main by DI pipe and I.E.P. back wash pipe line with UPVC pipe, Construction of Valve Chamber and Inspection pit and repairing Air-Blower and Air-Compressor of existing I.E.P. due to submerged in water during moon soon for Augmentation of Ramnagar W/S Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 815/Bon | 26/06/2025 | 45 | A.D.ENTERPRISE. | 4.96 | 0 | 0 | 0
3426 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC , SM/11533 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I under AKIPUR W/S Scheme District of 24 Pgs. (N) | 6380 / EMD | 14/08/2022 | 30 | A.S. ENTERPRISE | 13.05 | 9.86 | 75.56 | 1
3427 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC , SM/11533 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under AKIPUR W/S Scheme District of 24 Pgs. (N) | 6447 / EMD | 14/08/2022 | 30 | M/S GHOSH ENTERPRISE | 13.04 | 9.86 | 100 | 1
3428 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC , SM/11533 | Augmentation | Material Requisition To Resource Division | 2309/BD | 03/08/2022 | 0 | Resource Division | 11.42 | 0 | 0 | 0
3429 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC , SM/11533 | Augmentation | Material Requisition To Resource Division | 1100/BD | 06/04/2023 | 0 | Resource Division | 11.42 | 0 | 0 | 0
3430 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC , SM/11533 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Akipur water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | 3374/BD | 18/11/2022 | 90 | SUPER SKILL. | 145.01 | 105.64 | 72.85 | 50
3431 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC , SM/11533 | Augmentation | Acceptance cum work order for Balance FHTC works and Eucalyptus Bullah Pilling with earth filling in different location for protection of DI / UPVC distribution Pipe line for Augmentation of Akipur water supply scheme in Basirhat - II Block under Basirhat Sub-Division under Barasat Division, PHE Dte. | 512/BD | 20/02/2024 | 30 | SUPER SKILL. | 41.71 | 0 | 0 | 0
3432 | NORTH 24 PARGANAS | Central Drilling | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC , SM/11533 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Akipur W/S Scheme (T/W-I) , Basirhat-II Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | 548/CDD | 02/06/2023 | 395 | UTTAM KUMAR CHATTERJEE | 21.56 | 10.76 | 100 | 100
3433 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC , SM/11533 | Augmentation | Acceptance cum work order for Balance work of Providing FHTC (Functional Household Tap Connection) by Augmentation For Akipur Water Supply Scheme in Basirhat-II Block of North 24 Parganas District within Basirhat Sub-Division under Barasat Division PHE Dte. | 2000/BD | 17/06/2025 | 360 | M/S MITRA CONSTRUCTION. | 56.17 | 0 | 0 | 0
3434 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC , SM/11533 | Augmentation | Acceptance cum work order for Renovation of Iron Elimination Plant at Taranipur zone - I W/S Scheme (50.0 m3/hr) at Swarupnagar Block and Akhipur W/S Scheme (33.375m3/hr) at Basirhat - II Block under Basirhat Sub division, PHE Dte of Barasat Division PHE Dte. | 2022/BD | 18/06/2025 | 120 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 19.65 | 0 | 0 | 70
3435 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC , SM/11607 | Augmentation | Material Requisition To Resource Division | 490/BD | 17/02/2023 | 0 | Resource Division | 89.49 | 0 | 0 | 0
3436 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC , SM/11607 | Augmentation | Material Requisition To Resource Division | 604/BD | 23/02/2023 | 0 | Resource Division | 9.83 | 0 | 0 | 0
3437 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC , SM/11607 | Augmentation | Material Requisition To Resource Division | 4420/BD | 10/11/2023 | 0 | Resource Division | 9.36 | 0 | 0 | 0
3438 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC , SM/11607 | Augmentation | Acceptance cum work order for Renovation of Iron Elimination Plant at Shankarpur W/S Scheme at Basirhat- I Block under Basirhat Sub division, PHE Dte. Capacity- 93.0625 m3/hr. | 922/BD | 15/03/2024 | 60 | NEER UDYOG | 16.57 | 16.34 | 100 | 80
3439 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC , SM/11607 | Augmentation | New Service Connection at PH-I under Shankarpur W/S Scheme. | BP-311-23-24 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.84 | 0 | 0 | 0
3440 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC , SM/11607 | Augmentation | New Service Connection at PH-II under Shankarpur W/S Scheme. | BP-312-23-24 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.52 | 0 | 0 | 0
3441 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC , SM/11607 | Augmentation | Acceptance cum work order for Restoration of roads under different water supply schemes of Basirhat I Block under Barasat Division P.H.E.Dte. | 3626/BD | 20/12/2024 | 180 | NISHITH BANERJEE | 45.36 | 0 | 0 | 100
3442 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC , SM/11607 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Sankarpur and P/H-II under Debhog W/S Scheme with Pump House No-I under Gachharhati W/S Scheme District of 24 Pgs. (N). | 1483/EMD | 03/06/2024 | 298 | EASTERN INDIA SALES & SERVICE | 52.16 | 0 | 0 | 25
3443 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC , SM/11607 | Augmentation | Formal work order for Laying of DI/UPVC Distribution System pipeline and Providing FHTC (Functional Household Tap Connection ) for augmentation of Sankarpur water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | 3602/BD | 09/12/2022 | 923 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 459.43 | 346.92 | 78.51 | 76
3444 | NORTH 24 PARGANAS | Barasat Division | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (JHIKRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | 279/HSD | 09/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 1.46 | 1.46 | 100 | 1
3445 | NORTH 24 PARGANAS | Barasat Division | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (JHIKRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | 279/HSD | 09/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 1.46 | 0 | 0 | 1
3446 | NORTH 24 PARGANAS | Barasat Division | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (JHIKRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 278/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 0 | 0 | 1
3447 | NORTH 24 PARGANAS | Eastern Mechanical | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (New) under Jhikra W/S Scheme District of 24 Pgs. (N) | 4721/EMD | 04/08/2023 | 30 | DEY ENTERPRISE | 21.13 | 0 | 0 | 0
3448 | NORTH 24 PARGANAS | Barasat Division | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (JHIKRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 278/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
3449 | NORTH 24 PARGANAS | Barasat Division | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Material Requisition To Resource Division | 873/BD | 22/03/2023 | 0 | Resource Division | 17.57 | 0 | 0 | 0
3450 | NORTH 24 PARGANAS | Barasat Division | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Acceptance cum work order for Construction of RCC culvert, cut-off wall, approach road and other allied works at Over Head Reservoir site (HW site) for Jhikra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 677/BD | 01/03/2024 | 14 | NURJAHAN ENTERPRISE. | 8.5 | 7.51 | 88.42 | 86
3451 | NORTH 24 PARGANAS | Barasat Division | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Acceptance cum work order for Construction of RCC culvert, cut-off wall, approach road and other allied works at Kalil Khal N/H/O Rajjack Molla (Between node point 101 to 294) for Jhikra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1528/BD | 07/06/2024 | 271 | RUDRA DAS. | 9.89 | 7.87 | 79.58 | 85
3452 | NORTH 24 PARGANAS | Barasat Division | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Acceptance cum work order for Protection works for protection of newly laid UPVC distribution pipe line at near Jhikra Radhagobinda Mandir at Jhikra Purba para within Jhikra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 3465/BD | 09/12/2024 | 30 | STAR CONSTRUCTION. | 9.41 | 0 | 0 | 0
3453 | NORTH 24 PARGANAS | Barasat Division | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Acceptance cum work order for Protection works for protection of newly laid UPVC distribution pipe line at N/H/O Utpal Mondal at Jhikra Paschim para within Jhikra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E.Dte. | 3676/BD | 24/12/2024 | 30 | A. M. ENTERPRISE (BASIRHAT) | 9.06 | 0 | 0 | 0
3454 | NORTH 24 PARGANAS | Barasat Division | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Jhikra W/S scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 879/HSD | 07/08/2024 | 10 | M/S NIRMAN CONSTRUCTION. | 0.75 | 0.75 | 100 | 100
3455 | NORTH 24 PARGANAS | Eastern Mechanical | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Quotation for Service Connection Charges for PH- I under Jhikra W/S Scheme in the district of North 24 Pgs. | BP-352-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.54 | 0 | 0 | 0
3456 | NORTH 24 PARGANAS | Eastern Mechanical | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Service connection charges at PH-I under Jhikra W/S Scheme | BP-296-23-24 | 28/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.71 | 0 | 0 | 0
3457 | NORTH 24 PARGANAS | Eastern Mechanical | Jhikra Piped Water Supply Scheme. , SM/12719 | New | New service connection at P.H.No- I of Jhikra water supply scheme under EMSD-I ,PHE Dte .im24Pgs(N). | BP-299-23-24 | 28/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.53 | 0 | 0 | 0
3458 | NORTH 24 PARGANAS | Barasat Division | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Jhikra w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1704/BD | 08/06/2023 | 1086 | M/S NIRMAN CONSTRUCTION. | 403.64 | 320.05 | 79.29 | 80
3459 | NORTH 24 PARGANAS | Barasat Division | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Acceptance cum work order for Protection works for protection of newly laid UPVC distribution pipe line at N/H/O Pankaj Mondal at Jhikra Majher para within Jhikra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 3642/BD | 23/12/2024 | 120 | GAZI ENTERPRISE | 9.32 | 0 | 0 | 100
3460 | NORTH 24 PARGANAS | Barasat Division | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Acceptance cum work order for Construction of boundary wall with column structure at Head Work site (PH No-1) & PH No- 2 within Jhikra w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1027/BD | 28/03/2025 | 90 | M/S NIRMAN CONSTRUCTION. | 31.11 | 0 | 0 | 0
3461 | NORTH 24 PARGANAS | Barasat Division | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Acceptance cum work order for Protection works for protection of newly laid UPVC distribution pipe line at N/H/O Ashoke Patra at Jhikra Purba para within Jhikra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 3459/BD | 09/12/2024 | 90 | M/S TAMAL CHAKRABORTY. | 9.4 | 0 | 0 | 100
3462 | NORTH 24 PARGANAS | Barasat Division | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Acceptance cum work order for Protection works for protection of newly laid UPVC distribution pipe line at N/H/O Bakul Patra at Jhikra Madhya para within Jhikra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 3458/BD | 09/12/2024 | 60 | ARBINA ENTERPRISE. | 9.06 | 0 | 0 | 100
3463 | NORTH 24 PARGANAS | Barasat Division | Jhikra Piped Water Supply Scheme. , SM/12719 | New | Acceptance cum work order for Protection works for protection of newly laid UPVC distribution pipe line at N/H/O Barun Patra at Jhikra Purba para within Jhikra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 3464/BD | 09/12/2024 | 120 | ABDUL HAMID GAZI. | 9.72 | 0 | 0 | 100
3464 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-II) , SM/08075 | Retrofitting | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1 (Defunct tube well site) with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Rupmari w/s scheme (Zone-V), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 1750/BD | 20/06/2022 | 30 | M/S K.P.PAL. | 21.33 | 13.02 | 100 | 1
3465 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-II) , SM/08075 | Retrofitting | Material Requisition To Resource Division | 2991/BD | 29/09/2022 | 0 | Resource Division | 0.2 | 0 | 0 | 0
3466 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-II) , SM/08075 | Retrofitting | Material Requisition To Resource Division | 678/BD | 01/03/2023 | 0 | Resource Division | 24.64 | 0 | 0 | 0
3467 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for DIghari Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10098 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Dighari Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | 1185/NWSD-I | 31/12/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.52 | 3.52 | 100 | 1
3468 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for DIghari Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10098 | Augmentation | Material Requisition To Resource Division | 674/NWSD-I | 26/05/2022 | 0 | Resource Division | 81.68 | 0 | 0 | 0
3469 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for DIghari Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10098 | Augmentation | Material Requisition To Resource Division | 640/NWSD-I | 20/05/2022 | 0 | Resource Division | 18.63 | 0 | 0 | 0
3470 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for DIghari Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10098 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir of 550 Cum capacity at Head work site and other allied works at DIGHARI under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | 1239/NWSD-I | 18/08/2023 | 60 | MONDAL ENTERPRISE | 52.05 | 48.54 | 100 | 100
3471 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for DIghari Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10098 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House Hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC , Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of Dighari Water Supply Scheme under North 24 Parganas Water Supply Division-I PHE Dte. | 669/NWSD-I | 26/05/2022 | 90 | M/S. S.S. ENTERPRISE | 581.29 | 580.42 | 100 | 82
3472 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for DIghari Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10098 | Augmentation | Renovation of AIRP at Dighari Water Supply Scheme of capacity 110 Cu.m/hr of Bongaon Block under North 24 Pgs. W/S Div-I, PHE Dte. | 1750/NWSD-I | 29/11/2024 | 540 | MONDAL ENTERPRISE | 82.77 | 0 | 0 | 62
3473 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for DIghari Water Supply Scheme in Bongaon Block of North 24 Parganas District. , SM/10098 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1431/NWSD-I | 18/09/2024 | 7 | IMAGIN | 4.59 | 0 | 0 | 95
3474 | NORTH 24 PARGANAS | Barasat Division | Bamanpukuria Piped Water Supply Scheme. , SM/13814 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BAMANPUKURIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | 246/HSD | 03/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 3.99 | 3.99 | 100 | 1
3475 | NORTH 24 PARGANAS | Barasat Division | Bamanpukuria Piped Water Supply Scheme. , SM/13814 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BAMANPUKURIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 245/HSD | 03/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
3476 | NORTH 24 PARGANAS | Barasat Division | Bamanpukuria Piped Water Supply Scheme. , SM/13814 | New | Material Requisition To Resource Division | 887/BD | 22/03/2023 | 0 | Resource Division | 17.54 | 0 | 0 | 0
3477 | NORTH 24 PARGANAS | Barasat Division | Bamanpukuria Piped Water Supply Scheme. , SM/13814 | New | Acceptance cum work order for Arrangement Of Block Level Orientation programe involving stakeholders of PRI bodies including refreshments, training materials and related activities for 1 no Block (Minakhan) in North 24 Parganas under Barasat Division, P.H.E Dte. | 756/HSD | 19/07/2024 | 10 | IMAGIN | 0.49 | 0 | 0 | 100
3478 | NORTH 24 PARGANAS | Barasat Division | Bamanpukuria Piped Water Supply Scheme. , SM/13814 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 250 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at P.H. No.-1 (Size-5.40 x 3.60 mtr.) & P.H. No.-2 (Size-3.60 x 3.00 mtr.) for Bamanpukuria w/s scheme, Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | 1706/BD | 08/06/2023 | 1096 | MONDAL & CO. (BASIRHAT). | 462.55 | 332.94 | 71.98 | 86
3479 | NORTH 24 PARGANAS | Barasat Division | Bamanpukuria Piped Water Supply Scheme. , SM/13814 | New | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tube well by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for within Bamanpukuria & Khariberia w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 635/BD | 28/02/2025 | 45 | ACME CONSTRUCTION | 51.71 | 0 | 0 | 0
3480 | NORTH 24 PARGANAS | Barasat Division | Bamanpukuria Piped Water Supply Scheme. , SM/13814 | New | Formal work order for Additional Laying of UPVC distribution pipe line, protection works & other allied works within Bamanpukuria w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 2736/BD | 20/09/2024 | 300 | M.R.CONSTRUCTION. | 130.43 | 0 | 0 | 70
3481 | NORTH 24 PARGANAS | Barasat Division | Bamanpukuria Piped Water Supply Scheme. , SM/13814 | New | Acceptance cum work order for Protection works for newly laid different dia. UPVC/DI pipe line at near Head Work site for Bamanpukuria w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 2095/BD | 26/07/2024 | 149 | ANKUSH CONSTRUCTION & CO. | 8.12 | 0 | 0 | 100
3482 | NORTH 24 PARGANAS | Barasat Division | Bamanpukuria Piped Water Supply Scheme. , SM/13814 | New | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at OHR site within Bamanpukuria w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 540/HSD | 10/03/2025 | 10 | TRISHA ENTERPRISE & CO. | 0.95 | 0 | 0 | 100
3483 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC , SM/12895 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Bithari Z-II Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte | 452/BHT | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.75 | 4.75 | 100 | 1
3484 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC , SM/12895 | Augmentation | Additional Survey work for DPR Preparation for BITHARI ZONE -2 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 453/BHT | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.63 | 0.63 | 100 | 1
3485 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC , SM/12895 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. big dia. 330 mtr deep tubewell by D.R. Rig method using PVC pipe & strainer having 300 mm dia. 36 mtr. long filter for Augmentation of Bithari Zone-IIB water supply scheme in Baduria Block of Basirhat Sub-Division, under Barasat Division, P.H.E. Dte. | 2801/BD | 12/09/2023 | 30 | DHELA BABA ENTERPRISE | 23.31 | 0 | 0 | 0
3486 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC , SM/12895 | Augmentation | Material Requisition To Resource Division | 1263/BD | 25/04/2023 | 0 | Resource Division | 52.64 | 0 | 0 | 0
3487 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC , SM/12895 | Augmentation | Material Requisition To Resource Division | 4427/BD | 10/11/2023 | 0 | Resource Division | 23.94 | 0 | 0 | 0
3488 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC , SM/12895 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bithari Zone-II A water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | 1710/BD | 08/06/2023 | 629 | UTPAL CONSTRUCTION & CO. | 234.15 | 177.81 | 75.94 | 50
3489 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC , SM/12895 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-II)(Rep.) under Bithari W/S Scheme District of 24 Pgs. (N) | 4726/EMD | 04/08/2023 | 30 | SINHA ELECTRICALS | 26.08 | 5.77 | 22.14 | 60
3490 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bithari Zone-II to accommodate FHTC , SM/12895 | Augmentation | Regarding Restoration charges for road damages. | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 24.25 | 0 | 0 | 0
3491 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area Shankarpur Water Supply Scheme at Basirhat-I Block, Dist.-North 24 Parganas (Phase-I) , SM/07614 | Retrofitting | Acceptance cum work order for Additional Survey Work For DPR Preparation of Sandeshkhali Water Supply Scheme under Barasat Division, PHE Dte. | 2149/HSD | 28/12/2021 | 21 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 1.17 | 1.17 | 100 | 1
3492 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area Shankarpur Water Supply Scheme at Basirhat-I Block, Dist.-North 24 Parganas (Phase-I) , SM/07614 | Retrofitting | Acceptance cum work order for Additional Survey Work For DPR Preparation of Mohanpur (Zone-I & Zone-II) Water Supply Scheme under Barasat Division, PHE Dte. | 2141/HSD | 28/12/2021 | 21 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 2.33 | 2.32 | 100 | 1
3493 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area Shankarpur Water Supply Scheme at Basirhat-I Block, Dist.-North 24 Parganas (Phase-I) , SM/07614 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Sandeshkhali Water Supply Scheme under Barasat Division, PHE Dte. | 2148/HSD | 28/12/2021 | 21 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 3.92 | 3.92 | 100 | 1
3494 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area Shankarpur Water Supply Scheme at Basirhat-I Block, Dist.-North 24 Parganas (Phase-I) , SM/07614 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for SANKARPUR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | 192/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.24 | 4.24 | 100 | 1
3495 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area Shankarpur Water Supply Scheme at Basirhat-I Block, Dist.-North 24 Parganas (Phase-I) , SM/07614 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Shankarpur Supply Scheme at Basirhat-I Block under Barasat Division, PHE Dte. | 488/BD. | 26/02/2021 | 90 | UMWELT ENGINEER PVT.LTD. | 96.9 | 27.67 | 100 | 1
3496 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area Shankarpur Water Supply Scheme at Basirhat-I Block, Dist.-North 24 Parganas (Phase-I) , SM/07614 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Mohanpur (Zone-I & Zone-II) Water Supply Scheme under Barasat Division, PHE Dte. | 2140/HSD | 28/12/2021 | 21 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.77 | 4.77 | 100 | 1
3497 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12728 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-IA/II (Chak Kanthalia) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 329/NWSD-I | 24/03/2022 | 1 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.98 | 3.79 | 100 | 1
3498 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12728 | Augmentation | Material Requisition To Resource Division | 473/NWSD-I | 26/04/2023 | 0 | Resource Division | 90.86 | 0 | 0 | 0
3499 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12728 | Augmentation | Chak Kanthalia |  | 27/06/2023 | 0 | WBSEDCL | 1.66 | 0 | 0 | 0
3500 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12728 | Augmentation | Quotation for service connection for OHR site at Zone IA-II ( Chalk Kanthalia ) in Barrackpore-II block | 162 | 03/08/2023 | 0 | WBSEDCL | 5.04 | 0 | 0 | 0
3501 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12728 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I, A-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District. | 4889/ED | 27/12/2023 | 183 | BENGAL CONSTRUCTION | 59.48 | 0 | 0 | 0
3502 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12728 | Augmentation | Supply and installation of Display Board to be placeed at BILKANDA ZONE-I, BANDIPUR, BILKANDA ZONE-II, PATULIA and MOHANPUR, Zone-I-B (Telinipara), Zone-IA-II (Chak Kanthalia) pipe water supply scheme for Barrackpore-II Block under North 24 Pgs. Water Supply Division-I, PHE. Dte. | 70/NWSD-I | 10/01/2024 | 30 | BIBHAS PAL | 4.94 | 0.7 | 100 | 100
3503 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12728 | Augmentation | Material Requisition To Resource Division | 1709/NWSD-I | 26/11/2024 | 0 | Resource Division | 55.44 | 0 | 0 | 0
3504 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12728 | Augmentation | Supplimentary quotation for Patulia PH No 3 ( Near Ruiya Verir Gate ) |  | 27/07/2023 | 0 | WBSEDCL | 5.04 | 0 | 0 | 0
3505 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12728 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 60.45 | 6.42 | 2
3506 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12728 | Augmentation | Road restoration along flank portion of bituminous road of PWD/ PMGSY/ Zilla Parisad/ Panchayet road due to laying of pipeline under Augmentation work at Chak Kanthalia (Zone- IA-II) W/S Scheme in Barrackpore-II Block under North 24Pgs. W/S Division-I, P.H.E. Dte. | 771/NWSD-I | 23/05/2025 | 225 | A.K.C. SUPPLY & CONSTRUCTION | 36.5 | 0 | 0 | 60
3507 | NORTH 24 PARGANAS | Barasat Division | Debitala Piped Water Supply Scheme , SM/13523 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (DEBITALA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | 273/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.48 | 2.48 | 100 | 1
3508 | NORTH 24 PARGANAS | Barasat Division | Debitala Piped Water Supply Scheme , SM/13523 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (DEBITALA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 272/HSD | 09/02/2022 | 15 | UMWELT ENGINEER PVT.LTD. | 4.82 | 4.82 | 100 | 1
3509 | NORTH 24 PARGANAS | Barasat Division | Debitala Piped Water Supply Scheme , SM/13523 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BARGAN GOPALPUR Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | 248/HSD | 03/02/2022 | 15 | UMWELT ENGINEER PVT.LTD. | 3.2 | 3.2 | 100 | 1
3510 | NORTH 24 PARGANAS | Barasat Division | Debitala Piped Water Supply Scheme , SM/13523 | New | Material Requisition To Resource Division | 895/BD | 22/03/2023 | 0 | Resource Division | 27.76 | 0 | 0 | 0
3511 | NORTH 24 PARGANAS | Eastern Mechanical | Debitala Piped Water Supply Scheme , SM/13523 | New | Quotation for Service Connection Charges for PH- II under Debitala W/S Scheme in the district of North 24 Pgs. | BP-85-24-25 | 09/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.47 | 0 | 0 | 0
3512 | NORTH 24 PARGANAS | Barasat Division | Debitala Piped Water Supply Scheme , SM/13523 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 250 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Debitala w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1703/BD | 08/06/2023 | 911 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 399.18 | 306.61 | 76.81 | 86
3513 | NORTH 24 PARGANAS | Barasat Division | Debitala Piped Water Supply Scheme , SM/13523 | New | Formal work order for Protection of different dia. UPVC pipeline by UC bullah & Bamboo pile at diff. places and emergent restoration of road at HW site in Debitala w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | 3624/BD | 20/12/2024 | 180 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 147.18 | 0 | 0 | 85
3514 | NORTH 24 PARGANAS | Barasat Division | Debitala Piped Water Supply Scheme , SM/13523 | New | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection within Debitala water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 528/HSD | 10/03/2025 | 10 | SARKAR ENTERPRISE | 0.72 | 0 | 0 | 0
3515 | NORTH 24 PARGANAS | Barasat Division | Debitala Piped Water Supply Scheme , SM/13523 | New | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection within Debitala water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 932/HSD | 29/05/2025 | 10 | SARKAR ENTERPRISE | 0.72 | 0 | 0 | 100
3516 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa , SM/13528 | Retrofitting | Formal work order for Land development, Construction of Office cum Guard room and Switch cum Chlorine Room, Boundary wall, Surface drain and related allied works at Zonal Head work site - XIV i.e. Kumra /Zonal Head work site - XVI i.e.Nangla including Laying Distribution System within the jurisdiction of (Zone-XIV) /(Zone-XVI), Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Surface Water based Water Supply Scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoining Mouzas under North 24 Parganas District project within Barasat Division, P.H.E. Dte. Habra-I Block PART-C / Habra-I Block PART-E. | 110/BD | 10/01/2024 | 910 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3691.85 | 0 | 0 | 88
3517 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District proj , SM/13536 | Retrofitting | Formal work order for Laying of Distribution system, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works and Providing FHTC within the jurisdiction of (Zone-XXI) under Habra-Gaighata surface based PWSS of Gaighata Block under Barasat Division, P.H.E. Dte. | 2953/BD | 29/09/2023 | 901 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1791.33 | 451.1 | 61.32 | 85
3518 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District , SM/13538 | Retrofitting | Formal work order for Laying of Distribution system, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works and Providing FHTC within the jurisdiction of (Zone-XIX) under Habra-Gaighata surface based PWSS of Gaighata Block under Barasat Division, P.H.E. Dte. | 2954/BD | 29/09/2023 | 901 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1879.95 | 388.77 | 45.01 | 95
3519 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District , SM/14543 | Retrofitting | Formal work order for Laying of Distribution System, Providing FHTC, Construction of Office cum Guard room, Land development and Switch cum Chlorine Room, Boundary wall, Surface drain and other allied works within the jurisdiction of (Zone-XX) i.e. Matikumra / (Zone-XXII) i.e. Chikanpara under Habra-Gaighata surface based PWSS, of Gaighata Block under Barasat Division, P.H.E. Dte. GAIGHATA BLOCK, PART-B / Gaighata Block, PART-D | 4073/BD | 16/10/2023 | 1095 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2790.09 | 437.82 | 41.32 | 88
3520 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Kaugachhi Zone-I Piped Water Supply Scheme , SM/14499 | New | Survey, Design Drawing & DPR Preparation for NEW PWSS (KAUGACHHI ZONE-I Water Supply Scheme) in BARRACKPUR-I BLOCK under N 24 Pgs W/S Div-I, PHE Dte. | 123/NWSD-I | 02/02/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.96 | 4.96 | 100 | 1
3521 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Kaugachhi Zone-I Piped Water Supply Scheme , SM/14499 | New | Material Requisition To Resource Division | 451/NWSD-I | 26/04/2023 | 0 | Resource Division | 4.14 | 0 | 0 | 0
3522 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Kaugachhi Zone-I Piped Water Supply Scheme , SM/14499 | New | Laying of Distribution System, Rising Main including specials, valves and pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir with pile foundation and pipe connection including cost of pipes & specials with soil investigation, Construction of Pump House (4.88m X 3.66m) including Sanitary Arrangement, Construction of Boundary Wall, Construction of Service Road, Improvement Of Land, Pipe carring structure for a span of 25 Meter for crossing of a Canal / River etc. for Augmentation of Ground Water Based Piped Water Supply Scheme for KAUGACHHI ZONE-I in Barrackpur-I Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | 1676/NWSD-I | 30/10/2023 | 1096 | BANERJEE CONSTRUCTION | 386.74 | 0 | 0 | 0
3523 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Gar Shyamnagar Piped Water Supply Scheme , SM/14504 | New | Laying of Distribution System, Rising Main including specials, valves and pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir with pile foundation and pipe connection including cost of pipes & specials with soil investigation, Construction of Pump House (4.88m X 3.66m) including Sanitary Arrangement, Construction of Boundary Wall, Construction of Service Road, Improvement Of Land, Pipe carring structure for a span of 25 Meter for crossing of a Canal / River etc. for Augmentation of Ground Water Based Piped Water Supply Scheme for Gar Shyamnagar in Barrackpur-I Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | 1678/NWSD-I | 30/10/2023 | 365 | NOVELTY ENTERPRISE | 462.08 | 0 | 0 | 0
3524 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Gar Shyamnagar Piped Water Supply Scheme , SM/14504 | New | Survey, Design Drawing & DPR Preparation for NEW PWSS (GAR SHYAMNAGAR Water Supply Scheme) in BARRACKPUR-I BLOCK under N 24 Pgs W/S Div-I, PHE Dte. | 119/NWSD-I | 02/02/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 6.53 | 6.53 | 100 | 1
3525 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Gar Shyamnagar Piped Water Supply Scheme , SM/14504 | New | Material Requisition To Resource Division | 450/NWSD-I | 26/04/2023 | 0 | Resource Division | 58.51 | 0 | 0 | 0
3526 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Gar Shyamnagar Piped Water Supply Scheme , SM/14504 | New | Construction of Arsenic cum Iron removal Plants (AIRP) of capacity 70 cum/hr at Head work site of Gar Shyamnagar Water Supply Scheme within the Barrackpore-l Block and other ancillary work under North 24 Pgs. W/S Division-I, P.H.E. Dte. | 490/NWSD-I | 15/03/2024 | 180 | ODISSI INNOVATIONS ENGINEERS PVT. LTD. | 209.76 | 0 | 0 | 0
3527 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Gar Shyamnagar Piped Water Supply Scheme , SM/14504 | New | Shinking of 1 no. Tube well 300mm X 200mm Big Dia.Tube well 300 Mtr. Deep by Direct Rotary Rig method using PVC pipe & UPVC deep well screen pipes with ribs etc. Including cost of Materials for Gar shyamnagar Water Supply Scheme ( H/W site ) under North 24 Parganas wate supply Division-I, P.H.E. Dte. | 431/NWSD-I | 19/03/2025 | 148 | AUXILIARY TUBEWELL DRILLER | 22.7 | 0 | 0 | 100
3528 | NORTH 24 PARGANAS | Barasat Arsenic Division | TEGHARIA Piped Water Supply Scheme , SM/16457 | New | Survey, Design Drawing & DPR Preparation for TEGHARIA Water Supply Scheme (NEW PWSS) in BARASAT-II BLOCK under Barasat Arsenic Division, PHE Dte. | 982/B.Ar.D. | 20/04/2023 | 30 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 6.01 | 6.01 | 100 | 100
3529 | NORTH 24 PARGANAS | Barasat Arsenic Division | TEGHARIA Piped Water Supply Scheme , SM/16457 | New | Laying of Distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from distribution system within command area & construction of 2 nos. pump house & Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir including soil test as per Departmental design, drawing and specification including bored pile & pile cap at TEGHARIA water supply scheme, Barasat-II block under Barasat Arsenic Division, P.H.E. Dte. | 1883/B.Ar.D. | 04/08/2023 | 366 | R. K. MANDAL & CO. | 343.74 | 0 | 0 | 0
3530 | NORTH 24 PARGANAS | Barasat Arsenic Division | TEGHARIA Piped Water Supply Scheme , SM/16457 | New | Material Requisition To Resource Division | 74/B.Ar.D | 11/01/2024 | 0 | Resource Division | 8.9 | 0 | 0 | 0
3531 | NORTH 24 PARGANAS | Barasat Division | Bhandarkhali Piped Water Supply Scheme , SM/15827 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BHANDARKHALI Water Supply Scheme) in HINGALGANJ BLOCK under Barasat Division, PHE Dte. (PART-A) | 235/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
3532 | NORTH 24 PARGANAS | Barasat Division | Bhandarkhali Piped Water Supply Scheme , SM/15827 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BHANDARKHALI Water Supply Scheme) in HINGALGANJ BLOCK under Barasat Division, PHE Dte. (PART-B) | 236/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
3533 | NORTH 24 PARGANAS | Eastern Mechanical | Bhandarkhali Piped Water Supply Scheme , SM/15827 | New | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I and II under Bhandarkhali WS Scheme Block-Hingalganj New District of 24 Pgs. N | 4873/EMD | 14/08/2023 | 30 | DEBJYOTI BASU | 20.59 | 0 | 0 | 0
3534 | NORTH 24 PARGANAS | Eastern Mechanical | Bhandarkhali Piped Water Supply Scheme , SM/15827 | New | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No. III under Bhandarkhali WS Scheme Block-Hingalganj New District of 24 Pgs.N | 4874/EMD | 14/08/2023 | 30 | DAS ENTERPRISE (BARANAGAR) | 10.3 | 0 | 0 | 0
3535 | NORTH 24 PARGANAS | Barasat Division | Bhandarkhali Piped Water Supply Scheme , SM/15827 | New | Material Requisition To Resource Division | 869/BD | 22/03/2023 | 0 | Resource Division | 45.98 | 0 | 0 | 0
3536 | NORTH 24 PARGANAS | Barasat Division | Bhandarkhali Piped Water Supply Scheme , SM/15827 | New | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1, 2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Bhanderkhali w/s scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 918/BD | 15/03/2024 | 60 | SAHA CONSTRUCTION & CO | 77.65 | 0 | 0 | 0
3537 | NORTH 24 PARGANAS | Barasat Division | Bhandarkhali Piped Water Supply Scheme , SM/15827 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No- 2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Bhandarkhali water supply scheme, Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. under Barasat Division, P.H.E. Dte. | 2512/BD | 22/08/2023 | 366 | M/S NIRMAN CONSTRUCTION. | 521.98 | 270.1 | 51.75 | 60
3538 | NORTH 24 PARGANAS | Barasat Division | Bhandarkhali Piped Water Supply Scheme , SM/15827 | New | Acceptance cum work order for Sinking of 1 No. 400.00 mtr. Deep 100 X 50 mm. dia. Trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe and strainers at T/W site-1 for Bhanderkhali w/s scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 845-HSD | 19/05/2025 | 10 | M/S NIRMAN CONSTRUCTION. | 4.15 | 0 | 0 | 0
3539 | NORTH 24 PARGANAS | Eastern Mechanical | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Barasat- I & II And Habra-II Blocks in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. , SM/15762 | Solarisation | Solarisation of WBSEDCL Energised Electrical installation including net metering at different Pipe Water Supply Scheme at Barasat-I & II and Habra-II Blocks in North 24 Parganas District under E.M.D. P.H.E. Dte. | 6356/EMD | 16/10/2023 | 183 | EQUIPMENTS AND SPARES AGENCIES | 406.04 | 0 | 0 | 0
3540 | NORTH 24 PARGANAS | Barasat Division | Bargan Gopalpur Piped Water Supply Scheme , SM/15902 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BARGAN GOPALPUR Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 247/HSD | 03/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 4.82 | 100 | 0
3541 | NORTH 24 PARGANAS | Barasat Division | Bargan Gopalpur Piped Water Supply Scheme , SM/15902 | New | Material Requisition To Resource Division | 890/BD | 22/03/2023 | 0 | Resource Division | 46.13 | 0 | 0 | 0
3542 | NORTH 24 PARGANAS | Eastern Mechanical | Bargan Gopalpur Piped Water Supply Scheme , SM/15902 | New | New service connection for Bargan Gopalpur PH-I, Bargan Gopalpur minakhan | BP-253-23-24 | 20/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.97 | 0 | 0 | 0
3543 | NORTH 24 PARGANAS | Barasat Division | Bargan Gopalpur Piped Water Supply Scheme , SM/15902 | New | Acceptance cum work order for Strengthening of existing concrete road for movement of rig machineries for sinking of big dia Tube well at PH No 2 within Bargan Gopalpur w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | 2732/BD | 07/09/2023 | 7 | GIRIDHARI DAS | 5 | 4.96 | 100 | 100
3544 | NORTH 24 PARGANAS | Barasat Division | Bargan Gopalpur Piped Water Supply Scheme , SM/15902 | New | Acceptance cum work order for Strengthening of existing concrete road for movement of rig machineries for sinking of big dia Tube well at PH No-1 within Bargan Gopalpur w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | 2715/BD | 05/09/2023 | 10 | PRITAM MUKHOPADHYAY. | 8.46 | 8.45 | 100 | 100
3545 | NORTH 24 PARGANAS | Eastern Mechanical | Bargan Gopalpur Piped Water Supply Scheme , SM/15902 | New | New Service Connection at PH-II under Bargan Gopalpur W/S Scheme | BP-262-23-24 | 02/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.84 | 0 | 0 | 0
3546 | NORTH 24 PARGANAS | Barasat Division | Bargan Gopalpur Piped Water Supply Scheme , SM/15902 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Bargan Gopalpur w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1707/BD | 08/06/2023 | 732 | M/S PROGATI ENTERPRISE. | 403.93 | 304.05 | 80.14 | 100
3547 | NORTH 24 PARGANAS | Barasat Division | Bargan Gopalpur Piped Water Supply Scheme , SM/15902 | New | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection within Bargan Gopalpur water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 933/HSD | 29/05/2025 | 10 | M/S PROGATI ENTERPRISE. | 0.72 | 0 | 0 | 100
3548 | NORTH 24 PARGANAS | Barasat Division | Bargan Gopalpur Piped Water Supply Scheme , SM/15902 | New | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection within Bargan Gopalpur water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 526/HSD | 10/03/2025 | 10 | M/S DATTA ENTERPRISE. | 0.72 | 0 | 0 | 100
3549 | NORTH 24 PARGANAS | Eastern Mechanical | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Gaighata & Swarupnagar Blocks in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. , SM/15768 | Solarisation | Solarisation of WBSEDCL Energised Electrical installation including net metering at different Pipe Water Supply Scheme at Gaighata and Swarupnagar Blocks in North 24 Parganas District under E.M.D. P.H.E. Dte. | 6458/EMD | 02/11/2023 | 180 | SWITCHING AVO ELECTRO POWER LTD. | 359 | 0 | 0 | 0
3550 | NORTH 24 PARGANAS | Barasat Arsenic Division | JATRAGACHHI Piped Water Supply Scheme , SM/16625 | New | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 2nd Tube Well Site of JATRAGACHI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1651/B.Ar.D. | 17/07/2023 | 60 | R. UNIQUE CONSTRUCTION | 6.21 | 0 | 0 | 0
3551 | NORTH 24 PARGANAS | Barasat Arsenic Division | JATRAGACHHI Piped Water Supply Scheme , SM/16625 | New | Construction of 5.48 mtr. x 3.60 mtr. size new Pump House at Head Work Site of JATRAGACHI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1661/B.Ar.D. | 18/07/2023 | 60 | M.R.H CONSTRUCTION | 7.49 | 0 | 0 | 0
3552 | NORTH 24 PARGANAS | Barasat Arsenic Division | JATRAGACHHI Piped Water Supply Scheme , SM/16625 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at Head Work site of Jatragachhi Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1671/B.Ar.D. | 19/07/2023 | 45 | SARKAR ENTERPRISE AND CO | 18.23 | 0 | 0 | 0
3553 | NORTH 24 PARGANAS | Barasat Arsenic Division | JATRAGACHHI Piped Water Supply Scheme , SM/16625 | New | Jatragachhi Piped Water Supply Scheme with Rising Main, LDS, FHTC & construction of 350 cum capacity Overhead Reservoir (OHR) including Soil investigation and foundation design at Jatragachhi under Rajarhat block, Dist.- North 24 Parganas. | 1841/B.Ar.D. | 02/08/2023 | 366 | G. B. CONSTRUCTION AND CO. | 462.81 | 0 | 0 | 0
3554 | NORTH 24 PARGANAS | NTK Mechanical | JATRAGACHHI Piped Water Supply Scheme , SM/16625 | New | Supply & Installation of pumping machineries & other electro-mechanical accessories in Jatragachi piped W/S scheme under New Town Kolkata Mechanical Division, P.H.E. Dte. | 2132/NTKMD | 11/08/2023 | 180 | GLACIER ENGINEERING CO. | 43.91 | 0 | 0 | 0
3555 | NORTH 24 PARGANAS | Barasat Arsenic Division | JATRAGACHHI Piped Water Supply Scheme , SM/16625 | New | Survey, Design Drawing & DPR Preparation for NEW PWSS (JATRAGACHHI Water Supply Scheme) in RAJARHAT BLOCK under Barasat Arsenic Division, PHE Dte. | 983/B.Ar.D. | 20/04/2023 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 7.05 | 7.05 | 100 | 100
3556 | NORTH 24 PARGANAS | Barasat Arsenic Division | JATRAGACHHI Piped Water Supply Scheme , SM/16625 | New | Material Requisition To Resource Division | 80/B.Ar.D | 11/01/2024 | 0 | Resource Division | 12.65 | 0 | 0 | 0
3557 | NORTH 24 PARGANAS | Barasat Arsenic Division | JATRAGACHHI Piped Water Supply Scheme , SM/16625 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 2nd Pump House site of Jatragachhi Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1672/B.Ar.D. | 19/07/2023 | 45 | ANKUSH CONSTRUCTION & CO. | 18.22 | 0 | 0 | 0
3558 | NORTH 24 PARGANAS | Barasat Arsenic Division | BARDASIA Piped Water Supply Scheme , SM/16626 | New | Survey, Design Drawing & DPR Preparation for BARDASIA Water Supply Scheme (NEW PWSS) in BARASAT-II BLOCK under Barasat Arsenic Division, PHE Dte. | 981/B.Ar.D. | 20/04/2023 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 7.16 | 7.16 | 100 | 100
3559 | NORTH 24 PARGANAS | Barasat Arsenic Division | BARDASIA Piped Water Supply Scheme , SM/16626 | New | Laying of Distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from distribution system within command area, Construction of 2 nos pump house and Construction of 400 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir including soil test as per Departmental design, drawing and specification including bored pile & pile cap for BARDASIA Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 1882/B.Ar.D. | 04/08/2023 | 366 | SINGHA ROY AND CO | 430.21 | 0 | 0 | 0
3560 | NORTH 24 PARGANAS | Eastern Mechanical | BARDASIA Piped Water Supply Scheme , SM/16626 | New | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Bardasia Piped Water SupplyScheme, Block: Barasat-II Dist. North 24 Pgs under EMD, PHE Dte. | 4936/EMD | 18/08/2023 | 30 | H.K. DAS & CO. | 52.08 | 0 | 0 | 0
3561 | NORTH 24 PARGANAS | Barasat Arsenic Division | BARDASIA Piped Water Supply Scheme , SM/16626 | New | Material Requisition To Resource Division | 62/B.Ar.D | 09/01/2024 | 0 | Resource Division | 12.12 | 0 | 0 | 0
3562 | NORTH 24 PARGANAS | Eastern Mechanical | Implementation of Affordable IoT-enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Humaipur Water Supply Scheme on Pilot Basis at Barasat-II Block of North 24 Parganas District in , SM/17186 | IOT | Proposal for conducting model study in respect of implementation of affordable IOT enabled water service, delivery measurement and monitoring sensing system for Rural Deployment in the proposed villages under Humaipur Water Supply Scheme on pilot basis at Barasat-II block of North 24 Parganas. 1) Memo No. WTL/T3/PHED/23-24/0021 dt. 14.06.2023 and subsequent Memo No. WTL/T3/PHE/23-24/050-1 dt. 05.10.2023 addressed to Principal Scretary. il) Memo No. 3876-F dated 02.05.2005 of Finance Department, Govt. of West Bengal iii) Memo No. 4370-F (Y) dated 01.08.2019 of Finance Department, Govt. of West Bengal, PILE. Dept iv) Memo No. 7014-F (Y) /FA/O/2M/165/19 (NB) dated 26.12.2019 of Finance Department, Govt. of West Bengal v) Approval of P.H.E. Dept. vide e-file No. DPHE-11/68/2023-PD (DPHE)-DPHE (Computer No. 757730) dated 10.11.2023. vi) Acceptance order no. 1007/MC-III dt. 01.12.2023 | 7005/EMD | 20/12/2023 | 365 | WEBEL TECHNOLOGY LTD. | 16.88 | 16.88 | 100 | 100
3563 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Taranipur Zone II to accommodate FHTC , SM/17409 | Augmentation | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Taranipur Water Supply Scheme Zone - II at Swarupnagar Block under Barasat Division, PHE Dte. | 1176/BD | 19/04/2022 | 90 | UTPAL CONSTRUCTION & CO. | 137.41 | 25.64 | 56.23 | 13
3564 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Taranipur Zone II to accommodate FHTC , SM/17409 | Augmentation | Route Survey, Design Drawing & DPR Preparation for TARANIPUR ZONE -2 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 447 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.4 | 3.4 | 100 | 1
3565 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Taranipur Zone II to accommodate FHTC , SM/17409 | Augmentation | Material Requisition To Resource Division | 1261/BD | 25/04/2023 | 0 | Resource Division | 17.18 | 0 | 0 | 0
3566 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Taranipur Zone II to accommodate FHTC , SM/17409 | Augmentation | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Taranipur zone - II W/S Scheme including increasing the height of back wash water tank at Swarupnagar Block under Basirhat Sub Division, PHE Dte. Capacity- 50.00 Cum/hr. | 894/BD | 15/03/2024 | 60 | M/S R.K. ENTERPRISE | 18.02 | 0 | 0 | 0
3567 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Taranipur Zone II to accommodate FHTC , SM/17409 | Augmentation | Regarding Restoration charges for road damages. | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 40.09 | 0 | 0 | 0
3568 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Taranipur Zone II to accommodate FHTC , SM/17409 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Taranipur Zone-II water supply scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E Dte. | 1353/BD | 04/05/2023 | 676 | M/S JAYDEEP DASGUPTA | 159.14 | 144.49 | 91.06 | 56
3569 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-I Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07607 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-I Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (Phase-I) | 104/NWSD-I | 01/02/2021 | 75 | SUDHAMAY MAJUMDAR | 63.29 | 106.65 | 85.46 | 1
3570 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SANTOSHPUR ZONE-I Water Supply Scheme at BONGAON Block (PHASE-I) , SM/07607 | Retrofitting | Continuation order for the work of Hiring of 1 (one) no Motor Cab / Maxi Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Executive Engineer, North 24 Parganas W/S Division-I, P.H.E. Dte. for 184 (one hundred eighty four) days w.e.f 01/03/2023 to 31/08/2023.[Car No.WB 25L 4241]. | 168/NWSD-I | 16/02/2023 | 184 | M/S. SHUBHA ENTERPRISE | 0.87 | 1.06 | 100 | 65
3571 | NORTH 24 PARGANAS | Eastern Mechanical | KOLA Piped Water Supply Scheme , SM/18591 | New | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant (Headworks Site) at Kola Piped Water SupplyScheme, Block: Barasat-II, Dist. North 24 Pgs under EMD, PHE Dte. | 4934/EMD | 18/08/2023 | 30 | WESTERN ENGINEERING CO. | 52.69 | 0 | 0 | 0
3572 | NORTH 24 PARGANAS | Barasat Arsenic Division | KOLA Piped Water Supply Scheme , SM/18591 | New | Laying of Distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from distribution system within command area, construction of 2 nos. pump house & construction of 600 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir & soil test as per Departmental design, drawing and specification including bored pile & pile cap at KOLA water supply scheme, Barasat-II block under Barasat Arsenic Division, P.H.E. Dte | 1937/B.Ar.D. | 14/08/2023 | 366 | MONDAL ENTERPRISE | 639.02 | 0 | 0 | 0
3573 | NORTH 24 PARGANAS | Barasat Arsenic Division | KOLA Piped Water Supply Scheme , SM/18591 | New | Survey, Design Drawing & DPR Preparation for KOLA Water Supply Scheme (NEW PWSS) in BARASAT-II BLOCK under Barasat Arsenic Division, PHE Dte. | 1836/B.Ar.D. | 01/08/2023 | 30 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 11.36 | 11.36 | 100 | 100
3574 | NORTH 24 PARGANAS | Barasat Arsenic Division | KOLA Piped Water Supply Scheme , SM/18591 | New | Material Requisition To Resource Division | 68/B.Ar.D | 10/01/2024 | 0 | Resource Division | 20.22 | 0 | 0 | 0
3575 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC by augmentation (Functional Household Tap Connection) of Ground Water Based Piped Water Supply Scheme for Barakpur Zone-II in Bongaon Block of North 24 Parganas District under North 24 Pgs. Water Supply Division-I, PHE Dte. , SM/11555 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Barakpur (Zone-II) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | 1182/NWSD-I | 31/12/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.33 | 3.33 | 100 | 1
3576 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC by augmentation (Functional Household Tap Connection) of Ground Water Based Piped Water Supply Scheme for Barakpur Zone-II in Bongaon Block of North 24 Parganas District under North 24 Pgs. Water Supply Division-I, PHE Dte. , SM/11555 | Augmentation | Material Requisition To Resource Division | 1213/NWSD-I | 13/10/2022 | 0 | Resource Division | 14.25 | 0 | 0 | 0
3577 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC by augmentation (Functional Household Tap Connection) of Ground Water Based Piped Water Supply Scheme for Barakpur Zone-II in Bongaon Block of North 24 Parganas District under North 24 Pgs. Water Supply Division-I, PHE Dte. , SM/11555 | Augmentation | Material Requisition To Resource Division | 455/NWSD-I | 26/04/2023 | 0 | Resource Division | 15.13 | 0 | 0 | 0
3578 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC by augmentation (Functional Household Tap Connection) of Ground Water Based Piped Water Supply Scheme for Barakpur Zone-II in Bongaon Block of North 24 Parganas District under North 24 Pgs. Water Supply Division-I, PHE Dte. , SM/11555 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1430/NWSD-I | 18/09/2024 | 7 | BIBHAS PAL | 5.27 | 0.18 | 50 | 100
3579 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC by augmentation (Functional Household Tap Connection) of Ground Water Based Piped Water Supply Scheme for Barakpur Zone-II in Bongaon Block of North 24 Parganas District under North 24 Pgs. Water Supply Division-I, PHE Dte. , SM/11555 | Augmentation | New service connection at P.H.No- I ,Zone- II of Barakpur water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). | BP-387-23-24 | 28/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.33 | 0 | 0 | 0
3580 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC by augmentation (Functional Household Tap Connection) of Ground Water Based Piped Water Supply Scheme for Barakpur Zone-II in Bongaon Block of North 24 Parganas District under North 24 Pgs. Water Supply Division-I, PHE Dte. , SM/11555 | Augmentation | Laying of Distribution System including specials & valves, pipe carrying structure, Providing FHTC including supplying , laying, fitting, fixing of 15 mm NB PVC (Schedule 80) / 20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun meter ferrule, saddle piece etc. all complete, Construction works of R.C.C Elevated Reservoir 250 m3, Construction of Retaining Wall & Boundary wall, pump house (4.88M x 3.66M) including sanitary arrangement, Service Road (60Mtr. Length x 3 Mtr. Width) at Head Work site for Barakpur Zone-II in Bongaon Block of North 24 Parganas (S) District under North 24 Parganas Water Supply Division-I, PHE. Dte. | 1182/NWSD-I | 10/08/2023 | 729 | JOY HIND TUBEWELLS | 468.44 | 0 | 0 | 35
3581 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-C (Murali) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18258 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-IV/C (Murali) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 1026/NWSD-I | 26/07/2023 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.93 | 4.88 | 100 | 100
3582 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-C (Murali) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18258 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 0 | 0 | 2
3583 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-I (Kamdebkati) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18259 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Zone-I (Kamdebkati) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | 888/NWSD-I | 12/07/2023 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.83 | 3.8 | 100 | 100
3584 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-I (Kamdebkati) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18259 | Augmentation | Supply and installation of Sign Board (900mm X 600mm) determination of Land i.e." This land belongs to PHE. Dte. Govt. of West Bengal" under Surface Water based Pipe Water supply Scheme under North 24 Pgs. Water Supply Division-I, PHE. Dte. | 1432/NWSD-I | 18/09/2024 | 14 | S M TRADERS | 2.17 | 0 | 0 | 100
3585 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-I (Kamdebkati) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18259 | Augmentation | Material Requisition To Resource Division | 1301/NWSD-I | 30/08/2024 | 0 | Resource Division | 18.1 | 0 | 0 | 0
3586 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-I (Kamdebkati) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18259 | Augmentation | New service connection at P.H.No- OHR , Zone - I of Kamdebkati water supply scheme under EMSD-I ,PHE Dte. in 24Pgs(N). | BP-116-24-25 | 11/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.27 | 0 | 0 | 0
3587 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-I (Kamdebkati) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18259 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure, Proposed Rising Main System, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction of 450 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation (600 mm dia, 22 mtrs. deep and one pile cap adjoning 3 nos of piles) , pipe connection and cost of pipes, specials., Soil Investigation for the work of construction of OHR with staging height 20 mtr, Construction Of Pump House (4.88m X 3.66m) Including Sanitary Arrangement, Boundary Wall, Service Road for 60 M length, Improvement Of Land for Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of Zone-I KAMDEBKATI in Deganga Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | 1672/NWSD-I | 30/10/2023 | 365 | M/S. R. K. ENTERPRISE | 669.19 | 53.1 | 7.93 | 10
3588 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Eojnagar to accommodate FHTC , SM/11629 | Augmentation | Material Requisition To Resource Division | 488/BD | 17/02/2023 | 0 | Resource Division | 57.91 | 0 | 0 | 0
3589 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Eojnagar to accommodate FHTC , SM/11629 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method at Pump House 2 using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Eojnagar Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | 3257/BD | 25/11/2024 | 90 | GHOSH CONSTRUCTION. | 21.75 | 0 | 0 | 0
3590 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Eojnagar to accommodate FHTC , SM/11629 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Eojnagar water supply scheme in Basirhat-II Block under Barasat Division, P.H.E Dte. | 3603/BD | 09/12/2022 | 990 | KINGS & CO. | 361.31 | 306.28 | 90.74 | 74
3591 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Route Survey, Design Drawing & DPR Preparation for GOBINDAPUR DHOKRA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 205/ BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.86 | 3.77 | 50 | 1
3592 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Gobindapur-Dhokra W/S Scheme District of 24 Pgs. (N). (SM/11532) NIET No. 19 of EE/EMD of 2022-23 (Sl. No. - 07) | 6443/EMD | 25/11/2022 | 30 | CINZANO | 13.04 | 7.39 | 56.7 | 0
3593 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under Gobindapur dhokra W/S Scheme District of 24 Pgs. (N) | 6383 / EMD | 14/08/2022 | 30 | INDRANI ENTERPRISE | 13.02 | 9.85 | 75.65 | 1
3594 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Material Requisition To Resource Division | 1062/BD | 04/04/2023 | 0 | Resource Division | 53.92 | 0 | 0 | 0
3595 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Eucalyptus Bullah Piling for Emergency protection Work of Pipe line at Chak Farasatpur Mouza between Node Number 123 & 124 of Gobindapur Dhokra Water Supply Scheme under Basirhat Sub Division under Barasat Division P.H.E. Dte. (Length of Piling Work = 33) | 938/BHTSD | 24/05/2024 | 7 | PRASANTA KUMAR PAUL. | 0.98 | 0 | 0 | 0
3596 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Eucalyptus Bullah Piling for Emergency protection Work of Pipe line at Ramnarayanpur Mouza between Node Number 27 & 29 of Gobindapur Dhokra Water Supply Scheme under Basirhat Sub Division under Barasat Division P.H.E. Dte. (Length of Piling Work = 30) | 939/BHTSD | 24/05/2024 | 7 | J.D.ENTERPRISE. (BASIRHAT) | 0.91 | 0 | 0 | 0
3597 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gobindapur Dhokra water supply scheme in Basirhat-II Block under Barasat Division, P.H.E Dte. | 172/BD | 19/01/2023 | 90 | M/S MALLICK ENTERPRISE | 373.91 | 373.72 | 100 | 100
3598 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Repair of damaged concrete road due to laying of pipe line in various place (node 293 to 295, 101 to 422) of Gobindapur Dhokra pwss under Basirhat Sub-Division within Barasat Division, PHE Dte. | 1161/BHTSD | 30/07/2024 | 15 | MALLICK ENTERPRISE | 0.95 | 0 | 0 | 100
3599 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Repair of damaged concrete road due to laying of pipe line in various place (node 230 to 230A, 293 to 294, 232 to 233) of Gobindapur Dhokra pwss under Basirhat Sub-Division within Barasat Division, PHE Dte. | 1162/BHTSD | 30/07/2024 | 15 | MALLICK ENTERPRISE | 0.9 | 0 | 0 | 100
3600 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Repair of damaged concrete road due to laying of pipe line in various place (node 266A to 266B, 276 to 277, 290 to 293) of Gobindapur Dhokra pwss under Basirhat Sub-Division within Barasat Division, PHE Dte. | 1163/BHTSD | 30/07/2024 | 15 | MALLICK ENTERPRISE | 0.78 | 0 | 0 | 100
3601 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Restoration of sub-base of bituminous road from Node 40 to 2 to 65 to 62 to 68 in Gobindapur Dhokra W/S Scheme Under Basirhat Sub-Division P.H.E. Dte.Under Barasat Division, P.H.E.Dte. | 918/BHTSD | 24/05/2024 | 7 | M/S MAA TARA ENTERPRISE | 0.64 | 0.62 | 100 | 100
3602 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Eucalyptus Bullah Piling for Emergency protection Work of Pipe line at Ramnarayanpur Mouza between Node Number 27 & 28 of Gobindapur Dhokra Water Supply Scheme under Basirhat Sub Division under Barasat Division P.H.E. Dte. (Length of Piling Work = 24) | 940/BHTSD | 24/05/2024 | 7 | SELIM GAZI. | 0.73 | 0.73 | 100 | 100
3603 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Restoration of sub-base of bituminous road from Node 68 to 63 to 50 to 48 to 34 to 32 to 21 in Gobindapur Dhokra W/S Scheme Under Basirhat Sub-Division P.H.E. Dte.Under Barasat Division, P.H.E.Dte. | 917/BHTSD | 24/05/2024 | 7 | M/S MAA TARA ENTERPRISE | 0.92 | 0.9 | 100 | 100
3604 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Repair of OHR & Pump House and emergency repairing of pipeline in Gobindapur Dhokra W/S Scheme Under Basirhat Sub-Division P.H.E. Dte.Under Barasat Division, P.H.E.Dte. | 1170/BHTSD | 30/07/2024 | 15 | SELIM GAZI. | 0.95 | 0.94 | 100 | 100
3605 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Repair of damaged concrete road due to laying of pipe line in various place (node 82 to 84, 84 to 86, 725 to 726, 545 to 549, 546 to 552 ) of Gobindapur Dhokra pwss under Basirhat to Sub-Division within Barasat Division, PHE Dte. | 1167/BHTSD | 30/07/2024 | 15 | M/S MAA TARA ENTERPRISE | 0.99 | 0.99 | 100 | 100
3606 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Repair of damaged concrete road due to laying of pipe line in various place (node 711 to 718, 542 to 546, 552 to 554 ) of Gobindapur Dhokra pwss under Basirhat to Sub-Division within Barasat Division, PHE Dte. | 1165/BHTSD | 30/07/2024 | 15 | SWADESH MONDAL. | 0.95 | 0.95 | 100 | 100
3607 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Repair of damaged concrete road due to laying of pipe line in various place (node 549 to 551, 511 to 538, 575 to 579 ) of Gobindapur Dhokra pwss under Basirhat to Sub-Division within Barasat Division, PHE Dte. | 1166/BHTSD | 30/07/2024 | 15 | PRASANTA KUMAR PAUL. | 0.97 | 0.97 | 100 | 100
3608 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Repair of damaged concrete road due to laying of pipe line in various place (node 129 to 130, 291 to 296, 509 to 507, 503 to 507, 571 to 573, 573 tp 575, 554 to 555, 65 to 66, 456 to 457 ) of Gobindapur Dhokra pwss under Basirhat to Sub-Division within Barasat Division, PHE Dte. | 1164/BHTSD | 30/07/2024 | 15 | MALLICK ENTERPRISE | 0.95 | 0 | 0 | 100
3609 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Repair of damaged concrete road due to laying of pipe line in various place (node 72 to 80 to 81, 73 to 74, 80 to 82, 538 to 539, 736 to 737 ) of Gobindapur Dhokra pwss under Basirhat to Sub-Division within Barasat Division, PHE Dte. | 1168/BHTSD | 30/07/2024 | 15 | MD AMIRUL MOLLA. | 0.98 | 0.98 | 100 | 100
3610 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur Dhokra to accommodate FHTC , SM/11532 | Augmentation | Eucalyptus Bullah Piling for Emergency protection Work of Pipe line at Chak Farasatpur Mouza between Node Number 124 & 126 of Gobindapur Dhokra Water Supply Scheme under Basirhat Sub Division under Barasat Division P.H.E. Dte. (Length of piling work = 32 m) | 937/BHTSD | 24/05/2024 | 7 | TAJMAHAL ENTERPRISE | 0.98 | 0 | 0 | 100
3611 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-B (KHILIKAPUR) in Barasat-I Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. , SM/13434 | Augmentation | Material Requisition To Resource Division | 479/NWSD-I | 26/04/2023 | 0 | Resource Division | 35.35 | 0 | 0 | 0
3612 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-B (KHILIKAPUR) in Barasat-I Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. , SM/13434 | Augmentation | Material Requisition To Resource Division | 1713/NWSD-I | 26/11/2024 | 0 | Resource Division | 7.7 | 0 | 0 | 0
3613 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-B (KHILIKAPUR) in Barasat-I Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. , SM/13434 | Augmentation | Pole shifting from PHE Land. Ref ID: 860302827, Application ID: 100000110627 Date: 19.06.2024 | 101/PFMS/24-25 | 03/07/2024 | 0 | WBSEDCL | 0.55 | 0 | 0 | 0
3614 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-B (KHILIKAPUR) in Barasat-I Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. , SM/13434 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 174.62 | 25.5 | 2
3615 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-B (KHILIKAPUR) in Barasat-I Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. , SM/13434 | Augmentation | Special measure for protection of road and pipe line work at different location under the command area of khilkapur and Algoria scheme and other ancilary works under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | 106/NWSD-I | 17/01/2025 | 14 | OM CONSTRUCTION | 4.97 | 4.57 | 100 | 100
3616 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Preparation of Augmentation DPR for Dwarir Jangle Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | 1841/B.Ar.D | 19/09/2022 | 20 | RISHAN ENGINEERING CONSULTANCY | 0.99 | 0.98 | 100 | 1
3617 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Material Requisition To Resource Division | 2290/B.ar.D | 02/12/2022 | 0 | Resource Division | 9.3 | 0 | 0 | 0
3618 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No-I/II (Rep.) under Dwarir Jangle W/S Scheme District of 24 Pgs. (N) | 4796/EMD | 09/08/2023 | 30 | P.K. ENGINEERING | 11.63 | 0 | 0 | 0
3619 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir & other existing civil component of Capacity 250 Cu.m. at Dwarir Jungle W/S Scheme uder Sandeshkhali-II Block under Barasat Arsenic Division, PHE Dte. (SM/11707) | 2470/B.Ar.D. | 21/12/2022 | 60 | MONDAL ENTERPRISE | 16.13 | 15.35 | 100 | 1
3620 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Construction of Platform for FHTC works at Dwarir Jungle Ground Water Supply Scheme under Sandeshkhali-II Block under "Jal Jiban Mission" programme under Barasat Arsenic Division, PHE Dte. | 311/B.Ar.D. | 09/02/2023 | 30 | MONDAL ENTERPRISE | 2.97 | 2.97 | 100 | 100
3621 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Construction of Boundary Wall & Repairing of Pump House-II and approach road with allied work at PH-II for DWARIR JANGLE W/S Scheme Under Barasat Arsenic Division, PHE Dte. | 471/B.Ar.D. | 27/02/2023 | 45 | M/S ROY CHOWDHURY & CO. | 13.15 | 12.88 | 100 | 100
3622 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Laying of distribution System including specials all complete at Naskar Para, 3 no Para, 9 No Katkhali Para for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at DWARIR JANGLE under Sandeshkhali - II Block under Barasat Arsenic Division, PHE Dte. | 918/B.Ar.D. | 11/04/2023 | 45 | M/S DATTA ENTERPRISE | 46.93 | 30.57 | 100 | 100
3623 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Construction of Boundary Wall & Repairing of Pump House-I, IEP Room and approach road with allied work of Head Work Site for DWARIR JANGLE W/S Scheme Under Barasat Arsenic Division, PHE Dte. | 917/B.Ar.D. | 11/04/2023 | 45 | M/S. PROGATI ENTERPRISE | 28.62 | 26.88 | 100 | 100
3624 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Material Requisition To Resource Division | 2111/B.Ar.D. | 02/11/2022 | 0 | Resource Division | 4.33 | 0 | 0 | 0
3625 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab ( Car No. WB-07J-8656) with driver for official use for Deputy Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 17.01.2024 to 31.05.2024". | 85/B.Ar.D | 11/01/2024 | 136 | PROBIR SHAW | 0.65 | 1.12 | 172.77 | 70
3626 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Laying of Pipeline and Repairing of House Hold Connection and Allied works at Dwarir Jangle Water Supply Scheme under Barasat Arsenic Division PHE Dte. | 1523/B.Ar.D. | 12/09/2024 | 40 | MONDAL ENTERPRISE | 13.09 | 7.82 | 59.79 | 40
3627 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab ( Car No. WB-07J-8656) with driver for official use for Deputy Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 01.06.2024 to 30.06.2024". | 919/B.Ar.D | 30/05/2024 | 30 | PROBIR SHAW | 0.14 | 0.27 | 190.43 | 0
3628 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Eucalyptus - Bullah pilling for Protection of UPVC distribution pipe line at Sardarpara of Dwarir Jangle W/S Scheme under Sandeshkhali- II Block under Barasat Arsenic Division, P.H.E. Dte. | 1166/B.Ar.D. | 16/05/2023 | 21 | R. K. MANDAL & CO. | 4.79 | 4.69 | 100 | 100
3629 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Hiring of one (1) no. Diesel operated motor cab (Car No. WB-07J-8656) with driver for official use for Deputy Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 01.07.2023 to 16.01.2024. | 1472/B.Ar.D | 26/06/2023 | 200 | PROBIR SHAW | 0.95 | 1.81 | 100 | 100
3630 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Continuation Order for "Hiring of Power Driven Mini Launch of office of the Executive Engineer, Barasat Arsenic Division, P.H.E. Dte." for the period of 183 days (i.e. from 01.10.2023 to 31.03.2024)''. | 2397/B.Ar.D | 29/09/2023 | 183 | RANJIT KUMAR MANDAL | 2.1 | 3.46 | 100 | 100
3631 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Laying of Pipe line in place of damage portion of distribution system & Construction of 4.88 mtr. x 3.60 mtr. size new Pump House at 3 No. School Para of Dwarir Jangle Supply Scheme under Sandeshkhali-II Block under Barasat Arsenic Division, PHE Dte. | 387/B.Ar.D. | 21/02/2024 | 60 | A 8T CONSTRUCTION | 9.77 | 8.59 | 100 | 80
3632 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Pipe protection work with Sal- Bullah Pilling and FHTC Strengthening with other allied works at DWARIR JANGLE water supply scheme under Sandeshkhali - II Block under Barasat Arsenic Division, PHE Dte. | 385/B.Ar.D. | 21/02/2024 | 30 | SUTAPA ENTERPRISE | 14.21 | 13.61 | 100 | 100
3633 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Sinking of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method 3 No. School Para with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation of Dwarir Jangle w/s scheme of Sandeshkhali-II block under Barasat Arsenic Division, P.H.E. Dte. | 386/B.Ar.D. | 21/02/2024 | 45 | M/S RAJPATH CONSTRUCTION | 19.49 | 15.76 | 100 | 100
3634 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Quotation for Service Connection Charges for PH- III (New) under Dwarir Jangle W/S Scheme in the district of North 24 Pgs. | BP-128-24-25 | 01/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 14.73 | 0 | 0 | 0
3635 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. II under Chowlpur W/S Scheme and Pump House No-III (New) under Dwarir Jangle W/S Scheme District of 24 Pgs. (N) | 4805/EMD | 09/08/2023 | 542 | P.K. ENGINEERING | 21.79 | 0 | 0 | 50
3636 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DWARIR JANGLE to accommodate FHTC under Jal Swapna Mission under Sandeshkhali-II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11707 | Augmentation | Laying of distribution System, Laying of Rising Main including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at DWARIR JANGLE under Sandeshkhali - II Block under Barasat Arsenic Division, PHE Dte. | 1568/B.Ar.D. | 25/08/2022 | 939 | M/S DIPAK ENTERPRISE | 227.76 | 171.75 | 78.65 | 92
3637 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durgapur Baylani Zone-II to accommodate FHTC. , SM/11664 | Augmentation | Acceptance cum Work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Durgapur Baylani w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 1097/BD | 06/04/2023 | 30 | M/S RAJPATH CONSTRUCTION. | 21.46 | 16.98 | 79.09 | 0
3638 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durgapur Baylani Zone-II to accommodate FHTC. , SM/11664 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Durgapur Baylani water supply scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 89/BD | 11/01/2023 | 90 | M/S DATTA ENTERPRISE. | 349.57 | 348.44 | 100 | 0
3639 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durgapur Baylani Zone-II to accommodate FHTC. , SM/11664 | Augmentation | Material Requisition To Resource Division | 521/BD | 20/02/2023 | 0 | Resource Division | 138.01 | 0 | 0 | 0
3640 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Durgapur Baylani Zone-II to accommodate FHTC. , SM/11664 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) and III(New) (Zone-II) under Durgapur-Baylani W/S Scheme with P/H-I, II and III(any 2 nos) under Kankpul W/S Scheme in District of 24 Pgs. (N) NIET No.- 32 of EE/EMD of 2022-23 (Sl. No.- 09) | 1285/EMD | 28/03/2023 | 30 | BENGAL CONSTRUCTION | 60.96 | 25.26 | 63.54 | 40
3641 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durgapur Baylani Zone-II to accommodate FHTC. , SM/11664 | Augmentation | Formal work order for Construction of 300 cum capacity 20 mtr staging height R.C.C Over Head Reservoir as per Deptt. design, drawing & specification including bored pile with pile cap for Augmentation of Durgapur Baylani water supply scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 3021/BD | 05/10/2023 | 365 | ABDUL ALIM MONDAL. | 122.76 | 119.89 | 100 | 100
3642 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durgapur Baylani Zone-II to accommodate FHTC. , SM/11664 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection for the leftout portion at Kakaria, Dhanikhali & Paschim Khejurberia Mouza in connection with Augmentation of Durgapur Baylani water supply scheme (Z- II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 159/HSD | 27/01/2025 | 10 | PRASANTA MITRA. | 0.92 | 0 | 0 | 100
3643 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durgapur Baylani Zone-II to accommodate FHTC. , SM/11664 | Augmentation | Acceptance cum work order for Providing Functional fousehold tap connection at ICDS Centre no- 123, Bishpur Naba Adarsha FP School, Dakshin Bishpur Pubergheri SSK and Dakshin Durgapur FP School within the command area of Durgapur Baylani w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 953/HSD | 29/05/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.71 | 0 | 0 | 100
3644 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Durgapur Baylani Zone-II to accommodate FHTC. , SM/11664 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection with Augmentation for Durgapur Baylani (Z-II) water supply scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 148/HSD | 27/01/2025 | 10 | PRITAM MUKHOPADHYAY. | 0.6 | 0 | 0 | 100
3645 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Bahira & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07708 | Retrofitting | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Bahira & its adjoining mouza water supply scheme in Barasat -II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | 1692/B.Ar.D | 30/09/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.62 | 4.62 | 50 | 1
3646 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Bahira & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07708 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Fanindra Nath Karmakar and Kena Ghosh at Baghyabantapur under Bahira W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | 476/B.Ar.D | 16/03/2022 | 15 | SAHA ENTERPRISE | 4.73 | 4.72 | 99.94 | 1
3647 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Bahira & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07708 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Aribulla at Pagdha Dakshinpara under Bahira W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | 480/B.Ar.D | 16/03/2022 | 15 | DIPA CHHETRI | 4.59 | 4.59 | 50 | 1
3648 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Bahira & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07708 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Chakaminpur, Pakdaha and Balipur Mouzas of Barasat- II Block from Bahira Ground Water Supply Scheme Under "Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I). | 135/B.Ar.D. | 21/01/2021 | 90 | BANI ENGINEERING CO | 87.16 | 16.85 | 19.34 | 100
3649 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Bahira & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07708 | Retrofitting | Laying of UPVC Pipe Line at damaged portion of distribution network near Dadpur Gabtala Market of Bahira water supply scheme at Barasat-II Block due to construction of culvert and Drain under Barasat Arsenic Division, PHE Dte. under 'JAL JIBAN MISSION' Programme. (SM/07708) (Sl No. 3) | 2088/B.Ar.D. | 28/10/2022 | 21 | M/S DATTA ENTERPRISE | 4.93 | 4.92 | 100 | 1
3650 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Chandigarh Mouza (Part), Dariala, Birpur and Banspol mouzas within Humaipur Piped Water Supply Scheme at Barasat- , SM/08076 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Gopalpur Chandigarh Mouza (Part) within Humaipur Water Supply Scheme at Barasat II Block under Barasat Division, PHE Dte. Part-I Sl.No.4 | 171/BSD | 18/02/2021 | 14 | ANJALI ENTERPRISE. | 2.18 | 1.91 | 87.4 | 1
3651 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Chandigarh Mouza (Part), Dariala, Birpur and Banspol mouzas within Humaipur Piped Water Supply Scheme at Barasat- , SM/08076 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Gopalpur Chandigarh Mouza (Part-I), and Dariala, Birpur, Banspol mouzas within Humaipur Water Supply Scheme at Barasat II Block under Barasat Division, PHE Dte. Part-A(Phase-II). | 182/BD | 20/01/2022 | 45 | MONDAL ENTERPRISE. (BARASAT) | 88.28 | 86.9 | 98.44 | 1
3652 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Chandigarh Mouza (Part), Dariala, Birpur and Banspol mouzas within Humaipur Piped Water Supply Scheme at Barasat- , SM/08076 | Retrofitting | Restoration works | BP-2024-25-240 | 06/09/2024 | 0 | EXECUTIVE ENGINEER-II, P.W.D,BARASAT DIVN | 2.8 | 0 | 0 | 0
3653 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Chandigarh Mouza (Part), Dariala, Birpur and Banspol mouzas within Humaipur Piped Water Supply Scheme at Barasat- , SM/08076 | Retrofitting | Restoration works | BP-2024-25-240 | 06/09/2024 | 0 | EXECUTIVE ENGINEER-II, P.W.D,BARASAT DIVN | 16.77 | 0 | 0 | 0
3654 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Bagband Saiberia & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) . , SM/08177 | Retrofitting | Providing Functional House Hold Connection and Allied workas at Gobindapur, Madanpur Krishnapur and Andulia Mouzas of Barasat II Block from Bagband Saiberia & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | 466/B.Ar.D. | 19/02/2021 | 90 | BALAJEE ENTERPRISES | 79.53 | 108.85 | 136.88 | 1
3655 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Bagband Saiberia & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) . , SM/08177 | Retrofitting | Route survey, Distribution designe & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Bagband Saiberia & its adjoining mouza Water Supply Scheme in Barasat -II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | 1562/B.Ar.D. | 15/09/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 6.94 | 6.94 | 50 | 1
3656 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Bagband Saiberia & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) . , SM/08177 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Bablu Ali at Saiberia Uttarpara and Mosharef Ali at Saiberia Moral Para under Bagband Saiberia W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | 474/B.Ar.D | 16/03/2022 | 15 | WATERCOMP INDIA | 4.71 | 4.71 | 99.88 | 1
3657 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Bagband Saiberia & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) . , SM/08177 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Ajibar Baidhya at Saiberia Baidhyapara and Akkaj Ali at saiberia Uttar para under Bagbandh Saiberia W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | 561/B.Ar.D | 23/03/2022 | 15 | KAKALI ENTERPRISE | 4.71 | 4.71 | 99.92 | 100
3658 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-V) at Kharki OHR site under (Phase-I) for Arsenic affected areas of North 2 , SM/08046 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Surface Water Based Water Supply Scheme (Zone-V) at Kharki OHR site under Phase-I for Arsenic affected areas of North 24 Parganas Water Supply Division - I, P.H.E. Dte. of Barasat-I Block at Mouza Kharki, J.L. No.132, Naksa, J.L. No.131 and Kotra, J.L.No.133 under Kotra Gram Panchayat. | 413/NWSD-I | 27/05/2021 | 90 | H. I. ENTERPRISE | 91.88 | 78.29 | 50 | 1
3659 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ashudi Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-II) , SM/07619 | Retrofitting | Material Requisition To Resource Division | 3664/BD | 13/12/2022 | 0 | Resource Division | 2.09 | 0 | 0 | 0
3660 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Ashudi Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-II) , SM/07619 | Retrofitting | Material Requisition To Resource Division | 2239/BD | 24/11/2021 | 0 | Resource Division | 10.26 | 0 | 0 | 0
3661 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Mahishgadi & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07710 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Mahishgadi Mouza of Barasat- II Block from Mahishgadi Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I). | 134/B.Ar.D. | 21/01/2021 | 90 | BANI ENGINEERING CO | 96.59 | 136.24 | 141.04 | 1
3662 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Mahishgadi & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07710 | Retrofitting | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Mahisgadi & its adjoining mouza water supply scheme in Barasat - II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | 1700/B.Ar.D | 30/09/2021 | 15 | UMWELT ENGINEER PVT. LTD. | 2.95 | 2.95 | 50 | 1
3663 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Mahishgadi & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07710 | Retrofitting | Laying of MS Pipe and allied work at Haroa Khal Crossing of Mahisgadi water supply Scheme and Boaring works related to FHTC works of Mahisgadi water supply Scheme at Barasat-II Block under Barasat Arsenic Division, PHE Dte. | 479/B.Ar.D | 16/03/2022 | 15 | BALAJEE ENTERPRISES | 4.77 | 4.76 | 50 | 1
3664 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Paltadanga & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) , SM/07711 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Sondalia and Paltadanga Mouzas of Barasat- II Block from Paltadanga Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I) | 126/B.Ar.D. | 20/01/2021 | 90 | BALAJEE ENTERPRISES | 86.87 | 168 | 97.07 | 1
3665 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Hariharpur Water Supply Scheme at Bagdah Block (Phase-I) , SM/07847 | Retrofitting | Route Survey, Design Drawing & Preparation of DPR for Hariharpur Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 133/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.14 | 3.14 | 100 | 1
3666 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Dwarir Jangle Water Supply Scheme under Sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08725 | Retrofitting | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Dwarir Jangle water supply scheme in Sandeshkhali - II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | 1702/B.Ar.D | 30/09/2021 | 15 | SIRCON ENGINEERING SERVICES | 4.68 | 4.68 | 50 | 1
3667 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Dwarir Jangle Water Supply Scheme under Sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08725 | Retrofitting | Laying of UPVC Pipe at damaged portion at Karnakhali of Dwarir Jangal W/S scheme at Sandeshkhali Block- II for providing FHTC under Jalswapna Programme under Barasat Arsenic Division, PHE Dte. | 2257/B.Ar.D | 30/12/2021 | 30 | A P POWER AND CONCRETE | 4.12 | 4.12 | 99.87 | 1
3668 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Dwarir Jangle Water Supply Scheme under Sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08725 | Retrofitting | Laying of UPVC Pipe at damaged portion at Giri Para of Dwarir Jangal W/S scheme at Sandeshkhali Block- II for providing FHTC under Jalswapna Programme under Barasat Arsenic Division, PHE Dte. | 2233/B.Ar.D | 28/12/2021 | 30 | M/S L.P. CONSTRUCTION | 4.8 | 4.8 | 99.94 | 1
3669 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Dwarir Jangle Water Supply Scheme under Sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08725 | Retrofitting | Providing Functional House Hod Connection and Allied workas at 6 nos habitation of Dwarir Jangle Mouzas of Sandeshkhali II Block from Dwarir Jangle Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | 1711/B.Ar.D. | 01/10/2021 | 90 | A P POWER AND CONCRETE | 45.66 | 43.57 | 53.26 | 1
3670 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Dwarir Jangle Water Supply Scheme under Sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08725 | Retrofitting | Laying of UPVC Pipe at khulnaghat of Dwarirjangal W/S scheme at Sandeshkhali Block- II for providing FHTC under " JAL JIBAN MISSION" under Barasat Arsenic Division, PHE Dte. (SM/08725) (Sl No. 5) | 2125/B.Ar.D. | 04/11/2022 | 21 | A P POWER AND CONCRETE | 4.83 | 4.83 | 100 | 1
3671 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Dwarir Jangle Water Supply Scheme under Sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) , SM/08725 | Retrofitting | Protection of UPVC distribution pipe line at 7 no. Sarder Para of Dwarir Jungle W/S scheme at Sandeshkhali- II under Barasat Arsenic Division, P.H.E. Dte. (Length - 60 mtr. Approx) | 2483/B.Ar.D. | 21/12/2022 | 20 | M/S ASHA ENGINEERING | 5.41 | 5.41 | 100 | 1
3672 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Durgamandop Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) , SM/08764 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in different mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Durgamandop Water Supply scheme Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte.(Phase-I). | 1739/BD | 14/09/2021 | 45 | M/S B.K.ENTERPRISE. | 77.69 | 77.6 | 100 | 1
3673 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Durgamandop Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) , SM/08764 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | 1062/HSD | 31/08/2023 | 10 | ANKUSH CONSTRUCTION & CO. | 0.97 | 0.97 | 100 | 100
3674 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Durgamandop Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) , SM/08764 | Retrofitting | Acceptance cum work order for construction of additional 1 no. switch room cum chlorine room (5.40x3.60) with sanitary and water supply arrangement including plinth protection for augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 110/BD | 09/01/2025 | 75 | MD.SALIM GAZI. | 11.68 | 0 | 0 | 0
3675 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Korakati GP from 30.05.21 to 06.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 428/HSD(Camp) | 27/05/2021 | 8 | M/S NIRMAN CONSTRUCTION. | 4.77 | 4.77 | 100 | 0
3676 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Jeliakhali GP from 27.05.21 to 02.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 433/HSD(Camp) | 27/05/2021 | 7 | M/S NIRMAN CONSTRUCTION. | 4.62 | 4.62 | 100 | 0
3677 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sehara Radhanagar GP from 27.05.21 to 28.05.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 411/HSD(Camp) | 27/05/2021 | 2 | M/S PROGATI ENTERPRISE. | 4.94 | 4.94 | 100 | 0
3678 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sehara Radhanagar GP from 29.05.21 to 03.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 412/HSD(Camp) | 27/05/2021 | 6 | M/S PROGATI ENTERPRISE. | 4.85 | 4.85 | 100 | 0
3679 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Boyermari-II GP from 27.05.21 to 03.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 420/HSD(Camp) | 27/05/2021 | 8 | M/S PROGATI ENTERPRISE. | 4.93 | 4.93 | 100 | 0
3680 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Kalitala GP from 18.06.21 to 30.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 566/HSD(Camp) | 14/06/2021 | 13 | M/S PROGATI ENTERPRISE. | 4.72 | 4.72 | 100 | 0
3681 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Durgamandop GP from 05.06.21 to 11.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 472/HSD(Camp) | 03/06/2021 | 7 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.85 | 4.85 | 100 | 0
3682 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bermajur-I GP from 05.06.21 to 18.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 478/HSD(Camp) | 03/06/2021 | 14 | M/S NIRMAN CONSTRUCTION. | 4.67 | 4.67 | 100 | 0
3683 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bermajur-II GP from 05.06.21 to 18.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 479/HSD(Camp) | 03/06/2021 | 14 | M/S NIRMAN CONSTRUCTION. | 4.67 | 4.67 | 100 | 0
3684 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sehara Radhanagar GP from 04.06.21 to 09.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 480/HSD(Camp) | 03/06/2021 | 6 | M/S DATTA ENTERPRISE. | 4.85 | 4.85 | 100 | 0
3685 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 1, 2, 3, 4 from 03.06.21 to 14.06.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | 495/HSD(Camp) | 03/06/2021 | 12 | M/S RAJPATH CONSTRUCTION. | 4.61 | 4.61 | 100 | 0
3686 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Kalitala GP from 05.06.21 to 17.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte | 497/HSD(Camp) | 03/06/2021 | 13 | M/S PROGATI ENTERPRISE. | 4.73 | 4.73 | 100 | 0
3687 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Boyermari-I GP from 04.06.21 to 15.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 485/HSD(Camp) | 03/06/2021 | 12 | M/S DATTA ENTERPRISE. | 4.92 | 4.92 | 100 | 0
3688 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Dulduli GP from 03.06.21 to 12.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte | 494/HSD(Camp) | 03/06/2021 | 10 | TRISHA ENTERPRISE & CO. | 4.56 | 4.56 | 100 | 0
3689 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bishpur GP from 10.06.21 to 18.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 503/HSD(Camp) | 03/06/2021 | 9 | TRISHA ENTERPRISE & CO. | 4.67 | 4.67 | 100 | 0
3690 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bermajur-II GP from 27.05.21 to 04.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 435/HSD(Camp) | 27/05/2021 | 9 | S.K.ENTERPRISE. | 4.66 | 4.66 | 100 | 0
3691 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sarberia Agarhati GP from 27.05.21 to 02.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 422/HSD(Camp) | 27/05/2021 | 7 | M/S PROGATI ENTERPRISE. | 4.77 | 4.77 | 100 | 0
3692 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Durgamandop GP from 29.05.21 to 04.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 426/HSD(Camp) | 27/05/2021 | 7 | S.K.ENTERPRISE. | 4.86 | 4.86 | 100 | 0
3693 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Korakati GP from 27.05.21 to 29.05.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 427/HSD(Camp) | 27/05/2021 | 3 | M/S NIRMAN CONSTRUCTION. | 4.49 | 4.49 | 100 | 0
3694 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bishpur GP from 27.05.21 to 31.05.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 441/HSD(Camp) | 27/05/2021 | 5 | MONDAL & CO. (BASIRHAT). | 4.53 | 4.53 | 100 | 0
3695 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Dulduli GP from 27.05.21 to 30.05.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 439/HSD(Camp) | 27/05/2021 | 4 | M/S PROGATI ENTERPRISE. | 4.71 | 4.71 | 100 | 0
3696 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 15 & 16 from 27.05.21 to 01.06.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | 442/HSD(Camp) | 27/05/2021 | 6 | M/S RAJPATH CONSTRUCTION. | 4.68 | 4.68 | 100 | 0
3697 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 1, 2, 3, 4 from 27.05.21 to 02.06.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | 443/HSD(Camp) | 27/05/2021 | 7 | M/S RAJPATH CONSTRUCTION. | 4.9 | 4.9 | 100 | 0
3698 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Kalitala GP from 27.05.21 to 04.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 445/HSD(Camp) | 27/05/2021 | 9 | M/S DATTA ENTERPRISE. | 4.62 | 4.62 | 100 | 0
3699 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Korakati GP from 07.06.21 to 14.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 474/HSD(Camp) | 03/06/2021 | 8 | S.K.ENTERPRISE. | 4.76 | 4.76 | 100 | 0
3700 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bishpur GP from 01.06.21 to 09.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 452/HSD(Camp) | 27/05/2021 | 9 | TRISHA ENTERPRISE & CO. | 4.67 | 4.67 | 100 | 0
3701 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Jeliakhali GP from 03.06.21 to 13.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 477/HSD(Camp) | 03/06/2021 | 11 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.6 | 4.6 | 100 | 0
3702 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sarberia Agarhati GP from 03.06.21 to 13.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 488/HSD(Camp) | 03/06/2021 | 11 | M/S DATTA ENTERPRISE. | 4.89 | 4.89 | 100 | 0
3703 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Boyermari-I GP from 27.05.21 to 03.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 419/HSD(Camp) | 27/05/2021 | 8 | M/S DATTA ENTERPRISE. | 4.93 | 4.93 | 100 | 0
3704 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Durgamandop GP from 27.05.21 to 28.05.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 425/HSD(Camp) | 27/05/2021 | 2 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.87 | 4.87 | 100 | 0
3705 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Dulduli GP from 27.05.21 to 02.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 444/HSD(Camp) | 27/05/2021 | 7 | MONDAL & CO. (BASIRHAT). | 4.57 | 4.57 | 100 | 0
3706 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 15 & 16 from 02.06.21 to 16.06.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | 454/HSD(Camp) | 27/05/2021 | 15 | M/S RAJPATH CONSTRUCTION. | 4.8 | 4.8 | 100 | 0
3707 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sehara Radhanagar GP from 10.06.21 to 15.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 481/HSD(Camp) | 03/06/2021 | 6 | M/S PROGATI ENTERPRISE. | 4.85 | 4.85 | 100 | 0
3708 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Rupamari GP from 13.06.21.21 to 16.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 506/HSD(Camp) | 03/06/2021 | 4 | MONDAL & CO. (BASIRHAT). | 4.73 | 4.73 | 100 | 0
3709 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Dulduli GP from 13.06.21 to 22.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 507/HSD(Camp) | 03/06/2021 | 10 | MONDAL & CO. (BASIRHAT). | 4.55 | 4.55 | 100 | 0
3710 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sehara Radhanagar GP from 16.06.21 to 21.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 530/HSD(Camp) | 14/06/2021 | 6 | M/S DATTA ENTERPRISE. | 4.85 | 4.85 | 100 | 0
3711 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sehara Radhanagar GP from 22.06.21 to 27.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 531/HSD(Camp) | 14/06/2021 | 6 | M/S PROGATI ENTERPRISE. | 4.85 | 4.85 | 100 | 0
3712 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Boyermari-I GP from 16.06.21 to 27.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 537/HSD(Camp) | 14/06/2021 | 12 | M/S DATTA ENTERPRISE. | 4.91 | 4.91 | 100 | 0
3713 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Boyermari-II GP from 16.06.21 to 27.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 538/HSD(Camp) | 14/06/2021 | 12 | M/S PROGATI ENTERPRISE. | 4.91 | 4.91 | 100 | 0
3714 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sarberia Agarhati GP from 14.06.21 to 28.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 540/HSD(Camp) | 14/06/2021 | 15 | M/S PROGATI ENTERPRISE. | 4.89 | 4.89 | 100 | 0
3715 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Disinfection & repairing of tube wells at different places in different GPs within Sandeshkhali-I block due to cyclone 'YAAS' under Hasnabad Sub-Division, PHE Dte. | 541/HSD(Camp) | 14/06/2021 | 7 | M/S DATTA ENTERPRISE. | 4.95 | 4.95 | 100 | 0
3716 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Monipur GP from 16.06.21 to 21.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 542/HSD(Camp) | 14/06/2021 | 6 | M/S NIRMAN CONSTRUCTION. | 4.85 | 4.85 | 100 | 0
3717 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Monipur GP from 22.06.21 to 27.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 543/HSD(Camp) | 14/06/2021 | 6 | M/S NIRMAN CONSTRUCTION. | 4.85 | 4.85 | 100 | 0
3718 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Monipur GP from 28.06.21 to 03.07.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 544/HSD(Camp) | 14/06/2021 | 7 | M/S NIRMAN CONSTRUCTION. | 4.68 | 4.68 | 100 | 0
3719 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Durgamandop GP from 19.06.21 to 25.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 545/HSD(Camp) | 14/06/2021 | 7 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.85 | 4.85 | 100 | 0
3720 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Korakati GP from 15.06.21 to 20.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 547/HSD(Camp) | 14/06/2021 | 6 | S.K.ENTERPRISE. | 4.76 | 4.76 | 100 | 0
3721 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Korakati GP from 21.06.21 to 26.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 548/HSD(Camp) | 14/06/2021 | 6 | M/S NIRMAN CONSTRUCTION. | 4.75 | 4.75 | 100 | 0
3722 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Jeliakhali GP from 14.06.21 to 24.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 555/HSD(Camp) | 14/06/2021 | 11 | M/S NIRMAN CONSTRUCTION. | 4.6 | 4.6 | 100 | 0
3723 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Jeliakhali GP from 25.06.21 to 28.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 556/HSD(Camp) | 14/06/2021 | 4 | S.K.ENTERPRISE. | 1.67 | 1.67 | 100 | 0
3724 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bermajur-I GP from 19.06.21 to 28.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 557/HSD(Camp) | 14/06/2021 | 10 | M/S NIRMAN CONSTRUCTION. | 3.34 | 3.34 | 100 | 0
3725 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bermajur-II GP from 19.06.21 to 28.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 558/HSD(Camp) | 14/06/2021 | 10 | M/S NIRMAN CONSTRUCTION. | 3.33 | 3.33 | 100 | 0
3726 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Disinfection & repairing of tube wells at different places in different GPs within Sandeshkhali-II block due to cyclone 'YAAS' under Hasnabad Sub-Division, PHE Dte. | 559/HSD(Camp) | 14/06/2021 | 7 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.96 | 4.96 | 100 | 0
3727 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 1, 2, 3, 4 from 15.06.21 to 26.06.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | 563/HSD(Camp) | 14/06/2021 | 12 | M/S RAJPATH CONSTRUCTION. | 4.6 | 4.6 | 100 | 0
3728 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Rupamari GP from 17.06.21.21 to 20.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 564/HSD(Camp) | 14/06/2021 | 4 | MONDAL & CO. (BASIRHAT). | 4.73 | 4.73 | 100 | 0
3729 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bishpur GP from 19.06.21 to 27.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 567/HSD(Camp) | 14/06/2021 | 9 | MONDAL & CO. (BASIRHAT). | 4.67 | 4.67 | 100 | 0
3730 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sahebkhali GP from 21.06.21 to 23.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 568/HSD(Camp) | 14/06/2021 | 3 | M/S DATTA ENTERPRISE. | 2.01 | 2.01 | 100 | 0
3731 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Dulduli GP from 23.06.21 to 30.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 572/HSD(Camp) | 14/06/2021 | 8 | MONDAL & CO. (BASIRHAT). | 3.64 | 3.64 | 100 | 0
3732 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Rupamari GP from 25.06.21.21 to 28.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | 574/HSD(Camp) | 14/06/2021 | 4 | TRISHA ENTERPRISE & CO. | 4.74 | 4.74 | 100 | 0
3733 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Disinfection & repairing of tube wells at different places in different GPs within Hingalganj block due to cyclone 'YAAS' under Hasnabad Sub-Division, PHE Dte. | 575/HSD(Camp) | 14/06/2021 | 7 | TRISHA ENTERPRISE & CO. | 2 | 2 | 100 | 0
3734 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bermajur-I GP from 27.05.21 to 04.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | 434/HSD(Camp) | 27/05/2021 | 9 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.66 | 4.66 | 100 | 0
3735 | NORTH 24 PARGANAS | Barasat Division | Relief work in the form of Supply of Drinking Water through Tanker and Disinfection of Tube Wells at Different GPS in SANDESHKHALI-II & MINAKHAN block duly affected by cyclonic storm , SM/09153 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 15 & 16 from 17.06.21 to 30.06.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | 565/HSD(Camp) | 14/06/2021 | 14 | M/S RAJPATH CONSTRUCTION. | 4.48 | 4.48 | 100 | 0
3736 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)under command area of PASCHIM PANCHBERIA ZONE-II Water Supply Scheme at Bongaon Block (Phase-II). , SM/08240 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PASCHIM PANCHBERIA ZONE-II Water Supply Scheme at BONGAON Block under North 24 Parganas water supply Division - I, PHE Dte. (PHASE-II) | 880 / NWSD-I | 25/10/2021 | 60 | CHANDIMATA CONSTRUCTION | 49.34 | 49.95 | 100 | 1
3737 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-VI-Beraberia OHR) at Amdanga Block , SM/08241 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within command area of Surface water based Water Supply Scheme (Zone-VI) at BERABERIA OHR site from Arsenic affected areas of North 24 Parganas water supply Division - I, PHE Dte. | 1005/NWSD-I | 24/11/2021 | 90 | J. D. J. ENTERPRISE, A UNIT OF JDJ TRADERS PRIVATE LIMITED | 224.61 | 202.33 | 100 | 100
3738 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-VI-Beraberia OHR) at Amdanga Block , SM/08241 | Retrofitting | Material Requisition To Resource Division | 03/NWSD-I | 03/01/2022 | 0 | Resource Division | 11 | 0 | 0 | 0
3739 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-VI-Beraberia OHR) at Amdanga Block , SM/08241 | Retrofitting | Hiring of Diesel Cab having licensed carriage contract permit from Regional Transport Authority for the office of the Executive Engineer, North 24- Pgs. W/S Division-I, P.H.E. Dte. under the control of Assistant Engineer (HQ-II), North 24-Pgs. W/S Division-I, P.H.E. Dte. for 182 (One Hundrad Eighty Two) Days. w.e.f. 01.01.2024 to 30.06.2024. | 2196/NWSD-I | 29/12/2023 | 182 | BADAL GHOSH | 0.86 | 2.25 | 259.96 | 16
3740 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-VI-Beraberia OHR) at Amdanga Block , SM/08241 | Retrofitting | Continuation order for the work of Hiring of Diesel ambassador Car / Cab with contract carriage permit of R.T.A. In good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Assistant Engineer (HQ-I), North 24 Parganas W/S Division-I, P.H.E. Dte. [w.e.f. 01.06.2024 to 19.06.2024.(19 days)].(Car No.WB25J7778.) | 816/NWSD-I | 29/05/2024 | 19 | GITA DAS | 0.09 | 0.2 | 225.61 | 0
3741 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-VI-Beraberia OHR) at Amdanga Block , SM/08241 | Retrofitting | Continuation order for the work of Hiring of 1no. Diesel Motor Cab / Maxi Cab with contract carriage permit of R.T.A. in good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Executive Engineer, North 24 Parganas Water Supply Division-I, P.H.E. Dte. for 184 (One Hundred Eighty Four) w.e.f. 01.07.2024 to 31.12.2024. [Vehicle No.WB 25L4241]. | 932/NWSD-I | 21/06/2024 | 184 | M/S. SHUBHA ENTERPRISE | 0.87 | 1.87 | 213.43 | 0
3742 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-VI-Beraberia OHR) at Amdanga Block , SM/08241 | Retrofitting | Continuation order for the work of Hiring of Diesel Cab having licensed carriage contract permit from Regional Transport Authority for the office of the Executive Engineer, North 24- Pgs. W/S Division-I, P.H.E. Dte. under the control of Assistant Engineer (HQ-II), North 24-Pgs. W/S Division-I, P.H.E. Dte. for 184 (One Hundred Eighty Four) Days. w.e.f. 01.07.2024 to 31.12.2024. | 948/NWSD-I | 24/06/2024 | 184 | BADAL GHOSH | 0.87 | 2.22 | 253.8 | 0
3743 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kamarpur & Its Adjoining mouzas Piped Water Supply Scheme at Habra-II Block (Phase-I) , SM/08774 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Kamarpur & its adjoining mouzas Water Supply Scheme at Habra-II Block within the jurisdiction of Habra Sub-Division, under Barasat Division, PHE Dte. (Phase-I). | 2390/BD | 09/12/2021 | 45 | SHIBU BISWAS. | 53.39 | 50.82 | 95.2 | 1
3744 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kamarpur & Its Adjoining mouzas Piped Water Supply Scheme at Habra-II Block (Phase-I) , SM/08774 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Dakshin Bhebia Zone-II Water Supply Scheme under Barasat Division, PHE Dte. | 2181/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.93 | 3.93 | 100 | 1
3745 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kamarpur & Its Adjoining mouzas Piped Water Supply Scheme at Habra-II Block (Phase-I) , SM/08774 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Bergum W/S Scheme within the jurisdiction of the Habra Sub-Division under Barasat Division, PHE Dte. | 571/HAB | 23/12/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.71 | 4.71 | 100 | 1
3746 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bergum Piped Water Supply Scheme at Habra-I Block (Phase-I) , SM/08775 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Chaital Water Supply Scheme under Barasat Division, PHE Dte. | 2164/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.49 | 4.48 | 100 | 1
3747 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bergum Piped Water Supply Scheme at Habra-I Block (Phase-I) , SM/08775 | Retrofitting | Acceptance cum work order for Providing Functional House Hold Tap Connection (FHTC) from existing distribution system at Bergum Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte.( For balance work of Retrofitting). | 3582/ BD | 08/12/2022 | 30 | ANKUSH CONSTRUCTION & CO. | 16.19 | 15.18 | 100 | 1
3748 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bergum Piped Water Supply Scheme at Habra-I Block (Phase-I) , SM/08775 | Retrofitting | Continuation work order for Hiring Diesel Luxury Car on Daily basis (for 6 months from 01.04.2023 to 30.06.2023) for the office use of the Executive Engineer, Barasat Division, PHE Dte | 1044/BD | 31/03/2023 | 91 | MADHAB CHANDRA DAS | 0.45 | 0.69 | 100 | 100
3749 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bergum Piped Water Supply Scheme at Habra-I Block (Phase-I) , SM/08775 | Retrofitting | Material Requisition To Resource Division | 250/BD | 27/01/2022 | 0 | Resource Division | 1.99 | 0 | 0 | 0
3750 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bergum Piped Water Supply Scheme at Habra-I Block (Phase-I) , SM/08775 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Bergum Water Supply Scheme at Habra-I Block within the jurisdiction of Habra Sub-Division, under Barasat Division, PHE Dte. (Phase-I). | 2484/BD | 17/12/2021 | 1890 | UNICON INDIA. | 163.67 | 123.7 | 88.13 | 100
3751 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of NITYANANDAKATI BALTI W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08651 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Nityanandakati Balti Water Supply Scheme at Swarupnagar Block under Barasat Division, PHE Dte. (Phase I) | 2460/BD | 15/12/2021 | 45 | SHIBU BISWAS. | 66.16 | 65.92 | 99.63 | 1
3752 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of NITYANANDAKATI BALTI W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08651 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Durgamondop Water Supply Scheme under Barasat Division, PHE Dte. | 2175/HSD | 28/12/2021 | 21 | UMWELT ENGINEER PVT.LTD. | 4.15 | 4.15 | 100 | 1
3753 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of NITYANANDAKATI BALTI W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08651 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Monipur Water Supply Scheme under Barasat Division, PHE Dte. | 2150/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 100 | 1
3754 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08641 | Retrofitting | Continuation work order for the work of Hiring Diesel Luxury Car on daily basis (for 6months from 01-01-2022 to 30-06-2022) for the Office of the Assistant Engineer (HQ), Barasat Division, PHE Dte. | 2686/BD | 31/12/2021 | 181 | M/S SAMIT CHANDRA DEY. | 0.86 | 0.8 | 93.33 | 1
3755 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08641 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for BITHARI ZONE -1 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 450 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 0 | 0 | 1
3756 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08641 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for BARA BANKRA Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 441 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.57 | 0 | 0 | 1
3757 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08641 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for NITYANANDAKATI BALTI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 440 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.69 | 0 | 0 | 1
3758 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08641 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for MAMINPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 305/BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.15 | 0 | 0 | 1
3759 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08641 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for GOKULPUR Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 448 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.32 | 0 | 0 | 1
3760 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08641 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for TARANIPUR ZONE -1 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 446 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.69 | 0 | 0 | 1
3761 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08641 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for DOBILA Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 449 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.5 | 0 | 0 | 1
3762 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08641 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for KAPILESWARPUR Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 445 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.04 | 0 | 0 | 1
3763 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08641 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Gobindapur Water Supply Scheme at Baduria Block, Dist- North 24 Parganas under Barasat Division, PHE Dte.(Phase-I). | 2438/BD | 13/12/2021 | 90 | UTPAL CONSTRUCTION & CO. | 224.17 | 222.04 | 100 | 1
3764 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of GOBINDAPUR W/S Scheme at Swarupnagar Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08641 | Retrofitting | Material Requisition To Resource Division | 2859/BD | 21/09/2022 | 0 | Resource Division | 27.73 | 0 | 0 | 0
3765 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of DEBOG W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08643 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Debog Water Supply Scheme at Basirhat - I Block under Barasat Division, PHE Dte. (Phase - I) | 222/BD | 24/01/2022 | 45 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 91.48 | 35.12 | 49.11 | 1
3766 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of DEBOG W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08643 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for DEBHOG Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | 191/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.7 | 3.6 | 100 | 1
3767 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of DEBOG W/S Scheme at Basirhat I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase - I). , SM/08643 | Retrofitting | Material Requisition To Resource Division | 2339/BD | 26/09/2022 | 0 | Resource Division | 61.51 | 0 | 0 | 0
3768 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kalitala Piped Water Supply Scheme, Hingalganj Block (Phase-I) , SM/08257 | Retrofitting | Acceptance cum work Order for Providing Functional Household Tap Connection (FHTC) in diff. mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Kalitala W/S scheme, Hingalganj block under Hasnabad Sub-Division, PHE Dte. (Phase-I) | 94/BD | 17/01/2022 | 45 | MONDAL & CO. (BASIRHAT). | 80.01 | 79.76 | 99.69 | 1
3769 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kalitala Piped Water Supply Scheme, Hingalganj Block (Phase-I) , SM/08257 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Kalitala w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 251/HSD | 07/02/2022 | 10 | MONDAL & CO. (BASIRHAT). | 4.62 | 4.62 | 100 | 1
3770 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kalitala Piped Water Supply Scheme, Hingalganj Block (Phase-I) , SM/08257 | Retrofitting | Acceptance cum work order for Additional Laying of 75 mm dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Parghumti Mouza within Kalitala W/S scheme, Hingalganj block under Hasnabad Sub-Division within Barasat Division, PHE Dte. | 254/HSD | 07/02/2022 | 10 | MONDAL & CO. (BASIRHAT). | 4.54 | 4.54 | 100 | 1
3771 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kalitala Piped Water Supply Scheme, Hingalganj Block (Phase-I) , SM/08257 | Retrofitting | Acceptance cum work order for Additional Laying of 50 mm dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Parghumti Mouza within Kalitala W/S scheme, Hingalganj block under Hasnabad Sub-Division within Barasat Division, PHE Dte. | 255/HSD | 07/02/2022 | 10 | MONDAL & CO. (BASIRHAT). | 4.54 | 4.54 | 100 | 1
3772 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kalitala Piped Water Supply Scheme, Hingalganj Block (Phase-I) , SM/08257 | Retrofitting | Acceptance cum work order for Additional Laying of 63 mm dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Parghumti Mouza within Kalitala W/S scheme, Hingalganj block under Hasnabad Sub-Division within Barasat Division, PHE Dte. | 257/HSD | 07/02/2022 | 10 | MONDAL & CO. (BASIRHAT). | 4.52 | 4.52 | 100 | 1
3773 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kalitala Piped Water Supply Scheme, Hingalganj Block (Phase-I) , SM/08257 | Retrofitting | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places due to laying of new UPVC pipe line within Kalitala w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 252/HSD | 07/02/2022 | 7 | MONDAL & CO. (BASIRHAT). | 2.06 | 0 | 0 | 1
3774 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bagdah Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08261 | Retrofitting | Acceptance cum work order for Additional Survey Work For DPR Preparation of Kalitala Water Supply Scheme under Barasat Division, PHE Dte. | 2180/HSD | 28/12/2021 | 21 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 2.52 | 2.52 | 100 | 1
3775 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bagdah Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08261 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Panchita Water Supply Scheme under Bongaon Sub-Division, under Barasat Division,PHE.Dte. | 613/Bon | 31/12/2021 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.8 | 3.8 | 100 | 1
3776 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bagdah Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08261 | Retrofitting | Acceptance cum work order for Additional Survey Work For DPR Preparation of Kaniakati Kathalberia Zone I/A & Zone I/B Water Supply Scheme under Barasat Division, PHE Dte. | 2145/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.99 | 1.96 | 100 | 1
3777 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bagdah Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08261 | Retrofitting | Acceptance cum work order Route Survey, Design Drawing & DPR Preparation for Kaniakati Kathalberia Zone I/A & Zone I/B Water Supply Scheme under Barasat Division, PHE Dte. | 2144/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.76 | 4.76 | 100 | 1
3778 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bagdah Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08261 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Kaniakati Kathalberia Zone II/A & Zone II/B Water Supply Scheme under Barasat Division, PHE Dte. | 2142/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.76 | 4.73 | 100 | 1
3779 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bagdah Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08261 | Retrofitting | Acceptance cum work order Additional Survey Work For DPR Preparation of Kaniakati Kathalberia Zone II/A & Zone II/B Water Supply Scheme under Barasat Division, PHE Dte. | 2143/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.21 | 2.19 | 100 | 1
3780 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bagdah Piped Water Supply Scheme, Bagdah Block (Phase-I) , SM/08261 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAGDAH Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-I) | 990/BD. | 27/05/2021 | 45 | UMWELT ENGINEER PVT.LTD. | 89.35 | 7.1 | 11.58 | 1
3781 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Emergency repair and renovation of damaged FHTC and allied work in the aftermath of Cyclonic Storm " YASS " for Atapur water supply scheme at Sandeshkhali - II block under Barasat Arsenic Division, P.H.E. Dte. (Part -3) (Sl. No.-4)¿ | 1022 / B.Ar.D | 31/05/2021 | 21 | S. K. ENTERPRISE | 4.79 | 4.79 | 99.96 | 0
3782 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Emergency Repair & Renovation of damaged Rising main & Distribution system (CI/DI/HDPE/UPVC) due to super cyclone YASS for Atapur water supply scheme at Sandeshkhali -II block under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-1)¿ | 1002/B.Ar.D | 28/05/2021 | 21 | M/S NIRMAN CONSTRUCTION | 4.79 | 4.79 | 99.9 | 0
3783 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Protection of UPVC distribution pipe line near at house of Sanjit Sardar (Majher Para)of Atapur W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-1)¿ | 1019/ B.Ar.D | 31/05/2021 | 21 | ROY BISWAS CONSTRUCTION | 4.81 | 4.79 | 99.41 | 0
3784 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Protection of UPVC distribution pipe line at Atapur Gopaler Ghat of Atapur W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-6)¿ | 1007 / B.Ar.D | 28/05/2021 | 21 | BALAJEE ENTERPRISES | 4.74 | 9.46 | 100 | 0
3785 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Emergency laying of UPVC Pipe at damaged portion from Ttimohana to Ayla Bandh of Atapur W/S scheme due to super cyclone YASS at Sandeshkhali block II under Barasat Arsenic Division, PHE Dte. (Sl. No.-2)¿ | 1003 / B.Ar.D | 28/05/2021 | 21 | PRITAM MUKHOPADHYAY | 4.34 | 4.33 | 99.66 | 0
3786 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Protection of UPVC distribution pipe line at Atapur Aila Bandh of Atapur W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-7)¿ | 1008 / B.Ar.D | 28/05/2021 | 21 | S. K. ENTERPRISE | 4.73 | 4.72 | 99.74 | 0
3787 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Protection of UPVC distribution pipe line at Atapur SSK School, Majher Para (near house of Bhutta Sardar and Bholanath Sardar) of Atapur W/S scheme Due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-5)¿ | 1006 / B.Ar.D | 28/05/2021 | 21 | P. & S. ASSOCIATES | 4.74 | 4.71 | 99.28 | 0
3788 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Emergency laying of UPVC Pipe at damaged portion from Paruia More (near pump house - 1) to Taltala ghat of Atapur W/S scheme due to super cyclone YASS at Sandeshkhali block - II under Barasat Arsenic Division, PHE Dte. (Sl. No.-3)¿ | 1004 / B.Ar.D | 28/05/2021 | 21 | M/S NIRMAN CONSTRUCTION | 4.71 | 4.7 | 99.89 | 0
3789 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Fuel and operating maintenance charges of Mobile silent type diesel generating set / Open type diesel generating set on emergency basis for two nos w/s scheme of Sandeshkhali - II block under Dist. 24 Pgs. (N). on the impending Extremely Severe cyclonic Strom¿ YASS', under Barasat Arsenic Division, PHE Dte. (Sl. No.-15)¿ | 1016 / B.Ar.D | 28/05/2021 | 21 | MONDAL ENTERPRISE | 4.01 | 0 | 0 | 0
3790 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Protection of UPVC distribution pipe line from house of Tarun Das to H/O Pankaj Sardar (Mission Math) of Dawrir Jangle W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte.) (Sl. No.-13)¿ | 1031 / B.Ar.D | 31/05/2021 | 21 | M/S. SREEJIT ENTERPRISE | 4.66 | 4.66 | 99.94 | 0
3791 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Protection of UPVC distribution pipe line from H/O Rafiq Molla to H/O Khalil Molla of Jeliakhali Paschim Khanda W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-15)¿ | 1033 / B.Ar.D... | 31/05/2021 | 21 | BALAJEE ENTERPRISES | 4.74 | 4.74 | 99.99 | 0
3792 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Emergency repair and renovation of damaged FHTC and allied work in the aftermath of Cyclonic Storm " YASS " for Atapur water supply scheme at Sandeshkhali - II block under Barasat Arsenic Division, P.H.E. Dte. (Part-4) (Sl. No.-5)¿ | 1023/B.Ar.D | 31/05/2021 | 21 | P & S ASSOCIATES | 4.75 | 4.75 | 99.86 | 0
3793 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Protection of UPVC distribution pipe line from H/O Bidhan Mistri to H/O Goutam Mondal of Jeliakhali Paschim Khanda W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-14)¿ | 1032 / B.Ar.D | 31/05/2021 | 21 | BALAJEE ENTERPRISES | 4.71 | 4.71 | 99.89 | 0
3794 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Protection of UPVC distribution pipe line near at H/O Sontosh Patra (Majher Para) of Atapur W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-8)¿ | 1009 / B.Ar.D... | 28/05/2021 | 21 | BALAJEE ENTERPRISES | 4.74 | 4.72 | 99.65 | 0
3795 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Protection of UPVC distribution pipe line from H/O Sanatan Mondal to Chaitan Sarder (Part-I) at Natun Para of Dawrir jangle W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-12)¿ | 1013 / B.Ar.D | 28/05/2021 | 21 | UTPAL CONSTRUCTION AND CO | 4.7 | 4.69 | 99.9 | 0
3796 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Emergency laying of UPVC Pipe at damaged portion from Mohatali More to Gopaler Ghat of Atapur W/S scheme due to super cyclone YASS at Sandeshkhali Block II under Barasat Arsenic Division, PHE Dte. (Sl. No.-8)¿ | 1026 / B.Ar.D | 31/05/2021 | 21 | M/S NIRMAN CONSTRUCTION | 4.66 | 4.66 | 99.97 | 0
3797 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Emergency repair and renovation of damaged FHTC and allied work in the aftermath of Cyclonic Storm " YASS " for Atapur water supply scheme at Sandeshkhali - II block under Barasat Arsenic Division, P.H.E. Dte. (Part -2) (Sl. No.-3)¿ | 1021 / B.Ar.D | 31/05/2021 | 21 | M/S NIRMAN CONSTRUCTION | 4.79 | 4.77 | 99.75 | 0
3798 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Emergency repair and renovation of damaged FHTC and allied work in the aftermath of Cyclonic Storm " YASS " for Atapur water supply scheme at Sandeshkhali - II block under Barasat Arsenic Division, P.H.E. Dte. (Part -1). (Sl. No.-2)¿ | 1020 / B.Ar.D | 31/05/2021 | 21 | UNIFIED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.78 | 4.78 | 99.96 | 0
3799 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Emergency repair and renovation of damaged Rising main & Distribution system (CI/DI/HDPE/UPVC) & FHTC including protection work and allied work in the aftermath of Cyclonic Storm " YASS " for Jeliakhali Paschim khanda water supply scheme at Sandeshkhali - II block under Barasat Arsenic Division, PHE Dte. (Sl. No.-13)¿ | 1014/B.Ar.D | 28/05/2021 | 21 | MONDAL ENTERPRISE | 4.71 | 0 | 0 | 0
3800 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Emergency laying of UPVC Pipe at different damaged portion of Atapur W/S scheme due to super cyclone YASS at Sndeshkhali block II under Barasat Arsenic Division, PHE Dte. (Sl. No.-10)¿ | 1011/ B.Ar.D | 28/05/2021 | 21 | S. K. ENTERPRISE | 4.78 | 4.78 | 99.96 | 0
3801 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Emergency repair and renovation of Damaged FHTC and allied work in the aftermath of Cyclonic Storm " YASS " for Atapur water supply scheme at Sandeshkhali - II block under Barasat Arsenic Division, P.H.E. Dte. (Part -5) (Sl. No.-6)¿ | 1024 / B.Ar.D | 31/05/2021 | 21 | UNIFIED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.16 | 4.15 | 99.95 | 0
3802 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Emergency laying of UPVC Pipe at damaged portion at Bhyrabi Guest House and Dhuchnekhali Bazar of Atapur W/S scheme due to super cyclone YASS at Sanndeshkhali Block II under Barasat Arsenic Division, PHE Dte. (Sl. No.-11)¿ | 1029 / B.Ar.D | 31/05/2021 | 21 | BALAJEE ENTERPRISES | 4.79 | 4.79 | 99.96 | 0
3803 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Emergency laying of UPVC Pipe at damaged portion from Atapur High School to Trimhona of Atapur W/S scheme due to super cyclone YASS at Sandeshkhali Block II under Barasat Arsenic Division, PHE Dte. (Sl. No.-10)¿ | 1028 / B.Ar.D | 31/05/2021 | 21 | NEW BRIGHT CONSTRUCTION | 4.78 | 4.78 | 99.98 | 0
3804 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Emergency repair and renovation of damaged Rising main & Distribution system (CI/DI/HDPE/UPVC) & FHTC including protection work and allied work in the aftermath of Cyclonic Storm " YASS " for Dawrir Jangle water supply scheme at Sandeshkhali - II block under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-11)¿ | 1012 / B.Ar.D... | 28/05/2021 | 21 | UTPAL CONSTRUCTION AND CO | 4.65 | 4.65 | 99.85 | 0
3805 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Protection of UPVC distribution pipe line at Taltalaghat of Atapur W/S scheme Due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-9) | 1010/B.Ar.D | 28/05/2021 | 21 | DEEP EXERTION | 4.39 | 4.39 | 99.93 | 0
3806 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Emergency laying of UPVC Pipe at damaged portion at Gurumali Para & Kasari Para of Jeliakhali Paschim Khanda W/S scheme due to super cyclone YASS at Sandeshkhali Block II under Barasat Arsenic Division, PHE Dte. (Sl. No.-16)¿ | 1033 /A / B.Ar.D | 31/05/2021 | 21 | PREMANANDA ROY BISWAS | 4.77 | 4.77 | 99.96 | 0
3807 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Protection of UPVC distribution pipe line from house of Kinkar Das to H/O Tarun Das (Mission Math) of Dawrir Jangle W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-12)¿ | 1030 / B.Ar.D | 31/05/2021 | 21 | M/S. SREEJIT ENTERPRISE | 4.7 | 4.69 | 99.93 | 0
3808 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Protection of UPVC distribution pipe line at different places of Jeliakhali Paschim Khnda W/S scheme due to Super Cyclone YASS at Sandeshkhali - II under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-14)¿ | 1015/ B.Ar.D | 28/05/2021 | 21 | THREE MAA ENTERPRISE | 4.71 | 4.71 | 99.95 | 0
3809 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Supply Delivery and Distriction of Miscellaneous Stationery item and Refresment in connection with High Level meeting /assembly/congreation /conventions/discussions etc . at PHED Hedquaters office at Kolkata (Sl No-01) | 1143/B.Ar.D. | 13/07/2021 | 180 | CALCON CONSTRUCTIONS | 4.97 | 0 | 0 | 0
3810 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Emergency repair and renovation of Damaged Road and allied work in the aftermath of Cyclonic Storm " YASS " for Atapur water supply scheme at Sandeshkhali - II block under Barasat Arsenic Division, P.H.E. Dte. (Sl. No.-7)¿ | 1025 / B.Ar.D | 31/05/2021 | 21 | M/S NIRMAN CONSTRUCTION | 4.71 | 4.69 | 99.59 | 100
3811 | NORTH 24 PARGANAS | Barasat Arsenic Division | Relief and restoration work in the aftermath of cyclonic storm YASS for 3 nos of extensive damage ground water supply scheme of Sandeshkhali-II, block under North 24 Parganas under Barasat Arsenic Division, PHE Dte , SM/08996 | Disaster | Emergency laying of UPVC Pipe at damaged portion from Trimohanna (near house of Monoranjan Mondal ) to Das Para of Atapur W/S scheme due to super cyclone YASS at Sandeshkhali Block II under Barasat Arsenic Division, PHE Dte. (Sl. No.-9)¿ | 1027 / B.Ar.D | 31/05/2021 | 21 | BALAJEE ENTERPRISES | 4.71 | 4.71 | 99.97 | 100
3812 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. , SM/10412 | Augmentation | Survey, Design and preparation of Retrofitting DPR in connection with " Providing functional household tap connection to every Household under Bagangram Zone-I W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte. | 316/NWSD - I | 21/03/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.24 | 4.24 | 100 | 1
3813 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. , SM/10412 | Augmentation | Special repair and renovation of Pump House & allied works at Head Works Site & 2nd Tube Well Site at Bagangram Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 378/NWSD-I | 05/04/2023 | 45 | GHOSH CONSTRUCTION | 5.25 | 4.24 | 80.74 | 70
3814 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. , SM/10412 | Augmentation | Repair and renovation of Boundary wall for 40 m Length in 2nd Pump House site & Service road (50 Mtr. Length X 3 Mtr. Width at Head Works site at Bagangram Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 377/NWSD-I | 05/04/2023 | 45 | GHOSH CONSTRUCTION | 8.32 | 0 | 0 | 60
3815 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. , SM/10412 | Augmentation | Special Repair and renovation of Pump House & Allied Works at Head Works site & 2nd Tube Well site at Bagangram Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 378/NWSD-I. | 05/04/2023 | 45 | GHOSH CONSTRUCTION | 5.25 | 0 | 0 | 0
3816 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. , SM/10412 | Augmentation | Repair and renovation of Boundary wall for 40 m Length in 2nd Pump House site & Service road (50 Mtr. Length X 3 Mtr. Width at Head Works site at Bagangram Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 377/NWSD-I. | 05/04/2023 | 45 | GHOSH CONSTRUCTION | 8.32 | 8.21 | 100 | 100
3817 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. , SM/10412 | Augmentation | Material Requisition To Resource Division | 1135/NWSD-I | 04/08/2023 | 0 | Resource Division | 122.72 | 0 | 0 | 0
3818 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. , SM/10412 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) (Rep) under Bagangram W/S Scheme District of 24 Pgs. (N) | 4757/EMD | 07/08/2023 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 26.48 | 15.36 | 58 | 60
3819 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. , SM/10412 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system & Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of BAGANGRAM ZONE-I Water Supply Scheme under North 24 Parganas Water Supply Division-I, PHE,Dte. | 1094/NWSD-I | 12/09/2022 | 90 | M/S. NANDY ENTERPRISES | 413.37 | 255.78 | 61.88 | 75
3820 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. , SM/10412 | Augmentation | Repair and renovation works of R.C.C. Elevaced Reservoir 350 cum & Boundary Wall for 234 m Length in Head Works site at Bagangram Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 316/NWSD-I | 20/03/2023 | 45 | M/S. ASOKE GHOSH AND BROTHERS | 33.8 | 25.54 | 100 | 100
3821 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. , SM/10412 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1430/NWSD-I | 18/09/2024 | 7 | BIBHAS PAL | 5.27 | 0.18 | 50 | 100
3822 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate , SM/10531 | Augmentation | Repairing & renovation of Pump House No. - 1, 2 & 3 of Maslandapur W/S scheme (Zone - I) within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 489/HAB | 30/11/2021 | 30 | ANJALI CONSTRUCTION. | 2.77 | 2.71 | 100 | 1
3823 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate , SM/10531 | Augmentation | Material Requisition To Resource Division | 3794/BD | 22/12/2022 | 0 | Resource Division | 21.91 | 0 | 0 | 0
3824 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate , SM/10531 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 2 & 3 for Augmentation of Maslandapur (Zone - I) water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | 2773/BD | 11/09/2023 | 60 | NADIA TUBEWELLS | 28.96 | 0 | 0 | 0
3825 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate , SM/10531 | Augmentation | Continuation order for one motor launch (M.V. JOYMAKALI) on daily hire basis for use of Hasnabad Sub-Division, P.H.E. Dte. Period : 01.03.23 to 31.08.23 = 184 days. | 0255/HSD | 28/02/2023 | 184 | SUSMITA MANDAL. | 2.74 | 8.46 | 100 | 100
3826 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate , SM/10531 | Augmentation | Acceptance cum work order for Hiring of one no. DIESEL MOTOR CAB (BS-VI) on daily basis for smooth implementation of JJM work under office of the Assistant Engineer, HASNABAD SUB-DIVISION, PHE DTE. Period from 01.02.23 to 31.07.23. | 137/HSD | 31/01/2023 | 181 | SARKAR ENTERPRISE | 0.86 | 1.85 | 100 | 100
3827 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate , SM/10531 | Augmentation | Continuation order for Hiring of one no. Disel Motor Cab (BS-IV) on daily hire basis for use of the Assistant Engineer, Hasnabad Sub-Division, PHE Dte. Period from 01.10.2022 to 30.09.2023. | 1656/HSD | 28/09/2022 | 365 | SUSMITA MANDAL. | 1.72 | 3.72 | 100 | 50
3828 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate , SM/10531 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Maslandapur Water Supply Scheme (Zone - I) within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 2720/BD | 14/09/2022 | 90 | UMWELT ENGINEER PVT.LTD. | 512.52 | 480.61 | 100 | 1
3829 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate , SM/10531 | Augmentation | Material Requisition To Resource Division | 1557/BD | 23/05/2023 | 0 | Resource Division | 3.08 | 0 | 0 | 0
3830 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate , SM/10531 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II & III (Zone-I) under Maslandapur W/S Scheme and Pump House No-I an II uuder Kamarpur-Tazpur W/S Scheme (Rep.) District of 24 Pgs. (N) NIET No.- 29 of EE/EMD of 2022-23 (Sl. No.- 26) | 1320/EMD | 29/03/2023 | 30 | M/S DILIP MITRA | 53 | 25.78 | 81.06 | 80
3831 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate , SM/10531 | Augmentation | Acceptance cum work order for construction of the Boundary wall in Pump House No 2 & Pump House No. 3 of Maslandapur- I Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 1801/BD | 01/07/2024 | 45 | ANJALI CONSTRUCTION. | 6.11 | 0 | 0 | 0
3832 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate , SM/10531 | Augmentation | Acceptance cum work order for construction of the Service Road (88.00 Mtr. Length & 3.00 Mtr. Wide while 1.00 Mtr. wide road already existing) in Head Work Site of Maslandapur- I Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 2209/BD | 06/08/2024 | 15 | PUSPA CONSTRUCTION. | 5.6 | 0 | 0 | 0
3833 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate , SM/10531 | Augmentation | Acceptance cum work order for Sinking of 1 no. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Head Work Site of Maslandapur water supply scheme (Zone - I) within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | 1409/BD | 08/05/2023 | 30 | NADIA TUBEWELLS | 14.49 | 12 | 100 | 100
3834 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate , SM/10531 | Augmentation | Improvement of Iron Elimination Plant at Maslandapur W/S Scheme (Zone - I) within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 693/HAB | 02/11/2023 | 30 | ANJALI CONSTRUCTION. | 4.78 | 4.75 | 100 | 100
3835 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate , SM/10531 | Augmentation | Enhancement of GST for the work providing FHTC for Augmentation of Maslandapur (Zone-I) W/S Scheme | BP-2024-25-778 | 10/07/2024 | 0 | UMWELT ENGINEER PVT.LTD. | 25.55 | 0 | 0 | 0
3836 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate , SM/10531 | Augmentation | Acceptance cum work order for repairing of Boundary Wall in the Head Work site of Maslandapur I Piped water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | 1800/BD | 01/07/2024 | 135 | NEW MA TARA ENTERPRISE. | 5.94 | 0 | 0 | 100
3837 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Maslandapur Zone-I to accommodate , SM/10531 | Augmentation | Repair and renovation of High Lift Pump House, Clorine Room and CWR in the Head Work site of Maslandapur I Piped water supply scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 690/HAB | 24/07/2024 | 105 | TALUKDER & CO. | 4.13 | 0 | 0 | 100
3838 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. , SM/10546 | Augmentation | Survey, Design and preparation of Augmentation DPR in connection with Providing functional household tap connection to every Household under Paikpara Zone-II W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte. | 1172/NWSD-I | 31/12/2021 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.67 | 3.67 | 100 | 1
3839 | NORTH 24 PARGANAS | Eastern Mechanical | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. , SM/10546 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I(Z-II) under Paikpara W/S Scheme District of 24 Pgs. (N) (Block- Baduria). NIET No.- 15 of EE/EMD of 2022-23 (Sl. No.- 14) | 6151/EMD | 11/11/2022 | 30 | M/S DAS ENTERPRISE | 13.21 | 0 | 0 | 0
3840 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. , SM/10546 | Augmentation | Material Requisition To Resource Division | 1212/NWSD-I | 13/10/2022 | 0 | Resource Division | 22.89 | 0 | 0 | 0
3841 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. , SM/10546 | Augmentation | Material Requisition To Resource Division | 457/NWSD-I | 26/04/2023 | 0 | Resource Division | 58.1 | 0 | 0 | 0
3842 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. , SM/10546 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1430/NWSD-I | 18/09/2024 | 7 | BIBHAS PAL | 5.27 | 0.18 | 50 | 100
3843 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. , SM/10546 | Augmentation | Material Requisition To Resource Division | 1303/NWSD-I | 30/08/2024 | 0 | Resource Division | 22.89 | 0 | 0 | 0
3844 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. , SM/10546 | Augmentation | Laying of Distribution System including specials & valves, pipe carrying structure all complete, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, construction works of R.C.C. Elevated Reservoir 400 m3, construction of Pump House, Boundary Wall in Headwork Site, Construction of Service Road (60 Mtr. Length X 3 Mtr.Width) at Headwork site of Paikpara Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District. | 1681/NWSD-I | 30/10/2023 | 365 | PATHIK PABAN NANDI | 542.96 | 74.82 | 13.78 | 35
3845 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC , SM/10301 | Augmentation | Repairing & Renovation 2(Two) nos of Pump House and allied works of Kurulia (Zone-I&II) water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 593/Bon | 22/12/2021 | 21 | PRABIR KUMAR MONDAL. | 2.52 | 2.34 | 92.61 | 1
3846 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC , SM/10301 | Augmentation | Formal work order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of Kurulia(Zone-II) Water Supply Scheme under Bongaon Sub-Division, PHE Dte. (Augmentation). | 988/BD | 31/03/2022 | 90 | H.I.ENTERPRISE. | 360.51 | 360.44 | 100 | 1
3847 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC , SM/10301 | Augmentation | Making Suitable Foundation at out side of the PUmp House of 1000ltr at PH-I Z-II under Kurulia W/S Scheme, W/O-1037/SD-I, T.No.1131/SD-I | 1037/EMSD-I | 04/05/2021 | 30 | TAMAL ENTERPRISE | 0.64 | 0.64 | 100 | 0
3848 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC , SM/10301 | Augmentation | Making Suitable Foundation at out side of the PUmp House of 1000ltr PV Tank at PH-I Z-II under Kurulia W/S Scheme, W/O-1034/SD-I, T.No.1135/SD-I | 1034/ SD-I | 04/05/2021 | 30 | TAMAL ENTERPRISE | 0.69 | 0.69 | 100 | 1
3849 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC , SM/10301 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Kurulia (Zone-II) water supply scheme (2nd T/W site) under Bongaon Sub-Division P.H.E.Dte. | 3590/BD | 08/12/2022 | 15 | M/S SUKANTA ENTERPRISE. | 15.04 | 11.7 | 100 | 100
3850 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC , SM/10301 | Augmentation | Material Requisition To Resource Division | 1365/BD | 13/05/2022 | 0 | Resource Division | 18.73 | 0 | 0 | 0
3851 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC , SM/10301 | Augmentation | Material Requisition To Resource Division | 1673/BD | 13/06/2022 | 0 | Resource Division | 17.77 | 0 | 0 | 0
3852 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC , SM/10301 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Dobila W/S Scheme, Nabatkati W/S Scheme and Kurulia (Zone-II) W/S Scheme District of 24 Pgs. (N) | 4813/EMD | 09/08/2023 | 30 | DEBJYOTI BASU | 78.24 | 15.47 | 59.3 | 66
3853 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC , SM/10301 | Augmentation | Repairing and renovation of Boundary wall, Pump House and construction of Approach Road at 2nd Tube Well site for Augmentation of Kurulia (Zone-II) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1081/Bon | 02/09/2024 | 15 | M/S SAYAN ENTERPRISE. | 4.38 | 0 | 0 | 0
3854 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC , SM/10301 | Augmentation | Repairing and renovation of Compressor Room for Iron Elimination Plant under Augmentation of Kurulia (Zone-II) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 789/Bon | 10/10/2023 | 15 | A.D.ENTERPRISE. | 1.59 | 1.56 | 100 | 100
3855 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC , SM/10301 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Kurulia (Zone-I & II) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 521/BD | 20/02/2024 | 30 | PRABIR KUMAR MONDAL. | 13.94 | 7.45 | 34.89 | 100
3856 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC , SM/10301 | Augmentation | Health assessment of existing OHR of Kurulia (Zone-I) PWSS (225 cum) and ancillary structures, Bagdah Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 688/Bon | 07/06/2024 | 15 | SIRCON ENGINEERING SERVICES | 4.05 | 4.05 | 100 | 100
3857 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC , SM/10301 | Augmentation | Health assessment of existing OHR of Kurulia (Zone-II) PWSS (225 cum) and ancillary structures, Bagdah Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 689/Bon | 07/06/2024 | 15 | SIRCON ENGINEERING SERVICES | 4.53 | 4.53 | 100 | 100
3858 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC , SM/10301 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe and tube well connection under Augmentation work at Kurulia W/S Scheme (Zone - II) Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 3170/BD | 18/11/2024 | 30 | MA CONSTRUCTION. | 59.19 | 0 | 0 | 0
3859 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC , SM/10301 | Augmentation | Acceptance cum work order for Hire and labour charges for staging and scaffolding, bamboo baricading and removal of rubbish for dismantling of existing OHR at Head work Site of Kurulia Zone-II Water Supply Scheme Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. | 706/BD | 06/03/2025 | 60 | HAQUE ENTERPRISE | 8.76 | 0 | 0 | 0
3860 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC , SM/10301 | Augmentation | Construction of Latrine at Head Work site for Augmentation of Kurulia (Zone II) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 670/Bon | 26/05/2025 | 45 | SAMBHU RAY CHOWDHURY. | 1.76 | 0 | 0 | 0
3861 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kurulia Zone-II to accommodate FHTC , SM/10301 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Kurulia (Zone-II) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 520/BD | 20/02/2024 | 330 | ACHINTA KUMAR HALDER. | 13.7 | 0 | 0 | 100
3862 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole , SM/10302 | Augmentation | Acceptance cum work order for Restoration of RCC drain from Pintu Molla Garage to N/H/O Sahidul Molla for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1240/HSD | 20/07/2022 | 21 | JESMINE ENTERPRISE. | 4.74 | 4.67 | 50 | 1
3863 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole , SM/10302 | Augmentation | Acceptance cum work order for Restoration of RCC drain from N/H/O Sahidul Molla to near Julfikar Molla shop for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1246/HSD | 20/07/2022 | 21 | JESMINE ENTERPRISE. | 4.76 | 4.42 | 50 | 1
3864 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole , SM/10302 | Augmentation | Acceptance cum work order for Restoration of RCC drain from Joygram Bazar Idgah to near Pintu Molla Garage for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1238/HSD | 20/07/2022 | 21 | JESMINE ENTERPRISE. | 4.76 | 4.67 | 50 | 1
3865 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole , SM/10302 | Augmentation | Acceptance cum work order for Restoration of RCC drain from Near Julfikar Molla shop to N/H/O Sariful Molla for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1244/HSD | 20/07/2022 | 21 | JESMINE ENTERPRISE. | 3.39 | 3.26 | 50 | 1
3866 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole , SM/10302 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Kumarjole water supply scheme, Minakhan Block within Hasnabad Sub-Division, under Barasat Division, PHE Dte. | 2676/BD | 08/09/2022 | 90 | JAL PRAVAHIKA PVT. LTD. | 260 | 259.94 | 99.98 | 1
3867 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole , SM/10302 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 2437/BD | 22/08/2022 | 30 | AUXILIARY TUBE WELL DRILLERS. | 44.41 | 32.03 | 100 | 100
3868 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole , SM/10302 | Augmentation | Material Requisition To Resource Division | 2472/BD | 24/08/2022 | 0 | Resource Division | 8.92 | 0 | 0 | 0
3869 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Kumarjole , SM/10302 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Bira-Rajibpur W/S Scheme, Khasdelpur W/S Scheme and Kumarjole W/S Scheme with Pump House No-I under Sadpur W/S Scheme District of 24 Pgs. (N) | 4490/EMD | 14/07/2023 | 537 | EASTERN INDIA SALES & SERVICE | 74.22 | 19.26 | 90.83 | 90
3870 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole , SM/10302 | Augmentation | Formal work order for Construction of 400cum capacity 20mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Kumarjole water supply Scheme, Minakhan Block under Hasnabad Sub-Division PHE Dte. | 2612/BD | 29/08/2023 | 365 | S.S.ENTERPRISE. (BAMANGACHI) | 153.33 | 140.36 | 100 | 100
3871 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole , SM/10302 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation of Kumarjole water supply scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 37/HSD | 09/01/2024 | 10 | ABDUL ALIM MONDAL. | 0.83 | 0.8 | 100 | 100
3872 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole , SM/10302 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line and Providing Functional Household Tap Connection for the left out portion in connection with Augmentation of Kumarjole water supply scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 571/BD | 21/02/2025 | 120 | JAL PRAVAHIKA PVT. LTD. | 196.02 | 0 | 0 | 0
3873 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole , SM/10302 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 311/HSD | 04/02/2025 | 10 | ABDUL ALIM MONDAL. | 0.81 | 0 | 0 | 0
3874 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole , SM/10302 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1493/HSD | 14/07/2025 | 10 | ABDUL ALIM MONDAL. | 0.84 | 0 | 0 | 0
3875 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole , SM/10302 | Augmentation | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places in connection with augmentation of Kumarjole W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. (Phase-II) | 263/HSD | 30/01/2025 | 10 | ABDUL ALIM MONDAL. | 0.46 | 0 | 0 | 100
3876 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole , SM/10302 | Augmentation | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places in connection with augmentation of Kumarjole W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. (Phase-I) | 238/HSD | 30/01/2025 | 10 | ABDUL ALIM MONDAL. | 0.89 | 0 | 0 | 100
3877 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I , SM/10507 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Kalinagar W/s scheme (Zone-I), Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 1570/BD | 01/06/2022 | 90 | UMWELT ENGINEER PVT.LTD. | 274.51 | 255.99 | 93.25 | 1
3878 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I , SM/10507 | Retrofitting | Formal work order for Protection work for newly laid UPVC pipe line at different places of Ghoshpur, Kalinagar & Roypur Mouza in connection with retrofitting of Kalinagar w/s scheme (Z-I), Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1358/BD | 04/05/2023 | 30 | UMWELT ENGINEER PVT.LTD. | 134.62 | 134.69 | 100 | 100
3879 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I , SM/10507 | Retrofitting | Acceptance cum work order for Repairing of pump house & boundary wall at P.H.-3 within Kalinagar w/s scheme (Old), Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte | 2114/BD | 19/07/2023 | 21 | GOBINDA DAS. | 7.21 | 7.21 | 100 | 59
3880 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I , SM/10507 | Retrofitting | Acceptance cum work order for Repairing of pump house & boundary wall at PH No.-2 within Kalinagar w/s scheme (Old), Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | 2106/BD | 19/07/2023 | 21 | M/S GHOSH CONSTRUCTION. | 7.1 | 7.1 | 100 | 58
3881 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I , SM/10507 | Retrofitting | Acceptance cum work order for Repairing of existing boundary wall and other allied works at Pump House No.-1 within Kalinagar w/s scheme (Old), Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 2720/BD | 05/09/2023 | 21 | ABDUL ALIM MONDAL. | 9.09 | 9.09 | 100 | 100
3882 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I , SM/10507 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Ghoshpur mouza due to erosion of soil for heavy rain fall during monsoon season within Kalinagar w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 1060/HSD | 31/08/2023 | 10 | M/S RAJPATH CONSTRUCTION. | 0.93 | 0.93 | 100 | 100
3883 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I , SM/10507 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Roypur mouza due to erosion of soil for heavy rain fall during monsoon season within Kalinagar w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 1061/HSD | 31/08/2023 | 10 | M/S RAJPATH CONSTRUCTION. | 0.96 | 0.96 | 100 | 100
3884 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I , SM/10507 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Kalinagar mouza due to erosion of soil for heavy rain fall during monsoon season within Kalinagar w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 1063/HSD | 31/08/2023 | 10 | M/S RAJPATH CONSTRUCTION. | 0.97 | 0.97 | 100 | 100
3885 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I , SM/10507 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) for left out house holds under the command area of Kalinagar water supply scheme (Z-I) in order to provide Har Ghar Jal Certification, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 429/BD | 09/02/2024 | 30 | ABDUL ALIM MONDAL. | 70.78 | 44.11 | 100 | 75
3886 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I , SM/10507 | Retrofitting | Acceptance cum work order for Construction of boundary wall with RCC column & brick masonry & RCC Column structure at Head Work site & PH No- 3 within Kalinagar w/s scheme (Z-I), Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 4435/BD | 10/11/2023 | 720 | ABDUL HAMID GAZI. | 31.93 | 0 | 0 | 80
3887 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I , SM/10507 | Retrofitting | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Kalinagar w/s scheme (OLD), Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 2898/BD | 03/10/2024 | 90 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 94.98 | 0 | 0 | 100
3888 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I , SM/10507 | Retrofitting | Acceptance cum work order for Providing Functional household tap connection at ICDS Centre no-350, 50, 337, 55 and 39 within the command area of Kalinagar w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 549/HSD | 10/03/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.96 | 0 | 0 | 100
3889 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I , SM/10507 | Retrofitting | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in connection with augmentation of Kalinagar w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 163/HSD | 27/01/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.97 | 0 | 0 | 100
3890 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I , SM/10507 | Retrofitting | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Ph No- 2 within Kalinagar W/S scheme (Old), Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 1488/HSD | 14/07/2025 | 10 | SARKAR ENTERPRISE | 0.97 | 0 | 0 | 100
3891 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at different places of Boyermari Pandab para & Boyermari Gazipara in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1350/HSD | 03/08/2022 | 10 | ABDUL HAMID GAZI. | 4.38 | 4.35 | 99.36 | 1
3892 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Sankar Pradhan, Uttam Das at Pradhan para & N/H/O Asraf Molla at Gazi para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1325/HSD | 02/08/2022 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.82 | 0 | 0 | 1
3893 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Emergent resting of different dia UPVC/DI pipeline by UC bullah pile at different places in different mouza while laying of pipeline in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 573/HSD | 23/03/2022 | 15 | S. GHOSH & ASSOCIATES PVT. LTD. | 2.83 | 2.82 | 99.89 | 1
3894 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 1667/BD | 13/06/2022 | 90 | S. GHOSH & ASSOCIATES PVT. LTD. | 266.33 | 243.28 | 57.58 | 1
3895 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places in Chunchura mouza in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 1398/HSD | 08/08/2022 | 15 | ABDUL ALIM MONDAL. | 4.8 | 4.8 | 50 | 1
3896 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Nishith Patra, Tapas Patra at Boyermari Patra para & N/H/O Ramesh Mahato at Boyermari Mahato para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1326/HSD | 02/08/2022 | 10 | SARKAR ENTERPRISE | 4.81 | 4.79 | 50 | 1
3897 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at N/H/O Sukumar Mahato to N/H/O Mansaram Mahato at 6 no. Boyermari in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1327/HSD | 02/08/2022 | 10 | M/S K.B.ENTERPRISE. | 4.52 | 4.52 | 50 | 1
3898 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Protection work for newly laid different dia. UPVC/DI distribution pipeline at different places in Bayermari Mouza of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 2368/BD | 10/08/2022 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 60.68 | 60.66 | 50 | 1
3899 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places within Boyermari mouza in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 1404/HSD | 08/08/2022 | 15 | M/S RAJPATH CONSTRUCTION. | 4.78 | 4.78 | 50 | 1
3900 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Sankar Pradhan, Uttam Das at Pradhan para & N/H/O Asraf Molla at Gazi para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1325/HSD | 02/08/2022 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.82 | 4.81 | 50 | 1
3901 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Sibu Sardar at Boyermari Sardar para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1322/HSD | 02/08/2022 | 10 | M/S ANUBHAB CONSTRUCTION. | 4.42 | 4.42 | 100 | 1
3902 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Sibu Gayen at Boyermari Das para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1323/HSD | 02/08/2022 | 10 | M/S ANUBHAB CONSTRUCTION. | 4.5 | 4.5 | 100 | 1
3903 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Shibcharan Mahato, Chottu Mahato, Arabinda Mahato, Gopal Mahato & Chitta Mahato at Boyermari Mahato para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1324/HSD | 02/08/2022 | 10 | KABASI ENTERPRISE. | 4.72 | 4.71 | 50 | 1
3904 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at N/H/O Nirmal Sardar, Rohit Sardar, Naren Mali, Basudeb Mali at Boyermari Mali para & N/H/O Bablu Singh at Boyermari Choto Singh para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1328/HSD | 02/08/2022 | 10 | M/S LALTI ENTERPRISE | 3.63 | 3.63 | 50 | 1
3905 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Emergent resting of 250/200 mm dia DI pipeline by concrete block over existing concrete wall beside Basanti Highway at different places for Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 563/HSD | 22/03/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.41 | 4.3 | 50 | 1
3906 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Additional emergent resting of 150/100 mm dia DI pipeline by concrete block over existing concrete wall beside Basanti Highway at different places for Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 564/HSD | 22/03/2022 | 15 | ANKUSH CONSTRUCTION & CO. | 4.41 | 4.41 | 50 | 1
3907 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Emergent casing of UPVC pipe line at different locations over Khal, channel, culverts, roads within Chunchura W/S Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | 565/HSD | 22/03/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.38 | 4.37 | 50 | 1
3908 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Emergent resting of 100/150/200 mm dia DI pipeline by concrete block at different places from Kalupara more to N/H/O Sukumar Mahato within Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 566/HSD | 22/03/2022 | 15 | ANKUSH CONSTRUCTION & CO. | 4.32 | 4.03 | 50 | 1
3909 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Emergent resting of 100/150/200 mm dia DI pipeline by concrete block at different places from N/H/O Sukumar Mahato to Dheknimari High School within Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 567/HSD | 22/03/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.32 | 4.29 | 50 | 1
3910 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places within Boyermari mouza in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 355/HSD | 23/02/2022 | 15 | ABDUL ALIM MONDAL. | 4.78 | 4.78 | 50 | 1
3911 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places in connection with retrofitting of Chunchura mouza in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 356/hsd | 23/02/2022 | 15 | M/S RAJPATH CONSTRUCTION. | 4.8 | 4.8 | 50 | 1
3912 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Additional emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places in connection with retrofitting of Chunchura, Boyermari, Sankardaha Abad, Khas Sankardaha mouza in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 357/HSD | 23/02/2022 | 15 | M/S RAJPATH CONSTRUCTION. | 4.8 | 4.77 | 50 | 1
3913 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Formal work order for Protection work in different places of Chunchura, Boyermari, Sankardaha & Sankardaha Abad Mouza in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1696/BD | 08/06/2023 | 30 | AMAL DUTTA ROY | 140.16 | 129.43 | 99.43 | 81
3914 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Laltu Sardar at Boyermari Sardar para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1351/HSD | 03/08/2022 | 10 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 4.42 | 4.37 | 100 | 1
3915 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia. UPVC/DI distribution pipeline by UC bullah pile at different places within Chunchura Mouza in Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 1811/ BD | 27/06/2022 | 30 | MONDAL & CO. (BASIRHAT). | 76.73 | 76.7 | 50 | 1
3916 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Chunchura W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). , SM/10509 | Retrofitting | Formal Work order for Laying of DI rising main and DI/UPVC distribution pipe line and Construction of 900 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Chunchura & Rajbari water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division,PHE Dte. under Barasat Division, PHE Dte. | 767/Bd | 16/03/2022 | 12 | S. GHOSH & ASSOCIATES PVT. LTD. | 563.09 | 248.81 | 100 | 100
3917 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10110 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Santoshpur (Zone-II) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | 1196/NWSD-I | 31/12/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.62 | 4.62 | 100 | 1
3918 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10110 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting fixing of 15 mm NB PVC, schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of Santoshpur Zone-II Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE. Dte. | 544/NWSD-I | 28/04/2022 | 90 | PUSPA ENTERPRISE | 432.64 | 432.88 | 100 | 100
3919 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10110 | Augmentation | Material Requisition To Resource Division | 611/NWSD-I | 17/05/2022 | 0 | Resource Division | 10 | 0 | 0 | 0
3920 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10110 | Augmentation | Material Requisition To Resource Division | 647/NWSD-I | 23/05/2022 | 0 | Resource Division | 11.61 | 0 | 0 | 0
3921 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10110 | Augmentation | Repair and renovation works for 350 cum. capacity R.C.C. Over Head water Reservoir and other allied works at Santoshpur (Zone-II) W/S Scheme under North 24 Pgs Water Supply Division- I, P.H.E. Dte. | 1261/NWSD-I | 21/08/2023 | 60 | PUSPA ENTERPRISE | 51.13 | 45.55 | 100 | 100
3922 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10110 | Augmentation | Material Requisition To Resource Division | 1310/NWSD-I | 30/08/2024 | 0 | Resource Division | 2.46 | 0 | 0 | 0
3923 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10110 | Augmentation | Renovation of AIRP at Santoshpur-Zone-II Water Supply Scheme of capacity 82 Cu.m/hr of Bongaon Block under North 24 Pgs. W/S Div-I, PHE Dte. | 1669/NWSD-I | 19/11/2024 | 360 | J. D. J. ENTERPRISE, A UNIT OF JDJ TRADERS PRIVATE LIMITED | 70.28 | 0 | 0 | 30
3924 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Santoshpur Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10110 | Augmentation | Laying of distribution pipeline and allied work at Bongaon Block under Augmentation Scheme of Santoshpur W/S Scheme (Zone - II) within the jurisdiction of N24Pgs. W/S Division-I, P.H.E. Dte. | 774/NWSD-I | 23/05/2025 | 210 | M/S. S.S. ENTERPRISE | 19.51 | 0 | 0 | 0
3925 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. , SM/10101 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Ichhlampur (Zone-II) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | 1187/NWSD-I | 31/12/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.8 | 3.8 | 100 | 1
3926 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. , SM/10101 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of Ichhlampur Zone-II Water Supply Scheme under North 24 Parganas Water Supply Division-I, PHE. Dte. | 526/NWSD-I | 25/04/2022 | 90 | H. I. ENTERPRISE | 335.97 | 345.83 | 100 | 85
3927 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. , SM/10101 | Augmentation | Material Requisition To Resource Division | 608/NWSD-I | 17/05/2022 | 0 | Resource Division | 11.15 | 0 | 0 | 0
3928 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. , SM/10101 | Augmentation | Material Requisition To Resource Division | 650/NWSD-I | 23/05/2022 | 0 | Resource Division | 24.21 | 0 | 0 | 0
3929 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. , SM/10101 | Augmentation | Renovation of AIRP at Ichhlampur Zone-II Water Supply Scheme of capacity 66.75 Cu.m/hr of Bongaon Block under North 24 Pgs. W/S Div-I, PHE Dte. | 1587/NWSD-I | 29/10/2024 | 180 | GHOSH CONSTRUCTION | 54.12 | 0 | 0 | 0
3930 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. , SM/10101 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir OF 350 CUM, Pump House at Head Works Site, Special Repair & Renovation of Boundary Wall at Head Work Site & other allied works at Ichhlampur Zone-II W/S Scheme Under Bongaon Block In The District Of North 24 Pargana(S) Under N 24 Pgs W/S Div-I, Phe Dte. | 1394/NWSD-I | 05/09/2023 | 60 | SAHA CONSTRUCTION & CO. | 31.49 | 26.56 | 100 | 12
3931 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. , SM/10101 | Augmentation | Material Requisition To Resource Division | 1309/NWSD-I | 30/08/2024 | 0 | Resource Division | 1.23 | 0 | 0 | 0
3932 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. , SM/10101 | Augmentation | Continuation order for the work of Hiring of 1no. Diesel Motor Cab / Maxi Cab with contract carriage permit of R.T.A. in good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all other condition for use of the Executive Engineer, North 24 Parganas Water Supply Division-I, P.H.E. Dte. for 181 (One Hundred Eighty One) w.e.f. 01.01.2025 to 30.06.2025. [Vehicle No.WB 25L4241]. | 1976/NWSD-I | 31/12/2024 | 181 | M/S. SHUBHA ENTERPRISE | 0.86 | 0.89 | 168.21 | 0
3933 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. , SM/10101 | Augmentation | Additional laying of UPVC pipe and allied work under Augmentation work at Ichhlampur (Zone - II) W/S Scheme, Bongaon Block of North 24 Parganas District within the jurisdiction of N24Pgs. W/S Division-I, P.H.E. Dte. | 799/NWSD-I | 28/05/2025 | 210 | OM CONSTRUCTION | 16.95 | 0 | 0 | 67
3934 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ichhlampur Zone-II Block- Bongaon, Dist-North 24 Parganas. , SM/10101 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1431/NWSD-I | 18/09/2024 | 7 | IMAGIN | 4.59 | 0 | 0 | 95
3935 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10104 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Paschim Panchberia (Zone-II) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | 1193/NWSD-I | 31/12/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.96 | 3.96 | 100 | 1
3936 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10104 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 165 m Length in Head work site at PASCHIM PANCHBERIA ZONE-II Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 275/NWSD-I | 14/03/2023 | 45 | NIKHIL SAMADDAR | 19.75 | 18.57 | 100 | 100
3937 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10104 | Augmentation | Service Road (60 Mtr. Length X 3 Mtr. Width) at Headwork site & Service Road (25 Mtr. Length X 2 Mtr. Width) at pump house site at PASCHIM PANCHBERIA ZONE-II Water Supply scheme in Bongaon Block under North 24 Parganas Water Supply Division-I, PHE Dte. | 278/NWSD-I | 14/03/2023 | 45 | RAJ ENTERPRISE | 6.19 | 6.2 | 100 | 100
3938 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10104 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 40 m Length in 2nd Pump house site at PASCHIM PANCHBERIA ZONE-II Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 276/NWSD-I | 14/03/2023 | 45 | ASHIM ENTERPRISE | 5.18 | 3.9 | 100 | 100
3939 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10104 | Augmentation | Special Repair & Renovation of .Pump house and Allied Works at Head Works Site & 2nd Pump house site at PASCHIM PANCHBERIA ZONE-II Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 277/NWSD-I | 14/03/2023 | 45 | GHOSH CONSTRUCTION | 5.2 | 4.59 | 100 | 100
3940 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10104 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works within command area of Paschim Panchberia Zone-II Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE. Dte. | 617/NWSD-I | 17/05/2022 | 90 | UMWELT ENGINEER PRIVATE LIMITED | 326.94 | 308.13 | 100 | 85
3941 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10104 | Augmentation | Material Requisition To Resource Division | 613/NWSD-I | 17/05/2022 | 0 | Resource Division | 3.8 | 0 | 0 | 0
3942 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10104 | Augmentation | Material Requisition To Resource Division | 651/NWSD-I | 23/05/2022 | 0 | Resource Division | 7.22 | 0 | 0 | 0
3943 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10104 | Augmentation | Renovation of AIRP at Paschim Pachneria Zone-II Water Supply Scheme of capacity 59.88 Cu.m/hr of Bongaon Block under North 24 Pgs. W/S Div-I, PHE Dte. | 1739/NWSD-I | 28/11/2024 | 180 | MONDAL PRECISION PRIVATE LIMITED | 68.4 | 0 | 0 | 0
3944 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Panchberia Zone-II to Accommodate FHTC Block- Bongaon, Dist-North 24 Parganas. , SM/10104 | Augmentation | Repair and renovation works of R.C.C. Elevaced Reservoir 350 cum at Paschim Panchberia Zone-II Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | 1099/NWSD-I | 01/08/2023 | 45 | MONDAL CONSTRUCTION | 13.79 | 12.83 | 100 | 100
3945 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chowlpur water supply scheme for providing FHTC under Barasat Arsenic Division, P.H.E. Dte. (Phase - III) , SM/09934 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and allied works at left out portion of different Mouzas under command area of Chowlpur W/S scheme of Barasat - II blocks from Chowlpur and it adjoining mouzas ground water supply scheme under "JAL SWAPNA" programme under Barasat Arsenic Division, PHE Dte. (Phase - III). | 254/B.Ar.D. | 17/02/2022 | 90 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 81.34 | 43.28 | 53.21 | 1
3946 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chowlpur water supply scheme for providing FHTC under Barasat Arsenic Division, P.H.E. Dte. (Phase - III) , SM/09934 | Retrofitting | Repair & Renovation of Iron Elimination Plant of 69 M3 including Media Change of Chowlpur Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 1352/B.Ar.D | 22/07/2022 | 30 | WATERCOMP INDIA | 4.74 | 4.71 | 50 | 1
3947 | NORTH 24 PARGANAS | Barasat Arsenic Division | Retrofitting of Chowlpur water supply scheme for providing FHTC under Barasat Arsenic Division, P.H.E. Dte. (Phase - III) , SM/09934 | Retrofitting | Restoration due to laying of various dia UPVC/HDPE Pipe distribution line at Malrameswarpur mouza of Chowlpur W/S Scheme under Barasat -II block under Barasat Arsenic Division, PHE Dte. | 3030/B.Ar.D. | 29/12/2023 | 30 | SIRCON ENGINEERING SERVICES | 7.69 | 7.63 | 100 | 100
3948 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-A (Berunanpukuria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11826 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-II/A (Berunanpukuria) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 330/NWSD-I | 24/03/2022 | 1 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.2 | 4.01 | 100 | 1
3949 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-A (Berunanpukuria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11826 | Augmentation | Material Requisition To Resource Division | 472/NWSD-I | 26/04/2023 | 0 | Resource Division | 53.67 | 0 | 0 | 0
3950 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-A (Berunanpukuria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11826 | Augmentation | Payment to WBSEDCL |  | 27/06/2023 | 0 | WBSEDCL | 1.66 | 0 | 0 | 0
3951 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-A (Berunanpukuria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11826 | Augmentation | Material Requisition To Resource Division | 1708/NWSD-I | 26/11/2024 | 0 | Resource Division | 23.41 | 0 | 0 | 0
3952 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-A (Berunanpukuria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11826 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 134.54 | 20.28 | 2
3953 | NORTH 24 PARGANAS | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-A (Berunanpukuria) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/11826 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II, A (Berunanpukuria) in Barasat-I Block of North 24 Parganas District. | 4024/ED | 17/10/2023 | 748 | DIPALI CONSTRUCTION | 24.95 | 8.52 | 34.14 | 10
3954 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daora to accommodate FHTC , SM/11537 | Augmentation | Material Requisition To Resource Division | 1559/BD | 23/05/2023 | 0 | Resource Division | 7.62 | 0 | 0 | 0
3955 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Daora to accommodate FHTC , SM/11537 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Replacement) under Daora, Diara & Gokulpur W/S Scheme, District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 07) | 34/EMD | 03/01/2023 | 30 | AHALYA ENGINEERING WORKS | 70.02 | 20.11 | 95.73 | 76
3956 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daora to accommodate FHTC , SM/11537 | Augmentation | Hiring of 1 no. of Diesel Luxury Car (Euro ¿ IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer, for supervision of J.J.M. related work, executed within the entire jurisdiction of Habra Sub-Division, under Barasat Division P.H.E. Dte. (For the period from :01.09.23 to 29.02.24) | 476/HAB | 31/08/2023 | 182 | M/S SUKANTA ENTERPRISE. | 0.86 | 1.94 | 225.14 | 10
3957 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daora to accommodate FHTC , SM/11537 | Augmentation | construction of Service Road (55 Mtr. Length and 2 Mtr. Width) for Pump House No:1 of Deora Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 689/HAB | 24/07/2024 | 15 | M/S SUKANTA ENTERPRISE. | 3.52 | 0 | 0 | 0
3958 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daora to accommodate FHTC , SM/11537 | Augmentation | Acceptance cum work order for Special repair & renovation of boundary wall and other allied Works for Pump House No - 1 of Deora W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 1798/BD | 01/07/2024 | 30 | M/S SUKANTA ENTERPRISE. | 5.27 | 0 | 0 | 0
3959 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daora to accommodate FHTC , SM/11537 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Deora Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 1191/BD | 19/04/2023 | 90 | CHANDA CONSTRUCTION. | 267.73 | 261.22 | 100 | 100
3960 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daora to accommodate FHTC , SM/11537 | Augmentation | Acceptance cum work order for Sinking of 2 no. 300 mm. x 200 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 300 mm. dia. 36 mtr. long housing pipe & 200 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 for Augmentation of Deora water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | 2780/BD | 11/09/2023 | 60 | M/S SUKANTA ENTERPRISE. | 39.1 | 32.57 | 100 | 80
3961 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nityananda Kati Balti to accommodate FHTC , SM/11974 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Nityanadakati Balti Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 440/ BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.69 | 3.69 | 33.33 | 1
3962 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nityananda Kati Balti to accommodate FHTC , SM/11974 | Augmentation | Material Requisition To Resource Division | 860/BD | 20/03/2023 | 0 | Resource Division | 60.86 | 0 | 0 | 0
3963 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nityananda Kati Balti to accommodate FHTC , SM/11974 | Augmentation | Material Requisition To Resource Division | 4411/BD | 10/11/2023 | 0 | Resource Division | 7.39 | 0 | 0 | 0
3964 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Nityananda Kati Balti to accommodate FHTC , SM/11974 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Nityananda Kati Balti water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | 514/BD | 20/02/2023 | 766 | UTPAL CONSTRUCTION & CO. | 272.4 | 223.13 | 81.91 | 52
3965 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Nityananda Kati Balti to accommodate FHTC , SM/11974 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II(Rep.) under Nityananda-Katibalti W/S Scheme District of 24 Pgs. (N) | 4988/EMD | 22/08/2023 | 30 | SANKAR PRASAD DUTTA & CO | 13.17 | 0 | 0 | 0
3966 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC , SM/12569 | Augmentation | Route Survey, Design Drawing & DPR Preparation for SIMLA DURGAPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 376/BHTSD | 16/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.96 | 4.96 | 100 | 1
3967 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC , SM/12569 | Augmentation | Additional survey work for DPR Preparation for SIMLA DURGAPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 377/BHTSD | 16/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.66 | 1.65 | 100 | 1
3968 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC , SM/12569 | Augmentation | New connection charges for Simladurgapur W/s scheme. Memo no. 1006507278/Quot/03 |  | 21/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.46 | 0 | 0 | 0
3969 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC , SM/12569 | Augmentation | Material Requisition To Resource Division | 1247/BD | 25/04/2023 | 0 | Resource Division | 49.35 | 0 | 0 | 0
3970 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC , SM/12569 | Augmentation | Material Requisition To Resource Division | 1626/BD | 01/06/2023 | 0 | Resource Division | 44.17 | 0 | 0 | 0
3971 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC , SM/12569 | Augmentation | Material Requisition To Resource Division | 1647/BD | 02/06/2023 | 0 | Resource Division | 13.76 | 0 | 0 | 0
3972 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC , SM/12569 | Augmentation | New Service Connection for PH No.-under Simla Durgapur | 128/EMD | 09/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.46 | 0 | 0 | 0
3973 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC , SM/12569 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional Household Tap Connection for Augmentation of Simla Durgapur Zone-I water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | 1355/BD | 04/05/2023 | 775 | CHANCHAL ENTERPRISE & CO. | 300.04 | 248.54 | 82.83 | 71
3974 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC , SM/12569 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Simla Durgapur (Zone-II)water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | 1717/BD | 08/06/2023 | 698 | UTPAL CONSTRUCTION & CO. | 446.82 | 258.18 | 57.78 | 48
3975 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC , SM/12569 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Rep.) under Shimla-Durgapur W/S Scheme and Aturia W/S Scheme District of 24 Pgs. (N) | 4814/EMD | 09/08/2023 | 30 | ORIENTAL ENGINEERING CO. | 78.18 | 3.11 | 7.96 | 30
3976 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC , SM/12569 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. big dia. 300 mtr deep tubewell by D.R. Rig method using PVC pipe & strainer having 300 mm dia. 36 mtr. long filter for Augmentation of Shimla Durgapur Zone-II water supply scheme in Baduria Block of Basirhat Sub-Division, under Barasat Division, P.H.E. Dte. | 2804/BD | 12/09/2023 | 717 | SAHA CONSTRUCTION & CO | 21.53 | 0 | 0 | 100
3977 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-II to accommodate FHTC , SM/11657 | Augmentation | Acceptance cum work order for Construction of boundary wall for front & left side at PH No.-2 within Kanaikati Kathalberia w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 1366/HSD | 03/08/2022 | 21 | SHYAM SUNDAR DAS. | 2.68 | 2.66 | 100 | 1
3978 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-II to accommodate FHTC , SM/11657 | Augmentation | Acceptance cum work order for Construction of boundary wall for right & back side at PH No.-2 within Kanaikati Kathalberia w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 1367/HSD | 03/08/2022 | 21 | NEW LIFE CONSTRUCTION. | 3.22 | 3.22 | 100 | 1
3979 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-II to accommodate FHTC , SM/11657 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kanaikati Kathalberia w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 792/BD | 13/03/2023 | 30 | M/S PROGATI ENTERPRISE. | 26.25 | 21.62 | 100 | 100
3980 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-II to accommodate FHTC , SM/11657 | Augmentation | Acceptance cum work order for Repairing of Pump House No.-1 with allied works for Kanaikati Kathalberia w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 824/HSD | 14/07/2023 | 15 | STAR CONSTRUCTION. | 4.69 | 4.57 | 100 | 100
3981 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-II to accommodate FHTC , SM/11657 | Augmentation | Acceptance cum work order for Construction of approach road with cement concrete at PH No- 1 & 2 for Kanaikati Kathalberia w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 825/HSD | 14/07/2023 | 10 | STAR CONSTRUCTION. | 3.92 | 3.84 | 100 | 100
3982 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-II to accommodate FHTC , SM/11657 | Augmentation | Acceptance cum work order for Repairing of Pump House No-2 & other allied works for Kanaikati Kathalberia w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 826/HSD | 14/07/2023 | 10 | PRASANTA MITRA. | 4.2 | 3.74 | 100 | 100
3983 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-II to accommodate FHTC , SM/11657 | Augmentation | Material Requisition To Resource Division | 919/BD | 22/03/2023 | 0 | Resource Division | 34.37 | 0 | 0 | 0
3984 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-II to accommodate FHTC , SM/11657 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-II) (Rep.) under Kanaikathi-Kanthalberia W/S Scheme and Barberia W/S Scheme District of 24 Pgs. (N) NIET No.- 32 of EE/EMD of 2022-23 (Sl. No.- 14) | 1286/EMD | 28/03/2023 | 553 | BENGAL CONSTRUCTION | 54.33 | 24.6 | 67.91 | 50
3985 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-II to accommodate FHTC , SM/11657 | Augmentation | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap in connection with Augmentaion of Kanaikati Kathalberia water supply scheme (Zone-II), Hingalganj Block of Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | 4191/BD | 30/10/2023 | 365 | ABDUL ALIM MONDAL. | 139.6 | 63.75 | 45.66 | 58
3986 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-II to accommodate FHTC , SM/11657 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line and Providing Functional Household Tap Connection for the leftout portion in connection with Augmentation of Kanaikathi Kathalberia water supply scheme (Z-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 1717/BD | 26/06/2024 | 271 | KINGS & CO. | 148.51 | 41.13 | 27.69 | 80
3987 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-II to accommodate FHTC , SM/11657 | Augmentation | Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kanaikati Kathalberia w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 2495/BD | 18/08/2023 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 26.9 | 19.22 | 100 | 70
3988 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-II to accommodate FHTC , SM/11657 | Augmentation | Acceptance cum work order for Construction of temporary approach road for moving of rig machineries at PH No- 1 within Kanaikati Kathalberia w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 40/HSD | 09/01/2024 | 10 | M/S PROGATI ENTERPRISE. | 0.76 | 0.76 | 100 | 100
3989 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-II to accommodate FHTC , SM/11657 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Kanaikati Kathalberia water supply scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 516/BD | 20/02/2023 | 811 | KINGS & CO. | 434.98 | 396.75 | 91.21 | 100
3990 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-II to accommodate FHTC , SM/11657 | Augmentation | Acceptance cum work order for Construction of temporary approach road for moving of pilling rig machineries at OHR site in connection with augmentation of Kanaikati Kathalberia w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 154/HSD | 27/01/2025 | 10 | ABDUL ALIM MONDAL. | 0.99 | 0 | 0 | 100
3991 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC , SM/11660 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Dobila Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 449/ BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.5 | 3.5 | 50 | 1
3992 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC , SM/11660 | Augmentation | Laying of pipe line at Dobila W/s scheme due to widening of PWD ROAD at Dobila Water supply scheme of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. | 837 /BHTSD | 23/06/2022 | 10 | M/S SUKANTA ENTERPRISE. | 2.86 | 2.81 | 98.02 | 0
3993 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC , SM/11660 | Augmentation | Sand filling due laying of pipe line at Dobila W/s scheme of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. | 845 /BHTSD | 23/06/2022 | 10 | M/S SUKANTA ENTERPRISE. | 2.64 | 2.63 | 100 | 1
3994 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC , SM/11660 | Augmentation | Material Requisition To Resource Division | 1273/BD | 25/04/2023 | 0 | Resource Division | 94.49 | 0 | 0 | 0
3995 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC , SM/11660 | Augmentation | Material Requisition To Resource Division | 4407/BD | 10/11/2023 | 0 | Resource Division | 5.73 | 0 | 0 | 0
3996 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC , SM/11660 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Dobila W/S Scheme, Nabatkati W/S Scheme and Kurulia (Zone-II) W/S Scheme District of 24 Pgs. (N) | 4813/EMD | 09/08/2023 | 30 | DEBJYOTI BASU | 78.24 | 19.82 | 75.99 | 66
3997 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC , SM/11660 | Augmentation | Regarding Restoration charges for road damages. | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 28.09 | 0 | 0 | 0
3998 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC , SM/11660 | Augmentation | Acceptance cum work order for Restoration of roads under different water supply schemes of Swarupnagar Block within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | 3625/BD | 20/12/2024 | 90 | PUSPA CONSTRUCTION. | 57.26 | 0 | 0 | 0
3999 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC , SM/11660 | Augmentation | Acceptance cum work order for special repair and renovation of existing structure like Pump House, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Dobila, Eojnogar, Gobindapur Dhokra, Goknasree Gobindapur, Gotra, Sankchura and Mominpur Water Supply Scheme of different block within Basirhat Sub-Division under Barasat Division P.H.E. Dte. | 2464/BD | 16/07/2025 | 150 | M/S TARAFDAR CONSTRUCTION | 81.09 | 0 | 0 | 0
4000 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dobila to accommodate FHTC , SM/11660 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection) for Augmentation of Dobila Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E. Dte. | 1736/BD | 08/06/2023 | 905 | M/S B.N ENTERPRISE | 223.65 | 161.46 | 94.23 | 36
4001 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV (Keyadanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12414 | Augmentation | Detail route survey, design of distribution network and preparation of estimate drawing & DPR for providing FHTC in the scheme of Zone-XIV (Keyadanga) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | 1119/NWSD-I | 16/09/2022 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.82 | 3.8 | 100 | 0
4002 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV (Keyadanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12414 | Augmentation | Material Requisition To Resource Division | 463/NWSD-I | 26/04/2023 | 0 | Resource Division | 131.82 | 0 | 0 | 0
4003 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV (Keyadanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12414 | Augmentation | Material Requisition To Resource Division | 1206/NWSD-I | 14/08/2023 | 0 | Resource Division | 20.86 | 0 | 0 | 0
4004 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV (Keyadanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12414 | Augmentation | Laying of Distribution System including specials, valves all complete, Proposed Rising Main System, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Repair And Renovation Works Of R.C.C. Elevated Reservoir 1250 Cum, Construction Of Pump House (4.88m X 3.66m) Including Sanitary Arrangement, Special Repair And Renovation Of Chlorine Room And Guard Room, Repair & Renovation Of Boundary Wall For 170 M Length In Headwork Site, Construction Of Service Road (60 Mtr. Length X 3 Mtr. Width) At Pump House Site, for Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of ZONE - XIV KEADANGA in Deganga Block of North 24 Pargana(s) District under N24 Pgs W/S Div-I, PHE Dte. | 1058/NWSD-I | 31/07/2023 | 366 | H. I. ENTERPRISE | 569.31 | 563.24 | 100 | 100
4005 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV (Keyadanga) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12414 | Augmentation | New service connection at Keadanga P.H.No-OHR Zone- XIV water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). | BP-335-23-24 | 11/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.34 | 0 | 0 | 0
4006 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC , SM/10371 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Boyermari Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 2237/BD | 28/07/2022 | 30 | M/S K.P.PAL. | 44.4 | 28.38 | 63.91 | 1
4007 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC , SM/10371 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (replacement) under Boyermari Abad W/S Scheme in Sandeshkhali-I Block District of North 24 Pgs. Tender No.- 1452(Sl. No.-04) of EE/EMD of 2022-23, (1) Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC | 3386/ EMD | 14/08/2022 | 365 | M.S.C. ENTERPRISE | 10.81 | 9.96 | 92.1 | 1
4008 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC , SM/10371 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I under Boyermari W/S Scheme District of 24 Pgs. (N) | 3385 / EMD | 14/08/2022 | 30 | PERFECT AIR CONDITIONER | 10.82 | 0 | 0 | 0
4009 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC , SM/10371 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Boyermari Abad water supply scheme, Sandeshkhali-I Block within Hasnabad Sub-Division, under Barasat Division, PHE Dte. | 2928/BD | 26/09/2022 | 90 | S.S.ENTERPRISE. (BAMANGACHI) | 370.05 | 365.77 | 100 | 1
4010 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC , SM/10371 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (replacement) under Boyermari Abad W/S Scheme in Sandeshkhali-I Block District of North 24 Pgs. Tender No.- 08(Sl. No.-04) of EE/EMD of 2022-23 | 3385 /EMD | 14/08/2022 | 30 | PERFECT AIR CONDITIONER | 10.82 | 9.96 | 100 | 1
4011 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC , SM/10371 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Boyermari Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte | 785/HSD | 13/07/2023 | 10 | MD.SALIM GAZI. | 0.87 | 0.87 | 100 | 100
4012 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC , SM/10371 | Augmentation | Material Requisition To Resource Division | 931/BD | 22/03/2023 | 0 | Resource Division | 9.92 | 0 | 0 | 0
4013 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC , SM/10371 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Boyermari Abad W/S scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 1179/HSD | 30/09/2024 | 10 | M/S DATTA ENTERPRISE. | 0.89 | 0 | 0 | 100
4014 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC , SM/10371 | Augmentation | Acceptance cum work order for Emergent withdrawing, relaying and laying of different dia. UPVC/DI pipe line at Boyermari Abad water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E.Dte | 512/BD | 17/02/2025 | 60 | MUKHERJEE CONSTRUCTION (NADIA) | 17.75 | 0 | 0 | 0
4015 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC , SM/10371 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion (River side), protection works & other allied works in connection with Augmentation of Boyermari Abad w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 3129/BD | 12/11/2024 | 270 | S.S.ENTERPRISE. (BAMANGACHI) | 245.45 | 0 | 0 | 0
4016 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC , SM/10371 | Augmentation | Formal work order for Construction of 350 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Boyermari Abad water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 1732/BD | 08/06/2023 | 661 | M/S DATTA ENTERPRISE. | 152.98 | 109.79 | 74.19 | 72
4017 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC , SM/10371 | Augmentation | Acceptance cum work order Sinking of Additional 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Boyermari Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 3377/BD | 02/12/2024 | 60 | M/S K.P.PAL. | 25.88 | 0 | 0 | 100
4018 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Boyermari Abad to accommodate FHTC , SM/10371 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection for Augmentation of Boyermari Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 142/BD | 13/01/2025 | 150 | MD.SALIM GAZI. | 10.55 | 0 | 0 | 35
4019 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC , SM/11631 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Kalupur Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 122/BON | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.8 | 3.77 | 50 | 1
4020 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC , SM/11631 | Augmentation | Material Requisition To Resource Division | 3685/BD | 14/12/2022 | 0 | Resource Division | 117.82 | 0 | 0 | 0
4021 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC , SM/11631 | Augmentation | Material Requisition To Resource Division | 3659/BD | 13/12/2022 | 0 | Resource Division | 21.27 | 0 | 0 | 0
4022 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC , SM/11631 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Rep) under Shimulpur W/S Scheme and Pump House No-I and II (Rep.) under Ichapur W/S Scheme and Kalupur W/S Scheme District of 24 Pgs. (N) | 4798/EMD | 09/08/2023 | 30 | ORIENTAL ENGINEERING CO. | 91.05 | 24.26 | 93.24 | 80
4023 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC , SM/11631 | Augmentation | Acceptance cum work order for Construction of Boundary wall, Approach Road, Earth Filling and Construction of 3.60 mtr. X 3.00 mtr. size Guard Room with sanitary and water supply arrangement incl. plinth protection at OHR site of Kalupur Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 2417/BD | 23/08/2024 | 60 | ROY CHOWDHURY CONSTRUCTION. | 37.8 | 0 | 0 | 0
4024 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC , SM/11631 | Augmentation | Acceptance cum work order for Sinking of 2 (two) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tube well by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kalupur Water Supply Scheme (H/W Site & 2nd T/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | 2924/BD | 26/09/2023 | 60 | SAHA CONSTRUCTION & CO | 32.29 | 25.26 | 100 | 100
4025 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC , SM/11631 | Augmentation | Acceptance cum work order for Construction of Boundary wall at 1st Tube well site for Augmentation of Kalupur Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 560/BD | 22/02/2024 | 45 | MA CONSTRUCTION. | 9.33 | 9.31 | 100 | 100
4026 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC , SM/11631 | Augmentation | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and Construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Kalupur Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 562/BD | 22/02/2024 | 45 | RAJ ENTERPRISE. | 7.53 | 7.52 | 100 | 100
4027 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC , SM/11631 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Kalupur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 93/BD | 11/01/2023 | 1170 | M/S S.S.ENTERPRISE. (SOUTH) | 454.09 | 407.31 | 89.7 | 90
4028 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bagundi to accommodate FHTC , SM/11754 | Augmentation | Material Requisition To Resource Division | 3814/BD | 23/12/2022 | 0 | Resource Division | 17.36 | 0 | 0 | 0
4029 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bagundi to accommodate FHTC , SM/11754 | Augmentation | Acceptance cum work order for Laying of UPVC distribution main and Providing FHTC (Functional Household Tap Connection ) by augmentation for Dakshin Bagundi water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | 3511/BD | 02/12/2022 | 30 | ROY CHOWDHURY CONSTRUCTION. | 50.96 | 43.28 | 100 | 85
4030 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bagundi to accommodate FHTC , SM/11754 | Augmentation | Acceptance cum work order for Construction of Boundary Wall at the site of Pump House 1 of Dakshin Bagundi Water Supply Scheme under Basirhat Sub-Division within Barasat Division, P.H.E. Dte. | 3701/BD | 26/12/2024 | 270 | JEET ENTERPRISE. | 7.96 | 0 | 0 | 0
4031 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11706 | Augmentation | Preparation of Augmentation DPR for Krishnapara Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | 1836/B.Ar.D | 19/09/2022 | 20 | SIRCON ENGINEERING SERVICES | 0.98 | 0.98 | 100 | 1
4032 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11706 | Augmentation | Material Requisition To Resource Division | 2295/B.Ar.D | 02/12/2022 | 0 | Resource Division | 7.71 | 0 | 0 | 0
4033 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11706 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir of Capacity 250 Cu.m. at Krishnapara W/S Scheme of Hasnababad Block under Barasat Arsenic Division, PHE Dte. | 275/B.Ar.D. | 06/02/2023 | 60 | M/S SANJAY ADHIKARI | 13.9 | 13.58 | 100 | 0
4034 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11706 | Augmentation | Material Requisition To Resource Division | 2108/B.Ar.D. | 02/11/2022 | 0 | Resource Division | 1.07 | 0 | 0 | 0
4035 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11706 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. II (Rep.) under Krishnapara W/S Scheme District of 24 Pgs. (N). N.I.E.T No. 27 of EE / EMD of 2022-2023 (2022_PHED_431015_27) | 6730/EMD | 28/11/2023 | 30 | ASHUTOSH DAS & CO. | 9.82 | 0 | 0 | 0
4036 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11706 | Augmentation | Laying of distribution System Including specials all Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Krishnapara at Hasnabad Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | 1558/B.Ar.D. | 24/08/2022 | 90 | PALCON | 103.23 | 69.93 | 100 | 100
4037 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11706 | Augmentation | Construction of Remaining portion of boundary wall & allied works at Krishnapara Head Work site at Krishnapara Water Supply scheme of Hasnabad Block under Barasat Arsenic Division, P.H.E. Dte. | 2657/B.Ar.D. | 09/11/2023 | 45 | M/S DAS & CO | 8.62 | 8.56 | 100 | 100
4038 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11706 | Augmentation | Repair & Renovation of I.E.Plant (Capacity-38 Cu.m.) for Augmentation of Krishnapara Water Supply Scheme under Hasnabad Block under Barasat Arsenic Division, PHE Dte. | 578/B.Ar.D. | 24/03/2025 | 45 | SUNIL DULE | 3.77 | 0 | 0 | 80
4039 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11706 | Augmentation | Laying and Refixing of Ferrule of distribution Pipeline for Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area of Krishnapara W/S Scheme at Hasnabad Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. (SM/11706) | 795/B.Ar.D. | 30/04/2025 | 45 | BABUSONA CONSTRUCTION | 37.18 | 0 | 0 | 0
4040 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC , SM/11591 | Augmentation | supply delivery & installation of automatic programmable logic control system at P.h.IIat P.h no. II under Kachua-Swarupnagar w/s scheme. 24Pgs(N) | 605/EMSD I | 11/03/2022 | 7 | ESENCE ENGINEERING CONCERN | 2.76 | 0 | 0 | 1
4041 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC , SM/11591 | Augmentation | Material Requisition To Resource Division | 3817/BD | 23/12/2022 | 0 | Resource Division | 87.92 | 0 | 0 | 0
4042 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC , SM/11591 | Augmentation | Payment of Earnest Money for New Service Connection at Water Treatment Plant at Basirhat Swarupnagar |  | 07/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.2 | 0 | 0 | 0
4043 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC , SM/11591 | Augmentation | Material Requisition To Resource Division | 607/BD | 23/02/2023 | 0 | Resource Division | 8.6 | 0 | 0 | 0
4044 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC , SM/11591 | Augmentation | Material Requisition To Resource Division | 4422/BD | 10/11/2023 | 0 | Resource Division | 9.24 | 0 | 0 | 0
4045 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC , SM/11591 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Kachua Swarupnagar water supply scheme in Basirhat-II Block under Barasat Division, P.H.E Dte. | 3548/BD | 06/12/2022 | 90 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 395.76 | 390.22 | 100 | 65
4046 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC , SM/11591 | Augmentation | Acceptance cum work order for Restoration of Concrete roads and emergency protection work under different places of Kachua Swarupnagar Water Supply Scheme within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | 2673/BD | 30/07/2025 | 30 | ALAM ENTERPRISE | 7.99 | 0 | 0 | 0
4047 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC , SM/11591 | Augmentation | Acceptance cum work order for Restoration of Kachua Mandir to BaguaDanga Masjid road at Kachua Swarupnagar water supply scheme of Basirhat II Block within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | 3641/BD | 23/12/2024 | 30 | ABUL KALAM GAZI | 9.55 | 0 | 0 | 100
4048 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC , SM/11597 | Augmentation | Repairing & Renovation of 01No. Pump House and allied works at Ashudi water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 528/BON | 01/11/2021 | 21 | A.D.ENTERPRISE. | 2.52 | 2.48 | 100 | 1
4049 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC , SM/11597 | Augmentation | Material Requisition To Resource Division | 3697/BD | 14/12/2022 | 0 | Resource Division | 21.19 | 0 | 0 | 0
4050 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC , SM/11597 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Ashudi Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 3550/BD | 06/12/2022 | 90 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 156.77 | 99.89 | 100 | 0
4051 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC , SM/11597 | Augmentation | Laying of badly damaged distribution pipe line with bamboo pile beside road and other allied works at Ashudi water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 603/Bon | 04/08/2023 | 15 | ROY CHOWDHURY CONSTRUCTION. | 1.62 | 1.61 | 100 | 100
4052 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC , SM/11597 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Ashudi Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | 2943/BD | 27/09/2023 | 30 | JOY GURU ENTERPRISE | 16.12 | 14.83 | 100 | 100
4053 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC , SM/11597 | Augmentation | Acceptance cum work order for Repairing of Boundary wall and Construction of Approach Road at Head Work site and 2nd Pump House site under Augmentation of Ashudi Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 571/BD | 22/02/2024 | 45 | BHABANI ENTERPRISE. | 10.39 | 10.11 | 100 | 100
4054 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC , SM/11597 | Augmentation | Acceptance cum work order for Improvement of existing IEP & other related allied works and including adding 1 no. Polishing unit and Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Ashudi Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 626/BD | 28/02/2024 | 45 | R.K.MANDAL & CO. | 22.68 | 22.16 | 100 | 100
4055 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC , SM/11597 | Augmentation | Acceptance cum work order for Repairing and renovation works of 200 cum. capacity 20mtr. Staging height R.C.C. Over Head water Reservoir for Augmentation of Ashudi Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1538/BD | 07/06/2024 | 45 | A. R CONS | 12.57 | 12.54 | 100 | 100
4056 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC , SM/11597 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II Matiagacha (Block-Habra II) W/S Scheme and Pump House No.I & II Ashudi W/S scheme District of 24 Pgs. (N) | 6738/EMD | 29/11/2023 | 550 | M/S S.R. ENTERPRISE | 42.55 | 0 | 0 | 50
4057 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC , SM/11597 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe under Augmentation work at Ashudi W/S Scheme at Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 3228/BD | 21/11/2024 | 120 | NEW MILLENNIUM ENGG'S CO-OP-SO-LTD. | 45.8 | 0 | 0 | 100
4058 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC , SM/11597 | Augmentation | Acceptance cum work order for Additional laying of pipe line with UPVC pipe due to damage of existing pipe line and allied works and construction of IEP back wash drain and allied works under Augmentation work at Ashudi W/S Scheme at Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1524/BD | 14/05/2025 | 180 | NEW MILLENNIUM ENGG'S CO-OP-SO-LTD. | 33.14 | 0 | 0 | 80
4059 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur & Adjoing Mouza to accommodate FHTC , SM/11599 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Gobindapur water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 585/ BON | 15/12/2021 | 21 | M/S SAYAN ENTERPRISE. | 2.52 | 2.31 | 100 | 1
4060 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur & Adjoing Mouza to accommodate FHTC , SM/11599 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Gobindapur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | 3488/BD | 02/12/2022 | 90 | M/S NIRMAN CONSTRUCTION. | 341.88 | 296.38 | 100 | 99
4061 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur & Adjoing Mouza to accommodate FHTC , SM/11599 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gobindapur water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | 170/BD | 19/01/2023 | 858 | KINGS & CO. | 437.87 | 190.66 | 79.47 | 66
4062 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur & Adjoing Mouza to accommodate FHTC , SM/11599 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as to convert the mouzas into Swajal Gram including laying of UPVC pipe, Pump Connection of 1 no. newly sunk Replacement Tube well with rising main by DI pipe and allied works under Augmentation of Gobindapur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1384/BD | 30/04/2025 | 60 | M/S SAYAN ENTERPRISE. | 11.5 | 0 | 0 | 0
4063 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur & Adjoing Mouza to accommodate FHTC , SM/11599 | Augmentation | Acceptance cum work order for Repair and renovation works of 350cum capacity 20mtr. staging height R.C.C. Over Head Reservoir for Augmentation of Gobindapur Water Supply Scheme, Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | 3403/BD | 04/12/2024 | 90 | UPWARDS ENGINEERING PRIVATE LIMITED. | 8.62 | 0 | 0 | 100
4064 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC , SM/11601 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Hariharpur water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | 521/ BON | 28/10/2021 | 21 | ANKIT CONSTRUCTION | 2.51 | 2.46 | 100 | 1
4065 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC , SM/11601 | Augmentation | Material Requisition To Resource Division | 1256/BD | 25/04/2023 | 0 | Resource Division | 12.08 | 0 | 0 | 0
4066 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC , SM/11601 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Hariharpur Water Supply Scheme (H/W Site)within the jurisdiction of BongaonSub-Division, under Barasat Division, P.H.E. Dte. | 2939/BD | 27/09/2023 | 30 | JOY GURU ENTERPRISE | 16.11 | 15.08 | 100 | 100
4067 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC , SM/11601 | Augmentation | Acceptance cum work order for Repairing and renovation of Compressor Room for AIRP, Construction of Approach Road at 2nd Tube Well site and Construction of Boundary wall and Approach Road at Head Work and 2nd T/W site under Augmentation of Hariharpur Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 625/BD | 28/02/2024 | 45 | JEET ENTERPRISE. | 7.66 | 7.66 | 100 | 100
4068 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC , SM/11601 | Augmentation | Acceptance cum work order for Renovation of 35 Cum/hr of capacity AIRP and allied works at Head work site for Augmentation of Hariharpur Water Supply Scheme under Bongaon Sub-Division, Barasat Division P.H.E. Dte. | 511/BD | 20/02/2024 | 60 | DEBAPRASAD MONDAL. | 38.43 | 38.24 | 100 | 100
4069 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC , SM/11601 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Head Work site for Augmentation of Hariharpur Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 648/BD | 29/02/2024 | 30 | A.D.ENTERPRISE. | 13.35 | 13.34 | 100 | 100
4070 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC , SM/11601 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Hariharpur Water Supply Scheme, Bagdah Block under Bongaon Sub-Division, PHE Dte. | 175/BD | 19/01/2023 | 900 | M/S R.K. ENTERPRISE | 173.76 | 114.27 | 65.76 | 100
4071 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC , SM/11601 | Augmentation | Repairing and renovation of boundary illumination arrangement and allied works at P.H. No. I under Hariharpur W/S Scheme under EMSD-I, P.H.E.Dte. Dist.- 24PGS(N). | 454/EMSD-I | 08/04/2025 | 30 | POLYCON ENGINEERS | 3.37 | 0 | 0 | 100
4072 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-I to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11663 | Augmentation | Preparation of Augmentation DPR for Jasaikathi (Zone-I) Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | 1834/B.Ar.D | 19/09/2022 | 20 | SIRCON ENGINEERING SERVICES | 0.98 | 0.98 | 100 | 1
4073 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-I to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11663 | Augmentation | Material Requisition To Resource Division | 2293/B.Ar.D | 02/12/2022 | 0 | Resource Division | 11.83 | 0 | 0 | 0
4074 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-I to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11663 | Augmentation | Sinking for 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method near at Pump House no.-2 with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter at Jasaikathi (Z-I) w/s scheme of Baduria block under Barasat Arsenic Division, P.H.E. Dte. (Sl No. 2) | 2056/B.Ar.D. | 19/10/2022 | 45 | M/S RAJPATH CONSTRUCTION | 15.35 | 12.24 | 100 | 1
4075 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-I to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11663 | Augmentation | Construction of 3.6 mtr. x 3.0 mtr. size new Pump House ( Pump House-III ) with sanitary arrangement, construction of boundary wall and Allied Works for Jasaikathi ( Z-I ) W/S Scheme Under Baduria Block under Barasat Arsenic Division, PHE Dte. | 1795/B.Ar.D. | 28/07/2023 | 60 | DEL DELTA CONSTRUCTION | 11.59 | 11.49 | 100 | 100
4076 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-I to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11663 | Augmentation | Material Requisition To Resource Division | 2110/B.Ar.D. | 02/11/2022 | 0 | Resource Division | 0.92 | 0 | 0 | 0
4077 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-I to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11663 | Augmentation | New service connection at PH-III Zone-I under Jashaikati W/S Scheme. | BP-125-23-24 | 07/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.83 | 0 | 0 | 0
4078 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-I to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11663 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) (Rep.) under Jashaikathi W/S Scheme District of 24 Pgs. (N) | 4748/EMD | 07/08/2023 | 30 | BINAPANI ENTERPRISE | 26.07 | 12.07 | 46.32 | 47
4079 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-I to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11663 | Augmentation | Sinking for 1 no. 200 mm. x 150 mm. dia. 300 mtr deep Tubewell by D.R. Rig method near at Kankrasuti Mouza with PVC pipe & strainer having 200 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter at Jasaikathi (Z-I ) w/s scheme of Baduria block under Barasat Arsenic Division, P.H.E. Dte. | 82/B.Ar.D. | 11/01/2024 | 30 | M/S DATTA ENTERPRISE | 12.7 | 0 | 0 | 0
4080 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-I to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11663 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir of Capacity 450 Cu.m. at Jasaikathi (Z-I) W/S Scheme of Baduria Block under Barasat Arsenic Division, PHE Dte. | 2656/B.Ar.D. | 09/11/2023 | 45 | B. S. ENTERPRISE | 12.03 | 11.74 | 100 | 100
4081 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-I to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11663 | Augmentation | Construction of boundary wall & allied works at Jasaikathi 2nd T/W site at Jasaikathi ( Z-I ) Water Supply scheme of Baduria Block under Barasat Arsenic Division, P.H.E. Dte. | 2674/B.Ar.D. | 10/11/2023 | 45 | ASHIM ENTERPRISE | 7.02 | 7 | 100 | 100
4082 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-I to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11663 | Augmentation | Laying of UPVC/HDPE pipeline and Repairing, Renovation of Boundary wall, Fencing work etc and other allied works at Head work site of Jasaikathi-(Z-I) W/S Scheme under Baduria Block under Barasat Arsenic Division PHE Dte. | 392/B.Ar.D | 21/02/2024 | 45 | P. & S. ASSOCIATES | 12.55 | 12.4 | 100 | 100
4083 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-I to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11663 | Augmentation | Laying of distribution System Including specials all Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Jasaikathi Zone -I at Baduria Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | 1570/B.Ar.D. | 25/08/2022 | 900 | M/S DATTA ENTERPRISE | 216.55 | 157.03 | 74.02 | 90
4084 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-I to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/11663 | Augmentation | Repair & Renovation of Iron Elementation Plant of 90 M3 including Media Change of Jasaikathi (Z-I) Water Supply Scheme under Baduria Block Under Barasat Arsenic Division, PHE Dte. | 577/B.Ar.D. | 24/03/2025 | 45 | ASSOCIATED ENGINEERS AND TRADERS | 4.58 | 0 | 0 | 100
4085 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Maminpur to accommodate FHTC , SM/11665 | Augmentation | Route Survey, Design Drawing & DPR Preparation for MAMINPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 305/ BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.15 | 2.98 | 50 | 1
4086 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Maminpur to accommodate FHTC , SM/11665 | Augmentation | Material Requisition To Resource Division | 3820/BD | 23/12/2022 | 0 | Resource Division | 16.81 | 0 | 0 | 0
4087 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Maminpur to accommodate FHTC , SM/11665 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method for pump house no - 1 & 2 using PVC pipe & strainer having 300 mm Dia 36 mtr. long Housing Pipe and 200 mm Dia 30 mtr. long filter for Augmentation of Mominpur Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | 674/BD | 01/03/2023 | 30 | DHELA BABA ENTERPRISE | 42.67 | 0 | 0 | 0
4088 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Maminpur to accommodate FHTC , SM/11665 | Augmentation | Material Requisition To Resource Division | 4417/BD | 10/11/2023 | 0 | Resource Division | 11.09 | 0 | 0 | 0
4089 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Maminpur to accommodate FHTC , SM/11665 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Bansjhari-Mullickpur and Maminpur W/S Scheme with Pump House No-I under Rajnagar W/S Scheme District of 24 Pgs. (N) | 4809./EMD | 09/08/2023 | 30 | S.G. ENTERPRISE | 65.16 | 14.79 | 56.73 | 75
4090 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Maminpur to accommodate FHTC , SM/11665 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Maminpur water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | 3340/BD | 16/11/2022 | 769 | MONDAL PRECISION PVT.LTD | 194.77 | 155.27 | 79.72 | 83
4091 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC , SM/11526 | Augmentation | Repairing of Pump House No 1 at Rajandrapur Water Supply Scheme under Basirhat Sub-Division P.H.E. Dte. | 1237/BHT | 16/09/2021 | 20 | PROBAHA ENGINEER'S CO-OP-SOCIETY LTD. | 0.66 | 0.45 | 100 | 1
4092 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC , SM/11526 | Augmentation | Repairing of Pump House No 1 at Rajandrapur Water Supply Scheme under Basirhat Sub-Division P.H.E. Dte. | 1236 /BHTSD | 16/09/2021 | 20 | MD AMIRUL MOLLA. | 0.64 | 0.45 | 100 | 1
4093 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC , SM/11526 | Augmentation | Route Survey, Design Drawing & DPR Preparation for RAJENDRAPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 311/BHT | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.19 | 3.85 | 100 | 1
4094 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC , SM/11526 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Rajendrapur W/S Scheme District of 24 Pgs. (N). (SM/11526) NIET No. 19 of EE/EMD of 2022-23 (Sl. No. - 22) | 6441/EMD | 25/11/2022 | 30 | MAA TARA ENTERPRISE | 13.04 | 11.81 | 90.61 | 0
4095 | NORTH 24 PARGANAS | Central Drilling | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC , SM/11526 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Rajendrapur W/S Scheme (TW-II) , Barasat-II Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | 1648/CDD | 17/10/2023 | 30 | DIPALI CONSTUCTION | 21.78 | 0 | 0 | 0
4096 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC , SM/11526 | Augmentation | Material Requisition To Resource Division | 855/BD | 20/03/2023 | 0 | Resource Division | 71.29 | 0 | 0 | 0
4097 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC , SM/11526 | Augmentation | Material Requisition To Resource Division | 4416/BD | 10/11/2023 | 0 | Resource Division | 12.32 | 0 | 0 | 0
4098 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC , SM/11526 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Replacement) under Rajendrapur W/S Scheme District of 24 Pgs. (N). (SM/11526) NIET No. 19 of EE/EMD of 2022-23 (Sl. No. - 23) | 6440/EMD | 25/11/2022 | 70 | M.D. ENTERPRISE | 13.02 | 7.39 | 56.78 | 40
4099 | NORTH 24 PARGANAS | Central Drilling | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC , SM/11526 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Rajendrapur W/S Scheme (T/W-I) , Basirhat-II Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | 546/CDD | 02/06/2023 | 300 | UNIVERSAL ENTERPRISES | 21.54 | 14.5 | 100 | 100
4100 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC , SM/11526 | Augmentation | Acceptance cum work order for Restoration of roads and emergency protection work under different places of Rajendrapur Water Supply Scheme within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | 2452/BD | 16/07/2025 | 30 | ABDUL CHHAMAD MANDAL | 9.09 | 0 | 0 | 0
4101 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajendrapur to accommodate FHTC , SM/11526 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Rajendrapur water supply scheme in Basirhat-II Block under Barasat Division, P.H.E Dte. | 174/BD | 19/01/2023 | 799 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 376.42 | 326.51 | 90.9 | 70
4102 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC , SM/11527 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under dhobaberia W/S Scheme District of 24 Pgs. (N) | 6444 / EMD | 14/08/2022 | 30 | SINHA ELECTRICALS | 13.04 | 10.91 | 83.7 | 1
4103 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC , SM/11527 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Zone-I) (Replacement) under Dhopaberia W/S Scheme District of 24 Pgs. (N). (SM/11527) | 6382 / EMD | 24/11/2022 | 30 | ALPHA ENTERPRISE | 13.03 | 9.77 | 74.98 | 0
4104 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC , SM/11527 | Augmentation | Supply delivery & installation of Submersible pumping machinery alongwith allied electro-Mechanical Works Voltage stabilezer and automatic chlorinator in coonection with Aug. related to FHTC at Pump House-II Z-I under Dhopaberia W/S Scheme under Dist 24 Pgs North. | 6445/ EMD | 14/08/2022 | 30 | T.S.CONSTRUCTION | 9.48 | 9.48 | 100 | 0
4105 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC , SM/11527 | Augmentation | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) For Augmentation of Dhopaberia-Ganrakupia Water Supply Scheme in Basirhat-II Block of North 24 Parganas District under Barasat Division, PHE Dte. | 3475/ BD | 01/12/2022 | 90 | DIVINE | 311.55 | 303 | 100 | 93
4106 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC , SM/11527 | Augmentation | Material Requisition To Resource Division | 486/BD | 17/02/2023 | 0 | Resource Division | 22.66 | 0 | 0 | 0
4107 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC , SM/11527 | Augmentation | Material Requisition To Resource Division | 597/BD | 23/02/2023 | 0 | Resource Division | 6.69 | 0 | 0 | 0
4108 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC , SM/11527 | Augmentation | Material Requisition To Resource Division | 4420/BD | 10/11/2023 | 0 | Resource Division | 4.93 | 0 | 0 | 0
4109 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Dhopaberia to accommodate FHTC , SM/11527 | Augmentation | Acceptance cum work order for Restoration of roads and emergency protection work under different places of Dhopaberia Water Supply Scheme within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | 1111/BD | 08/04/2025 | 30 | MD AMIRUL MOLLA. | 23.39 | 0 | 0 | 0
4110 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. , SM/11556 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Barbaria of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 431/NWSD-I | 01/04/2022 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.95 | 3.95 | 100 | 1
4111 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. , SM/11556 | Augmentation | Repairing of unmanned panel by supplying of different electrical spares at P.H I under Barberia W/s scheme | 1695/EMSD I | 02/07/2021 | 17 | TAMAL ENTERPRISE | 0.16 | 0.16 | 100 | 1
4112 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. , SM/11556 | Augmentation | Sinking of 01 No. Tube well 300 x 200 mm dia, 300 mtr. depth at 2nd Tube Well site within command area of Barbaria Water Supply Scheme under North 24 Parganas Water Supply Division-I, PHE. Dte. | 1342/NWSD-I | 22/11/2022 | 20 | SAHA CONSTRUCTION & CO. | 20.97 | 14.66 | 100 | 1
4113 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. , SM/11556 | Augmentation | Sinking of 01 No. Tube well 300 x 200 mm dia, 300 mtr. depth at Head Works site within command area of Barbaria Water Supply Scheme under North 24 Parganas Water Supply Division-I, PHE. Dte. | 1340/NWSD-I | 22/11/2022 | 20 | SUDHAMAY MAJUMDAR | 20.97 | 15.1 | 100 | 1
4114 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. , SM/11556 | Augmentation | Site development, construction of Approach road, Bank potection by bullah piling and other ancillary works at Head work site of Barbaria water supply scheme and other ancilary works under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | 1398/NWSD-I | 05/09/2023 | 60 | M/S. SHUBHA ENTERPRISE | 18.04 | 17.45 | 100 | 100
4115 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. , SM/11556 | Augmentation | Material Requisition To Resource Division | 468/NWSD-I | 26/04/2023 | 0 | Resource Division | 36.83 | 0 | 0 | 0
4116 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. , SM/11556 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-II) (Rep.) under Kanaikathi-Kanthalberia W/S Scheme and Barberia W/S Scheme District of 24 Pgs. (N) NIET No.- 32 of EE/EMD of 2022-23 (Sl. No.- 14) | 1286/EMD | 28/03/2023 | 553 | BENGAL CONSTRUCTION | 54.33 | 0 | 0 | 50
4117 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. , SM/11556 | Augmentation | Construction of boundary wall at 3rd T/W site of Barbaria Water Supply Scheme under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | 1217/NWSD-I | 16/08/2024 | 45 | DAS TRADING | 8.01 | 0 | 0 | 0
4118 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. , SM/11556 | Augmentation | Construction of Service Road at 3rd T/W site of Barbaria Water Supply Scheme under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | 1219/NWSD-I | 16/08/2024 | 15 | OM CONSTRUCTION | 2.67 | 0 | 0 | 0
4119 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. , SM/11556 | Augmentation | Special Repair & Renovation , Construction of Boundary Wall and other ancilliary works under Augmentation of Ground water based Barbaria water supply scheme of North 24 Parganas District under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | 1435/NWSD-I | 11/09/2023 | 60 | ELIJA CONSTRUCTION | 11.61 | 8.32 | 100 | 100
4120 | NORTH 24 PARGANAS | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. , SM/11556 | Augmentation | New service connection at P.H.No- I, Zone-II of Barberia water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). | BP-347-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.32 | 0 | 0 | 0
4121 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. , SM/11556 | Augmentation | Construction of Iron elimination Plant (IEP) with concrete Platform, drain etc. at 3rd T/W site of Barbaria Water Supply Scheme under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | 1420/NWSD-I | 17/09/2024 | 495 | NEER UDYOG | 19.51 | 0 | 0 | 49
4122 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. , SM/11556 | Augmentation | Improvement of land of 3rd T/W site of Barbaria water supply scheme under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | 1220/NWSD-I | 16/08/2024 | 15 | OM CONSTRUCTION | 2.51 | 0 | 0 | 100
4123 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gachharati to accommodate FHTC , SM/11541 | Augmentation | Route Survey, Design Drawing & DPR Preparation for GACHHARATI Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | 199/ BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.69 | 2.63 | 50 | 1
4124 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gachharati to accommodate FHTC , SM/11541 | Augmentation | Material Requisition To Resource Division | 3812/BD | 23/12/2022 | 0 | Resource Division | 0.33 | 0 | 0 | 0
4125 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gachharati to accommodate FHTC , SM/11541 | Augmentation | Formal work order for Laying of UPVC distribution pipeline and Providing FHTC (Functional Household Tap Connection ) for augmentation of Gachharati water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | 2934/BD | 26/09/2022 | 90 | SANJOY BAKSHI | 140.52 | 53.21 | 37.86 | 46
4126 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gachharati to accommodate FHTC , SM/11541 | Augmentation | Acceptance cum work order for Sinking of 1nos. 300mm. x 200 mm. big dia 270 mtr deep Tube well by Direct Rotary Rig method at Pump House No.-1 using PVC pipe & strainer having 300 mm Dia 36 mtr. long Housing Pipe and 200 mm Dia 30 mtr. long filter for Augmentation of Gachharati Water Supply Scheme in Basirhat - I Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | 675/BD | 01/03/2023 | 30 | DHELA BABA ENTERPRISE | 19.62 | 0 | 0 | 100
4127 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Gachharati to accommodate FHTC , SM/11541 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Sankarpur and P/H-II under Debhog W/S Scheme with Pump House No-I under Gachharhati W/S Scheme District of 24 Pgs. (N). | 1483/EMD | 03/06/2024 | 298 | EASTERN INDIA SALES & SERVICE | 52.16 | 0 | 0 | 25
4128 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Maslandapur Piped Water Supply Scheme (Zone-II) at Habra-I Block (Phase-I) , SM/08779 | Retrofitting | Formal Work Order cor Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MASLANDAPUR Water Supply Scheme(ZONE-II) at Habra - I Block within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. (Phase - I). | 01/BD | 03/01/2022 | 90 | M/S B.K.ENTERPRISE. | 145.09 | 139.68 | 100 | 1
4129 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Maslandapur Piped Water Supply Scheme (Zone-II) at Habra-I Block (Phase-I) , SM/08779 | Retrofitting | Preparation of geo-referenced GIS mapping with integrated software showing georeferenced location of Households, Piped water supply scheme and Distribution network to be incorporated into map by using both GIS & CAD software keeping the essential Technical aspect of 6 numbers scheme namely Gobindapur Dhokra, Rajnagar, Sadiknagar Zone-I, Bithari Zone-I, Bithari Zone-II and Simla Durgapur of North 24 Pgs. District under the jurisdiction of Basirhat Sub-Division. | 945 / BHT SD | 19/07/2022 | 15 | M/S TECHVISION. | 2.91 | 2.91 | 100 | 1
4130 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Maslandapur Piped Water Supply Scheme (Zone-II) at Habra-I Block (Phase-I) , SM/08779 | Retrofitting | Material Requisition To Resource Division | 251/BD | 27/01/2022 | 0 | Resource Division | 1.99 | 0 | 0 | 0
4131 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Masia Nabastia to accommodate FHTC , SM/11654 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Masia Nabastia water supply scheme in Baduria block under Barasat Division, PHE Dte. | 3372/BD | 18/11/2022 | 90 | GHOSH CONSTRUCTION. | 146.63 | 126.32 | 86.15 | 85
4132 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Masia Nabastia to accommodate FHTC , SM/11654 | Augmentation | Material Requisition To Resource Division | 492/BD | 17/02/2023 | 0 | Resource Division | 12.12 | 0 | 0 | 0
4133 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Masia Nabastia to accommodate FHTC , SM/11654 | Augmentation | Material Requisition To Resource Division | 2307/BD | 03/08/2022 | 0 | Resource Division | 12.12 | 0 | 0 | 0
4134 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Masia Nabastia to accommodate FHTC , SM/11654 | Augmentation | Acceptance cum work order for balance works of Augmentation (including FHTC) within the command area of Masia and Nabastya Piped Water Supply Scheme at Baduria Block under Barasat Division, PHE Dte. | 3185/BD | 18/11/2024 | 330 | GHOSH CONSTRUCTION. | 32.23 | 0 | 0 | 80
4135 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC , SM/11633 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Gotra W/S Scheme District of 24 Pgs. (N). (SM/11633) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 09) | 6384/EMD | 24/11/2022 | 30 | JOYSHREE CONCERN | 12.98 | 9.69 | 74.68 | 0
4136 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC , SM/11633 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Replacement) under Gotra W/S Scheme District of 24 Pgs. (N). (SM/11633) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 10) | 6385/EMD | 24/11/2022 | 30 | KASHINATH PAL & CO. | 13.05 | 11.42 | 87.53 | 0
4137 | NORTH 24 PARGANAS | Central Drilling | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC , SM/11633 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 270 Mtrs. Depth) by utilising Departmental Machineries for Gotra W/S Scheme (T/W-I), Basirhat-I Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. (2ed Call) | 509/CDD | 01/06/2023 | 30 | UNIVERSAL ENTERPRISES | 19.93 | 0 | 0 | 0
4138 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC , SM/11633 | Augmentation | Material Requisition To Resource Division | 487/BD | 17/02/2023 | 0 | Resource Division | 237.82 | 0 | 0 | 0
4139 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC , SM/11633 | Augmentation | Material Requisition To Resource Division | 609/BD | 23/02/2023 | 0 | Resource Division | 19.95 | 0 | 0 | 0
4140 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC , SM/11633 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gotra water supply scheme in Basirhat-I Block under Barasat Division, P.H.E Dte. | 3547/BD | 06/12/2022 | 90 | BALAJI UDDYOG | 468.63 | 330.73 | 70.57 | 57
4141 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC , SM/11633 | Augmentation | Enhancement of GST for laying of distribution pipe line and providing FHTC for Augmentation of Gotra water supply scheme under Basirhat Sub-Division, P.H.E.Dte. | BP-2024-25-393 | 04/10/2024 | 0 | BALAJI UDDYOG | 16 | 0 | 0 | 0
4142 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC , SM/11633 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Gotra Water Supply Scheme in Basirhat - I Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | 3264/BD | 25/11/2024 | 120 | JOY GURU ENTERPRISE | 21.74 | 0 | 0 | 100
4143 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC , SM/11635 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Pipha W/S Scheme District of 24 Pgs. (N). (SM/11635) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 15) | 6389/EMD | 24/11/2022 | 30 | C.M.S. ENGINEERING CONCERN. | 13.05 | 11.8 | 90.43 | 0
4144 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC , SM/11635 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.III (Replacement) under Pipha W/S Scheme District of 24 Pgs. (N). (SM/11635) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 17) | 6391/EMD | 24/11/2022 | 30 | SANKAR PROSAD DUTTA & CO. | 13.02 | 0 | 0 | 0
4145 | NORTH 24 PARGANAS | Central Drilling | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC , SM/11635 | Augmentation | : Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 270 Mtrs. Depth) by utilising Departmental Machineries for Pipha W/S Scheme (TW-I), Barasat-I Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | 1653/CDD | 17/10/2023 | 30 | UNIVERSAL ENTERPRISES | 19.87 | 0 | 0 | 0
4146 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC , SM/11635 | Augmentation | Material Requisition To Resource Division | 495/BD | 17/02/2023 | 0 | Resource Division | 44.41 | 0 | 0 | 0
4147 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC , SM/11635 | Augmentation | Material Requisition To Resource Division | 599/BD | 23/02/2023 | 0 | Resource Division | 7.47 | 0 | 0 | 0
4148 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC , SM/11635 | Augmentation | Material Requisition To Resource Division | 4423/BD | 10/11/2023 | 0 | Resource Division | 6.16 | 0 | 0 | 0
4149 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC , SM/11635 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Pipha water supply scheme in Basirhat-I Block under Barasat Division, P.H.E Dte. | 3631/BD | 12/12/2022 | 787 | SANDIP BISWAS | 318.65 | 281.92 | 97.11 | 95
4150 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC , SM/11635 | Augmentation | Acceptance cum work order for Laying of UPVC Distribution pipe line and providing FHTC for augmentation of Pifa water Supply Scheme within Basirhat - I Block under Basirhat Sub-Division P.H.E Dte. | 3131/BD | 12/11/2024 | 180 | M/S MITRA CONSTRUCTION. | 49.39 | 0 | 0 | 100
4151 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC , SM/11635 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Basirhat-I Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - A) | 146/BHTSD | 29/01/2025 | 20 | BIBHAS PAL. | 0.88 | 0 | 0 | 90
4152 | NORTH 24 PARGANAS | Barasat Division | Ghipukuria Piped Water Supply Scheme. , SM/12718 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (GHIPUKURIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 274/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
4153 | NORTH 24 PARGANAS | Barasat Division | Ghipukuria Piped Water Supply Scheme. , SM/12718 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (GHIPUKURIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | 275/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.83 | 0.83 | 100 | 1
4154 | NORTH 24 PARGANAS | Barasat Division | Ghipukuria Piped Water Supply Scheme. , SM/12718 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (GHIPUKURIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | 275/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.83 | 0 | 0 | 1
4155 | NORTH 24 PARGANAS | Barasat Division | Ghipukuria Piped Water Supply Scheme. , SM/12718 | New | Material Requisition To Resource Division | 891/BD | 22/03/2023 | 0 | Resource Division | 15.9 | 0 | 0 | 0
4156 | NORTH 24 PARGANAS | Barasat Division | Ghipukuria Piped Water Supply Scheme. , SM/12718 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 150 cum capacity CWR , pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Ghipukuria w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1698/BD | 08/06/2023 | 1096 | TIRUPATI ENTERPRISES | 270.61 | 111.74 | 41.29 | 70
4157 | NORTH 24 PARGANAS | Barasat Division | Tapla Kusangra Piped Water Supply Scheme. , SM/12720 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (TAPLA KUSANGRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 310/HSD | 15/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.82 | 4.82 | 100 | 1
4158 | NORTH 24 PARGANAS | Barasat Division | Tapla Kusangra Piped Water Supply Scheme. , SM/12720 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (TAPLA KUSANGRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | 311/HSD | 15/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 0.52 | 0.52 | 100 | 1
4159 | NORTH 24 PARGANAS | Barasat Division | Tapla Kusangra Piped Water Supply Scheme. , SM/12720 | New | Material Requisition To Resource Division | 887/BD | 22/03/2023 | 0 | Resource Division | 12.08 | 0 | 0 | 0
4160 | NORTH 24 PARGANAS | Eastern Mechanical | Tapla Kusangra Piped Water Supply Scheme. , SM/12720 | New | Service connection charges at PH-I under Tapla Kusangra W/S Scheme | BP-289-23-24 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.21 | 0 | 0 | 0
4161 | NORTH 24 PARGANAS | Barasat Division | Tapla Kusangra Piped Water Supply Scheme. , SM/12720 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Tapla Kusangra w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1682/BD | 07/06/2023 | 1029 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 328.77 | 222.42 | 67.65 | 80
4162 | NORTH 24 PARGANAS | Barasat Division | Tapla Kusangra Piped Water Supply Scheme. , SM/12720 | New | Acceptance cum work order for Construction of boundary wall with column structure at Head Work site within Tapla Kusangra w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1031/BD | 28/03/2025 | 90 | ACHARJEE AND ASSOCIATES | 17.53 | 0 | 0 | 0
4163 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC , SM/12125 | Augmentation | Acceptance cum work order for Construction of boundary wall for Back & Left side at PH No.-1 within Kanaikati Kathalberia w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 1362/HSD | 03/08/2022 | 21 | BADAL GHOSH. | 3.87 | 3.84 | 100 | 1
4164 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC , SM/12125 | Augmentation | Acceptance cum work order for Emergent fencing work for protecting the adjacent land of PH no-1 within Kanaikati Kathalberia w/s scheme (Z-I), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | 793/HSD | 13/07/2023 | 10 | NEW LIFE CONSTRUCTION. | 0.91 | 0 | 0 | 0
4165 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC , SM/12125 | Augmentation | Acceptance cum work order for Construction of boundary wall for Front & Right side at PH No.-1 within Kanaikati Kathalberia w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 1363/HSD | 03/08/2022 | 21 | LAHIRI CONSTRUCTION. | 3.34 | 3.33 | 100 | 1
4166 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC , SM/12125 | Augmentation | Acceptance cum work order for Construction of boundary wall for right & back side at PH No.-2 within Kanaikati Kathalberia w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 1364/HSD | 03/08/2022 | 21 | STAR CONSTRUCTION. | 3.26 | 3.23 | 100 | 1
4167 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC , SM/12125 | Augmentation | Acceptance cum work order for Construction of boundary wall for front & left side at PH No.-2 within Kanaikati Kathalberia w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | 1365/HSD | 03/08/2022 | 21 | STAR CONSTRUCTION. | 2.66 | 2.66 | 100 | 1
4168 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC , SM/12125 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kanaikati Kathalberia w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 791/BD | 13/03/2023 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 26.26 | 18.02 | 100 | 7
4169 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC , SM/12125 | Augmentation | Acceptance cum work order for Repairing of pump house & construction of approach road with cement concrete at PH No.-2 for Kanaikati Kathalberia w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | 2116/BD | 19/07/2023 | 15 | M/S K.B.ENTERPRISE. | 5.59 | 5.35 | 100 | 100
4170 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC , SM/12125 | Augmentation | Material Requisition To Resource Division | 916/BD | 22/03/2023 | 0 | Resource Division | 13.65 | 0 | 0 | 0
4171 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC , SM/12125 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap connection for Augmentation of Kanaikati Kathalberia water Supply Scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division P.H.E.Dte. | 4201/BD | 31/10/2023 | 540 | KINGS & CO. | 707.01 | 538.15 | 76.12 | 80
4172 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC , SM/12125 | Augmentation | Acceptance cum work order for Construction of 150 cum capacity CWR , pipe connection and cost of pipes, specials for Augmentation of Kanaikati Kathalberia water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, P.H.E Dte. | 2520/BD | 02/09/2024 | 180 | SARKAR ENTERPRISE & CO. | 43.88 | 0 | 0 | 0
4173 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC , SM/12125 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) (Rep.) under Kanaikathi-Kanthalberia W/S Scheme District of 24 Pgs. (N) NIET No.- 27 of EE/EMD of 2022-23 (Sl. No.- 21) | 1233/EMD | 24/03/2023 | 30 | GLACIER ENGINEERING CO. | 27.79 | 23.98 | 100 | 100
4174 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC , SM/12125 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kanaikati Kathalberia w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | 2494/BD | 18/08/2023 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 26.9 | 20.67 | 100 | 33
4175 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Kanaikati kathalberia Zone-I to accommodate FHTC , SM/12125 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line and Providing Functional Household Tap Connection for the leftout portion in connection with Augmentation of Kanaikathi Kathalberia water supply scheme (Z-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | 3051/BD | 24/10/2024 | 30 | KINGS & CO. | 101.79 | 0 | 0 | 0
4176 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC , SM/12127 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.III (New) under Helencha W/S Scheme, District of 24 Pgs. (N). | 4722/EMD | 04/08/2023 | 30 | M/S. G.P. ENTERPRISE | 10.72 | 0 | 0 | 0
4177 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC , SM/12127 | Augmentation | Material Requisition To Resource Division | 1258/BD | 25/04/2023 | 0 | Resource Division | 147.75 | 0 | 0 | 0
4178 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC , SM/12127 | Augmentation | Hiring of an Additional Vehicle (Diesel) for the site inspection of different ongoing schemes under JJM Program at Bongaon Sub-Division, P.H.E.Dte. period from 01.01.2024 to 30.06.2024. | 1022/Bon | 29/12/2023 | 183 | VAI ENTERPRISE. | 0.86 | 1.95 | 226.06 | 0
4179 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC , SM/12127 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing (FHTC) for augmentation of Helencha Water Supply Scheme, Bagdah Block, under Bongaon Sub-Division, PHE Dte. | 754/BD | 09/03/2023 | 90 | MONDAL ENTERPRISE. (BARASAT) | 684.22 | 678.51 | 100 | 100
4180 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC , SM/12127 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Replacement) under Helencha W/S Scheme, District of 24 Pgs. (N). | 4723/EMD | 04/08/2023 | 30 | WESTERN ENGINEERING CO. | 21.41 | 19.67 | 100 | 100
4181 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC , SM/12127 | Augmentation | Acceptance cum work order for Sinking of 2 (two) no. 300 mm. x 200 mm. dia.250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Helencha Water Supply Scheme (H/W Site & 2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | 2941/BD | 27/09/2023 | 60 | JOY GURU ENTERPRISE | 32.22 | 26.95 | 100 | 100
4182 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC , SM/12127 | Augmentation | Repairing and renovation of Pump House No.- 3 under Augmentation of Helencha Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1396/Bon | 27/11/2024 | 20 | KAMAL HALDER. | 1.76 | 1.73 | 100 | 100
4183 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC , SM/12127 | Augmentation | Health assessment of existing OHR of Helencha PWSS (350 cum) and ancillary structures, Bagdah Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 690/Bon | 07/06/2024 | 15 | SIRCON ENGINEERING SERVICES | 4.58 | 4.58 | 100 | 100
4184 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC , SM/12127 | Augmentation | Repairing and renovation of Compressor Room for Iron Elimination Plant under Augmentation of Helencha Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 640/Bon | 14/08/2023 | 21 | MONDAL & CO.(BON) | 1.59 | 1.56 | 100 | 100
4185 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC , SM/12127 | Augmentation | Hiring of an Additional Vehicle (Diesel) for the site inspection of different ongoing schemes under JJM Program at Bongaon Sub-Division, P.H.E.Dte. period from 01.07.2024 to 31.08.2024. | 801/Bon | 28/06/2024 | 61 | VAI ENTERPRISE. | 0.29 | 0.59 | 200.75 | 0
4186 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC , SM/12127 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe and allied works under Augmentation work at Helencha W/S Scheme Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (Part-B). | 3267/BD | 25/11/2024 | 300 | ABDUL HAMID GAZI. | 27.07 | 0 | 0 | 35
4187 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC , SM/12127 | Augmentation | Hiring of an Additional Vehicle (Diesel) for the site inspection of different Bongaon ongoing schemes under JJM Program at Bongaon Sub-Division, P.H.E.Dte. (Period from:-01/09/2024 to 28/02/ 2025) | 1076/Bon | 30/08/2024 | 182 | PRIYAM ENTERPRISE | 0.86 | 1.75 | 203.95 | 0
4188 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC , SM/12127 | Augmentation | Acceptance cum work order for Repairing & renovation of Boundary wall, Earth Filling, Concreting and Repairing & renovation of 3.60 mtr. X 3.00 mtr. size Pump House with sanitary and water supply arrangement at 2nd TW Site of Helencha Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 1902/BD | 05/06/2025 | 120 | KAMAL HALDER. | 10.52 | 0 | 0 | 0
4189 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC , SM/12127 | Augmentation | Repairing and renovation of 150 Cum C.W.R. for Augmentation of Helencha Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 817/Bon | 26/06/2025 | 45 | KAMAL HALDER. | 2.15 | 0 | 0 | 0
4190 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC , SM/12127 | Augmentation | Construction of Latrine at Head Work site for Augmentation of Helencha Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 640/Bon | 21/05/2025 | 45 | KAMAL HALDER. | 2.4 | 0 | 0 | 0
4191 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC , SM/12127 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Helencha Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 537/BD | 21/02/2024 | 360 | ACHINTA KUMAR HALDER. | 15.42 | 3.99 | 20.94 | 100
4192 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC , SM/12127 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe and allied works under Augmentation work at Helencha W/S Scheme Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (Part-A). | 3387/BD | 03/12/2024 | 180 | KAMAL HALDER. | 11.54 | 0 | 0 | 100
4193 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Helencha to accommodate FHTC , SM/12127 | Augmentation | Acceptance cum work order for Repairing and renovation works for 350 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir for Augmentation of Helencha Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | 2686/BD | 18/09/2024 | 135 | RAKESH ENTERPRISE. | 17.39 | 6.8 | 28.14 | 100
4194 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC , SM/13350 | Augmentation | Additional Survey work for DPR Preparation for PARUI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE | 461 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.04 | 2.04 | 100 | 1
4195 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC , SM/13350 | Augmentation | Route Survey,design drawing & DPR Preparation for PARUI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 460/BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 100 | 1
4196 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC , SM/13350 | Augmentation | New connection charges for Parui W/s scheme. Memo no. 1006419455/Quot/03 |  | 21/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.51 | 0 | 0 | 0
4197 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC , SM/13350 | Augmentation | New Service Connection for PH No.- under Parui W/S Scheme | 95/EMD | 26/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.51 | 0 | 0 | 0
4198 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC , SM/13350 | Augmentation | Material Requisition To Resource Division | 1262/BD | 25/04/2023 | 0 | Resource Division | 190.25 | 0 | 0 | 0
4199 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC , SM/13350 | Augmentation | Material Requisition To Resource Division | 1645/BD | 02/06/2023 | 0 | Resource Division | 10.32 | 0 | 0 | 0
4200 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC , SM/13350 | Augmentation | Material Requisition To Resource Division | 4421/BD | 10/11/2023 | 0 | Resource Division | 39.07 | 0 | 0 | 0
4201 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC , SM/13350 | Augmentation | Formal work order for Laying of DI / UPVC distribution pipe line & Providing FHTC (Functional Household Tap Connection) by Augmentation for Parui (Zone - II) water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E. Dte. | 1711/BD | 08/06/2023 | 749 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 583.8 | 367.49 | 62.95 | 25
4202 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC , SM/13350 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing FHTC (Functional Household Tap Connection) for Augmentation of Parui Zone-I water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | 1440/BD | 11/05/2023 | 90 | SANJIB DEY | 113.91 | 109.5 | 100 | 60
4203 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC , SM/13350 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (rep.) under Parui W/S Scheme District of 24 Pgs. (N) | 4718/EMD | 04/08/2023 | 759 | A.S. ENTERPRISE | 39.16 | 0 | 0 | 40
4204 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Parui to accommodate FHTC , SM/13350 | Augmentation | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Parui W/S Scheme including increasing the height of back wash tank at Swarupnagar Block under Basirhat Sub Division, PHE Dte. capacity - 160.00 cum/hr. | 925/BD | 15/03/2024 | 360 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 37.26 | 0 | 0 | 50
4205 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-II-Berunanpukuria OHR) at Barasat-I Block , SM/08242 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within command area of surface water based water supply scheme ( Zone II) at Berunanpukuria OHR site at Barasat-I Block for Arsenic affected areas under North 24 Parganas water supply Division - I, PHE Dte. | 864/NWSD-I | 08/10/2021 | 75 | PUSPA ENTERPRISE | 79.59 | 81.18 | 100 | 1
4206 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Providing Functional Household Tap Connection (FHTC) inconnection with Jal Jeevan Mission (JJM and JAL SWAPNA)within the command area of Surface Water Based Water Supply Scheme (Zone-II-Berunanpukuria OHR) at Barasat-I Block , SM/08242 | Retrofitting | Hiring of 1 no. Diesel Ambassador Car/ Cab with contract carriage permit of R.T.A. in good running condition both in regards to body and engine with efficient driver with valid driving license as deemed fit on daily rental basis including fulfillment of all condition for use of the Assistant Engineer (HQ-I), North 24-Parganas W/S Division-I, P.H.E. Dte. from 20.08.2024 to 28.02.2025. i.e. 193 days. (Vehicle No. WB23E0645) | 1238/NWSD-I | 20/08/2024 | 193 | RAJESH JADAB | 0.92 | 1.95 | 212.89 | 0
4207 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC , SM/13040 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ATURIA Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 348/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.97 | 4.97 | 100 | 1
4208 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC , SM/13040 | Augmentation | Additional Survey work for DPR Preparation for ATURIA Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | 349/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.98 | 1.91 | 100 | 1
4209 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC , SM/13040 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. big dia. 300 mtr deep tubewell by D.R. Rig method using PVC pipe & strainer having 300 mm dia. 36 mtr. long filter for Augmentation of Aturia Zone-II water supply scheme in Baduria Block of Basirhat Sub-Division, under Barasat Division, P.H.E. Dte. | 2803/BD | 12/09/2023 | 30 | SAHA CONSTRUCTION & CO | 21.53 | 0 | 0 | 0
4210 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC , SM/13040 | Augmentation | Material Requisition To Resource Division | 1253/BD | 25/04/2023 | 0 | Resource Division | 86.25 | 0 | 0 | 0
4211 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC , SM/13040 | Augmentation | Material Requisition To Resource Division | 4409/BD | 10/11/2023 | 0 | Resource Division | 42.27 | 0 | 0 | 0
4212 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC , SM/13040 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Aturia Zone-II water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | 1305/BD | 26/04/2023 | 90 | JAL PRAVAHIKA PVT. LTD. | 282.82 | 143 | 50.56 | 31
4213 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC , SM/13040 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Aturia (Zone-I) water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | 1702/BD | 08/06/2023 | 876 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 546.47 | 462.6 | 84.65 | 41
4214 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC , SM/13040 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Rep.) under Shimla-Durgapur W/S Scheme and Aturia W/S Scheme District of 24 Pgs. (N) | 4814/EMD | 09/08/2023 | 30 | ORIENTAL ENGINEERING CO. | 78.18 | 0 | 0 | 30
4215 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC , SM/13040 | Augmentation | Regarding Restoration charges for road damages. | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 48.02 | 0 | 0 | 0
4216 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC , SM/13040 | Augmentation | Acceptance cum work order for Eucalyptus Bullah Pilling for Emergency protection Work of Pipe line at different places for Augmentation of Aturia Zone-I Water Supply Scheme of Basirhat Sub Division under Barasat Division P.H.E. | 724/BD | 07/03/2025 | 30 | SHIBU BISWAS. | 44.01 | 0 | 0 | 0
4217 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Aturia to accommodate FHTC , SM/13040 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Baduria Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - B) | 144/BHTSD | 29/01/2025 | 20 | M.R.CONSTRUCTION. | 0.88 | 0 | 0 | 90
4218 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-V/B (Gopalpur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12730 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-V/B (Gopalpur) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | 425/NWSD-I | 01/04/2022 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.3 | 4.3 | 100 | 1
4219 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-V/B (Gopalpur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12730 | Augmentation | Material Requisition To Resource Division | 475/NWSD-I | 26/04/2023 | 0 | Resource Division | 153.54 | 0 | 0 | 0
4220 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-V/B (Gopalpur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12730 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | 1424/NWSD-I | 08/09/2023 | 366 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 0 | 0 | 2
4221 | NORTH 24 PARGANAS | Barasat Division | Kharibaria Piped Water Supply Scheme. , SM/13519 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KHARIBARIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 282/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 0
4222 | NORTH 24 PARGANAS | Barasat Division | Kharibaria Piped Water Supply Scheme. , SM/13519 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KHARIBARIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B). | 283/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.49 | 2.49 | 100 | 0
4223 | NORTH 24 PARGANAS | Barasat Division | Kharibaria Piped Water Supply Scheme. , SM/13519 | New | Material Requisition To Resource Division | 896/BD | 22/03/2023 | 0 | Resource Division | 18.77 | 0 | 0 | 0
4224 | NORTH 24 PARGANAS | Barasat Division | Kharibaria Piped Water Supply Scheme. , SM/13519 | New | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 250 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Khariberia w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | 1705/BD | 08/06/2023 | 1095 | M/S PROGATI ENTERPRISE. | 400.07 | 272.17 | 68.03 | 90
4225 | NORTH 24 PARGANAS | Eastern Mechanical | Kharibaria Piped Water Supply Scheme. , SM/13519 | New | Service connection charges at PH-I under Khariberia W/S Scheme | BP-294-23-24 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 25.56 | 0 | 0 | 0
4226 | NORTH 24 PARGANAS | Barasat Division | Kharibaria Piped Water Supply Scheme. , SM/13519 | New | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tube well by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for within Bamanpukuria & Khariberia w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 635/BD | 28/02/2025 | 45 | ACME CONSTRUCTION | 51.71 | 0 | 0 | 0
4227 | NORTH 24 PARGANAS | Barasat Division | Kharibaria Piped Water Supply Scheme. , SM/13519 | New | Formal work order for Additional Laying of UPVC distribution pipe line with Protection works in Sankardaha, Khariberia, Bargan Gopalpur & Mallickgheri mouzas under Khariberia w/s scheme within Minakhan block, Hasnabad Sub-Division P.H.E. Dte. | 1798/BD | 30/05/2025 | 30 | ATCO ENTERPRISE | 118.72 | 0 | 0 | 0
4228 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Pa , SM/13529 | Retrofitting | Formal work order for Land development, Construction of Office cum Guard room and Switch cum Chlorine Room, Boundary wall, Surface drain and related allied works at Zonal Head work site - XIV i.e. Kumra /Zonal Head work site - XVI i.e.Nangla including Laying Distribution System within the jurisdiction of (Zone-XIV) /(Zone-XVI), Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Surface Water based Water Supply Scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoining Mouzas under North 24 Parganas District project within Barasat Division, P.H.E. Dte. Habra-I Block PART-C / Habra-I Block PART-E. | 110/BD | 10/01/2024 | 910 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3691.85 | 0 | 0 | 88
4229 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC , SM/14733 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 250 mm. x 150 mm. dia. 300 mtr deep as a Replacement of Tubewell by D.R. Rig method, having 250mm dia 36.0 mtr. long UPVC housing pipe & 150mm dia 30 mtr. long UPVC ribbed strainer for Augmentation of Kashimpur Water Supply Scheme at Head Work Site under Barasat Sub-Division, PHE Dte. | 2460/BD | 17/08/2023 | 30 | M/S K.P.PAL. | 16.08 | 11.87 | 100 | 100
4230 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC , SM/14733 | Augmentation | Material Requisition To Resource Division | 1671/BD | 06/06/2023 | 0 | Resource Division | 9.76 | 0 | 0 | 0
4231 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC , SM/14733 | Augmentation | Material Requisition To Resource Division | 1282/BD | 25/04/2023 | 0 | Resource Division | 13.18 | 0 | 0 | 0
4232 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC , SM/14733 | Augmentation | Acceptance cum work order for Hiring diesel luxury car daily basis (From 22.11.2023 to 31.05.2024) for the Office uses of the Assistant Engineer (HQ) Barasat Division, P.H.Dte. | 4461/BD | 21/11/2023 | 192 | KRISHNA SAHA. | 0.91 | 1.72 | 188.22 | 18
4233 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC , SM/14733 | Augmentation | Acceptance cum work order for the work of Hiring Diesel Luxury Car on daily basis for the Office of the Dy. Superintending Engineer-I, Monitoring Cell, PHE Dte. (Period from 01-01-2024 to 31-03-2024). | 4696/BD | 12/12/2023 | 91 | DIPANKAR NASKAR. | 0.43 | 0.9 | 208.57 | 100
4234 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC , SM/14733 | Augmentation | Acceptance cum work order for Hiring diesel luxury car daily basis (From 01.06.2024 to 30.11.2024) for the Office uses of the Assistant Engineer (HQ) Barasat Division, P.H.Dte. | 845/BD | 13/03/2024 | 183 | KRISHNA SAHA. | 0.87 | 0.76 | 86.88 | 0
4235 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC , SM/14733 | Augmentation | Acceptance cum work order for the work of Hiring Diesel Luxury Car on daily basis for the Office of the Dy. Superintending Engineer-I, Monitoring Cell, PHE Dte. (Period from 01-04-2024 to 30-09-2024). | 914/BD | 15/03/2024 | 183 | DIPANKAR NASKAR. | 0.87 | 1.2 | 138.61 | 100
4236 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC , SM/14733 | Augmentation | Preparation of DPR in connection of augumentation of Kashimpur Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | 666/BSD | 25/08/2022 | 30 | RADIANT | 3.04 | 2.88 | 100 | 100
4237 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC , SM/14733 | Augmentation | Formal work order for Construction of 200 cum capacity 20 mtr. height R.C.C. Over Head Reservoir as per Deptt. design, drawing & specification including bored pile & pile cap, laying of DI rising main & distribution pipe line by DI/UPVC and Providing FHTC for Augmentaion of Kashimpur water supply scheme under Barasat Sub-Division, P.H.E. Dte. | 1716/BD | 08/06/2023 | 366 | S.S.ENTERPRISE. (BAMANGACHI) | 318.43 | 317.44 | 100 | 90
4238 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC , SM/14733 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep) under Kashimpur W/S Scheme District of 24 Pgs. (N) | 4746/EMD | 07/08/2023 | 30 | MAHAMAYA ENTERPRISE. | 26.07 | 24.17 | 100 | 100
4239 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC , SM/14733 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 250 mm. x 150 mm. big dia. 210 mtr deep Tubewell by D.R. Rig method having 250 mm dia 42.0 mtr. long PVC housing pipe & 150 mm dia 30.0 mtr. long filter for Augmentation Kashimpur Water Supply Scheme (2nd T/W Site) of Barasat Sub-Division under Barasat Division, PHE Dte. | 587/BD | 23/02/2024 | 30 | SUBHAJIT SAHA | 11.22 | 9.99 | 100 | 100
4240 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC , SM/14733 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Barasat-I Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-B | 1121./1/BSD | 09/02/2024 | 4 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
4241 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC , SM/14733 | Augmentation | Different works in connection with Augmentation Kashimpur PWSS (1st Tubewell site - Pump House). | 586/BSD | 10/09/2024 | 20 | K.C. ENTERPRISE | 3.53 | 0 | 0 | 100
4242 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC , SM/14733 | Augmentation | Different works in connection with Augmentation Kashimpur PWSS (1st Tubewell site - Boundary Wall & Service Road). | 1001/BSD | 02/01/2025 | 20 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 2.86 | 0 | 0 | 100
4243 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based Kashimpur PWSS to accommodate FHTC , SM/14733 | Augmentation | Continuation order for Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Barasat-I Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. | 1135/BSD | 12/02/2024 | 20 | BIBHAS PAL. | 0.71 | 0 | 0 | 100
4244 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Balibhara Piped Water Supply Scheme , SM/14498 | New | Survey, Design Drawing & DPR Preparation for NEW PWSS (BALIBHARA Water Supply Scheme) in BARRACKPUR-I BLOCK under N 24 Pgs W/S Div-I, PHE Dte. | 120/NWSD-I | 02/02/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 7.04 | 7.04 | 100 | 1
4245 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Balibhara Piped Water Supply Scheme , SM/14498 | New | Material Requisition To Resource Division | 448/NWSD-I | 26/04/2023 | 0 | Resource Division | 26.75 | 0 | 0 | 0
4246 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Balibhara Piped Water Supply Scheme , SM/14498 | New | Construction of Arsenic cum Iron removal Plants (AIRP) of capacity 70 cum/hr at Head work site of Balibhara Water Supply Scheme within the Barrackpore-I Block and other anciliary work under North 24 Pgs. W/S Division-I, P.H.E. Dte. | 488/NWSD-I | 15/03/2024 | 180 | PUSPA ENTERPRISE | 209.81 | 0 | 0 | 0
4247 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Balibhara Piped Water Supply Scheme , SM/14498 | New | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1430/NWSD-I | 18/09/2024 | 7 | BIBHAS PAL | 5.27 | 0.18 | 50 | 100
4248 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Balibhara Piped Water Supply Scheme , SM/14498 | New | Material Requisition To Resource Division | 27/NWSD-I | 04/01/2024 | 0 | Resource Division | 15.04 | 0 | 0 | 0
4249 | NORTH 24 PARGANAS | Electrical | Balibhara Piped Water Supply Scheme , SM/14498 | New | Quotation for Balibhara w/s scheme TW no.- I | 116 | 17/05/2024 | 0 | WBSEDCL | 4.33 | 0 | 0 | 0
4250 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Balibhara Piped Water Supply Scheme , SM/14498 | New | Laying of Distribution System, Rising Main including specials, valves and pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, Construction of 350 cum capacity 20 Mtr. staging height RCC Over Head Reservoir with pile foundation and pipe connection including cost of pipes & specials with soil investigation, Construction of Pump House (4.88m X 3.66m) including Sanitary Arrangement, Construction of Boundary Wall, Construction of Service Road, Improvement Of Land, Pipe carring structure for a span of 25 Meter for crossing of a Canal / River etc. for Augmentation of Ground Water Based Piped Water Supply Scheme for BALIBHARA in Barrackpur-I Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | 1620/NWSD-I | 12/10/2023 | 365 | A.K.C. SUPPLY & CONSTRUCTION | 535.19 | 131.65 | 24.6 | 48
4251 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Kaugachhi Zone-II Piped Water Supply Scheme , SM/14500 | New | Laying of Distribution System, Rising Main including specials, valves and pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir with pile foundation and pipe connection including cost of pipes & specials with soil investigation, Construction of Pump House (4.88m X 3.66m) including Sanitary Arrangement, Construction of Boundary Wall, Construction of Service Road, Improvement Of Land, Pipe carring structure for a span of 25 Meter for crossing of a Canal / River etc. for Augmentation of Ground Water Based Piped Water Supply Scheme for KAUGACHHI ZONE-II in Barrackpur-I Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | 1679/NWSD-I | 30/10/2023 | 365 | NOVELTY ENTERPRISE | 487.91 | 0 | 0 | 0
4252 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Kaugachhi Zone-II Piped Water Supply Scheme , SM/14500 | New | Survey, Design Drawing & DPR Preparation for NEW PWSS (KAUGACHHI ZONE-II Water Supply Scheme) in BARRACKPUR-I BLOCK under N 24 Pgs W/S Div-I, PHE Dte. | 122/NWSD-I | 02/02/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 6.49 | 6.49 | 100 | 1
4253 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Kaugachhi Zone-II Piped Water Supply Scheme , SM/14500 | New | Material Requisition To Resource Division | 452/NWSD-I | 26/04/2023 | 0 | Resource Division | 47 | 0 | 0 | 0
4254 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Kaugachhi Zone-II Piped Water Supply Scheme , SM/14500 | New | Shinking of 1 no. Tube well 300mm X 200mm Big Dia.Tube well 300 Mtr. Deep by Direct Rotary Rig method using PVC pipe & UPVC deep well screen pipes with ribs etc. Including cost of Materials for Kaugachi Zone-II Water Supply Scheme ( H/W site ) under North 24 Parganas wate supply Division-I, P.H.E. Dte. | 432/NWSD-I | 19/03/2025 | 30 | B.K. ENTERPRISE | 22.7 | 0 | 0 | 0
4255 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Bidyadharpur & its Adjoining Mouzas Piped Water Supply Scheme under North 24 Parganas W/S Division-I, PHE Dte. , SM/14501 | New | Survey, Design Drawing & DPR Preparation for NEW PWSS (BIDYADHARPUR & ITS ADJOINING MOUZAS Water Supply Scheme) in BARRACKPUR-I BLOCK under N 24 Pgs W/S Div-I, PHE Dte. | 49/NWSD-I | 11/01/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.91 | 0.91 | 100 | 1
4256 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Bidyadharpur & its Adjoining Mouzas Piped Water Supply Scheme under North 24 Parganas W/S Division-I, PHE Dte. , SM/14501 | New | Material Requisition To Resource Division | 449/NWSD-I | 26/04/2023 | 0 | Resource Division | 0.38 | 0 | 0 | 0
4257 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Bidyadharpur & its Adjoining Mouzas Piped Water Supply Scheme under North 24 Parganas W/S Division-I, PHE Dte. , SM/14501 | New | Laying of Distribution System including specials, valves and pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, Construction of Pump House (4.88m X 3.66m) including Sanitary Arrangement, Construction of Boundary Wall, Construction of Service Road, Improvement of Land, for Augmentation of Ground Water Based Piped Water Supply Scheme for Bidyadharpur & its Adjoining Mouzas in Barrackpur-I Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | 1594/NWSD-I | 10/10/2023 | 90 | DAS TRADING | 56.49 | 28.3 | 50.1 | 32
4258 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Bidyadharpur & its Adjoining Mouzas Piped Water Supply Scheme under North 24 Parganas W/S Division-I, PHE Dte. , SM/14501 | New | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | 1430/NWSD-I | 18/09/2024 | 7 | BIBHAS PAL | 5.27 | 0.18 | 50 | 100
4259 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Bidyadharpur & its Adjoining Mouzas Piped Water Supply Scheme under North 24 Parganas W/S Division-I, PHE Dte. , SM/14501 | New | Material Requisition To Resource Division | 50/NWSD-I | 08/01/2024 | 0 | Resource Division | 0.79 | 0 | 0 | 0
4260 | NORTH 24 PARGANAS | Electrical | Bidyadharpur & its Adjoining Mouzas Piped Water Supply Scheme under North 24 Parganas W/S Division-I, PHE Dte. , SM/14501 | New | Quotation for new service connection at Bidyadharpur W/S Scheme PH No 1 ( SM/14501 ) | 34 | 09/04/2024 | 0 | WBSEDCL | 0.79 | 0 | 0 | 0
4261 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Bidyadharpur & its Adjoining Mouzas Piped Water Supply Scheme under North 24 Parganas W/S Division-I, PHE Dte. , SM/14501 | New | Laying of pipeline & special measure for protection of road and other allied work at different location under Augmentation work at Bidyadharpur W/S Scheme under North 24 Parganas District within the jurisdiction of N24Pgs. W/S Division-I, P.H.E. Dte. | 189/NWSD-I | 31/01/2025 | 30 | DAS TRADING | 9.86 | 0 | 0 | 0
4262 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadpur Piped Water Supply Scheme at Habra-I Block (Phase-I) , SM/08781 | Retrofitting | Acceptance cum work order for Restoration of different diameter existing pipe lines by laying UPVC pipes and allied works of Sadpur W/S scheme due to up gradation of different roads within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | 2047//BD | 21/09/2021 | 30 | MONDAL ENTERPRISE. (BARASAT) | 26.59 | 11.14 | 100 | 100
4263 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadpur Piped Water Supply Scheme at Habra-I Block (Phase-I) , SM/08781 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SADPUR Water Supply Scheme at Habra - I Block within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. (Phase - I) | 2627/BD | 05/09/2022 | 660 | M/S SUKANTA ENTERPRISE. | 48.49 | 26.76 | 55.26 | 100
4264 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XV (Chak Chandpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15818 | Augmentation | Detail route survey, design of distribution network and preparation of estimate drawing & DPR for providing FHTC in the scheme of Zone-XV (Chak Chandpur) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | 258/NWSD-I | 10/03/2023 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.17 | 4.17 | 100 | 0
4265 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XV (Chak Chandpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15818 | Augmentation | Material Requisition To Resource Division | 461/NWSD-I | 26/04/2023 | 0 | Resource Division | 142.13 | 0 | 0 | 0
4266 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XV (Chak Chandpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15818 | Augmentation | Supply and installation of Sign Board (900mm X 600mm) determination of Land i.e." This land belongs to PHE. Dte. Govt. of West Bengal" under Surface Water based Pipe Water supply Scheme under North 24 Pgs. Water Supply Division-I, PHE. Dte. | 1432/NWSD-I | 18/09/2024 | 14 | S M TRADERS | 2.17 | 0 | 0 | 100
4267 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XV (Chak Chandpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15818 | Augmentation | Material Requisition To Resource Division | 1313/NWSD-I | 30/08/2024 | 0 | Resource Division | 26.67 | 0 | 0 | 0
4268 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XV (Chak Chandpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15818 | Augmentation | Shifting of HTOH Pole at Chak Chadpur scheme | 182/PFMS/24-25 | 03/09/2024 | 0 | WBSEDCL | 5.81 | 0 | 0 | 0
4269 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XV (Chak Chandpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15818 | Augmentation | New service connection at P.H.No - OHR , Zone - XV of Chak Chandpur water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N) | BP-161-24-25 | 14/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.65 | 0 | 0 | 0
4270 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XV (Chak Chandpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/15818 | Augmentation | Shinking of 1 no. Tube well 300mm X 200mm Big Dia.Tube well 300 Mtr. Deep by Direct Rotary Rig method using PVC pipe & UPVC deep well screen pipes with ribs etc. Including cost of Materials under command area of Chak Chandpur Water Supply Scheme at Deganga Block under North 24 Parganas wate supply Division-I, P.H.E. Dte. | 436/NWSD-I | 19/03/2025 | 30 | ACME CONSTRUCTION | 22.68 | 0 | 0 | 0
4271 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (MATBARI ABAD Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-A). | 348/HSD | 21/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.83 | 4.83 | 100 | 1
4272 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (MATBARI ABAD Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-B) | 349/HSD | 21/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 4.82 | 100 | 1
4273 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Material Requisition To Resource Division | 868/BD | 22/03/2023 | 0 | Resource Division | 23.84 | 0 | 0 | 0
4274 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile, Construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap within Mathbari Abad W/S Scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | 2704/BD | 04/09/2023 | 1094 | M/S DATTA ENTERPRISE. | 442.43 | 305.29 | 69 | 85
4275 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for Hiring of one no. DIESEL MOTOR CAB (BS-VI) on daily hire basis for use of the Assistant Engineer, HASNABAD SUB-DIVISION, PHE DTE. Period from 01.11.23 to 30.04.24 | 1315/HSD | 30/10/2023 | 183 | RANJIT KUMAR MANDAL | 0.86 | 2.26 | 261.65 | 0
4276 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection with Augmentation of Gabberia water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | ABDULALIMMONDAL | 09/01/2024 | 10 | ABDUL ALIM MONDAL. | 0.79 | 0 | 0 | 0
4277 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Mathbari Abad W/S scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 282/HSD | 06/03/2024 | 10 | M/S DATTA ENTERPRISE. | 0.84 | 0.83 | 100 | 22
4278 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for Supply and installation of 150 mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Mathbari Abad (Scheme code-SM/15825) water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 1171/HSD | 26/09/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.79 | 0 | 0 | 100
4279 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for Emergent resting of pipeline with UC Bullah pilling at different places at Boyermari within Mathbari Abad w/s scheme (Scheme code-SM/15825) w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1003/HSD | 29/08/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.99 | 0.99 | 100 | 100
4280 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for Supply and installation of 100mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within within Mathbari Abad (Scheme code-SM/15825) water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 996/HSD | 29/08/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.91 | 0 | 0 | 100
4281 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for Supply and installation of 200 mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Mathbari Abad (Scheme code-SM/15825) water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 1000/HSD | 29/08/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.79 | 0 | 0 | 100
4282 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for Emergent resting of pipeline with UC Bullah pilling at different places at Khas Sankardaha & Sankardaha Abad within Mathbari Abad w/s scheme (Scheme code-SM/15825), Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1006/HSD | 29/08/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.99 | 0.99 | 100 | 100
4283 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for Emergent restoration of road for damage portion at different places in connection with retrofitting of Boyermari within Mathbari Abad (Scheme code-SM/15825) w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 992/HSD | 29/08/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.9 | 0.9 | 100 | 100
4284 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for Emergent resting of pipeline with bamboo pilling at different places at Khas Sankardaha & Sankardaha Abad within Mathbari Abad (Scheme code-SM/15825) w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 998/HSD | 29/08/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.97 | 0.97 | 100 | 100
4285 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection with Augmentation of Gabberia water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 35/HSD. | 09/01/2024 | 10 | ABDUL ALIM MONDAL. | 0.79 | 0 | 0 | 100
4286 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation of Gabberia water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | 36/HSD | 09/01/2024 | 10 | ABDUL ALIM MONDAL. | 0.79 | 0 | 0 | 100
4287 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for Supply and installation of 250 mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Mathbari Abad (Scheme code-SM/15825) water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 1160/HSD | 25/09/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.83 | 0 | 0 | 100
4288 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for Emergent resting of pipeline with bamboo pilling at different places at Boyermari within Mathbari Abad (Scheme code-SM/15825) w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | 1178/HSD | 30/09/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.99 | 0 | 0 | 100
4289 | NORTH 24 PARGANAS | Eastern Mechanical | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Quotation for Service Connection Charges for PH- I under Mathbari Abad W/S Scheme in the district of North 24 Pgs. | BP-364-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.37 | 0 | 0 | 0
4290 | NORTH 24 PARGANAS | Eastern Mechanical | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Service connection charges at PH-II under Mathbari Abad W/S Scheme | BP-295-23-24 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.79 | 0 | 0 | 0
4291 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Formal work order for Additional Laying of UPVC distribution pipe line, protection works & other allied works within Mathbari Abad w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 2796/BD | 25/09/2024 | 90 | M/S PROGATI ENTERPRISE. | 140.81 | 19.02 | 13.51 | 70
4292 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for Construction of anchor block for resting of 250/200 mm dia DI distribution main pipeline over existing concrete wall beside Basanti Highway at different places for Mathbari Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 2348/BD | 08/07/2025 | 60 | M/S DATTA ENTERPRISE. | 6.1 | 0 | 0 | 0
4293 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Mathbari Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 2899/BD | 03/10/2024 | 30 | M/S DATTA ENTERPRISE. | 25.25 | 14.92 | 45.11 | 100
4294 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for Construction of RCC culvert, cut-off wall, appron wing wall, approach road and other allied works at N/H/O Aazimuddin Molla within Mathbari Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 92/BD | 08/01/2025 | 45 | M/S DATTA ENTERPRISE. | 11.7 | 0 | 0 | 100
4295 | NORTH 24 PARGANAS | Barasat Division | Matbari Abad Piped Water Supply Scheme , SM/15825 | New | Acceptance cum work order for Temporary approach road for movement of rig machine and other allied machineries at PH No-2 within Mathbari Abad w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 938/HSD | 29/05/2025 | 10 | M/S DATTA ENTERPRISE. | 0.95 | 0 | 0 | 100
4296 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (ATPUKUR Z-I Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | 239/HSD | 02/02/2022 | 15 | UMWELT ENGINEER PVT.LTD. | 4.83 | 4.83 | 100 | 0
4297 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (ATPUKUR Z-I Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | 240/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.6 | 3.6 | 100 | 0
4298 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Material Requisition To Resource Division | 875/BD | 22/03/2023 | 0 | Resource Division | 28.4 | 0 | 0 | 0
4299 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-I). | 277/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
4300 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-J). | 278/HSD | 06/03/2024 | 10 | M.R.CONSTRUCTION. | 0.88 | 0 | 0 | 100
4301 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-C). | 283/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
4302 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-G). | 289/HSD | 06/03/2024 | 10 | S.M.TRADERS. | 0.87 | 0 | 0 | 100
4303 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-D). | 263/HSD | 06/03/2024 | 10 | S.M.TRADERS. | 0.88 | 0.88 | 100 | 100
4304 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-E). | 265-HSD. | 06/03/2024 | 10 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
4305 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-F). | 267/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
4306 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-B). | 258/HSD | 06/03/2024 | 10 | M.R.CONSTRUCTION. | 0.88 | 0.88 | 100 | 100
4307 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-G). | 270/HSD | 06/03/2024 | 10 | M.R.CONSTRUCTION. | 0.88 | 0.88 | 100 | 100
4308 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-A). | 256/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
4309 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-F). | 287/HSD | 06/03/2024 | 10 | M.R.CONSTRUCTION. | 0.88 | 0 | 0 | 100
4310 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-I). | 291/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.87 | 0 | 0 | 100
4311 | NORTH 24 PARGANAS | Eastern Mechanical | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Quotation for Service Connection Charges for PH- II, Zone- I under Atpukur W/S Scheme in the district of North 24 Pgs. | BP-365-23-24 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.6 | 0 | 0 | 0
4312 | NORTH 24 PARGANAS | Eastern Mechanical | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Service connection charges at PH-I under Atpukur W/S Scheme | BP-293-23-24 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 24.93 | 0 | 0 | 0
4313 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Atpukur W/S Scheme (Zone-I), Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | 2616/BD | 29/08/2023 | 1096 | M/S PROGATI ENTERPRISE. | 461.22 | 166.52 | 36.1 | 37
4314 | NORTH 24 PARGANAS | Barasat Division | Atpukur Zone-I Piped Water Supply Scheme , SM/15828 | New | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for within Atpukur (Z-I) and Uchildaha w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | 633/BD | 28/02/2025 | 45 | SHIBU BISWAS. | 51.76 | 0 | 0 | 0
4315 | NORTH 24 PARGANAS | Barasat Division | Petua Dhanihati Piped Water Supply Scheme , SM/15830 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (PETUA DHANIHATI Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-A) | 350/HSD | 21/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 1
4316 | NORTH 24 PARGANAS | Barasat Division | Petua Dhanihati Piped Water Supply Scheme , SM/15830 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (PETUA DHANIHATI Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-B) | 351/HSD | 21/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.51 | 4.51 | 100 | 1
4317 | NORTH 24 PARGANAS | Barasat Division | Petua Dhanihati Piped Water Supply Scheme , SM/15830 | New | Material Requisition To Resource Division | 879/BD | 22/03/2023 | 0 | Resource Division | 23.37 | 0 | 0 | 0
4318 | NORTH 24 PARGANAS | Barasat Division | Petua Dhanihati Piped Water Supply Scheme , SM/15830 | New | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Petua Dhanihati W/S scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | 1004/HSd | 29/08/2024 | 10 | S.K.ENTERPRISE. | 0.9 | 0 | 0 | 100
4319 | NORTH 24 PARGANAS | Eastern Mechanical | Petua Dhanihati Piped Water Supply Scheme , SM/15830 | New | Service connection charges at PH-I under Petuadhanihati W/S Scheme | BP-292-23-24 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.12 | 0 | 0 | 0
4320 | NORTH 24 PARGANAS | Barasat Division | Petua Dhanihati Piped Water Supply Scheme , SM/15830 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Petua Dhanihati W/S Scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | 2705/BD | 04/09/2023 | 1096 | M/S NIRMAN CONSTRUCTION. | 379.24 | 219.83 | 57.97 | 70
4321 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Fakirtakia Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) , SM/08765 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in Fakirtakia mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Fakirtakia w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. (Phase-I) | 180/BD | 20/01/2022 | 45 | R.K.MANDAL AND CO. | 74.88 | 74.79 | 100 | 1
4322 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Fakirtakia Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) , SM/08765 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia. UPVC distribution pipeline for providing FHTC by UC bullah pile at different places within Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. (Part-B) | 472/HSD | 10/03/2022 | 10 | M/S MITRA CONSTRUCTION. | 3.89 | 3.89 | 50 | 1
4323 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Fakirtakia Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) , SM/08765 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia. UPVC distribution pipeline for providing FHTC by UC bullah pile at different places within Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. (Part-A) | 471/HSD | 10/03/2022 | 10 | JESMINE ENTERPRISE. | 3.82 | 3.82 | 50 | 1
4324 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Fakirtakia Piped Water Supply Scheme, Sandeshkhali-I Block (Phase-I) , SM/08765 | Retrofitting | Material Requisition To Resource Division | 1821/BD | 19/06/2023 | 0 | Resource Division | 16.88 | 0 | 0 | 0
4325 | NORTH 24 PARGANAS | Eastern Mechanical | Solarizations of WBSEDCL Energized Electrical Installation including Net Metering at Different Piped Water Supply Schemes at Hasnabad Block in NORTH 24 PARGANAS District under Eastern Mechanical Division PHE Dte. , SM/15763 | Solarisation | Solarisation of WBSEDCL Energised Electrical installation including net metering at different Pipe Water Supply Scheme at Hasnabad Block in North 24 Parganas District under E.M.D. P.H.E. Dte. | 6408/EMD | 31/10/2023 | 182 | BINGAS ELECTRICAL ELECTRONICS & SOLAR SYSTEM | 258.41 | 0 | 0 | 0
4326 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GHONA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08648 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Ghona Water Supply Scheme at Basirhat-II Block under Barasat Division, PHE Dte.(Phase-I). | 1653/BD | 07/09/2021 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 57.32 | 55.48 | 96.78 | 1
4327 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GHONA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08648 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Kumarjole Water Supply Scheme under Barasat Division, PHE Dte. | 2171/HSD | 28/12/2021 | 21 | UMWELT ENGINEER PVT.LTD. | 4.24 | 0 | 0 | 1
4328 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GHONA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08648 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Kumarjole Water Supply Scheme under Barasat Division, PHE Dte. | 2171/HSD | 28/12/2021 | 21 | UMWELT ENGINEER PVT.LTD. | 4.24 | 4.24 | 100 | 1
4329 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM and Jal SWAPNA) under command area of GHONA W/S Scheme at Basirhat II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase-I). , SM/08648 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for GHONA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | 309/BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.15 | 3.15 | 100 | 1
4330 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18262 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Zone-VIII (Chyangdana) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | 891/NWSD-I | 12/07/2023 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.76 | 3.76 | 100 | 100
4331 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18262 | Augmentation | Material Requisition To Resource Division | 1835/NWSD-I | 10/11/2023 | 0 | Resource Division | 55.11 | 0 | 0 | 0
4332 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18262 | Augmentation | Supply and installation of Sign Board (900mm X 600mm) determination of Land i.e." This land belongs to PHE. Dte. Govt. of West Bengal" under Surface Water based Pipe Water supply Scheme under North 24 Pgs. Water Supply Division-I, PHE. Dte. | 1432/NWSD-I | 18/09/2024 | 14 | S M TRADERS | 2.17 | 0 | 0 | 100
4333 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18262 | Augmentation | Material Requisition To Resource Division | 39/NWSD-I | 05/01/2024 | 0 | Resource Division | 16.58 | 0 | 0 | 0
4334 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18262 | Augmentation | New service connection at Chyangdana P.H.No-I Zone- VIII water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). | BP-337-23-24 | 11/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.4 | 0 | 0 | 0
4335 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/18262 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure, Proposed Rising Main System, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction of 500 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation (600 mm dia, 22 mtrs. deep and one pile cap adjoning 3 nos of piles) , pipe connection and cost of pipes, specials., Soil Investigation for the work of construction of OHR with staging height 20 mtr, Construction Of Pump House (4.88m X 3.66m) Including Sanitary Arrangement, Boundary Wall, Service Road for 60 M length, Improvement Of Land for Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of Zone-VIII CHYANGDANA in Deganga Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | 1675/NWSD-I | 30/10/2023 | 884 | SINGHA ROY AND CO | 676.75 | 18.36 | 2.71 | 10
4336 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Preparation of Augmentation DPR for Puturia Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | 1953/B.Ar.D | 26/09/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0.99 | 100 | 1
4337 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Hiring of Contract carriage (BS-IV) of the office use of the DSE PIU N24PGS WBDWSIP PHE DTE. | 1402//B.Ar.D | 29/07/2022 | 184 | BISWADIP SIKDAR | 0.87 | 0.4 | 45.43 | 1
4338 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | construction order No - Horing of one (1) No Diseal Operated Motor Cab ( Car No -WB-25K-2915) with driver for offical use for Assistent Engineer (HQ-I) ,Barasat Arsenic Divisuion ,PHE Dte with all costs towards the owner except fuel cost i.e Diesel & Mobil oil for the period from 01.05.2022 to 30.04.2023 | 796//B.Ar.D | 26/04/2022 | 365 | PREMANANDA ROY BISWAS | 1.73 | 0 | 0 | 100
4339 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Submission of all documents regarding crossing of Railway track for laying Water Pipe line main for Puturia W/S Scheme in between Sondalia & Beliaghata Road Railway Station on Barasat - Hasnabad Section under Barasat-II Block. | 747/B.Ar.D. | 24/03/2023 | 15 | P & S ASSOCIATES | 1.96 | 1.96 | 100 | 0
4340 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (AC) (Car No. WB-25F-6815) with driver for official use for Chief Engineer (Head Quarters) in place of Director,WSSO, PHE Department. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 22.08.2022 to 21.02.2023." | 1520/B.Ar.D | 18/08/2022 | 184 | NASIRUDDIN BISWAS | 0.96 | 0.79 | 100 | 1
4341 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Hiring charges of vehicle. | 3812/EC | 30/12/2021 | 365 | PRABIR RONG | 1.73 | 0 | 0 | 1
4342 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | CONTINUATION ORDER for ''Hiring of one (1) no Diesel operated Motor cab 9Non AC) Car No WB-11C 8013) with driver for offical use for Chief Engineer & Director ,WSSO. PHE Department with all costs towards the owner excpet fuel cost i.e. Diesel & Mobil oil for the period from 22.08.2022 to 21.02.2023.'' | 1521 //B.Ar.D | 18/08/2022 | 184 | GOUR HARI SAHOO | 0.86 | 1.11 | 100 | 1
4343 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Continuation order for -Hiring of One (1) no Diesel operated cab (Car no-WB-25K-2915) with driver for offical use for Assistent Engineer (HQ-II) Barasat Arsenic Division PHE Dte with all cost towards the owner except fuel cost i.e Diesel & Mobil oil for the period from 01.05.2022 to 30.04.2023 | 796/ B.Ar.D | 26/04/2022 | 365 | PREMANANDA ROY BISWAS | 1.73 | 3.06 | 100 | 1
4344 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Eucalyptus Bullah piling for Protection of UPVC distribution pipe line at Bokanda Ghosh Para of Puturia W/S Scheme under Barasat- II Block under Barasat Arsenic Division, P.H.E. Dte. | 472/B.Ar.D. | 27/02/2023 | 30 | KAKALI ENTERPRISE | 10.72 | 10.7 | 100 | 100
4345 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Submission of all documents regarding crossing of Railway track for laying Water Pipe line main for Surface Based PWSS for Barasat-II Block in between Sondalia & Beliaghata Road Railway Station on Barasat - Hasnabad Section. | 748/B.Ar.D. | 24/03/2023 | 15 | P & S ASSOCIATES | 1.96 | 1.96 | 100 | 100
4346 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir & other existing civil component of Capacity 700 Cu.m. at Puturia W/S Scheme uder Barasat-II Block under Barasat Arsenic Division, PHE Dte. | 948/B.Ar.D. | 17/04/2023 | 60 | MONDAL ENTERPRISE | 16.73 | 14.13 | 100 | 100
4347 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Material Requisition To Resource Division | 26/B.Ar.D. | 05/01/2023 | 0 | Resource Division | 14.73 | 0 | 0 | 0
4348 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Material Requisition To Resource Division | 204/B.Ar.D. | 30/01/2023 | 0 | Resource Division | 258.81 | 0 | 0 | 0
4349 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Wayleave facility charges Sondalia to Beliaghata Road Halt | 236 | 16/08/2023 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS) | 5.95 | 0 | 0 | 0
4350 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Wayleave plan & survey charges (Stn.Sondalia to Beliaghata Road Halt) | 181 | 24/07/2023 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS) | 0.07 | 0 | 0 | 0
4351 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Puturia under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 1743/B.Ar.D. | 07/09/2022 | 90 | S. P. CONSTRUCTION | 382.09 | 292.34 | 100 | 100
4352 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Mochpol mouza for Augmentation of Ground Based Water Supply Scheme at Puturia under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 394/B.Ar.D | 21/02/2024 | 280 | THREE MAA ENTERPRISE | 46.15 | 19.53 | 29.81 | 100
4353 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Sinking for 1 nos 250 mm. x 150 mm. dia. 270 mtr deep Tubewell by D.R. Rig method with UPVC pipe & strainer having 250 mm dia 42 mtr. long housing pipe & 150 mm dia 30 mtr. long filter at Puturia W/S Scheme of Barasat-II block under Barasat Arsenic Division, P.H.E. Dte. | 997/B.Ar.D. | 19/06/2024 | 107 | B. S. ENTERPRISE | 13.46 | 11.79 | 100 | 100
4354 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Payment of quotation amount for new service connection at P/H No: IV under Puturia water supply scheme , Block: Barasat-II. | BP-162-24-25 | 14/11/2024 | 0 | W.B.S.E.D.C.L (KADAMBAGACHI C.C.C) | 2.73 | 0 | 0 | 0
4355 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Construction of 4.88 mtr. x 3.6 mtr. size new Pump House (Pump House-IV) with Boundary Wall and Allied Works for PUTURIA W/S Scheme Under Barasat Arsenic Division, PHE Dte. (SM/10551) | 329/B.Ar.D. | 27/02/2025 | 60 | GRAVITA ENTERPRISE | 9.11 | 0 | 0 | 100
4356 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for within leftout area of Falti and Bamandanga area for the scheme 'Augmentation of Ground Based Water Supply Scheme at Puturia under Barasat - II Block under Barasat Arsenic Division, PHE Dte'. (SM/10551) | 796/B.Ar.D. | 30/04/2025 | 180 | TOJO ENTERPRISE | 41.81 | 0 | 0 | 100
4357 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for restoration of Damaged Pipeline and house connection due to construction and widening of village Roads under Pathashree-3 from North 24 Parganas Zilla Parishad and other within command area of Bokanda, Puturia, Baidyapur and Tona for Augmentation of Ground Based Water Supply Scheme at Puturia under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 1582/B.Ar.D. | 23/09/2024 | 270 | M/S RAJPATH CONSTRUCTION | 22.02 | 0 | 0 | 90
4358 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Falti Beliaghata and Tona area for Augmentation of Ground Based Water Supply Scheme at Puturia under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 537/B.Ar.D. | 13/03/2024 | 280 | AYUSH ENTERPRISE | 49.47 | 12.87 | 20.94 | 5
4359 | NORTH 24 PARGANAS | Barasat Arsenic Division | Augmentation of Ground Water Based Pipes Water Supply Scheme for PUTURIA to Accommodate FHTC in Barasat-II Block of North 24 Parganas District under Barasat Arsenic Division, PHE Dte. , SM/10551 | Augmentation | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Tona area for Augmentation of Ground Based Water Supply Scheme at Puturia under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | 996/B.Ar.D. | 19/06/2024 | 320 | M/S CHANDIMATA CONSTRUCTION | 28.44 | 0 | 0 | 95
4360 | NORTH 24 PARGANAS | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme , SM/18617 | New | Route Survey, Design Drawing & Preparation of DPR for Kalupur Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | 122/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.8 | 0 | 0 | 1
4361 | NORTH 24 PARGANAS | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme , SM/18617 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (DAKSHIN AKHRATALA Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-A) | 314/HSD | 15/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 100
4362 | NORTH 24 PARGANAS | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme , SM/18617 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (DAKSHIN AKHRATALA Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-B) | 315/HSD | 15/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 4.82 | 100 | 100
4363 | NORTH 24 PARGANAS | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme , SM/18617 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (DAKSHIN AKHRATALA Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-C) | 336/HSD | 21/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100 | 100
4364 | NORTH 24 PARGANAS | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme , SM/18617 | New | Material Requisition To Resource Division | 872/BD | 22/03/2023 | 0 | Resource Division | 296.35 | 0 | 0 | 0
4365 | NORTH 24 PARGANAS | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme , SM/18617 | New | Material Requisition To Resource Division | 3442/BD | 06/12/2024 | 0 | Resource Division | 38.05 | 0 | 0 | 0
4366 | NORTH 24 PARGANAS | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme , SM/18617 | New | Formal work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2,3,4 (Size-3.60x3.00 mtr),Laying of DI rising main and DI/UPVC distribution pipe line,Providing Functional Household Tap Connection,Protection works for different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile at different places,Construction of 450 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Dakshin Akhratala water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | 4047/BD | 13/10/2023 | 1091 | M/S DATTA ENTERPRISE. | 753.32 | 382.2 | 50.74 | 80
4367 | NORTH 24 PARGANAS | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme , SM/18617 | New | Acceptance cum work order for sinking of Additional 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tube well by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Dakshin Akhratala w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 3376/BD | 02/12/2024 | 60 | M/S K.P.PAL. | 25.88 | 0 | 0 | 0
4368 | NORTH 24 PARGANAS | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme , SM/18617 | New | Acceptance cum work order for Additional Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection for Dakshin Akhratala w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 144/BD | 13/01/2025 | 75 | JESMINE ENTERPRISE. | 10.58 | 0 | 0 | 0
4369 | NORTH 24 PARGANAS | Eastern Mechanical | Dakshin Akhratala Piped Water Supply Scheme , SM/18617 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at P.H. No.-I, II, III IV (New) under Dakshin Akhratala W/S scheme under Block_ Sandeshkhali-I Dist. - 24Pgs(N) under EMD, PHE Dte. [SM/18617] | 1131/EMD | 04/06/2025 | 90 | ESENCE ENGINEERING CONCERN | 57.63 | 0 | 0 | 90
4370 | NORTH 24 PARGANAS | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme , SM/18617 | New | Formal work order for Sinking of 4 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1,2,3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Dakshin Akhratala w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | 3306/BD | 26/11/2024 | 90 | UTPAL CONSTRUCTION & CO. | 103.47 | 21.84 | 20.94 | 100
4371 | NORTH 24 PARGANAS | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme , SM/18617 | New | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at OHR site within Dakshin Akhratala w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | 996/HSD | 04/06/2025 | 10 | M/S DATTA ENTERPRISE. | 0.95 | 0 | 0 | 100
4372 | NORTH 24 PARGANAS | Barasat Division | Dakshin Akhratala Piped Water Supply Scheme , SM/18617 | New | Acceptance cum work order for Digitalisation of pipeline alignment, elevation survey and asset evaluation of under Nazat, Dakshin Akhratala mouza under Dakshin Akhratala W/S Scheme, Sandeshkhali-I block under Hasnabad Sub-Division. PHE Dte. | 578/HSD | 17/03/2025 | 10 | MERCHANDISE-INDIA | 2.11 | 0 | 0 | 100
4373 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Banglani to accommodate FHTC , SM/18618 | Augmentation | Additional Survey work for DPR Preparation for BANGLANI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 457 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.07 | 1.07 | 100 | 100
4374 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Banglani to accommodate FHTC , SM/18618 | Augmentation | Route Survey, Design Drawing & DPR Preparation for BANGLANI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | 456/BHT | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 4.95 | 100 | 100
4375 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Banglani to accommodate FHTC , SM/18618 | Augmentation | Material Requisition To Resource Division | 1238/BD | 25/04/2023 | 0 | Resource Division | 146.14 | 0 | 0 | 0
4376 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Banglani to accommodate FHTC , SM/18618 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection) for Augmentation of Banglani Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E. Dte. | 2518/BD | 22/08/2023 | 676 | KINGS & CO. | 606.14 | 433.25 | 71.48 | 59
4377 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) , SM/10552 | Retrofitting | Construction of boundary wall within brick structure & approach road at O.H.R. site within Sultanpur Water Supply Scheme. | 548/BD. | 23/02/2022 | 30 | MONDAL & CO. (BASIRHAT). | 14.69 | 14.69 | 100 | 1
4378 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) , SM/10552 | Retrofitting | Acceptance cum work order for Protection works for rising main of 150mm dia. DI pipe line at pond of Muyajjem Husien Molla within Sultanpur w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | 1143/HSD | 12/07/2022 | 10 | MONDAL & CO. (BASIRHAT). | 4.69 | 4.65 | 39.29 | 1
4379 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) , SM/10552 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by withdrawing & relaying of different dia. UPVC pipe line at different places of Turia mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | 603/HSD | 31/03/2022 | 15 | ANKUSH CONSTRUCTION & CO. | 4.78 | 4.61 | 100 | 1
4380 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) , SM/10552 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by laying of 90 mm dia. UPVC pipe line at different places of Patkelpota abad mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | 599/HSD | 31/03/2022 | 15 | ANKUSH CONSTRUCTION & CO. | 4.56 | 4.45 | 100 | 1
4381 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) , SM/10552 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by laying of 90 mm dia. UPVC pipe line at different places of Turia Mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | 587/HSD | 28/03/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.57 | 4.12 | 100 | 1
4382 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) , SM/10552 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places of Patkelpota mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | 601/HSD | 31/03/2022 | 15 | TRISHA ENTERPRISE & CO. | 4.53 | 4.29 | 100 | 1
4383 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) , SM/10552 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by laying of 90 mm dia. UPVC pipe line at different places of Patkelpota Mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | 579/HSD | 28/03/2022 | 15 | ANKUSH CONSTRUCTION & CO. | 4.55 | 4.13 | 100 | 1
4384 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) , SM/10552 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by withdrawing & relaying of 90mm dia. UPVC pipe line at different places of Joykrishnapur mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | 593/HSD | 29/03/2022 | 15 | ANKUSH CONSTRUCTION & CO. | 4.86 | 4.53 | 100 | 1
4385 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) , SM/10552 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by withdrawing & relaying of different dia. UPVC pipe line at different places of Turia mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | 595/HSD | 31/03/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.81 | 4.15 | 100 | 1
4386 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) , SM/10552 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by laying of 90 mm dia. UPVC pipe line at different places of Joykrishnapur Mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | 589/HSD | 28/03/2022 | 15 | ANKUSH CONSTRUCTION & CO. | 4.53 | 4.04 | 100 | 1
4387 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) , SM/10552 | Retrofitting | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places of Patkelpota abad mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | 591/HSD | 29/03/2022 | 15 | TRISHA ENTERPRISE & CO. | 4.51 | 4.24 | 100 | 1
4388 | NORTH 24 PARGANAS | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Sultanpur W/S Scheme, Minakhan Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase II & Final) , SM/10552 | Retrofitting | Material Requisition To Resource Division | 1816/BD | 19/06/2023 | 0 | Resource Division | 40.04 | 0 | 0 | 0
4389 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC , SM/12126 | Augmentation | Acceptance cum work order for Laying of 50 mm dia. UPVC pipe line for providing 3 nos. tap connection at near Sulkuni Abad area within Bhabanipur W/S Scheme, Hasnabad block under Hasnasbad Sub-Division, P.H.E.Dte. | 792/HSD | 13/07/2023 | 7 | M/S K.B.ENTERPRISE. | 0.86 | 0 | 0 | 0
4390 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC , SM/12126 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Zone-II) (Rep.) under Bhawanipur W/S Scheme District of 24 Pgs. (N) | 4754/EMD | 07/08/2023 | 30 | A.G ENTERPRISE. | 41.41 | 0 | 0 | 0
4391 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC , SM/12126 | Augmentation | Material Requisition To Resource Division | 911/BD | 22/03/2023 | 0 | Resource Division | 348.37 | 0 | 0 | 0
4392 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC , SM/12126 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, construction of 400cum capacity 20mtr staging height R.C.C Over head Reservoir as per Dept. design, drawing & specification including bored pile with pile cap and providing Functional Household Tap connection in connection with Augmentation of Bhabanipur Water Supply Scheme(Zone-I), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division PHE Dte. | 2651/BD | 01/09/2023 | 366 | SUPRITI ENTERPRISE. | 867.51 | 216.3 | 24.93 | 45
4393 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC , SM/12126 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bhabanipur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 931/BD | 15/03/2024 | 45 | AAHAN CONSTRUCTION | 59.17 | 0 | 0 | 0
4394 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC , SM/12126 | Augmentation | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tube well by D.R. Rig method at PH No.-1, 2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bhabanipur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 916/BD | 15/03/2024 | 60 | M/S K.P.PAL. | 89.28 | 59.32 | 100 | 100
4395 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC , SM/12126 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) (New) under Bhawanipur W/S Scheme District of 24 Pgs. (N) | 4753/EMD | 07/08/2023 | 30 | RMD TRADING | 27.98 | 0 | 0 | 70
4396 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC , SM/12126 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Construction of 600 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and providing Functional Household Tap Connection in connection with Augmentaion of Bhabanipur water supply scheme (Zone-II), Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | 2600/BD | 28/08/2023 | 579 | M/S S.S.ENTERPRISE. (SOUTH) | 956.1 | 499.7 | 52.26 | 70
4397 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC , SM/12126 | Augmentation | Acceptance cum work order for Land development at Pump House No-1 in connection with augmentation of Bhabanipur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 842/HSD | 15/05/2025 | 10 | MD.SALIM GAZI. | 1.49 | 0 | 0 | 0
4398 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC , SM/12126 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 (Size-3.60x3.00 mtr.) for Augmentation of Bhabanipur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | 1516/BD | 13/05/2025 | 90 | M/S MONDAL CONSTRUCTION | 17.62 | 0 | 0 | 0
4399 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC , SM/12126 | Augmentation | Acceptance cum work order for Emergent Construction of stand post & construction of platforms at Bhurkunda & Bedemari mouza in connection within Bhabanipur w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 535/HSD | 10/03/2025 | 10 | M/S K.B.ENTERPRISE. | 0.97 | 0 | 0 | 100
4400 | NORTH 24 PARGANAS | Barasat Division | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC , SM/12126 | Augmentation | Acceptance cum work order for Withdrawing and relaying of 90mm dia. UPVC pipe line at Bedemari mouza in connection with augmentation of Bhabanipur W/S scheme (Z-II), Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | 951/HSD | 29/05/2025 | 10 | M/S K.B.ENTERPRISE. | 0.94 | 0 | 0 | 100
4401 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IV (Chakla) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12383 | Augmentation | Detail route survey, design of distribution network and preparation of estimate drawing & DPR for providing FHTC in the scheme of Zone-IV (Chakla) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | 1061/NWSD-I | 05/09/2022 | 14 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.86 | 3.85 | 100 | 0
4402 | NORTH 24 PARGANAS | Central Drilling | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IV (Chakla) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12383 | Augmentation | Hiring of diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Superintending Engineer, M/E, PMU WBDWSIP under CMSD-II(D), CDD, P.H.Engineering Dte. | 41/CMSD-II | 16/02/2023 | 184 | SIDDHARTHA CHATTERJEE | 0.9 | 1.48 | 100 | 100
4403 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IV (Chakla) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12383 | Augmentation | Material Requisition To Resource Division | 462/NWSD-I | 26/04/2023 | 0 | Resource Division | 51.56 | 0 | 0 | 0
4404 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IV (Chakla) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12383 | Augmentation | Material Requisition To Resource Division | 1258/NWSD-I | 21/08/2023 | 0 | Resource Division | 17.45 | 0 | 0 | 0
4405 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IV (Chakla) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12383 | Augmentation | Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works from existing & new proposed distribution system within command area of Zone-IV (Chakla) in Deganga Block of North 24 Pgs. district under North 24 Parganas Water Supply Division-I, PHE. Dte. | 1312/NWSD-I | 14/11/2022 | 90 | BANI ENGINEERING CO. | 127 | 80.85 | 63.66 | 24
4406 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IV (Chakla) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12383 | Augmentation | Supply and installation of Sign Board (900mm X 600mm) determination of Land i.e." This land belongs to PHE. Dte. Govt. of West Bengal" under Surface Water based Pipe Water supply Scheme under North 24 Pgs. Water Supply Division-I, PHE. Dte. | 1432/NWSD-I | 18/09/2024 | 14 | S M TRADERS | 2.17 | 0 | 0 | 100
4407 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IV (Chakla) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12383 | Augmentation | Additional quotation for New service connection at P.H.No- I of Chakla water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N) | BP-385-23-24 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.31 | 0 | 0 | 0
4408 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IV (Chakla) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12383 | Augmentation | New service connection at P.H.No- I of Chakla water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). | BP-323-23-24 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.62 | 0 | 0 | 0
4409 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IV (Chakla) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. , SM/12383 | Augmentation | Providing FHTC, Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of Zone- IV (Chakla) in Deganga Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | 1298/NWSD-I | 24/08/2023 | 366 | SUPRITI ENTERPRISE | 511.44 | 102.7 | 20.08 | 25
4410 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC , SM/10570 | Augmentation | Repairing & renovation of Pump House No. 1 & 2 of Khosdelpur& adj. mouzas W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 513/HAB | 10/12/2021 | 30 | M/S SUKANTA ENTERPRISE. | 1.56 | 1.5 | 100 | 1
4411 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC , SM/10570 | Augmentation | Material Requisition To Resource Division | 3798/BD | 22/12/2022 | 0 | Resource Division | 9.95 | 0 | 0 | 0
4412 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC , SM/10570 | Augmentation | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Kosdelpur & Adj. Mouzas Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 2200/BD | 26/07/2022 | 90 | H.I.ENTERPRISE. | 333.61 | 333.61 | 100 | 1
4413 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC , SM/10570 | Augmentation | Material Requisition To Resource Division | 3105/BD | 18/10/2022 | 0 | Resource Division | 0.02 | 0 | 0 | 0
4414 | NORTH 24 PARGANAS | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC , SM/10570 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Bira-Rajibpur W/S Scheme, Khasdelpur W/S Scheme and Kumarjole W/S Scheme with Pump House No-I under Sadpur W/S Scheme District of 24 Pgs. (N) | 4490/EMD | 14/07/2023 | 537 | EASTERN INDIA SALES & SERVICE | 74.22 | 6.82 | 32.15 | 90
4415 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC , SM/10570 | Augmentation | Construction of Service Road (30 Mtr. Length X 2 Mtr. Width) for Pump House No:1 of khosdelpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 696/HAB | 25/07/2024 | 10 | M/S GUHA CONSTRUCTION. | 1.83 | 0 | 0 | 0
4416 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC , SM/10570 | Augmentation | Construction of Boundary Wall 30 m Length for Pump House No - 2 of Khosdelpur water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction Habra Sub-Division under Barasat Division P.H.E.Dte. | 912/HAB | 30/10/2024 | 40 | M/S SUKANTA ENTERPRISE. | 4.83 | 0 | 0 | 0
4417 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC , SM/10570 | Augmentation | Acceptance cum work order for Construction of Service Road (15 Mtr. Length X 2 Mtr. Width) for Pump House No:2 of Khosdelpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 170/HAB | 19/02/2024 | 15 | M/S SUKANTA ENTERPRISE. | 0.92 | 0 | 0 | 0
4418 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC , SM/10570 | Augmentation | Special repair and renovation of pump house and other Allied Works for Pump House No - 2 of Khosdelpur and Adj. Mouzas W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 915/HAB | 30/10/2024 | 20 | M/S SUKANTA ENTERPRISE. | 2.6 | 0 | 0 | 0
4419 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC , SM/10570 | Augmentation | Special repair & renovation of pump house and other Allied Works for Pump House No - 1 of Khosdelpur & Adj. Mouzas W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 925/HAB | 05/11/2024 | 20 | M/S SUKANTA ENTERPRISE. | 2.66 | 0 | 0 | 0
4420 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC , SM/10570 | Augmentation | Acceptance cum work order for Repairing of Boundary Wall for PH-1 of Khasdelpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | 3063/BD | 25/10/2024 | 30 | ANJALI CONSTRUCTION. | 5.08 | 0 | 0 | 0
4421 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC , SM/10570 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 for Augmentation of Khosdelpur & Adjoining Mouzas water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | 2774/BD | 11/09/2023 | 60 | ANJALI ENTERPRISE. | 28.99 | 12.33 | 100 | 80
4422 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC , SM/10570 | Augmentation | Improvement of Iron Elimination Plant at Khosdelpur & adj. Mouzas W/S Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | 688/HAB | 01/11/2023 | 30 | M/S SUKANTA ENTERPRISE. | 3.51 | 3.44 | 100 | 100
4423 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC , SM/10570 | Augmentation | Restoration of existing pipeline along the NH 35 due to widening and strengthening of existing NH 35 near Guma Chowmatha at Khosdelpur water supply scheme within the jurisdiction of Habra Sub-Division under Barasat Division PHE Dte. | 74/HAB | 29/01/2025 | 15 | M/S SUKANTA ENTERPRISE. | 0.95 | 0 | 0 | 100
4424 | NORTH 24 PARGANAS | Barasat Division | Augmentation of Ground water based piped water supply scheme for Khasdelpur to accommodate FHTC , SM/10570 | Augmentation | Restoration of existing pipeline along the NH 35 due to widening and strengthening of existing NH 35 near Khosdelpur Bazar at khosdelpur water supply scheme within the jurisdiction of Habra Sub-Division under Barasat Division PHE Dte. | 75/HAB | 29/01/2025 | 15 | M/S SUKANTA ENTERPRISE. | 0.97 | 0 | 0 | 100
4425 | NORTH 24 PARGANAS | Barasat Arsenic Division | GHUNI Piped Water Supply Scheme , SM/18537 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at Head Work site of Ghuni Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1942/B.Ar.D. | 14/08/2023 | 45 | ACME CONSTRUCTION | 18.27 | 0 | 0 | 0
4426 | NORTH 24 PARGANAS | Barasat Arsenic Division | GHUNI Piped Water Supply Scheme , SM/18537 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 3rd Pump House site of Ghuni Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1944/B.Ar.D. | 14/08/2023 | 45 | PIYALI CONSTRUCTION AND GENERAL ORDER SUPPLIERS | 18.26 | 0 | 0 | 0
4427 | NORTH 24 PARGANAS | NTK Mechanical | GHUNI Piped Water Supply Scheme , SM/18537 | New | Supply & Installation of pumping machineries & other electro-mechanical accessories in Ghuni piped W/S scheme under New Town Kolkata Mechanical Division, P.H.E. Dte. | 2135/NTKMD | 11/08/2023 | 180 | GLACIER ENGINEERING CO. | 65.81 | 0 | 0 | 0
4428 | NORTH 24 PARGANAS | Barasat Arsenic Division | GHUNI Piped Water Supply Scheme , SM/18537 | New | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 2nd Pump House site of Ghuni Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1943/B.Ar.D. | 14/08/2023 | 45 | NAJMUL HOQUE | 18.26 | 0 | 0 | 0
4429 | NORTH 24 PARGANAS | Barasat Arsenic Division | GHUNI Piped Water Supply Scheme , SM/18537 | New | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 2nd Tube Well Site of GHUNI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1985/B.Ar.D. | 18/08/2023 | 60 | M.R.CONSTRUCTION | 6.18 | 0 | 0 | 0
4430 | NORTH 24 PARGANAS | Barasat Arsenic Division | GHUNI Piped Water Supply Scheme , SM/18537 | New | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 3rd Tube Well Site of GHUNI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1986/B.Ar.D. | 18/08/2023 | 60 | JUPITER CONSTRUCTION | 6.2 | 0 | 0 | 0
4431 | NORTH 24 PARGANAS | Barasat Arsenic Division | GHUNI Piped Water Supply Scheme , SM/18537 | New | Construction of 4.88 mtr. x 3.60 mtr. size new Pump House at Head Work Site of GHUNI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. | 1984/B.Ar.D. | 18/08/2023 | 60 | SWAPNO ENTERPRISE | 7.02 | 0 | 0 | 0
4432 | NORTH 24 PARGANAS | Barasat Arsenic Division | GHUNI Piped Water Supply Scheme , SM/18537 | New | Ghuni Piped Water Supply Scheme with Rising Main, LDS, FHTC & construction of 900 cum capacity Overhead Reservoir (OHR) including Soil investigation and foundation design at Ghuni under Rajarhat block, Dist.- North 24 Parganas. | 2555/B.Ar.D. | 19/10/2023 | 366 | M/S. S. S. ENTERPRISE | 952.88 | 0 | 0 | 0
4433 | NORTH 24 PARGANAS | Barasat Arsenic Division | GHUNI Piped Water Supply Scheme , SM/18537 | New | Survey, Design Drawing & DPR Preparation for NEW PWSS (GHUNI Water Supply Scheme) in RAJARHAT BLOCK under Barasat Arsenic Division, PHE Dte. | 1809/B.Ar.D. | 31/07/2023 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 12.92 | 12.92 | 100 | 100
4434 | NORTH 24 PARGANAS | Barasat Arsenic Division | GHUNI Piped Water Supply Scheme , SM/18537 | New | Material Requisition To Resource Division | 77/B.Ar.D | 11/01/2024 | 0 | Resource Division | 35.76 | 0 | 0 | 0
4435 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Development of IT Network of Active Devices for LAN & WLAN along with EPABX System, CCTV Surveillance System, Conference Room Audio System for the office premises of North 24 Parganas W/S Division-I, Public Health Engineering Directorate, Govt. of West Be , SM/11648 | Support-MIS | Development of IT Network of Active Devices for LAN & WLAN along with EPABX System, CCTV Surveillance System, Conference Room Audio System for North 24 Pgs. W/S Division-I, Public Health Engineering Department, Govt. of West Bengal | 129/NWSD-I | 06/02/2023 | 30 | ALTAVISTA TECH SOLUTIONS | 31.8 | 31.73 | 99.79 | 0
4436 | NORTH 24 PARGANAS | Barasat Arsenic Division | Development of custom Document Archival System (DAS) software and selection of Service Provider for scanning / digitalization of documents for the Office of The Superintending Engineer, Eastern Circle, P.H.E. Dte. at Janasswasthya Karigari Bhawan, Public , SM/16510 | Support-MIS | Development of custom Document Archival System (DAS) Software and selection of Service Provider for scanning / digitization of documents for the Office of The Superintending Engineer, Eastern Circle, P.H.E. Dte at Janaswasthya Karigari Bhawan, Public Health Engineering Department, Govt. of West Bengal. | 790/B.Ar.D. | 28/03/2023 | 885 | ALTAVISTA TECH SOLUTIONS | 60.95 | 30 | 68.56 | 50
4437 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Work order for Supply of Chemicals, Glass Ware and accessories for different Water Testing Laboratories of North 24Pgs District Under Barasat Division, PHE Dte. | 1231/BD | 24/04/2023 | 30 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 56.46 | 56.46 | 100 | 100
4438 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of NGO Lab personnel for the Month of August¿23. | BP-2023-24-375 | 20/09/2023 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
4439 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of September'23. | BP-2023-24-506 | 17/10/2023 | 0 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
4440 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of October'23. | BP-2023-24-519 | 07/11/2023 | 0 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
4441 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of October'23. | BP-2023-24-516 | 07/11/2023 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
4442 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of October'23. | BP-2023-24-518 | 07/11/2023 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
4443 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of October'23. | BP-2023-24-517 | 07/11/2023 | 0 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
4444 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Ad-Hoc Bonus of Laboratory Personnel. | BP-2023-24-419 | 11/10/2023 | 0 | YOUTH DEVELOPMENT CENTER | 0.16 | 0 | 0 | 0
4445 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Ad-Hoc Bonus of Laboratory Personnel. | BP-2023-24-419 | 11/10/2023 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.11 | 0 | 0 | 0
4446 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of NGO Lab personnel for the month of August'23. | BP-2023-24-375 | 20/09/2023 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
4447 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of September'23. | BP-2023-24-507 | 17/10/2023 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
4448 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of October'23. | BP-2023-24-520 | 07/11/2023 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
4449 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of NGO Lab personnel for the Month of August¿23. | BP-2023-24-375 | 20/09/2023 | 0 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
4450 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of September'23. | BP-2023-24-504 | 17/10/2023 | 0 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
4451 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Ad-Hoc Bonus of Laboratory Personnel. | BP-2023-24-419 | 11/10/2023 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.16 | 0 | 0 | 0
4452 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of September'23. | BP-2023-24-502 | 17/10/2023 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
4453 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Payment of NGO Laboratory for the month of Nov'2023. | BP-2023-24-622 | 20/12/2023 | 0 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
4454 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Payment of NGO Laboratory for the month of Nov'2023. | BP-2023-24-621 | 20/12/2023 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
4455 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of NGO Lab personnel for the Month of August¿23. | BP-2023-24-375 | 20/09/2023 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
4456 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of September'23. | BP-2023-24-503 | 17/10/2023 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
4457 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of September'23. | BP-2023-24-505 | 17/10/2023 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
4458 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Ad-Hoc Bonus of Laboratory Personnel. | BP-2023-24-419 | 11/10/2023 | 0 | BITHARI DISHA. | 0.16 | 0 | 0 | 0
4459 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Payment of NGO Laboratory for the month of Nov'2023. | BP-2023-24-620 | 20/12/2023 | 0 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
4460 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of NGO Lab Personnel for the Month of October'23. | BP-2023-24-520 | 07/11/2023 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
4461 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Ad-Hoc Bonus of Laboratory Personnel. | BP-2023-24-419 | 11/10/2023 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.16 | 0 | 0 | 0
4462 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of NGO Lab personnel for the Month of August¿23. | BP-2023-24-375 | 20/09/2023 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
4463 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Ad-Hoc Bonus of Laboratory Personnel. | BP-2023-24-419 | 11/10/2023 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.16 | 0 | 0 | 0
4464 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of NGO Lab personnel for the Month of August¿23. | BP-2023-24-375 | 20/09/2023 | 0 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
4465 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Acceptance cum work order for Engagement of 16 personnel (2 nos. Chemist, 2 nos. Bacteriologist, 1 no. AAS Operator, 2 nos. Laboratory Assistant,4 nos. Sampling Assistant & 5 nos. Lab Attendent ) in different water testing laboratories under Barasat Division,PHE Dte. (North 24 Pargansa District Lab, Hingalganj Sub-District Lab, Bodai Sub-District Lab., Bagda Sub-District Lab, Chandpara Sub-District Lab, Habra Sub-District Lab, Basirhat Sub-Division Lab ) for 1(one)year (Effect from 01.01.2023 to 31.12.2023.) | 185/BD | 19/01/2023 | 365 | M/S B.K.ENTERPRISE. | 36.04 | 16.52 | 100 | 65
4466 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Procurement of Hot Air Oven and Thermometer-Hygrometer-Clock including demonstration & calibration of the instrument at North 24 Parganas District Water Testing laboratory under Barasat Division, PHE Dte. | 1052/BST | 17/11/2023 | 7 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 0.49 | 0.49 | 100 | 85
4467 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Acceptance cum work order for Chemicals & glassware for different water testing laboratories for 6 (Six) months related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, PHE Dte. | 844/BD | 13/03/2024 | 30 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 76.15 | 76.15 | 100 | 95
4468 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory Personnel @lab maintenance on month of December 23 | BP-2023-24-677 | 10/01/2024 | 0 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
4469 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance February-2024. | BP-2023-24-838 | 15/03/2024 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
4470 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance February-2024. | BP-2023-24-833 | 15/03/2024 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
4471 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance February-2024. | BP2023-24-835 | 15/03/2024 | 0 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
4472 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance March-2024. |  | 12/04/2024 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
4473 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory Personnel @lab maintenance on month of December 23 | BP-2023-24-675 | 10/01/2024 | 0 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
4474 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance January-2024. | BP-2023-24-768 | 15/02/2024 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
4475 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | remuneration of Laboratory Personnel & lab maintenance on month of December 23 | BP-2023-24-674 | 10/01/2024 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
4476 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance February-2024 | BP-2023-24-837 | 15/03/2024 | 0 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
4477 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance January-2024. | BP-2023-24-769 | 15/02/2024 | 0 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
4478 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-13 | 16/04/2024 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
4479 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory Personnel @lab maintenance on month of December 23 | BP-2023-24-676 | 10/01/2024 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
4480 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance January-2024. | BP-2023-24-767 | 15/02/2024 | 0 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
4481 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance February-2024 | BP-2023-24-838 | 13/03/2024 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
4482 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance February-2024. | BP-2023-24-834 | 15/03/2024 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
4483 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-11 | 16/04/2024 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
4484 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory Personnel @lab maintenance on month of December 23 | BP-2023-24-678 | 10/01/2024 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
4485 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-12 | 16/04/2024 | 0 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
4486 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel @lab maintenance on month of december 23 | BP-2023-24-673 | 10/01/2024 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
4487 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance | BP-2023-24-766 | 15/02/2024 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
4488 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance January-2024. | BP-2023-24-770 | 15/02/2024 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
4489 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance January-2024. | BP-2023-24-765 | 15/02/2024 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
4490 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-10 | 16/04/2024 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
4491 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Procurement of computers and peripherals for the office use in the Barasat Division and Sub-sequent sub division offices under Barasat Division P.H.E.Dte. | BP-2024-25-26 | 09/05/2024 | 0 | IONET | 0.76 | 0 | 0 | 0
4492 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Remuneration of Laboratory personnel and lab maintenance March-2024. |  | 12/04/2024 | 0 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
4493 | NORTH 24 PARGANAS | Barasat Division | Chemicals and glassware for different water testing laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, P.H.E.Dte. , SM/18144 | Support-WQMSP | Acceptance cum work order for Chemicals & glassware for different water testing laboratories for 2 (Two) months related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, PHE Dte. | 3828/BD | 31/12/2024 | 75 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 25.38 | 0 | 0 | 50
4494 | NORTH 24 PARGANAS | Eastern Mechanical | Procurement of Computer and peripherals for the office use in Eastern Mechanical Division, There Sub-Divisions and office of the Superintending Engineer, Mechanical Circle-III, PHE Dte. , SM/19116 | Support-MIS | GeM tender with item categories multifunction machines MFM All in One PC, Multifunction Machinery MFM, Multifunction Machines MFM, Pen. | 2091/EMD | 27/08/2024 | 96 | IONET | 35.64 | 35.64 | 100 | 100
4495 | NORTH 24 PARGANAS | Barasat Division | Survey of Drinking water & Sanitary. Arrangement of Schools, AWC within the District of North 24 paraganas , SM/09035 | Support-M&E | Survey & collection of data through mobile app regarding availability of drinking water sanitation facilities & other parameters in Primary & Upper Primary Schools, Aganwadi Centers within North 24 Parganas under Barasat Sub Division, P.H.E. Dte. (Part-B) Sl. No.-2 | 2109/BSD | 27/11/2020 | 30 | P.ENTERPRISE. | 4.17 | 4.17 | 100 | 0
4496 | NORTH 24 PARGANAS | Barasat Division | Survey of Drinking water & Sanitary. Arrangement of Schools, AWC within the District of North 24 paraganas , SM/09035 | Support-M&E | Survey & collection of data through mobile app regarding availability of drinking water sanitation facilities & other parameters in Primary & Upper Primary Schools, Aganwadi Centers within North 24 Parganas under Barasat Sub Division, P.H.E. Dte. (Part-C) Sl No.-3. | 2110/BSD | 27/11/2020 | 30 | MONDAL ENTERPRISE. (BARASAT) | 3.95 | 3.95 | 100 | 0
4497 | NORTH 24 PARGANAS | Barasat Division | Survey of Drinking water & Sanitary. Arrangement of Schools, AWC within the District of North 24 paraganas , SM/09035 | Support-M&E | Survey & collection of data through mobile app regarding availability of drinking water sanitation facilities & other parameters in Primary & Upper Primary Schools, Aganwadi Centers within North 24 Parganas under Barasat Sub-Division, P.H.E. Dte. (Part-A) Sl. No.-1 | 2108/BSD. | 27/11/2020 | 30 | SUN ENTERPRISE. | 3.67 | 3.67 | 100 | 0
4498 | NORTH 24 PARGANAS | Barasat Division | Drinking water sample collection and testing through Field Test Kit FTKs by ASHAs and uploading test result to WQMIS for three months related to Water Quality Monitoring and Surveillance programme under Jal Jeevan Mission , SM/13736 | Support-WQMSP | Acceptance cum work order for Collection & test the water sample from School & Anganwari Centres using FTK (Field Test Kit) & uploading test result in State Water Quality Dashboard under the programme of "Swachh Jal se Suraksha" campaign in North 24 Parganas district under Barasat Division,PHE Dte. | 430/BD | 13/02/2023 | 365 | M/S B.K.ENTERPRISE. | 11.45 | 10.4 | 90.84 | 0
4499 | NORTH 24 PARGANAS | Barasat Division | Drinking water sample collection and testing through Field Test Kit FTKs by ASHAs and uploading test result to WQMIS for three months related to Water Quality Monitoring and Surveillance programme under Jal Jeevan Mission , SM/13736 | Support-WQMSP | WATER SAMPLE TESTING AND AWARENESS GENERATION | BP-2023-24-350 | 11/09/2023 | 0 | DH & FWS NORTH 24 PGS. | 3.36 | 0 | 0 | 0
4500 | NORTH 24 PARGANAS | Barasat Division | Drinking water sample collection and testing through Field Test Kit FTKs by ASHAs and uploading test result to WQMIS for three months related to Water Quality Monitoring and Surveillance programme under Jal Jeevan Mission , SM/13736 | Support-WQMSP | Acceptance cum work order for Chemicals & glassware for different water testing laboratories for 2 (Two) months related to WQMSP in connection with Jal Jeevan Mission under Barasat Division, PHE Dte. | 3828/BD | 31/12/2024 | 75 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 25.38 | 0 | 0 | 50
4501 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Operational charges of Mangal Pandey WTP Water Testing Laboratory related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/12048 | Support-WQMSP | Engagement of Laboratory personnel for Day to Day water testing at Laboratory of Mangal Pandey Water Treatment Plant in the status of District Laboratory under North 24 Pgs. W/S Division-I, PHE. Dte for the period of 1 (One) year.(2nd Call) | 383/NWSD-I | 29/03/2022 | 1 | M/S PHOENIX INFRASTRUCTURE | 11.2 | 10.59 | 94.58 | 100
4502 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Operational charges of Mangal Pandey WTP Water Testing Laboratory related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/12048 | Support-WQMSP | Providing services for deputing resource person for supervision for desktop surveillance audit of NABL Accreditation as per ISO / IEC: 17025 : 2017, calibration of applicable analytical instruments & supply of reagents-consumables for Mangal Pandey Water Testing Laboratory under The Executive Engineer, North 24 Pgs. W/S Division-I, P.H.E Dte, Government of West Bengal. | 731/NWSD-I | 09/06/2022 | 183 | LAB ANALYTICS | 2.85 | 2.85 | 100 | 10
4503 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Operational charges of Mangal Pandey WTP Water Testing Laboratory related to Water Quality Monitoring & Surveillance including procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes. , SM/19088 | Support-WQMSP | Supply of chemical & Consumable reagents and other laboratory related items at Mangal Pandey WTP water Testing Laboratory under North 24 PGS. Water Supply Division-I, PHE. Dte. | 1175/NWSD-I | 05/08/2024 | 30 | M/S. LAXMI ENTERPRISE. | 0.25 | 0 | 0 | 0
4504 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Operational charges of Mangal Pandey WTP Water Testing Laboratory related to Water Quality Monitoring & Surveillance including procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes. , SM/19088 | Support-WQMSP | Engagement of Laboratory personnel for Day to Day Water testing at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. W/S. Division-I, PHE. Dte. For the period of 01 (One) year. i.e. 366 Days. (01.09.2023 to 31.08.2024) | 1324/NWSD-I | 29/08/2023 | 366 | M/S. PHOENIX INFRASTRUCTURE | 26.99 | 19.48 | 100 | 66
4505 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Operational charges of Mangal Pandey WTP Water Testing Laboratory related to Water Quality Monitoring & Surveillance including procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes. , SM/19088 | Support-WQMSP | Supply of chemical & Consumable reagents and other laboratory related items at Mangal Pandey WTP water Testing Laboratory under North 24 PGS. Water Supply Division-I, PHE. Dte. | 1176/NWSD-I | 05/08/2024 | 30 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 3.06 | 3.06 | 100 | 100
4506 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Operational charges of Mangal Pandey WTP Water Testing Laboratory related to Water Quality Monitoring & Surveillance including procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes. , SM/19088 | Support-WQMSP | Supply of chemical & Consumable reagents and other laboratory related items at Mangal Pandey WTP water Testing Laboratory under North 24 PGS. Water Supply Division-I, PHE. Dte. | 1177/NWSD-I | 05/08/2024 | 105 | SCIENTIFIC VENTURES | 0.58 | 0 | 0 | 100
4507 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Operational charges of Mangal Pandey WTP Water Testing Laboratory related to Water Quality Monitoring & Surveillance including procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes. , SM/19088 | Support-WQMSP | Supply of Requirement of materials for analysis of BOD, COD, Dissolved Oxygen at Laboratory with already available instrument at Mangal Pandey WTP Laboratory under North 24 PGS. Water Supply Division-I, PHE. Dte. | 592/NWSD-I | 21/04/2025 | 30 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 3.05 | 0 | 0 | 100
4508 | NORTH 24 PARGANAS | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. , SM/06629 | Support-WQMSP | Supply of Chemicals and accessories for different NGO managed Water Testing Laboratories on emergency basis of North 24Pgs District Under Barasat Division, PHE Dte. Sl.No.01 | 175/BST | 08/03/2022 | 31 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 4.97 | 4.97 | 100 | 0
4509 | NORTH 24 PARGANAS | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. , SM/06629 | Support-WQMSP | Supply of Silver diethyl -dithio- carbamate for analysis,( 5 gm pack) Merck for different Water Testing Laboratories of North 24Pgs District Under Barasat Division, PHE Dte. Sl.No.01 | 176/BST | 08/03/2022 | 31 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 4.83 | 4.83 | 100 | 0
4510 | NORTH 24 PARGANAS | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. , SM/06629 | Support-WQMSP | Supply of Ferrospectral Reagent (Fe.1) Range 0.005-5.00 mg/l Fe 2+(1000) test pack for different Water Testing Laboratories of North 24Pgs District Under Barasat Division, PHE Dte. Sl.No.03 | 178/BST | 08/03/2022 | 31 | LAB. SOLUTION | 4.89 | 4.89 | 50 | 0
4511 | NORTH 24 PARGANAS | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. , SM/06629 | Support-WQMSP | 3rd Party Calibration of pH Meter, Turbidity meter, Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & any other measuring Instruments required for calibration as per NABL traceability & conformity under Barasat Sub Division, P.H.E. Dte. Sl. No.-01 | 778/A/BSD | 26/11/2021 | 3 | LAB. SOLUTION | 0.58 | 0.58 | 100 | 0
4512 | NORTH 24 PARGANAS | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. , SM/06629 | Support-WQMSP | Renovation of laboratory building for NABL accreditation at Barasat District Laboratory under Barasat Sub Division, P.H.E. Dte. Part-B Sl. No.-13 | 342/BSD | 12/04/2022 | 20 | P.ENTERPRISE. | 4.43 | 4.43 | 50 | 0
4513 | NORTH 24 PARGANAS | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. , SM/06629 | Support-WQMSP | Acceptance cum work order for Supply of Chemicals, Glass Ware and accessories for different Water Testing Laboratories of North 24Pgs District Under Barasat Division, PHE Dte. | 1592/BD | 03/06/2022 | 30 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 41.92 | 41.92 | 50 | 0
4514 | NORTH 24 PARGANAS | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. , SM/06629 | Support-WQMSP | Procurement of consumables of OMAS for the month of June to July'2022 for the District of North 24 Parganas under Barasat Division, P.H.Engineering Dte. Sl.No.02 | 464/BST | 08/06/2022 | 61 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.29 | 4.29 | 50 | 0
4515 | NORTH 24 PARGANAS | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. , SM/06629 | Support-WQMSP | Electrification Works of laboratory building for NABL accreadiation at Barasat District Laboratory under Barasat Sub Division, P.H.E. Dte. Sl. No.-14 | 343/BSD | 12/04/2022 | 7 | ANJALI ENTERPRISE. | 4.6 | 4.6 | 50 | 0
4516 | NORTH 24 PARGANAS | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. , SM/06629 | Support-WQMSP | Renovation of laboratory building for NABL accreditation at Barasat District Laboratory under Barasat Sub Division, P.H.E. Dte. Part-A Sl. No.-12 | 341/BSD | 12/04/2022 | 20 | M/S K.P.PAL. | 4.58 | 4.58 | 50 | 0
4517 | NORTH 24 PARGANAS | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. , SM/06629 | Support-WQMSP | Engagement of Computer Operator / Data Entry Operator of different categories for the office of the Assistant Engineer, R.W.S Barasat Sub- Division, PHE Dte. (Period 01.11.2020 to 31.10.2021). | 551/BST | 14/10/2020 | 92 | M/S B.K.ENTERPRISE. | 0 | 0 | 0 | 0
4518 | NORTH 24 PARGANAS | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. , SM/06629 | Support-WQMSP | Supply of Chemicals and accessories for different Sub-Divisional Water Testing Laboratories of North 24Pgs District Under Barasat Division, PHE Dte. Sl.No.02 | 177/BST | 08/03/2022 | 31 | M/S LAXMI ENTERPRISE | 4.96 | 4.95 | 99.92 | 0
4519 | NORTH 24 PARGANAS | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. , SM/06629 | Support-WQMSP | Supply of Certified traceable to SI unit of Pt-Co-Color units Calibration Standard CRM at Asesh Roy Water Testing Laboratory, Chandpara Sub-District Water Testing laboratory & Turbidity standard solution at Bagdah Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. | 509/BST | 08/06/2023 | 7 | LAB. SOLUTION | 0.65 | 0.65 | 100 | 100
4520 | NORTH 24 PARGANAS | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. , SM/06629 | Support-WQMSP | Supply Turbidity standard solution at Asesh Roy Water Testing Laboratory & Chandpara Sub-District Water Testing laboratory under Barasat Division, PHE Dte. | 508/BST | 08/06/2023 | 7 | LAB. SOLUTION | 0.84 | 0.84 | 100 | 100
4521 | NORTH 24 PARGANAS | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. , SM/06629 | Support-WQMSP | Supply installation & calibration of Turbidity Meter for Bagdah & Gokna Water Testing Laboratories of North 24Pgs District Under Barasat Division, PHE Dte. Sl.No.01 | 334/BST | 21/04/2022 | 10 | LAB ANALYTICS | 2.13 | 0 | 0 | 0
4522 | NORTH 24 PARGANAS | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. , SM/06629 | Support-WQMSP | Payment of NGO Laboratory for the month of Nov'2023. | BP-2023-24-623 | 20/12/2023 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
4523 | NORTH 24 PARGANAS | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. , SM/06629 | Support-WQMSP | Payment of NGO laboratory for the Month of Nov'2023 | BP-2023-24-619 | 20/12/2023 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
4524 | NORTH 24 PARGANAS | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. , SM/06629 | Support-WQMSP | Acceptance cum work order for Engagement of 16 nos. personnel (1 no. Chemist/Bacteriologist & 1 nos. Lab Assistant) ) in 8 nos. laboratories under Barasat Division,PHE Dte.(Bodai Sub-District Water Testing Lab, Bishnupur Sub-District Water Testing Lab, Bagda Sub-District Water Testing Lab, Chandpara Sub-District Water Testing Lab, Habra Sub-District Water Testing Lab, Basirhat Sub-District Water Testing Lab ,Gokna Sub-District Water Testing Lab, Haroa Sub-District Water Testing Lab ) for 1(one) year)(Effect from 01-01-2023 to 31.12.2023.) | 184/BD | 19/01/2023 | 365 | FRONTLINE EX-SERVICEMEN BUREAU. | 36.96 | 6.11 | 44.04 | 100
4525 | NORTH 24 PARGANAS | Barasat Division | Renovation of District Laboratory for NABL set-up under Barasat Division. , SM/08691 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Habra Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.04 | 670/BST | 24/12/2021 | 90 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 3.64 | 75.66 | 0
4526 | NORTH 24 PARGANAS | Barasat Division | Renovation of District Laboratory for NABL set-up under Barasat Division. , SM/08691 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Bishnupur Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.06 | 672/BST | 24/12/2021 | 90 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 3.64 | 75.66 | 0
4527 | NORTH 24 PARGANAS | Barasat Division | Renovation of District Laboratory for NABL set-up under Barasat Division. , SM/08691 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Bodai Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.05 | 671/BST | 24/12/2021 | 3 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.81 | 3.64 | 100 | 0
4528 | NORTH 24 PARGANAS | Barasat Division | Renovation of District Laboratory for NABL set-up under Barasat Division. , SM/08691 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Gokna Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.03 | 669/BST | 24/12/2021 | 3 | M/S LAXMI ENTERPRISE | 4.83 | 2.01 | 84.26 | 0
4529 | NORTH 24 PARGANAS | Barasat Division | Renovation of District Laboratory for NABL set-up under Barasat Division. , SM/08691 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Basirhat Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.01 | 667/BST | 24/12/2021 | 90 | M/S LAXMI ENTERPRISE | 4.83 | 0 | 0 | 0
4530 | NORTH 24 PARGANAS | Barasat Division | Renovation of District Laboratory for NABL set-up under Barasat Division. , SM/08691 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Haroa Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.02 | 668/BST | 24/12/2021 | 90 | M/S LAXMI ENTERPRISE | 4.83 | 3.66 | 100 | 0
4531 | NORTH 24 PARGANAS | Barasat Division | Installation of 5 KLD NF-RO Based Desalination Plant on pilot basis for providing FHTC in Sundarban Island no. 61 , SM/10759 | Support-R&D | Acceptance cum work order for Construction of switch room excluding sub-structure for installation of 05 KLD NF-RO Based Desalination Plant at Sridharkati Zone No-28, Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | 1162/HSD | 12/07/2022 | 21 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 1.33 | 1.18 | 50 | 0
4532 | NORTH 24 PARGANAS | Barasat Division | Installation of 5 KLD NF-RO Based Desalination Plant on pilot basis for providing FHTC in Sundarban Island no. 61 , SM/10759 | Support-R&D | Acceptance cum work order for Sinking of 01 no. 100 X 50 mm. dia. 300 mtr. Deep Tube-well with PVC pipes & strainer and other allied works for installation of 05 KLD NF-RO Based Desalination Plant at Sridharkati Zone No-28, Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | 1161/HSD | 12/07/2022 | 15 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 4.61 | 4.13 | 50 | 0
4533 | NORTH 24 PARGANAS | Barasat Division | Installation of 5 KLD NF-RO Based Desalination Plant on pilot basis for providing FHTC in Sundarban Island no. 61 , SM/10759 | Support-R&D | Acceptance cum work order for Technical Assistance for Design and Demonstration of NF/RO Desalination Plant for Saline/Brackish Water Treatment for Drinking Water Supply at Sridharkati, Zone-XXVIII. | 3275/BD | 07/11/2022 | 365 | DR. P.S GHOSAL | 5.9 | 0 | 0 | 0
4534 | NORTH 24 PARGANAS | Barasat Division | Installation of 2 KLD UF-RO Based Desalination Plant on pilot basis for providing FHTC in Sundarban Island no. 61 , SM/10740 | Support-R&D | Acceptance cum work order for Sinking of 01 no. 100 X 50 mm. dia. 300 mtr. Deep Tube-well with PVC pipes & strainer and other allied works for installation of 02 KLD UF-RO Based Desalination Plant at Sridharkati Zone No-23, Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | 1159/HSD | 12/07/2022 | 15 | JESMINE ENTERPRISE. | 4.61 | 4.17 | 50 | 0
4535 | NORTH 24 PARGANAS | Barasat Division | Installation of 2 KLD UF-RO Based Desalination Plant on pilot basis for providing FHTC in Sundarban Island no. 61 , SM/10740 | Support-R&D | Acceptance cum work order for Construction of switch room excluding sub-structure for installation of 02 KLD UF-RO Based Desalination Plant at Sridharkati Zone No-23, Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | 1160/HSD | 12/07/2022 | 21 | JESMINE ENTERPRISE. | 1.33 | 1.18 | 50 | 0
4536 | NORTH 24 PARGANAS | Barasat Division | Installation of 2 KLD UF-RO Based Desalination Plant on pilot basis for providing FHTC in Sundarban Island no. 61 , SM/10740 | Support-R&D | Acceptance cum work order for Technical Assistance for Design and Demonstration of UF/RO Desalination Plant for Saline/Brackish Water Treatment for Drinking Water Supply at Sridharkati, Zone-XXIII. | 3276/BD | 07/11/2022 | 365 | DR. P.S GHOSAL | 4.72 | 0 | 0 | 0
4537 | NORTH 24 PARGANAS | Barasat Division | Installation of 2 KLD UF-RO Based Desalination Plant on pilot basis for providing FHTC in Sundarban Island no. 61 , SM/10740 | Support-R&D | Acceptance cum work order for Supply, Installation, Testing and commission of 2 KLD Desalination Ro plant; including transport, installation and GST. | 795/HSD | 27/05/2022 | 30 | ENVIROEXCELSIOR SOLUTIONS PVT. LTD. | 4.97 | 4.97 | 100 | 100
4538 | NORTH 24 PARGANAS | Barasat Division | Procurement of computer and peripherals for the office use in Barasat Division and subsequent Sub-Division offices under Barasat Division, P.H.E.Dte. , SM/13735 | Support-MIS | Procurement of Computer and Peripherals for Office uses in Barasat Division & Subsequent Sub-Division Office under HQ. | BP-2023-24-510 | 01/11/2023 | 0 | IONET | 1.89 | 0 | 0 | 0
4539 | NORTH 24 PARGANAS | Barasat Division | Procurement of computer and peripherals for the office use in Barasat Division and subsequent Sub-Division offices under Barasat Division, P.H.E.Dte. , SM/13735 | Support-MIS | Procurement of Computer and Peripherals for Office uses in Barasat Division & Subsequent Sub-Division Office under HQ. | BP-2023-24-521 | 07/11/2023 | 0 | IONET | 4.62 | 0 | 0 | 0
4540 | NORTH 24 PARGANAS | Barasat Division | Procurement of computer and peripherals for the office use in Barasat Division and subsequent Sub-Division offices under Barasat Division, P.H.E.Dte. , SM/13735 | Support-MIS | Procurement of computer and peripherals for the office use in Barasat Division and subsequent Sub-Division under Barasat Division. P H E Dte. | BP-2023-24-646 | 03/01/2024 | 0 | IONET | 0.63 | 0 | 0 | 0
4541 | NORTH 24 PARGANAS | Barasat Division | Procurement of computer and peripherals for the office use in Barasat Division and subsequent Sub-Division offices under Barasat Division, P.H.E.Dte. , SM/13735 | Support-MIS | Procurement of computers and peripherals for the office use in the Barasat Division and Sub-sequent sub division offices under Barasat Division P.H.E.Dte. | BP-2024-25-291 | 20/09/2024 | 0 | IONET | 0.13 | 0 | 0 | 0
4542 | NORTH 24 PARGANAS | Barasat Division | Procurement of computer and peripherals for the office use in Barasat Division and subsequent Sub-Division offices under Barasat Division, P.H.E.Dte. , SM/13735 | Support-MIS | Procurement of computers and peripherals for the office use in the Barasat Division and Sub-sequent sub division offices under Barasat Division P.H.E.Dte. | BP-2024-25-246 | 09/09/2024 | 0 | EASY DAY ENTERPRISE | 0.12 | 0 | 0 | 0
4543 | NORTH 24 PARGANAS | Barasat Division | Procurement of computer and peripherals for the office use in Barasat Division and subsequent Sub-Division offices under Barasat Division, P.H.E.Dte. , SM/13735 | Support-MIS | Procurement of computers and peripherals for the office use in the Barasat Division and Sub-sequent sub division offices under Barasat Division P.H.E.Dte. | BP-2024-25-2424 | 09/09/2024 | 0 | EASY DAY ENTERPRISE | 0.24 | 0 | 0 | 0
4544 | NORTH 24 PARGANAS | Barasat Division | Procurement of computer and peripherals for the office use in Barasat Division and subsequent Sub-Division offices under Barasat Division, P.H.E.Dte. , SM/13735 | Support-MIS | Procurement of computers and peripherals for the office use in the Barasat Division and Sub-sequent sub division offices under Barasat Division P.H.E.Dte | BP-2024-25-291 | 20/09/2024 | 0 | IONET | 0.87 | 0 | 0 | 0
4545 | NORTH 24 PARGANAS | Barasat Division | Procurement of computer and peripherals for the office use in Barasat Division and subsequent Sub-Division offices under Barasat Division, P.H.E.Dte. , SM/13735 | Support-MIS | Procurement of computers and peripherals for the office use in the Barasat Division and Sub-sequent sub division offices under Barasat Division P.H.E.Dte | BP-2024-25-291 | 20/09/2024 | 0 | IONET | 2.08 | 0 | 0 | 0
4546 | NORTH 24 PARGANAS | Barasat Division | Procurement of computer and peripherals for the office use in Barasat Division and subsequent Sub-Division offices under Barasat Division, P.H.E.Dte. , SM/13735 | Support-MIS | Procurement of computer and peripherals for tho office use in Baras. at Division and subsequent Sub-Division under Barasat Division. P H E Dte | BP-2023-24-645 | 03/01/2024 | 0 | IONET | 0.15 | 0 | 0 | 0
4547 | NORTH 24 PARGANAS | Barasat Division | Procurement of computer and peripherals for the office use in Barasat Division and subsequent Sub-Division offices under Barasat Division, P.H.E.Dte. , SM/13735 | Support-MIS | Procurement of computers and peripherals for the office use in the Barasat Division and Sub-sequent sub division offices under Barasat Division P.H.E.Dte. | BP-2024-25-244 | 06/09/2024 | 0 | IONET | 0.25 | 0 | 0 | 0
4548 | NORTH 24 PARGANAS | Barasat Division | Procurement of computer and peripherals for the office use in Barasat Division and subsequent Sub-Division offices under Barasat Division, P.H.E.Dte. , SM/13735 | Support-MIS | Procurement of computers and peripherals for the office use in the Barasat Division and Sub-sequent sub division offices under Barasat Division P.H.E.Dte. | BP-2024-25-291 | 20/09/2024 | 0 | IONET | 0.14 | 0 | 0 | 0
4549 | NORTH 24 PARGANAS | Barasat Division | Procurement of computer and peripherals for the office use in Barasat Division and subsequent Sub-Division offices under Barasat Division, P.H.E.Dte. , SM/13735 | Support-MIS | Procurement of computers and peripherals for the office use in the Barasat Division and Sub-sequent sub division offices under Barasat Division P.H.E.Dte. | BP-2024-25-291 | 20/09/2024 | 0 | IONET | 0.25 | 0 | 0 | 0
4550 | NORTH 24 PARGANAS | Barasat Division | Procurement of computer and peripherals for the office use in Barasat Division and subsequent Sub-Division offices under Barasat Division, P.H.E.Dte. , SM/13735 | Support-MIS | Procurement of computer and peripherals for the office use in Barasat Division and subsequent Sub-Division under Barasat Division. P H E Dte. | BP-2023-24-647 | 03/01/2024 | 0 | IONET | 0.13 | 0 | 0 | 0
4551 | NORTH 24 PARGANAS | Barasat Division | Procurement of computer and peripherals for the office use in Barasat Division and subsequent Sub-Division offices under Barasat Division, P.H.E.Dte. , SM/13735 | Support-MIS | Procurement of computer and peripherals for the office use in Barasat Division and subsequent Sub-Division offices under HQ | BP-2023-24-757 | 15/02/2024 | 0 | IONET | 4.75 | 0 | 0 | 0
4552 | NORTH 24 PARGANAS | Barasat Division | Collection, testing and uploading charges of drinking water sample (Phase-II) through Field Test Kits (FTK) (Phase-II) , SM/18143 | Support-WQMSP | Carriage of Field Test Kit (FTK) and Data Reporting Sheet (DRS)Phase-III including loading & unloading from Barasat Division Office to respective BMOH Office in North 24 Parganas District related to Water Quality Surveillance Programme under Jal Jeevan Mission. | 749/BST | 04/07/2024 | 7 | M/S R.B.S.ENTERPRISE. | 0.93 | 0 | 0 | 0
4553 | NORTH 24 PARGANAS | Barasat Division | Collection, testing and uploading charges of drinking water sample (Phase-II) through Field Test Kits (FTK) (Phase-II) , SM/18143 | Support-WQMSP | Acceptance cum work order for Uploading of FTK Data Sheet (Phase-II) to WQMIS related to Water Quality Monitering & Surveillance Programme under Jal Jeevan Mission of North 24 parganas. | 445/BD | 12/02/2024 | 29 | M/S B.K.ENTERPRISE. | 6.85 | 3.42 | 49.99 | 50
4554 | NORTH 24 PARGANAS | Barasat Division | Collection, testing and uploading charges of drinking water sample (Phase-II) through Field Test Kits (FTK) (Phase-II) , SM/18143 | Support-WQMSP | Acceptance cum work order for Collection of Water Sample in uninterrupted manner and submit the same to the respective PHED laboratory by engagement of agency where ever facilitator are not available, unwilling or inactive in North 24 Pargaanas District under Barasat Division, PHE Dte.(Phase-II). | 444/BD | 12/02/2024 | 29 | M/S B.K.ENTERPRISE. | 7.83 | 7.76 | 100 | 49
4555 | NORTH 24 PARGANAS | Barasat Division | Collection, testing and uploading charges of drinking water sample (Phase-II) through Field Test Kits (FTK) (Phase-II) , SM/18143 | Support-WQMSP | Water Sample testing awareness generation charges of ASAHs through FTK | C102413443387 | 04/10/2024 | 0 | DH & FWS NORTH 24 PGS. | 2.9 | 0 | 0 | 0
4556 | NORTH 24 PARGANAS | Barasat Division | Collection, testing and uploading charges of drinking water sample (Phase-II) through Field Test Kits (FTK) (Phase-II) , SM/18143 | Support-WQMSP | Regarding water sample testing and awareness generation charges of ASHS's through FTK for the financial year 2022-23 in favour of Basirhat Health District | BP-2023-24-764 | 15/02/2024 | 0 | BASIRHAT HEALTH DISTRICT. | 15.24 | 0 | 0 | 0
4557 | NORTH 24 PARGANAS | Barasat Division | Collection, testing and uploading charges of drinking water sample (Phase-II) through Field Test Kits (FTK) (Phase-II) , SM/18143 | Support-WQMSP | Regarding water sample testing and awareness generation charges of ASHA's through FTK for the financial year 2022-23 in favour of North 24 Parganas Health District. | BP-2023-24-763 | 15/02/2024 | 0 | DH & FWS NORTH 24 PGS. | 14.57 | 0 | 0 | 0
4558 | NORTH 24 PARGANAS | Barasat Division | Collection, testing and uploading charges of drinking water sample (Phase-II) through Field Test Kits (FTK) (Phase-II) , SM/18143 | Support-WQMSP | Water Sample testing awareness generation charges of ASAHs through FTK | BP-2024-25-401 | 04/10/2024 | 0 | BASIRHAT HEALTH DISTRICT. | 4.06 | 0 | 0 | 0
4559 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Improvement of IT Infrastructure by providing Desktop computers, printers, copies and its peripherals for water testing laboratory and Division & Sub Division offices under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/13407 | Support-MIS | Supply & installation of Canon Multifunction Machines Mfm, on site OEM warranty 3 year for the office of the Executive Engineer, North 24 Pgs. W/S Division-I, P.H.E. Dte. | 141/PFMS/23-24 | 14/07/2023 | 0 | IONET | 3.55 | 0 | 0 | 0
4560 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Improvement of IT Infrastructure by providing Desktop computers, printers, copies and its peripherals for water testing laboratory and Division & Sub Division offices under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/13407 | Support-MIS | Supply of HP Slim Desktop PC - 501 PF 2367 in PC System - i3, UPS, Laser Printer for office of the Executive Engineer, North 24 Pgs. W/S Division-I, P.H.E. Dte. | 312/DEP/2022-23 | 28/12/2022 | 0 | IONET | 2.87 | 0 | 0 | 0
4561 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Improvement of IT Infrastructure by providing Desktop computers, printers, copies and its peripherals for water testing laboratory and Division & Sub Division offices under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/13407 | Support-MIS | Supply of Canon Multifunction Machines Mfm, On Site OEM Warranty 3 year for office of the Executive Engineer, North 24 Pgs. W/S Division-I, P.H.E. Dte. | 396/DEP/2022-23 | 23/02/2023 | 0 | IONET | 1.28 | 0 | 0 | 0
4562 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Improvement of IT Infrastructure by providing Desktop computers, printers, copies and its peripherals for water testing laboratory and Division & Sub Division offices under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/13407 | Support-MIS | Supply of HP Intel Core i5 14 inch Laptop (Windows 11 Professional) for office of the Executive Engineer, North 24 Pgs. W/S Division-I, P.H.E. Dte. | 394/DEP/2022-23 | 23/02/2023 | 0 | IONET | 0.7 | 0 | 0 | 0
4563 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Improvement of IT Infrastructure by providing Desktop computers, printers, copies and its peripherals for water testing laboratory and Division & Sub Division offices under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/13407 | Support-MIS | Supply of Canon Multifunction Machines Mfm, On Site OEM Warranty 3 year for office of the AE, NWSSD-I, P.H.E.D. under Executive Engineer, North 24 Pgs. W/S Division-I, P.H.E. Dte. | 395/DEP/2022-23 | 23/02/2023 | 0 | IONET | 1.24 | 0 | 0 | 0
4564 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Improvement of IT Infrastructure by providing Desktop computers, printers, copies and its peripherals for water testing laboratory and Division & Sub Division offices under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/13407 | Support-MIS | Supply & installation of hp Intel Core i3 12100 8 GB / Windows 11 Home Desktop PC for the office of the Executive Engineer, North 24 Pgs. W/S Division-I, P.H.E. Dte. | 140/PFMS/23-24 | 14/07/2023 | 0 | IONET | 3.99 | 0 | 0 | 0
4565 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Annual Maintenance Contract (AMC) for Computers Printers UPS and other related peripherals installed in various water testing laboratories under office of the Executive Engineer, Barasat Division P.H.E.Dte. (for the period 01.10.2023 to 30.09.2024). | 871/BST | 29/09/2023 | 366 | CSS INFOSOLUTION. | 2.41 | 1.41 | 100 | 85
4566 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-453 | 19/11/2024 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
4567 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-462 | 10/12/2024 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
4568 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-351 | 01/10/2024 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.63 | 0 | 0 | 0
4569 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-465 | 10/12/2024 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
4570 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-455 | 20/11/2024 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
4571 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-467 | 10/12/2024 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
4572 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-456 | 19/11/2024 | 0 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
4573 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-466 | 10/12/2024 | 0 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
4574 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-454 | 19/11/2024 | 0 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
4575 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-464 | 10/12/2024 | 0 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
4576 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-347 | 01/10/2024 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.69 | 0 | 0 | 0
4577 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-462 | 10/12/2024 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
4578 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-346 | 01/10/2024 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.69 | 0 | 0 | 0
4579 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-457 | 19/11/2024 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
4580 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-452 | 19/11/2024 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
4581 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-359 | 01/10/2024 | 0 | BITHARI DISHA. | 0.69 | 0 | 0 | 0
4582 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-351 | 01/10/2024 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.69 | 0 | 0 | 0
4583 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Recurring expenditure of the Water Testing Laboratory managed by NGO'S under North 24 Parganas District. | BP-2024-25-348 | 01/10/2024 | 0 | YOUTH DEVELOPMENT CENTER | 0.69 | 0 | 0 | 0
4584 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Acceptance cum work order for Engagement of Laboratory personnel at 9(Nine) nos. Sub-District Water Testing Laboratory . (Bodai SDL, Bishnupur SDL, Bagda SDL, Chandpara SDL, Habra SDL, Basirhat SDL ,Gokna SDL, Haroa SDL & Hingalganj SDL) and North 24 Parganas District Water Laboratory for 12 (Twelve) months w.e.f 01.01.2024 to 31.12.2024. | 4879/BD | 29/12/2023 | 366 | M/S B.K.ENTERPRISE. | 95.2 | 46.34 | 100 | 81
4585 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Annual Maintenance Contract (AMC) for Computers Printers UPS and other related peripherals installed in various water testing laboratories under office of the Executive Engineer, Barasat Division P.H.E.Dte. (for the period 01.10.2024 to 31.12.2024) | 1120/BST | 30/09/2024 | 92 | CSS INFOSOLUTION. | 0.6 | 0.6 | 100 | 100
4586 | NORTH 24 PARGANAS | Barasat Division | Yearly Operational Charges of PHED and NGO managed Laboratories for 2024 related to WQMSP in connection with JJM under Barasat Division, P.H.E.Dte. , SM/19259 | Support-WQMSP | Annual Maintenance Contract (AMC) for Computers Printers UPS and other related peripherals installed in various water testing laboratories under office of the Executive Engineer, Barasat Division P.H.E.Dte. (for the period 01.01.2025 to 31.03.2025) | 1467/BST | 31/12/2024 | 90 | CSS INFOSOLUTION. | 0.6 | 0.6 | 100 | 100
4587 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes of Mangal Panday WTP Water Testing Laboratory under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/13849 | Support-WQMSP | Providing services for deputing resource person for supervision for renewal of NABL Accreditation as per ISO/IEC : 17025 : 2017, calibration of applicable analytical instruments & supply of reagents - consumables for Mangal Pandey Water Testing Laboratory under The Executive Engineer, North 24 Pgs W/S Division-I, PHE Dte, Government of West Bengal. | 952/NWSD-I | 12/11/2021 | 6 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.77 | 4.77 | 100 | 0
4588 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes of Mangal Panday WTP Water Testing Laboratory under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/13849 | Support-WQMSP | Supply delivery of chemical with valid CoA certificates for the smooth running of the laboratory testing for bottling plant (Prandhara Package Drinking Water ) for Mangal Pandey WTP Water Testing Laboratory under The Executive Engineer, North 24 Pgs W/S Division-I, PHE Dte, Government of West Bengal. | 953/NWSD-I | 12/11/2021 | 7 | LAB ANALYTICS | 1.39 | 1.39 | 100 | 0
4589 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes of Mangal Panday WTP Water Testing Laboratory under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/13849 | Support-WQMSP | Supply delivery & fixing of Analytical gases for Atomic Absorption Spectrophotometer (AAS), Spares for AAS Model- ICE3500-Thermo Scientific, different consumables for analysis of drinking water samples by AAS, ICE-3500 and standard reference materials for standardization of analytical instruments for Mangal Pandey WTP Water Testing Laboratory under The Executive Engineer, North 24 Pgs W/S Division-I, PHE Dte, Government of West Bengal. | 938/NWSD-I | 08/11/2021 | 7 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.67 | 4.67 | 100 | 0
4590 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes of Mangal Panday WTP Water Testing Laboratory under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/13849 | Support-WQMSP | Supply, delivery of different chemicals, consumables & glassware used for analysis of drinking water samples (as per ISO / IEC 17025: 2017 protocol) & standard replace materials for standardisation of analytical instruments for Mangal Pandey WTP Water Testing Laboratory under the Office of the Executive Engineer, North 24 Pgs W/S Division-I, P.H.E. Dte, Govt. of West Bengal. | 572/NWSD-I | 02/05/2022 | 1 | SCIENTIFIC VENTURES | 2.68 | 2.68 | 100 | 0
4591 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes of Mangal Panday WTP Water Testing Laboratory under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/13849 | Support-WQMSP | Supply of Chemicals & Consumables Reagents, Glassware, Standard Reference material & solutions traceble to NIST etc to comply with NABL ISO / IEC 17025 : 297 & BIS standards at Mangal Pandey WTP Water Testing Laboratory. | 879/NWSD-I | 12/07/2023 | 15 | M/S. LAXMI ENTERPRISE. | 0.66 | 0 | 0 | 0
4592 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes of Mangal Panday WTP Water Testing Laboratory under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/13849 | Support-WQMSP | Supply of Chemicals & Consumables Reagents, Glassware, Standard Reference material & solutions traceble to NIST etc. to comply with NABL ISO / IEC 17025 : 2017 & BIS standards at Mangal Pandey WTP Water Testing Laboratory. | 1470/NWSD-I | 15/09/2023 | 15 | LAB ANALYTICS | 0.49 | 0 | 0 | 100
4593 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes of Mangal Panday WTP Water Testing Laboratory under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/13849 | Support-WQMSP | Supply of Chemicals & Consumables Reagents, Glassware, Standard Reference material & solutions traceble to NIST etc to comply with NABL ISO / IEC 17025 : 297 & BIS standards at Mangal Pandey WTP Water Testing Laboratory. | 878/NWSD-I | 12/07/2023 | 15 | SCIENTIFIC VENTURES | 1.43 | 1.43 | 100 | 100
4594 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes of Mangal Panday WTP Water Testing Laboratory under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/13849 | Support-WQMSP | Supply of Chemicals & Consumables Reagents, Glassware, Standard Reference material & solutions traceble to NIST etc to comply with NABL ISO / IEC 17025 : 297 & BIS standards at Mangal Pandey WTP Water Testing Laboratory. | 877/NWSD-I | 12/07/2023 | 15 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.51 | 1.51 | 100 | 100
4595 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes of Mangal Panday WTP Water Testing Laboratory under North 24 Parganas Water Supply Division-I, PHE. Dte. , SM/13849 | Support-WQMSP | Supply of Chemicals & Consumables Reagents, Glassware, Standard Reference material & solutions traceble to NIST etc. to comply with NABL ISO / IEC 17025 : 2017 & BIS standards at Mangal Pandey WTP Water Testing Laboratory. | 1469/NWSD-I | 15/09/2023 | 15 | SCIENTIFIC VENTURES | 0.18 | 0.18 | 100 | 100
4596 | NORTH 24 PARGANAS | Barasat Division | Drinking water sample collection & testing through field test kits (FTKs) & uploading charges for the same related to Water Quality monitoring & Surveillance Programme Under JJM , SM/09243 | Support-WQMSP | Fund Transfer. | BP-2022-23-86 | 13/06/2022 | 0 | NORTH 24 PAGRANAS. | 9.24 | 0 | 0 | 0
4597 | NORTH 24 PARGANAS | Barasat Division | Drinking water sample collection & testing through field test kits (FTKs) & uploading charges for the same related to Water Quality monitoring & Surveillance Programme Under JJM , SM/09243 | Support-WQMSP | Find transferred. | BP-2022-23-82 | 13/06/2022 | 0 | BASIRHAT HEALTH DISTRICT. | 10.76 | 0 | 0 | 0
4598 | NORTH 24 PARGANAS | Barasat Division | Drinking water sample collection & testing through field test kits (FTKs) & uploading charges for the same related to Water Quality monitoring & Surveillance Programme Under JJM , SM/09243 | Support-WQMSP | WATER SAMPLE TESTING AND AWARENESS GENERATION CHARGES OF ASHAS' THROUGH FTK | BP-2023-24-330 | 01/09/2023 | 0 | BASIRHAT HEALTH DISTRICT. | 4.27 | 0 | 0 | 0
4599 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Engagement of Laboratory personnel to operate Atomic Absorption Spectrophotometer, Chemist for testing of bottling plant samples (PRANDHARA) & Data entry operator for BIS Documentation works as per IS 14543-2016 protocol including supply, delivery, instal , SM/10734 | Support-WQMSP | Supply,delivery, installation & calibration of 1 no UV-Visible spectrophotometer as per ISO/IEC 17025:2017 at Mangal Pandey Water Treatment Plant Water Testing Laboratory under office of The Executive Engineer, North 24 Pgs. W/S Division-I, P.H.E Dte. | 800/NWSD-I | 29/06/2022 | 15 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.82 | 4.82 | 100 | 100
4600 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Acceptance cum work order for Supply of Chemical & Bacteriological Laboratory personnel for water testing laboratory at A. R. Laboratory cum Inspection Bungalow at Taki, North 24 Parganas under Hasnabad Sub-Division, P.H.E. Dte. For the period 01.01.22 to 30.06.22. | 2209/HSD | 30/12/2021 | 182 | SUNDARBAN ENGINEERS-CO-OPERATIVE-SOCIETY LTD. | 2.51 | 2.51 | 50 | 0
4601 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Acceptance cum Work Order for Engagement of 2 personnel (One Chemist/Bacteriologist and one Lab Assistant) in each of 8 nos Laboratories of PHE Department in North 24 Parganas District of West Bengal under Barasat Division, PHE Dte.[w.e.f. 01.10.2021 to 30.09.2022 i.e for 1(one) year] (Amdanga, Bishnupur, Bagdah, Chandpara, Habra, Basirhat, Gokhna, Haroa Sub-District Lab). | 1959/ BD | 08/10/2021 | 365 | FRONTLINE EX-SERVICEMEN BUREAU. | 24.89 | 14.65 | 57.74 | 0
4602 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-199 | 30/08/2022 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.39 | 0 | 0 | 0
4603 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-160 | 04/08/2022 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
4604 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-162 | 04/08/2022 | 0 | BITHARI DISHA. | 0.39 | 0 | 0 | 0
4605 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-163 | 04/08/2022 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA. | 0.39 | 0 | 0 | 0
4606 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-287 | 23/09/2022 | 0 | BITHARI DISHA. | 0.14 | 0 | 0 | 0
4607 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-400 | 11/11/2022 | 0 | W.B.C.A.D.C | 0.27 | 0 | 0 | 0
4608 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | HONORIUM TO LABORATORY PERSONNEL |  | 12/12/2022 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.27 | 0 | 0 | 0
4609 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-286 | 23/09/2022 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.14 | 0 | 0 | 0
4610 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-288 | 23/09/2022 | 0 | W.B.C.A.D.C | 0.1 | 0 | 0 | 0
4611 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-395 | 11/11/2022 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.39 | 0 | 0 | 0
4612 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-365 | 21/10/2022 | 0 | BITHARI DISHA. | 0.39 | 0 | 0 | 0
4613 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-397 | 11/11/2022 | 0 | YOUTH DEVELOPMENT CENTER | 0.39 | 0 | 0 | 0
4614 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-398 | 11/11/2022 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
4615 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-396 | 11/11/2022 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.39 | 0 | 0 | 0
4616 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-200 | 30/08/2022 | 0 | YOUTH DEVELOPMENT CENTER | 0.39 | 0 | 0 | 0
4617 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-164 | 04/08/2022 | 0 | YOUTH DEVELOPMENT CENTER | 0.39 | 0 | 0 | 0
4618 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-161 | 04/08/2022 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.39 | 0 | 0 | 0
4619 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-366 | 21/10/2022 | 0 | W.B.C.A.D.C | 0.27 | 0 | 0 | 0
4620 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-362 | 21/10/2022 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.39 | 0 | 0 | 0
4621 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-285 | 23/09/2022 | 0 | YOUTH DEVELOPMENT CENTER | 0.14 | 0 | 0 | 0
4622 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-399 | 11/11/2022 | 0 | BITHARI DISHA. | 0.39 | 0 | 0 | 0
4623 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-284 | 23/09/2022 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.14 | 0 | 0 | 0
4624 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-364 | 21/10/2022 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
4625 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-165 | 04/08/2022 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.27 | 0 | 0 | 0
4626 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-159 | 04/08/2022 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.39 | 0 | 0 | 0
4627 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-361 | 21/10/2022 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.39 | 0 | 0 | 0
4628 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-201 | 30/08/2022 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
4629 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-198 | 30/08/2022 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.39 | 0 | 0 | 0
4630 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-203 | 30/08/2022 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.27 | 0 | 0 | 0
4631 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-202 | 30/08/2022 | 0 | BITHARI DISHA. | 0.39 | 0 | 0 | 0
4632 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-283 | 23/09/2022 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.14 | 0 | 0 | 0
4633 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-363 | 21/10/2022 | 0 | YOUTH DEVELOPMENT CENTER | 0.39 | 0 | 0 | 0
4634 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Acceptance cum Work Order for Engagement of Laboratory Personnel (Chemist, Bacteriologist, Laboratory & Sampling Assistants) for District Water Testing Laboratory along with Lab activities under Barasat Division P.H.E. Dte., 24 Pgs(N) for the period 01.01.2022 to 31.12.2022. | 2683/BD | 31/12/2021 | 12 | M/S B.K.ENTERPRISE. | 7.18 | 7.08 | 59.64 | 0
4635 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Engagement of 8 personnel (3 nos Sampling Assistant & 5 nos Lab Attendant) in different water testing Laboratories under Barasat Division, PHE Dte.(Amdanga Sub-District Lab, Bagdah Sub-District Lab, Chandpara Sub-District Lab, Habra Sub-District Lab, Basirhat Sub-District Lab & North 24 Parganas District Lab). [w.e.f. 01.01.2022 to 31.12.2022 i.e. 1(one) year] | 2684/BD | 31/12/2021 | 365 | M/S B.K.ENTERPRISE. | 10.51 | 5.02 | 66.96 | 0
4636 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Engagement of 3 personnel (1 no. Chemist,1 no.Bacteriologist & 1 nos. Lab Assistant) ) for Hingalganj Sub-District Water Testing Laboratory under Barasat Division,PHE Dte. (w.e.f 01.07.2022 to 31.12.2022 i.e for 6(Six) months). Sl.No.01 | 467/BST | 09/06/2022 | 183 | M/S B.K.ENTERPRISE. | 2.74 | 2.65 | 100 | 0
4637 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Continuation Work Order for Engagement of 2 personnel (One Chemist/Bacteriologist and one Lab Assistant) in each of 8 nos Laboratories of PHE Department in North 24 Parganas District of West Bengal under Barasat Division, PHE Dte.[w.e.f. 01.10.2022 to 31.12.2022 i.e for 3 (Three) months] (Amdanga, Bishnupur, Bagdah, Chandpara, Habra, Basirhat, Gokhna, Haroa Sub-District Lab). | 2964/BD | 28/09/2022 | 91 | FRONTLINE EX-SERVICEMEN BUREAU. | 6.01 | 5.68 | 100 | 0
4638 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Supply, erection of Sign Board at 1(One) No. NABL Accredited District Water Testing Laboratory and 6 (nos) NABL Recognized Sub District Water Testing Laboratory managed by NGO's under Barasat Division, P.H.Engg. Dte. | 880/BST | 27/12/2022 | 15 | PURBA SERVICES | 0.63 | 0.63 | 100 | 0
4639 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Supply, erection of Sign Board at 10 (Ten) Nos. NABL Recognized Sub District Water Testing Laboratory under Barasat Division, P.H.Engg. Dte. | 879/BST | 27/12/2022 | 15 | PURBA SERVICES | 0.84 | 0 | 0 | 0
4640 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Engagement of the Laboratory Site to Operate Atomic Absorption Spectrophotometer & Laboratory Assistant for a Period of One Year for the office of the Executive Engineer, Barasat Division, PHE Dte. (Period for 01.01.2022 to 31.12.2022= 12 months). Sl.No.02 | 663/BST | 22/12/2021 | 365 | M/S B.K.ENTERPRISE. | 3.74 | 0.45 | 100 | 0
4641 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Shifting of Hingalganj Sub District Water Testing Laboratory from Hingalganj Block campus to Store Campus of Hingalganj Water Supply Scheme at Sahapur, Village & PO. Hingalganj, North 24 Parganas to make it usable as water testing laboratory Under Barasat Division, P.H. Engineering Dte. | 132/BST | 28/02/2023 | 7 | M/S R.B.S.ENTERPRISE. | 0.95 | 0.95 | 100 | 0
4642 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL | BP-2022-23-480 | 16/12/2022 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
4643 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL | BP-2022-23-481 | 16/12/2022 | 0 | BITHARI DISHA. | 0.39 | 0 | 0 | 0
4644 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | REMUNERATION OF MAY'23 | BP-2023-24-147 | 26/06/2023 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
4645 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel.. | BP-2023-24-111 | 01/06/2023 | 0 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
4646 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel... | BP-2023-24-57 | 12/05/2023 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.35 | 0 | 0 | 0
4647 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel... | BP-2023-24-61 | 12/05/2023 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.35 | 0 | 0 | 0
4648 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL |  | 10/01/2023 | 0 | YOUTH DEVELOPMENT CENTER | 0.39 | 0 | 0 | 0
4649 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  |  | 10/01/2023 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.39 | 0 | 0 | 0
4650 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of NGO Lab personnel & lab maintenance. | BP-2022-23-625 | 27/02/2023 | 0 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
4651 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  |  | 13/03/2023 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
4652 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  |  | 13/03/2023 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.35 | 0 | 0 | 0
4653 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel.. | BP-2023-24-112 | 01/06/2023 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.35 | 0 | 0 | 0
4654 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | REMUNERATION | BP-2023-24-148 | 26/06/2023 | 0 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
4655 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel... | BP-2023-24-58 | 12/05/2023 | 0 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
4656 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL | BP-2022-23-547 | 18/01/2023 | 0 | BITHARI DISHA. | 0.39 | 0 | 0 | 0
4657 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of NGO managed Laboratory Personnel & Lab maintenance. | BP-2022-23-667 | 16/03/2023 | 0 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
4658 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | REMUNERATION OF MAY'23 |  | 22/06/2023 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.35 | 0 | 0 | 0
4659 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | REMUNERATION | BP-2023-24-146 | 26/06/2023 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
4660 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | REMUNERATION OF LABORATORY PERSONNEL FOR THE MONTH JUNE'2023. | BP-2023-24-197 | 11/07/2023 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.45 | 0 | 0 | 0
4661 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL | BP-2022-23-546 | 18/01/2023 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
4662 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of NGO Lab personnel & lab maintenance. | BP-2022-23-626 | 24/02/2023 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.35 | 0 | 0 | 0
4663 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of NGO Lab personnel & lab maintenance. | BP-2022-23-624 | 27/02/2023 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
4664 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  |  | 13/03/2023 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.35 | 0 | 0 | 0
4665 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of NGO managed laboratory personnel & Lab maintenance. | BP-2022-23-669 | 16/03/2023 | 0 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
4666 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of NGO managed Laboratory Personnel & lab maintenance. | BP-2022-23-666 | 16/03/2023 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.35 | 0 | 0 | 0
4667 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | REMUNERATION OF MAY'23 |  | 22/06/2023 | 0 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
4668 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel.. | BP-2023-24-107 | 01/06/2023 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
4669 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel.. | BP-2023-24-108 | 01/06/2023 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.35 | 0 | 0 | 0
4670 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel... | BP-2023-24-56 | 12/05/2023 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
4671 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel... | BP-2023-24-59 | 12/05/2023 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
4672 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL | BP-2022-23-543 | 18/01/2023 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.39 | 0 | 0 | 0
4673 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of NGO Lab personnel & lab maintenance. | BP-2022-23-622 | 27/02/2023 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.35 | 0 | 0 | 0
4674 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of NGO managed Laboratory Personnel & lab maintenance. | BP-2022-23-688 | 16/03/2023 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
4675 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of NGO managed Laboratory Personnel & lab maintenance. | BP-2022-23-670 | 16/03/2023 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.35 | 0 | 0 | 0
4676 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | REMUNERATION OF MAY'23 |  | 22/06/2023 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
4677 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel.. | BP-2023-24-110 | 01/06/2023 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.35 | 0 | 0 | 0
4678 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | REMUNERATION OF LABORATORY PERSONNEL FOR THE MONTH JUNE'2023. | BP-2023-24-192 | 11/07/2023 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.35 | 0 | 0 | 0
4679 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | REMUNERATION OF LABORATORY PERSONNEL FOR THE MONTH JUNE'2023. | BP-2023-24-195 | 11/07/2023 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
4680 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  | BP-2022-23-548 | 18/01/2023 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.27 | 0 | 0 | 0
4681 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL | BP-2022-23-477 | 16/12/2022 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.39 | 0 | 0 | 0
4682 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL | BP-2022-23-544 | 18/01/2023 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.39 | 0 | 0 | 0
4683 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of NGO Lab personnel & lab maintenance. | BP-2022-23-621 | 27/02/2023 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
4684 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of NGO Lab personnel & lab maintenance. | BP-2022-23-623 | 27/02/2023 | 0 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
4685 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  |  | 13/03/2023 | 0 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
4686 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL |  | 18/01/2023 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.27 | 0 | 0 | 0
4687 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of NGO managed Laboratory Personnel & lab maintenance. | BP-2022-23-665 | 16/03/2023 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
4688 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | REMUNERATION | BP-2023-24-149 | 26/06/2023 | 0 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
4689 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel.. | BP-2023-24-109 | 01/06/2023 | 0 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
4690 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel... | BP-2023-24-60 | 12/05/2023 | 0 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
4691 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | REMUNERATION | BP-2023-24-151 | 26/06/2023 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.35 | 0 | 0 | 0
4692 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | REMUNERATION OF LABORATORY PERSONNEL FOR THE MONTH JUNE'2023. | BP-2023-24-193 | 11/07/2023 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
4693 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | REMUNERATION OF LABORATORY PERSONNEL FOR THE MONTH JUNE'2023. | BP-2022-23-196 | 11/07/2023 | 0 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
4694 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL | BP-2022-23-479 | 16/12/2022 | 0 | YOUTH DEVELOPMENT CENTER | 0.39 | 0 | 0 | 0
4695 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL | BP-2022-23-548 | 18/01/2023 | 0 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.27 | 0 | 0 | 0
4696 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  |  | 13/03/2023 | 0 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
4697 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP |  |  | 13/03/2023 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
4698 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | REMUNERATION OF MAY'23 |  | 22/06/2023 | 0 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
4699 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | REMUNERATION OF MAY'23 | BP-2023-24-150 | 26/06/2023 | 0 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
4700 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | REMUNERATION OF LABORATORY PERSONNEL FOR THE MONTH JUNE'2023. | BP-2023-24-194 | 11/07/2023 | 0 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
4701 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Payment of NGO laboratory for the Month of Nov'2023. | BP-2023-24-618 | 20/12/2023 | 0 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
4702 | NORTH 24 PARGANAS | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. , SM/11625 | Support-WQMSP | Acceptance cum work order for Engagement of 16 personnel (2 nos. Chemist, 2 nos. Bacteriologist, 1 no. AAS Operator, 2 nos. Laboratory Assistant,4 nos. Sampling Assistant & 5 nos. Lab Attendent ) in different water testing laboratories under Barasat Division,PHE Dte. (North 24 Pargansa District Lab, Hingalganj Sub-District Lab, Bodai Sub-District Lab., Bagda Sub-District Lab, Chandpara Sub-District Lab, Habra Sub-District Lab, Basirhat Sub-Division Lab ) for 1(one)year (Effect from 01.01.2023 to 31.12.2023.) | 185/BD | 19/01/2023 | 365 | M/S B.K.ENTERPRISE. | 36.04 | 15.46 | 100 | 65
4703 | NORTH 24 PARGANAS | Barasat Arsenic Division | Improvement of IT Infrastructure by providing Desktop computers, printers, copiers and its peripherals for Barasat Arsenic Division & Barasat Arsenic Sub Division Offices, PHE Dte. , SM/17634 | Support-MIS | Supply of 1 no. HP intel Core i5 | 240 | 17/08/2023 | 0 | IONET | 0.83 | 0 | 0 | 0
4704 | NORTH 24 PARGANAS | Barasat Arsenic Division | Improvement of IT Infrastructure by providing Desktop computers, printers, copiers and its peripherals for Barasat Arsenic Division & Barasat Arsenic Sub Division Offices, PHE Dte. , SM/17634 | Support-MIS | Supply of 5 nos. HP intel Core i3 & 2 nos. HP multi function machine. | 239 | 17/08/2023 | 0 | EASY DAY ENTERPRISE | 3.46 | 0 | 0 | 0
4705 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Supply, Installation, Commissioning & Monitoring of INTELLIGENT Disinfection Systems for the complete, desired. Continuous, constant & external power free disinfection of drinking water (via the national JJM approved green technology) supplied through (PW , SM/14516 | Support-WQMSP | Supply, Installation, Commissioning & Monitoring of INTELLIGENT Disinfection Systems for the complete, desired. Continuous, constant & external power free disinfection of drinking water (via the national JJM approved green technology) supplied through (PWSS) maintained by the PHED, Govt. of West Bengal in different tail end sites coupled with the monitoring of dosage strength in-situ VIA ONSITE TESTING OF FREE RESIDUAL CHLORINE (FRC) at PAIKPARA Water Supply Scheme under NWSD-I, PHE. Dte | 93/NWSD-I | 27/01/2023 | 90 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 12.59 | 12.59 | 100 | 100
4706 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Procurement of Chemical & Consumables, Glassware etc. for smooth running of Mangal Pandey WTP Water Testing Laboratory under North 24 Parganas W/S Division-I, PHE Dte., Govt. of W.B. , SM/06633 | Support-WQMSP | Supply and delivery of Chemicals & Consumables Glassware etc. for the smooth running of the laboratory for 1 year for Block level sample, Private Sample & Referral sample testing monitoring under the Executive Engineer, North 24 Pgs. W/S Division-I, P.H.E. Dte. | 63/NWSD-I | 19/01/2021 | 366 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 5.74 | 5.74 | 50 | 0
4707 | NORTH 24 PARGANAS | North 24 Pgs W/S Division I | Procurement of Chemical & Consumables, Glassware etc. for smooth running of Mangal Pandey WTP Water Testing Laboratory under North 24 Parganas W/S Division-I, PHE Dte., Govt. of W.B. , SM/06633 | Support-WQMSP | Engagement of resource person for supervising the protocol/ standard operating procedure/ technical documentation of Water Testing Laboratory Quality management system as per ISO/IEC 17025:2017 including supply of required Reagents, Standard Reference material & solutions traceable to NIST, Chemicals & Consumables, Glassware,Calibration of instruments etc. to comply with NABL accreditation system of Mangal Pandey WTP Water testing laboratory. | 1001/NWSD-I | 08/12/2020 | 182 | LAB ANALYTICS | 4.56 | 4.56 | 50 | 0
4708 | NORTH 24 PARGANAS | Barasat Division | NABL accreditation of North 24 Parganas District laboratory as per ISO/IEC 17025:2017 related to Support Activities under JJM. , SM/08690 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Bagdah Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.07 | 673/BST | 24/12/2021 | 90 | LAB. SOLUTION | 4.83 | 3.66 | 75.66 | 0
4709 | NORTH 24 PARGANAS | Barasat Division | NABL accreditation of North 24 Parganas District laboratory as per ISO/IEC 17025:2017 related to Support Activities under JJM. , SM/08690 | Support-WQMSP | Purchase of Chemical for water testing & NABL accreditation of District Laboratory under Barasat Sub Division, P.H.E. Dte. PART-B Sl No.-2 | 715/BSD | 08/10/2021 | 7 | LAB. SOLUTION | 3.51 | 3.51 | 100 | 0
4710 | NORTH 24 PARGANAS | Barasat Division | NABL accreditation of North 24 Parganas District laboratory as per ISO/IEC 17025:2017 related to Support Activities under JJM. , SM/08690 | Support-WQMSP | Purchase of Chemical for water testing & NABL accreditation of District Laboratory under Barasat Sub Division, P.H.E. Dte. PART-C. | 761/BSD | 25/11/2021 | 7 | LAB. SOLUTION | 3.57 | 2.92 | 100 | 0
4711 | NORTH 24 PARGANAS | Barasat Division | NABL accreditation of North 24 Parganas District laboratory as per ISO/IEC 17025:2017 related to Support Activities under JJM. , SM/08690 | Support-WQMSP | Purchase of Chemical for water testing & NABL accreditation of District Laboratory under Barasat Sub Division, P.H.E. Dte. PART-A Sl No.-1 | 714/BSD | 08/10/2021 | 7 | LAB. SOLUTION | 1.62 | 1.62 | 100 | 0
4712 | NORTH 24 PARGANAS | Barasat Division | NABL accreditation of North 24 Parganas District laboratory as per ISO/IEC 17025:2017 related to Support Activities under JJM. , SM/08690 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Gokna Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.03 | 669/BST | 24/12/2021 | 3 | M/S LAXMI ENTERPRISE | 4.83 | 1.64 | 67.26 | 0
4713 | NORTH 24 PARGANAS | Barasat Division | NABL accreditation of North 24 Parganas District laboratory as per ISO/IEC 17025:2017 related to Support Activities under JJM. , SM/08690 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Haroa Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.02 | 668/BST | 24/12/2021 | 90 | M/S LAXMI ENTERPRISE | 4.83 | 0 | 0 | 0
4714 | NORTH 24 PARGANAS | Barasat Division | NABL accreditation of North 24 Parganas District laboratory as per ISO/IEC 17025:2017 related to Support Activities under JJM. , SM/08690 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Basirhat Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. Sl.No.01 | 667/BST | 24/12/2021 | 90 | M/S LAXMI ENTERPRISE | 4.83 | 3.66 | 100 | 0
4715 | NORTH 24 PARGANAS | Resource | Engagement of implementation support agency (ISA) for implementation of community mobilization and capacity building activities under Jal Jeevan Mission (JJM) support activities at North 24 Parganas District , SM/08991 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the North 24 Pgs . | 446/RS | 02/02/2023 | 212 | IMAGIN | 251.88 | 251.88 | 100 | 50
4716 | NORTH 24 PARGANAS | Resource | Engagement of implementation support agency (ISA) for implementation of community mobilization and capacity building activities under Jal Jeevan Mission (JJM) support activities at North 24 Parganas District , SM/08991 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the North 24 Parganas District. | 2854/RS | 20/05/2022 | 150 | HALDAH EASTERN DEVELOPMENT SOCIETY | 223.78 | 212.77 | 100 | 95
Total | [9 empty] | 742228.25 | 122717.16 | 16.53