## List of issued work order (Rs.
List of issued work order (Rs. in Lakh)
Sl No. | District | Division | Scheme | Scheme Category | Work Name | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SRIPUR Water Supply Scheme , SM/06991 | Retrofitting | FHTC |  | 15/03/2021 | 0 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 10 | 0 | 0 | 0
2 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SRIPUR Water Supply Scheme , SM/06991 | Retrofitting | FHTC |  | 28/01/2022 | 0 | MALLIKA ENTERPRISE | 29 | 0 | 0 | 0
3 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SRIPUR Water Supply Scheme , SM/06991 | Retrofitting | FHTC |  | 28/01/2022 | 0 | MALLIKA ENTERPRISE | 9.92 | 0 | 0 | 0
4 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SRIPUR Water Supply Scheme , SM/06991 | Retrofitting | Providing 1000 nos Functional Household Tap Connection (FHTC) within the command area of Sripur Balagar Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 2203/Hug | 14/12/2021 | 60 | MALLIKA ENTERPRISE | 46.52 | 26.77 | 100 | 0
5 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SRIPUR Water Supply Scheme , SM/06991 | Retrofitting | Material Requisition To Resource Division | 2195/HUG | 14/12/2021 | 0 | Resource Division | 1.59 | 0 | 0 | 0
6 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. , SM/07944 | Retrofitting | FHTC |  | 19/03/2021 | 0 | UNIQUE AGENCY | 20.43 | 0 | 0 | 0
7 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. , SM/07944 | Retrofitting | FHTC |  | 19/03/2021 | 0 | UNIQUE AGENCY | 16 | 0 | 0 | 0
8 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. , SM/07944 | Retrofitting | FHTC |  | 15/03/2021 | 0 | JAGADHATRI CONSTRUCTION | 3 | 0 | 0 | 0
9 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. , SM/07944 | Retrofitting | FHTC |  | 19/03/2021 | 0 | MAA TARA CONSTRUCTION | 4 | 0 | 0 | 0
10 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. , SM/07944 | Retrofitting | FHTC |  | 15/03/2021 | 0 | J B CONSTRUCTION | 2 | 0 | 0 | 0
11 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. , SM/07944 | Retrofitting | FHTC |  | 15/03/2021 | 0 | MAA TARA CONSTRUCTION | 4 | 0 | 0 | 0
12 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. , SM/07944 | Retrofitting | Providing 95 nos. F.H.T.C. in Uttar Rajyadharpur village of Uttar Rajyadharpur and its Adjoining Mouzas Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte.[Block-Serampore-Uttarpara] (Part-C) | 230/SER | 26/02/2021 | 30 | H.R. CONSTRUCTION | 2.63 | 2.38 | 90.39 | 100
13 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. , SM/07944 | Retrofitting | Computer Works | 844312 | 05/10/2021 | 0 | ARATI ENGINEERING | 0.13 | 0 | 0 | 0
14 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. , SM/07944 | Retrofitting | Placement of Fund | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
15 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. , SM/07944 | Retrofitting | Providing 20 nos. Functional Household Tap Connection (FHTC) within Chapsara & Uttar Rajyadharpur Mouzas in Uttar Rajyadharpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 06/SER | 10/04/2023 | 20 | SURAJIT SINGHA RAY | 0.97 | 0.96 | 100 | 100
16 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. , SM/07944 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) within Chapsara & Uttar Rajyadharpur Mouzas in Uttar Rajyadharpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 08/SER | 10/04/2023 | 20 | SURAJIT SINGHA RAY | 0.97 | 0.95 | 100 | 100
17 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. , SM/07944 | Retrofitting | Laying Additional Pipe line for Providing Functional Household Tap Connection (FHTC) within Chapsara & Uttar Rajyadharpur Mouzas in Uttar Rajyadharpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 07/SER | 10/04/2023 | 20 | SURAJIT SINGHA RAY | 0.97 | 0.96 | 100 | 100
18 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. , SM/07944 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within various habitation of Chapsara & Uttar Rajyadharpur Mouzas in Uttar Rajyadharpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte | 09/SER | 10/04/2023 | 20 | SURAJIT SINGHA RAY | 0.97 | 0.96 | 100 | 100
19 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. , SM/07944 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within left out habitation of Chapsara & Uttar Rajyadharpur Mouzas in Uttar Rajyadharpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 10/SER | 10/04/2023 | 20 | SURAJIT SINGHA RAY | 0.97 | 0.92 | 100 | 100
20 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. , SM/07944 | Retrofitting | Extension of pipeline for providing FHTC Connection for Uttar Rajyadharpur Mouza of Uttar Rajyadharpur Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte.[ Block- Serampore-Uttarpara] | 98/SER | 19/06/2023 | 30 | SURAJIT SINGHA RAY | 0.99 | 0.97 | 100 | 100
21 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. , SM/07944 | Retrofitting | Extension of pipeline due to providing FHTC Connection for Chapsara Mouza of Uttar Rajyadharpur Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte.[ Block- Serampore-Uttarpara] | 99/SER | 19/06/2023 | 30 | SURAJIT SINGHA RAY | 1 | 1 | 100 | 100
22 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. , SM/07944 | Retrofitting | Material Requisition To Resource Division | 2198/HUG | 14/12/2021 | 0 | Resource Division | 1.59 | 0 | 0 | 0
23 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. , SM/07956 | Retrofitting | FHTC |  | 21/09/2021 | 0 | M/S RAJKUMAR KHAN | 23.52 | 0 | 0 | 0
24 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. , SM/07956 | Retrofitting | FHTC |  | 30/09/2021 | 0 | M/S S.G. CONSTRUCTION | 18.9 | 0 | 0 | 0
25 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. , SM/07956 | Retrofitting | FHTC |  | 23/07/2021 | 0 | M/S RAJKUMAR KHAN | 32.53 | 0 | 0 | 0
26 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. , SM/07956 | Retrofitting | FHTC |  | 17/08/2021 | 0 | M/S S.G. CONSTRUCTION | 34.67 | 0 | 0 | 0
27 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. , SM/07956 | Retrofitting | FHTC |  | 23/07/2021 | 0 | M/S RAJKUMAR KHAN | 32.53 | 0 | 0 | 0
28 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. , SM/07956 | Retrofitting | Material Requisition To Resource Division | 2686/1/Hug | 01/12/2022 | 0 | Resource Division | 0.34 | 0 | 0 | 0
29 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. , SM/07956 | Retrofitting | FHTC |  | 28/01/2022 | 0 | M/S S.G. CONSTRUCTION | 20 | 0 | 0 | 0
30 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. , SM/07956 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of Tullyan, Keshabchak, Kulteghari, Mohanbati Mouza in KULTEGHORI PWSS, Block Tarakeswar under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | 2852/HUG | 16/12/2022 | 30 | S K ENTERPRISE | 14.97 | 14.45 | 100 | 100
31 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. , SM/07956 | Retrofitting | Material Requisition To Resource Division | 2098/1/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0 | 0
32 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. , SM/07956 | Retrofitting | Repairing of boundary wall at old 1st tubewell site of Kulteghari PWSS Scheme under Chandannagar Sub-Division, PHE Dte. | 917/CHAN | 21/07/2025 | 20 | M/S RAJKUMAR KHAN | 4.17 | 0 | 0 | 0
33 | HOOGHLY | Hooghly Division | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem , SM/06765 | Retrofitting | FHTC |  | 15/02/2021 | 0 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 36 | 0 | 0 | 0
34 | HOOGHLY | Hooghly Division | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem , SM/06765 | Retrofitting | Direct purchase of land for Lakshmipur PWSS | 844321 | 09/11/2021 | 0 | HOOGHLY ZILLA PARISHAD | 11.85 | 0 | 0 | 0
35 | HOOGHLY | Hooghly Division | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem , SM/06765 | Retrofitting | SURVEY |  | 28/01/2022 | 0 | SIKHA ENTERPRISE | 5.1 | 0 | 0 | 0
36 | HOOGHLY | Hooghly Division | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem , SM/06765 | Retrofitting | Construction of 3.6 X 3.0 m Swicth Room with Additional Plinth Height along with laying DI rising main at 3rd boosting tubewell site for Malia Water Supply Scheme under Chandannagar Sub - Division, PHE DTE. | 121/Chan | 24/02/2021 | 45 | M/S S.G. CONSTRUCTION | 4.97 | 4.9 | 100 | 100
37 | HOOGHLY | Hooghly Division | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem , SM/06765 | Retrofitting | Laying pipe line For damaged portion of MALIA Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | 2142/HUG | 26/09/2022 | 20 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 4.95 | 4.95 | 100 | 100
38 | HOOGHLY | Hooghly Division | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem , SM/06765 | Retrofitting | Material Requisition To Resource Division | 2197/HUG | 14/12/2021 | 0 | Resource Division | 1.59 | 0 | 0 | 0
39 | HOOGHLY | Hooghly Division | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem , SM/06765 | Retrofitting | Material Requisition To Resource Division | 1125/6/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
40 | HOOGHLY | Hooghly Division | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem , SM/06765 | Retrofitting | Repair and Renovation Works of R.C.C. Elevated Reservoir of MALIA PWSS under ChandannagarSub-Division of Hooghly Division, P.H.E. Dte. | 4071/HUG | 19/12/2024 | 90 | SHREEOM ENTERPRISE | 9.11 | 0 | 0 | 0
41 | HOOGHLY | Hooghly Division | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) , SM/06766 | Retrofitting | FHTC |  | 21/09/2021 | 0 | M/S R.M. CONSTRUCTION | 16.1 | 0 | 0 | 0
42 | HOOGHLY | Hooghly Division | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) , SM/06766 | Retrofitting | FHTC |  | 21/09/2021 | 0 | M/S RAJKUMAR KHAN | 9.49 | 0 | 0 | 0
43 | HOOGHLY | Hooghly Division | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) , SM/06766 | Retrofitting | FHTC |  | 24/05/2021 | 0 | M/S RAJKUMAR KHAN | 11.84 | 0 | 0 | 0
44 | HOOGHLY | Hooghly Division | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) , SM/06766 | Retrofitting | FHTC BORHAL (Z-I) PWSS | 113/SECC | 19/11/2021 | 35 | S & P ENTERPRISE | 53 | 53 | 100 | 100
45 | HOOGHLY | Hooghly Division | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) , SM/06766 | Retrofitting | FHTC |  | 28/01/2022 | 0 | S & P ENTERPRISE | 55 | 0 | 0 | 0
46 | HOOGHLY | Hooghly Division | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) , SM/06766 | Retrofitting | Providing 2200 nos F.H.T.C. in Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur, Budul Badul Hati, Bhandarhati, Ilampur, Gabtala, Dakshin Dilakash, Mandaran Dilakash, Khurigachhi, Kulakash, Kandar Panagar village of Borhal (Zone- II)and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | 1686/Hug | 17/12/2020 | 182 | S & P CONSTRUCTION | 24.9 | 0 | 0 | 98
47 | HOOGHLY | Hooghly Division | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) , SM/06766 | Retrofitting | Providing 28 nos F.H.T.C. including laying Pipe line in the left out portion of Borhal (Zone-I)and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | 331/Hug | 11/02/2021 | 30 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 31.68 | 0 | 0 | 100
48 | HOOGHLY | Central Drilling | Retrofitting Works for Borhal (Zone-I) PWSS for providing 1236 nos Functional Household Tap Connection(FHTC) , SM/06766 | Retrofitting | SUPPLY & DELIVERY of pea size gravels at site for construction of tube well at BORHAL Z-II, hooghly district under CMSD-I (D), CDD, PHE DTE. | 574/CMSD-I | 30/11/2022 | 7 | C.M. ENTERPRISE | 0.98 | 0.24 | 20.39 | 100
49 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAOTA WATER SUPPLY SCHEME. , SM/08737 | Retrofitting | FHTC |  | 24/09/2021 | 0 | SOUMYADIP DE | 44.16 | 0 | 0 | 0
50 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAOTA WATER SUPPLY SCHEME. , SM/08737 | Retrofitting | Providing 550 nos Functional Household Tap Connection (FHTC) within the left out Mouzas of SAOTA Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | 1090/Hug | 03/06/2022 | 30 | MESSRS FREEDOM CONSTRUCTION | 30.73 | 22.81 | 74.25 | 100
51 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIKUNTHAPUR WATER SUPPLY SCHEME. , SM/08738 | Retrofitting | Survey & Collection of Data through mobile app regarding availability of drinking water sanitation & others prarameters in primary schools, anganwari Centers. | 564/CH | 02/12/2021 | 12 | R.K. TRADERS | 3.64 | 3.64 | 100 | 100
52 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIKUNTHAPUR WATER SUPPLY SCHEME. , SM/08738 | Retrofitting | Providing 111 nos. Functional Household Tap Connection (F.H.T.C) with extention of pipeline at Adak Para, Dulepara & Bagpara Habitation of Baikunthapur Mouza of BAIKUNTHAPUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E. Dte. [Block-Pursurah]. | 615/Arg | 30/08/2022 | 20 | TANISA ENTERPRISE | 4.47 | 4.47 | 99.94 | 100
53 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIKUNTHAPUR WATER SUPPLY SCHEME. , SM/08738 | Retrofitting | Providing 112 nos. Functional Household Tap Connection (F.H.T.C) with extention of pipeline at Mallickpara, Palpara & Janapara Habitation of Baikunthapur Mouza of BAIKUNTHAPUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E. Dte. [Block-Pursurah]. | 616/Arg | 31/08/2022 | 20 | TANISA ENTERPRISE | 4.5 | 4.5 | 99.95 | 100
54 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIKUNTHAPUR WATER SUPPLY SCHEME. , SM/08738 | Retrofitting | Providing 111 nos. Functional Household Tap Connection (F.H.T.C) with extention of pipeline at Adak Para, Dulepara & Bagpara Habitation of Baikunthapur Mouza of BAIKUNTHAPUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E. Dte. [Block-Pursurah]. | 615/Arg | 31/08/2022 | 20 | TANISA ENTERPRISE | 4.47 | 0 | 0 | 100
55 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIKUNTHAPUR WATER SUPPLY SCHEME. , SM/08738 | Retrofitting | Providing 1950 nos F.H.T.C. in Baikunthapur Village of Baikunthapur and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursurah] | 935/Hug | 06/05/2021 | 40 | PRADIP KUMAR ADHYA | 96.28 | 87.64 | 100 | 100
56 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIKUNTHAPUR WATER SUPPLY SCHEME. , SM/08738 | Retrofitting | Providing 325 nos Functional Household Tap Connection (FHTC) with extension of pipeline at Baikunthapur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursurah] | 1309/HUG | 10/05/2023 | 30 | TANISA ENTERPRISE | 20.47 | 20.4 | 100 | 100
57 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KANPUR WATER SUPPLY SCHEME. , SM/09068 | Retrofitting | FHTC |  | 28/01/2022 | 0 | MANISHIKA CONSTRUCTION | 14.88 | 0 | 0 | 0
58 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KANPUR WATER SUPPLY SCHEME. , SM/09068 | Retrofitting | Providing 280 nos Functional Household Tap Connection (FHTC) within the command area of Kanpur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 1996/Hug | 12/11/2021 | 30 | MANISHIKA CONSTRUCTION | 14.98 | 14.88 | 100 | 100
59 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KANPUR WATER SUPPLY SCHEME. , SM/09068 | Retrofitting | Providing 280 nos Functional Household Tap Connection (FHTC) within the command area of KANPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | 46/Hug | 07/01/2022 | 30 | ASIT KUMAR KHANRUI | 7.34 | 0 | 0 | 100
60 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. , SM/09691 | Augmentation | Preparation of DPR for Augmentation of GOGHAT Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I]. | 611/Arg | 31/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.85 | 3.83 | 99.37 | 100
61 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. , SM/09691 | Augmentation | Material Requisition To Resource Division | 424/3/Hug | 07/03/2022 | 0 | Resource Division | 36.05 | 0 | 0 | 0
62 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. , SM/09691 | Augmentation | Material Requisition To Resource Division | 1124/1/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
63 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. , SM/09691 | Augmentation | Material Requisition To Resource Division | 1773/33/Hug | 29/08/2022 | 0 | Resource Division | 0.69 | 0 | 0 | 0
64 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. , SM/09691 | Augmentation | Material Requisition To Resource Division | 1688/6/HUG | 22/08/2022 | 0 | Resource Division | 22.44 | 0 | 0 | 0
65 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. , SM/09691 | Augmentation | Material Requisition To Resource Division | 1385/63/Hug | 15/05/2023 | 0 | Resource Division | 5.34 | 0 | 0 | 0
66 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. , SM/09691 | Augmentation | Material Requisition To Resource Division | 1234/3/Hug | 28/04/2023 | 0 | Resource Division | 1.38 | 0 | 0 | 0
67 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. , SM/09691 | Augmentation | Construction of 1 no.400 CUM capacity R.C.C. Elevated Reservoir with 20 m staging height Over R.C.C Bored Pile Foundation / Raft Foundation as per Departmental Type Drawing Design and Specification including pipeline connection and cost of pipes, specials alongwith Laying Distribution System,Laying CI/D.I pipes & specials for Rising Main pipe line in between T.W NO.-I &II to OHR and for Direct Pumping from Proposed T.W NO.-III to nearest feasible distribution system , Construction of 1 No. 3.6 M X3.00 M Switch Room with Additional Plinth Height without Sanitary and Water Supply Arrangements at 3rd T.W, Construction of Boundary wall at 3 rd T.W Site,Soil Investigation works for constrution of OHR including & Providing 2202 nos, FHTC in Goghat for Augmentation of Goghat Water Supply Scheme under Arambagh Sub-DivisionP.H.E. Dte. of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | 832/Hug | 20/04/2022 | 300 | M/S S.S. ENTERPRISE | 420.51 | 316.67 | 75.31 | 45
68 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. , SM/09691 | Augmentation | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GOGHAT Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | 594/HUG | 22/02/2024 | 60 | SPG ENTERPRISES | 31.67 | 0 | 0 | 0
69 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. , SM/09691 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) ANANDAPUR PWSS-4nos (2) BHADUR(BHAGARBAND) PWSS-6nos (3) GOGHAT PWSS-2nos (4) JOYKRISHNAPUR PWSS-2nos | 816/Arg | 23/08/2024 | 130 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.14 | 100 | 100
70 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. , SM/09691 | Augmentation | Construction of Boundary wall with internal Pathway at HW site of Goghat W/S Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte.Block Arambagh, District:- Hooghly | 4146/HUG | 26/12/2024 | 90 | DHIRENDRA ENGINEERING & CONSTRUCTION | 45.54 | 0 | 0 | 0
71 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Preparation of DPR for Augmentation of Rajbalhat (Zone-I & II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Jangipara] | 289/SER | 18/02/2022 | 20 | SRIJAN ECHOLOGICAL UPLIFTMENT PVT. LTD. | 4.01 | 4.01 | 100 | 100
72 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Preparation of DPR for Augmentation of Rajbalhat (Zone-III) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Jangipara] | 301/SER | 21/02/2022 | 20 | SRIJAN ECHOLOGICAL UPLIFTMENT PVT. LTD. | 2.12 | 1.96 | 92.42 | 100
73 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY KORES RIG MACHINE FOR RAJBALHAT W/S SCHEME, JANGIPARA BLOCK UNDER HOOGHLY DISTRICT, CMSD-II (D), CDD, PHE DTE. | 231/CMSD-II (D) | 20/05/2022 | 15 | M/S PRACHI ENGINEERING | 2.4 | 2.23 | 100 | 100
74 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJBALHAT W/S SCHEME IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 237/CMSD-II (D) | 20/05/2022 | 15 | M/S SAIKAT ENTERPRISE | 2.08 | 1.9 | 100 | 100
75 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | PROVIDING TUBE WELL MATERIALS OF 300 MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL ATY RAJBALHAT W/S SCHEME UNDER HOOGHLY DISTRICT, CMSD-II (D), CDD, PHE DTE. | 233/CMSD-II (D) | 20/05/2022 | 15 | M/S PRACHI ENGINEERING | 2.79 | 2.79 | 100 | 100
76 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | PROVIDING TUBE WELL MATERISLS OF 200 MM NOMINAL DIA. CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJBALHAT W/S SCHEME, UNDER HOOGHLY DISTRICT, CMSD-II (D), CDD, PHE DTE. | 234/CMSD-II (D) | 20/05/2022 | 15 | M/S PRACHI ENGINEERING | 3.87 | 3.41 | 100 | 90
77 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Quatation Bill for New Service Connection of WBSEDCL at Aug. of Rajbalhat W/S. Sch. PH-III | BP-2022-23-114 | 14/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.48 | 0 | 0 | 0
78 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Augmentation of RAJBALHAT Water Supply Scheme with Laying Distribution System, Rising Main, Construction of 3.6 M X3.00 M Switch Room, Boundary wall, Repairing of O.H.R, Bounday wall, Existing Switch Room & FHTC at Jangipara Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | 827/Hug | 20/04/2022 | 180 | DIPTI TRADERS | 458.18 | 444.62 | 97.04 | 70
79 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajbalhat water supply scheme, T.W. No. III, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | 3501/ED | 30/12/2022 | 90 | MAA KALI ENTERPRISE | 10.68 | 10.39 | 97.31 | 100
80 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajbalhat water supply scheme, T.W. No. IV, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | 1640/ED | 11/04/2023 | 90 | SUDIKSHA CONSTRUCTION | 10.68 | 10.39 | 97.31 | 0
81 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto180 Mtr at RAJBALHAT ZONE-III PWSS of SERAMPORE Sub-Division under Hooghly Division, PHE Dte. | 2482/HUG | 21/11/2022 | 30 | R CONSTRUCTION | 12.44 | 11.72 | 100 | 0
82 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Material Requisition To Resource Division | 422/3/Hug | 07/03/2022 | 0 | Resource Division | 39.63 | 0 | 0 | 0
83 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Material Requisition To Resource Division | 1122/6/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
84 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Material Requisition To Resource Division | 1384/17/Hug | 15/05/2023 | 0 | Resource Division | 1.71 | 0 | 0 | 0
85 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Quoation bill for new service connection at Rajbalhat | 151 | 08/02/2023 | 0 | WBSEDCL | 3.85 | 0 | 0 | 0
86 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RAJBALHAT PIPED W/S SCHEME, T.W. No. V, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 456/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 6.94 | 71.57 | 65
87 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Repairing of Damaged Road due to FHTC Works at Northern zone of Rajbalhat W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | 547/SER | 19/09/2024 | 7 | M/S SHIVAM UDYOG | 4.99 | 0 | 0 | 99
88 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Repairing of Damaged Road due to FHTC Works at Southern zone of Rajbalhat W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | 552/SER | 19/09/2024 | 7 | ARUN SEAL AND CO. | 4.99 | 0 | 0 | 99
89 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Repairing of Damaged Road due to FHTC Works at Western zone of Rajbalhat W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | 554/SER | 19/09/2024 | 7 | ARUN SEAL AND CO. | 4.97 | 0 | 0 | 99
90 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Repairing of Damaged Road due to FHTC Works at Eastern zone of Rajbalhat W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | 536/SER | 17/09/2024 | 7 | M/S SHIVAM UDYOG | 4.98 | 0 | 0 | 99
91 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Quotation money deposition for new service connection at Rajbalhat w/s scheme, T.W. No.-V, Dist.-Hooghly under PHE Dte. Application No- 5004123576 Reference ID- 503622497 SM Code- 09694 | 345 | 31/07/2024 | 0 | WBSEDCL | 3.8 | 0 | 0 | 0
92 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Quotation money deposition for new service connection at Rajbalhat w/s scheme, T.W. No.-V, Dist.-Hooghly under PHE Dte. Application No- 100000118583 Reference ID- 860312463 SM Code- 09694 | 480 | 01/10/2024 | 0 | WBSEDCL | 1.63 | 0 | 0 | 0
93 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Providing 200 nos. FHTC of Rajbalhat and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block- Jangipara]. | 3479/HUG | 29/11/2023 | 306 | SADHUKHAN ENTERPRISE | 21.58 | 16.02 | 74.23 | 99
94 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Laying pipe line within Morhal & Rajbalhat Mouza in Rajbalhat W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 59/SER | 20/01/2025 | 7 | ARUN SEAL AND CO. | 5 | 0 | 0 | 0
95 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. , SM/09694 | Augmentation | Shifting of existing water supply pipeline due to widening & strengthening of Box Culvert at neart Brindabon Chak, Badur Chak, Rajbalhat & Hariharpur, Block- Jangipara under Rajbalhat Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte . | 79/SER | 20/01/2025 | 10 | ARUN SEAL AND CO. | 3.98 | 0 | 0 | 0
96 | HOOGHLY | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, , SM/10273 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Providing 105 nos. tap connection at AWC,School, health center,community centers and GP building in Tarakeswar block under Chandannagar Sub-Division, P.H.E. Dte. | 516/chan | 01/11/2021 | 20 | SWASTIK ENTERPRISE | 4.36 | 4.34 | 100 | 0
97 | HOOGHLY | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, , SM/10273 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Providing 125 nos. tap connection at AWC,School, health center,community centers and GP building in Haripal block under Chandannagar Sub-Division, P.H.E. Dte. | 514/chan | 01/11/2021 | 20 | SIKHA ENTERPRISE | 4.69 | 4.68 | 100 | 0
98 | HOOGHLY | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, , SM/10273 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Running water supply arrangement with tube well including Soak Pit & Hand Wash Basin with electric power and pumping system at Sub-Centre & Primary Health Centre having Electrical power connection in Tarakeswar Block (10 Nos), Haripal Block (13 Nos) & Singur Block (17 Nos) under Hooghly Division, P.H.E. Dte. (Total 40 Nos) | 806/Hug | 19/04/2022 | 60 | M/S R.M. CONSTRUCTION | 71.55 | 25.01 | 34.96 | 0
99 | HOOGHLY | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, , SM/10273 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Running water supply arrangement with tube well including Soak Pit & Hand Wash Basin with electric power and pumping system at Sub-Centre & Primary Health Centre having Electrical power connection in Pandua Block (34 Nos) under Hooghly Division, P.H.E. Dte. (Total 34 Nos) | 807/Hug | 19/04/2022 | 45 | M/S RAJKUMAR KHAN | 60.36 | 41.48 | 100 | 35
100 | HOOGHLY | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, , SM/10273 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Material Requisition To Resource Division | 508/Hug | 16/03/2022 | 0 | Resource Division | 35.78 | 0 | 0 | 0
101 | HOOGHLY | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, , SM/10273 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Material Requisition To Resource Division | 509/Hug | 16/03/2022 | 0 | Resource Division | 19.25 | 0 | 0 | 0
102 | HOOGHLY | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, , SM/10273 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Material Requisition To Resource Division | 507/Hug | 16/03/2022 | 0 | Resource Division | 35.26 | 0 | 0 | 0
103 | HOOGHLY | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, , SM/10273 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Running water supply arrangement with tube well including Soak Pit & Hand Wash Basin with electric power and pumping system at Sub-Centre & Primary Health Centre having Electrical power connection in Chandital-I Block (5 Nos), Chanditala-II Block (16 Nos) & Jangipara Block (2 Nos) under Hooghly Division, P.H.E. Dte. (Total 23 Nos) | 822/Hug | 20/04/2022 | 45 | MANISHA ENTERPRISE | 40.95 | 19.45 | 47.49 | 95
104 | HOOGHLY | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 294 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER JANGIPARA, KHANAKUL-I & II, PANDUA, POLBA-DADPUR, PURSURAH, , SM/10273 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Running water supply arrangement with tube well including Soak Pit & Hand Wash Basin with electric power and pumping system at Sub-Centre & Primary Health Centre having Electrical power connection in Chinsurah-Mogra Block (5 Nos) & Balagar Block (10 Nos) under Hooghly Division, P.H.E. Dte. (Total 15 Nos) | 809/Hug | 19/04/2022 | 30 | SURAJIT SINGHA RAY | 26.82 | 20.58 | 100 | 98
105 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area Rameswarpur Water Supply Scheme of Pandua Block Under Hooghly Division, P.H.E Dte , SM/10132 | Retrofitting | Providing 890 nos Functional Household Tap Connection (FHTC) within the Rameswarpur Mouza of Rameswarpur Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | 476/Hug | 10/03/2022 | 40 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 44.49 | 43.85 | 98.56 | 0
106 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area Rameswarpur Water Supply Scheme of Pandua Block Under Hooghly Division, P.H.E Dte , SM/10132 | Retrofitting | Providing 810 nos Functional Household Tap Connection (FHTC) within the Chandpur, Danpur, Keshabbati & Nandigram Mouza of Rameswarpur Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | 477/Hug | 10/03/2022 | 40 | M/S RAJKUMAR KHAN | 40.4 | 36.55 | 90.47 | 0
107 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 800 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF BALI WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. , SM/11003 | Retrofitting | Providing 50 nos Functional Household Tap Connection (FHTC) within Kanaipur, Gohalisanra & Bali Village of Bali Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I] | 711/HUG | 07/04/2022 | 50 | S.D ENTERPRISE (SAMIR KR. DAS) | 2.37 | 2.43 | 100 | 0
108 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 800 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF BALI WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. , SM/11003 | Retrofitting | Material Requisition To Resource Division | 1124/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
109 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 800 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF BALI WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. , SM/11003 | Retrofitting | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of BALI PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 4150/HUG | 26/12/2024 | 90 | M/S T.K.B. CONSTRUCTION | 17.12 | 0 | 0 | 0
110 | HOOGHLY | Hooghly Division | CHAUTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12252 | New | Material Requisition To Resource Division | 1386/40/Hug | 15/05/2023 | 0 | Resource Division | 10.44 | 0 | 0 | 0
111 | HOOGHLY | Hooghly Division | CHAUTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12252 | New | Material Requisition To Resource Division | 1264/17/HUG | 03/05/2023 | 0 | Resource Division | 19.8 | 0 | 0 | 0
112 | HOOGHLY | Hooghly Division | CHAUTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12252 | New | Material Requisition To Resource Division | 3059/Hug | 11/10/2023 | 0 | Resource Division | 2.16 | 0 | 0 | 0
113 | HOOGHLY | Electrical | CHAUTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12252 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chautara water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | 3462/ED | 30/12/2022 | 90 | DAS ENTERPRISE | 20.46 | 16.79 | 82.09 | 35
114 | HOOGHLY | Electrical | CHAUTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12252 | New | Electric quot. of WBSEDCL for New Connection of Choutara T/W-I W/S scheme under ED PHE Dte. (SM/12252) | 909 | 21/03/2024 | 0 | WBSEDCL | 3.43 | 0 | 0 | 0
115 | HOOGHLY | Electrical | CHAUTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12252 | New | Electric quot. of WBSEDCL for New Connection of Choutara T/W-II W/S scheme under ED PHE Dte. (SM/12252) | 908 | 21/03/2024 | 0 | WBSEDCL | 3.41 | 0 | 0 | 0
116 | HOOGHLY | Hooghly Division | CHAUTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12252 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 130.33 | 24.7 | 30
117 | HOOGHLY | Hooghly Division | KAMRAI PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12258 | New | Material Requisition To Resource Division | 1386/29/Hug | 15/05/2023 | 0 | Resource Division | 5.16 | 0 | 0 | 0
118 | HOOGHLY | Hooghly Division | KAMRAI PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12258 | New | Material Requisition To Resource Division | 1264/5/HUG | 03/05/2023 | 0 | Resource Division | 11.27 | 0 | 0 | 0
119 | HOOGHLY | Electrical | KAMRAI PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12258 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kamrai water supply scheme, T.W. No. I & II, Block: Polba-Dadpur, District - Hooghly under Electrical Division, PHE Dte. | 3467/ED | 30/12/2022 | 630 | DEBJYOTI BASU | 22.37 | 22 | 98.36 | 95
120 | HOOGHLY | Electrical | KAMRAI PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12258 | New | Quotation for new service connection at KAMRAI water supply scheme (SM/12258), T/W No. - II, Vill. & P.O. - KAMRAI, Dist. - Hooghly. Ref. Id. - 503562460, Dated - 16-02-2024, Application No. - 5004013396 | 796 | 22/02/2024 | 0 | WBSEDCL | 0.35 | 0 | 0 | 0
121 | HOOGHLY | Electrical | KAMRAI PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12258 | New | Quotation for new service connection at KAMRAI water supply scheme (SM/12258), T/W No. - I, Vill. & P.O. - KAMRAI, Dist. - Hooghly. Ref. Id. - 503562461, Dated - 16-02-2024, Application No. - 5004013365, | 795 | 22/02/2024 | 0 | WBSEDCL | 9.09 | 0 | 0 | 0
122 | HOOGHLY | Hooghly Division | KAMRAI PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12258 | New | Ground Water Based Piped Water Supply Schemes (PWSS) under POLBA-DADPUR Block at DALIMBA, GHATAMPUR, HASNAN, KAMRAI, KUCHPALA, PATUL, UTTAR BABNAN (ZONE-I) & UTTAR BABNAN (ZONE-II) Mouzas including Construction of different capacities R.C.C. Over Head Reservoirs (OHRs), Sinking of Tube Wells, Laying Distribution Systems (LDS), Laying Rising Main Interconnection pipelines, providing Functional Household Tap Connections (FHTCs), Construction of Switch Rooms, Boundary Walls etc. under Hooghly Division P.H.E. Dte. in connection with JJM. | 955/HUG | 30/03/2023 | 887 | GREEN ROYAL INFRA CON PVT LTD | 3672.07 | 154.2 | 58.42 | 15
123 | HOOGHLY | Hooghly Division | KUCHPALA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/12238 | New | Material Requisition To Resource Division | 1386/39/Hug | 15/05/2023 | 0 | Resource Division | 13.21 | 0 | 0 | 0
124 | HOOGHLY | Hooghly Division | KUCHPALA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/12238 | New | Material Requisition To Resource Division | 3059/1/Hug | 11/10/2023 | 0 | Resource Division | 13.21 | 0 | 0 | 0
125 | HOOGHLY | Hooghly Division | KUCHPALA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/12238 | New | Material Requisition To Resource Division | 1264/6/HUG | 03/05/2023 | 0 | Resource Division | 27.64 | 0 | 0 | 0
126 | HOOGHLY | Electrical | KUCHPALA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/12238 | New | Quotation Bill for New Service Connection at Kuchpala W/S. Sch. TW-II | 434 | 21/11/2023 | 0 | WBSEDCL | 5.39 | 0 | 0 | 0
127 | HOOGHLY | Electrical | KUCHPALA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/12238 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kuchpala water supply scheme, T.W. No.- I & II, Block: Polba-Dadpur District- Hooghly under Electrical Division, PHE Dte. | 3496/ED | 30/12/2022 | 90 | M/S DILIP MITRA | 21.59 | 20.76 | 96.14 | 90
128 | HOOGHLY | Electrical | KUCHPALA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/12238 | New | Additional Quotation for new service connection at Kuchpala W/S Sch. , T/W No. - I [SM/12238] , Block - Polba-Dadpur, under Dadpur CCC, WBSEDCL, Ref Id. - 860296974, dt. - 15/04/2024, Application No. - 100000105244 | 74 | 18/04/2024 | 0 | WBSEDCL | 0.42 | 0 | 0 | 0
129 | HOOGHLY | Electrical | KUCHPALA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/12238 | New | Quotation for new service connection at Kuchpala W/S Sch., T/W No. - I, Block - Polba-Dadpur under Dadpur CCC, WBSEDCL, Ref. Id. - 503553646,dt. - 11-03-2024, Application No. - 5003998904 | 887 | 15/03/2024 | 0 | WBSEDCL | 12.43 | 0 | 0 | 0
130 | HOOGHLY | Hooghly Division | KUCHPALA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/12238 | New | Ground Water Based Piped Water Supply Schemes (PWSS) under POLBA-DADPUR Block at DALIMBA, GHATAMPUR, HASNAN, KAMRAI, KUCHPALA, PATUL, UTTAR BABNAN (ZONE-I) & UTTAR BABNAN (ZONE-II) Mouzas including Construction of different capacities R.C.C. Over Head Reservoirs (OHRs), Sinking of Tube Wells, Laying Distribution Systems (LDS), Laying Rising Main Interconnection pipelines, providing Functional Household Tap Connections (FHTCs), Construction of Switch Rooms, Boundary Walls etc. under Hooghly Division P.H.E. Dte. in connection with JJM. | 955/HUG | 30/03/2023 | 887 | GREEN ROYAL INFRA CON PVT LTD | 3672.07 | 366.41 | 84.22 | 15
131 | HOOGHLY | Hooghly Division | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12248 | New | Material Requisition To Resource Division | 1384/1/Hug | 15/05/2023 | 0 | Resource Division | 18.08 | 0 | 0 | 0
132 | HOOGHLY | Hooghly Division | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12248 | New | Material Requisition To Resource Division | 3005/20/Hug | 05/10/2023 | 0 | Resource Division | 5.56 | 0 | 0 | 0
133 | HOOGHLY | Hooghly Division | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12248 | New | Material Requisition To Resource Division | 3060/14/Hug | 11/10/2023 | 0 | Resource Division | 18.08 | 0 | 0 | 0
134 | HOOGHLY | Hooghly Division | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12248 | New | Material Requisition To Resource Division | 79/Hug | 06/01/2023 | 0 | Resource Division | 4.95 | 0 | 0 | 0
135 | HOOGHLY | Electrical | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12248 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bandhpur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | 3482/ED | 30/12/2022 | 90 | ASHUTOSH DAS & CO. | 21.38 | 20.83 | 97.43 | 90
136 | HOOGHLY | Electrical | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12248 | New | Quotation Bill for New Service Connection at Bandhpur W/S. Sch. PH-I | 506 | 08/12/2023 | 0 | WBSEDCL | 0.4 | 0 | 0 | 0
137 | HOOGHLY | Electrical | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12248 | New | Quotation Bill for New Service Connection at Bandhpur W/S. Sch. PH-II | 507 | 08/12/2023 | 0 | WBSEDCL | 12.9 | 0 | 0 | 0
138 | HOOGHLY | Hooghly Division | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12248 | New | PAYMENT TO ROAD RESTORATION TO PWD BANDPUR ICHAPASARA ROAD | BP-2024-25-500 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 8.03 | 0 | 0 | 0
139 | HOOGHLY | Hooghly Division | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12248 | New | BANDHPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHANDITALA-I Block of Serampore Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | 1371/HUG | 15/05/2023 | 865 | S GHOSH AND ASSOCIATES PVT LTD. | 632.36 | 418.44 | 66.17 | 10
140 | HOOGHLY | Electrical | BANDHPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12248 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BANDHPUR water supply scheme, TW No. III, Block: Chanditala-I, District - Hooghly under Electrical Division PHE Dte. | 479/ED | 18/03/2025 | 90 | S.K. ENTERPRISE | 11.3 | 0 | 0 | 0
141 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11466 | Augmentation | Preparation of DPR for Augmentation of Begampur (Zone- I & II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | 481/SER | 14/07/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.02 | 4.02 | 100 | 0
142 | HOOGHLY | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11466 | Augmentation | Quotation bill payment for Begampur w/s scheme |  | 04/11/2022 | 0 | WBSEDCL | 0.68 | 0 | 0 | 0
143 | HOOGHLY | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11466 | Augmentation | Supply, delivery and installation of voltage correcting device and other allied works for Begampur Purba Tajpur w/s scheme, P.H No.- I, Dist- Hooghly under Electrical Division, PHE Dte. | 726/HMSD | 24/03/2023 | 30 | ART CONSORTIUM | 3.24 | 3.24 | 100 | 0
144 | HOOGHLY | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11466 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Begampur water supply scheme, T.W. No. II, Block: Chanditala-II, District: Hooghly under Electrical Division, PHE Dte. | 2043 /ED | 01/12/2022 | 90 | BARISAL TRADING CO. | 10.61 | 10.32 | 97.34 | 0
145 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11466 | Augmentation | Sinking of 1 no 300 X200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at proposed Tube Well Site of BEGAMPUR ZONE-II W/S Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. | 162/HUG | 16/01/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 12.66 | 12.54 | 100 | 0
146 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11466 | Augmentation | Sinking of 1 no 300 X200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at proposed Tube Well Site of BEGAMPUR ZONE-I W/S Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. | 161/HUG | 16/01/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 12.66 | 12.54 | 100 | 0
147 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11466 | Augmentation | Material Requisition To Resource Division | 1384/3/Hug | 15/05/2023 | 0 | Resource Division | 5.77 | 0 | 0 | 0
148 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11466 | Augmentation | Material Requisition To Resource Division | 1107/1/HUG | 17/04/2023 | 0 | Resource Division | 6.16 | 0 | 0 | 0
149 | HOOGHLY | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11466 | Augmentation | Quotation Bill for New Service Connection of WBSEDCL for Begampur Kharsari P-II W/S. Sch. | 145 | 30/01/2023 | 0 | WBSEDCL | 0.68 | 0 | 0 | 0
150 | HOOGHLY | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11466 | Augmentation | payment of quotation of wbsedcl bill Begampur w/s scheme z II PH NO III | 33 | 12/05/2023 | 0 | WBSEDCL | 0.58 | 0 | 0 | 0
151 | HOOGHLY | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11466 | Augmentation | Payment of Wbsedcl Quotation for Begampur W/S Scheme Zone-I, PH-III | 32 | 12/05/2023 | 0 | WBSEDCL | 0.58 | 0 | 0 | 0
152 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11466 | Augmentation | HIRE CHARGES BILL ASSISTANT ENGINEER, SERAMPORE SUB-DIVISION, PHE DTE. | BP-2022-23-404 | 15/12/2022 | 0 | DHIRENDRA ENGINEERING & CONSTRUCTION | 2.36 | 0 | 0 | 0
153 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11466 | Augmentation | Laying Distribution of left out portion of pipeline to restore the water supply and other allied works at Begampur Water Supply Scheme (Zone-I) within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 530/HUG | 20/02/2024 | 15 | SURAJIT SINGHA RAY | 12.25 | 0 | 0 | 0
154 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11466 | Augmentation | Augmentation of BEGAMPUR (ZONE-II) Water Supply Scheme with LDS, Functional Household Tap Connection & Repairing of existing Switch Room at Chanditala II Block under Serampore Sub-Division, of Hooghly Division, PHE Dte. . [2nd call of NIeT No. WBPHE/EE/13/HUG/2022-23 Sl No. 02] SL NO - 06 | 1786/HUG | 26/08/2022 | 30 | SURAJIT SINGHA RAY | 26.17 | 20.01 | 100 | 30
155 | HOOGHLY | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11466 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Begampur water supply scheme, T.W. No.- I & II, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | 826/ED | 14/02/2023 | 90 | CINZANO | 21.49 | 21.49 | 100 | 99
156 | HOOGHLY | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11466 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Begampur Kharsarai water supply scheme, T.W. No. II, Block: Chanditala-II, District: Hooghly under Electrical Division, PHE Dte. | 2043/ED | 01/12/2022 | 90 | BARISAL TRADING CO. | 10.61 | 0.27 | 2.58 | 50
157 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11466 | Augmentation | REGARDING DAMAGE OF PMGSY ROAD 1.027-SONAKA SIDE TO BEGAMPUR PLATFORM VIDE PACKAGE NO.WB08329 IN CHANDITALA-II BLOCK. | BP-2024-25-97 | 02/05/2024 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 9 | 0 | 0 | 0
158 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Begampur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11466 | Augmentation | Augmentation of BEGAMPUR (ZONE-I) Water Supply Scheme with LDS, Functional Household Tap Connection & Repairing of existing Switch Room at Chanditala II Block under Serampore Sub-Division, of Hooghly Division, PHE Dte. | 2320/HUG | 02/11/2022 | 1096 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 245.02 | 192.73 | 78.66 | 25
159 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF PURBO THAKURANICHAK WATER SUPPLY SCHEME (FHTC : 5686 Nos) , SM/12002 | Retrofitting | Providing 1102 nos Functional Household Tap Connection (FHTC) within Paschim Thakurani Chak Mouza of PurbaThakurani Chak (Zone-I)Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I] | 888./HUG | 29/04/2022 | 40 | DIPTI TRADERS | 52.17 | 45.78 | 100 | 0
160 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF PURBO THAKURANICHAK WATER SUPPLY SCHEME (FHTC : 5686 Nos) , SM/12002 | Retrofitting | Laying Rising main with necessary interconnection with T.W., OHR & Distribution System of PURBATHAKURANICHAK ZONE-I Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E. Dte. | 1157/Hug | 20/04/2023 | 30 | SUDIPTA SINHA | 6.7 | 6.02 | 100 | 10
161 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF PURBO THAKURANICHAK WATER SUPPLY SCHEME (FHTC : 5686 Nos) , SM/12002 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of PURBA THAKURANICHAK ZONE-I PWSS under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 1429/HUG | 18/05/2023 | 45 | MA CONSTRUCTION | 28.31 | 26.36 | 100 | 100
162 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF PURBO THAKURANICHAK WATER SUPPLY SCHEME (FHTC : 5686 Nos) , SM/12002 | Retrofitting | Construction of Boundary Wall, Internal Pathway & Land development at the Head Work Site of PURBA THAKURANICHAK ZONE-II Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 2741/HUG | 07/12/2022 | 45 | DILIP KUMAR GHOSH | 13.62 | 13.29 | 100 | 50
163 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF PURBO THAKURANICHAK WATER SUPPLY SCHEME (FHTC : 5686 Nos) , SM/12002 | Retrofitting | Laying Rising main with necessary interconnection with T.W., OHR & Distribution System of PURBATHAKURANICHAK ZONE-II Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E. Dte | 1158/HUG | 20/04/2023 | 30 | RANA ENTERPRISE | 7.31 | 5.72 | 100 | 95
164 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF PURBO THAKURANICHAK WATER SUPPLY SCHEME (FHTC : 5686 Nos) , SM/12002 | Retrofitting | Sinking of 3 nos 300 X200 mm dia Tube Well ,210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of PURBO THAKURANICHAWK , RAJHATO , KAKNAN W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3167/HUG | 10/09/2024 | 250 | MONDAL PRECISION PRIVATE LIMITED | 48.47 | 0 | 0 | 66
165 | HOOGHLY | Hooghly Division | Mamudpur Mini Piped Water Supply Scheme , SM/13658 | New | MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-296 | 19/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 28.71 | 0 | 0 | 0
166 | HOOGHLY | Electrical | Mamudpur Mini Piped Water Supply Scheme , SM/13658 | New | Mini piped Water Supply scheme |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
167 | HOOGHLY | Electrical | Mamudpur Mini Piped Water Supply Scheme , SM/13658 | New | Mini Piped Water Supply Scheme | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0 | 0
168 | HOOGHLY | Hooghly Division | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13501 | New | Material Requisition To Resource Division | 1386/43/Hug | 15/05/2023 | 0 | Resource Division | 3.73 | 0 | 0 | 0
169 | HOOGHLY | Hooghly Division | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13501 | New | Material Requisition To Resource Division | 3057/23/Hug | 11/10/2023 | 0 | Resource Division | 3.73 | 0 | 0 | 0
170 | HOOGHLY | Hooghly Division | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13501 | New | Material Requisition To Resource Division | 127/26/Hug | 13/01/2023 | 0 | Resource Division | 19.18 | 0 | 0 | 0
171 | HOOGHLY | Hooghly Division | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13501 | New | Material Requisition To Resource Division | 2607/2/Hug | 29/08/2023 | 0 | Resource Division | 2.97 | 0 | 0 | 0
172 | HOOGHLY | Hooghly Division | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13501 | New | Material Requisition To Resource Division | 1263/5/Hug | 03/05/2023 | 0 | Resource Division | 18.83 | 0 | 0 | 0
173 | HOOGHLY | Electrical | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13501 | New | Quotation Bill for New Service Connection at Sahapur W/S. Sch. TW-II | 288 | 20/09/2023 | 0 | WBSEDCL | 7.41 | 0 | 0 | 0
174 | HOOGHLY | Electrical | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13501 | New | Quotation Bill for New Service Connection at Sahapur W/S. Sch. TW-I | 287 | 20/09/2023 | 0 | WBSEDCL | 5.55 | 0 | 0 | 0
175 | HOOGHLY | Hooghly Division | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13501 | New | SAHAPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block, District:- Hooghly [NEW SCHEME] | 617/HUG | 03/03/2023 | 270 | M/S RAJKUMAR KHAN | 266.71 | 249.15 | 93.42 | 80
176 | HOOGHLY | Electrical | Sahapur Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13501 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sahapur water supply scheme TW No I and II Block Pursurah, District Hooghly under ED PHED. | 864/ED | 14/02/2023 | 90 | TRIO CONCERN | 20.77 | 20.76 | 100 | 45
177 | HOOGHLY | Hooghly Division | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME , SM/13348 | Augmentation | Repairing of 3.6 mtr. x 3.0 mtr. size existing pump house of Purba Ramnagar PWSS scheme under Hooghly Division, P.H.E. Dte. | 660/CHAN | 27/12/2021 | 30 | SWASTIK ENTERPRISE | 2.75 | 2.58 | 100 | 0
178 | HOOGHLY | Hooghly Division | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME , SM/13348 | Augmentation | Repairing of 5.4 mtr x 3.6 mtr size existing pump house of Purba Ramnagar PWSS scheme under Hooghly Division, P.H.E. Dte. | 534/CHAN | 12/11/2021 | 30 | SWASTIK ENTERPRISE | 2.96 | 2.94 | 100 | 0
179 | HOOGHLY | Hooghly Division | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME , SM/13348 | Augmentation | Material Requisition To Resource Division | 2686/4/Hug | 01/12/2022 | 0 | Resource Division | 0.32 | 0 | 0 | 0
180 | HOOGHLY | Hooghly Division | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME , SM/13348 | Augmentation | Route survey Design drawing & DPR preparation of Purba Ramnagar PWSS under Chandannagar Sub-Division, P.H.E. Dte | 272/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.24 | 4.03 | 100 | 0
181 | HOOGHLY | Hooghly Division | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME , SM/13348 | Augmentation | Material Requisition To Resource Division | 1383/42/Hug | 15/05/2023 | 0 | Resource Division | 27.81 | 0 | 0 | 0
182 | HOOGHLY | Hooghly Division | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME , SM/13348 | Augmentation | Material Requisition To Resource Division | 1235/14/Hug | 28/04/2023 | 0 | Resource Division | 71.65 | 0 | 0 | 0
183 | HOOGHLY | Hooghly Division | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME , SM/13348 | Augmentation | Material Requisition To Resource Division | 3058/26/Hug | 11/10/2023 | 0 | Resource Division | 28 | 0 | 0 | 0
184 | HOOGHLY | Electrical | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME , SM/13348 | Augmentation | Purba Ramnagar w/s scheme,P H No 3 | 275 | 08/09/2023 | 0 | WBSEDCL | 4.62 | 0 | 0 | 0
185 | HOOGHLY | Hooghly Division | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME , SM/13348 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, CHANDANNAGORE SUB-DIVISION, PHE DTE. | BP-2022-23-546 | 21/02/2023 | 0 | GOUR KUMAR DAS | 0.65 | 0 | 0 | 0
186 | HOOGHLY | Electrical | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME , SM/13348 | Augmentation | Purba Ramnagar w/s scheme,P H NO 4 | 274 | 08/09/2023 | 0 | WBSEDCL | 5.06 | 0 | 0 | 0
187 | HOOGHLY | Electrical | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME , SM/13348 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Purba Ramnagar water supply scheme TW No I and II Block Tarakeswar, District Hooghly under ED PHED. | 853/ED | 14/02/2023 | 90 | C.M. ENTERPRISE | 21.49 | 20.88 | 97.14 | 85
188 | HOOGHLY | Electrical | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME , SM/13348 | Augmentation | Purba Ramnagar w/s scheme,P H No . 3 |  | 05/09/2023 | 0 | WBSEDCL | 4.62 | 0 | 0 | 0
189 | HOOGHLY | Hooghly Division | AUGMENTATION OF PURBA RAMNAGAR PIPED WATER SUPPLY SCHEME , SM/13348 | Augmentation | AUGMENTATION of PURBA RAMNAGAR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Repairing of Existing Switch Rooms, Boundary Wall of existing T.W Sites, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under TARAKESWAR Block, District:- Hooghly [AUGMENTATION SCHEME] [2nd Call of WBPHE/EE/33/HUG/2022-23(Sl No. 4)] | 2062/HUG | 17/07/2023 | 822 | BANSBERIA CONSTRUCTION CO. | 789.94 | 708.35 | 89.67 | 55
190 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13411 | Augmentation | Quotation bill for Sripur W/S. Sch. | 108 | 18/11/2022 | 0 | WBSEDCL | 2.96 | 0 | 0 | 0
191 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13411 | Augmentation | Quatation bill for Sripur W/S. Sch. PH-III |  | 10/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.96 | 0 | 0 | 0
192 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13411 | Augmentation | Construction of 3.60 m X 3.00 m Switch Room with Sanitary and Water Supply & Sanitation arrangement at 3rd T/W Site of SRIPUR (PANDUA) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | 725/CH | 23/08/2022 | 45 | TOTON MONDAL | 4.99 | 4.99 | 100 | 0
193 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13411 | Augmentation | "Supply, Delivery & Installation of S/P/M & other E/M equipments etc. for Sripur W/S. Sch. TW-III RA-I" | 1320/ED | 17/08/2022 | 90 | SWAPAN ENTERPRISE | 7.37 | 7.07 | 100 | 0
194 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13411 | Augmentation | Withdrawing of 10 HP submersible pumping machinery and installation of standby pumping machinery and allied electrical/mechanical works at Sripur w/s scheme, Dist- Hooghly under Electrical Division, PHE Dte. | 1991/HMSD | 10/11/2022 | 21 | KUSHANI ENTERPRISE | 2.45 | 2.36 | 100 | 0
195 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13411 | Augmentation | Material Requisition To Resource Division | 3004/2/Hug | 05/10/2023 | 0 | Resource Division | 37.77 | 0 | 0 | 0
196 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13411 | Augmentation | Supply Xerox Paper ofice of the EE PHE Dte | 253 | 31/03/2023 | 0 | BARRACKPORE CENTRAL ZONE | 0.09 | 0 | 0 | 0
197 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13411 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of different PWSS under PANDUA Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | 2429/HUG | 11/08/2023 | 30 | GHOSH CONSTRUCTION | 42.89 | 37.8 | 100 | 80
198 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13411 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SRIPUR PIPED W/S SCHEME, T.W. No. IV, Block: Pandua, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1193/ED | 14/06/2024 | 90 | SUBHRA ENTERPRISE | 10.75 | 8.25 | 76.76 | 60
199 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13411 | Augmentation | Construction of Boundary Wall ,Laying of C.I/D.I pipes & specials for connection of Proposed T.W with distribution system , FHTC of SRIPUR PANDUAH W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | 1338/HUG | 11/05/2023 | 30 | AMBIAN INFRASTRUTTURE | 16.02 | 16.02 | 100 | 85
200 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13411 | Augmentation | Sinking of 2 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) At KULIHANDA & SRIPUR W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. | 2409/HUG | 11/08/2023 | 30 | OSMAN SEKH | 32.34 | 16.14 | 100 | 100
201 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13411 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Sripur village under Pandua Block, Panpara village of Pandua Block and Akna village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | 263/CH | 14/03/2024 | 7 | ASHA ENTERPRISE | 0.95 | 0.95 | 100 | 100
202 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13411 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Sripur Pandua (Retrofit) PWSS 2. Digsui Heora Z-I (Retrofit) PWSS 3. Digsui Heora Z-II (Retrofit) PWSS | 213/CH | 29/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.48 | 0.48 | 100 | 45
203 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13411 | Augmentation | Quotation money deposition for new service connection at Sripur w/s scheme, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004132708 Reference ID- 503625865 SM Code- 13411 | 104 | 06/05/2024 | 0 | WBSEDCL | 3.47 | 0 | 0 | 0
204 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13411 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-3 of Sripur PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 267/CH | 20/02/2025 | 10 | ASHA ENTERPRISE | 1.66 | 0 | 0 | 0
205 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR (PANDUA) PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13411 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Sripur PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 246/CH | 19/02/2025 | 10 | ASHA ENTERPRISE | 2.73 | 0 | 0 | 0
206 | HOOGHLY | Hooghly Division | Par adra mini pipe water supply scheme , SM/13559 | New | Material Requisition To Resource Division | 1385/47/Hug | 15/05/2023 | 0 | Resource Division | 0.58 | 0 | 0 | 0
207 | HOOGHLY | Electrical | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. , SM/13347 | New | Rectification & overhualing of VCB Panel, LT Panel, ATS Panel, AVR and transformer at BS-I, Madhabpur under (N) 24 Pgs. Arsenic Area W/S. Sch. | 145/AE-I/ED | 18/02/2022 | 90 | ORIENTAL ENGINEERING CO. | 1.9 | 0 | 0 | 0
208 | HOOGHLY | Electrical | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. , SM/13347 | New | Supply & Installation of NRV and other allied works at BS-I, Madhabpur under (N) 24 Pgs. Arsenic Area W/S. Sch. | 1009/AE-I/ED | 13/08/2021 | 90 | ORIENTAL ENGINEERING CO. | 4.56 | 0 | 0 | 0
209 | HOOGHLY | Electrical | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. , SM/13347 | New | Supply & Installation of Butterfly valve for pump set no-2 at BS-I, Madhabpur under (N) 24 Pgs. Arsenic Area W/S. Sch. | 42/AE-I/ED | 14/01/2022 | 90 | ORIENTAL ENGINEERING CO. | 4.56 | 0 | 0 | 0
210 | HOOGHLY | Electrical | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. , SM/13347 | New | Supply & Installation of Butterfly valve & Check valve for pump set no-3 at BS-I, Madhabpur under (N) 24 Pgs. Arsenic Area W/S. Sch. | 43/AE-I/ED | 14/01/2022 | 90 | ORIENTAL ENGINEERING CO. | 4.56 | 0 | 0 | 0
211 | HOOGHLY | Hooghly Division | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. , SM/13347 | New | Material Requisition To Resource Division | 1384/14/Hug | 15/05/2023 | 0 | Resource Division | 11.08 | 0 | 0 | 0
212 | HOOGHLY | Hooghly Division | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. , SM/13347 | New | Material Requisition To Resource Division | 3060/12/Hug | 11/10/2023 | 0 | Resource Division | 11.08 | 0 | 0 | 0
213 | HOOGHLY | Hooghly Division | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. , SM/13347 | New | Material Requisition To Resource Division | 79/10/Hug | 06/01/2023 | 0 | Resource Division | 11.08 | 0 | 0 | 0
214 | HOOGHLY | Electrical | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. , SM/13347 | New | Madhavpur w/s scheme,P H No 1 | 273 | 08/09/2023 | 0 | WBSEDCL | 3.71 | 0 | 0 | 0
215 | HOOGHLY | Electrical | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. , SM/13347 | New | Madhavpur w/s scheme,P H No 2 | 554 | 21/12/2023 | 0 | WBSEDCL | 6.73 | 0 | 0 | 0
216 | HOOGHLY | Hooghly Division | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. , SM/13347 | New | Madhabpur Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHANDITALA-II Block, District:- Hooghly. | 326/HUG | 03/02/2023 | 788 | ARUN SEAL AND CO. | 443.64 | 229.81 | 51.8 | 50
217 | HOOGHLY | Hooghly Division | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. , SM/13347 | New | CONSTRUCTION OF 2Nos. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT MADHABPUR HW SITE AND KUMIRMORA Z-I 2ND TW SITE UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E DTE. | 430/SER | 31/07/2024 | 15 | SUNITI MAIRA | 0.68 | 0.66 | 100 | 95
218 | HOOGHLY | Electrical | MADHABPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY. , SM/13347 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Madhabpur water supply scheme TW No I and II Block Chanditala II District Hooghly under ED PHED. | 862/ED | 14/02/2023 | 899 | NEW RANBEE ENGINEERING | 20.36 | 17.07 | 84.01 | 40
219 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF GHOSHPUR PWSS FOR PROVIDING 4709 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE , SM/13354 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in GHOSHPUR PWSS, Block KHANAKUL-I under Arambag Sub-Division of Hooghly Division P.H.E Dte. | 2100/HUG | 19/07/2023 | 587 | GHOSH BROTHERS | 95.26 | 79.36 | 83.31 | 80
220 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF GHOSHPUR PWSS FOR PROVIDING 4709 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE , SM/13354 | Retrofitting | Supply of 200 mm dia CD pipe for Sinking of Tubewell at Ghoshpur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 470/Arg | 05/07/2023 | 15 | MAYA CONSTRUCTION | 0.97 | 0.97 | 100 | 100
221 | HOOGHLY | Hooghly Division | GROUND WATER BASED DAHAR KUNDU (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/14983 | New | Material Requisition To Resource Division | 3057/3/Hug | 11/10/2023 | 0 | Resource Division | 8.14 | 0 | 0 | 0
222 | HOOGHLY | Hooghly Division | GROUND WATER BASED DAHAR KUNDU (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/14983 | New | Material Requisition To Resource Division | 1234/16/Hug | 28/04/2023 | 0 | Resource Division | 8.15 | 0 | 0 | 0
223 | HOOGHLY | Electrical | GROUND WATER BASED DAHAR KUNDU (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/14983 | New | Quotation of New Service Connection for Dahar Kundu w/s Scheme,Zone-I,TW No-II Block-Arambag,Dist-Hooghly under Electrical Division PHE Dte. | 312 | 27/09/2023 | 0 | WBSEDCL | 8.01 | 0 | 0 | 0
224 | HOOGHLY | Electrical | GROUND WATER BASED DAHAR KUNDU (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/14983 | New | Quotation Bill for New Service Connection at Daharkundu W/S. Sch. Z-I. TW-I | 354 | 12/10/2023 | 0 | WBSEDCL | 4.97 | 0 | 0 | 0
225 | HOOGHLY | Electrical | GROUND WATER BASED DAHAR KUNDU (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/14983 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dahar Kundu water supply scheme, Zone-I, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 765/ED | 09/02/2023 | 90 | POLYCON ENGINEERS | 20.39 | 20.22 | 100 | 30
226 | HOOGHLY | Hooghly Division | GROUND WATER BASED DAHAR KUNDU (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/14983 | New | DAHAR KUNDU(ZONE-I) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under ARAMBAG Block, District:- Hooghly.[NEW SCHEME] | 1567/HUG | 29/05/2023 | 764 | ASIA CONSTRUCTION | 365.13 | 209.37 | 57.34 | 30
227 | HOOGHLY | Hooghly Division | GROUND WATER BASED DAHAR KUNDU (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/14983 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) MAYAPUR PWSS (Z-II)- 1no¿s (2) BALUNDI PWSS - 4no¿s (3) BHALIA PWSS (Z-I)- 2 no¿s (4) BHALIA PWSS (Z-II)- 1 no¿s (5) DAHARKUNDU PWSS (Z-I)- 2 no¿s, (6) DAHARKUNDU PWSS (Z-II)- 2 no¿s, (7) GOBINDANAGAR PWSS(Z-I) ¿2 no¿s | 1150/Arg | 10/12/2024 | 31 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0 | 0 | 0
228 | HOOGHLY | Hooghly Division | UTTAR BABNAN (ZONE-I) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14467 | New | Material Requisition To Resource Division | 1264/8/HUG | 03/05/2023 | 0 | Resource Division | 48.05 | 0 | 0 | 0
229 | HOOGHLY | Hooghly Division | UTTAR BABNAN (ZONE-I) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14467 | New | Material Requisition To Resource Division | 3059/2/Hug | 11/10/2023 | 0 | Resource Division | 1.68 | 0 | 0 | 0
230 | HOOGHLY | Electrical | UTTAR BABNAN (ZONE-I) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14467 | New | Quotation Bill for New Service Connection at Uttarbabnan W/S. Sch. TW-II, Z-I | 630 | 08/01/2024 | 0 | WBSEDCL | 24.56 | 0 | 0 | 0
231 | HOOGHLY | Hooghly Division | UTTAR BABNAN (ZONE-I) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14467 | New | ROAD RESTORATION PAYMENT TO PWD FOR BETA PORABAZAR ROAD | BP-2024-25-499 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 26.22 | 0 | 0 | 0
232 | HOOGHLY | Electrical | UTTAR BABNAN (ZONE-I) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14467 | New | Quotation Bill for New Service Connection at Uttarbabnan W/S. Sch. TW-I | 631 | 08/01/2024 | 0 | WBSEDCL | 0.35 | 0 | 0 | 0
233 | HOOGHLY | Electrical | UTTAR BABNAN (ZONE-I) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14467 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Uttar Babnan water supply scheme, Zone-I, T.W. No.- I, II & III and Zone-II, T.W. No.- I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | 932/ED | 22/02/2023 | 900 | DEY ENTERPRISE | 50.9 | 0 | 0 | 90
234 | HOOGHLY | Hooghly Division | UTTAR BABNAN (ZONE-I) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14467 | New | Ground Water Based Piped Water Supply Schemes (PWSS) under POLBA-DADPUR Block at DALIMBA, GHATAMPUR, HASNAN, KAMRAI, KUCHPALA, PATUL, UTTAR BABNAN (ZONE-I) & UTTAR BABNAN (ZONE-II) Mouzas including Construction of different capacities R.C.C. Over Head Reservoirs (OHRs), Sinking of Tube Wells, Laying Distribution Systems (LDS), Laying Rising Main Interconnection pipelines, providing Functional Household Tap Connections (FHTCs), Construction of Switch Rooms, Boundary Walls etc. under Hooghly Division P.H.E. Dte. in connection with JJM. | 955/HUG | 30/03/2023 | 887 | GREEN ROYAL INFRA CON PVT LTD | 3672.07 | 348.41 | 65.55 | 15
235 | HOOGHLY | Electrical | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14116 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mahisgot water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-I District- Hooghly under Electrical Division, PHE Dte. | 769/ED | 09/02/2023 | 90 | M/S S R ENTERPRISE | 20.27 | 0 | 0 | 0
236 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14116 | New | Material Requisition To Resource Division | 3057/4/Hug | 11/10/2023 | 0 | Resource Division | 12.4 | 0 | 0 | 0
237 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14116 | New | Material Requisition To Resource Division | 127/Hug | 13/01/2023 | 0 | Resource Division | 35.96 | 0 | 0 | 0
238 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14116 | New | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of MAHISHGOT Z-II Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 3659/HUG | 13/11/2024 | 90 | MAA BUNAMATA ENTERPRISE | 16.12 | 0 | 0 | 0
239 | HOOGHLY | Electrical | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14116 | New | Quotation of New Service Connection for Mahisgot w/s Scheme,Zone-II,TW No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/14116) Application No-5004015913 Reference Id-503563370 | 755 | 16/02/2024 | 0 | WBSEDCL | 5.89 | 0 | 0 | 0
240 | HOOGHLY | Electrical | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14116 | New | Quotation of New Service Connection for Mahisgot w/S Scheme,Zone-II,PH No-II Block-Khanakul-I Dist-Hooghly under ED,PHE Dte. (SM/14116) Application No-5004068599 Reference Id-503594190 | 892 | 18/03/2024 | 0 | WBSEDCL | 4.28 | 0 | 0 | 0
241 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14116 | New | MAHISGOT (ZONE-I), MAHISGOT (ZONE-II), POL, RADHABALLAVPUR (ZONE-I), UDAYPUR, UDNA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte | 3139/HUG | 16/10/2023 | 808 | MACKINTOSH BURN LIMITED | 3480.01 | 301.94 | 62.12 | 45
242 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAHISGOT (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14116 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0 | 0
243 | HOOGHLY | Hooghly Division | Shyampur Mini Piped Water Supply Scheme , SM/13421 | New | Material Requisition To Resource Division | 1385/24/Hug | 15/05/2023 | 0 | Resource Division | 0.57 | 0 | 0 | 0
244 | HOOGHLY | Hooghly Division | Shyampur Mini Piped Water Supply Scheme , SM/13421 | New | REQUISITION OF FUND FOR SAJAL GRAM SCHEME |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.12 | 0 | 0 | 0
245 | HOOGHLY | Hooghly Division | Shyampur Mini Piped Water Supply Scheme , SM/13421 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME |  | 23/06/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 33.47 | 0 | 0 | 0
246 | HOOGHLY | Hooghly Division | Shyampur Mini Piped Water Supply Scheme , SM/13421 | New | MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-342 | 31/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 31.93 | 0 | 0 | 0
247 | HOOGHLY | Electrical | Shyampur Mini Piped Water Supply Scheme , SM/13421 | New | Mini Piped water Supply Scheme | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
248 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | Construction of 1 no.150 CUM capacity R.C.C. Elevated Reservoir with 20 m staging height Over R.C.C Bored Pile Foundation/Raft Foundation as per Departmental Type Drawing Design and Specification including pipeline connection and cost of pipes, specials alongwith Laying Distribution System & Construction of 5.4 M X3.65 M Switch Room with Additional Plinth Height, Sanitary and Water Supply Arrangements including Soil Investigation works for construction of OHR at Head Work Site for BHANDARHATI W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | 1143/Hug | 29/06/2021 | 304 | UNIQUE AGENCY | 117.52 | 39.11 | 100 | 0
249 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | Construction of 5 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at BHANDARHATI (1NO.), PURBA THAKURANI CHAK (2NOS.), HARISH CHAK (2NOS.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3268/HUG | 08/11/2023 | 60 | KRISHNA MONDAL | 58.98 | 0 | 0 | 0
250 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BHANDARHATI (1NO.),PURBA THAKURANI CHAK( 2NOS.), HARISH CHAK( 2NOS.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3474/HUG | 29/11/2023 | 45 | CIVIL CRAFT | 88.67 | 0 | 0 | 0
251 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | Preparation of DPR for Augmentation of Bhanderhati Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | 66/CH | 27/01/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.77 | 4.77 | 100 | 0
252 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | Additional Survey work for Preparation of DPR for Augmentation of Bhanderhati Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | 67/CH | 27/01/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.35 | 0.31 | 100 | 0
253 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | Construction of approach road at Head work Site of BHANDARHATI Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E.Dte. [Block - Arambagh] | 734/Arg | 29/09/2022 | 15 | UNIQUE AGENCY | 3.67 | 3.62 | 100 | 0
254 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | Laying of pipe line for left out portion within command area of Samta, Dakshin Para, Kazi Para, Paschim Para habitation of Samta Village, Tnaksal, Dakshin Para habitation of Takshal Village & Balaichak, Kaji Para habitation of Balai Chak Village under BHANDARHATI Water Supply Scheme to facilate the FHTC under JALASWAPNA Programme of Arambagh Sub-Division, P.H.E. Dte., Dist-. Hooghly. [Block - Arambagh] | 736/Arg | 29/09/2022 | 25 | UNIQUE AGENCY | 1.59 | 1.59 | 100 | 0
255 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | Material Requisition To Resource Division | 226/3/Hug | 24/01/2023 | 0 | Resource Division | 60.58 | 0 | 0 | 0
256 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | Material Requisition To Resource Division | 1386/37/Hug | 15/05/2023 | 0 | Resource Division | 22.62 | 0 | 0 | 0
257 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | "Quotation Bill for New Service Connection at Bhandarhati W/S. Sch. TW-III" | 253 | 05/09/2023 | 0 | WBSEDCL | 6.25 | 0 | 0 | 0
258 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | Quotation for new service connection charge at Bhanderhati PWSS, TW - IV | 453 | 01/12/2023 | 0 | WBSEDCL | 4.22 | 0 | 0 | 0
259 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | "Quotation Bill for New Service Connection at Bhandarhati TW-III" | 311 | 29/09/2023 | 0 | WBSEDCL | 0.11 | 0 | 0 | 0
260 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | Quotation Bill for New Service Connection at Bhandarhati TW-III |  | 11/09/2023 | 0 | WBSEDCL | 6.36 | 0 | 0 | 0
261 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | Laying C.I/D.I pipes & specials for rising main pipe line in between T.W No. -I & II to O.H.R and interconnection with distribution system including allied work of BHANDARHATI W/S Scheme under Arambagh Sub - Division P.H.E. Dte. | 441/Arg | 22/06/2022 | 30 | UNIQUE AGENCY | 3.93 | 0 | 0 | 99
262 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in DASGHARA II GP of DHANIAKHALI Block. | 252/CH | 12/03/2024 | 30 | TOTON MONDAL | 4.99 | 4.95 | 100 | 90
263 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | ROAD RESTORATION PAYMENT TO PWD FOR CHINSURAH DHANIAKHALI | BP-2024-25-499 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 18.03 | 0 | 0 | 0
264 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | Quotation of New Service Connection for Bhandarhati w/s Scheme,PH No-V, Block-Dhaniakhali Dist-Hooghly under electrical division,PHE Dte.(SM/14040)Application No-5004059159 Reference Id-503589837. | 97 | 06/05/2024 | 0 | WBSEDCL | 10.74 | 0 | 0 | 0
265 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | ROAD RESTORATION PAYMENT TO PWD FORHARIPAL DHANIAKHALI ROAD | BP-2024-25-499 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 45.52 | 0 | 0 | 0
266 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | Electric quot. of WBSEDCL for Bhanderhati T/W-V W/S scheme under ED PHE Dte. (SM/14040) | 291 | 15/07/2024 | 0 | WBSEDCL | 1.77 | 0 | 0 | 0
267 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | Quotation for New Service Connection at Bhandarhati W/S. Sch. TW-I | 667 | 15/01/2024 | 0 | WBSEDCL | 8.52 | 0 | 0 | 0
268 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | ROAD RESTORATION PAYMENT TO PWD FOR HARIPAL BHANDARHATI ROAD | BP-2024-25-499 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 13.02 | 0 | 0 | 0
269 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bhandarhati water supply scheme, T.W. No.- I, II, III & IV, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | 828/ED | 14/02/2023 | 760 | EASTERN INDIA SALES & SERVICE | 42.97 | 10.44 | 24.3 | 25
270 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | BHANDARHATI ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr.Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site under DHANIAKHALI Block under Chinsurah Sub-Division, PHE Dte, District:- Hooghly [AUGMENTATION SCHEME] | 1357/HUG | 12/05/2023 | 842 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 302.26 | 104.6 | 34.61 | 50
271 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BHANDARHATI , SM/14040 | Augmentation | Sinking of Tube Well, Rising Main, Construction of switch-room & boundary wall at Proposed TW site, Repairing of Switch Room & Boundary wall, Repairing of OHR in Zone-I & FHTC within Zone-I & II For Augmentation of BHANDARHATI ZONE-I &II Piped Water Supply Scheme under DHANIAKHALI Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte, District:- Hooghly [AUGMENTATION SCHEME] | 845/HUG | 23/03/2023 | 916 | DAS ENTERPRISE | 184.79 | 85.5 | 47.18 | 85
272 | HOOGHLY | Hooghly Division | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly , SM/13333 | New | Material Requisition To Resource Division | 1385/55/Hug | 15/05/2023 | 0 | Resource Division | 12.9 | 0 | 0 | 0
273 | HOOGHLY | Hooghly Division | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly , SM/13333 | New | Material Requisition To Resource Division | 3057/15/Hug | 11/10/2023 | 0 | Resource Division | 12.71 | 0 | 0 | 0
274 | HOOGHLY | Hooghly Division | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly , SM/13333 | New | Material Requisition To Resource Division | 1234/43/Hug | 28/04/2023 | 0 | Resource Division | 30.64 | 0 | 0 | 0
275 | HOOGHLY | Electrical | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly , SM/13333 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Mostafapur water supply scheme, T.W. No. I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte | 326/ED | 21/02/2024 | 90 | M.S ENTERPRISE | 21.9 | 0 | 0 | 0
276 | HOOGHLY | Electrical | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly , SM/13333 | New | Quotation of New Service Connection for Mostafapur w/s scheme,TW No-II Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13333) Application No-5004151915 Reference Id-503634018 | 357 | 07/08/2024 | 0 | WBSEDCL | 8.49 | 0 | 0 | 0
277 | HOOGHLY | Electrical | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly , SM/13333 | New | Quotation of New Service Connection for Mostafapur w/s Scheme,PH No-I Block-Khanakul-II District-Hooghly under Electrical Division,PHE Dte.(SM/13333) Application No-5004136071 Reference Id-503627505. | 211 | 11/06/2024 | 0 | WBSEDCL | 3.42 | 0 | 0 | 0
278 | HOOGHLY | Hooghly Division | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly , SM/13333 | New | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 90.27 | 16.48 | 50
279 | HOOGHLY | Hooghly Division | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly , SM/13333 | New | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at POL (2Nos.), MOSTAFAPUR (2Nos.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3434/HUG | 03/10/2024 | 360 | DIBYENDU DHARA | 47.26 | 0 | 0 | 50
280 | HOOGHLY | Hooghly Division | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly , SM/13333 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0 | 0
281 | HOOGHLY | Electrical | Mostafapur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly , SM/13333 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MOSTAFAPUR water supply scheme, TW No. III, Block: Khanakul-II, District - Hooghly under Electrical Division PHE Dte. | 483/ED | 18/03/2025 | 90 | SUDIP PRADHAN | 11.3 | 0 | 0 | 0
282 | HOOGHLY | Electrical | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/13337 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Shrirampur water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | 2068/ED | 30/05/2023 | 90 | PURUSHOTTAM ENTERPRISE | 20.35 | 0 | 0 | 0
283 | HOOGHLY | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/13337 | New | Material Requisition To Resource Division | 3059/18/Hug | 11/10/2023 | 0 | Resource Division | 16.31 | 0 | 0 | 0
284 | HOOGHLY | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/13337 | New | Material Requisition To Resource Division | 1264/22/HUG | 03/05/2023 | 0 | Resource Division | 21.65 | 0 | 0 | 0
285 | HOOGHLY | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/13337 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For DASHGHARA ZONE-II (1 NO.), GURBARI, SHRIRAMPUR W/S Scheme under CHISURAH Sub-Division of Hooghly Division, P.H.E. Dte. | 2408/HUG | 11/08/2023 | 45 | GEE BEE NIRMAN CO PRIVATE LIMITED | 81.62 | 24.08 | 73.76 | 20
286 | HOOGHLY | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/13337 | New | ROAD RESTORATION PAYMENT TO PWD FOR BHANDARHATI KUMRUL ROAD | BP-2024-25-499 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 5.52 | 0 | 0 | 0
287 | HOOGHLY | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/13337 | New | Construction of Different Capacity RCC Over Head Reservoir over Pile/Raft Foundation including Sub-soil investigation works for OHR, with Laying Distribution System Providing Functional House hold Tap Connection for BISHNUPUR, DOSGHARA(zone-I), DOSGHARA(zone-II), GURBARI & SRIRAMPUR Piped Water Supply Scheme within DHANIAKHALI block under chinshuraH Sub-Division of Hooghly division, PHE Dte. Under Hooghly district in connection with JJM. | 2066/HUG | 17/07/2023 | 747 | GEE BEE NIRMAN CO PRIVATE LIMITED | 2255.89 | 172.02 | 38.13 | 20
288 | HOOGHLY | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/13337 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of switch-rooms & boundary walls at different TW site for Shrirampur Piped Water Supply Scheme under Chinsurah Sub-Division Block-Dhaniakhali , District:- Hooghly | 2418/HUG | 11/08/2023 | 589 | GEE BEE NIRMAN CO PRIVATE LIMITED | 52.91 | 8.57 | 16.2 | 25
289 | HOOGHLY | Hooghly Division | SHRIRAMPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/13337 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme under Dhaniakhali Block (Part-IV) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. | 408/CH | 10/03/2025 | 15 | TECHVISION | 4.2 | 0 | 0 | 0
290 | HOOGHLY | Hooghly Division | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13414 | New | Material Requisition To Resource Division | 1385/31/Hug | 15/05/2023 | 0 | Resource Division | 10.84 | 0 | 0 | 0
291 | HOOGHLY | Hooghly Division | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13414 | New | Material Requisition To Resource Division | 2607/Hug | 29/08/2023 | 0 | Resource Division | 35.3 | 0 | 0 | 0
292 | HOOGHLY | Hooghly Division | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13414 | New | Material Requisition To Resource Division | 3057/13/Hug | 11/10/2023 | 0 | Resource Division | 10.84 | 0 | 0 | 0
293 | HOOGHLY | Hooghly Division | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13414 | New | Material Requisition To Resource Division | 127/17/Hug | 13/01/2023 | 0 | Resource Division | 35.47 | 0 | 0 | 0
294 | HOOGHLY | Hooghly Division | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13414 | New | Material Requisition To Resource Division | 1234/25/Hug | 28/04/2023 | 0 | Resource Division | 30.08 | 0 | 0 | 0
295 | HOOGHLY | Electrical | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13414 | New | quotation of New Service Connection for Nakunda W/S Scheme, TW No-I Block-Goghat-I, Dist-Hooghly under ED,PHE Dte | 151 | 01/08/2023 | 0 | WBSEDCL | 5.07 | 0 | 0 | 0
296 | HOOGHLY | Electrical | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13414 | New | Quotation of New Service Connection for Nakunda W/s Scheme,TW No-2, Block-Goghat-II, Dist-Hooghly under ED,PHE Dte | 152 | 01/08/2023 | 0 | WBSEDCL | 5.56 | 0 | 0 | 0
297 | HOOGHLY | Electrical | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13414 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nakunda water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | 770/ED | 09/02/2023 | 90 | R.M.D TRADING. | 20.61 | 20.59 | 100 | 40
298 | HOOGHLY | Hooghly Division | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13414 | New | NAKUNDA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-I Block of Arambag SUb-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | 1502/HUG | 22/05/2023 | 664 | UNIQUE AGENCY | 554.69 | 332.9 | 60.02 | 50
299 | HOOGHLY | Hooghly Division | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block , SM/15787 | Augmentation | Repairing of Concrete Roads damaged due to Laying of Augmentation work of GHOSHPUR Water Supply Scheme under KHANAKUL-II Block under Arambag Sub-Division, PHE Dte. | 1102/HUG | 17/04/2023 | 30 | ARATI ENGINEERING | 18.55 | 0 | 0 | 0
300 | HOOGHLY | Hooghly Division | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block , SM/15787 | Augmentation | Material Requisition To Resource Division | 1385/61/Hug | 15/05/2023 | 0 | Resource Division | 0.31 | 0 | 0 | 0
301 | HOOGHLY | Hooghly Division | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block , SM/15787 | Augmentation | Material Requisition To Resource Division | 1263/16/Hug | 03/05/2023 | 0 | Resource Division | 61 | 0 | 0 | 0
302 | HOOGHLY | Electrical | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block , SM/15787 | Augmentation | Quotation Bill for New Service Connection at Ghoshpur W/S. Sch.PH-V | 585 | 28/12/2023 | 0 | WBSEDCL | 3.58 | 0 | 0 | 0
303 | HOOGHLY | Hooghly Division | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block , SM/15787 | Augmentation | AUGMENTATION of GHOSHPUR Piped Water Supply Scheme with Extension of LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. Block-KHANAKUL-I, District:- Hooghly. [AUGMENTATION SCHEME] | 2414/HUG | 11/08/2023 | 599 | GHOSH BROTHERS | 333.22 | 233.14 | 69.97 | 80
304 | HOOGHLY | Electrical | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block , SM/15787 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Ghoshpur water supply scheme, T.W. No. I, Block: Khanakul-I, District: Hooghly under Electrical Division, PHE Dte. | 335/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.43 | 0 | 0 | 0
305 | HOOGHLY | Electrical | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block , SM/15787 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARUNDA PIPED W/S SCHEME, Zone - II, T.W. No. V, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1176/ED | 14/06/2024 | 90 | P.K. ENTERPRISE | 10.72 | 0 | 0 | 0
306 | HOOGHLY | Hooghly Division | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block , SM/15787 | Augmentation | Protection works and other allied works at Head Work Site of GHOSHPUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte | 4056/HUG | 19/12/2024 | 90 | CITYCON UNEMPLOYED ENGINEERS CO-OP SOCIETY LTD | 23.74 | 0 | 0 | 0
307 | HOOGHLY | Hooghly Division | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block , SM/15787 | Augmentation | Protection works and other allied works at 3Nos. Proposed TubeWell Sites of Ghoshpur Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 4053/HUG | 19/12/2024 | 90 | M/S KAUSAR CONSTRUCTION | 23.36 | 0 | 0 | 0
308 | HOOGHLY | Hooghly Division | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block , SM/15787 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at GHOSHPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | 742/HUG | 15/03/2023 | 30 | MAYA CONSTRUCTION | 11.32 | 11.32 | 100 | 100
309 | HOOGHLY | Electrical | Source Augmentation of Paschim Joykrishnapur PWSS , SM/15795 | Augmentation | Supply, delivery and installation of voltage correcting device and other allied works for Joykrishnapur w/s scheme, P.H No.- I, Dist- Hooghly under Electrical Division, PHE Dte. | 727/HMSD | 24/03/2023 | 30 | KUNAL ENTERPRISE | 3.01 | 0 | 0 | 0
310 | HOOGHLY | Hooghly Division | Source Augmentation of Paschim Joykrishnapur PWSS , SM/15795 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at PASCHIM JOYKRISHNAPUR PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. [2nd Call of WBPHE/EE/45/HUG/2022-23, Sl No-18] | 1203/HUG | 26/04/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 12.43 | 12.09 | 97.26 | 0
311 | HOOGHLY | Electrical | Source Augmentation of Paschim Joykrishnapur PWSS , SM/15795 | Augmentation | Car Hire Charges Bill for official use office of the Executive Engineer Howrah Mechanical Sub-Division PHED | 959/HMSD | 20/04/2023 | 365 | SANJIB PRADHAN | 5 | 1.16 | 23.23 | 1
312 | HOOGHLY | Hooghly Division | Source Augmentation of Paschim Joykrishnapur PWSS , SM/15795 | Augmentation | Material Requisition To Resource Division | 3058/22/Hug | 11/10/2023 | 0 | Resource Division | 26.06 | 0 | 0 | 0
313 | HOOGHLY | Electrical | Source Augmentation of Paschim Joykrishnapur PWSS , SM/15795 | Augmentation | Quotation for new service Connection of Paschim Joykrishnapur w/s scheme,Zone-2,PH No-3 Distric- Hooghly under Electrical Division PHE Dte | 105 | 19/07/2023 | 0 | WBSEDCL | 3.19 | 0 | 0 | 0
314 | HOOGHLY | Electrical | Source Augmentation of Paschim Joykrishnapur PWSS , SM/15795 | Augmentation | Quotation of New Service Connection for Paschim Joykrishnapur W/S Scheme,Zone-I,TW No-III Block-Haripal Dist-hooghly under ED,PHE Dte. | 304 | 26/09/2023 | 0 | WBSEDCL | 10.44 | 0 | 0 | 0
315 | HOOGHLY | Electrical | Source Augmentation of Paschim Joykrishnapur PWSS , SM/15795 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). | 2830/HMSD | 30/10/2023 | 182 | SANJIB PRADHAN | 0.86 | 0 | 0 | 42
316 | HOOGHLY | Electrical | Source Augmentation of Paschim Joykrishnapur PWSS , SM/15795 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). | 3112/HMSD | 22/11/2023 | 196 | SIDDHARTHA CHATTERJEE. | 0.93 | 0 | 0 | 60
317 | HOOGHLY | Hooghly Division | Source Augmentation of Paschim Joykrishnapur PWSS , SM/15795 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Olipur,Kulteghori,Paschim Jaykrishnapur & Barakamalpur W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 1839/HUG | 26/06/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 80.45 | 14.39 | 100 | 100
318 | HOOGHLY | Electrical | Source Augmentation of Paschim Joykrishnapur PWSS , SM/15795 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Paschim Joykrishnapur water supply scheme, Zone-I, T.W. No. I & Zone-II, T.W. No. I, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | 1619/ED | 11/04/2023 | 897 | STANDARD ELECTRICALS | 21.81 | 19.77 | 90.63 | 40
319 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. , SM/09692 | Augmentation | Preparation of DPR for Augmentation of ATGHARA Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I]. | 609/Arg | 31/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.67 | 3.67 | 100 | 100
320 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. , SM/09692 | Augmentation | Sinking of I (one) No Big dia tube well (250 mm X 150mm) with supply of PVC Pipe and strainer and having depth upto 150 M at 3rd TW site of Arandi W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 1411/HUG | 12/07/2022 | 30 | OSMAN SEKH | 8.6 | 8.57 | 50 | 100
321 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. , SM/09692 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS FOR CONSTRUCTION OF TUBE WELL AT SOLEPUR DUTTAPUR (Z-II) PWSS, TARAKESWAR BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 530/CMSD-II | 01/12/2022 | 7 | C.M. ENTERPRISE | 0.98 | 0 | 0 | 100
322 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. , SM/09692 | Augmentation | Sinking of 1 no 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at proposed Tube Well Site of ATGHARA W/S Scheme under ARAMBAG Sub-Division of Hooghly Division, P.H.E. Dte. | 165/HUG | 16/01/2023 | 30 | M/S EMON ENTERPRISE | 12.83 | 0 | 0 | 0
323 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. , SM/09692 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS FOR CONSTRUCTION OF TUBE WELL AT ATGHARA PWSS TW-III, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 530/CMSD-II (D) | 01/12/2022 | 7 | C.M. ENTERPRISE | 0.98 | 0.83 | 100 | 100
324 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. , SM/09692 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 210 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR ATGHARA PWSS, TW-III, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 1562/CDD | 08/12/2022 | 30 | C.M. ENTERPRISE | 12.49 | 10 | 100 | 100
325 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. , SM/09692 | Augmentation | Augmentation of ATGHARA Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection within Shrirampur, Kaiba & Atghara Mouza, Repairing of existing OHR at Khanakul-I Block under Arambag Sub-Division, PHE Dte. | 1181/HUG | 15/06/2022 | 60 | RURAL CONSTRUCTION (MANIK CHANDRA ADAK) | 207.8 | 193.71 | 100 | 10
326 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. , SM/09692 | Augmentation | Construction of 1 No. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site OF ATGHARA Water Supply Scheme Under Arambagh Sub-Division Under Hooghly Division P.H.E Dte. | 1775/HUG | 15/06/2023 | 45 | SOUMYAJIT DUTTA | 7.34 | 7.34 | 100 | 100
327 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. , SM/09692 | Augmentation | Material Requisition To Resource Division | 424/5/Hug | 07/03/2022 | 0 | Resource Division | 36.05 | 0 | 0 | 0
328 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. , SM/09692 | Augmentation | Material Requisition To Resource Division | 1773/38/Hug | 29/08/2022 | 0 | Resource Division | 0.69 | 0 | 0 | 0
329 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. , SM/09692 | Augmentation | Material Requisition To Resource Division | 1385/17/Hug | 15/05/2023 | 0 | Resource Division | 5.48 | 0 | 0 | 0
330 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. , SM/09692 | Augmentation | WBSEDCL bill for Atghara PWSS | BP-2022-23-659 | 29/03/2023 | 0 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 5.37 | 0 | 0 | 0
331 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. , SM/09692 | Augmentation | Augmentation of ATGHARA Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection Within Sekendarpur & Helan Mouza, Repairing of Switch room, Boundary wall at Khanakul-I Block under Arambag Sub-Division, PHE Dte. | 1180/HUG | 15/06/2022 | 810 | M/S R.K. CHOUDHURI | 139.82 | 67.92 | 48.58 | 80
332 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. , SM/09692 | Augmentation | Protection works and other allied works at 3rd TubeWell Sites of Dihibagnan & Atghara Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 4051/HUG | 19/12/2024 | 90 | GOURI ENTERPRISE | 15.53 | 0 | 0 | 0
333 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. , SM/09692 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Atghara water supply scheme TW No I Block Khanakul I District Hooghly under ED PHED. | 936/ED | 22/02/2023 | 922 | OSMAN SEKH | 10.75 | 10.36 | 49.26 | 40
334 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. , SM/07440 | Retrofitting | FHTC |  | 16/11/2021 | 0 | GHOSH CONCERN | 24.1 | 0 | 0 | 0
335 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. , SM/07440 | Retrofitting | FHTC |  | 24/09/2021 | 0 | M/S T.K.B. CONSTRUCTION | 7.71 | 0 | 0 | 0
336 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. , SM/07440 | Retrofitting | FHTC |  | 12/04/2021 | 0 | M/S T.K.B. CONSTRUCTION | 6.96 | 0 | 0 | 0
337 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. , SM/07440 | Retrofitting | FHTC |  | 30/09/2021 | 0 | SAMRAT CONSTRUCTION | 19.34 | 0 | 0 | 0
338 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. , SM/07440 | Retrofitting | Providing 220 nos Functional Household Tap Connection (FHTC) within the command area of Namajgram & SUDARSHAN Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 117/Hug | 19/01/2022 | 15 | TOTON MONDAL | 18.26 | 17.93 | 98.19 | 0
339 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. , SM/07440 | Retrofitting | Providing 717 nos F.H.T.C. in Marsit&Kshirkundi Village of Namajgram and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | 400/Hug | 15/02/2021 | 30 | GHOSH CONCERN | 37.28 | 33.73 | 100 | 0
340 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NAMAJGRAM WATER SUPPLY SCHEME. , SM/07440 | Retrofitting | Providing 934 nos F.H.T.C. in Kulipukur & Matukpur Village of Namajgram and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | 959/Hug | 10/05/2021 | 30 | SAMRAT CONSTRUCTION | 48.63 | 45.38 | 100 | 80
341 | HOOGHLY | Hooghly Division | AUGMENTATION OF PATUL PIPED WATER SUPPLY SCHEME, BLOCK- KHANAKUL-I, DISTRICT-HOOGHLY , SM/16120 | Augmentation | Material Requisition To Resource Division | 1263/17/Hug | 03/05/2023 | 0 | Resource Division | 17.17 | 0 | 0 | 0
342 | HOOGHLY | Electrical | AUGMENTATION OF PATUL PIPED WATER SUPPLY SCHEME, BLOCK- KHANAKUL-I, DISTRICT-HOOGHLY , SM/16120 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Patul water supply scheme, T.W. No.-V, Block: Khanakul-I, District - Hooghly under Electrical Division, PHE Dte. | 4735/ED | 15/12/2023 | 90 | MAA KALI ENTERPRISE | 10.74 | 10.35 | 96.36 | 30
343 | HOOGHLY | Electrical | AUGMENTATION OF PATUL PIPED WATER SUPPLY SCHEME, BLOCK- KHANAKUL-I, DISTRICT-HOOGHLY , SM/16120 | Augmentation | Quotation Bill for New Service Connection at Patul W/S. Sch. Z-II, TW-II | 593 | 29/12/2023 | 0 | WBSEDCL | 3.51 | 0 | 0 | 0
344 | HOOGHLY | Hooghly Division | AUGMENTATION OF PATUL PIPED WATER SUPPLY SCHEME, BLOCK- KHANAKUL-I, DISTRICT-HOOGHLY , SM/16120 | Augmentation | Repairing of R.C.C. Elevated Reservoir of PATUL PWSS Under Arambagh Sub-Division Hooghly Division, P.H.E. Dte. | 4149/HUG | 26/12/2024 | 90 | R.K. TRADERS | 10.98 | 0 | 0 | 99
345 | HOOGHLY | Hooghly Division | AUGMENTATION OF PATUL PIPED WATER SUPPLY SCHEME, BLOCK- KHANAKUL-I, DISTRICT-HOOGHLY , SM/16120 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) KHANAKUL PWSS - 6 nos (2) KRISHNANAGAR PWSS - 4nos (3) PATUL PWSS - 4nos | 810/Arg | 23/08/2024 | 30 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
346 | HOOGHLY | Hooghly Division | Source Augmentation of PURBA RAYPUR Piped Water Supply Scheme under Arambag Block , SM/15806 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at PURBARAYPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte | 746/HUG | 15/03/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.32 | 0 | 0 | 0
347 | HOOGHLY | Electrical | Source Augmentation of PURBA RAYPUR Piped Water Supply Scheme under Arambag Block , SM/15806 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Purba Raypur water supply scheme, T.W. No. I, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 1621/ED | 11/04/2023 | 90 | ESENCE ENGINEERING CONCERN | 10.75 | 0 | 0 | 0
348 | HOOGHLY | Hooghly Division | Source Augmentation of PURBA RAYPUR Piped Water Supply Scheme under Arambag Block , SM/15806 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of PURBA RAYPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within ARAMBAGH Block. | 1497/HUG | 22/05/2023 | 30 | DEBANANDA CONSTRUCTION | 11.81 | 0 | 0 | 0
349 | HOOGHLY | Hooghly Division | Source Augmentation of PURBA RAYPUR Piped Water Supply Scheme under Arambag Block , SM/15806 | Augmentation | Material Requisition To Resource Division | 1263/11/Hug | 03/05/2023 | 0 | Resource Division | 5.69 | 0 | 0 | 0
350 | HOOGHLY | Hooghly Division | Source Augmentation of PURBA RAYPUR Piped Water Supply Scheme under Arambag Block , SM/15806 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of PURBARAYPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 4154/HUG | 26/12/2024 | 90 | M/S SHIVAM UDYOG | 11.84 | 0 | 0 | 0
351 | HOOGHLY | Electrical | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block , SM/15808 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jaykrishnapur water supply scheme, T.W. No. I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | 1502/ED | 28/03/2023 | 90 | M/S DILIP MITRA | 10.75 | 0 | 0 | 0
352 | HOOGHLY | Hooghly Division | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block , SM/15808 | Augmentation | Laying of pipe line for left out portion within command area of Jaykrishnapur Water Supply Scheme to facilate the FHTC Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 1170/HUG | 20/04/2023 | 30 | SADHUKHAN ENTERPRISE | 4.76 | 0 | 0 | 0
353 | HOOGHLY | Hooghly Division | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block , SM/15808 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of Jaykrishnapur Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-I Block. | 1494/HUG | 22/05/2023 | 30 | A.R. CONSTRUCTION | 11.83 | 0 | 0 | 0
354 | HOOGHLY | Electrical | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block , SM/15808 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jaykrishnapur water supply scheme, T.W. No. II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | 3438/ED | 11/08/2023 | 90 | J.K. ENGINEERING CO. | 10.74 | 0 | 0 | 0
355 | HOOGHLY | Hooghly Division | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block , SM/15808 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at JAYKRISHNAPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | 746/hug | 15/03/2023 | 30 | MAYA CONSTRUCTION | 11.32 | 10.58 | 100 | 100
356 | HOOGHLY | Hooghly Division | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block , SM/15808 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) ANANDAPUR PWSS-4nos (2) BHADUR(BHAGARBAND) PWSS-6nos (3) GOGHAT PWSS-2nos (4) JOYKRISHNAPUR PWSS-2nos | 816/Arg | 23/08/2024 | 130 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.14 | 100 | 100
357 | HOOGHLY | Electrical | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block , SM/15808 | Augmentation | Quotation of New Service Connection for Jaykrishnapur w/s Scheme,TW no-3 Block-Goghat-I Dist-Hooghly under ED,PHE Dte(SM/15808) Application No-5004009573 Reference Id-503561825 | 748 | 16/02/2024 | 0 | WBSEDCL | 3.95 | 0 | 0 | 0
358 | HOOGHLY | Hooghly Division | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block , SM/15808 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of JAYKRISHNAPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 4153/HUG | 26/12/2024 | 90 | BOSE ENTERPRISE (RATUL BOSE) | 11.84 | 0 | 0 | 0
359 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHIBRAI W/S SCHEME UNDER PANDUA BLOCK , SM/15801 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at SHIBRAI(2NOS.), SHANKHANAGAR CHAK BANSBERIA(2NOS.), BAKULIA ZONE-I(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. [3rd Call of WBPHE/EE/77/HUG/2022-23, Sl No-2] | 1507/HUG | 22/05/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 72.85 | 0 | 0 | 50
360 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHIBRAI W/S SCHEME UNDER PANDUA BLOCK , SM/15801 | Augmentation | Material Requisition To Resource Division | 3004/3/Hug | 05/10/2023 | 0 | Resource Division | 35.71 | 0 | 0 | 0
361 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHIBRAI W/S SCHEME UNDER PANDUA BLOCK , SM/15801 | Augmentation | Quotation Bill for New Service Connection at Shibrai W/S. Sch. | 202 | 21/08/2023 | 0 | WBSEDCL | 3.84 | 0 | 0 | 0
362 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHIBRAI W/S SCHEME UNDER PANDUA BLOCK , SM/15801 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Shibrai water supply scheme, T.W. No. I & II, Block: Pandua, District- Hooghly under Electrical Division, PHE Dte. | 1700/ED | 18/04/2023 | 90 | A.G. ENTERPRISE | 22.81 | 11.69 | 51.26 | 50
363 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHIBRAI W/S SCHEME UNDER PANDUA BLOCK , SM/15801 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at SHIBRAI(2NOS.), SHANKHANAGAR CHAK BANSBERIA(2NOS.), BAKULIA ZONE-I(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. [3rd Call of WBPHE/EE/77/HUG/2022-23, Sl No-2] | 1618/HUG | 02/06/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 72.85 | 23.3 | 100 | 65
364 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHIBRAI W/S SCHEME UNDER PANDUA BLOCK , SM/15801 | Augmentation | Quotation Bill for New Service Connection at Shibrai W/S. Sch. PH-IV Hooghly | 734 | 05/02/2024 | 0 | WBSEDCL | 7.63 | 0 | 0 | 0
365 | HOOGHLY | Hooghly Division | BASTA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/16763 | New | Material Requisition To Resource Division | 1386/8/Hug | 15/05/2023 | 0 | Resource Division | 3.33 | 0 | 0 | 0
366 | HOOGHLY | Hooghly Division | BASTA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/16763 | New | Material Requisition To Resource Division | 1264/10/HUG | 03/05/2023 | 0 | Resource Division | 9.67 | 0 | 0 | 0
367 | HOOGHLY | Hooghly Division | BASTA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/16763 | New | Material Requisition To Resource Division | 3059/16/Hug | 11/10/2023 | 0 | Resource Division | 3.33 | 0 | 0 | 0
368 | HOOGHLY | Electrical | BASTA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/16763 | New | Quotation Bill for New Service Connection at Basta W/S. Sch.TW-I | 578 | 27/12/2023 | 0 | WBSEDCL | 3.06 | 0 | 0 | 0
369 | HOOGHLY | Electrical | BASTA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/16763 | New | Quotation Bill for New Service Connection at Basta W/S. Sch. TW-II | 686 | 19/01/2024 | 0 | WBSEDCL | 3.61 | 0 | 0 | 0
370 | HOOGHLY | Hooghly Division | BASTA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/16763 | New | BASTA Piped Water Supply Scheme with Sinking of tube-well, Laying Distrubtuion System, Rising Main, Providing FHTC, construction of switch-rooms & boundary walls at different TW site under Hooghly Division, PHE Dte. within POLBA-DADPUR Block, District:- Hooghly | 844/HUG | 23/03/2023 | 923 | TOTON MONDAL | 142.86 | 81.67 | 57.16 | 60
371 | HOOGHLY | Hooghly Division | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block , SM/16130 | Augmentation | Providing 770 nos Functional Household Tap Connection (FHTC) within the command area of DIHIBAGNAN Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. Work Allotted : 385 Nos FHTC out of 770 Nos FHTC within the command area of DIHIBAGNAN Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Estimate Value : Rs. 1599635.50 (50% of Rs. 3199271.00) | 2231/HUG | 15/12/2021 | 30 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 12.8 | 12.09 | 94.47 | 95
372 | HOOGHLY | Electrical | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block , SM/16130 | Augmentation | Supply, delivery and installation of voltage correcting device and other allied works for Dihi Bagnan water supply scheme, T.W. No.-III, Dist.- Hooghly under Electrical Division, PHE Dte. | 657/HMSD | 04/04/2022 | 15 | BOSE & CHATTERJEE INDUSTRIES | 2.37 | 2.37 | 100 | 30
373 | HOOGHLY | Electrical | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block , SM/16130 | Augmentation | Hiring of diesel driven contract carriage along with driver for the official use of the SEMC-I PHED | 933_HMSD | 18/04/2023 | 365 | S.P. CONSTRUCTION | 5 | 1.58 | 31.66 | 30
374 | HOOGHLY | Electrical | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block , SM/16130 | Augmentation | Supply, delivery & installation of automatic Chlorinator for Dihi Bagnan water supply scheme, T.W. No.-III, Dist.- Hooghly under Electrical Division, PHE Dte. | 70/HMSD | 10/01/2023 | 7 | BISALAXMI ENTERPRISE | 0.8 | 0.8 | 100 | 100
375 | HOOGHLY | Electrical | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block , SM/16130 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for DIHI BAGNAN PIPED W/S SCHEME, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1452/ED | 25/07/2024 | 90 | BARMAN ROY TRADERS | 11.09 | 0 | 0 | 0
376 | HOOGHLY | Hooghly Division | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block , SM/16130 | Augmentation | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of RASULPUR, SHYAMBALLAVPUR , DIHIBAGNAN W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3531/HUG | 22/10/2024 | 45 | PADMA ENGINEERING CO. | 47.49 | 0 | 0 | 0
377 | HOOGHLY | Hooghly Division | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block , SM/16130 | Augmentation | Laying CI/DI pipes & specials for rising main pipe line in between T.W No.- III to O.H.R. and interconnection with distribution system at 3rd Tube Well Site of DIHI BAGNAN W/S Scheme under Arambagh Sub-Division, P.H.E. Dte. | 176/Arg | 21/03/2022 | 10 | M/S ROY ENTERPRISE | 4.83 | 3.72 | 100 | 100
378 | HOOGHLY | Hooghly Division | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block , SM/16130 | Augmentation | Providing 840 nos Functional Household Tap Connection (FHTC) within the command area of Dihibagnan Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | 1915/HUG | 27/10/2021 | 40 | M/S PRADYUT KUMAR HAZRA | 40.43 | 2.5 | 100 | 97
379 | HOOGHLY | Hooghly Division | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block , SM/16130 | Augmentation | Providing 1700 nos F.H.T.C. in Dihibagnan, Para Bagnan & Bhabanipur village of Dihibagnan and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh] | 1687/Hug | 17/12/2020 | 40 | M/S PRADYUT KUMAR HAZRA | 79.86 | 3.91 | 100 | 97
380 | HOOGHLY | Electrical | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block , SM/16130 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dihi Bagnan water supply scheme, T.W. No. III, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 552/ED | 22/03/2022 | 90 | BISALAXMI ENTERPRISE | 6.59 | 6.27 | 100 | 30
381 | HOOGHLY | Hooghly Division | Source Augmentation of DIHI BAGNAN Piped Water Supply Scheme under Arambag Block , SM/16130 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Belmuri village under Dhaniakhali Block, Jot Haranda village of Dhnaiakhali Block and Radhaballavpur village of Dhaniakhali Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | 259/CH | 14/03/2024 | 7 | R.K. TRADERS | 0.95 | 0.95 | 100 | 100
382 | HOOGHLY | Hooghly Division | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17716 | New | Material Requisition To Resource Division | 3057/9/Hug | 11/10/2023 | 0 | Resource Division | 12.23 | 0 | 0 | 0
383 | HOOGHLY | Hooghly Division | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17716 | New | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of DHARMMAPUR Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 3655/HUG | 13/11/2024 | 90 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 16.06 | 0 | 0 | 0
384 | HOOGHLY | Hooghly Division | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17716 | New | Construction of 3 nos. 5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of MOHISHGOT Zone-II, RADHABALLAVPUR Zone-I , DHARAMPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3780/HUG | 25/11/2024 | 60 | ROY ENTERPRISE | 55.39 | 0 | 0 | 0
385 | HOOGHLY | Electrical | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17716 | New | Quotation of New Service Connection for Dharmmapur w/s Scheme,PH No-I Block-Khanakul-I Dist-Hooghly under ED,PHE Dte(SM/17716) Application No-5004012408 Reference Id-503561211 | 741 | 08/02/2024 | 0 | WBSEDCL | 5.64 | 0 | 0 | 0
386 | HOOGHLY | Electrical | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17716 | New | Quotation of New Service Connection For Dharmmapur w/s scheme,PH No-II Block-Khanakul-I,Dist-Hooghly under ED,PHE Dte(SM/17716) Application no-5004012404 Reference Id-503561209 | 740 | 08/02/2024 | 0 | WBSEDCL | 3.59 | 0 | 0 | 0
387 | HOOGHLY | Electrical | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17716 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dharmmapur water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | 1794/ED | 24/04/2023 | 830 | M/S, GHOSH ENTERPRISE | 20.35 | 2.89 | 14.2 | 30
388 | HOOGHLY | Hooghly Division | GROUND WATER BASED DHARMMAPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17716 | New | DHARMMAPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANAKUL-I Block, District:- Hooghly [NEW SCHEME] | 1017/Hug | 06/04/2023 | 1057 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 407.11 | 113.73 | 27.94 | 50
389 | HOOGHLY | Hooghly Division | BHATUA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18098 | New | Material Requisition To Resource Division | 1386/35/Hug | 15/05/2023 | 0 | Resource Division | 4.56 | 0 | 0 | 0
390 | HOOGHLY | Hooghly Division | BHATUA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18098 | New | Material Requisition To Resource Division | 3004/11/Hug | 05/10/2023 | 0 | Resource Division | 2.71 | 0 | 0 | 0
391 | HOOGHLY | Electrical | BHATUA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18098 | New | Quotation for new service connection charge at Bhatua PWSS, TW - I | 455 | 01/12/2023 | 0 | WBSEDCL | 15.6 | 0 | 0 | 0
392 | HOOGHLY | Electrical | BHATUA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18098 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhatua water supply scheme, T.W. No. I & II, Block: Polba Dadpur, District - Hooghly under Electrical Division, PHE Dte. | 1924/ED | 15/05/2023 | 90 | UNITED ENTERPRISE | 23.21 | 11.53 | 49.7 | 50
393 | HOOGHLY | Hooghly Division | BHATUA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18098 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Ghatampur PWSS 2. Kanajoli PWSS 3. Bhatua PWSS 4. Shrirampur PWSS | 143/CH | 20/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.79 | 0.79 | 50 | 30
394 | HOOGHLY | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18105 | New | Material Requisition To Resource Division | 1384/7/Hug | 16/05/2023 | 0 | Resource Division | 7.93 | 0 | 0 | 0
395 | HOOGHLY | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18105 | New | Material Requisition To Resource Division | 3060/8/Hug | 11/10/2023 | 0 | Resource Division | 7.93 | 0 | 0 | 0
396 | HOOGHLY | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18105 | New | Material Requisition To Resource Division | 1236/4/Hug | 28/04/2023 | 0 | Resource Division | 32.71 | 0 | 0 | 0
397 | HOOGHLY | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18105 | New | Material Requisition To Resource Division | 3005/Hug | 05/10/2023 | 0 | Resource Division | 0.01 | 0 | 0 | 0
398 | HOOGHLY | Electrical | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18105 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Nilarpur water supply scheme, T.W. No. I & II, Block: Jangipara, District - Hooghly under Electrical Division, PHE Dte. | 1929/ED | 15/05/2023 | 90 | SWAPAN ENTERPRISE | 23.08 | 22.49 | 97.45 | 90
399 | HOOGHLY | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18105 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Mundalika-I PWSS 2. Mundalika-II PWSS 3. Nilarpur PWSS 4. Gopalpur PWSS 5. Bishnupur PWSS 6. Radhanagar PWSS | 114/SER | 23/02/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 80
400 | HOOGHLY | Electrical | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18105 | New | Quotation Bill for New Service Connection at Nilarpur W/S. Sch. | 635 | 08/01/2024 | 0 | WBSEDCL | 4.83 | 0 | 0 | 0
401 | HOOGHLY | Electrical | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18105 | New | Quotation Bill for New Service Connection at Nilarpur W/S. Sch. PH-I | 634 | 08/01/2024 | 0 | WBSEDCL | 8.22 | 0 | 0 | 0
402 | HOOGHLY | Hooghly Division | Nilarpur Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18105 | New | NILARPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block under Serampore Sub-Division of Hooghly Division, PHE Dte, District:- Hooghly [NEW SCHEME] | 2063/HUG | 17/07/2023 | 270 | BANSBERIA CONSTRUCTION CO. | 411.87 | 170.81 | 41.47 | 40
403 | HOOGHLY | Hooghly Division | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Hasampur Water Supply Scheme Under Dhaniakhali Block , SM/18111 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of HASAMPUR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 2306/HUG | 28/10/2022 | 60 | MALLIKA ENTERPRISE | 90.96 | 0 | 0 | 0
404 | HOOGHLY | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME , SM/16648 | Retrofitting | Construction of 1 (One) No. Pump House (3.0 x 3.6 m ) with additional plinth height including internal pathway at 6th tubewell site of Bandipur PWSS Scheme under Hooghly Sub-Division, PHE Dte. | 145/Chan | 16/03/2023 | 40 | BMR ENGINEERING & CONSTRUCTION | 4.99 | 3.25 | 100 | 80
405 | HOOGHLY | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME , SM/16648 | Retrofitting | Repairing of boundary wall at 2nd TW site of Bandipur Piped Water Supply Scheme Scheme under Chandannagar Sub-Division, PHE Dte. | 286/Chan | 15/03/2024 | 15 | SHREE JAGANNATH ENTERPRISE | 0.99 | 0.99 | 100 | 100
406 | HOOGHLY | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME , SM/16648 | Retrofitting | Repairing Damaged pipeline at Bandipur Piped Water Supply Scheme under Chandannagar Sub-Division P.H.E.Dte. | 292/Chan | 15/03/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.37 | 0.37 | 100 | 100
407 | HOOGHLY | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME , SM/16648 | Retrofitting | Laying of Rising main for Interconnection of Laying distribution system at 6th Tube well site of Bandipur Water Supply Scheme Under chandannagar Sub-Division under Hooghly Division,P.H.E Dte . | 287/Chan | 15/03/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.92 | 0.89 | 100 | 100
408 | HOOGHLY | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME , SM/16648 | Retrofitting | Repairing of pump house at 2nd TW site of Bandipur Piped Water Supply Scheme under Chandannagar Sub-Division, PHE Dte. | 285/Chan | 15/03/2024 | 15 | SHREE JAGANNATH ENTERPRISE | 1 | 0.97 | 100 | 100
409 | HOOGHLY | Hooghly Division | RETROFITTING FOR BANDIPUR WS SCHEME , SM/16648 | Retrofitting | Repairing of damaged FHTC connection at Bandipur PWSS under Chandannagar Sub-Division under Hooghly Division P.H.E Dte. | 152/Chan | 31/01/2025 | 15 | MS CHANDIMATA CONSTRUCTION | 0.91 | 0 | 0 | 100
410 | HOOGHLY | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) , SM/17719 | New | Material Requisition To Resource Division | 1234/28/Hug | 28/04/2023 | 0 | Resource Division | 18.54 | 0 | 0 | 0
411 | HOOGHLY | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) , SM/17719 | New | Material Requisition To Resource Division | 1385/41/Hug | 15/05/2023 | 0 | Resource Division | 5.59 | 0 | 0 | 0
412 | HOOGHLY | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) , SM/17719 | New | Material Requisition To Resource Division | 3057/33/Hug | 11/10/2023 | 0 | Resource Division | 5.59 | 0 | 0 | 0
413 | HOOGHLY | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) , SM/17719 | New | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at RADHABALLAVPUR Z-I, BENGAI, SAMANTAKHANDA and BHURKUNDA Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 724/HUG | 05/03/2024 | 60 | RUNA ENTERPRISE | 64.27 | 0 | 0 | 0
414 | HOOGHLY | Electrical | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) , SM/17719 | New | Quotation of New Service Connection for Bhur Kunda w/s Scheme,Zone-II,PH No-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/17719) Application No-5004320081 Reference Id- 503705387 | 339 | 30/07/2024 | 0 | WBSEDCL | 4.47 | 0 | 0 | 0
415 | HOOGHLY | Electrical | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) , SM/17719 | New | Quotation of New Service Connection for Bhurkunda w/s Scheme, Z-II,PH No-I Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/17719) Application No-5004034182 Reference Id-503574967 | 811 | 28/02/2024 | 0 | WBSEDCL | 3.9 | 0 | 0 | 0
416 | HOOGHLY | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) , SM/17719 | New | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | 3190/HUG | 31/10/2023 | 609 | M/S PRITI ENTERPRISE | 4251.5 | 140.7 | 47.39 | 30
417 | HOOGHLY | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-II) , SM/17719 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 464/HUG | 20/02/2025 | 30 | TECHVISION | 6.59 | 0 | 0 | 0
418 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Preparation of DPR for Augmentation of Mahespur Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Polba-Dadpur) | 68/CH | 27/01/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.77 | 4.76 | 100 | 0
419 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Additional Survey work for Preparation of Preparation of DPR for Augmentation of Mahespur Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Polba-Dadpur) | 69/CH | 27/01/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.38 | 0.37 | 100 | 0
420 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at MAHESHPUR (Zone-II) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 07 | 2012/HUG | 13/09/2022 | 30 | OSMAN SEKH | 11.32 | 10.59 | 100 | 0
421 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Construction of 1 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site of MAHESHPUR ZONE-II Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | 649/HUG | 09/03/2023 | 45 | M/S PAULAMI ENTERPRISE | 5.77 | 5.77 | 100 | 100
422 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Repairing Of Switch Room, Boundary wall for Augemntation Of MAHESHPUR ZONE-II W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly | 2440/HUG | 12/08/2023 | 45 | BASU & SONS | 5.31 | 5.28 | 100 | 95
423 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Repairing Of Switch Room, Boundary wall for Augemntation Of MAHESHPUR ZONE-I W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | 2458/HUG | 12/08/2023 | 45 | M/S BIMAL DAS AND CO. | 5.31 | 5.28 | 100 | 95
424 | HOOGHLY | Electrical | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer Mechanical Circle-II, PHE Dte. | 2385//HMSD | 27/12/2022 | 30 | DEBASHISH GHOSH | 0.29 | 0.29 | 100 | 30
425 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Material Requisition To Resource Division | 1123/6/HUG | 06/06/2022 | 0 | Resource Division | 5.5 | 0 | 0 | 0
426 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Material Requisition To Resource Division | 1991/HUG | 12/09/2022 | 0 | Resource Division | 42.71 | 0 | 0 | 0
427 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Material Requisition To Resource Division | 1105/2/Hug | 17/04/2023 | 0 | Resource Division | 47.53 | 0 | 0 | 0
428 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Material Requisition To Resource Division | 1386/36/Hug | 15/05/2023 | 0 | Resource Division | 11.14 | 0 | 0 | 0
429 | HOOGHLY | Electrical | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT MAHESHPUR (AUG.) W/S SCH., ZONE - II, P.H. NO. - III, dist. - Hooghly | 43 | 19/05/2023 | 0 | WBSEDCL | 2.71 | 0 | 0 | 0
430 | HOOGHLY | Electrical | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Quotation for new service connection charge at Maheshpur PWSS, Zone-I, TW - III | 456 | 01/12/2023 | 0 | WBSEDCL | 3.32 | 0 | 0 | 0
431 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, HEAD QUARTER, HOOGHLY DIVISION, PHE DTE. | BP-2023-24-232 | 31/07/2023 | 0 | PRADIP KUMAR ADHYA | 3.52 | 0 | 0 | 0
432 | HOOGHLY | Electrical | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAHESHPUR PIPED W/S SCHEME, Zone-I, T.W. No. IV, Block: Polba Dadpur, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1464/ED | 25/07/2024 | 90 | MAA TARA ENTERPRISE. | 11.1 | 0 | 0 | 30
433 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at MAHESHPUR (Zone-I) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 06 | 2011/HUG | 13/09/2022 | 30 | OSMAN SEKH | 11.32 | 11.23 | 100 | 25
434 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Augmentation of MAHESHPUR (ZONE-II) Water Supply Scheme with LDS, FHTC, Rising Main at POLBA-DADPUR Block under Chinsurah Sub-Division under Hooghly Division PHE Dte. | 1717/Hug | 24/08/2022 | 60 | M/S S.G. CONSTRUCTION | 207.78 | 186.81 | 100 | 100
435 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Augmentation of MAHESHPUR (ZONE-I) Water Supply Scheme with LDS, FHTC, Rising Main at POLBA-DADPUR Block Under Chinsurah Sub-Division of Hooghly Division, PHE Dte. [2nd call of NIeT No. WBPHE/EE/10/HUG/2022-23 Sl No. 02] | 961/Hug | 31/03/2023 | 90 | SAMRAT REALPROJECTS PRIVATE LIMITED, | 266.8 | 90.67 | 33.04 | 100
436 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipeline for inter connection between T.W & Distribution for Augmentation of MAHESPUR ZONE-II Piped Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.HE Dte. within POLBA-DADPUR Block. | 1478/HUG | 19/05/2023 | 45 | SHREEOM ENTERPRISE | 12.11 | 9.61 | 100 | 50
437 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir of MAHESHPUR Zone-I PWSS under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | 2456/HUG | 12/08/2023 | 60 | M/S S & P CONSTRUCTION | 9.75 | 9.23 | 100 | 80
438 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir of MAHESHPUR Zone-II PWSS under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | 2457/HUG | 12/08/2023 | 60 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 9 | 8.8 | 100 | 75
439 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Baichi PWSS 2. Mahespur PWSS 3. Uttar Chandannagar PWSS 4. Bahadurpur PWSS 5. Patna BhairavpurPWSS 6. Mandra PWSS | 212/CH | 29/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 45
440 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Providing FHTC in rest out portion At Sugandha of Mahespur PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | 218/CH | 29/02/2024 | 7 | M/S BIMAL DAS AND CO. | 0.85 | 0.85 | 100 | 25
441 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Construction of Protection Work at Maheshpur Zone - I under Chinsurah Sub-Division of Hooghly Division P.H.E. Dte. | 735/HUG | 05/03/2024 | 30 | SHREEOM ENTERPRISE | 7.63 | 6.47 | 100 | 70
442 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Laying Balance portion of Pipeline including other allied works at various Mouzas MAHESHPUR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 815/HUG | 11/03/2024 | 45 | MALLIKA ENTERPRISE | 35.45 | 3.96 | 20.94 | 100
443 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at various Mouzas MAHESHPUR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 812/HUG | 11/03/2024 | 30 | SWARNA ENTERPRISE | 27.22 | 20.29 | 100 | 65
444 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Providing FHTC in rest out portion At Amarpur Paschim Para of Mahespur Z-I PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | 273/CH | 14/03/2024 | 7 | M/S BIMAL DAS AND CO. | 0.98 | 0.98 | 100 | 80
445 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Providing FHTC in rest out portion At Choto Pachrakhi of Mahespur Z-I PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | 274/CH | 14/03/2024 | 7 | M/S BIMAL DAS AND CO. | 0.66 | 0.66 | 50 | 80
446 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Sinking of tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room ,boundary wall & Repairing of Existing OHR,Switch Rooms, Boundary walls at different TW sites for Augmentation of DHARAMPUR (Maheshpur) Piped Water Supply Scheme, District:- Hooghly | 3594/HUG | 05/12/2023 | 60 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 27.85 | 21.94 | 100 | 40
447 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | REGARDING DAMAGE OF PMGSY ROAD MAHESHPUR MORE TO BHAUSANARA PART OF ANANTPUR CMDA MAHESHPUR MORE IN POLBA DADPUR BLOCK HOOGHLY DISTRICT. | BP-2023-24-788 | 29/01/2024 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 17.94 | 0 | 0 | 0
448 | HOOGHLY | Electrical | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Quotation for new service connection at Maheshpur (Zone - I) W/S Sch., [SM/10451] T/W No. - IV, Nr. Sugandhya Panchyate, Block - Polba-Dadpur, Dist. Hooghly, under SM/Polba, WBSEDCL, Ref. Id. - 503594865, Dt. - 02-04-2024, Application No. - 5004069700 | 41 | 09/04/2024 | 0 | WBSEDCL | 4.4 | 0 | 0 | 0
449 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | ROAD RESTORATION CHARGES | BP-2024-25-343 | 02/08/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 3.89 | 0 | 0 | 0
450 | HOOGHLY | Electrical | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Maheshpur water supply scheme TW No I and II Block Polba Dadpur, District Hooghly under ED PHED. | 851/ED | 14/02/2023 | 472 | P.K. ENGINEERING | 21.49 | 21.09 | 98.15 | 95
451 | HOOGHLY | Hooghly Division | AUGMENTATION OF MAHESHPUR WATER SUPPLY SCHEME , SM/10451 | Augmentation | Sinking of tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room , boundary wall & Repairing of Existing OHR,Switch Rooms, Boundary walls at different TW sites for Augmentation of MAHESHPUR Piped Water Supply Scheme under CHINSURAH-MAGRA Block, District:- Hooghly | 3595/HUG | 05/12/2023 | 121 | TURNKEY BUSINESS ENGINEERS (I) PVT LTD | 32.82 | 0 | 0 | 40
452 | HOOGHLY | Hooghly Division | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly , SM/18593 | New | Material Requisition To Resource Division | 127/29/Hug | 13/01/2023 | 0 | Resource Division | 18.93 | 0 | 0 | 0
453 | HOOGHLY | Hooghly Division | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly , SM/18593 | New | Material Requisition To Resource Division | 3057/30/Hug | 11/10/2023 | 0 | Resource Division | 14.98 | 0 | 0 | 0
454 | HOOGHLY | Electrical | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly , SM/18593 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sunia water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | 3588/ED | 28/08/2023 | 90 | A.G. ENTERPRISE | 21.49 | 10.28 | 47.81 | 15
455 | HOOGHLY | Electrical | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly , SM/18593 | New | Quotation of New Service Connection for Sunia w/s Scheme,PH No-IV,Block-Goghat-I,Dist-Hooghly under Electrical Division,PHE Dte.(SM/18593) Application No-5004475105 Reference Id-503799038 | 616 | 05/12/2024 | 0 | WBSEDCL | 3.36 | 0 | 0 | 0
456 | HOOGHLY | Electrical | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly , SM/18593 | New | Quotation Bill for New Service Connection at Sunia PWSS W/S. Sch. | 747 | 08/02/2024 | 0 | WBSEDCL | 4.51 | 0 | 0 | 0
457 | HOOGHLY | Electrical | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly , SM/18593 | New | Quotation of New Service Connection for Sunia w/S Scheme,PH No-II, Block-Goghat-I Dist-Hooghly under Electrical Division PHE Dte.(SM/18593) Application No-5004479490 Reference Id-503802380 | 607 | 05/12/2024 | 0 | WBSEDCL | 7.79 | 0 | 0 | 0
458 | HOOGHLY | Hooghly Division | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly , SM/18593 | New | RAGHUBATI, SUNIA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at GOGHAT-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. [NEW SCHEME] | 2363/HUG | 08/08/2023 | 809 | P.B. ENTERPRISE (PINTU BHADURI) | 1481.45 | 345.13 | 49.72 | 50
459 | HOOGHLY | Hooghly Division | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly , SM/18593 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PUKHURIA PWSS- 3 nos (2) SELAMPUR PWSS (Z-I)- 2 nos (3) SHANTIPUR PWSS (Z-I)- 1 nos (4) KOTA PWSS - 4nos (5) SUNIA PWSS - 4nos | 1149/Arg | 10/12/2024 | 31 | TITAS CONSTRUCTION | 0.98 | 0 | 0 | 0
460 | HOOGHLY | Hooghly Division | BENGAI WATER SUPPLY SCHEME , SM/18597 | New | Material Requisition To Resource Division | 3057/19/Hug | 11/10/2023 | 0 | Resource Division | 20.1 | 0 | 0 | 0
461 | HOOGHLY | Hooghly Division | BENGAI WATER SUPPLY SCHEME , SM/18597 | New | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at RADHABALLAVPUR Z-I, BENGAI, SAMANTAKHANDA and BHURKUNDA Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 724/HUG | 05/03/2024 | 60 | RUNA ENTERPRISE | 64.27 | 0 | 0 | 0
462 | HOOGHLY | Electrical | BENGAI WATER SUPPLY SCHEME , SM/18597 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BENGAI PIPED W/S SCHEME, T.W. No. IV, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1162/ED | 14/06/2024 | 90 | S.G. TECHNICAL SERVICES | 10.74 | 0 | 0 | 0
463 | HOOGHLY | Electrical | BENGAI WATER SUPPLY SCHEME , SM/18597 | New | Supply of Fuel for 1(One) no Diesel luxury Taxi on contract Carriage for the office of the Assistant Engineer Howrah mechanical Sub Division PHE Dte(JJM Work for Hooghly District) for the Month of April 2024. | 191 | 10/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
464 | HOOGHLY | Electrical | BENGAI WATER SUPPLY SCHEME , SM/18597 | New | Quotation of New Service Connection for Bengai w/s Scheme,PH No-I Block-Goghat-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18597) Application No-5004215163 Reference Id-503657720 | 186 | 03/06/2024 | 0 | WBSEDCL | 5.66 | 0 | 0 | 0
465 | HOOGHLY | Electrical | BENGAI WATER SUPPLY SCHEME , SM/18597 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for Office of the Assistant Engineer-II, Electrical Division, PHE Dte. From 01.04.2024 to 30.04.2023 WB-15C-5554 | 187 | 03/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
466 | HOOGHLY | Electrical | BENGAI WATER SUPPLY SCHEME , SM/18597 | New | Quotation of New Service Connection for Bengai w/s Scheme, PH No-II Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/18597) Application No-5004034165 Reference Id-503574963 | 812 | 28/02/2024 | 0 | WBSEDCL | 3.33 | 0 | 0 | 0
467 | HOOGHLY | Electrical | BENGAI WATER SUPPLY SCHEME , SM/18597 | New | Quotation of New Service Connection for Bengai w/s Scheme, PH No-III Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/18597) Application No-5004190291 Reference Id-503647427. | 150 | 22/05/2024 | 0 | WBSEDCL | 3.24 | 0 | 0 | 0
468 | HOOGHLY | Hooghly Division | BENGAI WATER SUPPLY SCHEME , SM/18597 | New | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | 3190/HUG | 31/10/2023 | 609 | M/S PRITI ENTERPRISE | 4251.5 | 450 | 51.94 | 30
469 | HOOGHLY | Hooghly Division | BENGAI WATER SUPPLY SCHEME , SM/18597 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 464/HUG | 20/02/2025 | 30 | TECHVISION | 6.59 | 0 | 0 | 0
470 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Preparation of DPR for Augmentation of Bagnan Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | 130/CH | 17/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.03 | 4.01 | 99.46 | 0
471 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Sinking of I (one) No Big dia tube well (250 mm X 150mm) with supply of PVC Pipe and strainer and having depth upto 180 M at Proposed TW site of Badinan W/S Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | 1412/HUG | 12/07/2022 | 30 | OSMAN SEKH | 9.29 | 8.93 | 50 | 0
472 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Repair and Renovation of R.C.C Elevated Reservoir & Balance FHTC for augemntation Of BAGNAN ZONE-I Water Supply Scheme at Dhaniakhali Block under Chinsurah Sub-Divn. of Hooghly Division, P.H.E. Dte. | 2859/HUG | 16/12/2022 | 45 | M/S RAJKUMAR KHAN | 41 | 40.49 | 98.76 | 0
473 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bagnan water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | 822/ED | 14/02/2023 | 90 | A.S. ENTERPRISE | 21.45 | 18.52 | 86.33 | 30
474 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at BAGNAN ZONE-II(2NOS.), SIBAICHANDI ZONE-I(2NOS.), SRIKRISHNAPUR ZONE-II(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | 883/HUG | 27/03/2023 | 45 | B.K ENTERPRISE | 75.32 | 28.3 | 97.58 | 80
475 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Proposed Laying Distribution within Noapara & Bagnan Mouza & Repairing Of Switch Room of Existing T.W-1 & T.W-2 for Augemntation Of BAGNAN ZONE-I Water Supply Scheme at Dhaniakhali Block under Chinsurah Sub-Divn. of Hooghly Division, P.H.E. Dte. | 2902/HUG | 23/12/2022 | 90 | TOTON MONDAL | 103.85 | 102.37 | 100 | 100
476 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Material Requisition To Resource Division | 1386/50/Hug | 15/05/2023 | 0 | Resource Division | 3.28 | 0 | 0 | 0
477 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Material Requisition To Resource Division | 226/Hug | 24/01/2023 | 0 | Resource Division | 2.85 | 0 | 0 | 0
478 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Quotation Bill foe New Service Connection at Bagnan W/S. Sch. Z-II | 158 | 03/08/2023 | 0 | WBSEDCL | 3.74 | 0 | 0 | 0
479 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Quotation Bill for New Service Connection at Bagnan W/S. Sch. Z-II |  | 01/08/2023 | 0 | WBSEDCL | 10.74 | 0 | 0 | 0
480 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | QUOTATION FOR WBSEDCL FOR ELECTRICAL DIVISION, PHE DTE. | C112223783044 | 21/11/2022 | 0 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 3.2 | 0 | 0 | 0
481 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Quotation bill for new service connection charge at Bagnan w/s scheme, Zone-II, T.W. No.-I | 182 | 11/08/2023 | 0 | WBSEDCL | 10.74 | 0 | 0 | 0
482 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Proposed AUGMENTATION of BAGNAN Zone-II Piped Water Supply Scheme with Laying Distribution System , FHTC & Construction of 1 No 3.6 M X 3.0 M Switch Room with Sanitary and Water Supply Arrangements &Boundary wall at Proposed T.W Site at DHANIAKHALI Block under Chinsurah Sub-Division Under Hooghly Division PHE | 2860/HUG | 16/12/2022 | 45 | M/S ROY CONSTRUCTION AND CO. | 35.29 | 0 | 0 | 35
483 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Proposed Laying Distribution within Kanuibanka Mouza , FHTC& Repairing Of Boundary Wall of Existing T.W-1 & T.W-2 for Augemntation Of BAGNAN ZONE-I Water Supply Scheme at Dhaniakhali Block under Chinsurah Sub-Divn. of Hooghly Division, P.H.E. Dte. | 2891/HUG | 22/12/2022 | 60 | M/S.N. ISLAM AND CO. | 85.47 | 81.31 | 95.13 | 70
484 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas of BAGNAN ZONE-I (Bagnan, Khanpur, Balarambati, Noapara, Mihirpur) PWSS under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | 2426/HUG | 11/08/2023 | 30 | TOTON MONDAL | 19.11 | 22.89 | 100 | 98
485 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement and Boundary Wall for Augmentation of BAGNAN Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.HE Dte. | 3314/HUG | 10/11/2023 | 45 | SRI KRISHNA ENTERPRISE | 8.61 | 16.78 | 100 | 95
486 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Laying / Repairing Pipeline in damaged portion including providing FHTC at the left out portions of Bhuina Para area with restoration of village road damaged due to proiving FHTC in Bagnan Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly | 121/CH | 16/02/2024 | 15 | TOTON MONDAL | 4.79 | 9.3 | 100 | 95
487 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Laying / Repairing Pipeline in damaged portion including providing FHTC at the left out portions of Brahman Para area with restoration of village road damaged due to proiving FHTC in Bagnan Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 122/CH | 16/02/2024 | 15 | JOY GURU ENTERPRISE | 4.79 | 9.23 | 100 | 95
488 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Laying / Repairing Pipeline in damaged portion including providing FHTC at the left out portions of Kayastha Para area with restoration of village road damaged due to proiving FHTC in Bagnan Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 126/CH | 16/02/2024 | 15 | JOY GURU ENTERPRISE | 4.79 | 9.33 | 100 | 95
489 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Bagnan PWSS 2. Bhanderhati PWSS 3. Cheragram PWSS 4. Chopa PWSS 5. Dhamaitikri PWSS 6. Dhaniakhali PWSS | 203/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 100 | 50
490 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Sinking of 1 no. 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BAGNAN W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. | 819/HUG | 11/03/2024 | 30 | TAPAS ADHYA | 14.7 | 13.9 | 100 | 100
491 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Shifting of Pipeline in damaged portion including providing FHTC at the left out portions of Bagdi Para area with restoration of village road damaged due to proiving FHTC in Bagnan Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 546/CH | 14/06/2024 | 7 | TOTON MONDAL | 4.79 | 4.69 | 100 | 95
492 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Shifting of Pipeline in damaged portion including providing FHTC at the left out portions of Pritala area with restoration of village road damaged due to proiving FHTC in Bagnan Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 547/CH | 14/06/2024 | 7 | JOY GURU ENTERPRISE | 4.79 | 4.73 | 100 | 95
493 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGNAN , SM/11867 | Augmentation | Electric quot. of WBSEDCL for New service Connection of Bagnan T/W-V W/S scheme under Electrical Division PHE Dte. (SM/11867) | BP-24-25-599 | 21/11/2024 | 0 | WBSEDCL | 5.92 | 0 | 0 | 0
494 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HAZIPUR WATER SUPPLY SCHEME , SM/11998 | Retrofitting | Providing 300 nos Functional Household Tap Connection (FHTC) within the command area of HAZIPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte | 16/Hug | 04/01/2022 | 30 | M/S T.K.B. CONSTRUCTION | 19.85 | 20.37 | 100 | 0
495 | HOOGHLY | Hooghly Division | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17626 | New | Material Requisition To Resource Division | 1234/32/Hug | 28/04/2023 | 0 | Resource Division | 15.57 | 0 | 0 | 0
496 | HOOGHLY | Hooghly Division | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17626 | New | Material Requisition To Resource Division | 1385/4/Hug | 15/05/2023 | 0 | Resource Division | 8.26 | 0 | 0 | 0
497 | HOOGHLY | Hooghly Division | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17626 | New | Material Requisition To Resource Division | 3057/20/Hug | 11/10/2023 | 0 | Resource Division | 8.26 | 0 | 0 | 0
498 | HOOGHLY | Hooghly Division | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17626 | New | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of PUKURIA Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 3718/HUG | 19/11/2024 | 90 | JOY GURU ENTERPRISE | 16.06 | 0 | 0 | 0
499 | HOOGHLY | Hooghly Division | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17626 | New | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of PUKURIA, GARMANDARAN Zone-I , GARMANDARAN Zone -II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3781/HUG | 25/11/2024 | 60 | KAJAL DEY | 55.4 | 0 | 0 | 0
500 | HOOGHLY | Electrical | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17626 | New | Quotation of New Service Connection for Pukhuria w/s Scheme,PH No-I,Block-Goghat-II,Dist-Hooghly under Electrical Division,PHE Dte.(SM/17626) Application No-5004294636 Reference Id-503691998 | 313 | 23/07/2024 | 0 | WBSEDCL | 4.01 | 0 | 0 | 0
501 | HOOGHLY | Electrical | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17626 | New | Quotation of New Service Connection for Pukuria w/s Scheme,PH No-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/17626) Application No-5004151686 Reference Id-503633620 | 101 | 05/05/2024 | 0 | WBSEDCL | 4.13 | 0 | 0 | 0
502 | HOOGHLY | Electrical | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17626 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Pukhuria water supply scheme, T.W. No. I, II, III & IV, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | 1733/ED | 19/04/2023 | 988 | B.T. PROJECT PVT. LTD. | 41.11 | 0 | 0 | 10
503 | HOOGHLY | Hooghly Division | GROUND WATER BASED PUKHURIA PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17626 | New | PUKHURIA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-II Block, District:- Hooghly [NEW SCHEME] | 2290/HUG | 03/08/2023 | 810 | M/S R.M. CONSTRUCTION | 360.54 | 68.78 | 19.08 | 10
504 | HOOGHLY | Electrical | Providing electro-mechanical equipments and other allied works for additional 2 Nos. Tube Well sources under Bandipur water supply scheme. , SM/18930 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bandipur water supply scheme, T.W. No. V, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | 174_ED | 01/02/2022 | 90 | M/S DILIP MITRA | 6.74 | 6.74 | 100 | 50
505 | HOOGHLY | Electrical | Providing electro-mechanical equipments and other allied works for additional 2 Nos. Tube Well sources under Bandipur water supply scheme. , SM/18930 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bandipur water supply scheme, T.W. No. VI, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | 3483/ED | 30/12/2022 | 90 | M/S S.R. ENTERPRISE | 10.82 | 10.8 | 100 | 30
506 | HOOGHLY | Electrical | Providing electro-mechanical equipments and other allied works for additional 2 Nos. Tube Well sources under Bandipur water supply scheme. , SM/18930 | Augmentation | Quotation Bill for New Service Connection at Bandipur W/S. Sch | 738 | 07/02/2024 | 0 | WBSEDCL | 18.99 | 0 | 0 | 0
507 | HOOGHLY | Electrical | Providing Electro-Mechanical Equipment and other allied works for additional 4Nos Tube Well Source Under Baruipara Water Supply Scheme , SM/18931 | Augmentation | Supply delivery and installation of Chlorinator for Baruipara w/s scheme PH No. VII District Hooghly under Electrical Division, PHE dte. | 83/HMSD | 14/01/2022 | 30 | M/S CHANDIMATA ELECTRICALS | 0.76 | 0.76 | 100 | 100
508 | HOOGHLY | Electrical | Providing Electro-Mechanical Equipment and other allied works for additional 4Nos Tube Well Source Under Baruipara Water Supply Scheme , SM/18931 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baruipara water supply scheme, T.W. No. VI, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | 171/ED | 01/02/2022 | 90 | ESENCE ENGINEERING CONCERN | 6.58 | 6.58 | 100 | 100
509 | HOOGHLY | Electrical | Providing Electro-Mechanical Equipment and other allied works for additional 4Nos Tube Well Source Under Baruipara Water Supply Scheme , SM/18931 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baruipara water supply scheme, T.W. No. VII, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | 172/ED | 01/02/2022 | 90 | RAJIB COMPANY | 6.59 | 6.59 | 100 | 100
510 | HOOGHLY | Electrical | Providing Electro-Mechanical Equipment and other allied works for additional 4Nos Tube Well Source Under Baruipara Water Supply Scheme , SM/18931 | Augmentation | Supply delivery and installation of Chlorinator for BARUIPARA w/s scheme PH No. VI District Hooghly under Electrical Division, PHE dte. | 103/HMSD | 18/01/2022 | 7 | STANDARD ELECTRICALS | 0.76 | 0.76 | 100 | 100
511 | HOOGHLY | Electrical | Providing Electro-Mechanical Equipment and other allied works for additional 4Nos Tube Well Source Under Baruipara Water Supply Scheme , SM/18931 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baruipara water supply scheme, T.W. No. V, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | 170/ED | 01/02/2022 | 90 | BIJAN ENTERPRISE | 6.63 | 6.57 | 100 | 100
512 | HOOGHLY | Electrical | Providing Electro-Mechanical Equipment and other allied works for additional 4Nos Tube Well Source Under Baruipara Water Supply Scheme , SM/18931 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baruipara water supply scheme, T.W. No.- IV, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | 2442_ED | 13/10/2023 | 45 | R.N.S. TRADING | 6.14 | 5.99 | 100 | 50
513 | HOOGHLY | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12265 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kumrul water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | 3468/ED | 30/12/2022 | 90 | DEY ENTERPRISE | 23.33 | 0 | 0 | 0
514 | HOOGHLY | Hooghly Division | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12265 | New | Material Requisition To Resource Division | 1386/30/Hug | 15/05/2023 | 0 | Resource Division | 26.93 | 0 | 0 | 0
515 | HOOGHLY | Hooghly Division | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12265 | New | Material Requisition To Resource Division | 3004/21/Hug | 05/10/2023 | 0 | Resource Division | 17.29 | 0 | 0 | 0
516 | HOOGHLY | Hooghly Division | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12265 | New | Material Requisition To Resource Division | 3059/3/Hug | 11/10/2023 | 0 | Resource Division | 26.93 | 0 | 0 | 0
517 | HOOGHLY | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12265 | New | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. CAR NO.- WB-04G-2822 | 139_AE-I/ED | 29/01/2024 | 151 | DASHRATH KUMAR PRAJAPATI | 0.72 | 0.14 | 19.87 | 0
518 | HOOGHLY | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12265 | New | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. | 139/AE-I/ED | 29/01/2024 | 151 | DASHRATH KUMAR PRAJAPATI | 0.72 | 0.43 | 59.6 | 5
519 | HOOGHLY | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12265 | New | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. | 139_/AE-I/ED | 29/01/2024 | 151 | DASHRATH KUMAR PRAJAPATI | 0.72 | 0.15 | 20.53 | 0
520 | HOOGHLY | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12265 | New | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. WB-04G-2822 From 01/06/2024 to 30/06/2024 | 330 | 30/07/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
521 | HOOGHLY | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12265 | New | Quotation Bill for New Service Connection at Kumrul W/S. Sch. TW-II | 699 | 22/01/2024 | 0 | WBSEDCL | 5.76 | 0 | 0 | 0
522 | HOOGHLY | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12265 | New | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. From 01.04.2024 to 30.04.2024 WB-04G-2822 | 145 | 22/05/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
523 | HOOGHLY | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12265 | New | Supply of diesel and mobile for inspection car of AE-I under Electrical Division PHE Dte. | 90 | 26/04/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
524 | HOOGHLY | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12265 | New | Quotation Bill for New Service Connection at Kumrul W/S. Sch. TW-I | 698 | 22/01/2024 | 0 | WBSEDCL | 5.23 | 0 | 0 | 0
525 | HOOGHLY | Electrical | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12265 | New | Supply of diesel & mobile oil for inspection car of AE-I under ED , PHE Dte. | 891 | 18/03/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
526 | HOOGHLY | Hooghly Division | KUMRUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12265 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 359.37 | 52.46 | 30
527 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18969 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at CHAPTA (2Nos.), SOMRA (2Nos.), NAMAJGRAM (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3360/HUG | 21/11/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 87.88 | 29.32 | 83.41 | 40
528 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18969 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in Somara-I GP of Balagrah Block. | 240/CH | 12/03/2024 | 30 | MAA BUNAMATA ENTERPRISE | 4.98 | 4.83 | 100 | 70
529 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18969 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in Somara-II GP of Balagrah Block. | 241/CH | 12/03/2024 | 30 | ASHA ENTERPRISE | 4.98 | 4.77 | 100 | 50
530 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18969 | Augmentation | Quotation for new service connection for source Augmentation of SOMRA Water Supply Scheme, PH NO- IV in the district Hooghly under Electrical Division,PHE Dte. ( SM/18969), Reference Id- 503814868 Application no- 5004498035 | 630 | 18/12/2024 | 0 | WBSEDCL | 8.62 | 0 | 0 | 0
531 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18969 | Augmentation | Quotation for new service connection for source Augmentation of SOMRA Water Supply Scheme, PH NO- III in the district Hooghly under Electrical Division,PHE Dte. ( SM/18969), Reference Id- 503814816 Application no- 5004497772 | 629 | 18/12/2024 | 0 | WBSEDCL | 8.47 | 0 | 0 | 0
532 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18969 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at CHAPTA (2Nos.), SOMRA (2Nos.), NAMAJGRAM (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3237/HUG | 06/11/2023 | 632 | M/S T.K.B. CONSTRUCTION | 59.02 | 0 | 0 | 60
533 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18969 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4492/ED | 23/11/2023 | 710 | MAA TARA CONSTRUCTION | 21.47 | 0 | 0 | 50
534 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18971 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at NAMAJGRAM (1No.), RAMESWARPUR (2Nos.), KAMARPARA (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3238/HUG | 06/11/2023 | 60 | NIGAM CONSTRUCTION | 59.08 | 0 | 0 | 0
535 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18971 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4494/ED | 23/11/2023 | 90 | R.K.ENTERPRISE | 21.48 | 0 | 0 | 0
536 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18971 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at NAMAJGRAM (1No.), RAMESWARPUR (2Nos.), KAMARPARA (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3361/HUG | 21/11/2023 | 45 | RAJU CONSTRUCTION | 87.09 | 14.22 | 40.81 | 75
537 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18971 | Augmentation | Quotation for new service connection for source Augmentation of Rameswarpur Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18971), Reference Id- 503733787 Application no- 5004386169 | 479 | 01/10/2024 | 0 | WBSEDCL | 4.53 | 0 | 0 | 0
538 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18971 | Augmentation | Quotation for new service connection for source Augmentation of Rameswarpur Water Supply Scheme, TW NO- IV in the district Hooghly under Electrical Division, PHE Dte. (SM/18971), Reference Id- 503726898 Application no- 5004370950 | 481 | 01/10/2024 | 0 | WBSEDCL | 4.15 | 0 | 0 | 0
539 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18971 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Rameswarpur PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 270/CH | 20/02/2025 | 10 | SAMRAT CONSTRUCTION | 2.68 | 0 | 0 | 0
540 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF KAMARPARA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18972 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at NAMAJGRAM (1No.), RAMESWARPUR (2Nos.), KAMARPARA (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3238/HUG | 06/11/2023 | 60 | NIGAM CONSTRUCTION | 59.08 | 0 | 0 | 0
541 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF KAMARPARA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18972 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF KAMARPARA PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4495/ED | 23/11/2023 | 90 | PADMA ENGINEERING CO. | 21.49 | 0 | 0 | 0
542 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF KAMARPARA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18972 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at NAMAJGRAM (1No.), RAMESWARPUR (2Nos.), KAMARPARA (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3361/HUG | 21/11/2023 | 45 | RAJU CONSTRUCTION | 87.09 | 13.45 | 38.61 | 75
543 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF KAMARPARA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18972 | Augmentation | Quotation for new service connection for source Augmentation of KAMARPARA Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18972), Reference Id-503777915 Application no- 5004449275 | BP-24-25-585 | 19/11/2024 | 0 | WBSEDCL | 4.12 | 0 | 0 | 0
544 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18981 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4504/ED | 23/11/2023 | 90 | GOENKA ENTERPRISE | 10.75 | 0 | 0 | 0
545 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18981 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at DHAMAITIKAR (2Nos.), JAYRAMBATI (2 Nos.), DEPARA (1 Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3725/HUG | 18/12/2023 | 60 | BIMAL KUMAR HALDER | 59.73 | 0 | 0 | 0
546 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18981 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at DHAMAITIKAR (2Nos.), GUPTIPARA (1No.), ABDULPUR (1 No.), DEPARA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3385/HUG | 22/11/2023 | 628 | OSMAN SEKH | 87.83 | 0 | 0 | 40
547 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18981 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site of Depara PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 243/CH | 19/02/2025 | 10 | SAMRAT CONSTRUCTION | 4.08 | 0 | 0 | 0
548 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18981 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Depara PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 263/CH | 20/02/2025 | 10 | SAMRAT CONSTRUCTION | 2.75 | 0 | 0 | 0
549 | HOOGHLY | Hooghly Division | PATUL W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12259 | New | Material Requisition To Resource Division | 1386/11/Hug | 15/05/2023 | 0 | Resource Division | 13.46 | 0 | 0 | 0
550 | HOOGHLY | Hooghly Division | PATUL W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12259 | New | Material Requisition To Resource Division | 1264/7/HUG | 03/05/2023 | 0 | Resource Division | 18.31 | 0 | 0 | 0
551 | HOOGHLY | Electrical | PATUL W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12259 | New | Quotation Bill for New Service Connection at Patul W/S. Sch. TW-I | 386 | 01/11/2023 | 0 | WBSEDCL | 5.36 | 0 | 0 | 0
552 | HOOGHLY | Electrical | PATUL W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12259 | New | Quotation Bill for New Service Connection at Patul W/S. Sch. TW-II | 402 | 09/11/2023 | 0 | WBSEDCL | 7.87 | 0 | 0 | 0
553 | HOOGHLY | Hooghly Division | PATUL W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12259 | New | Ground Water Based Piped Water Supply Schemes (PWSS) under POLBA-DADPUR Block at DALIMBA, GHATAMPUR, HASNAN, KAMRAI, KUCHPALA, PATUL, UTTAR BABNAN (ZONE-I) & UTTAR BABNAN (ZONE-II) Mouzas including Construction of different capacities R.C.C. Over Head Reservoirs (OHRs), Sinking of Tube Wells, Laying Distribution Systems (LDS), Laying Rising Main Interconnection pipelines, providing Functional Household Tap Connections (FHTCs), Construction of Switch Rooms, Boundary Walls etc. under Hooghly Division P.H.E. Dte. in connection with JJM. | 955/HUG | 30/03/2023 | 887 | GREEN ROYAL INFRA CON PVT LTD | 3672.07 | 340.16 | 77.03 | 15
554 | HOOGHLY | Electrical | PATUL W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12259 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Patul water supply scheme, T.W. No. I & II, Block: Polba-Dadpur, District - Hooghly under Electrical Division, PHE Dte. | 3473/ED | 30/12/2022 | 901 | CINZANO | 20.51 | 0 | 0 | 90
555 | HOOGHLY | Hooghly Division | Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Under POlba Dadpur Block , SM/18953 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3406/HUG | 23/11/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 27.84 | 80.57 | 50
556 | HOOGHLY | Electrical | Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Under POlba Dadpur Block , SM/18953 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4517/ED | 23/11/2023 | 90 | APEX ENGINEERING & PROJECT CO. | 10.74 | 0 | 0 | 90
557 | HOOGHLY | Hooghly Division | Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Under POlba Dadpur Block , SM/18953 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Malipara village under Polba Dadpur Block, Manipur village of Polba Dadpur Block and Prasadpur village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | 265/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
558 | HOOGHLY | Electrical | Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Under POlba Dadpur Block , SM/18953 | Augmentation | Quotation for new service connection at Goswamimalipara (Aug.) [SM/18953] W/s Sch., T/W No. - IV, Village & P. O. - Shenet, Dt. - Hooghly under Dadpur CCC, WBSEDCL, Ref. Id. - 503669411, Dt. - 11-07-2024, Application No. - 5004243696 | 311 | 22/07/2024 | 0 | WBSEDCL | 3.44 | 0 | 0 | 0
559 | HOOGHLY | Electrical | Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Under POlba Dadpur Block , SM/18953 | Augmentation | Quotation for new service connection at Goswamimalipara (Aug.)[SM/18953] W/S Sch., T/W No. - III, Block - Polba-dadpur, under Dadpur CCC, WBSEDCL, Ref Id. - 503619160, dt. - 25-06-2024, Application No. - 5004116875. | 263 | 03/07/2024 | 0 | WBSEDCL | 9.13 | 0 | 0 | 0
560 | HOOGHLY | Hooghly Division | Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Under POlba Dadpur Block , SM/18953 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3245/HUG | 06/11/2023 | 600 | TAPAS ADHYA | 59.64 | 0 | 0 | 20
561 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of DHIBAGNAN Water Supply Scheme , SM/07463 | Retrofitting | FHTC |  | 12/04/2021 | 0 | M/S PRADYUT KUMAR HAZRA | 75.95 | 0 | 0 | 0
562 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of DHIBAGNAN Water Supply Scheme , SM/07463 | Retrofitting | FHTC |  | 19/03/2021 | 0 | M/S PRADYUT KUMAR HAZRA | 65 | 0 | 0 | 0
563 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of DHIBAGNAN Water Supply Scheme , SM/07463 | Retrofitting | Providing 770 nos Functional Household Tap Connection (FHTC) within the command area of DIHIBAGNAN Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. Work Allotted : 385 Nos FHTC out of 770 Nos FHTC within the command area of DIHIBAGNAN Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Estimate Value : Rs. 1599635.50 (50% of Rs. 3199271.00) | 2230/Hug | 15/12/2021 | 30 | M/S T.K.B. CONSTRUCTION | 25.6 | 9.48 | 37.03 | 0
564 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of DHIBAGNAN Water Supply Scheme , SM/07463 | Retrofitting | Providing 100 nos Functional Household Tap Connection (FHTC) within Dihibagnan, Para Bagnan & Bhabanipur Village of Dihibagnan Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte.[Block-Arambagh] | 713/Hug | 07/04/2022 | 25 | BAKSHI ENTERPRISE | 11 | 6.39 | 58.09 | 0
565 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of DHIBAGNAN Water Supply Scheme , SM/07463 | Retrofitting | Providing 840 nos Functional Household Tap Connection (FHTC) within the command area of Dihibagnan Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 1915/Hug | 27/10/2021 | 40 | M/S PRADYUT KUMAR HAZRA | 40.43 | 35.11 | 100 | 0
566 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of DHIBAGNAN Water Supply Scheme , SM/07463 | Retrofitting | Material Requisition To Resource Division | 2196/HUG | 14/12/2021 | 0 | Resource Division | 1.59 | 0 | 0 | 0
567 | HOOGHLY | Hooghly Division | Raghubati Piped Water Supply Scheme. , SM/18672 | New | Material Requisition To Resource Division | 3057/27/Hug | 11/10/2023 | 0 | Resource Division | 10.81 | 0 | 0 | 0
568 | HOOGHLY | Electrical | Raghubati Piped Water Supply Scheme. , SM/18672 | New | Quotation Bill for New Service Connection at Raghubati W/S. Sch.TW-I | 392 | 03/11/2023 | 0 | WBSEDCL | 5.08 | 0 | 0 | 0
569 | HOOGHLY | Hooghly Division | Raghubati Piped Water Supply Scheme. , SM/18672 | New | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for RAGHUBATI Piped Water Supply Scheme underARAMBAGH Sub Division of Hooghly Division, P.H.E. Dte. | 3466/HUG | 04/10/2024 | 60 | P. B. ENTERPRISE(PINTU BHADURI) | 53.65 | 0 | 0 | 0
570 | HOOGHLY | Electrical | Raghubati Piped Water Supply Scheme. , SM/18672 | New | Quotation Bill for New Service Connection at Raghubati W/S. Sch | 737 | 07/02/2024 | 0 | WBSEDCL | 4.7 | 0 | 0 | 0
571 | HOOGHLY | Electrical | Raghubati Piped Water Supply Scheme. , SM/18672 | New | Additional Quotation of New Service Connection for Raghubati w/S Scheme,PH No-I, Block-Goghat-I Dist-Hooghly under Electrical Division PHE Dte.(SM/18672) Application No-100000123537 Reference Id-860318457 | 606 | 05/12/2024 | 0 | WBSEDCL | 0.96 | 0 | 0 | 0
572 | HOOGHLY | Electrical | Raghubati Piped Water Supply Scheme. , SM/18672 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Raghubati water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | 3412/ED | 10/08/2023 | 541 | M/S NABIN GOPAL SENGUPTA | 20.36 | 5.21 | 25.57 | 50
573 | HOOGHLY | Hooghly Division | Raghubati Piped Water Supply Scheme. , SM/18672 | New | RAGHUBATI, SUNIA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at GOGHAT-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. [NEW SCHEME] | 2363/HUG | 08/08/2023 | 809 | P.B. ENTERPRISE (PINTU BHADURI) | 1481.45 | 434.8 | 55.22 | 50
574 | HOOGHLY | Electrical | Source Augmentation Of BAIKUNTHAPUR piped Water Supply Scheme under Pursurah Block , SM/18961 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of BAIKUNTHAPUR piped Water Supply Scheme Block- Pursura District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4522/ED | 23/11/2023 | 90 | TRIDENT ENTERPRISE | 22.03 | 0 | 0 | 0
575 | HOOGHLY | Hooghly Division | Source Augmentation Of BAIKUNTHAPUR piped Water Supply Scheme under Pursurah Block , SM/18961 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PABA (1 NO.),BAIKUNTHAPUR (2Nos.),SAOTA (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3475/HUG | 29/11/2023 | 45 | CIVIL CRAFT | 88.67 | 26.32 | 74.21 | 60
576 | HOOGHLY | Hooghly Division | Source Augmentation Of BAIKUNTHAPUR piped Water Supply Scheme under Pursurah Block , SM/18961 | Augmentation | Construction of 3 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 3 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 3 Nos. T.W & Distribution at BAIKUNTHAPUR (1Nos.), SAOTA (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3352/HUG | 17/11/2023 | 778 | A.R. CONSTRUCTION | 35.75 | 0 | 0 | 20
577 | HOOGHLY | Hooghly Division | Source Augmentation of PABA Piped Water Supply Scheme under Goghat-II Block , SM/18963 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PABA (1 NO.),BAIKUNTHAPUR (2Nos.),SAOTA (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3475/HUG | 29/11/2023 | 45 | CIVIL CRAFT | 88.67 | 0 | 0 | 60
578 | HOOGHLY | Electrical | Source Augmentation of PABA Piped Water Supply Scheme under Goghat-II Block , SM/18963 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Paba water supply scheme, T.W. No. III, Block: Goghat-II, District - Hooghly under Electrical Division, PHE Dte. | 2046/ED | 01/12/2022 | 90 | M/S G P ENTERPRISE | 11.11 | 10.8 | 100 | 30
579 | HOOGHLY | Hooghly Division | Source Augmentation of PABA Piped Water Supply Scheme under Goghat-II Block , SM/18963 | Augmentation | Connection of T.W. No. III with distribution, Construction of 5.4 x 3.65 m Pump Room with Sanitary arrangement and Boundary Wall at PABA Piped Water Supply Scheme under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. | 3482/HUG | 29/11/2023 | 60 | DHIRENDRA ENGINEERING & CONSTRUCTION | 23.74 | 17.73 | 100 | 100
580 | HOOGHLY | Electrical | Source Augmentation of HARADITYA Piped Water Supply Scheme under Arambag Block , SM/18964 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of HARADITYA Piped Water Supply Scheme Block- Arambag District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4524/ED | 23/11/2023 | 90 | WIZARDTECH SOLUTION | 21.49 | 0 | 0 | 0
581 | HOOGHLY | Hooghly Division | Source Augmentation of HARADITYA Piped Water Supply Scheme under Arambag Block , SM/18964 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at HARADITYA (2Nos.),GOURHATI (2Nos.),MAINAN (1No.)W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3476/HUG | 29/11/2023 | 45 | SPG ENTERPRISES | 87.88 | 0 | 0 | 20
582 | HOOGHLY | Hooghly Division | Source Augmentation of HARADITYA Piped Water Supply Scheme under Arambag Block , SM/18964 | Augmentation | Construction of 6 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at HARADITYA (2Nos.), GOURHATI (2Nos.), MAINAN (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3312/HUG | 10/11/2023 | 546 | DILIP KUMAR GHOSH | 70.72 | 0 | 0 | 32
583 | HOOGHLY | Electrical | Source Augmentation of Baksa W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] , SM/19161 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Baksa water supply scheme, T.W. No. I, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | 117/ED | 15/01/2024 | 90 | M.S.C. ENTERPRISE | 10.24 | 9.94 | 97.07 | 80
584 | HOOGHLY | Hooghly Division | Source Augmentation of Baksa W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] , SM/19161 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of BAKSA Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.HE Dte. within Chanditala-II Block. | 1536/HUG | 24/05/2023 | 30 | GHOSH ENTERPRISE | 11.79 | 9.45 | 100 | 100
585 | HOOGHLY | Electrical | Source Augmentation of Baksa W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] , SM/19161 | Augmentation | Additional quotation for Baksa w/s scheme against application no.- 5003987334 Ref ID: 860295228 | 13 | 04/04/2024 | 0 | WBSEDCL | 0.93 | 0 | 0 | 0
586 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. , SM/07436 | Retrofitting | FHTC |  | 21/09/2021 | 0 | M/S S.G. CONSTRUCTION | 23.77 | 0 | 0 | 0
587 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. , SM/07436 | Retrofitting | FHTC |  | 21/09/2021 | 0 | MS PRADIP KUMAR PAL | 14.04 | 0 | 0 | 0
588 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. , SM/07436 | Retrofitting | FHTC |  | 23/07/2021 | 0 | M/S S.G. CONSTRUCTION | 23.14 | 0 | 0 | 0
589 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. , SM/07436 | Retrofitting | FHTC |  | 23/07/2021 | 0 | MS PRADIP KUMAR PAL | 10.4 | 0 | 0 | 0
590 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. , SM/07436 | Retrofitting | Providing 400 nos Functional Household Tap Connection (FHTC) within the command area of Kulihanda & AMODGHATA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 116/Hug | 19/01/2022 | 20 | R.K. TRADERS | 25.16 | 24.33 | 96.7 | 0
591 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. , SM/07436 | Retrofitting | Construction of 3.65 m X 3.60 m Switch Room with Sanitary & Water Supply & Sanitation Arrangement at 4th T/W Site of Kulihanda W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | 399/CH | 06/05/2022 | 35 | SADHUKHAN ENTERPRISE | 4.99 | 4.2 | 84.28 | 0
592 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. , SM/07436 | Retrofitting | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KULIHANDA PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 135/S&WSD | 12/08/2022 | 15 | ASHUTOSH DAS & CO | 5 | 4.78 | 100 | 0
593 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. , SM/07436 | Retrofitting | SUPPLY & DELIVERY OF CONSUMABLES AND OTHERS WORKS AT SITE FOR construction of tube well at kulihanda pwss, polba dadpur block, hooghly district under cdd, phe dte. | 136/S&WSD | 12/08/2022 | 15 | ASHUTOSH DAS & CO | 4.99 | 2.73 | 100 | 0
594 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. , SM/07436 | Retrofitting | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT KULIHANDA PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 134/S&WSD | 12/08/2022 | 15 | ASHUTOSH DAS & CO | 3.92 | 3.74 | 50 | 0
595 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. , SM/07436 | Retrofitting | Providing 800 nos Functional Household Tap Connection (FHTC) within the command area of Kulihanda Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 1677/hug | 13/09/2021 | 30 | EVEREST CONSULTANT SERVICES | 35.63 | 33.42 | 100 | 0
596 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. , SM/07436 | Retrofitting | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | 1724/CDD | 29/12/2022 | 30 | DEY ENTERPRISE | 13.83 | 0 | 100 | 0
597 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. , SM/07436 | Retrofitting | Connection of 4th T.W. with existing distribution pipe line at Kulihanda W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | 824/CH | 31/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.96 | 0.96 | 100 | 80
598 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. , SM/07436 | Retrofitting | Sinking of 2 (Two) No Big dia tube well (250 mm X 150 mm) with supply of PVC Pipe and strainer and having depth upto 180 M at 3rd TW site of Kulihanda W/S Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | 817/HUG | 11/03/2024 | 30 | M/S. R. M. CONSTRUCTION | 19.52 | 12.49 | 42.1 | 100
599 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. , SM/07436 | Retrofitting | Providing FHTC at the left out portions of Different area for providing FHTC in Kulihanda Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 215/CH | 29/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.98 | 0.94 | 49.04 | 45
600 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. , SM/07436 | Retrofitting | Laying of HDPE Pipeline for providing FHTC at the left out portions of at Kulihanda Piped Water Supply Scheme under Chinsurah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 216/CH | 29/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.98 | 0.98 | 100 | 45
601 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULIHANDA WATER SUPPLY SCHEME. , SM/07436 | Retrofitting | Providing 1969 nos F.H.T.C. in Kulihanda (CT) Village of Kulihanda and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah Mogra] | 457CH | 01/10/2022 | 50 | MLG CONSTRUCTION | 102.5 | 0 | 0 | 0
602 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Mandaran Water Supply Scheme , SM/06993 | Retrofitting | FHTC |  | 17/08/2021 | 0 | MAA TARA CONSTRUCTION | 12.88 | 0 | 0 | 0
603 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Mandaran Water Supply Scheme , SM/06993 | Retrofitting | .... | 844334 | 19/08/2021 | 0 | MOUMITA SINGHA BHATTACHATYA | 0.48 | 0 | 0 | 0
604 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Mandaran Water Supply Scheme , SM/06993 | Retrofitting | Placement of Fund | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
605 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Mandaran Water Supply Scheme , SM/06993 | Retrofitting | Providing 823 nos F.H.T.C. in the Rudrashanda,Mandaran & Sankpur village of Mandaran and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | 1691/Hug | 17/12/2020 | 182 | MAA TARA CONSTRUCTION | 38.75 | 0 | 0 | 0
606 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Mandaran Water Supply Scheme , SM/06993 | Retrofitting | Material Requisition To Resource Division | 2097/34/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0 | 0
607 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. , SM/07949 | Retrofitting | FHTC |  | 06/04/2021 | 0 | M/S BISWAS CONSTRUCTION | 7.43 | 0 | 0 | 0
608 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. , SM/07949 | Retrofitting | FHTC |  | 12/04/2021 | 0 | GOBINDA MAITY | 3.29 | 0 | 0 | 0
609 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. , SM/07949 | Retrofitting | FHTC |  | 19/03/2021 | 0 | M/S BISWAS CONSTRUCTION | 12 | 0 | 0 | 0
610 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. , SM/07949 | Retrofitting | FHTC |  | 15/03/2021 | 0 | GOBINDA MAITY | 16.4 | 0 | 0 | 0
611 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. , SM/07949 | Retrofitting | Providing 600 nos Functional Household Tap Connection (FHTC) within the command area of GURAP Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 115/Hug | 19/01/2022 | 30 | MERCANTILE HALL | 43.98 | 44.14 | 100 | 100
612 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. , SM/07949 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of GURAP Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 1511/HUG | 22/07/2022 | 15 | R CONSTRUCTION | 19.73 | 17.48 | 100 | 100
613 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. , SM/07949 | Retrofitting | Placement of Fund | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
614 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. , SM/07949 | Retrofitting | Rising Main Pipe line in between 3rd T.W By to pass arrangement and interconnection with Distribution System for Gurap Water Supply Scheme Under Chinsurah Sub-Division. | 111/CH | 10/02/2022 | 25 | M/S S.G. CONSTRUCTION | 4.18 | 0 | 0 | 0
615 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. , SM/07949 | Retrofitting | Rising Main in between 2nd T.W to O.H.R Bypass arrangement and interconnection with Distribution System for Gurap Water Supply Scheme Under Chinsurah Sub-Division. | 398/CH | 06/05/2022 | 35 | M/S S.G. CONSTRUCTION | 2.69 | 0 | 0 | 100
616 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. , SM/07949 | Retrofitting | Rising Main in between 2nd T.W to OHR Bypass arrangement and interconnection with Distribution System for Gurap Water Supply Scheme Under Chinsurah Sub-Division. | 398/CH | 06/05/2022 | 35 | M/S S.G. CONSTRUCTION | 2.69 | 2.66 | 100 | 100
617 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AYMA NABABPUR WATER SUPPLY SCHEME. , SM/07957 | Retrofitting | FHTC |  | 30/09/2021 | 0 | JAL PRAVAHIKA PVT. LTD | 32.84 | 0 | 0 | 0
618 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AYMA NABABPUR WATER SUPPLY SCHEME. , SM/07957 | Retrofitting | Making Interconnection from newly bored tube well to existing distribution system at Dwarbasini under Dwarbasini Water Supply Scheme Under Chinsurah Subdivision under Hooghly division, PHE Dte. | 819/CH | 31/08/2023 | 15 | JOY GURU ENTERPRISE | 0.85 | 0.86 | 100 | 95
619 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AYMA NABABPUR WATER SUPPLY SCHEME. , SM/07957 | Retrofitting | Providing1663 nos F.H.T.C. in Bhuinpara, Sachitara,Kantagar & Prasadpur Village of Ayma Nababpur and its Adjoining Mouzas Water Supply Scheme UnderChinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | 932/HUG | 06/05/2021 | 40 | JAL PRAVAHIKA PVT. LTD | 13.14 | 13.14 | 100 | 100
620 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AYMA NABABPUR WATER SUPPLY SCHEME. , SM/07957 | Retrofitting | Material Requisition To Resource Division | 2097/31/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0 | 0
621 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | Repairing of Office Floor, Roof, main gate, painting of Boundary Wall, pump room etc. of Serampore Sub Division Office cum Head Work Site under Serampore Sub Division PHE Dte. (PHASE-II) | 129/SER | 10/09/2021 | 30 | DHIRENDRA ENGINEERING & CONSTRUCTION | 3.62 | 3.6 | 99.35 | 0
622 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | LAYING OF PIPELINE |  | 28/01/2022 | 0 | P.B. ENTERPRISE (PINTU BHADURI) | 6.42 | 0 | 0 | 0
623 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | Transportation charge for carriage and distribution of 300 ml. drinking Water Pouch packet from MTU placed at Arambagh, Khanakul to flood affected zone of Arambagh, Khanakul-I, Khanakul-II, Goghat-I & Pursurah Block during flood including loading, unloading and distribution considering flood like situation (August-2021). | 326/Arg | 02/08/2021 | 3 | M/S TANISA ENTERPRISE | 11.14 | 0 | 0 | 0
624 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | Repairing Work of O.H.R, Switch Room, Boundary Wall of Head Work & Spiral Stair Case of O.H.R. at Furfura water supply scheme under Serampore Sub-Division, P.H.E. Dte. (Damaged during AMPHAN) | 308/SER | 24/02/2022 | 30 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 4.3 | 0 | 0 | 0
625 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | Disinfection of spot sources of 36 nos. DWP / Mark-II and 164 nos. Ordinary tube well for flood situation at Khanakul-II Blocks under RWS Hooghly Sub-Divison under Hooghly Division, P.H.E. Dte. | 911/RWS | 07/08/2021 | 5 | TANISA ENTERPRISE | 0.48 | 0 | 0 | 0
626 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | DISINFECTION OF SPOT SOURCES OF 36NOS. DWP/ MARK - II AND 164 NOS. ORDINARY TUBE WELL FOR FLOOD SITUATION AT KHANAKUL-II BLOCKS UNDER RWS HOOGHLY SUB-DIVISION, P.H.E DTE. (PHASE - II) | 1000/hug | 01/10/2021 | 5 | TANISA ENTERPRISE | 0.47 | 0 | 0 | 0
627 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | DISINFECTION OF SPOT SOURCES OF 28NOS. DWP/ MARK - II AND 134 NOS. QRDINARY TUBE WELL FOR FLOOD SITUATION AT ARAMBAGH , GOGHAT - I & II AND KHANAKUL I & II BLOCKS UNDER RWS HOOGHLY SUB-DIVISION, P.H.E DTE. (PHASE - II) | 314/D/HUG | 07/01/2023 | 5 | ROY ENTERPRISE | 3.92 | 0 | 0 | 0
628 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | Repairing work of O.H.R. and allied works of Boundary Wall, Gate, Pump room etc. at PURBATAJPUR water supply scheme due to damages caused by Super Cyclone "AMPHAN" Under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 1919/Hug | 27/10/2021 | 30 | A.M. ENTERPRISE | 6.79 | 6.19 | 100 | 0
629 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | Distribution of Water Pouch at flood affected areas of Khanakul-I, Khanakul-II, Pursurah, Arambagh, and Goghat-I Block under Arambagh Sub-Division of Hooghly Division PHE Dte., Dist. Hooghly. (Aug-2021) | 336/Arg | 06/08/2021 | 3 | M/S TANISA ENTERPRISE | 4.07 | 4.07 | 100 | 0
630 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | Relaying of UPVC pipes & specials damaged during AMPHAN with construction of 12 nos. Street Standpost for Chanditala W/S Scheme under Serampore Sub - Division P.H.E. Dte. | 306/SER | 24/02/2022 | 20 | M/S SHIVAM UDYOG | 1.7 | 1.7 | 100 | 0
631 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | Restoration of Flood damaged portion of KAKNAN Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte., Dist. Hooghly. [ Block-Khanakul-II] | 620/Arg | 01/09/2022 | 15 | TITAS CONSTRUCTION | 4.98 | 4.89 | 100 | 0
632 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | Restoration of Flood damaged portion of LAKSHMIPUR & BALI Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte., Dist. Hooghly. [ Block-Goghat-I] | 727/Arg | 29/09/2022 | 15 | DHIRENDRA ENGINEERING & CONSTRUCTION | 2.23 | 2.23 | 100 | 0
633 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | Restoration of Flood damaged portion of KISHORPUR Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte., Dist. Hooghly. [ Block-Khanakul-I] | 617/Arg | 01/09/2022 | 15 | TITAS CONSTRUCTION | 4.84 | 4.77 | 100 | 0
634 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | Connection of Over Flow to the Discharge for the Pratapnagar, Gobindapur & Purbaraypur W/S Scheme under Arambagh Sub-Division P.H.E. Dte. | 622/Arg | 01/09/2022 | 15 | TITAS CONSTRUCTION | 3.73 | 3.12 | 100 | 0
635 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | Restoration of Flood damaged portion of GHORADAHA Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte., Dist. Hooghly. [ Block-Khanakul-II] PART-B | 619/Arg | 01/09/2022 | 15 | TITAS CONSTRUCTION | 4.92 | 4.86 | 100 | 0
636 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | DISINFECTION OF SPOT SOURCES OF 28NOS. DWP/ MARK - II AND 134 NOS. QRDINARY TUBE WELL FOR FLOOD SITUATION AT ARAMBAGH , GOGHAT - I & II AND KHANAKUL I & II BLOCKS UNDER RWS HOOGHLY SUB-DIVISION, P.H.E DTE. (PHASE - II) | 1823/HUG | 01/10/2021 | 5 | ROY ENTERPRISE | 3.92 | 3.92 | 100 | 0
637 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | DISINFECTION OF SPOT SOURCES OF 243 NOS. DWP/ MARK - II AND 1107 NOS. QRDINARY TUBE WELL FOR FLOOD SITUATION AT KHANAKUL-I & II BLOCKS UNDER RWS HOOGHLY SUB-DIVISION, P.H.E DTE. (PHASE - I) | 1817/HUG | 01/10/2021 | 5 | HAZRA CONSTRUCTION | 3.2 | 3.2 | 100 | 0
638 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | Connection of Over Flow to the Discharge for the Arandi & Kishorpur W/S Scheme under Arambagh Sub-Division P.H.E. Dte. | 621/Arg | 01/09/2022 | 15 | TITAS CONSTRUCTION | 3.85 | 3.46 | 100 | 0
639 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | Restoration of Flood damaged portion of GHORADAHA Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte., Dist. Hooghly. [ Block-Khanakul-II] PART-A | 618/Arg | 01/09/2022 | 15 | TITAS CONSTRUCTION | 2.73 | 2.69 | 100 | 0
640 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | DISINFECTION OF SPOT SOURCES OF 28NOS. DWP/ MARK - II AND 134 NOS. QRDINARY TUBE WELL FOR FLOOD SITUATION AT JANGIPARA, ARAMBAGH & RARAKESWAR BLOCKS UNDER RWS HOOGHLY SUB-DIVISION, P.H.E DTE. (PHASE - I) | 1358/HUG | 07/08/2021 | 5 | ARUN SEAL AND CO. | 0.38 | 0.38 | 100 | 0
641 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | DISINFECTION OF SPOT SOURCES OF 28NOS. DWP/ MARK - II AND 134 NOS. QRDINARY TUBE WELL FOR FLOOD SITUATION AT KHANAKUL - I & II BLOCKS UNDER RWS HOOGHLY SUB-DIVISION, P.H.E DTE. (PHASE - II) | 1824/HUG | 01/10/2021 | 5 | M/S RAJKUMAR KHAN | 2.5 | 2.5 | 100 | 0
642 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | DISINFECTION OF SPOT SOURCES OF 28NOS. DWP/ MARK - II AND 134 NOS. QRDINARY TUBE WELL FOR FLOOD SITUATION AT GOGHAT - I & II, KHANAKUL - I & II, BLOCKS UNDER RWS HOOGHLY SUB-DIVISION, P.H.E DTE. (PHASE - I) | 1359/HUG | 07/08/2021 | 5 | TITAS CONSTRUCTION | 3.8 | 3.8 | 100 | 0
643 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | DISINFECTION OF SPOT SOURCES OF 216 NOS. DWP/ MARK - II AND 983 NOS. QRDINARY TUBE WELL FOR FLOOD SITUATION AT KHANAKUL - I & II BLOCKS UNDER RWS HOOGHLY SUB-DIVISION, P.H.E DTE. (PHASE - II) | 1816/HUG | 01/10/2021 | 5 | M/S PRADYUT KUMAR HAZRA | 2.84 | 2.84 | 100 | 0
644 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | Disinfection of spot sources of 36 nos. DWP / Mark-II and 164 nos. Ordinary tube well for flood situation at Khanakul-II Blocks under RWS Hooghly Sub-Divison under Hooghly Division, P.H.E. Dte. | 1370/HUG | 07/08/2021 | 5 | TANISA ENTERPRISE | 0.48 | 0.48 | 100 | 0
645 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | Disinfection of spot sources of 112 nos. DWP / Mark-II and 507 nos. Ordinary tubewell for flood situation at Khanakul-II Blocks under RWS Hooghly Sub-Division under Hooghly Division, P.H.E. Dte. | 1369/HUG | 09/08/2021 | 7 | DILIP KUMAR GHOSH | 1.47 | 1.47 | 100 | 0
646 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | Disinfection of spot sources of 124 nos. DWP / Mark-II and 563 nos. Ordinary tubewell for flood situation at Khanakul-II Blocks under RWS Hooghly Sub-Division under Hooghly Division, P.H.E. Dte. [Phase - II] | 1838/HUG | 04/10/2021 | 5 | GLOBAL CONSTRUCTION | 1.63 | 1.63 | 100 | 0
647 | HOOGHLY | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. , SM/09025 | Disaster | DISINFECTION OF SPOT SOURCES OF 36NOS. DWP/ MARK - II AND 164 NOS. ORDINARY TUBE WELL FOR FLOOD SITUATION AT KHANAKUL-II BLOCKS UNDER RWS HOOGHLY SUB-DIVISION, P.H.E DTE. (PHASE - II) | 1815/hug | 01/10/2021 | 5 | TANISA ENTERPRISE | 0.47 | 0.47 | 100 | 0
648 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09773 | Retrofitting | Providing additional 20 nos FHTC in Morhal PWSS | 165/SER. | 26/10/2021 | 35 | TOTON MONDAL | 1.35 | 1.35 | 100 | 0
649 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09773 | Retrofitting | Providing Add. 90 nos FHTC within the Morhal PWSS | 164/Ser | 26/10/2021 | 30 | ARUN SEAL AND CO. | 3.78 | 3.78 | 100 | 0
650 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09773 | Retrofitting | Providing additional 800 nos Functional Household Tap Connection (FHTC) within the command area of Morhal Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | 470/Hug | 26/02/2021 | 30 | M/S SHIVAM UDYOG | 29.36 | 3.42 | 23.28 | 0
651 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09773 | Retrofitting | Construction of 3.6 m. X 3.0 m. Switch Room without sanitary and water supply arrangement at 3rd tube well site of Morhal W/S Scheme under Serampore Sub-Division of Hooghly Division, P. H. E. Directorate. | 297/SER | 21/02/2022 | 30 | BAKSHI ENTERPRISE | 3.32 | 1.89 | 100 | 0
652 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09773 | Retrofitting | Providing 150 nos Functional Household Tap Connection (FHTC) within the command area of RADHABALLAVPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte | 2232/Hug | 15/12/2021 | 20 | DREAM INFRASTRUCTURE | 4.92 | 4.91 | 100 | 100
653 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09773 | Retrofitting | Providing 250 nos Functional Household Tap Connection (FHTC) within the command area of Morhal Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte | 2206/Hug | 14/12/2021 | 20 | ARUN SEAL AND CO. | 13.6 | 13.66 | 100 | 100
654 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09773 | Retrofitting | Additional Work for Laying HDPE pipes & specials for connection with Main pipe line of Morhal Water Supply Scheme from Shaw para Kali Mandir to House of Harimohan Shaw under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 309/SER | 29/12/2023 | 30 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 1 | 1 | 100 | 100
655 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09773 | Retrofitting | Additional Work for Laying HDPE pipes & specials for connection with Main pipe line of Morhal Water Supply Scheme from House of Harimohan Shaw to Jora Culvert under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 308/SER | 29/12/2023 | 30 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 1 | 1 | 100 | 100
656 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09773 | Retrofitting | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Kotalpur PWSS 2. Morhal PWSS 3. Borhal PWSS 4. Antpur PWSS 5. Rajbalhat PWSS 6. Gopalpur-I PWSS | 113/SER | 23/02/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 80
657 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09773 | Retrofitting | Repairing of Damaged Road due to FHTC Works at Western zone of Morhal W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | 553/SER | 19/09/2024 | 7 | TOTON MONDAL | 4.97 | 4.39 | 46.87 | 98
658 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09773 | Retrofitting | Laying CI/DI pipes & specials for connection with Main pipe line & T.W. No.-3 and interconnection including allied work with laying distribution system for Development of Morhal Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. SL NO - 08 | 2089/Hug | 21/09/2022 | 30 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 14.32 | 14.32 | 99.99 | 99
659 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09773 | Retrofitting | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of MORHAL Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | 390/HUG | 08/02/2024 | 60 | BANSBERIA CONSTRUCTION CO. | 31.57 | 0 | 0 | 75
660 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09773 | Retrofitting | Repairing of Switch Room & Boundary Wall at existing TW sites, and Construction of Boundary wall at 3rdT.W Site of MORHAL Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 827/HUG | 11/03/2024 | 30 | BAKSHI ENTERPRISE | 13.28 | 5.92 | 44.56 | 60
661 | HOOGHLY | Hooghly Division | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12256 | New | Material Requisition To Resource Division | 1386/46/Hug | 15/05/2023 | 0 | Resource Division | 19.93 | 0 | 0 | 0
662 | HOOGHLY | Hooghly Division | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12256 | New | Material Requisition To Resource Division | 3059/37/Hug | 11/10/2023 | 0 | Resource Division | 19.93 | 0 | 0 | 0
663 | HOOGHLY | Hooghly Division | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12256 | New | Material Requisition To Resource Division | 1264/14/HUG | 03/05/2023 | 0 | Resource Division | 42.75 | 0 | 0 | 0
664 | HOOGHLY | Electrical | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12256 | New | Lokabati PH__II Water supply Scheme | 724 | 05/02/2024 | 0 | WBSEDCL | 17.53 | 0 | 0 | 0
665 | HOOGHLY | Electrical | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12256 | New | Lokabati PH__I Water supply Scheme | 725 | 05/02/2024 | 0 | WBSEDCL | 4.7 | 0 | 0 | 0
666 | HOOGHLY | Hooghly Division | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12256 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 371.19 | 63.91 | 30
667 | HOOGHLY | Hooghly Division | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12256 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme under Dhaniakhali Block (Part-III) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. | 407/CH | 10/03/2025 | 15 | TECHVISION | 4.2 | 0 | 0 | 0
668 | HOOGHLY | Electrical | LOKABATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12256 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Lokabati water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | 3469/ED | 30/12/2022 | 945 | INDRANI ENTERPRISE | 22.4 | 0 | 0 | 75
669 | HOOGHLY | Hooghly Division | BASUBATI PIPED WATER SUPPLY SCHEME , SM/12365 | New | Material Requisition To Resource Division | 2471/3/Hug | 18/11/2022 | 0 | Resource Division | 19.58 | 0 | 0 | 0
670 | HOOGHLY | Hooghly Division | BASUBATI PIPED WATER SUPPLY SCHEME , SM/12365 | New | Sinking of Five Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ATISARA, NANDA, NOWPARA, BASUBATI & ASTARA PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | 878/HUG | 27/03/2023 | 45 | MS D.PALIT AND CO. | 62.24 | 11.16 | 89.66 | 100
671 | HOOGHLY | Electrical | BASUBATI PIPED WATER SUPPLY SCHEME , SM/12365 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Basubati water supply scheme, T.W. No. III, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | 3446/ED | 11/08/2023 | 90 | BISALAXMI ENTERPRISE | 11.5 | 0 | 0 | 0
672 | HOOGHLY | Hooghly Division | BASUBATI PIPED WATER SUPPLY SCHEME , SM/12365 | New | Material Requisition To Resource Division | 109/1/Hug | 10/01/2023 | 0 | Resource Division | 55.09 | 0 | 0 | 0
673 | HOOGHLY | Hooghly Division | BASUBATI PIPED WATER SUPPLY SCHEME , SM/12365 | New | Material Requisition To Resource Division | 01/11/Hug | 02/01/2023 | 0 | Resource Division | 19.58 | 0 | 0 | 0
674 | HOOGHLY | Hooghly Division | BASUBATI PIPED WATER SUPPLY SCHEME , SM/12365 | New | Material Requisition To Resource Division | 1383/9/Hug | 15/05/2023 | 0 | Resource Division | 19.93 | 0 | 0 | 0
675 | HOOGHLY | Electrical | BASUBATI PIPED WATER SUPPLY SCHEME , SM/12365 | New | Quotation for new service connection at Basubati W/S Sch, TW-I (Head Work site), Dist. Hooghly | 90 | 13/07/2023 | 0 | WBSEDCL | 3.85 | 0 | 0 | 0
676 | HOOGHLY | Electrical | BASUBATI PIPED WATER SUPPLY SCHEME , SM/12365 | New | Quotation Bill for New Service Connection at Basubati W/S. Sch. TW-II | 553 | 21/12/2023 | 0 | WBSEDCL | 2.59 | 0 | 0 | 0
677 | HOOGHLY | Electrical | BASUBATI PIPED WATER SUPPLY SCHEME , SM/12365 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Basubati water supply scheme, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | 3484/ED | 30/12/2022 | 90 | ASHUTOSH DAS & CO. | 23.01 | 22.71 | 98.66 | 90
678 | HOOGHLY | Hooghly Division | BASUBATI PIPED WATER SUPPLY SCHEME , SM/12365 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at ATISARA, NANDA, NAWPARA,BASUBATI & ASTARA W/S Scheme underChandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | 1818/HUG | 22/06/2023 | 45 | OSMAN SEKH | 80.85 | 15.99 | 100 | 100
679 | HOOGHLY | Hooghly Division | BASUBATI PIPED WATER SUPPLY SCHEME , SM/12365 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Basubati PWSS, Purushottampur PWSS, Nawpara PWSS, Bighati Z-II PWSS, Shibrambati Z-I PWSS, Sinhal Pathan PWSS) | 303/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 50 | 100
680 | HOOGHLY | Hooghly Division | BASUBATI PIPED WATER SUPPLY SCHEME , SM/12365 | New | Construction of 500 cum capacity OHR with 20 mtr. staging height including Soil Investigation work, Laying Distribution System, Rising Main& Interconnection between O.H.R, TW No-I & II, Construction of 1 No 5.4M X 3.6M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at Head Work Site, Construction of 1 No 3.6M x 3.0M Switch Room with Sanitary & Water Supply arrangement & Boundary Wall at 2nd T/W Site including Providing FHTC in BASUBATI Water Supply Scheme at SINGUR Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | 683/Hug | 10/03/2023 | 935 | MINTU CHAKRABORTY | 618.81 | 221.78 | 35.84 | 70
681 | HOOGHLY | Hooghly Division | BASUBATI PIPED WATER SUPPLY SCHEME , SM/12365 | New | Sinking of 1no. additional tubewell with Construction of switch-room, Tubewell connection & Other works at BASUBATI Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | 670/HUG | 12/03/2025 | 90 | MINTU CHAKRABORTY | 92.31 | 0 | 0 | 0
682 | HOOGHLY | Hooghly Division | DURGAPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12243 | New | Material Requisition To Resource Division | 1386/19/Hug | 15/05/2023 | 0 | Resource Division | 12.09 | 0 | 0 | 0
683 | HOOGHLY | Hooghly Division | DURGAPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12243 | New | Material Requisition To Resource Division | 1264/20/HUG | 03/05/2023 | 0 | Resource Division | 16.64 | 0 | 0 | 0
684 | HOOGHLY | Hooghly Division | DURGAPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12243 | New | Material Requisition To Resource Division | 3059/11/Hug | 11/10/2023 | 0 | Resource Division | 3.18 | 0 | 0 | 0
685 | HOOGHLY | Electrical | DURGAPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12243 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Durgapur water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | 3489/ED | 30/12/2022 | 90 | M/S CHANDIMATA ELECTRICALS | 20.38 | 11.23 | 55.1 | 35
686 | HOOGHLY | Electrical | DURGAPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12243 | New | Quotation Bill for New Service Connection at Kamalpur W/S. Sch. TW-I | 693 | 22/01/2024 | 0 | WBSEDCL | 11.8 | 0 | 0 | 0
687 | HOOGHLY | Electrical | DURGAPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12243 | New | Quotation Bill for New Service Connection at Kamalpur W/S. Sch. TW-II | 694 | 22/01/2024 | 0 | WBSEDCL | 5.69 | 0 | 0 | 0
688 | HOOGHLY | Hooghly Division | DURGAPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12243 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 212.01 | 49.77 | 30
689 | HOOGHLY | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/11287 | New | Laying Distribution System, Laying D.I Pipes & Specials for Rising Main Pipe Line, Construction of 1No 3.6M X 3.0 M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at T.W Site including providing FHTC in BHAGABATIPUR Water Supply Scheme at HARIPAL Block under Chandannagar Sub-Division. | 2280/Hug | 19/10/2022 | 45 | BABUSONA CONSTRUCTION | 46.12 | 6.5 | 15.95 | 55
690 | HOOGHLY | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/11287 | New | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at BHAGABATIPUR PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | 752/HUG | 15/03/2023 | 30 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 12.44 | 0 | 0 | 100
691 | HOOGHLY | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/11287 | New | Supply and delivery of 300 mm dia UPVC pipe (CD) at Bhagabatipur Water Supply Scheme under Chandannagar Sub-Division under Hooghly Division PHE Dte. | 615/Chan | 21/08/2023 | 7 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 0.89 | 0 | 0 | 0
692 | HOOGHLY | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/11287 | New | Material Requisition To Resource Division | 109/ 13/Hug | 10/01/2023 | 0 | Resource Division | 1.75 | 0 | 0 | 0
693 | HOOGHLY | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/11287 | New | Material Requisition To Resource Division | 79/1/Hug | 06/01/2023 | 0 | Resource Division | 59.68 | 0 | 0 | 0
694 | HOOGHLY | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/11287 | New | Material Requisition To Resource Division | 1383/1/Hug | 15/05/2023 | 0 | Resource Division | 1.11 | 0 | 0 | 0
695 | HOOGHLY | Electrical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/11287 | New | Additional Quotation of New Service Connection for Bhagabatipur w/s Scheme,Tw no-I,Block-Haripal,Dist-Hooghly under Electrical Division PHE Dte | 296 | 21/09/2023 | 0 | WBSEDCL | 0.48 | 0 | 0 | 0
696 | HOOGHLY | Electrical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/11287 | New | Quotation for new service connection of Bhagabatipur W/s Scheme, PH No-I Dist-Hooghly under Electrical Division ,PHE Dte | 103 | 19/07/2023 | 0 | WBSEDCL | 2.6 | 0 | 0 | 0
697 | HOOGHLY | Electrical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/11287 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhagabatipur water supply scheme, T.W. No. I, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | 3459/ED | 30/12/2022 | 90 | NITESH MANAGEMENT | 10.16 | 10.15 | 100 | 40
698 | HOOGHLY | Electrical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/11287 | New | Quotation Bill for New Service Connection at Bhagabatipur W/S. Sch. | 793 | 22/02/2024 | 0 | WBSEDCL | 12.75 | 0 | 0 | 0
699 | HOOGHLY | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME , SM/11288 | New | Route Survey, Design Drawing & DPR Preparation of Bhanjipur PWSS under Chandannagar Sub - Division, PHE Dte. | 512/Chan | 29/09/2022 | 15 | ENVIROTECH SOLUTIONS | 4.78 | 4.78 | 100 | 0
700 | HOOGHLY | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME , SM/11288 | New | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of BHANJIPUR Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | 448/HUG | 16/02/2023 | 60 | AMBIAN INFRASTRUTTURE | 12.25 | 12.25 | 100 | 100
701 | HOOGHLY | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME , SM/11288 | New | Sinking of 2 nos 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tube Well Site of BHANJIPUR W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 156/HUG | 16/01/2023 | 45 | SURAJIT SINGHA RAY | 28.4 | 27.33 | 100 | 100
702 | HOOGHLY | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME , SM/11288 | New | Horizontal Auger boring with water jet system Including Approach Road at BHANJIPUR Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | 2904/HUG | 21/09/2023 | 30 | M/S. NANDY ENTERPRISE | 8.83 | 8.81 | 100 | 100
703 | HOOGHLY | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME , SM/11288 | New | Material Requisition To Resource Division | 109/ 23/Hug | 10/01/2023 | 0 | Resource Division | 23.69 | 0 | 0 | 0
704 | HOOGHLY | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME , SM/11288 | New | Material Requisition To Resource Division | 1383/10/Hug | 15/05/2023 | 0 | Resource Division | 15.6 | 0 | 0 | 0
705 | HOOGHLY | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME , SM/11288 | New | Material Requisition To Resource Division | 3005/5/Hug | 05/10/2023 | 0 | Resource Division | 19.24 | 0 | 0 | 0
706 | HOOGHLY | Electrical | BHANJIPUR PIPED WATER SUPPLY SCHEME , SM/11288 | New | Quotation Bill for New Service Connection at Bhanjipur W/S. Sch. PH-I | 493 | 07/12/2023 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
707 | HOOGHLY | Electrical | BHANJIPUR PIPED WATER SUPPLY SCHEME , SM/11288 | New | Quotation bill for WBSEDCL security deposit for Bhanjipur w/s scheme PH-I | 228 | 01/09/2023 | 0 | WBSEDCL | 4.65 | 0 | 0 | 0
708 | HOOGHLY | Electrical | BHANJIPUR PIPED WATER SUPPLY SCHEME , SM/11288 | New | Quotation bill for WBSEDCL security deposit for Bhanjipur w/s scheme, PH No.-II | 227 | 01/09/2023 | 0 | WBSEDCL | 4.93 | 0 | 0 | 0
709 | HOOGHLY | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME , SM/11288 | New | BHANJIPUR Piped Water Supply Scheme with LDS, FHTC & Construction of 400 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at TARAKESWAR Block under Chandannagar Sub-Division under Hooghly Division PHE Dte. | 2899/HUG | 22/12/2022 | 180 | M/S. NANDY ENTERPRISE | 457.97 | 240.5 | 52.51 | 60
710 | HOOGHLY | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME , SM/11288 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System & Protection Work at different TW site for BHANJIPUR Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | 2446/HUG | 12/08/2023 | 60 | R.K.CONSTRUCTION | 40.9 | 12.1 | 29.58 | 50
711 | HOOGHLY | Electrical | BHANJIPUR PIPED WATER SUPPLY SCHEME , SM/11288 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhanjipur water supply scheme, T.W. No. I & II, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | 3460/ED | 30/12/2022 | 90 | M.S. ENTERPRISE | 22.27 | 22.24 | 100 | 100
712 | HOOGHLY | Hooghly Division | BHANJIPUR PIPED WATER SUPPLY SCHEME , SM/11288 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Gouribati PWSS, Bhanjipur PWSS, Shibrambati zone-II PWSS, Aymachapsara PWSS, Balarambati PWSS, Chandanpur PWSS). | 310/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 100
713 | HOOGHLY | Hooghly Division | HARAT PIPED WATER SUPPLY SCHEME , SM/11290 | New | Route Survey, Design Drawing & DPR Preparation of Harat PWSS under Chandannagar Sub - Division, PHE Dte. | 511/Chan | 29/09/2022 | 15 | ENVIROTECH SOLUTIONS | 4.21 | 4.21 | 100 | 0
714 | HOOGHLY | Hooghly Division | HARAT PIPED WATER SUPPLY SCHEME , SM/11290 | New | Material Requisition To Resource Division | 109/ 15/Hug | 10/01/2023 | 0 | Resource Division | 31.12 | 0 | 0 | 0
715 | HOOGHLY | Hooghly Division | HARAT PIPED WATER SUPPLY SCHEME , SM/11290 | New | Material Requisition To Resource Division | 1383/5/Hug | 15/05/2023 | 0 | Resource Division | 11.78 | 0 | 0 | 0
716 | HOOGHLY | Hooghly Division | HARAT PIPED WATER SUPPLY SCHEME , SM/11290 | New | Material Requisition To Resource Division | 3058/1/Hug | 11/10/2023 | 0 | Resource Division | 116.86 | 0 | 0 | 0
717 | HOOGHLY | Electrical | HARAT PIPED WATER SUPPLY SCHEME , SM/11290 | New | Quotation of New Service Connection for Harat Water Supply Scheme,TW No-II,Block-Haripal, Dist-Hooghly under ED,PHE Dte | 224 | 28/08/2023 | 0 | WBSEDCL | 5.57 | 0 | 0 | 0
718 | HOOGHLY | Electrical | HARAT PIPED WATER SUPPLY SCHEME , SM/11290 | New | New Service Connection at Harat Piped W/S. Sch. TW-II | 170 | 09/08/2023 | 0 | WBSEDCL | 3.58 | 0 | 0 | 0
719 | HOOGHLY | Electrical | HARAT PIPED WATER SUPPLY SCHEME , SM/11290 | New | NEW SERVICE CONNECTION |  | 08/08/2023 | 0 | WBSEDCL | 3.58 | 0 | 0 | 0
720 | HOOGHLY | Electrical | HARAT PIPED WATER SUPPLY SCHEME , SM/11290 | New | Additional Quotation Of New Service Connection for Harat w/s Scheme,PH No-I,Block-Haripal,Dist-Hooghly under ED,PHE Dte | 349 | 11/10/2023 | 0 | WBSEDCL | 0.1 | 0 | 0 | 0
721 | HOOGHLY | Electrical | HARAT PIPED WATER SUPPLY SCHEME , SM/11290 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Harat water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | 3465/ED | 30/12/2022 | 90 | M/S A.K BANERJEE | 21.49 | 19.62 | 91.3 | 30
722 | HOOGHLY | Hooghly Division | HARAT PIPED WATER SUPPLY SCHEME , SM/11290 | New | Construction of 350 cum capacity OHR with 20 mtr. staging height including Soil Investigation work, Laying Distribution System, Rising Main & Interconnection between O.H.R, TW No-I & II, Construction of 1No 5.4 M X 3.6 M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at Head Work Site, Construction of 1No 3.6M x 3.0M Switch Room without Sanitary & Water Supply arrangement & Boundary Wall at 2nd T/W Site including Providing FHTC in HARAT Water Supply Scheme at HARIPAL Block under Chandannagar Sub-Division, PHE Dte. | 42/HUG | 04/01/2023 | 300 | TITAS CONSTRUCTION | 450.61 | 161.88 | 35.93 | 20
723 | HOOGHLY | Electrical | HARAT PIPED WATER SUPPLY SCHEME , SM/11290 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Harat water supply scheme, T.W. No. III, Block: Haripal, District: Hooghly under Electrical Division, PHE Dte. | 340/ED | 21/02/2024 | 90 | MOITRA ENGINEERING CO. | 10.74 | 10.44 | 97.21 | 10
724 | HOOGHLY | Hooghly Division | HARAT PIPED WATER SUPPLY SCHEME , SM/11290 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Harat& Panrra W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 1804/HUG | 21/06/2023 | 45 | OSMAN SEKH | 80.84 | 32.51 | 97.87 | 100
725 | HOOGHLY | Hooghly Division | HARAT PIPED WATER SUPPLY SCHEME , SM/11290 | New | Making of 2 nos 1.8m X 1.45m X 2.1m KIOSK at Rambati 2nd T/W site & Harat 2nd T/W Site under Chandannagar Sub-Division PHE Dte. | 282/Chan | 15/03/2024 | 15 | SUDIPTA SINHA | 0.88 | 0.82 | 100 | 100
726 | HOOGHLY | Electrical | HARAT PIPED WATER SUPPLY SCHEME , SM/11290 | New | Quotation of New Service Connection for Harat w/S Scheme,TW No-3 Block-Haripal Dist-Hooghly under ED,PHE Dte. (SM/11290) Application No-5003979859 Reference Id-503541273 | 902 | 19/03/2024 | 0 | WBSEDCL | 3.73 | 0 | 0 | 0
727 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | 2ND CONTINUATION ORDER FOR Deployment of 4 (four) Nos. Security Guard without Arm for guarding arrangement of Office cum store at SOMRA Water Supply Scheme under Chinsurah Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.04.2022 to 31.07.2022. | 616/Hug | 31/03/2022 | 122 | S.K. GHOSH | 3.41 | 0 | 0 | 0
728 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | 2ND CONTINUATION ORDER FOR Deployment of 4 (four) Nos. Security Guard without Arm for guarding arrangement of Office cum store at POLBA Water Supply Scheme under Chinsurah Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.04.2022 to 31.07.2022. | 619/Hug | 31/03/2022 | 122 | S.K. GHOSH | 3.41 | 0 | 0 | 0
729 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | Preparation of DPR for Augmentation of Dhaniakhali Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | 131/CH | 17/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.82 | 4.81 | 99.61 | 0
730 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | PAYMENT TO WBSEDCL |  | 11/11/2022 | 0 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 3.2 | 0 | 0 | 0
731 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at DHANIAKHALI (Zone-II) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL - 05 | 1955/HUG | 07/09/2022 | 45 | OSMAN SEKH | 22.63 | 21.96 | 100 | 0
732 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir of 182 cum capacity of Dhaniakhali Zone-I PWSS under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. SL NO - 01 | 1904/HUG | 05/09/2022 | 30 | ROY ENTERPRISE | 7.45 | 7.44 | 100 | 100
733 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | Augmentation of DHANIAKHALI (ZONE-I) Water Supply Scheme with LDS & FHTC At Dhaniakhali Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | 1657 | 16/08/2022 | 50 | SUJATA CONSTRUCTION | 177.27 | 173.43 | 100 | 100
734 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | Material Requisition To Resource Division | 1123/2/HUG | 06/06/2022 | 0 | Resource Division | 11 | 0 | 0 | 0
735 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | Material Requisition To Resource Division | 2211/1/Hug | 30/09/2022 | 0 | Resource Division | 30.8 | 0 | 0 | 0
736 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | Material Requisition To Resource Division | 1386/53/Hug | 15/05/2023 | 0 | Resource Division | 15.68 | 0 | 0 | 0
737 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | Material Requisition To Resource Division | 1105/1/Hug | 17/04/2023 | 0 | Resource Division | 60.84 | 0 | 0 | 0
738 | HOOGHLY | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | Quotation Bill for New Service Connection at DhaniakhaliZ-II, PH-II | 57 | 02/06/2023 | 0 | WBSEDCL | 5.86 | 0 | 0 | 0
739 | HOOGHLY | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | Quotation Bill for New Service Connection at Dhaniakhali W/S. Sch. W/S. Sch. Z-I | 155 | 03/08/2023 | 0 | WBSEDCL | 4.72 | 0 | 0 | 0
740 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | HIRE CHARGES BILL EXECUTIVE ENGINEER, HOOGHLY DIVISION, PHE DTE. | BP-2022-23-405 | 15/12/2022 | 0 | PRADIP KUMAR ADHYA | 2.07 | 0 | 0 | 0
741 | HOOGHLY | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dhaniakhali water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | 833/ED | 14/02/2023 | 90 | A.G. ENTERPRISE | 21.49 | 17.21 | 91.94 | 59
742 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | Construction of 1 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of DHANIAKHALI ZONE-I Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte | 650/Hug | 10/03/2023 | 60 | SOME ENTERPRISE | 6.08 | 6.08 | 100 | 95
743 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | Construction of 1 No. switch-room at Proposed TW site of DHANIAKHALI ZONE-II Water Supply Scheme under DHANIAKHALI Block, District:- Hooghly [AUGMENTATION SCHEME] | 1342/HUG | 11/05/2023 | 30 | SOMNATH ADHYA | 6.15 | 6.15 | 50 | 100
744 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | Replacing of Sluice Valve and allied works at Head Work Site of Dhaniakhali Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division, PHE Dte | 1114/CH | 15/12/2023 | 7 | M/S BIMAL DAS AND CO. | 0.95 | 0.85 | 100 | 100
745 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme underDhaniakhali Block (Part-II) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. | 696/CH | 09/08/2024 | 15 | TECHVISION | 4.2 | 4.2 | 100 | 100
746 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under DHANIAKHALI Block (New scheme) of Chinsurah Sub Division under Hooghly Division PHE Dte. | 929/CH | 05/11/2024 | 5 | M/S BIMAL DAS AND CO. | 2.82 | 2.16 | 43.4 | 90
747 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under DHANIAKHALI Block (Existing scheme) of Chinsurah Sub Division under Hooghly Division PHE Dte. | 928/CH | 05/11/2024 | 5 | TOTON MONDAL | 4.85 | 0 | 0 | 90
748 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme under Dhaniakhali Block (Part-I) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. | 695/CH | 09/08/2024 | 15 | TECHVISION | 4.2 | 4.2 | 100 | 90
749 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dhaniakhali , SM/11166 | Augmentation | AUGMENTATION of DHANIAKHALI ZONE-II Piped Water Supply Scheme with LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation under DHANIAKHALI Block, District:- Hooghly [AUGMENTATION SCHEME] | 2225/HUG | 31/07/2023 | 810 | PRADIP KUMAR ADHYA | 409.01 | 158.52 | 38.76 | 30
750 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF CHILADANGI WATER SUPPLY SCHEME , SM/12014 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in Chiladangi PWSS, Block Pursurah under Arambag Sub-Division of Hooghly Division P.H.E Dte. | 2099/HUG | 19/07/2023 | 45 | ARATI ENGINEERING | 94.38 | 0 | 0 | 0
751 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11464 | Augmentation | Preparation of DPR for Augmentation of Anandapur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I]. | 333/Arg | 02/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.22 | 3.35 | 79.29 | 0
752 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11464 | Augmentation | Providing 50 nos Functional Household Tap Connection (FHTC) within the command area of ANANDAPUR Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | 123/HUG | 26/09/2022 | 25 | M/S ROY CONSTRUCTION AND CO. | 15.22 | 15.22 | 100 | 100
753 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11464 | Augmentation | Laying Distribution System for ANANDAPUR (Zone-I) Piped Water Supply Scheme including Repairing of existing Switch rooms, Boundary walls (Zone-I & Zone-II) at Goghat-I Block under Arambagh Sub-Division of Hooghly Division P.H.E Dte. SL NO - 01 | 1780/HUG | 30/08/2022 | 45 | TAPAS ADHYA | 76.59 | 0 | 0 | 0
754 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11464 | Augmentation | Laying Distribution System of ANANDAPUR (Zone-II) Piped Water Supply Scheme including Construction of 2 Nos. 3.6 M X 3.0 M Switch Rooms & 2 Nos. Boundary wall at Goghat-I Block under Arambagh Sub-Division of Hooghly Division PHE Dte. SL NO-02 | 1781/HUG | 30/08/2022 | 45 | SARKAR CONSTRUCTION | 69.19 | 36.46 | 52.7 | 25
755 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11464 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 210 Mtr at ANANDAPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | 2511/HUG | 22/11/2022 | 45 | MS D.PALIT AND CO. | 27.59 | 20.07 | 100 | 0
756 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11464 | Augmentation | Material Requisition To Resource Division | 2209/Hug | 30/09/2022 | 0 | Resource Division | 30.8 | 0 | 0 | 0
757 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11464 | Augmentation | Material Requisition To Resource Division | 1773/32/Hug | 29/08/2022 | 0 | Resource Division | 0.69 | 0 | 0 | 0
758 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11464 | Augmentation | Material Requisition To Resource Division | 1590/5/Hug | 03/08/2022 | 0 | Resource Division | 15.4 | 0 | 0 | 0
759 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11464 | Augmentation | Material Requisition To Resource Division | 1385/18/Hug | 15/05/2023 | 0 | Resource Division | 0.49 | 0 | 0 | 0
760 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11464 | Augmentation | Material Requisition To Resource Division | 127/2/Hug | 13/01/2023 | 0 | Resource Division | 9.57 | 0 | 0 | 0
761 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11464 | Augmentation | Material Requisition To Resource Division | 1234/7/Hug | 28/04/2023 | 0 | Resource Division | 0.32 | 0 | 0 | 0
762 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11464 | Augmentation | Quotation Bill for New Service Connection at Anandapur W/S. Sch. TW-III & IV, Hooghly | 205 | 21/03/2023 | 0 | WBSEDCL | 1.46 | 0 | 0 | 0
763 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11464 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Anandapur water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | 1734/ED | 19/04/2023 | 90 | P.K. ENGINEERING | 21.49 | 20.91 | 97.3 | 70
764 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11464 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) ANANDAPUR PWSS-4nos (2) BHADUR(BHAGARBAND) PWSS-6nos (3) GOGHAT PWSS-2nos (4) JOYKRISHNAPUR PWSS-2nos | 816/Arg | 23/08/2024 | 130 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.28 | 100 | 100
765 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR ANANDAPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11464 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of ANANDAPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 4151/HUG | 26/12/2024 | 90 | M/S RAJKUMAR KHAN | 17.7 | 0 | 0 | 0
766 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | Preparation of DPR for Augmentation of Soaluk Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. | 339/Arg | 02/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.74 | 3.68 | 98.55 | 0
767 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | Laying Distribution System, of proposed pipe line of SOALUK (EAST,WEST,& SOUTH PORTION) Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 2888/HUG | 22/12/2022 | 90 | M/S CARE | 191.47 | 0 | 0 | 0
768 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | Construction of 1 No. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site OF SOALUK Water Supply Scheme Under Arambagh Sub-Division Under Hooghly Division P.H.E Dte. | 450/HUG | 16/02/2023 | 45 | TANISA ENTERPRISE | 7.5 | 7.5 | 100 | 0
769 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | Replacement of some electrical devices and equipments like mcc cum pdb etc. including allied works for Soaluk water supply scheme, P.H. No. I, District- Hooghly under Electrical Division, PHE Dte. | 494/HMSD | 02/03/2023 | 30 | N.S. TRADING | 4.21 | 4.21 | 100 | 0
770 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | Construction of Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Augmentation of SOALUK Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Pursurah Block. | 1459/HUG | 18/05/2023 | 30 | RAYCON COOPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD | 6.21 | 0 | 0 | 0
771 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection of SOALUK Piped Water Supply Scheme within Soaluk (North) Mouza including Repairing of existing Switch Rooms at PURSURAH Block under Arambagh Sub-Division of Hooghly Division PHE Dte. SL NO - 05 | 1783/HUG | 30/08/2022 | 30 | R.K. TRADERS | 52.81 | 52.81 | 100 | 0
772 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | Replacement of some electrical devices, equipments and items, outdoor lighting, voltage corrector etc. including allied works for Soaluk water supply scheme, P.H. No. I, District- Hooghly under Electrical Division, PHE Dte. | 492/HMSD | 02/03/2023 | 30 | RADHARANI ENTERPRISE | 2.99 | 2.99 | 100 | 100
773 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 210 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SOALUK W/S SCH, UNDER HOOGHLY DISTRICT CDD, PHE DTE. | 1559/CDD | 08/12/2022 | 30 | ASHUTOSH DAS & CO | 12.66 | 9.62 | 100 | 0
774 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | Material Requisition To Resource Division | 1773/42/Hug | 29/08/2022 | 0 | Resource Division | 1.38 | 0 | 0 | 0
775 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | Material Requisition To Resource Division | 1106/2/HUG | 17/04/2023 | 0 | Resource Division | 14.48 | 0 | 0 | 0
776 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | Material Requisition To Resource Division | 79/26/Hug | 06/01/2023 | 0 | Resource Division | 17.86 | 0 | 0 | 0
777 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | Quotation Bill for New Service Connection at Aug. of Soaluk W/S. Sch. PH-I | 208 | 22/03/2023 | 0 | WBSEDCL | 3 | 0 | 0 | 0
778 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | Laying Distribution System, of proposed pipe line of SOALUK (EAST,WEST,& SOUTH PORTION) Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 281/HUG | 01/02/2023 | 90 | M/S CARE | 191.47 | 145.99 | 76.25 | 70
779 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | Functional Household Tap Connection (FHTC) under JJM in SOALUK PWSS, Block. PURSURAH under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 2889/HUG | 22/12/2022 | 60 | M/S CARE | 86.64 | 82.65 | 95.39 | 70
780 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | Sinking of 1 no 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at proposed Tube Well Site of SOALUK W/S Scheme under ARAMBAG Sub-Division of Hooghly Division, P.H.E. Dte. | 170/HUG | 16/01/2023 | 30 | GITA ENTERPRISE | 13.54 | 13.54 | 100 | 100
781 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Soaluk water supply scheme, T.W. No.- I, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | 668/ED | 02/02/2023 | 90 | M/S BIPUL BANERJEE | 10.96 | 10.91 | 100 | 100
782 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | Electric quot. of WBSEDCL for New service Connection of Soaluk T/W-IV W/S scheme under Electrical Division PHE Dte. (SM/11467) | 376 | 12/08/2024 | 0 | WBSEDCL | 3.31 | 0 | 0 | 0
783 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir ,Construction of Boundary Wall Of Head Work site at SOALUK Piped Water Supply Scheme under ARAMBAGH Sub¿Division of Hooghly Division P.HE Dte | 2453/HUG | 12/08/2023 | 600 | P.K. GHOSH & CO. | 31.41 | 21.27 | 67.72 | 100
784 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE , SM/11467 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Soaluk water supply scheme, T.W. No. IV, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | 334/ED | 21/02/2024 | 435 | DEY ENTERPRISE | 10.43 | 0 | 0 | 35
785 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME , SM/11990 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Tilari, Dwaripara, Kakand Mouza in BADANGANJ PWSS, Block Goghat-II under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 2850/HUG | 16/12/2022 | 30 | TANISA ENTERPRISE | 23.9 | 18.73 | 78.35 | 0
786 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME , SM/11990 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Fului Mouza in BADANGANJ PWSS, Block Goghat-II under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 2848/HUG | 16/12/2022 | 45 | TITAS CONSTRUCTION | 47.25 | 46.85 | 99.15 | 0
787 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME , SM/11990 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Badanganj Mouza in BADANGANJ PWSS, Block Goghat-II under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 2922/HUG | 27/12/2022 | 30 | MS K.B CONSTRUCTION | 30.75 | 30.69 | 100 | 0
788 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME , SM/11990 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Shyambazar Mouza in BADANGANJ PWSS, Block Goghat-II under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 2853/HUG | 16/12/2022 | 45 | MS K.B CONSTRUCTION | 51.48 | 51.44 | 100 | 0
789 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME , SM/11990 | Retrofitting | Material Requisition To Resource Division | 1106/3/HUG | 17/04/2023 | 0 | Resource Division | 15.88 | 0 | 0 | 0
790 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME , SM/11990 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Betra Mouza in BADANGANJ PWSS, Block Goghat-II under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 2849/HUG | 16/12/2022 | 30 | KOUSIK MONDAL | 25.28 | 25.06 | 100 | 100
791 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME , SM/11990 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Kayapat, Shyampur, Tilati, Chakran Mouza in BADANGANJ PWSS, Block Goghat-II under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 2851/HUG | 16/12/2022 | 776 | I R CONSTRUCTION | 37.54 | 0 | 0 | 100
792 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BADANGANJ WATER SUPPLY SCHEME , SM/11990 | Retrofitting | Laying balance pipeline and other allied works at Badangnj and Fului village within Badanganj Zone - I PWSS under Arambagh Sub Division, PHE Dte. Hooghly | 663/HUG | 11/03/2025 | 45 | TITAS CONSTRUCTION | 39.19 | 0 | 0 | 0
793 | HOOGHLY | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Material Requisition To Resource Division | 2471/Hug | 18/11/2022 | 0 | Resource Division | 20.08 | 0 | 0 | 0
794 | HOOGHLY | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Sinking of Five Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ATISARA, NANDA, NOWPARA, BASUBATI & ASTARA PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | 878/HUG | 27/03/2023 | 45 | MS D.PALIT AND CO. | 62.24 | 10.89 | 87.46 | 100
795 | HOOGHLY | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Material Requisition To Resource Division | 109/Hug | 10/01/2023 | 0 | Resource Division | 102.73 | 0 | 0 | 0
796 | HOOGHLY | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Material Requisition To Resource Division | 01/04/Hug | 02/01/2023 | 0 | Resource Division | 20.08 | 0 | 0 | 0
797 | HOOGHLY | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Material Requisition To Resource Division | 902/Hug | 27/03/2023 | 0 | Resource Division | 20.08 | 0 | 0 | 0
798 | HOOGHLY | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Material Requisition To Resource Division | 1383/33/Hug | 15/05/2023 | 0 | Resource Division | 20.08 | 0 | 0 | 0
799 | HOOGHLY | Electrical | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Quotation Bill for New Service Connection at Atisara W/S. Sch. TW-II | 543 | 19/12/2023 | 0 | WBSEDCL | 2.96 | 0 | 0 | 0
800 | HOOGHLY | Electrical | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Quotation for new service connection at Atisara W/s Sch.,T/W - I, Block - Singur | 115 | 20/07/2023 | 0 | WBSEDCL | 5.59 | 0 | 0 | 0
801 | HOOGHLY | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Emergent requirement of rectification of damages caused to road under Hooghly Highway Division II | BP-2023-24-400 | 26/09/2023 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 10.04 | 0 | 0 | 0
802 | HOOGHLY | Electrical | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Atisara water supply scheme, T.W. No. I & II, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | 3479/ED | 30/12/2022 | 90 | R.N.S. TRADING | 23.26 | 11.28 | 48.5 | 49
803 | HOOGHLY | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Horizontal Auger boring with water jet system Including Approach road at Atisara W/S Scheme under Chandannagar Sub - Division of Hooghly Division, P.H.E. Dte.. | 450/HUG | 15/02/2024 | 324 | MINTU CHAKRABORTY | 36.19 | 0 | 0 | 2
804 | HOOGHLY | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Sinking of1 No. Additional tube-well , Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for atisara Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. | 3470/HUG | 04/10/2024 | 60 | M/S SHIVAM UDYOG | 26.55 | 0 | 0 | 0
805 | HOOGHLY | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at ATISARA, NANDA, NAWPARA,BASUBATI & ASTARA W/S Scheme underChandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | 1818/HUG | 22/06/2023 | 45 | OSMAN SEKH | 80.85 | 15.85 | 100 | 100
806 | HOOGHLY | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Atisara PWSS, Beraberi PWSS, Barakamplur PWSS, Diara PWSS, Kamarkundu PWSS, Nanda PWSS) | 299/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 100
807 | HOOGHLY | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Making of 2 nos 1.8m X 1.45m X 2.1m KIOSK at Purusatyampur H/W site & Atisara 2nd T/W Site under Chandannagar Sub-Division PHE Dte. | 281/Chan | 15/03/2024 | 15 | SUDIPTA SINHA | 0.88 | 0.82 | 100 | 100
808 | HOOGHLY | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Approach road at Atisara 2nd Tubewell site under Atisara water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. | 293/Chan | 15/03/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.94 | 0.94 | 100 | 100
809 | HOOGHLY | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Construction of 500 cum capacity OHR with 20 mtr. staging height including Soil Investigation work, Laying Distribution System, Rising Main& Interconnection between O.H.R , TW No-I & II, Construction of 1 No 5.4M X 3.6M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at Head Work Site, Construction of 1 No 3.6M x 3.0M Switch Room with Sanitary & Water Supply arrangement & Boundary Wall at 2nd T/W Site including Providing FHTC in ATISARA Water Supply Scheme at SINGUR Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | 404/HUG | 13/02/2023 | 899 | MINTU CHAKRABORTY | 769.58 | 608.6 | 79.08 | 97
810 | HOOGHLY | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Laying balance pipeline and other allied works at ATISARA PWSS under Chandannagar Sub Division, PHE Dte. Hooghly | 1173/HUG | 02/05/2025 | 60 | MINTU CHAKRABORTY | 33.71 | 0 | 0 | 0
811 | HOOGHLY | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Construction of boundary wall with Gate & Internal Pathway at ATISARA 2nd pump hou se site under Singur Block under Chandannagar Sub-Division, P.H.E. Dte. | 915/CHAN | 21/07/2025 | 20 | SARKAR CONSTRUCTION (DEBJIT SARKAR) | 5 | 0 | 0 | 0
812 | HOOGHLY | Hooghly Division | ATISARA PIPED WATER SUPPLY SCHEME , SM/12727 | New | Construction of road with plinth protection and land development at ATISARA 2nd pump house site under Singur block under Chandannagar Sub-Division, P.H.E. Dte. | 916/CHAN | 21/07/2025 | 20 | SARKAR CONSTRUCTION (DEBJIT SARKAR) | 5 | 0 | 0 | 0
813 | HOOGHLY | Electrical | Kapsit Mini Piped Water Supply Scheme , SM/13554 | New | Supply & Delivery of standby submersible pumping machinery for Kapsit & others W/S. Sch. | 556/HMSD | 17/03/2022 | 90 | DITHI ENTERPRISE | 0.79 | 0 | 0 | 0
814 | HOOGHLY | Hooghly Division | Kapsit Mini Piped Water Supply Scheme , SM/13554 | New | Material Requisition To Resource Division | 1385/46/Hug | 15/05/2023 | 0 | Resource Division | 0.33 | 0 | 0 | 0
815 | HOOGHLY | Hooghly Division | Kapsit Mini Piped Water Supply Scheme , SM/13554 | New | REQUISITION OF FUND FOR SAJAL GRAM SCHEME |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 26.6 | 0 | 0 | 0
816 | HOOGHLY | Hooghly Division | Kapsit Mini Piped Water Supply Scheme , SM/13554 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME |  | 23/06/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 29.55 | 0 | 0 | 0
817 | HOOGHLY | Hooghly Division | Kapsit Mini Piped Water Supply Scheme , SM/13554 | New | MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-343 | 31/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 28.37 | 0 | 0 | 0
818 | HOOGHLY | Electrical | Kapsit Mini Piped Water Supply Scheme , SM/13554 | New | Mini Piped water Supply Scheme | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
819 | HOOGHLY | Hooghly Division | Naopara Mini Piped Water Supply Scheme , SM/13562 | New | MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-298 | 19/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.41 | 0 | 0 | 0
820 | HOOGHLY | Electrical | Naopara Mini Piped Water Supply Scheme , SM/13562 | New | Mini Piped Water Supply Scheme | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0 | 0
821 | HOOGHLY | Electrical | Naopara Mini Piped Water Supply Scheme , SM/13562 | New | Mini piped Water Supply scheme |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
822 | HOOGHLY | Hooghly Division | Bhupatipur Mini Piped Water Supply Scheme , SM/13587 | New | Material Requisition To Resource Division | 1383/20/Hug | 15/05/2023 | 0 | Resource Division | 0.1 | 0 | 0 | 0
823 | HOOGHLY | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14117 | New | Material Requisition To Resource Division | 1385/23/Hug | 15/05/2023 | 0 | Resource Division | 9.95 | 0 | 0 | 0
824 | HOOGHLY | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14117 | New | Material Requisition To Resource Division | 3057/49/Hug | 11/10/2023 | 0 | Resource Division | 9.95 | 0 | 0 | 0
825 | HOOGHLY | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14117 | New | Material Requisition To Resource Division | 127/22/Hug | 13/01/2023 | 0 | Resource Division | 20.88 | 0 | 0 | 0
826 | HOOGHLY | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14117 | New | Material Requisition To Resource Division | 1234/37/Hug | 28/04/2023 | 0 | Resource Division | 11.79 | 0 | 0 | 0
827 | HOOGHLY | Electrical | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14117 | New | Quotation for new service connection charge at Radhaballavpur PWSS, Zone-II, TW - I | 459 | 01/12/2023 | 0 | WBSEDCL | 6.9 | 0 | 0 | 0
828 | HOOGHLY | Electrical | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14117 | New | Quotation for new service connection charge at Radhaballavpur PWSS, Zone-II, TW - II | 530 | 15/12/2023 | 0 | WBSEDCL | 13 | 0 | 0 | 0
829 | HOOGHLY | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14117 | New | RADHABALLAVPUR (ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch rooms & boundary walls at different TW site under KHANAKUL-I Block, District- Hooghly.[NEW SCHEME] | 833/HUG | 22/03/2023 | 832 | M/S S.G. CONSTRUCTION | 364.99 | 274.46 | 75.2 | 80
830 | HOOGHLY | Electrical | GROUND WATER BASED RADHABALLAVPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14117 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Radhaballavpur water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-I District- Hooghly under Electrical Division, PHE Dte. | 773/ED | 09/02/2023 | 812 | KARTICK BAL | 20.62 | 15.73 | 76.45 | 30
831 | HOOGHLY | Hooghly Division | UTTAR BABNAN (Z-II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14121 | New | Material Requisition To Resource Division | 3059/17/Hug | 11/10/2023 | 0 | Resource Division | 11.41 | 0 | 0 | 0
832 | HOOGHLY | Hooghly Division | UTTAR BABNAN (Z-II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14121 | New | Material Requisition To Resource Division | 1264/9/HUG | 03/05/2023 | 0 | Resource Division | 25.36 | 0 | 0 | 0
833 | HOOGHLY | Electrical | UTTAR BABNAN (Z-II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14121 | New | Quotation Bill for New Service Connection at Uttar Babnan W/S. Sch. TW-I,Z-II | 731 | 05/02/2024 | 0 | WBSEDCL | 0.35 | 0 | 0 | 0
834 | HOOGHLY | Electrical | UTTAR BABNAN (Z-II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14121 | New | Quotation Bill for New Service Connection at Uttar Babnan W/S. Sch. TW-II | 732 | 05/02/2024 | 0 | WBSEDCL | 10.71 | 0 | 0 | 0
835 | HOOGHLY | Electrical | UTTAR BABNAN (Z-II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14121 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Uttar Babnan water supply scheme, Zone-I, T.W. No.- I, II & III and Zone-II, T.W. No.- I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | 932/ED | 22/02/2023 | 900 | DEY ENTERPRISE | 50.9 | 0 | 0 | 90
836 | HOOGHLY | Hooghly Division | UTTAR BABNAN (Z-II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14121 | New | Ground Water Based Piped Water Supply Schemes (PWSS) under POLBA-DADPUR Block at DALIMBA, GHATAMPUR, HASNAN, KAMRAI, KUCHPALA, PATUL, UTTAR BABNAN (ZONE-I) & UTTAR BABNAN (ZONE-II) Mouzas including Construction of different capacities R.C.C. Over Head Reservoirs (OHRs), Sinking of Tube Wells, Laying Distribution Systems (LDS), Laying Rising Main Interconnection pipelines, providing Functional Household Tap Connections (FHTCs), Construction of Switch Rooms, Boundary Walls etc. under Hooghly Division P.H.E. Dte. in connection with JJM. | 955/HUG | 30/03/2023 | 887 | GREEN ROYAL INFRA CON PVT LTD | 3672.07 | 254.64 | 65.2 | 15
837 | HOOGHLY | Electrical | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14122 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Haripur water supply scheme, T.W. No.- I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | 3490 / ED | 30/12/2022 | 90 | P.K. ENGINEERING | 20.24 | 10.08 | 49.82 | 98
838 | HOOGHLY | Hooghly Division | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14122 | New | Material Requisition To Resource Division | 1386/34/Hug | 15/05/2023 | 0 | Resource Division | 4.92 | 0 | 0 | 0
839 | HOOGHLY | Hooghly Division | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14122 | New | Material Requisition To Resource Division | 3059/4/Hug | 11/10/2023 | 0 | Resource Division | 6.06 | 0 | 0 | 0
840 | HOOGHLY | Hooghly Division | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14122 | New | Material Requisition To Resource Division | 1264/HUG | 03/05/2023 | 0 | Resource Division | 10.79 | 0 | 0 | 0
841 | HOOGHLY | Hooghly Division | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14122 | New | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, CHINSURAH SUB-DIVISION, PHE DTE. UNDER HOOGHLY DIVISION, PHE DTE. | BP-2023-24-106 | 02/06/2023 | 0 | PRASUN ENTERPRISE (PRASUN BISWAS) | 3.59 | 0 | 0 | 0
842 | HOOGHLY | Electrical | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14122 | New | Quotation for new service connection at Haripur W/S Sch., T/W No. - II, Block - Polba-dadpur, Dist. - Hooghly | 147 | 26/07/2023 | 0 | WBSEDCL | 2.9 | 0 | 0 | 0
843 | HOOGHLY | Electrical | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14122 | New | Quotation for new service Connection at Haripur W/S Sch., T/W No. - I, Block - Polba-Dadpur, District - Hooghly | 252 | 05/09/2023 | 0 | WBSEDCL | 5.79 | 0 | 0 | 0
844 | HOOGHLY | Hooghly Division | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14122 | New | HARIPUR Piped Water Supply Scheme with Sinking of tube-well, Laying Distribution System, Rising Main, Providing FHTC, construction of switch-rooms & boundary walls at different TW site under Hooghly Division, PHE Dte. within POLBA-DADPUR Block, District-Hooghly | 363/HUG | 08/02/2023 | 90 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 183.69 | 173.36 | 100 | 95
845 | HOOGHLY | Hooghly Division | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14122 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. 1. Rudrani PWSS 2. Chalua PWSS 3. Kamrai PWSS 4. Haripur PWSS 5. Kumrul PWSS 6. Kuchpala PWSS | 141/CH | 20/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 50 | 30
846 | HOOGHLY | Electrical | HARIPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/14122 | New | Quotation for new service connection at Haripur W/S Sch.[SM/14122], Block - Polba-Dadpur, WBSEDCL, Ref. Id. - 503619164, Dt. - 25/04/2024, Application No. - 5004117110 | 135 | 17/05/2024 | 0 | WBSEDCL | 4.71 | 0 | 0 | 0
847 | HOOGHLY | Hooghly Division | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13320 | New | Material Requisition To Resource Division | 1234/24/Hug | 28/04/2023 | 0 | Resource Division | 74.78 | 0 | 0 | 0
848 | HOOGHLY | Hooghly Division | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13320 | New | Material Requisition To Resource Division | 3057/42/Hug | 11/10/2023 | 0 | Resource Division | 14.17 | 0 | 0 | 0
849 | HOOGHLY | Electrical | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13320 | New | Quotation of New Service Connection for Kota w/s Scheme,PH No-I Block-Goghat-I Dist-Hooghly under ED,PHE Dte (SM/13320) Application No-5004009660 Reference Id-503561831 | 742 | 08/02/2024 | 0 | WBSEDCL | 3.97 | 0 | 0 | 0
850 | HOOGHLY | Electrical | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13320 | New | Quotation of New Service Connection for KOTA w/s scheme PH No-2 Block-Goghat-I Dist-Hooghly under ED,PHE Dte. (SM/13320) Application No-5004018773 Reference Id-503565232 | 765 | 16/02/2024 | 0 | WBSEDCL | 4.68 | 0 | 0 | 0
851 | HOOGHLY | Hooghly Division | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13320 | New | GOBINDANAGAR (ZONE-I), KOTA, KUMURSA Piped Water Supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-I Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | 1602/HUG | 01/06/2023 | 1035 | P.B. ENTERPRISE (PINTU BHADURI) | 1078.43 | 292.77 | 50.26 | 65
852 | HOOGHLY | Hooghly Division | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13320 | New | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for KOTA Piped Water Supply Scheme underARAMBAGH Sub Division of Hooghly Division, P.H.E. Dte. | 3465/HUG | 04/10/2024 | 120 | P. B. ENTERPRISE(PINTU BHADURI) | 53.65 | 14.79 | 27.57 | 50
853 | HOOGHLY | Hooghly Division | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13320 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PUKHURIA PWSS- 3 nos (2) SELAMPUR PWSS (Z-I)- 2 nos (3) SHANTIPUR PWSS (Z-I)- 1 nos (4) KOTA PWSS - 4nos (5) SUNIA PWSS - 4nos | 1149/Arg | 10/12/2024 | 31 | TITAS CONSTRUCTION | 0.98 | 0 | 0 | 0
854 | HOOGHLY | Electrical | GROUND WATER BASED KOTA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13320 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kota water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | 767/ED | 09/02/2023 | 919 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 21.06 | 20.33 | 97.3 | 40
855 | HOOGHLY | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. , SM/15216 | Solarisation | Solar Quotation for Rajbalhat W/S Scheme,PH No-I under Electrical Division,PHE Dte.(SM/15216) Application No-5004073023 Reference Id-162187840 | 635 | 18/12/2024 | 0 | WBSEDCL | 0.4 | 0 | 0 | 0
856 | HOOGHLY | Electrical | Solarisation of WBSEDCL energised electrical installation at different PWSS in the District of Hooghly under Electrical Division, PHE Dte. , SM/15216 | Solarisation | Solarisation of WBSEDCL energised electrical installation at different PWSS in the district of Hooghly under Electrical Division, PHE Dte. | 3084/ED | 17/07/2023 | 899 | SWITCHING AVO ELECTRO POWER LIMITED | 119.77 | 71.86 | 60 | 40
857 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15797 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system, FHTC of SHANKHANAGAR CHAK BANSBERIA W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | 1772/HUG | 15/06/2023 | 45 | SURAJIT SINGHA RAY | 40.36 | 9.51 | 23.56 | 45
858 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15797 | Augmentation | Supply, delivery and installation of voltage correcting device and other allied works for Sankhanagar Chawk Bansberia w/s scheme, P.H No.- II, Dist- Hooghly under Electrical Division, PHE Dte. | 491/HMSD | 02/03/2023 | 30 | S.B.ENTERPRISE | 2.49 | 2.49 | 100 | 1
859 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15797 | Augmentation | Emmergency Reparing work of Different Dia Ditribution Pipeline under Chakbasberia water supply scheme under Chinsurah Sub Divusion undre Hooghly Division PHE Dte. | 822/CH | 31/08/2023 | 15 | MAA BUNAMATA ENTERPRISE | 0.63 | 0.63 | 100 | 95
860 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15797 | Augmentation | Material Requisition To Resource Division | 3059/24/Hug | 11/10/2023 | 0 | Resource Division | 1.85 | 0 | 0 | 0
861 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15797 | Augmentation | Material Requisition To Resource Division | 3004/8/Hug | 05/10/2023 | 0 | Resource Division | 37.77 | 0 | 0 | 0
862 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15797 | Augmentation | Quotation Bill for New Service Connection at Sankhanagar Chak Bansberia W/S. Sch. TW-I | 355 | 12/10/2023 | 0 | WBSEDCL | 6.63 | 0 | 0 | 0
863 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15797 | Augmentation | Quotation for new service connection at Sankhanagar Chakbansberia W/S Sch. , T/W No. - I(Aug.), Block - Chinsurah- Mogra, Dist. - Hooghly |  | 10/10/2023 | 0 | WBSEDCL | 6.63 | 0 | 0 | 0
864 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15797 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Sankhanagar & Chakbasnberia water supply scheme, T.W. No. I, Block: Chinsurah-Magra, District- Hooghly under Electrical Division, PHE Dte. | 1699/ED | 18/04/2023 | 90 | EMCON | 11.4 | 11.4 | 100 | 80
865 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15797 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at SHIBRAI(2NOS.), SHANKHANAGAR CHAK BANSBERIA(2NOS.), BAKULIA ZONE-I(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. [3rd Call of WBPHE/EE/77/HUG/2022-23, Sl No-2] | 1618/HUG | 02/06/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 72.85 | 23.77 | 100 | 65
866 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15797 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sankhanagar Chakbansberia (Replacement) water supply scheme, T.W. No. I, Block: Chinsura-Mogra, District - Hooghly under Electrical Division, PHE Dte. | 4738/ED | 15/12/2023 | 90 | S. DUTTA | 10.74 | 10.46 | 100 | 90
867 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF GURAP W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/15798 | Augmentation | Laying Rising main with necessary interconnection with T.W., OHR & Distribution System & Repairing works of 1st Pump House, Boundary Wall & Go-down Room for Gurap Water Supply Scheme Under Chinsurah Sub-Division. | 1108/HUG | 17/04/2023 | 30 | GOBINDA MAITY | 16.16 | 16.16 | 100 | 100
868 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF GURAP W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/15798 | Augmentation | Material Requisition To Resource Division | 3004/18/Hug | 05/10/2023 | 0 | Resource Division | 37.77 | 0 | 0 | 0
869 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF GURAP W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/15798 | Augmentation | New Service connection quotation charges for ph-4 Gurap pwss | 523 | 12/12/2023 | 0 | WBSEDCL | 10.02 | 0 | 0 | 0
870 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF GURAP W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/15798 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gurap water supply scheme, T.W. No. I, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | 1633/ED | 11/04/2023 | 90 | DITHI ENTERPRISE | 11.4 | 11.38 | 100 | 70
871 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF GURAP W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/15798 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | 882/HUG | 27/03/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 12.88 | 100 | 65
872 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF GURAP W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/15798 | Augmentation | Laying UPVC Pipeline for Proper Drainage of Washout / Overflow Water to Nearby Pond & Replacement Of Damaged Sluice Valve At Head Works Site For Gurap Piped Water Supply Scheme Under Dhaniakhali Block Of Chinsurah Sub-Division Under Hooghly Division, Phe Dte. | 314/CH | 21/02/2025 | 15 | ARUN SEAL AND CO. | 3.13 | 0 | 0 | 0
873 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF GURAP W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/15798 | Augmentation | REPAIRING & RENOVATION OF SWITCH ROOM INCLUDING BOUNDARY WALL AT HEAD WORKS SITE OF GURAP WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURAH SUB-DIVISION UNDER HOOGHLY DIVISION, PHE DTE. | 130/CH | 29/01/2025 | 10 | ARUN SEAL AND CO. | 4.83 | 0 | 0 | 0
874 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RADHABALLABHPUR WATER SUPPLY SCHEME , SM/07541 | Retrofitting | FHTC |  | 19/03/2021 | 0 | DOULPHIN ENTERPRISE (RANJIT KHANRA) | 42 | 0 | 0 | 0
875 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RADHABALLABHPUR WATER SUPPLY SCHEME , SM/07541 | Retrofitting | FHTC |  | 23/07/2021 | 0 | DOULPHIN ENTERPRISE (RANJIT KHANRA) | 1.97 | 0 | 0 | 0
876 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RADHABALLABHPUR WATER SUPPLY SCHEME , SM/07541 | Retrofitting | Placement of Fund | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
877 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RADHABALLABHPUR WATER SUPPLY SCHEME , SM/07541 | Retrofitting | Providing 150 nos Functional Household Tap Connection (FHTC) within the command area of Radhaballvpur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | 2123/Hug | 01/12/2021 | 20 | SWASTIK ENTERPRISE | 8.08 | 8.15 | 100 | 100
878 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RADHABALLABHPUR WATER SUPPLY SCHEME , SM/07541 | Retrofitting | Providing 150 nos Functional Household Tap Connection (FHTC) within the command area of RADHABALLAVPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte | 2232/Hug | 15/12/2021 | 20 | DREAM INFRASTRUCTURE | 4.92 | 0 | 0 | 100
879 | HOOGHLY | Hooghly Division | Surjyapur Mini Piped Water Supply Scheme , SM/13594 | New | Material Requisition To Resource Division | 1385/9/Hug | 15/05/2023 | 0 | Resource Division | 0.49 | 0 | 0 | 0
880 | HOOGHLY | Hooghly Division | Surjyapur Mini Piped Water Supply Scheme , SM/13594 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-250 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 31.76 | 0 | 0 | 0
881 | HOOGHLY | Electrical | Surjyapur Mini Piped Water Supply Scheme , SM/13594 | New | Mini Piped Water Supply Scheme. | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0 | 0
882 | HOOGHLY | Central Drilling | Development of Borhal (Zone-II) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore S , SM/16450 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BORHAL (Z-II, TW-I) JANGIPARA BLOCK, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 2003/CDD | 09/02/2023 | 30 | UTTAM KUMAR CHATTERJEE | 12.54 | 10.75 | 85.73 | 0
883 | HOOGHLY | Central Drilling | Development of Borhal (Zone-II) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore S , SM/16450 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 210 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BORHAL (Z-II) PWSS (TW-I), JANGIPARA BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 1774/CDD | 02/01/2023 | 30 | C.M. ENTERPRISE | 12.52 | 11.06 | 100 | 0
884 | HOOGHLY | Central Drilling | Development of Borhal (Zone-II) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore S , SM/16450 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BORHAL W/S SCH (ZONE-II) (TW-II), JANGIPARA BLOCK, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 1994/CDD | 07/02/2023 | 30 | CHANDA ENTERPRISE | 25.08 | 22.93 | 100 | 100
885 | HOOGHLY | Hooghly Division | Development of Borhal (Zone-II) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore S , SM/16450 | Augmentation | Material Requisition To Resource Division | 1384/4/Hug | 15/05/2023 | 0 | Resource Division | 0.62 | 0 | 0 | 0
886 | HOOGHLY | Electrical | Development of Borhal (Zone-II) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore S , SM/16450 | Augmentation | Quotation Bill for New Service Connection at Borhal W/S. Sch. PH-2 & 3 | 26 | 11/05/2023 | 0 | WBSEDCL | 11.8 | 0 | 0 | 0
887 | HOOGHLY | Electrical | Development of Borhal (Zone-II) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore S , SM/16450 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Borhal (Zone-II) water supply scheme, T.W. No. I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | 1632/ED | 11/04/2023 | 90 | INDTECH ASSOCIATES. | 22.81 | 22.17 | 97.21 | 85
888 | HOOGHLY | Hooghly Division | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/15886 | New | Material Requisition To Resource Division | 1385/33/Hug | 15/05/2023 | 0 | Resource Division | 9.36 | 0 | 0 | 0
889 | HOOGHLY | Hooghly Division | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/15886 | New | Material Requisition To Resource Division | 3057/40/Hug | 11/10/2023 | 0 | Resource Division | 9.36 | 0 | 0 | 0
890 | HOOGHLY | Hooghly Division | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/15886 | New | Material Requisition To Resource Division | 1234/11/Hug | 28/04/2023 | 0 | Resource Division | 25 | 0 | 0 | 0
891 | HOOGHLY | Electrical | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/15886 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Tirol (Zone-II) water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 1708/ED | 18/04/2023 | 90 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 22.05 | 5.59 | 25.37 | 40
892 | HOOGHLY | Hooghly Division | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/15886 | New | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of KRISHNANAGAR ZONE-II,MAYAPUR,TIROL ZONE-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3783/HUG | 25/11/2024 | 60 | DAS CONSTRUCTION | 55.5 | 0 | 0 | 0
893 | HOOGHLY | Electrical | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/15886 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for TIROL PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1189/ED | 14/06/2024 | 271 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 10.73 | 0 | 0 | 0
894 | HOOGHLY | Hooghly Division | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/15886 | New | Construction of Approach Road at Tirol Zone-I Piped Water Supply Scheme under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. | 3467/HUG | 04/10/2024 | 15 | MINTU CHAKRABORTY | 3.45 | 0 | 0 | 0
895 | HOOGHLY | Electrical | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/15886 | New | Quotation money deposition for new service connection at Tirol w/s scheme , Zone -II, T.W. No- II, Dist.- Hooghly, under Electrical Division, PHE Dte. Application No.- 5004038623 Ref. ID- 503577402 SM Code- 15886 | 831 | 04/03/2024 | 0 | WBSEDCL | 4.13 | 0 | 0 | 0
896 | HOOGHLY | Electrical | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/15886 | New | Quotation of New Service Connection for Tirol w/s Scheme, Zone-I,PH No-I Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.( SM/158668) Application No-5004061104 Reference Id-503590562 | 886 | 15/03/2024 | 0 | WBSEDCL | 4.62 | 0 | 0 | 0
897 | HOOGHLY | Electrical | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/15886 | New | Quotation money deposition for new service connection at Tirol w/s scheme , Zone -II, T.W. No- I, Dist.- Hooghly, under Electrical Division, PHE Dte. Application No.- 5004038621 Ref. ID- 503577388 SM Code- 15886 | 832 | 04/03/2024 | 0 | WBSEDCL | 6 | 0 | 0 | 0
898 | HOOGHLY | Hooghly Division | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/15886 | New | TIROL ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site, under ARAMBAGH Block, District:- Hooghly [NEW SCHEME] | 2279/HUG | 03/08/2023 | 591 | UNIQUE AGENCY | 361.39 | 332.79 | 92.09 | 70
899 | HOOGHLY | Hooghly Division | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/15886 | New | Laying rising main pipe for inter connection between Proposed T.W & Distribution including Protection work of TIROL Z-II Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 572/HUG | 04/03/2025 | 60 | UNIQUE AGENCY | 16.09 | 0 | 0 | 0
900 | HOOGHLY | Hooghly Division | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/15887 | New | Material Requisition To Resource Division | 1234/31/Hug | 28/04/2023 | 0 | Resource Division | 56.14 | 0 | 0 | 0
901 | HOOGHLY | Hooghly Division | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/15887 | New | Material Requisition To Resource Division | 3057/61/Hug | 11/10/2023 | 0 | Resource Division | 14.12 | 0 | 0 | 0
902 | HOOGHLY | Electrical | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/15887 | New | Quotation of New Service Connection Charge for Garmandaran w/s Scheme,Zone-II,PH No-I,Block-Goghat-I Dist-Hooghly under ED,PHE Dte | 241 | 01/09/2023 | 0 | WBSEDCL | 4.17 | 0 | 0 | 0
903 | HOOGHLY | Electrical | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/15887 | New | Quotation of New Service Connection Charge for Garmandaran w/s Scheme,Zone-II,PH No-II Block-Goghat-II, Dist-Hooghly under Electrical Division ,PHE Dte | 242 | 01/09/2023 | 0 | WBSEDCL | 5.35 | 0 | 0 | 0
904 | HOOGHLY | Hooghly Division | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/15887 | New | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GARMANDARAN Z-II Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 3656/HUG | 13/11/2024 | 90 | M/S BIMAL DAS AND CO. | 16.13 | 0 | 0 | 0
905 | HOOGHLY | Hooghly Division | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/15887 | New | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of PUKURIA, GARMANDARAN Zone-I , GARMANDARAN Zone -II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3781/HUG | 25/11/2024 | 60 | KAJAL DEY | 55.4 | 0 | 0 | 0
906 | HOOGHLY | Electrical | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/15887 | New | Quotation of New Service Connection for Gar Mandaran w/s Scheme,Zone-II,PH no-III Block-Goghat-II Dist-Hooghly under Electrical division,PHe Dte.(SM/15887) Application No-5004498949 Reference Id-503815611 | 638 | 18/12/2024 | 0 | WBSEDCL | 9.44 | 0 | 0 | 0
907 | HOOGHLY | Hooghly Division | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/15887 | New | GARMANDARAN ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-II Block of Arambag SUb-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | 1671/HUG | 08/06/2023 | 827 | TITAS CONSTRUCTION | 476.79 | 125.04 | 26.23 | 55
908 | HOOGHLY | Electrical | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/15887 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Garmandaran (Zone-II) water supply scheme, T.W. No. III & IV, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | 3450/ED | 11/08/2023 | 874 | M.D ENTERPRISE | 21.44 | 0 | 0 | 20
909 | HOOGHLY | Hooghly Division | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/15887 | New | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of PUKURIA , GARMANDARAN Zone-I , GARMANDARAN Zone-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3529/HUG | 22/10/2024 | 221 | KHAN ENTERPRISE | 48.02 | 0 | 0 | 66
910 | HOOGHLY | Hooghly Division | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/15887 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) RAGHUBATI PWSS- 2no¿s (2) GANESHBATI PWSS- 1 no¿s (3) BENGAI PWSS- 1 no¿s (4) BHURKUNDA PWSS(Z-I)- 1no¿s (5) GARMANDARAN (Z-I)- 4 no¿s, (6) GARMANDARAN PWSS (Z-II)- 4 no¿s, (7) SAMANTAKHANDA PWSS -1 no¿s | 1148/Arg | 10/12/2024 | 31 | TITAS CONSTRUCTION | 0.98 | 0 | 0 | 0
911 | HOOGHLY | Electrical | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/15887 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Garmandaran (Zone-II) water supply scheme, T.W. No. I, II, III & IV, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | 1706/ED | 18/04/2023 | 805 | UNITED TRADERS | 21.47 | 20.78 | 96.84 | 30
912 | HOOGHLY | Hooghly Division | Source Augmentation of BALI Piped Water Supply Scheme under Goghat-I Block , SM/15803 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at BALI PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | 743/HUG | 15/03/2023 | 30 | MAYA CONSTRUCTION | 11.32 | 9.91 | 100 | 100
913 | HOOGHLY | Electrical | Source Augmentation of BALI Piped Water Supply Scheme under Goghat-I Block , SM/15803 | Augmentation | Quotation of New Service Connection for Bali w/s Scheme, PH No-3 Block-Goghat-I,Dist-Hooghly under Electrical Division,PHE Dte.(SM/15803) Application No-5004191492 Reference Id-503647819. |  | 29/05/2024 | 0 | WBSEDCL | 7.09 | 0 | 0 | 0
914 | HOOGHLY | Hooghly Division | Source Augmentation of BALI Piped Water Supply Scheme under Goghat-I Block , SM/15803 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of BALI Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-I Block. | 1492/HUG | 22/05/2023 | 690 | P.K. GHOSH & CO. | 11.81 | 0 | 0 | 90
915 | HOOGHLY | Electrical | Source Augmentation of BALI Piped Water Supply Scheme under Goghat-I Block , SM/15803 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bali water supply scheme, T.W. No. I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | 1496/ED | 28/03/2023 | 795 | RUBY ENTERPRISE. | 10.75 | 0 | 0 | 30
916 | HOOGHLY | Hooghly Division | Source Augmentation of PATUL Piped Water Supply Scheme under Khanakul-I Block , SM/15804 | Augmentation | Material Requisition To Resource Division | 1263/15/Hug | 03/05/2023 | 0 | Resource Division | 5.69 | 0 | 0 | 0
917 | HOOGHLY | Hooghly Division | Source Augmentation of PATUL Piped Water Supply Scheme under Khanakul-I Block , SM/15804 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at PATUL PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte.. | 655/HUG | 09/03/2023 | 30 | R CONSTRUCTION | 11.31 | 9.95 | 100 | 100
918 | HOOGHLY | Electrical | Source Augmentation of PATUL Piped Water Supply Scheme under Khanakul-I Block , SM/15804 | Augmentation | Quotation Bill for New Service Connection at Patul W/S. Sch. Z-II, TW-I | 594 | 29/12/2023 | 0 | WBSEDCL | 3.55 | 0 | 0 | 0
919 | HOOGHLY | Electrical | Source Augmentation of PATUL Piped Water Supply Scheme under Khanakul-I Block , SM/15804 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Patul water supply scheme, T.W. No. I, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | 1620/ED | 11/04/2023 | 720 | NITESH MANAGEMENT | 10.74 | 0 | 0 | 50
920 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. , SM/08740 | Retrofitting | FHTC |  | 21/09/2021 | 0 | SATYA NARAYAN BISWAS | 20.9 | 0 | 0 | 0
921 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. , SM/08740 | Retrofitting | FHTC |  | 30/09/2021 | 0 | SIKHA ENTERPRISE | 4.58 | 0 | 0 | 0
922 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. , SM/08740 | Retrofitting | FHTC |  | 30/09/2021 | 0 | BRISTI CONSTRUCTION | 4.58 | 0 | 0 | 0
923 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. , SM/08740 | Retrofitting | FHTC |  | 30/09/2021 | 0 | SURAJIT SINGHA RAY | 5.04 | 0 | 0 | 0
924 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. , SM/08740 | Retrofitting | FHTC |  | 30/09/2021 | 0 | SATYA NARAYAN BISWAS | 9.09 | 0 | 0 | 0
925 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. , SM/08740 | Retrofitting | Providing 1634 nos F.H.T.C. in Baladbandha ,Basudebpur, Kaikala & Baramba Village of Kaikala Zone-II and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | 1147/HUG | 29/06/2021 | 40 | SATYA NARAYAN BISWAS | 72.55 | 17.52 | 24.15 | 100
926 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. , SM/08740 | Retrofitting | FHTC |  | 28/01/2022 | 0 | SWASTIK ENTERPRISE | 5.1 | 0 | 0 | 0
927 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. , SM/08740 | Retrofitting | Providing 1634 nos F.H.T.C. in Baladbandha ,Basudebpur, Kaikala & Baramba Village of Kaikala Zone-II and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | 1147/Hug | 29/06/2021 | 40 | SATYA NARAYAN BISWAS | 72.55 | 48.89 | 100 | 100
928 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. , SM/08740 | Retrofitting | Providing 91 nos. tap connection at Ichapur mouza of Kaikala water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. to make it "SWAJAL VILLAGE" | 14/chan | 05/01/2022 | 20 | SWASTIK ENTERPRISE | 5 | 5.02 | 100 | 100
929 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. , SM/08740 | Retrofitting | Providing balance 81 nos F.H.T.C. in Baladbandh village of kaikala Zone-1 and its adjoining mouzas water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. | 354/chan | 16/08/2021 | 20 | MGM ENTERPRISE | 4.93 | 3.55 | 100 | 100
930 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. , SM/08740 | Retrofitting | Construction of Boundary Wall and Laying of rising main at 3rd Tubewell site of KAIKALA Water Supply Scheme under Hooghly Division, PHE Dte. | 210/chan | 13/04/2022 | 30 | SWASTIK ENTERPRISE | 5 | 4.65 | 100 | 0
931 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. , SM/08740 | Retrofitting | Providing F.H.T.C in leftout portion of Choutara, Basudebpur, Baladbandh, Baramba, Ichapur, Kaikala village of Kaikala Zone-II and its adjoining mouzas water supply scheme under Chandannagar Sub-Division P.H.E. Dte. [Block-Haripal] of Hooghly Division P.H.E Dte. | 2139/HUG | 26/09/2022 | 45 | MALLIKA ENTERPRISE | 63.68 | 62.39 | 100 | 100
932 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOURHATI WATER SUPPLY SCHEME. , SM/08742 | Retrofitting | Providing 350 nos Functional Household Tap Connection (FHTC) within the command area of Gourhati Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh] | 715/Hug | 07/04/2022 | 30 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 16.57 | 12.35 | 74.56 | 100
933 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOURHATI WATER SUPPLY SCHEME. , SM/08742 | Retrofitting | Providing 300 nos Functional Household Tap Connection (FHTC) within the command area of GOURHATI Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | 463/Hug | 10/03/2022 | 20 | ZENITH CONSTRUCTION | 18.73 | 16.44 | 87.75 | 40
934 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOURHATI WATER SUPPLY SCHEME. , SM/08742 | Retrofitting | Providing 1050 nos Functional Household Tap Connection (FHTC) within the command area (left out portion) of Gourhati Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | 2127/Hug | 01/12/2021 | 40 | DILIP KUMAR GHOSH | 36.01 | 43.58 | 100 | 100
935 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOURHATI WATER SUPPLY SCHEME. , SM/08742 | Retrofitting | Material Requisition To Resource Division | 427/2-2/Hug | 07/03/2022 | 0 | Resource Division | 10.43 | 0 | 0 | 0
936 | HOOGHLY | Hooghly Division | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block , SM/15805 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at RADHABALLAVPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | 747/HUG | 15/03/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.32 | 10.28 | 90.77 | 0
937 | HOOGHLY | Electrical | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block , SM/15805 | Augmentation | Quotation of New Service Connection for Radhaballavpur w/s Scheme, TW No-3 Dist- Hooghly under ED,PHE Dte | 117 | 20/07/2023 | 0 | WBSEDCL | 2.82 | 0 | 0 | 0
938 | HOOGHLY | Electrical | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block , SM/15805 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Radhaballabpur water supply scheme, T.W. No. I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | 1622/ED | 11/04/2023 | 90 | M/S, GHOSH ENTERPRISE | 10.74 | 10.66 | 100 | 40
939 | HOOGHLY | Hooghly Division | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block , SM/15805 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) GANESHBATI PWSS-3nos (2) AMDOBA PWSS-2nos (3) BALI PWSS- 3nos (4) RADHABALLAVPUR PWSS- 3nos (5) RAMNAGAR PWSS-3 nos | 818/Arg | 23/08/2024 | 130 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.21 | 100 | 100
940 | HOOGHLY | Hooghly Division | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block , SM/15805 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of RADHABALLAVPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-I Block. | 1498/HUG | 22/05/2023 | 690 | P.K. GHOSH & CO. | 11.83 | 7.91 | 66.9 | 85
941 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15899 | Augmentation | Material Requisition To Resource Division | 3059/31/Hug | 11/10/2023 | 0 | Resource Division | 1.85 | 0 | 0 | 0
942 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15899 | Augmentation | Material Requisition To Resource Division | 3004/19/Hug | 05/10/2023 | 0 | Resource Division | 20.39 | 0 | 0 | 0
943 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15899 | Augmentation | Augmentation Kola PWSS | BP-2023-24-398 | 26/09/2023 | 0 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 4.22 | 0 | 0 | 0
944 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15899 | Augmentation | "Quotation Bill for New Service Connection at Kola W/S. Sch. " | 440 | 23/11/2023 | 0 | WBSEDCL | 3.17 | 0 | 0 | 0
945 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15899 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kola water supply scheme, T.W. No. I, Block: Chinsurah-Magra, District- Hooghly under Electrical Division, PHE Dte. | 1634/ED | 11/04/2023 | 90 | BIJAN ENTERPRISE | 11.4 | 11.08 | 97.24 | 95
946 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15899 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed T.W with distribution system , FHTC of KOLA W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | 1314/HUG | 10/05/2023 | 30 | M/S T.K.B. CONSTRUCTION | 32.26 | 31.34 | 100 | 50
947 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15899 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | 882/HUG | 27/03/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 13.08 | 100 | 65
948 | HOOGHLY | Hooghly Division | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block , SM/15814 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | 1420/HUG | 17/05/2023 | 30 | SB ASSOCIATES | 11.82 | 0 | 0 | 0
949 | HOOGHLY | Hooghly Division | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block , SM/15814 | Augmentation | Sinking of Two Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at KAPSIT PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | 2861/HUG | 20/09/2023 | 360 | SUBHAJIT BISWAS | 22.56 | 11.07 | 49.08 | 50
950 | HOOGHLY | Electrical | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block , SM/15814 | Augmentation | Quotation of New Service Connection for Kapsit w/s Scheme, PH No-3 Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/15814) Application No-5004276344 Reference Id-503683335. | 264 | 03/07/2024 | 0 | WBSEDCL | 3.77 | 0 | 0 | 0
951 | HOOGHLY | Electrical | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block , SM/15814 | Augmentation | Quotation of New Service Connection for Kapsit w/s Scheme,PH No-IV Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/15814) Application No-5004320167 Reference Id- 503705436 | 335 | 30/07/2024 | 0 | WBSEDCL | 11.46 | 0 | 0 | 0
952 | HOOGHLY | Electrical | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block , SM/15814 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kapsit water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 1504/ED | 28/03/2023 | 888 | A.K. ENTERPRISE | 21.93 | 8.12 | 37.05 | 100
953 | HOOGHLY | Electrical | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY , SM/15791 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mayapur (Zone-I) water supply scheme, T.W. No. I, II, III & IV, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 1711/ED | 18/04/2023 | 90 | D. K. ELECTRIC | 40.97 | 0 | 0 | 0
954 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY , SM/15791 | New | Material Requisition To Resource Division | 1234/13/Hug | 28/04/2023 | 0 | Resource Division | 44.08 | 0 | 0 | 0
955 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY , SM/15791 | New | Material Requisition To Resource Division | 1385/58/Hug | 15/05/2023 | 0 | Resource Division | 6.44 | 0 | 0 | 0
956 | HOOGHLY | Electrical | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY , SM/15791 | New | Quotation for new service connection charge at Mayapur PWSS, Zone-I, TW - I | 462 | 01/12/2023 | 0 | WBSEDCL | 4.9 | 0 | 0 | 0
957 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY , SM/15791 | New | Sinking of 3rd tube-well by D.R. Rig method ,Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of MAYAPUR (ZONE-I) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | 448/HUG | 15/02/2024 | 60 | MS PRADIP KUMAR PAL | 29.69 | 12.09 | 40.73 | 40
958 | HOOGHLY | Electrical | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY , SM/15791 | New | Quotation for New Service Connection at Mayapur W/S. Sch. Z=I | 611 | 04/01/2024 | 0 | WBSEDCL | 5.8 | 0 | 0 | 0
959 | HOOGHLY | Electrical | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY , SM/15791 | New | Quotaion of New Service Connection for Mayapur w/s Scheme,Zone-I,PH No-II Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/15791) Application No-5004314243 Reference Id-503702554 | 334 | 30/07/2024 | 0 | WBSEDCL | 7.67 | 0 | 0 | 0
960 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY , SM/15791 | New | MAYAPUR ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site, under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] | 1300 | 08/05/2023 | 812 | MS PRADIP KUMAR PAL | 360.88 | 159.06 | 44.08 | 15
961 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY , SM/15791 | New | Revised Geo-reference drawing (CAD-GIS) and redsign of Network Distribution System of Mayapur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte . | 805/Arg | 23/08/2024 | 10 | APEX ENGINEERING | 0.83 | 0 | 0 | 0
962 | HOOGHLY | Electrical | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16122 | Augmentation | Hire Charges Bill for official use office of the Assistant Engineer -I PHED | 203_ae1 | 27/03/2023 | 365 | DASHRATH KUMAR PRAJAPATI | 5 | 0.39 | 7.83 | 1
963 | HOOGHLY | Electrical | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16122 | Augmentation | Quotation of New Service Connection for Jagatpur w/s Scheme, TW No-4 Block-Khanakul-II,Dist-Hooghly under Electrical Division, PHE Dte | 308 | 27/09/2023 | 0 | WBSEDCL | 7.56 | 0 | 0 | 0
964 | HOOGHLY | Electrical | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16122 | Augmentation | Quotation of New Service Connection for Jagatpur w/s Scheme, TW no-5 Block-Khanakul-II,Dist-Hooghly under Electrical division,PHE Dte | 289 | 20/09/2023 | 0 | WBSEDCL | 6.65 | 0 | 0 | 0
965 | HOOGHLY | Electrical | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16122 | Augmentation | Hire Charges Bill of V.No.- WB-04G-2822 for official use of Electrical Division PHED. | 591_AE-1_ED | 21/08/2023 | 7 | DASHRATH KUMAR PRAJAPATI | 5 | 1.95 | 167.34 | 10
966 | HOOGHLY | Electrical | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16122 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jagatpur water supply scheme, T.W. No. I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | 1707/ED | 18/04/2023 | 90 | GHOSE ENGINEERING SYNDICATE | 21.93 | 21.82 | 100 | 40
967 | HOOGHLY | Hooghly Division | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16122 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system, For Source Augmentation of JAGATPUR W/S Scheme under Arambagh Sub - Division P.H.E. Dte. | 1444/HUG | 18/05/2023 | 30 | S.S. CONSULTANCY AND CONSTRUCTION | 31.19 | 31.18 | 100 | 65
968 | HOOGHLY | Electrical | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16122 | Augmentation | Quotation of New Service Connection for Jagatpur w/s Scheme,PH No-I Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/16122) Application No-5004134007 Reference Id-503627506 | 262 | 03/07/2024 | 0 | WBSEDCL | 12.35 | 0 | 0 | 0
969 | HOOGHLY | Hooghly Division | GROUND WATER BASED RAJABALLABHBATI PIPED W/S SCHEME , SM/16136 | New | Material Requisition To Resource Division | 1383/36/Hug | 15/05/2023 | 0 | Resource Division | 3.33 | 0 | 0 | 0
970 | HOOGHLY | Electrical | GROUND WATER BASED RAJABALLABHBATI PIPED W/S SCHEME , SM/16136 | New | Quotation Bill for New Service Connection at Rajballavbati W/S. Sch. TW-I | 412 | 09/11/2023 | 0 | WBSEDCL | 6.55 | 0 | 0 | 0
971 | HOOGHLY | Electrical | GROUND WATER BASED RAJABALLABHBATI PIPED W/S SCHEME , SM/16136 | New | Quotation for new service connection charge at Rajballabhbati PWSS, TW - II | 528 | 15/12/2023 | 0 | WBSEDCL | 1.71 | 0 | 0 | 0
972 | HOOGHLY | Hooghly Division | GROUND WATER BASED RAJABALLABHBATI PIPED W/S SCHEME , SM/16136 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Rajballabhbati Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-A). | 149/Chan | 16/02/2024 | 15 | TECHVISION | 0.84 | 0.84 | 100 | 98
973 | HOOGHLY | Electrical | GROUND WATER BASED RAJABALLABHBATI PIPED W/S SCHEME , SM/16136 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajaballabhbati water supply scheme, T.W. No. I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | 1710/ED | 18/04/2023 | 714 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 20.5 | 16.76 | 65.77 | 20
974 | HOOGHLY | Hooghly Division | Ramnagar Piped Water Supply Scheme. , SM/16757 | New | Material Requisition To Resource Division | 3057/34/Hug | 11/10/2023 | 0 | Resource Division | 15.7 | 0 | 0 | 0
975 | HOOGHLY | Hooghly Division | Ramnagar Piped Water Supply Scheme. , SM/16757 | New | Material Requisition To Resource Division | 1234/19/Hug | 28/04/2023 | 0 | Resource Division | 27.39 | 0 | 0 | 0
976 | HOOGHLY | Hooghly Division | Ramnagar Piped Water Supply Scheme. , SM/16757 | New | Material Requisition To Resource Division | 2607/1/Hug | 29/08/2023 | 0 | Resource Division | 14.19 | 0 | 0 | 0
977 | HOOGHLY | Electrical | Ramnagar Piped Water Supply Scheme. , SM/16757 | New | Quotation for New Service Connection of Ramnagar W/s scheme, PH No-I, District-Hooghly under Electrical Division, PHE Dte | 93 | 13/07/2023 | 0 | WBSEDCL | 11.28 | 0 | 0 | 0
978 | HOOGHLY | Electrical | Ramnagar Piped Water Supply Scheme. , SM/16757 | New | Quotation for New Service Connection of Ramnagar W/s Scheme, PH No-II, District-Hooghly Under Electrical Division PHE Dte | 94 | 13/07/2023 | 0 | WBSEDCL | 10.9 | 0 | 0 | 0
979 | HOOGHLY | Electrical | Ramnagar Piped Water Supply Scheme. , SM/16757 | New | Quotation of New Service Connection for Ramnagar w/s Scheme,PH No-3,Block-Arambag,Dist-Hooghly under Electrical Division, PHE Dte | 346 | 11/10/2023 | 0 | WBSEDCL | 12.88 | 0 | 0 | 0
980 | HOOGHLY | Electrical | Ramnagar Piped Water Supply Scheme. , SM/16757 | New | Quotation Bill for for New Service Connection at Salepue Paschimpara Ramnagar W/S. Sch. TW-3 | 428 | 17/11/2023 | 0 | WBSEDCL | 1.21 | 0 | 0 | 0
981 | HOOGHLY | Hooghly Division | Ramnagar Piped Water Supply Scheme. , SM/16757 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of RAMNAGAR Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | 3088/HUG | 12/10/2023 | 550 | UNIQUE AGENCY | 34.81 | 23.65 | 67.93 | 45
982 | HOOGHLY | Electrical | Ramnagar Piped Water Supply Scheme. , SM/16757 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ramnagar water supply scheme, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 1798/ED | 24/04/2023 | 90 | C.M. ENTERPRISE | 21.38 | 21.33 | 100 | 50
983 | HOOGHLY | Hooghly Division | Ramnagar Piped Water Supply Scheme. , SM/16757 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) GANESHBATI PWSS-3nos (2) AMDOBA PWSS-2nos (3) BALI PWSS- 3nos (4) RADHABALLAVPUR PWSS- 3nos (5) RAMNAGAR PWSS-3 nos | 818/Arg | 23/08/2024 | 130 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.21 | 100 | 100
984 | HOOGHLY | Hooghly Division | Ramnagar Piped Water Supply Scheme. , SM/16757 | New | RAMNAGAR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under ARAMBAG Block, District:- Hooghly [NEW SCHEME] | 1503/HUG | 22/05/2023 | 664 | UNIQUE AGENCY | 562.52 | 529.38 | 94.11 | 85
985 | HOOGHLY | Hooghly Division | Ramnagar Piped Water Supply Scheme. , SM/16757 | New | Laying Additional pipeline for connection of 3rd Tubewell with HDPE PE 80, PN 1.0 pipes with supporting structure, Horizontal Auger boring with water jet system and Approach Road at Ramnagar Piped Water Supply Scheme under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. | 3688/HUG | 14/11/2024 | 153 | UNIQUE AGENCY | 28.47 | 0 | 0 | 50
986 | HOOGHLY | Hooghly Division | SINHAL PATAN PIPED WATER SUPPLY SCHEME , SM/18103 | New | Material Requisition To Resource Division | 1383/45/Hug | 15/05/2023 | 0 | Resource Division | 1.42 | 0 | 0 | 0
987 | HOOGHLY | Hooghly Division | SINHAL PATAN PIPED WATER SUPPLY SCHEME , SM/18103 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sinhal Pathan Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-B). | 429/chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.84 | 0.84 | 100 | 100
988 | HOOGHLY | Hooghly Division | SINHAL PATAN PIPED WATER SUPPLY SCHEME , SM/18103 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sinhal Pathan Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-C). | 430/chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.78 | 0.78 | 100 | 100
989 | HOOGHLY | Hooghly Division | SINHAL PATAN PIPED WATER SUPPLY SCHEME , SM/18103 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sinhal Pathan Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-A). | 428/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.92 | 0.92 | 100 | 100
990 | HOOGHLY | Electrical | SINHAL PATAN PIPED WATER SUPPLY SCHEME , SM/18103 | New | Quotation for new service connection at Sinhal Patan water supply Scheme [SM/18103], T/W No. - I, Block - Singur, under Singur CCC, WBSEDCL, Ref. No. - 503588851, Dt. - 07-03-2024, Application No. - 5004057413 | 877 | 13/03/2024 | 0 | WBSEDCL | 3.3 | 0 | 0 | 0
991 | HOOGHLY | Hooghly Division | SINHAL PATAN PIPED WATER SUPPLY SCHEME , SM/18103 | New | SINHAL Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. Block Singur, District:- Hooghly [NEW SCHEME] | 1566/HUG | 29/05/2023 | 730 | BIMAL KUMAR HALDER | 79.42 | 0 | 0 | 90
992 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Construction of 600 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & FHTC In Daluigaccha Mouza For AUGMENTATION Of KAMARKUNDU (ZONE-VI) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | 2609/HUG | 29/08/2023 | 270 | SUJATA CONSTRUCTION | 227.52 | 0 | 0 | 0
993 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch. Z-II, TW-I | 575 | 27/12/2023 | 0 | WBSEDCL | 4.52 | 0 | 0 | 0
994 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch. Z-VI, TW-III | 576 | 27/12/2023 | 0 | WBSEDCL | 3.64 | 0 | 0 | 0
995 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Quotation for new service connection charge at Kamarkundu PWSS, Zone-VI, TW - II | 589 | 28/12/2023 | 0 | WBSEDCL | 3.79 | 0 | 0 | 0
996 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | AUGMENTATION of KAMARKUNDU (ZONE-IV) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of CHANDANNAGAR Sub Division, District:- Hooghly [AUGMENTATION ] | 3113/HUG | 13/10/2023 | 602 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 204.08 | 124.34 | 60.93 | 50
997 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Balance FHTC in SINGUR CT (P) Mouza For AUGMENTATION Of KAMARKUNDU (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | 763/HUG | 05/03/2024 | 15 | SRI KRISHNA ENTERPRISE | 7.1 | 0 | 0 | 0
998 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir of KAMARKUNDU PWSS under ChandannagarSub-Division of Hooghly Division, P.H.E. Dte. | 4057/HUG | 19/12/2024 | 120 | SWASTIK ENTERPRISE | 13 | 0 | 0 | 0
999 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Balance FHTC in various Mouzas For AUGMENTATION Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | 752/HUG | 05/03/2024 | 15 | ARUN SEAL AND CO. | 9.77 | 9.65 | 100 | 100
1000 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Laying left out pipe line For Augmentation of KAMARKUNDU Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | 761/HUG | 05/03/2024 | 15 | BOSE ENTERPRISE (RATUL BOSE) | 7.28 | 6.85 | 100 | 100
1001 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Laying additional pipe line For Restoration of water supply Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | 760/HUG | 05/03/2024 | 15 | BOSE ENTERPRISE (RATUL BOSE) | 9.97 | 9.89 | 100 | 100
1002 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Laying additional pipe line & FHTC in various Mouzas For AUGMENTATION Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | 754/HUG | 05/03/2024 | 15 | ARUN SEAL AND CO. | 9.79 | 9.72 | 100 | 100
1003 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Laying additional pipe line & FHTC in SINGUR (CT ) & BURIGEON Mouza For AUGMENTATION Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | 757/HUG | 05/03/2024 | 15 | DAS ENTERPRISE (SAMIR DAS) | 9.97 | 9.93 | 100 | 100
1004 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Kamarkundu (Z-7) 1st T/W site & Kamarkundu (Z-7) 2nd T/W site under Chandannagar Sub-Division PHE Dte. | 920/Chan | 05/11/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 0 | 100
1005 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Laying additional pipe line For Restoration of water supply Of KAMARKUNDU Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | 759/HUG | 05/03/2024 | 15 | ARUN SEAL AND CO. | 9.98 | 9.97 | 100 | 100
1006 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Balance FHTC in various Mouzas For AUGMENTATION Of KAMARKUNDU (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | 762/HUG | 05/03/2024 | 15 | DAS ENTERPRISE (SAMIR DAS) | 9.8 | 9.62 | 100 | 100
1007 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Laying additional pipe line in various Mouzas For AUGMENTATION Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | 753/HUG | 05/03/2024 | 15 | ARUN SEAL AND CO. | 9.78 | 9.66 | 100 | 100
1008 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Laying additional pipe line & FHTC in BURIGAON Mouza For AUGMENTATION Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | 755/HUG | 05/03/2024 | 15 | ARUN SEAL AND CO. | 10 | 9.97 | 100 | 100
1009 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Laying additional pipe line & FHTC in SINGUR(CT)Mouza For AUGMENTATION Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | 756/HUG | 05/03/2024 | 15 | DAS ENTERPRISE (SAMIR DAS) | 9.97 | 9.89 | 100 | 100
1010 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Quotation Bill for New Service Connection at Gopalnagar W/S. Sch.TW-II | 596A | 29/12/2023 | 0 | WBSEDCL | 3.79 | 0 | 0 | 0
1011 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-III | 719 | 29/01/2024 | 0 | WBSEDCL | 3.47 | 0 | 0 | 0
1012 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Quotation for new service connnection at Kamarkundu W/S. Sch. TW-I, Z-VII | 773 | 19/02/2024 | 0 | WBSEDCL | 4.67 | 0 | 0 | 0
1013 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Quotation money deposition for new service connection at Kamarkundu w/s scheme, Zone- VI, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004229746 Reference ID- 503663995 SM Code- 18397 | 218 | 18/06/2024 | 0 | WBSEDCL | 4.94 | 0 | 0 | 0
1014 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | PAYMENT FOR ROAD RESTORATION | BP-2024-25-185 | 06/06/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 26.97 | 0 | 0 | 0
1015 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Restoration Works for Singur-Ugly Road | BP-2023-24-852 | 21/02/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 1.49 | 0 | 0 | 0
1016 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch. Z-II, TW-II | 673 | 17/01/2024 | 0 | WBSEDCL | 6.51 | 0 | 0 | 0
1017 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch. Z-II, TW-III | 730 | 05/02/2024 | 0 | CESC LIMITED. | 5.17 | 0 | 0 | 0
1018 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-VI | 717 | 29/01/2024 | 0 | WBSEDCL | 4.81 | 0 | 0 | 0
1019 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Quotation for new service connection at Kamarkundu W/S Sch., Zone - V, T/W No. - I,[SM/18397], under Singur CCC, WBSEDCL, Ref. Id. - 503706067, Dt. - 30-07-2024, Application No. - 5004320836 | 356 | 07/08/2024 | 0 | WBSEDCL | 7.25 | 0 | 0 | 0
1020 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Quotation for new service connnection at Kamarkundu W/S. Sch. TW-II, Z-IV | 772 | 19/02/2024 | 0 | WBSEDCL | 7.2 | 0 | 0 | 0
1021 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | PAYMENT FOR ROAD RESTORATION | BP-2024-25-184 | 06/06/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 14.63 | 0 | 0 | 0
1022 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-I | 718 | 29/01/2024 | 0 | WBSEDCL | 3.02 | 0 | 0 | 0
1023 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Quotation for new service connnection at Kamarkundu W/S. Sch. TW-II, Z-VII | 771 | 19/02/2024 | 0 | WBSEDCL | 4.87 | 0 | 0 | 0
1024 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | PAYMENT FOR ROAD RESTORATION | BP-2024-25-183 | 06/06/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 23.44 | 0 | 0 | 0
1025 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-I | 720 | 31/01/2024 | 0 | WBSEDCL | 4.85 | 0 | 0 | 0
1026 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-IV | 716 | 29/01/2024 | 0 | WBSEDCL | 4.87 | 0 | 0 | 0
1027 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | AUGMENTATION of KAMARKUNDU (ZONE-III) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of CHANDANNAGAR Sub Division, District:- Hooghly [AUGMENTATION ] | 2111/HUG | 20/07/2023 | 744 | S.K. GHOSH | 289.99 | 19.94 | 6.88 | 10
1028 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | AUGMENTATION of KAMARKUNDU (ZONE-VII) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of CHANDANNAGAR Sub Division, District:- Hooghly [AUGMENTATION ] | 2112/HUG | 20/07/2023 | 896 | S. HATI | 288.45 | 59.13 | 20.5 | 70
1029 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | AUGMENTATION of KAMARKUNDU (ZONE-I) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of CHANDANNAGAR Sub Division, District:- Hooghly [AUGMENTATION ] | 2109/HUG | 20/07/2023 | 775 | BAPPADITYA BANERJEE | 318.37 | 120.82 | 37.95 | 33
1030 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | AUGMENTATION of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of CHANDANNAGAR Sub Division, District:- Hooghly [AUGMENTATION ] | 2110/HUG | 20/07/2023 | 780 | ARUN SEAL AND CO. | 410.87 | 292.23 | 71.12 | 10
1031 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | AUGMENTATION Of KAMARKUNDU (ZONE-VI) Piped Water Supply Scheme with Sinking of tube-well, FHTC within Kamarkundu & Singur Mouza, construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | 2610/HUG | 29/08/2023 | 820 | DAS ENTERPRISE | 149.29 | 88.36 | 59.19 | 60
1032 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | AUGMENTATION of KAMARKUNDU (ZONE-V) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of CHANDANNAGAR Sub Division, District:- Hooghly [AUGMENTATION ] | 3114/HUG | 13/10/2023 | 541 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 129.13 | 13 | 10.07 | 50
1033 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Hiring of Additional Diesel Motor Car (Non AC) for inspecting of JJM Schemes on daily hire rate basis for 05 months having contract carriage permit for plying within West Bengal from Regional Transport Authority for the office of the Asst Engineer Chandannagar Sub-Division, PHE Dte.[ Period from 01.12.2023 to 30.04.2024]. | 930/Chan | 30/11/2023 | 152 | PAUL AUTOMOBILES | 0.72 | 0 | 0 | 0
1034 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kamarkundu water supply scheme at different zone, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | 50/ED | 05/01/2024 | 731 | DAS ENTERPRISE | 172.16 | 53.44 | 31.04 | 55
1035 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | 1st Continuation order for the work of Hiring of Additional Diesel Motor Car (Non AC) for inspecting of JJM Schemes on daily hire rate basis for 02 months having contract carriage permit for plying within West Bengal from Regional Transport Authority for the office of the Asst Engineer Chandannagar Sub-Division, PHE Dte. (Period from 01/05/2024 to 30/06/2024) | 476/Chan | 26/04/2024 | 61 | PAUL AUTOMOBILES | 0.29 | 0 | 0 | 0
1036 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Construction of structural shed for storing Mechanical pumps and machineries at Kamarkundu Zone-II OHR work site under Chandannagar Sub division within Hooghly Division PHE Dte. | 897/CHAN | 21/07/2025 | 15 | TOTON MONDAL | 4.88 | 0 | 0 | 0
1037 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Repairing & Renovation work of Existing additional Room at under Kamarkundu zone-3 water supply scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. | 931/CHAN | 21/07/2025 | 20 | ASHA ENTERPRISE | 4.98 | 0 | 0 | 50
1038 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR , SM/18397 | Augmentation | Hiring of One number Diesel Motor Car (Non AC) for inspecting of JJM Schemes on daily hire rate basis for 06 (Six) months having contract carriage permit for playing within West Bengal from Regional Transport Authority for the office of the Assistant Engineer Chandannagar Sub-Division, PHE Dte. (Period from 01.10.2025 to 31.03.2026). | 1447/Chan | 23/09/2025 | 181 | ZENITH INFRASTRUCTURE | 0.86 | 0 | 0 | 0
1039 | HOOGHLY | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. , SM/18624 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kapasharia water supply scheme, T.W. No. V & VI, Block: Chanditala-II District- Hooghly under Electrical Division, PHE Dte. | 3454/ED | 11/08/2023 | 90 | R.N.S. TRADING | 20.83 | 0 | 0 | 0
1040 | HOOGHLY | Hooghly Division | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. , SM/18624 | New | Material Requisition To Resource Division | 3060/4/Hug | 11/10/2023 | 0 | Resource Division | 22.95 | 0 | 0 | 0
1041 | HOOGHLY | Hooghly Division | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. , SM/18624 | New | Material Requisition To Resource Division | 3005/16/Hug | 05/10/2023 | 0 | Resource Division | 22.91 | 0 | 0 | 0
1042 | HOOGHLY | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. , SM/18624 | New | "Quotation Bill for New Service Connection at Kapasaria W/S. Sch. | 211 | 24/08/2023 | 0 | WBSEDCL | 17.21 | 0 | 0 | 0
1043 | HOOGHLY | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. , SM/18624 | New | Quotation Bill for New Service Connection at Kapasaria W/S. Sch. PH-III & IV, Z-II | 317 & 318 | 03/10/2023 | 0 | WBSEDCL | 6.88 | 0 | 0 | 0
1044 | HOOGHLY | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. , SM/18624 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kapasharia water supply scheme, T.W. No.- I, II, III & IV, Block: Chanditala-II District- Hooghly under Electrical Division, PHE Dte. | 3589/ED | 28/08/2023 | 90 | R.N.S. TRADING | 41.38 | 38.54 | 93.14 | 90
1045 | HOOGHLY | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. , SM/18624 | New | Quotation money deposition for new service connection at Kapasaria w/s scheme, Zone- I, T.W. No.-I, Dist.-Hooghly under PHE Dte. Application No- 100000120622 Reference ID- 860314252 SM Code- 18624 | 559 | 11/11/2024 | 0 | WBSEDCL | 0.19 | 0 | 0 | 0
1046 | HOOGHLY | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. , SM/18624 | New | Quotation Bill for New Service Connection at Kapasaria W/S. Sch. Z-II, TW-IV | 608 | 04/01/2024 | 0 | WBSEDCL | 4.82 | 0 | 0 | 0
1047 | HOOGHLY | Hooghly Division | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. , SM/18624 | New | KAPASHARIA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site at ZONE-I & Sinking of tube-well, LDS, Rising Main, FHT, Construction of switch-rooms & boundary walls at different TW site at ZONE-II, under CHANDITALA-II Block, District:- Hooghly [NEW SCHEME] | 2335/HUG | 07/08/2023 | 549 | SAMIRON GHOSH | 934.14 | 592.08 | 63.38 | 10
1048 | HOOGHLY | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. , SM/18624 | New | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). Car No. WB-05-0982 | 331_AE-I/ED | 05/02/2025 | 176 | SWARUP LAL SARKAR | 0.84 | 0 | 0 | 0
1049 | HOOGHLY | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. , SM/18624 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KAPASARIA water supply scheme, TW No. VII, Block: Chanditala-II, District - Hooghly under Electrical Division PHE Dte. | 482/ED | 18/03/2025 | 90 | S.P. CONSTRUCTION | 11.42 | 0 | 0 | 0
1050 | HOOGHLY | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. , SM/18624 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KAPASARIA water supply scheme, TW No. IX, Block: Chanditala-II, District - Hooghly under Electrical Division PHE Dte. | 480/ED | 18/03/2025 | 90 | SWAPAN ENTERPRISE | 11.3 | 0 | 0 | 0
1051 | HOOGHLY | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. , SM/18624 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KAPASARIA water supply scheme, TW No. VIII, Block: Chanditala-II, District - Hooghly under Electrical Division PHE Dte. | 481/ED | 18/03/2025 | 90 | ANUPAMA ENGINEERING WORKS | 11.3 | 0 | 0 | 0
1052 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Route Survey, Design Drawing & DPR Preparation of Haripal Zone - I PWSS under Chandannagar Sub-Division, P.H.E. Dte | 270/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.83 | 2.84 | 100 | 0
1053 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Route Survey, Design Drawing & DPR Preparation of HARIPAL ZONE-II PWSS under Chandannagar Sub-Division, P.H.E. Dte | 275/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.45 | 3.21 | 93.03 | 0
1054 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Balance work for special repairing of UPVC pipeline damaged due to construction of road with drain of PWD at Balarampur of Ashutosh G.P. under the command area of Haripal water supply scheme under Chandannagar Sub-Division, P.H.E. Dte | 337/CHAN | 12/07/2022 | 10 | GOUR KUMAR DAS | 3.88 | 3.05 | 100 | 0
1055 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Material Requisition To Resource Division | 2686/8/Hug | 01/12/2022 | 0 | Resource Division | 0.33 | 0 | 0 | 0
1056 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Augmentation of HARIPAL (ZONE-I) Water Supply Scheme with Construction of 500 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work & LDS within Aminpur & Chandinagar (Part) Mouza at HARIPAL Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | 1347/Hug | 29/06/2022 | 300 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 183.24 | 145.88 | 79.61 | 50
1057 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Haripal water supply scheme, T.W. No.- I, II & III, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | 840/ED | 14/02/2023 | 90 | DAS ENTERPRISE | 32.23 | 21.41 | 66.44 | 50
1058 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Construction of 400 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work for Augmentation of HARIPAL (ZONE-II) Water Supply Scheme within HARIPAL Block under chandannagar Sub-Division of Hooghly Division, PHE Dte. | 1345/HUG | 29/06/2022 | 30 | SOUMYADIP DE | 110.86 | 70.82 | 63.88 | 0
1059 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 210 Mtr at HARIPAL (ZONE-I) PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | 2510/HUG | 22/11/2022 | 45 | SPG ENTERPRISES | 27.65 | 26.53 | 100 | 0
1060 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Horizontal road crossing by trenchless method at Gopinagar More of Baidyabati- Tarakeswar Road (SH-12)and Haripal Station to Basudevpur More Road under Haripal (Zone-II) PWSS, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | 2830/HUG | 14/09/2023 | 30 | SOUMYADIP DE | 8.98 | 8.98 | 100 | 100
1061 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Material Requisition To Resource Division | 157/6/Hug | 24/01/2022 | 0 | Resource Division | 1.03 | 0 | 0 | 0
1062 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Material Requisition To Resource Division | 1125/HUG | 06/06/2022 | 0 | Resource Division | 10.98 | 0 | 0 | 0
1063 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Material Requisition To Resource Division | 423/3/Hug | 07/03/2022 | 0 | Resource Division | 25.98 | 0 | 0 | 0
1064 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Material Requisition To Resource Division | 01/02/Hug | 02/01/2023 | 0 | Resource Division | 11.94 | 0 | 0 | 0
1065 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Material Requisition To Resource Division | 1383/13/Hug | 15/05/2023 | 0 | Resource Division | 11.2 | 0 | 0 | 0
1066 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Material Requisition To Resource Division | 109/6/Hug | 10/01/2023 | 0 | Resource Division | 20.79 | 0 | 0 | 0
1067 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | REPAIRING OF ROAD FROM MAHESHPUR TO BHAUSANARA PART OF ANANTAPUR | BP-2023-24-361 | 12/09/2023 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 32.06 | 0 | 0 | 0
1068 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | "Quotation Bill for New Service Connection at of Haripal W/S. Sch. | 01 | 11/04/2023 | 0 | WBSEDCL | 5.42 | 0 | 0 | 0
1069 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Quotation for New Service Connection of Haripal W/S scheme(Aug),Zone-II,PH No-II Hooghly under Electrical Division PHE Dte | 16 | 02/05/2023 | 0 | WBSEDCL | 3.78 | 0 | 0 | 0
1070 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, CANDANNAGORE SUB-DIVISION, PHE DTE. UNDER HOOGHLY DIVISION, PHE DTE. | BP-2023-24-136 | 15/06/2023 | 0 | GOUR KUMAR DAS | 0.77 | 0 | 0 | 0
1071 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Haripal Jagajibanpur Road Restoration | BP-2023-24-399 | 26/09/2023 | 0 | EXECUTIVE ENGINEER, (PWD) HOOGHLY CONSTRUCTION DIVISION | 18.03 | 0 | 0 | 0
1072 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Augmentation of HARIPAL(ZONE-I) Water Supply Scheme with Laying Distribution System within Chak Ananta (Part) Mouza & Functional Household Tap Connection, Construction of 1 No.Switch Room (3.6 M X 3.0M )& Boundary Wall at 2ND T.W Site, Proposed T.W Site & O.H.R Site, Repairing of existing Switch Rooms at Haripal Block under Chandannagar Sub-Division, PHE Dte. | 1563/HUG | 29/07/2022 | 45 | M/S R.M. CONSTRUCTION | 142.15 | 101.96 | 71.73 | 70
1073 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of BANIDPUR PWSS under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | 1281/HUG | 04/05/2023 | 45 | AYUSH ENTERPRISE | 93.94 | 93.5 | 99.53 | 100
1074 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer Mechanical Circle-II, PHE Dte. | 1381/HMSD | 14/06/2023 | 184 | DEBASHISH GHOSH | 0.87 | 1.45 | 119.35 | 20
1075 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at Gopinagar, Aminpur and Khamarchandi Village of Haripal Zone II and it's adjoining mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte [Block- Haripal] | 820/HUG | 11/03/2024 | 30 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 6.63 | 0 | 0 | 0
1076 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Construction of 400 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work for Augmentation of HARIPAL (ZONE-II) Water Supply Scheme within HARIPAL Block under chandannagar Sub-Division of Hooghly Division, PHE Dte. | 1345/Hug | 29/06/2022 | 270 | SOUMYADIP DE | 110.86 | 35.86 | 100 | 99
1077 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Augmentation of HARIPAL(ZONE-I) Water Supply Scheme with Laying Distribution System within Krishnapur, Chak Ananta(Part), Haripal, Chandinagar(Part), Kamar Chandi Mouza & Functional Household tap Connection, Rising Main at Haripal Block under Chandannagar Sub-Division, PHE Dte. | 1599/HUG | 04/08/2022 | 45 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 193.1 | 161.04 | 100 | 100
1078 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Augmentation of HARIPAL(ZONE-II)Water Supply Scheme with LDS within Kamarchandi(Part), Gopinagar(Part) Mouza & Functional Household tap Connection, Rising Main, Construction of Boundary Wall & Switch Room at H/W Site at Haripal Block under Chandannagar Sub-Division, PHE Dte. | 426/HUG | 15/02/2023 | 45 | SOUMYADIP DE | 128.29 | 123.02 | 100 | 100
1079 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | REGARDING DAMAGE OF PMGSY -III ROAD NAMELY NANDAKUTHI TO DALAPATIPUR PACKAGE NO.WB 08 350 UNDER HARIPAL BLOCK CAUSED BY LAYING OF PHE PIPE LINE. | BP-2024-25-3 | 08/04/2024 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 21 | 0 | 0 | 0
1080 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | ROAD RESTORATION PAYMENT TO PWD FOR HARIPAL JAGJEEBANPUR ROAD | BP-2024-25-498 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, (PWD) HOOGHLY CONSTRUCTION DIVISION | 7.19 | 0 | 0 | 0
1081 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | ROAD RESTORATION PAYMENT TO PWD FOR HARIPAL JAGJEEBANPUR ROAD | BP-2024-25-498 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, (PWD) HOOGHLY CONSTRUCTION DIVISION | 18.03 | 0 | 0 | 0
1082 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | DAMAGED PIPELINE OF PMGSY ROAD FROM NANDAKUTHI TO DALALPUR UNDER HARIPAL BLOCK | BP-2023-24-676 | 22/12/2023 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 16.03 | 0 | 0 | 0
1083 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto 210 Mtr at HARIPAL (ZONE-II) PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | 2499/HUG | 22/11/2022 | 771 | B.R SUPPLIERS | 13.81 | 0 | 0 | 100
1084 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Augmentation of HARIPAL(ZONE-II)Water Supply Scheme with LDS within Kamarchandi(Part), Gopinagar(Part) & Aminpur Mouza & Functional Household tap Connection, Construction of Boundary Wall & Switch Room at Proposed 2nd T.W Site at Haripal Block under Chandannagar Sub-Division, PHE Dte. | 2472/HUG | 18/11/2022 | 806 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 157.64 | 142.45 | 90.36 | 100
1085 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Construction of structural shed for storing Mechanical pumps and machineries at Haripal Zone-I OHR work site under Chandannagar Sub division within Hooghly Division PHE Dte. | 898/CHAN | 21/07/2025 | 15 | JOY GURU ENTERPRISE | 4.88 | 0 | 0 | 0
1086 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR HARIPAL , SM/09982 | Augmentation | Providing F.H.T.C in leftout portion (Anantapur, Avirampur, Mosapur, Dignagar, Gabati mouzas) of Haripal water supply scheme under Chandannagar Sub-Division P.H.E. Dte. | 2832/HUG | 17/11/2025 | 35 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 19.67 | 0 | 0 | 0
1087 | HOOGHLY | Hooghly Division | Improvement of ¿MEGHSAR¿ Piped Water Supply Scheme by laying of HDPE Pipeline by HDD Process & Open cut method including restoration work at Mahanad Bandel Road within Meghsar PWSS under Chinsurah Sub Division. , SM/18926 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Jatarpur village under Polba Dadpur Block, Tarabehari village of Polba Dadpur Block and Goai village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | 271/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
1088 | HOOGHLY | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK , SM/18339 | Augmentation | Material Requisition To Resource Division | 79/22/Hug | 06/01/2023 | 0 | Resource Division | 38.01 | 0 | 0 | 0
1089 | HOOGHLY | Electrical | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK , SM/18339 | Augmentation | Quotation Bill for for New Service Connection at Krishnanagar W/S. Sch. PH-II, Z-II, | 425 | 17/11/2023 | 0 | WBSEDCL | 3.94 | 0 | 0 | 0
1090 | HOOGHLY | Electrical | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK , SM/18339 | Augmentation | Quotation Bill for for New Service Connection at Krishnanagar W/S. Sch. PH-I, Z-II | 426 | 17/11/2023 | 0 | WBSEDCL | 5.3 | 0 | 0 | 0
1091 | HOOGHLY | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK , SM/18339 | Augmentation | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of KRISHNANAGAR Zone-II , MAYAPUR , TIROL Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3530/HUG | 22/10/2024 | 45 | PADMA ENGINEERING CO. | 47.5 | 0 | 0 | 0
1092 | HOOGHLY | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK , SM/18339 | Augmentation | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of KRISHNANAGAR ZONE-II,MAYAPUR,TIROL ZONE-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3783/HUG | 25/11/2024 | 60 | DAS CONSTRUCTION | 55.5 | 0 | 0 | 0
1093 | HOOGHLY | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK , SM/18339 | Augmentation | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of KRISHNANAGAR Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 3665/HUG | 13/11/2024 | 90 | M/S B N ENTERPRISE | 16.12 | 0 | 0 | 0
1094 | HOOGHLY | Electrical | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK , SM/18339 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KRISHNANAGAR PIPED W/S SCHEME, T.W. No. III, Block: Khanakul-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1205/ED | 14/06/2024 | 90 | SWAPAN ENTERPRISE | 10.75 | 0 | 0 | 0
1095 | HOOGHLY | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK , SM/18339 | Augmentation | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of NATIBPUR , SAIDPUR Zone-II , KRISHNANAGAR Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3170/HUG | 10/09/2024 | 45 | BIMAL KUMAR HALDER | 48.47 | 0 | 0 | 0
1096 | HOOGHLY | Electrical | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK , SM/18339 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KRISHNANAGAR PIPED W/S SCHEME, T.W. No. V, Block: Khanakul-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1207/ED | 14/06/2024 | 90 | D.S. ENTERPRISE | 10.74 | 0 | 0 | 0
1097 | HOOGHLY | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK , SM/18339 | Augmentation | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of NATIBPUR KRISHNANAGAR Zone-I , RASULPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte | 3782/HUG | 25/11/2024 | 60 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 55.13 | 0 | 0 | 0
1098 | HOOGHLY | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK , SM/18339 | Augmentation | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of KRISHNANAGAR Z-II Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte | 3660/HUG | 13/11/2024 | 90 | SUDIPTA DAS | 16.08 | 0 | 0 | 0
1099 | HOOGHLY | Electrical | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK , SM/18339 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Krishnanagar water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | 3788/ED | 26/09/2023 | 90 | GLACIER ENGINEERING CO. | 21.75 | 21.71 | 100 | 40
1100 | HOOGHLY | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK , SM/18339 | Augmentation | Augmentation of KRISHNANAGAR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls in ZONE-II & Repairing of Existing O.H.R, Switch Rooms, Boundary walls at different TW site, LDS, FHTC in ZONE-I under KHANAKUL-I Block, District:- Hooghly | 2036/HUG | 13/07/2023 | 812 | M/S PRADYUT KUMAR HAZRA | 642.46 | 488.05 | 75.97 | 15
1101 | HOOGHLY | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK , SM/18339 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) KHANAKUL PWSS - 6 nos (2) KRISHNANAGAR PWSS - 4nos (3) PATUL PWSS - 4nos | 810/Arg | 23/08/2024 | 30 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
1102 | HOOGHLY | Hooghly Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR PASCHIM NARAYANPUR PWSS, UNDER HOOGHLY DIVISION , BLOCK : HARIPAL, DISTRICT : HOOGHLY , SM/18346 | New | Material Requisition To Resource Division | 109/ 10/Hug | 10/01/2023 | 0 | Resource Division | 73.57 | 0 | 0 | 0
1103 | HOOGHLY | Hooghly Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR PASCHIM NARAYANPUR PWSS, UNDER HOOGHLY DIVISION , BLOCK : HARIPAL, DISTRICT : HOOGHLY , SM/18346 | New | Material Requisition To Resource Division | 3058/5/Hug | 11/10/2023 | 0 | Resource Division | 16.53 | 0 | 0 | 0
1104 | HOOGHLY | Electrical | GROUND WATER BASED WATER SUPPLY SCHEME FOR PASCHIM NARAYANPUR PWSS, UNDER HOOGHLY DIVISION , BLOCK : HARIPAL, DISTRICT : HOOGHLY , SM/18346 | New | Quotation Bill for New Service Connection at Paschim Narayanpur W/S. Sch.TW-I | 587 | 28/12/2023 | 0 | WBSEDCL | 3.95 | 0 | 0 | 0
1105 | HOOGHLY | Electrical | GROUND WATER BASED WATER SUPPLY SCHEME FOR PASCHIM NARAYANPUR PWSS, UNDER HOOGHLY DIVISION , BLOCK : HARIPAL, DISTRICT : HOOGHLY , SM/18346 | New | Quotation Bill for New Service Connection at Paschim Narayanpur W/S. Sch.TW-II | 586 | 28/12/2023 | 0 | WBSEDCL | 3.91 | 0 | 0 | 0
1106 | HOOGHLY | Hooghly Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR PASCHIM NARAYANPUR PWSS, UNDER HOOGHLY DIVISION , BLOCK : HARIPAL, DISTRICT : HOOGHLY , SM/18346 | New | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Kamarkundu (Zone-4) 1st T/W site & Paschim Narayanpur 1st T/W site under Chandannagar Sub-Division PHE Dte. | 927/Chan | 05/11/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 0 | 100
1107 | HOOGHLY | Hooghly Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR PASCHIM NARAYANPUR PWSS, UNDER HOOGHLY DIVISION , BLOCK : HARIPAL, DISTRICT : HOOGHLY , SM/18346 | New | ROAD RESTORATION PAYMENT TO PWD FOR HAZRA MORE TO SUNDARPUR MORE ROAD | BP-2024-25-498 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, (PWD) HOOGHLY CONSTRUCTION DIVISION | 37.84 | 0 | 0 | 0
1108 | HOOGHLY | Hooghly Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR PASCHIM NARAYANPUR PWSS, UNDER HOOGHLY DIVISION , BLOCK : HARIPAL, DISTRICT : HOOGHLY , SM/18346 | New | PASCHIM NARAYANPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under HARIPAL Block, District:- Hooghly [NEW SCHEME] | 2387/HUG | 09/08/2023 | 812 | PRASUN ENTERPRISE (PRASUN BISWAS) | 714.76 | 110.52 | 15.46 | 10
1109 | HOOGHLY | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF JANGIPARA, TARAKESWAR, HARIPAL & SINGUR IN HOOGHLY DISTRICT , SM/11584 | New | MINI WATER SUPPLY SCHEME | C092250849619 | 28/09/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 713.77 | 0 | 0 | 0
1110 | HOOGHLY | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF JANGIPARA, TARAKESWAR, HARIPAL & SINGUR IN HOOGHLY DISTRICT , SM/11584 | New | Preparation of DPR mini PWSS | C092252696982 | 29/09/2022 | 0 | APEX ENGINEERING | 4.4 | 0 | 0 | 0
1111 | HOOGHLY | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF JANGIPARA, TARAKESWAR, HARIPAL & SINGUR IN HOOGHLY DISTRICT , SM/11584 | New | REQUISITION OF SAJAL GRAM |  | 21/09/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 718.17 | 0 | 0 | 0
1112 | HOOGHLY | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF JANGIPARA, TARAKESWAR, HARIPAL & SINGUR IN HOOGHLY DISTRICT , SM/11584 | New | REQUISITION OF FUND FOR SAJAL GRAM |  | 15/09/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 718.17 | 0 | 0 | 0
1113 | HOOGHLY | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF JANGIPARA, TARAKESWAR, HARIPAL & SINGUR IN HOOGHLY DISTRICT , SM/11584 | New | Material Requisition To Resource Division | 1384/13/Hug | 15/05/2023 | 0 | Resource Division | 10.42 | 0 | 0 | 0
1114 | HOOGHLY | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/18642 | New | ARUNDA ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANAKUL-I Block of Arambag SUb-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | 2341/HUG | 07/08/2023 | 270 | SIBSANKAR CHOWDHURY | 833.08 | 0 | 0 | 0
1115 | HOOGHLY | Electrical | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/18642 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Arunda (Zone-I) water supply scheme, T.W. No. I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | 3596/ED | 28/08/2023 | 90 | ANJAN ENTERPRISE | 21.5 | 0 | 0 | 0
1116 | HOOGHLY | Electrical | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/18642 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Arunda (Zone-I) water supply scheme, T.W. No. III & IV, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | 3435/ED | 11/08/2023 | 90 | ANJAN ENTERPRISE | 21.5 | 0 | 0 | 0
1117 | HOOGHLY | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/18642 | New | Material Requisition To Resource Division | 3057/45/Hug | 11/10/2023 | 0 | Resource Division | 12.79 | 0 | 0 | 0
1118 | HOOGHLY | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/18642 | New | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at HAYATPUR and ARUNDA Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 723/HUG | 05/03/2024 | 60 | SPG ENTERPRISES | 64.34 | 0 | 0 | 50
1119 | HOOGHLY | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/18642 | New | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch room & boundary wall for ARUNDA ZONE-I Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3775/HUG | 25/11/2024 | 45 | I R CONSTRUCTION | 25.93 | 0 | 0 | 0
1120 | HOOGHLY | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/18642 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) KHANAKUL PWSS (Z-I)- 1 no?s (2) PURBATHAKURANICHAK PWSS (Z-I)-2 no?s (3) ARUNDA PWSS (Z-I)- 4 no?s (4) ARUNDA PWSS (Z-II)- 5 no?s (5) POL PWSS ? 2no?s | 1152/Arg | 10/12/2024 | 31 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
1121 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18937 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at EKTARPUR (2Nos.), BELUN (2Nos.), CHOPA (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3235/HUG | 06/11/2023 | 60 | EVERGREEN TRADERS | 59.68 | 0 | 0 | 0
1122 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18937 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4488/ED | 23/11/2023 | 90 | H.K.DAS & CO. | 21.88 | 0 | 0 | 0
1123 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18937 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at EKTARPUR (2Nos.), BELUN (2Nos.), CHOPA (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3358/HUG | 21/11/2023 | 45 | ACME CONSTRUCTION | 87.88 | 0 | 0 | 60
1124 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18937 | Augmentation | Laying / Repairing Pipeline in damaged portion and other allied works for Chopa & Dighir Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 23/CH | 05/01/2024 | 15 | BOSE ENTERPRISE (RATUL BOSE) | 1.58 | 1.5 | 100 | 100
1125 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18937 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at CHOPA (1 No.), HARAL (2Nos.), DWARBASINI (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3236/HUG | 06/11/2023 | 726 | DAS ENTERPRISE | 59.77 | 0 | 0 | 60
1126 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18937 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in GURAP-I GP of DHANIAKHALI Block. | 248/CH | 12/03/2024 | 30 | SAKALER SATHI SWAMBHAR GOSTHI | 4.98 | 0 | 0 | 65
1127 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18937 | Augmentation | Laying of HDPE pipeline and distribution at the left out portions of Chopa PWSS under Dhaniakhali Block of Chinsurah Sub-Division, PHE Dte. | 2345/HUG | 19/06/2024 | 300 | BOSE ENTERPRISE (RATUL BOSE) | 53.11 | 17.58 | 33.09 | 50
1128 | HOOGHLY | Hooghly Division | Source Augmentation Of Paunan Water Supply Scheme Under Polba Dadpur Block , SM/18951 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at PAUNAN (2Nos.), PUINAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3244/HUG | 06/11/2023 | 60 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 59.57 | 0 | 0 | 45
1129 | HOOGHLY | Hooghly Division | Source Augmentation Of Paunan Water Supply Scheme Under Polba Dadpur Block , SM/18951 | Augmentation | Sinking of 1no 300 X200 mm dia Tube Well 210 mtr. Depth by tube-well by D.R. Rig method for using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) to replace the exsisting T.W at head work site of Paonan Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.HE Dte. | 2344/HUG | 19/06/2024 | 30 | BANSBERIA CONSTRUCTION CO. | 16.03 | 0 | 0 | 0
1130 | HOOGHLY | Hooghly Division | Source Augmentation Of Paunan Water Supply Scheme Under Polba Dadpur Block , SM/18951 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed for Sajal Gram Display Board at different locations in 6 (six) Nos villages & HGJ villages of Paunan PWSS for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. | 144/CH | 20/02/2024 | 7 | R.K. TRADERS | 0.95 | 0.95 | 100 | 50
1131 | HOOGHLY | Electrical | Source Augmentation Of Paunan Water Supply Scheme Under Polba Dadpur Block , SM/18951 | Augmentation | Quotation for new service connection at Pownan W/S Sch. , (S. Aug.),[SM/18951] T/W No. - IV, Bihari Pally, Block - Polba-Dadpur, Dist. Hooghly, under SM/Polba, WBSEDCL, Ref. Id. - 503594866, Dt. - 02-04-2024, Application No. - 5004069653 | 39 | 09/04/2024 | 0 | WBSEDCL | 4.2 | 0 | 0 | 0
1132 | HOOGHLY | Hooghly Division | Source Augmentation Of Paunan Water Supply Scheme Under Polba Dadpur Block , SM/18951 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PAUNAN (2Nos.), PUINAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3405/HUG | 23/11/2023 | 571 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 13.51 | 39.1 | 25
1133 | HOOGHLY | Electrical | Source Augmentation Of Paunan Water Supply Scheme Under Polba Dadpur Block , SM/18951 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of Paunan Water Supply Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4515/ED | 23/11/2023 | 688 | S.S. ENTERPRISES | 21.91 | 2.91 | 13.26 | 50
1134 | HOOGHLY | Hooghly Division | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. , SM/18666 | New | Material Requisition To Resource Division | 79/9Hug | 06/01/2023 | 0 | Resource Division | 79.13 | 0 | 0 | 0
1135 | HOOGHLY | Hooghly Division | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. , SM/18666 | New | Material Requisition To Resource Division | 3060/3/Hug | 11/10/2023 | 0 | Resource Division | 22.95 | 0 | 0 | 0
1136 | HOOGHLY | Hooghly Division | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. , SM/18666 | New | Material Requisition To Resource Division | 3005/3/Hug | 05/10/2023 | 0 | Resource Division | 85.62 | 0 | 0 | 0
1137 | HOOGHLY | Electrical | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. , SM/18666 | New | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-I, Z-I | 505 | 08/12/2023 | 0 | WBSEDCL | 3.8 | 0 | 0 | 0
1138 | HOOGHLY | Electrical | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. , SM/18666 | New | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-I, Z-II | 503 | 08/12/2023 | 0 | WBSEDCL | 3.63 | 0 | 0 | 0
1139 | HOOGHLY | Electrical | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. , SM/18666 | New | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-II, Z-I | 504 | 08/12/2023 | 0 | WBSEDCL | 3.55 | 0 | 0 | 0
1140 | HOOGHLY | Electrical | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. , SM/18666 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kumirmora water supply scheme, Zone-I, T.W. No.- I & II, Block: Chanditala-I & II, District- Hooghly under Electrical Division, PHE Dte. | 3414/ED | 10/08/2023 | 90 | S.P. CONSTRUCTION | 22.37 | 21.63 | 96.71 | 70
1141 | HOOGHLY | Electrical | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. , SM/18666 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kumirmora water supply scheme, Zone-II, T.W. No.- I & II, Block: Chanditala-I & II, District- Hooghly under Electrical Division, PHE Dte. | 3413/ED | 10/08/2023 | 90 | MENAKA ENTERPRISE | 20.36 | 14.41 | 70.79 | 30
1142 | HOOGHLY | Electrical | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. , SM/18666 | New | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-II, Z-II | 502 | 08/12/2023 | 0 | WBSEDCL | 6.86 | 0 | 0 | 0
1143 | HOOGHLY | Hooghly Division | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. , SM/18666 | New | KUMIRMORA (ZONE-I & ZONE-II), PAIRAGACHA (ZONE-I & ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at CHANDITALA-I & CHANDITALA-II Block under SERAMPORE Sub-Division of Hooghly Division PHE Dte. [NEW SCHEME] | 2333/Hug | 07/08/2023 | 815 | S & P ENTERPRISE | 964.69 | 495.38 | 51.35 | 14
1144 | HOOGHLY | Hooghly Division | Source Augmentation of HARISH CHAK piped Water Supply Scheme Under Khanakul-II Block , SM/18957 | Augmentation | Construction of 5 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at BHANDARHATI (1NO.), PURBA THAKURANI CHAK (2NOS.), HARISH CHAK (2NOS.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3268/HUG | 08/11/2023 | 60 | KRISHNA MONDAL | 58.98 | 0 | 0 | 0
1145 | HOOGHLY | Electrical | Source Augmentation of HARISH CHAK piped Water Supply Scheme Under Khanakul-II Block , SM/18957 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of HARISH CHAK piped Water Supply Scheme Block- Khanakul-II District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4521/ED | 23/11/2023 | 90 | T S CONSTRUCTION | 21.47 | 0 | 0 | 0
1146 | HOOGHLY | Hooghly Division | Source Augmentation of HARISH CHAK piped Water Supply Scheme Under Khanakul-II Block , SM/18957 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BHANDARHATI (1NO.),PURBA THAKURANI CHAK( 2NOS.), HARISH CHAK( 2NOS.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3474/HUG | 29/11/2023 | 45 | CIVIL CRAFT | 88.67 | 0 | 0 | 0
1147 | HOOGHLY | Electrical | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca , SM/18966 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme Block- Chanditala-II District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4526/ED | 23/11/2023 | 90 | DEBJYOTI BASU | 10.75 | 10.46 | 97.38 | 90
1148 | HOOGHLY | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca , SM/18966 | Augmentation | Laying Distribution of left out portion of pipeline to restore the water supply at Chikrand Jalapara & Bankagacha (part) and other allied works at Chikrand (Zone-I) Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte | 746/HUG | 05/03/2024 | 20 | AMBIAN INFRASTRUCTURE | 23.36 | 9.41 | 40.27 | 50
1149 | HOOGHLY | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca , SM/18966 | Augmentation | Laying Distribution of left out portion and Land Development at Chikrand Jalapara at Chikrand (Zone-I) Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 745/HUG | 05/03/2024 | 300 | SADHUKHAN ENTERPRISE | 59.95 | 8.96 | 14.95 | 80
1150 | HOOGHLY | Electrical | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca , SM/18966 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHIKRAND MINI PIPED W/S SCHEME, Block: Chanditala-II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1479/ED | 25/07/2024 | 90 | SHIVAM ENTERPRISE | 7.58 | 0 | 0 | 0
1151 | HOOGHLY | Electrical | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca , SM/18966 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHIKRAND PIPED W/S SCHEME, Zone - I, T.W. No. IV, Block: Chanditala - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1200/ED | 14/06/2024 | 90 | NITESH MANAGEMENT | 10.72 | 0 | 0 | 0
1152 | HOOGHLY | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca , SM/18966 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at MAINAN(1No.),CHIKRAND ZONE-I (1No.),CHIKRAND ZONE-II (1No.) ,CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3388/HUG | 22/11/2023 | 45 | SPG ENTERPRISES | 87.88 | 14.26 | 100 | 100
1153 | HOOGHLY | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca , SM/18966 | Augmentation | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at CHIKRAND ZONE-I (1No.), CHIKRAND ZONE-II (1No.), CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3313/HUG | 10/11/2023 | 421 | S.D ENTERPRISE (SAMIR KR. DAS) | 47.18 | 11.75 | 100 | 40
1154 | HOOGHLY | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca , SM/18966 | Augmentation | Laying Distribution of left out portion of pipeline at Chikrand Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 822/HUG | 11/03/2024 | 30 | S D ENTERPRISE | 24.19 | 22.77 | 100 | 80
1155 | HOOGHLY | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca , SM/18966 | Augmentation | Designing making and erection of Display Board using logo and tag line of JalJeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Piarapur (P) village under Piarapur PWSS (2 nos.) 2. Baksa village under Baksa PWSS (2 nos.) 3. Naiti village under Chikrand PWSS (2 nos.) | 169/SER | 11/03/2024 | 7 | JOY GURU ENTERPRISE | 0.95 | 0.95 | 50 | 80
1156 | HOOGHLY | Electrical | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca , SM/18966 | Augmentation | Quotation money deposition for new service connection at Chikrand w/s scheme, Dist.-Hooghly under PHE Dte. Application No- 5004377254 Reference ID- 503729858 SM Code- 18966 | BP-24-25-584 | 19/11/2024 | 0 | WBSEDCL | 5.2 | 0 | 0 | 0
1157 | HOOGHLY | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca , SM/18966 | Augmentation | Sinking of Tubewell,Construction of Switch Room,Boundary wall,and rising main with interconnection at Danbatipur ,Chikrand W/s Scheme(Zone-1)Danbatipur , Naity; Chanditala-II Block underSerampore Sub-Division of Hooghly Division PHE Dte.. | 4042/HUG | 19/12/2024 | 183 | M/S T.K.B. CONSTRUCTION | 47.79 | 0 | 0 | 25
1158 | HOOGHLY | Hooghly Division | PAIRAGACHA PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II DISTRICT: HOOGHLY. , SM/18778 | New | Material Requisition To Resource Division | 3060/1/Hug | 11/10/2023 | 0 | Resource Division | 19.2 | 0 | 0 | 0
1159 | HOOGHLY | Electrical | PAIRAGACHA PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II DISTRICT: HOOGHLY. , SM/18778 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Pairagacha water supply scheme, Zone-I, T.W. No.- I & II, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | 3614/ED | 29/08/2023 | 90 | M/S P.P. ELECTRICALS | 20.34 | 16.06 | 78.94 | 40
1160 | HOOGHLY | Electrical | PAIRAGACHA PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II DISTRICT: HOOGHLY. , SM/18778 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Pairagacha water supply scheme, Zone-II, T.W. No.- I & II, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | 3615/ED | 29/08/2023 | 90 | INDRANI ENTERPRISE | 20.27 | 0 | 0 | 40
1161 | HOOGHLY | Electrical | PAIRAGACHA PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II DISTRICT: HOOGHLY. , SM/18778 | New | Quotation money deposition for new service connection at Pairagacha w/s scheme, Zone-II, T.W. No.-I, Dist.-Hooghly under PHE Dte. Application No- 5004303896 Reference ID- 503696996 SM Code- 18778 | 348 | 31/07/2024 | 0 | WBSEDCL | 3.68 | 0 | 0 | 0
1162 | HOOGHLY | Electrical | PAIRAGACHA PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II DISTRICT: HOOGHLY. , SM/18778 | New | Quotation money deposition for new service connection at Pairagacha w/s scheme, Zone-II, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004303977 Reference ID- 503697862 SM Code- 18778 | 346 | 31/07/2024 | 0 | WBSEDCL | 3.53 | 0 | 0 | 0
1163 | HOOGHLY | Electrical | PAIRAGACHA PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II DISTRICT: HOOGHLY. , SM/18778 | New | Quotation money deposition for new service connection at Pairagacha w/s scheme, Zone- I, T.W. NO- I, Dist.-Hooghly under PHE Dte. Application No- 5004091751 Reference ID- 503606734 SM Code- 18778 | 69 | 16/04/2024 | 0 | WBSEDCL | 4.86 | 0 | 0 | 0
1164 | HOOGHLY | Hooghly Division | PAIRAGACHA PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II DISTRICT: HOOGHLY. , SM/18778 | New | KUMIRMORA (ZONE-I & ZONE-II), PAIRAGACHA (ZONE-I & ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at CHANDITALA-I & CHANDITALA-II Block under SERAMPORE Sub-Division of Hooghly Division PHE Dte. [NEW SCHEME] | 2601/HUG | 29/08/2023 | 812 | S & P ENTERPRISE | 917.75 | 91.79 | 10 | 40
1165 | HOOGHLY | Hooghly Division | Naraharbati Mini Piped water Supply Scheme , SM/13662 | New | Material Requisition To Resource Division | 1385/28/Hug | 15/05/2023 | 0 | Resource Division | 0.37 | 0 | 0 | 0
1166 | HOOGHLY | Hooghly Division | Naraharbati Mini Piped water Supply Scheme , SM/13662 | New | REQUISITION OF FUND FOR SAJAL GRAM SCHEME |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 27.19 | 0 | 0 | 0
1167 | HOOGHLY | Hooghly Division | Naraharbati Mini Piped water Supply Scheme , SM/13662 | New | MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-341 | 31/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 28.96 | 0 | 0 | 0
1168 | HOOGHLY | Hooghly Division | Naraharbati Mini Piped water Supply Scheme , SM/13662 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME |  | 23/06/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.21 | 0 | 0 | 0
1169 | HOOGHLY | Electrical | Naraharbati Mini Piped water Supply Scheme , SM/13662 | New | Mini Piped water Supply Scheme | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
1170 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18944 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at JAMGRAM (2Nos.), PANDUA (2Nos.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3242/HUG | 06/11/2023 | 60 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 59.67 | 0 | 0 | 0
1171 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18944 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4508/ED | 23/11/2023 | 90 | GLACIER ENGINEERING CO. | 21.74 | 16.12 | 74.15 | 35
1172 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18944 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Sarbanandapur village under Dhaniakhali Block, Uttar Mogalpur village of Dhnaiakhali Block and Chandpur village of Dhaniakhali Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | 260/CH | 14/03/2024 | 7 | R.K. TRADERS | 0.95 | 0.95 | 100 | 100
1173 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18944 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Kedranagar village under Dhaniakhali Block, Acharpara village of Pandua Block and Balarampur village of PAndua Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | 261/CH | 14/03/2024 | 7 | R.K. TRADERS | 0.95 | 0.95 | 100 | 100
1174 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18944 | Augmentation | Electric quot. of WBSEDCL for New service Connection of Bahadurpur T/W-III W/S scheme under Electrical Division PHE Dte. (SM/18944) | 477 | 01/10/2024 | 0 | WBSEDCL | 5.51 | 0 | 0 | 0
1175 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18944 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at JAMGRAM (2Nos.), PANDUA (2Nos.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3384/HUG | 22/11/2023 | 710 | MS D.PALIT AND CO. | 87.87 | 0 | 0 | 80
1176 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18944 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at AYMA NABABPUR (2Nos.), DUMURDAHA (1No.), AKNA (1 No.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3356/HUG | 21/11/2023 | 715 | AYUSH ENTERPRISE | 58.97 | 0 | 0 | 80
1177 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18944 | Augmentation | REPAIRING & RENOVATION OF RCC OVERHEAD RESERVOIR AT HEAD WORKS SITE OF BAHADURPUR WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURAH SUB-DIVISION UNDER HOOGHLY DIVISION, PHE DTE. | 234/CH | 19/02/2025 | 10 | B.S. ENTERPRISE | 4.85 | 0 | 0 | 0
1178 | HOOGHLY | Electrical | Source Augmentation of RAJHATO Piped Water Supply Scheme under Khanakul-II Block , SM/18947 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of RAJHATO Piped Water Supply Scheme Block- Khanakul-II District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4511/ED | 23/11/2023 | 90 | PURUSHOTTAM ENTERPRISE | 21.47 | 20.86 | 100 | 30
1179 | HOOGHLY | Electrical | Source Augmentation of RAJHATO Piped Water Supply Scheme under Khanakul-II Block , SM/18947 | Augmentation | Quotation of New Service Connection for Rajhato w/s Scheme, PH No-II,Block-Khanakul-II, Dist-Hooghly under Electrical Division,PHE Dte.(SM/18947) Application No-5003994235 Reference Id-503551060. | 201 | 10/06/2024 | 0 | WBSEDCL | 10.3 | 0 | 0 | 0
1180 | HOOGHLY | Electrical | Source Augmentation of RAJHATO Piped Water Supply Scheme under Khanakul-II Block , SM/18947 | Augmentation | Quotation of New Service Connection for Rajhato w/s Scheme, PH No-I,Block-Khanakul-II, Dist-Hooghly under Electrical Division,PHE Dte.(SM/18947) Application No-5003994230 Reference Id-503551061. | 200 | 10/06/2024 | 0 | WBSEDCL | 10.68 | 0 | 0 | 0
1181 | HOOGHLY | Hooghly Division | Source Augmentation of RAJHATO Piped Water Supply Scheme under Khanakul-II Block , SM/18947 | Augmentation | Sinking of 3 nos 300 X200 mm dia Tube Well ,210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of PURBO THAKURANICHAWK , RAJHATO , KAKNAN W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3167/HUG | 10/09/2024 | 250 | MONDAL PRECISION PRIVATE LIMITED | 48.47 | 0 | 0 | 66
1182 | HOOGHLY | Hooghly Division | Source Augmentation of RAJHATO Piped Water Supply Scheme under Khanakul-II Block , SM/18947 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PABA PWSS-3nos (2) DIHIBAYRA PWSS- 3nos (3) HAYATPUR PWSS- 4nos (4) RAJHATO PWSS- 4nos | 811/Arg | 23/08/2024 | 30 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
1183 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NALDANGA WATER SUPPLY SCHEME. , SM/07437 | Retrofitting | OHR |  | 06/10/2021 | 0 | S.K. GHOSH | 23.55 | 0 | 0 | 0
1184 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NALDANGA WATER SUPPLY SCHEME. , SM/07437 | Retrofitting | FHTC |  | 21/09/2021 | 0 | M/S KAMALA ENTERPRISE | 7.63 | 0 | 0 | 0
1185 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NALDANGA WATER SUPPLY SCHEME. , SM/07437 | Retrofitting | FHTC |  | 17/08/2021 | 0 | SATYA NARAYAN BISWAS | 25.49 | 0 | 0 | 0
1186 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NALDANGA WATER SUPPLY SCHEME. , SM/07437 | Retrofitting | FHTC |  | 25/09/2021 | 0 | PRADIP KUMAR ADHYA | 11.12 | 0 | 0 | 0
1187 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NALDANGA WATER SUPPLY SCHEME. , SM/07437 | Retrofitting | Providing 1062nos F.H.T.C. in Akna & Kannagar Village of Naldanga and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah Mogra] | 397/HUG | 15/02/2021 | 30 | SATYA NARAYAN BISWAS | 17.96 | 17.96 | 100 | 0
1188 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NALDANGA WATER SUPPLY SCHEME. , SM/07437 | Retrofitting | FHTC |  | 28/01/2022 | 0 | S.K. GHOSH | 32 | 0 | 0 | 0
1189 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NALDANGA WATER SUPPLY SCHEME. , SM/07437 | Retrofitting | Providing 475 nos F.H.T.C. in KazidangaVillage of Naldanga and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah Mogra] | 396/Hug | 15/02/2021 | 30 | PRADIP KUMAR ADHYA | 24.82 | 23.36 | 94.12 | 0
1190 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NALDANGA WATER SUPPLY SCHEME. , SM/07437 | Retrofitting | Providing 2776 nos F.H.T.C. in Naldanga Village of Naldanga and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah Mogra] | 455/Hug | 24/02/2021 | 20 | S.K. GHOSH | 144.81 | 45.66 | 31.53 | 0
1191 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NALDANGA WATER SUPPLY SCHEME. , SM/07437 | Retrofitting | Providing 200 nos F.H.T.C. in Benabhauri Village of Naldanga and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah Mogra] | 395/Hug | 15/02/2021 | 20 | M/S KAMALA ENTERPRISE | 10.45 | 10.22 | 100 | 0
1192 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NALDANGA WATER SUPPLY SCHEME. , SM/07437 | Retrofitting | Providing 1062nos F.H.T.C. in Akna & Kannagar Village of Naldanga and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah Mogra] | 397/Hug | 15/02/2021 | 30 | SATYA NARAYAN BISWAS | 54.14 | 50.97 | 188.28 | 0
1193 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NALDANGA WATER SUPPLY SCHEME. , SM/07437 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of NALDANGA PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 1135/HUG | 19/04/2023 | 30 | S.D ENTERPRISE (SAMIR KR. DAS) | 14.93 | 11.31 | 100 | 100
1194 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NALDANGA WATER SUPPLY SCHEME. , SM/07437 | Retrofitting | Material Requisition To Resource Division | 428/2-5/Hug | 07/03/2022 | 0 | Resource Division | 10.98 | 0 | 0 | 0
1195 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Mandaran Dilakash, Khurigachhi, Kulakash, Kandar Panagar Mouza of Borhol Zone-II Water Supply Scheme , SM/06988 | Retrofitting | Providing 2200 nos F.H.T.C. in Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur, Budul Badul Hati, Bhandarhati, Ilampur, Gabtala, Dakshin Dilakash, Mandaran Dilakash, Khurigachhi, Kulakash, Kandar Panagar village of Borhal (Zone- II)and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | 1686/Hug. | 17/12/2020 | 40 | S & P ENTERPRISE | 103.59 | 0 | 0 | 98
1196 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme , SM/07462 | Retrofitting | Providing 50 nos. Functional Household Tap Connection (FHTC) to the Educational Institutions within the command area of various Water Supply Schemes (Retrofitting Schemes- Baksa, Chikrand, Panchghora & Augmentation Schemes- Chanditala, Janai, Begampur, Kharsarai, Purba Tajpur) under Serampore Sub-Division of Hooghly Division P.H.E. Dte. [Chanditala-II] | 219/SER | 20/12/2021 | 25 | M/S SHIVAM UDYOG | 2.08 | 2.08 | 100 | 0
1197 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme , SM/07462 | Retrofitting | Providing 500 nos Functional Household Tap Connection (FHTC) at Jaykrishnapur & Panchghora Mouza of Panchghara W/S Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte . | 718/Hug | 07/04/2022 | 35 | MANISHIKA CONSTRUCTION | 21.8 | 14.38 | 65.95 | 0
1198 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme , SM/07462 | Retrofitting | Providing 100 nos Functional Household Tap Connection (FHTC) within the command area of Panchghora Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte | 2308/Hug | 24/12/2021 | 20 | M/S S.G. CONSTRUCTION | 7.01 | 6.9 | 98.53 | 0
1199 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme , SM/07462 | Retrofitting | Survey of FHTC Work under Rajyadharpur, Rishra, Nabagram GP KMDA Water Supply areas and Jangalpara, Krishnarampur, Chanditala, Panchghora, Begampur & Mollarber Water Supply areas under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 294/SER | 21/02/2022 | 45 | BAKSHI ENTERPRISE | 2.99 | 0 | 0 | 0
1200 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme , SM/07462 | Retrofitting | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at PANCHGHORA PWSS of SERAMPORE Sub-Division under Hooghly Division, PHE Dte. | 879/HUG | 27/03/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.32 | 11.32 | 100 | 0
1201 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme , SM/07462 | Retrofitting | Repairing of Damaged Road due to FHTC Works at different mouzas (Joykrishnapur) of Panchghora W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | 638/SER | 05/11/2024 | 7 | MS CHANDIMATA CONSTRUCTION | 4.82 | 0 | 0 | 0
1202 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme , SM/07462 | Retrofitting | Sinking of Additional 300 X 200 mm dia Tubewell 180 mtr depth, Construction of Switch Room, Boundary wall and rising main with interconnection at Panchghora W/S Scheme, Chanditala-II Block under Hooghly Division P.H.E. Dte. | 378/HUG | 08/02/2024 | 90 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 35.41 | 29.9 | 100 | 80
1203 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme , SM/07462 | Retrofitting | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Panchghora PWSS 2. Chanditala PWSS 3. Madhabpur PWSS 4. Jagannathbati PWSS 5. Purbatajpur PWSS 6. Jangipara PWSS | 112/SER | 23/02/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 80
1204 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme , SM/07462 | Retrofitting | Laying Rising Main and Protection work at Panchghora Jolapara of Panchghora W/s Scheme Chanditala-II Block under Hooghly Division PHE Dte. | 327/HUG | 05/02/2025 | 352 | BIMAL KUMAR HALDER | 31.5 | 0 | 0 | 35
1205 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PANCHGHORA Water Supply Scheme , SM/07462 | Retrofitting | Laying of C.I/D.I pipes & specials for connection of T.W No.-III with distribution system at 3rd TW Site and Laying HDPE pipe for extension of LDS with FHTC & Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply & Sanitation arrangement of Panchghara W/S Scheme under Serampore Sub - Division P.H.E. Dte. | 998/HUG | 05/04/2023 | 727 | MS CHANDIMATA CONSTRUCTION | 77.55 | 41.06 | 61.72 | 50
1206 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. , SM/07945 | Retrofitting | FHTC |  | 23/07/2021 | 0 | DAS TRADING | 11.53 | 0 | 0 | 0
1207 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. , SM/07945 | Retrofitting | FHTC |  | 15/03/2021 | 0 | JAL PRAVAHIKA PVT. LTD | 32.35 | 0 | 0 | 0
1208 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. , SM/07945 | Retrofitting | FHTC |  | 15/02/2021 | 0 | M/S T.K.B. CONSTRUCTION | 4.8 | 0 | 0 | 0
1209 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. , SM/07945 | Retrofitting | FHTC |  | 21/09/2021 | 0 | DAS TRADING | 6.6 | 0 | 0 | 0
1210 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. , SM/07945 | Retrofitting | Providing 50 nos Functional Household Tap Connection (FHTC) within Dihibayra & Maheshpur Village of Dihibayra Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh] | 714/Hug | 07/04/2022 | 20 | SAKSHI ENTERPRISE | 4.79 | 4.79 | 99.99 | 100
1211 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. , SM/07945 | Retrofitting | Construction of boundary wall, Internal Pathway and allied works at 3rd TW Site of DIHI BAYARA Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte. | 439/Arg | 22/06/2022 | 30 | M/S TANISA ENTERPRISE | 4.43 | 0 | 0 | 100
1212 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. , SM/07945 | Retrofitting | Material Requisition To Resource Division | 1124/6/HUG | 06/06/2022 | 0 | Resource Division | 10.98 | 0 | 0 | 0
1213 | HOOGHLY | Central Drilling | Retrofitting Works for Digsui-Heora (Zone-I) PWSS for providing 502 nos Functional Household Tap Connection(FHTC) , SM/06760 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR DIGSUI HEORA W/S SCHEME (Z-I), CHINSURAH MOGRA BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 296/CDD | 27/04/2022 | 30 | C.M. ENTERPRISE | 11.21 | 3.99 | 100 | 100
1214 | HOOGHLY | Central Drilling | Retrofitting Works for Digsui-Heora (Zone-I) PWSS for providing 502 nos Functional Household Tap Connection(FHTC) , SM/06760 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR DIGSUI HEORA W/S SCHEME (Z-II) CHINSURAH MOGRA BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 299/CDD | 27/04/2022 | 30 | C.M. ENTERPRISE | 11.21 | 9.78 | 100 | 100
1215 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEPARA WATER SUPPLY SCHEME. , SM/07542 | Retrofitting | FHTC |  | 15/03/2021 | 0 | BANSBERIA CONSTRUCTION CO. | 30 | 0 | 0 | 0
1216 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEPARA WATER SUPPLY SCHEME. , SM/07542 | Retrofitting | FHTC |  | 12/04/2021 | 0 | BANSBERIA CONSTRUCTION CO. | 5.98 | 0 | 0 | 0
1217 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEPARA WATER SUPPLY SCHEME. , SM/07542 | Retrofitting | Providing 1414 nos F.H.T.C. in Depara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | 384/Hug | 15/02/2021 | 40 | BANBERIA CONSTRUCTION CO. | 73.86 | 105.42 | 151.81 | 100
1218 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEPARA WATER SUPPLY SCHEME. , SM/07542 | Retrofitting | Providing 675 nos Functional Household Tap Connection (FHTC) within the command area of Chikrand Zone-II Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte | 2205/Hug | 14/12/2021 | 40 | ROY ENTERPRISE | 43.29 | 0 | 0 | 100
1219 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. , SM/08739 | Retrofitting | FHTC |  | 30/09/2021 | 0 | KARALI MOHAN KHAMRUI | 42.88 | 0 | 0 | 0
1220 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. , SM/08739 | Retrofitting | Providing 1102 nos F.H.T.C. in Daulat chak, Khune chak & Chanpanagari Village of Palaspai and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II] | 943/Hug | 06/05/2021 | 40 | DILIP KUMAR GHOSH | 63.84 | 23.44 | 73.42 | 100
1221 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. , SM/08739 | Retrofitting | Providing 1670 nos F.H.T.C. in Narendapur & Palaspai Village of Palapai and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II] | 1149/Hug | 29/06/2021 | 40 | KARALI MOHAN KHAMRUI | 81.69 | 78.4 | 100 | 100
1222 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. , SM/08739 | Retrofitting | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room & Construction of Internal Pathway of PALASPAI PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 4079/HUG | 19/12/2024 | 90 | TAPAS ADHYA | 26.94 | 0 | 0 | 0
1223 | HOOGHLY | Hooghly Division | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09516 | Augmentation | Construction of 3.6 m X 3.00 m Switch Room without Sanitary and Water Supply arrangement at 3rd T/W Site for Rajhat (Z-I) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | 620/CH | 20/12/2021 | 40 | BOSE ENTERPRISE (RATUL BOSE) | 2.44 | 2.4 | 98.58 | 100
1224 | HOOGHLY | Electrical | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09516 | Augmentation | Electric Supply | 12 | 08/06/2022 | 0 | WBSEDCL | 7.29 | 0 | 0 | 0
1225 | HOOGHLY | Hooghly Division | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09516 | Augmentation | Laying of C.I/D.I pipes & specials for connection of T.W No. -III with distribution system & Protection work at 3rd TW Site of Rajhat (Z-I) W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | 619/CH | 20/12/2021 | 25 | BOSE ENTERPRISE (RATUL BOSE) | 4.16 | 0.86 | 100 | 100
1226 | HOOGHLY | Electrical | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09516 | Augmentation | Supply, Delivery & Installation of S/P/M & other allied works for Rajhat W/S. Sch. Z-I, TW-III Dist-Hooghly | 1035/ED | 28/06/2022 | 90 | C.M. ENTERPRISE | 9.45 | 9.4 | 100 | 100
1227 | HOOGHLY | Electrical | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09516 | Augmentation | Supply & installation of Automatic Chlorinator at Rajhat water supply scheme, Zone-I, P.H. No.- II, District - Hooghly under Electrical Division, PHE Dte. | 1770/HMSD | 28/09/2022 | 7 | GANGULY ENGINEERING CO. | 0.8 | 0.8 | 100 | 100
1228 | HOOGHLY | Electrical | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09516 | Augmentation | Supply & installation of LED board and outside display board for depicting details of Pump/Valve operators at Zone-I & II, P.H. No.-III of Rajhat w/s scheme, Dist.- Hooghly under Electrical Division, PHE Dte. | 2349/HMSD | 20/12/2022 | 10 | INDTECH ASSOCIATES. | 0.84 | 0.84 | 100 | 0
1229 | HOOGHLY | Electrical | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09516 | Augmentation | Supply & installation of LED board at Zone-I, P.H. No.-I & II of Rajhat water supply scheme, Dist.- Hooghly under Electrical Division, PHE Dte. | 2347/HMSD | 20/12/2022 | 10 | DAS ENTERPRISE | 0.79 | 0.79 | 100 | 0
1230 | HOOGHLY | Hooghly Division | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09516 | Augmentation | Material Requisition To Resource Division | 3004/9/Hug | 05/10/2023 | 0 | Resource Division | 2.86 | 0 | 0 | 0
1231 | HOOGHLY | Electrical | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09516 | Augmentation | Hire Charges Bill | 138 | 20/01/2023 | 0 | DILIP KUMAR GHOSH | 0.15 | 0 | 0 | 0
1232 | HOOGHLY | Electrical | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09516 | Augmentation | Fuel Charges Bill | 137 | 20/01/2023 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
1233 | HOOGHLY | Electrical | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09516 | Augmentation | Hiring Charges Bill | 146 | 31/01/2023 | 0 | SUNIL RAJAK | 0.26 | 0 | 0 | 0
1234 | HOOGHLY | Electrical | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09516 | Augmentation | Fuel Charges Bil | 147 | 31/01/2023 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.14 | 0 | 0 | 0
1235 | HOOGHLY | Hooghly Division | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09516 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, RWS HOOGHLY SUB-DIVISION, PHE DTE. | BP-2022-23-566 | 02/03/2023 | 0 | AATISH KUMAR SHAW | 0.77 | 0 | 0 | 0
1236 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Preparation of DPR for Augmentation of Janai (Zone-I) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | 302/SER | 21/02/2022 | 20 | SRIJAN ECHOLOGICAL UPLIFTMENT PVT. LTD. | 2.59 | 2.59 | 100 | 100
1237 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Preparation of DPR for Augmentation of Janai (Zone-II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | 303/SER | 21/02/2022 | 20 | SRIJAN ECHOLOGICAL UPLIFTMENT PVT. LTD. | 1.77 | 1.62 | 91.57 | 100
1238 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at JANAI ZONE-II PWSS of SERAMPORE Sub-Division under Hooghly Division, PHE Dte. | 2502/HUG | 22/11/2022 | 30 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 10.95 | 10.2 | 100 | 0
1239 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Janai water supply scheme, T.W. No.- I, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | 648/ED | 02/02/2023 | 90 | M/S BABUSONA ENTERPRISE | 10.74 | 10.47 | 97.41 | 100
1240 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Augmentation of Janai Zone-I Water Supply Scheme with Construction of 450 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work including Laying Distribution System, Rising Main, FHTC, of existing Switch Room, Boundary Wall & at Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | 868//hug | 27/04/2022 | 300 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 378.23 | 343.15 | 100 | 100
1241 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Material Requisition To Resource Division | 422/2/Hug | 07/03/2022 | 0 | Resource Division | 39.63 | 0 | 0 | 0
1242 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Material Requisition To Resource Division | 1122/4/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
1243 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Material Requisition To Resource Division | 1689/3/HUG | 22/08/2022 | 0 | Resource Division | 19.89 | 0 | 0 | 0
1244 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Material Requisition To Resource Division | 1369/Hug | 06/07/2022 | 0 | Resource Division | 15.6 | 0 | 0 | 0
1245 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Material Requisition To Resource Division | 2210/2/Hug | 30/09/2022 | 0 | Resource Division | 0.05 | 0 | 0 | 0
1246 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Material Requisition To Resource Division | 1291/3/Hug | 24/06/2022 | 0 | Resource Division | 6.16 | 0 | 0 | 0
1247 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Material Requisition To Resource Division | 1384/18/Hug | 15/05/2023 | 0 | Resource Division | 9.36 | 0 | 0 | 0
1248 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Quatation Bill for New Service Connection of WBSEDCL at Janai W/S. Sch. | 131 | 16/01/2023 | 0 | WBSEDCL | 0.68 | 0 | 0 | 0
1249 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Construction of switch-room & boundary wall, Rising Main for inter connection between T.W & Distribution, for AUGMENTATION of JANAI Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 3475/HUG | 04/10/2024 | 60 | SUNITI MAIRA | 11.75 | 0 | 0 | 0
1250 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Augmentation of Janai Zone-II Water Supply Scheme with Laying Distribution System, Laying Rising Main, Providing FHTC and Construction of 3.6 M X 3.00 M Switch Room, Boundary wall at Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | 834/Hug | 20/04/2022 | 90 | M/S S.C CIVIL ENTERPRISE | 146.57 | 111.95 | 100 | 65
1251 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Extension of Laying Distribution System for proposed Augemntation of JANAI Zone-I & II Water Supply Scheme Under Serampore Sub-Division under Hooghly Division,P.H.E Dte | 2064/HUG | 17/07/2023 | 90 | M/S SHIVAM UDYOG | 41.09 | 39.68 | 100 | 99
1252 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | CONSTRUCTION OF 2NOS. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT JANAI (ZONE-II) 2ND TW SITE AND CHANDITALA PWSS NEAR THERO AREA UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E DTE. | 428/SER | 31/07/2024 | 15 | SRI KRISHNA ENTERPRISE | 0.68 | 1.33 | 100 | 95
1253 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Kapasharia PWSS 2. Janai PWSS 3. Begampur PWSS 4. Baksa PWSS 5. Chikrand PWSS 6. Kharsarai PWSS | 111/SER | 23/02/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 80
1254 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Quotation money deposition for new service connection at Janai w/s scheme, Zone- II, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004099413 Reference ID- 503611354 SM Code- 09695 | 71 | 16/04/2024 | 0 | WBSEDCL | 4.56 | 0 | 0 | 0
1255 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Withdrawing and relaying of rising mainwith left out Functional Hosuehold Tap Connection at Janai Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 4050/HUG | 19/12/2024 | 45 | M/S SHIVAM UDYOG | 13.85 | 0 | 0 | 5
1256 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Sinking of 2 nos. 300 X200 mm dia Tube Well, 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 5th Tube Well Site of BILASPUR W/S Scheme & 3rd Tube Well Site of JANAI W/S Scheme(ZONE-I) under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 3523/HUG | 22/10/2024 | 102 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 29.4 | 0 | 0 | 50
1257 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II , SM/09695 | Augmentation | Additional works for laying of water supply pipeline by HDD process and Protection of Pipe Line along Pond embankment and road side at Zone II of JANAI Water Supply Scheme under Serampore SubDivision, P.H.E. Dte. | 744/HUG | 05/03/2024 | 514 | M/S S & P CONSTRUCTION | 45.19 | 0 | 0 | 60
1258 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Left bank of Sundeswari river) Water Supply Scheme , SM/06989 | Retrofitting | FHTC |  | 15/02/2021 | 0 | P.B. ENTERPRISE (PINTU BHADURI) | 77 | 0 | 0 | 0
1259 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Left bank of Sundeswari river) Water Supply Scheme , SM/06989 | Retrofitting | Providing 114 nos FHTC for different mouzas under Harishchak PWSS under Hooghly Division PHE Dte. | 524/ARG | 30/11/2021 | 45 | MAA JAGADHATRI CONSTRUCTION | 4.74 | 4.74 | 100 | 0
1260 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Left bank of Sundeswari river) Water Supply Scheme , SM/06989 | Retrofitting | Providing 450 nos Functional Household Tap Connection (FHTC) within the command area of Harischak Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | 1998/Hug | 12/11/2021 | 30 | M/S SHIVAM UDYOG | 20.68 | 15.86 | 100 | 0
1261 | HOOGHLY | Electrical | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12250 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Haripur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | 3490/ED | 30/12/2022 | 90 | P.K. ENGINEERING | 20.24 | 9.82 | 48.53 | 49
1262 | HOOGHLY | Hooghly Division | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12250 | New | Material Requisition To Resource Division | 3060/13/Hug | 11/10/2023 | 0 | Resource Division | 12.5 | 0 | 0 | 0
1263 | HOOGHLY | Electrical | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12250 | New | Quotation Bill for New Service Connection at Haripur W/S. Sch. PH-II | 508 | 08/12/2023 | 0 | WBSEDCL | 9.7 | 0 | 0 | 0
1264 | HOOGHLY | Electrical | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12250 | New | Quotation Bill for New Service Connection at Haripur W/S. Sch. PH-I | 501 | 08/12/2023 | 0 | WBSEDCL | 3.77 | 0 | 0 | 0
1265 | HOOGHLY | Electrical | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12250 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Haripur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | 785/ED | 09/02/2023 | 90 | SRI KRISHNA NIRMAN | 20.26 | 14.03 | 69.25 | 65
1266 | HOOGHLY | Hooghly Division | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12250 | New | CONSTRUCTION OF 2NOS. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT HARIPUR HW SITE AND 2ND SITE UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E DTE. | 426/SER | 31/07/2024 | 15 | SUNITI MAIRA | 0.68 | 0.66 | 100 | 95
1267 | HOOGHLY | Electrical | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12250 | New | Quotation money deposition for new service connection at Haripur w/s scheme, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 100000123497 Reference ID- 860318447 SM Code- 12250 | BP-24-25-597 | 21/11/2024 | 0 | WBSEDCL | 2.22 | 0 | 0 | 0
1268 | HOOGHLY | Hooghly Division | HARIPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12250 | New | Acceptance Order for NABABPUR, DUDHKALMI, HARIPUR, JAGMOHANPUR , GANGADHARPUR Piped Water Supply Scheme with.TW, Switch room, boundaryivall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at CHANDITALA-I Block under SERAMPORE Sub-Division Under Hooghly Division PHE Dte. | 2393/HUG | 10/08/2023 | 731 | GREEN ROYAL INFRA CON PVT LTD | 3243.22 | 283.99 | 49.92 | 9
1269 | HOOGHLY | Electrical | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12255 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hasnan water supply scheme, T.W. No. I & II, Block: Polba-Dadpur, District Hooghly under Electrical Division, PHE Dte. | 3466/ED | 30/12/2022 | 90 | T.N. BANERJEE | 21.6 | 0 | 0 | 0
1270 | HOOGHLY | Hooghly Division | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12255 | New | Material Requisition To Resource Division | 1386/41/Hug | 15/05/2023 | 0 | Resource Division | 19.37 | 0 | 0 | 0
1271 | HOOGHLY | Hooghly Division | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12255 | New | Material Requisition To Resource Division | 1264/4/HUG | 03/05/2023 | 0 | Resource Division | 17.97 | 0 | 0 | 0
1272 | HOOGHLY | Hooghly Division | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12255 | New | Material Requisition To Resource Division | 3059/41/Hug | 11/10/2023 | 0 | Resource Division | 19.37 | 0 | 0 | 0
1273 | HOOGHLY | Electrical | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12255 | New | Quotation for new service connection at Hasnan W/S Sch., T/W No. - I, Block - Polba-Dadpur, Dist. - Hooghly | 255 | 05/09/2023 | 0 | WBSEDCL | 12.17 | 0 | 0 | 0
1274 | HOOGHLY | Hooghly Division | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12255 | New | Road Restoration | BP-2023-24-529 | 17/10/2023 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 12 | 0 | 0 | 0
1275 | HOOGHLY | Electrical | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12255 | New | Quotation for new service connection at Hasnan W/S Sch. , T/W No - II, Block- Polba-Dadpur, Dist - Hooghly | 254 | 05/09/2023 | 0 | WBSEDCL | 4.01 | 0 | 0 | 0
1276 | HOOGHLY | Electrical | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12255 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hasnan water supply scheme, T.W. No. I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | 325/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 20.85 | 0 | 0 | 0
1277 | HOOGHLY | Hooghly Division | HASNAN PIPED W/S SCHEME UNDER POLBA-DADPUR BLOCK , SM/12255 | New | Ground Water Based Piped Water Supply Schemes (PWSS) under POLBA-DADPUR Block at DALIMBA, GHATAMPUR, HASNAN, KAMRAI, KUCHPALA, PATUL, UTTAR BABNAN (ZONE-I) & UTTAR BABNAN (ZONE-II) Mouzas including Construction of different capacities R.C.C. Over Head Reservoirs (OHRs), Sinking of Tube Wells, Laying Distribution Systems (LDS), Laying Rising Main Interconnection pipelines, providing Functional Household Tap Connections (FHTCs), Construction of Switch Rooms, Boundary Walls etc. under Hooghly Division P.H.E. Dte. in connection with JJM. | 955/HUG | 30/03/2023 | 887 | GREEN ROYAL INFRA CON PVT LTD | 3672.07 | 436.06 | 84.39 | 15
1278 | HOOGHLY | Hooghly Division | SIMLA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12260 | New | Material Requisition To Resource Division | 1264/16/HUG | 03/05/2023 | 0 | Resource Division | 19.93 | 0 | 0 | 0
1279 | HOOGHLY | Hooghly Division | SIMLA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12260 | New | Material Requisition To Resource Division | 3059/21/Hug | 11/10/2023 | 0 | Resource Division | 1.74 | 0 | 0 | 0
1280 | HOOGHLY | Electrical | SIMLA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12260 | New | Quotation Bill for New Service Connection at Simla W/S. Sch. TW-I | 696 | 22/01/2024 | 0 | WBSEDCL | 6.37 | 0 | 0 | 0
1281 | HOOGHLY | Electrical | SIMLA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12260 | New | Quotation Bill for New Service Connection at Simla W/S. Sch. TW-II | 697 | 22/01/2024 | 0 | WBSEDCL | 5.91 | 0 | 0 | 0
1282 | HOOGHLY | Electrical | SIMLA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12260 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Simla water supply scheme, T.W. No. I & II, Block: Dhaniakhali District - Hooghly under Electrical Division, PHE Dte. | 3476/ED | 30/12/2022 | 1678 | A.S. ENTERPRISE | 21.42 | 0 | 0 | 45
1283 | HOOGHLY | Hooghly Division | SIMLA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12260 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 292.8 | 78.6 | 30
1284 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR , SM/12370 | Augmentation | Material Requisition To Resource Division | 2686/14/Hug | 01/12/2022 | 0 | Resource Division | 0.36 | 0 | 0 | 0
1285 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR , SM/12370 | Augmentation | Route survey Design drawing & DPR preparation of Gopalnagar PWSS under Chandannagar Sub-Division, P.H.E. Dte | 262/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.24 | 4.11 | 100 | 0
1286 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR , SM/12370 | Augmentation | Sinking of Three Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at GOPALNAGAR PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | 2507/HUG | 22/11/2022 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 36.31 | 34.06 | 100 | 0
1287 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR , SM/12370 | Augmentation | Material Requisition To Resource Division | 01/06/Hug | 02/01/2023 | 0 | Resource Division | 28.33 | 0 | 0 | 0
1288 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR , SM/12370 | Augmentation | Material Requisition To Resource Division | 902/3/Hug | 27/03/2023 | 0 | Resource Division | 28.33 | 0 | 0 | 0
1289 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR , SM/12370 | Augmentation | Material Requisition To Resource Division | 1383/30/Hug | 15/05/2023 | 0 | Resource Division | 28.33 | 0 | 0 | 0
1290 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR , SM/12370 | Augmentation | Material Requisition To Resource Division | 79/13/Hug | 06/01/2023 | 0 | Resource Division | 134.26 | 0 | 0 | 0
1291 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR , SM/12370 | Augmentation | Quotation Bill for New Service Connection at Gopalnagar W/S. Sch. TW-III | 211 | 24/03/2023 | 0 | WBSEDCL | 0.7 | 0 | 0 | 0
1292 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR , SM/12370 | Augmentation | Quotation for new service connection at Gopalnagar W/S sch. , T/W - II, Dist. - Hooghly | 23 | 11/05/2023 | 0 | WBSEDCL | 2.53 | 0 | 0 | 0
1293 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR , SM/12370 | Augmentation | Damages of Road from Dewanbheri to Paunan | BP-2023-24-415 | 29/09/2023 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 15.81 | 0 | 0 | 0
1294 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR , SM/12370 | Augmentation | Revised Quotation Bill for New Service Connection at Gopal Nagar W/S. Sch. TW-IV | 338 | 10/10/2023 | 0 | WBSEDCL | 0 | 0 | 0 | 0
1295 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR , SM/12370 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT GOPALNAGAR W/S SCH. , T/W NO. - IV, DIST. - HOOGHLY | 25 | 11/05/2023 | 0 | WBSEDCL | 4.09 | 0 | 0 | 0
1296 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR , SM/12370 | Augmentation | RESTORATION OF DAMAGES ROAD NAMELY DEWANBHERI TO PAWNAN PART OF DEWANBHERI KACHARIMORE TO BILATPUR BRIDGE VIDE PACKAGE NO. WB-08-ADB-172 | BP-2023-24-887 | 04/03/2024 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 14.63 | 0 | 0 | 0
1297 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR , SM/12370 | Augmentation | Revised Quotation New service connection at Gopalnagar W/S Sch. , T/W No. - IV, Block - Singur, due to non payment of previous quotation for online banking transaction error. |  | 06/10/2023 | 0 | WBSEDCL | 4.09 | 0 | 0 | 0
1298 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR , SM/12370 | Augmentation | GOPALNAGAR Piped Water Supply Scheme with Sinking of tube-well, LDS, Construction of 600 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation under SINGUR Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte, District:- Hooghly [AUGMENTATION SCHEME] | 1211/HUG | 27/04/2023 | 1070 | S. HATI | 499.95 | 262.58 | 52.52 | 90
1299 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR , SM/12370 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gopalnagar water supply scheme, T.W. No.- I, II & III, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | 838/ED | 14/02/2023 | 791 | WEST BENGAL ENGINEERING CO. | 32.24 | 31.4 | 97.45 | 90
1300 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR GOPALNAGAR , SM/12370 | Augmentation | Sinking of Tube Well, Rising Main, Construction of switch-room & boundary wall at Proposed TW site, Repairing of Switch Room, Boundary wall & FHTC For Augmentation of GOPALNAGAR Piped Water Supply Scheme under SINGUR Block under Chandannagar Sub-Division, PHE Dte, District:- Hooghly [AUGMENTATION SCHEME] | 952/HUG | 30/03/2023 | 855 | LOKENIRMAN | 246.68 | 215.88 | 84.11 | 85
1301 | HOOGHLY | Hooghly Division | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12263 | New | Material Requisition To Resource Division | 1386/48/Hug | 15/05/2023 | 0 | Resource Division | 19.19 | 0 | 0 | 0
1302 | HOOGHLY | Hooghly Division | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12263 | New | Material Requisition To Resource Division | 3059/36/Hug | 11/10/2023 | 0 | Resource Division | 19.19 | 0 | 0 | 0
1303 | HOOGHLY | Electrical | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12263 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bishnupur water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | 3485/ED | 30/12/2022 | 90 | C.M.S. ENGINEERING CONCERN | 22.86 | 20.79 | 90.95 | 45
1304 | HOOGHLY | Hooghly Division | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12263 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BISHNUPUR, DASHGHARA ZONE-I, DASHGHARA ZONE-II (1NO.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.. | 2407/HUG | 11/08/2023 | 45 | GEE BEE NIRMAN CO PRIVATE LIMITED | 81.62 | 26.42 | 80.91 | 40
1305 | HOOGHLY | Hooghly Division | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12263 | New | Construction of Store room for temporary Chlorine and maintenance material storage For Dasghara Zone-I, Bishnupur and Shrirampur Piped Water Supply under Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 277/CH | 14/03/2024 | 7 | M/S BIMAL DAS AND CO. | 0.95 | 0.95 | 100 | 100
1306 | HOOGHLY | Electrical | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12263 | New | Bishnupur PH__I Water supply Scheme | 723 | 05/02/2024 | 0 | WBSEDCL | 7.9 | 0 | 0 | 0
1307 | HOOGHLY | Electrical | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12263 | New | Quotation of New service Connection Charge for Bishnupur w/s Scheme,TW No-II Block-Dhaniakhali Dist-Hooghly under ED,PHE Dte(SM/12263) Application no-5003995286 Reference Id-503552526 | 762 | 16/02/2024 | 0 | WBSEDCL | 3.9 | 0 | 0 | 0
1308 | HOOGHLY | Hooghly Division | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12263 | New | Construction of Different Capacity RCC Over Head Reservoir over Pile/Raft Foundation including Sub-soil investigation works for OHR, with Laying Distribution System Providing Functional House hold Tap Connection for BISHNUPUR, DOSGHARA(zone-I), DOSGHARA(zone-II), GURBARI & SRIRAMPUR Piped Water Supply Scheme within DHANIAKHALI block under chinshuraH Sub-Division of Hooghly division, PHE Dte. Under Hooghly district in connection with JJM. | 2066/HUG | 17/07/2023 | 747 | GEE BEE NIRMAN CO PRIVATE LIMITED | 2255.89 | 275.85 | 61.14 | 20
1309 | HOOGHLY | Hooghly Division | BISHNUPUR W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12263 | New | Laying of Rising main with necessary interconnection with T.W., OHR & DistributionSystem ,Construction of switch-rooms & boundary walls at different TW site for Bishnupur Piped Water Supply Scheme under Chinsurah Sub-Division Block-Dhaniakhali , District:-Hooghly | 2415/HUG | 11/08/2023 | 589 | GEE BEE NIRMAN CO PRIVATE LIMITED | 54.65 | 8.62 | 15.77 | 30
1310 | HOOGHLY | Electrical | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12233 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Routhkhana water supply scheme, T.W. No.- I & II, Block: Khanakul-II District- Hooghly under Electrical Division, PHE Dte. | 3502/ED | 30/12/2022 | 90 | BINAPANI ENTERPRISE | 21.48 | 0 | 0 | 0
1311 | HOOGHLY | Hooghly Division | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12233 | New | Material Requisition To Resource Division | 1385/11/Hug | 15/05/2023 | 0 | Resource Division | 15.88 | 0 | 0 | 0
1312 | HOOGHLY | Hooghly Division | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12233 | New | Material Requisition To Resource Division | 3057/50/Hug | 11/10/2023 | 0 | Resource Division | 15.88 | 0 | 0 | 0
1313 | HOOGHLY | Hooghly Division | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12233 | New | Material Requisition To Resource Division | 1234/42/Hug | 28/04/2023 | 0 | Resource Division | 48.75 | 0 | 0 | 0
1314 | HOOGHLY | Electrical | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12233 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ROUTHKHANA PIPED W/S SCHEME, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1172/ED | 14/06/2024 | 90 | BINAPANI ENTERPRISE | 10.64 | 0 | 0 | 0
1315 | HOOGHLY | Electrical | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12233 | New | Quotation of New Service Connection for Routhkhana w/s Scheme,TW No-II Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/12233) Application No-5003987362 Reference Id-503547192 | 760 | 16/02/2024 | 0 | WBSEDCL | 3.26 | 0 | 0 | 0
1316 | HOOGHLY | Electrical | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12233 | New | Quotation of New Service Connection for Routhkhana w/s Scheme,TW No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/12233) Application No-5003987354 Reference Id-503547191 | 758 | 16/02/2024 | 0 | WBSEDCL | 4.85 | 0 | 0 | 0
1317 | HOOGHLY | Hooghly Division | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12233 | New | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 369.63 | 59.79 | 50
1318 | HOOGHLY | Hooghly Division | GROUND WATER BASED ROUTHKHANA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12233 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0 | 0
1319 | HOOGHLY | Hooghly Division | NABABPUR PIPED WATER SUPPLY SCHEME BLOCK- CHANDITALA-I, DISTRICT: HOOGHLY , SM/12239 | New | Material Requisition To Resource Division | 3060/17/Hug | 11/10/2023 | 0 | Resource Division | 13.96 | 0 | 0 | 0
1320 | HOOGHLY | Electrical | NABABPUR PIPED WATER SUPPLY SCHEME BLOCK- CHANDITALA-I, DISTRICT: HOOGHLY , SM/12239 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nababpur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | 3498/ED | 30/12/2022 | 90 | ANJAN ENTERPRISE | 21.33 | 7.7 | 36.12 | 30
1321 | HOOGHLY | Electrical | NABABPUR PIPED WATER SUPPLY SCHEME BLOCK- CHANDITALA-I, DISTRICT: HOOGHLY , SM/12239 | New | Quotation money deposition for new service connection at Nababpur w/s scheme, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004064410 Reference ID- 503597307 SM Code- 12239 | 560 | 11/11/2024 | 0 | WBSEDCL | 4.18 | 0 | 0 | 0
1322 | HOOGHLY | Electrical | NABABPUR PIPED WATER SUPPLY SCHEME BLOCK- CHANDITALA-I, DISTRICT: HOOGHLY , SM/12239 | New | Quotation bill for new service connection charges at Nababpur PWSS P.H. No.-I, Hooghly. Application No. 5004064466 Ref ID: 503597309 | 21 | 05/04/2024 | 0 | WBSEDCL | 4.1 | 0 | 0 | 0
1323 | HOOGHLY | Electrical | NABABPUR PIPED WATER SUPPLY SCHEME BLOCK- CHANDITALA-I, DISTRICT: HOOGHLY , SM/12239 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nababpur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | 786/ED | 09/02/2023 | 727 | M/S P.P. ELECTRICALS | 22.36 | 0 | 0 | 50
1324 | HOOGHLY | Hooghly Division | NABABPUR PIPED WATER SUPPLY SCHEME BLOCK- CHANDITALA-I, DISTRICT: HOOGHLY , SM/12239 | New | Acceptance Order for NABABPUR, DUDHKALMI, HARIPUR, JAGMOHANPUR , GANGADHARPUR Piped Water Supply Scheme with.TW, Switch room, boundaryivall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at CHANDITALA-I Block under SERAMPORE Sub-Division Under Hooghly Division PHE Dte. | 2393/HUG | 10/08/2023 | 731 | GREEN ROYAL INFRA CON PVT LTD | 3243.22 | 164.38 | 28.62 | 9
1325 | HOOGHLY | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME , SM/11286 | New | Route Survey, Design Drawing & DPR Preparation of Astara PWSS under Chandannagar Sub - Division, PHE Dte. | 510/Chan | 29/09/2022 | 15 | ENVIROTECH SOLUTIONS | 4.07 | 4.07 | 100 | 0
1326 | HOOGHLY | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME , SM/11286 | New | Material Requisition To Resource Division | 2471/2/Hug | 18/11/2022 | 0 | Resource Division | 12.06 | 0 | 0 | 0
1327 | HOOGHLY | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME , SM/11286 | New | Sinking of Five Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ATISARA, NANDA, NOWPARA, BASUBATI & ASTARA PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | 878/HUG | 27/03/2023 | 45 | MS D.PALIT AND CO. | 62.24 | 11.94 | 95.92 | 100
1328 | HOOGHLY | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME , SM/11286 | New | Material Requisition To Resource Division | 109/ 22/Hug | 10/01/2023 | 0 | Resource Division | 27.67 | 0 | 0 | 0
1329 | HOOGHLY | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME , SM/11286 | New | Material Requisition To Resource Division | 01/05/Hug | 02/01/2023 | 0 | Resource Division | 12.06 | 0 | 0 | 0
1330 | HOOGHLY | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME , SM/11286 | New | Material Requisition To Resource Division | 1383/32/Hug | 15/05/2023 | 0 | Resource Division | 12.27 | 0 | 0 | 0
1331 | HOOGHLY | Electrical | ASTARA PIPED WATER SUPPLY SCHEME , SM/11286 | New | Astara w/s scheme,P H No-1 | 313 | 27/09/2023 | 0 | WBSEDCL | 5.81 | 0 | 0 | 0
1332 | HOOGHLY | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME , SM/11286 | New | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of ASTARA Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | 652/Hug | 10/03/2023 | 60 | APEX ENGINEERING | 12.25 | 12.25 | 100 | 100
1333 | HOOGHLY | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME , SM/11286 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at ATISARA, NANDA, NAWPARA,BASUBATI & ASTARA W/S Scheme underChandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | 1818/HUG | 22/06/2023 | 45 | OSMAN SEKH | 80.85 | 31.22 | 100 | 100
1334 | HOOGHLY | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME , SM/11286 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System & Protection Work at different TW site for ASTARA Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | 2445/HUG | 12/08/2023 | 60 | RURAL CONSTRUCTION (MANIK CHANDRA ADAK) | 44.85 | 16.42 | 49.32 | 100
1335 | HOOGHLY | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME , SM/11286 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Astara PWSS, Baligori Z-I PWSS, Baligori Z-II PWSS, Talpur PWSS, Kulteghori PWSS, Santoshpur PWSS) | 308/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 50 | 100
1336 | HOOGHLY | Electrical | ASTARA PIPED WATER SUPPLY SCHEME , SM/11286 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Astara water supply scheme, T.W. No. I & II, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | 3457/ED | 30/12/2022 | 90 | S S ENTERPRISES | 23.02 | 22.95 | 100 | 95
1337 | HOOGHLY | Electrical | ASTARA PIPED WATER SUPPLY SCHEME , SM/11286 | New | Quotation for new service connection for ASTARA water supply scheme PH NO-II , Dist- Hooghly Application NO.-5004031983 Ref. ID- 503573554 SM/11286 | 804 | 27/02/2024 | 0 | WBSEDCL | 6.23 | 0 | 0 | 0
1338 | HOOGHLY | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME , SM/11286 | New | Providing 48 Nos F.H.T.C in leftout portion of Astara water supply scheme under Chandannagar Sub-Division P.H.E. Dte. [PHASE -II] | 880/CHAN | 21/07/2025 | 20 | SWASTIK ENTERPRISE | 3.93 | 0 | 0 | 0
1339 | HOOGHLY | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME , SM/11286 | New | Providing 47 Nos F.H.T.C in leftout portion of Astara water supply scheme under Chandannagar Sub-Division P.H.E. Dte. [PHASE -I] | 879/CHAN | 21/07/2025 | 20 | KALYAN BANERJEE | 3.89 | 0 | 0 | 0
1340 | HOOGHLY | Hooghly Division | ASTARA PIPED WATER SUPPLY SCHEME , SM/11286 | New | Providing 48 Nos F.H.T.C in leftout portion of Astara water supply scheme under Chandannagar Sub-Division P.H.E. Dte. [PHASE -III] | 909/CHAN | 21/07/2025 | 20 | RITAM ENTERPRISE | 3.93 | 0 | 0 | 0
1341 | HOOGHLY | Hooghly Division | PANRRA PIPED WATER SUPPLY SCHEME , SM/11292 | New | Route Survey, Design Drawing & DPR Preparation of Panrra PWSS under Chandannagar Sub - Division, PHE Dte. | 514/Chan | 29/09/2022 | 15 | ENVIROTECH SOLUTIONS | 6.22 | 6.22 | 100 | 0
1342 | HOOGHLY | Hooghly Division | PANRRA PIPED WATER SUPPLY SCHEME , SM/11292 | New | Material Requisition To Resource Division | 109/ 16/Hug | 10/01/2023 | 0 | Resource Division | 80.63 | 0 | 0 | 0
1343 | HOOGHLY | Hooghly Division | PANRRA PIPED WATER SUPPLY SCHEME , SM/11292 | New | Material Requisition To Resource Division | 1383/11/Hug | 15/05/2023 | 0 | Resource Division | 18.47 | 0 | 0 | 0
1344 | HOOGHLY | Hooghly Division | PANRRA PIPED WATER SUPPLY SCHEME , SM/11292 | New | Material Requisition To Resource Division | 3058/35/Hug | 11/10/2023 | 0 | Resource Division | 18.14 | 0 | 0 | 0
1345 | HOOGHLY | Electrical | PANRRA PIPED WATER SUPPLY SCHEME , SM/11292 | New | Quotation of New Service Connection Charge for Pannra w/S Scheme,TW No-II, Block-Haripal Dist-Hooghly under ED,PHE Dte | 258 | 05/09/2023 | 0 | WBSEDCL | 3.16 | 0 | 0 | 0
1346 | HOOGHLY | Hooghly Division | PANRRA PIPED WATER SUPPLY SCHEME , SM/11292 | New | Construction of 400 cum capacity OHR with 20 mtr. staging height including Soil Investigation work, Laying Distribution System, Rising Main & Interconnection between O.H.R, TW No-I & II, Construction of 1No 5.4 M X 3.6 M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at Head Work Site, Construction of 1No 3.6M x 3.0M Switch Room without Sanitary & Water Supply arrangement & Boundary Wall at 2nd T/W Site including Providing FHTC in PANRRA Water Supply Scheme at HARIPAL Block under Chandannagar Sub-Division. | 988/Hug | 04/04/2023 | 300 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 611.8 | 281.67 | 46.04 | 80
1347 | HOOGHLY | Hooghly Division | PANRRA PIPED WATER SUPPLY SCHEME , SM/11292 | New | Horizontal Auger boring with water jet system Including Approach road at Panrra W/S Scheme under Chandannagar Sub - Division of Hooghly Division, P.H.E. Dte. | 451/HUG | 15/02/2024 | 30 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 20.55 | 0 | 0 | 0
1348 | HOOGHLY | Electrical | PANRRA PIPED WATER SUPPLY SCHEME , SM/11292 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Panrra water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | 3472/ED | 30/12/2022 | 90 | SANKAR PRASAD DUTTA & CO. | 23 | 20.88 | 90.77 | 30
1349 | HOOGHLY | Hooghly Division | PANRRA PIPED WATER SUPPLY SCHEME , SM/11292 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Harat& Panrra W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 1804/HUG | 21/06/2023 | 45 | OSMAN SEKH | 80.84 | 32.25 | 66.58 | 100
1350 | HOOGHLY | Electrical | PANRRA PIPED WATER SUPPLY SCHEME , SM/11292 | New | Quotation for New Service Connection at Pantra W/S. Sch. TW-I | 612 | 14/03/2024 | 0 | WBSEDCL | 4.96 | 0 | 0 | 0
1351 | HOOGHLY | Hooghly Division | Rautara Mini Piped Water Supply Scheme , SM/13667 | New | Material Requisition To Resource Division | 1385/37/Hug | 15/05/2023 | 0 | Resource Division | 0.6 | 0 | 0 | 0
1352 | HOOGHLY | Hooghly Division | Rautara Mini Piped Water Supply Scheme , SM/13667 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-249 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 27.81 | 0 | 0 | 0
1353 | HOOGHLY | Electrical | Rautara Mini Piped Water Supply Scheme , SM/13667 | New | Mini Piped Water Supply Scheme. | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0 | 0
1354 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF DEBANANDAPUR WATER SUPPLY SCHEME , SM/11997 | Retrofitting | Providing 300 nos Functional Household Tap Connection (FHTC) within the command area of Debanandapur Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 2201/HUG | 14/12/2021 | 30 | SARKAR CONSTRUCTION | 18.07 | 17.21 | 95.28 | 0
1355 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF DEBANANDAPUR WATER SUPPLY SCHEME , SM/11997 | Retrofitting | Providing 1400 nos Functional Household Tap Connection (FHTC) within the command area of Debanandapur Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 1681/HUG | 13/09/2021 | 40 | BIMAL KUMAR HALDER | 55 | 22.79 | 41.43 | 0
1356 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF DEBANANDAPUR WATER SUPPLY SCHEME , SM/11997 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DEBANANDAPUR PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 1130/HUG | 19/04/2023 | 45 | BAKSHI ENTERPRISE | 40.32 | 17.24 | 100 | 30
1357 | HOOGHLY | Hooghly Division | Char Sundalpur Mini Piped Water Supply Scheme , SM/13657 | New | MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-292 | 19/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 29.11 | 0 | 0 | 0
1358 | HOOGHLY | Electrical | Char Sundalpur Mini Piped Water Supply Scheme , SM/13657 | New | Mini piped Water Supply scheme |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
1359 | HOOGHLY | Electrical | Char Sundalpur Mini Piped Water Supply Scheme , SM/13657 | New | Mini Piped Water Supply Scheme | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0 | 0
1360 | HOOGHLY | Hooghly Division | Arazi Krittibaspur Mini Piped Water Supply Scheme , SM/13660 | New | Material Requisition To Resource Division | 1385/36/Hug | 15/05/2023 | 0 | Resource Division | 0.12 | 0 | 0 | 0
1361 | HOOGHLY | Hooghly Division | Arazi Krittibaspur Mini Piped Water Supply Scheme , SM/13660 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME. |  | 23/06/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 25.95 | 0 | 0 | 0
1362 | HOOGHLY | Hooghly Division | Arazi Krittibaspur Mini Piped Water Supply Scheme , SM/13660 | New | MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-335 | 31/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 25.08 | 0 | 0 | 0
1363 | HOOGHLY | Hooghly Division | Arazi Krittibaspur Mini Piped Water Supply Scheme , SM/13660 | New | Requisition for Sajal Gram |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 23.35 | 0 | 0 | 0
1364 | HOOGHLY | Electrical | Arazi Krittibaspur Mini Piped Water Supply Scheme , SM/13660 | New | Mini Piped water Supply Scheme | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
1365 | HOOGHLY | Hooghly Division | Dwariapur Mini Piped Water Supply Scheme , SM/13553 | New | Material Requisition To Resource Division | 1385/29/Hug | 15/05/2023 | 0 | Resource Division | 0.45 | 0 | 0 | 0
1366 | HOOGHLY | Hooghly Division | Dwariapur Mini Piped Water Supply Scheme , SM/13553 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME |  | 23/06/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 31.42 | 0 | 0 | 0
1367 | HOOGHLY | Hooghly Division | Dwariapur Mini Piped Water Supply Scheme , SM/13553 | New | REQUISITION OF FUND FOR SAJAL GRAM SCHEME |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 28.28 | 0 | 0 | 0
1368 | HOOGHLY | Hooghly Division | Dwariapur Mini Piped Water Supply Scheme , SM/13553 | New | MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-337 | 31/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.06 | 0 | 0 | 0
1369 | HOOGHLY | Electrical | Dwariapur Mini Piped Water Supply Scheme , SM/13553 | New | Mini Piped water Supply Scheme | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
1370 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13410 | Augmentation | Construction of 3.60 m X 3.00 m Switch Room with Sanitary and Water Supply & Sanitation arrangement at 3rd T/W Site of DIGSUI-HEORA ( Z-II) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | 723/CH | 23/08/2022 | 45 | SUDIPTA DAS | 4.98 | 4.93 | 100 | 100
1371 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13410 | Augmentation | Digsui Heora W/S. Sch. |  | 10/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 21.72 | 0 | 0 | 0
1372 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13410 | Augmentation | New Connection of Digsui Heora W/S. Sch. Z-I, PH-III | BP-2022-23-110 | 01/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.91 | 0 | 0 | 0
1373 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13410 | Augmentation | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. with effect from 01.04.2023 to 31.08.2023. | 203/AE-I/ED | 27/03/2023 | 153 | DASHRATH KUMAR PRAJAPATI | 0.73 | 0.39 | 53.97 | 5
1374 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13410 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Digsui Heora water supply scheme, Zone-II, T.W. No.- III, Block: Chinsurah Mogra, District - Hooghly under Electrical Division, PHE Dte. | 1917/ED | 21/11/2022 | 90 | M/S S.R. ENTERPRISE | 9.41 | 9.41 | 99.94 | 100
1375 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13410 | Augmentation | Construction of 3.60 m X 3.00 m Switch Room with Sanitary and Water Supply & Sanitation arrangement at 3rd T/W Site of DIGSUI-HEORA ( Z-I) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | 722/CH | 23/08/2022 | 45 | SWARNA ENTERPRISE | 4.98 | 4.97 | 100 | 0
1376 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13410 | Augmentation | Supply, delivery & installation of sautomatic chlorinatorfor Digsui Heora W/S. Sch. Z-I, TW-III Hooghly | 69/HMSD | 10/01/2023 | 7 | SRI KRISHNA NIRMAN | 0.8 | 0.8 | 100 | 100
1377 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13410 | Augmentation | Supply, Delivery & Installation of submersible pumping machinery & other Electrical Mechanical equipments etc. with allied works for Digsui- Heora W/S. Sch. TW-III | 1538/ED | 19/09/2022 | 90 | SRI KRISHNA NIRMAN | 8.93 | 8.88 | 100 | 100
1378 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13410 | Augmentation | Material Requisition To Resource Division | 3004/6/Hug | 05/10/2023 | 0 | Resource Division | 37.77 | 0 | 0 | 0
1379 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13410 | Augmentation | Quotation bill for New Connection of WBSEDCL at Digsui Heora W/S. Sch. | 127 | 17/01/2023 | 0 | WBSEDCL | 3.83 | 0 | 0 | 0
1380 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13410 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DIGSUI HEORAH PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte... | 1132/HUG | 19/04/2023 | 30 | RANA ENTERPRISE | 32.74 | 24.55 | 100 | 80
1381 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13410 | Augmentation | Construction of Boundary Wall ,Laying of C.I/D.I pipes & specials for connection of Proposed T.W with distribution system , FHTC of DIGSUI HOERA W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | 1339/HUG | 11/05/2023 | 30 | MAA JAGADHATRI CONSTRUCTION | 23.6 | 13.75 | 100 | 83
1382 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13410 | Augmentation | Emergency Repairing & Replacing Different dia distribution pipeline and necessary allied Works At Digsui Hoera Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | 19/CH | 04/01/2024 | 15 | MAA BUNAMATA ENTERPRISE | 2.1 | 2.09 | 100 | 55
1383 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13410 | Augmentation | Additional Laying of HDPE pipeline and interconnection work in distibution system of Digsui Heora Zone-I and Zone-II Water Supply Scheme for providing left over FHTC under Chinsurah Sub- Division, Under Hooghly Division, PHE Dte. | 535/HUG | 20/02/2024 | 15 | MAA JAGADHATRI CONSTRUCTION | 16.41 | 16.19 | 100 | 25
1384 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13410 | Augmentation | Repairing & Renovation of boundary wall, Switch room and Land development at H/W Site of Digsui Heora Z-II Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 489/CH | 04/04/2025 | 10 | DAS ENTERPRISE (SAMIR DAS) | 4.51 | 0 | 0 | 0
1385 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13410 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Digsui Heora Z-II Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 300/CH | 20/02/2025 | 10 | DAS ENTERPRISE (SAMIR DAS) | 2.06 | 0 | 0 | 0
1386 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DIGSUI HEORA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13410 | Augmentation | Shifting of distribution pipeline for widening of G.T. Roadfrom Naksa mouza to Hoera mouza of Digsui Hoera GP of Digsui Hoera Zone -I & Zone -II Water Supply Scheme under Chinsurah sub-division under Hooghly Division, PHE Dte. | 332/HUG | 05/02/2025 | 60 | SAMRAT CONSTRUCTION | 27.36 | 0 | 0 | 25
1387 | HOOGHLY | Hooghly Division | GROUND WATER BASED MARAKHANA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13324 | New | Material Requisition To Resource Division | 3057/62/Hug | 11/10/2023 | 0 | Resource Division | 14.29 | 0 | 0 | 0
1388 | HOOGHLY | Hooghly Division | GROUND WATER BASED MARAKHANA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13324 | New | Material Requisition To Resource Division | 1263/Hug | 03/05/2023 | 0 | Resource Division | 14.29 | 0 | 0 | 0
1389 | HOOGHLY | Electrical | GROUND WATER BASED MARAKHANA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13324 | New | Quotation of New Service Connection for Marakhana w/s Scheme,Zone-I,PH No-I Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13324) Application no-5004026546 Reference Id-503570690 | 110 | 09/05/2024 | 0 | WBSEDCL | 5.15 | 0 | 0 | 0
1390 | HOOGHLY | Electrical | GROUND WATER BASED MARAKHANA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13324 | New | Quotation of New Service Connection for Marakhana w/s Scheme,Zone-I,PH No-II Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13324) Application no-5004073228 Reference Id-503597246 | 125 | 17/05/2024 | 0 | WBSEDCL | 8.29 | 0 | 0 | 0
1391 | HOOGHLY | Hooghly Division | GROUND WATER BASED MARAKHANA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13324 | New | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 357.32 | 75.43 | 50
1392 | HOOGHLY | Hooghly Division | GROUND WATER BASED MARAKHANA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13324 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0 | 0
1393 | HOOGHLY | Hooghly Division | GROUND WATER BASED MARAKHANA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13324 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) NOAPARA PWSS- 1 no¿s, (2) HAYATPUR PWSS- 2 no¿s, (3) HIRAPUR PWSS (Z-I)- 1 no¿s, (4) HIRAPUR PWSS (Z-II)- 1 no¿s (5) MAROKHANA PWSS (Z-I)- 1 no¿s, (6) MOSTAFAPUR PWSS- 2 no¿s, (7) NATIBPUR PWSS- 2 no¿s, (8) ROUTHKHANA PWSS- 1 no¿s, (9) HARISCHAK PWSS- 2 no¿s, (10) PALASPAI PWSS- 1 no¿s | 1154/Arg | 10/12/2024 | 31 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
1394 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13343 | Augmentation | Quotation for new service connection at Dubir Bheri W/S Sch.(Aug.) , T/W no. - I, Dt. - Hooghly | 193 | 17/08/2023 | 0 | WBSEDCL | 10.34 | 0 | 0 | 0
1395 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13343 | Augmentation | Quotation for new service connection at Dubir Bheri W/S Sch(Aug.)., T/W No. - II, Hooghly | 194 | 17/08/2023 | 0 | WBSEDCL | 8.98 | 0 | 0 | 0
1396 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13343 | Augmentation | Preparation of DPR for Augmentation DUBIR BHERI Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-POLBA DADPUR]. | 693/CH | 09/08/2024 | 7 | APEX ENGINEERING | 4.5 | 0 | 0 | 0
1397 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13343 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed for Sajal Gram Display Board at different locations in 6 (Six) Nos villages & HGJ villages of Dubir Bheri PWSS for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. | 145/CH | 20/02/2024 | 7 | R.K. TRADERS | 0.95 | 0.95 | 100 | 50
1398 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13343 | Augmentation | Source Augmentation of DUBIRBHERI Piped Water Supply Scheme by Sinking 2 Nos. Tube well , Laying Distribution System, Laying rising main pipe line for interconnection between T.W & Distribution, Construction of Switch Room & Boundary Wall in Proposed T.W Sites, Repairing of Switch Room & Boundary Wall and other allied work to meet up the water demand, due to execution of FHTC under Hooghly Division P.H.E. Dte. within Polba Dadpur Block. | 282/HUG | 01/02/2023 | 732 | BIMAL KUMAR HALDER | 150.96 | 47.03 | 31.29 | 95
1399 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF DUBIR BHERI PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13343 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dubir Bheri water supply scheme, T.W. No.- I & II, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | 834/ED | 14/02/2023 | 450 | BARISAL TRADING CO. | 21.49 | 21.18 | 98.72 | 90
1400 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BAICHI PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13344 | Augmentation | Material Requisition To Resource Division | 3004/15/Hug | 05/10/2023 | 0 | Resource Division | 37.77 | 0 | 0 | 0
1401 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF BAICHI PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13344 | Augmentation | Quotation Bill for New Service Connection at Bainchi W/S. Sch. PH-IV | 545 | 19/12/2023 | 0 | WBSEDCL | 3.53 | 0 | 0 | 0
1402 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF BAICHI PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13344 | Augmentation | Quotation Bill for New Service Connection at Bainchi W/S. Sch. PH-V | 544 | 19/12/2023 | 0 | WBSEDCL | 36.89 | 0 | 0 | 0
1403 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF BAICHI PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13344 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Baichi water supply scheme, T.W. No.- I & II, Block: Pandua, District- Hooghly under Electrical Division, PHE Dte. | 823/ED | 14/02/2023 | 90 | SRI KRISHNA NIRMAN | 21.49 | 20.94 | 97.45 | 90
1404 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BAICHI PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/13344 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in BATIKA-BAINCHI GP of PANDUA Block. | 242/CH | 12/03/2024 | 30 | RAJMAHAL ENTERPRISE | 4.99 | 4.81 | 100 | 90
1405 | HOOGHLY | Hooghly Division | Telinipara Mini Piped Water Supply Scheme , SM/13599 | New | MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-300 | 19/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 29.33 | 0 | 0 | 0
1406 | HOOGHLY | Electrical | Telinipara Mini Piped Water Supply Scheme , SM/13599 | New | Mini piped Water Supply scheme |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
1407 | HOOGHLY | Electrical | Telinipara Mini Piped Water Supply Scheme , SM/13599 | New | Mini Piped Water Supply Scheme | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0 | 0
1408 | HOOGHLY | Hooghly Division | Chak Netara Mini Piped Water Supply Scheme , SM/13551 | New | Material Requisition To Resource Division | 1385/67/Hug | 15/05/2023 | 0 | Resource Division | 0.41 | 0 | 0 | 0
1409 | HOOGHLY | Hooghly Division | Chak Netara Mini Piped Water Supply Scheme , SM/13551 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-244 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.39 | 0 | 0 | 0
1410 | HOOGHLY | Electrical | Chak Netara Mini Piped Water Supply Scheme , SM/13551 | New | Mini Piped Water Supply Scheme. | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0 | 0
1411 | HOOGHLY | Hooghly Division | Augmentation of Chiladangi Piped Water Supply Scheme under Pursurah Block , SM/15788 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at CHILADANGI PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | 741/HUG | 15/03/2023 | 30 | MAYA CONSTRUCTION | 11.32 | 0 | 0 | 0
1412 | HOOGHLY | Electrical | Augmentation of Chiladangi Piped Water Supply Scheme under Pursurah Block , SM/15788 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Chiladangi water supply scheme, T.W. No. I, Block: Pursura, District- Hooghly under Electrical Division, PHE Dte. | 1498/ED | 28/03/2023 | 90 | DAS ENTERPRISE | 10.73 | 0 | 0 | 0
1413 | HOOGHLY | Hooghly Division | Augmentation of Chiladangi Piped Water Supply Scheme under Pursurah Block , SM/15788 | Augmentation | AUGMENTATION of CHILADANGI Piped Water Supply Scheme with Extension of LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. Block-PURSURAH, District:- Hooghly. [AUGMENTATION SCHEME] | 2147/HUG | 24/07/2023 | 90 | GHOSH BROTHERS | 215.95 | 0 | 0 | 0
1414 | HOOGHLY | Electrical | Augmentation of Chiladangi Piped Water Supply Scheme under Pursurah Block , SM/15788 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chiladangi water supply scheme, T.W. No. II, Block: Pursura, District- Hooghly under Electrical Division, PHE Dte. | 3004_ED | 29/12/2021 | 90 | A.G. ENTERPRISE | 10.52 | 0 | 0 | 0
1415 | HOOGHLY | Hooghly Division | Augmentation of Chiladangi Piped Water Supply Scheme under Pursurah Block , SM/15788 | Augmentation | Material Requisition To Resource Division | 1385/16/Hug | 15/05/2023 | 0 | Resource Division | 0.31 | 0 | 0 | 0
1416 | HOOGHLY | Hooghly Division | Augmentation of Chiladangi Piped Water Supply Scheme under Pursurah Block , SM/15788 | Augmentation | AUGMENTATION of CHILADANGI Piped Water Supply Scheme with Extension of LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. Block-PURSURAH, District:- Hooghly[AUGMENTATION SCHEME] | 2413/HUG | 11/08/2023 | 599 | GHOSH BROTHERS | 215.95 | 0 | 0 | 65
1417 | HOOGHLY | Hooghly Division | Retrofitting Works for BAMANJOL PWSS for providing 1342 nos Functional Household Tap Connection(FHTC) , SM/06763 | Retrofitting | FHTC |  | 23/07/2021 | 0 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 18.51 | 0 | 0 | 0
1418 | HOOGHLY | Hooghly Division | Retrofitting Works for BAMANJOL PWSS for providing 1342 nos Functional Household Tap Connection(FHTC) , SM/06763 | Retrofitting | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto180 Mtr at BAMONJOL PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. [2nd Call of WBPHE/EE/45/HUG/2022-23, Sl No-16] | 1201/HUG | 26/04/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 12.43 | 12.03 | 96.81 | 0
1419 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/15800 | Augmentation | Material Requisition To Resource Division | 3004/17/Hug | 05/10/2023 | 0 | Resource Division | 35.98 | 0 | 0 | 0
1420 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/15800 | Augmentation | New Service connection quotation charges for ph-3 Bhastara pwss | 521 | 12/12/2023 | 0 | WBSEDCL | 3.8 | 0 | 0 | 0
1421 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/15800 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dhaniakhali water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | 833/ED | 14/02/2023 | 90 | A.G. ENTERPRISE | 21.49 | 2.48 | 89.56 | 59
1422 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/15800 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bhastara water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | 1630/ED | 11/04/2023 | 90 | M.S ENTERPRISE | 22.83 | 11.11 | 48.69 | 50
1423 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/15800 | Augmentation | Preparation of DPR for BHASTARA Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-DHANIAKHALI]. | 692/CH | 09/08/2024 | 7 | APEX ENGINEERING | 4.5 | 0 | 0 | 0
1424 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/15800 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement and Boundary Wall for Augmentation of BHASTARA Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.HE Dte. | 3316/HUG | 10/11/2023 | 45 | SUDIPTA DAS | 8.59 | 7.11 | 100 | 95
1425 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/15800 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Digra Arsenic PWSS 2. Charsundalpur Arsenic PWSS 3. Asanpur Arsenic PWSS 4. Polba (Retrofit) PWSS 5. Baastara PWSS 6. Bakulia PWSS | 211/CH | 29/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 50 | 45
1426 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/15800 | Augmentation | New Service connection quotation charges for ph-4 Bhastara pwss | 522 | 12/12/2023 | 0 | WBSEDCL | 3.73 | 0 | 0 | 0
1427 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/15800 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | 882/HUG | 27/03/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 13.09 | 100 | 65
1428 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/15800 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in BHASTARA GP of DHANIAKHALI Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. (Phase-II) | 315/CH | 21/02/2025 | 15 | JOY GURU ENTERPRISE | 3.4 | 0 | 0 | 0
1429 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/15800 | Augmentation | REPAIRING & RENOVATION OF SWITCH ROOM INCLUDING BOUNDARY WALL AT 2ND TW SITE OF BHASTARA WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURAH SUB-DIVISION UNDER HOOGHLY DIVISION, PHE DTE. | 128/CH | 29/01/2025 | 10 | M/S B N ENTERPRISE | 4.12 | 0 | 0 | 0
1430 | HOOGHLY | Electrical | SAMANTA KHANDA WATER SUPPLY SCHEME , SM/16127 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Samanta Khanda water supply scheme, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | 1241/ED | 06/03/2023 | 90 | R.M.D TRADING. | 22.84 | 0 | 0 | 0
1431 | HOOGHLY | Hooghly Division | SAMANTA KHANDA WATER SUPPLY SCHEME , SM/16127 | New | Material Requisition To Resource Division | 1234/26/Hug | 28/04/2023 | 0 | Resource Division | 51.53 | 0 | 0 | 0
1432 | HOOGHLY | Hooghly Division | SAMANTA KHANDA WATER SUPPLY SCHEME , SM/16127 | New | Material Requisition To Resource Division | 3057/57/Hug | 11/10/2023 | 0 | Resource Division | 17.57 | 0 | 0 | 0
1433 | HOOGHLY | Hooghly Division | SAMANTA KHANDA WATER SUPPLY SCHEME , SM/16127 | New | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at RADHABALLAVPUR Z-I, BENGAI, SAMANTAKHANDA and BHURKUNDA Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 724/HUG | 05/03/2024 | 60 | RUNA ENTERPRISE | 64.27 | 0 | 0 | 0
1434 | HOOGHLY | Hooghly Division | SAMANTA KHANDA WATER SUPPLY SCHEME , SM/16127 | New | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of SELAMPUR, BACHHANARI & SAMANTAKHANDA W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3169/HUG | 10/09/2024 | 45 | BALAJI UDDYOG | 48.46 | 0 | 0 | 0
1435 | HOOGHLY | Electrical | SAMANTA KHANDA WATER SUPPLY SCHEME , SM/16127 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SAMANTA KHANDA PIPED W/S SCHEME, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1163/ED | 14/06/2024 | 90 | PADMA ENGINEERING CO. | 10.74 | 0 | 0 | 0
1436 | HOOGHLY | Electrical | SAMANTA KHANDA WATER SUPPLY SCHEME , SM/16127 | New | Quotation of New Service Connection for Samanta Khanda w/s Scheme, PH No-I Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/16127) Application No-5004034170 Reference Id-503574968 | 814 | 28/02/2024 | 0 | WBSEDCL | 4.75 | 0 | 0 | 0
1437 | HOOGHLY | Hooghly Division | SAMANTA KHANDA WATER SUPPLY SCHEME , SM/16127 | New | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | 3190/HUG | 31/10/2023 | 609 | M/S PRITI ENTERPRISE | 4251.5 | 220.57 | 36.25 | 30
1438 | HOOGHLY | Hooghly Division | SAMANTA KHANDA WATER SUPPLY SCHEME , SM/16127 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 464/HUG | 20/02/2025 | 30 | TECHVISION | 6.59 | 0 | 0 | 0
1439 | HOOGHLY | Hooghly Division | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly , SM/15888 | New | Material Requisition To Resource Division | 3058/21/Hug | 11/10/2023 | 0 | Resource Division | 7.76 | 0 | 0 | 0
1440 | HOOGHLY | Hooghly Division | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly , SM/15888 | New | Material Requisition To Resource Division | 1235/7/Hug | 28/04/2023 | 0 | Resource Division | 3.7 | 0 | 0 | 0
1441 | HOOGHLY | Electrical | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly , SM/15888 | New | Quotation Bill for New Service Connection at Shibrambati W/S. Sch. TW-III | 520 | 11/12/2023 | 0 | WBSEDCL | 4.42 | 0 | 0 | 0
1442 | HOOGHLY | Electrical | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly , SM/15888 | New | Quotation Bill for New Service Connection at Sibrambati W/S. Sch.TW-I, Z-II | 378 | 25/10/2023 | 0 | WBSEDCL | 5.8 | 0 | 0 | 0
1443 | HOOGHLY | Electrical | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly , SM/15888 | New | Quotation for new service connection at Sibrambati W/s Sch. Zone - II, T/W No. - III,[SM/15888], under Singur CCC, WBSEDCL, Ref. Id. - 503666629, Dt. - 18-06-2024, Application No. - 5004236084 | 247 | 24/06/2024 | 0 | WBSEDCL | 9.51 | 0 | 0 | 0
1444 | HOOGHLY | Hooghly Division | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly , SM/15888 | New | SIBRAMBATI ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of Chandannagar Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | 937/HUG | 29/03/2023 | 270 | M/S R.M. CONSTRUCTION | 311.17 | 247.04 | 79.39 | 100
1445 | HOOGHLY | Electrical | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly , SM/15888 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Shibrambati water supply scheme, Zone-II, T.W. No. III, Block: Singur, District: Hooghly under Electrical Division, PHE Dte. | 339/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.36 | 0 | 0 | 90
1446 | HOOGHLY | Electrical | Source Augmentation of KISHORPUR Piped Water Supply Scheme under Khanakul-I Block , SM/15802 | Augmentation | Emergency replacement of burnt submersible pump-motor set by newly supplied pump-motor set, rewinding of the burnt submersible motor, replacement of voltage corrector and related works at Kishorpur w/s scheme, P.H No-I, Dist- Hooghly. | 495/HMSD | 02/03/2023 | 30 | SOMNATH ENTERPRISE | 3.58 | 3.32 | 100 | 100
1447 | HOOGHLY | Hooghly Division | Source Augmentation of KISHORPUR Piped Water Supply Scheme under Khanakul-I Block , SM/15802 | Augmentation | Material Requisition To Resource Division | 1263/9/Hug | 03/05/2023 | 0 | Resource Division | 5.69 | 0 | 0 | 0
1448 | HOOGHLY | Hooghly Division | Source Augmentation of KISHORPUR Piped Water Supply Scheme under Khanakul-I Block , SM/15802 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at KISHORPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | 1428/HUG | 17/05/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.53 | 11.28 | 100 | 99
1449 | HOOGHLY | Electrical | Source Augmentation of KISHORPUR Piped Water Supply Scheme under Khanakul-I Block , SM/15802 | Augmentation | Quotation Bill for New Service Connection at Kishorepur W/S. Sch. PH-III | 675 | 18/01/2024 | 0 | WBSEDCL | 4.48 | 0 | 0 | 0
1450 | HOOGHLY | Hooghly Division | Source Augmentation of KISHORPUR Piped Water Supply Scheme under Khanakul-I Block , SM/15802 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of KISHORPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 4152/HUG | 26/12/2024 | 90 | MS PRADIP KUMAR PAL | 17.87 | 0 | 0 | 0
1451 | HOOGHLY | Electrical | Source Augmentation of KISHORPUR Piped Water Supply Scheme under Khanakul-I Block , SM/15802 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kishorpur water supply scheme, T.W. No. I, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | 1617/ED | 11/04/2023 | 751 | M/S G P ENTERPRISE | 10.74 | 7.95 | 74.58 | 20
1452 | HOOGHLY | Hooghly Division | Augmentation of Gobindapur Water Supply Scheme , SM/16351 | Augmentation | Providing 360 nos Functional Household Tap Connection (FHTC) within the command area of GOBINDAPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte | 15/Hug | 04/01/2022 | 30 | SWASTIK ENTERPRISE | 14.91 | 14.8 | 100 | 0
1453 | HOOGHLY | Hooghly Division | Augmentation of Gobindapur Water Supply Scheme , SM/16351 | Augmentation | Material Requisition To Resource Division | 1385/42/Hug | 15/05/2023 | 0 | Resource Division | 1.39 | 0 | 0 | 0
1454 | HOOGHLY | Electrical | Augmentation of Gobindapur Water Supply Scheme , SM/16351 | Augmentation | Quotation Bill for for New Service Connection at Gobindopur W/S. Sch. | 427 | 17/11/2023 | 0 | WBSEDCL | 4.41 | 0 | 0 | 0
1455 | HOOGHLY | Hooghly Division | Augmentation of Gobindapur Water Supply Scheme , SM/16351 | Augmentation | Sinking of 3 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Gobindapur, Rajhato & Kamarpukur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 2038/HUG | 13/07/2023 | 30 | SPG ENTERPRISES | 48.51 | 0 | 0 | 70
1456 | HOOGHLY | Electrical | Augmentation of Gobindapur Water Supply Scheme , SM/16351 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gobindapur water supply scheme, T.W. No. II, Block: Khanakul-I, District - Hooghly under Electrical Division, PHE Dte. | 138/ED | 16/01/2024 | 90 | MUKHERJEE ART CENTRE | 10.7 | 0 | 0 | 0
1457 | HOOGHLY | Hooghly Division | Augmentation of Gobindapur Water Supply Scheme , SM/16351 | Augmentation | Renovation Work of R.C.C. Elevated Reservoir of GOBINDAPUR PWSS Under Arambagh Sub-Division Hooghly Division, P.H.E. Dte. | 2370/HUG | 10/09/2025 | 90 | M/S BIMAL DAS AND CO. | 10.05 | 0 | 0 | 0
1458 | HOOGHLY | Hooghly Division | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly , SM/15789 | New | Material Requisition To Resource Division | 1385/49/Hug | 15/05/2023 | 0 | Resource Division | 13.46 | 0 | 0 | 0
1459 | HOOGHLY | Hooghly Division | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly , SM/15789 | New | Material Requisition To Resource Division | 3057/22/Hug | 11/10/2023 | 0 | Resource Division | 13.46 | 0 | 0 | 0
1460 | HOOGHLY | Hooghly Division | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly , SM/15789 | New | Material Requisition To Resource Division | 1234/12/Hug | 28/04/2023 | 0 | Resource Division | 43.14 | 0 | 0 | 0
1461 | HOOGHLY | Electrical | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly , SM/15789 | New | Quotation Bill for New Service Connectio at Bhalia W/S. Sch. Z-I, TW-IV | 396 | 06/11/2023 | 0 | WBSEDCL | 4.24 | 0 | 0 | 0
1462 | HOOGHLY | Electrical | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly , SM/15789 | New | "Quotation Bill for New Service Connection at Bhalia W/S. Sch. Z-I" | 401 | 09/11/2023 | 0 | WBSEDCL | 4.24 | 0 | 0 | 0
1463 | HOOGHLY | Electrical | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly , SM/15789 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BHALIA PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1204/ED | 14/06/2024 | 90 | C.M.S. ENGINEERING CONCERN | 10.95 | 0 | 0 | 0
1464 | HOOGHLY | Electrical | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly , SM/15789 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhalia (Zone-I) water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 1625/ED | 11/04/2023 | 90 | C.M.S. ENGINEERING CONCERN | 22.04 | 22.02 | 100 | 30
1465 | HOOGHLY | Hooghly Division | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly , SM/15789 | New | BHALIA ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site, under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] [2nd Call of WBPHE/EE/53/HUG/2022-23(Sl No. 2)] | 2079/HUG | 18/07/2023 | 898 | PRASUN ENTERPRISE (PRASUN BISWAS) | 496.11 | 93.78 | 18.9 | 30
1466 | HOOGHLY | Electrical | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block , SM/16124 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARANDI PIPED W/S SCHEME, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1450/ED | 25/07/2024 | 90 | MOITRA ENGINEERING CO. | 11.08 | 0 | 0 | 0
1467 | HOOGHLY | Hooghly Division | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block , SM/16124 | Augmentation | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at SAIDPUR ZONE-II (1No.), SAIDPUR ZONE-I (2Nos.) ARANDI (1 No.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3435/HUG | 03/10/2024 | 90 | T.K. INTERNATIONAL | 47.2 | 0 | 0 | 0
1468 | HOOGHLY | Hooghly Division | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block , SM/16124 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of ARANDI PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 4080/HUG | 19/12/2024 | 90 | SRI KRISHNA ENTERPRISE | 17.15 | 0 | 0 | 0
1469 | HOOGHLY | Hooghly Division | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block , SM/16124 | Augmentation | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site at ARANDI , BATANOL Zone-I , GOPALBATI W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3667/HUG | 13/11/2024 | 45 | DEV AND COMPANY | 31.66 | 0 | 0 | 0
1470 | HOOGHLY | Hooghly Division | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block , SM/16124 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of ARANDI Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | 1445/HUG | 18/05/2023 | 675 | SAKSHI ENTERPRISE | 11.81 | 0 | 0 | 40
1471 | HOOGHLY | Hooghly Division | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block , SM/16124 | Augmentation | Restoration of damaged pipe line of Arandi water supply scheme due to construction of drain by Arandi-I G.P. under Arambagh Sub-Division, P.H.E. Dte. (PART-A) [Block-Arambagh] | 287/Arg | 14/03/2024 | 15 | TITAS CONSTRUCTION | 0.96 | 0 | 0 | 0
1472 | HOOGHLY | Hooghly Division | Source Augmentation of ARANDI Piped Water Supply Scheme under Arambag Block , SM/16124 | Augmentation | Restoration of damaged pipe line of Arandi water supply scheme due to construction of drain by Arandi-I G.P. under Arambagh Sub-Division, P.H.E. Dte. (PART-B) [Block-Arambagh] | 288/Arg | 14/03/2024 | 15 | TITAS CONSTRUCTION | 0.84 | 0 | 0 | 0
1473 | HOOGHLY | Hooghly Division | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18095 | New | Material Requisition To Resource Division | 1386/42/Hug | 15/05/2023 | 0 | Resource Division | 2.94 | 0 | 0 | 0
1474 | HOOGHLY | Hooghly Division | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18095 | New | Material Requisition To Resource Division | 3004/14/Hug | 05/10/2023 | 0 | Resource Division | 2.71 | 0 | 0 | 0
1475 | HOOGHLY | Hooghly Division | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18095 | New | Material Requisition To Resource Division | 3059/15/Hug | 11/10/2023 | 0 | Resource Division | 2.94 | 0 | 0 | 0
1476 | HOOGHLY | Electrical | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18095 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Rajhat (for uncovered area) water supply scheme, T.W. No. I, Block: Polba Dadpur, District - Hooghly under Electrical Division, PHE Dte. | 1930/ED | 15/05/2023 | 90 | MOITRA ENGINEERING CO. | 11.6 | 11.3 | 97.43 | 90
1477 | HOOGHLY | Electrical | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18095 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RAJHAT UTTAR PROPOSED TW Site under Chirnurah Sub Division, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 459/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 7.16 | 73.86 | 90
1478 | HOOGHLY | Electrical | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18095 | New | Quotation Bill for New Service Connection at Rajhat Dakshinpara W/S. Sch. TW-I | 519 | 11/12/2023 | 0 | WBSEDCL | 10.03 | 0 | 0 | 0
1479 | HOOGHLY | Electrical | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18095 | New | Quotation for new service connection at Rajhat(Uncovered)[Rajhat Uttar] W/S Sch.[SM/18095], T/W No. - I, Mahashay Para, Dist. - Hooghly under Bandel CCC, WBSEDCL, Ref. Id. - 503599474, Dt. - 22-03-2024, Application No. - 5004078306 | 16 | 04/04/2024 | 0 | WBSEDCL | 11.27 | 0 | 0 | 0
1480 | HOOGHLY | Hooghly Division | RAJHAT PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18095 | New | RAJHAT Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. Block Polba-Dadpur, District:- Hooghly [NEW SCHEME] | 2078/HUG | 18/07/2023 | 741 | TAPAS ADHYA | 118.43 | 97.58 | 82.39 | 80
1481 | HOOGHLY | Hooghly Division | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Dighir Water Supply Scheme under Dhaniakhali Block , SM/18106 | Retrofitting | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Dighir PWSS 2. Gopinagar PWSS 3. Mandra PWSS 4. Jayramabti PWSS 5. Gurap PWSS 6. Hasampur PWSS | 204/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 100 | 50
1482 | HOOGHLY | Hooghly Division | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Dighir Water Supply Scheme under Dhaniakhali Block , SM/18106 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of DIGHIR, HASAMPUR, CHERAGRAM, GURAP PWSS under DHANIAKHALI Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | 323/HUG | 05/02/2025 | 25 | SWARNA ENTERPRISE | 8.63 | 0 | 0 | 0
1483 | HOOGHLY | Hooghly Division | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Gopinagar Water Supply Scheme Under Dhaniakhali Block , SM/18109 | Retrofitting | Providing FHTC in rest out portion of at Radhanagar of Gopinagar PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | 292/CH | 15/03/2024 | 7 | RAJMAHAL ENTERPRISE | 0.99 | 0.93 | 100 | 100
1484 | HOOGHLY | Hooghly Division | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Gopinagar Water Supply Scheme Under Dhaniakhali Block , SM/18109 | Retrofitting | Providing FHTC in rest out portion of at Gopinagar of Gopinagar PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | 291/CH | 15/03/2024 | 7 | RAJMAHAL ENTERPRISE | 0.99 | 0.93 | 100 | 100
1485 | HOOGHLY | Hooghly Division | GROUND WATER BASED GANDERPUKUR PIPED W/S SCHEME , SM/16651 | New | Material Requisition To Resource Division | 1235/10/Hug | 28/04/2023 | 0 | Resource Division | 15.57 | 0 | 0 | 0
1486 | HOOGHLY | Hooghly Division | GROUND WATER BASED GANDERPUKUR PIPED W/S SCHEME , SM/16651 | New | Material Requisition To Resource Division | 3058/16/Hug | 11/10/2023 | 0 | Resource Division | 8.67 | 0 | 0 | 0
1487 | HOOGHLY | Electrical | GROUND WATER BASED GANDERPUKUR PIPED W/S SCHEME , SM/16651 | New | Quotation for new service connection at Ganderpukur W/S Sch. , T/W No. - II, Block- Singur, Dt. - Hooghly | 347 | 11/10/2023 | 0 | WBSEDCL | 2.39 | 0 | 0 | 0
1488 | HOOGHLY | Electrical | GROUND WATER BASED GANDERPUKUR PIPED W/S SCHEME , SM/16651 | New | Quotation for new service connection at Ganderpukur W/S Sch., T/W No. - I, Block - Singur, Dt. - Hooghly | 339 | 10/10/2023 | 0 | WBSEDCL | 0.64 | 0 | 0 | 0
1489 | HOOGHLY | Hooghly Division | GROUND WATER BASED GANDERPUKUR PIPED W/S SCHEME , SM/16651 | New | GANDERPUKUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub-Division Block-SINGUR, District:- Hooghly [NEW SCHEME] | 1681/HUG | 08/06/2023 | 664 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 357.8 | 201.4 | 56.29 | 85
1490 | HOOGHLY | Electrical | GROUND WATER BASED GANDERPUKUR PIPED W/S SCHEME , SM/16651 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ganderpukur water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | 1727/ED | 19/04/2023 | 90 | M/S DAS ENTERPRISE | 21.05 | 20.98 | 100 | 49
1491 | HOOGHLY | Hooghly Division | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly , SM/17629 | New | Material Requisition To Resource Division | 1235/8/Hug | 28/04/2023 | 0 | Resource Division | 23.33 | 0 | 0 | 0
1492 | HOOGHLY | Hooghly Division | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly , SM/17629 | New | Material Requisition To Resource Division | 3058/11/Hug | 11/10/2023 | 0 | Resource Division | 5.75 | 0 | 0 | 0
1493 | HOOGHLY | Hooghly Division | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly , SM/17629 | New | Material Requisition To Resource Division | 1383/7/Hug | 15/05/2023 | 0 | Resource Division | 5.75 | 0 | 0 | 0
1494 | HOOGHLY | Electrical | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly , SM/17629 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bainchipota (Zone-II) water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | 1732/ED | 19/04/2023 | 90 | BINAPANI ENTERPRISE | 20.52 | 6.05 | 29.49 | 30
1495 | HOOGHLY | Hooghly Division | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly , SM/17629 | New | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Bainchipota (Zone-2) 1st T/W site & Bainchipota (Zone-2) 2nd T/W site under Chandannagar Sub-Division PHE Dte. | 925/Chan | 05/11/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.97 | 0.93 | 100 | 100
1496 | HOOGHLY | Electrical | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly , SM/17629 | New | Quotation for new service connection at Bainchipota(Zone- II) water supply Scheme [SM/17629], T/W No. - I, Block - Singur, under Nasibpur CCC, WBSEDCL, Ref. No. - 503589159, Dt. - 07-03-2024, Application No. - 5004058510 | 875 | 13/03/2024 | 0 | WBSEDCL | 9.63 | 0 | 0 | 0
1497 | HOOGHLY | Electrical | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly , SM/17629 | New | Quotation for new service connection at Bainchipota(Zone- II) water supply Scheme [SM/17629], T/W No. - II, Block - Singur, under Nasibpur CCC, WBSEDCL, Ref. No. - 503589664, Dt. - 07-03-2024, Application No. - 5004059136 | 874 | 13/03/2024 | 0 | WBSEDCL | 0.64 | 0 | 0 | 0
1498 | HOOGHLY | Hooghly Division | Bainchipota (Zone-II) Piped Water Supply Scheme, Block- Singur, District- Hooghly , SM/17629 | New | BAINCHIPOTA ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block, District:- Hooghly [NEW SCHEME] | 2365/HUG | 08/08/2023 | 877 | RAJ CONSTRUCTION | 300.28 | 74.12 | 24.68 | 60
1499 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11461 | Augmentation | Providing 225 nos Functional Household Tap Connection (FHTC) within the command area of Lakshmipur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 1995/Hug | 12/11/2021 | 30 | S. B. CONSTRUCTION | 11.36 | 4.84 | 70.59 | 100
1500 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11461 | Augmentation | Providing 225 nos Functional Household Tap Connection (FHTC) within the command area of LAKSHMIPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | 17/Hug | 04/01/2022 | 30 | S.M. ENTERPRISE | 8.23 | 8.47 | 100 | 0
1501 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11461 | Augmentation | Preparation of DPR for Augmentation of Lakshmipur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I]. | 364/Arg | 19/05/2022 | 30 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 3.24 | 3.2 | 100 | 0
1502 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11461 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 235 mtrs. Depth) by utilising Departmental machineries for Lakshmipur W/S Scheme (TW-I & II), Goghat-I block under hooghly District, CDD PHE Dte. | 18/CDD | 04/04/2023 | 30 | CHANDA ENTERPRISE | 30.35 | 12.81 | 42.2 | 42
1503 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11461 | Augmentation | ADDITIONAL WORK FOR CONSTRUCTION OF TUBE WELL AT LAKSHMIPUR PWSS TW-I, ARAMBAG BLOCK, UNDER CDD, PHE DTE. | 66/CMSD-I | 14/03/2023 | 10 | CHANDA ENTERPRISE | 0.86 | 0.86 | 100 | 100
1504 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11461 | Augmentation | Material Requisition To Resource Division | 2209/2/Hug | 30/09/2022 | 0 | Resource Division | 30.8 | 0 | 0 | 0
1505 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11461 | Augmentation | Material Requisition To Resource Division | 127/15/Hug | 13/01/2023 | 0 | Resource Division | 7.19 | 0 | 0 | 0
1506 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11461 | Augmentation | Quotation of New service Connection for Lakshmipur W/s Scheme, TW No-4, Block-Goghat-I, Dist-hooghly Under ED,PHE Dte | 150 | 01/08/2023 | 0 | WBSEDCL | 2.69 | 0 | 0 | 0
1507 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11461 | Augmentation | Quotation of New Service Connection for Lakshmipur w/s scheme,TW No-3 District-Hooghly under ED,PHE Dte | 118 | 20/07/2023 | 0 | WBSEDCL | 3.52 | 0 | 0 | 0
1508 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11461 | Augmentation | Augmentation of LAKSHMIPUR Water Supply Scheme with Laying of Distribution System at Goghat -I Block under Arambagh Sub-Division of Hooghly Division, PHE Dte. Hooghly. Sl no - 04 | 1800/HUG | 01/09/2022 | 45 | M/S RAJKUMAR KHAN | 112.72 | 107.91 | 100 | 96
1509 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11461 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Lakshmipur water supply scheme TW No I and II Block Goghat I District Hooghly under ED PHED. | 849/ED | 14/02/2023 | 90 | PRADIP KUMAR DHABAL | 21.51 | 21.46 | 100 | 40
1510 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11461 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system, For AUGMENTATION OF of LAKSHMIPUR W/S Scheme under ARAMBAGH Sub - Division P.H.E. Dte. | 1447/HUG | 18/05/2023 | 30 | M/S KHAMRUI CONSTRUCTION | 31.29 | 28.32 | 100 | 100
1511 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11461 | Augmentation | Repairing Of Switch Room, Boundary wall of T.W-1 & T.W-2 for Augemntation Of LAKSHMIPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | 2439/HUG | 12/08/2023 | 45 | SADHUKHAN ENTERPRISE | 9.47 | 7.32 | 100 | 95
1512 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR LAKSHMIPUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11461 | Augmentation | Loading unloading & Shifting of Drilling Accessories , Supporting Vehicles along with Rig Machine JOHN DR 1500-I from Lakshmipur PWSS , Block ¿ Goghat-I, Hooghly District to PANCHLA Store Howrah under CDD, PHE Dte. | 170/CMSD-II(D) | 30/06/2023 | 15 | UTTAM KUMAR CHATTERJEE | 0.51 | 0.46 | 100 | 100
1513 | HOOGHLY | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) , SM/17721 | New | Material Requisition To Resource Division | 1234/27/Hug | 28/04/2023 | 0 | Resource Division | 192.54 | 0 | 0 | 0
1514 | HOOGHLY | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) , SM/17721 | New | Material Requisition To Resource Division | 1385/50/Hug | 15/05/2023 | 0 | Resource Division | 17.48 | 0 | 0 | 0
1515 | HOOGHLY | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) , SM/17721 | New | Material Requisition To Resource Division | 3057/21/Hug | 11/10/2023 | 0 | Resource Division | 17.48 | 0 | 0 | 0
1516 | HOOGHLY | Electrical | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) , SM/17721 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BHURKUNDA PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1164/ED | 14/06/2024 | 90 | H.K.DAS & CO. | 10.89 | 0 | 0 | 0
1517 | HOOGHLY | Electrical | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) , SM/17721 | New | Quotation of New Service Connection for Bhurkunda w/s scheme, Zone-I,PH No-I Block-Goghat-II,under Electrical Division,PHE Dte.(SM/17721) Application No-5004243748 Reference Id-503669340. | 230 | 20/06/2024 | 0 | WBSEDCL | 3.15 | 0 | 0 | 0
1518 | HOOGHLY | Electrical | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) , SM/17721 | New | Quotation of New Service Connection for Bhurkunda w/s Scheme, Zone-I,PH No-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/17721) Application No-5004190543 Reference Id-503647430. | 149 | 22/05/2024 | 0 | WBSEDCL | 3.63 | 0 | 0 | 0
1519 | HOOGHLY | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) , SM/17721 | New | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | 3190/HUG | 31/10/2023 | 609 | M/S PRITI ENTERPRISE | 4251.5 | 155.48 | 27.9 | 30
1520 | HOOGHLY | Hooghly Division | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) , SM/17721 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 464/HUG | 20/02/2025 | 30 | TECHVISION | 6.59 | 0 | 0 | 0
1521 | HOOGHLY | Electrical | BHURKUNDA WATER SUPPLY SCHEME (ZONE-I) , SM/17721 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhurkunda water supply scheme, Zone-I, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | 1793/ED | 24/04/2023 | 668 | H.K.DAS & CO. | 22.39 | 0 | 0 | 40
1522 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ENAYETPUR WATER SUPPLY SCHEME. , SM/07438 | Retrofitting | Material Requisition To Resource Division | 2686/7/Hug | 01/12/2022 | 0 | Resource Division | 0.33 | 0 | 0 | 0
1523 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ENAYETPUR WATER SUPPLY SCHEME. , SM/07438 | Retrofitting | Material Requisition To Resource Division | 2098/9/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0 | 0
1524 | HOOGHLY | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18929 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at HARADITYA (2Nos.),GOURHATI (2Nos.),MAINAN (1No.)W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3476/HUG | 29/11/2023 | 45 | SPG ENTERPRISES | 87.88 | 13.29 | 75.6 | 20
1525 | HOOGHLY | Electrical | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18929 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAINAN PIPED W/S SCHEME, T.W. No. III & IV, Block: Khanakul-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1454/ED | 25/07/2024 | 90 | SUDIKSHA CONSTRUCTION | 22.11 | 0 | 0 | 0
1526 | HOOGHLY | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18929 | Augmentation | Protection works and other allied works at Head Work Site of MAINAN Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte | 4054/HUG | 19/12/2024 | 90 | DILIP KUMAR GHOSH | 22.94 | 0 | 0 | 0
1527 | HOOGHLY | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18929 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of MAINAN PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 4085/HUG | 19/12/2024 | 90 | M/S S & P CONSTRUCTION | 11.13 | 0 | 0 | 0
1528 | HOOGHLY | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18929 | Augmentation | Providing 1200 nos Functional Household Tap Connection (FHTC) within the command area of Mainan Water Supply Scheme at Mainan Mouza under Arambag Sub-Division of Hooghly Division P.H.E Dte | 2210/Hug | 14/12/2021 | 60 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 56 | 21.49 | 100 | 95
1529 | HOOGHLY | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18929 | Augmentation | Construction of 3.6 m X 3.00 m Switch Room with Additional Plinth Height, without Sanitary and Water Supply arrangement at 3rd TW Site of DIHI BAGNAN W/S Scheme under Arambag Sub-Division P.H.E. Dte. | 53/Arg | 31/01/2022 | 45 | ANNAPURNA CONSTRUCTION | 3.54 | 0 | 0 | 95
1530 | HOOGHLY | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18929 | Augmentation | Laying of pipe line for left out portion within command area of Bhunia Para, Dakshin Khan Para, Das Para, Ghorui Para, Mainan Pry School habitation of Mainan Village under MAINAN Water Supply Scheme to facilate the FHTC under JALASWAPNA Programme of Arambagh Sub-Division, P.H.E. Dte., Dist-. Hooghly. [Block-Khanakul-I]. (Part-A) | 608/Arg | 31/08/2022 | 30 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 4.92 | 4.92 | 100 | 95
1531 | HOOGHLY | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18929 | Augmentation | Laying of pipe line for left out portion within command area of Maity Para, Maj Mahissya Para, Mallik Para, Mete Para habitation of Mainan Village under MAINAN Water Supply Scheme to facilate the FHTC under JALASWAPNA Programme of Arambagh Sub-Division, P.H.E. Dte., Dist-. Hooghly. [Block-Khanakul-I]. (Part-B) | 609/Arg | 31/08/2022 | 30 | SARADA ENGINEERS CO OPERATIVE AND CONSTRUCTION SOCIETY LTD. | 4.9 | 4.9 | 100 | 95
1532 | HOOGHLY | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18929 | Augmentation | Laying of pipe line for left out portion within command area of Paschim Bha Para, Sk Para, Uttar Bera Para, Uttar Khan Para habitation of Mainan Village under MAINAN Water Supply Scheme to facilate the FHTC under JALASWAPNA Programme of Arambagh Sub-Division, P.H.E. Dte., Dist-. Hooghly. [Block-Khanakul-I]. (Part-D) | 611/Arg | 31/08/2022 | 30 | SUSANTA KUMAR | 4.75 | 4.75 | 100 | 95
1533 | HOOGHLY | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18929 | Augmentation | Laying of pipe line for left out portion within command area of Middya Para, Panchtik Middya Para, Panja Para, Paschim Bandh habitation of Mainan Village under MAINAN Water Supply Scheme to facilate the FHTC under JALASWAPNA Programme of Arambagh Sub-Division, P.H.E. Dte., Dist-. Hooghly. [Block-Khanakul-I]. (Part-C) | 610/Arg | 31/08/2022 | 30 | R.S. CONSTRUCTION & CONSULTANCY | 4.9 | 4.9 | 100 | 95
1534 | HOOGHLY | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18929 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at MAINAN(1No.),CHIKRAND ZONE-I (1No.),CHIKRAND ZONE-II (1No.) ,CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3388/HUG | 22/11/2023 | 45 | SPG ENTERPRISES | 87.88 | 12.83 | 100 | 100
1535 | HOOGHLY | Electrical | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18929 | Augmentation | Quotation of New Service Connection for Mainan w/s Scheme,PH No-4 Block-Khanakul-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18929) Application No-5004288912 Reference Id-503688427. | 293 | 15/07/2024 | 0 | WBSEDCL | 7.06 | 0 | 0 | 0
1536 | HOOGHLY | Electrical | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18929 | Augmentation | Quotation of New Service Connection for Mainan w/s Scheme,PH No-III Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/18929) Application No-5004320142 Reference Id- 503705441 | 336 | 30/07/2024 | 0 | WBSEDCL | 8.26 | 0 | 0 | 0
1537 | HOOGHLY | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18929 | Augmentation | Construction of 6 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at HARADITYA (2Nos.), GOURHATI (2Nos.), MAINAN (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3312/HUG | 10/11/2023 | 546 | DILIP KUMAR GHOSH | 70.72 | 0 | 0 | 32
1538 | HOOGHLY | Hooghly Division | Bhalia (Zone-II) Piped Water Supply Scheme, Block- Arambagh, District-Hooghly , SM/19014 | New | Material Requisition To Resource Division | 3057/25/Hug | 11/10/2023 | 0 | Resource Division | 2.06 | 0 | 0 | 0
1539 | HOOGHLY | Electrical | Bhalia (Zone-II) Piped Water Supply Scheme, Block- Arambagh, District-Hooghly , SM/19014 | New | Quotation of New Service Connection for Bhalia w/s Scheme,Zone-II,PH No-I Block-Arambag,Dist-Hooghly under Electrical Division,PHE Dte.(SM/19014) Application No-5004416386 Reference Id-503753715 | 478 | 01/10/2024 | 0 | WBSEDCL | 6.49 | 0 | 0 | 0
1540 | HOOGHLY | Hooghly Division | Bhalia (Zone-II) Piped Water Supply Scheme, Block- Arambagh, District-Hooghly , SM/19014 | New | BHALIA ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] | 3181/HUG | 30/10/2023 | 518 | TANISA ENTERPRISE | 96.9 | 36.01 | 37.17 | 20
1541 | HOOGHLY | Electrical | Bhalia (Zone-II) Piped Water Supply Scheme, Block- Arambagh, District-Hooghly , SM/19014 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhalia (Zone-II) water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 115/ED | 15/01/2024 | 502 | A.G. ENTERPRISE | 20.49 | 0 | 0 | 20
1542 | HOOGHLY | Hooghly Division | Hayatpur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly. , SM/18345 | New | Material Requisition To Resource Division | 3057/47/Hug | 11/10/2023 | 0 | Resource Division | 19.24 | 0 | 0 | 0
1543 | HOOGHLY | Hooghly Division | Hayatpur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly. , SM/18345 | New | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at HAYATPUR and ARUNDA Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 723/HUG | 05/03/2024 | 60 | SPG ENTERPRISES | 64.34 | 28.87 | 89.74 | 50
1544 | HOOGHLY | Electrical | Hayatpur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly. , SM/18345 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for HAYATPUR PIPED W/S SCHEME, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1177/ED | 14/06/2024 | 90 | M/S G P ENTERPRISE | 10.74 | 0 | 0 | 0
1545 | HOOGHLY | Electrical | Hayatpur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly. , SM/18345 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for HAYATPUR PIPED W/S SCHEME, T.W. No. IV, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1178/ED | 14/06/2024 | 90 | M/S. UTTAM KUMAR CHATTERJEE. | 10.74 | 0 | 0 | 0
1546 | HOOGHLY | Electrical | Hayatpur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly. , SM/18345 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hayatpur water supply scheme, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | 3161/ED | 27/07/2023 | 614 | GLACIER ENGINEERING CO. | 21.83 | 0 | 0 | 50
1547 | HOOGHLY | Hooghly Division | Hayatpur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly. , SM/18345 | New | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 397.14 | 57.64 | 50
1548 | HOOGHLY | Hooghly Division | Hayatpur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly. , SM/18345 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0 | 0
1549 | HOOGHLY | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK , SM/18644 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bakulia water supply scheme, T.W. No. I & II, Block: Balagarh, District- Hooghly under Electrical Division, PHE Dte. | 3597/ED | 28/08/2023 | 90 | R.M.D TRADING. | 21.89 | 0 | 0 | 0
1550 | HOOGHLY | Hooghly Division | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK , SM/18644 | Augmentation | Material Requisition To Resource Division | 226/1/Hug | 24/01/2023 | 0 | Resource Division | 178.88 | 0 | 0 | 0
1551 | HOOGHLY | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK , SM/18644 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. | 2829/HMSD | 30/10/2023 | 182 | ARINDAM AUDDY | 0.86 | 0.16 | 62.18 | 15
1552 | HOOGHLY | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK , SM/18644 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. | 2404/HMSD | 26/04/2024 | 153 | ARINDAM AUDDY | 0.73 | 0.74 | 101.93 | 0
1553 | HOOGHLY | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK , SM/18644 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. | 2829_/HMSD | 30/10/2023 | 182 | ARINDAM AUDDY | 0.86 | 0 | 0 | 0
1554 | HOOGHLY | Hooghly Division | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK , SM/18644 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at SHIBRAI(2NOS.), SHANKHANAGAR CHAK BANSBERIA(2NOS.), BAKULIA ZONE-I(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. [3rd Call of WBPHE/EE/77/HUG/2022-23, Sl No-2] | 1618/HUG | 02/06/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 72.85 | 24.5 | 100 | 65
1555 | HOOGHLY | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK , SM/18644 | Augmentation | Supply of Fuel of 1(One) no Diesel luxury Taxi on contract Carriage for the Office of the Assistant Engineer Howrah Mechanical Sub Division PHE Dte for the Month of April 2024. | 154 | 28/05/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
1556 | HOOGHLY | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK , SM/18644 | Augmentation | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of SEPTEMBER,2024 | 546 | 30/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.12 | 0 | 0 | 0
1557 | HOOGHLY | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK , SM/18644 | Augmentation | Quotation of New Service Connection for Bakulia w/s Scheme,PH No-IV under Electrical Division,PHE Dte.(SM/18644). Application No-5004111585. Reference Id-503617124. | 79 | 19/04/2024 | 0 | WBSEDCL | 7.52 | 0 | 0 | 0
1558 | HOOGHLY | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK , SM/18644 | Augmentation | Quotation of New Service Connection for Bakulia w/s Scheme,PH No-III under Electrical Division,PHE Dte.(SM/18644). Application No-5004112076. Reference Id-503617154. | 78 | 19/04/2024 | 0 | WBSEDCL | 19.66 | 0 | 0 | 0
1559 | HOOGHLY | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK , SM/18644 | Augmentation | Fuel Bill for Hiring of 1no Diesel Luxury Taxi on Contract Carriage for the Office of the Assistant Engineer Howrah Mechanical Sub Division,PHE Dte for the Month of September 2024 | 532 | 28/10/2024 | 0 | ARINDAM AUDDY | 0.07 | 0 | 0 | 0
1560 | HOOGHLY | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK , SM/18644 | Augmentation | Fuel Bill for Hiring of 1no Diesel Luxury Taxi on Contract Carriage for the Office of the Assistant Engineer Howrah Mechanical Sub Division,PHE Dte for the Month of September 2024. | 534 | 28/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.18 | 0 | 0 | 0
1561 | HOOGHLY | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK , SM/18644 | Augmentation | Supply of Fuel for 1(One) no. Diesel Luxury Taxi on Contract Carriage for the Office of the Assistant Engineer,Howrah mechanical Sub Division,PHE Dte for the Month of July 2024. | 413 | 22/08/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
1562 | HOOGHLY | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK , SM/18644 | Augmentation | Supply of Fuel for 1(One) no Diesel Luxury Taxi on Contract Carriage for the Office of the Assistant Engineer Howrah Mechanical Sub Division PHE DTe. for the Month of May 2024. Car No-WB 04H 0517 | 226 | 18/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
1563 | HOOGHLY | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK , SM/18644 | Augmentation | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte for the Month of August 2024. Car No. WB-04H-0517 From 01.08.2024 to 31.08.2024 | 467 | 01/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
1564 | HOOGHLY | Electrical | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK , SM/18644 | Augmentation | Supply of Fuel for 1(one) no Diesel Luxury taxi on Contract Carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte for the Month of June 2024. | 283 | 09/07/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
1565 | HOOGHLY | Hooghly Division | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK , SM/18644 | Augmentation | Repairing & Renovation of Switch Room & Store Room at Head Works Site of Bakulia Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 484/CH | 04/04/2025 | 10 | MAA BUNAMATA ENTERPRISE | 4.07 | 0 | 0 | 100
1566 | HOOGHLY | Hooghly Division | AUGMENTATION OF BAKULIA PIPED WATER SUPPLY SCHEME UNDER BALAGARH BLOCK , SM/18644 | Augmentation | Repairing & Renovation of Boundary Wall and Land Development at H/W Site of Bakulia Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 294/CH | 20/02/2025 | 29 | MAA BUNAMATA ENTERPRISE | 4.78 | 0 | 0 | 100
1567 | HOOGHLY | Electrical | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly , SM/18646 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Garmandaran (Zone-I) water supply scheme, T.W. No. III & IV, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | 3449/ED | 11/08/2023 | 90 | AMIT DAS | 21.46 | 0 | 0 | 0
1568 | HOOGHLY | Hooghly Division | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly , SM/18646 | New | Material Requisition To Resource Division | 3057/54/Hug | 11/10/2023 | 0 | Resource Division | 19.35 | 0 | 0 | 0
1569 | HOOGHLY | Hooghly Division | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly , SM/18646 | New | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of PUKURIA, GARMANDARAN Zone-I , GARMANDARAN Zone -II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3781/HUG | 25/11/2024 | 60 | KAJAL DEY | 55.4 | 0 | 0 | 0
1570 | HOOGHLY | Electrical | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly , SM/18646 | New | Quotation of New Service Connection for Garmandaran w/s Scheme,Zone-I,PH No-I Block-Goghat-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18646) Application No-5004423599 Reference Id-503761602 | 508 | 21/10/2024 | 0 | WBSEDCL | 4.87 | 0 | 0 | 0
1571 | HOOGHLY | Electrical | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly , SM/18646 | New | Quotation of New Service Connection for Garmandaran w/s Scheme,Zone-I,PH No-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/18646) Application No-5004191479 Reference Id-503647821. | 179 | 30/05/2024 | 0 | WBSEDCL | 3.9 | 0 | 0 | 0
1572 | HOOGHLY | Electrical | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly , SM/18646 | New | Quotation of New Service Connection For Garmandaran w/s Scheme,Zone-I,PH No-III Block-Goghat-II Dist-Hooghly under Electrical division,PHE Dte.(SM/18646) Application No-5004431289 Reference Id-503764743 | 516 | 21/10/2024 | 0 | WBSEDCL | 4.71 | 0 | 0 | 0
1573 | HOOGHLY | Hooghly Division | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly , SM/18646 | New | GARMANDARAN ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-II Block of Arambag Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | 2336/HUG | 07/08/2023 | 784 | KHAN ENTERPRISE | 678.8 | 0 | 0 | 75
1574 | HOOGHLY | Electrical | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly , SM/18646 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Garmandaran (Zone-I) water supply scheme, T.W. No. I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | 3599/ED | 28/08/2023 | 673 | UNITED TRADERS | 21.47 | 0 | 0 | 40
1575 | HOOGHLY | Hooghly Division | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly , SM/18646 | New | Sinking of 4 nos. tube-well by (300 X 200 mm) D.R. Rig method at SELAMPUR Z-I, SANTIPUR Z-I, SELAMPUR Z-II and GARMANDARAN Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 725/HUG | 05/03/2024 | 667 | AUXILIARY TUBEWELL DRILLERS | 64.32 | 13.98 | 86.97 | 70
1576 | HOOGHLY | Hooghly Division | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly , SM/18646 | New | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GARMANDARAN Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 3657/HUG | 13/11/2024 | 90 | ASHA ENTERPRISE | 16.14 | 0 | 0 | 0
1577 | HOOGHLY | Hooghly Division | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly , SM/18646 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) RAGHUBATI PWSS- 2no¿s (2) GANESHBATI PWSS- 1 no¿s (3) BENGAI PWSS- 1 no¿s (4) BHURKUNDA PWSS(Z-I)- 1no¿s (5) GARMANDARAN (Z-I)- 4 no¿s, (6) GARMANDARAN PWSS (Z-II)- 4 no¿s, (7) SAMANTAKHANDA PWSS -1 no¿s | 1148/Arg | 10/12/2024 | 31 | TITAS CONSTRUCTION | 0.98 | 0 | 0 | 0
1578 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DHAMAITIKAR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18978 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at DHAMAITIKAR (2Nos.), JAYRAMBATI (2 Nos.), DEPARA (1 Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3725/HUG | 18/12/2023 | 60 | BIMAL KUMAR HALDER | 59.73 | 0 | 0 | 0
1579 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF DHAMAITIKAR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18978 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DHAMAITIKAR PIPED W/S SCHEME Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4501/ED | 23/11/2023 | 678 | S.G.-ENTERPRISE | 21.5 | 0 | 0 | 45
1580 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DHAMAITIKAR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18978 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at DHAMAITIKAR (2Nos.), GUPTIPARA (1No.), ABDULPUR (1 No.), DEPARA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3385/HUG | 22/11/2023 | 628 | OSMAN SEKH | 87.83 | 34.59 | 98.46 | 40
1581 | HOOGHLY | Electrical | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block , SM/18958 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bachhanari water supply scheme, T.W. No. III, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 553_ED | 22/03/2022 | 90 | S.M. ELECTRICALS | 6.05 | 6.05 | 100 | 50
1582 | HOOGHLY | Electrical | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block , SM/18958 | Augmentation | Supply delivery and installation of voltage correcting device and other allied works for Bachhanari w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. | 659/HMSD | 04/04/2022 | 30 | NITESH MANAGEMENT | 2.74 | 2.74 | 100 | 100
1583 | HOOGHLY | Electrical | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block , SM/18958 | Augmentation | Supply delivery and installation of Chlorinator for Bachhanari w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. | 316/HMSD | 18/02/2022 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.76 | 0.76 | 100 | 100
1584 | HOOGHLY | Hooghly Division | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block , SM/18958 | Augmentation | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of SELAMPUR, BACHHANARI & SAMANTAKHANDA W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3169/HUG | 10/09/2024 | 45 | BALAJI UDDYOG | 48.46 | 0 | 0 | 0
1585 | HOOGHLY | Electrical | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block , SM/18958 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BACHHANARI PIPED W/S SCHEME, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1451/ED | 25/07/2024 | 90 | DAS ENTERPRISE | 11.08 | 0 | 0 | 0
1586 | HOOGHLY | Hooghly Division | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block , SM/18958 | Augmentation | Protection works and other allied works at 3rd & 4th TubeWell Site of BACCHANARI Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 4043/HUG | 19/12/2024 | 90 | MS CHANDIMATA CONSTRUCTION | 15.46 | 0 | 0 | 100
1587 | HOOGHLY | Hooghly Division | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block , SM/18958 | Augmentation | Repairing of Boundary Wall, Switch Room & R.C.C. Elevated Reservoir of BACHHANARI PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 573/HUG | 04/03/2025 | 60 | MS CHANDIMATA CONSTRUCTION | 12.45 | 0 | 0 | 0
1588 | HOOGHLY | Hooghly Division | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block , SM/18958 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SRIRAMPUR PWSS- 3nos (2) BACHHANARI PWSS- 3nos (3) MALAYPUR PWSS- 4nos (4) MANDRA PWSS- 4nos | 807/Arg | 23/08/2024 | 30 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
1589 | HOOGHLY | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block , SM/18960 | Augmentation | Supply delivery and installation of voltage correcting device and other allied works for Hayatpur w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. | 542/HMSD | 17/03/2022 | 30 | KASHINATH PAL & CO. | 2.74 | 2.72 | 99.29 | 100
1590 | HOOGHLY | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block , SM/18960 | Augmentation | Supply delivery and installation of Chlorinator for Hayatpur w/s scheme PH No. IV District Hooghly under Electrical Division, PHE dte. | 71/HMSD | 10/01/2023 | 7 | S P ENTERPRISE | 0.8 | 0.8 | 100 | 100
1591 | HOOGHLY | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block , SM/18960 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hayatpur water supply scheme, T.W. No. IV, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 473/ED | 10/03/2022 | 90 | S.P. ENTERPRISE | 6.92 | 6.36 | 92 | 50
1592 | HOOGHLY | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block , SM/18960 | Augmentation | Supply and installation of short MS casing pipe making TW foundation and S&F submersible AL. Ar. cable at Hayatpur w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. | 1928/HMSD | 03/11/2022 | 7 | DAS ENTERPRISE | 0.9 | 0.9 | 100 | 100
1593 | HOOGHLY | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block , SM/18960 | Augmentation | Supply delivery and installation of Chlorinator for Hayatpur w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. | 1878/HMSD | 20/10/2022 | 7 | DAS ENTERPRISE | 0.8 | 0.8 | 100 | 100
1594 | HOOGHLY | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block , SM/18960 | Augmentation | Supply delivery and installation of voltage correcting device and other allied works for Hayatpur w/s scheme PH No. IV District Hooghly under Electrical Division, PHE dte. | 540/HMSD | 17/03/2022 | 21 | MOITRA ENGINEERING CO. | 2.74 | 2.74 | 100 | 100
1595 | HOOGHLY | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block , SM/18960 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hayatpur water supply scheme, T.W. No. III, Block: Arambag , District- Hooghly under Electrical Division, PHE Dte. | 472/ED | 10/03/2022 | 90 | DAS ENTERPRISE | 6.89 | 6.57 | 100 | 100
1596 | HOOGHLY | Hooghly Division | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block , SM/18960 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of HAYATPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 4076/HUG | 19/12/2024 | 90 | ROY ENTERPRISE | 11.55 | 0 | 0 | 0
1597 | HOOGHLY | Hooghly Division | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block , SM/18960 | Augmentation | Protection works and other allied works OF 3rd & 4th TubeWell Site of HAYATPUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 4045/HUG | 19/12/2024 | 90 | S D ENTERPRISE | 15.52 | 0 | 0 | 0
1598 | HOOGHLY | Hooghly Division | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block , SM/18960 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PABA PWSS-3nos (2) DIHIBAYRA PWSS- 3nos (3) HAYATPUR PWSS- 4nos (4) RAJHATO PWSS- 4nos | 811/Arg | 23/08/2024 | 30 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
1599 | HOOGHLY | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18592 | New | Material Requisition To Resource Division | 3057/6/Hug | 11/10/2023 | 0 | Resource Division | 12.85 | 0 | 0 | 0
1600 | HOOGHLY | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18592 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SHANTIPUR PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1167/ED | 14/06/2024 | 90 | SRI KRISHNA NIRMAN | 10.54 | 5.84 | 55.4 | 30
1601 | HOOGHLY | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18592 | New | Quotation of New Service Connection for Shantipur w/s Scheme, Zone-I,PH No-III Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/18592) Application No-5004190445 Reference Id-503647425. | 151 | 22/05/2024 | 0 | WBSEDCL | 3.15 | 0 | 0 | 0
1602 | HOOGHLY | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18592 | New | Quotation of New service Connection at Shantipur w/s Scheme,Zone-I,PH No-I Block-Goghat-II District-Hooghly under Electrical division,PHE Dte.(SM/18592) Application No-5004135566 Reference Id-503626938. | 103 | 06/05/2024 | 0 | WBSEDCL | 10.73 | 0 | 0 | 0
1603 | HOOGHLY | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18592 | New | Quotation of New service Connection at Shantipur w/s Scheme,Zone-I,PH No-II Block-Goghat-II District-Hooghly under Electrical division,PHE Dte.(SM/18592) Application No-5004136337 Reference Id-503627274. | 102 | 06/05/2024 | 0 | WBSEDCL | 10.8 | 0 | 0 | 0
1604 | HOOGHLY | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18592 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Shantipur water supply scheme, Zone-I, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | 3587/ED | 28/08/2023 | 642 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 22.26 | 5.69 | 25.56 | 30
1605 | HOOGHLY | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18592 | New | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | 3190/HUG | 31/10/2023 | 609 | M/S PRITI ENTERPRISE | 4251.5 | 133.5 | 21.18 | 30
1606 | HOOGHLY | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18592 | New | Sinking of 4 nos. tube-well by (300 X 200 mm) D.R. Rig method at SELAMPUR Z-I, SANTIPUR Z-I, SELAMPUR Z-II and GARMANDARAN Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 725/HUG | 05/03/2024 | 667 | AUXILIARY TUBEWELL DRILLERS | 64.32 | 13.6 | 84.6 | 70
1607 | HOOGHLY | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18592 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 464/HUG | 20/02/2025 | 30 | TECHVISION | 6.59 | 0 | 0 | 0
1608 | HOOGHLY | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18592 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PUKHURIA PWSS- 3 nos (2) SELAMPUR PWSS (Z-I)- 2 nos (3) SHANTIPUR PWSS (Z-I)- 1 nos (4) KOTA PWSS - 4nos (5) SUNIA PWSS - 4nos | 1149/Arg | 10/12/2024 | 31 | TITAS CONSTRUCTION | 0.98 | 0 | 0 | 0
1609 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/18943 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4507/ED | 23/11/2023 | 90 | KARUNAMOY ENGINEERING | 10.74 | 4.07 | 37.93 | 90
1610 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/18943 | Augmentation | Providing Functional House Hold Tap Connection (FHTC) under JJM withing left out portion of AKNA PWSS under Chinsurah Sub Division of Hooghly Division P.H.E Dte. | 12/CH | 04/01/2024 | 15 | M/S BIMAL DAS AND CO. | 4.99 | 4.98 | 100 | 50
1611 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/18943 | Augmentation | Quotation for new service connection at Akna(S. Aug.) W/S Sch.[SM/18943], T/W No. - III, Barol Chowmatha, Block - Polba-Dadpur, Dist. - Hooghly under Mogra CCC, WBSEDCL, Ref. Id. - 503586679, Dt. - 27-03-2024, Application No. - 5004053218 | 14 | 04/04/2024 | 0 | WBSEDCL | 7.46 | 0 | 0 | 0
1612 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/18943 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at AYMA NABABPUR (2Nos.), DUMURDAHA (1No.), AKNA (1 No.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3356/HUG | 21/11/2023 | 715 | AYUSH ENTERPRISE | 58.97 | 0 | 0 | 80
1613 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/18943 | Augmentation | Construction of Approach Road for 3rd TW site of Akna PWSS in JJM under Polba Dadpur Block under Hooghly Division under Chinsurah Sub-Division PHE Dte | 316/CH | 21/02/2025 | 15 | ASHA ENTERPRISE | 4.99 | 0 | 0 | 0
1614 | HOOGHLY | Hooghly Division | Source Augmentation Of AMRA Piped W/S Scheme under Polba Dadbur Block , SM/18950 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at HANRAL (2Nos.), SUDARSHAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3243/HUG | 06/11/2023 | 60 | AMBIAN INFRASTRUCTURE | 59.26 | 0 | 0 | 0
1615 | HOOGHLY | Electrical | Source Augmentation Of AMRA Piped W/S Scheme under Polba Dadbur Block , SM/18950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of AMRA Piped W/S Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4514/ED | 23/11/2023 | 90 | SRI KRISHNA NIRMAN | 21.5 | 0 | 0 | 0
1616 | HOOGHLY | Hooghly Division | Source Augmentation Of AMRA Piped W/S Scheme under Polba Dadbur Block , SM/18950 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement ,Laying rising main pipe for inter connection between Proposed T.W & Distribution of AMRA Piped Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.HE Dte. | 3192/HUG | 31/10/2023 | 60 | R.K. TRADERS | 7.56 | 6.57 | 100 | 100
1617 | HOOGHLY | Hooghly Division | Source Augmentation Of AMRA Piped W/S Scheme under Polba Dadbur Block , SM/18950 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at PAUNAN (2Nos.), PUINAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3244/HUG | 06/11/2023 | 60 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 59.57 | 0 | 0 | 45
1618 | HOOGHLY | Electrical | Source Augmentation Of AMRA Piped W/S Scheme under Polba Dadbur Block , SM/18950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Amra water supply scheme, T.W. No. III, Block: Polba Dadpur, District - Hooghly under Electrical Division, PHE Dte. | 1914/ED | 21/11/2022 | 90 | M/S MANABESH ROY | 9.39 | 9.1 | 100 | 98
1619 | HOOGHLY | Hooghly Division | Source Augmentation Of AMRA Piped W/S Scheme under Polba Dadbur Block , SM/18950 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PAUNAN (2Nos.), PUINAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3405/HUG | 23/11/2023 | 571 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 0 | 0 | 25
1620 | HOOGHLY | Hooghly Division | Source Augmentation Of AMRA Piped W/S Scheme under Polba Dadbur Block , SM/18950 | Augmentation | Repairing of existing Switch room(5.4 M X3.6M)& Boundary wall at existing OHR Site of AMRA Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at POLBA DADPUR Block | 131/CH | 29/01/2025 | 31 | ASHA ENTERPRISE | 4.62 | 0 | 0 | 50
1621 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. , SM/07442 | Retrofitting | FHTC |  | 23/07/2021 | 0 | DIPTI TRADERS | 30.58 | 0 | 0 | 0
1622 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. , SM/07442 | Retrofitting | FHTC |  | 19/03/2021 | 0 | DIPTI TRADERS | 30 | 0 | 0 | 0
1623 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. , SM/07442 | Retrofitting | FHTC |  | 15/03/2021 | 0 | DIPTI TRADERS | 30 | 0 | 0 | 0
1624 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. , SM/07442 | Retrofitting | PROVIDING DRILLING CREWS AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR AMRA W/S SCHEME, POLBADADPUR BLOCK UNDER HOOGHLY DISTRICT , CDD, PHE DTE. | 294/CDD | 27/04/2022 | 30 | C.M. ENTERPRISE | 11.21 | 9.3 | 100 | 0
1625 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. , SM/07442 | Retrofitting | PROVIDING DRILLING CREWS AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR AMRA W/S SCHEME (HEAD WORKS), POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 302/CDD | 27/04/2022 | 30 | C.M. ENTERPRISE | 11.21 | 9.12 | 100 | 0
1626 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. , SM/07442 | Retrofitting | Placement of Fund | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
1627 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. , SM/07442 | Retrofitting | ROUTINE MAINTENANCE OF COMPRESSOR AND REPAIRING OF OTHERS ATTACHED WITH RIG MACHINE NO. KORES/DR/1000 UNDER CMSD-II (D), CDD, PHE DTE. | 635/CMSD-II (D) | 23/12/2021 | 15 | M/S B.P.TRADING CORPORATION | 3.37 | 3.34 | 100 | 0
1628 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. , SM/07442 | Retrofitting | REPAIRING OF MUD PUMP FLUID CHAMBER, TRANSMISSION LINE AND OTHERS WORKS ALONG WITH SUPPLY OF DRILLING ACCESSORYU OF RIG MACHINE- JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. | 72/CMSD-I | 30/03/2022 | 15 | PADMA ENGINEERING & CO. | 4 | 0.7 | 100 | 0
1629 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AMRA WATER SUPPLY SCHEME. , SM/07442 | Retrofitting | Material Requisition To Resource Division | 2195/1/HUG | 14/12/2021 | 0 | Resource Division | 1.59 | 0 | 0 | 0
1630 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. , SM/07443 | Retrofitting | FHTC |  | 24/05/2021 | 0 | DAS ENTERPRISE (SAMIR DAS) | 23.32 | 0 | 0 | 0
1631 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. , SM/07443 | Retrofitting | FHTC |  | 23/07/2021 | 0 | BIMAL KUMAR HALDER | 9.98 | 0 | 0 | 0
1632 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. , SM/07443 | Retrofitting | FHTC |  | 17/08/2021 | 0 | DAS ENTERPRISE (SAMIR DAS) | 14.73 | 0 | 0 | 0
1633 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. , SM/07443 | Retrofitting | FHTC |  | 19/03/2021 | 0 | DAS ENTERPRISE (SAMIR DAS) | 10.96 | 0 | 0 | 0
1634 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. , SM/07443 | Retrofitting | FHTC |  | 15/02/2021 | 0 | TOTON MONDAL | 16 | 0 | 0 | 0
1635 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. , SM/07443 | Retrofitting | FHTC |  | 21/09/2021 | 0 | TOTON MONDAL | 7.25 | 0 | 0 | 0
1636 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. , SM/07443 | Retrofitting | FHTC |  | 06/10/2021 | 0 | DAS ENTERPRISE (SAMIR DAS) | 6.67 | 0 | 0 | 0
1637 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. , SM/07443 | Retrofitting | FHTC |  | 23/07/2021 | 0 | BIMAL KUMAR HALDER | 9.98 | 0 | 0 | 0
1638 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. , SM/07443 | Retrofitting | ... | 844375 | 17/12/2021 | 0 | MOUMITA SINGHA BHATTACHATYA | 0.31 | 0 | 0 | 0
1639 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHAPTA WATER SUPPLY SCHEME. , SM/07443 | Retrofitting | Material Requisition To Resource Division | 428/5-5/Hug | 07/03/2022 | 0 | Resource Division | 11 | 0 | 0 | 0
1640 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme , SM/06992 | Retrofitting | FHTC |  | 21/09/2021 | 0 | RAJ CONSTRUCTION | 43.8 | 0 | 0 | 0
1641 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme , SM/06992 | Retrofitting | Providing 47 nos. Functional Household Tap Connection (FHTC) in AWG Centers (the command area of Jangalpara, Jangipara & Rajbalhat Water Supply Scheme) under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 220/SER | 20/12/2021 | 25 | M/S SAYAN CHAKRABORTY | 1.95 | 1.35 | 69.12 | 0
1642 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme , SM/06992 | Retrofitting | Providing 1487 nos F.H.T.C. in Jangalpara Village of Jangalpara and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Chanditala-I] | 473/Hug | 26/02/2021 | 40 | RAJ CONSTRUCTION | 51.8 | 51.8 | 100 | 0
1643 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme , SM/06992 | Retrofitting | Survey of FHTC Work under Rajyadharpur, Rishra, Nabagram GP KMDA Water Supply areas and Jangalpara, Krishnarampur, Chanditala, Panchghora, Begampur & Mollarber Water Supply areas under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 294/SER | 21/02/2022 | 45 | BAKSHI ENTERPRISE | 2.99 | 0.23 | 22.27 | 0
1644 | HOOGHLY | Central Drilling | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme , SM/06992 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR JANGALPARA W/S SCHEME, CHANDITALA-I BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 2000/CDD | 08/02/2023 | 30 | CHANDA ENTERPRISE | 12.54 | 8.98 | 71.62 | 0
1645 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme , SM/06992 | Retrofitting | Material Requisition To Resource Division | 2198/1/HUG | 14/12/2021 | 0 | Resource Division | 1.59 | 0 | 0 | 0
1646 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme , SM/06992 | Retrofitting | Material Requisition To Resource Division | 1122/1/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
1647 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jangalpara Water Supply Scheme , SM/06992 | Retrofitting | Providing 1487 nos F.H.T.C. in Jangalpara Village of Jangalpara and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Chanditala] | 473/HUG | 26/02/2021 | 40 | RAJ CONSTRUCTION | 69.87 | 0.72 | 1.03 | 72
1648 | HOOGHLY | Hooghly Division | Retrofitting Works for Providing Functional Household Tap Connection(FHTC) within the Jaysinhachak Mouza of Arandi Water Supply Scheme , SM/06759 | Retrofitting | FHTC |  | 15/02/2021 | 0 | MS CHANDIMATA CONSTRUCTION | 24 | 0 | 0 | 0
1649 | HOOGHLY | Hooghly Division | Retrofitting Works for Providing Functional Household Tap Connection(FHTC) within the Jaysinhachak Mouza of Arandi Water Supply Scheme , SM/06759 | Retrofitting | Placement of Fund | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
1650 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME. , SM/07946 | Retrofitting | FHTC |  | 21/09/2021 | 0 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 30.09 | 0 | 0 | 0
1651 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME. , SM/07946 | Retrofitting | Sinking of 3 nos. 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 2nd Tube Well Site of JANGIPARA ZONE-II W/S Scheme, 4th Tube Well Site of ANTPUR W/S Scheme, & 4th Tube Well Site of JANGALPARA W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. . | 3522/HUG | 22/10/2024 | 316 | WATER TECH | 29.57 | 0 | 0 | 45
1652 | HOOGHLY | Hooghly Division | Retrofitting Works for Digsui-Heora PWSS(Zone-II ) for providing 1065 nos Functional Household Tap Connection(FHTC) , SM/06761 | Retrofitting | FHTC |  | 12/04/2021 | 0 | M/S S.C CIVIL ENTERPRISE | 40.5 | 0 | 0 | 0
1653 | HOOGHLY | Central Drilling | Retrofitting Works for Digsui-Heora PWSS(Zone-II ) for providing 1065 nos Functional Household Tap Connection(FHTC) , SM/06761 | Retrofitting | CONTINUATION FOR HIRING DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE DRILLER IN CHARGE, CMSD-II (D), CDD, PHE DTE. | 361/CMSD-II (D) | 15/07/2022 | 30 | ASHUTOSH PAL | 0.73 | 0.52 | 71.58 | 100
1654 | HOOGHLY | Central Drilling | Retrofitting Works for Digsui-Heora PWSS(Zone-II ) for providing 1065 nos Functional Household Tap Connection(FHTC) , SM/06761 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR DIGSUI HEORA W/S SCHEME (Z-I), CHINSURAH MOGRA BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 296/CDD | 27/04/2022 | 30 | C.M. ENTERPRISE | 11.21 | 6.2 | 100 | 100
1655 | HOOGHLY | Hooghly Division | Retrofitting Works for Digsui-Heora PWSS(Zone-II ) for providing 1065 nos Functional Household Tap Connection(FHTC) , SM/06761 | Retrofitting | Providing 600 nos Functional Household Tap Connection (FHTC) within the command area of DIGSUI HOERA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 120/Hug | 19/01/2022 | 30 | DAS TRADING | 41.69 | 12.25 | 99.99 | 100
1656 | HOOGHLY | Central Drilling | Retrofitting Works for Digsui-Heora PWSS(Zone-II ) for providing 1065 nos Functional Household Tap Connection(FHTC) , SM/06761 | Retrofitting | CONTINUATION FOR HIRING OF DEASEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE DRILLER IN CHARGE , CMSD-II (D), CDD, PHE DTE. | 361/ CMSD-II | 15/07/2022 | 15 | ASHUTOSH PAL | 0.73 | 0.29 | 39.87 | 100
1657 | HOOGHLY | Central Drilling | Retrofitting Works for Digsui-Heora PWSS(Zone-II ) for providing 1065 nos Functional Household Tap Connection(FHTC) , SM/06761 | Retrofitting | Fuel charges for the month of November,22. car number - WB04H 6870. | BP-2022-23-300 | 06/01/2023 | 0 | MIRA SERVICE STATION | 0.24 | 0 | 0 | 0
1658 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme , SM/06767 | Retrofitting | FHTC |  | 30/09/2021 | 0 | M/S S.G. CONSTRUCTION | 13.22 | 0 | 0 | 0
1659 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme , SM/06767 | Retrofitting | Placement of Fund | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
1660 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme , SM/06767 | Retrofitting | Providing 512 nos F.H.T.C. in Krishnabati & Gazipur village of Malia and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | 1549/Hug | 24/11/2020 | 365 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 18.11 | 3 | 99.84 | 100
1661 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme , SM/06767 | Retrofitting | Providing 62 nos FHTC in Krishnabati village at Nawapara Habitation of Malia and its Adj. Mouzas Water Supply Scheme under Chandannagar Sub Division PHE Dte. | 59/Chan | 02/02/2021 | 16 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 2.17 | 0.31 | 99.84 | 100
1662 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme , SM/06767 | Retrofitting | PROVIDING 72 NOS FHTC FOR MALIA PWSS | 88/CHAN | 15/02/2021 | 30 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 3.16 | 0.41 | 99.66 | 100
1663 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme , SM/06767 | Retrofitting | Providing 112 nos F.H.T.C. & extension of pipe line in left out portion of Dakshinkul, Baganbati& Hamir gachhi village of Malia and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | 327/HUG | 11/02/2021 | 30 | M/S S.G. CONSTRUCTION | 10.08 | 10.08 | 100 | 100
1664 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme , SM/06767 | Retrofitting | Providing F.H.T.C in leftout portion and repairing boundary wall of Malia water supply scheme under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. | 3789/HUG | 25/11/2024 | 310 | ROSE ENTERPRISE | 11.75 | 0 | 0 | 100
1665 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATUL WATER SUPPLY SCHEME. , SM/07543 | Retrofitting | FHTC |  | 17/08/2021 | 0 | MS CHANDIMATA CONSTRUCTION | 5.11 | 0 | 0 | 0
1666 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATUL WATER SUPPLY SCHEME. , SM/07543 | Retrofitting | FHTC |  | 28/07/2021 | 0 | MS CHANDIMATA CONSTRUCTION | 41.45 | 0 | 0 | 0
1667 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATUL WATER SUPPLY SCHEME. , SM/07543 | Retrofitting | FHTC |  | 12/04/2021 | 0 | MS CHANDIMATA CONSTRUCTION | 5.04 | 0 | 0 | 0
1668 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATUL WATER SUPPLY SCHEME. , SM/07543 | Retrofitting | Providing 400 nos Functional Household Tap Connection (FHTC) within the left out Mouzas of PATUL Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | 1089/HUG | 03/06/2022 | 30 | K. JAGADHATRY & CO. | 23.18 | 0 | 0 | 0
1669 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. , SM/08743 | Retrofitting | FHTC |  | 28/01/2022 | 0 | SARKAR CONSTRUCTION | 7.5 | 0 | 0 | 0
1670 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. , SM/08743 | Retrofitting | Providing 224 nos Functional Household Tap Connection (FHTC) within the command area of Baidyapur Water Supply Scheme at Basudebpur Mouza Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte | 1444/Hug | 23/08/2021 | 30 | SARKAR CONSTRUCTION | 22.35 | 7.43 | 66.51 | 100
1671 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. , SM/08743 | Retrofitting | PROVIDING 94 NOS. FHTC IN MIRZAPUR VILLAGE OF BAIDYAPUR AND ITS ADJ MOUZAS PWSS | 89/CHAN | 15/02/2021 | 30 | TAPAS ADHYA | 4.62 | 1.55 | 33.55 | 100
1672 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. , SM/08743 | Retrofitting | Repair and Renovation Works of R.C.C. Elevated Reservoir of BAIDYAPUR PWSS under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 4075/HUG | 19/12/2024 | 90 | BIMAL KUMAR HALDER | 9.23 | 0 | 0 | 0
1673 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. , SM/08743 | Retrofitting | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Baidyapur PWSS,Madpur PWSS,Ghosha PWSS). | 309/chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.48 | 0.48 | 100 | 100
1674 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. , SM/08743 | Retrofitting | Providing F.H.T.C in leftout portion and construction of boundary wall at head work site and 3rd tubewell site, laying pumping main at 3rd tubewell site of Baidyapur water supply scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte | 3430/HUG | 03/10/2024 | 304 | BAPPADITYA BANERJEE | 65.68 | 0 | 0 | 50
1675 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. , SM/08743 | Retrofitting | Special repairing of Laying Distribution System including Rising main, FHTC & other essential components of Baidyapur W/S Scheme under Chandannagar Sub-Division P.H.E.Dte. | 889/CHAN | 21/07/2025 | 20 | SWASTIK ENTERPRISE | 4.97 | 0 | 0 | 100
1676 | HOOGHLY | Hooghly Division | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme , SM/09066 | Retrofitting | Providing 145 nos Functional Household Tap Connection (FHTC) within the command area of BACHHANARI Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | 14/Hug | 04/01/2022 | 20 | ROY ENTERPRISE | 6.02 | 6.02 | 100 | 100
1677 | HOOGHLY | Hooghly Division | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme , SM/09066 | Retrofitting | Construction of 3.6 m X 3.00 m Switch Room with Additional Plinth Height, without Sanitary and Water Supply arrangement at 3rd TW Site of BACHHANARI W/S Scheme under Arambagh Sub-Division P.H.E. Dte. | 52/Arg | 31/01/2022 | 45 | S. B. CONSTRUCTION | 3.43 | 2.75 | 80.36 | 100
1678 | HOOGHLY | Hooghly Division | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme , SM/09066 | Retrofitting | Hiring of well maintained Diesel Motor Cab for the office of the Executive Engineer, Hooghly Division PHE Dte. | 148/HQHUG | 30/12/2021 | 365 | PRADIP KUMAR ADHYA | 1.25 | 1.25 | 100 | 100
1679 | HOOGHLY | Hooghly Division | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme , SM/09066 | Retrofitting | Construction of approach road at 3rd Tube Well site of Bachhanari Piped Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte. | 215/ARG | 31/03/2022 | 7 | KARALI MOHAN KHAMRUI | 1.32 | 1.3 | 98.03 | 100
1680 | HOOGHLY | Central Drilling | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme , SM/09066 | Retrofitting | SUPPLY AND DELIVERY OF COTTON WASTE AND OTHER MATERIALS FOR DRILLING WORK AT BACHHANARI PWSS DISTRICT HOOGHLY AND OTHER PWSS UNDER CDD, PHE DTE. | 256/CMSD-I | 23/06/2022 | 15 | M/S PRACHI ENGINEERING | 1.92 | 0 | 0 | 100
1681 | HOOGHLY | Central Drilling | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme , SM/09066 | Retrofitting | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY KORES RIG MACHINE UNDER CMSD-II, CDD, PHE DTE. | 644/ CDD | 28/09/2021 | 30 | PADMA ENGINEERING & CO. | 11.2 | 8.36 | 100 | 100
1682 | HOOGHLY | Hooghly Division | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme , SM/09066 | Retrofitting | FHTC |  | 28/01/2022 | 0 | M/S SHIVAM UDYOG | 19.5 | 0 | 0 | 0
1683 | HOOGHLY | Hooghly Division | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme , SM/09066 | Retrofitting | Providing 450 nos F.H.T.C. in Bachhanari and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte.[Block-Arambagh] | 250/Hug | 03/02/2021 | 30 | PRADIP KUMAR ADHYA | 30.31 | 5.22 | 34.46 | 100
1684 | HOOGHLY | Hooghly Division | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme , SM/09066 | Retrofitting | Providing 145 nos Functional Household Tap Connection (FHTC) within the command area of Bachhanari Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | 1916/Hug | 27/10/2021 | 20 | ROY ENTERPRISE | 8.38 | 8.28 | 100 | 100
1685 | HOOGHLY | Central Drilling | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme , SM/09066 | Retrofitting | Supply & delivery of Cotton Waste and other materials for drilling work at Bachanari PWSS, District Hooghly and other PWSS under Central Drilling Division, PHE Dte. | 256/CMSD-I | 23/06/2023 | 15 | DEV ENTERPRISE | 1.46 | 0 | 0 | 0
1686 | HOOGHLY | Central Drilling | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme , SM/09066 | Retrofitting | PROVIDING TUBE WELL MATERIALS (150MM DIA CD), CONFORMING TO IS12:42 PM 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BACHHANARI, IN HOWRAH DISTRICT UNDER CMSD-I (D), CDD, PHE DTE. | 113/CMSD-I | 06/05/2022 | 15 | ASHUTOSH DAS & CO | 3.11 | 3.11 | 100 | 0
1687 | HOOGHLY | Central Drilling | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme , SM/09066 | Retrofitting | SUPPLY & DELIVERY OF CONSUMBLES AND OTHERS WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AMODGHATA W/S SCH, TW-II, HOOGHLY DISTRICT,UNDER CDD. PHE DTE. | 379/CMSD-II | 01/08/2022 | 15 | C.M. ENTERPRISE | 3.44 | 0.02 | 100 | 0
1688 | HOOGHLY | Central Drilling | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme , SM/09066 | Retrofitting | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | 1724/CDD | 29/12/2022 | 30 | DEY ENTERPRISE | 13.83 | 0.01 | 100 | 0
1689 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AKNA WATER SUPPLY SCHEME. , SM/09069 | Retrofitting | PROVIDING DRILLING CREW AND OTHER AIILIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR AKNA W/S SCHEME (Z-I), POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 292/ CDD | 27/04/2022 | 30 | PADMA ENGINEERING & CO. | 4.21 | 0 | 0 | 100
1690 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AKNA WATER SUPPLY SCHEME. , SM/09069 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR HANRAL W/S SCH, POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 292/CDD | 27/04/2022 | 30 | PADMA ENGINEERING & CO. | 11.23 | 4.21 | 100 | 90
1691 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNETION (FHTC) WITHIN THE COMMAND AREA OF DUBIR BHERI WATER SUPPLY SCHEME , SM/10131 | Retrofitting | Providing 1002 nos F.H.T.C. in Dakatiar Bheri & Dubir Bheri Village of Dubir Bheri and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | 408/Hug | 15/02/2021 | 30 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 49.74 | 12.16 | 48.91 | 0
1692 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNETION (FHTC) WITHIN THE COMMAND AREA OF DUBIR BHERI WATER SUPPLY SCHEME , SM/10131 | Retrofitting | Providing 1158 nos F.H.T.C. in Karichar Bheri, Maheswarbati & Ugly Village of Dubir Bheri and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | 409/Hug | 15/02/2021 | 30 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 58.94 | 10.08 | 34.19 | 0
1693 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Natun CharKrishnabati Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte. , SM/10133 | Retrofitting | Providing 433 nos Functional Household Tap Connection (FHTC) within the Char Rampur, Chhera Char Krishnabati, Guptipara Char & Sabek Char Krishnabati Mouza of Natunchar Krishnabati Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | 475/Hug | 10/03/2022 | 20 | BIMAL KUMAR HALDER | 21.7 | 18.13 | 100 | 0
1694 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Natun CharKrishnabati Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte. , SM/10133 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of NATUN CHAR KRISHNABATI Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 2307/HUG | 28/10/2022 | 30 | SARKAR CONSTRUCTION | 33.86 | 33.48 | 100 | 0
1695 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Natun CharKrishnabati Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte. , SM/10133 | Retrofitting | Providing 867 nos Functional Household Tap Connection (FHTC) within the Natunchar Krishnabati Mouza of Natunchar Krishnabati Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | 474/Hug | 10/03/2022 | 40 | M/S T.K.B. CONSTRUCTION | 43.24 | 34.45 | 100 | 25
1696 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Natun CharKrishnabati Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte. , SM/10133 | Retrofitting | Material Requisition To Resource Division | 428/1-1/Hug | 07/03/2022 | 0 | Resource Division | 10.98 | 0 | 0 | 0
1697 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR , SM/10004 | Augmentation | Repairing of 3.6 mtr x 3.0 mtr size existing pump house of Enayetpur PWSS scheme under Hooghly Division, PHE Dte. | 657/chan | 27/12/2021 | 30 | SURAJIT SINGHA RAY | 2.76 | 2.67 | 96.71 | 0
1698 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR , SM/10004 | Augmentation | Route Survey, Design Drawing & DPR Preparation of ENAYETPUR PWSS under Chandannagar Sub Division , PHE Dte. | 170/chan | 24/03/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.84 | 4.84 | 100 | 0
1699 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR , SM/10004 | Augmentation | Interconnection of replacement tube wells with existing Rising main at HWS of Enayetpur Water Supply Scheme under Hooghly Division, P.H.E. Dte. | 532/Chan | 12/11/2021 | 15 | SWASTIK ENTERPRISE | 2.29 | 2.03 | 88.4 | 0
1700 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR , SM/10004 | Augmentation | PROVIDING TUBE WELL MATERIALS (200 MM DIA CM PIPE) CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 175/CMSD-II | 27/07/2021 | 15 | KUNDU ELECTRICAL ENTERPRISE | 4.41 | 2.3 | 50 | 0
1701 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR , SM/10004 | Augmentation | SUPPLY & DELIVERY OF BENTONITE POWDER SODIUM BASED (RAJASTHAN VARIETY) FOR CONSTRUCTION OF TUBE WELLS AT ENAYATPUR PWSS TW-I UNDER CMSD-II (D), CDD, PHE DTE. | 339/CMSD-II | 13/09/2021 | 15 | S B S ENTERPRISE | 0.42 | 0.35 | 100 | 0
1702 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR , SM/10004 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 176/CMSD-II | 27/07/2021 | 30 | S B S ENTERPRISE | 4.86 | 3.3 | 100 | 0
1703 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR , SM/10004 | Augmentation | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 172/CMSD-II | 27/07/2021 | 15 | M/S PRACHI ENGINEERING | 4.17 | 4.17 | 100 | 0
1704 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR , SM/10004 | Augmentation | Central Drilling Payment | C022228292462 | 09/02/2022 | 0 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVN. P.H.E. DTE. | 55.06 | 0 | 0 | 0
1705 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR , SM/10004 | Augmentation | Providing 1000 nos Functional Household Tap Connection (FHTC) within the command area of Enayetpur Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte | 2204/Hug | 14/12/2021 | 60 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 40.46 | 41.84 | 100 | 0
1706 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR , SM/10004 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Enayetpur water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | 836/ED | 14/02/2023 | 90 | BISALAXMI ENTERPRISE | 21.48 | 0 | 0 | 0
1707 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR , SM/10004 | Augmentation | Material Requisition To Resource Division | 157/5/Hug | 24/01/2022 | 0 | Resource Division | 3.1 | 0 | 0 | 0
1708 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR , SM/10004 | Augmentation | Material Requisition To Resource Division | 1125/3/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
1709 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR , SM/10004 | Augmentation | Material Requisition To Resource Division | 423/2/Hug | 07/03/2022 | 0 | Resource Division | 25.98 | 0 | 0 | 0
1710 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR , SM/10004 | Augmentation | Material Requisition To Resource Division | 1383/14/Hug | 15/05/2023 | 0 | Resource Division | 23.96 | 0 | 0 | 0
1711 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR , SM/10004 | Augmentation | Material Requisition To Resource Division | 109/5/Hug | 10/01/2023 | 0 | Resource Division | 104.08 | 0 | 0 | 0
1712 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR , SM/10004 | Augmentation | Sinking of tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room, boundary wall & Repairing of Existing OHR, Switch Rooms, Boundary walls at different TW sites for Augmentation of ENAYETPUR Piped Water Supply Scheme under HARIPAL Block, District:- Hooghly | 1162/HUG | 20/04/2023 | 865 | P.B. ENTERPRISE (PINTU BHADURI) | 70.38 | 23.04 | 32.74 | 45
1713 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR , SM/10004 | Augmentation | ROAD RESTORATION PAYMENT TO PWD FOR BAIDYABATI TARAKESWAR CHAMPADANGA ROAD | BP-2024-25-498 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, (PWD) HOOGHLY CONSTRUCTION DIVISION | 10.6 | 0 | 0 | 0
1714 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR ENAYETPUR , SM/10004 | Augmentation | ENAYETPUR Piped Water Supply Scheme with LDS, FHTC & Construction of 400 cum capacity OHR with 20mtr. staging height including soil investigation work at HARIPAL Block under Chandannagar Sub- Division Under Hooghly Division PHE Dte. | 2298/HUG | 21/10/2022 | 1046 | P.B. ENTERPRISE (PINTU BHADURI) | 918.91 | 729.36 | 79.37 | 90
1715 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DHAMAITIKAR WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09774 | Retrofitting | Withdrawal & Re-Laying of DHAMAITIKAR and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division,P.H.E Dte. [Block - Dhaniakhali] | 719/CH | 23/08/2022 | 15 | SUDIPTA SINHA | 4.86 | 4.85 | 100 | 0
1716 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DHAMAITIKAR WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09774 | Retrofitting | Providing 502 nos F.H.T.C. in Dhamaitikar village of Dhamaitikar and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Dhaniakhali](Part-A) | 1337/HUG | 29/09/2020 | 30 | SOUMYADIP DE | 19.04 | 0.44 | 2.32 | 100
1717 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION , SM/11004 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Ajabnagar, Banamalipur & Mukundapur Mouza in MASAT PWSS, Block CHANDITALA-I under Serampore Sub-Division of Hooghly Division P.H.E Dte. | 2843/HUG | 16/12/2022 | 45 | BAKSHI ENTERPRISE | 46.45 | 42.95 | 100 | 20
1718 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION , SM/11004 | Retrofitting | Laying of Pipeline for left out portion of Masat and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte .[Block-Chanditala I] | 2450/HUG | 12/08/2023 | 468 | SADHUKHAN ENTERPRISE | 9.87 | 7.45 | 75.43 | 10
1719 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION , SM/11004 | Retrofitting | Sinking of tube-well by D.R. Rig method Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of MASAT Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | 823/HUG | 11/03/2024 | 60 | G. T. AGRO CENTRE | 31.46 | 0 | 0 | 0
1720 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION , SM/11004 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Masat Mouza in MASAT PWSS, Block CHANDITALA-I under Serampore Sub-Division of Hooghly Division P.H.E Dte. | 2844/HUG | 16/12/2022 | 60 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 66.74 | 65.02 | 100 | 30
1721 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION , SM/11004 | Retrofitting | Laying of Pipeline for left out portion of Masat , Banamalipur, AusbaliMouza of MASAT Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte .[Block-Chanditala I]. | 2451/HUG | 12/08/2023 | 30 | S.D ENTERPRISE (SAMIR KR. DAS) | 8.03 | 7.76 | 100 | 35
1722 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION , SM/11004 | Retrofitting | Laying Distribution System of Balanced portion with Additional laying including Repairing of Roads (Concrete) within Masat, Banamalipur, Ajabnagar and Ausbali mouzas in Masat W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte | 821/HUG | 11/03/2024 | 30 | DILIP KUMAR GHOSH | 31.69 | 31.07 | 100 | 96
1723 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION , SM/11004 | Retrofitting | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Mollarber PWSS 2. Uttar Rajyadharpur PWSS 3. Piarapur PWSS 4. Krishnarampur PWSS 5. Jangalpara PWSS 6. Masat PWSS | 108/SER | 23/02/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 80
1724 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION , SM/11004 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Chhunche & Ausbati Mouza in MASAT PWSS, Block CHANDITALA-I under Serampore Sub-Division of Hooghly Division P.H.E Dte. | 2842/HUG | 16/12/2022 | 770 | K. JAGADHATRY & CO. | 39.46 | 35.68 | 90.42 | 30
1725 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF TALPUR PWSS FOR PROVIDING 1224 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. , SM/11006 | Retrofitting | Providing 112 nos. tap connection at Nagadipara and Paschim para Habitation of TALPUR water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. to make it "SWAJAL HABITATION" | 216/chan | 13/04/2022 | 20 | SWASTIK ENTERPRISE | 4.99 | 4.69 | 93.84 | 0
1726 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF TALPUR PWSS FOR PROVIDING 1224 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. , SM/11006 | Retrofitting | Providing 107 nos. tap connection at Mirzapur and bajitpur mouza of Baidyapur water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. to make it "SWAJAL VILLAGE" | 215/chan | 13/04/2022 | 20 | M/S RAJKUMAR KHAN | 4.99 | 0 | 0 | 100
1727 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA , SM/09983 | Augmentation | Route Survey, Design Drawing & DPR Preparation of DWIPA PWSS under Chandannagar Sub Division , PHE Dte. | 169/chan | 24/03/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.24 | 3.99 | 94.05 | 0
1728 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA , SM/09983 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 210 Mtr at DWIPA PWSS (3rd & 4th Tube Well Site) of Chandannagar Sub-Division under Hooghly Division, PHE Dte. SL NO - 12 | 1999/HUG | 12/09/2022 | 45 | P.B. ENTERPRISE (PINTU BHADURI) | 26 | 23.08 | 88.76 | 0
1729 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA , SM/09983 | Augmentation | Material Requisition To Resource Division | 2686/6/Hug | 01/12/2022 | 0 | Resource Division | 0.34 | 0 | 0 | 0
1730 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA , SM/09983 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dwipa water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | 835/ED | 14/02/2023 | 90 | M/S PS & ASSOCIATES | 21.49 | 21.44 | 100 | 0
1731 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA , SM/09983 | Augmentation | Material Requisition To Resource Division | 1125/2/HUG | 06/06/2022 | 0 | Resource Division | 11.52 | 0 | 0 | 0
1732 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA , SM/09983 | Augmentation | Material Requisition To Resource Division | 423/5/Hug | 07/03/2022 | 0 | Resource Division | 25.98 | 0 | 0 | 0
1733 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA , SM/09983 | Augmentation | Material Requisition To Resource Division | 01/08/Hug | 02/01/2023 | 0 | Resource Division | 11.94 | 0 | 0 | 0
1734 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA , SM/09983 | Augmentation | Material Requisition To Resource Division | 1383/40/Hug | 15/05/2023 | 0 | Resource Division | 11.38 | 0 | 0 | 0
1735 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA , SM/09983 | Augmentation | Material Requisition To Resource Division | 109/ 9/Hug | 10/01/2023 | 0 | Resource Division | 34.08 | 0 | 0 | 0
1736 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA , SM/09983 | Augmentation | Quotation Bill for New service connection at (Aug.) of Dwipa W/S. Sch. PH-I | 183 | 10/03/2023 | 0 | WBSEDCL | 0.65 | 0 | 0 | 0
1737 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA , SM/09983 | Augmentation | Quotation Bill for New service connection at (Aug.) of Dwipa W/S. Sch. PH-II | 183 | 10/03/2023 | 0 | WBSEDCL | 3.08 | 0 | 0 | 0
1738 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA , SM/09983 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Dwipa PWSS, Enayetpur PWSS, Haripal zone-I PWSS, Haripal zone-II PWSS, Olipur zone-I PWSS, Olipur zone-II PWSS) | 301/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 100
1739 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA , SM/09983 | Augmentation | ROAD RESTORATION PAYMENT TO PWD FOR JANGIPARA ROAD | BP-2024-25-500 | 26/09/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 13.12 | 0 | 0 | 0
1740 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR DWIPA , SM/09983 | Augmentation | Augmentation of DWIPA Water Supply Scheme with Construction of 600 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work & LDS, Switch room, Boundary wall,Rising Main,FHTC Work,Repairing of existing Switch Rooms at Haripal Block under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | 830/Hug | 20/04/2022 | 1078 | P.B. ENTERPRISE (PINTU BHADURI) | 724.25 | 685.83 | 87.46 | 80
1741 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Route Survey, Design Drawing & DPR Preparation Beraberi PWSS under Chandannagar Sub Division , PHE Dte | 168/chan | 24/03/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.17 | 4.13 | 98.97 | 0
1742 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS CONSTRUCTION OF TUBE WELL AT AUG. OF BERABERI PWSS TW-II, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 371/CMSD-II(D) | 29/07/2022 | 15 | C.M. ENTERPRISE | 4.97 | 4.55 | 100 | 0
1743 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT AUG. OF BERABERI PWSS TW-II, HARTIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 370/CMSD-II(D) | 29/07/2022 | 15 | C.M. ENTERPRISE | 2.93 | 2.75 | 100 | 0
1744 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | SUPPLY & DELIVERY OF CONSUMABLES AT SITE AND OTHER WORKS FOR CONSTRUCTION OF TUBEWELL AT AUG. OF BERABERI PWSS TW-I, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 369/CMSD-II(D) | 28/07/2022 | 15 | C.M. ENTERPRISE | 3.52 | 2.6 | 100 | 0
1745 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | SUPPLY 7 DELIVERY OF CONSUMABLES AT SITE AND OTHER WORKKS FOR CONSTRUCTION OF TUBE WELL aUG. OF BERABERI PWSS TW-II, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 372/CMSD-II(D) | 29/07/2022 | 15 | C.M. ENTERPRISE | 3.52 | 2.62 | 100 | 0
1746 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITHJ OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AUG. OF BERABERI PWSS TW-I, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 368/CMSD-II(D) | 28/07/2022 | 15 | C.M. ENTERPRISE | 4.97 | 4.62 | 100 | 0
1747 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT AUG. OF BERABERI PWSS TW-I, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 367/CMSD-II(D) | 28/07/2022 | 15 | C.M. ENTERPRISE | 2.93 | 2.78 | 100 | 0
1748 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AUG. OF BERABERI PWSS TW-III, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 375/CMSD-II (D) | 01/08/2022 | 15 | C.M. ENTERPRISE | 4.97 | 4.7 | 100 | 0
1749 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | PROVIDING DRILLINGCREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT AUG. OF BERABERI PWSS TW-III, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 374/CMSD-II (D) | 01/08/2022 | 15 | C.M. ENTERPRISE | 2.93 | 2.75 | 100 | 0
1750 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES AT SITE AND OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT AUG. OF BERABERI PWSS TW-III, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 376/CMSD-II (D) | 01/08/2022 | 15 | C.M. ENTERPRISE | 3.52 | 2.6 | 100 | 0
1751 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Material Requisition To Resource Division | 2686/13/Hug | 01/12/2022 | 0 | Resource Division | 0.35 | 0 | 0 | 0
1752 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | New Connection of Electricity |  | 13/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.33 | 0 | 0 | 0
1753 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | New Connection | 80 | 16/09/2022 | 0 | WBSEDCL | 6.36 | 0 | 0 | 0
1754 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Quotation bill for New Connection at Beraberi W/S. Sch. PH-III | BP-2022-23-111 | 14/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.54 | 0 | 0 | 0
1755 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Electricity Bill New Connection |  | 13/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.03 | 0 | 0 | 0
1756 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. III, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | 1918/ED | 21/11/2022 | 90 | GLACIER ENGINEERING CO. | 10.67 | 10.38 | 97.32 | 0
1757 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | CONTINUATION FOR HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE DRILLER-IN-CHARGE, CMSD-II (D), CDD, PHE DTE. | 35/CMSD-II | 10/02/2023 | 15 | ASHUTOSH PAL | 0.29 | 0.29 | 98.36 | 0
1758 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Material Requisition To Resource Division | 157/4/Hug | 24/01/2022 | 0 | Resource Division | 2.58 | 0 | 0 | 0
1759 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Material Requisition To Resource Division | 1125/7/HUG | 06/06/2022 | 0 | Resource Division | 10.98 | 0 | 0 | 0
1760 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Material Requisition To Resource Division | 423/3/Hug | 07/03/2022 | 0 | Resource Division | 25.98 | 0 | 0 | 0
1761 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Material Requisition To Resource Division | 01/09/Hug | 02/01/2023 | 0 | Resource Division | 11.94 | 0 | 0 | 0
1762 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Material Requisition To Resource Division | 1383/43/Hug | 15/05/2023 | 0 | Resource Division | 7.81 | 0 | 0 | 0
1763 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Material Requisition To Resource Division | 3058/Hug | 11/10/2023 | 0 | Resource Division | 30.27 | 0 | 0 | 0
1764 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Material Requisition To Resource Division | 1235/Hug | 28/04/2023 | 0 | Resource Division | 223.26 | 0 | 0 | 0
1765 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | FUEL CHARGES FOR CAR NO - WB-04H-6870 | BP-2023-24-13 | 24/04/2023 | 0 | MIRA SERVICE STATION | 0.19 | 0 | 0 | 0
1766 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Augmentation of BERABARI Water Supply Scheme with Construction of 600 cum capacity OHR with 20 mtr. staging height including Soil Investigation work & LDS(S-2) & Functional Household tap Connection within Chak Kalikabari, Beraberi, Jampukur, Madhusudanpur, Khaser Bheri & Khagragachhi Mouza, Switch room, Boundary wall, Rising Main, Repairing of existing Switch Rooms at Singur Block under Chandannagar Sub-Division, PHE Dte. | 1383/Hug | 07/07/2022 | 300 | S & P ENTERPRISE | 461.01 | 460.96 | 99.99 | 50
1767 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Augmentation of BERABARI Water Supply Scheme with Laying Distribution System (S-1) & Functional Household Tap Connection at Baje Melia & Hijli Mouzas, Construction of Switch room at Proposed T.W Site, Boundary wall at Singur Block under Chandannagar Sub-Division, PHE Dte. | 1583/HUG | 02/08/2022 | 75 | M/S BISWAS CONSTRUCTION | 246.26 | 204.24 | 82.94 | 50
1768 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. I, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte | 1792/ED | 02/11/2022 | 90 | ALPHA ENTERPRISE | 10.67 | 10.38 | 97.31 | 99
1769 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Providing connection in leftout portion of beraberi mouza under Beraberi water supply scheme under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. | 2341/HUG | 19/06/2024 | 30 | MAA TARA CONSTRUCTION | 31.82 | 0 | 0 | 0
1770 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Horizontal Auger boring with water jet system including road restoration Work at Baje Melia & Hijli Mouzas under Beraberi Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte.Block Singur, District:- Hooghly. | 3675/HUG | 13/11/2024 | 45 | M/S BISWAS CONSTRUCTION | 42.93 | 0 | 0 | 0
1771 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of BERABERI Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.HE Dte. | 386/HUG | 08/02/2024 | 60 | BHATTACHARJEE CONSTRUCTION | 15.56 | 13.47 | 100 | 100
1772 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Sinking of 4 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Berabari (3rd TWS), Gouribati (3rd TWS), Naita (2nd TWS), Barakamalpur (2nd TWS) W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | 3379/HUG | 21/11/2023 | 45 | OSMAN SEKH | 64.2 | 15.97 | 100 | 100
1773 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Quotation for new service connection at Beraberi W/S Sch. , T/W No. - V [SM/09984] , Block - Singur, under Singur CCC, WBSEDCL, Ref Id. - 503614887, dt. - 12/04/2024, Application No. - 5004104119 | 75 | 18/04/2024 | 0 | WBSEDCL | 4.1 | 0 | 0 | 0
1774 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. IV, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte | 1548/ED | 20/09/2022 | 649 | PERFECT AIRCONDITION | 9.66 | 9.4 | 97.26 | 99
1775 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. V, Block: Singur, District: Hooghly under Electrical Division, PHE Dte. | 338/ED | 21/02/2024 | 540 | DEY ENTERPRISE | 10.41 | 10.13 | 97.32 | 90
1776 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR BERABARI , SM/09984 | Augmentation | Laying DI pipe and orther allied work for BERABERI PWSS UNDER singur block under chandannagar subdivision of of Hooghly Division P.H.E Dte. | 3618/HUG | 05/11/2024 | 241 | DAFFODIL | 72.7 | 0 | 0 | 80
1777 | HOOGHLY | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 297 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER Arambag, Balagarh, Chanditala-I & II, Chinsurah-Mogra, Dhan , SM/10248 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Running water supply arrangement with tube well including Soak Pit & Hand Wash Basin with electric power and pumping system at Sub-Centre & Primary Health Centre having Electrical power connection in Dhaniakhali Block (33 Nos) under Hooghly Division, P.H.E. Dte. (Total 33 Nos) | 808/Hug | 19/04/2022 | 45 | MS PRADIP KUMAR PAL | 59.11 | 40.92 | 69.23 | 25
1778 | HOOGHLY | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 297 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER Arambag, Balagarh, Chanditala-I & II, Chinsurah-Mogra, Dhan , SM/10248 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Running water supply arrangement with tube well including Soak Pit & Hand Wash Basin with electric power and pumping system at Sub-Centre & Primary Health Centre having Electrical power connection in Goghat-II Block (13 Nos), Khanakul-I Block (15 Nos) & Khanakul-II Block (5 Nos) under Hooghly Division, P.H.E. Dte. (Total 33 Nos) | 805/Hug | 19/04/2022 | 45 | DILIP KUMAR GHOSH | 58.9 | 19.79 | 33.6 | 0
1779 | HOOGHLY | Hooghly Division | WATER SUPPLY ARRANGEMENT FOR 297 Nos. SUB-CENTRES & PRIMARY HEALTH CENTRES RUNNING WITHIN GOVT PREMISES SITUATED NOT WITHIN THE COMMAND AREA OF PWSS UNDER HOOGHLY DIVISION PHE DTE (294 NOs) UNDER Arambag, Balagarh, Chanditala-I & II, Chinsurah-Mogra, Dhan , SM/10248 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Material Requisition To Resource Division | 510/Hug | 16/03/2022 | 0 | Resource Division | 92.24 | 0 | 0 | 0
1780 | HOOGHLY | Hooghly Division | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12246 | New | Material Requisition To Resource Division | 1386/10/Hug | 15/05/2023 | 0 | Resource Division | 20.6 | 0 | 0 | 0
1781 | HOOGHLY | Hooghly Division | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12246 | New | Material Requisition To Resource Division | 1264/12/HUG | 03/05/2023 | 0 | Resource Division | 7.36 | 0 | 0 | 0
1782 | HOOGHLY | Hooghly Division | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12246 | New | Protection Work at H/W & 2ND T.W Site for HASAMPUR W/S under Chinsurah Sub - Division of Hooghly Division P.H.E. Dte. | 2460/HUG | 12/08/2023 | 60 | CHAKRABORTY ENTERPRISE | 35.44 | 30.86 | 100 | 100
1783 | HOOGHLY | Electrical | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12246 | New | Barul PH__II Water supply Scheme | 726 | 05/02/2024 | 0 | WBSEDCL | 4.11 | 0 | 0 | 0
1784 | HOOGHLY | Electrical | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12246 | New | Barul PH__I Water supply Scheme | 727 | 05/02/2024 | 0 | WBSEDCL | 3.04 | 0 | 0 | 0
1785 | HOOGHLY | Electrical | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12246 | New | Add. Electric quot. of WBSEDCL for New service Connection of Barul T/W-I W/S scheme under Electrical Division PHE Dte. (SM/12246) App. No- 5003997215 Ref. Id- 503556940 | 539 | 29/10/2024 | 0 | WBSEDCL | 1.34 | 0 | 0 | 0
1786 | HOOGHLY | Electrical | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12246 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Barul water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | 3458/ED | 30/12/2022 | 1095 | T S CONSTRUCTION | 20.35 | 0 | 0 | 65
1787 | HOOGHLY | Hooghly Division | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12246 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 229.04 | 42.8 | 30
1788 | HOOGHLY | Hooghly Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI , SM/11293 | New | Material Requisition To Resource Division | 902/14/Hug | 27/03/2023 | 0 | Resource Division | 5.33 | 0 | 0 | 0
1789 | HOOGHLY | Hooghly Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI , SM/11293 | New | Material Requisition To Resource Division | 1383/38/Hug | 15/05/2023 | 0 | Resource Division | 5.43 | 0 | 0 | 0
1790 | HOOGHLY | Hooghly Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI , SM/11293 | New | Material Requisition To Resource Division | 109/ 20/Hug | 10/01/2023 | 0 | Resource Division | 10.76 | 0 | 0 | 0
1791 | HOOGHLY | Electrical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI , SM/11293 | New | Quotation bill for WBSEDCL security deposit for Rambati w/s scheme PH-I | 230 | 01/09/2023 | 0 | WBSEDCL | 9.37 | 0 | 0 | 0
1792 | HOOGHLY | Hooghly Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI , SM/11293 | New | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, RWS HOOGHLY SUB-DIVISION, PHE DTE. |  | 06/11/2023 | 0 | AATISH KUMAR SHAW | 0.8 | 0 | 0 | 0
1793 | HOOGHLY | Electrical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI , SM/11293 | New | Quotation bill for WBSEDCL security deposit for Rambati w/s scheme, PH No.-II | 229 | 01/09/2023 | 0 | WBSEDCL | 6.25 | 0 | 0 | 0
1794 | HOOGHLY | Electrical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI , SM/11293 | New | Revised Quotation Bill for New Service Connection at Rambati W/S. Sch. PH-I | 345 | 11/10/2023 | 0 | WBSEDCL | 0 | 0 | 0 | 0
1795 | HOOGHLY | Electrical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI , SM/11293 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Rambati water supply scheme, T.W. No. I & II, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | 3474/ED | 30/12/2022 | 90 | S.G. TECHNICAL SERVICES | 20.35 | 17.05 | 83.79 | 90
1796 | HOOGHLY | Hooghly Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI , SM/11293 | New | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of RAMBATI Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | 449/HUG | 16/02/2023 | 60 | RITAM ENTERPRISE | 12.29 | 12.29 | 100 | 50
1797 | HOOGHLY | Hooghly Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI , SM/11293 | New | Sinking of 2 nos 300 X 200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tube Well Site of RAMBATI W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 159/HUG | 16/01/2023 | 45 | SAMIRON GHOSH | 28.9 | 28.86 | 100 | 100
1798 | HOOGHLY | Electrical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI , SM/11293 | New | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle - II, PHE Dte. | 2871/HMSD | 04/06/2024 | 182 | DEBASHISH GHOSH | 0.86 | 0.12 | 13.44 | 0
1799 | HOOGHLY | Hooghly Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMBATI , SM/11293 | New | "RAMBATI" Piped Water Supply Scheme With LDS, FHTC & Construction of 150 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at TARAKESWAR Block under Chandannagar Sub - Division Under Hooghly Division PHE Dte. | 2559/HUG | 25/11/2022 | 1103 | BAPPADITYA BANERJEE | 230.53 | 186.6 | 65.03 | 45
1800 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF JAGATPUR PWSS FOR PROVIDING 4588 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. , SM/11225 | Retrofitting | Providing 155 nos Functional Household Tap Connection (FHTC) within the command area of JAGATPUR Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | 462/Hug | 10/03/2022 | 15 | M/S TANISA ENTERPRISE | 11.7 | 11.58 | 100 | 0
1801 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF JAGATPUR PWSS FOR PROVIDING 4588 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. , SM/11225 | Retrofitting | Providing 1487 nos F.H.T.C. in the villages of Sudarsan and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba Dadpur] | 242/HUG | 02/02/2021 | 40 | M/S BISWAS CONSTRUCTION | 69.94 | 13.94 | 44.31 | 0
1802 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF JAGATPUR PWSS FOR PROVIDING 4588 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. , SM/11225 | Retrofitting | Providing 800 nos Functional Household Tap Connection (FHTC) & extension of Laying Distribution System within the uncovered area of Baksa Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Chanditala-II] | 467/HUG | 26/02/2021 | 30 | TAPAS ADHYA | 44.33 | 0.97 | 4.91 | 100
1803 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF JAGATPUR PWSS FOR PROVIDING 4588 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. , SM/11225 | Retrofitting | Sinking of 1(one) No Big dia tube well (300 mm x 200mm) with supply of PVC Pipe and strainer and having depth upto 150Mtr at 4th TW site of JAGATPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 1274/HUG | 23/06/2022 | 30 | KAMIRUL SK AND CO | 9.96 | 9.27 | 100 | 100
1804 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF JAGATPUR PWSS FOR PROVIDING 4588 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. , SM/11225 | Retrofitting | Sinking of 1(one) No Big dia tube well (300 mm x 200mm) with supply of PVC Pipe and strainer and having depth upto 150Mtr at 5th TW site of JAGATPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 1275/HUG | 23/06/2022 | 30 | KAMIRUL SK AND CO | 9.96 | 8.84 | 100 | 100
1805 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BELUN WATER SUPPLY SCHEME (FHTC : 735 Nos) , SM/12012 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM in BELUN PWSS, Block-PANDUA under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO - 06 | 2087/HUG | 21/09/2022 | 30 | BAKSHI ENTERPRISE | 24.77 | 24.76 | 99.96 | 0
1806 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BELUN WATER SUPPLY SCHEME (FHTC : 735 Nos) , SM/12012 | Retrofitting | Laying of pipe line within left out portion for Providing Functional Household Tap Connection (FHTC) under JJM in BELUN PWSS, Block-PANDUA under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO - 07 | 2088/HUG | 21/09/2022 | 30 | TANISA ENTERPRISE | 26.3 | 20.62 | 78.41 | 80
1807 | HOOGHLY | Hooghly Division | Purba Chakla Mini Piped Water Supply Scheme , SM/13666 | New | Material Requisition To Resource Division | 1385/5/Hug | 15/05/2023 | 0 | Resource Division | 0.46 | 0 | 0 | 0
1808 | HOOGHLY | Hooghly Division | Purba Chakla Mini Piped Water Supply Scheme , SM/13666 | New | MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-340 | 31/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.2 | 0 | 0 | 0
1809 | HOOGHLY | Hooghly Division | Purba Chakla Mini Piped Water Supply Scheme , SM/13666 | New | REQUISITION OF FUND FOR SAJAL GRAM SCHEME |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 28.42 | 0 | 0 | 0
1810 | HOOGHLY | Hooghly Division | Purba Chakla Mini Piped Water Supply Scheme , SM/13666 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME |  | 23/06/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 31.58 | 0 | 0 | 0
1811 | HOOGHLY | Electrical | Purba Chakla Mini Piped Water Supply Scheme , SM/13666 | New | Mini Piped water Supply Scheme | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
1812 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13677 | Augmentation | Providing 400 nos Functional Household Tap Connection (FHTC) within the command area of RAJHAT & DHARAMPUR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 459/Hug | 10/03/2022 | 25 | MAHARAJA CONSTRUCTION CO. | 24.32 | 22.43 | 92.23 | 100
1813 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13677 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajhat water supply scheme, Zone-I, T.W. No.- IV, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | 865/ED | 14/02/2023 | 90 | DIPA CHHETRI | 10.17 | 10.16 | 99.95 | 100
1814 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13677 | Augmentation | Laying of Pipe Line for necessary interconnection with T.W.& Distribution System For RAJHAT Water Supply Scheme under CHINSURAH Sub-Division of HOOGHLY DIVISION P.H.E. Dte. | 1476/HUG | 19/05/2023 | 45 | R.K. TRADERS | 29.66 | 29.65 | 100 | 100
1815 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13677 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. | 959/HMSD | 20/04/2023 | 30 | SANJIB PRADHAN | 0.39 | 0.39 | 100 | 1
1816 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13677 | Augmentation | Car hiring and fuel bill for car no. WB02AB3954 from 01.07.2023 to 31.07.2023. | 363//AE-I/ED | 29/05/2023 | 31 | TRIDIP SARKAR | 0.38 | 0.36 | 100 | 1
1817 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13677 | Augmentation | Quotation bill for New service connection at Rajhat W/S. Sch Z-I, PH-IV | 173 | 28/02/2023 | 0 | WBSEDCL | 19.98 | 0 | 0 | 0
1818 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13677 | Augmentation | Quotation bill for new service connection at Rajhat w/s scheme | 173 | 28/02/2023 | 0 | WBSEDCL | 7.44 | 0 | 0 | 0
1819 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13677 | Augmentation | Diversion of Laying of Distribution Pipeline for Re-construction of Bridge by I & W Dept. at Chatimtala under Rajhat W/S Scheme under Chinsurah Sub Division Of Hooghly Division PHE Dte | 541/HUG | 20/02/2024 | 15 | MINTU CHAKRABORTY | 3.41 | 0 | 0 | 0
1820 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13677 | Augmentation | Preparation of DPR for Augmentation RAJHAT Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-POLBA DADPUR]. | 694/CH | 09/08/2024 | 7 | APEX ENGINEERING | 2.71 | 0 | 0 | 0
1821 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13677 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos.T.W with distribution system, FHTC of RAJHAT W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | 1419/Hug | 17/05/2023 | 45 | BOSE ENTERPRISE (RATUL BOSE) | 40.33 | 33.37 | 100 | 80
1822 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13677 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Uttar Babnan Z-I PWSS 2.Uttar Babnan Z-II PWSS 3. Rajhat PWSS | 147/CH | 20/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.48 | 0.48 | 100 | 30
1823 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13677 | Augmentation | Laying HDPE Pipeline From existing existing Distribution System for providing FHTC of Rajhat Zone-II W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | 129/CH | 16/02/2024 | 15 | BOSE ENTERPRISE (RATUL BOSE) | 4.94 | 4.94 | 100 | 15
1824 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13677 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in RAJHAT GP of POLBA-DADPUR Block. | 246/CH | 12/03/2024 | 30 | M/S BIMAL DAS AND CO. | 4.98 | 4.79 | 100 | 100
1825 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13677 | Augmentation | Repairing of concrete road due laying of pipe line at Antpukur of Rajhat PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | 552/CH | 14/06/2024 | 7 | M/S BIMAL DAS AND CO. | 1.81 | 1.79 | 100 | 80
1826 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13677 | Augmentation | Inter connection work of Rising main from Tube Well no. 6 to existing distribution system at Gotu of Rajhat W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | 58/CH | 10/01/2025 | 5 | M/S BIMAL DAS AND CO. | 0.93 | 0 | 0 | 50
1827 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13677 | Augmentation | Repairing of existing Switch room(5.4 M X3.6M)& Boundary wall at existing OHR Site of RAJHAT ZONE-I Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at POLBA DADPUR Block | 277/CH | 20/02/2025 | 10 | MAA JAGADHATRI CONSTRUCTION | 4.66 | 0 | 0 | 0
1828 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13677 | Augmentation | Repairing of existing Switch room(5.4 M X3.6M)& Boundary wall at existing OHR Site of RAJHAT (Z-II) Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at POLBA DADPUR Block | 220/CH | 19/02/2025 | 30 | MAA JAGADHATRI CONSTRUCTION | 4.63 | 0 | 0 | 0
1829 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13677 | Augmentation | Repairing of existing Switch room(3.0 M X3.6M)& Boundary wall at existing 2nd T.W Site of RAJHAT (Z-II) Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at POLBA DADPUR Block | 222/CH | 19/02/2025 | 30 | MAA JAGADHATRI CONSTRUCTION | 3.28 | 0 | 0 | 0
1830 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF AMDOBA WATER SUPPLY SCHEME , SM/12001 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area of AMDOBA Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte. | 155/HUG | 16/01/2023 | 50 | AICH CONSTRUCTION | 59.77 | 56.29 | 100 | 100
1831 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF AMDOBA WATER SUPPLY SCHEME , SM/12001 | Retrofitting | Construction of Boundary Wall, Internal Pathway at 2nd TW Site of AMDOBA Water Supply Scheme under Arambagh Sub-Division, of Hooghly Division, P.H.E. Dte. | 2735/HUG | 07/12/2022 | 480 | DREAM INFRASTRUCTURE | 4.83 | 3.24 | 67.16 | 60
1832 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF AMDOBA WATER SUPPLY SCHEME , SM/12001 | Retrofitting | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) GANESHBATI PWSS-3nos (2) AMDOBA PWSS-2nos (3) BALI PWSS- 3nos (4) RADHABALLAVPUR PWSS- 3nos (5) RAMNAGAR PWSS-3 nos | 818/Arg | 23/08/2024 | 130 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.14 | 100 | 100
1833 | HOOGHLY | Hooghly Division | Palpukur Mini Piped Water Supply Scheme , SM/13659 | New | Material Requisition To Resource Division | 1385/27/Hug | 15/05/2023 | 0 | Resource Division | 0.18 | 0 | 0 | 0
1834 | HOOGHLY | Hooghly Division | Palpukur Mini Piped Water Supply Scheme , SM/13659 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-248 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 26.82 | 0 | 0 | 0
1835 | HOOGHLY | Electrical | Palpukur Mini Piped Water Supply Scheme , SM/13659 | New | Mini Piped Water Supply Scheme. | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0 | 0
1836 | HOOGHLY | Hooghly Division | Sikil Beldiha Mini Piped Water Supply Scheme , SM/13661 | New | Material Requisition To Resource Division | 1385/Hug | 15/05/2023 | 0 | Resource Division | 0.4 | 0 | 0 | 0
1837 | HOOGHLY | Hooghly Division | Sikil Beldiha Mini Piped Water Supply Scheme , SM/13661 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME |  | 23/06/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.68 | 0 | 0 | 0
1838 | HOOGHLY | Hooghly Division | Sikil Beldiha Mini Piped Water Supply Scheme , SM/13661 | New | MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-339 | 31/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 29.38 | 0 | 0 | 0
1839 | HOOGHLY | Hooghly Division | Sikil Beldiha Mini Piped Water Supply Scheme , SM/13661 | New | REQUISITION OF FUND FOR SAJAL GRAM SCHEME |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 27.61 | 0 | 0 | 0
1840 | HOOGHLY | Electrical | Sikil Beldiha Mini Piped Water Supply Scheme , SM/13661 | New | Mini Piped water Supply Scheme | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
1841 | HOOGHLY | Hooghly Division | Jasapur mini pipe water supply scheme , SM/13664 | New | Material Requisition To Resource Division | 1385/52/Hug | 15/05/2023 | 0 | Resource Division | 0.59 | 0 | 0 | 0
1842 | HOOGHLY | Hooghly Division | Jasapur mini pipe water supply scheme , SM/13664 | New | Bhabapur Mini PWSS |  | 25/09/2024 | 0 | HOOGHLY ZILLA PARISHAD | 67.4 | 0 | 0 | 0
1843 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | Material Requisition To Resource Division | 2686/11/Hug | 01/12/2022 | 0 | Resource Division | 0.35 | 0 | 0 | 0
1844 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | Route survey Design drawing & DPR preparation of Sripatipur PWSS under Chandannagar Sub-Division, P.H.E. Dte. | 263/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.83 | 4.8 | 100 | 0
1845 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | Material Requisition To Resource Division | 1383/27/Hug | 15/05/2023 | 0 | Resource Division | 20.33 | 0 | 0 | 0
1846 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | Material Requisition To Resource Division | 109/7/Hug | 10/01/2023 | 0 | Resource Division | 20.06 | 0 | 0 | 0
1847 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | Quotation of New Service Connection for Sripatipur w/s scheme,Zone-II,TW No-II Block-Haripal Dist-Hooghly under ED,PHE Dte | 260 | 05/09/2023 | 0 | WBSEDCL | 6.19 | 0 | 0 | 0
1848 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | Quotation of New Service Connection for Sripatipur w/s Scheme,Z-I,TW No-3 Block-Haripal,District-Hooghly under Electrical Division PHE Dte | 299 | 22/09/2023 | 0 | WBSEDCL | 2.5 | 0 | 0 | 0
1849 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | Quotation of New Service Connection for Sripatipur W/S Scheme,Zone-I,TW No-I Block-Haripal,Dist-Hooghly under ED,PHE Dte | 262 | 05/09/2023 | 0 | WBSEDCL | 3.31 | 0 | 0 | 0
1850 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | Quotation for new service connection charge at Sripatipur PWSS, Zone-II, TW - II | 531 | 15/12/2023 | 0 | WBSEDCL | 3.22 | 0 | 0 | 0
1851 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, PHE DTE. | BP-2023-24-281 | 16/08/2023 | 0 | GOUR KUMAR DAS | 0.77 | 0 | 0 | 0
1852 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | Quotation of New Service Connection for sripatipur W/S Scheme,Zone-I,TW No-II Block-Haripal Dist-Hooghly under ED,PHE Dte | 261 | 05/09/2023 | 0 | WBSEDCL | 3.16 | 0 | 0 | 0
1853 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | AUGMENTATION of SRIPATIPUR ZONE-II Piped Water Supply Scheme with Construction of switch room, LDS, Boundary Wall, LDS under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. Block-SINGUR, District- Hooghly.[AUGMENTATION SCHEME] | 1063/HUG | 12/04/2023 | 90 | SATYA NARAYAN BISWAS | 215.71 | 171.28 | 79.41 | 50
1854 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | Construction of 400 cum capacity RCC OHR with 20.0 mtr.Staging height including soil investigation & construction of boundary wall at Proposed H.W site, Rising Main, FHTC For AUGMENTATION of SRIPATIPUR ZONE-II Piped Water Supply Schem under Chandannagar Sub-Division of Hooghly Division P.H.E Dte.Block Singur, District:- Hooghly [AUGMENTATION SCHEME] | 1555/HUG | 26/05/2023 | 270 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 227.21 | 40.02 | 17.61 | 20
1855 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | AUGMENTATION of SRIPATIPUR ZONE-I Piped Water Supply Scheme with Construction of Switch Room, Boundary Wall, LDS, under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. Block-SINGUR, District:- Hooghly [AUGMENTATION SCHEME] | 953/HUG | 30/03/2023 | 90 | MALLIKA ENTERPRISE | 156.56 | 144.41 | 100 | 100
1856 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of SRIPATIPUR W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 1819/HUG | 22/06/2023 | 45 | OSMAN SEKH | 80.85 | 80.54 | 100 | 45
1857 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | Construction of 300 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of boundary wall at Proposed H.W site, Rising Main, FHTC For AUGMENTATION of SRIPATIPUR ZONE-I Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. Block Singur, District:- Hooghly [AUGMENTATION SCHEME] | 1470/HUG | 19/05/2023 | 958 | SOUMYADIP DE | 181.5 | 82.92 | 45.69 | 70
1858 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | Providing FHTC for the leftout portion of Sripatipur Mouza of SRIPATIPUR ZONE 1 Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte | 3666/HUG | 13/11/2024 | 322 | TRIYA CONSTRUCTION | 36.22 | 0 | 0 | 100
1859 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | Construction of approach road at head work site of Sripatipur zone-I water supply scheme under Chandannagar Sub-Division P.H.E. Dte.(Part-B) | 195/Chan | 12/02/2025 | 20 | SOUMYADIP DE | 3.95 | 0 | 0 | 0
1860 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | :Estimate for Supply fitting and fixing of sluice valve for Sripatipur Zone-II Water Supply Scheme Under Chandannagar SubDivision,P.H.E Dte . | 905/CHAN | 21/07/2025 | 15 | MAA TARA CONSTRUCTION | 4.92 | 0 | 0 | 50
1861 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | Repairing of boundary wall at old 1st tubewell site of Sripatipur z-2 PWSS Scheme under Chandannagar Sub-Division, PHE Dte. | 919/CHAN | 21/07/2025 | 20 | M/S T.K.B. CONSTRUCTION | 4.18 | 0 | 0 | 0
1862 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | Repairing of boundary wall at old 2nd site of Sripatipur z-2 PWSS Scheme under Chandannagar Sub-Division, PHE Dte. | 920/CHAN | 21/07/2025 | 20 | M/S T.K.B. CONSTRUCTION | 2.09 | 0 | 0 | 0
1863 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRIPATIPUR , SM/13349 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Sripatipur water supply scheme TW No I II III IV and V, Block Haripal, District Hooghly under ED PHED. | 861/ED | 14/02/2023 | 884 | DEY ENTERPRISE | 53.74 | 52.19 | 97.2 | 65
1864 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF RAMNARAYANPUR PWSS FOR PROVIDING 2936 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE , SM/13353 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Gayeshpur & Bishnubati Mouza in RAMNARAYANPUR PWSS, Block TARAKESWAR underChandannagar Sub-Division of Hooghly Division P.H.E Dte.1 | 2846/HUG | 16/12/2022 | 30 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 31.27 | 30.56 | 97.72 | 0
1865 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF RAMNARAYANPUR PWSS FOR PROVIDING 2936 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE , SM/13353 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Gure & Makrar Mouza in RAMNARAYANPUR PWSS, Block TARAKESWAR underChandannagar Sub-Division of Hooghly Division P.H.E Dte. | 2847/HUG | 16/12/2022 | 30 | ARATI ENGINEERING | 34.16 | 34.12 | 100 | 100
1866 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF RAMNARAYANPUR PWSS FOR PROVIDING 2936 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE , SM/13353 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Ramnarayanpur Mouza in RAMNARAYANPUR PWSS, Block TARAKESWAR under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | 790/HUG | 20/03/2023 | 30 | AHS R INFRA PRIVATE LIMITED | 25.02 | 21.17 | 100 | 100
1867 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF RAMNARAYANPUR PWSS FOR PROVIDING 2936 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE , SM/13353 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Samanta Para of Ramnarayanpur PWSS under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. | 389/Chan | 09/06/2023 | 15 | KALYAN BANERJEE | 0.93 | 0.92 | 100 | 100
1868 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF RAMNARAYANPUR PWSS FOR PROVIDING 2936 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE , SM/13353 | Retrofitting | Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at various Mouzas of Ramnarayanpur water supply scheme under Chandannagar Sub-Division P.H.E. Dte. | 728/HUG | 05/03/2024 | 45 | SWASTIK ENTERPRISE | 33.9 | 17.91 | 52.91 | 80
1869 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF RAMNARAYANPUR PWSS FOR PROVIDING 2936 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE , SM/13353 | Retrofitting | Repairing of pump house at 1St and 2nd TW site of Ramnarayanpur PWSS under Chandannagar Sub-Division, PHE Dte. | 924/CHAN | 21/07/2025 | 20 | BAPPADITYA BANERJEE | 4.38 | 0 | 0 | 50
1870 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF RAMNARAYANPUR PWSS FOR PROVIDING 2936 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE , SM/13353 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Ketera Mouza in RAMNARAYANPUR PWSS, Block TARAKESWAR underChandannagar Sub-Division of Hooghly Division P.H.E Dte. | 2845/HUG | 16/12/2022 | 741 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 22.7 | 12.58 | 73.53 | 100
1871 | HOOGHLY | Hooghly Division | Barul mini pipe water supply scheme , SM/13548 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-242 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.98 | 0 | 0 | 0
1872 | HOOGHLY | Electrical | Barul mini pipe water supply scheme , SM/13548 | New | Mini Piped Water Supply Scheme. | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0 | 0
1873 | HOOGHLY | Hooghly Division | Jot Mahabhat Mini Piped Water Supply Scheme , SM/13555 | New | Material Requisition To Resource Division | 1385/22/Hug | 15/05/2023 | 0 | Resource Division | 0.36 | 0 | 0 | 0
1874 | HOOGHLY | Hooghly Division | Jot Mahabhat Mini Piped Water Supply Scheme , SM/13555 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-247 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 29.69 | 0 | 0 | 0
1875 | HOOGHLY | Electrical | Jot Mahabhat Mini Piped Water Supply Scheme , SM/13555 | New | Mini Piped Water Supply Scheme. | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0 | 0
1876 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13409 | Augmentation | Supply, delivery and installation of voltage correcting device and other allied works for Saptagram w/s scheme, P.H No.- IV, Dist- Hooghly under Electrical Division, PHE Dte. | 490/HMSD | 02/03/2023 | 30 | M.S.C. ENTERPRISE | 2.49 | 2.47 | 99.18 | 0
1877 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13409 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Saptagram water supply scheme, T.W. No. IV, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | 1318/ED | 17/08/2022 | 90 | M.S.C. ENTERPRISE | 7.28 | 7.28 | 99.93 | 0
1878 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13409 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of SAPTAGRAM PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte.. | 1131/HUG | 19/04/2023 | 30 | SWARNA ENTERPRISE | 24.19 | 12.67 | 100 | 98
1879 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13409 | Augmentation | Construction of Boundary Wall, Laying of C.I/D.I pipes & specials for connection of Proposed T.W with distribution system, FHTC of SAPTAGRAM W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | 1340/HUG | 11/05/2023 | 30 | SWARNA ENTERPRISE | 21.02 | 6.26 | 100 | 100
1880 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13409 | Augmentation | Material Requisition To Resource Division | 3004/4/Hug | 05/10/2023 | 0 | Resource Division | 36.39 | 0 | 0 | 0
1881 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13409 | Augmentation | Construction of 2nos. 3.6 mtr x3.0 mtr Switch Room with Additional Plinth Height, With Sanitary and Water Supply arrangement at Proposed T/W Sites for Saptagram Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at Chinsurah Mogra Block | 736/HUG | 05/03/2024 | 45 | M/S BIMAL DAS AND CO. | 11.17 | 0 | 0 | 50
1882 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13409 | Augmentation | Sinking of 2 (Two) No Big dia tube well (250 mm X 150 mm) with supply of PVC Pipe and strainer and having depth upto 180 M at 3rd TW site of Saptagram W/S Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | 737/HUG | 05/03/2024 | 30 | TAPAS ADHYA | 19.53 | 18.89 | 100 | 100
1883 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13409 | Augmentation | Providing FHTC at the left out portions of Mithapukur for proiving FHTC in Saptagram Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 280/CH | 14/03/2024 | 7 | BIMAL KUMAR HALDER | 0.97 | 0.97 | 100 | 80
1884 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13409 | Augmentation | Providing FHTC at the left out portions of Choto Khejuria for proiving FHTC in Saptagram Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 282/CH | 14/03/2024 | 7 | BIMAL KUMAR HALDER | 0.96 | 0.96 | 100 | 80
1885 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13409 | Augmentation | Providing FHTC at the left out portions of Bara Khejuria for proiving FHTC in Saptagram Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 283/CH | 14/03/2024 | 7 | BIMAL KUMAR HALDER | 0.97 | 0.97 | 100 | 80
1886 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13409 | Augmentation | Laying HDPE pipeline for proiving FHTC at different placess at Saptagram Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 281/CH | 14/03/2024 | 7 | BIMAL KUMAR HALDER | 0.96 | 0.96 | 100 | 80
1887 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13409 | Augmentation | Quotation for new service connection at Saptagram (S.Aug.) W/S Sch. [SM/13409], T/W No. - II (Chotokhejuria),Block -Chinsurah- Mogra under Saptagram CCC, WBSDCL. Ref. Id - 503643407, dt. - 10-05-2024, Application No. - 5004179275 | 126 | 17/05/2024 | 0 | WBSEDCL | 5.49 | 0 | 0 | 0
1888 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13409 | Augmentation | Quotation for new service connection at Saptagram (S.Aug.) W/S Sch. [SM/13409], T/W No. - I (Dingalghat, bansberia),Block -Chinsurah- Mogra under Saptagram CCC, WBSDCL. Ref. Id - 503643287, dt. - 10-05-2024, Application No. - 5004179261 | 123 | 17/05/2024 | 0 | WBSEDCL | 3.94 | 0 | 0 | 0
1889 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13409 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SAPTAGRAM PIPED W/S SCHEME, T.W. No. V & VI, Block: Chinsurah Mogra, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1457/ED | 25/07/2024 | 90 | D. K. ELECTRIC | 22.19 | 5.5 | 24.78 | 70
1890 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13409 | Augmentation | Repairing & Renovation of boundary wall, Switch room and Land development at H/W Site of Saptagram Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 486/CH | 04/04/2025 | 10 | BIMAL KUMAR HALDER | 4.53 | 0 | 0 | 100
1891 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SAPTAGRAM PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13409 | Augmentation | Repairing & Renovation of Switch room at PH-2 of Saptagram Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 296/CH | 20/02/2025 | 10 | BIMAL KUMAR HALDER | 1.33 | 0 | 0 | 100
1892 | HOOGHLY | Hooghly Division | Dumurpara Mini Piped water Supply Scheme , SM/13591 | New | Material Requisition To Resource Division | 1385/30/Hug | 15/05/2023 | 0 | Resource Division | 0.43 | 0 | 0 | 0
1893 | HOOGHLY | Hooghly Division | Dumurpara Mini Piped water Supply Scheme , SM/13591 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-246 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.62 | 0 | 0 | 0
1894 | HOOGHLY | Electrical | Dumurpara Mini Piped water Supply Scheme , SM/13591 | New | Mini Piped Water Supply Scheme. | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0 | 0
1895 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13345 | Augmentation | Hiring of Luxury Car/Ambassador (BS-IV) for official use of the Chief Engineer (Electrical/Mechanical) Southern Zone, PHE Dte. | 1072/HMSD | 11/05/2023 | 365 | ORIENTAL ENGINEERING CO. | 0.95 | 1.32 | 100 | 80
1896 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13345 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kulihanda water supply scheme, T.W. No.- V, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | 3497/ED | 30/12/2022 | 90 | H.K.DAS & CO. | 10.82 | 10.79 | 100 | 100
1897 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13345 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kulihanda W/S. Sch. TW-IV, Hooghly | 1037/ED | 28/06/2022 | 90 | STANDARD ELECTRICALS | 10.23 | 10.21 | 100 | 0
1898 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13345 | Augmentation | Quotation bill for New Service Connection Kulihanda W/S. Sch. pH-II | 175 | 28/02/2023 | 0 | WBSEDCL | 4.33 | 0 | 0 | 0
1899 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13345 | Augmentation | Quotation Bill for New Service Connection at Kulihanda W/S. Sch. TW-VI | 420 | 10/11/2023 | 0 | WBSEDCL | 5.1 | 0 | 0 | 0
1900 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13345 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kulihanda water supply scheme, T.W. No. VI, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | 3529/ED | 18/08/2023 | 90 | N.S. TRADING | 10.56 | 10.27 | 97.28 | 90
1901 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13345 | Augmentation | Sinking of 2 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) At KULIHANDA & SRIPUR W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. | 2409/HUG | 11/08/2023 | 30 | OSMAN SEKH | 32.34 | 15 | 48.75 | 100
1902 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13345 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of different PWSS under CHINSURAH-MOGRA Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | 2427/HUG | 11/08/2023 | 30 | SWASTIK ENTERPRISE | 42.74 | 41.58 | 100 | 95
1903 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13345 | Augmentation | Quotation for new service connection at Kulihanda[SM/13345] W/S Sch., T/W No. - VII, Sukantanagar, Dt. - Hooghly, Ref. Id. - 503611685, Dt. - 8/04/2024, Application No. - 5004102924 under Pipulpati CCC, WBSEDCL | 55 | 12/04/2024 | 0 | WBSEDCL | 8.56 | 0 | 0 | 0
1904 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13345 | Augmentation | Quotation for new service connection at Kulihanda W/S (Aug.)[SM/13345] Scheme, T/W No. - VIII,(Adarsha Nagar, Panditjir Dokan) under Bandel CCC, WBSEDCL, Ref. Id. - 503647843, Dt. - 17-05-2024, Application No. - 5004191804 | 177 | 30/05/2024 | 0 | WBSEDCL | 6.18 | 0 | 0 | 0
1905 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF KULIHANDA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13345 | Augmentation | Construction of Switch Room & Boundary Wall in Proposed T.W Sites, Laying Distribution System, Laying rising main pipe line for interconnection between T.W & Distribution, Repairing of Switch Room & Boundary Wall and other allied work for Source Augmentation of KULIHANDA Piped Water Supply Scheme Under Hooghly Division P.H.E. Dte. within Chinsurah Mogra Block. | 327/HUG | 03/02/2023 | 1063 | PREMANANDA ROY BISWAS | 121.55 | 83.44 | 68.65 | 80
1906 | HOOGHLY | Electrical | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly , SM/14982 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gobindanagar water supply scheme, Zone-II, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | 766/ED | 09/02/2023 | 90 | BARISAL TRADING CO. | 20.5 | 0 | 0 | 0
1907 | HOOGHLY | Hooghly Division | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly , SM/14982 | New | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement ,Construction of Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution of GOBINDANAGAR ZONE-II Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | 2452/HUG | 12/08/2023 | 60 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 16.55 | 0 | 0 | 0
1908 | HOOGHLY | Hooghly Division | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly , SM/14982 | New | Material Requisition To Resource Division | 1385/32/Hug | 15/05/2023 | 0 | Resource Division | 11.27 | 0 | 0 | 0
1909 | HOOGHLY | Hooghly Division | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly , SM/14982 | New | Material Requisition To Resource Division | 3057/41/Hug | 11/10/2023 | 0 | Resource Division | 11.27 | 0 | 0 | 0
1910 | HOOGHLY | Hooghly Division | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly , SM/14982 | New | Material Requisition To Resource Division | 1234/23/Hug | 28/04/2023 | 0 | Resource Division | 70.25 | 0 | 0 | 0
1911 | HOOGHLY | Electrical | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly , SM/14982 | New | Quotation of new Service Connection for Gobindanagar Water supply Scheme,Zone-II,PH No-I Block-Arambag Dist-hooghly under Electrical Division PHE Dte | 314 | 03/10/2023 | 0 | WBSEDCL | 4.73 | 0 | 0 | 0
1912 | HOOGHLY | Electrical | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly , SM/14982 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gobindanagar water supply scheme, Zone-II, T.W. No. III, Block: Goghat-I, District: Hooghly under Electrical Division, PHE Dte. | 333/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.43 | 0 | 0 | 0
1913 | HOOGHLY | Hooghly Division | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly , SM/14982 | New | GOBINDANAGAR (ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-I Block of Arambag Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | 1520/HUG | 23/05/2023 | 954 | BAPPADITYA BANERJEE | 500 | 295.72 | 59.14 | 20
1914 | HOOGHLY | Hooghly Division | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly , SM/14982 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GOBINDANAGAR (ZONE-II) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | 595/HUG | 22/02/2024 | 393 | BAPPADITYA BANERJEE | 31.58 | 0 | 0 | 50
1915 | HOOGHLY | Hooghly Division | Gobindanagar (Zone-II) Piped Water Supply Scheme, Block- Goghat-I, District- Hooghly , SM/14982 | New | Additional works for Laying Distribution main by HDD process at Gopalbati and Gobindanagar Zone II W/S Schme under Arambagh Sub Division of Hooghly Division, P.H.E. Dte. | 3687/HUG | 14/11/2024 | 331 | MS PRADIP KUMAR PAL | 14.33 | 0 | 0 | 0
1916 | HOOGHLY | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/14684 | New | Material Requisition To Resource Division | 1385/39/Hug | 15/05/2023 | 0 | Resource Division | 4.96 | 0 | 0 | 0
1917 | HOOGHLY | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/14684 | New | Material Requisition To Resource Division | 3057/36/Hug | 11/10/2023 | 0 | Resource Division | 4.96 | 0 | 0 | 0
1918 | HOOGHLY | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/14684 | New | Additional Quotation for Shantipur w/s Scheme,Zone-II,PH no-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte,(SM/14684) Application No-100000124534 Reference Id-860319604 | 636 | 18/12/2024 | 0 | WBSEDCL | 0.91 | 0 | 0 | 0
1919 | HOOGHLY | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/14684 | New | Quotation of New service Connection at Shantipur w/s Scheme,Zone-II,PH No-II Block-Goghat-II District-Hooghly under Electrical division,PHE Dte.(SM/14684) Application No-5004136393 Reference Id-503627261. | 96 | 06/05/2024 | 0 | WBSEDCL | 3.39 | 0 | 0 | 0
1920 | HOOGHLY | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/14684 | New | Quotation App. No.-5004182874 SM/14684 | 117 | 17/05/2024 | 0 | WBSEDCL | 13.85 | 0 | 0 | 0
1921 | HOOGHLY | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/14684 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Shantipur water supply scheme, Zone-II, T.W. No.- I & II, Block: Goghat-II District- Hooghly under Electrical Division, PHE Dte. | 775/ED | 09/02/2023 | 996 | A.G. ENTERPRISE | 20.26 | 0 | 0 | 40
1922 | HOOGHLY | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/14684 | New | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | 3190/HUG | 31/10/2023 | 609 | M/S PRITI ENTERPRISE | 4251.5 | 120.14 | 46.78 | 30
1923 | HOOGHLY | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/14684 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 464/HUG | 20/02/2025 | 30 | TECHVISION | 6.59 | 0 | 0 | 0
1924 | HOOGHLY | Electrical | GROUND WATER BASED RADHABALLAVPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14118 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Radhaballavpur water supply scheme, Zone-I, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | 772/ED | 09/02/2023 | 90 | BIJAN ENTERPRISE | 20.26 | 0 | 0 | 0
1925 | HOOGHLY | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14118 | New | Material Requisition To Resource Division | 1385/56/Hug | 15/05/2023 | 0 | Resource Division | 13.04 | 0 | 0 | 0
1926 | HOOGHLY | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14118 | New | Material Requisition To Resource Division | 3057/14/Hug | 11/10/2023 | 0 | Resource Division | 13.04 | 0 | 0 | 0
1927 | HOOGHLY | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14118 | New | Material Requisition To Resource Division | 127/23/Hug | 13/01/2023 | 0 | Resource Division | 29.92 | 0 | 0 | 0
1928 | HOOGHLY | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14118 | New | Material Requisition To Resource Division | 1234/36/Hug | 28/04/2023 | 0 | Resource Division | 29.41 | 0 | 0 | 0
1929 | HOOGHLY | Electrical | GROUND WATER BASED RADHABALLAVPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14118 | New | Quotation Bill for New Service Connection at Radhaballavpur W/S. Sch. TW-II | 572 | 27/12/2023 | 0 | WBSEDCL | 6.9 | 0 | 0 | 0
1930 | HOOGHLY | Electrical | GROUND WATER BASED RADHABALLAVPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14118 | New | Quotation Bill for New Service Connection at Radhaballavpur W/S. Sch. TW-I | 573 | 27/12/2023 | 0 | WBSEDCL | 11.45 | 0 | 0 | 0
1931 | HOOGHLY | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14118 | New | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at RADHABALLAVPUR Z-I, BENGAI, SAMANTAKHANDA and BHURKUNDA Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 724/HUG | 05/03/2024 | 60 | RUNA ENTERPRISE | 64.27 | 0 | 0 | 0
1932 | HOOGHLY | Electrical | GROUND WATER BASED RADHABALLAVPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14118 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RADHABALLAVPUR PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1179/ED | 14/06/2024 | 90 | BIJAN ENTERPRISE | 10.7 | 0 | 0 | 0
1933 | HOOGHLY | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14118 | New | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of RADHABALLAVPUR Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 3787/HUG | 25/11/2024 | 30 | SUDIPTA SINHA | 16.07 | 0 | 0 | 0
1934 | HOOGHLY | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14118 | New | Construction of 3 nos. 5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of MOHISHGOT Zone-II, RADHABALLAVPUR Zone-I , DHARAMPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3780/HUG | 25/11/2024 | 60 | ROY ENTERPRISE | 55.39 | 0 | 0 | 0
1935 | HOOGHLY | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14118 | New | MAHISGOT (ZONE-I), MAHISGOT (ZONE-II), POL, RADHABALLAVPUR (ZONE-I), UDAYPUR, UDNA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte | 3139/HUG | 16/10/2023 | 808 | MACKINTOSH BURN LIMITED | 3480.01 | 201.51 | 40.98 | 45
1936 | HOOGHLY | Hooghly Division | GROUND WATER BASED RADHABALLAVPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/14118 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0 | 0
1937 | HOOGHLY | Hooghly Division | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/14531 | New | Material Requisition To Resource Division | 1386/18/Hug | 15/05/2023 | 0 | Resource Division | 31.19 | 0 | 0 | 0
1938 | HOOGHLY | Hooghly Division | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/14531 | New | Material Requisition To Resource Division | 3059/13/Hug | 11/10/2023 | 0 | Resource Division | 31.19 | 0 | 0 | 0
1939 | HOOGHLY | Hooghly Division | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/14531 | New | Material Requisition To Resource Division | 1264/21/HUG | 03/05/2023 | 0 | Resource Division | 33.14 | 0 | 0 | 0
1940 | HOOGHLY | Electrical | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/14531 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dashghara water supply scheme, Zone-I, T.W. No. I & II and Zone-II, T.W. No. I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | 919/ED | 22/02/2023 | 90 | H.K.DAS & CO. | 43.01 | 18.12 | 42.12 | 35
1941 | HOOGHLY | Hooghly Division | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/14531 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BISHNUPUR, DASHGHARA ZONE-I, DASHGHARA ZONE-II (1NO.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.. | 2407/HUG | 11/08/2023 | 45 | GEE BEE NIRMAN CO PRIVATE LIMITED | 81.62 | 44.87 | 91.62 | 40
1942 | HOOGHLY | Hooghly Division | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/14531 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For DASHGHARA ZONE-II (1 NO.), GURBARI, SHRIRAMPUR W/S Scheme under CHISURAH Sub-Division of Hooghly Division, P.H.E. Dte. | 2408/HUG | 11/08/2023 | 45 | GEE BEE NIRMAN CO PRIVATE LIMITED | 81.62 | 14.09 | 86.32 | 20
1943 | HOOGHLY | Electrical | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/14531 | New | Quotation Bill for New Service Connection at Dashghara W/S. Sch. TW-I | 701 | 22/01/2024 | 0 | WBSEDCL | 12.21 | 0 | 0 | 0
1944 | HOOGHLY | Electrical | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/14531 | New | Quotation Bill for New Service Connection at Dhasghara W/S. Sch. Z-I, TW-II & Z-ii, TW-I | 676 & 677 | 18/01/2024 | 0 | WBSEDCL | 12.17 | 0 | 0 | 0
1945 | HOOGHLY | Electrical | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/14531 | New | Quotation Bill for New Service Connection at Dashghara W/S. Sch. TW-II | 700 | 22/01/2024 | 0 | WBSEDCL | 9.7 | 0 | 0 | 0
1946 | HOOGHLY | Hooghly Division | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/14531 | New | Construction of Different Capacity RCC Over Head Reservoir over Pile/Raft Foundation including Sub-soil investigation works for OHR, with Laying Distribution System Providing Functional House hold Tap Connection for BISHNUPUR, DOSGHARA(zone-I), DOSGHARA(zone-II), GURBARI & SRIRAMPUR Piped Water Supply Scheme within DHANIAKHALI block under chinshuraH Sub-Division of Hooghly division, PHE Dte. Under Hooghly district in connection with JJM. | 2066/HUG | 17/07/2023 | 747 | GEE BEE NIRMAN CO PRIVATE LIMITED | 2255.89 | 553.91 | 61.38 | 20
1947 | HOOGHLY | Hooghly Division | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/14531 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of switch-rooms & boundary walls at different TW site for Dasghara (Zone-II) Piped Water Supply Scheme under Chinsurah Sub-Division Block-Dhaniakhali , District:- Hooghly. | 2417/HUG | 11/08/2023 | 589 | GEE BEE NIRMAN CO PRIVATE LIMITED | 52.06 | 8.6 | 16.51 | 30
1948 | HOOGHLY | Hooghly Division | DASHGHARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/14531 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of switch-rooms & boundary walls at different TW site for Dasghara (Zone-I) Piped Water Supply Scheme under Chinsurah Sub-Division Block-Dhaniakhali , District:- Hooghly. | 2416/HUG | 11/08/2023 | 589 | GEE BEE NIRMAN CO PRIVATE LIMITED | 53.78 | 8.6 | 15.98 | 28
1949 | HOOGHLY | Hooghly Division | Development of Jangalpara Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat under , SM/16448 | Augmentation | Material Requisition To Resource Division | 1384/22/Hug | 15/05/2023 | 0 | Resource Division | 2.77 | 0 | 0 | 0
1950 | HOOGHLY | Electrical | Development of Jangalpara Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat under , SM/16448 | Augmentation | Quotation bill for new service connection at Jangalpara W/S. Sch. PH-III | 34 | 12/05/2023 | 0 | WBSEDCL | 2.96 | 0 | 0 | 0
1951 | HOOGHLY | Electrical | Development of Jangalpara Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat under , SM/16448 | Augmentation | New service connection charges for Jangalpara w/s scheme, PH No.-III | 87 | 12/07/2023 | 0 | WBSEDCL | 0.53 | 0 | 0 | 0
1952 | HOOGHLY | Electrical | Development of Jangalpara Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat under , SM/16448 | Augmentation | New service connection charges for Jangalpara w/s scheme, PH No.-III | 85 | 12/07/2023 | 0 | WBSEDCL | 2.95 | 0 | 0 | 0
1953 | HOOGHLY | Hooghly Division | Development of Jangalpara Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat under , SM/16448 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed T.W. with distribution system with FHTC For Development of JANGALPARA W/S Scheme under Serampore Sub - Division P.H.E. Dte. | 1439/HUG | 18/05/2023 | 45 | CITYCON UNEMPLOYED ENGINEERS CO-OP SOCIETY LTD | 35.13 | 24.27 | 100 | 20
1954 | HOOGHLY | Electrical | Development of Jangalpara Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat under , SM/16448 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jangalpara water supply scheme, T.W. No. I, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | 1501/ED | 28/03/2023 | 338 | INDRANI ENTERPRISE | 10.75 | 10.44 | 97.1 | 75
1955 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME , SM/15891 | Augmentation | Car Hire Charges Bill for official use of the Howrah Mechanical Sub-Division PHED | 958,HMSD | 20/04/2023 | 365 | ARINDAM AUDDY | 5 | 0.79 | 15.73 | 50
1956 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME , SM/15891 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DHARAMPUR PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 1129/HUG | 19/04/2023 | 45 | M/S SHIVAM UDYOG | 54.23 | 38.37 | 100 | 97
1957 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME , SM/15891 | Augmentation | Hire Charges Bill for official use office of the Howrah Mechanical Sub-Division PHED | 958/HmSD | 20/04/2023 | 365 | ARINDAM AUDDY | 5 | 0.39 | 100 | 1
1958 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME , SM/15891 | Augmentation | Material Requisition To Resource Division | 3059/32/Hug | 11/10/2023 | 0 | Resource Division | 14.49 | 0 | 0 | 0
1959 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME , SM/15891 | Augmentation | Material Requisition To Resource Division | 1234/35/Hug | 28/04/2023 | 0 | Resource Division | 19.68 | 0 | 0 | 0
1960 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME , SM/15891 | Augmentation | Supply, delivery and installation of voltage correcting device and other allied works for DHARAMPUR w/s scheme, P.H No.- II, Dist- Hooghly under Electrical Division, PHE Dte. | 177 | 02/03/2023 | 0 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 2.72 | 0 | 0 | 0
1961 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME , SM/15891 | Augmentation | Supply, delivery & installation of Automatic Chlorinator for Dharampur water supply scheme, P.H. No.- II, District - Hooghly under Electrical Division, PHE Dte. | 177 | 02/03/2023 | 0 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 0.76 | 0 | 0 | 0
1962 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME , SM/15891 | Augmentation | Supply, Delivery & Installation of Submersible Pumping machinery and other Electrical/mechanical equipments etc. including allied works for Dharampur w/s scheme | 178 | 02/03/2023 | 0 | H.K.DAS & CO. | 4.32 | 0 | 0 | 0
1963 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME , SM/15891 | Augmentation | Quotation for new service connection at Dharampur W/S Sch. , T/W No. -I (Aug.), Block - Chinsurah-Mogra, Dist. - Hooghly | 282 | 13/09/2023 | 0 | WBSEDCL | 0.64 | 0 | 0 | 0
1964 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME , SM/15891 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. | 2829/HMSD | 30/10/2023 | 182 | ARINDAM AUDDY | 0.86 | 1.57 | 259.98 | 15
1965 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME , SM/15891 | Augmentation | Construction of 1 No. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Construction of 2 nos. Boundary wall &Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos.T.W with distribution system, FHTC of DHARAMPUR W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | 1341/HUG | 11/05/2023 | 45 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 44.76 | 19.81 | 37.04 | 75
1966 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME , SM/15891 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Dharampur water supply scheme, T.W. No. I & II, Block: Chinsura-Mogra, District - Hooghly under Electrical Division, PHE Dte. | 4693/ED | 08/12/2023 | 90 | BISALAXMI ENTERPRISE | 21.99 | 21.97 | 100 | 49
1967 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME , SM/15891 | Augmentation | Supply of Fuel for 1(one) no Diesel Luxury Taxi on contract Carriage for the Office of the assistant Engineer Howrah Mechanical Sub Division PHE Dte for the Month of March 2024. |  | 12/04/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
1968 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME , SM/15891 | Augmentation | Quotation for new service connection at Augmentation of Dharampur W/S Sch.[SM/15891], T/W No. - II, South Simla, Block - Chinsurah-Mogra Dist. - Hooghly under Bandel CCC, WBSEDCL, Ref. Id. - 503599481, Dt. - 22-03-2024, Application No. - 5004078318 | 15 | 04/04/2024 | 0 | WBSEDCL | 7.75 | 0 | 0 | 0
1969 | HOOGHLY | Electrical | Source Augmentation of KANPUR Piped Water Supply Scheme under Arambag Block , SM/15811 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kanpur water supply scheme, T.W. No. I, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 1503/ED | 28/03/2023 | 90 | BISALAXMI ENTERPRISE | 10.73 | 0 | 0 | 0
1970 | HOOGHLY | Hooghly Division | Source Augmentation of KANPUR Piped Water Supply Scheme under Arambag Block , SM/15811 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of Kanpur Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | 1495/HUG | 22/05/2023 | 30 | SONAR BANGLA ENTERPRISE | 11.78 | 0 | 0 | 0
1971 | HOOGHLY | Hooghly Division | Source Augmentation of KANPUR Piped Water Supply Scheme under Arambag Block , SM/15811 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at KANPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | 1427/HUG | 17/05/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.53 | 0 | 0 | 0
1972 | HOOGHLY | Hooghly Division | Source Augmentation of KANPUR Piped Water Supply Scheme under Arambag Block , SM/15811 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir for KANPUR PWSS Under Arambagh Sub Division Hooghly Division, P.H.E. Dte. | 3778/HUG | 25/11/2024 | 40 | MAA JAGADHATRI CONSTRUCTION | 10.4 | 0 | 0 | 100
1973 | HOOGHLY | Electrical | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block , SM/15812 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dakshin Rasulpur water supply scheme, T.W. No. I, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 1499/ED | 28/03/2023 | 90 | KARUNAMOY ENGINEERING | 10.74 | 0 | 0 | 0
1974 | HOOGHLY | Hooghly Division | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block , SM/15812 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | 1493/HUG | 22/05/2023 | 30 | SHREEOM ENTERPRISE | 12.1 | 0 | 0 | 0
1975 | HOOGHLY | Hooghly Division | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block , SM/15812 | Augmentation | Material Requisition To Resource Division | 127/07/Hug | 13/01/2023 | 0 | Resource Division | 11.35 | 0 | 0 | 0
1976 | HOOGHLY | Hooghly Division | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block , SM/15812 | Augmentation | Material Requisition To Resource Division | 1263/6/Hug | 03/05/2023 | 0 | Resource Division | 9.76 | 0 | 0 | 0
1977 | HOOGHLY | Electrical | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block , SM/15813 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bhangamora water supply scheme, T.W. No. I, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | 1497/ED | 28/03/2023 | 90 | KAMAKHYA ENTERPRISE | 10.69 | 0 | 0 | 0
1978 | HOOGHLY | Hooghly Division | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block , SM/15813 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Pursurah Block. | 1461/HUG | 18/05/2023 | 30 | S. B. CONSTRUCTION | 11.97 | 0 | 0 | 0
1979 | HOOGHLY | Electrical | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block , SM/15813 | Augmentation | Quotation Bill for New Service Connection at Bhangamora W/S. Sch. TW-III | 391 | 03/11/2023 | 0 | WBSEDCL | 7.9 | 0 | 0 | 0
1980 | HOOGHLY | Hooghly Division | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block , SM/15813 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of BHANGAMORA, SAOTA, PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 4081/HUG | 19/12/2024 | 90 | R.K. TRADERS | 20.96 | 0 | 0 | 0
1981 | HOOGHLY | Hooghly Division | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block , SM/15813 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at BHANGAMORA PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | 744/HUG | 15/03/2023 | 30 | MAYA CONSTRUCTION | 11.32 | 11.36 | 100 | 100
1982 | HOOGHLY | Hooghly Division | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block , SM/15813 | Augmentation | Supply of 200 mm dia CD pipe for Sinking of Tubewell at Bhangamora W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 471/Arg | 05/07/2023 | 15 | MAYA CONSTRUCTION | 0.97 | 0.97 | 100 | 100
1983 | HOOGHLY | Hooghly Division | Bighati Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/16236 | New | Material Requisition To Resource Division | 1235/4/Hug | 28/04/2023 | 0 | Resource Division | 34.06 | 0 | 0 | 0
1984 | HOOGHLY | Electrical | Bighati Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/16236 | New | Quotation for new service connection at Bighati w/s sch. (Zone - I), T/W -II, dt. - Hooghly | 223 | 28/08/2023 | 0 | WBSEDCL | 5.21 | 0 | 0 | 0
1985 | HOOGHLY | Electrical | Bighati Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/16236 | New | Quotation Bill for New Service Connection at Bighati W/S. Sch. TW-I, Z-II | 423 | 10/11/2023 | 0 | WBSEDCL | 5.25 | 0 | 0 | 0
1986 | HOOGHLY | Electrical | Bighati Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/16236 | New | Quotation for new service connection at Bighati W/s Scheme, Zone - I, T/W - I | 380 | 25/10/2023 | 0 | WBSEDCL | 3.78 | 0 | 0 | 0
1987 | HOOGHLY | Hooghly Division | Bighati Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/16236 | New | Restoration work for the damages Chandannagar Nasibpur Road to Vhadreswar Station road | BP-2023-24-853 | 21/02/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 43.24 | 0 | 0 | 0
1988 | HOOGHLY | Electrical | Bighati Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/16236 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bighati water supply scheme, Zone-I, T.W. No.- I & II and Zone-II, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | 1242/ED | 06/03/2023 | 630 | ORIENTAL ENGINEERING CO. | 40.49 | 20.23 | 100 | 80
1989 | HOOGHLY | Hooghly Division | GROUND WATER BASED NAOPARA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/16237 | New | Material Requisition To Resource Division | 1385/10/Hug | 15/05/2023 | 0 | Resource Division | 0.47 | 0 | 0 | 0
1990 | HOOGHLY | Hooghly Division | GROUND WATER BASED NAOPARA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/16237 | New | Material Requisition To Resource Division | 3057/59/Hug | 11/10/2023 | 0 | Resource Division | 0.76 | 0 | 0 | 0
1991 | HOOGHLY | Hooghly Division | GROUND WATER BASED NAOPARA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/16237 | New | Material Requisition To Resource Division | 1263/2/Hug | 03/05/2023 | 0 | Resource Division | 24.41 | 0 | 0 | 0
1992 | HOOGHLY | Electrical | GROUND WATER BASED NAOPARA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/16237 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for NAOPARA MINI W/S SCHEME, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1191/ED | 14/06/2024 | 90 | MAA TARA CONSTRUCTION | 7.52 | 7.23 | 96.1 | 30
1993 | HOOGHLY | Electrical | GROUND WATER BASED NAOPARA PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/16237 | New | Quotation of new service Connection for Naopara w/s Scheme,PH No-I Block-Khanakul-II, Dist-Hooghly under ED,PHE Dte(SM/16237) Application No-5004015680 Reference Id-503563156 | 751 | 16/02/2024 | 0 | WBSEDCL | 0.2 | 0 | 0 | 0
1994 | HOOGHLY | Electrical | Source Augmentation of Hazipur Piped Water Supply Scheme under Goghat-II Block , SM/15815 | Augmentation | Supply, Delivery & Installation of submersible Pumping Machinery & other allied electrical/mechanical equipments etc. incliding allied works for Hazipur W/S. Sch. | 555/ED | 23/03/2022 | 90 | GLACIER ENGINEERING CO. | 6.62 | 0 | 0 | 60
1995 | HOOGHLY | Hooghly Division | Source Augmentation of Hazipur Piped Water Supply Scheme under Goghat-II Block , SM/15815 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room & Construction of boundary wall at 3rd Tube well Site of HAZIPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 4082/HUG | 19/12/2024 | 90 | DAS TRADING | 21.34 | 0 | 0 | 0
1996 | HOOGHLY | Hooghly Division | BALIDAHA PWSS PIPED WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK. , SM/18101 | New | Material Requisition To Resource Division | 1386/43/Hug | 15/05/2023 | 0 | Resource Division | 2.02 | 0 | 0 | 0
1997 | HOOGHLY | Hooghly Division | BALIDAHA PWSS PIPED WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK. , SM/18101 | New | Material Requisition To Resource Division | 3004/16/Hug | 05/10/2023 | 0 | Resource Division | 14.45 | 0 | 0 | 0
1998 | HOOGHLY | Electrical | BALIDAHA PWSS PIPED WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK. , SM/18101 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Balidaha water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | 1922/ED | 15/05/2023 | 90 | D. K. ELECTRIC | 22.6 | 11.01 | 48.71 | 50
1999 | HOOGHLY | Hooghly Division | BALIDAHA PWSS PIPED WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK. , SM/18101 | New | BALIDAHA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. Block DHANIAKHALI, District:- Hooghly [NEW SCHEME] | 1363/HUG | 12/05/2023 | 90 | MA KANKALI ENTERPRISE | 85.78 | 85.65 | 100 | 92
2000 | HOOGHLY | Hooghly Division | BALIDAHA PWSS PIPED WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK. , SM/18101 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Chautara PWSS 2. Hasnan PWSS 3. Bhatua PWSS 4. Balidaha PWSS 5. Dalimba PWSS 6. Simla PWSS | 142/CH | 20/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 50 | 30
2001 | HOOGHLY | Electrical | BALIDAHA PWSS PIPED WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK. , SM/18101 | New | Quotation Bill for New Service Connection at Balidaha W/S. Sch. TW-I | 682 | 19/01/2024 | 0 | WBSEDCL | 3.71 | 0 | 0 | 0
2002 | HOOGHLY | Hooghly Division | Retrofitting works for providing functional household tap connection within the left out mouza of Baruipara water supply scheme , SM/18110 | Retrofitting | Laying of rising main for Interconnection of Laying Distribution System & 7 th Tubewell Including Protection Work of BARUIPARA Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | 2141/HUG | 26/09/2022 | 20 | AMBIAN INFRASTRUTTURE | 5.97 | 5.96 | 99.94 | 0
2003 | HOOGHLY | Hooghly Division | Retrofitting works for providing functional household tap connection within the left out mouza of Baruipara water supply scheme , SM/18110 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas of BARUIPARA PWSS under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | 2433/HUG | 11/08/2023 | 90 | MALLIKA ENTERPRISE | 95.97 | 95.95 | 99.98 | 50
2004 | HOOGHLY | Hooghly Division | Retrofitting works for providing functional household tap connection within the left out mouza of Baruipara water supply scheme , SM/18110 | Retrofitting | Repair and Renovation Works of R.C.C. Elevated Reservoir of BARUIPARA PWSS under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 4070/HUG | 19/12/2024 | 90 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 13.04 | 0 | 0 | 0
2005 | HOOGHLY | Hooghly Division | Retrofitting works for providing functional household tap connection within the left out mouza of Baruipara water supply scheme , SM/18110 | Retrofitting | Surging/Development of old tubewell using suitable air compressor to increase the yield at different Water Supply Scheme within Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. (Baruipara 5 Tube Well, Bandipur 3rd Tube Well) | 958/CHAN | 23/07/2025 | 15 | G. T. AGRO CENTRE | 1.47 | 0 | 0 | 100
2006 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAHISHGOT PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17290 | New | Material Requisition To Resource Division | 3057/7/Hug | 11/10/2023 | 0 | Resource Division | 4.35 | 0 | 0 | 0
2007 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAHISHGOT PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17290 | New | Material Requisition To Resource Division | 1234/18/Hug | 28/04/2023 | 0 | Resource Division | 9.11 | 0 | 0 | 0
2008 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAHISHGOT PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17290 | New | MAHISGOT Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under ARAMBAGH Block, District:- Hooghly [NEW SCHEME] | 861/HUG | 24/03/2023 | 270 | M/S R.M. CONSTRUCTION | 221.92 | 69.65 | 31.39 | 15
2009 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAHISHGOT PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17290 | New | Construction of 3 nos. 5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of MOHISHGOT Zone-II, RADHABALLAVPUR Zone-I , DHARAMPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3780/HUG | 25/11/2024 | 60 | ROY ENTERPRISE | 55.39 | 0 | 0 | 0
2010 | HOOGHLY | Electrical | GROUND WATER BASED MAHISHGOT PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17290 | New | Quotation Bill for New Service Connection at Mahisgot W/S. Sch. PH-I | 794 | 22/02/2024 | 0 | WBSEDCL | 20.71 | 0 | 0 | 0
2011 | HOOGHLY | Electrical | GROUND WATER BASED MAHISHGOT PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17290 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Mahishgot water supply scheme TW No I and II Block Arambag, District Hooghly under ED PHED. | 1999/ED | 19/05/2023 | 958 | AMITAVA CHAKRABORTY | 20.29 | 0 | 0 | 30
2012 | HOOGHLY | Electrical | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly , SM/18310 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for POL water supply scheme, T.W. No.- I, II & III, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | 3158/ED | 27/07/2023 | 90 | DAS ENTERPRISE | 30.48 | 0 | 0 | 0
2013 | HOOGHLY | Hooghly Division | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly , SM/18310 | New | Material Requisition To Resource Division | 3057/2/Hug | 11/10/2023 | 0 | Resource Division | 19.44 | 0 | 0 | 0
2014 | HOOGHLY | Electrical | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly , SM/18310 | New | Quotation money deposition for new service connection at POL w/s scheme, T.W. No.-I, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004036811/Quot/03 Reference ID- 503576702 SM Code- 18310 | 821 | 01/03/2024 | 0 | WBSEDCL | 3.87 | 0 | 0 | 0
2015 | HOOGHLY | Electrical | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly , SM/18310 | New | Quotation money deposition for new service connection at POL w/s scheme, T.W. No.-II, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004037073/Quot/03 Reference ID- 503576717 SM Code- 18310 | 820 | 01/03/2024 | 0 | WBSEDCL | 3.54 | 0 | 0 | 0
2016 | HOOGHLY | Hooghly Division | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly , SM/18310 | New | MAHISGOT (ZONE-I), MAHISGOT (ZONE-II), POL, RADHABALLAVPUR (ZONE-I), UDAYPUR, UDNA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte | 3139/HUG | 16/10/2023 | 808 | MACKINTOSH BURN LIMITED | 3480.01 | 298.46 | 40.82 | 45
2017 | HOOGHLY | Hooghly Division | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly , SM/18310 | New | Sinking of 2 nos 300 X200 mm dia Tube Well ,210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of POL W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3527/HUG | 22/10/2024 | 221 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 32.12 | 0 | 0 | 50
2018 | HOOGHLY | Hooghly Division | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly , SM/18310 | New | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at POL (2Nos.), MOSTAFAPUR (2Nos.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3434/HUG | 03/10/2024 | 360 | DIBYENDU DHARA | 47.26 | 0 | 0 | 50
2019 | HOOGHLY | Hooghly Division | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly , SM/18310 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0 | 0
2020 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | Construction of 16.75 m X 12 m Pumphouse including plinth protection and surface drain at Pandua IBS-I site ofSurface Water Base Piped Water Supply Scheme Balagarh & Pandua Under Hooghly Division, P.H.E. Dte. | 3347/HUG | 17/11/2023 | 180 | MS PRADIP KUMAR PAL | 64.72 | 0 | 0 | 0
2021 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | Construction of 16.75 m X 12 m Pumphouse including plinth protection and surface drain at Pandua IBS-II site ofSurface Water Base Piped Water Supply Scheme Balagarh & Pandua Under Hooghly Division, P.H.E. Dte. | 3348/HUG | 17/11/2023 | 180 | R.G. INFRASTRUCTURE | 64.76 | 0 | 0 | 0
2022 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | Construction of C.W.R. (Clear water Reservoir) of capacity 350 Cu.m / 77000 Gallons & allied Work at Pandua IBS-I site of Surface Water Base Piped Water Supply Scheme Balagarh & Pandua Under Hooghly Division, P.H.E. Dte. | 3349/HUG | 17/11/2023 | 180 | MS PRADIP KUMAR PAL | 37.76 | 0 | 0 | 0
2023 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | Construction of C.W.R. (Clear water Reservoir) of capacity 450 Cu.m / 9900 Gallons & allied Work at Pandua IBS-II site of Surface Water Base Piped Water Supply Scheme Balagarh & Pandua Under Hooghly Division, P.H.E. Dte. | 3350/HUG | 17/11/2023 | 180 | R.G. INFRASTRUCTURE | 47.67 | 0 | 0 | 0
2024 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | Material Requisition To Resource Division | 3059/23/Hug | 11/10/2023 | 0 | Resource Division | 638.35 | 0 | 0 | 0
2025 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | ROAD RESTORATION PAYMENT TO PWD FOR G.T.ROAD TO SARAI LINK ROAD ROAD | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 3.96 | 0 | 0 | 0
2026 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | link road from STKK to Borail | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 3.85 | 0 | 0 | 0
2027 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | PAYMENT TO ROAD RESTORATION TO PWD PANDUA ROAD | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 7.96 | 0 | 0 | 0
2028 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | PAYMENT TO ROAD RESTORATION TO PWD PANDUA KANTAI ROAD | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 3.18 | 0 | 0 | 0
2029 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | Balagarh Inchura Road Restoration | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 16.53 | 0 | 0 | 0
2030 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | jeerat feeder road STKK to Balagarh | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 1.05 | 0 | 0 | 0
2031 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | Tamba Kamarpara Road Restoration | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 16.81 | 0 | 0 | 0
2032 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | feeder road from STKK to Balagarh | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 6.58 | 0 | 0 | 0
2033 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | Feeder road from STKK to Khamargachi | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 4.03 | 0 | 0 | 0
2034 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | Tamba Ilchoba Road Restoration | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 9.39 | 0 | 0 | 0
2035 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | PAYMENT TO ROAD RESTORATION TO PWD RAHIMPUR KALNA ROAD | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 7.15 | 0 | 0 | 0
2036 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | Pandua Kulti Road Restoration | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 19.73 | 0 | 0 | 0
2037 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | ROAD RESTORATION PAYMENT TO PWD FOR NAKSA DIGSUI INCHURA ROAD | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 24.45 | 0 | 0 | 0
2038 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | ROAD RESTORATION PAYMENT TO PWD FOR SINGUR UGLY ROAD | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 21.76 | 0 | 0 | 0
2039 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | Feeder road from STKK | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 10.3 | 0 | 0 | 0
2040 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | Feeder road from STKK to Sripur Bazar Road | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 4.27 | 0 | 0 | 0
2041 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Pandua Block in Hooghly District with three months trial run & subsequent O&M for one year.. | 3309/HUG | 10/11/2023 | 783 | ECO PROTECTIONENGINEERS PVT LTD. | 19490.9 | 3306.97 | 16.97 | 25
2042 | HOOGHLY | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh Block in Hooghly District with three months trial run & subsequent O&M for one year. | 3310/HUG | 10/11/2023 | 783 | ECO PROTECTIONENGINEERS PVT LTD. | 11029.1 | 1717.6 | 15.57 | 35
2043 | HOOGHLY | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District , SM/19036 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery for Intermediate Pumping Station (IPS-I) to be installed at Boinchi Gram and Intermediate Pumping Station (IPS-2) to be installed at Damdama Gram under Balagarh-Pandua Surface Based Pipe Water Supply Scheme, in the Dist. of Hooghly under Electrical Division, P.H.E, Dte. | 660/ED | 24/04/2025 | 30 | M/S S.S. ENTERPRISE | 234.37 | 0 | 0 | 0
2044 | HOOGHLY | Electrical | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18594 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Balundi water supply scheme, T.W. No.- I & II, Block: Aambag, District- Hooghly under Electrical Division, PHE Dte. | 3583/ED | 28/08/2023 | 90 | M/S G P ENTERPRISE | 21.47 | 0 | 0 | 0
2045 | HOOGHLY | Hooghly Division | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18594 | New | Material Requisition To Resource Division | 3057/46/Hug | 11/10/2023 | 0 | Resource Division | 15.4 | 0 | 0 | 0
2046 | HOOGHLY | Electrical | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18594 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BALUNDI PIPED W/S SCHEME, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1155/ED | 14/06/2024 | 90 | DEY ENTERPRISE | 10.75 | 0 | 0 | 0
2047 | HOOGHLY | Electrical | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18594 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BALUNDI PIPED W/S SCHEME, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1156/ED | 14/06/2024 | 90 | DEY ENTERPRISE | 10.75 | 0 | 0 | 0
2048 | HOOGHLY | Electrical | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18594 | New | Quotation of New Service Connection for Balundi w/s Scheme, PH No-III Block-Arambag, Dist-Hooghly under Electrical Division, PHE Dte.(SM/18594) Application No-5004182716 Reference Id-503644451. | 119 | 17/05/2024 | 0 | WBSEDCL | 4.71 | 0 | 0 | 0
2049 | HOOGHLY | Electrical | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18594 | New | Quotation of New Service Connection for Balundi w/s Scheme,PH No-I Block-Arambag,Dist-Hooghly under Electrical Division,PHE Dte.(SM/18594) Application No-5004415806 Reference Id-503753690 | 476 | 01/10/2024 | 0 | WBSEDCL | 8.08 | 0 | 0 | 0
2050 | HOOGHLY | Electrical | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18594 | New | Quotation of New Service Connection for Balundi w/s Scheme, PH No-II Block-Arambag, Dist-Hooghly under Electrical Division, PHE Dte.(SM/18594) Application No-5004182766 Reference Id-503644453. | 121 | 17/05/2024 | 0 | WBSEDCL | 4.54 | 0 | 0 | 0
2051 | HOOGHLY | Electrical | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18594 | New | Quotation of New Service Connection for Balundi w/s Scheme,PH No-IV Block-Arambag,Dist-Hooghly under Electrical Division,PHE Dte.(SM/18594) Application No-5004416593 Reference Id-503753758 | 475 | 01/10/2024 | 0 | WBSEDCL | 7.6 | 0 | 0 | 0
2052 | HOOGHLY | Hooghly Division | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18594 | New | BALUNDI,SELALPUR, MADHABPUR, DAHARKUNDU ZONE-II Piped Water Supply Scheme with T.W, SWITCH ROOM , BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at ARAMBAGH Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | 3191/HUG | 31/10/2023 | 731 | S & P ENTERPRISE | 2296.42 | 103.17 | 17.31 | 30
2053 | HOOGHLY | Hooghly Division | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18594 | New | Sinking of 3 nos 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of BULUNDI W/S Scheme under Arambagh Sub Division of Hooghly Division, P.H.E. Dte. | 3617/HUG | 05/11/2024 | 180 | S & P ENTERPRISE | 48.46 | 0 | 0 | 70
2054 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Construction of Protection Wall at O.H.R. Site from Flood Water for Bilaspur Zone-I Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 449/SER | 31/05/2022 | 45 | PRADIP KUMAR ADHYA | 4.99 | 4.97 | 99.66 | 0
2055 | HOOGHLY | Central Drilling | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY JOHN-1500-III RIG MACHINE UNDER CMSD-I (D), CDD, PHE DTE. | 476 /CDD | 06/09/2021 | 30 | PADMA ENGINEERING & CO. | 14.74 | 11.18 | 100 | 0
2056 | HOOGHLY | Central Drilling | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE JOHN/DR-III UNDER CDD, PHE DTE. | 1015/CDD | 15/12/2021 | 30 | PADMA ENGINEERING & CO. | 12.61 | 11.16 | 100 | 0
2057 | HOOGHLY | Central Drilling | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | ADDITIONAL DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE JOHN/DR-III AT BILASPUR ZONE-I, TW-I WITHIN JANGIPARA BLOCK UNDER CMSD-I (D), CDD, PHE DTE. | 07/CMSD-I | 04/01/2022 | 10 | PADMA ENGINEERING & CO. | 0.76 | 0.58 | 100 | 0
2058 | HOOGHLY | Central Drilling | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE WITHIN JANGIPARA BLOCK UNDER CDD, PHE DTE. | 1013/CDD | 15/12/2021 | 30 | PADMA ENGINEERING & CO. | 12.61 | 10.54 | 100 | 0
2059 | HOOGHLY | Central Drilling | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY WITHIN GHATAL BLOCK UNDER CMSD-I (D), CDD, PHE DTE. | 479/ CDD | 07/09/2021 | 30 | PADMA ENGINEERING & CO. | 14.74 | 11.14 | 100 | 0
2060 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | BIG DIA TUBE WELL |  | 19/01/2022 | 0 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVN. P.H.E. DTE. | 44.6 | 0 | 0 | 0
2061 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | BIG DIA TUBE WELL |  | 19/01/2022 | 0 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVN. P.H.E. DTE. | 44.6 | 0 | 0 | 0
2062 | HOOGHLY | Electrical | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Electric Supply | 13 | 04/07/2022 | 0 | WBSEDCL | 19.89 | 0 | 0 | 0
2063 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Central Drilling Payment | C022228292462 | 09/02/2022 | 0 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVN. P.H.E. DTE. | 55.06 | 0 | 0 | 0
2064 | HOOGHLY | Electrical | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Supply, Delivery & Installation of S/P/M & other E/M allied works for Bilaspur W/S. Sch. Hooghly Z-II, TW-II | 780/,ED | 05/05/2022 | 90 | TAMAL ENTERPRISE | 10.55 | 10.51 | 99.67 | 5
2065 | HOOGHLY | Electrical | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipment etc, including allied works for Bilaspur W/S. Sch. Z-II, TW-I, Dist- Hooghly | 779/ED | 05/05/2022 | 90 | H.K.DAS & CO. | 10.5 | 10.5 | 100 | 0
2066 | HOOGHLY | Electrical | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipment etc, including allied works for Bilaspur W/S. Sch. Z-I, TW-I, Dist- Hooghly | 778/ED | 05/02/2022 | 90 | M/S DAS ENTERPRISE | 10.52 | 10.26 | 100 | 0
2067 | HOOGHLY | Electrical | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Supply & installation of LED board and outside display board for depicting details of pump/valve operators at Zone-I, P.H. No.I & II of Bilashpur w/s scheme, Dist.-Hooghly under ED, PHE Dte. | 2410/HMSD | 30/12/2022 | 10 | DIPA CHHETRI | 0.84 | 0.84 | 100 | 0
2068 | HOOGHLY | Electrical | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Supply, Delivery & Installation of S/P/M & other E/M equipments etc. with allied works for Bilaspur W/S. Sch. TW- II, Z-I, Hooghly | 913 /ED | 07/06/2022 | 90 | A.S. ENTERPRISE | 10.48 | 10.23 | 100 | 0
2069 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Material Requisition To Resource Division | 986/Hug | 19/05/2022 | 0 | Resource Division | 33.77 | 0 | 0 | 0
2070 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Material Requisition To Resource Division | 987/Hug | 19/05/2022 | 0 | Resource Division | 9.33 | 0 | 0 | 0
2071 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Material Requisition To Resource Division | 1107/3/HUG | 17/04/2023 | 0 | Resource Division | 6.16 | 0 | 0 | 0
2072 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Material Requisition To Resource Division | 610/Hug | 02/03/2023 | 0 | Resource Division | 39.18 | 0 | 0 | 0
2073 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Material Requisition To Resource Division | 1384/10/Hug | 15/05/2023 | 0 | Resource Division | 38.51 | 0 | 0 | 0
2074 | HOOGHLY | Electrical | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | car hire charges | 157 | 10/02/2023 | 0 | DEBASHISH GHOSH | 0.15 | 0 | 0 | 0
2075 | HOOGHLY | Electrical | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Fuel Charge | 158 | 10/02/2023 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.21 | 0 | 0 | 0
2076 | HOOGHLY | Electrical | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Fuel Charges | 158 | 10/02/2023 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.14 | 0 | 0 | 0
2077 | HOOGHLY | Electrical | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | fuel charges | 158 | 10/02/2023 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.07 | 0 | 0 | 0
2078 | HOOGHLY | Electrical | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Fuel Charge | 157 | 10/02/2023 | 0 | DEBASHISH GHOSH | 0.17 | 0 | 0 | 0
2079 | HOOGHLY | Electrical | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bilaspur water supply scheme Zone-I, T.W. No. II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. |  | 27/02/2023 | 0 | A.S. ENTERPRISE | 10.23 | 0 | 0 | 0
2080 | HOOGHLY | Electrical | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Hire Charges | 157 | 10/02/2023 | 0 | DEBASHISH GHOSH | 0.18 | 0 | 0 | 0
2081 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Protection works and other allied works at Head Work Site & 2nd Tube Well Site of Bilaspur Zone-II under Serampore Sub-Division of Hooghly Division P.H.E Dte | 4044/HUG | 19/12/2024 | 90 | M/S. S.G. CONSTRUCTION | 30.66 | 0 | 0 | 0
2082 | HOOGHLY | Electrical | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BILASPUR PIPED W/S SCHEME, Zone-II, T.W. No. III, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 454/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 6.94 | 71.57 | 65
2083 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Laying of leftout pipeline and providing leftout FHTC and construction of Drain connecting to nearest Drain Culvert at Head work site,Land Development at 3rd Tubwell Site,Construction of Toilet ,Septic tank,soak well ,Plumbing work at 2nd Tubewell site at Bilaspur (Zone-I) W/S Scheme under Serampore Sub-Division, P.H.E. Dte. | 4047/HUG | 19/12/2024 | 90 | PRADIP KUMAR ADHYA | 40.81 | 0 | 0 | 0
2084 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Bilaspur (Zone-II) Water Supply scheme with LDS, Rising main, FHTC work, Pump House & 500 cum capacity OHR with 20 mtr. staging height including soil investigation at Jangipara Block in Serampore Sub-Division, District:- Hooghly under Hooghly Division, PHE Dte. (New Scheme) (2nd Call) | 755/Hug | 11/04/2022 | 12 | S. HATI | 507.65 | 507.48 | 100 | 99
2085 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Construction of balance portion of Boundary Wall, Land Development, Pathway, Drain at H/W Site & 2nd T/W Site and Other allied works at Bilaspur (Zone-I) W/S Scheme under Serampore Sub-Division, P.H.E. Dte. | 3561/HUG | 06/12/2023 | 60 | PRADIP KUMAR ADHYA | 51.59 | 50.49 | 100 | 80
2086 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Providing Functional Household Tap Connection (FHTC) within left out habitation of various Mouzas in Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 537/HUG | 20/02/2024 | 285 | SRI KRISHNA ENTERPRISE | 12.1 | 6.3 | 52.26 | 60
2087 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Laying of Balance portion of Additional Pipeline including other allied works at Borhal Mouza in Bilaspur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 590/HUG | 22/02/2024 | 120 | BAKSHI ENTERPRISE | 17.55 | 10.02 | 57.15 | 75
2088 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Balance LDS and Other works within left out habitation of various Mouzas in Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 531/HUG | 20/02/2024 | 15 | GOURI ENTERPRISE | 13.52 | 13.35 | 100 | 99
2089 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Providing Functional Household Tap Connection (FHTC) within left out habitation of various Mouzas in Bilaspur (Borhal Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 734/HUG | 05/03/2024 | 120 | SRI KRISHNA ENTERPRISE | 18.31 | 16.73 | 100 | 90
2090 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Repairing of Damaged Road due to FHTC Works at Bilaspur & Guti-Atra mouzas of Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | 534/SER | 17/09/2024 | 7 | ASHA ENTERPRISE | 4.97 | 4.95 | 100 | 99
2091 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Repairing of Damaged Road due to FHTC Works at Guti-Atra & Singti mouzas of Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | 537/SER | 17/09/2024 | 7 | ASHA ENTERPRISE | 4.97 | 4.97 | 100 | 99
2092 | HOOGHLY | Electrical | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Quotation bill for new service connection charges at Bilaspur PWSS Zone-II, P.H. No.-III, Hooghly. Application No. 5004065667 Ref ID: 503592945 | 45 | 09/04/2024 | 0 | WBSEDCL | 3.62 | 0 | 0 | 0
2093 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Providing Functional Household Tap Connection (FHTC) within left out habitation of Pashpur Mouza in Bilaspur (Z - II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 55/SER | 20/01/2025 | 7 | ROY ENTERPRISE | 5 | 0 | 0 | 0
2094 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Providing Functional Household Tap Connection (FHTC) within left out habitation of Ranjapur Mouza in Bilaspur (Z - II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 56/SER | 20/01/2025 | 7 | ROY ENTERPRISE | 5 | 0 | 0 | 0
2095 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at various Mouzas in Bilaspur (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 589/HUG | 22/02/2024 | 587 | ROY ENTERPRISE | 13.53 | 6.72 | 49.71 | 99
2096 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution at Paschim Gobindapur mouza of Bilaspur Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | 740/HUG | 05/03/2024 | 60 | RAJU CONSTRUCTION | 32.26 | 0 | 0 | 20
2097 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Sinking of 2 nos. 300 X200 mm dia Tube Well, 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 5th Tube Well Site of BILASPUR W/S Scheme & 3rd Tube Well Site of JANAI W/S Scheme(ZONE-I) under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 3523/HUG | 22/10/2024 | 102 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 29.4 | 3.74 | 25.45 | 50
2098 | HOOGHLY | Hooghly Division | Bilaspur Piped Water Supply Scheme. , SM/09825 | New | Bilaspur (Zone-I) Water Supply scheme with LDS, Rising main, FHTC work, Pump House, 450 cum capacity OHR with 20 mtr. staging height including soil investigation at Jangipara Block in Serampore Sub-Division, DiSt- Hooghly under Hooghly Divn.PHE DTE. | 639/Hug | 01/04/2022 | 1117 | PRADIP KUMAR ADHYA | 447.88 | 421.2 | 94.14 | 90
2099 | HOOGHLY | Hooghly Division | Retrofitting Works For providing Functional House hold Tap Connection(FHTC)Within the Command Area Bhabanipur Char Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte , SM/10135 | Retrofitting | Providing 350 nos Functional Household Tap Connection (FHTC) within the Durllabhpur, Gournagar & Raninagar Mouzas of Bhabanipur Char Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | 471/Hug | 10/03/2022 | 60 | BOSE ENTERPRISE (RATUL BOSE) | 17.42 | 16.63 | 95.47 | 0
2100 | HOOGHLY | Hooghly Division | Retrofitting Works For providing Functional House hold Tap Connection(FHTC)Within the Command Area Bhabanipur Char Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte , SM/10135 | Retrofitting | Providing 1350 nos Functional Household Tap Connection (FHTC) within the Bhabanipur Char Mouza of Bhabanipur Char Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | 470/Hug | 10/03/2022 | 60 | MALLIKA ENTERPRISE | 62.56 | 62.61 | 100 | 0
2101 | HOOGHLY | Hooghly Division | Retrofitting Works For providing Functional House hold Tap Connection(FHTC)Within the Command Area Bhabanipur Char Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte , SM/10135 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of BHABANIPUR CHAR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 1655/Hug | 16/08/2022 | 15 | BOSE ENTERPRISE (RATUL BOSE) | 5.19 | 5.18 | 100 | 0
2102 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Route Survey, Design Drawing & DPR Preparation of Paschim Gopinathpur PWSS under Chandannagar Sub Division , PHE Dte. | 167/chan | 24/03/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.77 | 3.7 | 98.24 | 0
2103 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT PASCHIM GOPINATHUR PWSS, HARIPAL BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 390/CMSD-II(D) | 01/08/2022 | 15 | M/S PRACHI ENGINEERING | 2.1 | 1.76 | 100 | 0
2104 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | PROVIDING STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CNSTRUCTION OF TUBE WELL AT PASCHIM GOPINATHPUR PWSS, HARIPAL BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 389/CMSD-II (D) | 01/08/2022 | 15 | M/S S.K.GHOSH & CO. | 2.91 | 2.09 | 100 | 0
2105 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 230 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR PASCHIM GOPINATHPUR PWSS, HARIPAL BLOCK, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 387/CMSD-II (D) | 01/08/2022 | 15 | M/S S.K.GHOSH & CO. | 3.14 | 2.97 | 100 | 0
2106 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | PROVIDING HOUSING PIPE CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT PASCHIM GOPINATHPUR PWSS, HARIPAL BLOCK UNDER HOOGHLY DISTRICT , CDD, PHR DTE. | 388/CMSD-II (D) | 01/08/2022 | 15 | M/S S.K.GHOSH & CO. | 2.44 | 2.44 | 100 | 0
2107 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Material Requisition To Resource Division | 2686/9/Hug | 01/12/2022 | 0 | Resource Division | 0.34 | 0 | 0 | 0
2108 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Paschim Gopinathpur water supply scheme T.W. No. IV, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | 921/ED | 22/02/2023 | 90 | MOITRA ENGINEERING CO. | 10.68 | 10.38 | 97.19 | 0
2109 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Baseline household survey work including collection of House Hold Details at Prescribed Format through Mobile App/Hard Copy for yearly data updation in JJM portal at HARIPAL Block under Chandannagar Sub-Division, P.H.E. Dte. | 220/chan | 13/04/2022 | 20 | M/S S.G. CONSTRUCTION | 4.98 | 4.72 | 50 | 100
2110 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well(250mm x 200mm x 230 Mtrs. Depth) by utilising Departmental Machineries for Paschim Gopinathpur WS Scheme TW-I , Haripal Block under Hooghly District , CDD,PHE Dte. | 1130/CDD | 04/11/2022 | 30 | M/S SAIKAT ENTERPRISE | 11.28 | 9.94 | 100 | 0
2111 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | PROVIDING STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT PASCHIM GOPINATHPUR PWSS, HARIPAL BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 440/CMSD-II | 12/09/2022 | 15 | M/S S.K.GHOSH & CO. | 3.06 | 1.43 | 100 | 0
2112 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Material Requisition To Resource Division | 157/11/Hug | 24/01/2022 | 0 | Resource Division | 1.03 | 0 | 0 | 0
2113 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Material Requisition To Resource Division | 423/4/Hug | 07/03/2022 | 0 | Resource Division | 25.98 | 0 | 0 | 0
2114 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Material Requisition To Resource Division | 1125/4/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
2115 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Material Requisition To Resource Division | 1370/Hug | 06/07/2022 | 0 | Resource Division | 101.79 | 0 | 0 | 0
2116 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Material Requisition To Resource Division | 01/Hug | 02/01/2023 | 0 | Resource Division | 11.94 | 0 | 0 | 0
2117 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Material Requisition To Resource Division | 1383/15/Hug | 15/05/2023 | 0 | Resource Division | 2.43 | 0 | 0 | 0
2118 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Material Requisition To Resource Division | 109/8/Hug | 10/01/2023 | 0 | Resource Division | 45.2 | 0 | 0 | 0
2119 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Quatation Bill for New Service Connection of WBSEDCL at Auf. of Paschim Gopinathpur W/S. Sch. TW-III | 121 | 28/12/2022 | 0 | WBSEDCL | 2.54 | 0 | 0 | 0
2120 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Quotation Bill for New Service Connection at Aug. of Paschin Gopinathpur W/S. Sch. | 184 | 10/03/2023 | 0 | WBSEDCL | 2.95 | 0 | 0 | 0
2121 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Paschim Gopinathpur water supply scheme T.W. No. III, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | 2047/ED | 01/12/2022 | 90 | MAHADEV ENTERPRISE | 10.17 | 10.16 | 100 | 30
2122 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Augmentation of PASCHIM GOPINATHPUR Water Supply Scheme with Construction of 350 cum capacity OHR with 20 mtr. staging height including Soil Investigation work & LDS, Rising Main, Construction of Switch Room (5.40 m x 3.60 m ), FHTC Work, Repairing of 2 Nos. existing Switch Room (3.6 m x 3.0m), Boundary Wall at O.H.R Site, Boundary wall at 2nd & 3 rd Tube well at Haripal Block under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | 831/Hug | 20/04/2022 | 300 | M/S S.S. ENTERPRISE | 464.29 | 399.84 | 86.12 | 100
2123 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Damage road repairing at different location at Panchgachia mouza under Paschim Gopinathpur PWSS under Haripal block of the Chandannagar sub division under Chandannagar Sub division PHE Dte | 929/CHAN | 21/07/2025 | 20 | M/S S.S. ENTERPRISE | 4.98 | 0 | 0 | 0
2124 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Damage road repairing at different location at Mora mouza under Paschim Gopinathpur PWSS under Haripal block of Chandannagar sub division PHE Dte | 937/CHAN | 21/07/2025 | 20 | M/S S.S. ENTERPRISE | 4.97 | 0 | 0 | 0
2125 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR PASCHIM GOPINATHPUR , SM/09791 | Augmentation | Damage road repairing at different location at Sodpur mouza under Paschim Gopinathpur PWSS under Haripal block of Chandannagar sub division PHE Dte | 936/CHAN | 21/07/2025 | 20 | M/S S.S. ENTERPRISE | 4.96 | 0 | 0 | 0
2126 | HOOGHLY | Hooghly Division | Improvement of PURBA THAKURANICHAK Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18928 | Augmentation | Construction of 5 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at BHANDARHATI (1NO.), PURBA THAKURANI CHAK (2NOS.), HARISH CHAK (2NOS.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3268/HUG | 08/11/2023 | 60 | KRISHNA MONDAL | 58.98 | 0 | 0 | 0
2127 | HOOGHLY | Hooghly Division | Improvement of PURBA THAKURANICHAK Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18928 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BHANDARHATI (1NO.),PURBA THAKURANI CHAK( 2NOS.), HARISH CHAK( 2NOS.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3474/HUG | 29/11/2023 | 45 | CIVIL CRAFT | 88.67 | 0 | 0 | 0
2128 | HOOGHLY | Electrical | Improvement of PURBA THAKURANICHAK Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18928 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for PURBA THAKURANICHAK PIPED W/S SCHEME, T.W. No. III & IV, Block: Khanakul-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1455/ED | 25/07/2024 | 90 | M.S. ENTERPRISE | 22.21 | 0 | 0 | 0
2129 | HOOGHLY | Hooghly Division | Improvement of PURBA THAKURANICHAK Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18928 | Augmentation | Protection works and other allied works at Head Work Site of PURBA THAKURANICHAK under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 4049/HUG | 19/12/2024 | 90 | M/S. R. M. CONSTRUCTION | 23.91 | 0 | 0 | 0
2130 | HOOGHLY | Hooghly Division | Improvement of PURBA THAKURANICHAK Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I , SM/18928 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of PURBA THAKURANICHAK ZONE-II PWSS under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 1424/HUG | 17/05/2023 | 45 | RANA ENTERPRISE | 23.85 | 20.43 | 100 | 100
2131 | HOOGHLY | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. , SM/18373 | New | Material Requisition To Resource Division | 3060/6/Hug | 11/10/2023 | 0 | Resource Division | 26.05 | 0 | 0 | 0
2132 | HOOGHLY | Electrical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. , SM/18373 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhagabatipur water supply scheme, Zone - I, T.W. No. I & II and Zone - II, T.W. No. I & II, Block: Chanditala-I, District - Hooghly under Electrical Division, PHE Dte. | 3619/ED | 29/08/2023 | 90 | M/S BIPUL BANERJEE | 46.53 | 33.79 | 72.62 | 60
2133 | HOOGHLY | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. , SM/18373 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Bhagabatipur-I PWSS 2. Bhagabatipur-II PWSS 3. Jagmohanpur PWSS 4. Bandhpur PWSS 5. Haripur PWSS 6. Pairagacha PWSS | 110/SER | 23/02/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 80
2134 | HOOGHLY | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. , SM/18373 | New | CONSTRUCTION OF 2NOS. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT BHAGABATIPUR Zone-I HW SITE AND 2ND TW SITE UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E DTE. | 424/SER | 31/07/2024 | 15 | SUNITI MAIRA | 0.68 | 0.66 | 100 | 95
2135 | HOOGHLY | Electrical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. , SM/18373 | New | Quotation bill for new service connection charges at Bhagabatipur PWSS Zone-I, P.H. No.-II, Hooghly. Application No. 5004066730 Ref ID: 503597305 | 87 | 23/04/2024 | 0 | WBSEDCL | 4.55 | 0 | 0 | 0
2136 | HOOGHLY | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. , SM/18373 | New | PAYMENT TO ROAD RESTORATION TO PWD KALACHARA BHAGABATIPUR ROAD | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 96.95 | 0 | 0 | 0
2137 | HOOGHLY | Electrical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. , SM/18373 | New | Quotation bill for new service connection charges at Bhagabatipur PWSS Zone-II, P.H. No.-II, Hooghly. Application No. 5004042700 Ref ID: 503581618 | 44 | 09/04/2024 | 0 | WBSEDCL | 10.61 | 0 | 0 | 0
2138 | HOOGHLY | Electrical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. , SM/18373 | New | Quotation for new service connection of Bhogatipur W/S. Sch. PH-I | 739 | 08/02/2024 | 0 | WBSEDCL | 6.31 | 0 | 0 | 0
2139 | HOOGHLY | Electrical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. , SM/18373 | New | Quotation bill for new service connection charges at Bhagabatipur PWSS Zone-II, P.H. No.-I, Hooghly. Application No. 5004034017 Ref ID: 503576013 | 86 | 23/04/2024 | 0 | WBSEDCL | 5.36 | 0 | 0 | 0
2140 | HOOGHLY | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. , SM/18373 | New | BHAGABATIPUR ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHANDITALA-I Block of Serampore Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | 2320/HUG | 04/08/2023 | 662 | S GHOSH AND ASSOCIATES PVT LTD. | 570.37 | 42.94 | 7.53 | 20
2141 | HOOGHLY | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. , SM/18373 | New | BHAGABATIPUR ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHANDITALA-I Block of Serampore Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | 2021/HUG | 11/07/2023 | 633 | TIRUPATI ENTERPRISES | 498.14 | 305.03 | 61.23 | 30
2142 | HOOGHLY | Hooghly Division | GROUND WATER BASED GOPALDAHA PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' , SM/19015 | New | Material Requisition To Resource Division | 3057/53/Hug | 11/10/2023 | 0 | Resource Division | 1.82 | 0 | 0 | 0
2143 | HOOGHLY | Electrical | GROUND WATER BASED GOPALDAHA PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' , SM/19015 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gopaldaha water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 05/ED | 02/01/2024 | 90 | M/S CHANDIMATA ELECTRICALS | 20.49 | 7.46 | 36.41 | 20
2144 | HOOGHLY | Electrical | GROUND WATER BASED GOPALDAHA PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' , SM/19015 | New | Quotation of New Service Connection for Gopaldaha w/s Scheme,PH No-I Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/19015) Application No-5004148688, Reference Id-503632547 | 100 | 06/05/2024 | 0 | WBSEDCL | 12.59 | 0 | 0 | 0
2145 | HOOGHLY | Electrical | Augmentation Of Piped Water Supply Scheme For KHANAKUL , SM/18645 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Khanakul water supply scheme, T.W. No. I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | 3600/ED | 28/08/2023 | 90 | M/S S.R. ENTERPRISE | 21.49 | 0 | 0 | 0
2146 | HOOGHLY | Hooghly Division | Augmentation Of Piped Water Supply Scheme For KHANAKUL , SM/18645 | Augmentation | Augmentation of KHANAKUL ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANAKUL-I Block of Arambag Sub-Division under Hooghly Division, PHE Dte. [AUGMENTATION SCHEME] | 2392/HUG | 10/08/2023 | 270 | SUBHANKAR BANERJEE | 387.3 | 43.69 | 11.28 | 15
2147 | HOOGHLY | Hooghly Division | Augmentation Of Piped Water Supply Scheme For KHANAKUL , SM/18645 | Augmentation | Sinking of 3rd tube-well by D.R. Rig method , Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of KHANAKUL (ZONE-I) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | 592/HUG | 22/02/2024 | 60 | TOTON MONDAL | 29.75 | 0 | 0 | 0
2148 | HOOGHLY | Hooghly Division | Augmentation Of Piped Water Supply Scheme For KHANAKUL , SM/18645 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme underKhanakul I & II &Goghat I & II Block (Part-I) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. | 2831/HUG | 09/08/2024 | 15 | HORIZEN | 1.6 | 0 | 0 | 100
2149 | HOOGHLY | Electrical | Augmentation Of Piped Water Supply Scheme For KHANAKUL , SM/18645 | Augmentation | Quotation money deposition for new service connection at Khanakul W/S Zone- I ,T.W No.-I , Hooghly APP. No.- 5004036875 SM/18645 | 824 | 01/03/2024 | 0 | WBSEDCL | 4.35 | 0 | 0 | 0
2150 | HOOGHLY | Electrical | Augmentation Of Piped Water Supply Scheme For KHANAKUL , SM/18645 | Augmentation | Quotation money deposition for new service connection at khanakul w/s scheme, zone-II, T.W. No.-II, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004036737/Quot/03 Reference ID- 503576720 SM Code- 18645 | 823 | 01/03/2024 | 0 | WBSEDCL | 3.39 | 0 | 0 | 0
2151 | HOOGHLY | Hooghly Division | Augmentation Of Piped Water Supply Scheme For KHANAKUL , SM/18645 | Augmentation | Augmentation of KHANAKUL ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANAKUL-I Block of Arambag Sub-Division under Hooghly Division, PHE Dte. [AUGMENTATION SCHEME] | 2368/HUG | 08/08/2023 | 601 | M/S. NANDY ENTERPRISE | 382.9 | 19.26 | 5.03 | 20
2152 | HOOGHLY | Hooghly Division | Augmentation Of Piped Water Supply Scheme For KHANAKUL , SM/18645 | Augmentation | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of KHANAKUL (ZONE-II) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | 596/HUG | 22/02/2024 | 540 | ANIRUDDHA FARUQUE | 29.6 | 13.16 | 44.44 | 50
2153 | HOOGHLY | Electrical | Augmentation Of Piped Water Supply Scheme For KHANAKUL , SM/18645 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KHANAKUL PIPED W/S SCHEME, T.W. No. IV, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1181/ED | 14/06/2024 | 630 | M/S A.K BANERJEE | 10.74 | 0 | 0 | 10
2154 | HOOGHLY | Electrical | Augmentation Of Piped Water Supply Scheme For KHANAKUL , SM/18645 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KHANAKUL PIPED W/S SCHEME, T.W. No. III, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1180/ED | 14/06/2024 | 382 | M/S A.K BANERJEE | 10.73 | 0 | 0 | 50
2155 | HOOGHLY | Hooghly Division | Augmentation Of Piped Water Supply Scheme For KHANAKUL , SM/18645 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) KHANAKUL PWSS - 6 nos (2) KRISHNANAGAR PWSS - 4nos (3) PATUL PWSS - 4nos | 810/Arg | 23/08/2024 | 30 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
2156 | HOOGHLY | Hooghly Division | Augmentation Of Piped Water Supply Scheme For KHANAKUL , SM/18645 | Augmentation | Construction of 2 nos new Pump House, Repairing and Renovation of Store cum Office room, Boundary wall of Khanakul PWSS under Arambagh Sub Division, PHE Dte. (2nd Call of WBPHE/EE/20/HUG/2024-25; SL-3) | 1495/HUG | 11/06/2025 | 60 | M/S PRADYUT KUMAR HAZRA (PARTNERSHIP) | 23.44 | 0 | 0 | 100
2157 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18974 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4497/ED | 23/11/2023 | 90 | BISALAXMI ENTERPRISE | 21.48 | 0 | 0 | 0
2158 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18974 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BHABANIPUR CHAR (2Nos.), JAYRAMBATI (2Nos.), DEBANANDAPUR (1 No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3389/HUG | 22/11/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 87.88 | 27.43 | 78.04 | 30
2159 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18974 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at DHAMAITIKAR (2Nos.), JAYRAMBATI (2 Nos.), DEPARA (1 Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3725/HUG | 18/12/2023 | 60 | BIMAL KUMAR HALDER | 59.73 | 0 | 0 | 0
2160 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18974 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in SOMASPUR I GP of DHANIAKHALI Block. | 250/CH | 12/03/2024 | 30 | SRI KRISHNA ENTERPRISE | 4.99 | 3.29 | 66.04 | 70
2161 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18974 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in SOMASPUR II GP of DHANIAKHALI Block. | 251/CH | 12/03/2024 | 30 | JOY GURU ENTERPRISE | 4.99 | 1.31 | 20.94 | 100
2162 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18974 | Augmentation | REPAIRING & RENOVATION OF SWITCH ROOM INCLUDING BOUNDARY WALL AT 2ND TW SITE OF JAYRAMBATI WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURAH SUB-DIVISION UNDER HOOGHLY DIVISION, PHE DTE. | 218/CH | 19/02/2025 | 30 | RAJMAHAL ENTERPRISE | 3.25 | 0 | 0 | 0
2163 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/18974 | Augmentation | REPAIRING & RENOVATION OF SWITCH ROOM INCLUDING BOUNDARY WALL AT HEAD WORKS SITE OF JAYRAMBATI WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURAH SUB DIVISION UNDER HOOGHLY DIVISION, PHE DTE. | 125/CH | 29/01/2025 | 10 | RAJMAHAL ENTERPRISE | 4.85 | 0 | 0 | 0
2164 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18935 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at EKTARPUR (2Nos.), BELUN (2Nos.), CHOPA (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3235/HUG | 06/11/2023 | 60 | EVERGREEN TRADERS | 59.68 | 0 | 0 | 0
2165 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18935 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4486/ED | 23/11/2023 | 90 | CINZANO | 21.5 | 0 | 0 | 0
2166 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18935 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at EKTARPUR (2Nos.), BELUN (2Nos.), CHOPA (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3358/HUG | 21/11/2023 | 45 | ACME CONSTRUCTION | 87.88 | 10.87 | 30.91 | 60
2167 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18935 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Musuria village under Balagrh Block, Akna village of Chinsurah Magra Block and Benabharui village of Chinsurah Magra Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | 258/CH | 14/03/2024 | 7 | R.K. TRADERS | 0.95 | 0.95 | 100 | 100
2168 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18935 | Augmentation | Quotation for new service connection for source Augmentation of EKTARPUR Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18935), Reference Id- 503777877 Application no- 5004449206 | BP-24-25-581 | 19/11/2024 | 0 | WBSEDCL | 11.08 | 0 | 0 | 0
2169 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18935 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at 2nd TW Site (PH-2) of Ektarpur PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at BALAGARH Block | 232/CH | 19/02/2025 | 25 | MAA BUNAMATA ENTERPRISE | 2.99 | 0 | 0 | 100
2170 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18939 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4490/ED | 23/11/2023 | 647 | M/S S.R. ENTERPRISE | 21.81 | 0 | 0 | 90
2171 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18939 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at CHOPA (1 No.), HARAL (2Nos.), DWARBASINI (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3236/HUG | 06/11/2023 | 726 | DAS ENTERPRISE | 59.77 | 0 | 0 | 60
2172 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18939 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Darbasini PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 244/CH | 19/02/2025 | 10 | SUNITI MAIRA | 2.72 | 0 | 0 | 0
2173 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18939 | Augmentation | Repairing & Renovation of boundary wall and Land development at H/W Site of Dwarbasini PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 261/CH | 20/02/2025 | 10 | BASU & SONS | 4.75 | 0 | 0 | 0
2174 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18939 | Augmentation | Repairing & Renovation of Switch room and Store Room at H/W Site Dwarbasini PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 262/CH | 20/02/2025 | 10 | BASU & SONS | 2.85 | 0 | 0 | 0
2175 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF CHAPTA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18940 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at CHAPTA (2Nos.), SOMRA (2Nos.), NAMAJGRAM (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3360/HUG | 21/11/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 87.88 | 29.56 | 84.09 | 40
2176 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF CHAPTA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18940 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Chapta PWSS 2. Haral PWSS 3. Namajgram PWSS 4. Rameswerpur PWSS 5. Depara PWSS 6. Sripur Pandua PWSS | 206/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 100 | 50
2177 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF CHAPTA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18940 | Augmentation | Quotation for new service connection for source Augmentation of Chapta Water Supply Scheme, TW NO- IV in the district Hooghly under Electrical Division,PHE Dte. ( SM/18940), Reference Id- 503751380 Application no- 5004412432 | BP-24-25-593 | 21/11/2024 | 0 | WBSEDCL | 8.08 | 0 | 0 | 0
2178 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF CHAPTA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18940 | Augmentation | Quotation for new service connection for source Augmentation of CHAPTA Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. (SM/18940), Reference Id- 503729663 Application no- 5004376500 | 473 | 01/10/2024 | 0 | WBSEDCL | 4.59 | 0 | 0 | 0
2179 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF CHAPTA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18940 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at CHAPTA (2Nos.), SOMRA (2Nos.), NAMAJGRAM (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3237/HUG | 06/11/2023 | 632 | M/S T.K.B. CONSTRUCTION | 59.02 | 0 | 0 | 60
2180 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF CHAPTA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18940 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF CHAPTA PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4491/ED | 23/11/2023 | 770 | MAA KALI ENTERPRISE | 21.49 | 0 | 0 | 50
2181 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF CHAPTA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18940 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Chapta PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 259/CH | 20/02/2025 | 10 | R.K. TRADERS | 2.23 | 0 | 0 | 0
2182 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF CHAPTA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18940 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site of Chapta PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 240/CH | 19/02/2025 | 10 | R.K. TRADERS | 4.79 | 0 | 0 | 0
2183 | HOOGHLY | Electrical | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/18670 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dihibatpur water supply scheme, T.W. No.- I, II & III, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | 3411/ED | 10/08/2023 | 90 | B.T. PROJECT PVT. LTD. | 32.89 | 0 | 0 | 0
2184 | HOOGHLY | Electrical | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/18670 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Dihibatpur water supply scheme, T.W. No. IV, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | 330/ED | 21/02/2024 | 90 | AMIT DAS | 10.72 | 0 | 0 | 0
2185 | HOOGHLY | Hooghly Division | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/18670 | Augmentation | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of DIHIBATPUR (ZONE-I) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | 597/HUG | 22/02/2024 | 60 | AMBIAN INFRASTRUCTURE | 29.67 | 0 | 0 | 0
2186 | HOOGHLY | Electrical | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/18670 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SAIDPUR PIPED W/S SCHEME, T.W. No. VII, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1183/ED | 14/06/2024 | 90 | STANDARD ELECTRICALS | 10.75 | 0 | 0 | 0
2187 | HOOGHLY | Electrical | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/18670 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SAIDPUR PIPED W/S SCHEME, T.W. No. VI, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1182/ED | 14/06/2024 | 90 | M/S CHANDIMATA ELECTRICALS | 10.73 | 0 | 0 | 0
2188 | HOOGHLY | Electrical | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/18670 | Augmentation | Electric quot. of WBSEDCL for New service Connection of Dihibatpur T/W-VI W/S scheme under Electrical Division PHE Dte. (SM/18670) | 373 | 12/08/2024 | 0 | WBSEDCL | 6.98 | 0 | 0 | 0
2189 | HOOGHLY | Hooghly Division | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/18670 | Augmentation | Augmentation of DIHIBATPUR Piped Water Supply Scheme with Sinking of 3 Nos. Tube Well within ZONE-I & II, Construction of 300 cum capacity RCC OHR in ZONE-I & Construction of 250 cum capacity RCC OHR in ZONE-II with 20.0 mtr. Staging height including soil investigation, Repairing of Existing Switch Rooms, Boundary walls at different TW site, LDS, Rising Main, FHTC, construction of 1 No. switch-room & boundary wall in ZONE-I & construction of 2 Nos. switch-room & 3 nos boundary wall , LDS, Rising Main, FHTC in ZONE-II under PURSURAH Block, District:- Hooghly | 2340/HUG | 07/08/2023 | 817 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 869.52 | 113.96 | 13.11 | 30
2190 | HOOGHLY | Electrical | Source Augmentation Of KEOTA Piped Water Supply Scheme Under Chinsurah Magra Block , SM/18955 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of KEOTA Piped Water Supply Scheme Block- ChinsurahMogra District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4519/ED | 23/11/2023 | 90 | SUJOY RANJAN BHOWMICK | 10.74 | 0 | 0 | 0
2191 | HOOGHLY | Hooghly Division | Source Augmentation Of KEOTA Piped Water Supply Scheme Under Chinsurah Magra Block , SM/18955 | Augmentation | Laying of pipe line for improvement of water supply in distribution system at Keota & Kulihanda W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | 823/CH | 31/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.96 | 0.96 | 100 | 80
2192 | HOOGHLY | Hooghly Division | Source Augmentation Of KEOTA Piped Water Supply Scheme Under Chinsurah Magra Block , SM/18955 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3406/HUG | 23/11/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 0 | 0 | 50
2193 | HOOGHLY | Hooghly Division | Source Augmentation Of KEOTA Piped Water Supply Scheme Under Chinsurah Magra Block , SM/18955 | Augmentation | Laying HDPE pipeline at Dunlop of KEOTA Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 630/CH | 15/07/2024 | 10 | BIMAL KUMAR HALDER | 4.85 | 4.84 | 100 | 55
2194 | HOOGHLY | Hooghly Division | Source Augmentation Of KEOTA Piped Water Supply Scheme Under Chinsurah Magra Block , SM/18955 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3245/HUG | 06/11/2023 | 600 | TAPAS ADHYA | 59.64 | 0 | 0 | 20
2195 | HOOGHLY | Electrical | Source Augmentation of HASAMPUR Piped Water Supply Scheme under Dhaniakhali Block , SM/18956 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of HASAMPUR Piped Water Supply Scheme Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4520/ED | 23/11/2023 | 90 | APEX ENGINEERING & PROJECT CO. | 10.74 | 0 | 0 | 0
2196 | HOOGHLY | Hooghly Division | Source Augmentation of HASAMPUR Piped Water Supply Scheme under Dhaniakhali Block , SM/18956 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3406/HUG | 23/11/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 13.72 | 79.41 | 50
2197 | HOOGHLY | Hooghly Division | Source Augmentation of HASAMPUR Piped Water Supply Scheme under Dhaniakhali Block , SM/18956 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in GURAP II GP of DHNIAKHALI Block. | 249/CH | 12/03/2024 | 30 | M/S MANGALCHANDI CONSTRUCTION | 4.98 | 0 | 0 | 89
2198 | HOOGHLY | Hooghly Division | Source Augmentation of HASAMPUR Piped Water Supply Scheme under Dhaniakhali Block , SM/18956 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3245/HUG | 06/11/2023 | 600 | TAPAS ADHYA | 59.64 | 0 | 0 | 20
2199 | HOOGHLY | Hooghly Division | Source Augmentation of HASAMPUR Piped Water Supply Scheme under Dhaniakhali Block , SM/18956 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of DIGHIR, HASAMPUR, CHERAGRAM, GURAP PWSS under DHANIAKHALI Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | 323/HUG | 05/02/2025 | 25 | SWARNA ENTERPRISE | 8.63 | 0 | 0 | 0
2200 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18945 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at JAMGRAM (2Nos.), PANDUA (2Nos.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3242/HUG | 06/11/2023 | 60 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 59.67 | 0 | 0 | 0
2201 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18945 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4509/ED | 23/11/2023 | 90 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 22.05 | 0 | 0 | 0
2202 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18945 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Jamgram PWSS 2. Pandua Z-I PWSS 3. Pandua Z-II PWSS 4. Pandua Z-III PWSS 5. Shibrai PWSS | 207/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.79 | 0.79 | 100 | 50
2203 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18945 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Benipukur Mini PWSS 2. Baro Nekua Mini PWSS 3. Muragacha (Bakulia) Mini PWSS 4. Arji Aschitpur Mini PWSS 5. Jamgram Mondalai Arsenic PWSS 6. Illampur Arsenic PWSS | 210/CH | 29/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 45
2204 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18945 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Jamgram village under Pandua Block, Mandalai village of Pandua Block and Sadhat village of Pandua Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | 262/CH | 14/03/2024 | 7 | R.K. TRADERS | 0.95 | 0.95 | 100 | 100
2205 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18945 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at JAMGRAM (2Nos.), PANDUA (2Nos.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3384/HUG | 22/11/2023 | 710 | MS D.PALIT AND CO. | 87.87 | 0 | 0 | 80
2206 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18945 | Augmentation | Repairing & Renovation of Switch room and Store room at H/W Site of Jamgram PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 242/CH | 19/02/2025 | 10 | M/S BIMAL DAS AND CO. | 3.07 | 0 | 0 | 0
2207 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18945 | Augmentation | Repairing & Renovation of Switch room at PH-3 of Jamgram PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 273/CH | 20/02/2025 | 10 | M/S BIMAL DAS AND CO. | 1.4 | 0 | 0 | 0
2208 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18945 | Augmentation | Repairing & Renovation of Switch room at PH-2 of Jamgram PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 265/CH | 20/02/2025 | 10 | M/S BIMAL DAS AND CO. | 1.56 | 0 | 0 | 0
2209 | HOOGHLY | Hooghly Division | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block , SM/18948 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at HANRAL (2Nos.), SUDARSHAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3243/HUG | 06/11/2023 | 60 | AMBIAN INFRASTRUCTURE | 59.26 | 0 | 0 | 0
2210 | HOOGHLY | Hooghly Division | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block , SM/18948 | Augmentation | Preparation of DPR for Augmentation HANRAL Z-II Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-POLBA DADPUR]. | 691/CH | 09/08/2024 | 7 | APEX ENGINEERING | 4.03 | 0 | 0 | 0
2211 | HOOGHLY | Hooghly Division | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block , SM/18948 | Augmentation | Laying of UPVC Pipe At damaged portion of distribution system due to widening of road At Maheswarpur of Hanral W/S Scheme under Chinsurah Sub Division of Hooghly division, P.H.E Dte. | 811/HUG | 11/03/2024 | 30 | M/S BIMAL DAS AND CO. | 9.75 | 9.69 | 100 | 80
2212 | HOOGHLY | Hooghly Division | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block , SM/18948 | Augmentation | Laying of UPVC Pipe At damaged portion of distribution system due to widening of road At Rashulpur of Hanral W/S Scheme under Chinsurah Sub Division of Hooghly division, P.H.E Dte. | 810/HUG | 11/03/2024 | 30 | M/S BIMAL DAS AND CO. | 9.01 | 8.94 | 100 | 80
2213 | HOOGHLY | Electrical | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block , SM/18948 | Augmentation | Quotation for new service connection for Hanral (S.Aug) T.W. - I [SM/18948] (Sekendarpur), Block - Polba-Dadpur, Dt. - Hooghly under WBSEDCL, Dadpur CCC, Ref. Id. -503739105, Dt. - 21-11-2024, Application No. - 5004394547 | 617 | 05/12/2024 | 0 | WBSEDCL | 4.17 | 0 | 0 | 0
2214 | HOOGHLY | Electrical | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block , SM/18948 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of HANRAL Piped Water Supply Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4512/ED | 23/11/2023 | 630 | KUSHANI ENTERPRISE | 10.74 | 0 | 0 | 30
2215 | HOOGHLY | Electrical | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block , SM/18948 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hanral water supply scheme, Zone-II, T.W. No. III, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | 90/ED | 10/01/2024 | 540 | WIZARDTECH SOLUTION | 10.68 | 0 | 0 | 90
2216 | HOOGHLY | Hooghly Division | Retrofitting Works of BALI PWSS for providing 1286 nos Functional Household Tap Connection (FHTC) , SM/06756 | Retrofitting | FHTC |  | 15/02/2021 | 0 | M/S SHIVAM UDYOG | 17 | 0 | 0 | 0
2217 | HOOGHLY | Hooghly Division | Retrofitting Works of BALI PWSS for providing 1286 nos Functional Household Tap Connection (FHTC) , SM/06756 | Retrofitting | FHTC |  | 21/09/2021 | 0 | M/S SHIVAM UDYOG | 16.72 | 0 | 0 | 0
2218 | HOOGHLY | Hooghly Division | Retrofitting Works of BALI PWSS for providing 1286 nos Functional Household Tap Connection (FHTC) , SM/06756 | Retrofitting | FHTC |  | 15/02/2021 | 0 | S.K. GHOSH | 32 | 0 | 0 | 0
2219 | HOOGHLY | Hooghly Division | Retrofitting Works of BALI PWSS for providing 1286 nos Functional Household Tap Connection (FHTC) , SM/06756 | Retrofitting | Placement of Fund | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
2220 | HOOGHLY | Hooghly Division | Retrofitting Works of BALI PWSS for providing 1286 nos Functional Household Tap Connection (FHTC) , SM/06756 | Retrofitting | Providing 720 nos FHTC in Bali Village under Bali PWSS | 1540/Hug | 24/11/2020 | 181 | S.K. GHOSH | 31.88 | 63.75 | 199.96 | 100
2221 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Right bank of Sundeswari river) Water Supply Scheme , SM/06990 | Retrofitting | FHTC |  | 15/02/2021 | 0 | P.B. ENTERPRISE (PINTU BHADURI) | 77 | 0 | 0 | 0
2222 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Right bank of Sundeswari river) Water Supply Scheme , SM/06990 | Retrofitting | FHTC |  | 12/04/2021 | 0 | P.B. ENTERPRISE (PINTU BHADURI) | 3.02 | 0 | 0 | 0
2223 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Harishchak (Right bank of Sundeswari river) Water Supply Scheme , SM/06990 | Retrofitting | Providing 1650 nos F.H.T.C. in Harishchak village of Harishchak and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II] | 1688/HUG | 17/12/2020 | 40 | P.B. ENTERPRISE (PINTU BHADURI) | 77.54 | 0 | 0 | 0
2224 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Shitalpur & Pandugram Mouza of Arandi Water Supply Scheme , SM/06762 | Retrofitting | FHTC |  | 15/02/2021 | 0 | M/S RAJKUMAR KHAN | 27 | 0 | 0 | 0
2225 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Shitalpur & Pandugram Mouza of Arandi Water Supply Scheme , SM/06762 | Retrofitting | Providing 100 nos Functional Household Tap Connection (FHTC) within the command area of Arandi Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 425/HUG | 01/12/2021 | 30 | M/S R K ENTERPRISE | 18.18 | 18.16 | 100 | 100
2226 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Shitalpur & Pandugram Mouza of Arandi Water Supply Scheme , SM/06762 | Retrofitting | Providing 100 nos Functional Household Tap Connection (FHTC) within the command area of ARANDI Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | 13/Hug | 04/01/2022 | 20 | MS CHANDIMATA CONSTRUCTION | 13.37 | 13.35 | 100 | 100
2227 | HOOGHLY | Central Drilling | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. , SM/09423 | Augmentation | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT ANTPUR PWSS, JAIGIPARA BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 177/CMSD-I (D) | 10/06/2022 | 15 | M/S S.K.GHOSH & CO. | 4.38 | 3.91 | 100 | 90
2228 | HOOGHLY | Central Drilling | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. , SM/09423 | Augmentation | Supply & Delivery of consumables at site for construction of TW at ANTPUR PWSS under CDD, PHE Dte. | 179/CMSD-I(D) | 10/06/2022 | 15 | S B S ENTERPRISE | 1.5 | 1.45 | 100 | 100
2229 | HOOGHLY | Central Drilling | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. , SM/09423 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT ANTPUR PWSS, JANGIPARA BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 180/CMSD-I(D) | 10/06/2022 | 15 | M/S S.K.GHOSH & CO. | 2.9 | 2.75 | 100 | 100
2230 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. , SM/09423 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Antpur (Aug) water supply scheme, T.W. No. III, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | 1321/ED | 17/08/2022 | 90 | M/S, GHOSH ENTERPRISE | 10.28 | 9.91 | 96.42 | 75
2231 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. , SM/09423 | Augmentation | Construction of One No. 3.60 m X 3.00 m Switch Room without Sanitary and Water Supply arrangement at 3rd T/W Site for ANTPUR W/S Scheme under Serampore Sub-Division of Hooghly Division,P.H.E. Dte. | 537/SER | 08/09/2022 | 60 | BAKSHI ENTERPRISE | 2.65 | 2.53 | 100 | 0
2232 | HOOGHLY | Central Drilling | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. , SM/09423 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBEWELL BY DEPARTMENTAL RIG MACHINE AT AMODGHATA W/S SCH TW-II, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 377/CMSD-II | 01/08/2022 | 15 | C.M. ENTERPRISE | 2.93 | 0.11 | 100 | 0
2233 | HOOGHLY | Central Drilling | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. , SM/09423 | Augmentation | PROVIDING TUBE WELL MATERIALS (250MM DIA CD) CONFORMING TO IS12:42 PM 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBEWELL ANTPUR, UNDER CMSD-I (D), CDD, PHE DTE. | 114/CMSD-I | 06/05/2022 | 15 | ASHUTOSH DAS & CO | 3.87 | 3.78 | 100 | 0
2234 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. , SM/09423 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ANTPUR PIPED W/S SCHEME, T.W. No. IV, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 458/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 0 | 0 | 65
2235 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. , SM/09423 | Augmentation | Repairing of Switch Room & Boundary Wall at Existing TW sites of ANTPUR PWSS under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 986/HUG | 16/03/2024 | 30 | SUNITI MAIRA | 6.18 | 0 | 0 | 0
2236 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. , SM/09423 | Augmentation | Construction of Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of ANTPUR Piped Water Supply Scheme under Hooghly Division P.HE Dte. within Jangipara Block, Serampore Sub Division of Hooghly Division, PHE Dte. | 98/HUG | 10/01/2023 | 150 | SHREEOM ENTERPRISE | 4.59 | 4.2 | 100 | 99
2237 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. , SM/09423 | Augmentation | Quotation bill for new service connection charges at Antpur PWSS P.H. No.-IV, Hooghly. Application No. 5004065652 Ref ID: 503592944 | 42 | 09/04/2024 | 0 | WBSEDCL | 5.37 | 0 | 0 | 0
2238 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR CHANDANNAGAR WATER SUPPLY SCHEME. , SM/09071 | Retrofitting | 1ST Continuation of Engagement of 2 nos Valve operators for the period from 01/07/2023 to 31/08/2023 for Dharampur & Uttarchandannagar W/S Scheme under Chinshurah Sub - Division, P.H.E. Dte. | 571/CH | 30/06/2023 | 124 | SOUMYADIP DE | 0.71 | 0 | 0 | 0
2239 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR CHANDANNAGAR WATER SUPPLY SCHEME. , SM/09071 | Retrofitting | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in CHINSURAH-MOGRA Block. | 253/CH | 12/03/2024 | 30 | BIMAL KUMAR HALDER | 4.99 | 0 | 0 | 75
2240 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Preparation of DPR for Augmentation of Jangipara (Zone-I & II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Jangipara] | 365/SER | 17/03/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.91 | 4.93 | 100 | 0
2241 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Preparation of DPR for Augmentation of Jangipara (Zone-III) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Jangipara] | 366/SER | 17/03/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.07 | 2.06 | 99.06 | 0
2242 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | ADDITIONAL WORK FOR CONSTRUCTION OF TUBEWELL AT JANGIPARA PWSS Z-II, HOOGHLY DISTRICT BY UTILIZING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. | 550/CMSD-I | 11/11/2022 | 3 | CHANDA ENTERPRISE | 0.43 | 0.43 | 100 | 0
2243 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR JANGIPARA (ZONE-II) W/S SCH, JANGIPARA BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 1373/CDD | 24/11/2022 | 30 | CHANDA ENTERPRISE | 12.87 | 12.07 | 100 | 0
2244 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 210 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR JANGIPARA (ZONE-III), HOOGHLY DISTRICT, CDD, PHE DTE. | 1560/CDD | 08/12/2022 | 30 | C.M. ENTERPRISE | 12.48 | 10.49 | 100 | 0
2245 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELLS AT JANGIPARA PWSS, HOOGHLY DISTRICT UNDER CMSD-I (D), CDD, PHE DTE. | 578/CMSD-I | 30/11/2022 | 7 | C.M. ENTERPRISE | 0.98 | 0.95 | 100 | 0
2246 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply & Sanitation arrangement at ProposedT/W Site of JANGIPARA ZONE-III W/S Scheme under SERAMPORE Sub-Division P.H.E. Dte. | 1021/HUG | 06/04/2023 | 30 | RAYCON COOPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD | 5.56 | 5.36 | 100 | 100
2247 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Material Requisition To Resource Division | 1122/3/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
2248 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Material Requisition To Resource Division | 2210/3/Hug | 30/09/2022 | 0 | Resource Division | 0.05 | 0 | 0 | 0
2249 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Material Requisition To Resource Division | 1291/1/Hug | 24/06/2022 | 0 | Resource Division | 9.24 | 0 | 0 | 0
2250 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Material Requisition To Resource Division | 1384/2/Hug | 15/05/2023 | 0 | Resource Division | 35.97 | 0 | 0 | 0
2251 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Material Requisition To Resource Division | 79/6/Hug | 06/01/2023 | 0 | Resource Division | 8.04 | 0 | 0 | 0
2252 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Quatation Bill for New Service Connection of WBSEDCL at Jangipara W/S. Sch. PH-III | 164 | 21/02/2023 | 0 | WBSEDCL | 7.85 | 0 | 0 | 0
2253 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Quatation Bill for New Service Connection of WBSEDCL at Jangipara W/S. Sch. PH-IV | 164 | 21/02/2023 | 0 | WBSEDCL | 2.77 | 0 | 0 | 0
2254 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, RWS HOOGHLY SUB-DIVISION, PHE DTE. | BP-2023-24-233 | 31/07/2023 | 0 | AATISH KUMAR SHAW | 0.39 | 0 | 0 | 0
2255 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Augmentation of JANGIPARA (ZONE-III) Water Supply Scheme with LDS,FHTC, Rising Main at JANGIPARA Block Under Serampore Sub-Division of Hooghly Division PHE Dte. | 2481/HUG | 21/11/2022 | 40 | MAA TARA CONSTRUCTION | 118.54 | 113.92 | 96.11 | 60
2256 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jangipara water supply scheme, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | 843/ED | 14/02/2023 | 90 | R.M.D TRADING. | 21.82 | 21.44 | 98.25 | 30
2257 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for JANGIPARA PIPED W/S SCHEME, Zone-I, T.W. No. III, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 455/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 6.94 | 71.57 | 60
2258 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for JANGIPARA PIPED W/S SCHEME, Zone-I, T.W. No. IV, Block: Jangipara, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1474/ED | 25/07/2024 | 90 | SARVATAH PROJECTS PRIVATE LIMITED | 11.1 | 0 | 0 | 0
2259 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under JANGIPARA Block of Serampore Sub Division under Hooghly Division PHE Dte. | 519/SER | 11/09/2024 | 5 | TOTON MONDAL | 4.77 | 4.72 | 100 | 95
2260 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving : ¦data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe : Water Supply Scheme under Chanditala I& Il & Jangipara Block (Part-l) in the District of Hooghly under Chinsurah Sub Division under Hooghly Division, PHE Dte. | 3211/HUG | 12/09/2024 | 15 | TECHVISION | 4.2 | 0 | 0 | 80
2261 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | AUGMENTATION of JANGIPARA ZONE-I Piped Water Supply Scheme with LDS, Rising Main, Repairing of Switch Room, Boundary wall of ZONE-I under Serampore Sub-Division Of Hooghly Division P.H.E Dte. Block-JANGIPARA, District:- Hooghly [AUGMENTATION SCHEME] | 1353/HUG | 12/05/2023 | 965 | ASIA CONSTRUCTION | 350.59 | 155.1 | 44.24 | 60
2262 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Construction of 700 cum capacity RCC OHR with 20.0 mtr Staging height including soil investigation & FHTC For AUGMENTATION Of JANGIPARA ZONE-I Piped Water Supply Scheme under Serampore Sub-Division Of Hooghly Division P.H.E Dte. Block-JANGIPARA, District:- Hooghly [AUGMENTATION SCHEME] | 1354/HUG | 12/05/2023 | 873 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 275.31 | 75.34 | 27.37 | 35
2263 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | AUGMENTATION of JANGIPARA ZONE-II Piped Water Supply Scheme with LDS,Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site under JANGIPARA BlockWithin Serampore Sub-Division Of Hooghly Division P.H.E Dte., District:- Hooghly [AUGMENTATION SCHEME] | 2410/HUG | 11/08/2023 | 600 | BALAJI UDDYOG | 291.59 | 77.8 | 26.68 | 60
2264 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Sinking of additional tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution at Anarbati mouza of Jangipara Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | 748/HUG | 05/03/2024 | 60 | BANSBERIA CONSTRUCTION CO. | 31.77 | 0 | 0 | 70
2265 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Sinking of 3rd tube-well by D.R. Rig method ,Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of JANGIPARA Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | 447/HUG | 15/02/2024 | 60 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 31.62 | 0 | 0 | 20
2266 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Laying of 225 MM & 250 MM pipeline by HDD process under Jangipara Water Supply Scheme under Serampore Sub-Division, P.H.E. Dte. | 743/HUG | 05/03/2024 | 347 | ASIA CONSTRUCTION | 88.55 | 0 | 0 | 87
2267 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Sinking of 3 nos. 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 2nd Tube Well Site of JANGIPARA ZONE-II W/S Scheme, 4th Tube Well Site of ANTPUR W/S Scheme, & 4th Tube Well Site of JANGALPARA W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. . | 3522/HUG | 22/10/2024 | 316 | WATER TECH | 29.57 | 0 | 0 | 45
2268 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Repairing & Renovation of existing room for Chemical test of drinking water at Headwork site of Jangipara Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. (Block- Jangipara) | 266/SER | 03/04/2025 | 10 | MAA TARA CONSTRUCTION | 4.99 | 0 | 0 | 99
2269 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANGIPARA. , SM/10339 | Augmentation | Sinking of `Two Nos Big Dia Tube Well (250 mm X 150 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at JANGIPARA ZONE-II PWSS of SERAMPORE Sub-Division under Hooghly Division, PHE Dte. | 2501/HUG | 22/11/2022 | 830 | GLOBAL CONSTRUCTION | 20.07 | 0 | 0 | 50
2270 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II , SM/09688 | Augmentation | Preparation of DPR for Augmentation of KAKNAN Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II]. | 612/Arg | 31/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.17 | 3.16 | 99.58 | 100
2271 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II , SM/09688 | Augmentation | Augmentation of KAKNAN (ZONE-I) Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection, of Switch room, Boundary wall, existing OHR at KHANAKUL-II Block under Arambag Sub-Division, PHE Dte. | 963//Hug | 17/05/2022 | 60 | UNIQUE AGENCY | 166.37 | 165.74 | 99.62 | 100
2272 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II , SM/09688 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at KAKNAN (ZONE-II) PWSS of Arambag Sub-Division under Hooghly Division, PHE Dte. SL NO - 10 | 1958/HUG | 07/09/2022 | 30 | OSMAN SEKH | 11.32 | 10.41 | 100 | 100
2273 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II , SM/09688 | Augmentation | Material Requisition To Resource Division | 424/4/Hug | 07/03/2022 | 0 | Resource Division | 36.05 | 0 | 0 | 0
2274 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II , SM/09688 | Augmentation | Material Requisition To Resource Division | 1124/4/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
2275 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II , SM/09688 | Augmentation | Material Requisition To Resource Division | 1773/40/Hug | 29/08/2022 | 0 | Resource Division | 1.38 | 0 | 0 | 0
2276 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II , SM/09688 | Augmentation | Material Requisition To Resource Division | 1590/2/Hug | 03/08/2022 | 0 | Resource Division | 6.15 | 0 | 0 | 0
2277 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II , SM/09688 | Augmentation | Material Requisition To Resource Division | 1385/13/Hug | 15/05/2023 | 0 | Resource Division | 1.79 | 0 | 0 | 0
2278 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II , SM/09688 | Augmentation | Quotation Bill for New Service Connection at Aug. of Kaknan W/S. Sch. TW-III Hooghly |  | 13/03/2023 | 0 | WBSEDCL | 3.65 | 0 | 0 | 0
2279 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II , SM/09688 | Augmentation | SUBMISSION OF QUOTATION BILL FOR THE WBSEDCL BILL RAISED BY THE EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE. | BP-2022-23-644 | 25/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.65 | 0 | 0 | 0
2280 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II , SM/09688 | Augmentation | Augmentation of KAKNAN (ZONE-II) Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection, Construction of Switch Room & Boundary Wall of 3rd T.W Site at KHANAKUL-II Block under Arambag Sub-Division, PHE Dte. | 1086/Hug | 02/06/2022 | 30 | SWASTIK ENTERPRISE | 66.2 | 49.6 | 100 | 50
2281 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II , SM/09688 | Augmentation | Construction of Drain, Internal Road & Land Development works at Head Work site of Kaknan W/S Scheme under Arambagh Sub - Division P.H.E. Dte. | 728/Arg | 29/09/2022 | 926 | UNIQUE AGENCY | 3.81 | 0 | 0 | 100
2282 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II , SM/09688 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kaknan water supply scheme, T.W. No.- I, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | 937/ED | 22/02/2023 | 922 | OSMAN SEKH | 10.75 | 10.38 | 97.43 | 83
2283 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. , SM/09689 | Augmentation | Repairing work of O.H.R. and allied works of Boundary Wall, Gate, Pump room etc. at KHARSARAI water supply scheme due to damages caused by Super Cyclone "AMPHAN" Under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 1918/HUg | 27/10/2021 | 30 | R.K. TRADERS | 6.22 | 6.2 | 99.66 | 100
2284 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. , SM/09689 | Augmentation | Repairing work of O.H.R. and allied works of Boundary Wall, Gate, Pump room etc. at KHARSARAI water supply scheme due to damages caused by Super Cyclone "AMPHAN" Under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 1867/Hug | 07/10/2021 | 30 | R.K. TRADERS | 6.22 | 0 | 0 | 100
2285 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. , SM/09689 | Augmentation | Preparation of DPR for Augmentation of Kharsarai Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | 287/SER | 18/02/2022 | 20 | SRIJAN ECHOLOGICAL UPLIFTMENT PVT. LTD. | 2.8 | 2.8 | 99.99 | 100
2286 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. , SM/09689 | Augmentation | Sinking of I(One) No Big dia tube well (300 mmx200mm) with supply of PVC Pipe and strainer and having depth upto 150M of Kharsarai W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 1416/HUG | 12/07/2022 | 30 | B.R SUPPLIERS | 9.8 | 9.47 | 96.56 | 100
2287 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. , SM/09689 | Augmentation | Material Requisition To Resource Division | 422/1/Hug | 07/03/2022 | 0 | Resource Division | 39.63 | 0 | 0 | 0
2288 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. , SM/09689 | Augmentation | Material Requisition To Resource Division | 1122/5/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
2289 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. , SM/09689 | Augmentation | Material Requisition To Resource Division | 1384/5/Hug | 15/05/2023 | 0 | Resource Division | 10.71 | 0 | 0 | 0
2290 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. , SM/09689 | Augmentation | Augmentation of Kharsari Piped WS scheme with LDS Rising main Construction of switch room without w/s & toilet construction repairing of boundary wall switch room with FHTC work at Chanditala II Block of Hooghly Dist under Hooghly Divn PHE Dte. | 638/HUG | 01/04/2022 | 180 | M/S S.G. CONSTRUCTION | 166.73 | 163.66 | 100 | 80
2291 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. , SM/09689 | Augmentation | Painting of OHR, Construction of Guard Wall with Boundary Wall, Pathwaty, Drain at Kharsarai Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 732/HUG | 05/03/2024 | 60 | M/S ATANU DAS | 20.89 | 15.67 | 100 | 80
2292 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. , SM/09689 | Augmentation | Laying Distribution of left out portion of pipeline to restore the water supply at Kharsarai Functional Hosuehold Tap Connection at Kharsarai Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 2224/HUG | 10/06/2024 | 30 | ARATI ENGINEERING | 14.18 | 13.75 | 100 | 100
2293 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Itagarh Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte , SM/10134 | Retrofitting | Providing 615 nos Functional Household Tap Connection (FHTC) within the Itagarh & Sargaria Mouzas of Itagarh Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | 473/Hug | 10/03/2022 | 30 | THREE MAA ENTERPRISE | 30.63 | 29.03 | 94.77 | 0
2294 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Itagarh Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte , SM/10134 | Retrofitting | Providing 385 nos Functional Household Tap Connection (FHTC) within the Bhalki & Malancha Mouzas of Itagarh Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | 472/Hug | 10/03/2022 | 20 | SURAJIT SINGHA RAY | 19.2 | 17.71 | 92.23 | 0
2295 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Itagarh Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte , SM/10134 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM in ITAGARH PWSS, Block-BALAGARH under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO - 04 | 2085/HUG | 21/09/2022 | 30 | SWARNA ENTERPRISE | 11.4 | 9.87 | 100 | 0
2296 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional House hold Tap Connection(FHTC)Within the Command Area of Itagarh Water Supply Scheme of Balagarh Block Under Hooghly Division, P.H.E Dte , SM/10134 | Retrofitting | Laying HDPE pipe and allied repairing works of Itagarh water supply scheme under Chinsurah Sub Divusion undre Hooghly Division PHE Dte. | 815/CH | 31/08/2023 | 15 | GHOSH CONSTRUCTION | 0.94 | 0.93 | 100 | 95
2297 | HOOGHLY | Hooghly Division | Retrofitting works for Providing Functional Household Tap Connection (FHTC) within the command are a of Shibrai W/S Scheme , SM/10136 | Retrofitting | Providing 489 nos Functional Household Tap Connection (FHTC) within the Bejpara, Radhanagar & Uttar Darshan Mouzas of Shibrai Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | 469/Hug | 10/03/2022 | 30 | TAPAS ADHYA | 24.49 | 19.93 | 81.36 | 0
2298 | HOOGHLY | Hooghly Division | Retrofitting works for Providing Functional Household Tap Connection (FHTC) within the command are a of Shibrai W/S Scheme , SM/10136 | Retrofitting | Providing 881 nos Functional Household Tap Connection (FHTC) within the Dakshin Darshan, Pakri & Shibrai Mouzas of Shibrai Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division PHE Dte | 468/Hug | 10/03/2022 | 40 | SOUMYADIP DE | 44.14 | 28.92 | 65.52 | 0
2299 | HOOGHLY | Hooghly Division | Retrofitting works for Providing Functional Household Tap Connection (FHTC) within the command are a of Shibrai W/S Scheme , SM/10136 | Retrofitting | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 Shibrai PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 269/CH | 20/02/2025 | 10 | AYUSH ENTERPRISE | 3.18 | 0 | 0 | 0
2300 | HOOGHLY | Hooghly Division | Retrofitting works for Providing Functional Household Tap Connection (FHTC) within the command are a of Shibrai W/S Scheme , SM/10136 | Retrofitting | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site (PH-I) of Shibrai PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 268/CH | 20/02/2025 | 10 | R.K. TRADERS | 4.82 | 0 | 0 | 0
2301 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KOLA WATER SUPPLY SCHEME UNDER CHINSURAH-MOGRA BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09775 | Retrofitting | Providing 1200 nos Functional Household Tap Connection (FHTC) within the command area of KOLA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 119/Hug | 19/01/2022 | 60 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 67.95 | 63.78 | 93.85 | 0
2302 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KOLA WATER SUPPLY SCHEME UNDER CHINSURAH-MOGRA BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09775 | Retrofitting | Providing 350 nos Functional Household Tap Connection (FHTC) within the command area of KOLA & HARAL ZONE-II Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 457/Hug | 10/03/2022 | 20 | ARATI ENGINEERING | 19.29 | 18.63 | 100 | 0
2303 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KOLA WATER SUPPLY SCHEME UNDER CHINSURAH-MOGRA BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09775 | Retrofitting | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT RAGHUNATHPUR W/S SCHEME TW-I, POLBA DADPUR BLOCK, HOOGHLY DIOSTRICT UNDER CDD, PHE DTE | 289/CMSD-II (D) | 01/06/2022 | 15 | C.M. ENTERPRISE | 4.99 | 0 | 0 | 0
2304 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KOLA WATER SUPPLY SCHEME UNDER CHINSURAH-MOGRA BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09775 | Retrofitting | Providing 800 nos F.H.T.C. in Kola and its Adjoining Mouzas Water Supply Scheme UnderChinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah-Mogra] | 940/Hug | 06/05/2021 | 30 | PRASUN ENTERPRISE (PRASUN BISWAS) | 39.21 | 6.16 | 31.44 | 0
2305 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KOLA WATER SUPPLY SCHEME UNDER CHINSURAH-MOGRA BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09775 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of KOLA PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 1133/HUG | 19/04/2023 | 30 | ROY ENTERPRISE | 33.33 | 32.86 | 100 | 100
2306 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BASUDEBBATI WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09777 | Retrofitting | Providing 40 nos. Functional House Hold Connection (FHTC) within the Command area of Basudebbati Water Supply Scheme Under Chinsurah Sub-Division. | 461/CH | 31/05/2022 | 20 | CREATION CONSTRUCTION | 4.3 | 4.28 | 100 | 0
2307 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BASUDEBBATI WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09777 | Retrofitting | Providing 1961 nos Functional Household Tap Connection (FHTC) within the command area of Basudebbati Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 2129/Hug | 01/12/2021 | 50 | CREATION CONSTRUCTION | 80.54 | 80.53 | 100 | 0
2308 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BASUDEBBATI WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09777 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) under JJM withing left out portion of BASUDEBBATI PWSS under Chinsurah Sub Division of Hooghly Division P.H.E Dte. | 28/CH | 05/01/2024 | 15 | M/S BIMAL DAS AND CO. | 4.35 | 4.34 | 100 | 50
2309 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BASUDEBBATI WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09777 | Retrofitting | Providing Functional House hold tap connection (FHTC) under JJM within left out portion at Basudevbati PWSS under Polba Dadpur Block of chinsurah sub Division of Hooghly Division, P.H.E Dte | 4046/HUG | 19/12/2024 | 90 | S.B. ENTERPRISE | 5.59 | 0 | 0 | 50
2310 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF BHASTARA PWSS FOR PROVIDING 2289 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. , SM/11001 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of BHASTARA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 2277/HUG | 19/10/2022 | 50 | SATYA NARAYAN BISWAS | 56.36 | 48.47 | 86.01 | 0
2311 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF BHASTARA PWSS FOR PROVIDING 2289 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH IN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION P.H.E DTE. , SM/11001 | Retrofitting | Material Requisition To Resource Division | 1123/2/HUG | 06/06/2022 | 0 | Resource Division | 11 | 0 | 0 | 0
2312 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SOMRA WATER SUPPLY SCHEME , SM/11005 | Retrofitting | Providing 1000 nos Functional Household Tap Connection (FHTC) within Bankipur, Jasra, Somra &Baligari Mouza of Somra Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | 1272/Hug | 23/06/2022 | 40 | S AND P CONSTRUCTION | 50.86 | 50.04 | 100 | 0
2313 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SOMRA WATER SUPPLY SCHEME , SM/11005 | Retrofitting | Functional Household Tap Connection (FHTC) under JJM in SOMRA PWSS, Block-BALAGARH under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO - 01 | 2082/HUG | 21/09/2022 | 45 | M/S T.K.B. CONSTRUCTION | 53.89 | 53.8 | 100 | 0
2314 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SOMRA WATER SUPPLY SCHEME , SM/11005 | Retrofitting | Providing 1000 nos Functional Household Tap Connection (FHTC) within Masara,Debipur, Belgachhi, Muragari,Rajaipur,Kanpara, Bhelurgari,Kolara & Sukharia Mouza of Somra Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | 728/Hug | 07/04/2022 | 40 | JAI BHARAT COMMERCIAL CORPORATION | 50.33 | 49.09 | 100 | 0
2315 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SOMRA WATER SUPPLY SCHEME , SM/11005 | Retrofitting | Material Requisition To Resource Division | 1123/1/HUG | 06/06/2022 | 0 | Resource Division | 11 | 0 | 0 | 0
2316 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SOMRA WATER SUPPLY SCHEME , SM/11005 | Retrofitting | RESTORATION COST FOR PIPE LAYING WORK BALAGARH INCHURA ROAD | BP-2024-25-96 | 02/05/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 33.75 | 0 | 0 | 0
2317 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SOMRA WATER SUPPLY SCHEME , SM/11005 | Retrofitting | Restoration Balagarh Inchura Road | BP-2024-25-1 | 08/04/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 33 | 0 | 0 | 0
2318 | HOOGHLY | Hooghly Division | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12262 | New | Material Requisition To Resource Division | 1386/20/Hug | 15/05/2023 | 0 | Resource Division | 15.66 | 0 | 0 | 0
2319 | HOOGHLY | Hooghly Division | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12262 | New | Material Requisition To Resource Division | 3059/10/Hug | 11/10/2023 | 0 | Resource Division | 15.66 | 0 | 0 | 0
2320 | HOOGHLY | Hooghly Division | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12262 | New | Material Requisition To Resource Division | 1264/15/HUG | 03/05/2023 | 0 | Resource Division | 32.44 | 0 | 0 | 0
2321 | HOOGHLY | Electrical | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12262 | New | Quotation Bill for New Service Connection at Khajurdaha W/S. Sch. TW-II | 680 | 19/01/2024 | 0 | WBSEDCL | 3.89 | 0 | 0 | 0
2322 | HOOGHLY | Electrical | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12262 | New | Quotation Bill for New Service Connection at Khajurdaha W/S. Sch. TW-I | 706 | 25/01/2024 | 0 | WBSEDCL | 4.32 | 0 | 0 | 0
2323 | HOOGHLY | Hooghly Division | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12262 | New | ROAD RESTORATION PAYMENT TO PWD FOR BHASTARA MAJINAN ROAD | 1234 | 27/09/2024 | 0 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 17.55 | 0 | 0 | 0
2324 | HOOGHLY | Hooghly Division | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12262 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 258.06 | 50.72 | 30
2325 | HOOGHLY | Electrical | KHAJURDAHA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12262 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Khajurdaha water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | 3495/ED | 30/12/2022 | 1555 | AHALYA ENGINEERING WORKS | 20.35 | 16.81 | 82.77 | 40
2326 | HOOGHLY | Hooghly Division | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12235 | New | Material Requisition To Resource Division | 1385/51/Hug | 15/05/2023 | 0 | Resource Division | 19.76 | 0 | 0 | 0
2327 | HOOGHLY | Hooghly Division | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12235 | New | Material Requisition To Resource Division | 3057/16/Hug | 11/10/2023 | 0 | Resource Division | 19.76 | 0 | 0 | 0
2328 | HOOGHLY | Hooghly Division | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12235 | New | Material Requisition To Resource Division | 1234/41/Hug | 28/04/2023 | 0 | Resource Division | 47.19 | 0 | 0 | 0
2329 | HOOGHLY | Hooghly Division | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12235 | New | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of NATIBPUR , SAIDPUR Zone-II , KRISHNANAGAR Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3170/HUG | 10/09/2024 | 45 | BIMAL KUMAR HALDER | 48.47 | 0 | 0 | 0
2330 | HOOGHLY | Hooghly Division | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12235 | New | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of NATIBPUR KRISHNANAGAR Zone-I , RASULPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte | 3782/HUG | 25/11/2024 | 60 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 55.13 | 0 | 0 | 0
2331 | HOOGHLY | Electrical | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12235 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for NATIBPUR PIPED W/S SCHEME, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1190/ED | 14/06/2024 | 90 | BARMAN ROY TRADERS | 10.47 | 0 | 0 | 0
2332 | HOOGHLY | Electrical | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12235 | New | Quotation Money depostion for new service connection at Natibpur pwss, P.H No-I, Dist- Hooghly uned ED, PHED. App. No.-5004020953 SM/12235 | BP-24-25-598 | 21/11/2024 | 0 | WBSEDCL | 8.56 | 0 | 0 | 0
2333 | HOOGHLY | Electrical | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12235 | New | Quotation money deposition for new service connection at Natibpur w/s scheme, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004216541 Reference ID- 503658560 SM Code-12235 | 410 | 21/08/2024 | 0 | WBSEDCL | 7.79 | 0 | 0 | 0
2334 | HOOGHLY | Electrical | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12235 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Natibpur water supply scheme, T.W. No. I & II, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. | 3471/ED | 30/12/2022 | 913 | BARMAN ROY TRADERS | 21.9 | 0 | 0 | 40
2335 | HOOGHLY | Hooghly Division | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12235 | New | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 245.84 | 36.93 | 50
2336 | HOOGHLY | Hooghly Division | GROUND WATER BASED NATIBPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12235 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0 | 0
2337 | HOOGHLY | Electrical | KAMALPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12229 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kamalpur water supply scheme, T.W. No.- I & II, Block: Dhaniakhali District- Hooghly under Electrical Division, PHE Dte. | 3492/ED | 30/12/2022 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 22.6 | 0 | 0 | 0
2338 | HOOGHLY | Hooghly Division | KAMALPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12229 | New | Material Requisition To Resource Division | 3059/35/Hug | 11/10/2023 | 0 | Resource Division | 22.49 | 0 | 0 | 0
2339 | HOOGHLY | Hooghly Division | KAMALPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12229 | New | Material Requisition To Resource Division | 1264/19/HUG | 03/05/2023 | 0 | Resource Division | 34.53 | 0 | 0 | 0
2340 | HOOGHLY | Electrical | KAMALPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12229 | New | Quotation Bill for New Service Connection at Kamalpur W/S. Sch. PH-I | 744 | 08/02/2024 | 0 | WBSEDCL | 14.44 | 0 | 0 | 0
2341 | HOOGHLY | Electrical | KAMALPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12229 | New | Quotation Bill for New Service Connection at Kamalpur W/S. Sch. PH-II | 743 | 08/02/2024 | 0 | WBSEDCL | 3.68 | 0 | 0 | 0
2342 | HOOGHLY | Electrical | KAMALPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12229 | New | Durgapur PH__II Water supply Scheme |  | 14/05/2024 | 0 | WBSEDCL | 3.68 | 0 | 0 | 0
2343 | HOOGHLY | Hooghly Division | KAMALPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12229 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 358.92 | 58.01 | 30
2344 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur , SM/11167 | Augmentation | Preparation of DPR for Augmentation of Madhusudanpur Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Chinsurah-Magra) | 133/CH | 17/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.01 | 2.96 | 98.55 | 0
2345 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur , SM/11167 | Augmentation | Material Requisition To Resource Division | 1123/4/HUG | 06/06/2022 | 0 | Resource Division | 11 | 0 | 0 | 0
2346 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur , SM/11167 | Augmentation | Material Requisition To Resource Division | 2211/2/Hug | 30/09/2022 | 0 | Resource Division | 30.8 | 0 | 0 | 0
2347 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur , SM/11167 | Augmentation | Material Requisition To Resource Division | 1991/2/HUG | 12/09/2022 | 0 | Resource Division | 21.16 | 0 | 0 | 0
2348 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur , SM/11167 | Augmentation | Material Requisition To Resource Division | 1386/14/Hug | 15/05/2023 | 0 | Resource Division | 11.35 | 0 | 0 | 0
2349 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur , SM/11167 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at MADHUSUDANPUR PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 08 | 1956/HUG | 07/09/2022 | 30 | OSMAN SEKH | 11.32 | 11.23 | 100 | 25
2350 | HOOGHLY | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur , SM/11167 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Madhusudanpur water supply scheme TW No I Block Chinsurah Mogra, District Hooghly under ED PHED. | 850/ED | 14/02/2023 | 567 | AMIT DAS | 10.75 | 10.45 | 97.45 | 90
2351 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur , SM/11167 | Augmentation | AUGMENTATION of MADHUSUDANPUR Piped Water Supply Scheme with Repairing of Switch Room & Boundary wall, Construction Of Switch Room, Boundary Wall & LDS, under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. Block-CHINSURAH MOGRA, District:- Hooghly [AUGMENTATION SCHEME] | 1016/HUG | 06/04/2023 | 90 | M/S T.K.B. CONSTRUCTION | 128.94 | 105.86 | 77.22 | 100
2352 | HOOGHLY | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur , SM/11167 | Augmentation | Quotation for new service connection at Madhusudanpur(S.Aug.) W/S Sch. , T/W No. -III (Nr. Tissu Bus stand) [SM/11167] under Mogra CCC, WBSEDCL, Ref Id. - 503586680, Dt. - 16/04/2024, Application No. - 5004053256, | 80 | 19/04/2024 | 0 | WBSEDCL | 4.7 | 0 | 0 | 0
2353 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur , SM/11167 | Augmentation | Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation, Rising Main, FHTC For AUGMENTATION of MADHUSUDANPUR Piped Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. Block CHINSURAH MOGRA, District:- Hooghly [AUGMENTATION SCHEME] | 1421/Hug | 17/05/2023 | 685 | SUBHANKAR GUHA | 166.98 | 51.52 | 30.85 | 30
2354 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Madhusudanpur , SM/11167 | Augmentation | Providing Functional House hold tap connection (FHTC) under JJM within Digirpara & Naapara of Madhusudanpur PWSS under Chinsurah Mogra Block of chinsurah sub Division of Hooghly Division, P.H.E Dte | 221/CH | 19/02/2025 | 30 | M/S T.K.B. CONSTRUCTION | 4.29 | 0 | 0 | 0
2355 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Additional survey work for preparation of DPR for Augmentation of Bhadur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I]. (Bhadur Part-B) | 335/Arg | 02/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.46 | 0.46 | 100 | 0
2356 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Preparation of DPR for Augmentation of Bhadur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I].(Bhadur Part-A) | 334/Arg | 02/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.68 | 3.6 | 76.84 | 0
2357 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Laying CI/D.I pipes & specials for Rising Main pipe line in between T.W NO.-I & II to OHR and interconnection with distribution system including allied work for Augmentation of BHADUR (ZONE-II) Water Supply Scheme at Goghat-I Block under Armabag Sub- Division of Hooghly Division, PHE Dte. | 2568/HUG | 24/08/2023 | 45 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 4.91 | 0 | 0 | 0
2358 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 235 mtrs. Depth) by utilising Departmental machineries for Bhadur W/S Scheme (Z-II, TW-I & II), Goghat-I block under hooghly District, CDD PHE Dte. | 2298/CDD | 30/03/2023 | 30 | CHANDA ENTERPRISE | 30.35 | 18.99 | 100 | 31
2359 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Material Requisition To Resource Division | 2211/3/Hug | 30/09/2022 | 0 | Resource Division | 30.8 | 0 | 0 | 0
2360 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Material Requisition To Resource Division | 1688/4/HUG | 22/08/2022 | 0 | Resource Division | 120.14 | 0 | 0 | 0
2361 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Material Requisition To Resource Division | 1773/13/Hug | 29/08/2022 | 0 | Resource Division | 1.03 | 0 | 0 | 0
2362 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Material Requisition To Resource Division | 1590/3/Hug | 03/08/2022 | 0 | Resource Division | 15.4 | 0 | 0 | 0
2363 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Material Requisition To Resource Division | 1106/5/HUG | 17/04/2023 | 0 | Resource Division | 23.22 | 0 | 0 | 0
2364 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Material Requisition To Resource Division | 1385/15/Hug | 15/05/2023 | 0 | Resource Division | 14.32 | 0 | 0 | 0
2365 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Material Requisition To Resource Division | 2607/3/Hug | 29/08/2023 | 0 | Resource Division | 18.58 | 0 | 0 | 0
2366 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Material Requisition To Resource Division | 3002/3/Hug | 05/10/2023 | 0 | Resource Division | 20.89 | 0 | 0 | 0
2367 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Material Requisition To Resource Division | 1105/5/Hug | 17/04/2023 | 0 | Resource Division | 86.37 | 0 | 0 | 0
2368 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Material Requisition To Resource Division | 1234/5/Hug | 28/04/2023 | 0 | Resource Division | 3.72 | 0 | 0 | 0
2369 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, ARAMBAGH SUB-DIVISION, PHE DTE. | BP-2022-23-547 | 21/02/2023 | 0 | M/S PRADYUT KUMAR HAZRA | 1.15 | 0 | 0 | 0
2370 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Quotation of New Service Connection for Bhadur w/s Scheme,Zone-I,TW No-III Dist-Hooghly Under ED,PHE Dte | 116 | 20/07/2023 | 0 | WBSEDCL | 6.86 | 0 | 0 | 0
2371 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Quotation of New Service Connection for Bhadur w/s scheme,zone-II,TW No-II Dist-Hooghly under ED,PHE Dte | 119 | 20/07/2023 | 0 | WBSEDCL | 2.8 | 0 | 0 | 0
2372 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Providing Functional Household Tap Connection in BHADUR (Zone-II) Piped Water Supply Scheme including Construction of 2 Nos. 3.6M X 3.0M Switch Room & 2 Nos. Boundary wall at Goghat-I Block under Arambagh Sub-Division of Hooghly Division PHE Dte. SL NO - 4 | 1782/HUG | 30/08/2022 | 45 | THREE MAA ENTERPRISE | 78.11 | 53.97 | 69.09 | 75
2373 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Augmentation of BHADUR (ZONE-I) Water Supply Scheme with LDS, FHTC, Rising Main & Construction of 350 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at GOGHAT-I Block under Arambagh Sub-Division under Hooghly Division PHE Dte. | 43/HUG | 04/01/2023 | 300 | TITAS CONSTRUCTION | 411.57 | 185.87 | 45.16 | 55
2374 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Protection works and other allied works at Head Work Site of BHADUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte | 4055/HUG | 19/12/2024 | 90 | AYUSH ENTERPRISE | 23.83 | 0 | 0 | 0
2375 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Laying Distribution System of BHADUR (Zone-II) Piped Water Supply Scheme within Bhadur, Mandalganti & Adra Mouza including Repairing of existing Switch rooms, Boundary walls of BHADUR (Zone-I & Zone-II) Water Supply Scheme at Goghat-I Block under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 2525/HUG | 23/11/2022 | 45 | M/S S & P CONSTRUCTION | 85 | 68.89 | 84.79 | 95
2376 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bhadur water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | 827/ED | 14/02/2023 | 90 | C.M.S. ENGINEERING CONCERN | 21.95 | 21.82 | 100 | 20
2377 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) ANANDAPUR PWSS-4nos (2) BHADUR(BHAGARBAND) PWSS-6nos (3) GOGHAT PWSS-2nos (4) JOYKRISHNAPUR PWSS-2nos | 816/Arg | 23/08/2024 | 130 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.42 | 100 | 100
2378 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Additional Quotation of Bhadur w/s Scheme,Zone-I,PH No-3 Block-Goghat-I Dist-Hooghly under Electrical division,PHE Dte.(SM/11463) Reference Id-860301435 | 183 | 03/06/2024 | 0 | WBSEDCL | 1.61 | 0 | 0 | 0
2379 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE , SM/11463 | Augmentation | Construction of 200 cum capacity OHR with 20 mtr. staging height including Soil Investigation work & LDS within Sekati(Part) Mouza for Augmentation of Bhadur (Zone-II) Water Supply Scheme at Goghat-I Block under Armabag Sub-Division of Hooghly Division, PHE Dte. | 1422/Hug | 12/07/2022 | 1025 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 98.87 | 46.61 | 47.15 | 50
2380 | HOOGHLY | Hooghly Division | Digra Mini Piped Water Supply Scheme , SM/13670 | New | Material Requisition To Resource Division | 1386/54/Hug | 15/05/2023 | 0 | Resource Division | 0.33 | 0 | 0 | 0
2381 | HOOGHLY | Hooghly Division | Digra Mini Piped Water Supply Scheme , SM/13670 | New | MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-293 | 19/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 28.12 | 0 | 0 | 0
2382 | HOOGHLY | Electrical | Digra Mini Piped Water Supply Scheme , SM/13670 | New | Mini piped Water Supply scheme |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
2383 | HOOGHLY | Electrical | Digra Mini Piped Water Supply Scheme , SM/13670 | New | Mini Piped Water Supply Scheme | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0 | 0
2384 | HOOGHLY | Hooghly Division | Basantapur Mini Piped Water Supply Scheme , SM/13560 | New | Material Requisition To Resource Division | 1386/25/Hug | 15/05/2023 | 0 | Resource Division | 0.57 | 0 | 0 | 0
2385 | HOOGHLY | Hooghly Division | Basantapur Mini Piped Water Supply Scheme , SM/13560 | New | xxx |  | 17/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 31.77 | 0 | 0 | 0
2386 | HOOGHLY | Hooghly Division | Basantapur Mini Piped Water Supply Scheme , SM/13560 | New | Implementation of single village Basantapur mini pipe water supply scheme |  | 27/09/2024 | 0 | HOOGHLY ZILLA PARISHAD | 1.54 | 0 | 0 | 0
2387 | HOOGHLY | Electrical | Basantapur Mini Piped Water Supply Scheme , SM/13560 | New | Mini piped Water Supply scheme |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
2388 | HOOGHLY | Hooghly Division | Basantapur Mini Piped Water Supply Scheme , SM/13560 | New | Bhabapur Mini PWSS |  | 25/09/2024 | 0 | HOOGHLY ZILLA PARISHAD | 67.4 | 0 | 0 | 0
2389 | HOOGHLY | Electrical | Basantapur Mini Piped Water Supply Scheme , SM/13560 | New | Mini Piped Water Supply Scheme | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0 | 0
2390 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13346 | Augmentation | Withdrawing Existing C.I Pipes & Specials & Laying CI/DI Pipes & Specials for Rising main pipeline for AMODGHATA W/S under Chinsurah Sub - Division P.H.E. Dte. | 717 CH | 23/08/2022 | 15 | SHREEOM ENTERPRISE | 1.77 | 1.75 | 100 | 0
2391 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13346 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Amodghata water supply scheme, T.W. No.- V, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | 945/ED | 22/02/2023 | 90 | JOYSHREE CONCERN | 10.83 | 0 | 0 | 0
2392 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13346 | Augmentation | Construction of 3.60 m X 3.00 m Switch Room with Sanitary and Water Supply & Sanitation arrangement at 4th T/W Site of AMODGHATA W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | 721/CH | 23/08/2022 | 45 | S B ENTERPRISE | 4.97 | 4.94 | 100 | 0
2393 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13346 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Amodghata water supply scheme, T.W. No.- V, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | 867/ED | 14/02/2023 | 90 | JOYSHREE CONCERN | 10.83 | 10.81 | 100 | 100
2394 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13346 | Augmentation | Construction of Switch Room & Boundary Wall in Proposed T.W Sites, Laying Distribution System, Laying rising main pipe line for interconnection between T.W & Distribution, Repairing of Switch Room & Boundary Wall and other allied work for Source Augmentation of AMODGHATA Piped Water Supply Scheme Under Hooghly Division P.H.E Dte within Chinsurah Mogra Block. | 283/HUG | 01/02/2023 | 90 | R.K. TRADERS | 115.44 | 98.11 | 71.12 | 75
2395 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13346 | Augmentation | Quotation bill for new service connection at Amodghata w/s scheme | 174 | 28/02/2023 | 0 | WBSEDCL | 7.19 | 0 | 0 | 0
2396 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13346 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed for Sajal Gram Display Board at different locations in 6 (Six) Nos villages & HGJ villages of Amodghata PWSS for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. | 146/CH | 20/02/2024 | 7 | R.K. TRADERS | 0.95 | 0.95 | 100 | 50
2397 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF AMODGHATA PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/13346 | Augmentation | Supply, Delivery & Installation of S/P/M & other E/M equipments etc. with allied works for Amodghata W/S. Sch. TW- IV, Hooghly | 1547/ED | 20/09/2022 | 90 | BISALAXMI ENTERPRISE | 9.64 | 9.63 | 99.95 | 99
2398 | HOOGHLY | Hooghly Division | BAHIRKHANDA PIPED WATER SUPPLY SCHEME , SM/13404 | New | Material Requisition To Resource Division | 1235/11/Hug | 28/04/2023 | 0 | Resource Division | 85.79 | 0 | 0 | 0
2399 | HOOGHLY | Hooghly Division | BAHIRKHANDA PIPED WATER SUPPLY SCHEME , SM/13404 | New | Material Requisition To Resource Division | 1383/6/Hug | 15/05/2023 | 0 | Resource Division | 22.24 | 0 | 0 | 0
2400 | HOOGHLY | Hooghly Division | BAHIRKHANDA PIPED WATER SUPPLY SCHEME , SM/13404 | New | Material Requisition To Resource Division | 3058/25/Hug | 11/10/2023 | 0 | Resource Division | 14.85 | 0 | 0 | 0
2401 | HOOGHLY | Electrical | BAHIRKHANDA PIPED WATER SUPPLY SCHEME , SM/13404 | New | new service connection | 164 | 03/08/2023 | 0 | WBSEDCL | 1.7 | 0 | 0 | 0
2402 | HOOGHLY | Electrical | BAHIRKHANDA PIPED WATER SUPPLY SCHEME , SM/13404 | New | new service connection | 165 | 03/08/2023 | 0 | WBSEDCL | 3.25 | 0 | 0 | 0
2403 | HOOGHLY | Electrical | BAHIRKHANDA PIPED WATER SUPPLY SCHEME , SM/13404 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bahirkhanda water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | 3481/ED | 30/12/2022 | 60 | S.M. ELECTRICALS | 21.48 | 21.44 | 100 | 60
2404 | HOOGHLY | Electrical | BAHIRKHANDA PIPED WATER SUPPLY SCHEME , SM/13404 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bahir Khanda water supply scheme, T.W. No. III, Block: Tarakeswar, District: Hooghly under Electrical Division, PHE Dte. | 342/ED | 21/02/2024 | 90 | JOYSHREE CONCERN | 10.58 | 10.36 | 97.42 | 20
2405 | HOOGHLY | Electrical | BAHIRKHANDA PIPED WATER SUPPLY SCHEME , SM/13404 | New | Quotation of New Service Connection for Bahir Khanda w/S Scheme,TW No-3 Block-Haripal Dist-Hooghly under ED,PHE Dte. (SM/13404) Application No-5003976156 Reference Id-503538913 | 900 | 19/03/2024 | 0 | WBSEDCL | 3.58 | 0 | 0 | 0
2406 | HOOGHLY | Hooghly Division | BAHIRKHANDA PIPED WATER SUPPLY SCHEME , SM/13404 | New | BAHIRKHANDA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under HARIPAL Block of Chandannagar Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] [2nd Call of WBPHE/EE/51/HUG/2022-23(Sl No. 3)] | 1670/HUG | 08/06/2023 | 938 | DIPTI TRADERS | 948.76 | 786.93 | 82.94 | 96
2407 | HOOGHLY | Hooghly Division | Adra mini pipe water supply scheme , SM/13589 | New | Material Requisition To Resource Division | 1385/48/Hug | 15/05/2023 | 0 | Resource Division | 0.56 | 0 | 0 | 0
2408 | HOOGHLY | Hooghly Division | Adra mini pipe water supply scheme , SM/13589 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-240 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 32.72 | 0 | 0 | 0
2409 | HOOGHLY | Electrical | Adra mini pipe water supply scheme , SM/13589 | New | Mini Piped Water Supply Scheme. | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0 | 0
2410 | HOOGHLY | Hooghly Division | BINAGRAM PIPED WATER SUPPLY SCHEME , SM/13568 | New | Material Requisition To Resource Division | 1235/15/Hug | 28/04/2023 | 0 | Resource Division | 47.05 | 0 | 0 | 0
2411 | HOOGHLY | Hooghly Division | BINAGRAM PIPED WATER SUPPLY SCHEME , SM/13568 | New | Material Requisition To Resource Division | 1383/2/Hug | 15/05/2023 | 0 | Resource Division | 16.44 | 0 | 0 | 0
2412 | HOOGHLY | Hooghly Division | BINAGRAM PIPED WATER SUPPLY SCHEME , SM/13568 | New | Material Requisition To Resource Division | 3058/24/Hug | 11/10/2023 | 0 | Resource Division | 14.55 | 0 | 0 | 0
2413 | HOOGHLY | Electrical | BINAGRAM PIPED WATER SUPPLY SCHEME , SM/13568 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Binagram water supply scheme, T.W. No.- I & II, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | 776/ED | 09/02/2023 | 90 | STANDARD ELECTRICALS | 22.4 | 13.05 | 58.24 | 50
2414 | HOOGHLY | Hooghly Division | BINAGRAM PIPED WATER SUPPLY SCHEME , SM/13568 | New | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Binagram 1st T/W site & Naita 2nd T/W site under Chandannagar Sub-Division PHE Dte. | 922/Chan | 19/07/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 0 | 100
2415 | HOOGHLY | Electrical | BINAGRAM PIPED WATER SUPPLY SCHEME , SM/13568 | New | Quotation Bill for New Service Connection at Binogram W/S. Sch. PH-I | 606 | 03/01/2024 | 0 | WBSEDCL | 7.72 | 0 | 0 | 0
2416 | HOOGHLY | Electrical | BINAGRAM PIPED WATER SUPPLY SCHEME , SM/13568 | New | Quotation Bill for New Service Connection at Binogram W/S. Sch. PH-II | 605 | 03/01/2024 | 0 | WBSEDCL | 20.72 | 0 | 0 | 0
2417 | HOOGHLY | Hooghly Division | BINAGRAM PIPED WATER SUPPLY SCHEME , SM/13568 | New | BINAGRAM Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub-Division of Hooghly Division P.H.E Dte under SINGUR Block, District:- Hooghly [NEW SCHEME] | 2238/HUG | 01/08/2023 | 552 | SIBSANKAR CHOWDHURY | 672.18 | 201.3 | 29.95 | 30
2418 | HOOGHLY | Hooghly Division | GHATAMPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13321 | New | Material Requisition To Resource Division | 1386/3/Hug | 15/05/2023 | 0 | Resource Division | 21.59 | 0 | 0 | 0
2419 | HOOGHLY | Hooghly Division | GHATAMPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13321 | New | Material Requisition To Resource Division | 1264/3/HUG | 03/05/2023 | 0 | Resource Division | 12.22 | 0 | 0 | 0
2420 | HOOGHLY | Hooghly Division | GHATAMPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13321 | New | Material Requisition To Resource Division | 3059/20/Hug | 11/10/2023 | 0 | Resource Division | 21.59 | 0 | 0 | 0
2421 | HOOGHLY | Electrical | GHATAMPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13321 | New | Quotation Bill for New Service Connection at Ghatampur W/S. Sch. | 430,431,432,433 | 21/11/2023 | 0 | WBSEDCL | 15.55 | 0 | 0 | 0
2422 | HOOGHLY | Electrical | GHATAMPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13321 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghatampur water supply scheme, T.W. No.- I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | 778/ED | 09/02/2023 | 90 | C.M.S. ENGINEERING CONCERN | 23.74 | 23.17 | 97.58 | 97
2423 | HOOGHLY | Electrical | GHATAMPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13321 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghatampur water supply scheme, T.W. No. III & IV, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | 3451/ED | 11/08/2023 | 90 | C.M.S. ENGINEERING CONCERN | 23.25 | 22.19 | 95.43 | 97
2424 | HOOGHLY | Hooghly Division | GHATAMPUR PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/13321 | New | Ground Water Based Piped Water Supply Schemes (PWSS) under POLBA-DADPUR Block at DALIMBA, GHATAMPUR, HASNAN, KAMRAI, KUCHPALA, PATUL, UTTAR BABNAN (ZONE-I) & UTTAR BABNAN (ZONE-II) Mouzas including Construction of different capacities R.C.C. Over Head Reservoirs (OHRs), Sinking of Tube Wells, Laying Distribution Systems (LDS), Laying Rising Main Interconnection pipelines, providing Functional Household Tap Connections (FHTCs), Construction of Switch Rooms, Boundary Walls etc. under Hooghly Division P.H.E. Dte. in connection with JJM. | 955/HUG | 30/03/2023 | 887 | GREEN ROYAL INFRA CON PVT LTD | 3672.07 | 551.22 | 84.73 | 15
2425 | HOOGHLY | Hooghly Division | Ground Water Based Bighati (Zone -II) PWSS , SM/15249 | New | Material Requisition To Resource Division | 1383/21/Hug | 15/05/2023 | 0 | Resource Division | 9.73 | 0 | 0 | 0
2426 | HOOGHLY | Hooghly Division | Ground Water Based Bighati (Zone -II) PWSS , SM/15249 | New | Material Requisition To Resource Division | 3058/23/Hug | 11/10/2023 | 0 | Resource Division | 9.73 | 0 | 0 | 0
2427 | HOOGHLY | Hooghly Division | Ground Water Based Bighati (Zone -II) PWSS , SM/15249 | New | Material Requisition To Resource Division | 1235/5/Hug | 28/04/2023 | 0 | Resource Division | 54.25 | 0 | 0 | 0
2428 | HOOGHLY | Electrical | Ground Water Based Bighati (Zone -II) PWSS , SM/15249 | New | Quotation bill of WBSEDCL security deposit for Bighati PWSS, TW No.- II | 524 | 13/12/2023 | 0 | WBSEDCL | 4.06 | 0 | 0 | 0
2429 | HOOGHLY | Electrical | Ground Water Based Bighati (Zone -II) PWSS , SM/15249 | New | Quotation for new service connection at Bighati W/S Sch., Zone- II, T/W No. - III, Block - Singur, [SM/15249], under WBSEDCL, Khalisani CCC, Ref ID- 503803673, Dt. - 26-11-2024, Application No. - 5004481450, | 608 | 05/12/2024 | 0 | WBSEDCL | 5.32 | 0 | 0 | 0
2430 | HOOGHLY | Hooghly Division | Ground Water Based Bighati (Zone -II) PWSS , SM/15249 | New | BIGHATI (ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch rooms & boundary walls at different TW site under SINGUR Block, District- Hooghly.[NEW SCHEME] | 1061/HUG | 12/04/2023 | 270 | RURAL CONSTRUCTION (MANIK CHANDRA ADAK) | 422.23 | 314.67 | 74.53 | 100
2431 | HOOGHLY | Hooghly Division | Ground Water Based Bighati (Zone -II) PWSS , SM/15249 | New | Sinking of 1no. tubewell with Construction of switch-room & boundary wall, Laying Rising Main at Proposed TW site at BIGHAT ZONE - II Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte.Block Singur, District:- Hooghly | 2367/HUG | 21/06/2024 | 539 | RURAL CONSTRUCTION (MANIK CHANDRA ADAK) | 31.59 | 8.19 | 25.93 | 100
2432 | HOOGHLY | Electrical | Ground Water Based Bighati (Zone -II) PWSS , SM/15249 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bighati water supply scheme, Zone-I, T.W. No.- I & II and Zone-II, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | 1242/ED | 06/03/2023 | 630 | ORIENTAL ENGINEERING CO. | 40.49 | 12.76 | 63.14 | 80
2433 | HOOGHLY | Central Drilling | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se , SM/16449 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 150 mtrs. Depth) by utilising Departmental machineries for Borhal W/S Scheme (Z-I), Jangipara block under hooghly District, CDD PHE Dte. | 2330/CDD | 30/03/2023 | 30 | C.M. ENTERPRISE | 22.68 | 10.58 | 46.67 | 47
2434 | HOOGHLY | Central Drilling | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se , SM/16449 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 180 mtrs. Depth) by utilising Departmental machineries for Borhal W/S Scheme (Z-I, TW-I), Jangipara block under hooghly District, CDD PHE Dte. | 1995/CDD | 07/02/2023 | 30 | UTTAM KUMAR CHATTERJEE | 12.54 | 10.58 | 100 | 100
2435 | HOOGHLY | Electrical | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se , SM/16449 | Augmentation | Borhal Z-I P H NO-3 | 145 | 26/07/2023 | 0 | WBSEDCL | 4.55 | 0 | 0 | 0
2436 | HOOGHLY | Electrical | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se , SM/16449 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Borhal (Zone-I) water supply scheme, T.W. No. I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | 1631/ED | 11/04/2023 | 90 | S.S. ENTERPRISES | 23.3 | 11.35 | 48.71 | 85
2437 | HOOGHLY | Electrical | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se , SM/16449 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MORHAL PIPED W/S SCHEME, T.W. No. IV, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 457/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 6.94 | 71.57 | 65
2438 | HOOGHLY | Hooghly Division | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se , SM/16449 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system, For Development of BORHAL (ZONE-I)W/S Scheme under Serampore Sub - Division P.H.E. Dte. | 1440/HUG | 18/05/2023 | 45 | CITYCON UNEMPLOYED ENGINEERS CO-OP SOCIETY LTD | 31.23 | 17.63 | 100 | 25
2439 | HOOGHLY | Electrical | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se , SM/16449 | Augmentation | Quotation money deposition for new service connection at Borhal w/s scheme, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004065635 Reference ID- 503592946 SM Code- 16449 | 146 | 22/05/2024 | 0 | WBSEDCL | 4.57 | 0 | 0 | 0
2440 | HOOGHLY | Electrical | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se , SM/16449 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of BORHAL Piped Water Supply Scheme Block- Jangipara District- Hooghly under JJM Program under Electrical Division PHE Dte. | 327/ED | 21/02/2024 | 842 | DEY ENTERPRISE | 20.85 | 0 | 0 | 45
2441 | HOOGHLY | Hooghly Division | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se , SM/16449 | Augmentation | Estimate of development at 3rd T/W site under BORHAL (Zone-II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 60/SER | 20/01/2025 | 7 | SURAJIT SINGHA RAY | 3.5 | 0 | 0 | 0
2442 | HOOGHLY | Hooghly Division | Development of Borhal (Zone-I) Piped Water Supply Scheme by Installing Two (2) Nos. Tube Well including Connection with Distribution, Switch Room & other allied work to meet up the additional water demand induced after execution of FHTC under Serampore Se , SM/16449 | Augmentation | Estimate of Development of 4th T/W Site under BORHAL (Zone-II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 61/SER | 20/01/2025 | 7 | SURAJIT SINGHA RAY | 2.75 | 0 | 0 | 0
2443 | HOOGHLY | Hooghly Division | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. , SM/15890 | New | Material Requisition To Resource Division | 1384/20/Hug | 15/05/2023 | 0 | Resource Division | 19.32 | 0 | 0 | 0
2444 | HOOGHLY | Hooghly Division | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. , SM/15890 | New | Material Requisition To Resource Division | 1236/2/Hug | 28/04/2023 | 0 | Resource Division | 56.85 | 0 | 0 | 0
2445 | HOOGHLY | Hooghly Division | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. , SM/15890 | New | Material Requisition To Resource Division | 3060/11/Hug | 11/10/2023 | 0 | Resource Division | 17.72 | 0 | 0 | 0
2446 | HOOGHLY | Hooghly Division | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. , SM/15890 | New | Material Requisition To Resource Division | 3005/4/Hug | 05/10/2023 | 0 | Resource Division | 4.3 | 0 | 0 | 0
2447 | HOOGHLY | Electrical | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. , SM/15890 | New | Quotation Bill for New Service Connection at Gopalpur W/S. Sch. PH-I, Z-I | 510 | 08/12/2023 | 0 | WBSEDCL | 4.72 | 0 | 0 | 0
2448 | HOOGHLY | Electrical | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. , SM/15890 | New | Quotation Bill for New Service Connection at Gopalpur Piped W/S. Sch. Z-II, PH-I | 577 | 27/12/2023 | 0 | WBSEDCL | 7.27 | 0 | 0 | 0
2449 | HOOGHLY | Electrical | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. , SM/15890 | New | Quotation Bill for New Service Connection at Gopalpur W/S. Sch. PH-II, Z-I | 509 | 08/12/2023 | 0 | WBSEDCL | 10.63 | 0 | 0 | 0
2450 | HOOGHLY | Electrical | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. , SM/15890 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gopalpur water supply scheme, Zone-I, T.W. No. III & IV, Block: jangipara, District- Hooghly under Electrical Division, PHE Dte. | 3453/ED | 11/08/2023 | 90 | DAS ENTERPRISE | 21.49 | 18.65 | 86.81 | 50
2451 | HOOGHLY | Electrical | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. , SM/15890 | New | upply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gopalpur water supply scheme, Zone-I, T.W. No. I & II Block: jangipara, District- Hooghly under Electrical Division, PHE Dte. | 1626/ED | 11/04/2023 | 810 | UNITED ENTERPRISE | 21.83 | 0 | 0 | 80
2452 | HOOGHLY | Hooghly Division | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. , SM/15890 | New | GOPALPUR ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr.Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block under Serampore Sub-Division of Hooghly Division, PHE Dte. [NEW SCHEME] | 2496/HUG | 17/08/2023 | 807 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 416.93 | 196.95 | 47.24 | 85
2453 | HOOGHLY | Hooghly Division | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. , SM/15890 | New | GOPALPUR ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block of Serampore Sub-Division under Hooghly Division PHE Dte. [NEW SCHEME] | 2497/HUG | 17/08/2023 | 776 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 498.12 | 320.97 | 64.44 | 80
2454 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. , SM/10341 | Augmentation | Preparation of DPR for Augmentation of MALAYPUR Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh]. | 363/Arg | 19/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.29 | 4.28 | 99.83 | 0
2455 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. , SM/10341 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x 180 Mtrs. Depth) by utilising departmental machineries for Malaypur W/S Scheme Arambagh Block under Hooghly District, Central Drilling Division, PHE Dte. | 2002/CDD | 09/02/2023 | 30 | M/S SAIKAT ENTERPRISE | 12.54 | 10.63 | 100 | 100
2456 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. , SM/10341 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x 150Mtrs. Depth) by utilising departmental machineries for Malaypur W/S Scheme (T/W I & II). Arambag Block under Hooghly District, Central Drilling Division, PHE Dte. | 17/CDD | 04/04/2023 | 30 | ASHUTOSH DAS & CO | 22.26 | 19.63 | 100 | 50
2457 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. , SM/10341 | Augmentation | Material Requisition To Resource Division | 1124/3/HUG | 06/06/2022 | 0 | Resource Division | 9.24 | 0 | 0 | 0
2458 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. , SM/10341 | Augmentation | Material Requisition To Resource Division | 1773/1/Hug | 29/08/2022 | 0 | Resource Division | 0.69 | 0 | 0 | 0
2459 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. , SM/10341 | Augmentation | Material Requisition To Resource Division | 1106/HUG | 17/04/2023 | 0 | Resource Division | 22.16 | 0 | 0 | 0
2460 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. , SM/10341 | Augmentation | Material Requisition To Resource Division | 1385/19/Hug | 15/05/2023 | 0 | Resource Division | 17.82 | 0 | 0 | 0
2461 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. , SM/10341 | Augmentation | Material Requisition To Resource Division | 1234/4/Hug | 28/04/2023 | 0 | Resource Division | 58.72 | 0 | 0 | 0
2462 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. , SM/10341 | Augmentation | PAYMENT TO ELECTRICAL DIVISION, PHE DTE.FOR THE PAYMENT TO WBSEDCL | BP-2023-24-390 | 19/09/2023 | 0 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 3.9 | 0 | 0 | 0
2463 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. , SM/10341 | Augmentation | PAYMENT TO EXECUTIVE ENGINEER,ELECTRICAL DIVISION, PHE DTE. FOR WBSEDCL AT MALAYPUR WATER SUPPLY SCHEME. | BP-2023-24-438 | 06/10/2023 | 0 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 4.78 | 0 | 0 | 0
2464 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. , SM/10341 | Augmentation | Continuation for hiring of diesel driven Motor Cab (BS-III & Above) having contract carriage permit along with driver for the office of the Executive Engineer, Central Drilling Division, P.H.E. Dte. | 120/S&WSD | 31/10/2023 | 61 | ASHUTOSH DAS & CO | 0.29 | 0.54 | 186.33 | 15
2465 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. , SM/10341 | Augmentation | Sinking of 3 nos. tube-well (300 X 200 MM) by D.R. Rig method at MAYAPUR, MALAYPUR (2 NOS.) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 987/HUG | 16/03/2024 | 30 | BIBHUTI SHAW | 46.75 | 0 | 0 | 0
2466 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. , SM/10341 | Augmentation | Construction of1 no.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site For AUGMENTATION of MALAYPPURW/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3785/HUG | 25/11/2024 | 60 | SRI KRISHNA ENTERPRISE | 10.78 | 0 | 0 | 0
2467 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. , SM/10341 | Augmentation | Hiring of diesel driven motor cab (BS-III & Above) (Non AC) having contract carriage permit along with driver for the Calcutta Mechanical Sub Division-I, P.H.Engineering Dte. under CMSD-II(D), CDD, P.H.E. Dte. | 217/CMSD-II(D) | 26/09/2023 | 92 | SUJATA BHOWMICK | 0.44 | 1.12 | 100 | 33
2468 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. , SM/10341 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 150 Mtrs. Depth) by utilising Departmental Machineries for Malaypur W/S Scheme (TW-I), under Hooghly District, Central Drilling Division, P.H.E. Dte. | 1434/CDD | 29/09/2023 | 30 | ASHUTOSH DAS & CO | 10.74 | 9.06 | 100 | 100
2469 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. , SM/10341 | Augmentation | MALAYPUR Piped Water Supply Scheme with LDS, FHTC, & Construction of 750 cum capacity OHR with 20 m. staging height including Soil Investigation work at ARAMBAG Block under ARAMBAG Sub-Division under Hooghly Division PHE Dte. | 2179/HUG | 29/09/2022 | 1082 | M/S PRADYUT KUMAR HAZRA | 663.67 | 542.86 | 81.8 | 90
2470 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. , SM/10341 | Augmentation | Hiring of Diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Superintending Engineer, M/E, PMU WBDWSIP P.H.E. Dte. under CMSD-I(D), CDD, P.H.E. Dte. | 379/CMSD-I | 24/12/2024 | 33 | SIDDHARTHA CHATTERJEE | 0.16 | 0 | 0 | 0
2471 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR MALAYPUR. , SM/10341 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Malaypur water supply scheme TW No I and II Block Arambag, District Hooghly under ED PHED. | 938/ED | 22/02/2023 | 875 | MAHADEV ENTERPRISE | 21.42 | 21.12 | 98.72 | 40
2472 | HOOGHLY | Hooghly Division | Augmentation of Kulteghori Piped Water Supply Scheme , SM/16564 | Augmentation | Material Requisition To Resource Division | 1383/39/Hug | 15/05/2023 | 0 | Resource Division | 0.33 | 0 | 0 | 0
2473 | HOOGHLY | Electrical | Augmentation of Kulteghori Piped Water Supply Scheme , SM/16564 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kulteghori (Aug.) water supply scheme, T.W. No. I, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | 1933/ED | 15/05/2023 | 90 | DAS ENTERPRISE | 11.48 | 0 | 0 | 30
2474 | HOOGHLY | Hooghly Division | Augmentation of Kulteghori Piped Water Supply Scheme , SM/16564 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Olipur,Kulteghori,Paschim Jaykrishnapur & Barakamalpur W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 1839/HUG | 26/06/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 80.45 | 0 | 0 | 100
2475 | HOOGHLY | Electrical | Augmentation of Kulteghori Piped Water Supply Scheme , SM/16564 | Augmentation | Quotation money deposition for new service connection at Kulteghori w/s scheme, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004314314 Reference ID- 503702908 SM Code- 16564 | 349 | 31/07/2024 | 0 | WBSEDCL | 24.36 | 0 | 0 | 0
2476 | HOOGHLY | Hooghly Division | Augmentation of Kulteghori Piped Water Supply Scheme , SM/16564 | Augmentation | Sinking of tube-well by D.R. Rig method ,Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement ,Construction of Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution of KULTEGHORI Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.HE Dte | 2516/HUG | 18/08/2023 | 941 | SHREE JAGANNATH ENTERPRISE | 32.57 | 1.95 | 6 | 40
2477 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15799 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Badinan water supply scheme, T.W. No. II, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | 3436/ED | 11/08/2023 | 90 | BIDYUT KUMAR MUKHERJEE | 11.41 | 0 | 0 | 0
2478 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15799 | Augmentation | Additional Quotation for new service connection at Badinan w/s sch. , P.H. No. III, Dist -Hooghly | 37 | 15/05/2023 | 0 | WBSEDCL | 0.48 | 0 | 0 | 0
2479 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15799 | Augmentation | Quatation bill for New service connection at Aug. of Badinan w/s scheme, P.H No.-3 | 176 | 02/03/2023 | 0 | WBSEDCL | 4.74 | 0 | 0 | 0
2480 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15799 | Augmentation | Preparation of DPR for Augmentation Hanral Z-I Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-POLBA DADPUR]. | 690/CH | 09/08/2024 | 7 | APEX ENGINEERING | 3.88 | 0 | 0 | 0
2481 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15799 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Badinan water supply scheme, T.W. No. III, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | 3480/ED | 30/12/2022 | 90 | INDIA ENTERPRISE | 10.64 | 10.3 | 97.34 | 90
2482 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15799 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Badinan water supply scheme, T.W. No. I, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | 1628/ED | 11/04/2023 | 90 | BIDYUT KUMAR MUKHERJEE | 11.41 | 11.4 | 100 | 99
2483 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15799 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos.T.W with distribution system, FHTC of BADINAN W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | 1337/HUG | 11/05/2023 | 45 | BAKSHI ENTERPRISE | 40.42 | 35.48 | 100 | 45
2484 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15799 | Augmentation | Sinking of 1 (One) No Big dia tube well (300 mm x200mm) with supply of PVC Pipe and strainer and having depth upto 180 Mtr at BADINAN W/S Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | 3318/HUG | 10/11/2023 | 30 | AUXILIARY TUBEWELL DRILLERS | 14.88 | 13.06 | 100 | 100
2485 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15799 | Augmentation | Providing FHTC at the left out portions of Priyanagar for proiving FHTC in Badinan Piped Water Supply Scheme under Polba Dapur Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 539/CH | 14/06/2024 | 7 | BIMAL KUMAR HALDER | 4.84 | 4.84 | 100 | 85
2486 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15799 | Augmentation | Providing FHTC at the left out portions of Payan majipara for proiving FHTC in Badinan Piped Water Supply Scheme under Polba Dapur Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 538/CH | 14/06/2024 | 7 | BIMAL KUMAR HALDER | 4.84 | 4.84 | 100 | 100
2487 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15799 | Augmentation | Providing FHTC at the left out portions at Itkhola for proiving FHTC in Badinan Piped Water Supply Scheme under Polba Dapur Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 537/CH | 14/06/2024 | 7 | BIMAL KUMAR HALDER | 2.81 | 2.81 | 100 | 100
2488 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15799 | Augmentation | Repairing Of Switch Room, Boundary wall for Badinan W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | 2408/HUG | 26/06/2024 | 30 | GHOSH CONSTRUCTION | 7.86 | 7.83 | 100 | 100
2489 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15799 | Augmentation | Quotation Bill for New Service Connection at Badinan W/S. Sch. TW-I | 632 | 08/01/2024 | 0 | WBSEDCL | 5.16 | 0 | 0 | 0
2490 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15799 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | 882/HUG | 27/03/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 0 | 0 | 65
2491 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15799 | Augmentation | Laying C.I/D.I pipes & specials for rising main pipe line in between T.W No.- 4 of Badinan W/S under Chinsurah Sub - Division P.H.E. Dte. | 65/CH | 10/01/2025 | 5 | BIMAL KUMAR HALDER | 0.97 | 0 | 0 | 0
2492 | HOOGHLY | Hooghly Division | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME , SM/18097 | New | KHORDAAPURBAPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. Block Singur, District:- Hooghly [NEW SCHEME] | 1686/HUG | 08/06/2023 | 90 | SATYA NARAYAN BISWAS | 146.57 | 110.2 | 75.19 | 60
2493 | HOOGHLY | Hooghly Division | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME , SM/18097 | New | Sinking of Additional tubewell with Construction of switch-room & boundary wall, Laying Rising Main at Proposed TW site at kharda-apurbapur Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte.Block Singur, District:- Hooghly | 2506/HUG | 03/07/2024 | 45 | KALPATARU ENTERPRISE | 37.6 | 3.71 | 9.86 | 50
2494 | HOOGHLY | Hooghly Division | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME , SM/18097 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Khordapurbapur Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-B). | 421/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.84 | 0.84 | 100 | 100
2495 | HOOGHLY | Hooghly Division | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME , SM/18097 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Khordapurbapur Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-A). | 420/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.73 | 0.73 | 100 | 100
2496 | HOOGHLY | Hooghly Division | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME , SM/18097 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Khordapurbapur Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-C). | 422/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.78 | 0.78 | 100 | 100
2497 | HOOGHLY | Hooghly Division | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME , SM/18097 | New | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Khordaapurbapur 1st T/W site & Kamarkundu (Zone-1) 1st T/W site under Chandannagar Sub-Division PHE Dte. | 928/Chan | 05/11/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.97 | 0.38 | 29.1 | 100
2498 | HOOGHLY | Electrical | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME , SM/18097 | New | Quotation for new service connection at Khorda Apurbapur [SM/18097] W/S Sch., T/W No. - I, Block - Singur, under Singur CCC, WBSEDCL, Ref Id. - 503675586, dt. - 26-06-2024, Application No. - 5004257575. | 261 | 03/07/2024 | 0 | WBSEDCL | 14.47 | 0 | 0 | 0
2499 | HOOGHLY | Electrical | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME , SM/18097 | New | Quotation for new service connection at Khorda Apurbapur [SM/18097] W/S Sch., T/W No. - II, Block - Singur, under Singur CCC, WBSEDCL, Ref Id. - 503678884, dt. - 26-06-2024, Application No. - 5004264232. | 260 | 03/07/2024 | 0 | WBSEDCL | 13.18 | 0 | 0 | 0
2500 | HOOGHLY | Electrical | KHORDAAPURBAPUR PIPED WATER SUPPLY SCHEME , SM/18097 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Khordaa purbapur water supply scheme, T.W. No. I, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | 1928/ED | 15/05/2023 | 655 | TAMAL ENTERPRISE | 11.65 | 9.05 | 77.7 | 50
2501 | HOOGHLY | Hooghly Division | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18104 | New | Material Requisition To Resource Division | 1384/12/Hug | 15/05/2023 | 0 | Resource Division | 5.49 | 0 | 0 | 0
2502 | HOOGHLY | Hooghly Division | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18104 | New | Material Requisition To Resource Division | 3060/9/Hug | 11/10/2023 | 0 | Resource Division | 5.49 | 0 | 0 | 0
2503 | HOOGHLY | Hooghly Division | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18104 | New | Material Requisition To Resource Division | 1236/3/Hug | 28/04/2023 | 0 | Resource Division | 5.49 | 0 | 0 | 0
2504 | HOOGHLY | Electrical | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18104 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hijali water supply scheme, T.W. No. I & II, Block: Jangipara, District - Hooghly under Electrical Division, PHE Dte. | 1925/ED | 15/05/2023 | 90 | GLACIER ENGINEERING CO. | 23.4 | 21 | 89.72 | 25
2505 | HOOGHLY | Hooghly Division | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18104 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Bilaspur-I PWSS 2. Bilaspur-II PWSS 3. Hijli PWSS 4. Jaganathpur PWSS | 115/SER | 23/02/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.64 | 0.64 | 100 | 80
2506 | HOOGHLY | Electrical | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18104 | New | Quotation Bill for New Service Connection at Hijali W/S. Sch. | 595 | 29/12/2023 | 0 | WBSEDCL | 6.03 | 0 | 0 | 0
2507 | HOOGHLY | Electrical | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18104 | New | Quotation Bill for New Service Connection at Hijali W/S. Sch. PH-I | 633 | 08/01/2024 | 0 | WBSEDCL | 3.59 | 0 | 0 | 0
2508 | HOOGHLY | Electrical | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18104 | New | Shifting of 11KV HTOH line at Hijali pump house No.-1 Application ID: 100000103017 Ref ID: 860295257 | 899 | 19/03/2024 | 0 | WBSEDCL | 6.79 | 0 | 0 | 0
2509 | HOOGHLY | Hooghly Division | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18104 | New | HIJALI Piped Water Supply Scheme with Sinking of tube-well, LDS,Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block, District:- Hooghly [NEW SCHEME] | 2239/HUG | 01/08/2023 | 571 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 350.15 | 145.76 | 41.63 | 10
2510 | HOOGHLY | Hooghly Division | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18104 | New | Construction of Shed on open terrace of Existing Laboratory building at Headwork site of Jangipara Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. (Block- Jangipara). | 267/SER | 03/04/2025 | 10 | MAA TARA CONSTRUCTION | 4.93 | 0 | 0 | 0
2511 | HOOGHLY | Hooghly Division | Hijali Piped Water Supply Scheme, Block-Jangipara, District-Hooghly , SM/18104 | New | Sinking of tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room , boundary wall & other works at Chandrahati mouza of HIJALI Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. | 1055/HUG | 24/04/2025 | 60 | R.K. TRADERS | 27.87 | 0 | 0 | 0
2512 | HOOGHLY | Hooghly Division | Retrofitting work for Providing Functional Household Tap Connection (FHTC) within the uncovered portion of Dantra Water Supply Scheme Under Polba Dadpur Block , SM/18107 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DANTRA PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 1776/HUG | 15/06/2023 | 45 | VAIDIK CONSTRUCTION | 11.42 | 0 | 0 | 70
2513 | HOOGHLY | Electrical | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18308 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Udaypur water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | 3162/ED | 27/07/2023 | 90 | DEBJYOTI BASU | 21.36 | 0 | 0 | 0
2514 | HOOGHLY | Hooghly Division | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18308 | New | Material Requisition To Resource Division | 3057/56/Hug | 11/10/2023 | 0 | Resource Division | 19.7 | 0 | 0 | 0
2515 | HOOGHLY | Hooghly Division | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18308 | New | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at MAHISHGOT ZONE I (2Nos.), UDAYPUR (2Nos.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3437/HUG | 03/10/2024 | 90 | SAHA CONSTRUCTION AND CO | 47.26 | 0 | 0 | 0
2516 | HOOGHLY | Electrical | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18308 | New | Quotation money deposition for new service connection at udaypur w/s scheme, T.W. No.-II, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004036968/Quot/03 Reference ID- 503576706 SM Code- 18308 | 819 | 01/03/2024 | 0 | WBSEDCL | 11.54 | 0 | 0 | 0
2517 | HOOGHLY | Electrical | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18308 | New | Quotation money deposition for new service connection at udaypur w/s scheme, T.W. No.-I, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004037021/Quot/03 Reference ID- 503576711 SM Code- 18308 | 818 | 03/03/2024 | 0 | WBSEDCL | 3.92 | 0 | 0 | 0
2518 | HOOGHLY | Hooghly Division | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18308 | New | MAHISGOT (ZONE-I), MAHISGOT (ZONE-II), POL, RADHABALLAVPUR (ZONE-I), UDAYPUR, UDNA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte | 3139/HUG | 16/10/2023 | 808 | MACKINTOSH BURN LIMITED | 3480.01 | 258.22 | 33.18 | 45
2519 | HOOGHLY | Hooghly Division | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18308 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0 | 0
2520 | HOOGHLY | Hooghly Division | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly , SM/18309 | New | Material Requisition To Resource Division | 3057/8/Hug | 11/10/2023 | 0 | Resource Division | 11.45 | 0 | 0 | 0
2521 | HOOGHLY | Electrical | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly , SM/18309 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for UDNA water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | 3159/ED | 27/07/2023 | 90 | MAA KALI ENTERPRISE | 20.23 | 14.81 | 73.2 | 100
2522 | HOOGHLY | Electrical | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly , SM/18309 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Udna water supply scheme, T.W. No. III & IV, Block: Khanakul-I, District: Hooghly under Electrical Division, PHE Dte. | 332/ED | 21/02/2024 | 90 | MAA KALI ENTERPRISE | 21.44 | 15.9 | 74.16 | 20
2523 | HOOGHLY | Hooghly Division | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly , SM/18309 | New | Sinking of 3 nos. tube-well (300 X 200 mm) by D.R. Rig method at HIRAPUR Z-II and UDNA Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 722/HUG | 05/03/2024 | 60 | ANIRUDDHA FARUQUE | 48.17 | 26.24 | 100 | 100
2524 | HOOGHLY | Electrical | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly , SM/18309 | New | Quotation of New Service Connection for UDNA w/s Scheme, PH No-I Block-Khanakul-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18309) Application No-5004114171 Reference Id-503617472 | 83 | 22/04/2024 | 0 | WBSEDCL | 3.38 | 0 | 0 | 0
2525 | HOOGHLY | Hooghly Division | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly , SM/18309 | New | MAHISGOT (ZONE-I), MAHISGOT (ZONE-II), POL, RADHABALLAVPUR (ZONE-I), UDAYPUR, UDNA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte | 3139/HUG | 16/10/2023 | 808 | MACKINTOSH BURN LIMITED | 3480.01 | 202.35 | 47.2 | 45
2526 | HOOGHLY | Hooghly Division | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly , SM/18309 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0 | 0
2527 | HOOGHLY | Hooghly Division | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY , SM/17176 | New | Material Requisition To Resource Division | 1384/15/Hug | 15/05/2023 | 0 | Resource Division | 4.88 | 0 | 0 | 0
2528 | HOOGHLY | Hooghly Division | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY , SM/17176 | New | Material Requisition To Resource Division | 3060/7/Hug | 11/10/2023 | 0 | Resource Division | 4.88 | 0 | 0 | 0
2529 | HOOGHLY | Hooghly Division | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY , SM/17176 | New | Material Requisition To Resource Division | 3005/13/Hug | 05/10/2023 | 0 | Resource Division | 4.88 | 0 | 0 | 0
2530 | HOOGHLY | Hooghly Division | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY , SM/17176 | New | CONSTRUCTION OF 1NO. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT JAGANNATHBATI HW SITE UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E, DTE. | 432/SER | 31/07/2024 | 15 | SRI KRISHNA ENTERPRISE | 0.36 | 0.36 | 100 | 95
2531 | HOOGHLY | Electrical | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY , SM/17176 | New | Quotation money deposition for new service connection at Jagannathbati w/s scheme, P.H. No.-I, Dist.-Hooghly under PHE Dte. Application No- 5004146914 Reference ID- 503632742 SM Code- 17176 | 128 | 17/05/2024 | 0 | WBSEDCL | 3.91 | 0 | 0 | 0
2532 | HOOGHLY | Electrical | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY , SM/17176 | New | Quotation money deposition for new service connection at Jagannathbati w/s scheme, P.H. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004146792 Reference ID- 503632743 SM Code- 17176 | 133 | 17/05/2024 | 0 | WBSEDCL | 9.39 | 0 | 0 | 0
2533 | HOOGHLY | Hooghly Division | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY , SM/17176 | New | JAGANNATHBATI Piped Water Supply Scheme with Sinking of tubewell, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHANDITALA-II Block, District:- Hooghly [NEW SCHEME] | 1042/Hug | 10/04/2023 | 997 | M/S SHIVAM UDYOG | 212.99 | 97.79 | 45.91 | 30
2534 | HOOGHLY | Electrical | JAGANNATHBATI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II, DISTRICT: HOOGHLY , SM/17176 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jagannathbati water supply scheme, T.W. No.- I & II, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | 1795/ED | 24/04/2023 | 799 | AHALYA ENGINEERING WORKS | 20.26 | 14.32 | 70.67 | 60
2535 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAHADURPUR WATER SUPPLY SCHEME. , SM/07958 | Retrofitting | Providing 1599 nos F.H.T.C. in Bahadurpur, Belmuri,Manikpur, Radha Ballabhpur & Uttar Mogalpur Village of Bahadurpur and its Adjoining Mouzas Water Supply Scheme UnderChinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Dhaniakhali] | 933/Hug | 06/05/2021 | 40 | ORIENT CONSTRUCTION | 92.76 | 69.85 | 97.42 | 100
2536 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAHADURPUR WATER SUPPLY SCHEME. , SM/07958 | Retrofitting | Material Requisition To Resource Division | 2097/20/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0 | 0
2537 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAHADURPUR WATER SUPPLY SCHEME. , SM/07958 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of different PWSS under DHANIAKHALI Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | 2430/HUG | 11/08/2023 | 30 | MUKHERJEE AND CO | 39.91 | 39.29 | 100 | 98
2538 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEBANANDAPUR WATER SUPPLY SCHEME. , SM/09072 | Retrofitting | Providing 300 nos Functional Household Tap Connection (FHTC) within the command area of Debanandapur Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 2201/Hug | 14/12/2021 | 30 | SARKAR CONSTRUCTION | 18.07 | 0 | 0 | 100
2539 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEBANANDAPUR WATER SUPPLY SCHEME. , SM/09072 | Retrofitting | Providing 90 nos Functional Household Tap Connection (FHTC) within the command area of Debanandapur Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 12/Hug | 04/01/2022 | 30 | BIMAL KUMAR HALDER | 16.49 | 0 | 0 | 100
2540 | HOOGHLY | Hooghly Division | GAURIBATI PIPED WATER SUPPLY SCHEME , SM/11289 | New | Route Survey, Design Drawing & DPR Preparation of Gouribati PWSS under Chandannagar Sub - Division, PHE Dte. | 509/Chan | 29/09/2022 | 15 | ENVIROTECH SOLUTIONS | 2.93 | 2.93 | 100 | 0
2541 | HOOGHLY | Hooghly Division | GAURIBATI PIPED WATER SUPPLY SCHEME , SM/11289 | New | Sinking of 2 nos 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tube Well Site of GAURIBATI W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 157/HUG | 16/01/2023 | 45 | SAMIRON GHOSH | 28.9 | 25.39 | 100 | 100
2542 | HOOGHLY | Hooghly Division | GAURIBATI PIPED WATER SUPPLY SCHEME , SM/11289 | New | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of GAURIBATI Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | 447/HUG | 16/02/2023 | 60 | AMBIAN INFRASTRUTTURE | 12.23 | 12.23 | 100 | 100
2543 | HOOGHLY | Electrical | GAURIBATI PIPED WATER SUPPLY SCHEME , SM/11289 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gauribati water supply scheme, T.W. No. I & II, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | 3463/ED | 30/12/2022 | 90 | POLYCON ENGINEERS | 22.28 | 22.27 | 100 | 100
2544 | HOOGHLY | Hooghly Division | GAURIBATI PIPED WATER SUPPLY SCHEME , SM/11289 | New | Material Requisition To Resource Division | 902/8/Hug | 27/03/2023 | 0 | Resource Division | 8.54 | 0 | 0 | 0
2545 | HOOGHLY | Hooghly Division | GAURIBATI PIPED WATER SUPPLY SCHEME , SM/11289 | New | Material Requisition To Resource Division | 1383/18/Hug | 15/05/2023 | 0 | Resource Division | 8.44 | 0 | 0 | 0
2546 | HOOGHLY | Hooghly Division | GAURIBATI PIPED WATER SUPPLY SCHEME , SM/11289 | New | Material Requisition To Resource Division | 3058/37/Hug | 11/10/2023 | 0 | Resource Division | 8.29 | 0 | 0 | 0
2547 | HOOGHLY | Hooghly Division | GAURIBATI PIPED WATER SUPPLY SCHEME , SM/11289 | New | Material Requisition To Resource Division | 109/ 21/Hug | 10/01/2023 | 0 | Resource Division | 22.52 | 0 | 0 | 0
2548 | HOOGHLY | Electrical | GAURIBATI PIPED WATER SUPPLY SCHEME , SM/11289 | New | Quation Money for Gauribati w/s scheme P.H.No-II | 104 | 19/07/2023 | 0 | WBSEDCL | 3.78 | 0 | 0 | 0
2549 | HOOGHLY | Electrical | GAURIBATI PIPED WATER SUPPLY SCHEME , SM/11289 | New | Gauribati water supply scheme,PHNo-I | 140 | 25/07/2023 | 0 | WBSEDCL | 3.83 | 0 | 0 | 0
2550 | HOOGHLY | Electrical | GAURIBATI PIPED WATER SUPPLY SCHEME , SM/11289 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gouribati water supply scheme, T.W. No. III, Block: Tarakeswar, District: Hooghly under Electrical Division, PHE Dte. | 341/ED | 21/02/2024 | 90 | J.K. ENGINEERING CO. | 10.74 | 7.71 | 71.82 | 40
2551 | HOOGHLY | Electrical | GAURIBATI PIPED WATER SUPPLY SCHEME , SM/11289 | New | Quotation Bill for New Service Connection at Gouribati W/S. Sch. TW-III | 733 | 05/02/2024 | 0 | WBSEDCL | 6.9 | 0 | 0 | 0
2552 | HOOGHLY | Hooghly Division | GAURIBATI PIPED WATER SUPPLY SCHEME , SM/11289 | New | "GAURIBATI" Piped Water Supply Scheme With LDS, FHTC & Construction of 250 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at TARAKESWAR Block under Chandannagar Sub - Division Under Hooghly Division PHE Dte. | 2558/HUG | 25/11/2022 | 1102 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 305.74 | 230.46 | 87.1 | 30
2553 | HOOGHLY | Electrical | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. , SM/18347 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SHYAMPUR PIPED W/S SCHEME, T.W. No. V, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1187/ED | 14/06/2024 | 90 | COOLING CARE CENTER | 10.74 | 0 | 0 | 0
2554 | HOOGHLY | Hooghly Division | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. , SM/18347 | Augmentation | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for Augmentation of SHYAMPUR Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. | 3719/HUG | 19/11/2024 | 60 | SIBSANKAR CHOWDHURY | 51.74 | 0 | 0 | 0
2555 | HOOGHLY | Electrical | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. , SM/18347 | Augmentation | Electric quot. of WBSEDCL for New Connection of Shyampur T/W-IV W/S scheme under ED PHE Dte (SM/18347) | 338 | 30/07/2024 | 0 | WBSEDCL | 4.57 | 0 | 0 | 0
2556 | HOOGHLY | Electrical | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. , SM/18347 | Augmentation | Electric quot. of WBSEDCL for New service Connection of Shyampur T/W-III W/S scheme under Electrical Division PHE Dte. (SM/18347) | 372 | 12/08/2024 | 0 | WBSEDCL | 26.41 | 0 | 0 | 0
2557 | HOOGHLY | Hooghly Division | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. , SM/18347 | Augmentation | Augmentation of SHYAMPUR Piped Water Supply Scheme with Sinking of 3 Nos. tube-well within ZONE-I, II & III, Repairing of Existing O.H.R, Switch Rooms, Boundary walls at different TW site, LDS, FHTC in ZONE-I, LDS, FHTC, construction of switch-rooms & boundary walls in ZONE-II, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & LDS, RISING MAIN, FHTC, construction of switch-rooms & boundary walls in ZONE-III under PURSURAH Block, District:- Hooghly | 2292/HUG | 03/08/2023 | 823 | SIBSANKAR CHOWDHURY | 745.98 | 247.41 | 33.17 | 45
2558 | HOOGHLY | Electrical | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. , SM/18347 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Shyampur water supply scheme, T.W. No.- I, II, III & IV, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | 3174/ED | 28/07/2023 | 644 | H.K.DAS & CO. | 43.01 | 2.77 | 6.44 | 25
2559 | HOOGHLY | Hooghly Division | Source Augmentation of Panchghora W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] , SM/18791 | Augmentation | Material Requisition To Resource Division | 1107/5/HUG | 17/04/2023 | 0 | Resource Division | 3.08 | 0 | 0 | 0
2560 | HOOGHLY | Electrical | Source Augmentation of Panchghora W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] , SM/18791 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for PANCHGHORA PIPED W/S SCHEME, T.W. No. IV, Block: Chanditala-II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 453/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 6.94 | 71.57 | 65
2561 | HOOGHLY | Electrical | Source Augmentation of Panchghora W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] , SM/18791 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Panchghora water supply scheme, T.W. No. I, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | 3789/ED | 26/09/2023 | 90 | SRI KRISHNA NIRMAN | 10.74 | 10.67 | 100 | 80
2562 | HOOGHLY | Electrical | Source Augmentation of Panchghora W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] , SM/18791 | Augmentation | Quotation bill for new service connection charges at Panchghara PWSS P.H. No.-IV, Hooghly. Application No. 5004090927 Ref ID: 503606723 | 148 | 22/05/2024 | 0 | WBSEDCL | 3.48 | 0 | 0 | 0
2563 | HOOGHLY | Hooghly Division | Mayapur Piped Water Supply Scheme. , SM/18833 | New | Material Requisition To Resource Division | 3057/26/Hug | 11/10/2023 | 0 | Resource Division | 14.6 | 0 | 0 | 0
2564 | HOOGHLY | Hooghly Division | Mayapur Piped Water Supply Scheme. , SM/18833 | New | Construction of 400 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & Providing FHTC IN MAYAPUR Water Supply Scheme under ARAMBAGH SUB DIVISION Block-Arambagh, District:- Hooghly [NEW SCHEME] | 3187/HUG | 30/10/2023 | 429 | DHIRENDRA ENGINEERING & CONSTRUCTION | 212.41 | 0 | 0 | 0
2565 | HOOGHLY | Hooghly Division | Mayapur Piped Water Supply Scheme. , SM/18833 | New | Laying Distribution System of proposed pipe line& construction of switch-rooms at different TW site of MAYAPUR Piped Water Supply Scheme under ARAMBAGH SUB DIVISION Block-Arambagh, District:- Hooghly [NEW SCHEME] | 3302/Hug | 10/11/2023 | 120 | EQUIPMENTS AND SPARES AGENCIES | 197.56 | 95.62 | 48.4 | 30
2566 | HOOGHLY | Hooghly Division | Mayapur Piped Water Supply Scheme. , SM/18833 | New | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of KRISHNANAGAR ZONE-II,MAYAPUR,TIROL ZONE-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3783/HUG | 25/11/2024 | 60 | DAS CONSTRUCTION | 55.5 | 0 | 0 | 0
2567 | HOOGHLY | Hooghly Division | Mayapur Piped Water Supply Scheme. , SM/18833 | New | Sinking of 3 nos. tube-well (300 X 200 MM) by D.R. Rig method at MAYAPUR, MALAYPUR (2 NOS.) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 987/HUG | 16/03/2024 | 30 | BIBHUTI SHAW | 46.75 | 0 | 0 | 0
2568 | HOOGHLY | Electrical | Mayapur Piped Water Supply Scheme. , SM/18833 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAYAPUR PIPED W/S SCHEME, T.W. No. II, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1202/ED | 14/06/2024 | 90 | D. K. ELECTRIC | 10.74 | 0 | 0 | 0
2569 | HOOGHLY | Electrical | Mayapur Piped Water Supply Scheme. , SM/18833 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAYAPUR PIPED W/S SCHEME, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1203/ED | 14/06/2024 | 90 | D. K. ELECTRIC | 10.74 | 0 | 0 | 0
2570 | HOOGHLY | Electrical | Mayapur Piped Water Supply Scheme. , SM/18833 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAYAPUR PIPED W/S SCHEME, T.W. No. I, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1201/ED | 14/06/2024 | 90 | WIZARDTECH SOLUTION | 10.75 | 0 | 0 | 0
2571 | HOOGHLY | Electrical | Mayapur Piped Water Supply Scheme. , SM/18833 | New | Quotation of New Service Connection for Mayapur w/s Scheme, PH No-II Block-Arambag,Dist-Hooghly under Electrical Division,PHE Dte. | 131 | 17/05/2024 | 0 | WBSEDCL | 4.32 | 0 | 0 | 0
2572 | HOOGHLY | Hooghly Division | Mayapur Piped Water Supply Scheme. , SM/18833 | New | MAYAPUR Piped Water Supply Scheme with Sinking of tube-well, Rising Main & construction of boundary walls at different TW site under ARAMBAGH SUB DIVISION Block-Arambagh, District:- Hooghly [NEW SCHEME] | 2916/HUG | 22/09/2023 | 542 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 72.39 | 0 | 0 | 35
2573 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF MANDARAN PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18977 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF MANDARAN PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4500/ED | 23/11/2023 | 90 | SANKAR PRASAD DUTTA & CO. | 21.71 | 0 | 0 | 0
2574 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF MANDARAN PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18977 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at NATAGARI (2Nos.), MANDARAN (2Nos.), DEBANANDAPUR (1No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3239/HUG | 06/11/2023 | 60 | RAJ AGRO SERVICE CENTRE | 59.62 | 0 | 0 | 20
2575 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF MANDARAN PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18977 | Augmentation | Providing Functional House Hold Tap Connection (FHTC) under JJM withing left out portion at Hatpukur Bakultala & Gopinathpara of MANDARAN PWSS under Chinsurah Sub Division of Hooghly Division P.H.E Dte. | 545/CH | 14/06/2024 | 7 | M/S SHIVAM UDYOG | 4.33 | 4.09 | 100 | 100
2576 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF MANDARAN PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18977 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at NATAGARI (2Nos.), MANDARAN (2Nos.), DEBANANDAPUR (1No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3383/HUG | 22/11/2023 | 627 | OSMAN SEKH | 87.84 | 0 | 0 | 20
2577 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF MANDARAN PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18977 | Augmentation | Repairing & Renovation of Switch Room Including Boundary Wall At Head Work Site Of Mandaran Water Supply Scheme Under Pandua Block Of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 223/CH | 19/02/2025 | 30 | GHOSH CONSTRUCTION | 4.65 | 0 | 0 | 0
2578 | HOOGHLY | Hooghly Division | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/18668 | New | Material Requisition To Resource Division | 3057/18/Hug | 11/10/2023 | 0 | Resource Division | 19.1 | 0 | 0 | 0
2579 | HOOGHLY | Hooghly Division | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/18668 | New | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of KRISHNANAGAR Zone-II , MAYAPUR , TIROL Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3530/HUG | 22/10/2024 | 45 | PADMA ENGINEERING CO. | 47.5 | 0 | 0 | 0
2580 | HOOGHLY | Electrical | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/18668 | New | Quotation of New Service Connection for Tirol w/s Scheme,Zone-I,PH No-II Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/18668) Application No-5004138271, Reference Id-503628273 | 94 | 06/05/2024 | 0 | WBSEDCL | 3.14 | 0 | 0 | 0
2581 | HOOGHLY | Electrical | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/18668 | New | Quotation of New Service Connection for Tirol w/s Scheme,Z-I,PH No-III Block-Arambag Dist-Hooghly under Electrical Division, PHE Dte.(SM/18668) Application No-5004097240 Reference Id-503608902 | 37 | 09/04/2024 | 0 | WBSEDCL | 3.72 | 0 | 0 | 0
2582 | HOOGHLY | Electrical | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/18668 | New | Quotation of New Service Connection for Tirol w/s Scheme, Zone-I, PH No-4 Block-Arambag, Dist-Hooghly Under Electrical division, PHE Dte.(SM/18668) Application No-5004256486, Reference Id-503674894. | 255 | 03/07/2024 | 0 | WBSEDCL | 5.29 | 0 | 0 | 0
2583 | HOOGHLY | Hooghly Division | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/18668 | New | TIROL ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site, under ARAMBAGH Block, District:- Hooghly [NEW SCHEME] | 2338/HUG | 07/08/2023 | 878 | MINTU CHAKRABORTY | 737.4 | 452.1 | 61.31 | 50
2584 | HOOGHLY | Hooghly Division | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK , SM/18668 | New | Sinking of 3rd and 4th tube-well by D.R. Rig method, Construction of 2 nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of 2 nos. Boundary Wall at TIROL (ZONE-I) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | 539/HUG | 20/02/2024 | 404 | MINTU CHAKRABORTY | 59.45 | 19.73 | 33.18 | 50
2585 | HOOGHLY | Electrical | Baligari Piped Water Supply Scheme. , SM/18671 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baligari water supply scheme, Zone-I, T.W. No. III & IV, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | 3444/ED | 11/08/2023 | 90 | BINAPANI ENTERPRISE | 21.38 | 0 | 0 | 0
2586 | HOOGHLY | Electrical | Baligari Piped Water Supply Scheme. , SM/18671 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baligari water supply scheme, Zone-II, T.W. No. III & IV, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | 3445/ED | 11/08/2023 | 90 | ASHUTOSH DAS & CO. | 20.35 | 0 | 0 | 0
2587 | HOOGHLY | Hooghly Division | Baligari Piped Water Supply Scheme. , SM/18671 | New | Material Requisition To Resource Division | 3058/3/Hug | 11/10/2023 | 0 | Resource Division | 9.82 | 0 | 0 | 0
2588 | HOOGHLY | Electrical | Baligari Piped Water Supply Scheme. , SM/18671 | New | Quotation Bill for New Service Connection at Baligari W/S. Sch. PH-I, Z-II | 494 | 07/12/2023 | 0 | WBSEDCL | 12.83 | 0 | 0 | 0
2589 | HOOGHLY | Electrical | Baligari Piped Water Supply Scheme. , SM/18671 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baligari water supply scheme, Zone-II, T.W. No.- I & II, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | 3417/ED | 10/08/2023 | 90 | ASHUTOSH DAS & CO. | 20.35 | 19.8 | 97.31 | 90
2590 | HOOGHLY | Electrical | Baligari Piped Water Supply Scheme. , SM/18671 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baligari water supply scheme, Zone-I, T.W. No.- I & II, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | 3418/ED | 10/08/2023 | 90 | BINAPANI ENTERPRISE | 21.36 | 20.72 | 96.98 | 30
2591 | HOOGHLY | Hooghly Division | Baligari Piped Water Supply Scheme. , SM/18671 | New | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for BALIGARI Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 3474/HUG | 04/10/2024 | 60 | DIPTI TRADERS | 53.05 | 0 | 0 | 0
2592 | HOOGHLY | Hooghly Division | Baligari Piped Water Supply Scheme. , SM/18671 | New | Construction of Boundary Wall at H/W site & Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at Talpur Mouza of Baligari water supply scheme under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. | 730/HUG | 05/03/2024 | 60 | DAS CONSTRUCTION | 47.63 | 44.24 | 100 | 100
2593 | HOOGHLY | Electrical | Baligari Piped Water Supply Scheme. , SM/18671 | New | Quotation Bill for New Service Connection at Baligori W/S. Sch. PH-I, Z-I | 628 | 08/01/2024 | 0 | WBSEDCL | 9.44 | 0 | 0 | 0
2594 | HOOGHLY | Electrical | Baligari Piped Water Supply Scheme. , SM/18671 | New | Quotation bill for new service connection at Baligori water supply scheme, Zone-I, P.H. No.-I, Hooghly Application No.- 100000101765 Referance ID: 860294205 | 860 | 11/03/2024 | 0 | WBSEDCL | 0.47 | 0 | 0 | 0
2595 | HOOGHLY | Electrical | Baligari Piped Water Supply Scheme. , SM/18671 | New | Additional quotation for effecting new service connection of Baligori Zone-II, P.H. No.-I Ref ID: 860293430 | 898 | 19/03/2024 | 0 | WBSEDCL | 0.12 | 0 | 0 | 0
2596 | HOOGHLY | Electrical | Baligari Piped Water Supply Scheme. , SM/18671 | New | Additional Quotation Charge for Effecting New PHE Connection at PHE-2, Baligori, Monoharpur | 674 | 17/01/2024 | 0 | WBSEDCL | 1.12 | 0 | 0 | 0
2597 | HOOGHLY | Electrical | Baligari Piped Water Supply Scheme. , SM/18671 | New | Quotation Bill for New Service Connection at Baligari W/S. Sch. PH-II, Z-I | 627 | 08/01/2024 | 0 | WBSEDCL | 4.34 | 0 | 0 | 0
2598 | HOOGHLY | Electrical | Baligari Piped Water Supply Scheme. , SM/18671 | New | Quotation Bill for New Service Connection at Baligari W/S. Sch. PH-II, Z-II | 626 | 08/01/2024 | 0 | WBSEDCL | 4.59 | 0 | 0 | 0
2599 | HOOGHLY | Hooghly Division | Baligari Piped Water Supply Scheme. , SM/18671 | New | BALIGARI (ZONE-I & ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR at ZONE-I & Construction of 300 cum capacity RCC OHR at ZONE-II with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under TARAKESWAR Block, District:- Hooghly [NEW SCHEME] | 2337/HUG | 07/08/2023 | 872 | DIPTI TRADERS | 963.28 | 648.11 | 67.28 | 5
2600 | HOOGHLY | Hooghly Division | Baligari Piped Water Supply Scheme. , SM/18671 | New | Sinking of1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for NANDANBATI Mouza of Baligari Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 184/HUG | 24/01/2025 | 60 | SPG ENTERPRISES | 26.58 | 0 | 0 | 0
2601 | HOOGHLY | Hooghly Division | Baligari Piped Water Supply Scheme. , SM/18671 | New | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for BAIDYAPUR mouza of Baligari Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 801/HUG | 25/03/2025 | 60 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 26.48 | 0 | 0 | 0
2602 | HOOGHLY | Hooghly Division | Baligari Piped Water Supply Scheme. , SM/18671 | New | Road restoration at Madpur under Baligori PWSS under Chandannagar Sub-Division P.H.E. Dte. (Part C) | 940/CHAN | 21/07/2025 | 20 | SARKAR CONSTRUCTION (DEBJIT SARKAR) | 4.91 | 0 | 0 | 100
2603 | HOOGHLY | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18772 | New | Material Requisition To Resource Division | 3057/37/Hug | 11/10/2023 | 0 | Resource Division | 22.02 | 0 | 0 | 0
2604 | HOOGHLY | Electrical | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18772 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHINRA PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1170/ED | 14/06/2024 | 90 | ANJAN ENTERPRISE | 10.71 | 0 | 0 | 0
2605 | HOOGHLY | Electrical | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18772 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHINRA PIPED W/S SCHEME, Zone - II, T.W. No. IV, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1171/ED | 14/06/2024 | 90 | R.K.ENTERPRISE | 10.74 | 0 | 0 | 0
2606 | HOOGHLY | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18772 | New | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for CHINRA ZONE-IIPiped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3669/HUG | 13/11/2024 | 45 | MAYA CONSTRUCTION | 26.56 | 0 | 0 | 0
2607 | HOOGHLY | Electrical | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18772 | New | Quotation money deposition for new service connection at Chingra w/s scheme, Zone- 2, T.W. No.-2, Dist.-Hooghly under PHE Dte. Application No- 5004136093 Reference ID- 503627504 SM Code- 18772 | 180 | 30/05/2024 | 0 | WBSEDCL | 3.92 | 0 | 0 | 0
2608 | HOOGHLY | Electrical | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18772 | New | Quotation of New Service Connection for Chinra w/s Scheme, Zone-II,TW No-III Block-Khanakul-II Dist-Hooghly under Electrical Division Phe Dte.(SM/18772) Application No-5004383077 Reference Id-503732160 | 454 | 10/09/2024 | 0 | WBSEDCL | 3.57 | 0 | 0 | 0
2609 | HOOGHLY | Electrical | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18772 | New | Quotation of New Service Connection for Chinra w/s Scheme,Zone-II,TW No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/18772) Application No-5003988265 Reference Id-503547190 | 759 | 16/02/2024 | 0 | WBSEDCL | 6.73 | 0 | 0 | 0
2610 | HOOGHLY | Electrical | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18772 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chinra water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | 3611/ED | 29/08/2023 | 682 | MAHADEV ENTERPRISE | 22.26 | 2.84 | 12.75 | 30
2611 | HOOGHLY | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18772 | New | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 224.24 | 30.73 | 50
2612 | HOOGHLY | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18772 | New | Sinking of 4 (Four) Nos tube well (250 mm X 150 mm) with supply of PVC Pipe and strainer and having depth upto 180 M at CHINRA Z-II and ARUNDA Z-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 726/HUG | 05/03/2024 | 366 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 39.06 | 0 | 0 | 75
2613 | HOOGHLY | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18772 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0 | 0
2614 | HOOGHLY | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18772 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) CHILADANGI PWSS- 2no's (2) PATUL PWSS -1 no's (3) RADHABALLAVPUR PWSS (Z-I)- 1 no's (4) RADHABALLAVPUR PWSS (Z-II)- 2 no's (5) UDAYPUR PWSS - 2no's, (6) UDNA PWSS - 2no's, (7) CHINRA PWSS (Z-I)- 1 no's, (8) CHINRA PWSS (Z-II)- 3 no's | 1153/Arg | 10/12/2024 | 31 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
2615 | HOOGHLY | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18772 | New | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of Chinra Zone-II Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Pursurah Block. | 1460/HUG | 18/05/2023 | 30 | GLOBAL CONSTRUCTION | 11.78 | 0 | 0 | 0
2616 | HOOGHLY | Hooghly Division | Providing Functional Household Tap Connection(FHTC) within the Paschim Gobindapur, Nikash and Mathurabati Mouza of Borhal (Zone-I) PWSS , SM/06754 | Retrofitting | COLLECTION DATA FOR FHTC IN BORHAL |  | 08/12/2020 | 0 | ARUN SEAL AND CO. | 2.15 | 0 | 0 | 0
2617 | HOOGHLY | Hooghly Division | Providing Functional Household Tap Connection(FHTC) within the Paschim Gobindapur, Nikash and Mathurabati Mouza of Borhal (Zone-I) PWSS , SM/06754 | Retrofitting | Partial Modification & Extension of HDPE Water Distribution Line at Jangalsufi village of Borhal (Zone-I) & its adjoining mouzas Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Jangipara] | 448/Ser | 31/05/2022 | 15 | ARUN SEAL AND CO. | 4.85 | 4.85 | 99.97 | 100
2618 | HOOGHLY | Hooghly Division | Providing Functional Household Tap Connection(FHTC) within the Paschim Gobindapur, Nikash and Mathurabati Mouza of Borhal (Zone-I) PWSS , SM/06754 | Retrofitting | Providing 2200 nos F.H.T.C. in Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur, Budul Badul Hati, Bhandarhati, Ilampur, Gabtala, Dakshin Dilakash, Mandaran Dilakash, Khurigachhi, Kulakash, Kandar Panagar village of Borhal (Zone- II)and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | 1686/Hug | 17/12/2020 | 182 | S & P CONSTRUCTION | 24.9 | 24.9 | 100 | 98
2619 | HOOGHLY | Hooghly Division | Providing Functional Household Tap Connection(FHTC) within the Paschim Gobindapur, Nikash and Mathurabati Mouza of Borhal (Zone-I) PWSS , SM/06754 | Retrofitting | Estimate of Construction of Boundary Wall at 3rd T/W Site under BORHAL (Zone-II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 63/SER | 20/01/2025 | 7 | SURAJIT SINGHA RAY | 5 | 0 | 0 | 0
2620 | HOOGHLY | Hooghly Division | Providing Functional Household Tap Connection(FHTC) within the Paschim Gobindapur, Nikash and Mathurabati Mouza of Borhal (Zone-I) PWSS , SM/06754 | Retrofitting | Estimate of Construction of Boundary Wall at 4th T/W Site under BORHAL (Zone-II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 62/SER | 20/01/2025 | 7 | SURAJIT SINGHA RAY | 5 | 0 | 0 | 0
2621 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MANDARA WATER SUPPLY SCHEME. , SM/07441 | Retrofitting | FHTC |  | 24/09/2021 | 0 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 41.41 | 0 | 0 | 0
2622 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MANDARA WATER SUPPLY SCHEME. , SM/07441 | Retrofitting | FHTC |  | 24/09/2021 | 0 | K. JAGADHATRY & CO. | 7.39 | 0 | 0 | 0
2623 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MANDARA WATER SUPPLY SCHEME. , SM/07441 | Retrofitting | Providing 253 nos F.H.T.C. in Gangarampur Village of Mandara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Dhaniakhali] | 394/Hug | 15/02/2021 | 20 | K. JAGADHATRY & CO. | 13.2 | 12.85 | 100 | 0
2624 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MANDARA WATER SUPPLY SCHEME. , SM/07441 | Retrofitting | Providing 1693nos F.H.T.C. in Mandara Village of Mandara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Dhaniakhali] | 393/Hug | 15/02/2021 | 50 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 88.47 | 60.72 | 100 | 0
2625 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MANDARA WATER SUPPLY SCHEME. , SM/07441 | Retrofitting | Providing 1693nos F.H.T.C. in Mandara Village of Mandara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Dhaniakhali] | 393/HUG | 15/02/2021 | 50 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 88.47 | 21.9 | 100 | 100
2626 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MANDARA WATER SUPPLY SCHEME. , SM/07441 | Retrofitting | Material Requisition To Resource Division | 428/3-5/Hug | 07/03/2022 | 0 | Resource Division | 10.98 | 0 | 0 | 0
2627 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jaykrishnapur (Mathura,Shyambati,Ballabhbati,Dhulepur mouza) Water Supply Scheme , SM/07149 | Retrofitting | FHTC |  | 29/01/2021 | 0 | BANBERIA CONSTRUCTION CO. | 60 | 0 | 0 | 0
2628 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jaykrishnapur (Mathura,Shyambati,Ballabhbati,Dhulepur mouza) Water Supply Scheme , SM/07149 | Retrofitting | Placement of Fund | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
2629 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jaykrishnapur (Mathura,Shyambati,Ballabhbati,Dhulepur mouza) Water Supply Scheme , SM/07149 | Retrofitting | Providing 90 nos Functional Household Tap Connection (FHTC) within Jaykrishnapur & Dhulepur Village of Jaykrishnapur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I] | 716/Hug | 07/04/2022 | 20 | SADHUKHAN ENTERPRISE | 4.26 | 0 | 0 | 0
2630 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jaykrishnapur (Mathura,Shyambati,Ballabhbati,Dhulepur mouza) Water Supply Scheme , SM/07149 | Retrofitting | Material Requisition To Resource Division | 2096/32/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0 | 0
2631 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jaykrishnapur (Purba Amarpur,Jaykrishnapur mouza) Water Supply Scheme under , SM/07150 | Retrofitting | Providing 220 nos FHTC Mathura village of Joukrishnapur and its Adj. Mouzas PWSS | 1440/Hug. | 02/02/2021 | 45 | R AND D TRADERS | 10.01 | 10.01 | 100 | 0
2632 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Jaykrishnapur (Purba Amarpur,Jaykrishnapur mouza) Water Supply Scheme under , SM/07150 | Retrofitting | Providing 220 nos F.H.T.C. in Mathura village of Jaykrishnapur and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I] | 243/Hug | 02/02/2021 | 20 | R AND D TRADERS | 10.05 | 0 | 0 | 0
2633 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme , SM/07460 | Retrofitting | FHTC |  | 15/02/2021 | 0 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 78 | 0 | 0 | 0
2634 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme , SM/07460 | Retrofitting | FHTC |  | 06/10/2021 | 0 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 8.41 | 0 | 0 | 0
2635 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme , SM/07460 | Retrofitting | ... | 844327 | 08/03/2021 | 0 | HOOGHLY ZILLA PARISHAD | 7.8 | 0 | 0 | 0
2636 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme , SM/07460 | Retrofitting | FHTC |  | 30/09/2021 | 0 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 3.36 | 0 | 0 | 0
2637 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme , SM/07460 | Retrofitting | Material Requisition To Resource Division | 2686/Hug | 01/12/2022 | 0 | Resource Division | 0.34 | 0 | 0 | 0
2638 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme , SM/07460 | Retrofitting | Material Requisition To Resource Division | 2197/1/HUG | 14/12/2021 | 0 | Resource Division | 1.59 | 0 | 0 | 0
2639 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme , SM/07460 | Retrofitting | Material Requisition To Resource Division | 2098/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0 | 0
2640 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme , SM/07460 | Retrofitting | Repair and Renovation Works of R.C.C. Elevated Reservoir of SANTOSHPUR PWSS under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 4074/HUG | 19/12/2024 | 90 | RAJ CONSTRUCTION | 9.25 | 0 | 0 | 0
2641 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme , SM/07460 | Retrofitting | Sinking of tube-well by D.R. Rig method at SANTOSHPUR Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E. Dte. | 538/HUG | 20/02/2024 | 30 | ANIRUDDHA FARUQUE | 15.99 | 13.57 | 100 | 100
2642 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of SANTOSHPUR Water Supply Scheme , SM/07460 | Retrofitting | Repairing of boundary wall at old 1st tubewell site of Santoshpur PWSS Scheme under Chandannagar Sub-Division, PHE Dte | 1075/CHAN | 31/07/2025 | 20 | M/S RAJKUMAR KHAN | 4.18 | 0 | 0 | 0
2643 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. , SM/07953 | Retrofitting | FHTC |  | 15/03/2021 | 0 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 10.5 | 0 | 0 | 0
2644 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. , SM/07953 | Retrofitting | FHTC |  | 15/03/2021 | 0 | JAI BHARAT COMMERCIAL CORPORATION | 25 | 0 | 0 | 0
2645 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. , SM/07953 | Retrofitting | Providing 130 nos. tap connection at Bagbari mouza, Kanaipur mouza, Nazirpur mouza and sardarpur mouza of Madpur water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. to make them "SWAJAL VILLAGE" | 15/chan | 05/01/2022 | 20 | M/S RAJKUMAR KHAN | 5 | 10.06 | 100 | 100
2646 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. , SM/07953 | Retrofitting | Construction of Boundary Wall and Laying of rising main at 3rd Tubewell site of MADPUR Water Supply Scheme under Hooghly Division, PHE Dte. | 209/chan | 13/04/2022 | 30 | M/S RAJKUMAR KHAN | 4.99 | 1.99 | 100 | 100
2647 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. , SM/07953 | Retrofitting | Providing 132 nos. tap connection at Madpur mouza, Maheshpur mouza, Radhanagar mouza and Nandanbati mouza of Madpur water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. to make them "SWAJAL VILLAGE" | 221/chan | 13/04/2022 | 20 | M/S RAJKUMAR KHAN | 4.99 | 5.13 | 100 | 100
2648 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. , SM/07953 | Retrofitting | Material Requisition To Resource Division | 1125/5/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
2649 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MADPUR WATER SUPPLY SCHEME. , SM/07953 | Retrofitting | Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at various Mouzas of Madpur water supply scheme under Chandannagar Sub-Division P.H.E. Dte. | 727/HUG | 05/03/2024 | 30 | BAKSHI ENTERPRISE | 9.55 | 9.38 | 100 | 100
2650 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Arandi & Mandaran Mouza of Arandi Water Supply Scheme , SM/06764 | Retrofitting | FHTC WORKS |  | 15/12/2020 | 0 | TITAS CONSTRUCTION | 22.3 | 0 | 0 | 0
2651 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Arandi & Mandaran Mouza of Arandi Water Supply Scheme , SM/06764 | Retrofitting | FHTC |  | 12/04/2021 | 0 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 2.71 | 0 | 0 | 0
2652 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Arandi & Mandaran Mouza of Arandi Water Supply Scheme , SM/06764 | Retrofitting | FHTC |  | 15/02/2021 | 0 | TITAS CONSTRUCTION | 14.09 | 0 | 0 | 0
2653 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Arandi & Mandaran Mouza of Arandi Water Supply Scheme , SM/06764 | Retrofitting | Placement of Fund | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
2654 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Arandi & Mandaran Mouza of Arandi Water Supply Scheme , SM/06764 | Retrofitting | Providing 887 nos FHTC in Jaysinghachak & Pandugram village of Arandi PWSS | 1539/Hug | 24/11/2020 | 181 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 38.52 | 29.23 | 75.87 | 100
2655 | HOOGHLY | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection (FHTC) within the Arandi & Mandaran Mouza of Arandi Water Supply Scheme , SM/06764 | Retrofitting | Providing 100 nos Functional Household Tap Connection (FHTC) within the command area of ARANDI Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | 13/Hug | 04/01/2022 | 20 | MS CHANDIMATA CONSTRUCTION | 13.37 | 0 | 0 | 100
2656 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. , SM/07537 | Retrofitting | FHTC |  | 30/09/2021 | 0 | RAJ CONSTRUCTION | 40.07 | 0 | 0 | 0
2657 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. , SM/07537 | Retrofitting | SUPPLY & DELIVERY OF BENTONITE POWDER SODIUM BASED (RAJASTHAN VARIETY) FOR CONSTRUCTION OF TUBE WELLS ATDHARAMPUR W/S SCH TW-I (REPLACEMENT) & UDANG W/S SCG TW-I HW SITE (REPLACEMENT) UNDER CMSD-II (D), CDD, PHE DTE. | 236/CMSD-II (D) | 23/08/2021 | 30 | S B S ENTERPRISE | 0.85 | 0.43 | 50 | 100
2658 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. , SM/07537 | Retrofitting | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 248/CMSD-II (D) | 24/08/2021 | 30 | S B S ENTERPRISE | 2.88 | 0.12 | 100 | 100
2659 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. , SM/07537 | Retrofitting | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELLS AT DHARAMPUR W/S SCH TW-I (REPLACEMENT) UNDER CMSD-II (D), CDD, PHE DTE. | 234/CMSD-II (D) | 23/08/2021 | 30 | S B S ENTERPRISE | 0.96 | 0.71 | 100 | 100
2660 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. , SM/07537 | Retrofitting | PROVIDING TUBE WELL MATERIALS (200 CM PIPE & 200 MM RMS FILTER)CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 249/CMSD-II (D) | 24/08/2021 | 30 | S B S ENTERPRISE | 4.85 | 1.63 | 100 | 100
2661 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. , SM/07537 | Retrofitting | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 255/CMSD-II (D) | 24/08/2021 | 15 | S B S ENTERPRISE | 4.86 | 1.69 | 100 | 100
2662 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. , SM/07537 | Retrofitting | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 351/CMSD-II (D) | 15/09/2021 | 30 | S B S ENTERPRISE | 4.17 | 4.17 | 100 | 100
2663 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. , SM/07537 | Retrofitting | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG M/C IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 350/CMSD-II (D) | 15/09/2021 | 30 | S B S ENTERPRISE | 4.86 | 3.3 | 100 | 100
2664 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. , SM/07537 | Retrofitting | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS:12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN HOWRAH DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 352/CMSD-II (D) | 15/09/2021 | 30 | S B S ENTERPRISE | 2.38 | 1.95 | 100 | 100
2665 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. , SM/07537 | Retrofitting | SUPPLY & DELIVERY OF GRAVELS & BENTONITE POWDER AT SITE FOR CONSTRUCTION OF TUBE WELL AT DHARAMPUR TW-I (REPLACEMENT TUBE WELL) HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 222/CMSD-II (D) | 17/08/2021 | 15 | S B S ENTERPRISE | 0.89 | 0.35 | 100 | 100
2666 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. , SM/07537 | Retrofitting | Providing 1439 nos F.H.T.C. in Chanparai and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah Mogra] | 380/Hug | 15/02/2021 | 40 | RAJ CONSTRUCTION | 74.99 | 70.99 | 100 | 100
2667 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. , SM/07537 | Retrofitting | Material Requisition To Resource Division | 2097/11/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0 | 0
2668 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. , SM/07537 | Retrofitting | Fuel charges for car no. WB-25H-5187 for the month of JANUARY 2023 | BP-2022-23-345 | 02/03/2023 | 0 | MIRA SERVICE STATION | 0.2 | 0 | 0 | 0
2669 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BHANGAMORA WATER SUPPLY SCHEME. , SM/08744 | Retrofitting | Providing 800 nos Functional Household Tap Connection (FHTC) within the command area of BHANGAMORA Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte | 2229/Hug | 15/12/2021 | 60 | BIMAL KUMAR HALDER | 40.78 | 38.51 | 94.43 | 100
2670 | HOOGHLY | Central Drilling | Augmentation of PANDUA ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09604 | Augmentation | PROVIDING PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL AT PANDUA BLOCK UNDER CDD, PHE DTE. | 328/CMSD-I | 15/07/2022 | 10 | INDRANI ENTERPRISE | 0.93 | 0.73 | 100 | 100
2671 | HOOGHLY | Central Drilling | Augmentation of PANDUA ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09604 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN PANDUA, SUTAHATA BLOCK UNDER CMSD-I (D), CDD, PHE DTE. | 223/CMSD-I | 20/06/2022 | 15 | INDRANI ENTERPRISE | 4.98 | 4.98 | 100 | 100
2672 | HOOGHLY | Central Drilling | Augmentation of PANDUA ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09604 | Augmentation | SINKING OF 200 MM X 100 MM DIA TUBE WELL WITH OTHER WOORKS AT SITE IN PANDUA, GHATAL BLOCK UNDER CDD, PHE DTE. | 396/CMSD-I | 05/08/2022 | 15 | INDRANI ENTERPRISE | 5 | 4.92 | 100 | 100
2673 | HOOGHLY | Central Drilling | Augmentation of PANDUA ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09604 | Augmentation | PROVIDING BENTONITE POWDER SODIUM BASED WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT PANDUA BLOCK UNDER CDD, PHE DTE. | 329/CMSD-I | 15/07/2022 | 10 | INDRANI ENTERPRISE | 0.97 | 0.73 | 100 | 100
2674 | HOOGHLY | Electrical | Augmentation of PANDUA ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09604 | Augmentation | Replacement of some electrical accessories, voltage correcting device and other allied works for Pandua water supply scheme, Zone-III, P.H. No. I, District- Hooghly under Electrical Division, PHE Dte. | 493/HMSD | 02/03/2023 | 30 | KARUNAMOY ENGINEERING | 3.06 | 3.06 | 100 | 0
2675 | HOOGHLY | Hooghly Division | Augmentation of DEBANANDAPUR Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09207 | Augmentation | Providing of 87 nos Functional House Hold Tap Connection Within Debanandapur Mouza of Debanandapur Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 91/CH | 03/02/2022 | 25 | BIMAL KUMAR HALDER | 4.99 | 4.57 | 91.6 | 100
2676 | HOOGHLY | Hooghly Division | Augmentation of DEBANANDAPUR Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09207 | Augmentation | Providing 70 nos. Functional House Hold Connection (FHTC) within the Command area of DEBANANDAPUR (Z-II) Water Supply Scheme Under Chinsurah Sub-Division. (Block: Chinsurah-Magra) | 730/CH | 26/08/2022 | 15 | BIMAL KUMAR HALDER | 4.96 | 4.96 | 100 | 100
2677 | HOOGHLY | Hooghly Division | Augmentation of DEBANANDAPUR Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09207 | Augmentation | Providing 80 nos. Functional House Hold Connection (FHTC) within the Command area of DEBANANDAPUR (Z-I) Water Supply Scheme Under Chinsurah Sub-Division. (Block: Chinsurah-Magra) | 756/Ch | 05/09/2022 | 15 | BIMAL KUMAR HALDER | 4.97 | 4.79 | 100 | 100
2678 | HOOGHLY | Hooghly Division | Augmentation of DEBANANDAPUR Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09207 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DEBANANDAPUR PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 1130/HUG | 19/04/2023 | 45 | BAKSHI ENTERPRISE | 40.32 | 16.69 | 100 | 30
2679 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. , SM/07535 | Retrofitting | FHTC |  | 23/07/2021 | 0 | M/S T.K.B. CONSTRUCTION | 13.44 | 0 | 0 | 0
2680 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. , SM/07535 | Retrofitting | FHTC |  | 19/03/2021 | 0 | DILIP KUMAR GHOSH | 15 | 0 | 0 | 0
2681 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. , SM/07535 | Retrofitting | FHTC |  | 17/08/2021 | 0 | M/S T.K.B. CONSTRUCTION | 5.51 | 0 | 0 | 0
2682 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. , SM/07535 | Retrofitting | FHTC |  | 23/07/2021 | 0 | DILIP KUMAR GHOSH | 13.44 | 0 | 0 | 0
2683 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. , SM/07535 | Retrofitting | Providing 50 nos Functional Household Tap Connection (FHTC) within the command area of LAKSHMIPUR Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | 124/Hug | 19/01/2022 | 15 | SADHUKHAN ENTERPRISE | 3.79 | 3.78 | 99.99 | 100
2684 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. , SM/07535 | Retrofitting | Placement of Fund | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
2685 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. , SM/07535 | Retrofitting | Material Requisition To Resource Division | 2096/15/Hug | 26/11/2021 | 0 | Resource Division | 0.82 | 0 | 0 | 0
2686 | HOOGHLY | Hooghly Division | Augmentation of Chanparai Water Supply Scheme , SM/10467 | Augmentation | Preparation of DPR for Augmentation of Chanparai Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Chinsurah-Magra) | 128/CH | 17/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.38 | 3.38 | 100 | 0
2687 | HOOGHLY | Hooghly Division | Augmentation of Chanparai Water Supply Scheme , SM/10467 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at CHANPARAI PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 03 | 2009/HUG | 13/09/2022 | 45 | OSMAN SEKH | 22.63 | 11.03 | 100 | 0
2688 | HOOGHLY | Hooghly Division | Augmentation of Chanparai Water Supply Scheme , SM/10467 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe line for inter connection between T.W & Distribution System for Augmentation of CHANPARAI Piped Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.HE Dte. within CHINSURAH-MOGRA Block. | 1477/HUG | 19/05/2023 | 45 | SRI KRISHNA ENTERPRISE | 11.81 | 11.25 | 100 | 100
2689 | HOOGHLY | Hooghly Division | Augmentation of Chanparai Water Supply Scheme , SM/10467 | Augmentation | Material Requisition To Resource Division | 1123/HUG | 06/06/2022 | 0 | Resource Division | 5.5 | 0 | 0 | 0
2690 | HOOGHLY | Hooghly Division | Augmentation of Chanparai Water Supply Scheme , SM/10467 | Augmentation | Material Requisition To Resource Division | 1991/1/HUG | 12/09/2022 | 0 | Resource Division | 7.86 | 0 | 0 | 0
2691 | HOOGHLY | Hooghly Division | Augmentation of Chanparai Water Supply Scheme , SM/10467 | Augmentation | Material Requisition To Resource Division | 1105/Hug | 17/04/2023 | 0 | Resource Division | 7.86 | 0 | 0 | 0
2692 | HOOGHLY | Electrical | Augmentation of Chanparai Water Supply Scheme , SM/10467 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT CHANPARAI W/S SCH., P.H. NO. - III | 53 | 31/05/2023 | 0 | WBSEDCL | 3.17 | 0 | 0 | 0
2693 | HOOGHLY | Hooghly Division | Augmentation of Chanparai Water Supply Scheme , SM/10467 | Augmentation | Augmentation of CHANPARAI Water Supply Scheme with LDS, FHTC, Rising Main at CHINSURAH MOGRA Block of Chinsurah Sub-Division under Hooghly Division, P.H.E. Dte. | 2178/HUG | 29/09/2022 | 75 | RAJ CONSTRUCTION | 251.9 | 230.86 | 100 | 10
2694 | HOOGHLY | Hooghly Division | Augmentation of Chanparai Water Supply Scheme , SM/10467 | Augmentation | Repairing & Renovation of boundary wall, Switch room and Land development at PH-2 of Chanparai Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 490/CH | 04/04/2025 | 10 | RAJ CONSTRUCTION | 1.97 | 0 | 0 | 0
2695 | HOOGHLY | Hooghly Division | Augmentation of Chanparai Water Supply Scheme , SM/10467 | Augmentation | Repairing & Renovation of boundary wall, Switch room and Land development at H/W Site of Chanparui Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 488/CH | 04/04/2025 | 10 | RAJ CONSTRUCTION | 4.79 | 0 | 0 | 0
2696 | HOOGHLY | Electrical | Augmentation of Chanparai Water Supply Scheme , SM/10467 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Chanparai water supply scheme, T.W. No.- I, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | 830/ED | 14/02/2023 | 259 | NITESH MANAGEMENT | 10.73 | 10.4 | 97.11 | 97
2697 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Preparation of DPR for Augmentation of Polba Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Polba-Dadpur) | 143/CH | 21/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.76 | 4.76 | 99.99 | 0
2698 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Additional Survey Work for Preparation of DPR for Augmentation of Polba Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Polba-Dadpur) | 144/CH | 21/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.41 | 0.4 | 98.08 | 0
2699 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at POLBA (Zone-II) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 04 | 2010/HUG | 13/09/2022 | 45 | OSMAN SEKH | 22.63 | 21.12 | 93.33 | 0
2700 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site Of POLBA ZONE-II Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | 443/HUG | 16/02/2023 | 60 | MAA JAGADHATRI CONSTRUCTION | 12.24 | 12.24 | 100 | 55
2701 | HOOGHLY | Electrical | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Polba water supply scheme TW No I and II Block Polba Dadpur, District Hooghly under ED PHED. | 852/ED | 14/02/2023 | 90 | S.P. CONSTRUCTION | 21.49 | 20.78 | 96.67 | 98
2702 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir of 450 cum capacity of POLBA Zone-I PWSS under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. SL NO - 02 | 1905/HUG | 05/09/2022 | 30 | M/S T.K.B. CONSTRUCTION | 9.49 | 9.49 | 100 | 0
2703 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Augmentation of POLBA (ZONE-I) Water Supply Scheme with LDS & FHTC At Polba-Dadpur Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. SL NO - 04 | 1885/HUG | 01/09/2022 | 90 | P.B. ENTERPRISE (PINTU BHADURI) | 411.46 | 392.41 | 100 | 65
2704 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Repairing Of Switch Room, Boundary wall for Augemntation Of POLBA ZONE-I W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | 2455/HUG | 12/08/2023 | 45 | SUDIPTA DAS | 9.47 | 18.87 | 100 | 100
2705 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Material Requisition To Resource Division | 1991/3/HUG | 12/09/2022 | 0 | Resource Division | 20.25 | 0 | 0 | 0
2706 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Material Requisition To Resource Division | 1386/38/Hug | 15/05/2023 | 0 | Resource Division | 0.98 | 0 | 0 | 0
2707 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Material Requisition To Resource Division | 3059/30/Hug | 11/10/2023 | 0 | Resource Division | 24.79 | 0 | 0 | 0
2708 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Material Requisition To Resource Division | 1105/4/Hug | 17/04/2023 | 0 | Resource Division | 14.69 | 0 | 0 | 0
2709 | HOOGHLY | Electrical | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Quotation bill for new service connection charges of WBSEDCL at Polba w/s scheme, Zone-II, P.H. No.-I | 163 | 20/02/2023 | 0 | WBSEDCL | 12.44 | 0 | 0 | 0
2710 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Pawan Ochai Road Restoration | BP-2023-24-396 | 26/09/2023 | 0 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 6.79 | 0 | 0 | 0
2711 | HOOGHLY | Electrical | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Quotation bill for security money of WBSEDCL at Polba w/s scheme, Zone-II, P.H. No.-II | 163 | 20/02/2023 | 0 | WBSEDCL | 2.81 | 0 | 0 | 0
2712 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Pandua Polba Road Restoration | BP-2023-24-397 | 26/09/2023 | 0 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 33.08 | 0 | 0 | 0
2713 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Augmentation of POLBA (ZONE-II) Water Supply Scheme with LDS & FHTC At Polba-Dadpur Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | 1718/Hug | 24/08/2022 | 40 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 110.96 | 102.3 | 100 | 85
2714 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in POLBA GP of POLBA-DADPUR Block. | 245/CH | 12/03/2024 | 30 | R.K. TRADERS | 4.98 | 4.96 | 100 | 75
2715 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in DADPUR GP of POLBA-DADPUR Block | 243/CH | 12/03/2024 | 30 | SHREEOM ENTERPRISE | 4.98 | 1.31 | 20.94 | 70
2716 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Birpala village under Polba Dadpur Block, Gopalnagar village of Polba Dadpur Block and Kasemaligar village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | 264/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
2717 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Sonatikri village under Polba Dadpur Block, Banshdarun village of Polba Dadpur Block and Arzi Jatchandi village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | 266/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
2718 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Banseya village under Polba Dadpur Block, Barunanpara village of Polba Dadpur Block and Ramnagar Bheri village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | 267/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
2719 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Dubir Bheri village under Polba Dadpur Block, Dakshin Babnan village of Polba Dadpur Block and Chanda village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | 268/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
2720 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Khurigachi village under Polba Dadpur Block, Musar village of Polba Dadpur Block and Nonadanga village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | 269/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
2721 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Meghsar village under Polba Dadpur Block, Baral Malimpur village of Polba Dadpur Block and Sangrampur village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | 270/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
2722 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Construction of Guard Room at Polba (Z-I) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | 128/CH | 16/02/2024 | 15 | MAA BUNAMATA ENTERPRISE | 3.76 | 3.75 | 100 | 15
2723 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under POLBA Block (Existing scheme) of Chinsurah Sub Division under Hooghly Division PHE Dte. | 930/CH | 05/11/2024 | 5 | R.K. TRADERS | 4.85 | 4.68 | 49.1 | 90
2724 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under POLBA Block (New scheme) of Chinsurah Sub Division under Hooghly Division PHE Dte. | 934/CH | 11/11/2024 | 5 | TAPAS ADHYA | 2.12 | 2.12 | 100 | 90
2725 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Laying C.I/D.I pipes & specials for interconnection between T.W No. -I & II with distribution pipe line at Polba (Z-II) W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | 543/CH | 18/06/2024 | 7 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 2.66 | 2.59 | 100 | 50
2726 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Road Restoration | BP-2023-24-591 | 16/11/2023 | 0 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 93 | 0 | 0 | 0
2727 | HOOGHLY | Electrical | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Quotation for new service connection at Polba[SM/10468] W/S Sch. , Zone - I, T/W No. - IV, (Nr. Kasundipara primary school), Block - Polba-Dadpur, under Polba CCC, WBSEDCL, Ref. Id. - 503595736, Dt. - 05/04/2024, Application No. - 5004071216, | 35 | 09/04/2024 | 0 | WBSEDCL | 7.13 | 0 | 0 | 0
2728 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Providing Functional House hold tap connection (FHTC) under JJM within left out mouzas/habitations of differet PWSS under Polba Dadpur Block of chinsurah sub Division of Hooghly Division, P.H.E Dte | 231/CH | 19/02/2025 | 10 | M/S BIMAL DAS AND CO. | 2.86 | 0 | 0 | 0
2729 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Sinking of 1 No. tube-well, Rising Main for inter connection between T.W & Distribution, construction of boundary wall at PUINAN mouza of POLBA Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | 4144/HUG | 24/12/2024 | 30 | BANSBERIA CONSTRUCTION CO. | 20.34 | 0 | 0 | 0
2730 | HOOGHLY | Hooghly Division | Augmentation of Polba Water Supply Scheme , SM/10468 | Augmentation | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall at GOSWAMIMALIPARA mouza of POLBA Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | 4145/HUG | 24/12/2024 | 45 | BANSBERIA CONSTRUCTION CO. | 26.48 | 0 | 0 | 0
2731 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. , SM/09790 | Augmentation | Preparation of DPR for Augmentation of KAMARPUKUR Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-II]. | 614/Arg | 31/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.61 | 3.62 | 100 | 0
2732 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. , SM/09790 | Augmentation | 1ST CONTINUATION ORDER FOR Deployment of 5 (five) Nos. Security Guard without Arm for guarding arrangement of Office cum store at Chandannagar Sub-Division Office under Chandannagar Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.12.2021 to 31.03.2022. | 2110/hug | 30/11/2021 | 121 | PRASUN ENTERPRISE (PRASUN BISWAS) | 4.22 | 0 | 0 | 0
2733 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. , SM/09790 | Augmentation | 1ST CONTINUATION ORDER FOR Deployment of 5 (five) Nos. Security Guard without Arm for guarding arrangement of Office cum store at Hooghly Division & Chinsurah Sub-Division Office under Chinsurah Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.12.2021 to 31.03.2022. | 2105/Hug | 29/11/2021 | 121 | PRASUN ENTERPRISE (PRASUN BISWAS) | 4.22 | 0 | 0 | 0
2734 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. , SM/09790 | Augmentation | Repairing of Rising Main due to Construction of Box Culvert by PWD and laying D.I pipes & specials for Rising Main pipe line for KAMARPUKUR Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. [Block-Goghat-II] | 733/Arg | 29/09/2022 | 20 | DHIRENDRA ENGINEERING & CONSTRUCTION | 4.17 | 4.15 | 100 | 0
2735 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. , SM/09790 | Augmentation | Material Requisition To Resource Division | 1124/5/HUG | 06/06/2022 | 0 | Resource Division | 10.98 | 0 | 0 | 0
2736 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. , SM/09790 | Augmentation | Material Requisition To Resource Division | 1773/28/Hug | 29/08/2022 | 0 | Resource Division | 0.69 | 0 | 0 | 0
2737 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. , SM/09790 | Augmentation | Material Requisition To Resource Division | 1590/6/Hug | 03/08/2022 | 0 | Resource Division | 18.45 | 0 | 0 | 0
2738 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. , SM/09790 | Augmentation | Material Requisition To Resource Division | 79/20/Hug | 06/01/2023 | 0 | Resource Division | 1.78 | 0 | 0 | 0
2739 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. , SM/09790 | Augmentation | Material Requisition To Resource Division | 1385/60/Hug | 15/05/2023 | 0 | Resource Division | 9.22 | 0 | 0 | 0
2740 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. , SM/09790 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, CHANDANNAGORE SUB-DIVISION, PHE DTE. |  | 06/11/2023 | 0 | GOUR KUMAR DAS | 0.76 | 0 | 0 | 0
2741 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. , SM/09790 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kamarpukur water supply scheme, T.W. No.- I, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | 844/ED | 14/02/2023 | 90 | SUTRADHAR TRADERS | 10.78 | 0 | 0 | 35
2742 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. , SM/09790 | Augmentation | Sinking of 3 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Gobindapur, Rajhato & Kamarpukur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 2038/HUG | 13/07/2023 | 30 | SPG ENTERPRISES | 48.51 | 11.91 | 73.68 | 70
2743 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. , SM/09790 | Augmentation | Special Repairing, maintenance work of damaged R.C.C. Elevated Resovoir of KAMARPUKUR Water Supply Scheme under Arambagh Sub - Division, P.H.E. Dte., Hooghly. | 3677/HUG | 13/11/2024 | 60 | ZEST INFRACON | 28.14 | 0 | 0 | 0
2744 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. , SM/09790 | Augmentation | Route survey Design drawing & DPR preparation of Kamarkundu Zone- I, II & III PWSS under Chandannagar Sub-Division, P.H.E. Dte | 271/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.97 | 4.93 | 100 | 100
2745 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. , SM/09790 | Augmentation | Additional pipeline due to shifting of 3rd Tubewell site under Augmentation of Kamarpukur Zone-II water supply scheme under Goghat- II block of Arambagh Sub-Division, Hooghly Division, P.H.E. Dte. | 379/HUG | 08/02/2024 | 203 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 17.75 | 17.75 | 100 | 100
2746 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. , SM/09790 | Augmentation | Augmentation of KAMARPUKUR Water Supply Scheme (Zone-II) with Laying Distribution System, Construction of switch room & boundary wall at proposed 3rd TW site and FHTC Work under Goghat-II Block of Arambag Sub-Division, Hooghly Division, PHE Dte. | 853/Hug | 25/04/2022 | 45 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 104.29 | 31.67 | 30.37 | 80
2747 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARPUKUR. , SM/09790 | Augmentation | Augmentation of KAMARPUKUR Water Supply Scheme (Zone-I) with Laying Distribution System, repairing of existing OHR, switch rooms & boundary wall and FHTC Work under Goghat-II Block of Arambag Sub-Division, Hooghly Division, PHE Dte. | 1150/Hug | 09/06/2022 | 1218 | TITAS CONSTRUCTION | 231.61 | 144.09 | 62.21 | 80
2748 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Preparation of DPR for Augmentation of Chanditala (Zone-III & IV) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | 364/SER | 17/03/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.56 | 3.55 | 99.72 | 0
2749 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Preparation of DPR for Augmentation of Chanditala (Zone-I & II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | 363/SER | 17/03/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.33 | 4.33 | 100 | 0
2750 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | 2ND CONTINUATION ORDER FOR Deployment of 3 (three) Nos. Security Guard without Arm for guarding arrangement of Office cum store at SEAKHALA Water Supply Scheme under Serampore Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.04.2022 to 31.07.2022. | 623/Hug | 31/03/2022 | 122 | P.B. ENTERPRISE (PINTU BHADURI) | 2.56 | 0 | 0 | 0
2751 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | 2ND CONTINUATION ORDER FOR Deployment of 3 (three) Nos. Security Guard without Arm for guarding arrangement of Office cum store at CHANDITALA Water Supply Scheme under Serampore Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.04.2022 to 31.07.2022. | 622/Hug | 31/03/2022 | 122 | P.B. ENTERPRISE (PINTU BHADURI) | 2.56 | 0 | 0 | 0
2752 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | PROVIDING TUBE WELL MATERIALS OF 300 MM NOMINAL DIA. CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHANDITALA W/S SCHEME UNDER HOOGHLY DISTRICT, CMSD-II(D), CDD, PHE DTE. | 235/CMSD-II(D) | 20/05/2022 | 15 | S B S ENTERPRISE | 2.79 | 2.79 | 100 | 0
2753 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHANDITALA W/S IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 238/CMSD-II(D) | 20/05/2022 | 15 | M/S S.K.GHOSH & CO. | 1.97 | 1.71 | 100 | 0
2754 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OGF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY KORES RIG MACHINE FOR CHANDITALA W/S SCHEME CHANDITALA -II BLOCK UNDER HOOGHLY DISTRICT, CMSD-II (D), CDD, PHE DTE. | 232/CMSD-II (D) | 20/05/2022 | 15 | S B S ENTERPRISE | 2.4 | 2.26 | 100 | 0
2755 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | PROVIDING TUBE WELL MATERIALS OF 200MM NOMINAL DIA. CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHANDITALA W/S SCHEME, UNDER HOOGHLY DISTRICT, CMSD-II (D), CDD, PHE DTE. | 236/CMSD-II(D) | 20/05/2022 | 15 | S B S ENTERPRISE | 3.98 | 3.2 | 100 | 0
2756 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR CHANDITALA PWSS, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 1374/CDD | 24/11/2022 | 30 | M/S SAIKAT ENTERPRISE | 12.9 | 11.13 | 100 | 0
2757 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Quotation bill for Chanditala W/S. Sch. | 109 | 18/11/2022 | 0 | WBSEDCL | 0.66 | 0 | 0 | 0
2758 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Quatation Bill for Chanditala W/S. Sch. PH-X |  | 16/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.66 | 0 | 0 | 0
2759 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-IV) Water Supply Scheme with LDS within Makhalpara, Khanpur, and part of Garalgacha & Krishnapur Mouza with Functional Household tap Connection, Repairing of existing Switch Room & Boundary Wall at Chanditala - II Block under Serampore Sub-Division, PHE Dte. | 1421/HUG | 12/07/2022 | 45 | S.B. ASSOCIATES | 78.39 | 44.01 | 56.15 | 0
2760 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-I) Water Supply Scheme with LDS within Chanditala Mouza & Functional Household Tap Connection, Construction of 1 No.Switch Room (3.6M X 3.0M ) and Boundary Wall at 10th T.W Site & Repairing of 1 no existing Switch Room at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | 1418/HUG | 12/07/2022 | 45 | EVEREST CONSULTANT SERVICES (SUBRATA KUNDU) | 73.77 | 38.85 | 52.66 | 0
2761 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-I) Water Supply Scheme with LDS within Barijhati and Thero Mouza & Functional Household tap Connection, Repairing of 2 Nos. existing Switch Room and Boundary Wall & Repairing of OHR with Boundary Wall at H.W Site (Barijhati) at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | 1419/HUG | 12/07/2022 | 45 | CHAKRABORTTI ENTERPRISE | 88.54 | 66.85 | 75.5 | 0
2762 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-II) Water Supply Scheme with LDS within Garalgacha and Krishnapur Mouza & Functional Household tap Connection, Repairing of 2 Nos. existing Switch Room and Boundary Wall & Repairing of OHR with Boundary Wall at H.W Site (Garalgacha) at Chanditala-II Block under Serampore Sub-Division, PHE Dte | 1539/HUG | 27/07/2022 | 60 | DAS TRADING | 86.11 | 64.06 | 100 | 100
2763 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chanditala water supply scheme, T.W. No. X, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | 3529/ED | 30/12/2022 | 90 | BISALAXMI ENTERPRISE | 10.66 | 10.65 | 100 | 0
2764 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-II) Water Supply Scheme with LDS within Barijhati & Bledanga Mouza & Functional Household tap Connection & Repairing of 1 no existing Switch Room at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | 1538/HUG | 27/07/2022 | 45 | M/S SHIVAM UDYOG | 56.4 | 40.37 | 100 | 100
2765 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | HIRING OF DIESEL DRIVEN MOTOR CAP (BS-III & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH FOR THE OFFICE OF THE SUPERINTENDING ENGINEER, M/E, PMU WBDWSIP UNDER CMSD-I (D), CDD, PHE DTE. | 261/CMSD-I | 27/06/2022 | 15 | SIDDHARTHA CHATTERJEE | 0.9 | 1.49 | 100 | 0
2766 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS FOR CONSTRUCTION OF TUBEWELL AT CHANDITALA, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 508/CMSDII | 11/11/2022 | 7 | SUBHRA ENTERPRISE | 0.98 | 0.9 | 100 | 0
2767 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Providing drilling crew and other works for construction of TW (300mm x 200mm x 210 mtr. depth) by utilising Departmental machineries for Chanditala PWSS under Hooghly District, CDD, PHE Dte. | 1561/CDD | 08/12/2022 | 30 | SUBHRA ENTERPRISE | 12.67 | 10.2 | 100 | 0
2768 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Material Requisition To Resource Division | 1122/2/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
2769 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Material Requisition To Resource Division | 2210/1/Hug | 30/09/2022 | 0 | Resource Division | 30.8 | 0 | 0 | 0
2770 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Material Requisition To Resource Division | 1291/2/Hug | 24/06/2022 | 0 | Resource Division | 9.24 | 0 | 0 | 0
2771 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Material Requisition To Resource Division | 1384/19/Hug | 15/05/2023 | 0 | Resource Division | 18.64 | 0 | 0 | 0
2772 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Quotation bill for new service connection of WBSEDC at Chanditalaw/s scheme, T.W. No.-XII | 149 | 08/02/2023 | 0 | WBSEDCL | 0.54 | 0 | 0 | 0
2773 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Quotation bill for new service connection of WBSEDC at Chanditala w/s scheme, T.W. No.-XI | 149 | 08/02/2023 | 0 | WBSEDCL | 0.54 | 0 | 0 | 0
2774 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Piped water supply scheme at CHANDITALA PANCHGHORA NANDANKANAN area under Chanditala - II block of Hooghly Division. | 2286/HUG | 14/06/2024 | 60 | AMBIAN INFRASTRUCTURE | 42.77 | 0 | 0 | 0
2775 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Construction of Switch Room,Boundary wall,and rising main with interconnection atChanditalaW/s Scheme(Zone 1)Beledanga,Chanditala-II Block under Hooghly Division PHE Dte.Source Augmentation. | 3614/HUG | 05/11/2024 | 60 | S D ENTERPRISE | 25.82 | 0 | 0 | 0
2776 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHANDITALA PIPED W/S SCHEME, T.W. No. XIV, Block: Chanditala-II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 452/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 6.94 | 71.57 | 65
2777 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Sinking of tube-well by D.R. Rig method Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of KRISHNARAMPUR (CHANDITALA) Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | 816/HUG | 11/03/2024 | 60 | CHAKRABORTY ENTERPRISE | 31.68 | 6.15 | 19.42 | 78
2778 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme under Chanditala I & II & Jangipara Block (Phase-III) in the District of Hooghly under Serampore Sub Division under Hooghly Division, PHE Dte. | 644/SER | 05/11/2024 | 15 | TECHVISION | 4.94 | 0 | 0 | 0
2779 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Construction of Boundary wall,Toilet,Plumbing arrangement,Path way and repairing of Existing Pump House at Pump house No 12ofChanditala water Supply Scheme under Serampur SubDivision;of Hooghly Division P.H.E Dte. | 4041/HUG | 19/12/2024 | 90 | TOTON MONDAL | 10.75 | 0 | 0 | 0
2780 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-IV) Water Supply Scheme with LDS within Makhalpara, Khanpur, and part of Garalgacha & Krishnapur Mouza with Functional Household tap Connection, Repairing of existing Switch Room & Boundary Wall at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | 1421/Hug | 12/07/2022 | 45 | S.B. ASSOCIATES | 78.39 | 17.33 | 100 | 20
2781 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Chanditala water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | 829/ED | 14/02/2023 | 687 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 22.05 | 19.69 | 89.35 | 95
2782 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Augmentation of CHANDITALA (ZONE-III) Water Supply Scheme with LDS within Eklakhi and part of Krishnapur Mouza with Functional Household tap Connection, Repairing of existing Switch Room & Boundary Wall at Chanditala-II Block under Serampore Sub-Division, PHE Dte. | 1420/HUG | 12/07/2022 | 45 | BIMAL KUMAR HALDER | 56.66 | 54.61 | 100 | 99
2783 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system,For AUGMENTATION OF of CHANDITALA W/S Scheme under Serampore Sub - Division P.H.E. Dte. | 1446/HUG | 18/05/2023 | 30 | SB ASSOCIATES | 31.08 | 14.8 | 100 | 70
2784 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at MAINAN(1No.),CHIKRAND ZONE-I (1No.),CHIKRAND ZONE-II (1No.) ,CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3388/HUG | 22/11/2023 | 45 | SPG ENTERPRISES | 87.88 | 28.3 | 100 | 100
2785 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at CHIKRAND ZONE-I (1No.), CHIKRAND ZONE-II (1No.), CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3313/HUG | 10/11/2023 | 421 | S.D ENTERPRISE (SAMIR KR. DAS) | 47.18 | 23.09 | 58.5 | 40
2786 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Laying of Balance pipeline and allied works due to road widening work at Chanditala W/S Scheme under Serampore Sub-Division, P.H.E. Dte. | 3562/HUG | 05/12/2023 | 30 | P. B. ENTERPRISE(PINTU BHADURI) | 43.61 | 40.54 | 100 | 60
2787 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Augumention of Electro Mechanical Equipments and other electro mechanical accessories at Pump House under Barijhati GP and Garalgacha Gram Panchayet of Chanditala - II Block, Dist-Hooghly under Electrical Divisio, PHE Dte. | 4892/ED | 27/12/2023 | 90 | D. K. ELECTRIC | 31.09 | 30.98 | 100 | 100
2788 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under CHANDITALA I & SERAMPORE-UTTARPARA Block of Serampore Sub Division under Hooghly Division PHE Dte. | 517/SER | 11/09/2024 | 5 | JOY GURU ENTERPRISE | 3.53 | 6.99 | 100 | 95
2789 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte.(Phase-I) for Serampore Uttarpara, Chanditala-I, Chanditala-II & Jangipara Block | 522/SER | 12/09/2024 | 5 | TOTON MONDAL | 4.93 | 4.93 | 100 | 95
2790 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte.(Phase-II) for Serampore Uttarpara, Chanditala-I, Chanditala-II & Jangipara Block | 523/SER | 12/09/2024 | 5 | TOTON MONDAL | 4.93 | 4.93 | 100 | 95
2791 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under CHANDITALA II Block of Serampore Sub Division under Hooghly Division PHE Dte. | 518/SER | 11/09/2024 | 5 | TOTON MONDAL | 4.15 | 4.12 | 100 | 95
2792 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | CONSTRUCTION OF 1NO. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT CHANDITALA PWSS NEAR EKLAKI UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E, DTE. | 431/SER | 31/07/2024 | 15 | SRI KRISHNA ENTERPRISE | 0.36 | 0.35 | 100 | 95
2793 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Quotation bill for new service connection charges at Chanditala PWSS Zone-I, P.H. No.-V, Hooghly. Application No. 5004085765 Ref ID: 503603819 | 20 | 05/04/2024 | 0 | WBSEDCL | 3.33 | 0 | 0 | 0
2794 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Quotation bill for new service connection charges at Chanditala PWSS Zone-II, P.H. No.-IV, Hooghly. Application No. 5004085812 Ref ID: 503603818 | 19 | 05/04/2024 | 0 | WBSEDCL | 6.27 | 0 | 0 | 0
2795 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Quotation money deposition for new service connection at Chanditala w/s scheme, Zone- I, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004099440 Reference ID- 503611397 SM Code- 18966 | 152 | 22/05/2024 | 0 | WBSEDCL | 3.84 | 0 | 0 | 0
2796 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Quotation money deposition for new service connection at Chanditala w/s scheme, Zone- III, T.W. NO- III, Dist.-Hooghly under PHE Dte. Application No- 5004091705 Reference ID- 503606735 SM Code- 10338 | 70 | 16/04/2024 | 0 | WBSEDCL | 8.21 | 0 | 0 | 0
2797 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Estimate for construction of 2 nos Toilets at Piarapur Pump House No-2 and Krishnarampur Pump Hose No-2 under Chanditala PWSS under Serampore Sub - Division of Hooghly Division P.H.E. Dte. | 74/SER | 20/01/2025 | 10 | M/S RAJKUMAR KHAN | 3.91 | 0 | 0 | 50
2798 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Estimate for jack pushing of Road due to interconnection of Existing pipeline to 3rd Pump House of Krishnarampur mouza under Chanditala W/S Supply scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | 76/SER | 20/01/2025 | 10 | CHAKRABORTY ENTERPRISE | 3.93 | 0 | 0 | 0
2799 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHANDITALA PIPED W/S SCHEME, T.W. No. XII & XIII, Block: Chanditala-II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 420/ED | 29/02/2024 | 564 | DEY ENTERPRISE | 20.85 | 10.14 | 48.62 | 40
2800 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Sinking of tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room , boundary wall & Repairing of Existing OHR,Switch Rooms, Boundary walls at 3rd TW sites for CHANDITALA (PIARAPUR) Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. | 2340/HUG | 19/06/2024 | 339 | MS PRADIP KUMAR PAL | 27.85 | 0 | 0 | 55
2801 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Estimate for Reconstruction of boundary wall, Internal Pathway and allied works Head Works Site of Seakhala under Chanditala Water Supply Scheme under Serampore sub Division of Hooghly Division P.H.E. Dte. | 285/SER | 17/04/2025 | 25 | M/S RAJKUMAR KHAN | 4.68 | 0 | 0 | 92
2802 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Balance works for laying of water supply pipeline by HDD process under Chanditala Water Supply Scheme under Serampore Sub-Division, P.H.E. Dte. | 652/HUG | 10/03/2025 | 30 | M/S SHIVAM UDYOG | 35.39 | 0 | 0 | 0
2803 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANDITALA. , SM/10338 | Augmentation | Sinking of 01 nos. (size 100 X 40 mm dia) 154.0 Mtr. Deep, Indian Mark-II Tube well with PVC pipe & Strainer near Chanditala Police Station under Chanditala Water Supply Scheme of Hooghly Division. | 539/SER | 29/08/2025 | 10 | PANKAJ KUMAR MANNA | 0.99 | 0 | 0 | 0
2804 | HOOGHLY | Electrical | RUDRANI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12251 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Rudrani water supply scheme, T.W. No. I & II, Block: Dhaniakhali District - Hooghly under Electrical Division, PHE Dte. | 3475/ED | 30/12/2022 | 90 | INDTECH ASSOCIATES. | 21.42 | 0 | 0 | 0
2805 | HOOGHLY | Hooghly Division | RUDRANI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12251 | New | Material Requisition To Resource Division | 3059/7/Hug | 11/10/2023 | 0 | Resource Division | 14.89 | 0 | 0 | 0
2806 | HOOGHLY | Hooghly Division | RUDRANI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12251 | New | Material Requisition To Resource Division | 1264/11/HUG | 03/05/2023 | 0 | Resource Division | 24.6 | 0 | 0 | 0
2807 | HOOGHLY | Electrical | RUDRANI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12251 | New | Quotation Bill for New Service Connection at Rudrarani W/S. Sch. TW-II | 704 | 25/01/2024 | 0 | WBSEDCL | 5.78 | 0 | 0 | 0
2808 | HOOGHLY | Electrical | RUDRANI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12251 | New | Quotation Bill for New Service Connection at Rudrarani W/S. Sch. TW-I | 705 | 25/01/2024 | 0 | WBSEDCL | 3.55 | 0 | 0 | 0
2809 | HOOGHLY | Hooghly Division | RUDRANI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12251 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 320.3 | 66.16 | 30
2810 | HOOGHLY | Hooghly Division | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12254 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of switch-rooms & boundary walls at different TW site for GURBARI Piped Water Supply Scheme under Chinsurah Sub-Division Block-Dhaniakhali , District:- Hooghly | 2422/HUG | 11/08/2023 | 90 | GEE BEE NIRMAN CO PRIVATE LIMITED | 51.96 | 0 | 0 | 0
2811 | HOOGHLY | Electrical | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12254 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gurbari water supply scheme, T.W. No. I & II, Block: Dhaniakhali District - Hooghly under Electrical Division, PHE Dte. | 3464/ED | 30/12/2022 | 90 | A.G. ENTERPRISE | 21.58 | 0 | 0 | 0
2812 | HOOGHLY | Hooghly Division | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12254 | New | Material Requisition To Resource Division | 1386/45/Hug | 15/05/2023 | 0 | Resource Division | 17.02 | 0 | 0 | 0
2813 | HOOGHLY | Hooghly Division | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12254 | New | Material Requisition To Resource Division | 1264/23/HUG | 03/05/2023 | 0 | Resource Division | 12.17 | 0 | 0 | 0
2814 | HOOGHLY | Hooghly Division | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12254 | New | Material Requisition To Resource Division | 3059/38/Hug | 11/10/2023 | 0 | Resource Division | 17.02 | 0 | 0 | 0
2815 | HOOGHLY | Hooghly Division | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12254 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For DASHGHARA ZONE-II (1 NO.), GURBARI, SHRIRAMPUR W/S Scheme under CHISURAH Sub-Division of Hooghly Division, P.H.E. Dte. | 2408/HUG | 11/08/2023 | 45 | GEE BEE NIRMAN CO PRIVATE LIMITED | 81.62 | 25.04 | 76.7 | 20
2816 | HOOGHLY | Electrical | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12254 | New | Quotation Bill for New Service Connection at Gurbari W/S. Sch. TW-I | 681 | 19/01/2024 | 0 | WBSEDCL | 3.25 | 0 | 0 | 0
2817 | HOOGHLY | Hooghly Division | GURBARI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12254 | New | Construction of Different Capacity RCC Over Head Reservoir over Pile/Raft Foundation including Sub-soil investigation works for OHR, with Laying Distribution System Providing Functional House hold Tap Connection for BISHNUPUR, DOSGHARA(zone-I), DOSGHARA(zone-II), GURBARI & SRIRAMPUR Piped Water Supply Scheme within DHANIAKHALI block under chinshuraH Sub-Division of Hooghly division, PHE Dte. Under Hooghly district in connection with JJM. | 2066/HUG | 17/07/2023 | 747 | GEE BEE NIRMAN CO PRIVATE LIMITED | 2255.89 | 93.02 | 20.62 | 20
2818 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | Preparation of DPR for Augmentation of Mandra Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambag]. | 365/Arg | 19/05/2022 | 30 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 3.64 | 3.59 | 98.65 | 0
2819 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | Sinking of 2 nos 300 X 200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of MANDRA W/S Scheme under ARAMBAG Sub-Division of Hooghly Division, P.H.E. Dte. | 160/HUG | 16/01/2023 | 45 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 28.39 | 0 | 0 | 0
2820 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIESFOR MANDRA W/S SCH UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 1679/CDD | 28/12/2022 | 30 | C.M. ENTERPRISE | 18.1 | 0 | 0 | 0
2821 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR MANDRA W/S SCH UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 1678/CDD | 28/12/2022 | 30 | C.M. ENTERPRISE | 18.1 | 0 | 0 | 0
2822 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site of Mandra Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 442/HUG | 16/02/2023 | 60 | BENGAL TRADERS | 12.32 | 12.32 | 100 | 100
2823 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | PROVIDING DRILLING CREQW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR MANDRA PWSS TW-IV, ARAMBAG BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 1679/ CDD | 28/12/2022 | 30 | C.M. ENTERPRISE | 18.1 | 9.51 | 100 | 0
2824 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR MANDRA PWSS TW-III, ARAMBAG BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 1678/ CDD | 28/12/2022 | 30 | C.M. ENTERPRISE | 18.1 | 10.73 | 100 | 0
2825 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | Material Requisition To Resource Division | 1688/3/HUG | 22/08/2022 | 0 | Resource Division | 11.15 | 0 | 0 | 0
2826 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | Material Requisition To Resource Division | 2209/3/Hug | 30/09/2022 | 0 | Resource Division | 30.8 | 0 | 0 | 0
2827 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | Material Requisition To Resource Division | 1773/20/Hug | 29/08/2022 | 0 | Resource Division | 0.69 | 0 | 0 | 0
2828 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | Material Requisition To Resource Division | 1106/1/HUG | 17/04/2023 | 0 | Resource Division | 13.56 | 0 | 0 | 0
2829 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | Material Requisition To Resource Division | 1385/65/Hug | 15/05/2023 | 0 | Resource Division | 13.13 | 0 | 0 | 0
2830 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | Material Requisition To Resource Division | 127/16/Hug | 13/01/2023 | 0 | Resource Division | 10.67 | 0 | 0 | 0
2831 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | New service connection of WBSEDCL for Mandra w/s scheme | 161 | 16/02/2023 | 0 | WBSEDCL | 0.31 | 0 | 0 | 0
2832 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | New Service Connection at Mandara W/S. Sch. PH-III | 15 | 24/04/2023 | 0 | WBSEDCL | 9.72 | 0 | 0 | 0
2833 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | Quotation Bill for New Service Connection at Mandara W/S. Sch. PH-IV | 190 | 16/03/2023 | 0 | WBSEDCL | 2.76 | 0 | 0 | 0
2834 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, RWS HOOGHLY SUB-DIVISION, PHE DTE. |  | 22/08/2023 | 0 | AATISH KUMAR SHAW | 0.4 | 0 | 0 | 0
2835 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MALAYPUR PIPED W/S SCHEME, T.W. No. V, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1153/ED | 14/06/2024 | 90 | S.G. TECHNICAL SERVICES | 10.74 | 0 | 0 | 0
2836 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ATGHARA PIPED W/S SCHEME, T.W. No. IV, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1199/ED | 14/06/2024 | 90 | EMCON | 10.74 | 0 | 0 | 0
2837 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | Protection works and other allied works at 3rd & 4th TubeWell Site of MANDRA under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 4048/HUG | 19/12/2024 | 90 | MUNSHI TAJUDDIN | 15.5 | 0 | 0 | 0
2838 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MALAYPUR PIPED W/S SCHEME, T.W. No. VI, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1154/ED | 14/06/2024 | 90 | S.G. TECHNICAL SERVICES | 10.74 | 0 | 0 | 0
2839 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Mandra water supply scheme, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 1715/ED | 18/04/2023 | 90 | M/S A.K BANERJEE | 21.89 | 21.66 | 100 | 75
2840 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SRIRAMPUR PWSS- 3nos (2) BACHHANARI PWSS- 3nos (3) MALAYPUR PWSS- 4nos (4) MANDRA PWSS- 4nos | 807/Arg | 23/08/2024 | 30 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
2841 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR MANDRA UNDER ARAMBAGH SUB DIV PHE DTE , SM/11468 | Augmentation | Augmentation of MANDRA Water Supply Scheme with LDS, FHTC, Rising Main & Construction of 350 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at ARAMBAGH Block under Arambagh Sub-Division Under Hooghly Division PHE Dte. | 2173/HUG | 28/09/2022 | 1009 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 404.56 | 351.98 | 88.59 | 60
2842 | HOOGHLY | Hooghly Division | PURUSHOTTAMPUR PIPED WATER SUPPLY SCHEME , SM/11582 | New | Material Requisition To Resource Division | 109/3/Hug | 10/01/2023 | 0 | Resource Division | 44.45 | 0 | 0 | 0
2843 | HOOGHLY | Hooghly Division | PURUSHOTTAMPUR PIPED WATER SUPPLY SCHEME , SM/11582 | New | Material Requisition To Resource Division | 3058/31/Hug | 11/10/2023 | 0 | Resource Division | 10.44 | 0 | 0 | 0
2844 | HOOGHLY | Electrical | PURUSHOTTAMPUR PIPED WATER SUPPLY SCHEME , SM/11582 | New | Quotation Bill for New Service Connection at Purushattampur W/S. Sch. TW-I | 413 | 10/11/2023 | 0 | WBSEDCL | 3.4 | 0 | 0 | 0
2845 | HOOGHLY | Electrical | PURUSHOTTAMPUR PIPED WATER SUPPLY SCHEME , SM/11582 | New | Quotation for new service connection at Purushottampur W/S Sch. , T/W No. - II | 381 | 25/10/2023 | 0 | WBSEDCL | 2.72 | 0 | 0 | 0
2846 | HOOGHLY | Electrical | PURUSHOTTAMPUR PIPED WATER SUPPLY SCHEME , SM/11582 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Purushottampur water supply scheme, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | 3500/ED | 30/12/2022 | 90 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 21.49 | 19.47 | 90.58 | 80
2847 | HOOGHLY | Hooghly Division | PURUSHOTTAMPUR PIPED WATER SUPPLY SCHEME , SM/11582 | New | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for PURUSHOTTAMPUR Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division, P.H.E. Dte. | 3779/HUG | 25/11/2024 | 362 | WATER TECH | 50.34 | 0 | 0 | 30
2848 | HOOGHLY | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT , SM/11583 | New | Material Requisition To Resource Division | 1386/49/Hug | 15/05/2023 | 0 | Resource Division | 10.2 | 0 | 0 | 0
2849 | HOOGHLY | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT , SM/11583 | New | MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-295 | 19/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 206.54 | 0 | 0 | 0
2850 | HOOGHLY | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT , SM/11583 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-211 | 14/07/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 232.26 | 0 | 0 | 0
2851 | HOOGHLY | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT , SM/11583 | New | REQUISITION OF FUND FOR SAJAL GRAM SCHEME |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 215.31 | 0 | 0 | 0
2852 | HOOGHLY | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT , SM/11583 | New | GROUND WATER BASED NAOPARA PIPED WATER SUPPLY SCHEME IN KHANAKUL - II BLOCK UNDER HOOGHLY DISTRICT (TSM/020222) | 1104/HUG | 17/04/2023 | 150 | RAJMAHAL ENTERPRISE | 41.84 | 32.87 | 78.57 | 70
2853 | HOOGHLY | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT , SM/11583 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Muragari Mini PWSS 2. Charsundalpur Mini PWSS 3. Digra Mini PWSS 4. Rampur Mini PWSS 5. Naopara Mini PWSS 6. Telinipara Mini PWSS | 209/CH | 29/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 45
2854 | HOOGHLY | Electrical | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT , SM/11583 | New | Mini piped Water Supply scheme |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
2855 | HOOGHLY | Electrical | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF GOGHAT-II,KHANAKUL-I, KHANAKUL-II, PURSURA & BALAGARH IN HOOGHLY DISTRICT , SM/11583 | New | Mini Piped water Supply Scheme | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
2856 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE , SM/11462 | Augmentation | Preparation of DPR for Augmentation of Baradangal Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh]. | 337/Arg | 02/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.01 | 3.98 | 99.13 | 0
2857 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE , SM/11462 | Augmentation | Additional work for Preparation of DPR for Augmentation of Baradangal Piped Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambag]. Part-B | 624/Arg | 01/09/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.3 | 1.3 | 100 | 0
2858 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE , SM/11462 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 150 mtrs. Depth) by utilising Departmental machineries for Baradangal W/S Scheme (Z-II, TW-I&II), Arambag block under hooghly District, CDD PHE Dte. | 2329/CDD | 30/03/2023 | 30 | ASHUTOSH DAS & CO | 22.73 | 18.83 | 100 | 100
2859 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE , SM/11462 | Augmentation | Material Requisition To Resource Division | 1773/3/Hug | 29/08/2022 | 0 | Resource Division | 0.69 | 0 | 0 | 0
2860 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE , SM/11462 | Augmentation | Material Requisition To Resource Division | 1385/62/Hug | 15/05/2023 | 0 | Resource Division | 6.84 | 0 | 0 | 0
2861 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE , SM/11462 | Augmentation | Material Requisition To Resource Division | 1234/8/Hug | 28/04/2023 | 0 | Resource Division | 26.55 | 0 | 0 | 0
2862 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE , SM/11462 | Augmentation | Quotation for New Service Connection of Baradangal w/s Scheme,Zone-II,PH No-II District-Hooghly Under ED,PHE Dte | 92 | 13/07/2023 | 0 | WBSEDCL | 4.6 | 0 | 0 | 0
2863 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE , SM/11462 | Augmentation | Quotation for New Service Connection of Baradangal w/s Scheme,Zone-II,PH No-I Dist-Hooghly under ED, PHE Dte. | 91 | 13/07/2023 | 0 | WBSEDCL | 5.05 | 0 | 0 | 0
2864 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE , SM/11462 | Augmentation | Augmentation of BARADANGAL ZONE-II PWSS with LDS, FHTC, Rising Main and Construction of 200 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at Arambagh Block under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 2827/HUG | 15/12/2022 | 204 | JAHANGIR ALAM | 266.1 | 161.13 | 60.55 | 60
2865 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE , SM/11462 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir Of BARADANGAL Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | 2454/HUG | 12/08/2023 | 60 | TANISA ENTERPRISE | 7.86 | 7.65 | 97.3 | 95
2866 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE , SM/11462 | Augmentation | Augmentation of BARADANGAL ZONE-I Water Supply Scheme with Laying Distribution System including providing Functional Household Tap Connection (FHTC) at Arambagh Block under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 1702/Hug | 22/08/2022 | 60 | M/S CARE | 193.77 | 181.56 | 100 | 99
2867 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE , SM/11462 | Augmentation | Construction of 2 nos. 5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement, Construction of 2 nos. Boundary Wall at BARADANGAL Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | 540/HUG | 20/02/2024 | 425 | DIAMOND ENGINEERS CO OP AND CONSTRUCTION SOCIETY LTD | 27.35 | 16.36 | 59.8 | 70
2868 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR BARADANGAL UNDER ARAMBAGH SUB DIV PHE DTE , SM/11462 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Baradangal water supply scheme, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 825/ED | 14/02/2023 | 926 | OSMAN SEKH | 21.5 | 1.75 | 7.56 | 70
2869 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF EKTARPUR WATER SUPPLY SCHEME. , SM/07955 | Retrofitting | FHTC |  | 30/09/2021 | 0 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 27.03 | 0 | 0 | 0
2870 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF EKTARPUR WATER SUPPLY SCHEME. , SM/07955 | Retrofitting | Providing 310 nos Functional Household Tap Connection (FHTC) within the command area of EKTARPUR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 118/Hug | 19/01/2022 | 20 | YOUNG ENGINEERS CO-OPERATIVE SOCIETY LTD. | 22.53 | 21.77 | 96.65 | 100
2871 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF EKTARPUR WATER SUPPLY SCHEME. , SM/07955 | Retrofitting | Providing 1338 nos F.H.T.C. in Dwarpara, Beleswar& Basna Village of Ektarpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | 937/Hug | 06/05/2021 | 40 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 77.59 | 75.44 | 100 | 100
2872 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF EKTARPUR WATER SUPPLY SCHEME. , SM/07955 | Retrofitting | Providing 780 nos Functional Household Tap Connection (FHTC) within the command area of EKTARPUR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 458/Hug | 10/03/2022 | 40 | MAA TARA CONSTRUCTION | 52.71 | 44.22 | 100 | 100
2873 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF EKTARPUR WATER SUPPLY SCHEME. , SM/07955 | Retrofitting | Material Requisition To Resource Division | 2097/1/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0 | 0
2874 | HOOGHLY | Hooghly Division | Retrofitting Works for Digsui-Heora (Zone-I) PWSS for providing 1374 nos Functional Household Tap Connection(FHTC) , SM/06757 | Retrofitting | COLLECTION OF DATA FOR FHTC OF DIGSUI HEORA W/S/S |  | 08/12/2020 | 0 | R AND D TRADERS | 4.98 | 0 | 0 | 0
2875 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF DWARBASINI PWSS FOR PROVIDING 2150 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE , SM/13355 | Retrofitting | Making Interconnection from newly bored tube well to existing Over Head Reservoir at Pandua under Pandua Zone-I Water Supply Scheme Under Chinsurah Subdivision under Hooghly division, PHE Dte. | 816/CH | 31/08/2023 | 15 | JOY GURU ENTERPRISE | 0.7 | 0.7 | 100 | 90
2876 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF DWARBASINI PWSS FOR PROVIDING 2150 NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE , SM/13355 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of different PWSS under PANDUA Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | 2429/HUG | 11/08/2023 | 30 | GHOSH CONSTRUCTION | 42.89 | 0 | 0 | 80
2877 | HOOGHLY | Electrical | GROUND WATER BASED MARAKHANA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13322 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Marakhana water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | 782/ED | 09/02/2023 | 90 | S.G. TECHNICAL SERVICES | 20.49 | 0 | 0 | 0
2878 | HOOGHLY | Hooghly Division | GROUND WATER BASED MARAKHANA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13322 | New | Material Requisition To Resource Division | 1385/38/Hug | 15/05/2023 | 0 | Resource Division | 12.02 | 0 | 0 | 0
2879 | HOOGHLY | Hooghly Division | GROUND WATER BASED MARAKHANA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13322 | New | Material Requisition To Resource Division | 3057/Hug | 11/10/2023 | 0 | Resource Division | 12.02 | 0 | 0 | 0
2880 | HOOGHLY | Hooghly Division | GROUND WATER BASED MARAKHANA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13322 | New | Material Requisition To Resource Division | 1263/1/Hug | 03/05/2023 | 0 | Resource Division | 41.15 | 0 | 0 | 0
2881 | HOOGHLY | Electrical | GROUND WATER BASED MARAKHANA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13322 | New | Quotation of New Service Connection for Marakhana w/sScheme,Zone-II,PH No-II Block-Khanakul-II Dist-Hooghly under Electrical division,PHE Dte.(SM/13322). Application No-5004325249, Reference Id-503707789 | 350 | 31/07/2024 | 0 | WBSEDCL | 7.6 | 0 | 0 | 0
2882 | HOOGHLY | Electrical | GROUND WATER BASED MARAKHANA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13322 | New | Quotation of New Service Connection for Marakhana w/s Scheme,Zone-II,Ph No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte.(SM/13322) Application No-5004011194 Reference Id-503561404 | 901 | 19/03/2024 | 0 | WBSEDCL | 3.37 | 0 | 0 | 0
2883 | HOOGHLY | Hooghly Division | GROUND WATER BASED MARAKHANA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13322 | New | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 79.33 | 17.9 | 50
2884 | HOOGHLY | Hooghly Division | GROUND WATER BASED MARAKHANA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13322 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0 | 0
2885 | HOOGHLY | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) , SM/14685 | New | Material Requisition To Resource Division | 1234/30/Hug | 28/04/2023 | 0 | Resource Division | 25.45 | 0 | 0 | 0
2886 | HOOGHLY | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) , SM/14685 | New | Material Requisition To Resource Division | 3057/60/Hug | 11/10/2023 | 0 | Resource Division | 13.4 | 0 | 0 | 0
2887 | HOOGHLY | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) , SM/14685 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Selampur water supply scheme, Zone-II, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | 774/ED | 09/02/2023 | 965 | S S ENTERPRISES | 22.09 | 17.9 | 81.01 | 10
2888 | HOOGHLY | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) , SM/14685 | New | Quotation of New Service Connection for Selampur w/s Scheme, Z-II,PH No-I Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/14685) Application No-5004034199 Reference Id-503574970 | 809 | 28/02/2024 | 0 | WBSEDCL | 4.48 | 0 | 0 | 0
2889 | HOOGHLY | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) , SM/14685 | New | Quotation of New Service Connection For Selampur w/s Scheme,Zone-II,PH No-III Block-Goghat-II Dist-Hooghly under Electrical division,PHE Dte.(SM/14685) Application No-5004431262 Reference Id-503764740 | 537 | 28/10/2024 | 0 | WBSEDCL | 4.39 | 0 | 0 | 0
2890 | HOOGHLY | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) , SM/14685 | New | Quotation of New Service Connection for Selampur w/s Scheme, Z-II,PH No-II Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/14685) Application No-5004034192 Reference Id-503574969. | 810 | 28/02/2024 | 0 | WBSEDCL | 4.41 | 0 | 0 | 0
2891 | HOOGHLY | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) , SM/14685 | New | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | 3190/HUG | 31/10/2023 | 609 | M/S PRITI ENTERPRISE | 4251.5 | 230.57 | 45.18 | 30
2892 | HOOGHLY | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) , SM/14685 | New | Sinking of 4 nos. tube-well by (300 X 200 mm) D.R. Rig method at SELAMPUR Z-I, SANTIPUR Z-I, SELAMPUR Z-II and GARMANDARAN Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 725/HUG | 05/03/2024 | 667 | AUXILIARY TUBEWELL DRILLERS | 64.32 | 11.01 | 68.48 | 70
2893 | HOOGHLY | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) , SM/14685 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SELAMPUR PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1166/ED | 14/06/2024 | 474 | S.S. ENTERPRISES | 10.95 | 0 | 0 | 0
2894 | HOOGHLY | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-II) , SM/14685 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 464/HUG | 20/02/2025 | 30 | TECHVISION | 6.59 | 0 | 0 | 0
2895 | HOOGHLY | Hooghly Division | Chak mamrej mini pipe water supply scheme , SM/13590 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-243 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 32.46 | 0 | 0 | 0
2896 | HOOGHLY | Electrical | Chak mamrej mini pipe water supply scheme , SM/13590 | New | Mini Piped Water Supply Scheme. | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0 | 0
2897 | HOOGHLY | Electrical | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15243 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Harit water supply scheme, T.W. No.- I & II, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | 841/ED | 14/02/2023 | 90 | DEBJYOTI BASU | 21.49 | 10.41 | 48.43 | 50
2898 | HOOGHLY | Hooghly Division | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15243 | Augmentation | Material Requisition To Resource Division | 226/5/Hug | 24/01/2023 | 0 | Resource Division | 39.48 | 0 | 0 | 0
2899 | HOOGHLY | Hooghly Division | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15243 | Augmentation | Material Requisition To Resource Division | 1386/51/Hug | 15/05/2023 | 0 | Resource Division | 6.49 | 0 | 0 | 0
2900 | HOOGHLY | Hooghly Division | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15243 | Augmentation | Material Requisition To Resource Division | 1264/1/HUG | 03/05/2023 | 0 | Resource Division | 39.48 | 0 | 0 | 0
2901 | HOOGHLY | Hooghly Division | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15243 | Augmentation | Augmentation of HARIT Piped Water Supply Scheme with Sinking of Tube-Well, LDS, Rising Main, FHTC, construction of switch-rooms , boundary walls& Repairing of Existing O.H.R, Switch Rooms, Boundary walls at different TW site under POLBA-DADPUR Block, District:- Hooghly | 379/HUG | 09/02/2023 | 90 | DAS ENTERPRISE (SAMIR DAS) | 238.76 | 218.37 | 91.46 | 92
2902 | HOOGHLY | Hooghly Division | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15243 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in HARIT GP of POLBA-DADPUR Block | 244/CH | 12/03/2024 | 30 | BASU & SONS | 4.98 | 4.97 | 100 | 75
2903 | HOOGHLY | Hooghly Division | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15243 | Augmentation | Providing FHTC in rest out portion of at Majher Para of Harit PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | 287/CH | 15/03/2024 | 7 | DAS ENTERPRISE (SAMIR DAS) | 0.99 | 0.98 | 100 | 85
2904 | HOOGHLY | Hooghly Division | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15243 | Augmentation | Providing FHTC in rest out portion of at Ichapur of Harit PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | 288/CH | 15/03/2024 | 7 | DAS ENTERPRISE (SAMIR DAS) | 0.82 | 0.79 | 100 | 95
2905 | HOOGHLY | Hooghly Division | AUGMENTATION OF HARIT PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15243 | Augmentation | Providing FHTC in rest out portion of at Kelor Para of Harit PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | 284/CH | 14/03/2024 | 7 | DAS ENTERPRISE (SAMIR DAS) | 0.99 | 0.97 | 100 | 100
2906 | HOOGHLY | Electrical | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly , SM/15247 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gobindanagar water supply scheme, Zone-I, T.W. No. III & IV, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | 3452/ED | 11/08/2023 | 90 | PERFECT AIRCONDITION | 20.49 | 0 | 0 | 0
2907 | HOOGHLY | Hooghly Division | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly , SM/15247 | New | Horizontal Auger boring with water jet system Including Approach Road at GOBINDANAGAR ZONE-I, KUMURSA, KOTA, RAGHUBATI & SUNIA Piped Water Supply Scheme under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. | 3592/HUG | 05/12/2023 | 30 | P. B. ENTERPRISE(PINTU BHADURI) | 7.29 | 7.05 | 100 | 100
2908 | HOOGHLY | Hooghly Division | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly , SM/15247 | New | Material Requisition To Resource Division | 1385/40/Hug | 15/05/2023 | 0 | Resource Division | 11.06 | 0 | 0 | 0
2909 | HOOGHLY | Hooghly Division | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly , SM/15247 | New | Material Requisition To Resource Division | 3057/35/Hug | 11/10/2023 | 0 | Resource Division | 11.06 | 0 | 0 | 0
2910 | HOOGHLY | Hooghly Division | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly , SM/15247 | New | Material Requisition To Resource Division | 1234/22/Hug | 28/04/2023 | 0 | Resource Division | 9.97 | 0 | 0 | 0
2911 | HOOGHLY | Electrical | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly , SM/15247 | New | Quotation Bill for New Service Connection at Gobindanagar W/S. Sch. Z-I, PH-I | 393 | 03/11/2023 | 0 | WBSEDCL | 3.97 | 0 | 0 | 0
2912 | HOOGHLY | Electrical | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly , SM/15247 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gobindanagar water supply scheme, Zone-I, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | 930/ED | 22/02/2023 | 90 | T S CONSTRUCTION | 20.5 | 19.86 | 96.92 | 25
2913 | HOOGHLY | Electrical | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly , SM/15247 | New | Quotation of New Service Connection for Gobindanagar w/s scheme,Zone-I,PH No-II Block-Goghat-I Dist-Hooghly under Electrical Division PHE Dte.(SM/15247) Application No-5004049800, Reference Id-503584072 | 839 | 01/03/2024 | 0 | WBSEDCL | 3.68 | 0 | 0 | 0
2914 | HOOGHLY | Hooghly Division | Gobindanagar (Zone-I) Piped Water Supply Scheme, Block-Goghat-I, District-Hooghly , SM/15247 | New | GOBINDANAGAR (ZONE-I), KOTA, KUMURSA Piped Water Supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-I Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | 1602/HUG | 01/06/2023 | 1035 | P.B. ENTERPRISE (PINTU BHADURI) | 1078.43 | 311.49 | 62.8 | 65
2915 | HOOGHLY | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-I) , SM/15252 | New | Material Requisition To Resource Division | 1234/29/Hug | 28/04/2023 | 0 | Resource Division | 40.15 | 0 | 0 | 0
2916 | HOOGHLY | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-I) , SM/15252 | New | Material Requisition To Resource Division | 3057/48/Hug | 11/10/2023 | 0 | Resource Division | 14.49 | 0 | 0 | 0
2917 | HOOGHLY | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-I) , SM/15252 | New | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of SELAMPUR, BACHHANARI & SAMANTAKHANDA W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3169/HUG | 10/09/2024 | 45 | BALAJI UDDYOG | 48.46 | 0 | 0 | 0
2918 | HOOGHLY | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-I) , SM/15252 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SELAMPUR PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1165/ED | 14/06/2024 | 90 | ANUPAMA ENGINEERING WORKS | 10.75 | 0 | 0 | 0
2919 | HOOGHLY | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-I) , SM/15252 | New | Quotation of New Service Connection for Selampur w/s Scheme,Zone-I, PH No-I Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/15252) Application No-5004151889 Reference Id-503633694 | 95 | 06/05/2024 | 0 | WBSEDCL | 3.94 | 0 | 0 | 0
2920 | HOOGHLY | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-I) , SM/15252 | New | Quotation of New Service Connection for Selampur w/s Scheme,Zone-I,PH No-II,Block-Goghat-II,Dist-Hooghly under Electrical Division,PHE Dte.(SM/15252) Application No-5004294581 Reference Id-503691996 | 312 | 22/07/2024 | 0 | WBSEDCL | 3.33 | 0 | 0 | 0
2921 | HOOGHLY | Electrical | SELAMPUR WATER SUPPLY SCHEME (ZONE-I) , SM/15252 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Selampur water supply scheme, Zone-I, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | 931/ED | 22/02/2023 | 769 | GHOSE ENGINEERING SYNDICATE | 22.1 | 0.46 | 2.09 | 30
2922 | HOOGHLY | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-I) , SM/15252 | New | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | 3190/HUG | 31/10/2023 | 609 | M/S PRITI ENTERPRISE | 4251.5 | 286.56 | 54.57 | 30
2923 | HOOGHLY | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-I) , SM/15252 | New | Sinking of 4 nos. tube-well by (300 X 200 mm) D.R. Rig method at SELAMPUR Z-I, SANTIPUR Z-I, SELAMPUR Z-II and GARMANDARAN Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 725/HUG | 05/03/2024 | 667 | AUXILIARY TUBEWELL DRILLERS | 64.32 | 0 | 0 | 70
2924 | HOOGHLY | Hooghly Division | SELAMPUR WATER SUPPLY SCHEME (ZONE-I) , SM/15252 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 464/HUG | 20/02/2025 | 30 | TECHVISION | 6.59 | 0 | 0 | 0
2925 | HOOGHLY | Electrical | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY , SM/15790 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mayapur (Zone-II) water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 1702/ED | 18/04/2023 | 90 | NUPUR CHANDRA HALDER | 20.8 | 0 | 0 | 0
2926 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY , SM/15790 | New | Material Requisition To Resource Division | 3057/12/Hug | 11/10/2023 | 0 | Resource Division | 6.12 | 0 | 0 | 0
2927 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY , SM/15790 | New | Material Requisition To Resource Division | 1385/57/Hug | 15/05/2023 | 0 | Resource Division | 2.68 | 0 | 0 | 0
2928 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY , SM/15790 | New | Material Requisition To Resource Division | 1234/14/Hug | 28/04/2023 | 0 | Resource Division | 25.34 | 0 | 0 | 0
2929 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY , SM/15790 | New | MAYAPUR ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] | 1618/hug | 02/06/2023 | 270 | M/S RAJKUMAR KHAN | 246.71 | 56.24 | 22.8 | 20
2930 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY , SM/15790 | New | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of KRISHNANAGAR Zone-II , MAYAPUR , TIROL Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3530/HUG | 22/10/2024 | 45 | PADMA ENGINEERING CO. | 47.5 | 0 | 0 | 0
2931 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY , SM/15790 | New | Laying of Additional Pipeline for MAYAPUR Piped Water Supply Scheme under ARAMBAGH SUB DIVISION Block Arambagh. | 3439/HUG | 03/10/2024 | 30 | DILIP KUMAR GHOSH | 54.57 | 0 | 0 | 0
2932 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY , SM/15790 | New | MAYAPUR ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] | 1618/Hug | 02/06/2023 | 270 | M/S RAJKUMAR KHAN | 246.71 | 13.25 | 100 | 15
2933 | HOOGHLY | Electrical | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY , SM/15790 | New | Quotation for New Service Connection at Mayapur W/S. Sch. Z=II | 610 | 04/01/2024 | 0 | WBSEDCL | 6.44 | 0 | 0 | 0
2934 | HOOGHLY | Hooghly Division | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/15889 | New | Material Requisition To Resource Division | 902/6/Hug | 27/03/2023 | 0 | Resource Division | 7.76 | 0 | 0 | 0
2935 | HOOGHLY | Hooghly Division | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/15889 | New | Material Requisition To Resource Division | 3058/20/Hug | 11/10/2023 | 0 | Resource Division | 15.5 | 0 | 0 | 0
2936 | HOOGHLY | Hooghly Division | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/15889 | New | Material Requisition To Resource Division | 1235/6/Hug | 28/04/2023 | 0 | Resource Division | 36.75 | 0 | 0 | 0
2937 | HOOGHLY | Hooghly Division | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/15889 | New | SIBRAMBATI ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of Chandannagar Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | 2296/HUG | 03/08/2023 | 270 | M/S BISWAS CONSTRUCTION | 551.83 | 139.35 | 25.25 | 40
2938 | HOOGHLY | Hooghly Division | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/15889 | New | Horizontal Auger boring with water jet system Including Approach Road at SIBRAMBATI ZONE-I Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | 3232/HUG | 03/11/2023 | 30 | M/S BISWAS CONSTRUCTION | 20.63 | 20.63 | 100 | 100
2939 | HOOGHLY | Hooghly Division | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/15889 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sibrambati (Zone-I) Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-A). | 152/Chan | 16/02/2024 | 15 | TECHVISION | 0.84 | 0.84 | 100 | 98
2940 | HOOGHLY | Hooghly Division | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/15889 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sibrambati (Zone-I) Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-C). | 154/Chan | 16/02/2024 | 15 | TECHVISION | 0.96 | 0.96 | 100 | 98
2941 | HOOGHLY | Hooghly Division | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/15889 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sibrambati (Zone-I) Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-B). | 153/Chan | 16/02/2024 | 15 | TECHVISION | 0.73 | 0.73 | 100 | 98
2942 | HOOGHLY | Hooghly Division | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/15889 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sibrambati (Zone-I) Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-D). | 155/Chan | 16/02/2024 | 15 | TECHVISION | 0.78 | 0.78 | 100 | 98
2943 | HOOGHLY | Hooghly Division | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/15889 | New | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Shibrambati (Zone-1) 1st T/W site & Shibrambati (Zone-1) 2nd T/W site under Chandannagar Sub-Division PHE Dte. | 926/Chan | 05/11/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 0 | 100
2944 | HOOGHLY | Electrical | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/15889 | New | Quotation for new service connection at Sibrambati water supply Scheme [SM/15889],Zone - I, T/W No. - I, Block - Singur, under Singur CCC, WBSEDCL, Ref. Id. - 503588850, Dt. - 11-03-2024, Application No. - 5004057590 | 882 | 13/03/2024 | 0 | WBSEDCL | 5.7 | 0 | 0 | 0
2945 | HOOGHLY | Electrical | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/15889 | New | Quotation for new service connection at Sibrambati W/S Sch., (Zone - I), T/W No. - II,[SM/15889] Block - Singur under Singur CCC, WBSEDCL, Ref. Id. - 503591781, Dt. - 12-03-2024, Application No. - 5004061900 | 893 | 18/03/2024 | 0 | WBSEDCL | 6.69 | 0 | 0 | 0
2946 | HOOGHLY | Electrical | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly , SM/15889 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sibrambati water supply scheme, Zone-I, T.W. No. I & II, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | 4695/ED | 08/12/2023 | 540 | A.K. ENTERPRISE | 22.43 | 16.25 | 72.43 | 70
2947 | HOOGHLY | Hooghly Division | Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambag Block , SM/15807 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | 1471/HUG | 19/05/2023 | 30 | S.B. ASSOCIATES | 11.81 | 0 | 0 | 0
2948 | HOOGHLY | Hooghly Division | Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambag Block , SM/15807 | Augmentation | Material Requisition To Resource Division | 127/19/Hug | 13/01/2023 | 0 | Resource Division | 11.5 | 0 | 0 | 0
2949 | HOOGHLY | Hooghly Division | Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambag Block , SM/15807 | Augmentation | Material Requisition To Resource Division | 1263/10/Hug | 03/05/2023 | 0 | Resource Division | 11.38 | 0 | 0 | 0
2950 | HOOGHLY | Hooghly Division | Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambag Block , SM/15807 | Augmentation | Sinking of Two Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at PRATAPNAGAR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | 2862/HUG | 20/09/2023 | 360 | B.R SUPPLIERS | 22.63 | 11.04 | 48.77 | 60
2951 | HOOGHLY | Electrical | Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambag Block , SM/15807 | Augmentation | Quotation of New Service Connection for Pratapnagar w/s Scheme,PH No-3, Block-Arambag, Dist-Hooghly under Electrical division,PHE Dte.(SM/15807) Application No-5004254598 Reference Id-503673919 | 248 | 24/06/2024 | 0 | WBSEDCL | 7.9 | 0 | 0 | 0
2952 | HOOGHLY | Electrical | Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambag Block , SM/15807 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Pratapnagar water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 1698/ED | 18/04/2023 | 989 | GOENKA ENTERPRISE | 20.5 | 15.17 | 74 | 10
2953 | HOOGHLY | Hooghly Division | IMPROVEMENT OF KOLA W/S SCHEME BY LAYING OF HDPE PIPELINE BY HDD PROCESS UNDER CHINSURAH SUB DIVISION UNDER CHINSURAH MAGRA BLOCK , SM/15901 | Augmentation | Laying of HDPE Pipe by HDD Process from Spandan Electronics at Magra Ganj towards Natungram Shib Manidr via Rathtala Suriya Sangha Club at Mogra-Gurap (23 No.) Road within KOLA PWSS, under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 1161/HUG | 20/04/2023 | 45 | MAA TARA CONSTRUCTION | 96.46 | 76.91 | 79.73 | 50
2954 | HOOGHLY | Electrical | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/15792 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Arunda (Zone-II) water supply scheme, T.W. No. I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | 1495/ED | 28/03/2023 | 90 | BARISAL TRADING CO. | 21.49 | 0 | 0 | 0
2955 | HOOGHLY | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/15792 | New | Material Requisition To Resource Division | 1385/3/Hug | 15/05/2023 | 0 | Resource Division | 12.79 | 0 | 0 | 0
2956 | HOOGHLY | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/15792 | New | Material Requisition To Resource Division | 3057/58/Hug | 11/10/2023 | 0 | Resource Division | 11.7 | 0 | 0 | 0
2957 | HOOGHLY | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/15792 | New | Material Requisition To Resource Division | 1234/33/Hug | 28/04/2023 | 0 | Resource Division | 25.46 | 0 | 0 | 0
2958 | HOOGHLY | Electrical | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/15792 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARUNDA PIPED W/S SCHEME, Zone - II, T.W. No. V, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1176/ED | 14/06/2024 | 90 | P.K. ENTERPRISE | 10.72 | 0 | 0 | 0
2959 | HOOGHLY | Electrical | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/15792 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARUNDA PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1174/ED | 14/06/2024 | 90 | BARISAL TRADING CO. | 10.74 | 0 | 0 | 0
2960 | HOOGHLY | Electrical | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/15792 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARUNDA PIPED W/S SCHEME, Zone - II, T.W. No. IV, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1175/ED | 14/06/2024 | 90 | S.M. ELECTRICALS | 10.74 | 0 | 0 | 0
2961 | HOOGHLY | Electrical | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/15792 | New | Quotation of New Service Connection for Arunda w/s Scheme,Zone-II, PH No-I Block-Khanakul-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/15792) Application No-5004460466 Reference Id-503787366 | 628 | 18/12/2024 | 0 | WBSEDCL | 5.68 | 0 | 0 | 0
2962 | HOOGHLY | Electrical | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/15792 | New | Quotation of New Service Connection for Arunda w/s Scheme,Zone-II, PH No-III Block-Khanakul-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/15792) Application No-5004460458 Reference Id-503787369 | BP-24-25-579 | 19/11/2024 | 0 | WBSEDCL | 4.06 | 0 | 0 | 0
2963 | HOOGHLY | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/15792 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) KHANAKUL PWSS (Z-I)- 1 no?s (2) PURBATHAKURANICHAK PWSS (Z-I)-2 no?s (3) ARUNDA PWSS (Z-I)- 4 no?s (4) ARUNDA PWSS (Z-II)- 5 no?s (5) POL PWSS ? 2no?s | 1152/Arg | 10/12/2024 | 31 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
2964 | HOOGHLY | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/15792 | New | ARUNDA ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANAKUL-I Block of Arambag Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | 2280/HUG | 03/08/2023 | 270 | M/S. NANDY ENTERPRISE | 501.51 | 0 | 0 | 25
2965 | HOOGHLY | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY , SM/15792 | New | Sinking of 4 (Four) Nos tube well (250 mm X 150 mm) with supply of PVC Pipe and strainer and having depth upto 180 M at CHINRA Z-II and ARUNDA Z-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 726/HUG | 05/03/2024 | 366 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 39.06 | 9.57 | 32.68 | 75
2966 | HOOGHLY | Hooghly Division | BHANDARDAHA PIPED WATER SUPPLY SCHEME , SM/18096 | New | Material Requisition To Resource Division | 3058/10/Hug | 11/10/2023 | 0 | Resource Division | 22.67 | 0 | 0 | 0
2967 | HOOGHLY | Electrical | BHANDARDAHA PIPED WATER SUPPLY SCHEME , SM/18096 | New | Quotation Bill for New Service Connection at Bhandardaha W/S. Sch. TW-I | 408 | 09/11/2023 | 0 | WBSEDCL | 2.37 | 0 | 0 | 0
2968 | HOOGHLY | Hooghly Division | BHANDARDAHA PIPED WATER SUPPLY SCHEME , SM/18096 | New | BHANDARDAHA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. Block Singur, District:- Hooghly [NEW SCHEME] | 1518/HUG | 23/05/2023 | 90 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 91.84 | 89.89 | 100 | 100
2969 | HOOGHLY | Hooghly Division | BHANDARDAHA PIPED WATER SUPPLY SCHEME , SM/18096 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Bhandardaha Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-A). | 412/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.73 | 0.73 | 100 | 100
2970 | HOOGHLY | Hooghly Division | BHANDARDAHA PIPED WATER SUPPLY SCHEME , SM/18096 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Bhandardaha Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-B). | 413/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.84 | 0.84 | 100 | 100
2971 | HOOGHLY | Hooghly Division | BHANDARDAHA PIPED WATER SUPPLY SCHEME , SM/18096 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Bhandardaha Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-C) | 414/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.78 | 0.78 | 100 | 100
2972 | HOOGHLY | Hooghly Division | KALACHHARA PIPED WATER SUPPLY SCHEME , SM/18100 | New | Material Requisition To Resource Division | 1383/8/Hug | 15/05/2023 | 0 | Resource Division | 1.8 | 0 | 0 | 0
2973 | HOOGHLY | Electrical | KALACHHARA PIPED WATER SUPPLY SCHEME , SM/18100 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kalachhara water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | 1926/ED | 15/05/2023 | 90 | S.G. TECHNICAL SERVICES | 22.6 | 10.77 | 47.65 | 25
2974 | HOOGHLY | Electrical | KALACHHARA PIPED WATER SUPPLY SCHEME , SM/18100 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Balipur water supply scheme, T.W. No. III & IV, Block: Khanakul-I District: Hooghly under Electrical Division, PHE Dte. | 331/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 20.85 | 0 | 0 | 0
2975 | HOOGHLY | Hooghly Division | KALACHHARA PIPED WATER SUPPLY SCHEME , SM/18100 | New | KALACHHARA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. Block Singur, District:- Hooghly [NEW SCHEME] | 1484/HUG | 19/05/2023 | 425 | CONCORD PROJECTS PRIVATE LIMITED | 82.76 | 79.78 | 100 | 15
2976 | HOOGHLY | Hooghly Division | KALACHHARA PIPED WATER SUPPLY SCHEME , SM/18100 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Rajballavbati PWSS, Kalachara PWSS, Paschim Narayanpur PWSS, Mahistikari Z-I PWSS, Mahistikari Z-II PWSS, Parjana PWSS) | 305/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 50 | 100
2977 | HOOGHLY | Hooghly Division | KALACHHARA PIPED WATER SUPPLY SCHEME , SM/18100 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Kalachara Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-A). | 416/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.93 | 0.93 | 100 | 100
2978 | HOOGHLY | Hooghly Division | KALACHHARA PIPED WATER SUPPLY SCHEME , SM/18100 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Kalachara Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-B). | 417/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.84 | 0.84 | 100 | 100
2979 | HOOGHLY | Hooghly Division | KALACHHARA PIPED WATER SUPPLY SCHEME , SM/18100 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Kalachara Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-C). | 419/Chan | 09/04/2024 | 15 | ENVIROTECH SOLUTIONS | 0.78 | 0.78 | 100 | 100
2980 | HOOGHLY | Electrical | KALACHHARA PIPED WATER SUPPLY SCHEME , SM/18100 | New | Quotation for New Service Connection at Kalachara W/S. Sch. TW-I | 649 | 10/01/2024 | 0 | WBSEDCL | 1.47 | 0 | 0 | 0
2981 | HOOGHLY | Hooghly Division | NAWPARA PIPED WATER SUPPLY SCHEME , SM/18241 | New | Sinking of Five Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ATISARA, NANDA, NOWPARA, BASUBATI & ASTARA PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | 878/HUG | 27/03/2023 | 45 | MS D.PALIT AND CO. | 62.24 | 12.32 | 98.95 | 100
2982 | HOOGHLY | Hooghly Division | NAWPARA PIPED WATER SUPPLY SCHEME , SM/18241 | New | Material Requisition To Resource Division | 109/4/Hug | 10/01/2023 | 0 | Resource Division | 52 | 0 | 0 | 0
2983 | HOOGHLY | Hooghly Division | NAWPARA PIPED WATER SUPPLY SCHEME , SM/18241 | New | Material Requisition To Resource Division | 3058/6/Hug | 11/10/2023 | 0 | Resource Division | 17.71 | 0 | 0 | 0
2984 | HOOGHLY | Electrical | NAWPARA PIPED WATER SUPPLY SCHEME , SM/18241 | New | Quotation Bill for New Service Connection at Nawpara W/S. Sch. TW-II | 547 | 19/12/2023 | 0 | WBSEDCL | 15.9 | 0 | 0 | 0
2985 | HOOGHLY | Electrical | NAWPARA PIPED WATER SUPPLY SCHEME , SM/18241 | New | Quotation for service connection for Nawpara W/S Sch. , T/W -I, Block - Singur | 111 | 19/07/2023 | 0 | WBSEDCL | 2.63 | 0 | 0 | 0
2986 | HOOGHLY | Hooghly Division | NAWPARA PIPED WATER SUPPLY SCHEME , SM/18241 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at ATISARA, NANDA, NAWPARA,BASUBATI & ASTARA W/S Scheme underChandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | 1818/HUG | 22/06/2023 | 45 | OSMAN SEKH | 80.85 | 16.41 | 100 | 100
2987 | HOOGHLY | Electrical | NAWPARA PIPED WATER SUPPLY SCHEME , SM/18241 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nawpara water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | 3063/ED | 12/07/2023 | 90 | POLYCON ENGINEERS | 21.71 | 21.69 | 100 | 92
2988 | HOOGHLY | Hooghly Division | NAWPARA PIPED WATER SUPPLY SCHEME , SM/18241 | New | Construction of 400 cum capacity OHR with 20 mtr. staging height including Soil Investigation work, Laying Distribution System, Rising Main & Interconnection between O.H.R, TW No-I & II, Construction of 1 No 5.4M X 3.6M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at Head Work Site, Construction of 1 No 3.6M x 3.0M Switch Room with Sanitary & Water Supply arrangement & Boundary Wall at 2nd T/W Site including Providing FHTC in NAWPARA Water Supply Scheme at SINGUR Block under Chandannagar Sub- Division, PHE Dte. | 2294/HUG | 03/08/2023 | 785 | DIPTI TRADERS | 757.77 | 598.38 | 78.97 | 87
2989 | HOOGHLY | Hooghly Division | NAWPARA PIPED WATER SUPPLY SCHEME , SM/18241 | New | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for NAWPARA Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 3471/HUG | 04/10/2024 | 454 | DIPTI TRADERS | 26.55 | 0 | 0 | 60
2990 | HOOGHLY | Hooghly Division | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS , SM/17289 | New | Material Requisition To Resource Division | 902/2/Hug | 27/03/2023 | 0 | Resource Division | 10.56 | 0 | 0 | 0
2991 | HOOGHLY | Hooghly Division | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS , SM/17289 | New | Material Requisition To Resource Division | 1235/9/Hug | 28/04/2023 | 0 | Resource Division | 13.03 | 0 | 0 | 0
2992 | HOOGHLY | Electrical | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS , SM/17289 | New | Quotation for new service connection at Boinchipota W/S Sch,, Zone - I. T/W No. - II | 382 | 25/10/2023 | 0 | WBSEDCL | 2.44 | 0 | 0 | 0
2993 | HOOGHLY | Electrical | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS , SM/17289 | New | Quotation for new service connection at Boinchipota W/s sch. , T/W - I, Block- Singur, Dist. -hooghly | 110 | 19/07/2023 | 0 | WBSEDCL | 3.99 | 0 | 0 | 0
2994 | HOOGHLY | Hooghly Division | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS , SM/17289 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte. (Baichipota Z-I PWSS, Baichipota Z-II PWSS, Kharda Apurbapur PWSS, Baruipara PWSS, Sripatipur PWSS, Paschim Gopinathpur PWSS) | 304/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 100
2995 | HOOGHLY | Electrical | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS , SM/17289 | New | Additional Quotation for new service connection at Bainchipota[SM/17289] W/S Sch., Zone - I, T/W No. - II under Nasibpur CCC, WBSEDCL, Ref. Id. - 860298080, Dt. - 23/04/2024, Application ID. - 100000106100 | 98 | 06/05/2024 | 0 | WBSEDCL | 0.25 | 0 | 0 | 0
2996 | HOOGHLY | Hooghly Division | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS , SM/17289 | New | BAINCHIPOTA (ZONE-I) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block, District:- Hooghly [NEW SCHEME] | 1041/Hug | 10/04/2023 | 792 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 491.76 | 429.8 | 87.4 | 60
2997 | HOOGHLY | Electrical | GROUND WATER BASED BAINCHIPOTA(ZONE-I) PWSS , SM/17289 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bainchipota water supply scheme, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | 1797/ED | 24/04/2023 | 360 | MITRA ASSOCIATES | 20.2 | 19.88 | 98.64 | 97
2998 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAHISGOT (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18595 | New | Material Requisition To Resource Division | 3057/29/Hug | 11/10/2023 | 0 | Resource Division | 16.38 | 0 | 0 | 0
2999 | HOOGHLY | Electrical | GROUND WATER BASED MAHISGOT (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18595 | New | Quotation for new service connection charge at Mohisgot PWSS, Zone-I, TW - I | 457 | 01/12/2023 | 0 | WBSEDCL | 5.39 | 0 | 0 | 0
3000 | HOOGHLY | Electrical | GROUND WATER BASED MAHISGOT (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18595 | New | Quotation for new service connection charge at Mohisgot PWSS, Zone-I, TW - II | 458 | 01/12/2023 | 0 | WBSEDCL | 6.15 | 0 | 0 | 0
3001 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAHISGOT (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18595 | New | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at MAHISHGOT ZONE I (2Nos.), UDAYPUR (2Nos.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3437/HUG | 03/10/2024 | 90 | SAHA CONSTRUCTION AND CO | 47.26 | 0 | 0 | 0
3002 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAHISGOT (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18595 | New | MAHISGOT (ZONE-I), MAHISGOT (ZONE-II), POL, RADHABALLAVPUR (ZONE-I), UDAYPUR, UDNA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte | 3139/HUG | 16/10/2023 | 808 | MACKINTOSH BURN LIMITED | 3480.01 | 359.39 | 63.72 | 45
3003 | HOOGHLY | Hooghly Division | GROUND WATER BASED MAHISGOT (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18595 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0 | 0
3004 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | Providing 200 nos Functional Household Tap Connection (FHTC) within the command area of Rajhat Zone-I Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 2202/Hug | 14/12/2021 | 20 | GHOSH CONSTRUCTION | 13.02 | 13.02 | 100 | 0
3005 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | Providing 500 nos Functional Household Tap Connection (FHTC) within the command area of RAJHAT & HARAL ZONE-I Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 456/Hug | 10/03/2022 | 30 | M/S S.C CIVIL ENTERPRISE | 31.96 | 31.4 | 98.27 | 0
3006 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR RAJHAT W/S SCHEME (Z-II) POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 303/ CDD | 27/04/2022 | 30 | C.M. ENTERPRISE | 14.67 | 2.21 | 100 | 0
3007 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | REPAIRING OF PTO AND OTHER FOR RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. | 214/CMSD-I(D) | 09/11/2021 | 15 | PADMA ENGINEERING & CO. | 4.52 | 0.29 | 100 | 0
3008 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | PROVIDING TUBE WELL MATERIALS OF 200MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN POLBA DADPUR BLOCK AT RAJHAT (ZONE-II) W/S SCHEME UNDER CDD, PHE DTE. | 90/ CMSD-I (D) | 19/04/2022 | 15 | C.M. ENTERPRISE | 5 | 4.07 | 100 | 0
3009 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | PROVIDING TUBE WELL MATERIALS OF 300MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN POLBA DADPUR BLOCK AT RAJHAT (ZONE-I) W/S SCHEME UNDER CDD, PHE DTE. | 87/CMSD-I (D) | 18/04/2022 | 15 | C.M. ENTERPRISE | 4.99 | 4.55 | 100 | 0
3010 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300 MM X 200 MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR RAJHAT W/S SCH (Z-II), POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 303/CDD | 27/04/2022 | 30 | C.M. ENTERPRISE | 14.67 | 3.45 | 100 | 0
3011 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | PROVIDING TUBE WELL MATERIALS OF 300MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN POLBA DADPUR BLOCK AT RAJHAT (ZONE-II) W/S SCHEME UNDER CDD, PHE DTE. | 89/CMSD-I (D) | 19/04/2022 | 15 | C.M. ENTERPRISE | 4.99 | 4.99 | 100 | 0
3012 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | PROVIDING TUBE WELL MATERIALS OF 200MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELLIN POLBA DADPUR BLOCK AT RAJHAT (ZONE-I) W/S SCHEME UNDER CDD, PHE DTE. | 88/CMSD-I (D) | 18/04/2022 | 15 | C.M. ENTERPRISE | 5 | 4.69 | 100 | 0
3013 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | PROVIDING TUBE WELL MATERIALS, (300MM DIA) CONFORMING TO IS: 12818:2010 AND OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJHAT (Z-I) PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 476/CMSD-II | 11/10/2022 | 7 | TAMAL ENTERPRISE | 0.53 | 0.51 | 100 | 0
3014 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJHAT (Z-I), POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 138/S&WSD | 12/08/2022 | 15 | TAMAL ENTERPRISE | 5 | 4.55 | 100 | 0
3015 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | SUPPLY & DELIVERY OF CONSUMABLES AND OTHERS WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJHAT (Z-I) PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 139/S&WSD | 12/08/2022 | 15 | DEY ENTERPRISE | 4.99 | 2.83 | 100 | 0
3016 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT RAJHAT (Z-I) PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 137/S&WSD | 12/08/2022 | 15 | TAMAL ENTERPRISE | 3.92 | 3.74 | 100 | 0
3017 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | SUPPLY & DELIVERY OF CONSUMBLES AND OTHERS WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJHAT (Z-II) PWSS, POLBA DADPUR BLOCK, HOOGHLT DISTRICT UNDER CDD, PHE DTE. | 141/S&WSD | 12/08/2022 | 15 | M/S P P ELECTRICALS | 4.98 | 3.69 | 100 | 0
3018 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT RAJHAT (Z-II) PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 140/S&WSD | 12/08/2022 | 15 | M/S P P ELECTRICALS | 3.91 | 3.8 | 100 | 0
3019 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | PROCVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJHAT (Z-II) PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 142/S&WSD | 12/08/2022 | 15 | M/S P P ELECTRICALS | 5 | 4.78 | 100 | 0
3020 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | PROVIDING DRILLING CREWS AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS. DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR RAJHAT W/S SCHEME (Z-I) POLBA DADPUR BLOCK HOOGHLY DISTRICT, CDD, PHE DTE. | 301/CDD | 27/04/2022 | 30 | C.M. ENTERPRISE | 14.67 | 5.74 | 100 | 0
3021 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | Providing 1480 nos Functional Household Tap Connection (FHTC) within the command area of Rajhat (Zone-II) Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 1676/Hug | 13/09/2021 | 40 | M/S BUILDWELL | 59.06 | 27.65 | 93.63 | 0
3022 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | Providing 1480 nos Functional Household Tap Connection (FHTC) within the command area of Rajhat (Zone-II) Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 1676/HUG | 13/09/2021 | 40 | M/S BUILDWELL | 59.06 | 31.4 | 100 | 100
3023 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | Construction of Boundary Wall & Pathway Development of Rajhat(Z-I) at H/W Site W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | 462/CH | 31/05/2022 | 40 | S. G. ENTERPRISE | 3.36 | 0 | 0 | 0
3024 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-III & ABOVE) (NON AC) HIVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE CALCUTTA MECHANICAL SUB DIVISION -I (D), PHE DTE. | 483/CMSD-I | 23/09/2022 | 10 | SUJATA BHOWMICK | 0.86 | 1.69 | 100 | 0
3025 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-III & ABOVE) (NON AC) HIVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE CALCUTTA MECHANICAL SUB DIVISION -I (D), PHE DTE. | 483/CMSD-I (RA-VI & F) | 23/09/2022 | 15 | SUJATA BHOWMICK | 0.39 | 0.39 | 100 | 0
3026 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of RAJHAT Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 1509/Hug | 22/07/2022 | 20 | GHOSH CONSTRUCTION | 20.38 | 19.74 | 100 | 100
3027 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09772 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of different PWSS under POLBA-DADPUR Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | 2431/HUG | 11/08/2023 | 30 | DILIP KUMAR GHOSH | 42.76 | 41.91 | 100 | 95
3028 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR BALAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18932 | Augmentation | Construction of 5 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at SRIPUR BALAGARH (1No.), NATUNCHAR KRISHNABATI (2Nos.), ITAGARH (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3234/HUG | 06/11/2023 | 60 | RAJDEEP CONSTRUCTION | 59 | 0 | 0 | 0
3029 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF SRIPUR BALAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18932 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF SRIPUR BALAGARH PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4483/ED | 23/11/2023 | 90 | M/S A.K BANERJEE | 21.49 | 0 | 0 | 0
3030 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR BALAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18932 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at SRIPUR BALAGARH (1No.), NATUNCHAR KRISHNABATI (2Nos.), ITAGARH (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3357/HUG | 21/11/2023 | 90 | B.K ENTERPRISE | 88.58 | 14.86 | 83.87 | 60
3031 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR BALAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18932 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under BALAGARH Block of Chinsurah Sub Division under Hooghly Division PHE Dte. | 927/CH | 05/11/2024 | 5 | MAA BUNAMATA ENTERPRISE | 3.7 | 0.98 | 20.94 | 90
3032 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR BALAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18932 | Augmentation | Special Repairing, maintenance work of damaged R.C.C. Elevated Resovoir, Switch Room & Boundary wall of SRIPUR BALAGARH Water Supply Scheme under Chinsurah Sub - Division, P.H.E. Dte., Hooghly | 3678/HUG | 13/11/2024 | 160 | DIPTI TRADERS | 29.54 | 0 | 0 | 100
3033 | HOOGHLY | Hooghly Division | Augmentation of Balipur Water Supply Scheme , SM/18770 | Augmentation | Material Requisition To Resource Division | 79/17/Hug | 06/01/2023 | 0 | Resource Division | 56.05 | 0 | 0 | 0
3034 | HOOGHLY | Electrical | Augmentation of Balipur Water Supply Scheme , SM/18770 | Augmentation | Quotation of New Service Connection for Balipur w/s scheme,zone-I,TW no-3, Block-khanakul-I,Dist-Hooghly under Electrical Division PHE Dte | 297 | 21/09/2023 | 0 | WBSEDCL | 10.61 | 0 | 0 | 0
3035 | HOOGHLY | Electrical | Augmentation of Balipur Water Supply Scheme , SM/18770 | Augmentation | Quotation of New Service Connection for Balipur w/s Scheme, Zone-I,TW No-III Block-Khanakul-I,Dist-Hooghly under Electrical Division PHE Dte. | 232 | 01/09/2023 | 0 | WBSEDCL | 3.1 | 0 | 0 | 0
3036 | HOOGHLY | Hooghly Division | Augmentation of Balipur Water Supply Scheme , SM/18770 | Augmentation | Augmentation of BALIPUR ZONE-I(A) Piped Water Supply Scheme with LDS, FHTC, Repairing of Existing O.H.R, Switch Rooms, Boundary walls at different TW site, under KHANAKUL-I Block, District:- Hooghly. | 2600/HUG | 29/08/2023 | 90 | M/S R K ENTERPRISE | 267.18 | 101.47 | 37.98 | 55
3037 | HOOGHLY | Electrical | Augmentation of Balipur Water Supply Scheme , SM/18770 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Balipur water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | 3613/ED | 29/08/2023 | 90 | PURUSHOTTAM ENTERPRISE | 21.72 | 18.17 | 83.68 | 30
3038 | HOOGHLY | Hooghly Division | Augmentation of Balipur Water Supply Scheme , SM/18770 | Augmentation | Sinking of Tube-Well, Laying Distribution System, Laying Rising Main, Providing FHTC, Construction of Switch-Rooms & Boundary Walls at different TW site For Augmentation of BALIPUR ZONE-I(B) under Arambagh SubDivision of Hooghly Division P.H.E Dte. Block- Khanakul-I, District:- Hooghly | 2591/HUG | 28/08/2023 | 90 | M/S R.M. CONSTRUCTION | 308.46 | 148.3 | 48.08 | 45
3039 | HOOGHLY | Electrical | Augmentation of Balipur Water Supply Scheme , SM/18770 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Balipur water supply scheme, T.W. No. III & IV, Block: Khanakul-I District: Hooghly under Electrical Division, PHE Dte. | 331/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 20.85 | 0 | 0 | 0
3040 | HOOGHLY | Hooghly Division | Augmentation of Balipur Water Supply Scheme , SM/18770 | Augmentation | Augmentation of BALIPUR ZONE-II Piped Water Supply Scheme with LDS, FHTC, Repairing of Switch Rooms, Boundary walls at different TW site, under Hooghly Division P.H.E Dte.Block- KHANAKUL-I , District:- Hooghly | 2597/HUG | 29/08/2023 | 630 | DHIRENDRA ENGINEERING & CONSTRUCTION | 172.47 | 133.75 | 77.55 | 75
3041 | HOOGHLY | Hooghly Division | Augmentation of Balipur Water Supply Scheme , SM/18770 | Augmentation | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for AUGMENTATION Of BALIPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 1479/HUG | 10/06/2025 | 45 | TANISA ENTERPRISE | 26.56 | 0 | 0 | 0
3042 | HOOGHLY | Hooghly Division | Augmentation of Balipur Water Supply Scheme , SM/18770 | Augmentation | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for Augmentation of BALIPUR Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. | 1480/HUG | 10/06/2025 | 60 | DAS ENTERPRISE (SAMIR DAS) | 52.97 | 0 | 0 | 0
3043 | HOOGHLY | Hooghly Division | Augmentation of Balipur Water Supply Scheme , SM/18770 | Augmentation | Sinking of 1 No. Replacement tube-well at Balipur Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 2309/HUG | 02/09/2025 | 30 | OSMAN SEKH | 15.48 | 0 | 0 | 0
3044 | HOOGHLY | Hooghly Division | GROUND WATER BASED PURBBA KRISHNAPUR PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17625 | New | Material Requisition To Resource Division | 1385/35/Hug | 15/05/2023 | 0 | Resource Division | 8.34 | 0 | 0 | 0
3045 | HOOGHLY | Hooghly Division | GROUND WATER BASED PURBBA KRISHNAPUR PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17625 | New | Material Requisition To Resource Division | 1234/20/Hug | 28/04/2023 | 0 | Resource Division | 40.63 | 0 | 0 | 0
3046 | HOOGHLY | Hooghly Division | GROUND WATER BASED PURBBA KRISHNAPUR PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17625 | New | Material Requisition To Resource Division | 3057/31/Hug | 11/10/2023 | 0 | Resource Division | 8.34 | 0 | 0 | 0
3047 | HOOGHLY | Hooghly Division | GROUND WATER BASED PURBBA KRISHNAPUR PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17625 | New | PURBBA KRISHNAPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under ARAMBAGH SUB-DIVISION, Block-ARAMBAGH, District:- Hooghly [NEW SCHEME] | 1682/HUG | 08/06/2023 | 270 | M/S R K ENTERPRISE | 442.41 | 71.31 | 16.12 | 10
3048 | HOOGHLY | Electrical | GROUND WATER BASED PURBBA KRISHNAPUR PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17625 | New | Quotation of New Service Connection for Purba Krishnapur w/s Scheme, PH No-II,Block-Arambag, Dist-Hooghly under Electrical Division,PHE Dte.(SM/17625) Application No-5004208366 Reference Id-503655425. | 203 | 10/06/2024 | 0 | WBSEDCL | 3.71 | 0 | 0 | 0
3049 | HOOGHLY | Electrical | GROUND WATER BASED PURBBA KRISHNAPUR PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17625 | New | Quotation of New Service Connection for Purba Krishnapur w/s Scheme, PH No-I,Block-Arambag, Dist-Hooghly under Electrical Division,PHE Dte.(SM/17625) Application No-5004208398 Reference Id-503655423. | 202 | 10/06/2024 | 0 | WBSEDCL | 4.86 | 0 | 0 | 0
3050 | HOOGHLY | Electrical | GROUND WATER BASED PURBBA KRISHNAPUR PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/17625 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Purbba Krishnapur water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 1730/ED | 19/04/2023 | 804 | CINZANO | 20.96 | 0 | 0 | 50
3051 | HOOGHLY | Hooghly Division | GROUND BASED PWSS FOR NASIBPUR , SM/17627 | New | Material Requisition To Resource Division | 902/5/Hug | 27/03/2023 | 0 | Resource Division | 15.17 | 0 | 0 | 0
3052 | HOOGHLY | Hooghly Division | GROUND BASED PWSS FOR NASIBPUR , SM/17627 | New | Material Requisition To Resource Division | 1235/2/Hug | 28/04/2023 | 0 | Resource Division | 69.72 | 0 | 0 | 0
3053 | HOOGHLY | Hooghly Division | GROUND BASED PWSS FOR NASIBPUR , SM/17627 | New | Material Requisition To Resource Division | 1383/26/Hug | 15/05/2023 | 0 | Resource Division | 15.17 | 0 | 0 | 0
3054 | HOOGHLY | Hooghly Division | GROUND BASED PWSS FOR NASIBPUR , SM/17627 | New | Material Requisition To Resource Division | 3058/13/Hug | 11/10/2023 | 0 | Resource Division | 15.17 | 0 | 0 | 0
3055 | HOOGHLY | Electrical | GROUND BASED PWSS FOR NASIBPUR , SM/17627 | New | Quotation for new service connection at Nasibpur W/s Sch.,H/W Site(T/W No. - I), Dist. - Hooghly | 89 | 12/07/2023 | 0 | WBSEDCL | 3.56 | 0 | 0 | 0
3056 | HOOGHLY | Electrical | GROUND BASED PWSS FOR NASIBPUR , SM/17627 | New | Quotation for new service connection charge at Nasibpur PWSS, TW - II | 527 | 14/12/2023 | 0 | WBSEDCL | 0.73 | 0 | 0 | 0
3057 | HOOGHLY | Electrical | GROUND BASED PWSS FOR NASIBPUR , SM/17627 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nasibpur water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | 1729/ED | 19/04/2023 | 90 | ANIK & CO. | 20.5 | 9.97 | 48.64 | 45
3058 | HOOGHLY | Hooghly Division | GROUND BASED PWSS FOR NASIBPUR , SM/17627 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Harat& Panrra W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 1804/HUG | 21/06/2023 | 45 | OSMAN SEKH | 80.84 | 15.95 | 50 | 100
3059 | HOOGHLY | Hooghly Division | GROUND BASED PWSS FOR NASIBPUR , SM/17627 | New | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution of NASIBPUR Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.HE Dte. | 384/HUG | 08/02/2024 | 60 | M/S ALPHA CONSTRUCTION | 15.5 | 13.39 | 100 | 100
3060 | HOOGHLY | Electrical | GROUND BASED PWSS FOR NASIBPUR , SM/17627 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Nasibpur water supply scheme, T.W. No. III, Block: Singur, District: Hooghly under Electrical Division, PHE Dte. | 337/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.36 | 10.35 | 100 | 100
3061 | HOOGHLY | Hooghly Division | GROUND BASED PWSS FOR NASIBPUR , SM/17627 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Nasibpur PWSS, Bhandardaha PWSS, Ganderpukur PWSS, Bighati zone-I PWSS, Gopalnagar PWSS, Bahirkhanda PWSS) | 300/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 100
3062 | HOOGHLY | Electrical | GROUND BASED PWSS FOR NASIBPUR , SM/17627 | New | Quotation for new service connection at Nasibpur water supply Scheme [SM/17627], T/W No. - III, Block - Singur, under Nasibpur CCC, WBSEDCL, Ref. Id. - 503584530, Dt. - 07-03-2024, Application No. - 5004050532 | 872 | 13/03/2024 | 0 | WBSEDCL | 2.63 | 0 | 0 | 0
3063 | HOOGHLY | Hooghly Division | GROUND BASED PWSS FOR NASIBPUR , SM/17627 | New | NASIBPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub-Division of Hooghly Division P.H.E Dte under SINGUR Block, District:- Hooghly [NEW SCHEME] | 1679/HUG | 08/06/2023 | 938 | BAPPADITYA BANERJEE | 499.98 | 218.29 | 43.66 | 60
3064 | HOOGHLY | Hooghly Division | GROUND BASED PWSS FOR NASIBPUR , SM/17627 | New | Horizontal road crossing by trenchless method along CN Road(PWD) for NASIBPUR pwss under Chandannagar Sub Division,Hooghly Division P.H.E. Dte. | 3476/HUG | 04/10/2024 | 335 | BAPPADITYA BANERJEE | 56.52 | 0 | 0 | 80
3065 | HOOGHLY | Hooghly Division | Source Augmentation of BORHAL Piped Water Supply Scheme by installing new Two (2) Nos. Tube Wells including Connection with Distribution & other allied work to meet up the water demand under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. , SM/18968 | Augmentation | Balance LDS and other allied works within left out habitation of various Mouzas in Borhal (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 532/HUG | 20/02/2024 | 15 | MA CONSTRUCTION | 16.06 | 16.06 | 100 | 80
3066 | HOOGHLY | Hooghly Division | Source Augmentation of BORHAL Piped Water Supply Scheme by installing new Two (2) Nos. Tube Wells including Connection with Distribution & other allied work to meet up the water demand under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. , SM/18968 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Nikash village under Borhal PWSS (2 nos.) 2. Borhal under Borhal PWSS (2 nos.) 3. Satghara village under Borhal PWSS (2 nos.) | 175/SER | 11/03/2024 | 7 | TOTON MONDAL | 0.95 | 0.95 | 100 | 80
3067 | HOOGHLY | Hooghly Division | Source Augmentation of BORHAL Piped Water Supply Scheme by installing new Two (2) Nos. Tube Wells including Connection with Distribution & other allied work to meet up the water demand under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. , SM/18968 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Kumarbazar village under Antpur PWSS (2 nos.) 2. Paschim Durgapur village under Borhal PWSS (2 nos.) 3. Ilampur village under Borhal PWSS (2 nos.) | 172/SER | 11/03/2024 | 7 | JOY GURU ENTERPRISE | 0.95 | 0.95 | 100 | 80
3068 | HOOGHLY | Hooghly Division | Source Augmentation of BORHAL Piped Water Supply Scheme by installing new Two (2) Nos. Tube Wells including Connection with Distribution & other allied work to meet up the water demand under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. , SM/18968 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Dakshin Dilakash village under Borhal PWSS (2 nos.) 2. Mandaran Dilakash village under Borhal PWSS (2 nos.) 3. Khurigachhi village under Borhal PWSS (2 nos.) | 173/SER | 11/03/2024 | 7 | TOTON MONDAL | 0.95 | 0.95 | 100 | 80
3069 | HOOGHLY | Hooghly Division | Source Augmentation of BORHAL Piped Water Supply Scheme by installing new Two (2) Nos. Tube Wells including Connection with Distribution & other allied work to meet up the water demand under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. , SM/18968 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Kulakash village under Borhal PWSS (2 nos.) 2. Kandar Panagar village under Borhal PWSS (2 nos.) 3. Paschim Gobindapur village under Borhal PWSS (2 nos.) | 174/SER | 11/03/2024 | 7 | TOTON MONDAL | 0.95 | 0.95 | 100 | 80
3070 | HOOGHLY | Hooghly Division | Source Augmentation of BORHAL Piped Water Supply Scheme by installing new Two (2) Nos. Tube Wells including Connection with Distribution & other allied work to meet up the water demand under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. , SM/18968 | Augmentation | Designing making and erection of Display Board using logo and tag line of JalJeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Mathurabati village under Borhal PWSS (2 nos.) 2. Masinan village under Radhanagar PWSS (2 nos.) 3. Kuliara village under Morhal PWSS (2 nos.) | 176/SER | 11/03/2024 | 7 | JOY GURU ENTERPRISE | 0.95 | 0.95 | 100 | 80
3071 | HOOGHLY | Electrical | Source Augmentation of BORHAL Piped Water Supply Scheme by installing new Two (2) Nos. Tube Wells including Connection with Distribution & other allied work to meet up the water demand under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. , SM/18968 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of BORHAL Piped Water Supply Scheme Block- Jangipara District- Hooghly under JJM Program under Electrical Division PHE Dte. | 327/ED | 21/02/2024 | 842 | DEY ENTERPRISE | 20.85 | 0 | 0 | 45
3072 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF ABDULPUR PIPED W/S SCHEME UNDER BALAGAH BLOCK , SM/18980 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF ABDULPUR PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4503/ED | 23/11/2023 | 90 | ESENCE ENGINEERING CONCERN | 10.72 | 0 | 0 | 0
3073 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF ABDULPUR PIPED W/S SCHEME UNDER BALAGAH BLOCK , SM/18980 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. 1. Abdulpur PWSS 2. Bhabanipur PWSS 3. Dumurdaha PWSS 4. Guptipara PWSS 5. Itagarh PWSS 6. Kamarpara PWSS | 196/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 100 | 50
3074 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF ABDULPUR PIPED W/S SCHEME UNDER BALAGAH BLOCK , SM/18980 | Augmentation | Inter connection work of Rising main from newly bored 2nd Tube Well to OHR of Abdulpur W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | 214/CH | 29/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.87 | 0.86 | 100 | 50
3075 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF ABDULPUR PIPED W/S SCHEME UNDER BALAGAH BLOCK , SM/18980 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at DHAMAITIKAR (2Nos.), GUPTIPARA (1No.), ABDULPUR (1 No.), DEPARA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3385/HUG | 22/11/2023 | 628 | OSMAN SEKH | 87.83 | 0 | 0 | 40
3076 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF ABDULPUR PIPED W/S SCHEME UNDER BALAGAH BLOCK , SM/18980 | Augmentation | Repairing & Renovation of Boundary Wall, Switch Room and Land Development at PH-II Site of Abdulpur Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 302/CH | 20/02/2025 | 10 | M/S. R. M. CONSTRUCTION | 3.48 | 0 | 0 | 0
3077 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18938 | Augmentation | Quotation for new service connection for source Augmentation of HARAL Water Supply Scheme, Zone-III, TW NO- I in the district Hooghly under Electrical Division, PHE Dte. (SM/18938), Reference Id- 503705756, Application no- 5004321019 | 374 | 12/08/2024 | 0 | WBSEDCL | 23.02 | 0 | 0 | 0
3078 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18938 | Augmentation | Quotation for new service connection for source Augmentation of HARAL Water Supply Scheme, Zone-III, TW NO- II in the district Hooghly under Electrical Division, PHE Dte. (SM/18938), Reference Id- 503697548, Application no- 5004304981 | 337 | 30/07/2024 | 0 | WBSEDCL | 3.93 | 0 | 0 | 0
3079 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18938 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at CHOPA (1 No.), HARAL (2Nos.), DWARBASINI (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3236/HUG | 06/11/2023 | 726 | DAS ENTERPRISE | 59.77 | 0 | 0 | 60
3080 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18938 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4489/ED | 23/11/2023 | 495 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 21.49 | 0 | 0 | 80
3081 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18938 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Haral Z-II PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 272/CH | 20/02/2025 | 10 | M/S SHIVAM UDYOG | 3.18 | 0 | 0 | 0
3082 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18938 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site of Haral Z-I PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 241/CH | 19/02/2025 | 10 | M/S SHIVAM UDYOG | 4.84 | 0 | 0 | 0
3083 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18938 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Haral Z-I PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 245/CH | 19/02/2025 | 10 | M/S SHIVAM UDYOG | 2.62 | 0 | 0 | 0
3084 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18938 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site (PH-I) Haral Z-II PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 264/CH | 20/02/2025 | 10 | M/S SHIVAM UDYOG | 4.49 | 0 | 0 | 0
3085 | HOOGHLY | Electrical | Source Augmentation of DIHI BAYARA Piped Water Supply Scheme Under Arambag Block , SM/18959 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Dihibayra water supply scheme, T.W. No. III, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 471_ED | 10/03/2022 | 90 | T S CONSTRUCTION | 6.4 | 6.4 | 100 | 50
3086 | HOOGHLY | Electrical | Source Augmentation of DIHI BAYARA Piped Water Supply Scheme Under Arambag Block , SM/18959 | Augmentation | Supply delivery and installation of voltage correcting device and other allied works for Dihibayra w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. | 544/HMSD | 17/03/2022 | 30 | WIZARDTECH SOLUTION | 2.36 | 2.36 | 100 | 100
3087 | HOOGHLY | Hooghly Division | Source Augmentation of DIHI BAYARA Piped Water Supply Scheme Under Arambag Block , SM/18959 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir , Bounary Wall of DIHIBAYRA PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3777/HUG | 25/11/2024 | 40 | M/S PRADYUT KUMAR HAZRA (PARTNERSHIP) | 12.75 | 0 | 0 | 0
3088 | HOOGHLY | Hooghly Division | Source Augmentation of DIHI BAYARA Piped Water Supply Scheme Under Arambag Block , SM/18959 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PABA PWSS-3nos (2) DIHIBAYRA PWSS- 3nos (3) HAYATPUR PWSS- 4nos (4) RAJHATO PWSS- 4nos | 811/Arg | 23/08/2024 | 30 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
3089 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18942 | Augmentation | Inter connection work of Rising main from newly bored Tube Well to existing Distribution Main of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | 1111/CH | 15/12/2023 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.89 | 100 | 100
3090 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18942 | Augmentation | Laying HDPE Pipeline From existing existing Distribution System for providing FHTC of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | 1112/CH | 15/12/2023 | 10 | MAA BUNAMATA ENTERPRISE | 0.94 | 0.94 | 100 | 100
3091 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18942 | Augmentation | Carriage for Chlorine From Polba Store to different Pump Houses at Pandua & Balagarh Block under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | 1113/CH | 15/12/2023 | 7 | MAA BUNAMATA ENTERPRISE | 0.53 | 0.53 | 100 | 100
3092 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18942 | Augmentation | Laying HDPE Pipeline From existing existing Distribution System for providing FHTC of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | 26/CH | 05/01/2024 | 15 | MAA BUNAMATA ENTERPRISE | 1.93 | 1.93 | 100 | 60
3093 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18942 | Augmentation | Providing FHTC at the left out portions of Nayasarai of Dumurdaha Piped Water Supply Scheme under Balagarh Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 276/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.98 | 0.97 | 100 | 80
3094 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18942 | Augmentation | Providing FHTC at the left out portions of Ramnagar of Dumurdaha Piped Water Supply Scheme under Balagarh Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 275/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.98 | 0.97 | 100 | 80
3095 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18942 | Augmentation | Laying HDPE Pipeline From existing Distribution System for providing FHTC of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | 535/CH | 14/06/2024 | 7 | MAA BUNAMATA ENTERPRISE | 4.83 | 4.82 | 100 | 80
3096 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18942 | Augmentation | Laying HDPE Pipeline From existing existing Distribution System for providing FHTC of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | 544/CH | 18/06/2024 | 7 | MAA BUNAMATA ENTERPRISE | 4.43 | 4.43 | 100 | 80
3097 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18942 | Augmentation | Quotation for new service connection for source Augmentation of DUMURDHA Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. (SM/18942), Reference Id- 503718763 Application no- 5004350181 | 425 | 01/10/2024 | 0 | WBSEDCL | 8.83 | 0 | 0 | 0
3098 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18942 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4506/ED | 23/11/2023 | 495 | INDTECH ASSOCIATES. | 10.76 | 0 | 0 | 80
3099 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18942 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at AYMA NABABPUR (2Nos.), DUMURDAHA (1No.), AKNA (1 No.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3356/HUG | 21/11/2023 | 715 | AYUSH ENTERPRISE | 58.97 | 0 | 0 | 80
3100 | HOOGHLY | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13334 | New | Material Requisition To Resource Division | 3057/17/Hug | 11/10/2023 | 0 | Resource Division | 15.63 | 0 | 0 | 0
3101 | HOOGHLY | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13334 | New | Material Requisition To Resource Division | 127/09/Hug | 13/01/2023 | 0 | Resource Division | 22.34 | 0 | 0 | 0
3102 | HOOGHLY | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13334 | New | Material Requisition To Resource Division | 1263/4/Hug | 03/05/2023 | 0 | Resource Division | 13.62 | 0 | 0 | 0
3103 | HOOGHLY | Electrical | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13334 | New | Quotation Bill for New Service Connection at Gholdhuguri W/S. Sch. | 123 | 20/07/2023 | 0 | WBSEDCL | 3.77 | 0 | 0 | 0
3104 | HOOGHLY | Electrical | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13334 | New | Quotation Bill for New Service Connection at Ghol Digrui W/S. Sch. Zone-I PH-I | 171 | 10/08/2023 | 0 | WBSEDCL | 5.99 | 0 | 0 | 0
3105 | HOOGHLY | Electrical | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13334 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-I, T.W. No. III, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | 328/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.43 | 0 | 0 | 0
3106 | HOOGHLY | Electrical | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13334 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-I, T.W. No.- I & II, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | 779/ED | 09/02/2023 | 90 | TRIO CONCERN | 22.03 | 22 | 100 | 75
3107 | HOOGHLY | Electrical | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13334 | New | Quotation money deposition for new service connection at Gholedigrui w/s scheme, Zone- I, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004475357 Reference ID- 503799179 SM Code- 13334 | BP-24-25-596 | 21/11/2024 | 0 | WBSEDCL | 6.98 | 0 | 0 | 0
3108 | HOOGHLY | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13334 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GHOLDIGRUI (ZONE-II) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | 591/HUG | 22/02/2024 | 679 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 31.57 | 13.75 | 43.57 | 70
3109 | HOOGHLY | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13334 | New | Sinking of 3rd tube-well by D.R. Rig method ,Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GHOLDIGRUI (ZONE-I) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | 809/HUG | 11/03/2024 | 661 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 31.59 | 13.44 | 42.53 | 70
3110 | HOOGHLY | Hooghly Division | Ghol Digrui (Zone-I) Piped Water Supply Scheme, Block- Pursura, District-Hooghly , SM/13334 | New | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for GHOLDIGRUI ZONE-I Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3670/HUG | 13/11/2024 | 414 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 26.4 | 0 | 0 | 0
3111 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme , SM/07461 | Retrofitting | FHTC |  | 12/04/2021 | 0 | MONDAL PRECESSION PVT LTD. | 22.48 | 0 | 0 | 0
3112 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme , SM/07461 | Retrofitting | FHTC |  | 05/10/2021 | 0 | MONDAL PRECESSION PVT LTD. | 40.25 | 0 | 0 | 0
3113 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme , SM/07461 | Retrofitting | Providing 304 nos Functional Household Tap Connection (FHTC) within the command area of Pratapnagar Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Work Allotted : 152 Nos FHTC out of 304 Nos FHTC within the command area of Pratapnagar Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Estimate Value : Rs. 707651.50(50% of Rs. 1415303.00) | 1965/Hug | 02/11/2021 | 30 | GHOSH ENTERPRISE | 11.32 | 5.43 | 47.92 | 0
3114 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme , SM/07461 | Retrofitting | Providing 304 nos Functional Household Tap Connection (FHTC) within the command area of PROTAPNAGAR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | 18/Hug | 04/01/2022 | 30 | SURAJIT SINGHA RAY | 12.56 | 12.21 | 97.22 | 0
3115 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme , SM/07461 | Retrofitting | Providing 304 nos FHTC for Pratapnagar PWSS | 1998/Hug. | 12/11/2021 | 35 | MESSRS FREEDOM CONSTRUCTION | 5.58 | 5.58 | 100 | 0
3116 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme , SM/07461 | Retrofitting | Providing FHTC for Pratapnagar PWSS | 525/Arg. | 30/11/2021 | 45 | BENGAL TRADERS | 4.84 | 4.84 | 100 | 0
3117 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme , SM/07461 | Retrofitting | FHTC |  | 28/01/2022 | 0 | MESSRS. FREEDOM CONSTRUCTION | 5.58 | 0 | 0 | 0
3118 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme , SM/07461 | Retrofitting | Material Requisition To Resource Division | 2196/1/HUG | 14/12/2021 | 0 | Resource Division | 1.59 | 0 | 0 | 0
3119 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. , SM/07950 | Retrofitting | FHTC |  | 24/09/2021 | 0 | K. JAGADHATRY & CO. | 4.01 | 0 | 0 | 0
3120 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. , SM/07950 | Retrofitting | FHTC |  | 24/09/2021 | 0 | K. JAGADHATRY & CO. | 4.01 | 0 | 0 | 0
3121 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. , SM/07950 | Retrofitting | FHTC |  | 15/02/2021 | 0 | ASHOK GHOSH & BROTHERS | 20 | 0 | 0 | 0
3122 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. , SM/07950 | Retrofitting | FHTC |  | 30/09/2021 | 0 | RURAL CONSTRUCTION (MANIK CHANDRA ADAK) | 4.5 | 0 | 0 | 0
3123 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. , SM/07950 | Retrofitting | FHTC |  | 16/08/2021 | 0 | PRADIP KUMAR ADHYA | 59.27 | 0 | 0 | 0
3124 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. , SM/07950 | Retrofitting | FHTC |  | 24/09/2021 | 0 | YOUNG ENGINEERS CO-OPERATIVE SOCIETY LTD. | 11.55 | 0 | 0 | 0
3125 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. , SM/07950 | Retrofitting | Providing 250 nos F.H.T.C. in Kotalpur village of Patna Bhairabpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | 262/Hug | 03/02/2021 | 20 | K JAGADHATRY & CO | 13.62 | 3.85 | 75.93 | 0
3126 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. , SM/07950 | Retrofitting | Providing 200 nos F.H.T.C. in Patna Bhairabpur village of Patna Bhairabpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | 263/Hug | 03/02/2021 | 20 | YOUNG ENGINEERS CO OPERATIVE SOCIETY LTD. | 14.3 | 11.55 | 99.95 | 85
3127 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY , SM/07954 | Retrofitting | FHTC |  | 08/11/2021 | 0 | BANSBERIA CONSTRUCTION CO. | 7.95 | 0 | 0 | 0
3128 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY , SM/07954 | Retrofitting | FHTC |  | 19/03/2021 | 0 | BANSBERIA CONSTRUCTION CO. | 31 | 0 | 0 | 0
3129 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY , SM/07954 | Retrofitting | FHTC |  | 30/09/2021 | 0 | UNIQUE AGENCY | 43.59 | 0 | 0 | 0
3130 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY , SM/07954 | Retrofitting | FHTC |  | 30/09/2021 | 0 | UNIQUE AGENCY | 41.52 | 0 | 0 | 0
3131 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY , SM/07954 | Retrofitting | Providing1527 nos F.H.T.C. in Chaitanyapur, Chak Ananta,Kulubati Bhagabatipur & Radha Krishnapur Village of Paschim Joykrishnapur and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | 944/HUG | 06/05/2021 | 40 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 88.35 | 13.56 | 15.35 | 100
3132 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY , SM/07954 | Retrofitting | Placement of Fund | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
3133 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY , SM/07954 | Retrofitting | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of PASCHIM JAYKRISHNAPUR Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. within HARIPAL Block. | 1474/HUG | 19/05/2023 | 30 | S.B. ENTERPRISE | 11.8 | 9.82 | 100 | 80
3134 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY , SM/07954 | Retrofitting | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Paschim Jaykrishnapur PWSS, Kaikala PWSS, Bandipur PWSS, Bamonjol PWSS, Binagram PWSS, Rambati PWSS). | 307/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 100
3135 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY , SM/07954 | Retrofitting | Reparing of Damage Pipeline at Paschim Jaykrishnapur Water Supply Scheme Under chandannagar Sub-Division under Hooghly Division,P.H.E Dte . | 289/Chan | 15/03/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.57 | 0.57 | 100 | 100
3136 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY , SM/07954 | Retrofitting | Making of 2 nos 1.8m X 1.45m X 2.1m KIOSK at Gouribati 3rd T/W site & Paschim Joykrishnapur (Zone-1) 3rd T/W Site under Chandannagar Sub-Division PHE Dte. | 280/Chan | 15/03/2024 | 15 | SUDIPTA SINHA | 0.88 | 0.82 | 100 | 100
3137 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY , SM/07954 | Retrofitting | Repairing of boundary wall at 2nd site of Paschim Joykrishnapur zone 1 PWSS Scheme under Chandannagar Sub-Division, PHE Dte. | 942/CHAN | 21/07/2025 | 20 | MAHAMAYA CONSTRUCTION | 2.08 | 0 | 0 | 0
3138 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. , SM/07536 | Retrofitting | FHTC |  | 19/03/2021 | 0 | M/S R.K. CHOUDHURI | 40 | 0 | 0 | 0
3139 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. , SM/07536 | Retrofitting | Providing 360 nos Functional Household Tap Connection (FHTC) within the command area of Gobindapur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | 2126/Hug | 01/12/2021 | 30 | M/S T.K.B. CONSTRUCTION | 13.29 | 15.71 | 100 | 100
3140 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. , SM/07536 | Retrofitting | Providing 114 nos. Functional Household Tap Connection (F.H.T.C) within Command area of Mollah Para, Malik Para Habitation of Maikhanda Village under Gobindapur Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte. [Block-Khanakul-I] [ 2nd Call] | 174/Arg | 21/03/2022 | 30 | BAKSHI ENTERPRISE | 4.69 | 4.57 | 97.42 | 100
3141 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. , SM/07536 | Retrofitting | Providing 1207 nos F.H.T.C. in Gobindapur and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I] | 406/HUG | 15/02/2021 | 30 | M/S R.K. CHOUDHURI | 62.52 | 0.62 | 0.99 | 100
3142 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. , SM/07536 | Retrofitting | FHTC |  | 27/01/2022 | 0 | M/S T.K.B. CONSTRUCTION | 0 | 0 | 0 | 0
3143 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. , SM/07536 | Retrofitting | Operation & Maintenance of OHR, FHTC & Laying Distribution System including Street stand Post, Rising Main & other essential components of Gobindapur, Patul & Khanakul W/S Scheme for the period of 01.09.21 to 31.08.22 under Arambagh Sub- Division P.H.E Dte. SL-54 | 1603/Hug | 03/09/2021 | 363 | M/S PRADYUT KUMAR HAZRA | 9.37 | 0 | 0 | 0
3144 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. , SM/07536 | Retrofitting | Material Requisition To Resource Division | 2096/23/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0 | 0
3145 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NATAGARI WATER SUPPLY SCHEME. , SM/07538 | Retrofitting | FHTC |  | 21/09/2021 | 0 | ARUN SEAL AND CO. | 15.14 | 0 | 0 | 0
3146 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NATAGARI WATER SUPPLY SCHEME. , SM/07538 | Retrofitting | Providing 477 nos F.H.T.C. in Natagari and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | 402/HUG | 15/02/2021 | 30 | ARUN SEAL AND CO. | 6.69 | 6.69 | 100 | 100
3147 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NATAGARI WATER SUPPLY SCHEME. , SM/07538 | Retrofitting | Providing 477 nos F.H.T.C. in Natagari and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | 402/Hug | 15/02/2021 | 30 | ARUN SEAL AND CO. | 24.94 | 15.13 | 100 | 100
3148 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NATAGARI WATER SUPPLY SCHEME. , SM/07538 | Retrofitting | Material Requisition To Resource Division | 2097/4/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0 | 0
3149 | HOOGHLY | Hooghly Division | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09208 | Augmentation | WBSEDCL PAYMENT FROM ELECTRICAL DIVISION,PHE DTE. |  | 20/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.2 | 0 | 0 | 0
3150 | HOOGHLY | Hooghly Division | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09208 | Augmentation | Laying of C.I/D.I pipes & specials for connection of T.W No. -III with distribution system at 4TH TW Site of Naldanga W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | 598/CH | 14/12/2021 | 25 | R.K. TRADERS | 4.05 | 1.31 | 100 | 100
3151 | HOOGHLY | Hooghly Division | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09208 | Augmentation | Providing Functional Household Tap Connection at Subhaspally of Kadalia-2 Gram Panchyet under Naldanga W/S scheme under Chinsurah Sub- Division, PHE Dte. | 693/CH | 27/07/2023 | 15 | S.D ENTERPRISE (SAMIR KR. DAS) | 0.97 | 0.97 | 100 | 100
3152 | HOOGHLY | Hooghly Division | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09208 | Augmentation | Providing Functional Household Tap Connection at Natunpara Talpukur of Kadalia-2 Gram Panchyet under Naldanga W/S scheme under Chinsurah Sub- Division, PHE Dte. | 694/CH | 27/07/2023 | 15 | S.D ENTERPRISE (SAMIR KR. DAS) | 0.97 | 0.97 | 100 | 100
3153 | HOOGHLY | Hooghly Division | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09208 | Augmentation | Connecting Rising main From Newly Bored Tube Well at Jatileswer Tala to the Existing distribution system and allied works of Naldanga water supply scheme under Chinsurah Sub Division undre Hooghly Division PHE Dte. | 817/CH | 31/08/2023 | 15 | R.K. TRADERS | 0.98 | 0.96 | 100 | 80
3154 | HOOGHLY | Hooghly Division | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09208 | Augmentation | Connecting Rising main with Existing distribution system and allied works at Simla Village of Naldanga water supply scheme under Chinsurah Sub Divusion undre Hooghly Division PHE Dte. | 821/CH | 31/08/2023 | 15 | R.K. TRADERS | 1 | 1 | 100 | 80
3155 | HOOGHLY | Hooghly Division | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09208 | Augmentation | Laying distribution of Pipeline and allied works at Jatileswar Tala, Natun Para, Simla Village of Naldanga water supply scheme under Chinsurah Sub Divusion under Hooghly Division PHE Dte. | 818/CH | 31/08/2023 | 15 | R.K. TRADERS | 0.96 | 0.96 | 100 | 80
3156 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MEGSAR WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. , SM/09776 | Retrofitting | Laying of HDPE Pipe by HDD Process & Open cut method including restoration work at Mohanad Bandel Road within MEGHSAR PWSS, under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO - 09 | 2090/HUG | 21/09/2022 | 45 | M/S BISWAS CONSTRUCTION | 87.34 | 99.97 | 114.47 | 80
3157 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BAINCHI WATER SUPPLY SCHEME , SM/11002 | Retrofitting | Providing 1000 nos Functional Household Tap Connection (FHTC) within Bainchi Mouza of Bainchi Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | 722/Hug | 07/04/2022 | 40 | TOTON MONDAL | 50.96 | 50.95 | 100 | 0
3158 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BAINCHI WATER SUPPLY SCHEME , SM/11002 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of BAINCHI Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 2275/HUG | 19/10/2022 | 40 | M/S T.K.B. CONSTRUCTION | 45.7 | 45.54 | 99.64 | 0
3159 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BAINCHI WATER SUPPLY SCHEME , SM/11002 | Retrofitting | BAINCHIPOTA (ZONE-I) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block, District:- Hooghly [NEW SCHEME] | 613/HUG | 02/03/2023 | 270 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 491.76 | 0 | 0 | 0
3160 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BAINCHI WATER SUPPLY SCHEME , SM/11002 | Retrofitting | Providing 1000 nos Functional Household Tap Connection (FHTC) within Batika & Chau Bera Mouza of Bainchi Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | 723/Hug | 07/04/2022 | 40 | M/S ASHA CONSTRUCTION. | 48.21 | 43.01 | 100 | 0
3161 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BAINCHI WATER SUPPLY SCHEME , SM/11002 | Retrofitting | Material Requisition To Resource Division | 1123/5/HUG | 06/06/2022 | 0 | Resource Division | 5.5 | 0 | 0 | 0
3162 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BAINCHI WATER SUPPLY SCHEME , SM/11002 | Retrofitting | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, RWS HOOGHLY SUB DIVISION, PHE DTE. | BP-2022-23-630 | 22/03/2023 | 0 | AATISH KUMAR SHAW | 0.4 | 0 | 0 | 0
3163 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Route Survey, Design Drawing & DPR Preparation of Olipur Zone - I PWSS under Chandannagar Sub-Division, P.H.E. Dte. | 264/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.93 | 3.86 | 98.1 | 0
3164 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Route Survey, Design Drawing & DPR Preparation of Olipur Zone - II PWSS under Chandannagar Sub-Division, P.H.E. Dte. | 265/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.24 | 4.02 | 94.79 | 0
3165 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Material Requisition To Resource Division | 2686/10/Hug | 01/12/2022 | 0 | Resource Division | 0.34 | 0 | 0 | 0
3166 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Repairing of 5.4 mtr. x 3.4 mtr. size existing pump house of Olipur PWSS under Hooghly Division, P.H.E. Dte. | 535/CHAN | 12/11/2021 | 30 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 3.58 | 3.43 | 95.89 | 0
3167 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Repairing of 5.4 mtr x 3.6 mtr. size existing pump house of Olipur PWSS scheme under Hooghly Division, P.H.E. Dte. | 535/CHAN | 15/11/2021 | 30 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 3.58 | 0 | 0 | 0
3168 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Sinking of Four Nos Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto 210 Mtr at OLIPUR (ZONE-I) PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | 2500/HUG | 22/11/2022 | 45 | M/S SYCHROTECH INDUSTRY | 55.58 | 0 | 0 | 0
3169 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Material Requisition To Resource Division | 157/10/Hug | 24/01/2022 | 0 | Resource Division | 1.55 | 0 | 0 | 0
3170 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Material Requisition To Resource Division | 1125/1/HUG | 06/06/2022 | 0 | Resource Division | 10.98 | 0 | 0 | 0
3171 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Material Requisition To Resource Division | 423/1/Hug | 07/03/2022 | 0 | Resource Division | 25.98 | 0 | 0 | 0
3172 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Material Requisition To Resource Division | 01/10/Hug | 02/01/2023 | 0 | Resource Division | 11.94 | 0 | 0 | 0
3173 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Material Requisition To Resource Division | 1383/29/Hug | 15/05/2023 | 0 | Resource Division | 10.61 | 0 | 0 | 0
3174 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Material Requisition To Resource Division | 2502/Hug | 17/08/2023 | 0 | Resource Division | 10.8 | 0 | 0 | 0
3175 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Material Requisition To Resource Division | 1782/Hug | 15/06/2023 | 0 | Resource Division | 158.24 | 0 | 0 | 0
3176 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Quotation for New Service Connection of Olipur W/S Scheme ,Zone-I,PH No-II District-Hooghly under ED,PHE DTe | 100 | 19/07/2023 | 0 | WBSEDCL | 1.93 | 0 | 0 | 0
3177 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Quotation Bill for New Service Connection at Oilipur W/S. Sch. | 03 | 13/04/2023 | 0 | WBSEDCL | 0.96 | 0 | 0 | 0
3178 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Quotation Bill for New Service Connection at Aug. of Olipur W/S. Sch. Z-I & II, PH-III & I | 220 | 27/03/2023 | 0 | WBSEDCL | 4.54 | 0 | 0 | 0
3179 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | QUOTATION for new Service Connection of Olipur W/S Scheme ,Zone-I,PH No-I, Block-Haripal,Dist-Hooghly under Electrical Division, PHE Dte | 101 | 19/07/2023 | 0 | WBSEDCL | 3.26 | 0 | 0 | 0
3180 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | New service connection | 163 | 03/08/2023 | 0 | WBSEDCL | 11.4 | 0 | 0 | 0
3181 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch room & boundary wall for OLIPUR ZONE-II Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 3472/HUG | 04/10/2024 | 60 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 26.54 | 0 | 0 | 0
3182 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Olipur water supply scheme, T.W. No.- I, II, III & IV, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | 1716/ED | 18/04/2023 | 90 | D. K. ELECTRIC | 42.97 | 42.53 | 100 | 45
3183 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Olipur,Kulteghori,Paschim Jaykrishnapur & Barakamalpur W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 1839/HUG | 26/06/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 80.45 | 44.35 | 100 | 100
3184 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Road Restoration | BP-2023-24-589 | 16/11/2023 | 0 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 13 | 0 | 0 | 0
3185 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for OLIPUR ZONE-I Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 3473/HUG | 04/10/2024 | 343 | RAJMAHAL ENTERPRISE | 26.48 | 0 | 0 | 80
3186 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for OLIPUR water supply scheme, Zone-II, TW No. IV, Block: Haripal, District - Hooghly under Electrical Division PHE Dte. | 477/ED | 18/03/2025 | 90 | SUBHRA ENTERPRISE | 11.3 | 0 | 0 | 0
3187 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Balance Laying of Pipeline of Purba Narayanpur Mouzas (JL - 80) of Olipur Zone - II water supply scheme under Chandannagar Sub-Division P.H.E. Dte. | 647/HUG | 10/03/2025 | 30 | T.K. INTERNATIONAL | 9.66 | 0 | 0 | 0
3188 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Road restoration at Olipur zone-1 water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part I) | 861/CHAN | 22/07/2025 | 20 | MAA TARA CONSTRUCTION | 4.89 | 0 | 0 | 50
3189 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PWSS FOR OLIPUR , SM/10022 | Augmentation | Augmentation of OLIPUR (ZONE-I) Water Supply Scheme with Construction of 500 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work & LDS & Functional Household Tap Connection, Construction of 4 Nos.Switch Room(1No. 5.4 M x 3.6M & 3Nos. 3.6 M x 3.0M) & 3 Nos. Boundary Wall at 2nd T.W Site, Proposed T.W Site, O.H.R Site, Laying Rising Main, Repairing of existing Switch Rooms at Haripal Block under Chandannagar Sub-Division, PHE Dte. | 1719/Hug | 24/08/2022 | 1012 | S & P ENTERPRISE | 758.77 | 727.35 | 86.72 | 90
3190 | HOOGHLY | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme , SM/10023 | Augmentation | Route Survey, Design Drawing & DPR Preparation of SOLEPUR-DUTTAPUR ZONE - I PWSS under Chandannagar Sub-Division, P.H.E. Dte | 273/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.76 | 3.23 | 85.67 | 0
3191 | HOOGHLY | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme , SM/10023 | Augmentation | Route Survey, Design Drawing & DPR Preparation of SOLEPUR-DUTTAPUR ZONE - II PWSS under Chandannagar Sub-Division, P.H.E. Dte | 274/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.15 | 3.15 | 100 | 0
3192 | HOOGHLY | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme , SM/10023 | Augmentation | Material Requisition To Resource Division | 2686/5/Hug | 01/12/2022 | 0 | Resource Division | 0.32 | 0 | 0 | 0
3193 | HOOGHLY | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme , SM/10023 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 210 Mtr at SOLEPUR DUTTAPUR (ZONE-I) PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | 2508/HUG | 22/11/2022 | 30 | SPG ENTERPRISES | 13.82 | 12.23 | 100 | 0
3194 | HOOGHLY | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme , SM/10023 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 210 Mtr at SOLEPUR DUTTAPUR (ZONE-II) PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | 2509/HUG | 22/11/2022 | 30 | SPG ENTERPRISES | 13.82 | 13 | 100 | 0
3195 | HOOGHLY | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme , SM/10023 | Augmentation | Material Requisition To Resource Division | 1690/HUG | 22/08/2022 | 0 | Resource Division | 93.17 | 0 | 0 | 0
3196 | HOOGHLY | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme , SM/10023 | Augmentation | Material Requisition To Resource Division | 1383/41/Hug | 15/05/2023 | 0 | Resource Division | 5.14 | 0 | 0 | 0
3197 | HOOGHLY | Electrical | Augmentation of Salepur-Duttapur Water Supply Scheme , SM/10023 | Augmentation | Quation Money for Salepur Duttapur PH No-I | 102 | 19/07/2023 | 0 | WBSEDCL | 3.35 | 0 | 0 | 0
3198 | HOOGHLY | Electrical | Augmentation of Salepur-Duttapur Water Supply Scheme , SM/10023 | Augmentation | Augmentation Of Solepur-Duttapur Water Supply Scheme. TW-3, Z-II | 248 | 30/03/2023 | 0 | WBSEDCL | 2.82 | 0 | 0 | 0
3199 | HOOGHLY | Electrical | Augmentation of Salepur-Duttapur Water Supply Scheme , SM/10023 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Salepur Duttapur water supply scheme TW No I and II Block Tarakeswar, District Hooghly under ED PHED. | 857/ED | 14/02/2023 | 90 | ALPHA ENTERPRISE | 21.49 | 21.44 | 99.75 | 45
3200 | HOOGHLY | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme , SM/10023 | Augmentation | Augmentation of SALEPURDUTTAPUR (ZONE-I)Water Supply Scheme with LDS & Functional Household tap Connection, Construction of 1 No. Switch Room(3.6 M X 3.0M)& Boundary Wall at 2ND T.W Site, Proposed T.W Site & O.H.R Site, Repairing of existing Switch Rooms & Boundary Wall at Tarakeswar Block under Chandannagar Sub-Division under Hooghly Division, PHE Dte. | 1952/HUG | 07/09/2022 | 847 | UNIQUE AGENCY | 288.28 | 275.2 | 93.94 | 100
3201 | HOOGHLY | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme , SM/10023 | Augmentation | Construction of 400 cum capacity OHR with 20 mtr. staging height including Soil Investigation work for Augmentation of SALEPUR-DUTTAPUR (ZONE-II) Water Supply Scheme with & Laying Rising Main at Tarakeswar Block under Chandannagar Sub-Division, PHE Dte. | 1346/Hug | 29/06/2022 | 300 | DAS ENTERPRISE (SAMIR DAS) | 110.01 | 109.92 | 100 | 45
3202 | HOOGHLY | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme , SM/10023 | Augmentation | Augmentation of SALEPUR-DUTTAPUR (ZONE - II) Water Supply Scheme with LDS & Functional Household Tap Connection, Construction of 1 No. Switch Room (3.6 M X 3.0 M) & Boundary Wall at 2nd T.W. Site, Proposed T.W. Site & O.H.R. Site, Repairing of existing Switch Rooms & Boundary Wall at Tarakswar Block under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 2236/Hug | 13/10/2022 | 90 | S & P ENTERPRISE | 476.56 | 470.01 | 100 | 50
3203 | HOOGHLY | Hooghly Division | Augmentation of Salepur-Duttapur Water Supply Scheme , SM/10023 | Augmentation | Construction of 300 cum capacity OHR with 20 mtr. staging height including Soil Investigation work for Augmentation of SALEPUR-DUTTAPUR (ZONE-I) Water Supply Scheme & Laying Rising Main, at Tarakeswar Block under Chandannagar Sub-Division, PHE Dte. | 1284/Hug | 23/06/2022 | 1043 | ARUN SEAL AND CO. | 96.23 | 76.33 | 79.6 | 40
3204 | HOOGHLY | Hooghly Division | KANAJOLI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12253 | New | Material Requisition To Resource Division | 1386/5/Hug | 15/05/2023 | 0 | Resource Division | 11.59 | 0 | 0 | 0
3205 | HOOGHLY | Hooghly Division | KANAJOLI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12253 | New | Material Requisition To Resource Division | 1264/18/HUG | 03/05/2023 | 0 | Resource Division | 15.5 | 0 | 0 | 0
3206 | HOOGHLY | Electrical | KANAJOLI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12253 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kanajoli water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | 3493/ED | 30/12/2022 | 90 | CHATTERJEE BROTHERS | 20.25 | 16.41 | 81.06 | 35
3207 | HOOGHLY | Electrical | KANAJOLI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12253 | New | Quotation Bill for New Service Connection at Kanajoli W/S. Sch. TW-I | 685 | 19/01/2024 | 0 | WBSEDCL | 11.72 | 0 | 0 | 0
3208 | HOOGHLY | Electrical | KANAJOLI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12253 | New | Quotation Bill for New Service Connection at Kanajoli W/S. Sch. TW-II | 684 | 19/01/2024 | 0 | WBSEDCL | 4.03 | 0 | 0 | 0
3209 | HOOGHLY | Hooghly Division | KANAJOLI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12253 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 467.08 | 92.74 | 30
3210 | HOOGHLY | Electrical | CHALUA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12257 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chalua water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | 3461/ED | 30/12/2022 | 90 | M/S P.P. ELECTRICALS | 22.94 | 0 | 0 | 0
3211 | HOOGHLY | Hooghly Division | CHALUA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12257 | New | Material Requisition To Resource Division | 1386/28/Hug | 15/05/2023 | 0 | Resource Division | 22.55 | 0 | 0 | 0
3212 | HOOGHLY | Hooghly Division | CHALUA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12257 | New | Material Requisition To Resource Division | 3059/6/Hug | 11/10/2023 | 0 | Resource Division | 22.55 | 0 | 0 | 0
3213 | HOOGHLY | Hooghly Division | CHALUA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12257 | New | Material Requisition To Resource Division | 1264/13/HUG | 03/05/2023 | 0 | Resource Division | 16.96 | 0 | 0 | 0
3214 | HOOGHLY | Electrical | CHALUA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12257 | New | Quotation of New Service Connection for Chalua w/s Scheme,TW No-I,Block-Dhaniakhali Dist-Hooghly under ED,PHE Dte.(SM/12257) Application No-5003977900 Reference Id-503540601 | 764 | 16/02/2024 | 0 | WBSEDCL | 4.74 | 0 | 0 | 0
3215 | HOOGHLY | Electrical | CHALUA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12257 | New | Quotation of New Service Connection for Chalua w/s Scheme,PH No-II Block-Dhaniakhali Dist-Hooghly under ED,PHE Dte(SM/12257) Application No-5003977943 Reference Id-503540606 | 763 | 16/02/2024 | 0 | WBSEDCL | 6.68 | 0 | 0 | 0
3216 | HOOGHLY | Hooghly Division | CHALUA W/S SCHEME UNDER DHANIAKHALI BLOCK , SM/12257 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | 2494/HUG | 17/08/2023 | 746 | S. P. CONSTRUCTION | 5872.33 | 328.47 | 52.14 | 30
3217 | HOOGHLY | Electrical | DUDHKALMI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12245 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dudhkalmi water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | 3488/ED | 30/12/2022 | 90 | S.P. CONSTRUCTION | 21.37 | 0 | 0 | 0
3218 | HOOGHLY | Hooghly Division | DUDHKALMI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12245 | New | Material Requisition To Resource Division | 1384/16/Hug | 15/05/2023 | 0 | Resource Division | 16.88 | 0 | 0 | 0
3219 | HOOGHLY | Hooghly Division | DUDHKALMI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12245 | New | Material Requisition To Resource Division | 3060/15/Hug | 11/10/2023 | 0 | Resource Division | 16.88 | 0 | 0 | 0
3220 | HOOGHLY | Hooghly Division | DUDHKALMI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12245 | New | Material Requisition To Resource Division | 1236/1/Hug | 28/04/2023 | 0 | Resource Division | 28.77 | 0 | 0 | 0
3221 | HOOGHLY | Electrical | DUDHKALMI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12245 | New | Dudhkalmi w/s scheme,P H No 1 | 559 | 21/12/2023 | 0 | WBSEDCL | 5.64 | 0 | 0 | 0
3222 | HOOGHLY | Electrical | DUDHKALMI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12245 | New | Quotation bill for new service connection charges at Dudhkalmi PWSS P.H. No.-II, Hooghly. Application No. 5004031077 Ref ID: 503576014 | 24 | 05/04/2024 | 0 | WBSEDCL | 5.3 | 0 | 0 | 0
3223 | HOOGHLY | Hooghly Division | DUDHKALMI PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/12245 | New | Acceptance Order for NABABPUR, DUDHKALMI, HARIPUR, JAGMOHANPUR , GANGADHARPUR Piped Water Supply Scheme with.TW, Switch room, boundaryivall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at CHANDITALA-I Block under SERAMPORE Sub-Division Under Hooghly Division PHE Dte. | 2393/HUG | 10/08/2023 | 731 | GREEN ROYAL INFRA CON PVT LTD | 3243.22 | 283.71 | 45.17 | 9
3224 | HOOGHLY | Hooghly Division | DALIMBA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/12247 | New | Material Requisition To Resource Division | 1386/Hug | 15/05/2023 | 0 | Resource Division | 11.38 | 0 | 0 | 0
3225 | HOOGHLY | Hooghly Division | DALIMBA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/12247 | New | Material Requisition To Resource Division | 1264/2/HUG | 03/05/2023 | 0 | Resource Division | 4.63 | 0 | 0 | 0
3226 | HOOGHLY | Hooghly Division | DALIMBA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/12247 | New | Material Requisition To Resource Division | 3059/22/Hug | 11/10/2023 | 0 | Resource Division | 0.47 | 0 | 0 | 0
3227 | HOOGHLY | Electrical | DALIMBA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/12247 | New | Quotation for new service connection at Dalimba W/S Sch., T/W No. - II, Block - Polba-Dadpur, Dist. - Hooghly. | 350 | 11/10/2023 | 0 | WBSEDCL | 3.11 | 0 | 0 | 0
3228 | HOOGHLY | Electrical | DALIMBA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/12247 | New | Quotation for new service connection at Dalimba W/S Sch., T/W No. - I, Dist. - Hooghly | 283 | 13/09/2023 | 0 | WBSEDCL | 4.85 | 0 | 0 | 0
3229 | HOOGHLY | Hooghly Division | DALIMBA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/12247 | New | Ground Water Based Piped Water Supply Schemes (PWSS) under POLBA-DADPUR Block at DALIMBA, GHATAMPUR, HASNAN, KAMRAI, KUCHPALA, PATUL, UTTAR BABNAN (ZONE-I) & UTTAR BABNAN (ZONE-II) Mouzas including Construction of different capacities R.C.C. Over Head Reservoirs (OHRs), Sinking of Tube Wells, Laying Distribution Systems (LDS), Laying Rising Main Interconnection pipelines, providing Functional Household Tap Connections (FHTCs), Construction of Switch Rooms, Boundary Walls etc. under Hooghly Division P.H.E. Dte. in connection with JJM. | 955/HUG | 30/03/2023 | 887 | GREEN ROYAL INFRA CON PVT LTD | 3672.07 | 311.42 | 70.43 | 15
3230 | HOOGHLY | Electrical | DALIMBA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/12247 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dalimba water supply scheme, T.W. No.- I & II, Block: Polba - Dadpur, District- Hooghly under Electrical Division, PHE Dte. | 3487/ED | 30/12/2022 | 810 | A.K. ENTERPRISE | 20.38 | 16.47 | 66.04 | 90
3231 | HOOGHLY | Hooghly Division | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Material Requisition To Resource Division | 902/9/Hug | 27/03/2023 | 0 | Resource Division | 9.01 | 0 | 0 | 0
3232 | HOOGHLY | Hooghly Division | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Material Requisition To Resource Division | 1383/37/Hug | 15/05/2023 | 0 | Resource Division | 9.17 | 0 | 0 | 0
3233 | HOOGHLY | Hooghly Division | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Material Requisition To Resource Division | 1235/13/Hug | 28/04/2023 | 0 | Resource Division | 59.23 | 0 | 0 | 0
3234 | HOOGHLY | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Quotation bill of WBSEDCL new service connection charges at Aima Chapsara PWSS, TW-I | 526 | 14/12/2023 | 0 | WBSEDCL | 8.35 | 0 | 0 | 0
3235 | HOOGHLY | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Quotation bill of WBSEDCL new service connection charges at Aima Chapsara PWSS, TW-II | 525 | 14/12/2023 | 0 | WBSEDCL | 2.72 | 0 | 0 | 0
3236 | HOOGHLY | Hooghly Division | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Sinking of 2 nos 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tube Well Site of AIMA CHAPSARA W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. [2nd Call of WBPHE/EE/35/HUG/2022-23, Sl No-1] | 1200/HUG | 26/04/2023 | 45 | PRASUN ENTERPRISE (PRASUN BISWAS) | 28.83 | 27.45 | 95.23 | 100
3237 | HOOGHLY | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. | 1645/AE-II/ED | 29/07/2024 | 184 | DILIP KUMAR GHOSH | 0.87 | 0.58 | 66.3 | 0
3238 | HOOGHLY | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for Office of the Assistant Engineer - II, Electrical Division, PHE Dte | 218_AE-II_ED | 20/02/2024 | 182 | DILIP KUMAR GHOSH | 0.86 | 0.44 | 50.55 | 0
3239 | HOOGHLY | Hooghly Division | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of AIMA CHAPSARA Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | 651/Hug | 10/03/2023 | 60 | KAPTON | 12.29 | 12.29 | 100 | 100
3240 | HOOGHLY | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Aima Chapsara water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | 3456/ED | 30/12/2022 | 90 | TAMAL ENTERPRISE | 21.5 | 21.46 | 100 | 30
3241 | HOOGHLY | Hooghly Division | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Ayma Chapsara H/W site & Kamarkundu (Zone-VI) 3rd T/W site under Chandannagar Sub-Division PHE Dte. | 924/Chan | 05/11/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 0 | 100
3242 | HOOGHLY | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Fuel consumption bill 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No. WB-15C-5554 | 623 | 18/12/2024 | 0 | DILIP KUMAR GHOSH | 0.02 | 0 | 0 | 0
3243 | HOOGHLY | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for Office of the Assistant Engineer-II, Electrical Division, PHE Dte Car No.- WB-15C-5554 | 281 | 09/07/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
3244 | HOOGHLY | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No. WB-15C-5554 From 01.09.2024 to 30.09.2024 | 550 | 30/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.16 | 0 | 0 | 0
3245 | HOOGHLY | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No.WB-15C-5554 | 549 | 30/10/2024 | 0 | DILIP KUMAR GHOSH | 0.08 | 0 | 0 | 0
3246 | HOOGHLY | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Fuel consumption bill of 1 (one) no. Diesel luxuary Taxi on contract carriage for Office of the Assistant Engineer-II, Electrical Division, PHE Dte. From 01.05.2024 to 31.05.2024 WB-15C-5554 | 266 | 03/07/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
3247 | HOOGHLY | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Fuel consumption bill 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No. WB-15C-5554 From 01/10/2024 to 31/10/2024 | 619 | 05/12/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0 | 0
3248 | HOOGHLY | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for Office of the Assistant Engineer - II, Electrical Division, PHE Dte 01/07/2024 to 31/07/2024 WB-15C-5554 | 412 | 22/08/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
3249 | HOOGHLY | Electrical | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No.- WB-15C-5554 From 01.08.2024 to 31.08.2024 | 468 | 01/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
3250 | HOOGHLY | Hooghly Division | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | AIMA CHAPSARA Piped Water Supply Scheme with Laying Distribution System, FHTC & Construction of 300 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work at HARIPAL BLOCK under Chandannagar Sub-Division under Hooghly Division PHE Dte. | 2896/HUG | 22/12/2022 | 970 | PRASUN ENTERPRISE (PRASUN BISWAS) | 370.57 | 100.09 | 27.01 | 20
3251 | HOOGHLY | Hooghly Division | AIMA CHAPSARA PIPED WATER SUPPLY SCHEME , SM/11581 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of boundary walls at different TW site for AIMACHAPSARA Piped Water Supply Scheme under Chandannagar Sub-Division , District:- Hooghly | 2423/HUG | 11/08/2023 | 568 | AMBIAN INFRASTRUCTURE | 41.36 | 3.9 | 9.44 | 50
3252 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HARADITYA WATER SUPPLY SCHEME , SM/12015 | Retrofitting | Preparation & Improvement of foundation due to continuous comprehensive seepage after starting of excavation for raft foundation at Head Work Site of HARADITYA Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E. Dte. (Part-B) | 739/Arg | 29/09/2022 | 30 | ANUP PAUL | 1.48 | 0 | 0 | 0
3253 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HARADITYA WATER SUPPLY SCHEME , SM/12015 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of HARADITYA PWSS under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 1426/HUG | 17/05/2023 | 45 | GANESH RAY | 37.07 | 0 | 0 | 0
3254 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HARADITYA WATER SUPPLY SCHEME , SM/12015 | Retrofitting | Providing 1319 nos Functional Household Tap Connection (FHTC) within Haraditya & Shyamgram Village of Haraditya Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh] | 884/HUG | 29/04/2022 | 40 | ANUP PAUL | 62.53 | 54.75 | 100 | 0
3255 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HARADITYA WATER SUPPLY SCHEME , SM/12015 | Retrofitting | Providing 1301 nos Functional Household Tap Connection (FHTC) within Amgaon, Birati & Chhandra Village of Haraditya Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh] | 885/HUG | 29/04/2022 | 40 | PREMANANDA ROY BISWAS | 58.31 | 58.24 | 100 | 0
3256 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF HARADITYA WATER SUPPLY SCHEME , SM/12015 | Retrofitting | Construction of Boundary Wall, Internal Pathway at 2nd TW Site of HARADITYA Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 2739/HUG | 07/12/2022 | 30 | S.D ENTERPRISE (SAMIR KR. DAS) | 4.87 | 4.87 | 100 | 100
3257 | HOOGHLY | Hooghly Division | Jot ram mini pipe water supply scheme , SM/13672 | New | Material Requisition To Resource Division | 1385/6/Hug | 15/05/2023 | 0 | Resource Division | 0.47 | 0 | 0 | 0
3258 | HOOGHLY | Hooghly Division | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/13762 | New | Material Requisition To Resource Division | 1234/40/Hug | 28/04/2023 | 0 | Resource Division | 120.19 | 0 | 0 | 0
3259 | HOOGHLY | Hooghly Division | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/13762 | New | Material Requisition To Resource Division | 1385/44/Hug | 15/05/2023 | 0 | Resource Division | 12.89 | 0 | 0 | 0
3260 | HOOGHLY | Hooghly Division | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/13762 | New | Material Requisition To Resource Division | 3057/5/Hug | 11/10/2023 | 0 | Resource Division | 12.89 | 0 | 0 | 0
3261 | HOOGHLY | Hooghly Division | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/13762 | New | Sinking of 3 nos. tube-well (300 X 200 mm) by D.R. Rig method at HIRAPUR Z-II and UDNA Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 722/HUG | 05/03/2024 | 60 | ANIRUDDHA FARUQUE | 48.17 | 13.6 | 100 | 100
3262 | HOOGHLY | Electrical | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/13762 | New | Quotation of New Service Connection for Hirapur w/s Scheme,Zone-II,PH No-II Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13762) Application no-5004034787 Reference Id-503576010 | 127 | 17/05/2024 | 0 | WBSEDCL | 6.13 | 0 | 0 | 0
3263 | HOOGHLY | Electrical | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/13762 | New | Quotation money deposition for new service connection at Hirapur w/s scheme, Zone- II, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004210670 Reference ID- 503656455 SM Code- 13762 | 222 | 18/06/2024 | 0 | WBSEDCL | 3.09 | 0 | 0 | 0
3264 | HOOGHLY | Electrical | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/13762 | New | Quotation of New Service Connection for Hirapur w/s Scheme,Zone-II,PH No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte.(SM/13762). Application No-5004034769 Reference Id-503576011 | 53 | 12/04/2024 | 0 | WBSEDCL | 3.94 | 0 | 0 | 0
3265 | HOOGHLY | Electrical | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/13762 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hirapur water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | 780/ED | 09/02/2023 | 873 | M.D ENTERPRISE | 20.49 | 0 | 0 | 10
3266 | HOOGHLY | Hooghly Division | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/13762 | New | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 225.15 | 40.38 | 50
3267 | HOOGHLY | Electrical | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/13762 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for HIRAPUR PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1173/ED | 14/06/2024 | 90 | PS & ASSOCIATES | 10.75 | 0 | 0 | 50
3268 | HOOGHLY | Hooghly Division | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/13762 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0 | 0
3269 | HOOGHLY | Hooghly Division | Hirapur (Zone-II) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/13762 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) NOAPARA PWSS- 1 no¿s, (2) HAYATPUR PWSS- 2 no¿s, (3) HIRAPUR PWSS (Z-I)- 1 no¿s, (4) HIRAPUR PWSS (Z-II)- 1 no¿s (5) MAROKHANA PWSS (Z-I)- 1 no¿s, (6) MOSTAFAPUR PWSS- 2 no¿s, (7) NATIBPUR PWSS- 2 no¿s, (8) ROUTHKHANA PWSS- 1 no¿s, (9) HARISCHAK PWSS- 2 no¿s, (10) PALASPAI PWSS- 1 no¿s | 1154/Arg | 10/12/2024 | 31 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
3270 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF BATANAL WATER SUPPLY SCHEME , SM/11999 | Retrofitting | Providing 1591 nos Functional Household Tap Connection (FHTC) within Benga & Batanal Mouza of Batanal(Zone-I) Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh] | 886 | 29/04/2022 | 50 | M/S PRADYUT KUMAR HAZRA | 75.31 | 73.68 | 100 | 98
3271 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME , SM/12000 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within left out habitation of various Mouzas in Antpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte | 829/HUG | 11/03/2024 | 30 | SURAJIT SINGHA RAY | 30.4 | 30.4 | 100 | 99
3272 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME , SM/12000 | Retrofitting | Designing making and erection of Display Board using logo and tag line of JalJeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Lohagachhi village under Antpur PWSS (2 nos.) 2. Ranibazar village under Antpur PWSS (2 nos.) 3. Anarbati village under Antpur PWSS (2 nos.) | 170/SER | 11/03/2024 | 7 | TOTON MONDAL | 0.95 | 0.95 | 100 | 80
3273 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME , SM/12000 | Retrofitting | Designing making and erection of Display Board using logo and tag line of JalJeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Raipur village under Antpur PWSS (2 nos.) 2. Atpur village under Antpur PWSS (2 nos.) 3. Palgachha village under Antpur PWSS (2 nos.) | 171/SER | 11/03/2024 | 7 | TOTON MONDAL | 0.95 | 0.95 | 100 | 80
3274 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME , SM/12000 | Retrofitting | Repairing of Damaged Road due to FHTC Works at Ranibazar & Lohagacchi mouzas of Antpur W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | 549/SER | 19/09/2024 | 7 | TOTON MONDAL | 4.99 | 0 | 0 | 98
3275 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME , SM/12000 | Retrofitting | Providing 1250 nos Functional Household Tap Connection (FHTC) & extension of Laying Distribution System within the uncovered area of Antpur Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | 466/HUG | 26/02/2021 | 1039 | GHOSH CONCERN | 96.72 | 4.55 | 4.7 | 72
3276 | HOOGHLY | Hooghly Division | Chak Behala mini pipe water supply scheme , SM/13656 | New | Material Requisition To Resource Division | 1385/26/Hug | 15/05/2023 | 0 | Resource Division | 0.23 | 0 | 0 | 0
3277 | HOOGHLY | Hooghly Division | Rampur Mini Piped Water Supply Scheme , SM/13563 | New | MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-299 | 19/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 31.91 | 0 | 0 | 0
3278 | HOOGHLY | Electrical | Rampur Mini Piped Water Supply Scheme , SM/13563 | New | Mini Piped Water Supply Scheme | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0 | 0
3279 | HOOGHLY | Electrical | Rampur Mini Piped Water Supply Scheme , SM/13563 | New | Mini piped Water Supply scheme |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
3280 | HOOGHLY | Hooghly Division | Dewanchak Mini Piped Water Supply Scheme , SM/13586 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-245 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 26.52 | 0 | 0 | 0
3281 | HOOGHLY | Electrical | Dewanchak Mini Piped Water Supply Scheme , SM/13586 | New | Mini Piped Water Supply Scheme. | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0 | 0
3282 | HOOGHLY | Hooghly Division | Ghosha Mini Piped Water Supply Scheme , SM/13595 | New | Material Requisition To Resource Division | 1383/24/Hug | 15/05/2023 | 0 | Resource Division | 0.57 | 0 | 0 | 0
3283 | HOOGHLY | Hooghly Division | Belun Mini Piped Water Supply Scheme , SM/13552 | New | Material Requisition To Resource Division | 1385/8/Hug | 15/05/2023 | 0 | Resource Division | 0.52 | 0 | 0 | 0
3284 | HOOGHLY | Hooghly Division | Belun Mini Piped Water Supply Scheme , SM/13552 | New | MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-336 | 31/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 31.34 | 0 | 0 | 0
3285 | HOOGHLY | Hooghly Division | Belun Mini Piped Water Supply Scheme , SM/13552 | New | REQUISITION OF FUND FOR SAJAL GRAM SCHEME |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 29.54 | 0 | 0 | 0
3286 | HOOGHLY | Hooghly Division | Belun Mini Piped Water Supply Scheme , SM/13552 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME |  | 23/06/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 32.82 | 0 | 0 | 0
3287 | HOOGHLY | Electrical | Belun Mini Piped Water Supply Scheme , SM/13552 | New | Mini Piped water Supply Scheme | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
3288 | HOOGHLY | Hooghly Division | Durlabhpur Mini Piped Water Supply Scheme , SM/13561 | New | MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-294 | 19/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 29.83 | 0 | 0 | 0
3289 | HOOGHLY | Electrical | Durlabhpur Mini Piped Water Supply Scheme , SM/13561 | New | Mini Piped Water Supply Scheme | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0 | 0
3290 | HOOGHLY | Electrical | Durlabhpur Mini Piped Water Supply Scheme , SM/13561 | New | Mini piped Water Supply scheme |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
3291 | HOOGHLY | Hooghly Division | Bara Kumursa mini pipe water supply scheme , SM/13592 | New | Material Requisition To Resource Division | 1385/2/Hug | 15/05/2023 | 0 | Resource Division | 0.39 | 0 | 0 | 0
3292 | HOOGHLY | Hooghly Division | Bara Kumursa mini pipe water supply scheme , SM/13592 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-241 | 02/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.09 | 0 | 0 | 0
3293 | HOOGHLY | Electrical | Bara Kumursa mini pipe water supply scheme , SM/13592 | New | Mini Piped Water Supply Scheme. | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0 | 0
3294 | HOOGHLY | Hooghly Division | PARJANA PIPED WATER SUPPLY SCHEME , SM/13335 | New | Material Requisition To Resource Division | 109/ 11/Hug | 10/01/2023 | 0 | Resource Division | 11.55 | 0 | 0 | 0
3295 | HOOGHLY | Hooghly Division | PARJANA PIPED WATER SUPPLY SCHEME , SM/13335 | New | Material Requisition To Resource Division | 902/10/Hug | 27/03/2023 | 0 | Resource Division | 14.48 | 0 | 0 | 0
3296 | HOOGHLY | Hooghly Division | PARJANA PIPED WATER SUPPLY SCHEME , SM/13335 | New | Material Requisition To Resource Division | 1383/12/Hug | 15/05/2023 | 0 | Resource Division | 14.48 | 0 | 0 | 0
3297 | HOOGHLY | Hooghly Division | PARJANA PIPED WATER SUPPLY SCHEME , SM/13335 | New | Material Requisition To Resource Division | 3058/28/Hug | 11/10/2023 | 0 | Resource Division | 14.48 | 0 | 0 | 0
3298 | HOOGHLY | Electrical | PARJANA PIPED WATER SUPPLY SCHEME , SM/13335 | New | upply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Parjana water supply scheme, T.W. No.- I, II & III, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | 771/ED | 09/02/2023 | 90 | WEST BENGAL ENGINEERING CO. | 32.05 | 20.58 | 64.19 | 30
3299 | HOOGHLY | Hooghly Division | PARJANA PIPED WATER SUPPLY SCHEME , SM/13335 | New | PARJANA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under HARIPAL Block, District:- Hooghly [NEW SCHEME] | 1406/Hug | 17/05/2023 | 270 | S & P ENTERPRISE | 659.08 | 451.88 | 68.56 | 50
3300 | HOOGHLY | Hooghly Division | PARJANA PIPED WATER SUPPLY SCHEME , SM/13335 | New | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Barakamalpur (Z-4) 1st T/W site & Parjana 2nd T/W site under Chandannagar Sub-Division PHE Dte. | 921/Chan | 05/11/2024 | 15 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 0 | 100
3301 | HOOGHLY | Electrical | PARJANA PIPED WATER SUPPLY SCHEME , SM/13335 | New | Quotation Bill for New Service Connection at Parjana W/S. Sch. TW-II | 722 | 31/01/2024 | 0 | WBSEDCL | 7.3 | 0 | 0 | 0
3302 | HOOGHLY | Electrical | PARJANA PIPED WATER SUPPLY SCHEME , SM/13335 | New | Quotation Bill for New Service Connection at Parjana W/S. Sch. TW-I | 721 | 31/01/2024 | 0 | WBSEDCL | 8.41 | 0 | 0 | 0
3303 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF AMODGHATA PWSS FOR PROVIDING 600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. , SM/13357 | Retrofitting | Providing 232 nos Functional Household Tap Connection (FHTC) within the command area of Amodghata Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 2001/HUG | 12/11/2021 | 30 | R.K. TRADERS | 10.07 | 10.03 | 99.53 | 0
3304 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF AMODGHATA PWSS FOR PROVIDING 600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. , SM/13357 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of AMODGHATAPWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 1128/HUG | 19/04/2023 | 30 | ASIT KUMAR KHAMRUI | 27.23 | 21.72 | 100 | 55
3305 | HOOGHLY | Hooghly Division | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15250 | New | Material Requisition To Resource Division | 1386/56/Hug | 15/05/2023 | 0 | Resource Division | 6.75 | 0 | 0 | 0
3306 | HOOGHLY | Hooghly Division | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15250 | New | Material Requisition To Resource Division | 3059/34/Hug | 11/10/2023 | 0 | Resource Division | 6.75 | 0 | 0 | 0
3307 | HOOGHLY | Electrical | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15250 | New | Quotation for new service connection at Refaitpur W/S Sch., Zone - I, T/w No. - I, Dist. - Hooghly | 305 | 26/09/2023 | 0 | WBSEDCL | 6.1 | 0 | 0 | 0
3308 | HOOGHLY | Electrical | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15250 | New | Quotation Bill for New Service Connection at Refaitpur W/S. Sch. TW- I & II, & Z-II | 388&389 | 02/11/2023 | 0 | WBSEDCL | 11.2 | 0 | 0 | 0
3309 | HOOGHLY | Electrical | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15250 | New | Quotattion for new service connection at Refaitpur W/S Sch., Zon - I, T/W -II, Block - Chinsurah-Mogra, Dt. - Hooghly | 315 | 03/10/2023 | 0 | WBSEDCL | 13.11 | 0 | 0 | 0
3310 | HOOGHLY | Electrical | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15250 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Refaitpur water supply scheme Zone I TW No I and II and Zone II TW No I and II Block Chinsurah Mogra, District Hooghly under ED PHED. | 863/ED | 14/02/2023 | 90 | ORIENTAL ENGINEERING CO. | 40.5 | 19.09 | 94.26 | 90
3311 | HOOGHLY | Hooghly Division | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15250 | New | REFAITPUR ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHINSURAH MAGRA Block, District:- Hooghly [NEW SCHEME] | 684/Hug | 10/03/2023 | 270 | SATYA NARAYAN BISWAS | 261.02 | 157.29 | 60.26 | 40
3312 | HOOGHLY | Hooghly Division | REFAITPUR (ZONE-I) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15250 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. 1. Gurbari PWSS 2. Lokabati PWSS 3. Bishnupur PWSS 4. Kamalpur PWSS 5. Refaitpur Z-I PWSS 6. Barul PWSS | 139/CH | 20/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
3313 | HOOGHLY | Hooghly Division | REFAITPUR (ZONE-II) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15251 | New | Material Requisition To Resource Division | 3059/9/Hug | 11/10/2023 | 0 | Resource Division | 9.67 | 0 | 0 | 0
3314 | HOOGHLY | Electrical | REFAITPUR (ZONE-II) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15251 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Refaitpur water supply scheme Zone I TW No I and II and Zone II TW No I and II Block Chinsurah Mogra, District Hooghly under ED PHED. | 863/ED | 14/02/2023 | 90 | ORIENTAL ENGINEERING CO. | 40.5 | 19.92 | 98.37 | 90
3315 | HOOGHLY | Hooghly Division | REFAITPUR (ZONE-II) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15251 | New | REFAITPUR ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHINSURAH MAGRA Block, District:- Hooghly [NEW SCHEME] | 975/Hug | 31/03/2023 | 270 | DAS ENTERPRISE (SAMIR DAS) | 244.77 | 177.94 | 72.69 | 30
3316 | HOOGHLY | Hooghly Division | REFAITPUR (ZONE-II) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15251 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. 1. Dashghara PWSS 2. Patul PWSS 3. Durgapur PWSS 4. Khajurdaha PWSS 5. Refaitpur Z-II PWSS 6. Kalora PWSS | 140/CH | 20/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 50 | 30
3317 | HOOGHLY | Hooghly Division | REFAITPUR (ZONE-II) PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/15251 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Refaitpur Z-II PWSS 2. Sankhangar Chakbasberia PWSS 3. Basudebbati PWSS 4. Dantra PWSS 5. Goswami Malipara PWSS 6. Amra PWSS | 200/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 100 | 50
3318 | HOOGHLY | Hooghly Division | Source Augmentation of Santoshpur Piped Water Supply scheme, Block- Tarakeswar, District-Hooghly , SM/15793 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at SANTOSHPUR PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | 751/HUG | 15/03/2023 | 30 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 12.44 | 0 | 0 | 0
3319 | HOOGHLY | Hooghly Division | Source Augmentation of Santoshpur Piped Water Supply scheme, Block- Tarakeswar, District-Hooghly , SM/15793 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of Santoshpur Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. within Tarakeswar Block. | 1312/HUG | 10/05/2023 | 30 | SRI KRISHNA ENTERPRISE | 11.78 | 3.57 | 30.28 | 40
3320 | HOOGHLY | Electrical | Source Augmentation of Santoshpur Piped Water Supply scheme, Block- Tarakeswar, District-Hooghly , SM/15793 | Augmentation | Quotation money deposition for new service connection at Santoshpur w/s scheme, P.H. No.-3, Dist.-Hooghly under PHE Dte. Application No- 5004085290 Reference ID- 503609191 SM Code- 15793 | 129 | 17/05/2024 | 0 | WBSEDCL | 6.12 | 0 | 0 | 0
3321 | HOOGHLY | Electrical | Source Augmentation of Santoshpur Piped Water Supply scheme, Block- Tarakeswar, District-Hooghly , SM/15793 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Santoshpur water supply scheme, T.W. No. I, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | 1623/ED | 11/04/2023 | 720 | UNIVERSAL ENTERPRISES | 10.75 | 0 | 0 | 100
3322 | HOOGHLY | Electrical | Source Augmentation of Bamonjol PWSS , SM/15794 | Augmentation | Quotation of New Service Connection of Bamonjol W/S Scheme(Aug) TW No-3 District-Hooghly under Electrical Division, PHE Dte | 113 | 19/07/2023 | 0 | WBSEDCL | 0.79 | 0 | 0 | 0
3323 | HOOGHLY | Electrical | Source Augmentation of Bamonjol PWSS , SM/15794 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bamonjol water supply scheme, T.W. No. I, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | 1629/ED | 11/04/2023 | 90 | ANIK & CO. | 11.41 | 11.05 | 96.91 | 40
3324 | HOOGHLY | Hooghly Division | Source Augmentation of Bamonjol PWSS , SM/15794 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of BAMONJOL Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. within HARIPAL Block. | 1472/HUG | 19/05/2023 | 30 | GOURI ENTERPRISE | 11.8 | 11.12 | 100 | 100
3325 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. , SM/07952 | Retrofitting | FHTC |  | 24/09/2021 | 0 | LOKENIRMAN | 28.24 | 0 | 0 | 0
3326 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. , SM/07952 | Retrofitting | FHTC |  | 30/09/2021 | 0 | M/S S.S. ENTERPRISE | 26.38 | 0 | 0 | 0
3327 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. , SM/07952 | Retrofitting | Providing 390 nos Functional Household Tap Connection (FHTC) within the command area of HANRAL & DWARBASINI Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 460/Hug | 10/03/2022 | 25 | M/S R.M. CONSTRUCTION | 28.34 | 26.75 | 94.42 | 100
3328 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. , SM/07952 | Retrofitting | LOADING UNLOADING & SHIFTING OF DRILLING ACCESSORIES, SUPPORTING VEHICLES ALONG WITH RIG MACHINE JOHN/DR/1500-I FROM HANRAL (Z-II) PWSS, BLOCK - POLBA DADPUR, HOOGHLY DISTRICT TO PANCHLA STORE, HOWRAH, UNDER CDD, PHE DTE. | 519/CMSD-I | 21/10/2022 | 3 | DEV ENTERPRISE | 0.32 | 0 | 0 | 100
3329 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. , SM/07952 | Retrofitting | LOADING UNLOADING & SHIFTING OF DRILLING ACCESSORIES, SUPPORTING VEHICLES ALONG WITH RIG MACHINE JOHN/DR/1500-I FROM HANRAL (Z-I) PWSS, BLOCK- POLBA DADPUR, HOOGHLY DISTRICT TO PANCHLA STORE, HOWRAH, UNDER CDD, PHE DTE. | 491/CMSD-I | 28/09/2022 | 7 | DEV ENTERPRISE | 0.32 | 0 | 0 | 100
3330 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. , SM/07952 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR HANRAL W/S SCH, POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 293/CDD | 27/04/2022 | 30 | PADMA ENGINEERING & CO. | 11.23 | 9.23 | 100 | 100
3331 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. , SM/07952 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR HANRAL W/S SCH, POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 292/CDD | 27/04/2022 | 30 | PADMA ENGINEERING & CO. | 11.23 | 5.2 | 100 | 90
3332 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. , SM/07952 | Retrofitting | Providing 1507 nos F.H.T.C. in Samsara, Hodla,Aima,Kharsat, Rasulpur,Khidirpur, Dakshin Dadpur,Maheshwarpur& Tamila Village of Hanral Zone-II and its Adjoining Mouzas Water Supply Scheme UnderChinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dapur] | 1146/Hug | 29/06/2021 | 40 | LOKENIRMAN | 87 | 87 | 100 | 100
3333 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. , SM/07952 | Retrofitting | Providing1670 nos F.H.T.C. in Sarkhola, Hanral,Mogalpur,Kantul, Anantapur,Krishnapur, Shrirampur,Kantagare & Sekendarpur Village of Hanral Zone-I and its Adjoining Mouzas Water Supply Scheme UnderChinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dapur] | 938/Hug | 06/05/2021 | 40 | M/S S.S. ENTERPRISE | 96.09 | 77.65 | 100 | 100
3334 | HOOGHLY | Electrical | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und , SM/16447 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Krishnarampur water supply scheme, T.W. No. I, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | 1635/ED | 11/04/2023 | 90 | D.S. ENTERPRISE | 11.41 | 11.13 | 97.55 | 70
3335 | HOOGHLY | Central Drilling | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und , SM/16447 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR KRISHNARAMPUR W/S SCH, CHANDITALA-I BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 1999/CDD | 08/02/2023 | 30 | UNIVERSAL ENTERPRISES | 12.65 | 11 | 100 | 0
3336 | HOOGHLY | Hooghly Division | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und , SM/16447 | Augmentation | Material Requisition To Resource Division | 1384/21/Hug | 15/05/2023 | 0 | Resource Division | 8.93 | 0 | 0 | 0
3337 | HOOGHLY | Electrical | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und , SM/16447 | Augmentation | Quotation bill for new service connection at Krishnarampur W/S. Sch. PH-III | 31 | 12/05/2023 | 0 | WBSEDCL | 2.37 | 0 | 0 | 0
3338 | HOOGHLY | Electrical | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und , SM/16447 | Augmentation | New service connection charges for Krishnarampur w/s scheme, PH No.-III | 86 | 12/07/2023 | 0 | WBSEDCL | 2.37 | 0 | 0 | 0
3339 | HOOGHLY | Hooghly Division | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und , SM/16447 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed T.W. with distribution system with FHTC of KRISHNARAMPUR W/S Scheme under Serampore Sub - Division P.H.E. Dte. | 1172/HUG | 20/04/2023 | 45 | TAPAS ADHYA | 63.38 | 51.97 | 100 | 35
3340 | HOOGHLY | Electrical | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und , SM/16447 | Augmentation | Quotation bill for new service connection charges at Krishnarampur PWSS P.H. No.-IV, Hooghly. Application No. 5004062824 Ref ID: 503597308 | 43 | 09/04/2024 | 0 | WBSEDCL | 3.42 | 0 | 0 | 0
3341 | HOOGHLY | Electrical | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und , SM/16447 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KRISHNARAMPUR PIPED W/S SCHEME, T.W. No. IV, Block: Chanditala - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1198/ED | 14/06/2024 | 322 | P.P. CONCERN | 10.75 | 0 | 0 | 75
3342 | HOOGHLY | Hooghly Division | Development of Krishnarampur Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by Local Panchayat und , SM/16447 | Augmentation | Estimate for Construction of boundary wall, Internal Pathway and allied works at 3rd TW Site of Krishnarampur Water Supply Scheme under Serampore sub Division of Hooghly Division P.H.E. Dte. | 64/SER | 20/01/2025 | 7 | SURAJIT SINGHA RAY | 4.42 | 0 | 0 | 0
3343 | HOOGHLY | Hooghly Division | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16121 | Augmentation | Sinking of I (one) No Big dia tube well (250 mm X 150mm) with supply of PVC Pipe and strainer and having depth upto 150 M at 3rd TW site of Sabalsinghapur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 1413/Hug | 12/07/2022 | 30 | SUBHAJIT BISWAS | 7.88 | 7.32 | 92.84 | 0
3344 | HOOGHLY | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16121 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sabalsinghapur water supply scheme, T.W. No. IV, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. | 2048/ED | 01/12/2022 | 90 | BOSE & CHATTERJEE INDUSTRIES | 10.57 | 0 | 0 | 0
3345 | HOOGHLY | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16121 | Augmentation | "Quotation Bill for New Service Connection at Sabalsinghapur W/S. Sch. PH-IV Hooghly" | 180 | 09/03/2023 | 0 | WBSEDCL | 2.75 | 0 | 0 | 0
3346 | HOOGHLY | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16121 | Augmentation | Quotation Bill for New Service Connection at Sabalsinghapur W/S. Sch. PH-III | 180 | 09/03/2023 | 0 | WBSEDCL | 2.81 | 0 | 0 | 0
3347 | HOOGHLY | Hooghly Division | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16121 | Augmentation | Protection works and other allied works at 2nd TubeWell Sites of Soaluk & Sabalsinghapur Water Supply Scheme under Arambagh Sub Division of Hooghly Division P.H.E Dte. | 4052/HUG | 19/12/2024 | 90 | TANISA ENTERPRISE | 15.54 | 0 | 0 | 0
3348 | HOOGHLY | Hooghly Division | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16121 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of SABALSINGHAPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 4078/HUG | 19/12/2024 | 90 | CHAKRABORTY ENTERPRISE | 14.1 | 0 | 0 | 0
3349 | HOOGHLY | Hooghly Division | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16121 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system, For Source Augmentation of SABALSINGHAPUR W/S Scheme under Arambagh Sub - Division P.H.E. Dte. | 1443/HUG | 18/05/2023 | 390 | KARALI MOHAN KHAMRUI | 31.29 | 31.26 | 100 | 94
3350 | HOOGHLY | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16121 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Sabalsinghapur water supply scheme, T.W. No. III, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. | 3442/ED | 11/08/2023 | 90 | BISALAXMI ENTERPRISE | 10.74 | 10.66 | 100 | 25
3351 | HOOGHLY | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16121 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sabalsinghapur water supply scheme, T.W. No. IV, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. | 4190/ED | 01/11/2023 | 90 | D. K. ELECTRIC | 10.83 | 10.75 | 100 | 40
3352 | HOOGHLY | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16121 | Augmentation | Quotation money deposition for new service connection at Udna w/s scheme, T.W. No.-III, Sabal Singapur pwss, Dist.-Hooghly under PHE Dte. Application No- 5004235310 Reference ID- 5004235310 SM Code- 16121 | 220 | 18/06/2024 | 0 | WBSEDCL | 5.73 | 0 | 0 | 0
3353 | HOOGHLY | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16121 | Augmentation | Quotation money deposition for new service connection at Udna w/s scheme, T.W. No.-IV, Sabal Singapur pwss, Dist.-Hooghly under PHE Dte. Application No- 5004235292 Reference ID- 503666262 SM Code- 16121 | 221 | 18/06/2024 | 0 | WBSEDCL | 4.03 | 0 | 0 | 0
3354 | HOOGHLY | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block , SM/16121 | Augmentation | Quotation money deposition for new service connection at Udna w/s scheme, T.W. No.-II, Sabal Singapur pwss, Dist.-Hooghly under PHE Dte. Application No- 5004234490 Reference ID- 503666255 SM Code- 16121 | 219 | 18/06/2024 | 0 | WBSEDCL | 7.27 | 0 | 0 | 0
3355 | HOOGHLY | Central Drilling | Development of ANIYA Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC. Block : Chanditala-I, Distric , SM/15898 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS.) BY UTILISING DEPARTMENTAL RIG MACHINERIES FOR ANIYA SCHEME (P/H-3), CHANDITALA-I BLOCK UNDER HOOGHLY DISTRICT, CENTRAL DRILLING DIVISION , PHE DTE. | 872/CDD | 11/07/2023 | 30 | UTTAM KUMAR CHATTERJEE | 10.73 | 10.41 | 100 | 100
3356 | HOOGHLY | Hooghly Division | Development of ANIYA Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC. Block : Chanditala-I, Distric , SM/15898 | Augmentation | Material Requisition To Resource Division | 1384/8/Hug | 16/05/2023 | 0 | Resource Division | 1.23 | 0 | 0 | 0
3357 | HOOGHLY | Electrical | Development of ANIYA Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC. Block : Chanditala-I, Distric , SM/15898 | Augmentation | Aniya water supply scheme,P H No-3 | 142 | 25/07/2023 | 0 | WBSEDCL | 3.2 | 0 | 0 | 0
3358 | HOOGHLY | Electrical | Development of ANIYA Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC. Block : Chanditala-I, Distric , SM/15898 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Aniya water supply scheme, T.W. No. I, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | 1627/ED | 11/04/2023 | 90 | ANIK & CO. | 11.41 | 11.11 | 97.37 | 85
3359 | HOOGHLY | Hooghly Division | Development of ANIYA Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC. Block : Chanditala-I, Distric , SM/15898 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed T.W. with distribution system & FHTC For Development of ANIYA W/S Scheme under Serampore Sub - Division P.H.E. Dte. | 1442/HUG | 18/05/2023 | 30 | M/S KAMALA ENTERPRISE | 26.42 | 14.91 | 100 | 80
3360 | HOOGHLY | Central Drilling | Development of ANIYA Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC. Block : Chanditala-I, Distric , SM/15898 | Augmentation | Additional work for construction of tube well at Aniya PWSS TW-I, Chanditala-I Block, Hooghly District by utilizing skilled departmental crew and departmental mechaneries CDD, PHE Dte. | 193/CMSD-II | 26/07/2023 | 10 | UTTAM KUMAR CHATTERJEE | 0.67 | 0.69 | 100 | 100
3361 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15900 | Augmentation | Material Requisition To Resource Division | 3059/28/Hug | 11/10/2023 | 0 | Resource Division | 1.85 | 0 | 0 | 0
3362 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15900 | Augmentation | Material Requisition To Resource Division | 3004/Hug | 05/10/2023 | 0 | Resource Division | 1.5 | 0 | 0 | 0
3363 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15900 | Augmentation | Quotation for new service connection at Patna Bhirabpur W/S Sch. T/W - I (Aug.), Dist. - Hooghly | 259 | 05/09/2023 | 0 | WBSEDCL | 5.61 | 0 | 0 | 0
3364 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15900 | Augmentation | Horizontal Auger boring with water jet system including Protection Work at Patna Bhairabpur W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | 3676/HUG | 13/11/2024 | 30 | SAMRAT CONSTRUCTION | 8.16 | 0 | 0 | 0
3365 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15900 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Patna Bhairavpur water supply scheme, T.W. No. I, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | 1636/ED | 11/04/2023 | 90 | DIPA CHHETRI | 11.5 | 11.47 | 100 | 90
3366 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15900 | Augmentation | Maintanance work for improvement of water supply in distribution system at Patna Bhairabpur W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | 24/CH | 05/01/2024 | 15 | SUNITI MAIRA | 4.47 | 0 | 0 | 50
3367 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15900 | Augmentation | Laying of pipe line and other necessary maintanance work for improvement of water supply in distribution system at Patna Bhairabpur W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | 25/CH | 05/01/2024 | 15 | SUNITI MAIRA | 4.67 | 4.54 | 100 | 50
3368 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/15900 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | 882/HUG | 27/03/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 13.08 | 100 | 65
3369 | HOOGHLY | Hooghly Division | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/15913 | New | Material Requisition To Resource Division | 3057/10/Hug | 11/10/2023 | 0 | Resource Division | 13.55 | 0 | 0 | 0
3370 | HOOGHLY | Hooghly Division | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/15913 | New | Material Requisition To Resource Division | 1234/17/Hug | 28/04/2023 | 0 | Resource Division | 42.83 | 0 | 0 | 0
3371 | HOOGHLY | Electrical | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/15913 | New | Quotation Bill for New Service Connection at Dahar Kundu W/S. Sch.TW-I, Z-II | 588 | 28/12/2023 | 0 | WBSEDCL | 6.53 | 0 | 0 | 0
3372 | HOOGHLY | Electrical | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/15913 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for DAHARKUNDU PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1160/ED | 14/06/2024 | 90 | B.P. TRADING CORPORATION | 10.75 | 0 | 0 | 0
3373 | HOOGHLY | Electrical | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/15913 | New | Quotation of New Service Connection for Dahar Kundu w/s Scheme,Zone-II,TW No-II Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/15913) Application No-5004015927 Reference Id-503563368 | 754 | 16/02/2024 | 0 | WBSEDCL | 16.1 | 0 | 0 | 0
3374 | HOOGHLY | Electrical | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/15913 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dahar Kundu water supply scheme, Zone-II, T.W. No.- I & II, Block: Armbag, District- Hooghly under Electrical Division, PHE Dte. | 1240/ED | 06/03/2023 | 787 | ALPHA ENTERPRISE | 20.47 | 0 | 0 | 30
3375 | HOOGHLY | Hooghly Division | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/15913 | New | BALUNDI,SELALPUR, MADHABPUR, DAHARKUNDU ZONE-II Piped Water Supply Scheme with T.W, SWITCH ROOM , BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at ARAMBAGH Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | 3191/HUG | 31/10/2023 | 731 | S & P ENTERPRISE | 2296.42 | 176.39 | 37.14 | 30
3376 | HOOGHLY | Hooghly Division | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/15913 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) MAYAPUR PWSS (Z-II)- 1no¿s (2) BALUNDI PWSS - 4no¿s (3) BHALIA PWSS (Z-I)- 2 no¿s (4) BHALIA PWSS (Z-II)- 1 no¿s (5) DAHARKUNDU PWSS (Z-I)- 2 no¿s, (6) DAHARKUNDU PWSS (Z-II)- 2 no¿s, (7) GOBINDANAGAR PWSS(Z-I) ¿2 no¿s | 1150/Arg | 10/12/2024 | 31 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0 | 0 | 0
3377 | HOOGHLY | Hooghly Division | AUGMENTATION OF HANRAL Z-I PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/16119 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of HARALPWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 1134/HUG | 19/04/2023 | 30 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 14.97 | 14.95 | 100 | 100
3378 | HOOGHLY | Hooghly Division | AUGMENTATION OF HANRAL Z-I PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/16119 | Augmentation | Material Requisition To Resource Division | 1386/52/Hug | 15/05/2023 | 0 | Resource Division | 1.23 | 0 | 0 | 0
3379 | HOOGHLY | Electrical | AUGMENTATION OF HANRAL Z-I PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/16119 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT HANRAL W/S SCHEME, T/W NO. - III, DIST. - HOOGHLY | 45 | 23/05/2023 | 0 | WBSEDCL | 10.88 | 0 | 0 | 0
3380 | HOOGHLY | Electrical | AUGMENTATION OF HANRAL Z-I PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/16119 | Augmentation | Quotation Bill for New Service Connection at Hanral W/S. Sch. PH-III, Z-I Hooghly | 179 | 09/03/2023 | 0 | WBSEDCL | 2.86 | 0 | 0 | 0
3381 | HOOGHLY | Electrical | AUGMENTATION OF HANRAL Z-I PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/16119 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hanral water supply scheme, Zone-I, T.W. No. III, Block: Polba Dadpur, District - Hooghly under Electrical Division, PHE Dte. | 969/ED | 25/02/2023 | 90 | TRIDENT ENTERPRISE | 11.08 | 2.93 | 20.94 | 90
3382 | HOOGHLY | Electrical | AUGMENTATION OF HANRAL Z-I PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/16119 | Augmentation | Quotation for new service connection at Hanral W/S Sch., Zone -I, T/W No. - III [SM/16119] under SM/Dadpur, WBSEDCL, Ref Id. - 503657583, dt. - 25-06-2024, Application No. - 5004214131 | 256 | 03/07/2024 | 0 | WBSEDCL | 3.53 | 0 | 0 | 0
3383 | HOOGHLY | Hooghly Division | AUGMENTATION OF HANRAL Z-I PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK , SM/16119 | Augmentation | Sinking of tube-well, LDS, Rising Main, Connection with Existing FHTC, construction of switch-room & boundary wall & Repairing of Existing Switch Rooms, Boundary walls at different TW sites of both zones for Augmentation of HANRAL Piped Water Supply Scheme under POLBA DADPUR Block, District:- Hooghly | 1683/HUG | 08/06/2023 | 180 | ASIA CONSTRUCTION | 503.22 | 116.17 | 23.08 | 45
3384 | HOOGHLY | Hooghly Division | KALORA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18099 | New | Material Requisition To Resource Division | 3059/8/Hug | 11/10/2023 | 0 | Resource Division | 3.22 | 0 | 0 | 0
3385 | HOOGHLY | Hooghly Division | KALORA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18099 | New | Material Requisition To Resource Division | 3004/13/Hug | 05/10/2023 | 0 | Resource Division | 2.71 | 0 | 0 | 0
3386 | HOOGHLY | Hooghly Division | KALORA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18099 | New | Material Requisition To Resource Division | 1386/4/Hug | 15/05/2023 | 0 | Resource Division | 3.22 | 0 | 0 | 0
3387 | HOOGHLY | Electrical | KALORA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18099 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kalora water supply scheme, T.W. No. I & II, Block: Polba Dadpur, District - Hooghly under Electrical Division, PHE Dte. | 1927/ED | 15/05/2023 | 90 | MAA KALI ENTERPRISE | 22.96 | 11.19 | 48.75 | 50
3388 | HOOGHLY | Hooghly Division | KALORA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18099 | New | KALORA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. Block Polba-Dadpur, District:- Hooghly [NEW SCHEME] | 2098/HUG | 19/07/2023 | 90 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 98.59 | 18.07 | 18.33 | 20
3389 | HOOGHLY | Electrical | KALORA PIPED W/S SCHEME (FOR UNCOVERED AREA) UNDER POLBA DADPUR BLOCK , SM/18099 | New | Quotation for new service connection at Kalora W/S Sch.,Near Majhar, [SM/18099], T/W No. - I, Block - Polba-Dadpur under Bandel CCC, WBSEDCL | 850 | 07/03/2024 | 0 | WBSEDCL | 10.7 | 0 | 0 | 0
3390 | HOOGHLY | Hooghly Division | Bara Mallikpur Mini Piped Water Supply Scheme, Block- Dhaniakhali, District-Hooghly , SM/18102 | New | Material Requisition To Resource Division | 1386/44/Hug | 15/05/2023 | 0 | Resource Division | 0.59 | 0 | 0 | 0
3391 | HOOGHLY | Electrical | Bara Mallikpur Mini Piped Water Supply Scheme, Block- Dhaniakhali, District-Hooghly , SM/18102 | New | Quotation Bill for New Service Connection at Basa Mallikpur mini piped W/S. Sch. | 452 | 29/11/2023 | 0 | WBSEDCL | 0.32 | 0 | 0 | 0
3392 | HOOGHLY | Hooghly Division | Bara Mallikpur Mini Piped Water Supply Scheme, Block- Dhaniakhali, District-Hooghly , SM/18102 | New | Ground Water based BARAMALLIKPUR Piped Water Supply Scheme in Dhaniakhali Block under Chinsurah Sub-Division P.H.E. Dte. District:- Hooghly [NEW SCHEME] | 1364/HUG | 12/05/2023 | 90 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.69 | 31.77 | 100 | 98
3393 | HOOGHLY | Electrical | Bara Mallikpur Mini Piped Water Supply Scheme, Block- Dhaniakhali, District-Hooghly , SM/18102 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bara Mallikpur Mini Piped W/S Scheme Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. | 5175/ED | 28/12/2023 | 90 | RISHAV ENTERPRISE | 7.25 | 7.25 | 100 | 55
3394 | HOOGHLY | Hooghly Division | Bara Mallikpur Mini Piped Water Supply Scheme, Block- Dhaniakhali, District-Hooghly , SM/18102 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Uttar HazipurMini PWSS 2. Bara Mallikpur Mini PWSS 3. Sripala Mini PWSS 4. Alasin Mini PWSS 5. Chautpur Mini PWSS 6. Jangalpur Mini PWSS | 272/CH | 14/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
3395 | HOOGHLY | Hooghly Division | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY , SM/18320 | New | Material Requisition To Resource Division | 3060/10/Hug | 11/10/2023 | 0 | Resource Division | 27.04 | 0 | 0 | 0
3396 | HOOGHLY | Hooghly Division | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY , SM/18320 | New | Material Requisition To Resource Division | 3005/1/Hug | 05/10/2023 | 0 | Resource Division | 65.04 | 0 | 0 | 0
3397 | HOOGHLY | Electrical | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY , SM/18320 | New | Quotation Bill for New Service Connection at Mundalika W/S. Sch. PH-I, Z-II | 623 | 08/01/2024 | 0 | WBSEDCL | 8.9 | 0 | 0 | 0
3398 | HOOGHLY | Electrical | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY , SM/18320 | New | Quotation for New service connection at Mundalika W/S. Sch.Z-I, PH-I | 826 | 01/03/2024 | 0 | WBSEDCL | 5.4 | 0 | 0 | 0
3399 | HOOGHLY | Electrical | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY , SM/18320 | New | Quotation Bill for New Service Connection at Mundalika W/S. Sch. Z-I, PH-I | 664 | 11/01/2024 | 0 | WBSEDCL | 3.37 | 0 | 0 | 0
3400 | HOOGHLY | Electrical | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY , SM/18320 | New | Quotation Bill for New Service Connection at Mundalika W/S. Sch. PH-II, Z-II | 622 | 08/01/2024 | 0 | WBSEDCL | 12.14 | 0 | 0 | 0
3401 | HOOGHLY | Hooghly Division | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY , SM/18320 | New | MUNDALIKA ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS,Rising Main, FHTC, Construction of 300 cum capacity RCC OHR At ZONE-I & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block, District:- Hooghly [NEW SCHEME] | 2295/HUG | 03/08/2023 | 727 | GHOSH CONCERN | 585.3 | 228.02 | 38.96 | 50
3402 | HOOGHLY | Electrical | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY , SM/18320 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mundalika water supply scheme, Zone-I, T.W. No. I & II and Zone-II, T.W. No. I & II Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | 3176/ED | 28/07/2023 | 613 | R.N.S. TRADING | 43.65 | 0 | 0 | 10
3403 | HOOGHLY | Hooghly Division | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY , SM/18320 | New | MUNDALIKA ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR At ZONE-I & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block of Serampore Sub-Division of Hooghly Division, PHE Dte. [NEW SCHEME] | 2293/HUG | 03/08/2023 | 821 | JAL PRAVAHIKA PVT. LTD | 608.12 | 201.6 | 33.15 | 20
3404 | HOOGHLY | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME , SM/11291 | New | Route Survey, Design Drawing & DPR Preparation of Naita PWSS under Chandannagar Sub - Division, PHE Dte. | 513/Chan | 29/09/2022 | 15 | ENVIROTECH SOLUTIONS | 5.15 | 5.15 | 100 | 0
3405 | HOOGHLY | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME , SM/11291 | New | "NAITA" Piped Water Supply Scheme With LDS, FHTC & Construction of 350 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at TARAKESWAR Block under Chandannagar Sub - Division Under Hooghly Division PHE Dte. | 2546/HUG | 24/11/2022 | 180 | SIBSANKAR CHOWDHURY | 504.76 | 241.93 | 47.93 | 65
3406 | HOOGHLY | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME , SM/11291 | New | Sinking of 2 nos 300 X 200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tube Well Site of NAITA W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 158/HUG | 16/01/2023 | 45 | M/S SYCHROTECH INDUSTRY | 28.77 | 0 | 0 | 0
3407 | HOOGHLY | Central Drilling | NAITA PIPED WATER SUPPLY SCHEME , SM/11291 | New | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x180 Mtrs.) byn utilising departmental rig machineries for naita W/S Scheme (TW-I & II), Tarakeswar Block under Hooghly District, CDD, PHE Dte. | 873/CDD | 11/07/2023 | 30 | CHANDA ENTERPRISE | 24.62 | 11.57 | 47 | 50
3408 | HOOGHLY | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME , SM/11291 | New | Material Requisition To Resource Division | 109/ 24/Hug | 10/01/2023 | 0 | Resource Division | 40.3 | 0 | 0 | 0
3409 | HOOGHLY | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME , SM/11291 | New | Material Requisition To Resource Division | 902/11/Hug | 27/03/2023 | 0 | Resource Division | 13.29 | 0 | 0 | 0
3410 | HOOGHLY | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME , SM/11291 | New | Material Requisition To Resource Division | 1383/35/Hug | 15/05/2023 | 0 | Resource Division | 4.49 | 0 | 0 | 0
3411 | HOOGHLY | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME , SM/11291 | New | Material Requisition To Resource Division | 3003/Hug | 05/10/2023 | 0 | Resource Division | 41.04 | 0 | 0 | 0
3412 | HOOGHLY | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME , SM/11291 | New | Material Requisition To Resource Division | 3058/36/Hug | 11/10/2023 | 0 | Resource Division | 13.24 | 0 | 0 | 0
3413 | HOOGHLY | Electrical | NAITA PIPED WATER SUPPLY SCHEME , SM/11291 | New | Naita w/s scheme,P H No -I | 307 | 26/09/2023 | 0 | WBSEDCL | 4.39 | 0 | 0 | 0
3414 | HOOGHLY | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME , SM/11291 | New | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of NAITA Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | 653/Hug | 10/03/2023 | 60 | GOURI ENTERPRISE | 12.25 | 12.25 | 100 | 50
3415 | HOOGHLY | Hooghly Division | NAITA PIPED WATER SUPPLY SCHEME , SM/11291 | New | Sinking of 4 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Berabari (3rd TWS), Gouribati (3rd TWS), Naita (2nd TWS), Barakamalpur (2nd TWS) W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | 3379/HUG | 21/11/2023 | 45 | OSMAN SEKH | 64.2 | 31.65 | 100 | 100
3416 | HOOGHLY | Electrical | NAITA PIPED WATER SUPPLY SCHEME , SM/11291 | New | Quotation for new service connection for NAITA water supply scheme PH NO-II , Dist- Hooghly Application NO.-5004032139 Ref. ID- 503573584 SM/11291 | 803 | 27/02/2024 | 0 | WBSEDCL | 6.57 | 0 | 0 | 0
3417 | HOOGHLY | Electrical | NAITA PIPED WATER SUPPLY SCHEME , SM/11291 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Naita water supply scheme, T.W. No. I & II, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | 3470/ED | 30/12/2022 | 810 | GOENKA ENTERPRISE | 21.49 | 15.43 | 71.91 | 70
3418 | HOOGHLY | Hooghly Division | GROUND BASED PIPED WATER SUPPLY SCHEME FOR DIARA PWSS , SM/17628 | New | Material Requisition To Resource Division | 902/4/Hug | 27/03/2023 | 0 | Resource Division | 14.2 | 0 | 0 | 0
3419 | HOOGHLY | Hooghly Division | GROUND BASED PIPED WATER SUPPLY SCHEME FOR DIARA PWSS , SM/17628 | New | Material Requisition To Resource Division | 1235/3/Hug | 28/04/2023 | 0 | Resource Division | 33.96 | 0 | 0 | 0
3420 | HOOGHLY | Hooghly Division | GROUND BASED PIPED WATER SUPPLY SCHEME FOR DIARA PWSS , SM/17628 | New | Material Requisition To Resource Division | 1383/16/Hug | 15/05/2023 | 0 | Resource Division | 3.01 | 0 | 0 | 0
3421 | HOOGHLY | Electrical | GROUND BASED PIPED WATER SUPPLY SCHEME FOR DIARA PWSS , SM/17628 | New | Quotation New Service Connection for Diara Water Supply Scheme, Block - Singur, Dist - hooghly | 172 | 10/08/2023 | 0 | WBSEDCL | 3.96 | 0 | 0 | 0
3422 | HOOGHLY | Electrical | GROUND BASED PIPED WATER SUPPLY SCHEME FOR DIARA PWSS , SM/17628 | New | Quotation Bill for New Service Connection at Diara W/S. Sch. TW-II | 714 | 29/01/2024 | 0 | WBSEDCL | 8.07 | 0 | 0 | 0
3423 | HOOGHLY | Hooghly Division | GROUND BASED PIPED WATER SUPPLY SCHEME FOR DIARA PWSS , SM/17628 | New | DIARA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub-Division of Hooghly Division P.H.E Dte under SINGUR Block, District:- Hooghly [NEW SCHEME] | 1678/HUG | 08/06/2023 | 938 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 451.08 | 180.65 | 40.05 | 60
3424 | HOOGHLY | Hooghly Division | GROUND BASED PIPED WATER SUPPLY SCHEME FOR DIARA PWSS , SM/17628 | New | Horizontal road crossing by trenchless method across BTC Road (PWD) at yuger more & allied works in Diara pwss under Chandannagar Sub-Division, of Hooghly Division P.H.E. Dte | 3433/HUG | 03/10/2024 | 335 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 11.39 | 0 | 0 | 80
3425 | HOOGHLY | Hooghly Division | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18288 | New | Material Requisition To Resource Division | 3057/1/Hug | 11/10/2023 | 0 | Resource Division | 17.17 | 0 | 0 | 0
3426 | HOOGHLY | Electrical | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18288 | New | Quotation Bill for New Service Connection at Madhabpur W/S. Sch. TW-I | 399 | 09/11/2023 | 0 | WBSEDCL | 3.86 | 0 | 0 | 0
3427 | HOOGHLY | Electrical | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18288 | New | Quotation for new service connection charge at Madhabpur PWSS, TW - II | 463 | 01/12/2023 | 0 | WBSEDCL | 8.57 | 0 | 0 | 0
3428 | HOOGHLY | Electrical | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18288 | New | Hiring of Luxury Car (BS-IV) for the Official use of the Executive Engineer, Electrical Division, PHE Dte. w.e.f. 01.12.2023 to 31.05.2024. | 876/AE-I/ED | 23/11/2023 | 182 | TRIDIP SARKAR | 0.87 | 2.4 | 275.53 | 10
3429 | HOOGHLY | Hooghly Division | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18288 | New | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at SELALPUR (2Nos.), MADHABPUR (2Nos.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3469/HUG | 04/10/2024 | 90 | AMWOODO ECO PRODUCTS PRIVATE LIMITED | 47.22 | 0 | 0 | 0
3430 | HOOGHLY | Electrical | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18288 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MADHABPUR PIPED W/S SCHEME, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1159/ED | 14/06/2024 | 90 | SANKAR PRASAD DUTTA & CO. | 10.91 | 0 | 0 | 0
3431 | HOOGHLY | Hooghly Division | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18288 | New | Sinking of 2 nos 300 X200 mm dia Tube Well ,210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Siteof MADHABPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte | 3526/HUG | 22/10/2024 | 30 | GITA ENTERPRISE | 31.35 | 0 | 0 | 0
3432 | HOOGHLY | Hooghly Division | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18288 | New | BALUNDI,SELALPUR, MADHABPUR, DAHARKUNDU ZONE-II Piped Water Supply Scheme with T.W, SWITCH ROOM , BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at ARAMBAGH Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | 3191/HUG | 31/10/2023 | 731 | S & P ENTERPRISE | 2296.42 | 294.27 | 48.31 | 30
3433 | HOOGHLY | Hooghly Division | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT , SM/18288 | New | Horizontal Auger boring with water jet system & other ancillary works at Madhabpur Water Suply Scheme under Serampur Sub Division of Hooghly Division PHE Dte, | 333/HUG | 05/02/2025 | 60 | ARUN SEAL AND CO. | 28.35 | 0 | 0 | 0
3434 | HOOGHLY | Hooghly Division | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18307 | New | Material Requisition To Resource Division | 3057/32/Hug | 11/10/2023 | 0 | Resource Division | 15.03 | 0 | 0 | 0
3435 | HOOGHLY | Hooghly Division | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18307 | New | Material Requisition To Resource Division | 3616/Hug | 06/12/2023 | 0 | Resource Division | 20.86 | 0 | 0 | 0
3436 | HOOGHLY | Electrical | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18307 | New | Quotation Bill for New Service Connection at Kumursha W/S. Sch. | 488 | 06/12/2023 | 0 | WBSEDCL | 4.16 | 0 | 0 | 0
3437 | HOOGHLY | Hooghly Division | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18307 | New | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for KUMURSA Piped Water Supply Scheme underARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. | 3463/HUG | 04/10/2024 | 60 | P. B. ENTERPRISE(PINTU BHADURI) | 53.64 | 0 | 0 | 0
3438 | HOOGHLY | Electrical | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18307 | New | Quotation of New Service Connection for Kumursa w/s Scheme,PH No-II Block-Goghat-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18307) Application No-5004423612 Reference Id-503761600 | 513 | 21/10/2024 | 0 | WBSEDCL | 6.05 | 0 | 0 | 0
3439 | HOOGHLY | Hooghly Division | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18307 | New | KUMURSA Piped Water Supply Scheme with Sinking of tube-well, LDS,Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-I Block, District:-Hooghly [NEW SCHEME] | 2213/Hug | 28/07/2023 | 978 | P.B. ENTERPRISE (PINTU BHADURI) | 660.63 | 421.28 | 63.77 | 80
3440 | HOOGHLY | Hooghly Division | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18307 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SELALPUR PWSS - 4no's (2) TIROL PWSS (Z-I)- 4 no's (3) KUMURSA PWSS- 2no's (4) MADHABPUR PWSS- 4no's | 1151/Arg | 10/12/2024 | 31 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0 | 0 | 0
3441 | HOOGHLY | Hooghly Division | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18596 | New | Material Requisition To Resource Division | 3057/52/Hug | 11/10/2023 | 0 | Resource Division | 3.38 | 0 | 0 | 0
3442 | HOOGHLY | Electrical | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18596 | New | Quotation Bill for New Service Connection at Selalpur W/S. Sch. TW-I | 400 | 09/11/2023 | 0 | WBSEDCL | 3.98 | 0 | 0 | 0
3443 | HOOGHLY | Hooghly Division | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18596 | New | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at SELALPUR (2Nos.), MADHABPUR (2Nos.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3469/HUG | 04/10/2024 | 90 | AMWOODO ECO PRODUCTS PRIVATE LIMITED | 47.22 | 0 | 0 | 0
3444 | HOOGHLY | Hooghly Division | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18596 | New | Sinking of 2 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of SELALPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3525/HUG | 22/10/2024 | 30 | GITA ENTERPRISE | 31.35 | 0 | 0 | 0
3445 | HOOGHLY | Electrical | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18596 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SELALPUR PIPED W/S SCHEME, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1157/ED | 14/06/2024 | 90 | M/S DILIP MITRA | 10.74 | 0 | 0 | 0
3446 | HOOGHLY | Electrical | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18596 | New | Quotation of New Service Connection for Selalpur w/s Scheme,PH No-II Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/18596) Application No-5004135212, Reference Id-503626837 | 99 | 06/05/2024 | 0 | WBSEDCL | 7.66 | 0 | 0 | 0
3447 | HOOGHLY | Electrical | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18596 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Selalpur water supply scheme, T.W. No.- I & II, Block: Aambag, District- Hooghly under Electrical Division, PHE Dte. | 3586/ED | 28/08/2023 | 551 | M/S DILIP MITRA | 21.5 | 14.35 | 66.74 | 30
3448 | HOOGHLY | Hooghly Division | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18596 | New | BALUNDI,SELALPUR, MADHABPUR, DAHARKUNDU ZONE-II Piped Water Supply Scheme with T.W, SWITCH ROOM , BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at ARAMBAGH Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | 3191/HUG | 31/10/2023 | 731 | S & P ENTERPRISE | 2296.42 | 298.71 | 48.47 | 30
3449 | HOOGHLY | Hooghly Division | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18596 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SELALPUR PWSS - 4no's (2) TIROL PWSS (Z-I)- 4 no's (3) KUMURSA PWSS- 2no's (4) MADHABPUR PWSS- 4no's | 1151/Arg | 10/12/2024 | 31 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0 | 0 | 0
3450 | HOOGHLY | Hooghly Division | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Material Requisition To Resource Division | 3060/5/Hug | 11/10/2023 | 0 | Resource Division | 25.93 | 0 | 0 | 0
3451 | HOOGHLY | Hooghly Division | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Material Requisition To Resource Division | 3005/10/Hug | 05/10/2023 | 0 | Resource Division | 25.89 | 0 | 0 | 0
3452 | HOOGHLY | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Gangadharpur w/s scheme,P H No 1 | 560 | 21/12/2023 | 0 | WBSEDCL | 3.67 | 0 | 0 | 0
3453 | HOOGHLY | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gangadharpur water supply scheme, Zone-I, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | 3590/ED | 28/08/2023 | 90 | GOENKA ENTERPRISE | 21.37 | 15.91 | 74.45 | 60
3454 | HOOGHLY | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). | 3054/HMSD | 20/06/2024 | 184 | SIDDHARTHA CHATTERJEE. | 0.87 | 0.17 | 19.48 | 0
3455 | HOOGHLY | Hooghly Division | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Construction of 200 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation at Gangadharpur Zone - II under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 3674/HUG | 13/11/2024 | 45 | TOTON MONDAL | 81.06 | 0 | 0 | 0
3456 | HOOGHLY | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. | 2502_/HMSD | 26/09/2023 | 152 | S.P. CONSTRUCTION | 0.72 | 0.43 | 59.87 | 0
3457 | HOOGHLY | Hooghly Division | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | CONSTRUCTION OF 2NOS. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT GANGADHARPUR Z-I HW SITE AND Zone-II HW SITE UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E DTE. | 425/SER | 31/07/2024 | 15 | SUNITI MAIRA | 0.68 | 0.68 | 100 | 95
3458 | HOOGHLY | Hooghly Division | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Gangadharpur (Zone-I) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte | 116/SER | 23/02/2024 | 15 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 100
3459 | HOOGHLY | Hooghly Division | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Gangadharpur (Zone-II) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 117/SER | 23/02/2024 | 15 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 100
3460 | HOOGHLY | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. Car No. WB-02AT-8617 | 605 | 05/12/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.06 | 0 | 0 | 0
3461 | HOOGHLY | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. From:- 01/03/2024 to 31/03/2024 Bill No.- 1469 | 353 | 31/07/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
3462 | HOOGHLY | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of January,2024 | 233 | 20/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0 | 0
3463 | HOOGHLY | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of December, 2023. | 238 | 20/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0 | 0
3464 | HOOGHLY | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Quotation bill for new service connection charges at Gangadharpur PWSS Zone-I, P.H. No.-II, Hooghly. Application No. 5004064346 Ref ID: 503597306 | 22 | 05/04/2024 | 0 | WBSEDCL | 5.4 | 0 | 0 | 0
3465 | HOOGHLY | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). Car No. WB-11C-1616 01.08.2024 to 31.08.2024 | 563 | 11/11/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0 | 0
3466 | HOOGHLY | Hooghly Division | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | PAYMENT TO ROAD RESTORATION TO PWD JANGIPARA GANGADHARPUR ROAD | BP-2024-25-501 | 26/09/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 23.35 | 0 | 0 | 0
3467 | HOOGHLY | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). Car No.- WB-11C-1616 From 01.07.2024 to 31.07.2024 | 463 | 13/09/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0 | 0
3468 | HOOGHLY | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Fuel consumption bill of luxuary car/ Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. From 01.04.2024 to 30.04.2024 WB-02AT-8617 Bill No : 0100 Bill Date : 30/04/2024 | 250 | 24/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.11 | 0 | 0 | 0
3469 | HOOGHLY | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Quotation bill for new service connection charge at Gangadharpur, Zone-II, P.H. No.-II, District-Hooghly Application No.- 5004481099 Ref No.: 503803227 Scheme Code: SM/18623 | 611 | 05/12/2024 | 0 | WBSEDCL | 3.85 | 0 | 0 | 0
3470 | HOOGHLY | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Fuel consumption bill of luxuary car/ Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. From 01.05.2024 to 31.05.2024 WB-02AT-8617 Bill No : 0239 Bill Date : 31/05/2024 | 253 | 24/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.11 | 0 | 0 | 0
3471 | HOOGHLY | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of November, 2023. | 237 | 20/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.2 | 0 | 0 | 0
3472 | HOOGHLY | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Quotation bill for new service connection charges at Gangadharpur w/s scheme, Zone-II, PH No.-I, Hooghly. Application No.- 5004040971 Ref ID: 503579949 | 885 | 15/03/2024 | 0 | WBSEDCL | 5.59 | 0 | 0 | 0
3473 | HOOGHLY | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). Car No.- WB-11C-1616 From 01.09.2024 to 30.09.2024 | 564 | 11/11/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.15 | 0 | 0 | 0
3474 | HOOGHLY | Hooghly Division | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. , SM/18623 | New | Acceptance Order for NABABPUR, DUDHKALMI, HARIPUR, JAGMOHANPUR , GANGADHARPUR Piped Water Supply Scheme with.TW, Switch room, boundaryivall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at CHANDITALA-I Block under SERAMPORE Sub-Division Under Hooghly Division PHE Dte. | 2393/HUG | 10/08/2023 | 731 | GREEN ROYAL INFRA CON PVT LTD | 3243.22 | 469.55 | 52.27 | 9
3475 | HOOGHLY | Hooghly Division | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/18771 | New | Material Requisition To Resource Division | 3057/28/Hug | 11/10/2023 | 0 | Resource Division | 16.38 | 0 | 0 | 0
3476 | HOOGHLY | Electrical | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/18771 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for HIRAPUR PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1168/ED | 14/06/2024 | 90 | SRI KRISHNA NIRMAN | 10.54 | 0 | 0 | 0
3477 | HOOGHLY | Electrical | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/18771 | New | Quotation of New Service Connection Hirapur w/s Scheme, Zone-I,PH No-I Block-Khanakul-II Dist-Hooghly under Electrical Division, PHE Dte.(SM/18771) Application No-5004008491 Reference Id-503559063 | 883 | 15/03/2024 | 0 | WBSEDCL | 4.21 | 0 | 0 | 0
3478 | HOOGHLY | Electrical | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/18771 | New | Quotation of New Service Connection Hirapur w/s Scheme, Zone-I,PH No-II Block-Khanakul-II Dist-Hooghly under Electrical Division, PHE Dte.(SM/18771) Application No-5004008503 Reference Id-503559062 | 884 | 15/03/2024 | 0 | WBSEDCL | 8.68 | 0 | 0 | 0
3479 | HOOGHLY | Electrical | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/18771 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hirapur water supply scheme, Zone-I, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | 3612/ED | 29/08/2023 | 642 | TRIO CONCERN | 17.37 | 10.61 | 61.1 | 15
3480 | HOOGHLY | Hooghly Division | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/18771 | New | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 208.21 | 33.48 | 50
3481 | HOOGHLY | Hooghly Division | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/18771 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0 | 0
3482 | HOOGHLY | Hooghly Division | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly , SM/18771 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) NOAPARA PWSS- 1 no¿s, (2) HAYATPUR PWSS- 2 no¿s, (3) HIRAPUR PWSS (Z-I)- 1 no¿s, (4) HIRAPUR PWSS (Z-II)- 1 no¿s (5) MAROKHANA PWSS (Z-I)- 1 no¿s, (6) MOSTAFAPUR PWSS- 2 no¿s, (7) NATIBPUR PWSS- 2 no¿s, (8) ROUTHKHANA PWSS- 1 no¿s, (9) HARISCHAK PWSS- 2 no¿s, (10) PALASPAI PWSS- 1 no¿s | 1154/Arg | 10/12/2024 | 31 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
3483 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PUINAN WATER SUPPLY SCHEME. , SM/07947 | Retrofitting | Providing 1380 nos Functional Household Tap Connection (FHTC) within the command area of Puinan Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 2130/Hug | 01/12/2021 | 40 | TOTON MONDAL | 57.38 | 51.7 | 100 | 100
3484 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PUINAN WATER SUPPLY SCHEME. , SM/07947 | Retrofitting | Material Requisition To Resource Division | 1123/7/HUG | 06/06/2022 | 0 | Resource Division | 5.5 | 0 | 0 | 0
3485 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. , SM/07540 | Retrofitting | FHTC |  | 21/09/2021 | 0 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 15.6 | 0 | 0 | 0
3486 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. , SM/07540 | Retrofitting | FHTC |  | 21/09/2021 | 0 | TAPAS ADHYA | 11.3 | 0 | 0 | 0
3487 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. , SM/07540 | Retrofitting | Providing 446 nos F.H.T.C. in Kamardanga Village of Abdulpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | 375/Hug | 15/02/2021 | 30 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 23.29 | 16.02 | 100 | 100
3488 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. , SM/07540 | Retrofitting | Providing 569 nos F.H.T.C. in Char Sundalpur & Abdulpur Village of Abdulpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | 374/Hug | 15/02/2021 | 30 | TAPAS ADHYA | 29.72 | 27.34 | 100 | 100
3489 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. , SM/07540 | Retrofitting | Laying of C.I/D.I pipes & specials for Rising main Pipeline inbetween T.W No.-I & II to O.H.R. including Bypass arrangement & interconnection with distribution system for Abdulpur W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | 90/CH | 03/02/2022 | 25 | ARUN SEAL AND CO. | 2.36 | 1.8 | 100 | 100
3490 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. , SM/07540 | Retrofitting | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 150 mtrs. Depth) by utilising Departmental machineries for Abdulpur W/S Scheme, Balagarh block under hooghly District, CDD PHE Dte. | 2342/CDD | 31/03/2023 | 30 | UNIVERSAL ENTERPRISES | 11.38 | 10.28 | 100 | 100
3491 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. , SM/07540 | Retrofitting | Material Requisition To Resource Division | 2097/3/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0 | 0
3492 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME , SM/11165 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of DUMURDAHA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 2276/HUG | 19/10/2022 | 15 | TAPAS ADHYA | 10.76 | 10.75 | 100 | 0
3493 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME , SM/11165 | Retrofitting | Hiring of diesel drive motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of The Superintending Engineer, M/E, PMU WBDWSIP under CMSD-II (D), CDD, P.H.E. Dte. | 45/CMSD-II(D) | 27/02/2023 | 181 | SIDDHARTHA CHATTERJEE | 0.9 | 0 | 0 | 0
3494 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME , SM/11165 | Retrofitting | Providing 1000 nos Functional Household Tap Connection (FHTC) within Dadpur, Kamalpur, Sija & Ramnagar Mouza of Dumurdaha Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | 725/Hug | 07/04/2022 | 40 | DAS ENTERPRISE (SAMIR DAS) | 51.08 | 50.37 | 65.69 | 0
3495 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME , SM/11165 | Retrofitting | Providing drilling crew and other allied works for construction of Tube Well (300mmx200mmx150Mtrs) by utilisiling departmental rig machineries for Durmurdaha W/S Scheme, balagarh Block under Hooghly Division, CDD, PHE Dte. | 62/CDD | 06/04/2023 | 30 | UNIVERSAL ENTERPRISES | 11.38 | 9.95 | 100 | 100
3496 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME , SM/11165 | Retrofitting | Providing 1000 nos Functional Household Tap Connection (FHTC) within Dumurdaha dham & Aschitpur Mouza of Dumurdaha Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | 724/Hug | 07/04/2022 | 40 | MS PRADIP KUMAR PAL | 51.01 | 49.54 | 100 | 0
3497 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME , SM/11165 | Retrofitting | Material Requisition To Resource Division | 1123/3/HUG | 06/06/2022 | 0 | Resource Division | 11 | 0 | 0 | 0
3498 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME , SM/11165 | Retrofitting | Hiring of diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of The Superintending Engineer, M/E, PMU WBDWSIP under CMSD-II (D), CDD, P.H.E. Dte. | 209/CMSD-II(D) | 25/08/2023 | 122 | SIDDHARTHA CHATTERJEE | 0.94 | 0.88 | 93.17 | 0
3499 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAN AREA OF DUMURDAHA WATER SUPPLY SCHEME , SM/11165 | Retrofitting | Repairing of Existing O.H.R at H/W site of Dumurdaha Zone- II Water supply scheme under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. Block Polba-Balagarh, District:- Hooghly | 536/HUG | 20/02/2024 | 45 | DAS ENTERPRISE (SAMIR DAS) | 8.36 | 8.03 | 100 | 100
3500 | HOOGHLY | Hooghly Division | JAGMOHANPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/17632 | New | Material Requisition To Resource Division | 1384/Hug | 15/05/2023 | 0 | Resource Division | 13.1 | 0 | 0 | 0
3501 | HOOGHLY | Hooghly Division | JAGMOHANPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/17632 | New | Material Requisition To Resource Division | 3060/Hug | 11/10/2023 | 0 | Resource Division | 12.43 | 0 | 0 | 0
3502 | HOOGHLY | Hooghly Division | JAGMOHANPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/17632 | New | Material Requisition To Resource Division | 1236/Hug | 28/04/2023 | 0 | Resource Division | 25.53 | 0 | 0 | 0
3503 | HOOGHLY | Electrical | JAGMOHANPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/17632 | New | Quotation money deposition for new service connection at Jogmohanpur w/s scheme, T.W. No.-I, Dist.-Hooghly under PHE Dte. Application No- 5003805642 Reference ID- 503409286 SM Code- 17632 | 347 | 31/07/2024 | 0 | WBSEDCL | 3.2 | 0 | 0 | 0
3504 | HOOGHLY | Electrical | JAGMOHANPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/17632 | New | Quotation bill for new service connection charges at Jagmohanpur w/s scheme, P.H. No.-I, Dist: Hooghly. Application No.-5004024656 Ref ID: 503569651 | 863 | 12/03/2024 | 0 | WBSEDCL | 7.56 | 0 | 0 | 0
3505 | HOOGHLY | Electrical | JAGMOHANPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/17632 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jagmohanpur water supply scheme, T.W. No.- I & II, Block: Chanditala-I District- Hooghly under Electrical Division, PHE Dte. | 1796/ED | 24/04/2023 | 648 | MASSK ENGINEERING WORKS. | 20.35 | 6.65 | 32.65 | 75
3506 | HOOGHLY | Hooghly Division | JAGMOHANPUR PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-I, DISTRICT: HOOGHLY. , SM/17632 | New | Acceptance Order for NABABPUR, DUDHKALMI, HARIPUR, JAGMOHANPUR , GANGADHARPUR Piped Water Supply Scheme with.TW, Switch room, boundaryivall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at CHANDITALA-I Block under SERAMPORE Sub-Division Under Hooghly Division PHE Dte. | 2393/HUG | 10/08/2023 | 731 | GREEN ROYAL INFRA CON PVT LTD | 3243.22 | 29.61 | 5.16 | 9
3507 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF NATUNCHAR KRISHNABATI PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18933 | Augmentation | Construction of 5 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at SRIPUR BALAGARH (1No.), NATUNCHAR KRISHNABATI (2Nos.), ITAGARH (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3234/HUG | 06/11/2023 | 60 | RAJDEEP CONSTRUCTION | 59 | 0 | 0 | 0
3508 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF NATUNCHAR KRISHNABATI PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18933 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF NATUNCHAR KRISHNABATI PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4484/ED | 23/11/2023 | 90 | A.S. ENTERPRISE | 21.82 | 0 | 0 | 0
3509 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF NATUNCHAR KRISHNABATI PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18933 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at SRIPUR BALAGARH (1No.), NATUNCHAR KRISHNABATI (2Nos.), ITAGARH (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3357/HUG | 21/11/2023 | 90 | B.K ENTERPRISE | 88.58 | 0 | 0 | 60
3510 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF NATUNCHAR KRISHNABATI PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18933 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Natunchar Krishnabati Mini PWSS 2. Charkrishnabti Mini PWSS 3. Guptipara Char Mini PWSS 4. Rampur Mini PWSS 5. Raninagar Mini PWSS 6. Basantapur Mini PWSS | 208/CH | 29/02/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 50 | 45
3511 | HOOGHLY | Hooghly Division | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly , SM/18348 | New | Material Requisition To Resource Division | 3002/5/Hug | 05/10/2023 | 0 | Resource Division | 54.23 | 0 | 0 | 0
3512 | HOOGHLY | Electrical | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly , SM/18348 | New | Quotation Bill for New Service Connection at Ghol Digrui W/S. Sch. Z-II, TW-II | 285 | 18/09/2023 | 0 | WBSEDCL | 3.29 | 0 | 0 | 0
3513 | HOOGHLY | Electrical | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly , SM/18348 | New | Electric quot for Ghol Digrui Zone-II T/W-I W/S scheme | 166 | 04/08/2023 | 0 | WBSEDCL | 3.16 | 0 | 0 | 0
3514 | HOOGHLY | Electrical | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly , SM/18348 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-II, T.W. No. III, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | 329/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.43 | 0 | 0 | 0
3515 | HOOGHLY | Electrical | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly , SM/18348 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-II, T.W. No.- I & II, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | 3160/ED | 27/07/2023 | 90 | DIPALI CONSTRUCTION | 21.49 | 21.46 | 100 | 30
3516 | HOOGHLY | Hooghly Division | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly , SM/18348 | New | GHOL DIGRUI (ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block, District:- Hooghly [NEW SCHEME] | 2035/HUG | 12/07/2023 | 270 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 568.38 | 36.04 | 100 | 60
3517 | HOOGHLY | Hooghly Division | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly , SM/18348 | New | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for GHOLDIGRUI ZONE-II Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. | 3668/HUG | 13/11/2024 | 414 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 52.78 | 0 | 0 | 0
3518 | HOOGHLY | Electrical | Source Augmentation of CHIKRAND ZONE-II Piped Water Supply Scheme by installing One (1) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by local , SM/18967 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of CHIKRAND ZONE-II Piped Water Supply Scheme Block- Chanditala-II District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4527/ED | 23/11/2023 | 525 | DEBJYOTI BASU | 10.75 | 10.43 | 97.08 | 75
3519 | HOOGHLY | Hooghly Division | Source Augmentation of CHIKRAND ZONE-II Piped Water Supply Scheme by installing One (1) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by local , SM/18967 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at MAINAN(1No.),CHIKRAND ZONE-I (1No.),CHIKRAND ZONE-II (1No.) ,CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3388/HUG | 22/11/2023 | 45 | SPG ENTERPRISES | 87.88 | 14.02 | 100 | 100
3520 | HOOGHLY | Hooghly Division | Source Augmentation of CHIKRAND ZONE-II Piped Water Supply Scheme by installing One (1) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by local , SM/18967 | Augmentation | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at CHIKRAND ZONE-I (1No.), CHIKRAND ZONE-II (1No.), CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3313/HUG | 10/11/2023 | 421 | S.D ENTERPRISE (SAMIR KR. DAS) | 47.18 | 7.08 | 40.58 | 40
3521 | HOOGHLY | Electrical | Source Augmentation of CHIKRAND ZONE-II Piped Water Supply Scheme by installing One (1) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by local , SM/18967 | Augmentation | Quotation money deposition for new service connection at Chikrand w/s scheme, Dist.-Hooghly under PHE Dte. Application No- 5004485180 Reference ID- 503806101 SM Code- 18967 v | 615 | 04/12/2024 | 0 | WBSEDCL | 10.74 | 0 | 0 | 0
3522 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18970 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at NAMAJGRAM (1No.), RAMESWARPUR (2Nos.), KAMARPARA (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3238/HUG | 06/11/2023 | 60 | NIGAM CONSTRUCTION | 59.08 | 0 | 0 | 0
3523 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18970 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4493/ED | 23/11/2023 | 90 | M.S. ENTERPRISE | 21.51 | 0 | 0 | 0
3524 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18970 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at NAMAJGRAM (1No.), RAMESWARPUR (2Nos.), KAMARPARA (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3361/HUG | 21/11/2023 | 45 | RAJU CONSTRUCTION | 87.09 | 12.85 | 73.77 | 75
3525 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18970 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at CHAPTA (2Nos.), SOMRA (2Nos.), NAMAJGRAM (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3360/HUG | 21/11/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 87.88 | 13.22 | 75.24 | 40
3526 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18970 | Augmentation | Quotation for new service connection for source Augmentation of NAMAJGRAM Water Supply Scheme, TW NO- IV in the district Hooghly under Electrical Division, PHE Dte. ( SM/18970), Reference Id- 503802582 Application no- 5004479726 | 602 | 05/12/2024 | 0 | WBSEDCL | 19.9 | 0 | 0 | 0
3527 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18970 | Augmentation | Quotation for new service connection for source Augmentation of NAMAJGRAM Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18970), Reference Id- 503802583 Application no- 5004479665 | 612 | 05/12/2024 | 0 | WBSEDCL | 4.24 | 0 | 0 | 0
3528 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18970 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at CHAPTA (2Nos.), SOMRA (2Nos.), NAMAJGRAM (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3237/HUG | 06/11/2023 | 632 | M/S T.K.B. CONSTRUCTION | 59.02 | 0 | 0 | 60
3529 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18970 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Namajgram PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 274/CH | 20/02/2025 | 10 | GHOSH CONSTRUCTION | 2.58 | 0 | 0 | 0
3530 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18970 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site of Namajgram PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 266/CH | 20/02/2025 | 10 | GHOSH CONSTRUCTION | 4.53 | 0 | 0 | 0
3531 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF GUPTIPARA PIPED W/S SCHEME UNDER BALAGAH BLOCK , SM/18979 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF GUPTIPARA PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4502/ED | 23/11/2023 | 90 | DIPA CHHETRI | 11.05 | 0 | 0 | 0
3532 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF GUPTIPARA PIPED W/S SCHEME UNDER BALAGAH BLOCK , SM/18979 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at DHAMAITIKAR (2Nos.), GUPTIPARA (1No.), ABDULPUR (1 No.), DEPARA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3385/HUG | 22/11/2023 | 628 | OSMAN SEKH | 87.83 | 0 | 0 | 40
3533 | HOOGHLY | Electrical | Augmentation Of Piped Water Supply Scheme For SRIRAMPUR , SM/18643 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Srirampur water supply scheme, Zone-I, T.W. No. I and Zone-II, T.W. No. I, Block: Pursura, District- Hooghly under Electrical Division, PHE Dte. | 118/ED | 15/01/2024 | 90 | PRADIP KUMAR DHABAL | 21.51 | 0 | 0 | 0
3534 | HOOGHLY | Electrical | Augmentation Of Piped Water Supply Scheme For SRIRAMPUR , SM/18643 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SRIRAMPUR PIPED W/S SCHEME, T.W. No. IV, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1186/ED | 14/06/2024 | 90 | SOMNATH ENTERPRISE | 10.66 | 0 | 0 | 0
3535 | HOOGHLY | Hooghly Division | Augmentation Of Piped Water Supply Scheme For SRIRAMPUR , SM/18643 | Augmentation | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for Augmentation of SRIRAMPUR Piped Water Supply Scheme under ARAMBAGH Sub Division of Hooghly Division, P.H.E. Dte. | 3774/HUG | 25/11/2024 | 60 | M/S SHIVAM UDYOG | 51.47 | 0 | 0 | 0
3536 | HOOGHLY | Electrical | Augmentation Of Piped Water Supply Scheme For SRIRAMPUR , SM/18643 | Augmentation | Electric quot. of WBSEDCL for New service Connection of Srirampur T/W-II W/S scheme under Electrical Division PHE Dte. (SM/18643) | 637 | 18/12/2024 | 0 | WBSEDCL | 4.17 | 0 | 0 | 0
3537 | HOOGHLY | Hooghly Division | Augmentation Of Piped Water Supply Scheme For SRIRAMPUR , SM/18643 | Augmentation | Augmentation of SRIRAMPUR Piped Water Supply Scheme with Sinking of 2 Nos. tube-well within ZONE-II, Construction of 600cum capacity RCC OHR in ZONE-II with 20.0 mtr. Staging height including soil investigation, Repairing of Existing Switch Rooms, Boundary walls at different TW sites of ZONE-I, LDS, FHTC in ZONE-I & construction of 2 Nos. switch-room & 2 Nos boundary wall, LDS, Rising Main, FHTC in ZONE-II under PURSURAH Block of Arambag Sub-Division under Hooghly Division, PHE Dte. [AUGMENTATION SCHEME] | 2339/HUG | 07/08/2023 | 782 | M/S PRADYUT KUMAR HAZRA | 812.72 | 180.61 | 22.22 | 20
3538 | HOOGHLY | Hooghly Division | Augmentation Of Piped Water Supply Scheme For SRIRAMPUR , SM/18643 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SRIRAMPUR PWSS- 3nos (2) BACHHANARI PWSS- 3nos (3) MALAYPUR PWSS- 4nos (4) MANDRA PWSS- 4nos | 807/Arg | 23/08/2024 | 30 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
3539 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/18975 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at NATAGARI (2Nos.), MANDARAN (2Nos.), DEBANANDAPUR (1No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3239/HUG | 06/11/2023 | 60 | RAJ AGRO SERVICE CENTRE | 59.62 | 11.16 | 93.57 | 20
3540 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/18975 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME Block- ChinsurahMogra District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4498/ED | 23/11/2023 | 90 | R.N.S. TRADING | 22.03 | 10.67 | 48.4 | 40
3541 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/18975 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BHABANIPUR CHAR (2Nos.), JAYRAMBATI (2Nos.), DEBANANDAPUR (1 No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3389/HUG | 22/11/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 87.88 | 13.65 | 77.66 | 30
3542 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/18975 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. 1. Debanandapur PWSS 2. Digsui Heora Z-I PWSS 3. Digsui Heora Z-II PWSS 4. Keota PWSS 5. Saptagram PWSS 6. Chanparui PWSS | 198/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 100 | 50
3543 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/18975 | Augmentation | Reparing & Washing of Existing Ferrule and Laying of HDPE Pipeline From existing Distribution System for providing FHTC of Debanandapur W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | 127/CH | 16/02/2024 | 15 | BIMAL KUMAR HALDER | 2.16 | 2.16 | 100 | 45
3544 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/18975 | Augmentation | Quotation for the new service connection at Debanandapur (Source Aug.) [SM/18975] W/S Sch. T/W No. - II, (Manaspur near Lalbaba Ashram ) Block- - Chinsura-Mogra, Hooghly under BANDEL CCC, WBSEDCL, Application No. - 5004045960, Reference No. - 503581923 | 840 | 04/03/2024 | 0 | WBSEDCL | 20.45 | 0 | 0 | 0
3545 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/18975 | Augmentation | Quotation for the new service connection at Debanandapur (Source Aug.) [SM/18975] W/S Sch. T/W No. - I, (Near Sarat Library ) Block- - Chinsura-Mogra, Hooghly under BANDEL CCC, WBSEDCL, Application No. - 5004045949, Reference No. - 503581960 | 836 | 04/03/2024 | 0 | WBSEDCL | 3.7 | 0 | 0 | 0
3546 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/18975 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at NATAGARI (2Nos.), MANDARAN (2Nos.), DEBANANDAPUR (1No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3383/HUG | 22/11/2023 | 627 | OSMAN SEKH | 87.84 | 17.31 | 98.53 | 20
3547 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/18975 | Augmentation | Repairing & Renovation of Switch room and Store room at H/W Site of Debanandapur Z-I Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 297/CH | 20/02/2025 | 10 | BIMAL KUMAR HALDER | 3.41 | 0 | 0 | 100
3548 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/18975 | Augmentation | Repairing & Renovation of boundary wall and Land development at H/W Site of Debanandapur Z-I Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 301/CH | 20/02/2025 | 10 | BIMAL KUMAR HALDER | 2.58 | 0 | 0 | 100
3549 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK , SM/18975 | Augmentation | Laying C.I/D.I & HDPE pipes & specials for rising main & interconnection of Tube well No. 7 & Distribution line at Lal Baba Asram of Debanandapur W/S under Chinsurah Sub - Division P.H.E. Dte. | 2833/HUG | 17/11/2025 | 60 | BIMAL KUMAR HALDER | 15.19 | 0 | 0 | 0
3550 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18976 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4499/ED | 23/11/2023 | 90 | R.M.D TRADING. | 22.05 | 0 | 0 | 0
3551 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18976 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at NATAGARI (2Nos.), MANDARAN (2Nos.), DEBANANDAPUR (1No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3239/HUG | 06/11/2023 | 60 | RAJ AGRO SERVICE CENTRE | 59.62 | 0 | 0 | 20
3552 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18976 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. 1. Natagarh PWSS 2. Natunchar Krishnabati PWSS 3. Somra PWSS 4. Sripur Balagarh PWSS 5. Amodghata PWSS 6. Dharampur PWSS | 197/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 100 | 50
3553 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18976 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at NATAGARI (2Nos.), MANDARAN (2Nos.), DEBANANDAPUR (1No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3383/HUG | 22/11/2023 | 627 | OSMAN SEKH | 87.84 | 0 | 0 | 20
3554 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18976 | Augmentation | Repairing & Renovation of Switch Room and Store Room at H/W Site of Natagari Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 288/CH | 20/02/2025 | 10 | SOMNATH ADHYA | 3.42 | 0 | 0 | 0
3555 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18976 | Augmentation | Repairing & Renovation of boundary wall and Land development at H/W Site of Natagari Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 287/CH | 20/02/2025 | 10 | SOMNATH ADHYA | 3.03 | 0 | 0 | 0
3556 | HOOGHLY | Hooghly Division | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18429 | New | Material Requisition To Resource Division | 3057/51/Hug | 11/10/2023 | 0 | Resource Division | 19.68 | 0 | 0 | 0
3557 | HOOGHLY | Hooghly Division | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18429 | New | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of RASULPUR Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 3654/HUG | 13/11/2024 | 90 | BAKSHI ENTERPRISE | 16.15 | 0 | 0 | 0
3558 | HOOGHLY | Electrical | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18429 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RASULPUR PIPED W/S SCHEME, T.W. No. IV, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1185/ED | 14/06/2024 | 90 | M/S, GHOSH ENTERPRISE | 10.73 | 0 | 0 | 0
3559 | HOOGHLY | Hooghly Division | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18429 | New | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of NATIBPUR KRISHNANAGAR Zone-I , RASULPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte | 3782/HUG | 25/11/2024 | 60 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 55.13 | 0 | 0 | 0
3560 | HOOGHLY | Electrical | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18429 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RASULPUR PIPED W/S SCHEME, T.W. No. III, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1184/ED | 14/06/2024 | 90 | RISHAV ENTERPRISE | 10.75 | 0 | 0 | 0
3561 | HOOGHLY | Hooghly Division | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18429 | New | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of RASULPUR, SHYAMBALLAVPUR , DIHIBAGNAN W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3531/HUG | 22/10/2024 | 45 | PADMA ENGINEERING CO. | 47.49 | 0 | 0 | 0
3562 | HOOGHLY | Hooghly Division | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18429 | New | RASULPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block of Arambag Sub-Division, PHE Dte. [NEW SCHEME] | 2188/HUG | 26/07/2023 | 796 | KHAN ENTERPRISE | 741.7 | 0 | 0 | 5
3563 | HOOGHLY | Electrical | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18429 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Soaluk water supply scheme, T.W. No. IV, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | 334/ED | 21/02/2024 | 435 | DEY ENTERPRISE | 10.43 | 0 | 0 | 35
3564 | HOOGHLY | Hooghly Division | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/18429 | New | Sinking of 2 Nos. Additional tube-well at Rasulpur Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 651/HUG | 10/03/2025 | 30 | AUXILIARY TUBEWELL DRILLERS | 29.39 | 0 | 0 | 0
3565 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18936 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at EKTARPUR (2Nos.), BELUN (2Nos.), CHOPA (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3235/HUG | 06/11/2023 | 60 | EVERGREEN TRADERS | 59.68 | 0 | 0 | 0
3566 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18936 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at EKTARPUR (2Nos.), BELUN (2Nos.), CHOPA (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3358/HUG | 21/11/2023 | 45 | ACME CONSTRUCTION | 87.88 | 26.43 | 75.18 | 60
3567 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18936 | Augmentation | Quotation for new service connection for source Augmentation of BELUN Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18936 ), Reference Id- 503802585 Application no- 5004479701 | 613 | 05/12/2024 | 0 | WBSEDCL | 5.48 | 0 | 0 | 0
3568 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18936 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4487/ED | 23/11/2023 | 709 | C.M.S. ENGINEERING CONCERN | 21.64 | 2.79 | 12.91 | 50
3569 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18936 | Augmentation | Repairing & Renovation of boundary wall and Land development at H/W Site of Belun PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 237/CH | 19/02/2025 | 10 | TOTON MONDAL | 4.6 | 0 | 0 | 100
3570 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18936 | Augmentation | Repairing & Renovation of Switch room and Store Room at H/W Site Belun PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 256/CH | 20/02/2025 | 10 | JOY GURU ENTERPRISE | 3.06 | 0 | 0 | 100
3571 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18936 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Belun PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 257/CH | 20/02/2025 | 10 | TOTON MONDAL | 2.58 | 0 | 0 | 100
3572 | HOOGHLY | Hooghly Division | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block , SM/18954 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3406/HUG | 23/11/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 0 | 0 | 50
3573 | HOOGHLY | Electrical | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block , SM/18954 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of NALDANGA piped W/S Scheme Block- ChinsurahMogra District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4518/ED | 23/11/2023 | 90 | SUBHRA ENTERPRISE | 21.49 | 8.24 | 38.34 | 70
3574 | HOOGHLY | Electrical | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block , SM/18954 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Naldanga w/s scheme, T.W No. V, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | 4444/ED | 17/11/2023 | 90 | MOITRA ENGINEERING CO. | 10.92 | 9.97 | 100 | 90
3575 | HOOGHLY | Hooghly Division | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block , SM/18954 | Augmentation | Providing and installation of 150 mm x 100 mm dia. tubewell by Rig Bored system with Switch Room and allied works at Madrasi Para Under Naldanga Piped Water Supply Scheme In Chinsurah Sub-Division Of Hooghly Division, P.H.E. Dte | 3564/HUG | 05/12/2023 | 30 | SOUMYADIP DE | 16.51 | 12.95 | 100 | 50
3576 | HOOGHLY | Hooghly Division | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block , SM/18954 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Kola PWSS 2. Kulihanda PWSS 3. Madhusudanpur PWSS 4. Naldanga PWSS 5. Raghunathpur PWSS 6. Refaitpur Z-I PWSS | 199/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 100 | 50
3577 | HOOGHLY | Hooghly Division | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block , SM/18954 | Augmentation | Providing FHTC at the left out portions of Different area for proiving FHTC in Kulihanda, Naldanga & Debanandapur Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 540/CH | 14/06/2024 | 7 | MAA BUNAMATA ENTERPRISE | 4.85 | 4.85 | 100 | 80
3578 | HOOGHLY | Electrical | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block , SM/18954 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for NALDANGA MINI W/S SCHEME, Block: Chinsura Mogra, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1192/ED | 14/06/2024 | 90 | TULIP ENTERPRISE | 7.53 | 7.41 | 100 | 95
3579 | HOOGHLY | Electrical | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block , SM/18954 | Augmentation | Quotation for additional quotation for Naldanga(S.Aug.) W/s Sch., T.W. No. - VII [SM/18954], Ref Id- 860316928, Application Id. - 100000122348, dt. - 30-10-2024 | 567 | 13/11/2024 | 0 | WBSEDCL | 0.81 | 0 | 0 | 0
3580 | HOOGHLY | Electrical | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block , SM/18954 | Augmentation | Quotation for new service connection at Naldanga(S.Aug.) [SM/18954], T/W NO. - I, under Pipulpati CCC, WBSEDCL, Ref. Id. - 503644538, dt.- 14-05-2024, Application No. - 5004183039 | 181 | 30/05/2024 | 0 | WBSEDCL | 8.65 | 0 | 0 | 0
3581 | HOOGHLY | Electrical | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block , SM/18954 | Augmentation | Quotation for new service connection at Naldanga (Source Aug.) water supply Scheme [SM/18954], T/W No. - VI(Mini), Block - Chinsurah-Mogra, under Bandel CCC, WBSEDCL, Ref. Id. - 503582004, Dt. - 29-02-2024, Application No. - 5004045934 | 878 | 13/03/2024 | 0 | WBSEDCL | 4.35 | 0 | 0 | 0
3582 | HOOGHLY | Hooghly Division | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block , SM/18954 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3245/HUG | 06/11/2023 | 600 | TAPAS ADHYA | 59.64 | 0 | 0 | 20
3583 | HOOGHLY | Hooghly Division | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block , SM/18954 | Augmentation | Construction of approach Road for Head Works site of NALDANGA piped water supply scheme in JJM under Chinsurah-Mogra Block. | 376/CH | 04/03/2025 | 7 | DUTTA CONSTRUCTION | 0.94 | 0 | 0 | 0
3584 | HOOGHLY | Hooghly Division | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block , SM/15809 | Augmentation | Sinking of Two Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto150 Mtr at GANESHBATI PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | 656/HUG | 09/03/2023 | 45 | R CONSTRUCTION | 22.63 | 13.05 | 57.69 | 0
3585 | HOOGHLY | Hooghly Division | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block , SM/15809 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangment , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of GANESHBATI Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-I Block. | 1779/HUG | 15/06/2023 | 30 | ROY ENTERPRISE | 12.01 | 0 | 0 | 0
3586 | HOOGHLY | Hooghly Division | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block , SM/15809 | Augmentation | Material Requisition To Resource Division | 1263/14/Hug | 03/05/2023 | 0 | Resource Division | 11.5 | 0 | 0 | 0
3587 | HOOGHLY | Electrical | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block , SM/15809 | Augmentation | Quotation for New Service Connection of Ganeshbati W/S Scheme(Aug) TW No-4 District-Hooghly under Electrical Division PHE Dte. | 42 | 17/05/2023 | 0 | WBSEDCL | 3.31 | 0 | 0 | 0
3588 | HOOGHLY | Hooghly Division | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block , SM/15809 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir of GANESHBATI PWSS Under Arambagh Sub-Division Hooghly Division, P.H.E. Dte. | 3672/HUG | 13/11/2024 | 40 | TAPAS ADHYA | 12.36 | 0 | 0 | 0
3589 | HOOGHLY | Hooghly Division | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block , SM/15809 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) GANESHBATI PWSS-3nos (2) AMDOBA PWSS-2nos (3) BALI PWSS- 3nos (4) RADHABALLAVPUR PWSS- 3nos (5) RAMNAGAR PWSS-3 nos | 818/Arg | 23/08/2024 | 130 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.21 | 100 | 100
3590 | HOOGHLY | Electrical | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block , SM/15809 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Ganeshbati water supply scheme, T.W. No. I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | 1500/ED | 28/03/2023 | 826 | ASHUTOSH DAS & CO. | 21.49 | 0 | 0 | 30
3591 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18941 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4505/ED | 23/11/2023 | 90 | A.G. ENTERPRISE | 21.49 | 0 | 0 | 0
3592 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18941 | Augmentation | Quotation for new service connection for source Augmentation of AYMA NABABPUR Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18941), Reference Id- 503802584 Application no- 5004479744 | 603 | 05/12/2024 | 0 | WBSEDCL | 4.01 | 0 | 0 | 0
3593 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18941 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at AYMA NABABPUR (2Nos.), DUMURDAHA (1No.), AKNA (1 No.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3356/HUG | 21/11/2023 | 715 | AYUSH ENTERPRISE | 58.97 | 0 | 0 | 80
3594 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18941 | Augmentation | Construction of Store room for temporary Chlorine and maintenance material storage For Pandua Block under Chinsurah Sub-Division under Hooghly Division, PHE Dte.under Chinsurah Sub Division of Hooghly Division PHE Dte. | 286/CH | 15/03/2024 | 7 | MAA BUNAMATA ENTERPRISE | 0.95 | 0 | 0 | 30
3595 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18941 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site of Ayma nababpur PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 235/CH | 19/02/2025 | 10 | YOUNG ENGINEERS CO OPERATIVE SOCIETY LTD. | 4.49 | 0 | 0 | 0
3596 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18941 | Augmentation | Repairing & Renovation of Switch room at PH-II of Ayma nababpur PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 236/CH | 19/02/2025 | 10 | AYUSH ENTERPRISE | 1.36 | 0 | 0 | 0
3597 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18941 | Augmentation | Laying CI/DI pipes and specials for connection of proposed TW with existing rising main pipeline for Source AUGMENTATION Of Aymanababpur Piped Water Supply Scheme underPandua Block, District:- Hooghly | 357/CH | 28/02/2025 | 7 | M/S KAMALA ENTERPRISE | 1 | 0 | 0 | 0
3598 | HOOGHLY | Hooghly Division | Source Augmentation of SUDARSHAN Piped W/S Scheme Under Polba Dadpur Block. , SM/18949 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at HANRAL (2Nos.), SUDARSHAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3243/HUG | 06/11/2023 | 60 | AMBIAN INFRASTRUCTURE | 59.26 | 0 | 0 | 0
3599 | HOOGHLY | Hooghly Division | Source Augmentation of SUDARSHAN Piped W/S Scheme Under Polba Dadpur Block. , SM/18949 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed for Sajal Gram Display Board at different locations in 6 (Six) Nos villages & HGJ villages of Sudarshan PWSS for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. | 148/CH | 20/02/2024 | 7 | R.K. TRADERS | 0.95 | 0.95 | 100 | 50
3600 | HOOGHLY | Electrical | Source Augmentation of SUDARSHAN Piped W/S Scheme Under Polba Dadpur Block. , SM/18949 | Augmentation | Quotation for new service connection at Sudarshan Water Supply Scheme [SM/18949](S.Aug.),T.W. No. - III, sarangpur, Block - Polba-Dadpur, Dt. - Hooghly, under Polba CCC, Ref. Id. - 503787954, Application No. - 5004461023, Dt.-11-11-2024 | BP-24-25-582 | 19/11/2024 | 0 | WBSEDCL | 6.27 | 0 | 0 | 0
3601 | HOOGHLY | Hooghly Division | Source Augmentation of SUDARSHAN Piped W/S Scheme Under Polba Dadpur Block. , SM/18949 | Augmentation | Replacement of damaged pipe line with HDPE & CI/DI pipeline and Shifting House Connection from existing main to new main for smooth operation of water supply at Sudarshan Piped Water Supply Scheme of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 330/HUG | 05/02/2025 | 30 | RAJ CONSTRUCTION | 7.01 | 0 | 0 | 0
3602 | HOOGHLY | Hooghly Division | Retrofitting Works of BAKSA PWSS for providing 1522 nos Functional Household Tap Connection(FHTC) , SM/06755 | Retrofitting | FHTC |  | 15/03/2021 | 0 | MLG CONSTRUCTION | 35 | 0 | 0 | 0
3603 | HOOGHLY | Hooghly Division | Retrofitting Works of BAKSA PWSS for providing 1522 nos Functional Household Tap Connection(FHTC) , SM/06755 | Retrofitting | Placement of Fund | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
3604 | HOOGHLY | Hooghly Division | Retrofitting Works of BAKSA PWSS for providing 1522 nos Functional Household Tap Connection(FHTC) , SM/06755 | Retrofitting | Providing 800 nos Functional Household Tap Connection (FHTC) & extension of Laying Distribution System within the uncovered area of Baksa Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Chanditala-II] | 467/Hug | 26/02/2021 | 30 | TAPAS ADHYA | 44.33 | 60.54 | 167.49 | 100
3605 | HOOGHLY | Hooghly Division | Retrofitting Works of BAKSA PWSS for providing 1522 nos Functional Household Tap Connection(FHTC) , SM/06755 | Retrofitting | Providing 800 nos Functional Household Tap Connection (FHTC) & extension of Laying Distribution System within the uncovered area of Baksa Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Chanditala-II] | 467/HUG | 26/02/2021 | 30 | TAPAS ADHYA | 44.33 | 0 | 0 | 100
3606 | HOOGHLY | Hooghly Division | Retrofitting Works of BAKSA PWSS for providing 1522 nos Functional Household Tap Connection(FHTC) , SM/06755 | Retrofitting | Material Requisition To Resource Division | 1122/7/HUG | 06/06/2022 | 0 | Resource Division | 6.16 | 0 | 0 | 0
3607 | HOOGHLY | Hooghly Division | Retrofitting Works for Providing Functional Household Tap Connection(FHTC) within the Rajarambati, Talandu, Taragun Mouza of Digsui-Heora (Zone-II) PWSS , SM/06758 | Retrofitting | Providing 600 nos Functional Household Tap Connection (FHTC) within the command area of DIGSUI HOERA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 120/Hug | 19/01/2022 | 30 | DAS TRADING | 41.69 | 29.43 | 100 | 100
3608 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KISHORPUR WATER SUPPLY SCHEME. , SM/07439 | Retrofitting | FHTC |  | 08/11/2021 | 0 | SAMRAT REALPROJECTS PRIVATE LIMITED, | 37.7 | 0 | 0 | 0
3609 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KISHORPUR WATER SUPPLY SCHEME. , SM/07439 | Retrofitting | FHTC |  | 23/07/2021 | 0 | DULAL CHANDRA ROY | 21.01 | 0 | 0 | 0
3610 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KISHORPUR WATER SUPPLY SCHEME. , SM/07439 | Retrofitting | FHTC |  | 12/04/2021 | 0 | DULAL CHANDRA ROY | 2.67 | 0 | 0 | 0
3611 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KISHORPUR WATER SUPPLY SCHEME. , SM/07439 | Retrofitting | FHTC |  | 21/09/2021 | 0 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 59.08 | 0 | 0 | 0
3612 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KISHORPUR WATER SUPPLY SCHEME. , SM/07439 | Retrofitting | FHTC |  | 08/11/2021 | 0 | SAMRAT REALPROJECTS PRIVATE LIMITED, | 37.7 | 0 | 0 | 0
3613 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KISHORPUR WATER SUPPLY SCHEME. , SM/07439 | Retrofitting | Providing 500 nos Functional Household Tap Connection (FHTC) within the command area of KISHORPUR Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | 461/Hug | 10/03/2022 | 30 | MS CHANDIMATA CONSTRUCTION | 26.43 | 25.98 | 98.3 | 0
3614 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur (Within BepariPara, DharaPara, Doctor Para, Gowas Para, Hazra Para, Jamadar Para, Jana Para, Manna Para, Mehadi Para, Moral Para Habitatio , SM/06994 | Retrofitting | FHTC |  | 12/04/2021 | 0 | TITAS CONSTRUCTION | 8.56 | 0 | 0 | 0
3615 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur (Within BepariPara, DharaPara, Doctor Para, Gowas Para, Hazra Para, Jamadar Para, Jana Para, Manna Para, Mehadi Para, Moral Para Habitatio , SM/06994 | Retrofitting | FHTC |  | 15/03/2021 | 0 | TITAS CONSTRUCTION | 68 | 0 | 0 | 0
3616 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur (Within BepariPara, DharaPara, Doctor Para, Gowas Para, Hazra Para, Jamadar Para, Jana Para, Manna Para, Mehadi Para, Moral Para Habitatio , SM/06994 | Retrofitting | FHTC |  | 23/07/2021 | 0 | TITAS CONSTRUCTION | 12.14 | 0 | 0 | 0
3617 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur(Within Munshi Para, Patra Para,Pramanik Para, Roy Para- Danga, Sabalsinghapur, Dolui Para, Sanki Para, Santra Para, Santra Para-North,Seik , SM/07151 | Retrofitting | FHTC |  | 12/04/2021 | 0 | TITAS CONSTRUCTION | 8.56 | 0 | 0 | 0
3618 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur(Within Munshi Para, Patra Para,Pramanik Para, Roy Para- Danga, Sabalsinghapur, Dolui Para, Sanki Para, Santra Para, Santra Para-North,Seik , SM/07151 | Retrofitting | FHTC |  | 23/07/2021 | 0 | TITAS CONSTRUCTION | 12.14 | 0 | 0 | 0
3619 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur(Within Munshi Para, Patra Para,Pramanik Para, Roy Para- Danga, Sabalsinghapur, Dolui Para, Sanki Para, Santra Para, Santra Para-North,Seik , SM/07151 | Retrofitting | Providing 650 nos Functional Household Tap Connection (FHTC) within the command area of SABALSINGHAPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte | 19/Hug | 04/01/2022 | 60 | M/S R.K. CHOUDHURI | 26.47 | 0 | 0 | 0
3620 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur(Within Munshi Para, Patra Para,Pramanik Para, Roy Para- Danga, Sabalsinghapur, Dolui Para, Sanki Para, Santra Para, Santra Para-North,Seik , SM/07151 | Retrofitting | Providing 575 nos Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | 1997/Hug | 12/11/2021 | 40 | STP ENTERPRISE | 31.38 | 28.46 | 100 | 0
3621 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur(Within Munshi Para, Patra Para,Pramanik Para, Roy Para- Danga, Sabalsinghapur, Dolui Para, Sanki Para, Santra Para, Santra Para-North,Seik , SM/07151 | Retrofitting | Providing 114 nos. Functional Household Tap Connection (F.H.T.C) within Command area of Munshipara Habitation of Sabalsinghapur Village under Sabalsinghapur Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte. [Block-Khanakul-II] | 527/Arg | 30/11/2021 | 30 | P.K. GHOSH & CO. | 4.7 | 0 | 0 | 0
3622 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of Sabalsinghapur(Within Munshi Para, Patra Para,Pramanik Para, Roy Para- Danga, Sabalsinghapur, Dolui Para, Sanki Para, Santra Para, Santra Para-North,Seik , SM/07151 | Retrofitting | Providing 114 nos. Functional Household Tap Connection (F.H.T.C) within Command area of Munshipara Habitation of Sabalsinghapur Village under Sabalsinghapur Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte. [Block-Khanakul-II] | 527/ARG | 15/02/2022 | 30 | P.K. GHOSH & CO. | 4.79 | 4.79 | 100 | 0
3623 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. , SM/07948 | Retrofitting | FHTC |  | 15/03/2021 | 0 | BANSBERIA CONSTRUCTION CO. | 35 | 0 | 0 | 0
3624 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. , SM/07948 | Retrofitting | FHTC |  | 12/04/2021 | 0 | BANERJEE CONSTRUCTION | 11.71 | 0 | 0 | 0
3625 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. , SM/07948 | Retrofitting | FHTC |  | 06/04/2021 | 0 | BANERJEE CONSTRUCTION | 6.85 | 0 | 0 | 0
3626 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. , SM/07948 | Retrofitting | FHTC |  | 29/01/2021 | 0 | MINTU CHAKRABORTY | 26.7 | 0 | 0 | 0
3627 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. , SM/07948 | Retrofitting | Placement of Fund | 844368 | 19/01/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
3628 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. , SM/07948 | Retrofitting | Providing 158 nos Functional Household Tap Connection (FHTC) & extension of Laying Distribution System within the uncovered area of Bandipur and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | 468/Hug | 26/02/2021 | 20 | MINTU CHAKRABORTY | 19.87 | 14.82 | 100 | 100
3629 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. , SM/07948 | Retrofitting | Providing 122 nos F.H.T.C. & extension of pipe line in left out portion of Dilalpur village of Bandipur and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | 322/Hug | 11/02/2021 | 20 | BANERJEE CONSTRUCTION | 25.9 | 31.83 | 200 | 100
3630 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PAUNAN WATER SUPPLY SCHEME. , SM/07951 | Retrofitting | FHTC |  | 21/09/2021 | 0 | M/S S.G. CONSTRUCTION | 8.61 | 0 | 0 | 0
3631 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PAUNAN WATER SUPPLY SCHEME. , SM/07951 | Retrofitting | FHTC |  | 15/02/2021 | 0 | M/S S.G. CONSTRUCTION | 47 | 0 | 0 | 0
3632 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PAUNAN WATER SUPPLY SCHEME. , SM/07951 | Retrofitting | FHTC |  | 17/08/2021 | 0 | TIRUPATI ENTERPRISE | 30.33 | 0 | 0 | 0
3633 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PAUNAN WATER SUPPLY SCHEME. , SM/07951 | Retrofitting | Providing 1680 nos F.H.T.C. in Amnan, Araji Jotchandi ,Banseye, Barun Napara,Kedar nagar, Ramnagar , Mirzzapur & Jatarpur village of Paunan and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | 1682HUG. | 17/12/2020 | 40 | TIRUPATI ENTERPRISES | 11 | 11 | 100 | 100
3634 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PAUNAN WATER SUPPLY SCHEME. , SM/07951 | Retrofitting | Providing 1680 nos F.H.T.C. in Amnan, Araji Jotchandi ,Banseye, Barun Napara,Kedar nagar, Ramnagar , Mirzzapur & Jatarpur village of Paunan and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | 1682/Hug | 17/12/2020 | 182 | TIRUPATI ENTERPRISE | 53.57 | 60.66 | 113.24 | 100
3635 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PAUNAN WATER SUPPLY SCHEME. , SM/07951 | Retrofitting | Providing 220 nos Functional Household Tap Connection (FHTC) within the command area of PAUNAN Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 465/Hug | 10/03/2022 | 20 | SAMRAT CONSTRUCTION | 19.02 | 0 | 0 | 100
3636 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. , SM/07534 | Retrofitting | FHTC |  | 12/04/2021 | 0 | R AND D TRADERS | 1.5 | 0 | 0 | 0
3637 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. , SM/07534 | Retrofitting | FHTC |  | 19/03/2021 | 0 | M/S R.M. CONSTRUCTION | 18 | 0 | 0 | 0
3638 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. , SM/07534 | Retrofitting | FHTC |  | 17/08/2021 | 0 | M/S R.M. CONSTRUCTION | 14.97 | 0 | 0 | 0
3639 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. , SM/07534 | Retrofitting | FHTC |  | 15/03/2021 | 0 | R AND D TRADERS | 5 | 0 | 0 | 0
3640 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. , SM/07534 | Retrofitting | FHTC |  | 12/04/2021 | 0 | M/S R.M. CONSTRUCTION | 2.96 | 0 | 0 | 0
3641 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. , SM/07534 | Retrofitting | FHTC |  | 17/08/2021 | 0 | ARATI ENGINEERING | 10.31 | 0 | 0 | 0
3642 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. , SM/07534 | Retrofitting | Providing 50 nos Functional Household Tap Connection (FHTC) within the command area of ANANDAPUR Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | 123/Hug | 19/01/2022 | 25 | M/S ROY CONSTRUCTION AND CO. | 14.88 | 0 | 0 | 100
3643 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. , SM/07534 | Retrofitting | Providing 114 nos. Functional Household Tap Connection (F.H.T.C) within Command area of Mohanpur Village under Anandapur Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte. [Block-Goghat-I]. | 526/Arg | 30/11/2021 | 30 | M/S TANISHA ENTERPRISE | 4.7 | 4.81 | 100 | 0
3644 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. , SM/07534 | Retrofitting | Providing 304 nos Functional Household Tap Connection (FHTC) within the command area of Anandapur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | 2124/Hug | 01/12/2021 | 30 | GHOSH CONSTRUCTION | 12.06 | 10.04 | 100 | 0
3645 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. , SM/07534 | Retrofitting | Providing 285 nos Functional Household Tap Connection (FHTC) within the command area of ANANDAPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | 21/Hug | 04/01/2022 | 30 | ARATI ENGINEERING | 11.81 | 0 | 0 | 0
3646 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. , SM/07534 | Retrofitting | Material Requisition To Resource Division | 2096/11/Hug | 26/11/2021 | 0 | Resource Division | 0.82 | 0 | 0 | 0
3647 | HOOGHLY | Hooghly Division | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09517 | Augmentation | Construction of 3.6 m X 3.00 m Switch Room without Sanitary and Water Supply arrangement at 3rd T/W Site for Rajhat (Z-II) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | 622/CH | 20/12/2021 | 40 | SURAJ ENTERPRISE | 2.44 | 2.44 | 99.98 | 100
3648 | HOOGHLY | Electrical | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09517 | Augmentation | Supply, Delivery & Installation of S/P/M & other Electrical/Mechanical equipment etc. including allied works for Rajhat W/S. Sch. Z-II, TW-III | 1036/ED | 28/06/2022 | 99 | INDIA ENTERPRISE | 9.21 | 9.21 | 100 | 100
3649 | HOOGHLY | Electrical | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09517 | Augmentation | Electric Supply | 14 | 07/07/2022 | 0 | WBSEDCL | 4.53 | 0 | 0 | 0
3650 | HOOGHLY | Hooghly Division | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09517 | Augmentation | Laying of C.I/D.I pipes & specials for connection of T.W No. -III with distribution system & Protection work at 3rd TW Site of Rajhat (Z-II) W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | 621/CH | 20/12/2021 | 25 | BIMAL KUMAR HALDER | 4.16 | 0.86 | 100 | 100
3651 | HOOGHLY | Hooghly Division | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09517 | Augmentation | Construction of Boundary Wall & Pathway Development of RAJHAT (Z-II) at 3rd T/W Site W/S Scheme under Chinsurah Sub-Division P.H.E. Dte | 731/CH | 26/08/2022 | 30 | SURAJ ENTERPRISE | 4.85 | 4.42 | 100 | 100
3652 | HOOGHLY | Electrical | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09517 | Augmentation | Supply & installation of LED board at Zone-II, P.H. No.-I & II of Rajhat water supply scheme, Dist.- Hooghly under Electrical Division, PHE Dte. | 2348/HMSD | 20/12/2022 | 10 | SUDHIKSHA CONSTRUCTION | 0.79 | 0.79 | 100 | 0
3653 | HOOGHLY | Electrical | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09517 | Augmentation | 'Hire Charges Bill of V.No.- WB07J-317301.03.23 to 14.05.23' with fuel bill | 215//AE-II/ED | 24/03/2023 | 30 | INDRANI ENTERPRISE | 0.63 | 0.63 | 100 | 1
3654 | HOOGHLY | Electrical | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09517 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajhat water supply scheme, Zone-II, T.W. No.- IV, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | 866/ED | 14/02/2023 | 90 | KUSHANI ENTERPRISE | 10.17 | 10.17 | 100 | 100
3655 | HOOGHLY | Electrical | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09517 | Augmentation | "Hire Charges Bill of V.No.- WB07J-3173 01.03.23 to 14.05.23" with fuel bill | 215//AE-II/ED | 24/03/2023 | 30 | INDRANI ENTERPRISE | 0.62 | 0 | 0 | 1
3656 | HOOGHLY | Hooghly Division | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. , SM/09517 | Augmentation | Material Requisition To Resource Division | 3004/10/Hug | 05/10/2023 | 0 | Resource Division | 2.86 | 0 | 0 | 0
3657 | HOOGHLY | Central Drilling | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | SINKING OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR CHANDANPUR W/S SCHEME TARAKESWAR BLOCK, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 1295/CDD | 17/02/2022 | 30 | C.M. ENTERPRISE | 11.21 | 10.17 | 100 | 100
3658 | HOOGHLY | Central Drilling | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 210 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BANDIPUR W/S SCHEME (TW-II), HARIPAL BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 300/CDD | 27/04/2022 | 30 | PADMA ENGINEERING & CO. | 12.84 | 11.6 | 100 | 100
3659 | HOOGHLY | Central Drilling | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | SINKING OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING RIG MACHINE FOR CHANDANPUR W/S SCHEME UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 1294/CDD | 17/02/2022 | 30 | C.M. ENTERPRISE | 11.21 | 9.2 | 100 | 90
3660 | HOOGHLY | Hooghly Division | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | QUOTATION BILL ON ACCOUNT OF WBSEDCL FOR THE CHANDANPUR W/S/S |  | 12/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.64 | 0 | 0 | 0
3661 | HOOGHLY | Hooghly Division | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | WBSEDCL PAYMENT FROM ELECTRICAL DIVISION,PHE DTE. | C092248441540 | 27/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.43 | 0 | 0 | 0
3662 | HOOGHLY | Electrical | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chandanpur water supply scheme, T.W. No. I, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | 2044/ED | 01/12/2022 | 90 | R.N.S. TRADING | 10.29 | 0 | 0 | 0
3663 | HOOGHLY | Hooghly Division | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | Baseline household survey work including collection of House Hold Details at Prescribed Format through Mobile App/Hard Copy for yearly data updation in JJM portal at HARIPAL Block under Chandannagar Sub-Division, P.H.E. Dte. | 220/chan | 13/04/2022 | 20 | M/S S.G. CONSTRUCTION | 4.98 | 0 | 0 | 100
3664 | HOOGHLY | Central Drilling | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBEWELL BY DEPARTMENTAL RIG MACHINE AT AMODGHATA W/S SCH TW-II, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 377/CMSD-II | 01/08/2022 | 15 | C.M. ENTERPRISE | 2.93 | 2.63 | 100 | 0
3665 | HOOGHLY | Hooghly Division | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | Jack pushing / Horizontal direct drilling along Railway land and below Railway track for laying 600 mm dia M.S Casing Pipe,150 mm dia M.S Carrier Pipe through in between Mast no 40/1057-40/29 & 49/29A-40/30A on HWH-BWN (Chord) Section Chandanpur to Porabazar Station for Chandanpur Piped Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | 2432/HUG | 11/08/2023 | 60 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 37.98 | 37.82 | 100 | 98
3666 | HOOGHLY | Hooghly Division | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | Material Requisition To Resource Division | 1370/4/Hug | 06/07/2022 | 0 | Resource Division | 24.77 | 0 | 0 | 0
3667 | HOOGHLY | Hooghly Division | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | Material Requisition To Resource Division | 109/ 17/Hug | 10/01/2023 | 0 | Resource Division | 23.6 | 0 | 0 | 0
3668 | HOOGHLY | Hooghly Division | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | Material Requisition To Resource Division | 1383/23/Hug | 15/05/2023 | 0 | Resource Division | 3.45 | 0 | 0 | 0
3669 | HOOGHLY | Hooghly Division | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | PAYMENT FOR QUOTATION BILL TO WBSEDCL FOR CHANDANPUR WATER SUPPLY SCHEME UNDER CHANDANNAGORE SUB-DIVISION, PHE DTE. BILL WAS ALREADY SUBMITTED BY THE EXECUTIVE ENGINEER, HOOGHLY DIVISION, PHE DTE. | BP-2022-23-471 | 18/01/2023 | 0 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 2.4 | 0 | 0 | 0
3670 | HOOGHLY | Hooghly Division | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | Way leave Facility Charges | BP-2022-23-529 | 02/02/2023 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 6.78 | 0 | 0 | 0
3671 | HOOGHLY | Hooghly Division | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | PAYMENT IN RESPECT OF WBSEDCL TO THE ELECTRICAL DIVISION, PHE DTE. FOR THE CHANDANPUR W/S/SCH | BP-2023-24-98 | 26/05/2023 | 0 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 19.19 | 0 | 0 | 0
3672 | HOOGHLY | Hooghly Division | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | WBSEDCL | BP-2022-23-414 | 20/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.64 | 0 | 0 | 0
3673 | HOOGHLY | Hooghly Division | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, CHANDANNAGORE SUB-DIVISION, PHE DTE. | BP-2022-23-570 | 03/03/2023 | 0 | GOUR KUMAR DAS | 1.29 | 0 | 0 | 0
3674 | HOOGHLY | Electrical | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chandanpur water supply scheme, T.W. No. II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | 1319/ED | 17/08/2022 | 90 | ANJAN ENTERPRISE | 9.78 | 0 | 0 | 100
3675 | HOOGHLY | Hooghly Division | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | Laying Extra D.I Pipe for Interconnection Between OHR, Head work T.W &, 2nd t.w & allied works for Chandandanpur W/S Scheme under Chandannagar Sub - Division, PHE Dte. | 2441/HUG | 12/08/2023 | 445 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 56.42 | 25.62 | 45.41 | 52
3676 | HOOGHLY | Hooghly Division | Chandanpur Piped Water Supply Scheme. , SM/08995 | New | Construction of 1 no. 250 CUM capacity R.C.C. Elevated Reservoir with 20 m staging height Over R.C.C Bored Pile Foundation/Raft Foundation as per Departmental Type Drawing Design and Specification including pipeline connection and cost of pipes, specials, and Soil Investigation works for construction of OHR and Laying Distribution System, Laying CI/D.I pipes & specials for Rising Main pipe line in between T.W NO.-I & II to OHR and interconnection with distribution system including allied work, Construction of 1 No 5.9 M X 4.1 M Switch Room with Sanitary and Water Supply Arrangements, Construction of 1 no 4.10M x 3.5M Switch Room without Sanitary & Water Supply arrangement at 2nd T/W Site including Providing 1105 nos, FHTC in Chandanpur Water Supply Scheme of HARIPAL BLOCK under CHANDANNAGAR Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | 1606/Hug | 05/08/2022 | 791 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 278.64 | 234.7 | 75.12 | 70
3677 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAPSIT WATER SUPPLY SCHEME , SM/09067 | Retrofitting | Providing 280 Nos FHTC TAP Connection For Kapsit PWSS | 1917/Hug. | 27/10/2021 | 30 | M/S S & P CONSTRUCTION | 16.74 | 16.74 | 100 | 100
3678 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAPSIT WATER SUPPLY SCHEME , SM/09067 | Retrofitting | Providing 550 nos Functional Household Tap Connection (FHTC) within the left out Mouzas of KAPSIT Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | 1088/HUG | 03/06/2022 | 30 | BRISTI CONSTRUCTION | 30.74 | 23.5 | 76.46 | 100
3679 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAPSIT WATER SUPPLY SCHEME , SM/09067 | Retrofitting | Providing 250 nos Functional Household Tap Connection (FHTC) within the command area of KAPSIT Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | 464/Hug | 10/03/2022 | 20 | KOUSIK MONDAL | 12.26 | 12.14 | 99.06 | 30
3680 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAPSIT WATER SUPPLY SCHEME , SM/09067 | Retrofitting | FHTC |  | 28/01/2022 | 0 | S AND P CONSTRUCTION | 16.74 | 0 | 0 | 0
3681 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAPSIT WATER SUPPLY SCHEME , SM/09067 | Retrofitting | Providing 280 nos Functional Household Tap Connection (FHTC) within the command area of Kapsit Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | 1917/Hug | 27/10/2021 | 30 | S AND P CONSTRUCTION | 16.75 | 0 | 0 | 100
3682 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAPSIT WATER SUPPLY SCHEME , SM/09067 | Retrofitting | Construction of Boundary wall, Pathway & Land development at the Head Work site of Kapsit W/S Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte | 1536/HUG | 24/11/2020 | 1451 | KAPTON | 13.57 | 0 | 0 | 100
3683 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. , SM/09070 | Retrofitting | Providing 1600 nos Functional Household Tap Connection (FHTC) within the command area of Saptagram Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 1674/HUG | 13/09/2021 | 40 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 73.56 | 29.38 | 39.93 | 100
3684 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. , SM/09070 | Retrofitting | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT SAPTAGRAM PWSS, CHINSURAH MOGRA BLOCK, HOOGHLY DISTRICT UNDER CMSD-I (D), CDD, PHE DTE. | 178/CMSD-I (D) | 10/06/2022 | 15 | S B S ENTERPRISE | 3.88 | 3.73 | 100 | 100
3685 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. , SM/09070 | Retrofitting | SUPPLY & DELIVERY OF CONSUMBLES AT SITE FOR CONSTRUCTION OF TUBE WELL AT SAPTAGRAM PWSS, CHINSURAH MOGRA BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 181/CMSD-I (D) | 20/06/2022 | 15 | M/S PRACHI ENGINEERING | 1.88 | 1.77 | 100 | 100
3686 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. , SM/09070 | Retrofitting | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT SAPTAGRAM PWSS, CHINSURAH MOGRA BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 176/CMSD-I (D) | 10/06/2022 | 15 | S B S ENTERPRISE | 4.85 | 4.36 | 100 | 100
3687 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. , SM/09070 | Retrofitting | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELLS AT HARIPAL (Z-I) PWSS, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-I (D), CDD, PHE DTE. | 574/CMSD-I (D) (P-II) | 30/11/2022 | 7 | C.M. ENTERPRISE | 0.7 | 0.06 | 100 | 0
3688 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. , SM/09070 | Retrofitting | Construction of 3.60 m X 3.00 m Switch Room with Sanitary and Water Supply & Sanitation arrangement at 4th T/W Site of SAPTAGRAM W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | 724/CH | 23/08/2022 | 45 | SRI KRISHNA ENTERPRISE | 4.97 | 4.97 | 100 | 100
3689 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. , SM/09070 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of SAPTAGRAM Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 2936/HUG | 28/12/2022 | 50 | STP ENTERPRISE | 48.34 | 43.73 | 48.69 | 90
3690 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. , SM/09070 | Retrofitting | ADDITIONAL WORK FOR CONSTRUCTION OF TUBEWELL AT IIEST TW-I, SHIBPUR, HOWRAH DISTRICT BY UTILISING SKIILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. | 111/CMSD-I | 29/04/2022 | 15 | ASHUTOSH DAS & CO | 0.93 | 0.93 | 100 | 0
3691 | HOOGHLY | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. , SM/09070 | Retrofitting | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | 1724/CDD | 29/12/2022 | 30 | DEY ENTERPRISE | 13.83 | 0.15 | 100 | 0
3692 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | 1ST CONTINUATION ORDER FOR Deployment of 2 (two) Nos. Security Guard without Arm for guarding arrangement of Office cum store at Kamarpukur Bunglow under Arambag Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.12.2021 to 31.03.2022. | 2089/Hug | 25/11/2021 | 121 | PEACOCK SECURITY SERVICE | 1.69 | 0 | 0 | 0
3693 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | 2ND CONTINUATION ORDER FOR Deployment of 5 (five) Nos. Security Guard without Arm for guarding arrangement of Office cum store at SODEPUR Water Supply Scheme under Arambag Sub-Division, under Hooghly Division, PHE Dte.. Period 4 months from 01.04.2022 to 31.07.2022. | 626/Hug | 31/03/2022 | 122 | PEACOCK SECURITY SERVICE | 4.26 | 0 | 0 | 0
3694 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Power Connection for Saidpur W/S. Sch. | 5003400960/Quot/03 | 11/07/2022 | 365 | WBSEDCL | 13.34 | 0 | 0 | 0
3695 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Additional survey work for preparation of DPR for Augmentation of Saidpur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. (Saidpur Part-B) | 408/Arg | 07/06/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.17 | 0 | 0 | 0
3696 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Preparation of DPR for Augmentation of Saidpur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. (Saidpur Part-A) | 407/Arg | 07/06/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.68 | 6.85 | 100 | 0
3697 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | SINKING OF TUBE WELL (300MMX200MMX250 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR SAIDPUR W/S SCH UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 1297/CDD | 17/02/2022 | 30 | PADMA ENGINEERING & CO. | 14.58 | 11.25 | 100 | 0
3698 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Construction of approach road at 3rd Tube Well Site of Saidpur Zone-I Piped Water Supply Scheme under Arambagh Sub-Division , P.H.E.Dte. | 614/Arg | 31/08/2022 | 20 | M/S KHAMRUI CONSTRUCTION | 1.42 | 1.37 | 100 | 0
3699 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Electric Supply | 15 | 15/07/2022 | 0 | WBSEDCL | 13.34 | 0 | 0 | 0
3700 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | 1ST CONTINUATION ORDER FOR Deployment of 4 (four) Nos. Security Guard without Arm for guarding arrangement of Office cum store at Arambag Sub-Division Office under Arambag Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.12.2021 to 31.03.2022. | 2088/Hug | 25/11/2021 | 121 | PEACOCK SECURITY SERVICE | 3.38 | 0 | 0 | 0
3701 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | 2nd Continuation for Operation & Maintenance of OHR, FHTC & Laying Distribution System including Street stand Post, Rising Main & other essential components ofSrirumpore, Shyampur & Saidpur (Zone-I & II) W/S Scheme for the period of 01.12.22 to 31.12.22 under Arambag Sub- Division P.H.E Dte. SL-37 | 2614/HUG | 30/11/2022 | 31 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 0.83 | 0 | 0 | 0
3702 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Supply, Delivery & Installation of S/P/M & other E/M equipments etc. including allied works for Saidpur W/S. Sch. Z-I, TW-III. Hooghly | 1038/ED | 28/06/2022 | 90 | P.K. ENGINEERING | 10.19 | 9.86 | 96.72 | 0
3703 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Repairing of Concrete Road damaged due to Laying Distribution System and Interconnection Pipeline with other allied works of SAIDPUR Zone-II Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | 1126/HUG | 19/04/2023 | 30 | MINTU CHAKRABORTY | 35.76 | 0 | 0 | 0
3704 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at SAIDPUR (ZONE-I) PWSS of Arambag Sub-Division under Hooghly Division, PHE Dte. SL - 09 | 1957/HUG | 07/09/2022 | 30 | OSMAN SEKH | 11.32 | 10.33 | 100 | 0
3705 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at SAIDPUR ZONE-II PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | 2505/HUG | 22/11/2022 | 30 | OSMAN SEKH | 12.72 | 12.45 | 100 | 100
3706 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | REPAIRING OF MUD PUMP FLUID CHAMBER, TRANSMISSION LINE AND OTHERS WORKS ALONG WITH SUPPLY OF DRILLING ACCESSORYU OF RIG MACHINE- JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. | 72/CMSD-I | 30/03/2022 | 15 | PADMA ENGINEERING & CO. | 4 | 2.39 | 100 | 0
3707 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | DEFIXING, DISMOUNTING AND DISMANTLING THE MUD PUMP OIL CHAMBER, FLUID CHAMBER, PTO FOR RIG MACHINE JOHN/DR/1000 (MUD PUMP) UNDER CMSD-I (D), CDD, PHE DTE. | 141/CMSD-I | 23/08/2021 | 7 | PADMA ENGINEERING & CO. | 0.11 | 0.11 | 100 | 0
3708 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Material Requisition To Resource Division | 1124/2/HUG | 06/06/2022 | 0 | Resource Division | 9.24 | 0 | 0 | 0
3709 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Material Requisition To Resource Division | 127/27/Hug | 13/01/2023 | 0 | Resource Division | 39.26 | 0 | 0 | 0
3710 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Material Requisition To Resource Division | 1773/41/Hug | 29/08/2022 | 0 | Resource Division | 1.38 | 0 | 0 | 0
3711 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Material Requisition To Resource Division | 1590/1/Hug | 03/08/2022 | 0 | Resource Division | 24.64 | 0 | 0 | 0
3712 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Material Requisition To Resource Division | 1385/59/Hug | 15/05/2023 | 0 | Resource Division | 39.55 | 0 | 0 | 0
3713 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Quotation Bill for New Service Connection at Aug. of Saidpur W/S. Sch. Z-II, PH-III & II | 218 | 27/03/2023 | 0 | WBSEDCL | 15.33 | 0 | 0 | 0
3714 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Augmentation of Saidpur (Zone-II) Water Supply scheme with LDS, Rising main, FHTC work, Pump House & 500 cum capacity OHR with 20 mtr. staging height including soil investigation at Pursurah Block in Arambag Sub-Division, District:- Hooghly under Hooghly Division, PHE Dte. | 1020/Hug | 27/05/2022 | 365 | MINTU CHAKRABORTY | 602.3 | 511.77 | 84.97 | 75
3715 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Saidpur water supply scheme Zone I TW No I and Zone II TW No I Block Pursurah, District Hooghly under ED PHED. | 856/ED | 14/02/2023 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 21.48 | 20.91 | 97.34 | 65
3716 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Sinking of 2 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of SAIDPUR Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3185/HUG | 11/09/2024 | 30 | B.K ENTERPRISE | 32.31 | 0 | 0 | 0
3717 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at SAIDPUR ZONE-II (1No.), SAIDPUR ZONE-I (2Nos.) ARANDI (1 No.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3435/HUG | 03/10/2024 | 90 | T.K. INTERNATIONAL | 47.2 | 0 | 0 | 0
3718 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of NATIBPUR , SAIDPUR Zone-II , KRISHNANAGAR Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3170/HUG | 10/09/2024 | 45 | BIMAL KUMAR HALDER | 48.47 | 0 | 0 | 0
3719 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Interconnection of T.W. III with LDS for AUGMENTATION of SAIDPUR ZONE-II Piped Water Supply Scheme under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. Block-Arambagh, District:- Hooghly | 2417/HUG | 26/06/2024 | 30 | MINTU CHAKRABORTY | 25.39 | 0 | 0 | 0
3720 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Repairing of existing Switch Rooms and Construction of Boundary Wall with Internal Pathway and Drain at H/W Site for Saidpur Zone-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, PHE Dte. | 4147/HUG | 26/12/2024 | 90 | BANSBERIA CONSTRUCTION CO. | 48.83 | 0 | 0 | 0
3721 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Repairing of existing Switch Rooms and Construction of Boundary Wall for HW & 2nd TW Site with Construction of Toilet at 2nd T/W Site for Saidpur Zone-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, PHE Dte. | 4148/HUG | 26/12/2024 | 90 | TANISA ENTERPRISE | 49.97 | 0 | 0 | 0
3722 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR SAIDPUR. , SM/10340 | Augmentation | Augmentation of Saidpur (Zone-I) Water Supply scheme with LDS, Rising main, FHTC work, Pump House & 600 cum capacity OHR with 20 mtr. staging height including soil investigation at Pursurah Block in Arambag Sub-Division, District:- Hooghly under Hooghly Division, PHE Dte. (2nd Call) | 1182/Hug | 15/06/2022 | 1200 | BANSBERIA CONSTRUCTION CO. | 600.84 | 551.71 | 91.83 | 92
3723 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. , SM/09690 | Augmentation | Preparation of DPR for Augmentation of Aniya Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-I] | 288/SER | 18/02/2022 | 20 | SRIJAN ECHOLOGICAL UPLIFTMENT PVT. LTD. | 3.22 | 3.19 | 99.11 | 100
3724 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. , SM/09690 | Augmentation | Augmentation of ANIYA Water Supply Scheme with Laying Distribution System within ANIYA Mouza (Part), Shyamsundarpur & Kalyanbati Mouza, Repairing of existing OHR, Switch Rooms (H/W & 2ND T.W Site) & Construction of Boundary wall at H/W Site and FHTC Work under Chanditala-I Block of Serampore Sub-Division, Hooghly Division, PHE Dte | 828/Hug | 20/04/2022 | 60 | ARUN SEAL AND CO. | 155.99 | 149.62 | 95.92 | 30
3725 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. , SM/09690 | Augmentation | Augmentation of ANIYA Water Supply Scheme with Laying Distribution System within ANIYA Mouza (Part), Construction of boundary wall at 2nd TW site and FHTC Work under Chanditala-I Block of Serampore Sub-Division, Hooghly Division, PHE Dte. | 829/Hug | 20/04/2022 | 30 | DAS ENTERPRISE (SAMIR DAS) | 84.14 | 80.13 | 95.23 | 30
3726 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. , SM/09690 | Augmentation | Material Requisition To Resource Division | 422/4/Hug | 07/03/2022 | 0 | Resource Division | 39.63 | 0 | 0 | 0
3727 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. , SM/09690 | Augmentation | Material Requisition To Resource Division | 1122/HUG | 06/06/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
3728 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. , SM/09690 | Augmentation | Material Requisition To Resource Division | 1689/HUG | 22/08/2022 | 0 | Resource Division | 0.87 | 0 | 0 | 0
3729 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. , SM/09690 | Augmentation | Material Requisition To Resource Division | 2210/Hug | 30/09/2022 | 0 | Resource Division | 0.05 | 0 | 0 | 0
3730 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. , SM/09690 | Augmentation | Material Requisition To Resource Division | 1291/Hug | 24/06/2022 | 0 | Resource Division | 6.16 | 0 | 0 | 0
3731 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. , SM/09690 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Seakhala PWSS 2. Aniya PWSS 3. Dudhkalmi PWSS 4. Nababpur PWSS 5. Gangadharpur PWSS 6. Kumirmora PWSS | 109/SER | 23/02/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 80
3732 | HOOGHLY | Hooghly Division | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte , SM/10357 | New | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at H/W SITE OF TANTISAL PWSS of Arambag Sub-Division under Hooghly Division, PHE Dte. SL NO - 11 | 2013/HUG | 13/09/2022 | 30 | PRASUN ENTERPRISE (PRASUN BISWAS) | 11.75 | 10.45 | 100 | 0
3733 | HOOGHLY | Central Drilling | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte , SM/10357 | New | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 150 mtrs. Depth) by utilising Departmental machineries for tantisal W/S Scheme (TW-I), Khanakul-II block under hooghly District, CDD PHE Dte. | 11/CDD | 04/04/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 11.14 | 10.4 | 100 | 100
3734 | HOOGHLY | Hooghly Division | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte , SM/10357 | New | Material Requisition To Resource Division | 1385/25/Hug | 15/05/2023 | 0 | Resource Division | 17.73 | 0 | 0 | 0
3735 | HOOGHLY | Hooghly Division | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte , SM/10357 | New | Material Requisition To Resource Division | 3057/44/Hug | 11/10/2023 | 0 | Resource Division | 17.73 | 0 | 0 | 0
3736 | HOOGHLY | Hooghly Division | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte , SM/10357 | New | Material Requisition To Resource Division | 1234/38/Hug | 28/04/2023 | 0 | Resource Division | 17.89 | 0 | 0 | 0
3737 | HOOGHLY | Electrical | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte , SM/10357 | New | Quotation for New Service Connection for Tantisal water Supply Scheme,TW No-II, Block-Khanakul-I,Dist-Hooghly under ED PHE Dte. | 221 | 25/08/2023 | 0 | WBSEDCL | 3.77 | 0 | 0 | 0
3738 | HOOGHLY | Electrical | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte , SM/10357 | New | Quotation Bill for New Service Connection at Tantisal W/S Sch. TW-I | 226 | 29/03/2023 | 0 | WBSEDCL | 3.13 | 0 | 0 | 0
3739 | HOOGHLY | Hooghly Division | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte , SM/10357 | New | Tantisal W/S scheme with LDS Rising mainFHTC workPump House(5.9mx4.1m) with sanitary w/s arrangementsPump house(4.1mx3.5m)450 cum capacityOHR with20 mtr. staging height including soil investigation at Khanakul-IBlockin ArambaghSub-Divn, Dist-Hooghly | 640/Hug | 01/04/2022 | 12 | PRASUN ENTERPRISE (PRASUN BISWAS) | 464.21 | 376.55 | 81.12 | 25
3740 | HOOGHLY | Electrical | Ground Based Piped Water Supply Scheme Tantisal PWSS under Khanakul I Block of Arambagh Sub Division under Hooghly Division PHE Dte , SM/10357 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Tantisal water supply scheme, T.W. No. I & II, Block: Khanakul-I, District - Hooghly under Electrical Division, PHE Dte. | 3478/ED | 30/12/2022 | 90 | GHOSE ENGINEERING SYNDICATE | 22.37 | 21.99 | 98.77 | 60
3741 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. , SM/09698 | Augmentation | Preparation of DPR for Augmentation of ANUR Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-II]. | 610/Arg | 31/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.48 | 3.48 | 100 | 100
3742 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. , SM/09698 | Augmentation | Sinking of I (one) No Big dia tube well (250 mm X150mm) with supply of PVC Pipe and strainer and having depth upto 150 M at 4th TW site of Sabalsinghapur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 1414/HUG | 12/07/2022 | 30 | OSMAN SEKH | 8.6 | 8.44 | 50 | 100
3743 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. , SM/09698 | Augmentation | Augmentation of ANUR (ZONE-I) Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection, Repairing of Switch room, Boundary wall, existing OHR at GOGHAT-II Block under Arambag Sub-Division, PHE Dte. | 1600/Hug | 04/08/2022 | 75 | SIBSANKAR CHOWDHURY | 200.45 | 127.81 | 63.76 | 40
3744 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. , SM/09698 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Anur water supply scheme, T.W. No.- I, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | 820/ED | 14/02/2023 | 90 | SUTRADHAR TRADERS | 10.78 | 10.75 | 99.77 | 0
3745 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. , SM/09698 | Augmentation | Augmentation of ANUR (ZONE-II) Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection, Construction of Switch Room, Boundary Wall of 3rd T.W. Site at GOGHAT-II Block under Arambag Sub-Division, PHE Dte. | 1087/Hug | 02/06/2022 | 40 | M/S SHIVAM UDYOG | 81.78 | 69.32 | 100 | 100
3746 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. , SM/09698 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ANUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | 2503/HUG | 22/11/2022 | 30 | M/S SHIVAM UDYOG | 12.72 | 10.81 | 100 | 0
3747 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. , SM/09698 | Augmentation | Material Requisition To Resource Division | 424/1/Hug | 07/03/2022 | 0 | Resource Division | 36.05 | 0 | 0 | 0
3748 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. , SM/09698 | Augmentation | Material Requisition To Resource Division | 1773/23/Hug | 29/08/2022 | 0 | Resource Division | 0.69 | 0 | 0 | 0
3749 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. , SM/09698 | Augmentation | Material Requisition To Resource Division | 1590/4/Hug | 03/08/2022 | 0 | Resource Division | 18.48 | 0 | 0 | 0
3750 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. , SM/09698 | Augmentation | Material Requisition To Resource Division | 1385/20/Hug | 15/05/2023 | 0 | Resource Division | 2.3 | 0 | 0 | 0
3751 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. , SM/09698 | Augmentation | Quotation Bill for New Service Connection at Annur W/S. Sch. Z-II, PH-I | 186 | 13/03/2023 | 0 | WBSEDCL | 4.44 | 0 | 0 | 0
3752 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. , SM/09698 | Augmentation | Sinking of 2 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Siteof ANUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 3168/HUG | 10/09/2024 | 30 | KALPATARU ENTERPRISE | 32.25 | 0 | 0 | 0
3753 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. , SM/09698 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of ANUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 4086/HUG | 19/12/2024 | 90 | DHIRENDRA ENGINEERING & CONSTRUCTION | 9.58 | 0 | 0 | 0
3754 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. , SM/09698 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SAOTA PWSS- 3nos (2) ANUR PWSS- 3nos (3) Badanganj PWSS (Z- I)- 4nos (4) Badanganj PWSS (Z- II)-4nos | 808/Arg | 23/08/2024 | 130 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.21 | 100 | 100
3755 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. , SM/09698 | Augmentation | Quotation money deposition for new service connection at kamarpukur,Anur w/s scheme, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004182874 Reference ID- 503645387 SM Code- 09698 | 147 | 22/05/2024 | 0 | WBSEDCL | 5.57 | 0 | 0 | 0
3756 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Laying of UPVC pipe for crossing through culvert below National Highway - 2 including repairing of damage AC pipe for providing water supply at BORAI under BoraKamalpur water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. | 214/chan | 13/04/2022 | 15 | G.K ENTERPRISE (GOUR KUMAR DAS) | 1.7 | 1.7 | 100 | 0
3757 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Material Requisition To Resource Division | 2686/12/Hug | 01/12/2022 | 0 | Resource Division | 0.33 | 0 | 0 | 0
3758 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Horizontal road crossing by trenchless method & parallel shifting of distribution pipe line at Ghanashyampur, Kamarkundu, Bora telermore, Sheetpara -Borai Beside NH12 Within Kamarpukur & Barakamalpur PWSS, under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | 2523/HUG | 23/11/2022 | 30 | SURAJIT SINGHA RAY | 25.39 | 25.37 | 99.93 | 0
3759 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Route survey Design drawing & DPR preparation of Barakamalpur Zone- I & II PWSS under Chandannagar Sub-Division, P.H.E. Dte. | 266/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.98 | 4.98 | 100 | 0
3760 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Route survey Design drawing & DPR preparation of Barakamalpur Zone- III & IV PWSS under Chandannagar Sub-Division, P.H.E. Dte | 267/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.71 | 4.69 | 100 | 0
3761 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Material Requisition To Resource Division | 79/14/Hug | 06/01/2023 | 0 | Resource Division | 320.94 | 0 | 0 | 0
3762 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Material Requisition To Resource Division | 902/7/Hug | 27/03/2023 | 0 | Resource Division | 34.55 | 0 | 0 | 0
3763 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Material Requisition To Resource Division | 1383/16/Hug | 15/05/2023 | 0 | Resource Division | 77.76 | 0 | 0 | 0
3764 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Quotation for new service connection charge at Bora Kamalpur PWSS, Zone-II, TW - VI | 532 | 15/12/2023 | 0 | WBSEDCL | 3.43 | 0 | 0 | 0
3765 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Quotation for new service connection at Barakamalpur W/S Sch., Zone - II, T/W - III | 385 | 25/10/2023 | 0 | WBSEDCL | 3.13 | 0 | 0 | 0
3766 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Quotation Bill for New Service Connection at Barakamalpur W/S. Sch. Z-II, TW-IV | 384 | 25/10/2023 | 0 | WBSEDCL | 5.89 | 0 | 0 | 0
3767 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Quotation for new service connection for Barakamalpur , Zone - III, T/W - I, Block Singur, Dist - hooghly | 173 | 10/08/2023 | 0 | WBSEDCL | 3.52 | 0 | 0 | 0
3768 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Quotation Bill for New Service Connection at Aug. of Bora Kamalpur W/S. Sch. Z-II | 403 | 09/11/2023 | 0 | WBSEDCL | 3.93 | 0 | 0 | 0
3769 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Quotation Bill for New Service Connection at Aug. of Bora Kamalpur W/S. Sch. Z-III | 404 | 09/11/2023 | 0 | WBSEDCL | 3.23 | 0 | 0 | 0
3770 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | AUGMENTATION of BARAKAMALPUR (ZONE-IV) Piped Water Supply Scheme with LDS, FHTC, Sinking of Tube Well & construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub-Division of Hooghly Division P.HE Dte. Block SINGUR, District:- Hooghly [AUGMENTATION SCHEME] | 889/HUG | 27/03/2023 | 717 | YOUNG ENGINEERS CO OPERATIVE SOCIETY LTD. | 98.75 | 0 | 0 | 50
3771 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for BARAKAMALPUR water supply scheme at different zone, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | 1371/ED | 14/03/2023 | 365 | M/S S.S. ENTERPRISE | 130.31 | 98.37 | 75.49 | 70
3772 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Olipur,Kulteghori,Paschim Jaykrishnapur & Barakamalpur W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 1839/HUG | 26/06/2023 | 45 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 80.45 | 14.85 | 100 | 100
3773 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Balance Laying Distribution System of proposed pipeline of BARAKAMALPURZONE-III Water Supply Scheme For AUGMENTATION of BARAKAMALPUR (ZONE-III) Piped Water Supply Scheme underChandannagarSub-Division of Hooghly Division P.HE Dte. Block SINGUR,District:-Hooghly[AUGMENTATION SCHEME] | 2902/HUG | 21/09/2023 | 90 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 96.84 | 96.75 | 100 | 100
3774 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Laying D.I Pipe& HDPE Pipe For AUGMENTATION of BARAKAMALPUR (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. Block SINGUR , District:- Hooghly [AUGMENTATION SCHEME] | 3117/HUG | 16/10/2023 | 90 | SURAJIT SINGHA RAY | 91.89 | 91.72 | 100 | 80
3775 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Laying Distribution System of proposed pipeline of BARAKAMALPURZONE-III Water Supply Scheme For AUGMENTATION of BARAKAMALPUR (ZONE-III)PipedWater Supply Scheme under ChandannagarSub-Division of Hooghly Division P.HEDte.Block SINGUR, District:-Hooghly[AUGMENTATIONSCHEME] | 3153/HUG | 17/10/2023 | 90 | M/S KAUSAR CONSTRUCTION | 93.46 | 93.41 | 100 | 100
3776 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Withdrawing & relaying of distribution main at H/W site of Bora -Kamalpur (Zone - II) W/S Scheme under Chandannagar Sub - Division, PHE Dte. | 758/HUG | 05/03/2024 | 15 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 2.98 | 2.97 | 100 | 100
3777 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Sinking of 4 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Berabari (3rd TWS), Gouribati (3rd TWS), Naita (2nd TWS), Barakamalpur (2nd TWS) W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | 3379/HUG | 21/11/2023 | 45 | OSMAN SEKH | 64.2 | 15.88 | 100 | 100
3778 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Quotation Bill for New Service Connection at Barakamalpur W/S. Sch. Z-III, TW-IV | 766 | 16/02/2024 | 0 | WBSEDCL | 3.94 | 0 | 0 | 0
3779 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Quotation Bill for New Service Connection at Barakamalpur W/S. Sch. Z-III, TW-III | 805 | 27/02/2024 | 0 | WBSEDCL | 5.78 | 0 | 0 | 0
3780 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Quotation for new service connection at Barakamalpur W/S Sch.[SM/12369], Zone - IV, T/W No. - I, (Gobindapur Dulepara), Block - Singur, Dt. - Hooghly under Nasibpur CCC, WBSEDCL, Ref. Id. - 503600456, Dated - 22-03-2024, Application No. - 5004079502 | 12 | 04/04/2024 | 0 | WBSEDCL | 2.81 | 0 | 0 | 0
3781 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Quotation Bill for New Service Connection at Barakamalpur W/S. Sch. Z-I, TW-I & TW-II | 665 & 666 | 11/01/2024 | 0 | WBSEDCL | 10.85 | 0 | 0 | 0
3782 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Construction of 600 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation, T.W, Rising Main, FHTC For AUGMENTATION of BARAKAMALPUR (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. Block SINGUR, District:- Hooghly [AUGMENTATION SCHEME] | 1355/HUG | 12/05/2023 | 720 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 419.11 | 90.43 | 21.58 | 60
3783 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | AUGMENTATION of BARAKAMALPUR (ZONE-I) Piped Water Supply Scheme with LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Chandannagar Sub-Division of Hooghly Division P.HE Dte. Block SINGUR, District:- Hooghly | 1356/HUG | 12/05/2023 | 904 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 310.94 | 42.31 | 13.61 | 80
3784 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Construction of 900 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation, T.W, LDS, Rising Main, FHTC & Construction of 4 Nos. Switch Room & Boundary wall at Proposed T.W Site For AUGMENTATION of BARAKAMALPUR (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. Block SINGUR , District:- Hooghly [AUGMENTATION SCHEME] | 2391/HUG | 10/08/2023 | 869 | P.B. ENTERPRISE (PINTU BHADURI) | 1034.2 | 312.15 | 30.18 | 15
3785 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Construction of 4 Nos. Switch Room & Boundary wall at Proposed T.W Site For AUGMENTATION of BARAKAMALPUR (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. Block SINGUR , District:- Hooghly [AUGMENTATION SCHEME] | 3105/HUG | 13/10/2023 | 597 | T.K. INTERNATIONAL | 54.41 | 36.42 | 66.94 | 75
3786 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARAKAMALPUR , SM/12369 | Augmentation | Horizontal Auger boring with water jet system including Laying of additional pipe line at molla-simla & pahalanpur mouza For AUGMENTATION of BARAKAMALPUR (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. Block SINGUR, District-Hooghly [AUGMENTATION SCHEME] | 3661/HUG | 13/11/2024 | 180 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 59.69 | 5.35 | 8.96 | 70
3787 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Preparation of DPR for Augmentation of Raghunathpur Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Chinsurah-Magra) | 129/CH | 17/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.13 | 4.12 | 99.76 | 0
3788 | HOOGHLY | Central Drilling | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT RAGHUNATHPUR W/S SCHEME TW-I, POLBA DADPUR BLOCK, HOOGHLY DIOSTRICT UNDER CDD, PHE DTE | 289/CMSD-II (D) | 01/06/2022 | 15 | C.M. ENTERPRISE | 4.99 | 4.73 | 100 | 0
3789 | HOOGHLY | Central Drilling | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT RAGHUNATHPUR W/S SCHEME TW-I, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 288/CDD | 01/06/2022 | 15 | C.M. ENTERPRISE | 3.07 | 2.9 | 100 | 0
3790 | HOOGHLY | Central Drilling | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | SUPPLY & DELIVERY CONSUMBLES SITE FOR CONSTRUCTION OF TUBE WELL AT RAGHUNATHPUR W/S SCH TW-I, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 290/CMSD-II (D) | 01/06/2022 | 15 | C.M. ENTERPRISE | 2.45 | 2.4 | 100 | 0
3791 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Special Repairing, maintenance work of damaged R.C.C. Elevated Reservoir of Capacity 1,36,200 litre of Raghunathpur & Damra Water Supply Scheme under Chinsurah Sub - Division of Hooghly Division, P.H.E. Dte. SL NO - 03 | 1906/HUG | 05/09/2022 | 45 | M/S SHIVAM UDYOG | 25.15 | 25.12 | 99.88 | 0
3792 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | 2nd Continuation for Operation & Maintenance of OHR, FHTC & Laying Distribution System including Street stand Post, Rising Main & other essential components of Raghunathpur & Somra W/S Scheme for the period of 01.12.2022 to 31.12.2022 under Chinsurah Sub- Division P.H.E Dte. | 2593/HUG | 30/11/2022 | 31 | M/S BISWAS CONSTRUCTION | 0.49 | 0 | 0 | 0
3793 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Augmentation of Raghunathpur (ZONE-II) with LDS, FHTC, Laying Rising Main & Interconnection with Distribution system at CHINSURAH-MOGRA Block under Chinsurah Sub-Division Under Hooghly Division P.H.E Dte | 1572/HUG | 01/08/2022 | 40 | DAS ENTERPRISE (SAMIR DAS) | 96.59 | 87.61 | 90.7 | 50
3794 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Construction of 1 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site of RAGHUNATHPUR ZONE-I Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | 444/HUG | 16/02/2023 | 45 | SHREEOM ENTERPRISE | 6.29 | 6.29 | 100 | 0
3795 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | 3rd Continuation for Operation & Maintenance of OHR, FHTC & Laying Distribution System including Street stand Post, Rising Main & other essential components of Raghunathpur & Somra W/S Scheme for the period of 01.01.23 to 31.08.22 under Chinsurah Sub- Division P.H.E Dte. SL-15 | 2974/HUG | 30/12/2022 | 243 | M/S BISWAS CONSTRUCTION | 3.96 | 0 | 0 | 0
3796 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at RAGHUNATHPUR(Zone-I) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 01 | 1953/HUG | 07/09/2022 | 45 | ARUN SEAL AND CO. | 23.79 | 23 | 100 | 0
3797 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at RGHUNATHPUR(Zone-II) PWSS of Chinsurah Sub-Division under Hooghly Division, PHE Dte. SL NO - 02 | 1954/HUG | 07/09/2022 | 45 | DAS ENTERPRISE (SAMIR DAS) | 23.78 | 22.92 | 100 | 0
3798 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement at Proposed T.W Site of RAGHUNATHPUR ZONE-II Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | 445/HUG | 16/02/2023 | 60 | DAS TRADING | 12.25 | 12.25 | 100 | 100
3799 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Dismantaling of old damaged Switch room at Ragunathpur 3rd Tube well site of Agumentation of Raghunathpur W/S Scheme under Chinsurah Sub- Division, PHE Dte. | 690/CH | 27/07/2023 | 10 | SRI KRISHNA ENTERPRISE | 0.31 | 0.31 | 100 | 100
3800 | HOOGHLY | Electrical | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Assistant Chief Engineer (M/E), PHE Dte. | 2382/HMSD | 27/12/2022 | 121 | BHOLA DEY | 1.11 | 1.11 | 100 | 1
3801 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Material Requisition To Resource Division | 2211/Hug | 30/09/2022 | 0 | Resource Division | 0.05 | 0 | 0 | 0
3802 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Material Requisition To Resource Division | 1383/31/Hug | 15/05/2023 | 0 | Resource Division | 17.69 | 0 | 0 | 0
3803 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Material Requisition To Resource Division | 226/8/Hug | 24/01/2023 | 0 | Resource Division | 59.6 | 0 | 0 | 0
3804 | HOOGHLY | Electrical | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT RAGHUNATHPUR, P.H. NO. - I | 52 | 31/05/2023 | 0 | WBSEDCL | 8.32 | 0 | 0 | 0
3805 | HOOGHLY | Electrical | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT RAGHUNATHPUR, P.H. NO. - IV | 52 | 31/05/2023 | 0 | WBSEDCL | 5.95 | 0 | 0 | 0
3806 | HOOGHLY | Electrical | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT RAGHUNATHPUR, P.H. NO. - II | 52 | 31/05/2023 | 0 | WBSEDCL | 2.64 | 0 | 0 | 0
3807 | HOOGHLY | Electrical | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT RAGHUNATHPUR, P.H. NO. - III | 52 | 31/05/2023 | 0 | WBSEDCL | 6.07 | 0 | 0 | 0
3808 | HOOGHLY | Electrical | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Raghunathpur water supply scheme TW No I II III and IV, Block Chinsurah Mogra, District Hooghly under ED PHED. | 855/ED | 14/02/2023 | 90 | D. K. ELECTRIC | 42.97 | 42.89 | 100 | 95
3809 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement and Boundary Wall for Augmentation of RAGHUNATHPUR Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.HE Dte. | 3315/HUG | 10/11/2023 | 45 | DIBYENDU DHARA | 8.56 | 7.98 | 100 | 65
3810 | HOOGHLY | Electrical | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sankhanagar Chakbansberia (Replacement) water supply scheme, T.W. No. I, Block: Chinsura-Mogra, District - Hooghly under Electrical Division, PHE Dte. | 4738/ED | 15/12/2023 | 90 | S. DUTTA | 10.74 | 0 | 0 | 90
3811 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Shifting House Connection from existing main to new main and allied works from Bispara to Demra of Raghunathpur Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 532/CH | 14/06/2024 | 7 | R.K. TRADERS | 4.85 | 0 | 0 | 75
3812 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Shifting House Connection from existing main to new main and allied works from Kuntighat More of Bispara of Raghunathpur Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 541/CH | 14/06/2024 | 7 | R.K. TRADERS | 4.84 | 0 | 0 | 75
3813 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Shifting HDPE pipeline and allied works from Kuntighat to Demra of Raghunathpur Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 542/CH | 14/06/2024 | 7 | R.K. TRADERS | 3.15 | 0 | 0 | 75
3814 | HOOGHLY | Hooghly Division | AUGMENTATION OF RAGHUNATHPUR PIPED WATER SUPPLY SCHEME , SM/11969 | Augmentation | Augmentation of Raghunathpur (ZONE-I) with LDS, FHTC, Rising Main & Construction of 500 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at CHINSURAH-MOGRA Block under Chinsurah Sub-Division Under Hooghly Division PHE Dte. | 2172/HUG | 28/09/2022 | 1380 | PRADIP KUMAR ADHYA | 433.19 | 235.24 | 54.3 | 55
3815 | HOOGHLY | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME , SM/12567 | New | Sinking of Five Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ATISARA, NANDA, NOWPARA, BASUBATI & ASTARA PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | 878/HUG | 27/03/2023 | 45 | MS D.PALIT AND CO. | 62.24 | 11.14 | 89.51 | 100
3816 | HOOGHLY | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME , SM/12567 | New | Material Requisition To Resource Division | 109/2/Hug | 10/01/2023 | 0 | Resource Division | 65.22 | 0 | 0 | 0
3817 | HOOGHLY | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME , SM/12567 | New | Material Requisition To Resource Division | 1235/1/Hug | 28/04/2023 | 0 | Resource Division | 75.7 | 0 | 0 | 0
3818 | HOOGHLY | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME , SM/12567 | New | Material Requisition To Resource Division | 902/1/Hug | 27/03/2023 | 0 | Resource Division | 14.85 | 0 | 0 | 0
3819 | HOOGHLY | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME , SM/12567 | New | Material Requisition To Resource Division | 3058/2/Hug | 11/10/2023 | 0 | Resource Division | 14.85 | 0 | 0 | 0
3820 | HOOGHLY | Electrical | NANDA PIPED WATER SUPPLY SCHEME , SM/12567 | New | Quotation for new service connection at Nanda W/S Sch., T/W No. - II, District - Hooghly | 301 | 22/09/2023 | 0 | WBSEDCL | 0.64 | 0 | 0 | 0
3821 | HOOGHLY | Electrical | NANDA PIPED WATER SUPPLY SCHEME , SM/12567 | New | Quotation for new service connection for Nanda W/s Sch., H/W Site(T/W No.- I), Dist - Hooghly | 88 | 12/07/2023 | 0 | WBSEDCL | 7.92 | 0 | 0 | 0
3822 | HOOGHLY | Electrical | NANDA PIPED WATER SUPPLY SCHEME , SM/12567 | New | Additional Quotation for Nanda W/S Sch., T/W no. - I, Block - Singur, Dt. - Hooghly | 196 | 17/08/2023 | 0 | WBSEDCL | 0.43 | 0 | 0 | 0
3823 | HOOGHLY | Electrical | NANDA PIPED WATER SUPPLY SCHEME , SM/12567 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nanda water supply scheme, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | 3499/ED | 30/12/2022 | 90 | RAJIB COMPANY | 21.48 | 21.45 | 100 | 95
3824 | HOOGHLY | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME , SM/12567 | New | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at ATISARA, NANDA, NAWPARA,BASUBATI & ASTARA W/S Scheme underChandannagar Sub-Division of Hooghly Division, P.H.E. Dte.. | 1818/HUG | 22/06/2023 | 45 | OSMAN SEKH | 80.85 | 16.06 | 100 | 100
3825 | HOOGHLY | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME , SM/12567 | New | Road Restoration of Anandanagar Health Centre Road | BP-2024-25-2 | 08/04/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 11.11 | 0 | 0 | 0
3826 | HOOGHLY | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME , SM/12567 | New | Construction of 400 cum capacity OHR with 20 mtr. staging height including Soil Investigation work, Laying Distribution System, Rising Main & Interconnection between O.H.R, TW No-I & II, Construction of 1 No 5.4M X 3.6M Switch Room with Sanitary and Water Supply Arrangements & Boundary Wall at Head Work Site, Construction of 1 No 3.6M x 3.0M Switch Room with Sanitary & Water Supply arrangement & Boundary Wall at 2nd T/W Site including Providing FHTC in NANDA Water Supply Scheme at SINGUR Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | 682/HUG | 10/03/2023 | 902 | PRASUN ENTERPRISE (PRASUN BISWAS) | 614.2 | 328.83 | 53.54 | 85
3827 | HOOGHLY | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME , SM/12567 | New | Sinking of Additional tubewell with Construction of switch-room & boundary wall, Laying Rising Main at Proposed 3rd TW site at Nanda Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | 1174/HUG | 02/05/2025 | 90 | PRASUN ENTERPRISE (PRASUN BISWAS) | 30.43 | 0 | 0 | 0
3828 | HOOGHLY | Hooghly Division | NANDA PIPED WATER SUPPLY SCHEME , SM/12567 | New | Laying balance pipeline and other allied works at NANDA PWSS under Chandannagar Sub Division, PHE Dte. Hooghly | 1175/HUG | 02/05/2025 | 60 | PRASUN ENTERPRISE (PRASUN BISWAS) | 44.68 | 0 | 0 | 0
3829 | HOOGHLY | Hooghly Division | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12232 | New | Material Requisition To Resource Division | 3057/24/Hug | 11/10/2023 | 0 | Resource Division | 10.79 | 0 | 0 | 0
3830 | HOOGHLY | Hooghly Division | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12232 | New | Material Requisition To Resource Division | 127/33/Hug | 13/01/2023 | 0 | Resource Division | 40.69 | 0 | 0 | 0
3831 | HOOGHLY | Hooghly Division | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12232 | New | KELEPARA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block of Arambag Sub-Division, PHE Dte. [NEW SCHEME] | 2236/HUG | 01/08/2023 | 270 | M/S R K ENTERPRISE | 502.36 | 87.56 | 17.43 | 10
3832 | HOOGHLY | Electrical | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12232 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KELEPARA PIPED W/S SCHEME, T.W. No. III, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1188/ED | 14/06/2024 | 90 | PADMA ENGINEERING CO. | 10.74 | 0 | 0 | 0
3833 | HOOGHLY | Electrical | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12232 | New | Electric quot. of WBSEDCL for New service Connection of Kelepara T/W-II W/S scheme under Electrical Division PHE Dte. (SM/12232) | 375 | 12/08/2024 | 0 | WBSEDCL | 3.67 | 0 | 0 | 0
3834 | HOOGHLY | Electrical | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12232 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kelepara water supply scheme, T.W. No.- I & II, Block: Pursura, District- Hooghly under Electrical Division, PHE Dte. | 3494/ED | 30/12/2022 | 900 | PADMA ENGINEERING CO. | 20.47 | 0 | 0 | 30
3835 | HOOGHLY | Hooghly Division | GROUND WATER BASED KELEPARA PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/12232 | New | Laying Distribution main by HDD process with HDPE pipe at Mayapur Z1, Kelepara, Krishnanagar Z1 & Z2 W/S Schme under Arambagh Sub Division of Hooghly Division, P.H.E. Dte. | 3438/HUG | 03/10/2024 | 360 | MS PRADIP KUMAR PAL | 15.93 | 0 | 0 | 40
3836 | HOOGHLY | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF POLBA-DADPUR, DHANIAKHALI, CHANDITALA-I & JANGIPARA IN HOOGHLY DISTRICT , SM/11621 | New | REQUISITION FOR SAJAL GRAM | C092250848485 | 28/09/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 350.65 | 0 | 0 | 0
3837 | HOOGHLY | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF POLBA-DADPUR, DHANIAKHALI, CHANDITALA-I & JANGIPARA IN HOOGHLY DISTRICT , SM/11621 | New | MINI WATER SUPPLY SCHEME |  | 13/09/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 786.94 | 0 | 0 | 0
3838 | HOOGHLY | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF POLBA-DADPUR, DHANIAKHALI, CHANDITALA-I & JANGIPARA IN HOOGHLY DISTRICT , SM/11621 | New | REQUISITION FOR SAJAL GRAM |  | 15/09/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 350.65 | 0 | 0 | 0
3839 | HOOGHLY | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF POLBA-DADPUR, DHANIAKHALI, CHANDITALA-I & JANGIPARA IN HOOGHLY DISTRICT , SM/11621 | New | Material Requisition To Resource Division | 1386/9/Hug | 15/05/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
3840 | HOOGHLY | Hooghly Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR THE BLOCKS OF POLBA-DADPUR, DHANIAKHALI, CHANDITALA-I & JANGIPARA IN HOOGHLY DISTRICT , SM/11621 | New | REQUISITION OF FUND FOR SAJAL GRAM SCHEME | BP-2022-23-434 | 30/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 151.83 | 0 | 0 | 0
3841 | HOOGHLY | Hooghly Division | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY , SM/12242 | New | Material Requisition To Resource Division | 1384/6/Hug | 16/05/2023 | 0 | Resource Division | 2.91 | 0 | 0 | 0
3842 | HOOGHLY | Hooghly Division | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY , SM/12242 | New | Material Requisition To Resource Division | 3060/16/Hug | 11/10/2023 | 0 | Resource Division | 2.91 | 0 | 0 | 0
3843 | HOOGHLY | Hooghly Division | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY , SM/12242 | New | Material Requisition To Resource Division | 792/2/Hug | 06/01/2023 | 0 | Resource Division | 2.91 | 0 | 0 | 0
3844 | HOOGHLY | Electrical | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY , SM/12242 | New | Bishnupur water supply scheme,PH No-II | 144 | 26/07/2023 | 0 | WBSEDCL | 2.89 | 0 | 0 | 0
3845 | HOOGHLY | Electrical | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY , SM/12242 | New | Bishnupur water supply scheme, P H No -I | 141 | 25/07/2023 | 0 | WBSEDCL | 3.39 | 0 | 0 | 0
3846 | HOOGHLY | Electrical | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY , SM/12242 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bishnupur water supply scheme, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | 3486/ED | 30/12/2022 | 90 | BARMAN ROY TRADERS | 20.46 | 19.87 | 97.11 | 85
3847 | HOOGHLY | Electrical | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY , SM/12242 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BILASPUR PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Jangipara, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1195/ED | 14/06/2024 | 706 | MAA KALI ENTERPRISE | 10.7 | 0 | 0 | 40
3848 | HOOGHLY | Hooghly Division | BISHNUPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY , SM/12242 | New | BISHNUPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block of Serampore Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | 749/Hug | 15/03/2023 | 749 | TOTON MONDAL | 232.56 | 158.88 | 68.32 | 92
3849 | HOOGHLY | Hooghly Division | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. , SM/12249 | New | Material Requisition To Resource Division | 1384/11/Hug | 15/05/2023 | 0 | Resource Division | 13.26 | 0 | 0 | 0
3850 | HOOGHLY | Hooghly Division | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. , SM/12249 | New | Material Requisition To Resource Division | 3060/18/Hug | 11/10/2023 | 0 | Resource Division | 13.26 | 0 | 0 | 0
3851 | HOOGHLY | Hooghly Division | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. , SM/12249 | New | Material Requisition To Resource Division | 79/5/Hug | 06/01/2023 | 0 | Resource Division | 13.26 | 0 | 0 | 0
3852 | HOOGHLY | Hooghly Division | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. , SM/12249 | New | CONSTRUCTION OF 2NOS. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT JAGANNATHPUR HW SITE AND 2ND SITE UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E DTE. | 427/SER | 31/07/2024 | 15 | SUNITI MAIRA | 0.68 | 0.66 | 100 | 95
3853 | HOOGHLY | Electrical | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. , SM/12249 | New | Quotation Bill for New Service Connection at Jagganathpur W/S. Sch. PH-I | 621 | 08/01/2024 | 0 | WBSEDCL | 6.73 | 0 | 0 | 0
3854 | HOOGHLY | Electrical | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. , SM/12249 | New | Quotation for New service connection at Jagannathpur W/S. Sch. | 825 | 01/03/2024 | 0 | WBSEDCL | 10.23 | 0 | 0 | 0
3855 | HOOGHLY | Electrical | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. , SM/12249 | New | Quotation Bill for Suplimentary Quotation for NSC Jagannathpur W/S. Sch PH-I | 695 | 22/01/2024 | 0 | WBSEDCL | 0.06 | 0 | 0 | 0
3856 | HOOGHLY | Electrical | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. , SM/12249 | New | Quotation Bill for New Service Connection at Jagannathpur W/S. Sch.PH-II | 607 | 04/01/2024 | 0 | WBSEDCL | 3.37 | 0 | 0 | 0
3857 | HOOGHLY | Hooghly Division | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. , SM/12249 | New | JAGANNATHPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block of Serampore Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | 2237/HUG | 01/08/2023 | 548 | SIBSANKAR CHOWDHURY | 584.82 | 224.7 | 38.42 | 40
3858 | HOOGHLY | Electrical | JAGANNATHPUR PIPED WATER SUPPLY SCHEME BLOCK: JANGIPARA, DISTRICT: HOOGHLY. , SM/12249 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jagannathpur water supply scheme, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | 3491/ED | 30/12/2022 | 848 | BISALAXMI ENTERPRISE | 20.31 | 17.69 | 87.36 | 50
3859 | HOOGHLY | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly , SM/12228 | Augmentation | Preparation of DPR for Augmentation of Ghoradaha Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II]. | 390/Arg | 31/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.22 | 3.34 | 100 | 0
3860 | HOOGHLY | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly , SM/12228 | Augmentation | Material Requisition To Resource Division | 1385/21/Hug | 15/05/2023 | 0 | Resource Division | 19.81 | 0 | 0 | 0
3861 | HOOGHLY | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly , SM/12228 | Augmentation | Material Requisition To Resource Division | 1234/10/Hug | 28/04/2023 | 0 | Resource Division | 17.59 | 0 | 0 | 0
3862 | HOOGHLY | Electrical | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly , SM/12228 | Augmentation | Quotation for New Service Connection of Goradaha w/s Scheme,TW No-3 Block-Khanakul-I,Dist-Hooghly under ED,PHE Dte | 220 | 25/08/2023 | 0 | WBSEDCL | 6.53 | 0 | 0 | 0
3863 | HOOGHLY | Electrical | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly , SM/12228 | Augmentation | Quotation Bill for New Service Connection at | 390 | 02/11/2023 | 0 | WBSEDCL | 8.75 | 0 | 0 | 0
3864 | HOOGHLY | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly , SM/12228 | Augmentation | Augmentation of GHORADAHA Piped Water Supply Scheme with Construction of Boundary wall at 1st T.W Site, Repairing of Switch room, Laying of Rising main with necessary interconnection with T.W. & Distribution System & Functional Household tap Connection under Arambag SUb-Division of Hooghly Division, PHE Dte. within Khanakul -II Block. | 493/HUG | 20/02/2023 | 90 | DILIP KUMAR GHOSH | 149.07 | 110.91 | 74.4 | 25
3865 | HOOGHLY | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly , SM/12228 | Augmentation | Augmentation of GHORADAHA Piped Water Supply Scheme by Sinking of 2 Nos. Tube well, Laying Distribution System, Construction of 2 Nos. Switch Room at 3rd & 4th Tubewell site and Boundary wall at 2nd, 3rd & 4th Tubewell site under Arambag Sub-Division of Hooghly Division PHE Dte. within Khanakul - II Block. | 396/HUG | 10/02/2023 | 90 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 202.79 | 137.89 | 68 | 20
3866 | HOOGHLY | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly , SM/12228 | Augmentation | Laying of Additional pipe line for Augmentation of GHORADAHA water Supply Scheme under, Arambagh Sub Division,of Hooghly Division PHE Dte. (Khanakul - II Block) | 3662/HUG | 13/11/2024 | 270 | M/S T.K.B. CONSTRUCTION | 79.95 | 0 | 0 | 50
3867 | HOOGHLY | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly , SM/12228 | Augmentation | Construction of supporting arrangement for LDS and allied works of GHORADAHA Piped Water Supply Scheme under Arambag Sub-Division of Hooghly Division, PHE Dte. | 2407/HUG | 26/06/2024 | 270 | DILIP KUMAR GHOSH | 17.92 | 0 | 0 | 75
3868 | HOOGHLY | Electrical | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly , SM/12228 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Goradaha water supply scheme, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | 839/ED | 14/02/2023 | 838 | M/S S R ENTERPRISE | 21.49 | 11.63 | 51.53 | 15
3869 | HOOGHLY | Hooghly Division | SIRAZPUR PIPED WATER SUPPLY SCHEME , SM/11580 | New | Material Requisition To Resource Division | 109/ 14/Hug | 10/01/2023 | 0 | Resource Division | 58.72 | 0 | 0 | 0
3870 | HOOGHLY | Hooghly Division | SIRAZPUR PIPED WATER SUPPLY SCHEME , SM/11580 | New | Material Requisition To Resource Division | 902/13/Hug | 27/03/2023 | 0 | Resource Division | 12.82 | 0 | 0 | 0
3871 | HOOGHLY | Electrical | SIRAZPUR PIPED WATER SUPPLY SCHEME , SM/11580 | New | Quotation for new service connection of Sirazpur w/s scheme,PH No-I Dist-Hooghly under ED,PHE Dte | 112 | 19/07/2023 | 0 | WBSEDCL | 5.08 | 0 | 0 | 0
3872 | HOOGHLY | Electrical | SIRAZPUR PIPED WATER SUPPLY SCHEME , SM/11580 | New | Quotation Bill for New Service Connection at Uttar Sirazpur W/S. Sch. TW-II | 443 | 24/11/2023 | 0 | WBSEDCL | 5.56 | 0 | 0 | 0
3873 | HOOGHLY | Hooghly Division | SIRAZPUR PIPED WATER SUPPLY SCHEME , SM/11580 | New | Laying of Rising main with necessary interconnection with T.W., OHR & Distribution System ,Construction of boundary walls at different TW site for SIRAZPUR Piped Water Supply Scheme under Chandannagar Sub-Division , District:- Hooghly | 2420/HUG | 11/08/2023 | 60 | M/S T.K.B. CONSTRUCTION | 41.15 | 18.21 | 44.26 | 70
3874 | HOOGHLY | Hooghly Division | SIRAZPUR PIPED WATER SUPPLY SCHEME , SM/11580 | New | Horizontal Auger boring with water jet system Including Approach Road at SIRAZPUR Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | 2903/HUG | 21/09/2023 | 30 | M/S T.K.B. CONSTRUCTION | 13.8 | 4.14 | 30 | 50
3875 | HOOGHLY | Hooghly Division | SIRAZPUR PIPED WATER SUPPLY SCHEME , SM/11580 | New | Sinking of 2 nos 300 X 200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tube Well Site of SIRAZPUR W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | 164/HUG | 16/01/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 28.19 | 28.13 | 100 | 100
3876 | HOOGHLY | Electrical | SIRAZPUR PIPED WATER SUPPLY SCHEME , SM/11580 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sirazpur water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | 3477/ED | 30/12/2022 | 90 | DIPALI CONSTRUCTION | 21.47 | 21.09 | 98.72 | 30
3877 | HOOGHLY | Hooghly Division | SIRAZPUR PIPED WATER SUPPLY SCHEME , SM/11580 | New | Construction of 2 Nos. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site Of SIRAZPUR Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.H.E Dte. | 446/HUG | 16/02/2023 | 60 | M/S T.K.B. CONSTRUCTION | 12.21 | 12.21 | 100 | 85
3878 | HOOGHLY | Hooghly Division | SIRAZPUR PIPED WATER SUPPLY SCHEME , SM/11580 | New | Making of 2 nos 1.8m X 1.45m X 2.1m KIOSK at Sirazpur 2nd T/W site & Kolachora PWSS under Chandannagar Sub-Division PHE Dte. | 279/Chan | 15/03/2024 | 15 | SUDIPTA SINHA | 0.88 | 0.82 | 100 | 100
3879 | HOOGHLY | Hooghly Division | SIRAZPUR PIPED WATER SUPPLY SCHEME , SM/11580 | New | SIRAZPUR Piped Water Supply Scheme with LDS, FHTC & Construction of 350 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work at HARIPAL Block under Chandannagar Sub-Division under Hooghly Division PHE Dte. | 2897/HUG | 22/12/2022 | 180 | PRASUN ENTERPRISE (PRASUN BISWAS) | 489.75 | 163.38 | 33.36 | 19
3880 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SRIPUR-BALAGARH WATER SUPPLY SCHEME , SM/12013 | Retrofitting | Providing 1000 nos Functional Household Tap Connection (FHTC) within the command area of Sripur Balagar Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 2203/Hug | 14/12/2021 | 60 | MALLIKA ENTERPRISE | 46.52 | 30.15 | 100 | 0
3881 | HOOGHLY | Hooghly Division | Bhabapur mini pipe water supply scheme , SM/13673 | New | Material Requisition To Resource Division | 1385/54/Hug | 15/05/2023 | 0 | Resource Division | 0.48 | 0 | 0 | 0
3882 | HOOGHLY | Hooghly Division | Bhabapur mini pipe water supply scheme , SM/13673 | New | Bhabapur Mini PWSS |  | 25/09/2024 | 0 | HOOGHLY ZILLA PARISHAD | 67.4 | 0 | 0 | 0
3883 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME , SM/11924 | Augmentation | Preparation of DPR for Augmentation of Cheragram Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | 146/CH | 21/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.48 | 4.44 | 100 | 0
3884 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME , SM/11924 | Augmentation | Material Requisition To Resource Division | 1386/13/Hug | 15/05/2023 | 0 | Resource Division | 13.66 | 0 | 0 | 0
3885 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME , SM/11924 | Augmentation | Material Requisition To Resource Division | 3059/33/Hug | 11/10/2023 | 0 | Resource Division | 13.66 | 0 | 0 | 0
3886 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME , SM/11924 | Augmentation | Material Requisition To Resource Division | 226/4/Hug | 24/01/2023 | 0 | Resource Division | 20.31 | 0 | 0 | 0
3887 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME , SM/11924 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Cheragram water supply scheme, T.W. No.- I, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | 831/ED | 14/02/2023 | 90 | INDRAJIT MITRA | 10.98 | 10.68 | 97.28 | 57
3888 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME , SM/11924 | Augmentation | Sinking of 1 no. 300 X200 mm dia Replacement Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Cheragram W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.. | 3593/HUG | 05/12/2023 | 30 | OSMAN SEKH | 16.05 | 0 | 0 | 100
3889 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME , SM/11924 | Augmentation | Quotation Bill for New Service Connection at Cheragram W/S. Sch. | 683 | 19/01/2024 | 0 | WBSEDCL | 13.03 | 0 | 0 | 0
3890 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME , SM/11924 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of DIGHIR, HASAMPUR, CHERAGRAM, GURAP PWSS under DHANIAKHALI Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | 323/HUG | 05/02/2025 | 25 | SWARNA ENTERPRISE | 8.63 | 0 | 0 | 0
3891 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHERAGRAM W/S SCHEME , SM/11924 | Augmentation | Construction of 2 Nos. 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation in ZONE-I & II, Sinking of tube-well, LDS, Rising Main, FHTC, construction of switch-room & boundary wall in ZONE-I & Repairing of Existing Switch Rooms, Boundary walls at different TW sites of both zones, LDS, Rising Main, FHTC in ZONE-II for Augmentation of CHERAGRAM Piped Water Supply Scheme under DHANIAKHALI Block, District:- Hooghly | 561/HUG | 27/02/2023 | 795 | TAPU SAHA | 543.92 | 410.67 | 75.51 | 98
3892 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | 2ND CONTINUATION ORDER FOR Deployment of 5 (five) Nos. Security Guard without Arm for guarding arrangement of Office cum store at Hooghly Division & Chinsurah Sub-Division Office under Chinsurah Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.04.2022 to 31.07.2022. | 621/Hug | 31/03/2022 | 122 | PRASUN ENTERPRISE (PRASUN BISWAS) | 4.26 | 0 | 0 | 0
3893 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | Preparation of DPR for Augmentation of Sibaichandi Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | 92/CH | 03/02/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.07 | 4.02 | 100 | 0
3894 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at BAGNAN ZONE-II(2NOS.), SIBAICHANDI ZONE-I(2NOS.), SRIKRISHNAPUR ZONE-II(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | 883/HUG | 27/03/2023 | 45 | B.K ENTERPRISE | 75.32 | 14.62 | 84.4 | 80
3895 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | Sinking of 1 (One) No Big dia tube well (300 mm x200mm) with supply of PVC Pipe and strainer and having depth upto 180 Mtr at SHIBAICHANDI W/S Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | 3317/HUG | 10/11/2023 | 30 | B.K ENTERPRISE | 14.48 | 14.42 | 100 | 95
3896 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | Material Requisition To Resource Division | 2209/1/Hug | 30/09/2022 | 0 | Resource Division | 0.05 | 0 | 0 | 0
3897 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | Material Requisition To Resource Division | 1386/58/Hug | 15/05/2023 | 0 | Resource Division | 12.71 | 0 | 0 | 0
3898 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | Material Requisition To Resource Division | 1264/24/HUG | 03/05/2023 | 0 | Resource Division | 33.5 | 0 | 0 | 0
3899 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | "Quotation Bill for New Service Connection at Sibaichandi TW-I & II | 309 & 310 | 27/09/2023 | 0 | WBSEDCL | 4.03 | 0 | 0 | 0
3900 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | "Quotation Bill for New Service Connection at Sibaichandi W/S. Sch. TW-I & II | 250, 251 | 05/09/2023 | 0 | WBSEDCL | 27.99 | 0 | 0 | 0
3901 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Sibaichandi water supply scheme TW No I and II Block DhaniakhalI District Hooghly under ED PHED. | 858/ED | 14/02/2023 | 90 | ANJAN ENTERPRISE | 21.45 | 19.65 | 91.61 | 45
3902 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | AUGMENTATION Of SIBAICHANDI ZONE-I Piped Water Supply Scheme with LDS, Rising Main & construction of boundary wall at HW site under DHANIAKHALI Block, District:- Hooghly [AUGMENTATION SCHEME] | 1787/HUG | 16/06/2023 | 90 | M/S BISWAS CONSTRUCTION | 138.84 | 94.78 | 68.27 | 30
3903 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | Laying Pipeline in left out portions including Repairing of RCC OHR, Switch Room, Boundary Wall, Pathway etc. of Sibaichandi Zone-I Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 534/HUG | 20/02/2024 | 30 | M/S BISWAS CONSTRUCTION | 32.28 | 0 | 0 | 0
3904 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | AUGMENTATION Of SIBAICHANDI ZONE-II Piped Water Supply Scheme with LDS, Rising Main& construction of boundary wall at HW site under DHANIAKHALI Block, District:- Hooghly [AUGMENTATION SCHEME] | 1219/HUG | 27/04/2023 | 60 | SK MAIDUL ISLAM | 54.16 | 53.97 | 100 | 95
3905 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | Construction of 2 Nos. switch-room at different TW site of SIBAICHANDI Water Supply Scheme under DHANIAKHALI Block, District:- Hooghly [AUGMENTATION SCHEME] | 1343/HUG | 11/05/2023 | 45 | SUDIPTA DAS | 12.29 | 12.29 | 100 | 95
3906 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Sibaichandi PWSS 2. Srikrishnapur PWSS 3. Aymanbabpur PWSS 4. Baichi PWSS 5. Balun PWSS 6. Dwarbasini PWSS | 205/CH | 29/02/2024 | 7 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 100 | 50
3907 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | Laying Balance pipeline within left out Mouzas / Habitations of different PWSS under DHANIAKHALI Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | 3563/HUG | 05/12/2023 | 30 | MUKHERJEE AND CO | 43.92 | 41.46 | 100 | 95
3908 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | DAMAGED PIPELINE OF PMGSY ROAD FROM RUHIA TO MAJINAN VIA SHIBAICHANDI RAILWAY STATION UNDER DHANIAKHALI BLOCK | BP-2023-24-677 | 22/12/2023 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 16.58 | 0 | 0 | 0
3909 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | Regarding damage of PMGSY Road | BP-2024-25-294 | 10/07/2024 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 9.93 | 0 | 0 | 0
3910 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | Laying Pipeline in uncovered areas and providing FHTC at the left out portions of Sibachandi (Zone-I & Zone-II) Piped Water Supply Scheme under Dhaniakhali-II Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 2365/HUG | 21/06/2024 | 285 | MAA JAGADHATRI CONSTRUCTION | 9.77 | 7.81 | 79.94 | 80
3911 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI , SM/11866 | Augmentation | Providing FHTC (At ZONE-I & ZONE-II), construction of boundary wall at Proposed TW site OF ZONE-I For AUGMENTATION of SIBAICHANDI ZONE-I & ZONE-II Piped Water Supply Scheme under DHANIAKHALI Block, District:- Hooghly [AUGMENTATION SCHEME] | 1220/HUG | 27/04/2023 | 363 | R. CONSTRUCTION | 82.07 | 72.08 | 88.08 | 96
3912 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR , SM/11868 | Augmentation | Preparation of DPR for Augmentation of Srikrishnapur Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | 145/CH | 21/02/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.76 | 4.73 | 99.33 | 0
3913 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR , SM/11868 | Augmentation | AUGMENTATION of SRIKRISHNAPUR (Zone-II) Piped Water Supply Scheme with LDS Within West portion, providing FHTC & Construction of Boundary Wall, Internal Pathway at H/W Site at DHANIAKHALI Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | 2858/HUG | 16/12/2022 | 60 | SAMRAT CONSTRUCTION | 87.74 | 61.98 | 70.64 | 20
3914 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR , SM/11868 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at BAGNAN ZONE-II(2NOS.), SIBAICHANDI ZONE-I(2NOS.), SRIKRISHNAPUR ZONE-II(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | 883/HUG | 27/03/2023 | 45 | B.K ENTERPRISE | 75.32 | 28.69 | 98.94 | 80
3915 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR , SM/11868 | Augmentation | Hiring of Luxury Car (BS-IV) for the Official us of the Executive Engineer, Electrical Division PHED wef 01.06.23 to 30.11.23 | 363_AE-I_ED | 29/05/2023 | 365 | TRIDIP SARKAR | 5 | 1.19 | 23.89 | 40
3916 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR , SM/11868 | Augmentation | Material Requisition To Resource Division | 226/9/Hug | 24/01/2023 | 0 | Resource Division | 33.67 | 0 | 0 | 0
3917 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR , SM/11868 | Augmentation | Material Requisition To Resource Division | 1386/57/Hug | 15/05/2023 | 0 | Resource Division | 13.9 | 0 | 0 | 0
3918 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR , SM/11868 | Augmentation | Quotation bill for new service connection charge at Srikrishnapur w/s scheme, T.W. No.-II | 181 | 11/08/2023 | 0 | WBSEDCL | 4.91 | 0 | 0 | 0
3919 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR , SM/11868 | Augmentation | Quotation Bill for New Service Connection at SRIKRISHNAPUR W/S. Sch. Z-II | 156 | 03/08/2023 | 0 | WBSEDCL | 3.84 | 0 | 0 | 0
3920 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR , SM/11868 | Augmentation | Quotation Bill for New Service Connection at SRIKRISHNAPUR W/S. Sch. Z-II |  | 01/08/2023 | 0 | WBSEDCL | 4.91 | 0 | 0 | 0
3921 | HOOGHLY | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR , SM/11868 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Srikrishnapur water supply scheme TW No I and II Block DhaniakhalI District Hooghly under ED PHED. | 860/ED | 14/02/2023 | 90 | ASHUTOSH DAS & CO. | 21.49 | 20.91 | 97.29 | 50
3922 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR , SM/11868 | Augmentation | AUGMENTATION of SRIKRISHNAPUR (Zone-I) Piped Water Supply Scheme with Laying Distribution System Within Srikrishnapur Mouza(Part), providing FHTC & repairing of of Switch Room (3.6 M x 3.0M) & Boundary wall at existing 2nd T.W Site at DHANIAKHALI Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | 2855/HUG | 16/12/2022 | 60 | DAS TRADING | 78.15 | 67.56 | 100 | 75
3923 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR , SM/11868 | Augmentation | AUGMENTATION of SRIKRISHNAPUR (Zone-I) Piped Water Supply Scheme with Laying Distribution System Within Srikrishnapur Zone-I (North), providng FHTC & Construction of 3.6m x3.0 m Switch Room at Zone-II at DHANIAKHALI Block under Chinsurah Sub-Division Under Hooghly Division PHE Dte. | 2856/HUG12 | 16/12/2022 | 60 | DILIP KUMAR GHOSH | 68.2 | 59.71 | 100 | 80
3924 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR , SM/11868 | Augmentation | AUGMENTATION of SRIKRISHNAPUR (ZONE-I) Piped Water Supply Scheme with Laying Distribution System Within Dasghara G.P., providing FHTC & repairing of of 272 cum capacity RCC OHR, Boundary Wall, Switch Room at DHANIAKHALI Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | 2854/HUG | 16/12/2022 | 60 | SWASTIK ENTERPRISE | 72.14 | 67.11 | 100 | 75
3925 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR , SM/11868 | Augmentation | AUGMENTATION of SRIKRISHNAPUR (Zone-II) Piped Water Supply Scheme with LDS within South East, providing FHTC & Construction of Boundary Wall, Internal Pathway at 2nd TW Site at DHANIAKHALI Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. | 2857/HUG | 16/12/2022 | 60 | MS PRADIP KUMAR PAL | 77.87 | 62.03 | 74.74 | 100
3926 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR , SM/11868 | Augmentation | AUGMENTATION of SRIKRISHNAPUR (Zone-II) Piped Water Supply Scheme with Laying Distribution System Within South West, providing FHTC & Construction of 1 No 5.4 M X 3.6 M Switch Room with Sanitary and Water Supply Arrangements at Head Work Site at DHANIAKHALI Block under Chinsurah Sub-Division Under Hooghly Division PHE Dte. | 2890/HUG | 22/12/2022 | 60 | G.S CONSTRUCTION AND CO. | 61.25 | 55.58 | 100 | 67
3927 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SUPPLY SCHEME FOR SRIKRISHNAPUR , SM/11868 | Augmentation | Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (Superstructure part as per Departmental Drawing), pipe connection and cost of pipes & specials with necessary soil investigation with foundation design as per soil test report For AUGMENTATION of SRIKRISHNAPUR ZONE-II & its adjoining moujas water supply Scheme within DHANIAKHALI Block under Chinsurah Sub-Division of Hooghly Division, P.H.E.Dte. Dist. Hooghly. | 1103/HUG | 17/04/2023 | 728 | M/S SHIVAM UDYOG | 93.02 | 37.97 | 40.81 | 70
3928 | HOOGHLY | Hooghly Division | Uttar Hazipur Mini Piped Water Supply Scheme , SM/13663 | New | REQUISITION OF FUND FOR SAJAL GRAM SCHEME |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 29.32 | 0 | 0 | 0
3929 | HOOGHLY | Hooghly Division | Uttar Hazipur Mini Piped Water Supply Scheme , SM/13663 | New | Uttar Hazipur Mini PWSS | BP-2023-24-330 | 29/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 29.62 | 0 | 0 | 0
3930 | HOOGHLY | Electrical | Uttar Hazipur Mini Piped Water Supply Scheme , SM/13663 | New | Mini Piped Water Supply Scheme | 377 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 8.49 | 0 | 0 | 0
3931 | HOOGHLY | Hooghly Division | Dwaripara Mini Piped Water Supply Scheme , SM/13665 | New | Material Requisition To Resource Division | 1385/53/Hug | 15/05/2023 | 0 | Resource Division | 0.6 | 0 | 0 | 0
3932 | HOOGHLY | Hooghly Division | Dwaripara Mini Piped Water Supply Scheme , SM/13665 | New | PAYMENT FOR MINI PIPED WATER SUPPLY SCHEME |  | 23/06/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 34 | 0 | 0 | 0
3933 | HOOGHLY | Hooghly Division | Dwaripara Mini Piped Water Supply Scheme , SM/13665 | New | MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-338 | 31/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 32.41 | 0 | 0 | 0
3934 | HOOGHLY | Hooghly Division | Dwaripara Mini Piped Water Supply Scheme , SM/13665 | New | REQUISITION OF FUND FOR SAJAL GRAM SCHEME |  | 27/12/2022 | 0 | DISTRICT MAGISTRATE HOOGHLY | 30.6 | 0 | 0 | 0
3935 | HOOGHLY | Electrical | Dwaripara Mini Piped Water Supply Scheme , SM/13665 | New | Mini Piped water Supply Scheme | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
3936 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF GUPTIPARA PWSS FOR PROVIDING 6938NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE , SM/12882 | Retrofitting | Providing 700 nos Functional Household Tap Connection (FHTC) within the command area of GUPTIPARA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 2363/HUG | 07/11/2022 | 35 | ARUN SEAL AND CO. | 41.06 | 41.02 | 100 | 0
3937 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF GUPTIPARA PWSS FOR PROVIDING 6938NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE , SM/12882 | Retrofitting | Providing Functional Household Tap Connection at Roypara ( Mirdanga) village of Guptipara 1 No. Gram Panchyet under Guptipara W/S scheme under Chinsurah Sub- Division, PHE Dte. | 691/CH | 27/07/2023 | 15 | MAA BUNAMATA ENTERPRISE | 0.97 | 0.97 | 100 | 100
3938 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF GUPTIPARA PWSS FOR PROVIDING 6938NOS. FUNCTIONAL HOUSE HOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION, PHE DTE , SM/12882 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of different PWSS under BALAGARH Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | 2428/HUG | 11/08/2023 | 30 | SB ASSOCIATES | 42.72 | 38.01 | 100 | 85
3939 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. , SM/13356 | Retrofitting | Functional Household Tap Connection (FHTC) under JJM in DHARAMPUR PWSS, Block-CHINSURAH MOGRA under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO -02 | 2083/HUG | 21/09/2022 | 30 | M/S RAJKUMAR KHAN | 16.76 | 16.44 | 100 | 0
3940 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. , SM/13356 | Retrofitting | Rising Main in between 4th T.W to OHR Bypass arrangement and interconnection with Distribution System for DHARAMPUR Water Supply Scheme Under Chinsurah Sub-Division. | 720/CH | 23/08/2022 | 15 | SOUMYADIP DE | 3.71 | 3.27 | 100 | 0
3941 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. , SM/13356 | Retrofitting | Laying of Pipe line within left out portion for providing Functional Household Tap Connection (FHTC) under JJM in DHARAMPUR PWSS, Block-CHINSURAH MOGRA under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO - 03 | 2084/HUG | 21/09/2022 | 30 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 17.05 | 16.52 | 100 | 0
3942 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. , SM/13356 | Retrofitting | Connection of replacement T.W. with existing rising main pipe line at head works site for Dharampur W/S under Chinsurah Sub - Division P.H.E. Dte. | 12B/CH | 06/01/2023 | 15 | M/S BIMAL DAS AND CO. | 0.97 | 0.96 | 100 | 0
3943 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. , SM/13356 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DHARAMPUR PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 1129/HUG | 19/04/2023 | 45 | M/S SHIVAM UDYOG | 54.23 | 0 | 0 | 97
3944 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. , SM/13356 | Retrofitting | Construction of 1 No. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Construction of 2 nos. Boundary wall &Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos.T.W with distribution system, FHTC of DHARAMPUR W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | 1341/HUG | 11/05/2023 | 45 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 44.76 | 0 | 0 | 75
3945 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. , SM/13356 | Retrofitting | Providing FHTC in rest out portion of at Chatterjee Bagan of Dharampur PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | 289/CH | 15/03/2024 | 7 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 0.96 | 0.95 | 100 | 80
3946 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. , SM/13356 | Retrofitting | Providing FHTC in rest out portion of at Maynadanga of Dharampur PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | 290/CH | 15/03/2024 | 7 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 0.96 | 0.95 | 100 | 80
3947 | HOOGHLY | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. , SM/13356 | Retrofitting | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | 882/HUG | 27/03/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 13.09 | 100 | 65
3948 | HOOGHLY | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13325 | New | Material Requisition To Resource Division | 1385/45/Hug | 15/05/2023 | 0 | Resource Division | 8.35 | 0 | 0 | 0
3949 | HOOGHLY | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13325 | New | Material Requisition To Resource Division | 3059/43/Hug | 11/10/2023 | 0 | Resource Division | 8.35 | 0 | 0 | 0
3950 | HOOGHLY | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13325 | New | Material Requisition To Resource Division | 1234/39/Hug | 28/04/2023 | 0 | Resource Division | 14.42 | 0 | 0 | 0
3951 | HOOGHLY | Electrical | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13325 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHINRA PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | 1169/ED | 14/06/2024 | 90 | GOENKA ENTERPRISE | 10.74 | 0 | 0 | 0
3952 | HOOGHLY | Electrical | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13325 | New | Quotation money deposition for new service connection at Chingra w/s scheme, Zone- I, T.W. No.-2, Dist.-Hooghly under PHE Dte. Application No- 5004201533 Reference ID- 503652893 SM Code- 13325 | 223 | 18/06/2024 | 0 | WBSEDCL | 3.33 | 0 | 0 | 0
3953 | HOOGHLY | Electrical | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13325 | New | Quotation of New Service Connection for Chinra w/s Scheme,Zone-I,PH No-III Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13325) Application No-5004308863 Reference Id-503700260 | 510 | 21/10/2024 | 0 | WBSEDCL | 3.75 | 0 | 0 | 0
3954 | HOOGHLY | Electrical | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13325 | New | Quotation for Shifting Existing LT Structure at Chinra w/s Scheme,Zone-I,PH No-I Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13325).Application No-100000121107 Reference Id-860315657 | 548 | 30/10/2024 | 0 | WBSEDCL | 0.63 | 0 | 0 | 0
3955 | HOOGHLY | Electrical | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13325 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chinra water supply scheme, Zone-I, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | 777/ED | 09/02/2023 | 898 | GOENKA ENTERPRISE | 20.48 | 10.43 | 50.95 | 10
3956 | HOOGHLY | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13325 | New | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | 3168/HUG | 19/10/2023 | 805 | MACKINTOSH BURN LIMITED | 5743.06 | 77.58 | 19.56 | 50
3957 | HOOGHLY | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13325 | New | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of Chingra Zone-I Piped Water Supply Scheme under Khanakul-II Block of ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | 3658/HUG | 13/11/2024 | 212 | M/S KAUSAR CONSTRUCTION | 16.1 | 0 | 0 | 50
3958 | HOOGHLY | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13325 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | 463/HUG | 20/02/2025 | 45 | TECHVISION | 14.8 | 0 | 0 | 0
3959 | HOOGHLY | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT , SM/13325 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) CHILADANGI PWSS- 2no's (2) PATUL PWSS -1 no's (3) RADHABALLAVPUR PWSS (Z-I)- 1 no's (4) RADHABALLAVPUR PWSS (Z-II)- 2 no's (5) UDAYPUR PWSS - 2no's, (6) UDNA PWSS - 2no's, (7) CHINRA PWSS (Z-I)- 1 no's, (8) CHINRA PWSS (Z-II)- 3 no's | 1153/Arg | 10/12/2024 | 31 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
3960 | HOOGHLY | Electrical | BADE DIGARIA PIPED WATER SUPPLY SCHEME , SM/13336 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bade Digaria water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | 559/ED | 02/02/2023 | 90 | M/S A.K BANERJEE | 21.37 | 0 | 0 | 0
3961 | HOOGHLY | Hooghly Division | BADE DIGARIA PIPED WATER SUPPLY SCHEME , SM/13336 | New | Material Requisition To Resource Division | 109/ 12/Hug | 10/01/2023 | 0 | Resource Division | 3.49 | 0 | 0 | 0
3962 | HOOGHLY | Hooghly Division | BADE DIGARIA PIPED WATER SUPPLY SCHEME , SM/13336 | New | Material Requisition To Resource Division | 902/12/Hug | 27/03/2023 | 0 | Resource Division | 10.26 | 0 | 0 | 0
3963 | HOOGHLY | Hooghly Division | BADE DIGARIA PIPED WATER SUPPLY SCHEME , SM/13336 | New | Material Requisition To Resource Division | 1383/19/Hug | 15/05/2023 | 0 | Resource Division | 10.26 | 0 | 0 | 0
3964 | HOOGHLY | Hooghly Division | BADE DIGARIA PIPED WATER SUPPLY SCHEME , SM/13336 | New | Material Requisition To Resource Division | 3058/27/Hug | 11/10/2023 | 0 | Resource Division | 10.26 | 0 | 0 | 0
3965 | HOOGHLY | Electrical | BADE DIGARIA PIPED WATER SUPPLY SCHEME , SM/13336 | New | Quotation for new Service Connection of Bade Digaria w/s Scheme, TW No-II, Block- Haripal, District- Hooghly under ED ,PHE DTE | 99 | 17/07/2023 | 0 | WBSEDCL | 2.3 | 0 | 0 | 0
3966 | HOOGHLY | Electrical | BADE DIGARIA PIPED WATER SUPPLY SCHEME , SM/13336 | New | Quotation for New Service Connection of Bade Digaria W/S scheme,TW No-I, Block-Haripal, District- Hooghly under ED ,PHE Dte | 98 | 17/07/2023 | 0 | WBSEDCL | 3.05 | 0 | 0 | 0
3967 | HOOGHLY | Electrical | BADE DIGARIA PIPED WATER SUPPLY SCHEME , SM/13336 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bade Digaria water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | 764/ED | 09/02/2023 | 90 | M/S A.K BANERJEE | 21.37 | 21.33 | 100 | 40
3968 | HOOGHLY | Hooghly Division | BADE DIGARIA PIPED WATER SUPPLY SCHEME , SM/13336 | New | Horizontal Auger boring with water jet system Including Culvert, Approach Road at BADE DIGHARIA Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | 3006/HUG | 05/10/2023 | 60 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 11.3 | 11.18 | 100 | 100
3969 | HOOGHLY | Hooghly Division | BADE DIGARIA PIPED WATER SUPPLY SCHEME , SM/13336 | New | Route Survey, Design Drawing & DPR preparation of Bade Digharia PWSS under Chandannagar Sub-Division P.H.E. Dte. | 521/Chan | 12/10/2023 | 15 | APEX ENGINEERING | 4.19 | 4.19 | 100 | 100
3970 | HOOGHLY | Hooghly Division | BADE DIGARIA PIPED WATER SUPPLY SCHEME , SM/13336 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Bade Digaria PWSS, Bhagabatipur PWSS, Sirazpur PWSS, Harat PWSS, panrra PWSS, Malia PWSS) | 306/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 100
3971 | HOOGHLY | Hooghly Division | BADE DIGARIA PIPED WATER SUPPLY SCHEME , SM/13336 | New | BADE DIGARIA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch rooms & boundary walls at different TW site under HARIPAL Block, District- Hooghly.[NEW SCHEME] | 1062/HUG | 12/04/2023 | 811 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 423.74 | 268.74 | 63.42 | 25
3972 | HOOGHLY | Hooghly Division | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at MALIA PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. [2nd Call of WBPHE/EE/45/HUG/2022-23, Sl No-17] | 1202/HUG | 26/04/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 12.43 | 11.93 | 96.02 | 0
3973 | HOOGHLY | Electrical | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Supply & Delivery of S/P/M for Malia W/S. Sch. PH-III, Hooghly | 863/HMSD | 13/05/2021 | 90 | DEY ENTERPRISE | 0.51 | 0.51 | 100 | 0
3974 | HOOGHLY | Electrical | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Supply, Delivery & Installation of automatic chlorinator for Malia W/S. Sch. PH-III | 862/HMSD | 13/05/2021 | 90 | DEY ENTERPRISE | 0.71 | 0.71 | 100 | 0
3975 | HOOGHLY | Electrical | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Internal Electrification & allied works at Malia W/S. Sch. PH-III Hooghly | 861/HMSD | 13/05/2021 | 90 | DEY ENTERPRISE | 0.59 | 0.59 | 100 | 0
3976 | HOOGHLY | Electrical | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Supply, Installation of MCC panel & allied works at Malia W/S. Sch. PH-III Hooghly | 503/HMSD | 12/03/2021 | 90 | DEY ENTERPRISE | 2.7 | 2.7 | 100 | 0
3977 | HOOGHLY | Electrical | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Supply, Delivery & Installation of actuor operated butterfly valve for Malia W/S. Sch. PH-III | 865/HMSD | 13/05/2021 | 90 | DEY ENTERPRISE | 1 | 1 | 100 | 0
3978 | HOOGHLY | Electrical | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Supply, Delivery & Installation of voltage correcting device & other allied works for Malia W/S. Sch. PH-III | 322/HMSD | 15/02/2021 | 90 | DEY ENTERPRISE | 1.7 | 1.7 | 100 | 0
3979 | HOOGHLY | Electrical | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Supply & Delivery of electro-mechanical equipments & Installation of S/P/M & other allied works for Malia W/S. Sch. PH-III, Hooghly | 864/HMSD | 13/05/2021 | 90 | DEY ENTERPRISE | 0.72 | 0.72 | 100 | 0
3980 | HOOGHLY | Hooghly Division | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of MALIA Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. within HARIPAL Block. | 1473/HUG | 19/05/2023 | 30 | SUDIPTA SINHA | 11.92 | 10.71 | 100 | 98
3981 | HOOGHLY | Electrical | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Supply ,delivery & installation of Voltage correcting device and other allied works for Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. |  | 28/02/2023 | 0 | DEY ENTERPRISE | 1.7 | 0 | 0 | 0
3982 | HOOGHLY | Electrical | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Supply & delivery of submersible pumping machinery for Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. |  | 28/02/2023 | 0 | DEY ENTERPRISE | 0.51 | 0 | 0 | 0
3983 | HOOGHLY | Electrical | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Supply ,delivery & installation of Actuator operated butterfly valve for for Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. |  | 28/02/2023 | 0 | DEY ENTERPRISE | 1 | 0 | 0 | 0
3984 | HOOGHLY | Electrical | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Internal electrification and works at Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. |  | 28/02/2023 | 0 | DEY ENTERPRISE | 0.59 | 0 | 0 | 0
3985 | HOOGHLY | Electrical | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Supply & Delivery of S/P/M for Malia W/S. Sch. PH-III |  | 28/02/2023 | 0 | DEY ENTERPRISE | 0.51 | 0 | 0 | 0
3986 | HOOGHLY | Electrical | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Supply & installation of MCC Panel & allied works at Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. |  | 28/02/2023 | 0 | DEY ENTERPRISE | 2.7 | 0 | 0 | 0
3987 | HOOGHLY | Electrical | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Supply & installation of Automatic Chlorinator at Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. |  | 28/02/2023 | 0 | DEY ENTERPRISE | 0.71 | 0 | 0 | 0
3988 | HOOGHLY | Electrical | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Supply & delivery of electro-mechanical equipments and installation of submersible pumping machinery & other allied works for Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. |  | 28/02/2023 | 0 | DEY ENTERPRISE | 0.72 | 0 | 0 | 0
3989 | HOOGHLY | Electrical | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Quotation of New Service Connection of Malia W/S Scheme(Aug) T.W No-4 District-Hooghly under Electrical Division PHE Dte | 114 | 19/07/2023 | 0 | WBSEDCL | 2.28 | 0 | 0 | 0
3990 | HOOGHLY | Electrical | Source Augmentation of Malia PWSS , SM/15796 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Malia water supply scheme, T.W. No. I, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | 1618/ED | 11/04/2023 | 90 | A.S. ENTERPRISE | 10.71 | 10.69 | 100 | 50
3991 | HOOGHLY | Hooghly Division | Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme Under Goghat-I Block , SM/15810 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at SHYAMBALLAVPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | 654/HUG | 09/03/2023 | 30 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.32 | 9.65 | 85.23 | 0
3992 | HOOGHLY | Hooghly Division | Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme Under Goghat-I Block , SM/15810 | Augmentation | Construction of Boundary wall, land development, Internal Pathway at Head Work site of Shyamballavpur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 208/HUG | 04/02/2020 | 30 | MOHANLAL CHATTERJEE | 15.28 | 0 | 0 | 0
3993 | HOOGHLY | Electrical | Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme Under Goghat-I Block , SM/15810 | Augmentation | Quotation of New Service Connection for Shyamballavpur w/s Scheme,TW No-3,Dist-Hooghly under ED,PHE Dte | 122 | 20/07/2023 | 0 | WBSEDCL | 4.38 | 0 | 0 | 0
3994 | HOOGHLY | Hooghly Division | Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme Under Goghat-I Block , SM/15810 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-I Block. | 1311/HUG | 10/05/2023 | 510 | MUNSHI TAJUDDIN | 11.82 | 10.42 | 88.13 | 90
3995 | HOOGHLY | Electrical | Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme Under Goghat-I Block , SM/15810 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Shyamballavpur water supply scheme, T.W. No. I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | 1624/ED | 11/04/2023 | 90 | S.G.-ENTERPRISE | 10.73 | 10.64 | 100 | 40
3996 | HOOGHLY | Hooghly Division | Mahishtikri (Zone-I) Piped Water Supply Scheme, Block- Haripal, District-Hooghly , SM/16979 | New | Material Requisition To Resource Division | 1383/25/Hug | 15/05/2023 | 0 | Resource Division | 5.09 | 0 | 0 | 0
3997 | HOOGHLY | Hooghly Division | Mahishtikri (Zone-I) Piped Water Supply Scheme, Block- Haripal, District-Hooghly , SM/16979 | New | Material Requisition To Resource Division | 1235/12/Hug | 28/04/2023 | 0 | Resource Division | 58.83 | 0 | 0 | 0
3998 | HOOGHLY | Electrical | Mahishtikri (Zone-I) Piped Water Supply Scheme, Block- Haripal, District-Hooghly , SM/16979 | New | Quotation Bill for New Service Connection at Mahishtikri W/S. Sch. TW-I, Z-I | 407 | 09/11/2023 | 0 | WBSEDCL | 3.04 | 0 | 0 | 0
3999 | HOOGHLY | Electrical | Mahishtikri (Zone-I) Piped Water Supply Scheme, Block- Haripal, District-Hooghly , SM/16979 | New | Quotation Bill for New Service Connection at Mahishtikari W/S. Sch. TW-II, Z-I | 406 | 09/11/2023 | 0 | WBSEDCL | 3.91 | 0 | 0 | 0
4000 | HOOGHLY | Electrical | Mahishtikri (Zone-I) Piped Water Supply Scheme, Block- Haripal, District-Hooghly , SM/16979 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mahishtikri (Zone-I) water supply scheme, T.W. No. I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | 1728/ED | 19/04/2023 | 866 | MENAKA ENTERPRISE | 20.26 | 19.47 | 96.64 | 30
4001 | HOOGHLY | Hooghly Division | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly , SM/16138 | New | Material Requisition To Resource Division | 1383/44/Hug | 15/05/2023 | 0 | Resource Division | 3.76 | 0 | 0 | 0
4002 | HOOGHLY | Hooghly Division | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly , SM/16138 | New | Material Requisition To Resource Division | 3058/18/Hug | 11/10/2023 | 0 | Resource Division | 3.76 | 0 | 0 | 0
4003 | HOOGHLY | Electrical | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly , SM/16138 | New | Quotation of New Service Connection for Mahistikri w/s Scheme,Zone-2,TW No-2 Block-Haripal,Dist-Hooghly under ED,PHE Dte | 263 | 07/09/2023 | 0 | WBSEDCL | 3.24 | 0 | 0 | 0
4004 | HOOGHLY | Electrical | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly , SM/16138 | New | Quotation of New Service Connection Charge for Mahishtikri w/s Scheme,Zone-2,TW No-I Block-Haripal Dist-Hooghly under ED,PHE Dte | 264 | 07/09/2023 | 0 | WBSEDCL | 9.89 | 0 | 0 | 0
4005 | HOOGHLY | Hooghly Division | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly , SM/16138 | New | Horizontal Auger boring with water jet system Including Approach road with culvert at MAHISHTIKRI (ZONE-I & ZONE-II) under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. | 2285/HUG | 14/06/2024 | 30 | MAA TARA CONSTRUCTION | 4.82 | 0 | 0 | 100
4006 | HOOGHLY | Electrical | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly , SM/16138 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mahishtikri (Zone-II) water supply scheme, T.W. No. I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | 1701/ED | 18/04/2023 | 90 | DEBJYOTI BASU | 20.5 | 0 | 0 | 60
4007 | HOOGHLY | Hooghly Division | Mahishtikri (Zone-II) Piped Water Supply Scheme, Block- Haripal, District-Hooghly , SM/16138 | New | Making of 2 nos 1.8m X 1.45m X 2.1m KIOSK at Maheshtikri Zone 2 PWSS under Chandannagar Sub-Division Phe Dte. | 278/Chan | 15/03/2024 | 15 | SUDIPTA SINHA | 0.88 | 0.84 | 100 | 100
4008 | HOOGHLY | Hooghly Division | Gopalbati Piped Water Supply Scheme. , SM/16756 | New | Material Requisition To Resource Division | 1385/34/Hug | 15/05/2023 | 0 | Resource Division | 6.52 | 0 | 0 | 0
4009 | HOOGHLY | Hooghly Division | Gopalbati Piped Water Supply Scheme. , SM/16756 | New | Material Requisition To Resource Division | 3057/39/Hug | 11/10/2023 | 0 | Resource Division | 6.52 | 0 | 0 | 0
4010 | HOOGHLY | Hooghly Division | Gopalbati Piped Water Supply Scheme. , SM/16756 | New | Material Requisition To Resource Division | 1234/21/Hug | 28/04/2023 | 0 | Resource Division | 19.42 | 0 | 0 | 0
4011 | HOOGHLY | Electrical | Gopalbati Piped Water Supply Scheme. , SM/16756 | New | Quotation Bill for New Service Connection at Gopalbati W/S. Sch. | 487 | 06/12/2023 | 0 | WBSEDCL | 3.95 | 0 | 0 | 0
4012 | HOOGHLY | Electrical | Gopalbati Piped Water Supply Scheme. , SM/16756 | New | Quotation of New Service Connection for Gopalbati w/s Scheme,PH No-II,Block-Goghat-I,Dist-Hooghly under Electrical Division,PHE Dte.(SM/16756) Application No-5004475080 Reference Id-503799042 | 618 | 05/12/2024 | 0 | WBSEDCL | 4.72 | 0 | 0 | 0
4013 | HOOGHLY | Electrical | Gopalbati Piped Water Supply Scheme. , SM/16756 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gopalbati water supply scheme TW No I and II Block Goghat I District Hooghly under ED PHED. | 1800/ED | 24/04/2023 | 708 | KAMAKHYA ENTERPRISE | 20.26 | 0 | 0 | 30
4014 | HOOGHLY | Hooghly Division | Gopalbati Piped Water Supply Scheme. , SM/16756 | New | GOPALBATI Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-I Block of Arambag SUb-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | 1491/HUG | 22/05/2023 | 955 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 339.91 | 74.04 | 21.78 | 30
4015 | HOOGHLY | Hooghly Division | Gopalbati Piped Water Supply Scheme. , SM/16756 | New | Additional works for Laying Distribution main by HDD process at Gopalbati and Gobindanagar Zone II W/S Schme under Arambagh Sub Division of Hooghly Division, P.H.E. Dte. | 3687/HUG | 14/11/2024 | 331 | MS PRADIP KUMAR PAL | 14.33 | 0 | 0 | 0
4016 | HOOGHLY | Hooghly Division | Gopalbati Piped Water Supply Scheme. , SM/16756 | New | Laying of Additional Pipeline for GOPALBATI Piped Water Supply Scheme under ARAMBAGH SUB DIVISION Block-Arambagh. | 3431/HUG | 03/10/2024 | 182 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 23.25 | 0 | 0 | 15
4017 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18934 | Augmentation | Construction of 5 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at SRIPUR BALAGARH (1No.), NATUNCHAR KRISHNABATI (2Nos.), ITAGARH (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3234/HUG | 06/11/2023 | 60 | RAJDEEP CONSTRUCTION | 59 | 0 | 0 | 0
4018 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18934 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at SRIPUR BALAGARH (1No.), NATUNCHAR KRISHNABATI (2Nos.), ITAGARH (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3357/HUG | 21/11/2023 | 90 | B.K ENTERPRISE | 88.58 | 28.58 | 80.66 | 60
4019 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18934 | Augmentation | Quotation for new service connection for source Augmentation of ITAGARH Water Supply Scheme, PH NO- III in the district Hooghly under Electrical Division,PHEDte. ( SM/18934), Reference Id- 503814971 Application no- 5004498167 | 631 | 18/12/2024 | 0 | WBSEDCL | 6.54 | 0 | 0 | 0
4020 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18934 | Augmentation | Quotation for new service connection for source Augmentation of ITAGARH Water Supply Scheme, TW NO- IV in the district Hooghly under Electrical Division, PHE Dte. ( SM/18934), Reference Id- 503795724 Application no- 5004470487 | BP-24-25-594 | 21/11/2024 | 0 | WBSEDCL | 7.02 | 0 | 0 | 0
4021 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18934 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME Block- Balagarh, District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4485/ED | 23/11/2023 | 770 | BARISAL TRADING CO. | 21.49 | 0 | 0 | 25
4022 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18934 | Augmentation | Repairing & Renovation of boundary wall and Land Development at H/W Site of Itagarh Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 289/CH | 20/02/2025 | 10 | TAPAS ADHYA | 4.29 | 0 | 0 | 0
4023 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18934 | Augmentation | Repairing & Renovation of Switch Room and Store Room at H/W Site of Itagarh Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 290/CH | 20/02/2025 | 10 | TAPAS ADHYA | 3.17 | 0 | 0 | 0
4024 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | FHTC |  | 16/11/2021 | 0 | MINTU CHAKRABORTY | 28.28 | 0 | 0 | 0
4025 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | Providing 200 nos Functional Household Tap Connection (FHTC) within the command area of Goswami Malipara Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 2208/Hug | 14/12/2021 | 20 | M/S KAMALA ENTERPRISE | 13.84 | 13.37 | 96.63 | 100
4026 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | Providing 1963 nos F.H.T.C. in Hadilpur, Bali Kukhari, Mirkhila, Chaupala & Goswami Malipara Village of Goswami Malipara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | 364/Hug | 15/02/2021 | 30 | MINTU CHAKRABORTY | 92.96 | 5.85 | 12.59 | 100
4027 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | Construction of Boundary Wall, Pathway & Repairing of Switch room at Head Works site & 2nd T/W Site of PAUNAN W/S Scheme under Chinsurah Sub-Division under Hooghly Division P.H.E. Dte. | 1922/Hug | 27/10/2021 | 40 | M/S S.G. CONSTRUCTION | 26.25 | 12.44 | 57.97 | 100
4028 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | Providing 12 Nos. House Connection Within Goswami Malipara & It¿s Adjoining mouzas W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | 400/CH | 06/05/2022 | 15 | MINTU CHAKRABORTY | 4.74 | 4.73 | 100 | 100
4029 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of Goswami Malipara PWSS, Block POLBA DADPUR under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | 2841/HUG | 16/12/2022 | 30 | BOSE ENTERPRISE (RATUL BOSE) | 29.55 | 29.52 | 100 | 40
4030 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | Repairing of concrete road due to laying of pipe line at Choska Para of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | 756/CH | 14/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.91 | 0.91 | 100 | 97
4031 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | Repairing of concrete road due laying of pipe line at Purba Para of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | 770/CH | 18/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.89 | 0.85 | 100 | 97
4032 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | Repairing of concrete road due laying of pipe line at Doltala of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | 760/CH | 14/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.9 | 0.9 | 100 | 97
4033 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | Repairing of concrete road due laying of pipe line at Doltala of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | 762/CH | 16/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.8 | 1.52 | 100 | 97
4034 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | Repairing of concrete road due to laying of pipe line at Kolor Par of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | 771/CH | 18/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.91 | 0.9 | 100 | 97
4035 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | Repairing of concrete road due laying of pipe line at Kalyan danga Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | 772/CH | 18/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.87 | 0.86 | 100 | 97
4036 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | Repairing of concrete road due laying of pipe line at Doltala of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | 773/CH | 18/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.84 | 1.67 | 100 | 97
4037 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | Repairing of concrete road due to laying of pipe line at Kallyandanga of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | 763/CH | 16/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.91 | 0.9 | 100 | 97
4038 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | Repairing of concrete road due laying of pipe line at Bhagarpar of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | 764/CH | 16/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.89 | 0.89 | 100 | 97
4039 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | Repairing of concrete road due to laying of pipe line at Dengor para of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | 757/CH | 14/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.87 | 0.85 | 100 | 97
4040 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | Repairing of concrete road due laying of pipe line at Gosai para of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | 759/CH | 14/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.87 | 0.86 | 100 | 97
4041 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | Repairing of concrete road due laying of pipe line at Purba Para of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | 777/CH | 21/08/2023 | 15 | M/S BIMAL DAS AND CO. | 0.52 | 0.49 | 100 | 97
4042 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. , SM/08741 | Retrofitting | Providing 1350 nos F.H.T.C. in Talchinan- Sanihati, Popai & Dhanijpur Village of Goswami Malipara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | 957/Hug | 10/05/2021 | 40 | MINTU CHAKRABORTY | 61.16 | 52.83 | 100 | 100
4043 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAMARPARA WATER SUPPLY SCHEME. , SM/07539 | Retrofitting | FHTC |  | 30/09/2021 | 0 | SWASTIK ENTERPRISE | 13 | 0 | 0 | 0
4044 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAMARPARA WATER SUPPLY SCHEME. , SM/07539 | Retrofitting | Providing 85 nos Functional Household Tap Connection (FHTC) within the command area of Kamarpara Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | 20/Hug | 04/01/2022 | 20 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 6.07 | 5.92 | 97.66 | 100
4045 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAMARPARA WATER SUPPLY SCHEME. , SM/07539 | Retrofitting | Providing 513 nos F.H.T.C. in Kamarpara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | 958/Hug | 10/05/2021 | 30 | SWASTIK ENTERPRISE | 26.53 | 26.5 | 100 | 100
4046 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAMARPARA WATER SUPPLY SCHEME. , SM/07539 | Retrofitting | Material Requisition To Resource Division | 2097/2/Hug | 26/11/2021 | 0 | Resource Division | 0.83 | 0 | 0 | 0
4047 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAMARPARA WATER SUPPLY SCHEME. , SM/07539 | Retrofitting | Material Requisition To Resource Division | 1968/HUG | 03/11/2021 | 0 | Resource Division | 9.31 | 0 | 0 | 0
4048 | HOOGHLY | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAMARPARA WATER SUPPLY SCHEME. , SM/07539 | Retrofitting | Material Requisition To Resource Division | 428/4-5/Hug | 07/03/2022 | 0 | Resource Division | 10.98 | 0 | 0 | 0
4049 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur,Budul Badul Hati,Bhandarhati,Ilampur, Gabtala,Dakshin Dilakash Mouza of Borhol Zone-II Water Supply Scheme , SM/06987 | Retrofitting | Providing 375 nos Functional Household Tap Connection (FHTC) within the command area of BORHAL(ZONE-I) Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte | 122/Hug | 19/01/2022 | 25 | K. JAGADHATRY & CO. | 15.98 | 15.98 | 99.98 | 100
4050 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur,Budul Badul Hati,Bhandarhati,Ilampur, Gabtala,Dakshin Dilakash Mouza of Borhol Zone-II Water Supply Scheme , SM/06987 | Retrofitting | Providing 250 nos F.H.T.C. in Kotalpur village of Patna Bhairabpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | 262/Hug | 03/02/2021 | 20 | K JAGADHATRY & CO | 13.62 | 8.38 | 100 | 0
4051 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur,Budul Badul Hati,Bhandarhati,Ilampur, Gabtala,Dakshin Dilakash Mouza of Borhol Zone-II Water Supply Scheme , SM/06987 | Retrofitting | Providing 28 nos F.H.T.C. including laying Pipe line in the left out portion of Borhal (Zone-I)and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | 331/Hug | 11/02/2021 | 30 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 31.68 | 16.31 | 100 | 100
4052 | HOOGHLY | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur,Budul Badul Hati,Bhandarhati,Ilampur, Gabtala,Dakshin Dilakash Mouza of Borhol Zone-II Water Supply Scheme , SM/06987 | Retrofitting | Providing 2200 nos F.H.T.C. in Akuti, Radhaballabhpur, Baidyagari, Paschim Durgapur, Budul Badul Hati, Bhandarhati, Ilampur, Gabtala, Dakshin Dilakash, Mandaran Dilakash, Khurigachhi, Kulakash, Kandar Panagar village of Borhal (Zone- II)and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | 1686/Hug. | 17/12/2020 | 40 | S & P ENTERPRISE | 103.59 | 17.89 | 100 | 98
4053 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11465 | Augmentation | Preparation of DPR for Augmentation of Purba Tajpur Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | 482/SER | 14/07/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.85 | 2.85 | 100 | 0
4054 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11465 | Augmentation | Augmentation of PURBATAJPUR (ZONE-I) Water Supply Scheme with LDS, Functional Household Tap Connection & Repairing of existing Switch Room at Chanditala II Block under Serampore Sub-Division of Hooghly Division, PHE Dte. | 1609/Hug | 05/08/2022 | 40 | MS CHANDIMATA CONSTRUCTION | 76.17 | 74.19 | 100 | 98
4055 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11465 | Augmentation | Sinking of 1 no 300 X 200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at proposed Tube Well Site of PURBATAJPUR ZONE-II W/S Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. | 163/HUG | 16/01/2023 | 30 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 12.86 | 12.86 | 100 | 100
4056 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11465 | Augmentation | Material Requisition To Resource Division | 1107/HUG | 17/04/2023 | 0 | Resource Division | 6.16 | 0 | 0 | 0
4057 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11465 | Augmentation | Material Requisition To Resource Division | 1384/9/Hug | 15/05/2023 | 0 | Resource Division | 10.9 | 0 | 0 | 0
4058 | HOOGHLY | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11465 | Augmentation | Purba Tajpur w/s scheme, P H No 1 | 442 | 24/11/2023 | 0 | WBSEDCL | 5.52 | 0 | 0 | 0
4059 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11465 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, SERAMPORE SUB-DIVISION, PHE DTE. |  | 06/11/2023 | 0 | P. B. ENTERPRISE(PINTU BHADURI) | 1.02 | 0 | 0 | 0
4060 | HOOGHLY | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11465 | Augmentation | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. | 2502/HMSD | 26/09/2023 | 152 | S.P. CONSTRUCTION | 0.72 | 1.16 | 152.1 | 15
4061 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11465 | Augmentation | Sinking of tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room , boundary wall & Repairing of Existing OHR, Switch Rooms, Boundary walls at 2nd TW sites for PURBA TAJPUR (ZONE-I) Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division, P.H.E. Dte. | 2339/HUG | 19/06/2024 | 60 | TAPAS ADHYA | 28.13 | 0 | 0 | 0
4062 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11465 | Augmentation | Augmentation of PURBATAJPUR (ZONE-II) Water Supply Scheme with LDS, Functional Household Tap Connection & Repairing of existing Switch Room at Chanditala II Block under Serampore Sub-Division of Hooghly Division, PHE Dte. | 2526/HUG | 23/11/2022 | 40 | BIMAL KUMAR HALDER | 76.75 | 67.85 | 100 | 98
4063 | HOOGHLY | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11465 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Purba Tajpur water supply scheme TW No I Block Chanditala II District Hooghly under ED PHED. | 854/ED | 14/02/2023 | 90 | A.K. SIKDAR | 10.72 | 10.67 | 100 | 99
4064 | HOOGHLY | Hooghly Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11465 | Augmentation | Left out pipeline to restore the water supply and development of head work site at Purbatajpur Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | 824/HUG | 11/03/2024 | 30 | DAS CONSTRUCTION | 22.87 | 22.33 | 100 | 95
4065 | HOOGHLY | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11465 | Augmentation | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. From 01.02.2024 to 29.02.2024 WB19J-7094 SM Code- 11465 | 229 | 18/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.26 | 0 | 0 | 0
4066 | HOOGHLY | Electrical | Augmentation of Ground Water Based Piped Water Supply Scheme for Purba Tajpur under Serampore Sub-Division of Hooghly Division , P.H.E. Dte. , SM/11465 | Augmentation | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. From 01.01.2024 to 31.01.2024 WB19J-7094 SM Code- 11465 | 228 | 18/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
4067 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | Preparation of DPR for Augmentation of RAJHATO Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II]. | 613/Arg | 31/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.79 | 3.78 | 99.61 | 100
4068 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-III & ABOVE) (NON AC) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH FOR THE OFFICE OF THE CALCUTTA MECHANICAL SUB DIVISION-I, PHE DTE. | 67/CMSD-I (D) | 22/03/2022 | 7 | SUJATA BHOWMICK | 0.87 | 0 | 0 | 67
4069 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | SUPPLY AND DELIVERY OF TENT FOR DRILLING WORK AT RAJHATO PWSS UNDER CDD, PHE DTE. | 255/CMSD-I | 23/06/2022 | 15 | M/S S.K.GHOSH & CO. | 4.56 | 0 | 0 | 100
4070 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | CONTINGENCY BILL | BP-2022-23-40 | 15/07/2022 | 0 | SUJATA BHOWMICK | 0.14 | 0 | 0 | 0
4071 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | CONTINGENCY BILL | BP-2022-23-41 | 15/07/2022 | 0 | ASHUTOSH PAL | 0.29 | 0 | 0 | 0
4072 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE DRILLER-IN-CHARGE, CMSD-II (D), CDD, PHE DTE. | 55/CMSD-II (D) | 31/01/2022 | 7 | ASHUTOSH PAL | 0.86 | 0 | 0 | 64
4073 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 240 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR AUGMENTATION OF MIDNAPORE MEDICAL COLLEGE & HOSPITAL W/S SCHEME (TW0II) UNDER PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | 1077/CDD | 28/10/2022 | 30 | PADMA ENGINEERING & CO. | 16.51 | 4.28 | 77.81 | 0
4074 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | MISCELLANEOUS REPAIRING OF MUD PUMP ATTACHED WITH RIG MACHINE NO. KORES/DR/1000 UNDER CMSD-II (D), CDD, PHE DTE. | 634/CMSD-II (D) | 23/12/2021 | 15 | M/S B.P.TRADING CORPORATION | 3.28 | 3.22 | 100 | 100
4075 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto150 Mtr at RAJHATO PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | 2506/HUG | 22/11/2022 | 45 | OSMAN SEKH | 22.53 | 22.24 | 100 | 100
4076 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | Supply & Delivery of Tent for Drilling work at Rajhato PWSS, Dist Hooghly and other PWSS under CDD, PHE Dte. | 336/CMSD-I(D) | 18/07/2022 | 15 | M/S S.K.GHOSH & CO. | 4.37 | 4.37 | 100 | 100
4077 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | Supply of UPVC Pipe for TW-III of RAJHATO Water Supply Scheme under Arambagh Sub-Division, of Hooghly Division P.H.E. Dte. [Block-Khanakul-II] | 209/Arg | 31/03/2023 | 15 | OSMAN SEKH | 0.69 | 0.69 | 100 | 100
4078 | HOOGHLY | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x 150mtrs Depth ) by utilising Departmental Machineries for Rajhato W/S Scheme ,Arambag Block under hooghly District ,CDD,PHE Dte. | 61/CDD | 06/04/2023 | 30 | UNIVERSAL ENTERPRISES | 11.38 | 10.14 | 100 | 100
4079 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | Material Requisition To Resource Division | 424/2/Hug | 07/03/2022 | 0 | Resource Division | 36.05 | 0 | 0 | 0
4080 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | Material Requisition To Resource Division | 1590/Hug | 03/08/2022 | 0 | Resource Division | 24.64 | 0 | 0 | 0
4081 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | Material Requisition To Resource Division | 1773/9/Hug | 29/08/2022 | 0 | Resource Division | 0.69 | 0 | 0 | 0
4082 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | Material Requisition To Resource Division | 1385/14/Hug | 15/05/2023 | 0 | Resource Division | 0.2 | 0 | 0 | 0
4083 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | Material Requisition To Resource Division | 79/23/Hug | 06/01/2023 | 0 | Resource Division | 26.55 | 0 | 0 | 0
4084 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | Quotation for New Service Connection of Rajhato(Aug) w/s Scheme, PH No-2 District-Hooghly Under Electrical division PHE Dte | 84 | 10/07/2023 | 0 | WBSEDCL | 2.57 | 0 | 0 | 0
4085 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | Quotation bill for New Service connection of Rajhato w/s scheme,TW-I | 20 | 04/05/2023 | 0 | WBSEDCL | 2.22 | 0 | 0 | 0
4086 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | Sinking of 3 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Gobindapur, Rajhato & Kamarpukur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 2038/HUG | 13/07/2023 | 30 | SPG ENTERPRISES | 48.51 | 13.73 | 84.94 | 70
4087 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall of RAJHATO PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 4083/HUG | 19/12/2024 | 90 | M/S PRADYUT KUMAR HAZRA (PARTNERSHIP) | 21.43 | 0 | 0 | 0
4088 | HOOGHLY | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Rajhato water supply scheme, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | 939/ED | 22/02/2023 | 90 | MAA KALI ENTERPRISE | 21.48 | 21.31 | 100 | 60
4089 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply & Sanitation arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Augmentation of RAJHATO Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Khanakul-II Block. | 1458/HUG | 18/05/2023 | 30 | BENGAL TRADERS | 10.29 | 10.28 | 100 | 100
4090 | HOOGHLY | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. , SM/09693 | Augmentation | Augmentation of RAJHATO Water Supply Scheme with LDS, Switch room, Boundary wall,Rising Main,FHTC Work, of existing Switch Rooms& Boundary Wall at Khanakul-II Block. | 826//Hug | 20/04/2022 | 1261 | M/S PRADYUT KUMAR HAZRA | 404.28 | 365.14 | 90.32 | 80
4091 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Route Survey, Design Drawing & DPR Preparation of Champadanga PWSS under Chandannagar Sub-Division, P.H.E. Dte. | 261/CHAN | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.96 | 4.96 | 99.88 | 0
4092 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Laying of HDPE distribution pipe due to widening & construction of 4-lane of champadanga-Chanditala road under WBHDCL for providing water supply at Champadanga water supply scheme under Chandannagar Sub-Division P.H.E.Dte. | 208/HUG | 13/04/2022 | 15 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 4.67 | 4.65 | 99.63 | 0
4093 | HOOGHLY | Central Drilling | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AUG. CHAMPADANGA PWSS, TARAKESWAR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 382/CMSD-II | 01/08/2022 | 15 | C.M. ENTERPRISE | 4.97 | 4.31 | 100 | 0
4094 | HOOGHLY | Central Drilling | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES AT SITE AND OTHER WORKS FOR CONSUMBLES OF TUBEWELL AT AUG. OF CHAMPADANGA PWSS, TARAKESSWAR BLOCK, HOOGHLY BLOCK UNDER CDD, PHE DTE. | 383/CMSD-II | 01/08/2022 | 15 | C.M. ENTERPRISE | 4.68 | 2.64 | 100 | 0
4095 | HOOGHLY | Central Drilling | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT AUG. OF CHAMPADANGA PWSS, TARAKESWAR BLOCK, HOOGHLY DISTRICT CDD, PHE DTE. | 381/CMSD-II | 01/08/2022 | 15 | C.M. ENTERPRISE | 3.34 | 3.16 | 100 | 0
4096 | HOOGHLY | Central Drilling | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | SUPPLY & DELIVERY OF BATS AT SITE FOR MAKING APPROACH ROADS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT CHAMPADANGAPWSS, TARAKESWAR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | 464/CMSD-II | 27/09/2022 | 7 | C.M. ENTERPRISE | 0.26 | 0.25 | 100 | 0
4097 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Material Requisition To Resource Division | 2686/3/Hug | 01/12/2022 | 0 | Resource Division | 0.33 | 0 | 0 | 0
4098 | HOOGHLY | Electrical | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chapadanga water supply scheme, T.W. No.- IV & V, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | 946/ED | 22/02/2023 | 90 | STANDARD ELECTRICALS | 21.96 | 0 | 0 | 0
4099 | HOOGHLY | Central Drilling | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR CHAMPADANGA UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | 1677/CDD | 28/12/2022 | 30 | C.M. ENTERPRISE | 11.34 | 9.18 | 100 | 0
4100 | HOOGHLY | Central Drilling | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHAMPADANGA, HOOGHLY DISTRICT UNDER CMSD-I (D), CDD, PHE DTE. | 575/CMSD-I | 30/11/2022 | 7 | C.M. ENTERPRISE | 0.98 | 0.86 | 100 | 0
4101 | HOOGHLY | Central Drilling | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Hiring of Diesel Driven Motor Vab (BS-III & Above) (Non AC) hiving contract carriage permit along with driven for office of the Calcutta Mechanical Sub Division -I, PHE Dte. under CMSD-II (D), CDD, PHE Dte. | 40/CMSD-II(D) | 16/02/2023 | 150 | SUJATA BHOWMICK | 0.87 | 2.28 | 100 | 51
4102 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Baseline household survey work including collection of House Hold Details at Prescribed Format through Mobile App/Hard Copy for yearly data updation in JJM portal at TARAKESWAR Block under Chandannagar Sub-Division, P.H.E. Dte. | 218/chan | 13/04/2022 | 20 | M/S S.G. CONSTRUCTION | 4.97 | 4.97 | 50 | 0
4103 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Material Requisition To Resource Division | 423/6/Hug | 07/03/2022 | 0 | Resource Division | 25.98 | 0 | 0 | 0
4104 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Material Requisition To Resource Division | 1370/2/Hug | 06/07/2022 | 0 | Resource Division | 133.19 | 0 | 0 | 0
4105 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Material Requisition To Resource Division | 109/ 18/Hug | 10/01/2023 | 0 | Resource Division | 96.26 | 0 | 0 | 0
4106 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Material Requisition To Resource Division | 01/01/Hug | 02/01/2023 | 0 | Resource Division | 11.94 | 0 | 0 | 0
4107 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Material Requisition To Resource Division | 1383/28/Hug | 15/05/2023 | 0 | Resource Division | 5.78 | 0 | 0 | 0
4108 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | QUOTATION BILL ON ACCOUNT OF WBSEDCL FOR AUGMENTATION OF CHAMPDANGA W/S/S | BP-2022-23-413 | 20/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.71 | 0 | 0 | 0
4109 | HOOGHLY | Electrical | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Augmentation Of Champadanga Water Supply Scheme TW-4 | 250, 251 | 31/03/2023 | 0 | WBSEDCL | 6.95 | 0 | 0 | 0
4110 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Horizontal road crossing by trenchless method at Champadanga Pairadinghi kalitala Node(538-541), Champadanga Kalitala Node(256-260), Champadanga Mansatala Node(159-170),DVC Santhashitala(Hanuman Temple) Node(135-138),Muktarpur Electric substation Node(232-234) beside SH 15 & SH 12 under Chandannagar Sub-Division. | 3481/HUG | 29/11/2023 | 45 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 12.41 | 24.8 | 100 | 100
4111 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Laying of Rising main for Interconnection of Laying distribution system at Laskarpur in Champadanga Water Supply Scheme Under chandannagar Sub-Division under Hooghly Division,P.H.E Dte. (Part A). | 934/Chan | 30/11/2023 | 15 | AMBIAN INFRASTRUCTURE | 0.91 | 0.7 | 100 | 100
4112 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Laying of Rising main for Interconnection of Laying distribution system at Laskarpur in Champadanga Water Supply Scheme Under chandannagar Sub-Division under Hooghly Division,P.H.E Dte. (Part B). | 935/Chan | 30/11/2023 | 15 | AMBIAN INFRASTRUCTURE | 0.63 | 0.57 | 100 | 100
4113 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Champadanga PWSS, Naita PWSS, Purbaramnagar PWSS, Ramnaryanpur PWSS, Salepur-Duttapur zone-I PWSS, Salepur-Duttapur zone-II PWSS). | 302/Chan | 15/03/2024 | 7 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 100
4114 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Pipeline shifting at different location for irrigation canal crossing at Champadanga Water Supply Scheme in Tarakeswar Block of Hooghly District under Hooghly Division, PHE Dte. | 294/Chan | 15/03/2024 | 15 | MAHABIR CONSTRUCTION | 0.99 | 0 | 0 | 99
4115 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Pipeline shifting at different location for irrigation canal crossing at Champadanga Water Supply Scheme in Tarakeswar Block of Hooghly District under Hooghly Division, PHE Dte. | 295/Chan | 15/03/2024 | 15 | MAHABIR CONSTRUCTION | 0.95 | 0 | 0 | 95
4116 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Pipeline shifting at different location for irrigation canal crossing at Champadanga Water Supply Scheme in Tarakeswar Block of Hooghly District under Hooghly Division, PHE Dte. | 298/Chan | 15/03/2024 | 15 | MAHABIR CONSTRUCTION | 0.98 | 0 | 0 | 99
4117 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Augmentation of CHAMPADANGA Water Supply Scheme with Laying Distribution System within MOKTARPUR & LASKARPUR Mouza, Construction of Switch room & Boundary wall for Proposed Switch Room-IV, Repairing of existing Switch Room-III & Boundary Wall & FHTC Work within MOKTARPUR & LASKARPUR Mouza at Tarakeswar Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | 833/Hug | 20/04/2022 | 1076 | ALOK ENTERPRISE, A UNIT OF SAKET TREXIM PVT. LTD. | 348.19 | 277.19 | 79.61 | 100
4118 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Augmentation of CHAMPADANGA Water Supply Scheme with Construction of 750 cum capacity OHR with 20 mtr. staging height including Soil Investigation work , Laying Distribution System Within CHAMPADANGA & SACHAK Mouza, Construction of Switch rooms at Proposed Pump House-V, Boundary wall at Proposed 5th T.W Site, Rising Main, FHTC Work, Repairing of existing Switch Rooms & Boundary Wall of Existing T.W-1 & 2 at Tarakeswar Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. | 1151/HUG | 09/06/2022 | 1327 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 687.43 | 585.19 | 85.13 | 95
4119 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Left OutPortion of LDS AND FHTC Work of champadanga Water Supply Scheme under mouza champadanga and sachak Under chandannagar Sub-Division of Hooghly Division,P.H.E Dte. | 3522/HUG | 30/11/2023 | 747 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 96.7 | 25.04 | 25.9 | 95
4120 | HOOGHLY | Central Drilling | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Hiring of diesel driven Motor Cab (BS-III & Above) having contract carriage permit along with driver for the office of The Executive Engineer, , Central Drilling Division, P.H.E. Dte. | 188/S&WSD | 25/09/2024 | 182 | SUJIT DAS | 0.86 | 1.12 | 129.52 | 0
4121 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Necessary Maintenance Work for Improvement of water supply in distribution system at Laskarpur & Muktarpur mouza under Champadanda Water Supply Scheme under Chandannagar Sub - Division P.H.E. Dte. | 877/CHAN | 21/07/2025 | 20 | ASHA ENTERPRISE | 1.49 | 0 | 0 | 100
4122 | HOOGHLY | Hooghly Division | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Shifting of UVPC Pipe Line & Allied works for new culvert construction of irrigation at Laskarpur mouza under Champadanga Water Supply Scheme under Chandannagar Sub-Division, PHE Dte. | 1004/Chan | 30/07/2025 | 10 | SARKAR CONSTRUCTION (DEBJIT SARKAR) | 0.96 | 0 | 0 | 0
4123 | HOOGHLY | Electrical | Augmentation of Champadanga Water Supply Scheme , SM/10005 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chapadanga water supply scheme, T.W. No.- IV & V, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | 868/ED | 14/02/2023 | 745 | STANDARD ELECTRICALS | 21.96 | 21.95 | 100 | 95
4124 | HOOGHLY | Hooghly Division | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' , SM/19013 | New | Material Requisition To Resource Division | 3057/38/Hug | 11/10/2023 | 0 | Resource Division | 3.29 | 0 | 0 | 0
4125 | HOOGHLY | Electrical | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' , SM/19013 | New | Quotation of New Service Connection for Ghar Gohal w/s scheme, PH No-II Block-Arambag, Dist-Hooghly under Electrical Division, PHE Dte.(SM/19013) Application No-5004282784 Reference Id-503686105 | 286 | 09/07/2024 | 0 | WBSEDCL | 6.42 | 0 | 0 | 0
4126 | HOOGHLY | Electrical | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' , SM/19013 | New | Quotation of New Service Connection for Ghar Gohal w/s scheme, PH No-I Block-Arambag, Dist-Hooghly under Electrical Division, PHE Dte.(SM/19013) Application No-5004282705 Reference Id-503686110 | 285 | 09/07/2024 | 0 | WBSEDCL | 5.39 | 0 | 0 | 0
4127 | HOOGHLY | Hooghly Division | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' , SM/19013 | New | GHAR GOHAL Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-rooms & boundary walls at different TW site under ARAMBAGH SUB-DIVISION Block-ARAMBAGH, District:- Hooghly [NEW SCHEME] | 3183/HUG | 30/10/2023 | 720 | DAS TRADING | 194.07 | 109.72 | 56.53 | 30
4128 | HOOGHLY | Electrical | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' , SM/19013 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghar Gohal water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | 116/ED | 15/01/2024 | 531 | GLACIER ENGINEERING CO. | 21.1 | 0 | 0 | 30
4129 | HOOGHLY | Electrical | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' , SM/19013 | New | Hiring of Luxury Car / Ambassadar (BS-IV) for Officical use of the Assistant Chief Engineer (M/E), PHE Dte. | 2870/HMSD | 04/06/2024 | 182 | BHOLA DEY | 0.86 | 0 | 0 | 0
4130 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18973 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4496/ED | 23/11/2023 | 90 | PERPETUAL ENTERPRISE | 21.7 | 0 | 0 | 0
4131 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18973 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BHABANIPUR CHAR (2Nos.), JAYRAMBATI (2Nos.), DEBANANDAPUR (1 No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3389/HUG | 22/11/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 87.88 | 0 | 0 | 30
4132 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18973 | Augmentation | Replacement of damaged AC pipe line with HDPE pipeline and Shifting House Connection from existing main to new main at Khayramari Char of Bhawanipur Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 536/CH | 14/06/2024 | 7 | MAA BUNAMATA ENTERPRISE | 2.51 | 2.51 | 100 | 90
4133 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18973 | Augmentation | Repairing & Renovation of Boundary Wall and Land Development At Head Works Site of Bhabanipur Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 285/CH | 20/02/2025 | 10 | MAA BUNAMATA ENTERPRISE | 3.85 | 0 | 0 | 100
4134 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18973 | Augmentation | Repairing & Renovation of Boundary Wall, Switch Room and Land Development At PH-II Site of Bhabanipur Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 303/CH | 20/02/2025 | 10 | SWARNA ENTERPRISE | 2.15 | 0 | 0 | 0
4135 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME UNDER BALAGARH BLOCK , SM/18973 | Augmentation | Repairing & Renovation of Boundary Wall extensions, Switch Room & IP Room At Head Works Site of Bhabanipur Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | 295/CH | 20/02/2025 | 10 | MAA BUNAMATA ENTERPRISE | 4.49 | 0 | 0 | 100
4136 | HOOGHLY | Hooghly Division | Muragari Mini Piped Water Supply Scheme , SM/13564 | New | MINI PIPED WATER SUPPLY SCHEME | BP-2023-24-297 | 19/08/2023 | 0 | DISTRICT MAGISTRATE HOOGHLY | 28.23 | 0 | 0 | 0
4137 | HOOGHLY | Electrical | Muragari Mini Piped Water Supply Scheme , SM/13564 | New | Mini Piped Water Supply Scheme | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0 | 0
4138 | HOOGHLY | Electrical | Muragari Mini Piped Water Supply Scheme , SM/13564 | New | Mini piped Water Supply scheme |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0 | 0
4139 | HOOGHLY | Hooghly Division | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block , SM/18952 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at PAUNAN (2Nos.), PUINAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3244/HUG | 06/11/2023 | 60 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 59.57 | 0 | 0 | 45
4140 | HOOGHLY | Electrical | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block , SM/18952 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of PUINAN piped Water Supply Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4516/ED | 23/11/2023 | 90 | SUTRADHAR TRADERS | 21.47 | 6.16 | 28.7 | 30
4141 | HOOGHLY | Hooghly Division | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block , SM/18952 | Augmentation | Replacement of damaged pipe line with HDPE pipeline and Shifting House Connection from existing main to new main at Tin MandirTala of Puinan Piped Water Supply Scheme of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 550/CH | 14/06/2024 | 7 | MAA BUNAMATA ENTERPRISE | 4.97 | 4.97 | 100 | 80
4142 | HOOGHLY | Hooghly Division | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block , SM/18952 | Augmentation | Replacement of damaged pipe line with HDPE pipeline and Shifting House Connection from existing main to new main at Ser Gram of Puinan Piped Water Supply Scheme of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | 549/CH | 14/06/2024 | 7 | MAA BUNAMATA ENTERPRISE | 5 | 4.99 | 100 | 80
4143 | HOOGHLY | Electrical | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block , SM/18952 | Augmentation | Quotation for new servce connection at Puinan (S.Aug.) [SM/18952] , T/W No. - IV, Block - Polba-Dadpur, Dist. - Hooghly under Dadpur CCC, WBSEDCL, Ref, Id. - 503619159, Dt. - 13-05-2024, Application No. - 5004116723 | 122 | 17/05/2024 | 0 | WBSEDCL | 6.36 | 0 | 0 | 0
4144 | HOOGHLY | Electrical | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block , SM/18952 | Augmentation | Quotation for new servce connection at Puinan (S.Aug.) [SM/18952] , T/W No. - III, Block - Polba-Dadpur, Dist. - Hooghly under Dadpur CCC, WBSEDCL, Ref, Id. - 503619158, Dt. - 13-05-2024, Application No. - 5004116682 | 124 | 17/05/2024 | 0 | WBSEDCL | 3.22 | 0 | 0 | 0
4145 | HOOGHLY | Hooghly Division | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block , SM/18952 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PAUNAN (2Nos.), PUINAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3405/HUG | 23/11/2023 | 571 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 28.08 | 81.25 | 25
4146 | HOOGHLY | Electrical | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. , SM/18667 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kotalpur water supply scheme, Zone-I, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | 3416/ED | 10/08/2023 | 90 | P.K. ENGINEERING | 22.13 | 0 | 0 | 0
4147 | HOOGHLY | Hooghly Division | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. , SM/18667 | New | Material Requisition To Resource Division | 3060/2/Hug | 11/10/2023 | 0 | Resource Division | 31.37 | 0 | 0 | 0
4148 | HOOGHLY | Hooghly Division | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. , SM/18667 | New | Material Requisition To Resource Division | 3005/17/Hug | 05/10/2023 | 0 | Resource Division | 71.65 | 0 | 0 | 0
4149 | HOOGHLY | Electrical | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. , SM/18667 | New | Quotation Bill for New Service Connection at Kotalpur W/S. Sch.Z-II, PH-II | 519A | 11/12/2023 | 0 | WBSEDCL | 6.86 | 0 | 0 | 0
4150 | HOOGHLY | Electrical | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. , SM/18667 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kotalpur water supply scheme, Zone-II, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | 3415/ED | 10/08/2023 | 90 | A.S. ENTERPRISE | 20.34 | 14.41 | 70.84 | 60
4151 | HOOGHLY | Electrical | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. , SM/18667 | New | Quotation Bill for New Service Connection at Kotalpur W/S. Sch. PH-I | 624 | 08/01/2024 | 0 | WBSEDCL | 7.5 | 0 | 0 | 0
4152 | HOOGHLY | Electrical | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. , SM/18667 | New | Quotation Bill for New Service Connection at Kotalpur W/S. Sch.Z-I, PH-I | 596 | 29/12/2023 | 0 | WBSEDCL | 0.74 | 0 | 0 | 0
4153 | HOOGHLY | Electrical | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. , SM/18667 | New | Quotation Bill for New Service Connection at Kotalpur W/S. Sch. PH-II | 625 | 08/01/2024 | 0 | WBSEDCL | 5.57 | 0 | 0 | 0
4154 | HOOGHLY | Electrical | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. , SM/18667 | New | Quotation Bill for New Service Connection at Kotalpur W/S. Sch. | 597 | 29/12/2023 | 0 | WBSEDCL | 5.03 | 0 | 0 | 0
4155 | HOOGHLY | Hooghly Division | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. , SM/18667 | New | KOTALPUR (ZONE-I & ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR At ZONE-I & Construction of 300 cum capacity RCC OHR At ZONE-II with 20.0 mtr Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site of ZONE-I & ZONE-II under Serampore Sub-Division of Hooghly Division P.H.E Dte. Block-JANGIPARA, District:- Hooghly [NEW SCHEME] | 2321/HUG | 04/08/2023 | 1732 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 1457.97 | 364.27 | 24.98 | 45
4156 | HOOGHLY | Electrical | Source Augmentation of SAOTA Piped Water Supply Scheme Under Pursura Block , SM/18962 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of SAOTA Piped Water Supply Scheme Block- Pursura District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4523/ED | 23/11/2023 | 90 | TRIO CONCERN | 21.48 | 0 | 0 | 0
4157 | HOOGHLY | Hooghly Division | Source Augmentation of SAOTA Piped Water Supply Scheme Under Pursura Block , SM/18962 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PABA (1 NO.),BAIKUNTHAPUR (2Nos.),SAOTA (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3475/HUG | 29/11/2023 | 45 | CIVIL CRAFT | 88.67 | 14.3 | 40.31 | 60
4158 | HOOGHLY | Hooghly Division | Source Augmentation of SAOTA Piped Water Supply Scheme Under Pursura Block , SM/18962 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of BHANGAMORA, SAOTA, PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | 4081/HUG | 19/12/2024 | 90 | R.K. TRADERS | 20.96 | 0 | 0 | 0
4159 | HOOGHLY | Hooghly Division | Source Augmentation of SAOTA Piped Water Supply Scheme Under Pursura Block , SM/18962 | Augmentation | Construction of 3 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 3 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 3 Nos. T.W & Distribution at BAIKUNTHAPUR (1Nos.), SAOTA (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3352/HUG | 17/11/2023 | 778 | A.R. CONSTRUCTION | 35.75 | 0 | 0 | 20
4160 | HOOGHLY | Hooghly Division | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME , SM/18657 | New | Material Requisition To Resource Division | 3058/4/Hug | 11/10/2023 | 0 | Resource Division | 20.62 | 0 | 0 | 0
4161 | HOOGHLY | Electrical | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME , SM/18657 | New | Qoutation for new service connection at Balarambati W/S Sch., Head works Site, (T/W No - I), Dt. - Hooghly | 233 | 01/09/2023 | 0 | WBSEDCL | 3.21 | 0 | 0 | 0
4162 | HOOGHLY | Electrical | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME , SM/18657 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Balarambati water supply scheme, T.W. No. I, II & III, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | 3410/ED | 10/08/2023 | 90 | ORIENTAL ENGINEERING CO. | 32.24 | 0 | 0 | 80
4163 | HOOGHLY | Hooghly Division | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME , SM/18657 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of BALARAMBATI Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.HE Dte. | 3008/HUG | 05/10/2023 | 60 | S.K ENTERPRISE | 33.79 | 60.79 | 100 | 100
4164 | HOOGHLY | Electrical | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME , SM/18657 | New | Quotation for new service connection at Balarambati W/S Sch., T/W No. - III, [SM/18657], Block - Singur, under Singur CCC, WBSEDCL, Ref. Id. - 503584700, Dt. - 12-03-2024, Application No. - 5004050064 | 894 | 18/03/2024 | 0 | WBSEDCL | 5.07 | 0 | 0 | 0
4165 | HOOGHLY | Hooghly Division | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME , SM/18657 | New | PAYMENT FOR ROAD RESTORATION | BP-2024-25-186 | 06/06/2024 | 0 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 10.78 | 0 | 0 | 0
4166 | HOOGHLY | Electrical | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME , SM/18657 | New | Quotation Bill for New Service Connection at Balarambati W/S. Sch. TW-II | 715 | 29/01/2024 | 0 | WBSEDCL | 6.84 | 0 | 0 | 0
4167 | HOOGHLY | Hooghly Division | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME , SM/18657 | New | BALARAMBATI Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. [NEW SCHEME] | 2334/HUG | 07/08/2023 | 686 | SAMIRON GHOSH | 782.6 | 616.94 | 78.83 | 100
4168 | HOOGHLY | Electrical | Source Augmentation of GOURHATI piped Water Supply Scheme Under Arambag Block , SM/18965 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of GOURHATI piped Water Supply Scheme Block- Arambag District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4525/ED | 23/11/2023 | 90 | UNIVERSAL ENTERPRISES | 21.49 | 0 | 0 | 0
4169 | HOOGHLY | Hooghly Division | Source Augmentation of GOURHATI piped Water Supply Scheme Under Arambag Block , SM/18965 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at HARADITYA (2Nos.),GOURHATI (2Nos.),MAINAN (1No.)W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | 3476/HUG | 29/11/2023 | 45 | SPG ENTERPRISES | 87.88 | 12.28 | 34.93 | 20
4170 | HOOGHLY | Hooghly Division | Source Augmentation of GOURHATI piped Water Supply Scheme Under Arambag Block , SM/18965 | Augmentation | Construction of 6 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at HARADITYA (2Nos.), GOURHATI (2Nos.), MAINAN (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3312/HUG | 10/11/2023 | 546 | DILIP KUMAR GHOSH | 70.72 | 0 | 0 | 32
4171 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18946 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at JAMGRAM (2Nos.), PANDUA (2Nos.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3242/HUG | 06/11/2023 | 60 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 59.67 | 0 | 0 | 0
4172 | HOOGHLY | Electrical | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18946 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. | 4510/ED | 23/11/2023 | 90 | INDIA ENTERPRISE | 21.48 | 0 | 0 | 0
4173 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18946 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at JAMGRAM (2Nos.), PANDUA (2Nos.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | 3384/HUG | 22/11/2023 | 710 | MS D.PALIT AND CO. | 87.87 | 0 | 0 | 80
4174 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18946 | Augmentation | Repairing & Renovation of boundary wall and Land development at H/W Site of Pandua Z-II PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 275/CH | 20/02/2025 | 10 | JOY GURU ENTERPRISE | 4.78 | 0 | 0 | 100
4175 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18946 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site of Pandua Z-III PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 271/CH | 20/02/2025 | 10 | TOTON MONDAL | 3.38 | 0 | 0 | 100
4176 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18946 | Augmentation | Repairing & Renovation of Switch room and Store room at H/W Site of Pandua Z-II PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 281/CH | 20/02/2025 | 10 | TOTON MONDAL | 3.18 | 0 | 0 | 100
4177 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18946 | Augmentation | Repairing & Renovation of Switch room and Store room at H/W Site of Pandua Z-I PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 278/CH | 20/02/2025 | 10 | TOTON MONDAL | 2.84 | 0 | 0 | 100
4178 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18946 | Augmentation | Repairing & Renovation of Switch room at PH-2 of Pandua Z-I PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 279/CH | 20/02/2025 | 10 | JOY GURU ENTERPRISE | 2.23 | 0 | 0 | 100
4179 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18946 | Augmentation | Repairing & Renovation of boundary wall and Land development at H/W Site of Pandua Z-I PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 238/CH | 19/02/2025 | 10 | JOY GURU ENTERPRISE | 4.78 | 0 | 0 | 100
4180 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18946 | Augmentation | Repairing & Renovation of Switch room at PH-3 of Pandua Z-I PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 483/CH | 04/04/2025 | 10 | TOTON MONDAL | 1.4 | 0 | 0 | 100
4181 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18946 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-3 of Pandua Z-II PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 283/CH | 20/02/2025 | 10 | JOY GURU ENTERPRISE | 2.9 | 0 | 0 | 100
4182 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18946 | Augmentation | Emargency replacement of valves and allied works at Pandua Water Supply Scheme under Pandua Block under Chinsurah sub-division under Hooghly Division, PHE Dte. | 304/CH | 20/02/2025 | 10 | JOY GURU ENTERPRISE | 3.26 | 0 | 0 | 100
4183 | HOOGHLY | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK , SM/18946 | Augmentation | Repairing & Renovation of boundary wall, Switch room and Land development at PH-2 of Pandua Z-II PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | 485/CH | 04/04/2025 | 10 | JOY GURU ENTERPRISE | 1.72 | 0 | 0 | 100
4184 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | 3rd Continuation order for Engagement of 5 personnel (Sampling Assistant) & 1 (Lab Attendant) in water Testing Laboratories under Hooghly Division PHE Dte. | 28/HQ/HUG | 28/03/2022 | 6 | ARUN SEAL AND CO. | 3.23 | 3 | 100 | 0
4185 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | NGO LAB REMUNERATION | C092252697841 | 29/09/2022 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.99 | 0 | 0 | 0
4186 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | NGO LAB REMUNERATION | C092252697237 | 29/09/2022 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.99 | 0 | 0 | 0
4187 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | NGO LAB REMUNERATION | C092252697880 | 29/09/2022 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.99 | 0 | 0 | 0
4188 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | Engagement of 3 personnel (Chemist / Bacteriologist ) in Serampore /Chandannaga/Kamarpukur/Sub District Water Testing Laboratory under Hooghly Division PHE Dte. | 87/HQ/HUG | 13/03/2023 | 31 | TANISA ENTERPRISE | 0.64 | 0.64 | 100 | 0
4189 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | 4th Continuation order for Engagement of 5 personnel (Sampling Assistant) & 1 (Lab Attendant) in Water Testing Laboratories under Hooghly Division PHE Dte. | 187/HQ/HUG | 19/09/2022 | 181 | ARUN SEAL AND CO. | 3.23 | 3.23 | 100 | 0
4190 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | Engagement of 3 personnel (Chemist / Bacteriologist / Lab Assistant) in Chandannagar Sub District water testing laboratory II under Hooghly Division, P.H.E. Dte ( from 01.04.2022 to 28.02.2023) 11 months. | 91/HQ/HUG | 23/06/2022 | 334 | ARUN SEAL AND CO. | 4.9 | 4.9 | 100 | 0
4191 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | Engagement of 3 personnel (Chemist/Bacteriologist/Lab Assistant) in Serampore sub district water testing laboratory II under Hooghly Division, P.H.E. Dte. (from 01.04.2022 to 28.02.21023) 11 months. | 92/HQ/HUG | 23/06/2022 | 334 | ARUN SEAL AND CO. | 4.9 | 4.9 | 100 | 0
4192 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | 5TH CONTINUATION OF WORK ORDER FOR ENGAGEMENT OF LABORATORY PERSONNEL (CHEMIST/BACTERIOLOGIST AND LAB ASSISTANT) IN 3 (THREE), NEW WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, PHEDTE. | 193/HQ/HUG | 23/09/2022 | 153 | CLIFFORD FACILITY SERVICES PVT LTD. | 4.42 | 4.08 | 100 | 0
4193 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | 1st Continuation Engagement of 3 personnel (Chemist / Bacteriologist / Lab Assistant) in Chandannagar Sub District Water Testing Laboratory II under Hooghly Division PHE Dte. (From 01/03/2023 to 30/06/2023) 04 Months. | 64/HQ/HUG | 24/02/2023 | 59 | ARUN SEAL AND CO. | 1.71 | 0.86 | 100 | 100
4194 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | 5th Continuation order for Engagement of 5 personnel (Sampling Assistant) & 1 (Lab Attendant) in Water Testing Laboratories under Hooghly Division PHE Dte. [FROM 01.04.2023 TO 30.04.2023] 01 MONTH | 121/HQ/HUG | 29/03/2023 | 31 | ARUN SEAL AND CO. | 0.54 | 0.54 | 100 | 100
4195 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | 6th Continuation of Work order for Engagement of Laboratory Personnel (Chemist / Bacteriologist and Lab Assistant) in 3 (Three), New Water Testing Laboratories under Hooghly Division, P.H.E. Dte. [ FROM 01.03.2023 TO 30.04.2023] 2 MONTHS | 65/HQ/HUG | 24/02/2023 | 59 | CLIFFORD FACILITY SERVICES PVT LTD. | 1.64 | 1.64 | 100 | 100
4196 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | WORK OF CALIBRATION CERTIFICATE REQUIREMENT FOR SERAMPORE SUB-DISTRICT WATER TESTING LABORATORY UNDER HOOGHLY DIVISION, P.H.E. DTE. [SL NO. 01] | 156/HQ/HUG | 24/04/2023 | 5 | LAB SOLUTION | 0.38 | 0.38 | 100 | 100
4197 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | WORK OF CALIBRATION CERTIFICATE REQUIREMENT FOR CHANDANNAGAR SUB-DISTRICT WATER TESTING LABORATORY UNDER HOOGHLY DIVISION, P.H.E. DTE. [SL NO. 02] | 157/HQ/HUG | 24/04/2023 | 5 | LAB SOLUTION | 0.38 | 0.38 | 100 | 100
4198 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | WORK OF CALIBRATION CERTIFICATE REQUIREMENT FOR KAMARPUKUR SUB-DISTRICT WATER TESTING LABORATORY UNDER HOOGHLY DIVISION, P.H.E. DTE. [SL NO. 03] | 158/HQ/HUG | 24/04/2023 | 5 | LAB SOLUTION | 0.38 | 0.38 | 100 | 100
4199 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | 7TH CONTINUATION OF WORK ORDER FOR ENGAGEMENT OF LABORATORY 06 NOS. PERSONNEL (CHEMIST/BACTERIOLOGIST AND LAB ASSISTANT) IN 3 (THREE), NEW WATER TESTING LABORATORIES UNDER HOOGHLY DIVISION, PHEDTE. [ FROM 01.05.2023 TO 30.06.2023] 02 MONTHS. | 166/HQ/HUG | 28/04/2023 | 61 | CLIFFORD FACILITY SERVICES PVT LTD. | 1.64 | 1.64 | 100 | 100
4200 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | 1st Continuation order of Engagement of 3 personnel (Chemist / Bacteriologist ) in Serampore /Chandannaga/Kamarpukur/Sub District Water Testing Laboratory under Hooghly Division PHE Dte. [From 01.05.2023 to 31.05.2023] 01 month. | 167/HQ/HUG | 28/04/2023 | 61 | TANISA ENTERPRISE | 0.64 | 0.64 | 100 | 10
4201 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | 2nd Continuation order of Engagement of 3 personnel (Chemist / Bacteriologist ) in Serampore /Chandannaga/Kamarpukur/Sub District Water Testing Laboratory under Hooghly Division PHE Dte. [From 01.06.2023 to 30.06.2023] 01 month. | 207/HQ/HUG | 30/05/2023 | 31 | TANISA ENTERPRISE | 0.64 | 0.64 | 100 | 10
4202 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | NGO LAB PERSONEL REMUNERATION | BP-2022-23-426 | 29/12/2022 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.66 | 0 | 0 | 0
4203 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | NGO LAB PERSONEL REMUNERATION | BP-2022-23-427 | 29/12/2022 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.66 | 0 | 0 | 0
4204 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB | BP-2022-23-541 | 21/02/2023 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.45 | 0 | 0 | 0
4205 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | Claim for expenses incurred for salary of staff | BP-2022-23-603 | 16/03/2023 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.45 | 0 | 0 | 0
4206 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | NGO LAB PAYMENT |  | 26/06/2023 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.45 | 0 | 0 | 0
4207 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | Salary Payment for the month of July 2023 to NGO LAB | BP-2023-24-260 | 07/08/2023 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.45 | 0 | 0 | 0
4208 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | Salary Payment for the month of July 2023 to NGO LAB | BP-2023-24-261 | 07/08/2023 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.45 | 0 | 0 | 0
4209 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB | BP-2022-23-542 | 21/02/2023 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.45 | 0 | 0 | 0
4210 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT FOR NGO MANAGED LAB FOR THE MONTH OF APRIL-23 | BP-2023-24-128 | 19/06/2023 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.45 | 0 | 0 | 0
4211 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB | BP-2023-24-455 | 11/10/2023 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.67 | 0 | 0 | 0
4212 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT FOR NGO MANAGED LAB FOR THE MONTH OF MARCH-23 & APRIL-23 | BP-2023-24-85 | 19/05/2023 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.45 | 0 | 0 | 0
4213 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB | C012333953659 | 13/01/2023 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.33 | 0 | 0 | 0
4214 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT FOR NGO MANAGED LAB FOR THE MONTH OF MARCH-23 & APRIL-23 | BP-2023-24-130 | 19/06/2023 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.45 | 0 | 0 | 0
4215 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB | BP-2023-24-456 | 11/10/2023 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.67 | 0 | 0 | 0
4216 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | Salary Payment for the month of June 2023 to NGO LAB | BP-2023-24-264 | 07/08/2023 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.45 | 0 | 0 | 0
4217 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | Salary Payment for the month of June 2023 to NGO LAB | BP-2023-24-266 | 07/08/2023 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.45 | 0 | 0 | 0
4218 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | NGO LAB PAYMENT | C112227098079 | 21/11/2022 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.47 | 0 | 0 | 0
4219 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | NGO LAB PAYMENT | C112227097979 | 21/11/2022 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.47 | 0 | 0 | 0
4220 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB | BP-2022-23-467 | 13/01/2023 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.33 | 0 | 0 | 0
4221 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB |  | 13/04/2023 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.45 | 0 | 0 | 0
4222 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | Claim for Expenses incurred for salary of staff | BP-2022-23-604 | 16/03/2023 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.45 | 0 | 0 | 0
4223 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB |  | 13/04/2023 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.45 | 0 | 0 | 0
4224 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT FOR NGO MANAGED LAB FOR THE MONTH OF MARCH-23 & APRIL-23 |  | 17/05/2023 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.9 | 0 | 0 | 0
4225 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB | BP-2023-24-384 | 20/09/2023 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.51 | 0 | 0 | 0
4226 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB | BP-2022-23-543 | 21/02/2023 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.45 | 0 | 0 | 0
4227 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT FOR NGO MANAGED LAB FOR THE MONTH OF MARCH-23 & APRIL-23 |  | 17/05/2023 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.9 | 0 | 0 | 0
4228 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | Salary Payment for the month of July 2023 to NGO LAB | BP-2023-24-262 | 07/08/2023 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.45 | 0 | 0 | 0
4229 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB | C112227098256 | 21/11/2022 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.47 | 0 | 0 | 0
4230 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | NGO LAB PERSONEL REMUNERATION | BP-2022-23-428 | 29/12/2022 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.66 | 0 | 0 | 0
4231 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT FOR NGO MANAGED LAB FOR THE MONTH OF MARCH-23 & APRIL-23 |  | 17/05/2023 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.9 | 0 | 0 | 0
4232 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | Claim for expenses incurred for salary of staff | BP-2022-23-605 | 16/03/2023 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.45 | 0 | 0 | 0
4233 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | NGO LAB PAYMENT |  | 26/06/2023 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.45 | 0 | 0 | 0
4234 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | NGO LAB PAYMENT |  | 26/06/2023 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.45 | 0 | 0 | 0
4235 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT FOR NGO MANAGED LAB FOR THE MONTH OF MARCH-23 & APRIL-23 | BP-2023-24-86 | 19/05/2023 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.45 | 0 | 0 | 0
4236 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB | BP-2023-24-225 | 21/07/2023 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.45 | 0 | 0 | 0
4237 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB | BP-2023-24-385 | 20/09/2023 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.51 | 0 | 0 | 0
4238 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB | BP-2022-23-468 | 13/01/2023 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.33 | 0 | 0 | 0
4239 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB |  | 13/04/2023 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.45 | 0 | 0 | 0
4240 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT FOR NGO MANAGED LAB FOR THE MONTH OF MARCH-23 & APRIL-23 | BP-2023-24-87 | 19/05/2023 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.45 | 0 | 0 | 0
4241 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT FOR NGO MANAGED LAB FOR THE MONTH OF MARCH-23 & APRIL-23 | BP-2023-24-129 | 12/06/2023 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.45 | 0 | 0 | 0
4242 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | Laboratory Bill | BP-2022-23-425 | 29/12/2022 | 0 | CLIFFORD FACILITY SERVICES PVT LTD. | 4.46 | 0 | 0 | 0
4243 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | Salary Payment for the month of June 2023 to NGO LAB | BP-2023-24-265 | 07/08/2023 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.45 | 0 | 0 | 0
4244 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB | BP-2023-24-226 | 21/07/2023 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.45 | 0 | 0 | 0
4245 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB | BP-2023-24-454 | 11/10/2023 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.67 | 0 | 0 | 0
4246 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB | BP-2023-24-383 | 20/09/2023 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.51 | 0 | 0 | 0
4247 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | Laboratory Staff Payment | BP-2023-24-794 | 30/01/2024 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.51 | 0 | 0 | 0
4248 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | NGO LAB PAYMENT | BP-2023-24-655 | 15/12/2023 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 1.03 | 0 | 0 | 0
4249 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB FOR THE MONTH OF NOV-23 | BP-2023-24-658 | 18/01/2024 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.51 | 0 | 0 | 0
4250 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | PAYMENT TO NGO LAB | BP-2023-24-227 | 21/07/2023 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.45 | 0 | 0 | 0
4251 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | Laboratory Bill payment | BP-2023-24-793 | 30/01/2024 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.51 | 0 | 0 | 0
4252 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | Laboratory Staff Payment | BP-2023-24-796 | 30/01/2024 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.51 | 0 | 0 | 0
4253 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | NGO LAB PAYMENT FOR THE MONTH OF OCT-23 & NOV-23 | BP-2023-24-658 | 14/12/2023 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 1.03 | 0 | 0 | 0
4254 | HOOGHLY | Hooghly Division | Operational charges of PHED & NGO managed Laboratories related to WQMSP under Jal Jeevan Mission for 12 months under Hooghly Division, PHE Dte. , SM/11989 | Support-WQMSP | NGO LAB PAYMENT FOR THE MONTH OF OCT-23 & NOV-23 | BP-2023-24-656 | 14/12/2023 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.74 | 0 | 0 | 0
4255 | HOOGHLY | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte , SM/19085 | Support-WQMSP | Engagement of 3 personnel (Chemist / Bacteriologist / Lab Assistant) in Serampore Sub District Water Testing Laboratory II under Hooghly Division PHE Dte For a period of 9 Months | 1597/HUG | 01/06/2023 | 274 | DAS ENTERPRISE (SAMIR DAS) | 6.99 | 6.41 | 91.73 | 80
4256 | HOOGHLY | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte , SM/19085 | Support-WQMSP | Deployment of laboratory personnel i.e. one no. Chemist one no, Bacteriologist & one no. Lab-Assistant cum Data Entry Operator & One no. Sampling Assistant of District Laboratory under Hooghly Division PHE Dte For a Period of 01/12/2023 to 31/10/2024 (11 months) | 3532/A/HUG | 01/12/2023 | 336 | PRADIP KUMAR ADHYA | 9.2 | 9.2 | 100 | 100
4257 | HOOGHLY | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte , SM/19085 | Support-WQMSP | PAYMENT OF NGO LAB FOR SALARY FOR THE MONTH OF JANUARY-24 & FEBRUARY-24 | BP-2023-24-885 | 06/03/2024 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 1.03 | 0 | 0 | 0
4258 | HOOGHLY | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte , SM/19085 | Support-WQMSP | PAYMENT OF NGO LAB FOR SALARY FOR THE MONTH OF JANUARY-24 & FEBRUARY-24 | BP-2023-24-883 | 06/03/2024 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 1.03 | 0 | 0 | 0
4259 | HOOGHLY | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte , SM/19085 | Support-WQMSP | NGO LAB PAYMENT FOR THE MONTH OF APRIL-24 | BP-2024-25-158 | 22/05/2024 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.51 | 0 | 0 | 0
4260 | HOOGHLY | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte , SM/19085 | Support-WQMSP | Salary for the Staff For the month of August 2024 | BP-2024-25-437 | 12/09/2024 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.51 | 0 | 0 | 0
4261 | HOOGHLY | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte , SM/19085 | Support-WQMSP | Remunaration of Oct 2024 | BP-2024-25-633 | 13/11/2024 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.51 | 0 | 0 | 0
4262 | HOOGHLY | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte , SM/19085 | Support-WQMSP | Salary for the Staff For the month of August 2024 | BP-2024-25-438 | 12/09/2024 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.51 | 0 | 0 | 0
4263 | HOOGHLY | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte , SM/19085 | Support-WQMSP | PAYMENT OF NGO LAB FOR SALARY FOR THE MONTH OF JANUARY-24 & FEBRUARY-24 | BP-2023-24-884 | 06/03/2024 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 1.03 | 0 | 0 | 0
4264 | HOOGHLY | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte , SM/19085 | Support-WQMSP | PAYMENT TO NGO LAB FOR THE MONTH OF-APRIL-24 | BP-2024-25-160 | 22/05/2024 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.51 | 0 | 0 | 0
4265 | HOOGHLY | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte , SM/19085 | Support-WQMSP | Remunaration of Oct 2024 | BP-2024-25-634 | 13/11/2024 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.51 | 0 | 0 | 0
4266 | HOOGHLY | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte , SM/19085 | Support-WQMSP | NGO LAB PAYMENT FOR THE MONTH OF APRIL-24 | BP-2024-25-159 | 22/05/2024 | 0 | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.51 | 0 | 0 | 0
4267 | HOOGHLY | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte , SM/19085 | Support-WQMSP | Salary for the Staff For the month of August 2024 | BP-2024-25-436 | 12/09/2024 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.51 | 0 | 0 | 0
4268 | HOOGHLY | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte , SM/19085 | Support-WQMSP | Remunaration month of Oct 2024 | BP-2024-25-635 | 13/11/2024 | 0 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.51 | 0 | 0 | 0
4269 | HOOGHLY | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte , SM/19085 | Support-WQMSP | NGO LAB PAYMENT FOR THE MONTH OF JULY-24 | BP-2024-25-366 | 06/08/2024 | 0 | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.51 | 0 | 0 | 0
4270 | HOOGHLY | Hooghly Division | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. , SM/08967 | Support-WQMSP | Supply and Delivery Chemicals of 09 nos. Water Testing Laboratories under Hooghly District under Hooghly Division, P.H.E. Dte. | 304/HQ/HUG | 30/12/2022 | 10 | LAB SOLUTION | 0.86 | 0.86 | 100 | 0
4271 | HOOGHLY | Hooghly Division | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. , SM/08967 | Support-WQMSP | Supply and Delivery Chemicals of 09 nos. Water Testing Laboratories under Hooghly District under Hooghly Division, P.H.E. Dte. | 305/HQ/HUG | 30/12/2022 | 10 | LAB SOLUTION | 0.86 | 0.86 | 100 | 0
4272 | HOOGHLY | Hooghly Division | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. , SM/08967 | Support-WQMSP | Supply and Delivery Chemicals of 09 nos. Water Testing Laboratories under Hooghly District under Hooghly Division, P.H.E. Dte. | 306/HQ/HUG | 30/12/2022 | 10 | LAB SOLUTION | 0.86 | 0.86 | 100 | 0
4273 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR and Bid documents for new Ground / Surface source based Single / Multi Village Schemes in the uncovered areas of Hooghly District under under Chinsurah Sub Division, Hooghly Division, PHE Dte. | 793/Hug | 18/04/2022 | 75 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 125.19 | 113.17 | 100 | 0
4274 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for Augmentation of MALAYPUR Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh]. | 615/Arg | 31/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.29 | 0 | 0 | 0
4275 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for Augmentation of Dihibatpur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. (Dihibatpur Part-A) | 340/Arg | 02/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.68 | 4.62 | 98.71 | 0
4276 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for Augmentation of Shyampur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. (Shyampur Part-A) | 342/Arg | 02/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.73 | 4.72 | 99.79 | 0
4277 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Additional survey work for preparation of DPR for Augmentation of Shyampur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. (Shyampur Part-B) | 343/Arg | 02/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.3 | 1.25 | 95.69 | 0
4278 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Additional survey work for preparation of DPR for Augmentation of Dihibatpur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. (Dihibatpur Part-B) | 341/Arg | 02/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.46 | 0.46 | 98.27 | 0
4279 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Additional survey work for preparation of DPR for Augmentation of Krishnanagar Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I]. (Krishnanagar Part-B) | 392/Arg | 31/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.34 | 0.34 | 99.73 | 0
4280 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for Augmentation of Khanakul Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I]. | 393/Arg | 31/05/2022 | 30 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 4.74 | 4.68 | 98.76 | 0
4281 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for Augmentation of Gobindapur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I]. | 394/Arg | 31/05/2022 | 30 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 3.3 | 3.25 | 98.49 | 0
4282 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for Augmentation of Balipur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I]. (Balipur Part-B) | 406/Arg | 07/06/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.02 | 1.96 | 97.38 | 0
4283 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for Augmentation of Krishnanagar Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I]. (Krishnanagar Part-A). | 391/Arg | 31/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.68 | 4.64 | 99.15 | 0
4284 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Rambati PWSS under Chandannagar Sub - Division, PHE Dte. | 664/Chan | 13/12/2022 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.51 | 0 | 0 | 0
4285 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Paschim Narayanpur PWSS under Chandannagar Sub - Division, PHE Dte. | 670/Chan | 13/12/2022 | 15 | INDRANIL DUTTA & ASSOCIATES | 7.18 | 0 | 0 | 0
4286 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for Augmentation of Srirampur Piped Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. Part-A | 623/Arg | 01/09/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.42 | 4.35 | 98.41 | 0
4287 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Atisara PWSS under Chandannagar Sub - Division, PHE Dte. | 673/Chan | 13/12/2022 | 15 | M/S R. DUTTA & CO. | 8.52 | 0 | 0 | 0
4288 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Additional survey work for Preparation of DPR for Augmentation of Srirampur Piped Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. Part-B | 625/Arg | 01/09/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.13 | 1.12 | 99.01 | 0
4289 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Nanda PWSS under Chandannagar Sub - Division, PHE Dte. | 0666/Chan | 13/12/2022 | 15 | INDRANIL DUTTA & ASSOCIATES | 7.34 | 0 | 0 | 0
4290 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Basubati PWSS under Chandannagar Sub - Division, PHE Dte. | 0668/Chan | 13/12/2022 | 15 | INDRANIL DUTTA & ASSOCIATES | 7.3 | 0 | 0 | 0
4291 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preperation of Paschim Narayanpur PWSS under Chandannagar Sub - Division, P.H.E. Dte | 670/1/Hug | 13/12/2022 | 15 | INDRANIL DUTTA & ASSOCIATES | 7.2 | 0 | 0 | 0
4292 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, design, drawing & DPR Preparation of Nawpara PWSS under Chandannagar Sub-Division, of Hooghly Division, P.H.E. Dte. | 2177/HUG | 29/09/2022 | 15 | ENVIROTECH SOLUTIONS | 7 | 0 | 0 | 0
4293 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preperation of Bahirkhanda PWSS under Chandannagar Sub - Division, PHE Dte | 672/1/hug | 13/12/2022 | 15 | M/S R. DUTTA & CO. | 10.43 | 0 | 0 | 0
4294 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for Augmentation of Balipur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I]. (Balipur Part-A) | 395/Arg | 31/05/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.58 | 4.56 | 99.68 | 0
4295 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR and Bid documents for new Ground / Surface source based Single / Multi Village Schemes in the uncovered areas of Hooghly District under Arambag Sub Division, Hooghly Division, PHE Dte. | 792/Hug | 18/04/2022 | 90 | RADIANT | 227.1 | 227.08 | 100 | 0
4296 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR and Bid documents for new Ground / Surface source based Single / Multi Village Schemes in the uncovered areas of Hooghly District under under Serampore Sub Division, Hooghly Division, PHE Dte. | 791/Hug | 18/04/2022 | 75 | THE NISARGA CONSULTANCY | 120.96 | 114.99 | 100 | 0
4297 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Bainchipota (Zone-II) PWSS under Chandannagar Sub - Division, PHE Dte. | 618/Chan | 02/12/2022 | 15 | TECHVISION | 2.57 | 2.57 | 100 | 0
4298 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Bighati(Zone-II) PWSS under Chandannagar Sub - Division, PHE Dte. | 621/Chan | 02/12/2022 | 15 | TECHVISION | 4.48 | 4.48 | 100 | 0
4299 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Bahirkhanda PWSS under Chandannagar Sub - Division, PHE Dte. | 672/Chan | 13/12/2022 | 15 | M/S R. DUTTA & CO. | 10.42 | 10.42 | 100 | 100
4300 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Bainchipota (Zone -I)PWSS under Chandannagar Sub - Division, PHE Dte | 619/Chan | 02/12/2022 | 15 | TECHVISION | 4.7 | 4.7 | 100 | 0
4301 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Bighati(Zone -I) PWSS under Chandannagar Sub - Division, PHE Dte. | 620/Chan | 02/12/2022 | 15 | TECHVISION | 5.01 | 5.01 | 100 | 0
4302 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Nawpara PWSS under Chandannagar Sub - Division, PHE Dte. | 515/Chan | 29/09/2022 | 15 | ENVIROTECH SOLUTIONS | 6.83 | 6.83 | 100 | 100
4303 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Bhagabatipur PWSS under Chandannagar Sub - Division, PHE Dte. | 97/Chan | 27/02/2023 | 15 | APEX ENGINEERING | 0.63 | 0.63 | 100 | 0
4304 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Parjana PWSS under Chandannagar Sub - Division, PHE Dte. | 98/Chan | 27/02/2023 | 15 | APEX ENGINEERING | 5.99 | 5.99 | 100 | 0
4305 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Sirazpur PWSS under Chandannagar Sub - Division, PHE Dte. | 101/Chan | 27/02/2023 | 15 | APEX ENGINEERING | 5.11 | 5.11 | 100 | 0
4306 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Aima Chapsara PWSS under Chandannagar Sub - Division, PHE Dte. | 99/Hug | 27/02/2023 | 15 | APEX ENGINEERING | 4.38 | 4.38 | 100 | 0
4307 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Purushottampur PWSS under Chandannagar Sub - Division, PHE Dte. | 100/Hug | 27/02/2023 | 15 | APEX ENGINEERING | 4.29 | 4.29 | 100 | 0
4308 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preperation of ATISARA PWSS under Chandannagar Sub - Division, P.H.E. Dte | 673/1/Hug | 13/12/2022 | 15 | M/S R. DUTTA & CO. | 9.62 | 8.52 | 100 | 100
4309 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preperation of Basubati PWSS under Chandannagar Sub - Division, P.H.E. Dte | 668/1/Hug | 13/12/2022 | 15 | INDRANIL DUTTA & ASSOCIATES | 8.25 | 7.3 | 100 | 100
4310 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preperation of Nasibpur PWSS under Chandannagar Sub - Division, P.H.E. Dte | 667/1/Hug | 13/12/2022 | 15 | INDRANIL DUTTA & ASSOCIATES | 7.51 | 7.18 | 100 | 100
4311 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preperation of Rambati PWSS under Chandannagar Sub - Division, P.H.E. Dte | 664/1/Hug | 13/12/2022 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.52 | 2.51 | 100 | 100
4312 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of 1 No. DPR for New Ground / Surface source based Single / Multi Village Schemes in the uncovered areas of Hooghly District under CHANDANNAGAR Sub Division, Hooghly Division, PHE Dte. under JJM. (Annexure-I) | 3063/HUG | 11/10/2023 | 45 | HORIZEN | 9.65 | 9.65 | 100 | 98
4313 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Nasibpur PWSS under Chandannagar Sub - Division, PHE Dte. | 669/Chan | 13/12/2022 | 15 | INDRANIL DUTTA & ASSOCIATES | 5.59 | 0 | 0 | 0
4314 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route survey Design drawing & DPR preparation of Kamarkundu Zone- VI & VII PWSS under Chandannagar Sub-Division, P.H.E. Dte | 269/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.3 | 4.26 | 100 | 95
4315 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preperation of Nanda PWSS under Chandannagar Sub - Division, P.H.E. Dte | 666/1/Hug | 13/12/2022 | 15 | INDRANIL DUTTA & ASSOCIATES | 8.29 | 7.34 | 100 | 100
4316 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route survey Design drawing & DPR preparation of Kamarkundu Zone- IV & V PWSS under Chandannagar Sub-Division, P.H.E. Dte | 268/Chan | 31/05/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.74 | 4.7 | 100 | 95
4317 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Ganderpukur Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division (PART-A). | 1002/Chan | 21/12/2023 | 15 | TECHVISION | 0.84 | 0.84 | 100 | 98
4318 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sibrambati (Zone-II) Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division (PART-C). | 1001/Chan | 21/12/2023 | 15 | TECHVISION | 0.78 | 0.78 | 100 | 98
4319 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sibrambati (Zone-II) Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division (PART-B) | 1000/Chan | 21/12/2023 | 15 | TECHVISION | 0.98 | 0.98 | 100 | 98
4320 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Ganderpukur Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division (PART-B) | 1003/Chan | 21/12/2023 | 15 | TECHVISION | 0.73 | 0.73 | 100 | 98
4321 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Ganderpukur Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division (PART-C) | 1004/Chan | 21/12/2023 | 15 | TECHVISION | 0.37 | 0.37 | 100 | 98
4322 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sibrambati (Zone-II) Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division (PART-A) | 999/Chan | 21/12/2023 | 15 | TECHVISION | 0.84 | 0 | 0 | 98
4323 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Ganderpukur Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division (PART-D). | 1005/Chan | 21/12/2023 | 15 | TECHVISION | 0.78 | 0.78 | 100 | 98
4324 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Kapasharia (Zone-II) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 127/SER | 23/02/2024 | 15 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
4325 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Gopalpur(Zone-II) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 135/SER | 23/02/2024 | 15 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
4326 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection(FHTC) of Rajballabhbati Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub - Division PHE Dte. (Part- C) | 748/Chan | 29/08/2024 | 15 | TECHVISION | 0.78 | 0.78 | 100 | 100
4327 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Jagmohanpur Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 121/SER | 23/02/2024 | 15 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
4328 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Krishna Ballabhbati Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-B) | 745/Chan | 29/08/2024 | 15 | ENVIROTECH SOLUTIONS | 0.95 | 0.95 | 100 | 100
4329 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection(FHTC) of Rajballabhbati Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub - Division PHE Dte. (Part- B) | 747/Chan | 29/08/2024 | 15 | TECHVISION | 0.84 | 0.84 | 100 | 100
4330 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Mundalika (Zone-I) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 131/SER | 23/02/2024 | 15 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
4331 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Mundalika (Zone-II) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 132/SER | 23/02/2024 | 15 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
4332 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Pairagacha (Zone-II) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 137/SER | 23/02/2024 | 15 | APEX TECHNOLOGIES | 0.84 | 0.84 | 100 | 95
4333 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Bandhpur Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 122/SER | 23/02/2024 | 15 | APEX TECHNOLOGIES | 0.84 | 0.84 | 100 | 95
4334 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Bhagabatipur (Zone-I) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 123/SER | 23/02/2024 | 15 | APEX TECHNOLOGIES | 0.84 | 0.84 | 100 | 95
4335 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Nababpur Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 125/SER | 23/02/2024 | 15 | APEX TECHNOLOGIES | 0.84 | 0.84 | 100 | 95
4336 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for different works for providng Functional Household Tap Connection (FHTC) of Krishna BALLABHBATI Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub-Division, P.H.E Dte. (PART-A) | 744/Chan | 29/08/2024 | 15 | ENVIROTECH SOLUTIONS | 0.84 | 0.84 | 100 | 100
4337 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Kumirmora (Zone-II) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 119/SER | 23/02/2024 | 15 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
4338 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Krishna Ballabhbati Piped Water Supply Scheme under Haripal Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-C) | 746/Chan | 29/08/2024 | 15 | ENVIROTECH SOLUTIONS | 0.78 | 0.78 | 100 | 100
4339 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Bhagabatipur (Zone-II) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 124/SER | 23/02/2024 | 15 | APEX TECHNOLOGIES | 0.84 | 0.84 | 100 | 95
4340 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Pairagacha (Zone-I) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 136/SER | 23/02/2024 | 15 | APEX TECHNOLOGIES | 0.84 | 0.84 | 100 | 95
4341 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Kapasharia (Zone-I) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 126/SER | 23/02/2024 | 15 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
4342 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Kotalpur (Zone-I) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 129/SER | 23/02/2024 | 15 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
4343 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Kotalpur (Zone-II) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 130/SER | 23/02/2024 | 15 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
4344 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Jagannathpur Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 133/SER | 23/02/2024 | 15 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
4345 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Gopalpur(Zone-I) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 134/SER | 23/02/2024 | 15 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
4346 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Kumirmora (Zone-I) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 118/SER | 23/02/2024 | 15 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
4347 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Haripur Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 120/SER | 23/02/2024 | 15 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
4348 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Dudhkalmi Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | 128/SER | 23/02/2024 | 15 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 90
4349 | HOOGHLY | Hooghly Division | Procurement of service consultants for preparation of DPR of New Piped Water Supply Scheme for uncovered rural area of Hooghly District in West Bengal. , SM/11504 | Support-M&E | Route Survey, Design Drawing & DPR Preparation of Binagram PWSS under Chandannagar Sub - Division, PHE Dte. | 667/Chan | 13/12/2022 | 15 | INDRANIL DUTTA & ASSOCIATES | 7.5 | 0 | 0 | 100
4350 | HOOGHLY | Hooghly Division | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues Under Jal Jeevan Mission (JJM) Support Activities , SM/18131 | Support-IEC | Conceptualization, design and implementing mass awareness generation through Tableau and using Bus Panel advisement at Hooghly district and printing & Supply 6 types of IEC leaflets & banner for distribution on FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Water Quality issues , water conservation and WASH related issues as per guideline of JJM and preparation of web based Digital (A/V) awareness generation cum training material (Bengali) with voice over showcasing IEC and HRD initiative at Hooghly District under Hooghly Division, PHE Dte, Govt. of West Bengal.. | 3054/HUG | 11/10/2023 | 449 | DEBNATH BROTHERS | 59.07 | 39.09 | 66.19 | 100
4351 | HOOGHLY | Hooghly Division | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues Under Jal Jeevan Mission (JJM) Support Activities , SM/18131 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Hooghly district and Conceptualization, design , implementing mass awareness generation through Wall Painting and miking by dissemination of awareness generation IEC messages FHTC , Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues , water conservation and WASH related issues as per guideline of JJM at Hooghly District under Hooghly Division, PHE Dte, , Govt. of West Bengal. | 3053/HUG | 11/10/2023 | 183 | LIMRA SOCIAL WELFARE SOCIETY | 55.23 | 40.67 | 100 | 74
4352 | HOOGHLY | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. , SM/06617 | Support-WQMSP | Supply & Delivery of Water Testing Chemicals, Media, Reagent, etc. for (9) Nine Water Testing Laboratories in Hooghly District under Hooghly Division, P.H.E. Dte. | 1693/Hug | 15/09/2021 | 20 | M/S LAXMI ENTERPRISE | 20.34 | 20.34 | 100 | 0
4353 | HOOGHLY | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. , SM/06617 | Support-WQMSP | Supply and Delivery of Consumables for On-site Mobile Analysis System, including cost of facilitating and coordinating for onsite testing of drinking water sources through OMAS App ensuring 50 tests per month by data updation on State Water Quality Dashboard on a monthly basis. | 282/Hug | 17/02/2022 | 1 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 3.86 | 3.86 | 100 | 0
4354 | HOOGHLY | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. , SM/06617 | Support-WQMSP | SUPPLY AND DELIVERY OF CONSUMABLE BY OMAS APP |  | 24/06/2022 | 0 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 3.86 | 0 | 0 | 0
4355 | HOOGHLY | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. , SM/06617 | Support-WQMSP | LAB |  | 07/07/2022 | 0 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 1 | 0 | 0 | 0
4356 | HOOGHLY | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. , SM/06617 | Support-WQMSP | Testing total arsenic for status review of habitations that remained quality affected by Arsenic at Hooghly District under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. | 200/HQ/HUG | 22/05/2023 | 10 | ARUN SEAL AND CO. | 0.82 | 0 | 0 | 0
4357 | HOOGHLY | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. , SM/06617 | Support-WQMSP | Testing total arsenic for status review of habitations that remained quality affected by Arsenic at Hooghly District under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. | 201/HQ/HUG | 22/05/2023 | 10 | SOUMYADIP DE | 0.77 | 0 | 0 | 0
4358 | HOOGHLY | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. , SM/06617 | Support-WQMSP | Testing total arsenic for status review of habitations that remained quality affected by Arsenic at Hooghly District under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal | 203/HQ/HUG | 22/05/2023 | 10 | SOUMYADIP DE | 0.5 | 0 | 0 | 0
4359 | HOOGHLY | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. , SM/06617 | Support-WQMSP | Testing total arsenic for status review of habitations that remained quality affected by Arsenic at Hooghly District under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. | 202/HQ/HUG | 22/05/2023 | 10 | SOUMYADIP DE | 0.77 | 0 | 0 | 0
4360 | HOOGHLY | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. , SM/06617 | Support-WQMSP | Procurement of CRMs for NABL Recognized 3 Sub District Water Testing Laboratories in Hooghly District under Hooghly Division, P.H.E. Dte. | 137/HQ/HUG | 18/04/2023 | 7 | A.R. CONSTRUCTION | 0.9 | 0.9 | 100 | 100
4361 | HOOGHLY | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. , SM/06617 | Support-WQMSP | Procurement of CRMs for NABL Recognized 3 Sub District Water Testing Laboratories in Hooghly District under Hooghly Division, P.H.E. Dte. | 138/HQ/HUG | 18/04/2023 | 7 | A.R. CONSTRUCTION | 0.9 | 0.9 | 100 | 100
4362 | HOOGHLY | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. , SM/06617 | Support-WQMSP | Procurement of CRMs for NABL Recognized 3 Sub District Water Testing Laboratories in Hooghly District under Hooghly Division, P.H.E. Dte. | 148/HQ/HUG | 18/04/2023 | 7 | LAB SOLUTION | 0.83 | 0.83 | 100 | 100
4363 | HOOGHLY | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. , SM/06617 | Support-WQMSP | Procurement of CRMs for NABL Recognized 3 Sub District Water Testing Laboratories in Hooghly District under Hooghly Division, P.H.E. Dte. | 149/HQ/HUG | 18/04/2023 | 7 | A.R. CONSTRUCTION | 0.88 | 0.88 | 100 | 100
4364 | HOOGHLY | Hooghly Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer , Hooghly Division, PHE Dte , SM/18130 | Support-MIS | Supply & Delivery hp Intel Core i3 12100 8 GB/1000 GB HDD/Windows 11 professional. | 1290/HUG | 05/05/2023 | 10 | IONET | 4.96 | 4.96 | 100 | 0
4365 | HOOGHLY | Hooghly Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer , Hooghly Division, PHE Dte , SM/18130 | Support-MIS | SUPPLY DELIVERY OF SYSTEM HP 285 G8 RYZEN 3 AND TFT HP 19.5" LED V20 HD+ UNDER HOOGHLY DIVISION, P.H.E. DTE. | 2144/HUG | 24/07/2023 | 10 | PLANET COMPUTER | 4.4 | 4.4 | 100 | 100
4366 | HOOGHLY | Hooghly Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer , Hooghly Division, PHE Dte , SM/18130 | Support-MIS | Supply & Delivery of SHARP Multifunction Machines Mfm, on site OEM Warranty 1 year Mechanic Serial no-33001475 | 2173/HUG | 25/07/2023 | 10 | GLOBAL POINT | 0.92 | 0.92 | 100 | 100
4367 | HOOGHLY | Hooghly Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer , Hooghly Division, PHE Dte , SM/18130 | Support-MIS | Supply & Delivery of 5 nos. L1 HP mono MFP 136nw (4ZB87A) Scanner Cum Printer under Hooghly Division, P.H.E. Dte. | 2527/HUG. | 21/08/2023 | 10 | PLANET COMPUTER | 1.17 | 1.17 | 100 | 100
4368 | HOOGHLY | Hooghly Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer , Hooghly Division, PHE Dte , SM/18130 | Support-MIS | SUPPLY AND DELIVERY OF SHARP MULTIFUNCTION MACHINES MFM, ON SITE OEM WARRANTY 1 YEAR MACHINE [SERIAL NO. 33006497] | 2560/HUG | 23/08/2023 | 10 | GLOBAL POINT | 0.92 | 0.92 | 100 | 100
4369 | HOOGHLY | Hooghly Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer , Hooghly Division, PHE Dte , SM/18130 | Support-MIS | Supply & Delivery of 10 nos. L1 HP MONO SFP 208DW (6GW64A) Printer under Hooghly Division, P.H.E. Dte. | 2528/HUG | 21/08/2023 | 10 | PLANET COMPUTER | 1.9 | 1.9 | 100 | 100
4370 | HOOGHLY | Hooghly Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer , Hooghly Division, PHE Dte , SM/18130 | Support-MIS | SUPPLY DELIVERY OF L1 HP MONO SFP 3004 DW/ 33PPM 3G658A UNDER HOOGHLY DIVISION, P.H.E. DTE. | 3091/HUG | 12/10/2023 | 10 | PLANET COMPUTER | 0.91 | 0.91 | 100 | 100
4371 | HOOGHLY | Hooghly Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer , Hooghly Division, PHE Dte , SM/18130 | Support-MIS | SUPPLY DELIVERY OF SYS HP DESKTOP UNDER HOOGHLY DIVISION, P.H.E. DTE. | 3095/HUG | 12/10/2023 | 10 | PLANET COMPUTER | 0.45 | 0.45 | 100 | 100
4372 | HOOGHLY | Hooghly Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer , Hooghly Division, PHE Dte , SM/18130 | Support-MIS | SUPPLY DELIVERY OF COPIER HP MFP M438 NDA A3 (8AF45A) UNDER HOOGHLY DIVISION, P.H.E. DTE. | 3090/HUG | 12/10/2023 | 10 | PLANET COMPUTER | 1.96 | 1.96 | 100 | 100
4373 | HOOGHLY | Hooghly Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer , Hooghly Division, PHE Dte , SM/18130 | Support-MIS | SUPPLY DELIVERY OF UPS CYBER POWER UT 650 EG UNDER HOOGHLY DIVISION, P.H.E. DTE. | 3092/HUG | 12/10/2023 | 10 | PLANET COMPUTER | 0.25 | 0.25 | 100 | 100
4374 | HOOGHLY | Hooghly Division | Supply, Delivery and Installation of Desktop Computer, UPS, Scanner, printer etc. through GeM portal for Office of the Executive Engineer , Hooghly Division, PHE Dte , SM/18130 | Support-MIS | SUPPLY DELIVERY OF SYS HP DESKTOP UNDER HOOGHLY DIVISION, P.H.E. DTE. | 3096/HUG | 12/10/2023 | 10 | PLANET COMPUTER | 2 | 2 | 100 | 100
4375 | HOOGHLY | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR , SM/11996 | Support-WQMSP | Supply and Delivary of Water Testing Chemical and Other Consumable Requirement of 9 nos Water Testing Laboratories for 3 Months in Hooghly District under Hooghly Division PHE Dte. | 109/HQ/HUG | 29/06/2022 | 3 | LAB SOLUTION | 2.08 | 2.08 | 100 | 0
4376 | HOOGHLY | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR , SM/11996 | Support-WQMSP | Work Order for the Chemical requirement for habitation wise Arsenic Testing Special Drive, Hooghly Division, P.H.E. Dte. [SL NO. 01] | 254/HQ/HUG | 21/10/2022 | 10 | A.R. CONSTRUCTION | 0.49 | 0.49 | 100 | 0
4377 | HOOGHLY | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR , SM/11996 | Support-WQMSP | Chemical Requirement for Habitation Wise Arsenic Testing Special Drive, Hooghly Division, P.H.E. DTE. | 25/HQ/HUG | 17/01/2023 | 5 | R CONSTRUCTION | 0.94 | 0.94 | 100 | 0
4378 | HOOGHLY | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR , SM/11996 | Support-WQMSP | Chemical Requirement for Habitation Wise Arsenic Testing Special Drive, Hooghly Division, P.H.E. DTE. | 24/HQ/HUG | 17/01/2023 | 5 | R CONSTRUCTION | 0.94 | 0.94 | 100 | 0
4379 | HOOGHLY | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR , SM/11996 | Support-WQMSP | Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. | 309/HQ/HUG | 02/09/2023 | 10 | DAS TRADING | 0.75 | 0.67 | 100 | 98
4380 | HOOGHLY | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR , SM/11996 | Support-WQMSP | Supply of Chemicals, Glasswares, etc. for Testing of potable water at different water Testing Laboratories & District Laboratory under Hooghly Division PHE Dte. | 933/HUG | 29/03/2023 | 20 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 5.91 | 5.91 | 100 | 99
4381 | HOOGHLY | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR , SM/11996 | Support-WQMSP | Engagement of resources person for supervision of SURVELLIANCE AUDIT the protocol / standard operating procedures/ technical documentation of laboratory water testing activities as per ISO/IEC 17025:2017 including performing statutory internal audit, refresher course and any other required laboratory management process and allied works to comply NABL accreditation retention system of Hooghly District Water testing Laboratory, PHE Dte for a period of four months. | 1180/Hug | 24/04/2023 | 120 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 2.77 | 2.77 | 100 | 99
4382 | HOOGHLY | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR , SM/11996 | Support-WQMSP | Supply of required CRMs for upcoming Surveillance Audit by NABL to maintain ISO/IEC 17025:2017 Accreditation status of Hooghly Dist. Water Testing Laboratory under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal | HQ/HUG/281 | 11/08/2023 | 5 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.58 | 0.58 | 100 | 95
4383 | HOOGHLY | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR , SM/11996 | Support-WQMSP | Supply and delivery chemical requirement for Amartya Rural Welfare & Research Centre Water Testing Laboratory at Balagarh Block under Hooghly Division, P.H.E. DTE. | 348/HQ/HUG | 11/10/2023 | 10 | LAB SOLUTION | 0.42 | 0.42 | 100 | 100
4384 | HOOGHLY | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR , SM/11996 | Support-WQMSP | Chemical and others consumable requirement of Kamarpukur Sub - District Water Testing Laboratory for one month under Hooghly Division, P.H.E. Dte. | 401/HQ/HUG | 08/12/2023 | 10 | LAB SOLUTION | 0.73 | 0.73 | 100 | 100
4385 | HOOGHLY | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR , SM/11996 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | 234B/HQ/HUG | 23/09/2024 | 5 | PRADIP KUMAR ADHYA | 0.96 | 0 | 0 | 0
4386 | HOOGHLY | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR , SM/11996 | Support-WQMSP | COLLECTION FOR TESTING AND UPLOADING CHARGES OF DRINKING WATER SAMPLES THROUGH FTKS W.R.T. WATER QUALITY MONITORING AND SURVEILLANCE UNDER JJM AT 18 NOS. BLOCKS UNDER HOOGHLY DISTRICT UNDER HOOGHLY DIVISION, P.H.E. DTE. | 234A/HQ/HUG | 23/09/2024 | 5 | PRADIP KUMAR ADHYA | 0.83 | 0 | 0 | 0
4387 | HOOGHLY | Hooghly Division | REQUIREMENT OF CHEMICAL AND OTHER CONSUMABLE FOR 9 WATER TESTING LABORATORIES FOR 1(ONE) YEAR AND SUPPLY OF STANDARD REFERENCE MATERIALS AND ASSOCIATED SAFETY EQUIPMENTS FOR ARRAINGING ADEQUACY AGAINST NABL-GLAP ASSESSMENT FROM NABL AUTHORITY OF SUB DISTR , SM/11996 | Support-WQMSP | 3rd Continuation work order for Collection of water sample from various villages under Hooghly District for Water Quality Monitoring under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. PERIOD : 3 MONTHS (01.04.2024 TO 30.06.2024) | 74/HQ/HUG | 28/03/2024 | 91 | DAS TRADING | 0.75 | 0 | 0 | 0
Total | [9 empty] | 431853.19 | 79682.62 | 18.45