6297 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas , SM/06796 | Retrofitting | Work Order for Household survey in Lakshmisagar (43) mouza to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 35) | 277/KSD | 10/12/2020 | 62 | M/S TARUN KUMAR PATRA | 0.47 | 0 | 0 | 0
6298 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas , SM/06796 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | 1419/BQA | 09/10/2020 | 30 | M/S TARUN KUMAR PATRA | 36.53 | 0 | 0 | 20
6299 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas , SM/06796 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) | 1420/BQA | 09/10/2020 | 30 | M/S TARUN KUMAR PATRA | 28.21 | 0 | 0 | 20
6300 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas , SM/06796 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lakshmisagar (43) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) | 1421/BQA | 09/10/2020 | 30 | M/S TARUN KUMAR PATRA | 30.11 | 0 | 0 | 20
6301 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | laying extra UPVC pipe line to cover KELEBOLA mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 818/BSD | 06/08/2021 | 15 | BISWARUP BOSE | 3.02 | 0 | 0 | 0
6302 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | Laying Extra UPVC Pipe Line to Cover Roybandh, Bankati mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 141/BSD | 18/02/2021 | 10 | PRANABANANDA TEWARI | 4.39 | 0 | 0 | 0
6303 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | laying extra UPVC pipe line to cover KELEBOLA mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 819/BSD | 06/08/2021 | 15 | PRANABANANDA TEWARI | 2.84 | 0 | 0 | 0
6304 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | Laying Extra UPVC Pipe Line to Cover Duyaranda, Kelebela mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI(Zone- R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 139/ BSD | 18/02/2021 | 10 | SOUMITRA BOSE | 4.84 | 0 | 0 | 0
6305 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | Laying HDPE Pipe Line from BANKATI Main Road to Radharamanpur Village to increase presure in Radharamanpur mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (ZONE-R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 894/BQA | 18/04/2022 | 30 | SOUMITRA KUMAR DAS | 10.04 | 0 | 0 | 0
6306 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 ,Gadardihi (PART-B ), Total House Hold - 115 | FHTC/26 | 26/02/2022 | 0 | BEAUTY CHATTERJEE | 1.34 | 0 | 0 | 0
6307 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | Extra HDPE pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR- KOTALPUKUR (Zone - B), No. of Mouza:- 05 nos, (Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)). (PART-A) | FHTC/28 | 28/01/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.83 | 0 | 0 | 0
6308 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 01,Susunia Total House Hold - 160 | FHTC/20 | 20/01/2022 | 0 | I.R.CONSTRUCTION | 9.24 | 0 | 0 | 0
6309 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | Work Order for Replacement Laying extra HDPE pipeline to cover Bhuakana (63) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 06) | FHTC/20 | 20/01/2022 | 0 | PRADYUMNA KOLEY | 3.25 | 0 | 0 | 0
6310 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | extra UPVC pipe line retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) )from Sirsha Nutanpally to Palsona more under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - JOYKRISHNAPUR (Zone - I), Name of mouza - Sirsha, Palsona. | FHTC/26 | 26/02/2022 | 0 | M/S T.P. HAZRA & SONS | 3.48 | 0 | 0 | 0
6311 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | Extra HDPE pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone- B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR- KOTALPUKUR (Zone - B), No. of Mouza:- 05 nos, (Purakonda, Sitalpur, Suratpur, Chandi & Balaram pur (Purba)). (PART- B) | FHTC/28 | 28/01/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.77 | 0 | 0 | 0
6312 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | "Laying extra HDPE pipe line to cover Jantadumur(178) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection') by retrofitting Zone-L (Dhankura) of Khatra- Hirbandh-Ranibandh Water Supply scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under JAL SWAPNA & vJal Jeevan Mission (JJM) Programme under Khatra Sub - Division of Bankura Division, PHE Dte. " | FHTC/26 | 26/02/2022 | 0 | UNITED TRADERS | 4.55 | 0 | 0 | 0
6313 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Brahmadanga (33) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-E (Naria) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 07) | FHTC/26 | 26/02/2022 | 0 | UNITED TRADERS | 2.37 | 0 | 0 | 0
6314 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | Laying extra HDPE pipe lineto cover Gorabari & Bansi mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Jagdallal (Zone - S) OHR under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | FHTC/26 | 26/02/2022 | 0 | M/S TARUN KUMAR PATRA | 29.87 | 0 | 0 | 0
6315 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rajadali (156), Sibarampur (157), Loadihi (158), Satsol (160), Sarga (161), Jhanti Pahari (162) & Sunrigara (163) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 07 Nos. Total Household - 149 Nos.' | FHTC/26 | 26/02/2022 | 0 | ROY CHOWDHURY ENTERPRISE | 0.54 | 0 | 0 | 0
6316 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 0 1 , Sangrampur (Part-B), Total House Hold 124 (Sl .No.- 9) | FHTC/26 | 26/02/2022 | 0 | BEAUTY CHATTERJEE | 1.38 | 0 | 0 | 0
6317 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 04 nos, (Ramdihi, Choto Kalajharia, Radharaman Pur, Barokalojuria, ), Total House Hold - 429." | 1378/BQA | 08/10/2020 | 30 | BISWARUP BOSE | 28.47 | 0 | 0 | 100
6318 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 01 nos, (Roybandh), Total House Hold - 168." | 1387/BQA | 09/10/2020 | 30 | PRANABANANDA TEWARI | 11.62 | 0 | 0 | 100
6319 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 02 nos, (Duyaranda, Kelebela), Total House Hold - 422." | 1377/BQA | 08/10/2020 | 30 | SOUMITRA BOSE | 27.89 | 0 | 0 | 100
6320 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 11 nos mouzas (Ramdihi, Roybandh, Tajaria , SM/06811 | Retrofitting | "Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 03 nos, (Gajariabari, Maslia, Chaitali), Total House Hold - 167." | 1386/BQA | 09/10/2020 | 30 | SHYAMAL KUMAR DAS | 11.58 | 0 | 0 | 100
6321 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ramchandrapur (5), Nutangar (34) & Junbakra(35) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas , SM/06792 | Retrofitting | Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection') in Ramchandrapur (5) & Nutangar (34) mouza by retrofitting zone - l piped water supply for Lakshmisagar & its adjoining mouzas at block - Simlapal dist. Bankura under Jal Swapan & Jal Jeevan Mission programme under Khatra Sub - Division of Bankura Division, PHE Dte. ( MB No - 3947) | FHTC/260 | 04/02/2021 | 0 | M/S TARUN KUMAR PATRA | 19.64 | 0 | 0 | 0
6322 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ramchandrapur (5), Nutangar (34) & Junbakra(35) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas , SM/06792 | Retrofitting | Work Order for Household survey in Ramchandrapur (5), Nutangar (34) & Junbakra (35) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 36) | 278/KSD | 10/12/2020 | 62 | M/S TARUN KUMAR PATRA | 0.31 | 0 | 0 | 0
6323 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ramchandrapur (5), Nutangar (34) & Junbakra(35) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas , SM/06792 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Junbakra (35) mouza by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 1423/BQA | 09/10/2020 | 30 | APEX ENTERPRISE | 34.84 | 0 | 0 | 0
6324 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ramchandrapur (5), Nutangar (34) & Junbakra(35) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas , SM/06792 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Ramchandrapur (5) & Nutangar (34) mouzas by retrofitting Zone-I of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 1422/BQA | 09/10/2020 | 30 | M/S TARUN KUMAR PATRA | 31.87 | 0 | 0 | 20
6325 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Andharthol, Sutijor, Shyam , SM/07326 | Retrofitting | Supplying, laying, fiting , fixing , and joining of UPVC pipes in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Andharthol Zone - V W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. block - Bankura - l Name of OHR - Andharthol, name of village - Andharthol (school more) |  | 22/07/2022 | 0 | TARINI CHARAN UPADHYAY | 4.21 | 0 | 0 | 0
6326 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Andharthol, Sutijor, Shyam , SM/07326 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No. of Mouza :- 06 nos, (Tantkanali, Salboni, Harialgora, Keshra, Jugsaha & Shitaldihi), Total House Hold - 2035 nos. | FHTC/4 | 04/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 63.56 | 0 | 0 | 0
6327 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Andharthol, Sutijor, Shyam , SM/07326 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Sonadaha (Zone - Q ) under Bankura l, ll & & Barjora block water supply scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. . Block - Bankura l, Name of OHR - Sonadaha (Zone - Q0 No.of Mouza :- 01 no, ( Bagatapal ) part - Total House Hold - 31 nos. | FHTC/30 | 30/03/2022 | 0 | PRADIP CHAKRABORTY | 2.61 | 0 | 0 | 0
6328 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Andharthol, Sutijor, Shyam , SM/07326 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Itamara (60), Jambeda (64), & Domohani (154) mouzas by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | FHTC/30 | 30/03/2022 | 0 | PRADIP CHAKRABORTY | 2.22 | 0 | 0 | 0
6329 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Andharthol, Sutijor, Shyam , SM/07326 | Retrofitting | Supplying, laying, fiting , fixing , and joining of UPVC pipes in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Andharthol Zone - V W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. block - Bankura - l Name of OHR - Andharthol, name of village - Andharthol (village) |  | 22/07/2022 | 0 | TARINI CHARAN UPADHYAY | 4.6 | 0 | 0 | 0
6330 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Andharthol, Sutijor, Shyam , SM/07326 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANDHARTHOL (Zone - V) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharsole, No.of Mouza :- 01 (Andharthol (PART) Total House Hold - 499 | FHTC/30 | 30/03/2022 | 0 | MUNMUN UPADHYAY | 35.35 | 0 | 0 | 0
6331 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Andharthol, Sutijor, Shyam , SM/07326 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANDHARTHOL (Zone - V) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharsole, No.of Mouza :- 01 (Andharthol (PART) Total House Hold - 499 | 618/BQA | 10/02/2021 | 30 | MUNMUN UPADHYAY | 35.35 | 0 | 0 | 100
6332 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos mousas (Andharthol, Sutijor, Shyam , SM/07326 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANDHARTHOL (Zone - V) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharsole, No.of Mouza :- 09 (Andharthol (PART) , Sutijor, Shyamdanga, Ramjibanpur, Sunukpahari, Jamboni, Dabar, Tariba teridi & Haru Malliker Bonkata) Total House Hold - 499 | 619/BQA | 10/02/2021 | 30 | MUNMUN UPADHYAY | 35.36 | 0 | 0 | 0
6333 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | 179/BQA | 18/01/2021 | 30 | SUBHANKAR BANERJEE | 10.47 | 0 | 0 | 0
6334 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) | 181/BQA | 18/01/2021 | 30 | SUBHANKAR BANERJEE | 10.39 | 0 | 0 | 0
6335 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 175/BQA | 18/01/2021 | 30 | SUBHANKAR BANERJEE | 16.09 | 0 | 0 | 0
6336 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Malian (23) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 10) | 117/KSD | 11/02/2021 | 20 | SUBHANKAR BANERJEE | 4.76 | 0 | 0 | 0
6337 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | 15/03/2021 | 0 | SUBHANKAR BANERJEE | 15.02 | 0 | 0 | 0
6338 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) |  | 15/03/2021 | 0 | SUBHANKAR BANERJEE | 9.49 | 0 | 0 | 0
6339 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) |  | 15/03/2021 | 0 | PRADIP CHAKRABORTY | 9.31 | 0 | 0 | 0
6340 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) |  | 15/03/2021 | 0 | SUBHANKAR BANERJEE | 9.65 | 0 | 0 | 0
6341 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) & Deuli (25) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 05) | 769/KSD | 25/11/2021 | 7 | SUBHANKAR BANERJEE | 4.9 | 0 | 0 | 0
6342 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Laying HDPE pipeline from Naba Chiyada village to Mukundapur Primary School and Dulalpur Primary School to increase pressure in Mukundapur (21) and Dulalpur (32) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-I (Hatikheda) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 919/BQA | 19/04/2022 | 30 | GON ASSOCIATES | 8 | 0 | 0 | 0
6343 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Work Order for Household survey in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 17) | 322/KSD | 29/12/2020 | 61 | SUBHANKAR BANERJEE | 0.4 | 0 | 0 | 0
6344 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Work Order for Laying HDPE pipeline to increase pressure in Malian (23) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 03) | 1282/BQA | 15/06/2022 | 10 | SUBHANKAR BANERJEE | 4.69 | 0 | 0 | 0
6345 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | laying extra UPVC pipe line to cover Lalbazar (24 ), mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting of water supply scheme for Belatikri zone - Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | FHTC/30 | 30/03/2022 | 0 | I.R.CONSTRUCTION | 2.85 | 0 | 0 | 0
6346 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lalbazar (24) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | FHTC/27 | 27/03/2022 | 0 | I.R.CONSTRUCTION | 4.78 | 0 | 0 | 0
6347 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lalbazar (24) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | 176/BQA | 18/01/2021 | 30 | I.R.CONSTRUCTION | 10.82 | 0 | 0 | 50
6348 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lalbazar (24) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) | 178/BQA | 18/01/2021 | 30 | I.R.CONSTRUCTION | 10.68 | 0 | 0 | 50
6349 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lalbazar (24) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) | 177/BQA | 18/01/2021 | 30 | I.R.CONSTRUCTION | 10.82 | 0 | 0 | 100
6350 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Malian (23) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 11) | 118/KSD | 11/02/2021 | 20 | SUBHANKAR BANERJEE | 4.05 | 0 | 0 | 0
6351 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malian (23) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 3086/BQA | 13/12/2021 | 30 | SUBHANKAR BANERJEE | 15.9 | 0 | 0 | 95
6352 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lalbazar (24) mouza by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 3180/BQA | 21/12/2021 | 30 | I.R.CONSTRUCTION | 18.4 | 0 | 0 | 95
6353 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Work Order for Laying HDPE pipeline to increase pressure in Malian (23) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 21) | 1300/BQA | 15/06/2022 | 10 | SUBHANKAR BANERJEE | 3.77 | 0 | 0 | 0
6354 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Work Order for Laying HDPE pipeline to increase pressure in Malian (23) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No. 24) | 1303/BQA | 15/06/2022 | 10 | SUBHANKAR BANERJEE | 3.06 | 0 | 0 | 0
6355 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 | FHTC/10 | 10/01/2023 | 0 | M/S TARUN KUMAR PATRA | 34.61 | 0 | 0 | 0
6356 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Malian (23), Lalbazar (24), Deuli (25) & Dulalpur (26) mouzas by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dis , SM/07334 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Damodarpur (122), Simla (123), Rangibari (125) & Gopi Sagar (235) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 199/BQA | 18/01/2021 | 30 | EARTHMOVING (INDIA) | 38.78 | 24.01 | 100 | 0
6357 | BANKURA | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Zone E of Aguribandh Punisole PWSS and Zone C of Puncha PWSS executed under BRGF in Onda Block of Bankura District , SM/08311 | Retrofitting | Household survey in Providing Functional House Hold Tap Connection (FHTC) to each and every household within command area of Zone- C of Puncha & Zone- E of Aguribandh Punisole PWSS executed under BRGF in Onda Block of Bankura District under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Name of Mouza For Zone- C of Puncha - ( Kushtara (94), Kelemele (95), Chhinpur (243), Barpetya (244), Malpur (245), Lapur (246), Bar Magura (247), Ram Sagar (248), Teghara (249), Sur Managar (250), Mathura (251), Radha Madhabpur (252), Dhulyapur (253) & Shinhati (254).No of House Hold - 2986 nos ). ( Name of Mouza For Zone -E of Aguribandh Punisole - Aguri Band Punisol (55). No of House Hold- 4107 nos.). Total No of House Hold = (2986 nos + 4107 nos )= 7093. Nos. | 107/BSD | 28/01/2022 | 59 | TAPAS DEY | 2.37 | 0 | 0 | 0
6358 | BANKURA | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Zone E of Aguribandh Punisole PWSS and Zone C of Puncha PWSS executed under BRGF in Onda Block of Bankura District , SM/08311 | Retrofitting | Material Requisition To Resource Division | 2036/BQA | 29/09/2022 | 0 | Resource Division | 0.04 | 0 | 0 | 0
6359 | BANKURA | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Zone E of Aguribandh Punisole PWSS and Zone C of Puncha PWSS executed under BRGF in Onda Block of Bankura District , SM/08311 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) to each and every household within command area of Zone -C of Puncha &Zone -E of Aguribandh Punisole PWSS executed under BRGF in Onda Block of Bankura District under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Name of Mouza For Zone -C of Puncha - ( Kushtara (94), Kelemele (95), Chhinpur (243), Barpetya (244), Malpur (245), Lapur (246), Bar Magura (247), Ram Sagar (248), Teghara (249), Sur Managar (250), Mathura (251), Radha Madhabpur (252), Dhulyapur (253) & Shinhati (254) .No of House Hold - 2986 nos ).( Name of Mouza For Zone -E of Aguribandh Punisole - Aguri Band Punisol (55) .No of House Hold - 4107 nos.). Total No of House Hold = ( 2986 nos +4107 nos ) =7093. Nos | 1083/BQA | 12/05/2022 | 1389 | M/S TARUN KUMAR PATRA | 216.67 | 0 | 0 | 76
6360 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE - I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone - I, Name of Mouza:- 01 no., (Harakabad), Total House Hold - 174 nos. | 2835/BQA | 16/11/2021 | 30 | RAHUL CHATERJEE | 6.51 | 0 | 0 | 0
6361 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE - I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma zone -I, Name of Mouza:-- 2 no., (Barasali, Kukirakur), Total House Hold - 332 nos. | 2831/BQA | 16/11/2021 | 30 | TAPAS KUMBHAKAR | 16.02 | 0 | 0 | 0
6362 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma zone -II, Name of Mouza:-- 1 no., (Kamalhir), Total House Hold - 344 nos. | 2800/BQA | 11/11/2021 | 30 | JAGADISH BANERJEE | 16.69 | 0 | 0 | 0
6363 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -II, Name of Mouza:-- 2 no., (Bakulia, Saheb danga), Total House Hold - 255 nos. | 2801/BQA | 11/11/2021 | 30 | ACHARJEE & SON | 12.25 | 0 | 0 | 0
6364 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -II, Name of Mouza:-- 1 no., (Dahuka), Total House Hold - 277 nos. | 2802/BQA | 11/11/2021 | 30 | GOURANGA CHATTERJEE | 13.68 | 0 | 0 | 0
6365 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -II, Name of Mouza:-- 3 nos, (Bhuban Bandi, Swattwakuri, Saltura), Total House Hold - 273 nos. | 2803/BQA | 11/11/2021 | 30 | GOUTAM GHOSH | 13.5 | 0 | 0 | 0
6366 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone - I, Name of Mouza:-- 2 no., (Bhangucha , Illambajar), Total House Hold - 264 nos. | 2804/BQA | 11/11/2021 | 30 | PARESH CHANDRA LAYEK | 12.67 | 0 | 0 | 0
6367 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -I, Name of Mouza:-- 03 nos, (Chandbad, Chaukhuri, Singhir), Total House Hold - 257 nos. | 2832/BQA | 16/11/2021 | 30 | GANGADHAR MONDAL | 12.17 | 0 | 0 | 0
6368 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -I, Name of Mouza:-- 02 no., (Kechka, Chuaberia), Total House Hold - 483 nos. | 2833/BQA | 16/11/2021 | 30 | SRIKANTA MONDAL | 22.08 | 0 | 0 | 0
6369 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -I, Name of Mouza:-- 1 no., (Beltikri), Total House Hold - 242 nos. | 2830/BQA | 16/11/2021 | 30 | M/S SUPRIYA CHATTERJEE | 11.6 | 0 | 0 | 0
6370 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -(II), Name of Mouza:-- 1 no., (Salma), Total House Hold - 881 nos. | 2799/BQA | 11/11/2021 | 30 | DAUD ALI KHAN | 38.77 | 0 | 0 | 0
6371 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying extra UPVC Pipe Line to Cover (Bhuban Bandi, Swattwakuri, Saltura), mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 252/BSD | 15/03/2022 | 10 | GOUTAM GHOSH | 2.34 | 0 | 0 | 0
6372 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Water supply arrangement at different school of Salma & Cleaning of Chokage Existing pipelinefrom Kastora Bouripara to Muslimpara & Bhangucha to Beltukri of Salma (Zone I & III) under Salma W/S Scheme of Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | 810/BSD | 06/08/2021 | 10 | TAPAN KUMAR MANDAL | 2.94 | 0 | 0 | 0
6373 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying of extra UPVC pipe from Bhaghucha to Chuaberia to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 541/BSD | 28/07/2022 | 30 | TAPAN KUMAR MANDAL | 4.49 | 0 | 0 | 0
6374 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying extra UPVC Pipe Line to Cover Majit mouza and dismantling, reconstruction of concrete for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 560/BSD | 29/07/2022 | 21 | MD. AFSAR ALI | 3.57 | 0 | 0 | 0
6375 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - II) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - II), No. of Mouza :- 01 no., Salma (Part), Habitation- Dahuka, Gopalnagar, Total House Hold- 43 nos. | 222/BSD | 11/03/2022 | 10 | DAUD ALI KHAN | 3.88 | 0 | 0 | 0
6376 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - I) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - I), No. of Mouza :- 01 no., (Kukrakuli), Total House Hold- 67 nos. | 218/BSD | 11/03/2022 | 10 | TAPAS KUMBHAKAR | 3.8 | 0 | 0 | 0
6377 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone - II) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - II), No. of Mouza :- 01 no., Salma (Part), Habitation- Gobindpur, Total House Hold- 98 nos. | 223/BSD | 11/03/2022 | 10 | SAMIRUDDIN KHAN | 4.98 | 0 | 0 | 0
6378 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - I) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - I), No. of Mouza :- 01 no., (Beltukri), Total House Hold- 23 nos. | 224/BSD | 11/03/2022 | 10 | M/S SUPRIYA CHATTERJEE | 4.57 | 0 | 0 | 0
6379 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying extra UPVC Pipe Line to Cover Bakulia & Sahebdanga mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE - II W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 234/BSD | 15/03/2022 | 10 | ACHARJEE & SON | 3.32 | 0 | 0 | 0
6380 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying extra UPVC /HDPE Pipe Line to cover Dahuka village interconnection with house connection pipe & Dismantling, reconstruction of concrete for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 562/ BSD | 29/07/2022 | 21 | DAUD ALI KHAN | 0.71 | 0 | 0 | 0
6381 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying Extra HDPE Pipe Line to Cover Gobindpur mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA (ZONE - II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | 164/BSD | 16/02/2022 | 10 | DAUD ALI KHAN | 2.6 | 0 | 0 | 0
6382 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying extra UPVC Pipe Line to Cover , (Bhangucha , Illambajar), mouza & Dismantling & reconstruction of concrete for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-I W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte . | 279/BSD | 17/03/2022 | 10 | PARESH CHANDRA LAYEK | 4.32 | 0 | 0 | 0
6383 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying extra HDPE Pipe Line from OHR Zone II to Dahuka village to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 561/ BSD | 29/07/2022 | 21 | DAUD ALI KHAN | 4.92 | 0 | 0 | 0
6384 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying of 15 mm NB PVC (schedule 80) /20 mm OD HDPE (PE100, Pn16) to Cover Salma mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA (ZONE - II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | 281/BSD | 17/03/2022 | 10 | DAUD ALI KHAN | 1.58 | 0 | 0 | 0
6385 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying extra HDPE Pipe Line to Cover Gobindpur mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone - II) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 19 | FHTC/27 | 27/09/2022 | 0 | DAUD ALI KHAN | 1.72 | 0 | 0 | 0
6386 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying extra UPVC pipeline to cover Kechka & Chuaberia mouzas for retrofitting works 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I ) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | FHTC/14 | 14/07/2022 | 0 | SRIKANTA MONDAL | 3.81 | 0 | 0 | 0
6387 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -II, Name of Mouza:-- 2 no., (Bakulia, Saheb danga), Total House Hold - 255 nos | FHTC/12 | 12/08/2022 | 0 | ACHARJEE & SON | 12.25 | 0 | 0 | 0
6388 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying extra UPVC pipe lineto cover Beltikri mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma zone - l water supply scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | FHTC/23 | 23/03/2022 | 0 | M/S SUPRIYA CHATTERJEE | 2.98 | 0 | 0 | 0
6389 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | laying extra UPVC pipe line to cover Horakabaid mouzas Retrofitting works for creation 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Salma Zone - l under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | FHTC/30 | 30/03/2022 | 0 | RAHUL CHATERJEE | 2.52 | 0 | 0 | 0
6390 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01 ( Ratganj Madhav pur ), Total House Hold -154 | FHTC/26 | 26/02/2022 | 0 | RUFIKUL MONDAL | 10.75 | 0 | 0 | 0
6391 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | laying extra HDPE pipe line to cover Gopalnagar mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma zone - ll water supply scheme under Bankura sadar sub - Division of Bankura Division, PHE Dte. | FHTC/26 | 26/03/2022 | 0 | DAUD ALI KHAN | 4.07 | 0 | 0 | 0
6392 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | laying extra UPVC pipe line to cover Kamalhit mouzas Construction and commissioning of of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma zone - ll W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | FHTC/30 | 30/03/2022 | 0 | SOMA BANERJEE | 4.51 | 0 | 0 | 0
6393 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying extra UPVC pipe to cover Bhuban Bandi, Swattwakuri mouza for retrofitting works for creation of FHTC in connection with Jal Jeevan Mission Programme and Jal Swapna of Salma Zone -II W/S Scheme |  | 18/07/2022 | 0 | GOUTAM GHOSH | 2.29 | 0 | 0 | 0
6394 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Harakabad of pipe water supply scheme for SALMA & adjoining mouzas (Zone I & II) under Bankura Sadar Sub - Division of Ba | FHTC/15 | 15/09/2022 | 0 | RAHUL CHATERJEE | 2.05 | 0 | 0 | 0
6395 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying extra UPVC pipe lineto cover Chandbad , Chaukhuri, Singhir Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA Salma (Zone - l ) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. . | FHTC/26 | 26/03/2022 | 0 | GANGADHAR MONDAL | 0.74 | 0 | 0 | 0
6396 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | laying extra HDPE pipe line to cover Gopalnagar mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma zone - ll water supply scheme under Bankura sadar sub - Division of Bankura Division, PHE Dte. | FHTC/26 | 26/03/2022 | 0 | DAUD ALI KHAN | 4.74 | 0 | 0 | 0
6397 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | SURVEY WORK of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of EKTESWAR (Zone - I) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - NOT Name of Mouza:-- Ekteswar (Part) & Sankardihi, Total House Hold - 452 nos. | FHTC/12 | 12/04/2022 | 0 | TAPAS DEY | 0.15 | 0 | 0 | 0
6398 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | FHTC/26 | 26/02/2022 | 0 | PARAMESWAR CHOWDHURY | 47.88 | 0 | 0 | 0
6399 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 02 ( Bahadur pur , Oltara(PART-A), Total House Hold -141 | FHTC/26 | 26/02/2022 | 0 | RUFIKUL MONDAL | 9.81 | 0 | 0 | 0
6400 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Survey work for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme for SALMA & adjoining mouzas (Zone I & II) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma zone -II, Name of Mouza:-- 20 nos, (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, Swattwakuri, Harakabad Kukirakuri, Chandbad Chaukhuri, Singhir, Majit, Bhanguch , Illambajar, Barasal, Kechka, Chuaberia, Beltikri), Total House Hold - 3957 nos. | FHTC/12 | 12/04/2022 | 0 | TAPAS DEY | 1.13 | 0 | 0 | 0
6401 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone - II) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - II), No. of Mouza :- 01 no., Salma (Part), Habitation- Gobindpur, Total House Hold- 98 nos. | FHTC/27 | 27/09/2022 | 0 | SAMIRUDDIN KHAN | 4.97 | 0 | 0 | 0
6402 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - II) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - II), No. of Mouza :- 02 no., (Bakulia & Sahebdanga) Total House Hold- 70 nos. | 253/BSD | 15/03/2022 | 10 | BASUDEB ACHARJEE | 4.96 | 0 | 0 | 0
6403 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone - I) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - I), No. of Mouza :- 01 no., (Beltukri), Total House Hold- 23 nos. | 224/BSD | 11/03/2022 | 10 | M/S SUPRIYA CHATTERJEE | 4.57 | 0 | 0 | 0
6404 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying HDPE Pipe Line from Durlavpur air valve to Durlavpur Muslim para for increase water pressure at Swattkuri, Kamalhir, Durlavpu for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone- I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 566/BSD | 29/07/2022 | 21 | JAGADISH BANERJEE | 3.35 | 0 | 0 | 0
6405 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone - I, Name of Mouza:-- 02 no., Majit ( Part), Singhir (Part), Total House Hold - 20 nos. | 462/BSD | 06/06/2022 | 10 | MD. AFSAR ALI | 1.66 | 0 | 0 | 0
6406 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying extra UPVC Pipe Line to Dahuka village of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE- II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 458/BSD | 06/06/2022 | 15 | GOURANGA CHATTERJEE | 3.75 | 0 | 0 | 0
6407 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying extra UPVC pipe line & extra 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, Pn16) pipe to Cover Kendana mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 273/BSD | 17/03/2022 | 10 | SK. SAHAJAHAN | 3.63 | 0 | 0 | 0
6408 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Dismantaling & reconstruction of Kastora, Singhir & Majit mouza & Cleaning Wasing the pipeline from Bhaghucha to kechka for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-I W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 543/BSD | 28/07/2022 | 30 | TAPAN KUMAR MANDAL | 4.14 | 0 | 0 | 0
6409 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Restoration & renovation 100 mm dia connecting line carrying structure including all related works & Clearing the chokage of upvc line Durlavpur to Bhubanbadhi, interconnection with BRGF Line for W/S arrangement at Salma Zone- III including contruction of valve chamber at Salma zone-II Water Supply Scheme under Bankura Sadar Sub-Division, of Bankura Division, P.H.E. Dte. | 469/BSD | 06/06/2022 | 15 | DAUD ALI KHAN | 4.95 | 0 | 0 | 0
6410 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone - I, Name of Mouza:-- 01 no., (Majit), Total House Hold - 175 nos. | 2834/BQA | 16/11/2021 | 30 | MD. AFSAR ALI | 7.96 | 0 | 0 | 0
6411 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying of extra UPVC pipe from Bhaghucha to Chuaberia to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | FHTC/19 | 19/01/2023 | 0 | TAPAN KUMAR MANDAL | 4.49 | 0 | 0 | 0
6412 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, , SM/09316 | Retrofitting | Laying of extra UPVC pipeline from OHR Zone- III to Kendana village to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | FHTC/19 | 19/01/2023 | 0 | TAPAN KUMAR MANDAL | 4.68 | 0 | 0 | 0
6413 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas, (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IV) Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE- IV), No. of Mouza :- 03 nos, (Sahorjora, Namobandh Sitarampur, Muktatore), Total House Hold -1096 nos | 2793/BQA | 11/11/2021 | 30 | APEX ENTERPRISE | 63.39 | 0 | 0 | 0
6414 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos Mouzas, (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IV) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-IV), No.of Mouza :- 03 nos, (Dejuri, Asuria Madhabpur, Deucha), Total House Hold - 594 nos. | 2990/BQA | 25/11/2021 | 30 | GOUTAM BHATTACHRYYA | 34.31 | 0 | 0 | 0
6415 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Supply of VALVE including loading, unloading, stacking etc. all comlete for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas Sahorjora ,Dejuri, Asuria Madhabpur , Namobandh Sitarampur,Muktatore , Deucha) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IV) | 346/BSD | 12/04/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.95 | 0 | 0 | 0
6416 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kalipur (Zone- C) under Chatna Block of Saltora - Chatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Kalipur (Zone - C) . No.of Mouza :- 03 ( Nangla, Gidhuria, Majdihi) Total House Hold -436 | FHTC/24 | 24/02/2022 | 0 | GOUTAM BHATTACHRYYA | 14.34 | 0 | 0 | 0
6417 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 nos Sonareka (Part), Total House Hold- 70 (Sl No of Work- 10) | FHTC/24 | 24/02/2022 | 0 | MANOJ GHOSAL | 0.2 | 0 | 0 | 0
6418 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Baranimdiha (13) and Rajabandh (15) mouzas under Parsola, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | FHTC/24 | 24/02/2022 | 0 | GANGADHAR MONDAL | 10.83 | 0 | 0 | 0
6419 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Laying extra UPVC pipe line to cover in Kayerpara (206), Harinarayanpur (207), and Ganganala (230) mouzas Construction and commissioning of FHTC (Functional Household Tap Connection) by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | FHTC/24 | 24/02/2022 | 0 | TARINI CHARAN UPADHYAY | 4.98 | 0 | 0 | 0
6420 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jamrepara (295) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 1 No. Total Household:- 285 Nos. | FHTC/24 | 24/02/2022 | 0 | ASHIS PAL | 10.97 | 0 | 0 | 0
6421 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 , Jagannath pur (Part- C), Total House Hold -106 | FHTC/24 | 24/02/2022 | 0 | GOURANGA NANDI | 0.77 | 0 | 0 | 0
6422 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Extra UPVC pipe line from Soragara Village to Enayetpur village of retrofitting work for creation of FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GODARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block- Barjora, Name of OHR:- GODARDIHI (Zone - E), Name of Mouza:- Enayetpur. | FHTC/24 | 24/02/2022 | 0 | SUBHANKAR BANERJEE | 4.32 | 0 | 0 | 0
6423 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Kadakuli Roy Para, Total House Hold -75 | FHTC/24 | 24/02/2022 | 0 | SANJOY MONDAL | 0.23 | 0 | 0 | 0
6424 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IV) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-IV). No.of Mouza :- 06 nos, (Sahorjora , Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha), Total House Hold - 1690 nos. | FHTC/12 | 12/04/2022 | 0 | TAPAS DEY | 0.56 | 0 | 0 | 0
6425 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Lobason Bauri Para, Chandar Shib mondir Namo Para & Brimhon para Total House Hold -50. | FHTC/24 | 24/02/2022 | 0 | M/S PAUL BROTHERS | 0.36 | 0 | 0 | 0
6426 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II and Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 2 (Jharia ,Kalla ), Total House Hold - 133 | FHTC/24 | 24/02/2022 | 0 | TAPAS PAL | 0.9 | 0 | 0 | 0
6427 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :-01 (Talanjuri (PART-A) Total House Hold -114 | FHTC/24 | 24/02/2022 | 0 | JAGADISH BANERJEE | 2.99 | 0 | 0 | 0
6428 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 01 ,Jagannath pur (Part- B), Total House Hold -107 | FHTC/24 | 24/02/2022 | 0 | GOURANGA NANDI | 0.85 | 0 | 0 | 0
6429 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Baragram (86) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 4) | FHTC/24 | 24/02/2022 | 0 | DAUD ALI KHAN | 3.51 | 0 | 0 | 0
6430 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 03(Enayetpur , Namoghansara , Ekariya ), Total House Hold - 204 | FHTC/24 | 24/02/2022 | 0 | AJIT KUMAR PAUL | 1.39 | 0 | 0 | 0
6431 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha) of BARJORA Water S , SM/09329 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- 02 nos (Pinguri (Part-C) &Tentuldoha ), Total House Hold -249 | FHTC/24 | 24/02/2022 | 0 | BEAUTY CHATTERJEE | 1.32 | 0 | 0 | 0
6432 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas by , SM/09235 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 2768/BQA | 08/11/2021 | 30 | UNIVERSAL CONSTRUCTION | 42.15 | 0 | 0 | 0
6433 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas by , SM/09235 | Retrofitting | Household survey in Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | FHTC/6 | 06/06/2022 | 0 | TAPAS DEY | 0.29 | 0 | 0 | 0
6434 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas by , SM/09235 | Retrofitting | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Patrasayer Sub-District Water Testing Laboratory under Bankura Division, PHE Dte. Sl no.- 05 | FHTC/15 | 15/02/2022 | 0 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 4.83 | 0 | 0 | 0
6435 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas by , SM/09235 | Retrofitting | laying extra UPVC pipe line to cover Kadamahara (54 ), Mayna (55) ,Gobindapur Damdi (56) Sirsa ( 131) & Baramaliara (132) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting of water supply scheme for Belatikri zone - B and its adjoning mouzas under Sarenga Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division | FHTC/30 | 30/03/2022 | 0 | UNIVERSAL CONSTRUCTION | 2.9 | 0 | 0 | 0
6436 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas by , SM/09235 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-L (Dhankura) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-L (Dhankura) :- Ghagra (115), Garra (116), Bauripal (156), Kalabani (157), Katro (158), Huang Khana (160), Punshya (161), Sindriam (162), Kankri Jharna (172), Khejur Khanma (173), Chalkigara (174), Dhoba Kacha (175), Madankata (176), Dangarda (177), Jantadumur (178), Barikul (179) & Lep-Am (180)Total Mouza:- 17 Nos. Total Household - 2137 Nos. |  | 16/03/2022 | 0 | ALOK ENTERPRISE | 59.06 | 0 | 0 | 0
6437 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas by , SM/09235 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | FHTC/4 | 04/03/2022 | 0 | SOUMITRA BHATTACHARYA | 43.3 | 0 | 0 | 0
6438 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Tapta (52), Banshkhopa (53), Kadamdahara (54), Mayna (55), Gobindapur Damdi (56), Beoncha (115), Beliakala (116), Kherurabad (130), Sirsa (131) & Baramaliara (132) mouzas by , SM/09235 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No. of Mouza :- 06 nos, (Tantkanali, Salboni, Harialgora, Keshra, Jugsaha & Shitaldihi), Total House Hold - 2035 nos. | FHTC/4 | 04/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 63.56 | 0 | 0 | 0
6439 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Gholgora, Teghori, Bagjuri, Dardali, Kendsaer, Naise, Naoadihi) , SM/09630 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Bloc k of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Lakshmanpur, No. of Mouza :- 7 nos, (Gholgora, Teghori, Bagjuri, Dardali, Kendsaer, Bansura, Naoadihi) Total House Hold - 1960 nos. | 3360/BQA | 31/12/2021 | 60 | PARAMESWAR CHOWDHURY | 90.29 | 0 | 0 | 0
6440 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Gholgora, Teghori, Bagjuri, Dardali, Kendsaer, Naise, Naoadihi) , SM/09630 | Retrofitting | Laying Extra HDPE Pipe Line to Cover Gholgora, Naoadihi mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | 341/KSD | 16/08/2022 | 20 | PARAMESWAR CHOWDHURY | 3.97 | 0 | 0 | 0
6441 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Gholgora, Teghori, Bagjuri, Dardali, Kendsaer, Naise, Naoadihi) , SM/09630 | Retrofitting | Construction of S.S.P including laying of P.V.C extension pipe Line at Tegori Hari Mandir to Namapara & Golgora Bouripara of Chhatna block under Saltora -Chhatna W/S Scheme under BQA (HQ) of Bankura Division P.H.E. Dte. | 691/BSD | 11/06/2021 | 15 | SIB SANKAR CHOWDHURY | 4.91 | 0 | 0 | 0
6442 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Gholgora, Teghori, Bagjuri, Dardali, Kendsaer, Naise, Naoadihi) , SM/09630 | Retrofitting | Survey work for Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Block Saltora- Chhatn W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Lakshmanpur, No.of Mouza :- 07 nos, (Gholgora, Teghori, Bagjuri,Dardali, Kendsaer, Niasa Naoadihi), Total House Hold - 1960 nos. | 74/BSD | 14/01/2022 | 90 | TAPAS DEY | 0.65 | 0 | 0 | 99
6443 | BANKURA | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Gholgora, Teghori, Bagjuri, Dardali, Kendsaer, Naise, Naoadihi) , SM/09630 | Retrofitting | Laying of HDPE Pipe Line from Jagannath more to Tegori & Bankura-Purulia main road (NH-60) to Gholgora to increase water pressure at Gholgora, Teghori mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) of Chhatna Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 1338/BQA | 01/06/2023 | 670 | SUNIL KUMAR MANDAL | 8.49 | 0 | 0 | 5
6444 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Betanal Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mangalpur, No. of Mouza :- 12 nos. i.e. Jashdighi-96, Behar-103, Parikkhapara-104, Maheshpur-105, Bagajal-106, Bhurbandi-107, Gowalapuskarini-108, Mangalpur-109 & Jadupur-110, Betanal-111, Kishorekona-115 & Baktarpur-116, Total House Hold - 3399 | 1175/BQA | 25/05/2022 | 60 | KHAN ENTERPRISE | 316.87 | 0 | 0 | 0
6445 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. for 12 (twelve) months from 01.02.2021 to 31.01.2022. | 44/VSD | 29/01/2021 | 365 | SWAPAN KUMAR BIT | 1.73 | 0 | 0 | 0
6446 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 30/11/2022 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | 300/A/VSD | 28/10/2022 | 31 | TAPAN KUMAR UPADHYAY | 0.23 | 0 | 0 | 0
6447 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/12/2022 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | 317/A/VSD | 29/11/2022 | 30 | TAPAN KUMAR UPADHYAY | 0.23 | 0 | 0 | 0
6448 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/01/2023 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | 363/VSD | 28/12/2022 | 31 | TAPAN KUMAR UPADHYAY | 0.25 | 0 | 0 | 0
6449 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Continuation of Hiring vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. for 06 (six) months from 01.08.2022 to 31.01.2023. | 237/VSD | 26/07/2022 | 184 | SWAPAN KUMAR BIT | 0.86 | 0 | 0 | 35
6450 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/05/2023 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | 82VSD | 28/04/2023 | 22 | TAPAN KUMAR UPADHYAY | 0.33 | 0 | 0 | 20
6451 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 30/04/2023 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | 63VSD | 27/03/2023 | 19 | TAPAN KUMAR UPADHYAY | 0.25 | 0 | 0 | 20
6452 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Carriage of Departmental Materials i.e. FERRULE, CHOLORINE etc. In connection with Jal Jeevan Mission & JAL SWAPNA Under Bishnupur Sub-Division under Bankura Division, P.H.E. Dte. | 437/VSD | 08/10/2021 | 180 | TAPAS KUMAR HAZRA | 3.2 | 0 | 0 | 100
6453 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 30/09/2022 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | 260A/VSD | 28/08/2022 | 31 | AJIT KUMAR DUTTA | 0.09 | 0 | 0 | 25
6454 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 30/04/2022 for supervision of work related to land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division | 82A/VSD | 31/03/2022 | 30 | SWAPAN KUMAR BIT | 0.11 | 0 | 0 | 20
6455 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/05/2023 for supervision of work releted to land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division | 121VSD | 28/04/2022 | 30 | SWAPAN KUMAR BIT | 0.11 | 0 | 0 | 20
6456 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/10/2022 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | 281A/VSD | 27/09/2022 | 30 | AJIT KUMAR DUTTA | 0.09 | 0 | 0 | 20
6457 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/07/2022 for supervision of work related to land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | 181VSD | 30/06/2022 | 31 | SWAPAN KUMAR BIT | 0.1 | 0 | 0 | 20
6458 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 30/06/2022 for supervision of work releted to land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | 160VSD | 30/05/2022 | 31 | SWAPAN KUMAR BIT | 0.1 | 0 | 0 | 20
6459 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/03/2022 for supervision of work related to land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | 54VSD | 28/02/2022 | 31 | SWAPAN KUMAR BIT | 0.09 | 0 | 0 | 20
6460 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/08/2022 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | 230VSD | 26/07/2022 | 31 | AJIT KUMAR DUTTA | 0.09 | 0 | 0 | 20
6461 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Extra Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)'at different school, ICDS, health centre and House Holds in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Betanal zone - A and Kushmuri zone -A (BRGF ph- I) W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. | 113/VSD | 19/04/2022 | 21 | MANORANJAN GHOSH | 4.84 | 0 | 0 | 0
6462 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Submission of bill from 01.06.23 to 31.08.23 with running details regarding hiring of additional vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E Dte. | FHTC/11 | 29/11/2023 | 0 | TAPAN KUMAR UPADHYAY | 1.01 | 0 | 0 | 0
6463 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Continuation of Hiring vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. for 06 (six) months from 01.02.2023 to 31.07.2023. | 11/VSD | 30/01/2023 | 181 | SWAPAN KUMAR BIT | 0.86 | 0 | 0 | 100
6464 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring of additional vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. for 06 (six) months from 01.06.2023 to 30.11.2023 | 134VSD | 30/05/2023 | 184 | TAPAN KUMAR UPADHYAY | 0.86 | 0 | 0 | 25
6465 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring of vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division, PHE Dte. for the period from 01/08/2023 to 31/01/2024. (Sl. No.: 01) | 226/VSD | 01/08/2023 | 156 | SWAPAN KUMAR BIT | 0.75 | 0 | 0 | 40
6466 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Continuation of Hiring of addtional vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. for 02 (two) months from 01.12.2023 to 31.01.2024. | 363/A/VSD | 29/11/2023 | 61 | TAPAN KUMAR UPADHYAY | 0.29 | 0 | 0 | 40
6467 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. from 01.02.2024 to 31.07.2024. | 37/VSD | 31/01/2024 | 182 | SWAPAN KUMAR BIT | 0.75 | 0 | 0 | 0
6468 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required from 01/08/2024 to 31/08/2024 for supervision of all works of water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM project within Bishnupur Sub-Division of Bankura Division PHE Dte. | 412/VSD | 19/07/2024 | 30 | KHUR SHID ALAM KHAN | 0.1 | 0 | 0 | 0
6469 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required from 01/04/2024 to 30/04/2024 for supervision of all works of potable water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJMP project within Bishnupur Sub-Division of Bankura Division. | 114/A/VSD | 15/03/2024 | 31 | KHUR SHID ALAM KHAN | 0.09 | 0 | 0 | 0
6470 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/03/2024 for supervision of all works of potable water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM Project within Bishnupur Sub-Division of Bankura Division P.H.E. Dte. | 86/VSD | 01/03/2024 | 31 | KHUR SHID ALAM KHAN | 0.09 | 0 | 0 | 0
6471 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required from 01/09/2024 to 30/09/2024 for supervision of all works of water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM project within Bishnupur Sub-Division of Bankura Division, PHE Dte. | 472/VSD | 21/08/2024 | 30 | KHUR SHID ALAM KHAN | 0.1 | 0 | 0 | 0
6472 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring of addtional vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. from 01.02.2024 to 31.07.2024 | 38/VSD | 30/01/2024 | 182 | TAPAN KUMAR UPADHYAY | 0.75 | 0 | 0 | 0
6473 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 29/02/2024 for supervision of all works of potable water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM Project within Bishnupur Sub-Division of Bankura Division. | 40/VSD | 02/02/2024 | 29 | KHUR SHID ALAM KHAN | 0.1 | 0 | 0 | 0
6474 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/01/2024 for supervision of all works of potable water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM Project within Bishnupur Sub-Division of Bankura Division. | 03/VSD | 03/01/2024 | 31 | KHUR SHID ALAM KHAN | 0.1 | 0 | 0 | 0
6475 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring of additional vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. for 06 (six) months from 01.06.2023 to 30.11.2023 | FHTC/02 | 29/02/2024 | 0 | TAPAN KUMAR UPADHYAY | 1.1 | 0 | 0 | 0
6476 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring of vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. from 01.08.2024 to 31.01.2025. | 432/VSD | 31/07/2024 | 184 | SWAPAN KUMAR BIT | 0.88 | 0 | 0 | 0
6477 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required from 01/12/2024 to 31/12/2024 for supervision of all works of water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM project within Bishnupur Sub-Division of Bankura Division, PHE Dte. | 776/VSD | 30/11/2024 | 31 | KHUR SHID ALAM KHAN | 0.1 | 0 | 0 | 0
6478 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required from 01/10/2024 to 31/10/2024 for supervision of all works of water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM project within Bishnupur Sub-Division of Bankura Division, PHE Dte. | 626/VSD | 30/09/2024 | 31 | KHUR SHID ALAM KHAN | 0.1 | 0 | 0 | 0
6479 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required from 01/01/2025 to 31/01/2025 for supervision of all works of water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM project within Bishnupur Sub-Division of Bankura Division, PHE Dte. | 857/VSD | 30/12/2024 | 31 | KHUR SHID ALAM KHAN | 0.1 | 0 | 0 | 0
6480 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring of additional vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. from 01.08.2024 to 31.01.2025. | 431/VSD | 31/07/2024 | 184 | TAPAN KUMAR UPADHYAY | 0.88 | 0 | 0 | 0
6481 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required from 01/11/2024 to 30/11/2024 for supervision of all works of water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM project within Bishnupur Sub-Division of Bankura Division, PHE Dte. | 655/VSD | 28/10/2024 | 31 | KHUR SHID ALAM KHAN | 0.1 | 0 | 0 | 0
6482 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring of additional vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. from 01.02.2025 to 31.07.2025. | 91/VSD | 29/01/2025 | 181 | TAPAN KUMAR UPADHYAY | 0.87 | 0 | 0 | 0
6483 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Hiring of vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. from 01.02.2025 to 31.07.2025. | 90/VSD | 29/01/2025 | 181 | SWAPAN KUMAR BIT | 0.87 | 0 | 0 | 0
6484 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required from 01/04/2025 to 30/04/2025 for supervision of all works of water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM project within Bishnupur Sub-Division of Bankura Division, PHE Dte. | 164/A/VSD | 25/03/2025 | 31 | KHUR SHID ALAM KHAN | 0.1 | 0 | 0 | 0
6485 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Betanal Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 12 nos. mouzas (Jashdighi-96, Behar-103, Parikkhapara-104, , SM/09631 | Retrofitting | Work order for hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required from 01/05/2025 to 31/05/2025 for supervision of all works of water supply schemes including BRGF schemes, augmentation schemes, new schemes & single village water supply schemes running under JJM project within Bishnupur Sub-Division of Bankura Division, PHE Dte. | 175/A/VSD | 23/04/2025 | 30 | KHUR SHID ALAM KHAN | 0.1 | 0 | 0 | 0
6486 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos. mouzas (Dhabani-136, Chitrang-137, Baliguma-1 , SM/09637 | Retrofitting | Retrofitting works for creation of 'FHTC (FunCtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Sashpur Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Dangalan, No. of Mouza :- 09 nos. i.e. Banki-85, Chotogobindapur-86, Adilpur-87 & Haldi-83, Mandra-88, Berghosh-84, Dangalan-91, Musarbar-92 & Ashwinpur-93, Total House Hold - 2639 | FHTC/29 | 29/09/2022 | 0 | J. D. J. ENTERPRISE | 77 | 0 | 0 | 0
6487 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos. mouzas (Dhabani-136, Chitrang-137, Baliguma-1 , SM/09637 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuporsol Zone- A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Majuria, No. of Mouza :- 08 nos. i.e. Dhabani- 136, Chitrang-137,Baliguma-138, Indkuri-139,Taldangra-140,Domberya-141,Majdiha-142 and Hetagara-143 Total house hold - 799 ( Out of 949) | 3029/BQA | 29/11/2021 | 30 | SUMITA UPADHYAY | 61.96 | 0 | 0 | 0
6488 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Murakata Ghosh Para, Total House Hold -75 | 562/ BSD | 13/11/2020 | 21 | SOMA BANERJEE | 4.81 | 0 | 0 | 0
6489 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Lobason Bauri Para, Total House Hold -76 | 558/ BSD | 13/11/2020 | 21 | TAPAS PAL | 4.85 | 0 | 0 | 0
6490 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- Murakata Roy Para, Total House Hold -75 | 561/ BSD | 13/11/2020 | 21 | ASHIS PAL | 4.8 | 0 | 0 | 0
6491 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Murakata ,Chandar Durgamondir para (part), Total House Hold -45. | 13/BSD | 06/01/2021 | 21 | JAGADISH BANERJEE | 4.73 | 0 | 0 | 0
6492 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Lobason Bauri Para, Chandar Shib mondir Namo Para & Brimhon para Total House Hold -50. | 26/BSD | 06/01/2021 | 21 | M/S PAUL BROTHERS | 4.7 | 0 | 0 | 0
6493 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- ChandarBardgan Para (Part- A), Total House Hold -50. | 27/BSD | 06/01/2021 | 21 | MAYA CONSTRUCTION | 4.44 | 0 | 0 | 0
6494 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Chandar Bardgan Para (Part- B), Total House Hold - 50. | 14/BSD | 06/01/2021 | 21 | TAPAN KUMAR UPADHYAY | 4.48 | 0 | 0 | 0
6495 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- By pass Pipe line Kadakuli more to Chandar main Bazar, Gosh para ,Chandar maibazar Total House Hold -20 | 28 / BSD | 06/01/2021 | 21 | BIDHAN BANERJEE | 4.84 | 0 | 0 | 0
6496 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , G.P -Chandar , Name of Village Kadakuli Man Para, Total House Hold -70 | 556/ BSD | 13/11/2020 | 21 | GON ASSOCIATES | 4.59 | 0 | 0 | 0
6497 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Kadakuli Roy Para, Total House Hold -75 | 557/ BSD | 13/11/2020 | 21 | SANJOY MONDAL | 4.82 | 0 | 0 | 0
6498 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P- Chandar, Name of Village-Lobason Roy Para, Total House Hold -73 | 559/ BSD | 13/11/2020 | 21 | M/S BANERJEE & BANERJEE | 4.71 | 0 | 0 | 0
6499 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- By pass Pipe line Chandar main Bazar to Chandar gram end & Baroma kali than (Chomatha), Bramhon para (Part), Chandar maibazar, Total House Hold -25. | 29/BSD | 06/01/2021 | 21 | SOMENATH ACHARYYA | 4.81 | 0 | 0 | 0
6500 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P- Chandar, Name of Village-Lobason Roy Para, Chandar main road to Bhramhon para, Dom para, Total House Hold -34. | 11/BSD | 06/01/2021 | 21 | M/S BANERJEE & BANERJEE | 4.83 | 0 | 0 | 0
6501 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- By pass Pipe line Kadakuli more to Chandar main Bazar, Gosh para ,Chandar maibazar Total House Hold -20. | 28/BSD | 06/01/2021 | 21 | BIDHAN BANERJEE | 4.84 | 0 | 0 | 0
6502 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- Murakata ,Main road to durga mondir (Part), Total House Hold -35. | 12/BSD | 06/01/2021 | 21 | ASHIS PAL | 4.75 | 0 | 0 | 0
6503 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- Lobason Maheswa Para, Total House Hold -75 | 560/ BSD | 13/11/2020 | 21 | SOMENATH ACHARYYA | 4.81 | 0 | 0 | 0
6504 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Simlabandh (45) & Bhedua (46) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 13), | FHTC/25 | 25/01/2022 | 0 | GANESH ROY | 4.98 | 0 | 0 | 0
6505 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Betanal Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no. 43Block - Indas, Name of OHR - Dighalgram, No. of Mouza :- 02 nos. i.e. Barabaikunthapur-125 & Habispur-127 , Total House Hold - 245 (245 out of 549) | FHTC/25 | 25/01/2022 | 0 | TAPAN KUMAR MANDAL | 16.4 | 0 | 0 | 0
6506 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 3 nos. i.e. Jamdoba-154, Ichharia-155 and Bhabanipur- 165 , Habitation's Name : Jamdoba, Roypara, Tantipara,Ichharia,Dhallapara,Amchura, Kalaberia, Kalyanpur,Bhramanpara,Bhabanipur & Murhura. Total House Hold - 162 | FHTC/25 | 25/01/2022 | 0 | MOHAN KUMAR ROY | 4.69 | 0 | 0 | 0
6507 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 ( Barapukura), Total House Hold -114 | FHTC/25 | 25/01/2022 | 0 | TAPAN KUMAR SARKAR | 1.1 | 0 | 0 | 0
6508 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block , Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 01, Shyampu (part) Total House Hold - 453. | FHTC/5 | 05/03/2022 | 0 | GOUTAM BHATTACHRYYA | 27.54 | 0 | 0 | 0
6509 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 02 , (Saldanga , Muktapur ), Total House Hold -253 | FHTC/25 | 25/01/2022 | 0 | SUBHENDU SEKHAR GORAI | 1.78 | 0 | 0 | 0
6510 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-5) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara- 24 ( 455 out of 714), Total House Hold - 455 | FHTC/25 | 25/01/2022 | 0 | AMIYA KUMAR BIT | 35.44 | 0 | 0 | 0
6511 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- Lobason Maheswa Para, Total House Hold -75 | FHTC/25 | 25/01/2022 | 0 | SOMENATH ACHARYYA | 4.79 | 0 | 0 | 0
6512 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - JOYKRISHNAPUR (Zone- I) Name of mouza - 03 nos, Phulberia (PART- B), Sirsa & Joykrishna pur Sarenga (PART- A) | FHTC/25 | 25/01/2022 | 0 | M/S T.P. HAZRA & SONS | 3.25 | 0 | 0 | 0
6513 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-3) DPR no - 36.Block - Bishnupur,Name of OHR - Bhara,No. of Mouza :- 1 no. i.e.Shaluka - 21(110 out of 125) House Hold - 110 | FHTC/25 | 25/01/2022 | 0 | MRITYUNJOY HAZRA | 8.3 | 0 | 0 | 0
6514 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P- Chandar, Name of Village-Lobason Roy Para, Chandar main road to Bhramhon para, Dom para, Total House Hold -34. | FHTC/25 | 25/01/2022 | 0 | M/S BANERJEE & BANERJEE | 4.81 | 0 | 0 | 0
6515 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mukundapur (114), Khakrakanali (115) & Nagri (116) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | FHTC/25 | 25/01/2022 | 0 | APEX ENTERPRISE | 6.7 | 0 | 0 | 0
6516 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 03 (Ladna, Mathana, Kodalia(PART-A)), Total House Hold -430 | FHTC/25 | 25/01/2022 | 0 | UNIVERSAL CONSTRUCTION | 34.9 | 0 | 0 | 0
6517 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01, Magra(PART-II )Total House Hold - 139.' | FHTC/25 | 25/01/2022 | 0 | TAPAN KUMAR UPADHYAY | 2.37 | 0 | 0 | 0
6518 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BELIATORE Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name. of Mouza :- Murakata, Total House Hold - 45 nos. | 12/BSD | 07/01/2022 | 15 | BIDHAN BANERJEE | 4.98 | 0 | 0 | 0
6519 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BELIATORE Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name. of Mouza :- Nabasan, Total House Hold - 35 nos. | 10/BSD | 07/01/2022 | 15 | SOMENATH ACHARYYA | 4.9 | 0 | 0 | 65
6520 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BELIATORE Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name. of Mouza :- Chhandar (Part), Total House Hold - 40 nos. | 11/BSD | 07/01/2022 | 15 | SOMENATH ACHARYYA | 4.98 | 0 | 0 | 0
6521 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , G.P -Chandar, Name of Village - Kadakuli Man Para, Chandar Bramhon Para & Chatterjee para Total House Hold -40. | 31/BSD | 06/01/2021 | 21 | GON ASSOCIATES | 4.47 | 0 | 0 | 10
6522 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Kadakuli Roy Para, Chandar Rail line para, school , health center, Total House Hold -52. | 10/BSD | 06/01/2021 | 21 | SANJOY MONDAL | 4.8 | 0 | 0 | 0
6523 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} , SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Chandar Bardgan Para (Part- C), Total House Hold -50. | 30/BSD | 06/01/2021 | 21 | MANAS DEY | 4.56 | 0 | 0 | 10
6524 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (7 , SM/09552 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (79), Nimaipur (80), Sirsha (81), Kumardoba (82), Dhabani (83), Kallaicha (84) & Manipur (85) mouzas by retrofitting of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 1926 nos. | 437/BQA | 03/03/2022 | 45 | PRINCE INDUTRIES (INDIA) | 97.43 | 0 | 0 | 0
6525 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (7 , SM/09552 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Asna (72), Dhanisukni (74) & Nimaipur (80) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 13) | 1292/BQA | 15/06/2022 | 10 | PRINCE INDUTRIES (INDIA) | 4.86 | 0 | 0 | 0
6526 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (7 , SM/09552 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Baramakarkol (70), Kalabati (79), Sirsha (81) & Kallaicha (84) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 18) | 1297/BQA | 15/06/2022 | 10 | PRINCE INDUTRIES (INDIA) | 4.8 | 0 | 0 | 0
6527 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (7 , SM/09552 | Retrofitting | Work Order for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? in Baramakarkol (70) mouzas by retrofitting of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) | 1281/BQA | 15/06/2022 | 10 | PRINCE INDUTRIES (INDIA) | 1.58 | 0 | 0 | 0
6528 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (7 , SM/09552 | Retrofitting | Work Order for Household survey in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (79), Nimaipur (80), Sirsha (81), Kumardoba (82), Dhabani (83), Kallaicha (84) & Manipur (85) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 22) | 861/KSD | 31/12/2021 | 90 | TAPAS DEY | 0.64 | 0 | 0 | 0
6529 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and , SM/09618 | Retrofitting | Work Order for Household survey in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 09) | 795/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.37 | 0 | 0 | 0
6530 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and , SM/09618 | Retrofitting | Household survey in Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | FHTC/6 | 06/06/2022 | 0 | TAPAS DEY | 0.37 | 0 | 0 | 0
6531 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and , SM/09618 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone - II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Kakila, No. of Mouza :- 2 nos. i.e. Janta-83 & Nayer-84 . Name of Habitation - Janta,Naer.Total House Hold - 530 | FHTC/23 | 23/02/2022 | 0 | PARTHA PRATIM CHHATAIT | 32.04 | 0 | 0 | 0
6532 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and , SM/09618 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jamsol (285), Baligura (286), Asna (287), Chhotagarra (288), Dakharang (290), Kadma (291) & Chingra (292) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | FHTC/23 | 23/02/2022 | 0 | SUBHADIP KOLEY | 42.16 | 0 | 0 | 0
6533 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and , SM/09618 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Birasimul, No. of Mouza :- 4 nos. i.e. Birasimul-70, Shakrul-71, Suripuskarini-72 & Dhamur-73, Total House Hold - 1343 | FHTC/4 | 04/03/2022 | 0 | M/S TARUN KUMAR PATRA | 71.95 | 0 | 0 | 0
6534 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and , SM/09618 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | FHTC/26 | 26/02/2022 | 0 | PARAMESWAR CHOWDHURY | 47.88 | 0 | 0 | 0
6535 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and , SM/09618 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone - I, Name of Mouza:-- 01 no., (Majit), Total House Hold - 175 nos. | 2834/BQA | 16/11/2021 | 30 | MD. AFSAR ALI | 7.96 | 0 | 0 | 0
6536 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and , SM/09618 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 2497/BQA | 23/09/2021 | 30 | PARAMESWAR CHOWDHURY | 68.16 | 0 | 0 | 50
6537 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamasina Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos. mouzas (Bhagaband -1,Binodbati -2,Arjunpur - 3, , SM/09624 | Retrofitting | Material Requisition To Resource Division | 472/BQA | 04/03/2022 | 0 | Resource Division | 8.81 | 0 | 0 | 0
6538 | BANKURA | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamasina Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos. mouzas (Bhagaband -1,Binodbati -2,Arjunpur - 3, , SM/09624 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR -Narikala, No. of Mouza :- 08 nos. i.e.Bhagaband-1,Binodbati-2,Arjunpur-3,Nityanandapur-4,Balarampur-5,Tarajuri Gangarampur-14, Narikala-15,Karoan-16.Total House Hold - 1461 | 438/BQA | 03/03/2022 | 1487 | PRINCE INDUTRIES (INDIA) | 107.14 | 0 | 0 | 80
6539 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Block under Bishnupur Sub - Division of Bankura D , SM/09473 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA at different Mouza's of Left out House Holds of Morar Zone-A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Benebandhi, No. of Mouza :- 7 nos. i.e.Dadwasbati-98, Kusumbani-99, Chougan-102, Dundure-116, Morar-117, Ghugimura-121, Jharia-122, Total House Hold -70 | 110/VSD | 19/04/2022 | 21 | AJIT KUMAR DUTTA | 4.52 | 0 | 0 | 0
6540 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Block under Bishnupur Sub - Division of Bankura D , SM/09473 | Retrofitting | Material Requisition To Resource Division | 2036/BQA | 29/09/2022 | 0 | Resource Division | 3.85 | 0 | 0 | 0
6541 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Na , SM/09478 | Retrofitting | Material Requisition To Resource Division | 2891/BQA | 22/11/2021 | 0 | Resource Division | 165.74 | 0 | 0 | 0
6542 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Na , SM/09478 | Retrofitting | Material Requisition To Resource Division | 150/BQA | 27/01/2022 | 0 | Resource Division | 11.94 | 0 | 0 | 0
6543 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Na , SM/09478 | Retrofitting | Material Requisition To Resource Division | 567/BQA | 17/03/2022 | 0 | Resource Division | 15.6 | 0 | 0 | 0
6544 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Na , SM/09478 | Retrofitting | Household survey in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Nagar (261), Jagannath Bati (262), Bhaji Bari (263), Ramar Chun Puan (264), Agarda Purusottampur (271), Basuri Bera (272), Gopinathpur (273), Chak Tunka (274), Muktapur (275), Lauria (276) & Kanaijuri (277) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Agarda and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | 87/BSD | 28/01/2022 | 59 | TAPAS DEY | 0.85 | 0 | 0 | 100
6545 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Na , SM/09478 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Nagar (261), Jagannath Bati (262), Bhaji Bari (263), Ramar Chun Puan (264), Agarda Purusottampur (271), Basuri Bera (272), Gopinathpur (273), Chak Tunka (274), Muktapur (275), Lauria (276) & Kanaijuri (277) mouzas by retrofitting Agarda and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household - 2536 nos. | 318/BQA | 22/02/2022 | 60 | UNIVERSAL CONSTRUCTION | 123.11 | 0 | 0 | 0
6546 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bathan Tara (113), Elyati (114), Nikunjapur (115), Pingrui (116), Balatukri (117), Hira Dangar (137), Tentul Muri (138), Maitha (139), Jambani (140), Nayananandapur (193), Ma , SM/09534 | Retrofitting | Household survey in Bathan Tara (113), Elyati (114), Nikunjapur (115), Pingrui (116), Balatukri (117), Hira Dangar (137), Tentul Muri (138), Maitha (139), Jambani (140), Nayananandapur (193), Majdiha (194) & Balarampur (195) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Nikunjapur (Zone-B) Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | 100/BSD | 28/01/2022 | 59 | TAPAS DEY | 0.78 | 0 | 0 | 0
6547 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bathan Tara (113), Elyati (114), Nikunjapur (115), Pingrui (116), Balatukri (117), Hira Dangar (137), Tentul Muri (138), Maitha (139), Jambani (140), Nayananandapur (193), Ma , SM/09534 | Retrofitting | Material Requisition To Resource Division | 579/BQA | 17/03/2022 | 0 | Resource Division | 14.41 | 0 | 0 | 0
6548 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bathan Tara (113), Elyati (114), Nikunjapur (115), Pingrui (116), Balatukri (117), Hira Dangar (137), Tentul Muri (138), Maitha (139), Jambani (140), Nayananandapur (193), Ma , SM/09534 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bathan Tara (113), Elyati (114), Nikunjapur (115), Pingrui (116), Balatukri (117), Hira Dangar (137), Tentul Muri (138), Maitha (139), Jambani (140), Nayananandapur (193), Majdiha (194) & Balarampur (195) mouzas by retrofitting Nikunjapur and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 2339 nos. | 1062/BQA | 10/05/2022 | 720 | M/S CARE | 122.18 | 0 | 0 | 97
6549 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Benagari (163), Chhagulia (164), Amarpur (165), Chaulabad (168), Ambari Hazari Gram (169), Bet Jhuria (280), Chak Nakaijuri (281), Mohanpur (282) & Agayanandanpur (283) mouza , SM/09535 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Benagari (163), Chhagulia (164), Amarpur (165), Chaulabad (168), Ambari Hazari Gram (169), Bet Jhuria (280), Chak Nakaijuri (281), Mohanpur (282) & Agayanandanpur (283) mouzas by retrofitting Chaknakaijuri and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 1713 nos. | 435/BQA | 03/03/2022 | 45 | SUBHANKAR BANERJEE | 100.63 | 0 | 0 | 0
6550 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Benagari (163), Chhagulia (164), Amarpur (165), Chaulabad (168), Ambari Hazari Gram (169), Bet Jhuria (280), Chak Nakaijuri (281), Mohanpur (282) & Agayanandanpur (283) mouza , SM/09535 | Retrofitting | Household survey in Benagari (163), Chhagulia (164), Amarpur (165), Chaulabad (168), Ambari Hazari Gram (169), Bet Jhuria (280), Chak Nakaijuri (281), Mohanpur (282) & Agayanandanpur (283) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Chaknakaijuri and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | 94/BSD | 28/01/2022 | 59 | TAPAS DEY | 0.57 | 0 | 0 | 20
6551 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Benagari (163), Chhagulia (164), Amarpur (165), Chaulabad (168), Ambari Hazari Gram (169), Bet Jhuria (280), Chak Nakaijuri (281), Mohanpur (282) & Agayanandanpur (283) mouza , SM/09535 | Retrofitting | Material Requisition To Resource Division | 581/BQA | 17/03/2022 | 0 | Resource Division | 10.55 | 0 | 0 | 0
6552 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10947 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6553 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10947 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6554 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10947 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6555 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KHAKRA KANALI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10951 | New | P.H.E Dte. Khakrakanali, Ps-Khatra Dist- Bankura | Elec05 | 15/05/2023 | 0 | KHATRA CCC | 0.12 | 0 | 0 | 0
6556 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KHAKRA KANALI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10951 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6557 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KHAKRA KANALI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10951 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6558 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KHAKRA KANALI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10951 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6559 | BANKURA | Bankura Division | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (JJM REVISION) , SM/08983 | Augmentation | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir of capacity 450 cum and staging height 20 mtr for Augmentation of piped water supply scheme for Sanabundh and Kargahir and its adjoining mouzas (JJM REVISION) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | 360/BSD | 13/04/2022 | 15 | SHINE ENGINEERING CONSULTANT | 1.85 | 0 | 0 | 0
6560 | BANKURA | Bankura Division | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (JJM REVISION) , SM/08983 | Augmentation | Material Requisition To Resource Division | 1120/BQA | 12/05/2023 | 0 | Resource Division | 0.92 | 0 | 0 | 0
6561 | BANKURA | Bankura Mechanical | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (JJM REVISION) , SM/08983 | Augmentation | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (JJM REVISION) |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
6562 | BANKURA | Bankura Division | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (JJM REVISION) , SM/08983 | Augmentation | Construction of 450m3 capacity RCC OHR based on Departmental Design [ref Drawing No. ¿ PC ¿ 1 / OHR / 4 / 2012 Rev. No. ¿ 1 (Sheet 1 & 2)] with 20.00 mtr. Staging height including foundation, pipe line connection and cost of pipes, specials etc. and allied works for Augmentation of Surface Based Piped W/S Scheme for SANABUNDH, KARGAHIR and Adjoining Mouzas (JJM Revision) under Bankura Division, PHE Dte. (Part ¿ A) and Distribution System with FHTC for the Augmentation of Piped Water Supply Scheme for Augmentation of Surface Water Based Piped W/S Scheme for ¿SANABUNDH, KARGAHIR¿ and Adjoining Mouzas (JJM Revision) under Bankura Division, PHE Dte. (Part ¿ B) | 1178/BQA | 25/05/2022 | 1407 | GOPAL CHANDRA CHOWDHURY | 395.61 | 0 | 0 | 86
6563 | BANKURA | Bankura Division | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (JJM REVISION) , SM/08983 | Augmentation | Creation of Balance 'FHTC' & construction of Platfrom of Existing 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of Surface Water Based Piped W/S Scheme for SANABUNDH, KARGAHIR and Adjoining Mouzas (JJM Revision) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 1350/BQA | 02/06/2023 | 1034 | GOPAL CHANDRA CHOWDHURY | 72.42 | 0 | 0 | 94
6564 | BANKURA | Bankura Division | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (JJM REVISION) , SM/08983 | Augmentation | Augmentation of Surface water based piped water supply scheme for Sanabundh, Kargahir and Adjoining Mouzas (JJM Revision) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 2355/BQA | 14/08/2023 | 961 | GOPAL CHANDRA CHOWDHURY | 102.5 | 0 | 0 | 87
6565 | BANKURA | Bankura Mechanical | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (JJM REVISION) , SM/08983 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift pumping machineries and other electromechanical accessories for Augmentation od surface water based piped water supply scheme for Sanband, Kargahir and adjoining mouza under Bankura Mechanical Division PHE Dte Block-Bankura-I Dist -Bankura. | 1015/BMD | 22/05/2023 | 720 | M.S. ENTERPRISE | 43.65 | 0 | 0 | 100
6566 | BANKURA | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) , SM/10290 | Augmentation | Construction of Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.50 m x 4.5 m) for augmentation of Nabakishore Water Supply Scheme under Bishnupur Sub Division of Bankura Division P.H.E. Dte. (TSM/008518) (SM/10290) (AAFS- PH212245028S000) | 65/BQA | 05/01/2023 | 90 | SANU KARMAKAR | 6.51 | 0 | 0 | 86
6567 | BANKURA | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) , SM/10290 | Augmentation | Repairing of one no pump house for augmentation of Nabakishore water supply scheme under Bishnupur Sub Division of Bankura Division, PHE Dte. (TSM/008518) (SM/10290) (AAFS- PH212245028S000) | 522/BQA | 14/03/2023 | 45 | MOHAN KUMAR ROY | 2.01 | 0 | 0 | 85
6568 | BANKURA | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) , SM/10290 | Augmentation | Material Requisition To Resource Division | 3345/BQA | 06/12/2023 | 0 | Resource Division | 50.07 | 0 | 0 | 0
6569 | BANKURA | Bankura Mechanical | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) , SM/10290 | Augmentation | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.4 | 0 | 0 | 0
6570 | BANKURA | Bankura Mechanical | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) , SM/10290 | Augmentation | Acceptance cum Formal work order for the work of Name of Work:Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmantation of Nabakishore Ground Base piped water supply scheme under JJM program under Bankura Mechanical Division, PHE Dte Block : Patrasayar, Dist: Bankura | 934/BMD | 12/05/2023 | 180 | M/S NABIN GOPAL SENGUPTA | 56.49 | 0 | 0 | 76
6571 | BANKURA | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) , SM/10290 | Augmentation | Construction of boundary wall approx 132 mtr long for augmentation of Nabakishore water supply scheme (pump house no 1) under Bishnupur Sub Division of Bankura Division, PHE Dte. (TSM/008518) (SM/10290) (AAFS- PH212245028S000) | 64/BQA | 05/01/2023 | 30 | GANGADHAR MONDAL | 9.38 | 0 | 0 | 10
6572 | BANKURA | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) , SM/10290 | Augmentation | Construction of boundary wall approx 60 mtr long at 3rd TW site of Augmentation of Nabakishore water supply scheme within Patrasayer Block under Bishnupur Sub-Division of Bankura Division P.H.E Dte. | 1868/BQA | 12/07/2024 | 30 | M/S ABU KADER KHAN | 3.84 | 0 | 0 | 90
6573 | BANKURA | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) , SM/10290 | Augmentation | Material Requisition To Resource Division | 111/BQA | 10/01/2024 | 0 | Resource Division | 28.91 | 0 | 0 | 0
6574 | BANKURA | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) , SM/10290 | Augmentation | Patrasayer market road from 0.00 kmp 02.50 kmp restoration work of both side of road due to laying of pipeline by Bankura Division PHE Dte. under Bankura Highway Division in the district of Bankura, (1) Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) | FHTC/12 | 13/12/2023 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 46.31 | 0 | 0 | 0
6575 | BANKURA | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) , SM/10290 | Augmentation | Construction & Commissioning of 700 m3 capacity 20 Mtr. staging height RCC Over Head Reservoir (Ref. of Drg.no.-PC-I/OHR/6/2012(Rev-01){Sheet-1/2 &2/2} of SE,PC-I,PHE Dte.) staging height 20 mtr. with Laying Distribution System as per LDS drawing, including FHTC works for Augmentation of Nabakishore Piped Water Supply Scheme under Patrasayer Block of Bankura Division, PHE Dte. | 2277/BQA | 01/08/2023 | 821 | SATYANARAYAN ENGINEERS' CO-OP.SOCIETY LTD | 623.97 | 0 | 0 | 89
6576 | BANKURA | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) , SM/10290 | Augmentation | Sinking of 2 Nos. Tubewell (Rotary Method) with construction of 2 Nos. Pump House & Boundary Wall and Laying of Distribution System under Augmentation of Nabakishore Water Supply Scheme under Jal Jeevan Mission (JJM) within Patrasayer Block under Bishnupur Sub-division of Bankura Division, P.H.E. Dte. (SM/10290) | 1232/BQA | 02/06/2025 | 259 | M/S S. CHOUDHURY | 158.01 | 0 | 0 | 40
6577 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR TARIBATERDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10906 | New | Taribatardihi, Bankura-I | FHTC/06 | 02/06/2023 | 0 | LALBAZAR CCC | 0.08 | 0 | 0 | 0
6578 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR TARIBATERDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10906 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6579 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR TARIBATERDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10906 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6580 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR TARIBATERDIHI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10906 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6581 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHOWGHARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10916 | New | Bmsd Phe Dte vill- Chowghora, Po-G/Dubrajpur, Ps- Chhatna | FHTC/06 | 05/06/2023 | 0 | CHHATNA CCC | 0.12 | 0 | 0 | 0
6582 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHOWGHARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10916 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6583 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHOWGHARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10916 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6584 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHOWGHARA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10916 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6585 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DALPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10918 | New | New service connection for "Pathardanga" Mini water supply scheme under Bankura Division PHE DT |  | 26/04/2024 | 0 | CHHATNA CCC | 0.11 | 0 | 0 | 0
6586 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DALPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10918 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6587 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DALPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10918 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6588 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DALPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10918 | New | MINI PIPED WATER SUPPLY SCHEME FOR DALPUR VILLAGE (Pathardanga) HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | BP-77/2024-25 | 22/05/2024 | 0 | CHHATNA CCC | 0.11 | 0 | 0 | 0
6589 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DALPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER CHHATNA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10918 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6590 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHHOLA BAID VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10932 | New | Quotation of WBSEDCL for the scheme of SM/10932 | BP-289/2024-25 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.2 | 0 | 0 | 0
6591 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHHOLA BAID VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10932 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6592 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DHANJHAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11112 | New | Bmsd Phe Dhanjhar ( C/o Sudip Saha , Dhanjhar, Ranibandh | FHTC/08 | 04/08/2023 | 0 | RANIBANDH CCC | 0.11 | 0 | 0 | 0
6593 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DHANJHAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11112 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6594 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DHANJHAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11112 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6595 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DHANJHAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11112 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6596 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BARAPACHA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11115 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6597 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BARAPACHA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11115 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6598 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BARAPACHA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11115 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6599 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BARAPACHA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11115 | New | Work Order Installation of scheme information board for different mini piped water supply scheme within Ranibandh Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme:- (1) Mini Piped Water Supply Scheme for Barapacha Village (SM/11115), (2) Mini Piped Water Supply Scheme for Ledapakur Village (SM/11116), (3) Mini Piped Water Supply Scheme for Sutan Village (SM/11120), (4) Mini Piped Water Supply Scheme for Burisal Village (SM/11117), (5) Mini Piped Water Supply Scheme for Goalmuri Village (SM/11118) and (6) Mini Piped Water Supply Scheme for Kawatanga Village (SM/11109) | 190\KSD | 10/03/2025 | 10 | S. B. CONSTRUCTION | 0.9 | 0 | 0 | 90
6600 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KALASOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11022 | New | New connection at Jl No-96, Mouza-Kalasol, Block-Raipur in connection with 431 mini PWSS under BMSD, PHE Dte. | FHTC/06 | 07/06/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0 | 0
6601 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KALASOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11022 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6602 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KALASOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11022 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6603 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KALASOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11022 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6604 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KUCHAIPAL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11023 | New | New connection at Jl No-95, Mouza-Kuchaipal, Block-Raipur in connection with 431 mini PWSS under BMSD, PHE Dte. | FHTC/06 | 07/06/2023 | 0 | RAIPUR CCC | 0.12 | 0 | 0 | 0
6605 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KUCHAIPAL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11023 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6606 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KUCHAIPAL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11023 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6607 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KUCHAIPAL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11023 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6608 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Setai Puskarini, House Hold No.: 50) , SM/11084 | New | Assistant Engineer Bankura Mech S.D.P.H.E (site - sajalpuskurini, Kotulpur) | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0 | 0
6609 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Setai Puskarini, House Hold No.: 50) , SM/11084 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6610 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Setai Puskarini, House Hold No.: 50) , SM/11084 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6611 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Setai Puskarini, House Hold No.: 50) , SM/11084 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6612 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PARASHI DANGA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10953 | New | P.H.E Dte. Parashidanga, Ps-Khatra Dist-Bankura | Elec05 | 15/05/2023 | 0 | KHATRA CCC | 0.12 | 0 | 0 | 0
6613 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PARASHI DANGA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10953 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6614 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PARASHI DANGA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10953 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6615 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR PARASHI DANGA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER KHATRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10953 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6616 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Dhamsa, House Hold:38) , SM/11151 | New | New Connection at Dhamsa,Patrasayer Bishnupur PHE Dte | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0 | 0
6617 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Dhamsa, House Hold:38) , SM/11151 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6618 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Dhamsa, House Hold:38) , SM/11151 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6619 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Dhamsa, House Hold:38) , SM/11151 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6620 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Khejurmura, House Hold:34) , SM/11154 | New | New Connection at Khejurmura,Patrasayer Bishnupur PHE Dte | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0 | 0
6621 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Khejurmura, House Hold:34) , SM/11154 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6622 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Khejurmura, House Hold:34) , SM/11154 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6623 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Khejurmura, House Hold:34) , SM/11154 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6624 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Chak Delwar, House Hold No.: 81) , SM/11157 | New | (site - Chakdelwar, Deshra Kotulpur) quotation bill | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0 | 0
6625 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Chak Delwar, House Hold No.: 81) , SM/11157 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6626 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Chak Delwar, House Hold No.: 81) , SM/11157 | New | Quotation for New service connection at CHAKDELWAR | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0 | 0
6627 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Chak Delwar, House Hold No.: 81) , SM/11157 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6628 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer (Village Name: Chak Delwar, House Hold No.: 81) , SM/11157 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6629 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DHEPUA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11130 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6630 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DHEPUA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11130 | New | New service connection for Dhepua Mini water supply scheme under Bankura Division PHE DTE. | BP-85/2024-25 | 29/05/2024 | 0 | SARENGA CCC | 0.12 | 0 | 0 | 0
6631 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DHEPUA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11130 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6632 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DHEPUA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11130 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6633 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Chhakraghu, House Hold No.: 55) , SM/11091 | New | (site - Chakraghu, M.M.P , Kotulpur) quotation bill | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0 | 0
6634 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Chhakraghu, House Hold No.: 55) , SM/11091 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6635 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Chhakraghu, House Hold No.: 55) , SM/11091 | New | Quotation for New service connection at CHAKRAGHU | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0 | 0
6636 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Chhakraghu, House Hold No.: 55) , SM/11091 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6637 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Chhakraghu, House Hold No.: 55) , SM/11091 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6638 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BARISOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11062 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6639 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BARISOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11062 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6640 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BARISOL VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11062 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6641 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR AMBEDYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10977 | New | New service connection for Ambedia Mini water supply scheme under Bankura Division PHE DTE. | BP-77/2024-25 | 22/05/2024 | 0 | INDPUR CCC | 0.12 | 0 | 0 | 0
6642 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR AMBEDYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10977 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6643 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR AMBEDYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10977 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6644 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR AMBEDYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10977 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6645 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR GILIRBONA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10978 | New | Quotation bill for Gilirbona Dubrajpur | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0 | 0
6646 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR GILIRBONA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10978 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6647 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR GILIRBONA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10978 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6648 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR GILIRBONA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10978 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6649 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHHOTA LACHHIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10933 | New | New service connection for Bhalukkunia Mini water supply scheme under Bankura Division PHE DTE |  | 28/05/2024 | 0 | SARENGA CCC | 0.12 | 0 | 0 | 0
6650 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHHOTA LACHHIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10933 | New | MINI PIPED WATER SUPPLY SCHEME FOR CHHOTA LACHHIPUR VILLAGE (Bhalukkunia) HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME(SM/10933) | BP-91/2024-25 | 04/06/2024 | 0 | SARENGA CCC | 0.12 | 0 | 0 | 0
6651 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR CHHOTA LACHHIPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10933 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6652 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Gachhgera, House Hold:96) , SM/11136 | New | Assistant Engineer Bankura Mech S.D.P.H.E (site - gachhgere, Nr. Primary school, Lowgram, Kotulpur) | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0 | 0
6653 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Gachhgera, House Hold:96) , SM/11136 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6654 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Gachhgera, House Hold:96) , SM/11136 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6655 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Gachhgera, House Hold:96) , SM/11136 | New | Quotation for New service connection at Gachhgere | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0 | 0
6656 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Gachhgera, House Hold:96) , SM/11136 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6657 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Dai Chapri, House Hold No.: 93) , SM/11095 | New | Assistant Engineer Bankura Mech S.D.P.H.E (site - Diachapri, lowgram, Kotulpur) | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0 | 0
6658 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Dai Chapri, House Hold No.: 93) , SM/11095 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6659 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Dai Chapri, House Hold No.: 93) , SM/11095 | New | Quotation for New service connection at DIACHAPRI | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0 | 0
6660 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Dai Chapri, House Hold No.: 93) , SM/11095 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6661 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Dai Chapri, House Hold No.: 93) , SM/11095 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6662 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Chhota Pagla, House Hold No.: 87) , SM/11097 | New | Assistant Engineer Bankura Mech S.D.P.H.E (site - chatpagla, Nr. Manshatala, Lowgram, Kotulpur) | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0 | 0
6663 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Chhota Pagla, House Hold No.: 87) , SM/11097 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6664 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Chhota Pagla, House Hold No.: 87) , SM/11097 | New | Quotation for New service connection at CHATPAGLA | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0 | 0
6665 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Chhota Pagla, House Hold No.: 87) , SM/11097 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6666 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Chhota Pagla, House Hold No.: 87) , SM/11097 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6667 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Brahmadanga, House Hold No.: 75) , SM/11101 | New | Quatation bill Balita Brahamdanga, Kotulpur | Elec03 | 15/03/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0 | 0
6668 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Brahmadanga, House Hold No.: 75) , SM/11101 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6669 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Brahmadanga, House Hold No.: 75) , SM/11101 | New | Quotation for New service connection at BATILA | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0 | 0
6670 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Brahmadanga, House Hold No.: 75) , SM/11101 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6671 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Brahmadanga, House Hold No.: 75) , SM/11101 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6672 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Bankajol, House Hold No.: 22) , SM/11105 | New | Bankajol Chorgere Sihar, Kotulpur | Elec03 | 15/03/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0 | 0
6673 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Bankajol, House Hold No.: 22) , SM/11105 | New | QUOTATION FOR NEW CONNECTION AT BANKAJOL | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0 | 0
6674 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Bankajol, House Hold No.: 22) , SM/11105 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6675 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Bankajol, House Hold No.: 22) , SM/11105 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6676 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Bankajol, House Hold No.: 22) , SM/11105 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6677 | BANKURA | Bankura Division | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC , SM/12379 | Augmentation | Work Order for Preparation of Detailed Project Report for Augmentation of Chhoto Birbhanpur Piped Water Supply Scheme, Block : Sarenga, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 16) | 194/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.37 | 0 | 0 | 0
6678 | BANKURA | Bankura Division | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC , SM/12379 | Augmentation | Material Requisition To Resource Division | 1120/BQA | 12/05/2023 | 0 | Resource Division | 46.12 | 0 | 0 | 0
6679 | BANKURA | Bankura Mechanical | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC , SM/12379 | Augmentation | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
6680 | BANKURA | Bankura Mechanical | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC , SM/12379 | Augmentation | Acceptance cum Formal work order for the work of Providing, & installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chotobirbhanpur piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Sarenga Dist: Bankura. | 964/BMD | 19/05/2023 | 60 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 39.1 | 0 | 0 | 70
6681 | BANKURA | Bankura Division | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC , SM/12379 | Augmentation | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | 643/BQA | 24/03/2023 | 30 | P. K. TEWARY DRILLING CO | 8.41 | 0 | 0 | 99
6682 | BANKURA | Bankura Division | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC , SM/12379 | Augmentation | Material Requisition To Resource Division | 116/BQA | 10/01/2024 | 0 | Resource Division | 6.82 | 0 | 0 | 0
6683 | BANKURA | Bankura Division | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC , SM/12379 | Augmentation | Laying of DI (K7) pipe with supplying, laying, fitting, fixing, jointing of HDPE (Materials grade PE-100, PN-6) pipes for distribution system with ancillary works with providing ¿FHTC (Functional House Hold Tap Connection)¿, Laying Rising Main using different dia D.I. - K9 pipes and Construction of 200 m³ Capacity R.C.C OHR (based on Departmental Design) with 20 mtr. staging height including foundation, pipeline connection and cost of pipes, specials etc. and allied works for Augmentation for Chhoto - Birbhanpur Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 970/BQA | 28/04/2023 | 270 | PARTHA PRATIM CHHATAIT | 289.03 | 0 | 0 | 60
6684 | BANKURA | Bankura Mechanical | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC , SM/12379 | Augmentation | Acceptance cum Formal work order for the work of Name of Providing, & installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chotobirbhanpur piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Sarenga Dist: Bankura. | 1013/BMD | 22/05/2023 | 180 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 47.59 | 0 | 0 | 0
6685 | BANKURA | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. , SM/09880 | Augmentation | Construction of boundary wall approx 30 mtr long for Augmentation of Joyrambati water supply scheme (2nd T/W Site) under Bishnupur Sub Division of Bankura Division, PHE Dte. (2nd Call) TSM No.-TSM/005083 , AAFS Project Id :- PH212246197M000 | 764/BQA | 04/04/2023 | 30 | MRITYUNJOY HAZRA | 1.66 | 0 | 0 | 0
6686 | BANKURA | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. , SM/09880 | Augmentation | Construction of Ground Level Reservoir (capacity 50 m3) for Matri Mandir, Joyrambati, Bankura under Joyrambati water supply scheme within Bishnupur Sub-Division of Bankura Division PHE. Dte. | 661/BQA | 23/03/2022 | 90 | MOHAN KUMAR ROY | 16.99 | 0 | 0 | 20
6687 | BANKURA | Bankura Mechanical | Augmentation of Jayrambati Piped Water Supply Scheme. , SM/09880 | Augmentation | Augmentation of Jayrambati Piped Water Supply Scheme. |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.6 | 0 | 0 | 0
6688 | BANKURA | Bankura Mechanical | Augmentation of Jayrambati Piped Water Supply Scheme. , SM/09880 | Augmentation | Augmentation of Jayrambati Piped Water Supply Scheme. |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
6689 | BANKURA | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. , SM/09880 | Augmentation | Creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM Revision) for Augmentation of Joyrambati W/S Scheme Block- Kotulpur under Bishnupur Sub - Division of Bankura Division, PHE Dte. TSM No.-TSM/005083 , AAFS Project Id :- PH212246197M000 Block -Kotulpur, Name of OHR -Joyrambati, No. of Mouza :- 4 nos. i.e. (i) Joyrambati - J.L No-164 , (ii) Haldi J.L. No-165, (iii) Malpur J.L No-166 & (iv) Masinapur J.L No-167 . Total House Hold - 1287 | 179/BQA | 30/01/2023 | 480 | DIPAYAN DEY | 66.36 | 0 | 0 | 35
6690 | BANKURA | Bankura Mechanical | Augmentation of Jayrambati Piped Water Supply Scheme. , SM/09880 | Augmentation | Acceptance cum Formal work order for the work of Name of Work:Providing, & installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Joyrambati piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Kotulpur Dist: Bankura. | 935/BMD | 12/05/2023 | 180 | KASHINATH DEY | 29.69 | 0 | 0 | 77
6691 | BANKURA | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. , SM/09880 | Augmentation | Laying distribution system including allied works of Augmentation of Joyrambati Piped W/S. Scheme (JJM Revesion ) at Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE. Dte. | 901/BQA | 20/04/2023 | 276 | BISWARUP BOSE | 110.15 | 0 | 0 | 45
6692 | BANKURA | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. , SM/09880 | Augmentation | Emergent repairing for laying of pipe line by the PHE department at Joyrambati-Kamarpukur road at Malpur Prathamik Vidyalaya under Bishnupur Division PWD in the District of Bankura during the year 2023-2024 | FHTC/12 | 01/12/2023 | 0 | EXECUTIVE ENGINEER , BISHNUPUR DIVISION P.W.DTE. | 0.96 | 0 | 0 | 0
6693 | BANKURA | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. , SM/09880 | Augmentation | Restoration work of side shoulder due to damage caused for the laying of pipeline by PHE department in the different stretches in joyrambati - kamarpukur road under Bishnupur division P.W.Dte. in the district of Bankura . | FHTC/02 | 02/02/2024 | 0 | EXECUTIVE ENGINEER , BISHNUPUR DIVISION P.W.DTE. | 43.62 | 0 | 0 | 0
6694 | BANKURA | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. , SM/09880 | Augmentation | Construction of Office cum Godown with sanitary and water supply arrangement at Head Work Site of 60 sqmtr. (approx) area at water supply scheme for surface water based for Augmentation of Joyrambati water supply scheme under Bishnupur Sub-Division, Bankura Division PHE Dte. (2nd Call) TSM No.-TSM/005083 , AAFS Project Id :- PH212246197M000 | 763/BQA | 04/04/2023 | 728 | M/S T.P. HAZRA & SONS | 12.53 | 0 | 0 | 20
6695 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BALIKHUN VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10852 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6696 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MUKHUTIDI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10858 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6697 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MUKHUTIDI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10858 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6698 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MUKHUTIDI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10858 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6699 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10868 | New | Quotation bill for Raghunathpur Baga | ELCO03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0 | 0
6700 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10868 | New | Phe Complex Ailakandi, Raghunathpur Nayada |  | 29/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0 | 0
6701 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10868 | New | Quotation bill for Raghunathpur Baga | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0 | 0
6702 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10868 | New | WBSEDCL Quotation bill for Scheme code - SM/10868. | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0 | 0
6703 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10868 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6704 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10868 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6705 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAGHUNATHPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10868 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6706 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JAGATPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10874 | New | Quotation bill for Jagatpur, Durbrajpur |  | 27/02/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0 | 0
6707 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JAGATPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10874 | New | Quotation bill for Krishnanagar Purusottampur | Elec03 | 15/03/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0 | 0
6708 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JAGATPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10874 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6709 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JAGATPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10874 | New | New service connection for Jagatpur, Bibarda Mini water supply scheme under Bankura Division PHE DTE. | BP-77/2024-25 | 22/05/2024 | 0 | TALDANGRA CCC | 0.12 | 0 | 0 | 0
6710 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JAGATPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10874 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6711 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JAGATPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10874 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6712 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Ghagara, House Hold No.: 75) , SM/11175 | New | WBSEDCL service connection on Ghagara site in connection of 431 Nos. Mini Piped water supply scheme under Bankura Mechanical Division PHE Dte. | Joypur CC | 31/01/2023 | 0 | JOYPUR CCC | 0.12 | 0 | 0 | 0
6713 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Ghagara, House Hold No.: 75) , SM/11175 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6714 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Ghagara, House Hold No.: 75) , SM/11175 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6715 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Joypur & Kotulpur (Village Name: Ghagara, House Hold No.: 75) , SM/11175 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6716 | BANKURA | Bankura Division | Harinashuli Piped Water Supply Scheme , SM/12422 | New | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | 351/BQA | 21/02/2023 | 30 | MABCO CONSULTANT | 15.12 | 0 | 0 | 30
6717 | BANKURA | Bankura Division | Harinashuli Piped Water Supply Scheme , SM/12422 | New | Material Requisition To Resource Division | 79BQA | 06/01/2023 | 0 | Resource Division | 118.81 | 0 | 0 | 0
6718 | BANKURA | Bankura Division | Harinashuli Piped Water Supply Scheme , SM/12422 | New | Material Requisition To Resource Division | 2522/BQA | 08/09/2023 | 0 | Resource Division | 14.41 | 0 | 0 | 0
6719 | BANKURA | Bankura Mechanical | Harinashuli Piped Water Supply Scheme , SM/12422 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk at TW No-I & T.W No-II of Harinashuli piped water supply scheme Block : Joypur under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | 876/BMD | 04/05/2023 | 180 | MITRA ENTERPRISE | 39.3 | 0 | 0 | 50
6720 | BANKURA | Bankura Division | Harinashuli Piped Water Supply Scheme , SM/12422 | New | Jack Pussing, Land development & Rock cutting for foundation of 500 M3 capacity RCC OHR with 20 Mtr. staging height of Jadabnagar Water Supply Scheme & 450 M3 capacity RCC OHR with 20 Mtr. staging height of Harinasuli Water Supply Scheme under Bishnupur Sub Division of Bankura Division, P.H.E. Dte. | 3001/BQA | 03/11/2023 | 45 | GOPAL CHANDRA CHOWDHURY | 74.67 | 0 | 0 | 95
6721 | BANKURA | Bankura Mechanical | Harinashuli Piped Water Supply Scheme , SM/12422 | New | Harinsuli T/W-I | BP-2023-24-46 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.01 | 0 | 0 | 0
6722 | BANKURA | Bankura Mechanical | Harinashuli Piped Water Supply Scheme , SM/12422 | New | Harinasuli T/W-II | BP-2023-24-47 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.23 | 0 | 0 | 0
6723 | BANKURA | Bankura Division | Harinashuli Piped Water Supply Scheme , SM/12422 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR HARINASHULI & JADABNAGAR PIPED WATER SUPPLY SCHEME, BLOCK- JOYPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | 1918/BQA | 13/07/2023 | 810 | GOPAL CHANDRA CHOWDHURY | 1591.82 | 0 | 0 | 85
6724 | BANKURA | Bankura Division | Pankhai Piped Water Supply Scheme , SM/12427 | New | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Joypur Block under Bishnupur Sub-Division under Bankura Division, PHE Dte. | 1117/BQA | 18/05/2022 | 60 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 120.45 | 0 | 0 | 100
6725 | BANKURA | Bankura Division | Pankhai Piped Water Supply Scheme , SM/12427 | New | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | 351/BQA | 21/02/2023 | 30 | MABCO CONSULTANT | 15.12 | 0 | 0 | 30
6726 | BANKURA | Bankura Division | Pankhai Piped Water Supply Scheme , SM/12427 | New | Material Requisition To Resource Division | 79BQA | 06/01/2023 | 0 | Resource Division | 55.83 | 0 | 0 | 0
6727 | BANKURA | Bankura Mechanical | Pankhai Piped Water Supply Scheme , SM/12427 | New | Pankhai Piped Water Supply Scheme | BP-2023-24-103 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.68 | 0 | 0 | 0
6728 | BANKURA | Bankura Mechanical | Pankhai Piped Water Supply Scheme , SM/12427 | New | New service connection at Pankhai t/w-II ,hetia gp of joypur block under BMD PHE Dte. | BP-2024-25-37 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.17 | 0 | 0 | 0
6729 | BANKURA | Bankura Mechanical | Pankhai Piped Water Supply Scheme , SM/12427 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Pankhai Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | 457/BMD | 10/06/2025 | 90 | A.G.ENTERPRISE | 11.86 | 0 | 0 | 0
6730 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Khanabari, House Hold No.: 53) , SM/11676 | New | SVS single phase connection for Shantipur colony | FHTC/04 | 29/04/2024 | 0 | RADHANAGAR CCC | 0.13 | 0 | 0 | 0
6731 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Khanabari, House Hold No.: 53) , SM/11676 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6732 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Benabendi, House Hold No.: 93) , SM/11678 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6733 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Benabendi, House Hold No.: 93) , SM/11678 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6734 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Benabendi, House Hold No.: 93) , SM/11678 | New | SVS single phase connection for Dhangora village | FHTC/04 | 29/04/2024 | 0 | RADHANAGAR CCC | 0.13 | 0 | 0 | 0
6735 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Bishnupur, Indas & Joypur (Village Name: Benabendi, House Hold No.: 93) , SM/11678 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6736 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Benda, House Hold:71) , SM/11434 | New | New Connection at Benda ,Patrasayer Bishnupur PHE Dte | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0 | 0
6737 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Benda, House Hold:71) , SM/11434 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6738 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Benda, House Hold:71) , SM/11434 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6739 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Benda, House Hold:71) , SM/11434 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6740 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Asanbani, House Hold:82) , SM/11435 | New | New Connection at Asabani,Patrasayer Bishnupur PHE Dte | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0 | 0
6741 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Asanbani, House Hold:82) , SM/11435 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6742 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Asanbani, House Hold:82) , SM/11435 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6743 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, (Village Name :Asanbani, House Hold:82) , SM/11435 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6744 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Barika Bhanupur, House Hold:53 , SM/11442 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6745 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Barika Bhanupur, House Hold:53 , SM/11442 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6746 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Patrasayer & Sonamukhi, Village Name :Barika Bhanupur, House Hold:53 , SM/11442 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6747 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Paschim Nandarampur,Household-92) , SM/11416 | New | New Connection at Paschim Nandarampur, Sonamukhi, PHE Dte | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0 | 0
6748 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Paschim Nandarampur,Household-92) , SM/11416 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6749 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Paschim Nandarampur,Household-92) , SM/11416 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6750 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Paschim Nandarampur,Household-92) , SM/11416 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6751 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi ( Village Name-Basu Nandanpur, Household-79) , SM/11418 | New | New Connection at Basu Nandaram, Sonamukhi PHE Dte | FHTC/08 | 04/08/2023 | 0 | SONAMUKHI CCC | 0.12 | 0 | 0 | 0
6752 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi ( Village Name-Basu Nandanpur, Household-79) , SM/11418 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6753 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi ( Village Name-Basu Nandanpur, Household-79) , SM/11418 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6754 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi ( Village Name-Basu Nandanpur, Household-79) , SM/11418 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6755 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Rajgola, Household-62) , SM/11424 | New | New service connection at Uttar Palsura(Bud Bud) Sonamukhi PHE Dte. | FHTC/03 | 12/03/2024 | 0 | BUDBUD CCC | 2.63 | 0 | 0 | 0
6756 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Rajgola, Household-62) , SM/11424 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6757 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Rajgola, Household-62) , SM/11424 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6758 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name-Rajgola, Household-62) , SM/11424 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6759 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MUKUNDAPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MEJIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/13252 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6760 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MUKUNDAPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MEJIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/13252 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6761 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MUKUNDAPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MEJIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/13252 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6762 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JAMRA MADHABPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/13264 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6763 | BANKURA | Bankura Mechanical | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/A WATER SUPPLY SCHEME , SM/15007 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Pumping machineries with other electro-mechanical accessories for OHR site Zone-1A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | 1119/BMD | 24/05/2023 | 45 | KASHINATH DEY | 26.4 | 0 | 0 | 0
6764 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/A WATER SUPPLY SCHEME , SM/15007 | Augmentation | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-1A) (Sl. No. 01) | 179/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.34 | 0 | 0 | 0
6765 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/A WATER SUPPLY SCHEME , SM/15007 | Augmentation | Material Requisition To Resource Division | 79BQA | 06/01/2023 | 0 | Resource Division | 3.99 | 0 | 0 | 0
6766 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/A WATER SUPPLY SCHEME , SM/15007 | Augmentation | Material Requisition To Resource Division | 116/BQA | 10/01/2024 | 0 | Resource Division | 3.48 | 0 | 0 | 0
6767 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/A WATER SUPPLY SCHEME , SM/15007 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- I/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 973/BQA | 28/04/2023 | 980 | EARTH MOVING (INDIA) | 119.88 | 0 | 0 | 82
6768 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/A WATER SUPPLY SCHEME , SM/15007 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 185 Cum., staging height 20 Mtr.) including by pass arrangement and construction of boundary wall with other allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- I/A Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 486/BQA | 25/02/2025 | 60 | PRADIP CHAKRABORTY | 25.6 | 0 | 0 | 0
6769 | BANKURA | Bankura Mechanical | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐I/A WATER SUPPLY SCHEME , SM/15007 | Augmentation | Acceptance cum Formal work order for the work of Providing, and installation of Flow Meter with other electro mechanical accessories of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme for OHR site Zone 1A under Bankura Mechanical Division, PHE Dte. Dist: Bankura | 3062/BMD | 12/03/2024 | 360 | UNITED TRADERS | 9.08 | 0 | 0 | 100
6770 | BANKURA | Bankura Mechanical | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME , SM/15008 | Augmentation | Acceptance cum Formal work order for the work of Providing & installation of Pumping machineries with other electro-mechanical accessories for OHR site Zone-2A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | 1784/BMD | 01/08/2023 | 120 | S P ENTERPRISE (SILIGURI) | 26.41 | 0 | 0 | 0
6771 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME , SM/15008 | Augmentation | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-2A) (Sl. No. 03) | 181/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.44 | 0 | 0 | 0
6772 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME , SM/15008 | Augmentation | Material Requisition To Resource Division | 79BQA | 06/01/2023 | 0 | Resource Division | 3.64 | 0 | 0 | 0
6773 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME , SM/15008 | Augmentation | Construction of CWR & Pump House at OHR site under Augmentation of (Mukutmanipur, Khatra & Ranibundh) Zone- II/A Water supply scheme under Khatra Sub- Division of Bankura Division, P.H.E. Dte. | 351/BQA | 05/02/2024 | 120 | GOUR GORAI | 20.72 | 0 | 0 | 50
6774 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME , SM/15008 | Augmentation | Material Requisition To Resource Division | 116/BQA | 10/01/2024 | 0 | Resource Division | 5.9 | 0 | 0 | 0
6775 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME , SM/15008 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 135 Cum., staging height 20 Mtr.) including by pass arrangement, guard room, boundary wall with other allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- II/A Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 487/BQA | 25/02/2025 | 259 | PARTHA SARATHI PATRA | 10.43 | 0 | 0 | 0
6776 | BANKURA | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐II/A WATER SUPPLY SCHEME , SM/15008 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- II/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 972/BQA | 28/04/2023 | 705 | GOUTAM BHOWMIK | 166.52 | 0 | 0 | 40
6777 | BANKURA | Bankura Division | Lego Piped Water Supply Scheme , SM/14177 | New | Material Requisition To Resource Division | 79BQA | 06/01/2023 | 0 | Resource Division | 86.97 | 0 | 0 | 0
6778 | BANKURA | Bankura Division | Lego Piped Water Supply Scheme , SM/14177 | New | QUOTATION FOR NEW SERVICE CONNECTION | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0 | 0
6779 | BANKURA | Bankura Division | Lego Piped Water Supply Scheme , SM/14177 | New | Instalation of scheme information board for 3 nos. sites of Panahar Piped Water Supply Scheme (SM/18790) & 2 nos. sites of Lego Piped Water Supply Scheme (SM/14177) within Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | 555/VSD | 27/09/2024 | 15 | SAFIQUE AHAMMAD KHAN | 0.75 | 0 | 0 | 100
6780 | BANKURA | Bankura Mechanical | Lego Piped Water Supply Scheme , SM/14177 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Lego Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | 443/BMD | 10/06/2025 | 90 | TAPAN KUMAR SARKAR | 11.86 | 0 | 0 | 0
6781 | BANKURA | Bankura Division | Naruala Piped Water Supply Scheme , SM/13789 | New | Material Requisition To Resource Division | 79BQA | 06/01/2023 | 0 | Resource Division | 13.87 | 0 | 0 | 0
6782 | BANKURA | Bankura Division | Naruala Piped Water Supply Scheme , SM/13789 | New | Material Requisition To Resource Division | 2994/BQA | 28/11/2024 | 0 | Resource Division | 6.46 | 0 | 0 | 0
6783 | BANKURA | Bankura Mechanical | Naruala Piped Water Supply Scheme , SM/13789 | New | New Service Connection for NARUALA TW-2(JL NO-122, PLOT-70) Water supply scheme under Bankura Mechanical Division PHE DTE | BP-2023-24 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.8 | 0 | 0 | 0
6784 | BANKURA | Bankura Mechanical | Naruala Piped Water Supply Scheme , SM/13789 | New | New Service Connection for NARUALA TW-1 Water supply scheme(JLNO-123,PLOT-1041) under Bankura Mechanical Division PHE DTE | BP-2024-25-34 | 10/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.47 | 0 | 0 | 0
6785 | BANKURA | Bankura Mechanical | Naruala Piped Water Supply Scheme , SM/13789 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Narula Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | 449/BMD | 10/06/2025 | 90 | S. G. TECHNICAL SERVICE | 10.9 | 0 | 0 | 0
6786 | BANKURA | Bankura Mechanical | Construction of Grid-Connected solar photo -voltaic system for Patrasayer PWSS scheme Dist Bankura , SM/15313 | Solarisation | Acceptance cum Formal work order for the work of Construction of Grid-connected Solar Photo-voltaic System for P/H No-I of Patrasayar PWS Scheme under Bankura Mechanical Division PHE Dte. Dist: Bankura. | 484/BMD | 23/03/2023 | 60 | UNICON | 5.95 | 0 | 0 | 90
6787 | BANKURA | Bankura Mechanical | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME , SM/16261 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Pumping machineries with other electro-mechanical accessories for OHR site Zone-8A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | 1120/BMD | 24/05/2023 | 45 | AMITAVA CHAKRABORTY | 26.24 | 0 | 0 | 0
6788 | BANKURA | Bankura Division | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME , SM/16261 | Augmentation | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Ranibandh, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-8A) (Sl. No. 14) | 192/KSD | 24/05/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.46 | 0 | 0 | 0
6789 | BANKURA | Bankura Division | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME , SM/16261 | Augmentation | Material Requisition To Resource Division | 79BQA | 06/01/2023 | 0 | Resource Division | 1.24 | 0 | 0 | 0
6790 | BANKURA | Bankura Division | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME , SM/16261 | Augmentation | Material Requisition To Resource Division | 116/BQA | 10/01/2024 | 0 | Resource Division | 8.72 | 0 | 0 | 0
6791 | BANKURA | Bankura Division | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME , SM/16261 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone‐ VIII/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (SM/16261) |  | 09/08/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 13.33 | 0 | 0 | 0
6792 | BANKURA | Bankura Division | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME , SM/16261 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone‐ VIII/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (SM/16261) | BP-226/2024-25 | 13/08/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 13.33 | 0 | 0 | 0
6793 | BANKURA | Bankura Division | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME , SM/16261 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing FHTC (Functional House Hold Tap Connection)¿ for Mukutmanipur, Khatra & Ranibundh (Zone- VIII/A) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 1135/BQA | 15/05/2023 | 901 | SWAPAN KUMAR UPADHYAY | 228.33 | 0 | 0 | 45
6794 | BANKURA | Bankura Division | AUGMENTATION OF MUKUTMANIPUR, KHATRA & RANIBUNDH ZONE‐VIII A WATER SUPPLY SCHEME , SM/16261 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 180 Cum., staging height 20 Mtr.) including by pass arrangement and boundary wall with other allied works for Augmentation of Mukutmanipur, Khatra & Ranibundh Zone- VIII/A Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 491/BQA | 25/02/2025 | 243 | TAPAN KUMAR MANDAL | 9.46 | 0 | 0 | 0
6795 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) , SM/07272 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KUSTORA (Zone - W) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Kushtora. No.of Mouza :- 10 (Baraleddya, Dhagoria, Banchingra, Nangalbera, Dinagram, Ekaria, Junkanali, Kendbona, Kalaboti & Batdeuli). Total House Hold - 811, | FHTC/11 | 11/10/2021 | 0 | PRINCE INDUTRIES (INDIA) | 50.27 | 0 | 0 | 0
6796 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) , SM/07272 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - SAULIA (Zone - G) . No.of Mouza :- 03 (Cahndanpur, Swargabati, Gopinathpur), Total House Hold -456, | FHTC/08 | 08/10/2021 | 0 | MUNMUN UPADHYAY | 33.29 | 0 | 0 | 0
6797 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) , SM/07272 | Retrofitting | Laying extra UPVC Pipe Line to Cover chotochaka, sonarekh mouzas for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte., | FHTC/08 | 08/10/2021 | 0 | KASTURI ROY | 2.17 | 0 | 0 | 0
6798 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) , SM/07272 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Indas W/S Scheme under Bishnupur Sub-Division, PHE Dte. | FHTC/11 | 11/10/2021 | 0 | SWAPAN KUMAR DE | 6.15 | 0 | 0 | 0
6799 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) , SM/07272 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 289 | 613/BQA | 10/02/2021 | 30 | OSMAN SEKH | 18.09 | 0 | 0 | 0
6800 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) , SM/07272 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 125 | 609/BQA | 10/02/2021 | 30 | OSMAN SEKH | 8.39 | 0 | 0 | 0
6801 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) , SM/07272 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 290 | 612/BQA | 10/02/2021 | 30 | SWAPAN KUMAR BIT | 19.65 | 0 | 0 | 0
6802 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) , SM/07272 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 140 | 610/BQA | 10/02/2021 | 30 | SWAPAN KUMAR BIT | 9.6 | 0 | 0 | 0
6803 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) , SM/07272 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANDHARTHOL (Zone - V) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharsole, No.of Mouza :- 09 (Andharthol (PART) , Sutijor, Shyamdanga, Ramjibanpur, Sunukpahari, Jamboni, Dabar, Tariba teridi & Haru Malliker Bonkata) Total House Hold - 499 | 619/BQA | 10/02/2021 | 30 | MUNMUN UPADHYAY | 35.36 | 0 | 0 | 0
6804 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) , SM/07272 | Retrofitting | Work Order for Laying HDPE pipeline from Dhabani Shib Mandir to Keliapathar village to increase pressure in Keliapathar village in Gobarda (152) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 06) | 210/KSD | 03/06/2022 | 20 | D. S. ENTERPRISE | 4.02 | 0 | 0 | 0
6805 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) , SM/07272 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67, Total House Hold - 166 out of 1275 Part-A (Phase-2) | 3047/BQA | 01/12/2021 | 30 | KOUSIK MONDAL | 12.53 | 0 | 0 | 0
6806 | BANKURA | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-A) , SM/07272 | Retrofitting | Material Requisition To Resource Division | 2036/BQA | 29/09/2022 | 0 | Resource Division | 1.9 | 0 | 0 | 0
6807 | BANKURA | Bankura Division | Nandagram Piped Water Supply Scheme , SM/14248 | New | Material Requisition To Resource Division | 79BQA | 06/01/2023 | 0 | Resource Division | 105.33 | 0 | 0 | 0
6808 | BANKURA | Bankura Division | Nandagram Piped Water Supply Scheme , SM/14248 | New | Material Requisition To Resource Division | 2994/BQA | 28/11/2024 | 0 | Resource Division | 19.29 | 0 | 0 | 0
6809 | BANKURA | Bankura Mechanical | Nandagram Piped Water Supply Scheme , SM/14248 | New | Nandagram Piped Water Supply Scheme | BP-2023-24-100 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 18.36 | 0 | 0 | 0
6810 | BANKURA | Bankura Division | Nandagram Piped Water Supply Scheme , SM/14248 | New | Construction of FHTC Platform, Sinking of Tubewell and Construction of Boundary Wall & Pump House for Augmentation of Joyrambati Piped Water Supply Scheme & Nandagram Piped Water Supply Scheme. | 657/BQA | 11/03/2025 | 90 | S B ASSOCIATES | 63.67 | 0 | 0 | 0
6811 | BANKURA | Bankura Division | Nandagram Piped Water Supply Scheme , SM/14248 | New | Instalation of scheme information board for 3 nos. sites of Nandagram Piped Water Supply Scheme (SM/14248) & 2 nos. sites of Khiri Piped Water Supply Scheme (SM/18436) within Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | 559/VSD | 27/09/2024 | 15 | SAFIQUE AHAMMAD KHAN | 0.75 | 0 | 0 | 100
6812 | BANKURA | Bankura Mechanical | Nandagram Piped Water Supply Scheme , SM/14248 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Nandagram Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | 444/BMD | 10/06/2025 | 90 | AMITAVA CHAKRABORTY | 12.97 | 0 | 0 | 0
6813 | BANKURA | Bankura Division | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/16959 | Augmentation | Material Requisition To Resource Division | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.23 | 0 | 0 | 0
6814 | BANKURA | Bankura Mechanical | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/16959 | Augmentation | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
6815 | BANKURA | Bankura Mechanical | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/16959 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Godardihi ( Zone-E) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | 1405/BMD | 18/07/2023 | 60 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 81.77 | 0 | 0 | 74
6816 | BANKURA | Bankura Division | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/16959 | Augmentation | Augmentation of Godardihi (Zone - E) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 2361/BQA | 14/08/2023 | 870 | MUNMUN UPADHYAY | 177.79 | 0 | 0 | 77
6817 | BANKURA | Bankura Division | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/16959 | Augmentation | Material Requisition To Resource Division | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.23 | 0 | 0 | 0
6818 | BANKURA | Bankura Division | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/16959 | Augmentation | Construction of High Lift Pump House and Boundary Wall under Augmentation works for Godardihi (Zone- E) under Bankura - I, II, Barjora Block Water Supply Scheme (BRGF Ph - I Project) | 45/BQA | 02/01/2025 | 454 | MUNMUN UPADHYAY | 31.04 | 0 | 0 | 0
6819 | BANKURA | Bankura Division | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/16967 | Augmentation | Material Requisition To Resource Division | 2732/BQA | 03/10/2023 | 0 | Resource Division | 4.42 | 0 | 0 | 0
6820 | BANKURA | Bankura Mechanical | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/16967 | Augmentation | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
6821 | BANKURA | Bankura Mechanical | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/16967 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electro mechanical accessories for Augmentation work for Harialgara (Zone O) under Bankura -I ,II Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | 1882/BMD | 17/08/2023 | 120 | MAHADEV ENTERPRISE | 81.83 | 0 | 0 | 42
6822 | BANKURA | Bankura Division | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/16967 | Augmentation | Material Requisition To Resource Division | 193/BQA | 22/01/2024 | 0 | Resource Division | 4.42 | 0 | 0 | 0
6823 | BANKURA | Bankura Division | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/16967 | Augmentation | Material Requisition To Resource Division | 1736/BQA | 05/07/2024 | 0 | Resource Division | 16.9 | 0 | 0 | 0
6824 | BANKURA | Bankura Mechanical | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/16967 | Augmentation | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | BP-2023-24-138 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.43 | 0 | 0 | 0
6825 | BANKURA | Bankura Division | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/16967 | Augmentation | Augmentation of HARIALGORA (Zone - O) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 2044/BQA | 24/07/2023 | 891 | PRADIP RAJAK | 310.94 | 0 | 0 | 54
6826 | BANKURA | Bankura Division | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/16967 | Augmentation | Balance allied works of augmentation works for Harialgara ( Zone-O ) under Bankura - I, II & Barjora Block water supply scheme. | 1815/BQA | 11/07/2024 | 570 | SUBHADIP KOLE | 245 | 0 | 0 | 0
6827 | BANKURA | Bankura Mechanical | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/16967 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System at Harialgara (Zone-O) OHR under Bankura-I.II and Barjora Water Supply Scheme under BMD PHE Dte. Dist Bankura. | 436/BMD | 10/06/2025 | 90 | M.S. ENTERPRISE | 26.28 | 0 | 0 | 0
6828 | BANKURA | Bankura Division | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/16967 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Harialgara (Zone- O) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | 450/BQA | 08/02/2024 | 30 | LEMNISCATE | 3.08 | 0 | 0 | 100
6829 | BANKURA | Bankura Mechanical | Construction of Grid-connected Solar Photo-Voltaic system for Joypur pump house-I of Joypur PWSS scheme,Dist: Bankura , SM/16932 | Solarisation | Acceptance cum Formal work order for the work of Construction of Grid-connected Solar Photo-voltaic System for Joypur Pumping Station P/H No-I of Joypur PWS Scheme under Bankura Mechanical Division PHE Dte. Dist: Bankura. | 659/BMD | 17/04/2023 | 831 | SUTRADHAR TRADERS | 6.65 | 0 | 0 | 90
6830 | BANKURA | Bankura Division | Augmentation of Sarberia Water Supply Schemes (Including Left Out BRGF Mouzas). , SM/16950 | Augmentation | Material Requisition To Resource Division | 2732/BQA | 03/10/2023 | 0 | Resource Division | 0.28 | 0 | 0 | 0
6831 | BANKURA | Bankura Division | Augmentation of Sarberia Water Supply Schemes (Including Left Out BRGF Mouzas). , SM/16950 | Augmentation | payment to rail | Rail04 | 11/04/2023 | 0 | SOUTH EASTERN RAILWAY | 0.98 | 0 | 0 | 0
6832 | BANKURA | Bankura Division | Augmentation of Sarberia Water Supply Schemes (Including Left Out BRGF Mouzas). , SM/16950 | Augmentation | Material Requisition To Resource Division | 193/BQA | 22/01/2024 | 0 | Resource Division | 0.28 | 0 | 0 | 0
6833 | BANKURA | Bankura Division | Augmentation of Sarberia Water Supply Schemes (Including Left Out BRGF Mouzas). , SM/16950 | Augmentation | Proposal of i) Bankura Saltora Road from CH : 11.715 KM and CH: 14.20 KM permanent restoration of road for the purpose of Jack pushing and opened cut method and pipe laying along Bankura Saltora Road for works under Augmentation of Sarberia water supply scheme by PHE under Bankura HIGHWAY Division in the district of Bankura. | FHTC/12 | 13/12/2023 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 78.25 | 0 | 0 | 0
6834 | BANKURA | Bankura Division | Augmentation of Sarberia Water Supply Schemes (Including Left Out BRGF Mouzas). , SM/16950 | Augmentation | Construction and Commissioning of Balance 'FHTC (Funtional House Hold Tap Connection) in mouzas of Augmentation of Sarberia Water Supply Schemes (Including Left Out BRGF Mouzas). Block - Chhatna, Dist.- Bankura under Jal Jeevan Mission programe under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block : - Chhatna, Name of Zone - Sarberia (Zone - I & II), No. of Mouza :- 38 nos. (Barabakra, Khairkanali, Laxminarayanpur, Kantasol, Pinasgoria, Ghoramuli, Dubrajpur, Bamunkuli, Mandaspara, Chowghara, Panchpukhuria, Janardanpur, Jhagrapur, Bhalaidiha, Brajamohanpur, Dhengakend, Gharamora, Musibdihi, Lohagar, Benagoria, Kalpathar, Ghosergram, Chamkara, Basulibandh, Karra, Beliara, Hari bandi, Migra, Siuligarya, Sarberia, Pathardihi, Mujra Kundi, Jamdahari, Kamarkuli, Kuludihi, Gurpota, Kalaiberia & Banagram). Total House Hold - 50 nos. | 803/BQA | 11/04/2023 | 996 | MANAS DEY | 13.61 | 0 | 0 | 91
6835 | BANKURA | Bankura Mechanical | Ground Water Based Nakaijuri Pipe Water Supply Scheme under Bankura Division, Block - Onda, District - Bankura. , SM/16694 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for proposed ground water based Nakaijuri piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Onda , Dist Bankura | 1709/BMD | 28/07/2023 | 60 | M/S BIPUL BANERJEE | 37.92 | 0 | 0 | 48
6836 | BANKURA | Bankura Division | Ground Water Based Nakaijuri Pipe Water Supply Scheme under Bankura Division, Block - Onda, District - Bankura. , SM/16694 | New | Material Requisition To Resource Division | 1120/BQA | 12/05/2023 | 0 | Resource Division | 9.91 | 0 | 0 | 0
6837 | BANKURA | Bankura Division | Ground Water Based Nakaijuri Pipe Water Supply Scheme under Bankura Division, Block - Onda, District - Bankura. , SM/16694 | New | Material Requisition To Resource Division | 2732/BQA | 03/10/2023 | 0 | Resource Division | 2.56 | 0 | 0 | 0
6838 | BANKURA | Bankura Division | Ground Water Based Nakaijuri Pipe Water Supply Scheme under Bankura Division, Block - Onda, District - Bankura. , SM/16694 | New | Supply , Delivery, Construction , Commissioning and completion of all Civil works including all allied, related and enabling works for Proposed Ground Water Based Nakaijuri Piped Water Supply Scheme under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Barjora, District -Bankura . Name of Mouza - Nakaijuri & Gorasol under JJM including Trial run for 3 months and O&M for a period of 3 years under Bankura Division, PHE Dte. | 2274/BQA | 01/08/2023 | 270 | SUBHANKAR BANERJEE | 263.83 | 0 | 0 | 25
6839 | BANKURA | Bankura Mechanical | Ground Water Based Nakaijuri Pipe Water Supply Scheme under Bankura Division, Block - Onda, District - Bankura. , SM/16694 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at TW No-III of Nakaijuri and its Adjoining mouza water supply scheme under Onda Block under Bankura Mechanical Division, PHE Dte. Dist: Bankura | 491/BMD | 09/07/2024 | 120 | SWAPAN ENTERPRISE | 19.95 | 0 | 0 | 0
6840 | BANKURA | Bankura Division | Ground Water Based Nakaijuri Pipe Water Supply Scheme under Bankura Division, Block - Onda, District - Bankura. , SM/16694 | New | Preparation of piped network system & design the same including Route Survey using DGPS & all related failed work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS for Gorasol (JL No- 278), Nakaijuri (JL No- 279) mouza under Onda Block all complete in consultation with PHED Planning Wings and clearance from SLSSC under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. | 284\BSD | 21/03/2022 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.74 | 0 | 0 | 97
6841 | BANKURA | Bankura Division | Ground Water Based Nakaijuri Pipe Water Supply Scheme under Bankura Division, Block - Onda, District - Bankura. , SM/16694 | New | Material Requisition To Resource Division | 193/BQA | 22/01/2024 | 0 | Resource Division | 2.56 | 0 | 0 | 0
6842 | BANKURA | Bankura Mechanical | Ground Water Based Nakaijuri Pipe Water Supply Scheme under Bankura Division, Block - Onda, District - Bankura. , SM/16694 | New | Ground Water Based Nakaijuri Pipe Water Supply Scheme under Bankura Division, Block - Onda, District - Bankura. | BP-2023-24-140 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.34 | 0 | 0 | 0
6843 | BANKURA | Bankura Division | Ground Water Based Nakaijuri Pipe Water Supply Scheme under Bankura Division, Block - Onda, District - Bankura. , SM/16694 | New | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir (Intze type with solid raft) of capacity 100 cum and staging height 20 mtr as per approved drawing (No:-PC-I/OHR/3/2012) in connection with Jal Jeevan Mission (JJM) for Proposed Ground Water Based Nakaijuri PIped Water Supply Scheme under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Onda, District -Bankura . Name of Muza - Gorasole & Nakaijuri | 574/BQA | 17/03/2023 | 929 | MS G. MITRA AND ASSOCIATES | 0.68 | 0 | 0 | 100
6844 | BANKURA | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). , SM/16952 | Augmentation | Continuation for supply 01 (One) no. Diesel / LPG / CNG driven Luxury Taxi / Bolero / Scorpio / Innova on hire basis for official use of Deputy Superintendig Engineer, PIU, WBDWSIP, PHE Dte. For the period from 01/04/2023 to 30/09/2023 (183 Days). | 287\BSD | 24/03/2023 | 183 | TARUN KUMAR BHATTACHARYYA | 0.87 | 0 | 0 | 100
6845 | BANKURA | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). , SM/16952 | Augmentation | Material Requisition To Resource Division | 2732/BQA | 03/10/2023 | 0 | Resource Division | 0.64 | 0 | 0 | 0
6846 | BANKURA | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). , SM/16952 | Augmentation | Material Requisition To Resource Division | 193/BQA | 22/01/2024 | 0 | Resource Division | 0.64 | 0 | 0 | 0
6847 | BANKURA | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). , SM/16952 | Augmentation | Bankura ¿Saltora Road at Ch:20.300 km to Ch: 24.00 Km Permanent restoration of road for the purpose of laying of UPVC pipe along and across of Jhantipahari HighSchool-Chhatna Saltora Road 20.30 km to 24.00km ( Bankura-Saltora Road) in connection with Augmentation of Sub-Surface water basd water supply scheme for Jhantipahari to accommodate FHTC in Chhatna Block under Bankura Highway Division in the district of Bankura. |  | 20/09/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 11.42 | 0 | 0 | 0
6848 | BANKURA | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). , SM/16952 | Augmentation | Bankura ¿Saltora Road at Ch:20.300 km to Ch: 24.00 Km Permanent restoration of road for the purpose of laying of UPVC pipe along and across of Jhantipahari HighSchool-Chhatna Saltora Road 20.30 km to 24.00km ( Bankura-Saltora Road) in connection with Augmentation of Sub-Surface water basd water supply scheme for Jhantipahari to accommodate FHTC in Chhatna Block under Bankura Highway Division in the district of Bankura. | BP-314/2024-25 | 25/09/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 11.42 | 0 | 0 | 0
6849 | BANKURA | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). , SM/16952 | Augmentation | Jhantipahari-Kashipur Road from Ch: 0.060 km to 0.760 Km Permanent Restoration of Road for the purpose of 'laying of UPVC pipe along & across of Jhantipahari High School ¿Chhatna Saltora Road 20.30 km to 24.00 km ( Bankura­Saltora Road) in connection with Augmentation of Sub-Surface water based water supply, scheme for Jhantipahari to accommodate FHTC in Chhatna Block' under Bankura Highway Division in the district of Bankura. SL NO:-4 |  | 20/09/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 63.73 | 0 | 0 | 0
6850 | BANKURA | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). , SM/16952 | Augmentation | Jhantipahari-Kashipur Road from Ch: 0.060 km to 0.760 Km Permanent Restoration of Road for the purpose of 'laying of UPVC pipe along & across of Jhantipahari High School ¿Chhatna Saltora Road 20.30 km to 24.00 km ( Bankura­Saltora Road) in connection with Augmentation of Sub-Surface water based water supply, scheme for Jhantipahari to accommodate FHTC in Chhatna Block' under Bankura Highway Division in the district of Bankura. SL NO:-4 | BP-313/2024-25 | 25/09/2024 | 0 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 63.73 | 0 | 0 | 0
6851 | BANKURA | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). , SM/16952 | Augmentation | Augmentation of Jhantipahari piped W/S Scheme (Zone - I) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | 2269/BQA | 01/08/2023 | 974 | M/S TARUN KUMAR PATRA | 153.91 | 0 | 0 | 82
6852 | BANKURA | Bankura Division | Augmentation for Gouripur Water Supply Scheme. , SM/17120 | Augmentation | Material Requisition To Resource Division | 2732/BQA | 03/10/2023 | 0 | Resource Division | 0.43 | 0 | 0 | 0
6853 | BANKURA | Bankura Mechanical | Augmentation for Gouripur Water Supply Scheme. , SM/17120 | Augmentation | Augmentation for Gouripur Water Supply Scheme. |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
6854 | BANKURA | Bankura Division | Augmentation for Gouripur Water Supply Scheme. , SM/17120 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection) & Sinking of 01 (One) no. 200 mm X 165 mm dia.X 280 mtr. deep Rig bore Tube Well (by DTH Rig machine) with allied works for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of Gouripur W/S Scheme under Bankura Sadar Sub -Division of Bankura division P.H.E.Dte. at Block- Bankura-I, Dist.- Bankura. No. of Household- 120 nos | 795/BQA | 11/04/2023 | 90 | SAIKAT CHOWDHURY | 50.64 | 0 | 0 | 85
6855 | BANKURA | Bankura Division | Augmentation for Gouripur Water Supply Scheme. , SM/17120 | Augmentation | Material Requisition To Resource Division | 193/BQA | 22/01/2024 | 0 | Resource Division | 0.43 | 0 | 0 | 0
6856 | BANKURA | Bankura Division | Augmentation for Gouripur Water Supply Scheme. , SM/17120 | Augmentation | Construction of 01 (One) no. Pump House (5.40 M X 3.6M) including sanitary arrangement & land development work in connection with Jal Jeevan Mission (JJM) for Augmentation of Gouripur W/S Scheme under Bankura Sadar Sub -Division of Bankura division P.H.E.Dte. at Block- Bankura-I, Dist.- Bankura | 886/BQA | 19/04/2023 | 713 | ARIJIT GUHA | 8.25 | 0 | 0 | 100
6857 | BANKURA | Bankura Mechanical | Augmentation for Gouripur Water Supply Scheme. , SM/17120 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Gouripur Water Supply Scheme under Bankura Mechanical Division, PHE Dte. Block : Bankura-I ,Dist: Bankura | 1778/BMD | 01/08/2023 | 600 | KASHINATH DEY | 23.42 | 0 | 0 | 100
6858 | BANKURA | Bankura Division | Augmentation for Gouripur Water Supply Scheme. , SM/17120 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation for Gouripur Water Supply Scheme. under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | 443/BQA | 08/02/2024 | 30 | LEMNISCATE | 0.46 | 0 | 0 | 100
6859 | BANKURA | Bankura Division | Augmentation works for Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) , SM/17123 | Augmentation | Material Requisition To Resource Division | 1120/BQA | 12/05/2023 | 0 | Resource Division | 25.08 | 0 | 0 | 0
6860 | BANKURA | Bankura Mechanical | Augmentation works for Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) , SM/17123 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation work for Banpukuria under Khatra- Hirbandh- Ranibandh water supply scheme Block- Ranibandh under Bankura Mechanical Division, P.H.E. Dte. | 2207/BMD | 21/11/2023 | 180 | M/S BIPUL BANERJEE | 40.48 | 0 | 0 | 78
6861 | BANKURA | Bankura Division | Augmentation works for Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) , SM/17123 | Augmentation | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | 2953/BQA | 31/10/2023 | 60 | K S GROUP | 5.18 | 0 | 0 | 70
6862 | BANKURA | Bankura Division | Augmentation works for Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) , SM/17123 | Augmentation | Material Requisition To Resource Division | 116/BQA | 10/01/2024 | 0 | Resource Division | 3.35 | 0 | 0 | 0
6863 | BANKURA | Bankura Division | Augmentation works for Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) , SM/17123 | Augmentation | Sinking of 2 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) to CWR with allied works, Construction of 50 Cum. Clear Water Reservoir, Pump House and Boundary Wall, Construction of Over Head Reservoir (100 Cum.) with ancillary works, Laying Rising Main, Distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for Augmentation works for Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 2359/BQA | 14/08/2023 | 270 | SUMITA UPADHYAY | 164.56 | 0 | 0 | 30
6864 | BANKURA | Bankura Mechanical | Construction of Grid-connected Solar Photo-voltaic System for Mukutmonipur Pumping Station of Mukutmonipur PWS Scheme, Dist: Bankura. , SM/17238 | Solarisation | Acceptance cum Formal work order for the work of Construction of Grid-connected Solar Photo-voltaic System for Mukutmanipur PWS Scheme under Bankura Mechanical Division PHE Dte. Dist: Bankura. | 650/BMD | 17/04/2023 | 60 | UNITED TRADERS | 49.25 | 0 | 0 | 80
6865 | BANKURA | Bankura Mechanical | Construction of Grid-connected Solar Photo-voltaic System for Mukutmonipur Pumping Station of Mukutmonipur PWS Scheme, Dist: Bankura. , SM/17238 | Solarisation | Application for Solar Power Plant of 90KWp Solar Power Plant at Mukutmanipur old WTP site [Consumer Id No-942311700 ] under Bankura Mechanical Division P.H.E Dte | BP-2024-25-110 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.02 | 0 | 0 | 0
6866 | BANKURA | Bankura Mechanical | Construction of Grid-connected Solar Photo-voltaic System for Mukutmonipur Pumping Station of Mukutmonipur PWS Scheme, Dist: Bankura. , SM/17238 | Solarisation | Acceptance cum Formal work order for the work of Construction of Grid-connected Solar Photo-voltaic System for Mukutmanipur PWS Scheme at new WTP site under Bankura Mechanical Division PHE Dte. Dist: Bankura | 3067/BMD | 12/03/2024 | 360 | M/S INSILICA | 71.69 | 0 | 0 | 100
6867 | BANKURA | Bankura Mechanical | Construction of Grid-connected Solar Photo-voltaic System for Mukutmonipur Pumping Station of Mukutmonipur PWS Scheme, Dist: Bankura. , SM/17238 | Solarisation | Acceptance cum Formal work order for the work of Provide installation of Zero Export Device with other accessories for Construction of Grid connected Solar Photo voltaic System for Mukutmanipur PWS Scheme under Bankura Mechanical Division PHE Dte. Dist: Bankura | 3061/BMD | 12/03/2024 | 455 | UNITED TRADERS | 5.5 | 0 | 0 | 100
6868 | BANKURA | Bankura Mechanical | Construction of Grid-Connected solar photo -voltaic system for Chhoto Birbhanpur PWSS scheme Dist Bankura , SM/17239 | Solarisation | Acceptance cum Formal work order for the work of Construction of Grid-connected Solar Photo-voltaic System for Chhoto Birbhanpur Pump House No-II PWS Scheme under Bankura Mechanical Division PHE Dte. Dist: Bankura. | 649/BMD | 17/04/2023 | 60 | M/S BIPUL BANERJEE | 7.8 | 0 | 0 | 80
6869 | BANKURA | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) , SM/17254 | Augmentation | Work Order for Interconnection of newly laid pipeline and existing pipeline near Arkama village of Augmentation works for Arkama (Zone- H) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | 254/KSD | 24/08/2023 | 7 | M/S SUPRIYA CHATTERJEE | 0.95 | 0 | 0 | 20
6870 | BANKURA | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) , SM/17254 | Augmentation | Work Order for Interconnection of newly laid pipeline and existing pipeline near Sindurpeti village of Augmentation works for Arkama (Zone- H) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 258/KSD | 24/08/2023 | 7 | GOURANGA CHATTERJEE | 0.7 | 0 | 0 | 20
6871 | BANKURA | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) , SM/17254 | Augmentation | Work Order for Interconnection of newly laid pipeline and existing pipeline near Arkama village of Augmentation works for Arkama (Zone- H) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) | 256/KSD | 24/08/2023 | 7 | M/S SUPRIYA CHATTERJEE | 0.7 | 0 | 0 | 20
6872 | BANKURA | Bankura Mechanical | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) , SM/17254 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of High lift and Low Lift Pumping machineries with other electro-mechanical accessories at tail end and CWR site for for Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) under Bankura Mechanical Division, PHE Dte. Block : Khatra , Dist: Bankura | 511/BMD | 09/07/2024 | 120 | RAJIB COMPANY | 44.01 | 0 | 0 | 0
6873 | BANKURA | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) , SM/17254 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-H (Arkama) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 726/BQA | 30/03/2023 | 45 | UTTAM KUMAR SINHAMAHAPATRA | 48.95 | 0 | 0 | 100
6874 | BANKURA | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) , SM/17254 | Augmentation | Laying HDPE pipeline to increase pressure in Damodarpur Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection) of Zone-H (Arkama) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 247/BQA | 25/01/2024 | 30 | BIKASH MANDAL | 5.11 | 0 | 0 | 80
6875 | BANKURA | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) , SM/17254 | Augmentation | Material Requisition To Resource Division | 116/BQA | 10/01/2024 | 0 | Resource Division | 2.96 | 0 | 0 | 0
6876 | BANKURA | Bankura Division | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) , SM/17254 | Augmentation | Sinking of 2 Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine), Construction of 1 No. CWR at OHR site, Construction of 1 No. Pump House at Tubewell site, Laying of pipeline and Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Augmentation works for Zone-H (Arkama) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 1521/BQA | 19/06/2024 | 30 | SINGHA ENTERPRISE | 51.88 | 0 | 0 | 70
6877 | BANKURA | Bankura Mechanical | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) , SM/17254 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of High lift and Low Lift Pumping machineries with other electro-mechanical accessories at CWR site for for Augemention works for Arkama (zone H) Under Khatra Hirbandh Ranibandh Water Supply Scheme under Bankura Mechanical Division, PHE Dte. Block Khatra , Dist Bankura | 2040/BMD | 07/03/2025 | 120 | M/S TARUN KUMAR PATRA | 42.61 | 0 | 0 | 0
6878 | BANKURA | Bankura Mechanical | Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) , SM/17254 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Arkama (Zone H) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura | 247/BMD | 14/05/2025 | 90 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 29.11 | 0 | 0 | 0
6879 | BANKURA | Bankura Division | Augmentation of Kushmuri Zone-A Water Supply Scheme , SM/17420 | Augmentation | Construction of 2nos. boundary wall approx 60 mtr long for Kushmuri Zone- A water supply scheme in Indas Block under Bishnupur Sub Division of Bankura Division, PHE Dte. | 2630/BQA | 21/09/2023 | 180 | ANNDAMAYEE CONSTRUCTION | 8.86 | 0 | 0 | 0
6880 | BANKURA | Bankura Mechanical | Augmentation of Kushmuri Zone-A Water Supply Scheme , SM/17420 | Augmentation | Augmentation of Kushmuri Zone-A Water Supply Scheme |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
6881 | BANKURA | Bankura Division | Augmentation of Kushmuri Zone-A Water Supply Scheme , SM/17420 | Augmentation | Construction of Boundary Wall and Pump House for Augmentation of Kushmuri (Zone-A) Piped Water Supply Scheme. | 3178/BQA | 24/12/2024 | 90 | BIJOY KOLEY | 12.97 | 0 | 0 | 0
6882 | BANKURA | Bankura Division | Augmentation of Kushmuri Zone-A Water Supply Scheme , SM/17420 | Augmentation | Laying distribution system for Kushmuri Zone- A W/S Scheme (BRGF Phase-I) within Indas Block in connection with Jal Jeevan Mission (JJM) under Bishnupur Sub-Division of Bankura Division, PHE Dte. | 2628/BQA | 21/09/2023 | 222 | MAYA CONSTRUCTION | 10.92 | 0 | 0 | 15
6883 | BANKURA | Bankura Mechanical | Augmentation of Kushmuri Zone-A Water Supply Scheme , SM/17420 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Kushmuri (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura. | 1700/BMD | 28/07/2023 | 891 | TAPAN KUMAR SARKAR | 59.31 | 0 | 0 | 53
6884 | BANKURA | Bankura Division | Augmentation of Kushmuri Zone-A Water Supply Scheme , SM/17420 | Augmentation | Construction of 2 nos. Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.0 m x 4.0 m) for Kushmuri Zone- A Water Supply Scheme wihin Indas block under Bishnupur Sub Division of Bankura Division P.H.E. Dte. | 2629/BQA | 21/09/2023 | 553 | SAYED PAHALOWAN | 13.23 | 0 | 0 | 30
6885 | BANKURA | Bankura Division | Augmentation of Kushmuri Zone-A Water Supply Scheme , SM/17420 | Augmentation | Creation of 'FHTC (Funtional House Hold Tap Connection)' for extra house hold in connection with Jal Jeevan Mission (JJM) of Kushmuri Zone- A W/S Scheme (BRGF Phase-I) within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. Block Name:- Indas, Location of OHR :- Gobindapur, No. of Mouzas Covered :- 5 nos., Name of Mouzas & JL No.:- Sanpura (57), Jagaldwip (58), Dasaratbati (61), Bhabapur (100), Kushmuri (98) Total No. House Hold:- 55 | 2865/BQA | 11/10/2023 | 45 | MOHAN KUMAR ROY | 28.65 | 0 | 0 | 45
6886 | BANKURA | Bankura Division | Augmentation of Kushmuri Zone-A Water Supply Scheme , SM/17420 | Augmentation | Creation of 'FHTC (Funtional House Hold Tap Connection)' for extra house hold in connection with Jal Jeevan Mission (JJM) of Kushmuri Zone- A W/S Scheme (BRGF Phase-I) within Indas Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. Block Name:- Indas, Location of OHR :- Gobindapur, No. of Mouzas Covered :- 5 nos., Name of Mouzas & JL No.:- Sanpura (57), Jagaldwip (58), Dasaratbati (61), Bhabapur (100), Kushmuri (98) Total No. House Hold:- 55 | 2864/BQA | 11/10/2023 | 538 | GOURANGA NANDI | 28.65 | 0 | 0 | 95
6887 | BANKURA | Bankura Mechanical | Augmentation of Kushmuri Zone-A Water Supply Scheme , SM/17420 | Augmentation | Acceptance cum Formal work order for the work of Augmentation of sub- station equipment at Kushmuri (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura. | 776/BMD | 20/08/2024 | 120 | M.S. ENTERPRISE | 14.05 | 0 | 0 | 100
6888 | BANKURA | Bankura Division | Augmentation of Prakash Zone-A Water Supply Scheme , SM/17222 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PRAKASH ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | 1966/BQA | 18/07/2023 | 624 | SIB SANKAR CHOWDHURY | 164.12 | 0 | 0 | 60
6889 | BANKURA | Bankura Division | Augmentation of Prakash Zone-A Water Supply Scheme , SM/17222 | Augmentation | Sinking of 1 no Tubewell and Construction of Pump House for Augmentation of Prakash (Zone - A) Water Supply Scheme. | 3130/BQA | 19/12/2024 | 90 | ZAKIR HOSSIN MONDAL | 20.45 | 0 | 0 | 15
6890 | BANKURA | Bankura Division | Nandur Piped Water Supply Scheme , SM/18252 | New | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Patrasayer Block under Bishnupur Sub-Division under Bankura Division, PHE Dte.. | 1116/BQA | 18/05/2022 | 60 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 156.95 | 0 | 0 | 100
6891 | BANKURA | Bankura Division | Nandur Piped Water Supply Scheme , SM/18252 | New | Material Requisition To Resource Division | 79BQA | 06/01/2023 | 0 | Resource Division | 163.02 | 0 | 0 | 0
6892 | BANKURA | Bankura Mechanical | Nandur Piped Water Supply Scheme , SM/18252 | New | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Nandur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | 581/BMD | 04/07/2025 | 90 | OSMAN SEKH | 12.68 | 0 | 0 | 0
6893 | BANKURA | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17697 | Augmentation | Creation of Balance FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) of CHERABASTA (Zone - K)) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Cherabasta No.of Mouza :- 01 nos. Teleghara . Total House Hold -13 nos. | 61/BSD | 24/01/2023 | 7 | COSMIC CONSTRUCTION | 0.97 | 0 | 0 | 100
6894 | BANKURA | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17697 | Augmentation | Material Requisition To Resource Division | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.92 | 0 | 0 | 0
6895 | BANKURA | Bankura Mechanical | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17697 | Augmentation | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
6896 | BANKURA | Bankura Mechanical | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17697 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Cherabasta (Zone-K) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | 1411/BMD | 18/07/2023 | 60 | DEBJYOTI BASU | 81.81 | 0 | 0 | 80
6897 | BANKURA | Bankura Mechanical | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17697 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories for P/H No- I at Tail End site of Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II and Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Mechanical Division, P.H.E. Dte | 856/BMD | 29/08/2024 | 120 | CHAKRABORTY MINING & ENGINEERING. | 9.23 | 0 | 0 | 60
6898 | BANKURA | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17697 | Augmentation | Design Making & Erection of Disply board using Logo and tag line of Jal Jeevan Mission to the place at Gopinathpur (271), Teleghara (286 ), Bagneja (287), Ailtha (281) & Cherabasta (256), of Swajal Gram/Har Ghar Jal Villages for awareness generation among the pepole of Bankura Sadar Sub-Division under Bankura Division, PHE Dte. | 1176/BSD | 22/11/2023 | 15 | TAPAS DEY | 0.69 | 0 | 0 | 100
6899 | BANKURA | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17697 | Augmentation | Material Requisition To Resource Division | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.92 | 0 | 0 | 0
6900 | BANKURA | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17697 | Augmentation | Wayleave/Track crossing proposal with application ID:SER-ADRA-WL-12 For Cherabasta (zone-k) SM Code-SM/SM/17697 | FHTC/04 | 26/04/2024 | 0 | SOUTH EASTERN RAILWAY | 0.11 | 0 | 0 | 0
6901 | BANKURA | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17697 | Augmentation | Payment of Wayleave facility charges of CHERABASTA (ZONE-K) W/S Scheme. Scheme Code-SM/17697. Application ID-SER-ADRA-2024-WL-12 | BP-113/2024-25 | 19/06/2024 | 0 | SOUTH EASTERN RAILWAY | 6.4 | 0 | 0 | 0
6902 | BANKURA | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17697 | Augmentation | Augmentation works for CHERABASTA (ZONE - K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Phase - I Project). | 2001/BQA | 19/07/2023 | 983 | S.N POLYMERS PVT LTD | 297.16 | 0 | 0 | 55
6903 | BANKURA | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17697 | Augmentation | Construction of High lift Pump House, Pump House cum chlorine room & Toilet, Boundary wall of Augmentation of CHERABASTA (Zone - K) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 360/BQA | 07/02/2025 | 328 | SAIKAT CHOWDHURY | 37.52 | 0 | 0 | 0
6904 | BANKURA | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17697 | Augmentation | Crossing Rail Track ( South Eastern RLY. K.M. 234/10 -11) in between Bikna Rly. Station and Bankura Rly. station in Mobarakpur mouza, P.S. Bankura,by HDD method with 300 mm (OD) MS Casing Pipe with 150 mm dia. MS carrier pipe for Rising main pipe line under Augmentation of CHERABASTA (Zone - K) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 1327/BQA | 17/06/2025 | 45 | GOPAL CHANDRA CHOWDHURY | 47.66 | 0 | 0 | 0
6905 | BANKURA | Bankura Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17697 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Cherabasta (Zone- K) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | 446/BQA | 08/02/2024 | 30 | LEMNISCATE | 2.31 | 0 | 0 | 100
6906 | BANKURA | Bankura Division | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17698 | Augmentation | Material Requisition To Resource Division | 2732/BQA | 03/10/2023 | 0 | Resource Division | 1.95 | 0 | 0 | 0
6907 | BANKURA | Bankura Mechanical | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17698 | Augmentation | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
6908 | BANKURA | Bankura Mechanical | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17698 | Augmentation | Acceptance cum Formal work order for the work ofProviding and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Chaterkanali (Zone-L) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | 1464/BMD | 18/07/2023 | 60 | TAPAN KUMAR DEY | 81.77 | 0 | 0 | 64
6909 | BANKURA | Bankura Division | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17698 | Augmentation | Augmentation of CHATARKANALI (Zone - L) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 2271/BQA | 01/08/2023 | 270 | MADHU SUDAN RAKSHIT | 198.06 | 0 | 0 | 70
6910 | BANKURA | Bankura Division | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17698 | Augmentation | Material Requisition To Resource Division | 193/BQA | 22/01/2024 | 0 | Resource Division | 1.95 | 0 | 0 | 0
6911 | BANKURA | Bankura Division | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17698 | Augmentation | Laying of 150 mm dia underground water pipe line carrier with 600 mm dia MS casing under Railway Track of KM 239/4-5 in beet ween Rly station Bikna Nabanda station beet ween Bankura Masagram section | FHTC/04 | 18/04/2024 | 0 | SOUTH EASTERN RAILWAY | 5.63 | 0 | 0 | 0
6912 | BANKURA | Bankura Division | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17698 | Augmentation | Construction of High lift Pump House at OHR Site of departmental design & drawing in connection with Jal Jeevan Mission (JJM) for Augmentation of CHATARKANALI (Zone - L) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 2343/BQA | 09/09/2024 | 660 | ASHIS PAL | 18 | 0 | 0 | 0
6913 | BANKURA | Bankura Division | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17698 | Augmentation | Crossing Rail Track ( South Eastern RLY. K.M. 239/4 -5) in between Bikna-Nobanda) Rly. Station and Bankura-Masagram Rly. station in Nabanda mouza, P.S. Bankura,by HDD method with 300 mm (OD) MS Casing Pipe with 150 mm dia. MS carrier pipe for distribution pipe under Augmentation of CHAtarkanali (Zone - L) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | 1326/BQA | 17/06/2025 | 45 | M/S TARUN KUMAR PATRA | 50.82 | 0 | 0 | 0
6914 | BANKURA | Bankura Division | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). , SM/17698 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Chatarkanali (Zone- L) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | 447/BQA | 08/02/2024 | 30 | LEMNISCATE | 1.69 | 0 | 0 | 100
6915 | BANKURA | Bankura Division | Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) , SM/17304 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-E (Naria) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 557/BQA | 17/03/2023 | 45 | ASHOKE KUMAR DEY | 72.75 | 0 | 0 | 55
6916 | BANKURA | Bankura Division | Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) , SM/17304 | Augmentation | Work Order for Extension of UPVC pipeline at Debedia village under Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) | 262/KSD | 24/08/2023 | 15 | S. S. S. ENTERPRISES | 0.6 | 0 | 0 | 25
6917 | BANKURA | Bankura Division | Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) , SM/17304 | Augmentation | Work Order for Extension of UPVC pipeline at Debedia village under Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | 260/KSD | 24/08/2023 | 15 | S. S. S. ENTERPRISES | 0.74 | 0 | 0 | 25
6918 | BANKURA | Bankura Division | Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) , SM/17304 | Augmentation | Material Requisition To Resource Division | 116/BQA | 10/01/2024 | 0 | Resource Division | 2.59 | 0 | 0 | 0
6919 | BANKURA | Bankura Mechanical | Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) , SM/17304 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Naria (Zone E) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | 252/BMD | 14/05/2025 | 90 | WEST BENGAL ENGINEERING CO. | 28.18 | 0 | 0 | 0
6920 | BANKURA | Bankura Division | Augmentation works for Naria (Zone- E) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) , SM/17304 | Augmentation | Laying HDPE pipeline from Dighi to Dhajamanipur and at Brahmadanga village to increase pressure at Dhajamanipur and Brahmadanga village in connection with Augmentation of Naria (Zone-E) Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 2304/BQA | 04/09/2024 | 485 | MANAS DEY | 7.44 | 0 | 0 | 90
6921 | BANKURA | Bankura Mechanical | Augmentation of Somsar (BRGF) Water Supply Scheme , SM/17579 | Augmentation | Acceptance cum Formal work order for the work of Supply, delivery and installation of HSC Pumping machinery set with other allied works at CWR site for augmentation of Somsar water supply scheme under Bankura Mechanical Division P.H.E Dte. | 785/BMD | 20/08/2024 | 240 | ABHIJIT MUKHERJEE | 34.91 | 0 | 0 | 60
6922 | BANKURA | Bankura Division | Augmentation of Somsar (BRGF) Water Supply Scheme , SM/17579 | Augmentation | Repairing and Renovation of RCC Elevated Over Head Reservoir of 250 cum capacity with staging height 20 m and other allied works in connection with Somsar (BRGF) water supply scheme within Bishnupur Sub-Division under Bankura Division, PHE Dte. | 2351/BQA | 09/09/2024 | 204 | TAPAN KUMAR MANDAL | 9.49 | 0 | 0 | 100
6923 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas by retrofitting of Water S , SM/09234 | Retrofitting | Work Order for Household survey in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 03) | 789/KSD | 14/12/2021 | 90 | TAPAS DEY | 0.32 | 0 | 0 | 0
6924 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas by retrofitting of Water S , SM/09234 | Retrofitting | Laying HDPE pipeline to cover Jamirapara (50) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 546/BQA | 11/03/2022 | 30 | ASHOKE KUMAR DEY | 24.68 | 0 | 0 | 0
6925 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas by retrofitting of Water S , SM/09234 | Retrofitting | Household survey in Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. | FHTC/6 | 06/06/2022 | 0 | TAPAS DEY | 0.3 | 0 | 0 | 0
6926 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas by retrofitting of Water S , SM/09234 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Patpur (214), Maharadihi (215), Dharampur (216), Baragari (220), Datarampur (221), Pithabaid (222), Radhanathpur (259) & Saluka (260) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | FHTC/4 | 04/03/2022 | 0 | MUNMUN UPADHYAY | 34.71 | 0 | 0 | 0
6927 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas by retrofitting of Water S , SM/09234 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 02 no, (Sanpura, Kalipahari), Total House Hold - 451 | FHTC/4 | 04/03/2022 | 0 | TARINI CHARAN UPADHYAY | 27.97 | 0 | 0 | 0
6928 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas by retrofitting of Water S , SM/09234 | Retrofitting | Laying of extra UPVC pipeline in Parashia (47) & Jamirapara (50) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 509/BQA | 13/03/2023 | 45 | MANAS DEY | 4.52 | 0 | 0 | 0
6929 | BANKURA | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas by retrofitting of Water S , SM/09234 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 2496/BQA | 23/09/2021 | 30 | ASOKE BHATTACHARYYA | 52.85 | 0 | 0 | 0
6930 | BANKURA | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Work Order for Relaying of distribution main by UPVC pipe along with allied works at culvert portion (Culvert No. 01) for Strengthening - Widening of road from Moukura Pitch road to Bardi Nadighat by PMGSY of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 196/KSD | 13/07/2023 | 7 | S. B. CONSTRUCTION | 0.97 | 0 | 0 | 95
6931 | BANKURA | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Work Order for Relaying of distribution main by UPVC pipe along with allied works at culvert portion (Culvert No. 02) for Strengthening - Widening of road from Moukura Pitch road to Bardi Nadighat by PMGSY of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 197/KSD | 13/07/2023 | 7 | S. B. CONSTRUCTION | 0.97 | 0 | 0 | 95
6932 | BANKURA | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Work Order for Relaying of distribution main by UPVC pipe along with allied works at culvert portion (Culvert No. 03) for Strengthening - Widening of road from Moukura Pitch road to Bardi Nadighat by PMGSY of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 198/KSD | 13/07/2023 | 7 | S. B. CONSTRUCTION | 0.97 | 0 | 0 | 90
6933 | BANKURA | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Work Order for Relaying of distribution main by UPVC pipe along with allied works at culvert portion (Culvert No. 04) for Strengthening - Widening of road from Moukura Pitch road to Bardi Nadighat by PMGSY of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 199/KSD | 13/07/2023 | 7 | S. B. CONSTRUCTION | 0.95 | 0 | 0 | 95
6934 | BANKURA | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
6935 | BANKURA | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Voltage Stabilizer and submersible pumping machineries with other allied works for Augmentation of Sarenga water supply scheme under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | 573/BMD | 23/07/2024 | 120 | TAPAN KUMAR SARKAR | 25.19 | 0 | 0 | 0
6936 | BANKURA | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Belatikari (Zone A) piped water supply scheme (BRGF Phase-I) at tubewell No I Pump House No I under Bankura Mechanical Division, PHE Dte. Block : Sarenga , Dist: Bankura | 2964/BMD | 29/02/2024 | 180 | INDRAJIT MITRA | 12.8 | 0 | 0 | 50
6937 | BANKURA | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Belatikari (Zone A) piped water supply scheme (BRGF Phase I) at tubewell No III Pump House No III under Bankura Mechanical Division, PHE Dte. Block : Sarenga , Dist: Bankura | 2970/BMD | 29/02/2024 | 180 | M/S DAS & SARKAR ENTERPRISE | 12.76 | 0 | 0 | 50
6938 | BANKURA | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Laying of HDPE pipeline, Sinking of 3 Nos. 300 mm X 200 mm X 250 Metre deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe, Construction of Valve Chamber for Augmentation of Water Supply Scheme for Belatikri, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 1484/BQA | 18/06/2024 | 90 | SIBSANKAR CHOWDHURY | 96.77 | 0 | 0 | 0
6939 | BANKURA | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Relaying of distribution main by HDPE pipe along with allied works for Strengthening - Widening of road from Moukura Pitch road to Bardi Nadighat by PMGSY of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 2944/BQA | 30/10/2023 | 30 | RAHIBUDDIN MANDAL | 11.74 | 0 | 0 | 100
6940 | BANKURA | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub Division of Bankura Division, P.H.E. Dte. | 2960/BQA | 31/10/2023 | 30 | MEASURE LAND | 2.37 | 0 | 0 | 96
6941 | BANKURA | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Relaying of distribution main by HDPE pipe along with allied works for Strengthening - Widening of road from Moukura Pitch road to Bardi Nadighat by PMGSY of Augmentation works for Belatikri, Zone-A Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 2943/BQA | 30/10/2023 | 120 | M/S SUPRIYA CHATTERJEE | 11.74 | 0 | 0 | 100
6942 | BANKURA | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Acceptance cum Formal work order for the work of Additional work for Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation for Belatikri Zone-A water supply scheme(BRGF Ph-I) under Jal Jeevan Mission Progremme under Bankura Mechanical Division PHE Dte, Dist.-Bankura. | 519/BMSD(D) | 11/06/2024 | 21 | M.S. ENTERPRISE | 2.8 | 0 | 0 | 100
6943 | BANKURA | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Material Requisition To Resource Division | 116/BQA | 10/01/2024 | 0 | Resource Division | 2.96 | 0 | 0 | 0
6944 | BANKURA | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | New service connection for Belatikri Zone-A , Jl -39, Plot-233 | BP-2024-25-279 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.22 | 0 | 0 | 0
6945 | BANKURA | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | New3 Phase Service Connection for Belatikri | BP-2024-25-162 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0 | 0
6946 | BANKURA | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | New service connection for Belatikri Zone-A JL-30, Plot-104 | BP-2024-25-278 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.65 | 0 | 0 | 0
6947 | BANKURA | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | New service connection for Belatikri water supply scheme under Bankura Mechanical Division PHE Dte. | BP-2024-25-83 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0 | 0
6948 | BANKURA | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well (Replacement Tubewell), using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas for Augmentation of Water Supply Scheme for Belatikri, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 2039/BQA | 24/07/2023 | 270 | UNIVERSAL CONSTRUCTION | 154.39 | 0 | 0 | 30
6949 | BANKURA | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Belatikari (Zone A) piped water supply scheme (BRGF Phase I) at tubewell No II Pump House No II under Bankura Mechanical Division, PHE Dte. Block : Sarenga , Dist: Bankura | 2967/BMD | 29/02/2024 | 712 | PRADIP KUMAR DHABAL | 12.8 | 0 | 0 | 65
6950 | BANKURA | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Repairing and painting of Over Head Reservoir (Capacity 350 Cum., staging height 20 Mtr.), High lift Pump House, Operator Room, Clear Water Reservoir, WBSEDCL Room, Chlorination Room, Guard Room and Boundary Wall with all allied works of Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 670/BQA | 12/03/2025 | 90 | SAIKAT CHOWDHURY | 18.11 | 0 | 0 | 0
6951 | BANKURA | Bankura Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Construction of 3 (Three) Nos. Pump House and Boundary wall at Tubewell site for Augmentation of Water Supply Scheme for Belatikri, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 832/BQA | 07/04/2025 | 184 | TAPAS KUMAR HAZRA | 58.06 | 0 | 0 | 0
6952 | BANKURA | Bankura Mechanical | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. , SM/17713 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation for Belatikri Zone-A water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | 2026/BMD | 01/09/2023 | 911 | M.S. ENTERPRISE | 96.39 | 0 | 0 | 70
6953 | BANKURA | Bankura Division | Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) , SM/17430 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-IIB (Hetiasol) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 559/BQA | 17/03/2023 | 45 | SK. SAHAJAHAN | 32.01 | 0 | 0 | 50
6954 | BANKURA | Bankura Division | Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) , SM/17430 | Augmentation | Sinking of 3 (Three) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works for Zone-IIB (Hetiasol) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 202/BQA | 24/01/2024 | 75 | UTTAM KUMAR SINHAMAHAPATRA | 22.34 | 0 | 0 | 90
6955 | BANKURA | Bankura Division | Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) , SM/17430 | Augmentation | Material Requisition To Resource Division | 116/BQA | 10/01/2024 | 0 | Resource Division | 1.91 | 0 | 0 | 0
6956 | BANKURA | Bankura Mechanical | Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) , SM/17430 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low lift pumping machineries and other electromechanical accessories for Dahala W.S Scheme under Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) under Bankura Mechanical Division PHE Dte, Dist :Bankura. | 494/BMD | 09/07/2024 | 328 | ABHIJIT MUKHERJEE | 65.43 | 0 | 0 | 63
6957 | BANKURA | Bankura Mechanical | Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) , SM/17430 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Hetiasol (Zone IIB) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | 245/BMD | 14/05/2025 | 90 | TAPAN KUMAR DEY | 28.18 | 0 | 0 | 0
6958 | BANKURA | Bankura Division | Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) , SM/17430 | Augmentation | Laying HDPE pipeline from Dakai to Madhabpur village to increase pressure at Madhabpur Village in connection with Augmentation of Hetiasole (Zone-IIB) Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 2303/BQA | 04/09/2024 | 151 | JAGABANDHU MONDAL | 2.78 | 0 | 0 | 70
6959 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Laying districution system using different dia D.I K7 pipes for improvement of Khatra - Ranibandh-Hirbandh water supply scheme under BRGF ph - 1 under Bankura Division PHE Dte. Zone - K Sl no - 04 | FHTC/17 | 17/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 11.88 | 0 | 0 | 0
6960 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Laying extra HDPE pipe lineto cover Budhkhila (60) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- J (Rudra ) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 19 | IMP/K-R-H | 15/03/2022 | 0 | GOPAL CHANDRA CHOWDHURY | 4.7 | 0 | 0 | 0
6961 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Supply of M.S pipe for laying the sa,e during HDD boring including cutting, welding and other allied works for road crossing in connection with the work of Improvement to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. zone - M2 sl no - 18 | IMP/K-R-H | 15/03/2022 | 0 | DEBAKI RANJAN SARKAR | 3.38 | 0 | 0 | 0
6962 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Biradihi (39) & Diktor (40) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | IMP/K-R-H | 15/03/2022 | 0 | PARTHA PRATIM CHHATAIT | 23.59 | 0 | 0 | 0
6963 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Making HDD (Horizontal directional) bore & laying of various size casing pipes/water main inside HDD bore in rocky zone area ......including cutting the driving & receiving pit as per required size for crossing the national /..............using various machineries such as crane, jack, jacking materials, pushing jack technology .performing the work including mobilization charge of machneries required fro performing the work as per direction of the EIC conncetion with Improvement to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) under Khatra Sub - Division of Bankura Division, PHE Dte. zone - M2 sl no - 17 | IMP/K-R-H | 15/03/2022 | 0 | DEBAKI RANJAN SARKAR | 3.71 | 0 | 0 | 0
6964 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Making HDD (Horizontal directional) bore & laying of various size casing pipes/water main inside HDD bore in rocky zone area ......including cutting the driving & receiving pit as per required size for crossing the national /..............using various machineries such as crane, jack, jacking materials, pushing jack technology .performing the work including mobilization charge of machneries required fro performing the work as per direction of the EIC conncetion with Improvement to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) under Khatra Sub - Division of Bankura Division, PHE Dte. zone - M2 sl no - 16 | IMP/K-R-H | 15/03/2022 | 0 | DEBAKI RANJAN SARKAR | 3.93 | 0 | 0 | 0
6965 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Laying distribution system using different dia D.I - K 7 pipes for improvement of Khatra-Ranibandh-Hirbandh W/S Scheme (BRGF ph - I project) under Khatra Sub - Division of Bankura Division, PHE Dte. Zone - M1 sl no - 01 | IMP/K-R-H | 15/03/2022 | 0 | KONAR CONSTRUCTION | 58.1 | 0 | 0 | 0
6966 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | 1st Ad-interim Payment against F/F bill for the work :- Improvement of Khatra, Ranibandh-Hirbandh works supply scheme under BRGF (PH-I) | IMP/K-R-H | 11/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 500 | 0 | 0 | 0
6967 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Balance work of construction of boundary wall including construction of Path way at Over Head Reservoir Site for for Improvement of Khatra - Ranibandh - Hirbandh water supply scheme under BRGF (Phase - I) under Bankura Division, P.H.E. Dte. (Zone-Ashatara, Distance 48 Km. from Bankura) (Length -130 Mtr, No of Columns=38 Nos. Centre to Centre-3.5 Mtr.) For Single Tie Beam. | 498/BQA | 13/03/2023 | 45 | MD. AFSAR ALI | 14.25 | 0 | 0 | 0
6968 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Continuation Work order for Supply of 1 (One) No. Diesel/LPG/CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. under Bankura Division, P.H.E. Dte. for the period from 01/07/2022 to 31/12/2022. | 234/KSD | 29/06/2022 | 184 | BISWAJIT LAI | 0.87 | 0 | 0 | 50
6969 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Javi (69), Bagdiha (70), Ledapakur (120), Mahadebsinan (121), Barapacha (123), Khata-Am (124), Raygar (125), Goalmuri (152), Sutan (153), Bhulagara (154), Dhankura (159) & Dhanjhar (164) mouzas by retrofitting Zone- M2 of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 2533/BQA | 08/09/2023 | 45 | GANESH ROY | 36.75 | 0 | 0 | 0
6970 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Crossing road by 200 mm dia MS pipe by Jack pushing method, interconnection of Rising Main (Zone-M1 & M2) with pumping main, laying & fabrication of MS pipe in another 3 (Three) Nos. places with all allied works for balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 828/BQA | 17/04/2023 | 30 | M/S TARUN KUMAR PATRA | 12.53 | 0 | 0 | 100
6971 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Continuation Work order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for Office of the Executive Engineer, Bankura Division, P.H.E. Dte. for the Period from 01/11/2022 to 31/01/2023. | 390/KSD | 28/10/2022 | 92 | SRIKANTA MONDAL | 0.44 | 0 | 0 | 20
6972 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Material Requisition To Resource Division | 1708/BQA | 29/07/2022 | 0 | Resource Division | 155.57 | 0 | 0 | 0
6973 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Material Requisition To Resource Division | 1120/BQA | 12/05/2023 | 0 | Resource Division | 182.72 | 0 | 0 | 0
6974 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Purchase of land for proposed 02 Nos. of OHR for Improvement of khatra-Hirbandh-Ranibandh w/s scheme under BRGF (Phase - I) |  | 30/11/2022 | 0 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 22.6 | 0 | 0 | 0
6975 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Continuation Work Order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for Office of the Executive Engineer, Bankura Division, P.H.E. Dte. for the Period from 01.05.2023 to 31.07.2023. | 85/KSD | 24/04/2023 | 92 | SRIKANTA MONDAL | 0.44 | 0 | 0 | 50
6976 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Continuation Work order for Supply of 1 (One) No. Diesel/LPG/CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. under Bankura Division, P.H.E. Dte. for the period from 01/07/2023 to 31/12/2023. | 161/KSD | 30/06/2023 | 184 | BISWAJIT LAI | 0.87 | 0 | 0 | 40
6977 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Continuation Work Order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for Office of the Executive Engineer, Bankura Division, P.H.E. Dte. for the Period from 01.08.2023 to 31.10.2023. | 217/KSD | 31/07/2023 | 92 | SRIKANTA MONDAL | 0.44 | 0 | 0 | 40
6978 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Construction of 200 m³ Capacity R.C.C OHR (based on Departmental Design) with 20 mtr. staging height, Construction of Chlorine Room and Construction of Operator cum Guard Room of Ashatora (Zone-CE) under balance work of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 3163/BQA | 24/12/2024 | 90 | SUBHANKAR BANERJEE | 90.99 | 0 | 0 | 0
6979 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Construction of 200 m³ Capacity R.C.C OHR (based on Departmental Design) with 20 mtr. staging height, Construction of Chlorine Room and Construction of Operator cum Guard Room of Zone-M2 under balance work of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 3164/BQA | 24/12/2024 | 90 | S B ASSOCIATES | 91.37 | 0 | 0 | 0
6980 | BANKURA | Bankura Mechanical | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Formal work order for the work of Providing And Installation Of Pumping Machineries, Substation Equipments And Other Electro-Mechanical Accessories at Head Works site for Improvement of Khatra-Ranibandh-Hirbandh Water supply Scheme, Block- Ranibandh, Dist- Bankura under Bankura Mechanical Division, PHE Dte. | 1319/BMD | 18/11/2020 | 181 | DEY ENTERPRISE | 107.65 | 0 | 0 | 95
6981 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Work Order for Supply, Delivery and Stacking of C.I.D.F. Sluice Valve of under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) | 323\KSD | 10/11/2023 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 1 | 0 | 0 | 100
6982 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Material Requisition To Resource Division | 116/BQA | 10/01/2024 | 0 | Resource Division | 15.54 | 0 | 0 | 0
6983 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Javi (69), Bagdiha (70), Ledapakur (120), Mahadebsinan (121), Barapacha (123), Khata-Am (124), Raygar (125), Goalmuri (152), Sutan (153), Bhulagara (154), Dhankura (159) & Dhanjhar (164) mouzas by retrofitting Zone- M2 of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( Total FHTC- 1033) No of FHTC- 517 ( PART-B ) | 2534/BQA | 08/09/2023 | 936 | MUNMUN UPADHYAY | 36.75 | 0 | 0 | 0
6984 | BANKURA | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. , SM/10295 | Augmentation | Construction of 250 m³ Capacity R.C.C OHR (based on Departmental Design) with 20 mtr. staging height, Construction of Chlorine Room and Construction of Operator cum Guard Room of Zone-M1 under balance work of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 3165/BQA | 24/12/2024 | 90 | SUBHENDU SEKHAR GORAI | 92.86 | 0 | 0 | 5
6985 | BANKURA | Bankura Division | Augmentation works for Ashatora (Zone- CE) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) , SM/18231 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-CE (Ashatora) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 556/BQA | 17/03/2023 | 90 | LABIR MIRSHAD KHAN | 19.63 | 0 | 0 | 90
6986 | BANKURA | Bankura Division | Augmentation works for Ashatora (Zone- CE) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) , SM/18231 | Augmentation | Material Requisition To Resource Division | 116/BQA | 10/01/2024 | 0 | Resource Division | 1.91 | 0 | 0 | 0
6987 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MENJUA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10889 | New | New service connection at Mini Piped w/s scheme at Menjua, P.O-Bheduasole under Bankura Mechanical Division PHE Dte | FHTC/09 | 07/09/2023 | 0 | INDPUR CCC | 0.12 | 0 | 0 | 0
6988 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MENJUA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10889 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6989 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MENJUA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10889 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6990 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MENJUA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10889 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6991 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DUNDURIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11199 | New | New Connection at Dhunduria,Taldangra,Pin-722102,PHE Dte | FHTC/11 | 10/11/2023 | 0 | TALDANGRA CCC | 0.12 | 0 | 0 | 0
6992 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DUNDURIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11199 | New | Assistant Engineer Bankura Mech S.D.P.H.E (site - Pritchak, Mirzapur, Kotulpur) |  | 18/01/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0 | 0
6993 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DUNDURIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11199 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6994 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DUNDURIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11199 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6995 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DUNDURIA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11199 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
6996 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Nanda Mohanpur, Household-91) , SM/11414 | New | New service connection at Khag Baikuntapur, Panchal Sonamukhi, PHE Dte. | FHTC/09 | 07/09/2023 | 0 | BELIATORE CCC | 0.12 | 0 | 0 | 0
6997 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Nanda Mohanpur, Household-91) , SM/11414 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
6998 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Nanda Mohanpur, Household-91) , SM/11414 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
6999 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Sonamukhi (Village Name- Nanda Mohanpur, Household-91) , SM/11414 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
7000 | BANKURA | Bankura Division | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme , SM/18424 | Augmentation | Work Order for Repairing of Collecting line with other allied works of Lakshmisagar Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 261/KSD | 24/08/2023 | 7 | S.S. CONSTRUCTION | 0.97 | 0 | 0 | 0
7001 | BANKURA | Bankura Division | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme , SM/18424 | Augmentation | Sinking of 4 (Four) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, fitting & fixing 100 mm dia M.S collecting line from river bed tube well to CWR with allied works for in connection with Augmentation of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 359/BQA | 06/02/2024 | 30 | SIBSANKAR CHOWDHURY | 50.22 | 0 | 0 | 45
7002 | BANKURA | Bankura Division | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme , SM/18424 | Augmentation | Material Requisition To Resource Division | 116/BQA | 10/01/2024 | 0 | Resource Division | 2.03 | 0 | 0 | 0
7003 | BANKURA | Bankura Mechanical | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme , SM/18424 | Augmentation | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme | BP-2023-24-175 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.19 | 0 | 0 | 0
7004 | BANKURA | Bankura Division | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme , SM/18424 | Augmentation | Sinking of 1 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas in connection with Augmentation of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 2453/BQA | 28/08/2023 | 948 | GOUTAM BHOWMIK | 93.63 | 0 | 0 | 20
7005 | BANKURA | Bankura Mechanical | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme , SM/18424 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation works for Augmentation of piped water supply scheme for Lakshmisagar and its adjoining mouzas under Jal Jeevan mission programe under Bankura Mechanical Division, P.H.E. Dte | 2090/BMD | 12/09/2023 | 840 | MAHADEV ENTERPRISE | 86.97 | 0 | 0 | 13
7006 | BANKURA | Bankura Mechanical | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme , SM/18424 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories in boosting site and HWS site for Augmentation works for Piped Water Supply Scheme for Lakshmisagar and Its Adjoining Mouzas under Jal Jeevan Mission Programme under under Bankura Mechanical Division, P.H.E. Dte | 488/BMD | 09/07/2024 | 600 | MAHADEV ENTERPRISE | 54.94 | 0 | 0 | 23
7007 | BANKURA | Bankura Division | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme , SM/18424 | Augmentation | Sinking of 3 Nos. 300 mm X 200 mm X 200 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe and Construction of 3 Nos. Pump Houses with ancillary works, Laying of HDPE pipeline and Construction of Valve Chamber with all allied works in connection with Augmentation of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 1485/BQA | 18/06/2024 | 45 | S B ASSOCIATES | 96.61 | 0 | 0 | 80
7008 | BANKURA | Bankura Division | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme , SM/18424 | Augmentation | Repairing and painting of 2 Nos. Over Head Reservoir (Capacity 450 Cum. & 350 Cum., staging height 20 Mtr.) including by pass arrangement, construction of boundary wall (OHR site Zone- I & II, Intake site), repairing of CWR, pump house, WBSEDCL room, guard room with all other allied woorks for Augmentation of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas (Zone-I & II) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 493/BQA | 25/02/2025 | 60 | BEAUTY CHATTERJEE | 39.16 | 0 | 0 | 0
7009 | BANKURA | Bankura Division | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme , SM/18424 | Augmentation | Laying additional pipeline in connection with Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | 1324/BQA | 17/06/2025 | 45 | GOUTAM BHOWMIK | 18.24 | 0 | 0 | 0
7010 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SUTAN VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11120 | New | Bmsd Phe Dte sutan C/o Sudip saha,sutan, Ranibandh | FHTC/08 | 04/08/2023 | 0 | RANIBANDH CCC | 0.11 | 0 | 0 | 0
7011 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SUTAN VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11120 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
7012 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SUTAN VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11120 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
7013 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SUTAN VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/11120 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
7014 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Kushadwip, House Hold:20) , SM/11156 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
7015 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Kushadwip, House Hold:20) , SM/11156 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
7016 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Kushadwip, House Hold:20) , SM/11156 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
7017 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DAMODAR MOHAN VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10963 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
7018 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DAMODAR MOHAN VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10963 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
7019 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DAMODAR MOHAN VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER MEJHIA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/10963 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
7020 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Piritchak, House Hold No.: 89) , SM/11085 | New | Assistant Engineer Bankura Mech S.D.P.H.E (site - Pritchak, deshra, Kotulpur) | Kotulpur-CCC/02 | 02/02/2023 | 0 | KOTULPUR CCC | 0.12 | 0 | 0 | 0
7021 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Piritchak, House Hold No.: 89) , SM/11085 | New | Quotation for New service connection at Pritchak | BP-436/2024-25 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0 | 0
7022 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Piritchak, House Hold No.: 89) , SM/11085 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
7023 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Piritchak, House Hold No.: 89) , SM/11085 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
7024 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Piritchak, House Hold No.: 89) , SM/11085 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
7025 | BANKURA | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR HATIBAND VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ONDA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. , SM/13254 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
7026 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo , SM/07341 | Retrofitting | Laying extra HDPE pipe line to cover Susunia mouza for construction and commissioning ofF 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Hapania (Zone - D) under Saltora- Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | 934/ BSD | 04/10/2021 | 15 | I.R.CONSTRUCTION | 3.39 | 0 | 0 | 0
7027 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo , SM/07341 | Retrofitting | Restoration of concrete at Susunia mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Hapania (Zone- D) under Saltora- Block, Saltora-Chhatna W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte | 935/ BSD | 04/10/2021 | 15 | I.R.CONSTRUCTION | 4.11 | 0 | 0 | 0
7028 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo , SM/07341 | Retrofitting | Laying Extra HDPE Pipe Line to Cover Susunia mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | 346/BSD | 16/08/2022 | 20 | I.R.CONSTRUCTION | 4.94 | 0 | 0 | 0
7029 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo , SM/07341 | Retrofitting | Laying Extra HDPE Pipe Line to Cover Susunia (Upor Para) mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | 348/KSD | 16/08/2022 | 20 | I.R.CONSTRUCTION | 2.36 | 0 | 0 | 0
7030 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo , SM/07341 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Tilabaid, No.of Mouza :- 4, Belebad,Moulahir, Mujrakundi Raj band Total House Hold -576 . | FHTC/3 | 03/02/2022 | 0 | M/S BIPUL BANERJEE | 20.03 | 0 | 0 | 0
7031 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo , SM/07341 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debgram (296) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 1 No. Total Household:- 201 Nos. | FHTC/31 | 31/01/2022 | 0 | SANJOY MONDAL | 9.21 | 0 | 0 | 0
7032 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo , SM/07341 | Retrofitting | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 01,Susunia Total House Hold - 160 | 459/BQA | 05/02/2021 | 30 | I.R.CONSTRUCTION | 11.01 | 0 | 0 | 0
7033 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo , SM/07341 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. . Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 02 no, (Jirra, Ramnathpur), Total House Hold - 645 nos. | 2533/BQA | 23/09/2021 | 30 | BISWARUP BOSE | 36.29 | 0 | 0 | 0
7034 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo , SM/07341 | Retrofitting | Dismantling & reconstruction of concrete at Phaspa mouza retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. [Jal Jeevan Mission (JJM) and JAL SWAPNA Fund] | 344/KSD | 16/08/2022 | 20 | I.R.CONSTRUCTION | 3.61 | 0 | 0 | 80
7035 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo , SM/07341 | Retrofitting | Laying of HDPE Pipe Line from Susunia More to Murut Baha Eco-Park at Susunia mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Hapania (Zone - D) under Chhatna Bloc k of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. | 636/BQA | 24/03/2023 | 45 | SK SAMSA ALAM | 1.96 | 0 | 0 | 10
7036 | BANKURA | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Jirrah, Ramnathpur, Susunia Jamthole, Chatatola, Phapsa, Namo , SM/07341 | Retrofitting | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 04, Chhatatola, Phaspa, Namosusunia, Susunia Pahar Total House Hold - 322 | 460/BQA | 05/02/2021 | 30 | I.R.CONSTRUCTION | 28.91 | 0 | 0 | 95
7037 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Sain Buni, House Hold:46) , SM/11145 | New | New Connection at Saibuni,Patrasayer Bishnupur PHE Dte | FHTC/06 | 26/06/2023 | 0 | PATRASAYER CCC | 0.12 | 0 | 0 | 0
7038 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Sain Buni, House Hold:46) , SM/11145 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  | 03/07/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
7039 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Sain Buni, House Hold:46) , SM/11145 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna | BP-214/2024-25 | 08/08/2024 | 0 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
7040 | BANKURA | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur & Patrasayer, (Village Name :Sain Buni, House Hold:46) , SM/11145 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | 1731/BQA | 03/08/2022 | 697 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
7041 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas , SM/09924 | Augmentation | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir of capacity 500 cum and staging height 20 mtr for Augmentation of piped water supply scheme for Beliatore and its adjoining mouzas (JJM REVISION) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | 358/BSD | 13/04/2022 | 15 | VISCOUS ENGINEERS PVT. LTD. | 1.84 | 0 | 0 | 0
7042 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas , SM/09924 | Augmentation | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir (Intze type with solid raft) of capacity 100 cum and staging height 20 mtr as per approved drawing (No:-PC-I/OHR/3/2012) in connection with Jal Jeevan Mission (JJM) for Proposed Surface Water Based Dhabani PIped Water Supply Scheme under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Barjora, District -Bankura . Name of Muza - Kanchchhala, Samantamara & Dhabani. | 571/BQA | 17/03/2023 | 15 | MS G. MITRA AND ASSOCIATES | 0 | 0 | 0 | 0
7043 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas , SM/09924 | Augmentation | Material Requisition To Resource Division | 79BQA | 06/01/2023 | 0 | Resource Division | 26.02 | 0 | 0 | 0
7044 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas , SM/09924 | Augmentation | Rail bhoomi crossing seva | FHTC/08 | 31/08/2023 | 0 | SOUTH EASTERN RAILWAY | 1.06 | 0 | 0 | 0
7045 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas , SM/09924 | Augmentation | Laying DI (K7) & UPVC pipe line for distribution system and Construction and commissioning of 500 m3 capacity R.C.C. OHR (based on Departmental Design Ref. Drawing No. PC - 1 / OHR / 5 / 12 (Sheet 1 & 2) with 20 mtr. Staging height including foundation, pipeline connection and cost of pipes, specials etc. and allied works for the proposed Augmentation of piped water supply scheme for Beliatore and its adjoining mouzas (JJM) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, District - Bankura (Part - A) and Construction and commissioning of 500 m3 capacity RCC OHR (based on Departmental Design Ref. Drawing No. PC - 1 / OHR / 5 / 12 (Sheet 1 & 2) with 20 mtr. staging including foundation, pipeline connection and cost of pipes, specials etc., and allied works for the proposed Augmentation of piped water supply scheme for Beliatore and its adjoining (JJM) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, District - Bankura (Part - B) | 1973/BQA | 22/09/2022 | 540 | SIB SANKAR CHOWDHURY | 349.96 | 0 | 0 | 48
7046 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas , SM/09924 | Augmentation | Survey work for Augmentation for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for 10 nos. Mouzas of proposed Augmentation of piped water supply scheme for Beliatore and its adjoining mouzas (JJM) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Barjora , District -Bankura | 1069/BQA | 04/05/2023 | 360 | TAPAS DEY | 1.15 | 0 | 0 | 70
7047 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas , SM/09924 | Augmentation | Augmentation of Beliatore and its adjoining mouzas under Bankura Division, PHE Dte. | 1959/BQA | 18/07/2023 | 270 | I.R.CONSTRUCTION | 125.11 | 0 | 0 | 35
7048 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas , SM/09924 | Augmentation | Crossing road by 150 mm dia MS carrier pipe by Jack pushing method, inetrconnection of MS carrier pipe with UPVC pipeline including fabrication of MS pipe & allied works for Augmentation of Beliatore Piped Water Supply Scheme (JJM Revision) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Location of site near Indira Statue at Beliatore towards Sonamukhi Road) | 3005/BQA | 03/11/2023 | 45 | SIBSANKAR CHOWDHURY | 6.01 | 0 | 0 | 0
7049 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas , SM/09924 | Augmentation | Crossing road by 150 mm dia MS carrier pipe by Jack pushing method, inetrconnection of MS carrier pipe with UPVC pipeline including fabrication of MS pipe & allied works for Augmentation of Beliatore Piped Water Supply Scheme (JJM Revision) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Location of site near Murakata Village Road) | 3006/BQA | 03/11/2023 | 45 | SIBSANKAR CHOWDHURY | 6.55 | 0 | 0 | 0
7050 | BANKURA | Bankura Mechanical | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas , SM/09924 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for Beliatore w/s scheme under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | 518/BMD | 09/07/2024 | 120 | DEY ENTERPRISE | 17.63 | 0 | 0 | 0
7051 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas , SM/09924 | Augmentation | Repair & Restoration of collecting Pipe line 4 (four) nos 100mm dia. from river bed Tube Well to CWR in river Sali under Beliatore W/S Scheme under Bankura Sadar Sub -Division of Bankura division P.H.E.Dte. | 2946/BQA | 30/10/2023 | 30 | SOMA BANERJEE | 10.86 | 0 | 0 | 100
7052 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas , SM/09924 | Augmentation | Service connection charge for Beliatore OHR site water supply scheme at head works site Barjora block under BMD,PHE Dte.(SM/09924) | BP-242/2024-25 | 28/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.63 | 0 | 0 | 0
7053 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas , SM/09924 | Augmentation | Laying Rising Main DI (K9) pipe & Construction of CWR (100 CUM CAPACITY) with plinth protection for the proposed Augmentation of piped water supply scheme for Beliatore and its adjoining mouzas (JJM) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block- Barjora , District -Bankura. ( Sl.No-03) | 524/BQA | 10/03/2022 | 1574 | AJIT KUMAR PAUL | 22.63 | 0 | 0 | 75
7054 | BANKURA | Bankura Mechanical | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas , SM/09924 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift pumping machineries and other electromechanical accessories for Augmentation of Beliatore its adjoining mouzas piped water supply scheme (JJM Revision) under Bankura Mechanical Division PHE Dte Block Borjora Dist Bankura. | 1876/BMD | 17/08/2023 | 720 | DEY ENTERPRISE | 64.51 | 0 | 0 | 51
7055 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas , SM/09924 | Augmentation | Construction of High Lift Pump House with all allied works at Beliatore under Augmentation of Beliatore Water Supply Scheme under Bankura Sadar Sub- Division of Bankura Division, P.H.E. Dte. | 3155/BQA | 24/12/2024 | 342 | ASHIS PAL | 25.67 | 0 | 0 | 75
7056 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas , SM/09924 | Augmentation | Crossing road by 150 mm dia MS carrier pipe by Jack pushing method, inetrconnection of MS carrier pipe with UPVC pipeline including fabrication of MS pipe & allied works for Augmentation of Beliatore Piped Water Supply Scheme (JJM Revision) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Location of site Beliatore - Sonamukhi More at Beliatore) | 1303/BQA | 17/06/2025 | 45 | I R CONSTRUCTION | 12.43 | 0 | 0 | 0
7057 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas , SM/09924 | Augmentation | Crossing road by 300 mm dia MS carrier pipe by Jack pushing method, inetrconnection of MS carrier pipe with UPVC & DI pipeline including fabrication of MS pipe & allied works for Augmentation of Beliatore Piped Water Supply Scheme (JJM Revision) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. (Location of site near Beliatore Girls High School at Beliatore) | 1020/BQA | 25/04/2025 | 90 | I R CONSTRUCTION | 9.71 | 0 | 0 | 0
7058 | BANKURA | Bankura Division | Augmentation of piped water supply schemes for Beliatore and its adjoining mouzas , SM/09924 | Augmentation | Cannel/Drain Crossing work by 150 mm dia MS carrier pipe & 300 mm dia casing pipe by Jack pushing method on the road SH-8 from Beliatore towards Chandar inetrconnection of MS carrier pipe with UPVC pipeline including fabrication of MS pipe & allied works and laying different dia proposed extra HDPE line to be laid at mouza Beliatore city, Natungram, Challa, Dangar para for Augmentation of Beliatore Water Supply Scheme under JJM under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte | 691/BQA | 12/03/2025 | 190 | SIBSANKAR CHOWDHURY | 176.06 | 0 | 0 | 31
7059 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Continuation work order for providing services for operation of 10 (ten) nos Laboratory under Bankura Division, P.H.E.Dte. for the period from 01.05.2022 to 31.10.2022 i.e.06 (Six) months. | 901/BQA | 18/04/2022 | 6 | CLIFFORD FACILITY SERVICES PVT. LTD. | 19.78 | 0 | 0 | 0
7060 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Continuation Work order for Providing services for operation of 10 (Ten) nos. laboratory under Bankura Division PHE Dte. for the period from 01.05.2022 to 31.10.2022 i.e. 06 (Six) months. | 2079/BQA | 21/10/2022 | 182 | CLIFFORD FACILITY SERVICES PVT. LTD. | 18.48 | 0 | 0 | 0
7061 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Supply of different Chemicals, sample container etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. (Sl No.- 01) | 69/BK | 25/04/2023 | 30 | SONU SINGH | 0.96 | 0 | 0 | 0
7062 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Providing services for operation of 03 (three) nos Laboratory under Bankura Division, P.H.E.Dte. for the period from 11.07.2022 to 30.06.2023 i.e.12 ( twelve) months. | 1530 /BQA | 08/07/2022 | 365 | CLIFFORD FACILITY SERVICES PVT. LTD. | 16.14 | 0 | 0 | 50
7063 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Supply of different Chemicals,sample container etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. (Sl No.- 02) | 70/BK | 25/04/2023 | 30 | ABHIRUP MALLA | 0.95 | 0 | 0 | 30
7064 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Supply of different chemicals, reagents for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. | 134/BK | 07/06/2023 | 30 | LAB SOLUTION | 4.38 | 0 | 0 | 30
7065 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Work order for procurement of necessary Chemicals/reagents for available chlorine & chlorine demand testing purpose of Laboratories under Bankura Division , P.H.E. Dte. | 213/BK | 22/09/2023 | 30 | SONU SINGH | 0.97 | 0 | 0 | 95
7066 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Providing services for operation of 10 (ten) nos Laboratory w.e.f.01.06.2023 to 30.04.2024 & 03 ( Three) nos.Laboratory w.e.f.01.06.2023 to 30.04.2024 under Bankura Division, P.H.E.Dte. (SL.NO-01) | 1306/BQA | 30/05/2023 | 365 | CLIFFORD FACILITY SERVICES PVT. LTD. | 74.67 | 0 | 0 | 98
7067 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Supply of different Chemicals, Manganese, Ferospectral Reagent etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. | 231/BK | 12/10/2023 | 31 | LAXMI ENTERPRISE | 3.7 | 0 | 0 | 98
7068 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Supply of different Chemicals, Membrane Filter, DPD tablet, Biosol etc. for 16 nos Water Testing Laboratories of Bankura RWS Sub -Division under Bankura Division, PHE Dte. | 232/BK | 12/10/2023 | 31 | LAXMI ENTERPRISE | 3.53 | 0 | 0 | 96
7069 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Work order for Annual Maintenance Contract for computers Printers, UPS and other related peripherals for Bankura District Laboratory , Mukutmanipur WTP Laboratory and 05 Nos NGO Managed Laboratories under Bankura Division PHE Dte. w.e.f. 01.06.2023 to 30.09.2023 . | 131/BK | 31/05/2023 | 122 | TAPAS DEY | 0.42 | 0 | 0 | 98
7070 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Work order for Maintenance Of Computer Of 09 ( Nine) Nos. PHED Laboratories (Patrasayer Sub District Lab, Bishnupur Sub District Lab, Onda Sub District Lab, Taldangra Sub District Lab, Raipur Sub District Lab , Sanabandh Sub District Lab , Sarberia Sub District Lab, Saltora Sub District Lab & G.Ghati Sub District Lab) in the district of Bankura under Bankura Division, P.H.E. Dte. for the period from 01/07/2023 to 30/09/2023 (Three Months). | 161\BK | 30/06/2023 | 92 | TAPAS DEY | 0.34 | 0 | 0 | 98
7071 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Supply of different Chemicals, Reagent, Membrane Filter etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. | 192/BQA | 22/01/2024 | 10 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 10.02 | 0 | 0 | 98
7072 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Procurement of necessary Chemicals/reagents for available chlorine & chlorine demand testing purpose of Laboratories under Bankura Division , P.H.E. Dte. | 214\BK | 22/09/2023 | 30 | ABHIRUP MALLA | 0.97 | 0 | 0 | 100
7073 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Taldangra sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. (Sl NO.-01) | 279/BK | 29/12/2023 | 62 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
7074 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Onda sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. | 281/BK | 29/12/2023 | 62 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 80
7075 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Saltora sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. | 283\BK | 29/12/2023 | 62 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 95
7076 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Sarberia sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. | 286\BK | 29/12/2023 | 62 | LAB ANALYTICS | 0.9 | 0 | 0 | 95
7077 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Gangajalghati sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. | 288\BK | 29/12/2023 | 62 | LAB ANALYTICS | 0.9 | 0 | 0 | 100
7078 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Work order for Supply of Sample container, Chemicals etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. ( Sl No.-1) | 43/BK | 21/02/2024 | 15 | TAPAS DEY | 0.96 | 0 | 0 | 100
7079 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Work order for Supply of Sample container, Chemicals etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. | 75\BK | 13/03/2024 | 15 | SONU SINGH | 0.96 | 0 | 0 | 98
7080 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Mukutmanipur WTP sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. (Sl NO.-02) | 280/BK | 29/12/2023 | 62 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
7081 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Bishnupur under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. | 287\BK | 29/12/2023 | 62 | DULAL MAJUMDER | 0.9 | 0 | 0 | 100
7082 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Raipur sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. | 284\BK | 29/12/2023 | 62 | LAB ANALYTICS | 0.9 | 0 | 0 | 100
7083 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Prayer for release fund for laboratory persoanal's Puja Festival's Bonus for the year 2023. |  | 05/03/2024 | 0 | HIJALDIHA VIVEKANANDA SEVA SAMITY | 0.16 | 0 | 0 | 0
7084 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Prayer for release fund for laboratory personal for the month of July 2023 to september 2023 | FHTC/02 | 09/02/2024 | 0 | HIJALDIHA VIVEKANANDA SEVA SAMITY | 1.35 | 0 | 0 | 0
7085 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Supply of different Chemicals, Manganese, Ferospectral Reagent etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. (Sl No. -01) | 47/A/BK | 24/03/2023 | 15 | SUBHADIP KOLEY | 4.33 | 0 | 0 | 10
7086 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/15260 | Support-WQMSP | Supply of different Chemicals, Manganese, Ferospectral Reagent etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. (Sl No. -02) | 48/BK | 24/03/2023 | 15 | SUBHADIP KOLEY | 4.61 | 0 | 0 | 10
7087 | BANKURA | Bankura Division | Operational charges of PHED Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19264 | Support-WQMSP | Day to day Operation & Maintenance for 16 (Sixteen) Nos. PHED Managed Laboratories for 12 (Twelve) Months w.e.f 01.01.2025 to 31.12.2025 under Bankura Division P.H.E.Dte. | 3212/BQA | 30/12/2024 | 365 | UTSAV AGENCY | 3.59 | 0 | 0 | 0
7088 | BANKURA | Bankura Division | Operational charges of PHED Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19264 | Support-WQMSP | Continuation Work Order for Day to day Operation & Maintenance for the Assistant Engineer, R.W.S. Bankura Sub- Division office building and office premises under Bankura Division, P.H.E. Dte. (for 06 months) w.e.f. 01.07.2025 to 31.12.2025. | 117/BK | 25/06/2025 | 183 | TAPAS DEY | 0.48 | 0 | 0 | 0
7089 | BANKURA | Bankura Division | Operational charges of PHED Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19264 | Support-WQMSP | Continuation Work Order for Providing services for operation of 1(one) No.District Water Testing Laboratory & 12 ( Twelve) Nos. Sub-District Water Testing Laboratories w.e.f. 01.10.2024 to 31.12.2024(03 Months) under Bankura Division, P.H.E.Dte. | 2459/BQA | 26/09/2024 | 92 | CLIFFORD FACILITY SERVICES PVT. LTD. | 23.43 | 0 | 0 | 99
7090 | BANKURA | Bankura Mechanical | Supply and delivery of Desktop Computer and other related accessories for Bankura Mechanical Division P.H.E. Dte. Dist-Bankura , SM/10348 | Support-MIS | Supply and Delivery desktop computer and other related accessories for bankura Mechanical Division PHE Dte. | BP-2022-23-6 | 02/05/2022 | 0 | IONET | 0.25 | 0 | 0 | 0
7091 | BANKURA | Bankura Mechanical | Supply and delivery of Desktop Computer and other related accessories for Bankura Mechanical Division P.H.E. Dte. Dist-Bankura , SM/10348 | Support-MIS | Supply and Delivery desktop computer and other related accessories for bankura Mechanical Division PHE Dte. | BP-2022-23-7 | 02/05/2022 | 0 | IONET | 0.2 | 0 | 0 | 0
7092 | BANKURA | Bankura Mechanical | Supply and delivery of Desktop Computer and other related accessories for Bankura Mechanical Division P.H.E. Dte. Dist-Bankura , SM/10348 | Support-MIS | Supply and Delivery desktop computer and other related accessories for bankura Mechanical Division PHE Dte. | BP-2022-23-4 | 02/05/2022 | 0 | IONET | 1.87 | 0 | 0 | 0
7093 | BANKURA | Bankura Mechanical | Supply and delivery of Desktop Computer and other related accessories for Bankura Mechanical Division P.H.E. Dte. Dist-Bankura , SM/10348 | Support-MIS | Supply and Delivery desktop computer and other related accessories for bankura Mechanical Division PHE Dte. | BP-2022-23-2 | 02/05/2022 | 0 | IONET | 3.73 | 0 | 0 | 0
7094 | BANKURA | Bankura Mechanical | Supply and delivery of Desktop Computer and other related accessories for Bankura Mechanical Division P.H.E. Dte. Dist-Bankura , SM/10348 | Support-MIS | Supply and Delivery desktop computer and other related accessories for bankura Mechanical Division PHE Dte. | BP-2022-23-9 | 02/05/2022 | 0 | IONET | 0.15 | 0 | 0 | 0
7095 | BANKURA | Bankura Mechanical | Supply and delivery of Desktop Computer and other related accessories for Bankura Mechanical Division P.H.E. Dte. Dist-Bankura , SM/10348 | Support-MIS | Supply and Delivery desktop computer and other related accessories for bankura Mechanical Division PHE Dte. | BP-2022-23-3 | 02/05/2022 | 0 | IONET | 4.13 | 0 | 0 | 0
7096 | BANKURA | Bankura Mechanical | Supply and delivery of Desktop Computer and other related accessories for Bankura Mechanical Division P.H.E. Dte. Dist-Bankura , SM/10348 | Support-MIS | Supply and Delivery desktop computer and other related accessories for bankura Mechanical Division PHE Dte. |  | 20/04/2022 | 0 | IONET | 5.35 | 0 | 0 | 0
7097 | BANKURA | Bankura Mechanical | Supply and delivery of Desktop Computer and other related accessories for Bankura Mechanical Division P.H.E. Dte. Dist-Bankura , SM/10348 | Support-MIS | Supply and Delivery desktop computer and other related accessories for bankura Mechanical Division PHE Dte. | BP-2022-23-10 | 02/05/2022 | 0 | IONET | 0.1 | 0 | 0 | 0
7098 | BANKURA | Bankura Mechanical | Supply and delivery of Desktop Computer and other related accessories for Bankura Mechanical Division P.H.E. Dte. Dist-Bankura , SM/10348 | Support-MIS | Supply and delivery of Desktop Computer and other related accessories for Bankura Mechanical Division P.H.E. Dte. Dist-Bankura |  | 20/04/2022 | 0 | IONET | 5.35 | 0 | 0 | 0
7099 | BANKURA | Bankura Mechanical | Supply and delivery of Desktop Computer and other related accessories for Bankura Mechanical Division P.H.E. Dte. Dist-Bankura , SM/10348 | Support-MIS | Supply and Delivery desktop computer and other related accessories for bankura Mechanical Division PHE Dte. | BP-2022-23-5 | 02/05/2022 | 0 | IONET | 0.24 | 0 | 0 | 0
7100 | BANKURA | Bankura Mechanical | Supply and delivery of Desktop Computer and other related accessories for Bankura Mechanical Division P.H.E. Dte. Dist-Bankura , SM/10348 | Support-MIS | Supply and Delivery desktop computer and other related accessories for bankura Mechanical Division PHE Dte. | BP-2022-23-8 | 02/05/2022 | 0 | IONET | 0.03 | 0 | 0 | 0
7101 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Annual Maintenance Contract for computers Printers, UPS and other related peripherals for Bankura District Laboratory , Mukutmanipur WTP Laboratory and 05 Nos NGO Managed Laboratories under Bankura Division PHE Dte. w.e.f. 01.12.2021 to 30.11.2022 . (Twelve Months) (Sl No-02) | 151 /B/BK | 30/11/2021 | 365 | TAPAS DEY | 1.19 | 0 | 0 | 0
7102 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Procurement of consumables & reagents for 4 nos On-site Mobile Analysis System (4 nos OMAS Kit) under Bankura Division PHE Dte. for testing public drinking water sources. | 61 /BK | 18/04/2022 | 15 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 4.72 | 0 | 0 | 0
7103 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Supply of different chemicals, reagents for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. | 71 /BK | 02/05/2022 | 15 | LAB SOLUTION | 4.72 | 0 | 0 | 0
7104 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Continuation for Supply of different chemicals, reagents for 16 nos Water Testing Laboratories of Bankura RWS Sub -Division under Bankura Division, PHE Dte. | 46/BK | 11/03/2022 | 15 | GOPAL CHANDRA CHOWDHURY | 4.83 | 0 | 0 | 0
7105 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Continuation for Procurement of consumables & reagents for 4 nos On-site Mobile Analysis System (4 nos OMAS Kit) under Bankura Division PHE Dte. for testing public drinking water sources. | 125/BK | 12/08/2022 | 15 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 4.72 | 0 | 0 | 0
7106 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Maintenance of computer of 09 ( nine) nos. PHED Laboratories in the district of Bankura under Bankura Division, PHE. Dte. For the period from 01/01/2022 to 31/12/2022 (twelve months). (Sl No-01) | 180 /BK | 31/12/2021 | 365 | TAPAS DEY | 1.35 | 0 | 0 | 0
7107 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Continuation for Supply of different chemicals, reagents for 16 nos Water Testing Laboratories of Bankura RWS Sub -Division under Bankura Division, PHE Dte. | 110 /BK | 14/09/2021 | 15 | GOPAL CHANDRA CHOWDHURY | 4.83 | 0 | 0 | 0
7108 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Engagement of Resource person to implement water testing laboratory quality management system as per ISO/IEC: 17025 and preparation of quality measurement as per ISO guideline, Supervising, Document preparation and all such components as given in BOQ for NABL accreditation including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instruments & calibration of measuring instruments as per ISO 17025: 2017 protocol for Bankura District Water Testing Laboratory under the Executive Engineer, Bankura Division, PHE Dte, Government of West Bengal. | 2889/BQA | 22/11/2021 | 20 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 18.92 | 0 | 0 | 0
7109 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Continuation Work order for Supply of different chemicals, reagents for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. | 155/BK | 09/11/2022 | 15 | LAB SOLUTION | 4.72 | 0 | 0 | 0
7110 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Continuation work order for providing services for operation of 10 (ten) nos Laboratory under Bankura Division, P.H.E. Dte. for the period from 01.05.2022 to 31.10.2022 i.e.06 (Six) months. | 901 /BQA | 18/04/2022 | 6 | CLIFFORD FACILITY SERVICES PVT. LTD. | 19.78 | 0 | 0 | 0
7111 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Day to day Operation & Maintenance for the different Laboratories under Bankura Division, P.H.E. Dte. (for 12 months) w.e.f. 01.01.2022 to 31.12.2022. (Sl No-02) | 181 /BK | 31/12/2021 | 365 | TAPAS DEY | 4.61 | 0 | 0 | 0
7112 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | 1 (one) No. Diesel/ LPG/ CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, R.W.S. Bankura Sub- Division, P.H.E. Dte. W.e.f. 22.01.2022 to 21.01.2023. | 10/A/BK | 21/01/2022 | 365 | CHANPA SINGHA | 1.73 | 0 | 0 | 0
7113 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Supply of different Chemicals, Manganese, Ferospectral Reagent etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. | 121/Bk | 04/08/2022 | 1 | GOPAL CHANDRA CHOWDHURY | 4.81 | 0 | 0 | 0
7114 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Providing services for operation of 03 (three) nos Laboratory under Bankura Division, P.H.E. Dte. for the period from 01.06.2022 to 10.07.2022 i.e.1 month 10 days. | 87 /C/BK | 26/05/2022 | 40 | TAPAS DEY | 1.73 | 0 | 0 | 0
7115 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Day to day operation & Maintenance for the different Laboratories under Bankura Division , P.H.E. Dte. (for 07 months) w.e.f. 01.06.2022 to 31.12.2022 | 87/E/BK | 31/05/2022 | 214 | TAPAS DEY | 0.49 | 0 | 0 | 0
7116 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Repair & Renovation of Electrification work under Bankura II, Sub District Water Testing Laboratory under P.H.E DTE., during the year 2022-23 . | 28/A/BK | 24/02/2023 | 365 | TAPAS DEY | 0.47 | 0 | 0 | 0
7117 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Continuation Work order for providing services for operation of 10 (ten) nos Laboratory w.e.f.01.05.2023 to 31.05.2023 under Bankura Division, P.H.E.Dte. | 964/BQA | 27/04/2023 | 30 | CLIFFORD FACILITY SERVICES PVT. LTD. | 3.08 | 0 | 0 | 20
7118 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Prayer for release fund for laboratory personal's for the month of may 2022 | FHTC/17 | 17/01/2023 | 0 | SONAMUKHI BIKALPA UNNAYAN SAMITY | 0.33 | 0 | 0 | 0
7119 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | submission of utilization certificate of June 2022 and july 2022 lab maintains cost & administrative expence | FHTC/17 | 17/01/2023 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.1 | 0 | 0 | 0
7120 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Payment festival bonous of laboratory staff | FHTC/24 | 24/02/2023 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.14 | 0 | 0 | 0
7121 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Prayer for release fund for laboratory personal's for the month of march 2022 to may 2022 | FHTC/17 | 17/01/2023 | 0 | HIJALDIHA VIVEKANANDA SEVA SAMITY | 0.99 | 0 | 0 | 0
7122 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Prayer for release fund for laboratory maintenance for the month of march 2022 to may 2022 | FHTC/10 | 10/01/2023 | 0 | CHHOTO SARENGA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 0 | 0
7123 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Prayer for release fund for laboratory maintenance for the month of April 2021 to march 2022 | FHTC/10 | 10/01/2023 | 0 | CHHOTO SARENGA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 0.39 | 0 | 0 | 0
7124 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Prayer for release fund for maintenance of laboratory for the month of march 2022 to july 2022 | FHTC/17 | 17/01/2023 | 0 | HIJALDIHA VIVEKANANDA SEVA SAMITY | 0.25 | 0 | 0 | 0
7125 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Water Testing Laboratary of our samity (BTMSKS) for administrative expe September-2023 to November -2023 | FHTC/12 | 19/12/2023 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.14 | 0 | 0 | 0
7126 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Prayer for release fund for laboratory personal's for the month of may 2022 | FHTC/10 | 10/01/2023 | 0 | MALLABHUM MAHILA KALYAN SAMITY | 0.33 | 0 | 0 | 0
7127 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Repairing of refrigerate of sonamukhi sub division of water testing labotary sonamukhi Bankura of the office RWS Sub division PHE DTE. | FHTC/24 | 24/02/2023 | 0 | KUSUM HARANATH REFRIGERATOR | 0.04 | 0 | 0 | 0
7128 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | payment of laboratory staff for the month of august 22 to dec 22 | FHTC/24 | 24/02/2023 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 1.65 | 0 | 0 | 0
7129 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Prayer for release fund for laboratory maintenance for the month of December 2019 to may 2020 | FHTC/10 | 10/01/2023 | 0 | CHHOTO SARENGA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 0.12 | 0 | 0 | 0
7130 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Prayer for release fund for laboratory maintenance for the month of may 2022 | FHTC/10 | 10/01/2023 | 0 | MALLABHUM MAHILA KALYAN SAMITY | 0.06 | 0 | 0 | 0
7131 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | submission of utilization certificate of august 2022 to December 2022 with relevant documents voucher etc of water testing laboratory of our samity for administrative expenses. | FHTC/24 | 24/02/2023 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.25 | 0 | 0 | 0
7132 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | payment of laboratory staff for the month of september 2023 to november 2023 | FHTC/12 | 19/12/2023 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 1.35 | 0 | 0 | 0
7133 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Prayer for release fund for laboratory Maintenance for the month of june 2020 to march 2021 | FHTC/10 | 10/01/2023 | 0 | CHHOTO SARENGA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 0.38 | 0 | 0 | 0
7134 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Payment of laboratory staff for the month June 2022 & July 2022 | FHTC/17 | 17/01/2023 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.66 | 0 | 0 | 0
7135 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Bankura Mechanical sub division Phe Sonamukhi Municipality | FHTC/28 | 28/04/2023 | 0 | SONAMUKHI CCC | 1.23 | 0 | 0 | 0
7136 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Prayer for release fund for laboratory personal's for the month of January 2023 to March 2023 | FHTC/09 | 29/09/2023 | 0 | HIJALDIHA VIVEKANANDA SEVA SAMITY | 1.35 | 0 | 0 | 0
7137 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Festival bonous for the financial year 2022-2023 of the month september 2023 to november 2023 | FHTC/01 | 03/01/2024 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.16 | 0 | 0 | 0
7138 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | prayer for release fund for laboratory personal's for the month of april 2023 to june 2023 | FHTC/12 | 05/12/2023 | 0 | HIJALDIHA VIVEKANANDA SEVA SAMITY | 1.35 | 0 | 0 | 0
7139 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | prayer for release fund for laboratory for the month of january 2023 to june 2023 | FHTC/12 | 05/12/2023 | 0 | HIJALDIHA VIVEKANANDA SEVA SAMITY | 0.31 | 0 | 0 | 0
7140 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Supply of different Chemicals, Membrane Filter, C.C.Agar etc. for 16 nos Water Testing Laboratories of Bankura RWS Sub -Division under Bankura Division, PHE Dte. (Sl No. -02) | 172/BK | 20/12/2021 | 15 | SUBHADIP KOLEY | 4.61 | 0 | 0 | 0
7141 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Supply of different Chemicals, Manganese, Ferospectral Reagent etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. (Sl No. -01) | 171 /BK | 20/12/2021 | 15 | SUBHADIP KOLEY | 4.67 | 0 | 0 | 0
7142 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Supply of different Chemicals, Membrane Filter, C.C.Agar etc. for 16 nos Water Testing Laboratories of Bankura RWS Sub -Division under Bankura Division, PHE Dte. (Sl No. -02) | 172 /BK | 20/12/2021 | 15 | SUBHADIP KOLEY | 4.61 | 0 | 0 | 0
7143 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the different Laboratories. , SM/06634 | Support-WQMSP | Continuation Work order for Supply of different Chemicals, Manganese, Ferospectral Reagent etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. (Sl No. -01) | 177/A/BK | 19/12/2022 | 15 | SUBHADIP KOLEY | 4.67 | 0 | 0 | 0
7144 | BANKURA | Resource | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Bankura District. , SM/08977 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Bankura. | 2855/RS | 20/05/2022 | 150 | KARNAJORA AGNIBINA SEVA SAMITY | 221.62 | 0 | 0 | 0
7145 | BANKURA | Resource | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Bankura District. , SM/08977 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the Bankura. | 487/RS | 07/02/2023 | 210 | KARNAJORA AGNIBINA SEVA SAMITY | 206.33 | 0 | 0 | 49
7146 | BANKURA | Bankura Division | Survey & collection of data through mobile app regarding availability of drinking water, sanitation facilities & other parameters in primary, upper primary schools anganwadi centers within Bankura District for the financial year 2020-2021 , SM/09928 | Support-WQMSP | Survey & Collection of data through mobile app regarding availability of drinking water, sanitation facilities & other parameters in Primary, Upper primary Schools, Anganwadi Centers under Khatra Sub Division within Bankura district under Bankura Division PHE Dte. (Sl no.- 03) | 07/BK | 10/01/2022 | 15 | TAPAS KUMAR HAZRA | 3.97 | 0 | 0 | 0
7147 | BANKURA | Bankura Division | Survey & collection of data through mobile app regarding availability of drinking water, sanitation facilities & other parameters in primary, upper primary schools anganwadi centers within Bankura District for the financial year 2020-2021 , SM/09928 | Support-WQMSP | Survey & collection of data through mobilr app regarding availability of drinking water sanitation facility & other parameter in prymary upper pryment school, Anganwadi centre under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Sl no - 01 | FHTC/02 | 02/05/2022 | 0 | PRASANTA BHUIN | 3.5 | 0 | 0 | 0
7148 | BANKURA | Bankura Division | Survey & collection of data through mobile app regarding availability of drinking water, sanitation facilities & other parameters in primary, upper primary schools anganwadi centers within Bankura District for the financial year 2020-2021 , SM/09928 | Support-WQMSP | Survey & collection of data through mobilr app regarding availability of drinking water sanitation facility & other parameter in prymary upper pryment school, Anganwadi center under Bishnupur Sub - Division of Bankura Division, PHE Dte. | FHTC/02 | 02/05/2022 | 0 | TAPAS KUMBHAKAR | 3.85 | 0 | 0 | 0
7149 | BANKURA | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-ll)& uploading charges for the samerelated toWater Quality Monitoring & SurveillanceProgrammeUnder Jal Jeevan Mission , SM/19084 | Support-WQMSP | Sample collection, testing by Field Test Kit (FTKs) & data uploadig charges of test results in State Water Quality Dashboard through mobile application as a part of SWACHHA JAL SE SURAKSHA (SJSS) campaign in High School, Primary School, Uper Primary & Sisu Siksha Kendra & Anganwari Centers of 22 blocks within Bankura District under BankuraDivision PHE Dte . | 362/BQA | 06/02/2024 | 30 | TAPAS DEY | 8.28 | 0 | 0 | 98
7150 | BANKURA | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-ll)& uploading charges for the samerelated toWater Quality Monitoring & SurveillanceProgrammeUnder Jal Jeevan Mission , SM/19084 | Support-WQMSP | Work order for collection of drinking Water samples & uploading charges of field data related to Water Quality Monitoring & Surveillance from where facilitator are not available or inactive under Bankura Sadar Sub Division under Jal Jeevan Mission. (sl. no.-03) | 277/BK | 27/12/2024 | 182 | SONU SINGH | 0.93 | 0 | 0 | 0
7151 | BANKURA | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-ll)& uploading charges for the samerelated toWater Quality Monitoring & SurveillanceProgrammeUnder Jal Jeevan Mission , SM/19084 | Support-WQMSP | Work order for collection of drinking Water samples & uploading charges of field data related to Water Quality Monitoring & Surveillance from where facilitator are not available or inactive under Bishnupur Sub Division under Jal Jeevan Mission.(Sl.No.-01) | 275/BK | 27/12/2024 | 182 | TAPAS DEY | 0.93 | 0 | 0 | 45
7152 | BANKURA | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-ll)& uploading charges for the samerelated toWater Quality Monitoring & SurveillanceProgrammeUnder Jal Jeevan Mission , SM/19084 | Support-WQMSP | Work order for collection of drinking Water samples & uploading charges of field data related to Water Quality Monitoring & Surveillance from where facilitator are not available or inactive under Khatra Sub Division under Jal Jeevan Mission(sl no-02) | 276/BK | 27/12/2024 | 182 | ABHIRUP MALLA | 0.7 | 0 | 0 | 30
7153 | BANKURA | Bankura Division | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE , SM/18829 | Support-MIS | Supply & Installation microtek line interactive UPS with AVR of rating 0.65 KVA for the use of Executive Engineer Bankura Division PHE Dte. | 3482/BQA | 21/12/2023 | 15 | SHIVAM ENTERPRISE | 1.07 | 0 | 0 | 0
7154 | BANKURA | Bankura Division | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE , SM/18829 | Support-MIS | Supply & installation of SSD, Desktop, HDD & laser CLMFM Duplex wifi for the use of Executive Engineer Bankura Division Phe Dte | 3169/BQA | 21/11/2023 | 15 | IONET | 29.91 | 0 | 0 | 0
7155 | BANKURA | Bankura Division | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE , SM/18829 | Support-MIS | Supply,delivery,installation of Computer and peripheral for the official use under the office of the Superintending Engineer,PIU,Bankura,WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Officers under Bankura Division, PHE Dte., (1) Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE Dte. | FHTC/02 | 28/02/2024 | 0 | STAR POWER ENTERPRISES | 0.24 | 0 | 0 | 0
7156 | BANKURA | Bankura Division | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE , SM/18829 | Support-MIS | Supply,delivery,installation of Computer and peripheral for the official use under the office of the Superintending Engineer,PIU,Bankura,WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Officers under Bankura Division, PHE Dte., (1) Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE Dte. | FHTC/02 | 28/02/2024 | 0 | SHIVAM ENTERPRISE | 0.24 | 0 | 0 | 0
7157 | BANKURA | Bankura Division | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE , SM/18829 | Support-MIS | Supply,delivery,installation of Computer and peripheral for the official use under the office of the Superintending Engineer,PIU,Bankura,WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Officers under Bankura Division, PHE Dte., (1) Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE Dte. | FHTC/02 | 28/02/2024 | 0 | STAR POWER ENTERPRISES | 0.24 | 0 | 0 | 0
7158 | BANKURA | Bankura Division | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE , SM/18829 | Support-MIS | Supply and Installation of HP AIO(440 G9) i5-12500. (SM/18829) | BP-396/2024-25 | 05/10/2024 | 0 | JD ENGINEERING | 2.83 | 0 | 0 | 0
7159 | BANKURA | Bankura Division | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE , SM/18829 | Support-MIS | Supply of Computer Table.(SM/18829) | BP-389/2024-25 | 05/10/2024 | 0 | SHIVAM ENTERPRISE | 0.25 | 0 | 0 | 0
7160 | BANKURA | Bankura Division | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE , SM/18829 | Support-MIS | Supply,delivery,installation of Computer and peripheral for the official use under the office of the Superintending Engineer,PIU,Bankura,WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Officers under Bankura Division, PHE Dte. | FHTC/02 | 28/02/2024 | 0 | EASY DAY ENTERPRISE | 2.5 | 0 | 0 | 0
7161 | BANKURA | Bankura Division | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE , SM/18829 | Support-MIS | Supply,delivery,installation of Computer and peripheral for the official use under the office of the Superintending Engineer,PIU,Bankura,WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Officers under Bankura Division, PHE Dte. | FHTC/02 | 28/02/2024 | 0 | SHIVAM ENTERPRISE | 0.24 | 0 | 0 | 0
7162 | BANKURA | Bankura Division | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE , SM/18829 | Support-MIS | Supply of HP Laserjet Printer.(SM/18829) | BP-395/2024-25 | 05/10/2024 | 0 | JD ENGINEERING | 4.01 | 0 | 0 | 0
7163 | BANKURA | Bankura Division | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE , SM/18829 | Support-MIS | Supply Of Computer Table (SM/18829) | BP-390/2024-25 | 05/10/2024 | 0 | STAR POWER ENTERPRISES | 0.17 | 0 | 0 | 0
7164 | BANKURA | Bankura Division | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE , SM/18829 | Support-MIS | Supply,delivery,installation of Computer and peripheral for the official use under the office of the Superintending Engineer,PIU,Bankura,WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Officers under Bankura Division, PHE Dte., (1) Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE Dte. | FHTC/02 | 28/02/2024 | 0 | STAR POWER ENTERPRISES | 0.1 | 0 | 0 | 0
7165 | BANKURA | Bankura Division | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Superintending Engineer, PIU Bankura, WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Offices under Bankura Division , PHE , SM/18829 | Support-MIS | Supply,delivery,installation of Computer and peripheral for the official use under the office of the Superintending Engineer,PIU,Bankura,WBDWSIP & The Executive Engineer Bankura Division and Different Sub-Division Officers under Bankura Division, PHE Dte. | FHTC/02 | 28/02/2024 | 0 | IONET | 15.85 | 0 | 0 | 0
7166 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/19269 | Support-WQMSP | Contuinuation Work Order for Supply of different Chemicals, Reagent, Membrane Filter etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. | 2192/BQA | 14/08/2024 | 10 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 10.02 | 0 | 0 | 95
7167 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/19269 | Support-WQMSP | Supply of different Chemicals, Reagent, Membrane Filter etc. for 16 nos Water Testing Laboratories of RWS Bankura Sub -Division under Bankura Division, PHE Dte. | 350/BQA | 04/02/2025 | 365 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 51.55 | 0 | 0 | 90
7168 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/19269 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Bankura-II under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. | 159/BK | 28/06/2024 | 61 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.39 | 0 | 0 | 95
7169 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/19269 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Brajarajpur Tentuliya Mahila & Sishu Kalyan Samity sub district water testing laboratories under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. | 160/BK | 28/06/2024 | 61 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.39 | 0 | 0 | 96
7170 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/19269 | Support-WQMSP | Work order for Supervision and extend support to NABL recognised Water Quality Testing Sub District Laboratory i.e.Hijaldiha Vivekananda Seva Samity sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site survelliance by NABL for a period of month from the date of commencement. | 161/BK | 28/06/2024 | 61 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.4 | 0 | 0 | 96
7171 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/19269 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Patrasayer sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. | 282/BK | 29/12/2023 | 62 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.9 | 0 | 0 | 100
7172 | BANKURA | Bankura Division | Procurement of Chemicals & Consumables, glassware etc. required for smooth running of the different laboratories under Bankura Division, PHE Dte. , SM/19269 | Support-WQMSP | Work order for Supervision and extend support to NABL recognised Water Quality Testing Sub District Laboratory i.e. Sonamukhi sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site survelliance by NABL for a period of month from the date of commencement. | 163/BK | 28/06/2024 | 61 | BHARATI CHEMICALS & SCIENTIFIC WORKS | 0.39 | 0 | 0 | 96
7173 | BANKURA | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission. , SM/15258 | Support-WQMSP | Uploading charges of drinking Water samples tested through FTKs related to Water Quality Monitoring & Surveillance Programme under Hirbandh, Indpur, Khatra,Ranibandh,Raipur, Sarenga, Simlapal & Taldangra block Bankura Division PHE Dte. (Part-A) | 135/BK | 08/06/2023 | 15 | ABHIRUP MALLA | 0.97 | 0 | 0 | 100
7174 | BANKURA | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission. , SM/15258 | Support-WQMSP | Uploading charges of drinking Water samples tested through FTKs related to Water Quality Monitoring & Surveillance Programme under Bankura-II,Barjora, Chhatna, Saltora, Gangajalghati & Mejia block Bankura Division PHE Dte. (Part-C) | 137/BK | 08/06/2023 | 15 | ABHIRUP MALLA | 0.97 | 0 | 0 | 100
7175 | BANKURA | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission. , SM/15258 | Support-WQMSP | Uploading charges of drinking Water samples tested through FTKs related to Water Quality Monitoring & Surveillance Programme under Bankura-I, Onda, Bishnupur, Joypur, Kotulpur, Indus, Patrasayer & Sonamukhi block under Bankura Division PHE Dte.(Part-B) | 136/BK | 30/06/2023 | 15 | ABHIRUP MALLA | 0.97 | 0 | 0 | 100
7176 | BANKURA | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission. , SM/15258 | Support-WQMSP | Work order for Shifting of different materials Like FTKs (Fe,FRC,Bacteria, pH, TDS & Turbidity ) including Training Manuals, Data Record Sheet Book & Bags for carrying kits from Office of The Assistant Engineer ,R.W.S Bankura Sub-Division P.H.E. Dte. to Ranibandh, Indus, Bankura-I, Bankura-II & Onda B.M.O.H Office under Bankura District (Sl No.-02) | 53/BK | 04/03/2024 | 7 | ABHIRUP MALLA | 0.09 | 0 | 0 | 95
7177 | BANKURA | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission. , SM/15258 | Support-WQMSP | Work order for Shifting of different materials Like FTKs (Fe, FRC, Bacteria, pH, TDS, Turbidity & Fluoride) including Training Manuals, Data Record Sheet Book & Bags for carrying kits from Office of The Assistant Engineer ,R.W.S Bankura Sub-Division P.H.E. Dte. to Raipur, Hirbandh, Saltora & Bishnupur B.M.O.H Office under Bankura District (Sl No.-03) | 54/BK | 04/03/2024 | 7 | ABHIRUP MALLA | 0.09 | 0 | 0 | 95
7178 | BANKURA | Bankura Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission. , SM/15258 | Support-WQMSP | Work order for Shifting of different materials Like FTKs (Fe,FRC,Bacteria, pH, TDS,Turbidity & Fluoride) including Training Manuals, Data Record Sheet Book & Bags for carrying kits from Office of The Assistant Engineer ,R.W.S Bankura Sub-Division P.H.E. Dte. to Kotulpur, Khatra, Simlapal, Chhatna & Sonamukhi B.M.O.H Office under Bankura District (Sl No.-04) | 55/BK | 04/03/2024 | 7 | ABHIRUP MALLA | 0.09 | 0 | 0 | 95
7179 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Repairing and renovation of bankura district Labortary under Bankura Division, P.H.E.Dte ( Part-I ) | 760/BQA | 04/04/2023 | 60 | GANESH ROY | 3.71 | 0 | 0 | 0
7180 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Upgradation of Water Testing Laboratory of Simlapal Sub District Water Testing Laboratory (Chhoto Sarenga Labour contract & constructive society Ltd) under Bankura Division, P.H.E.Dte. ( Annexure-II) | 756/BQA | 04/04/2023 | 60 | TAPAS DEY | 5.53 | 0 | 0 | 50
7181 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Repairing and renovation of Bankura District Labortary under Bankura Division, P.H.E. Dte. | 27/A/BK | 23/02/2023 | 28 | TAPAS DEY | 0.58 | 0 | 0 | 0
7182 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Supply & Installation 1.5 Ton split A.C for Bacteriological Room at Bankura District Laboratory under Bankura Division, P.H.E. Dte. (Sl No.- 01) | 32/BK | 06/03/2023 | 15 | TAPAS DEY | 0.52 | 0 | 0 | 0
7183 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Supply & Installation 1.5 Ton split A.C for Chemical Room at Bankura District Laboratory under Bankura Division, P.H.E. Dte. (Sl No.- 02) | 34/BK | 06/03/2023 | 15 | TAPAS DEY | 0.52 | 0 | 0 | 0
7184 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Supply & Installation 1.5 Ton split A.C for Wet Laboratory Room at Bankura District Laboratory under Bankura Division, P.H.E. Dte. (Sl No.- 03) | 37/BK | 10/03/2023 | 15 | TAPAS DEY | 0.52 | 0 | 0 | 0
7185 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Submission of U.C for the lab contegency month of January 2022 of March 2022 | FHTC/10 | 04/10/2023 | 0 | SONAMUKHI BIKALPA UNNAYAN SAMITY | 0.08 | 0 | 0 | 0
7186 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | submission of U.C for the lab contegency month of april 2022 to may 2022 | FHTC/10 | 12/10/2023 | 0 | SONAMUKHI BIKALPA UNNAYAN SAMITY | 0.09 | 0 | 0 | 0
7187 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Prayer for release fund for laboratory personal's puja Festival's Bonus for the year 2022 | FHTC/06 | 02/06/2023 | 0 | HIJALDIHA VIVEKANANDA SEVA SAMITY | 0.14 | 0 | 0 | 0
7188 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | water testing laboratoryof our samity (BTMSKS) for administrative expenses for the month of January 2023 to March 2023 |  | 25/05/2023 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 1.5 | 0 | 0 | 0
7189 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Submission of U.C For The Lab Contegency Month of (April 2022 to May 2022) |  | 03/10/2023 | 0 | SONAMUKHI BIKALPA UNNAYAN SAMITY | 0.09 | 0 | 0 | 0
7190 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | water testing laboratory of our samity (BTMSKS) for administrative expense for the month of January 2023 to march 2023 | FHTC/06 | 02/06/2023 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.15 | 0 | 0 | 0
7191 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Payment of laboratory staff of the month May 2023 to August 2023 | FHTC/10 | 04/10/2023 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 1.8 | 0 | 0 | 0
7192 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Administrative expenses of water testing laboratory of our samity (BTMSKS) of the month April 2023 | FHTC/10 | 04/10/2023 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.04 | 0 | 0 | 0
7193 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | payment of laboratory staff for the month of january 2023 to march 2023 | FHTC/06 | 02/06/2023 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 1.35 | 0 | 0 | 0
7194 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Administrative expenses of water testing laboratory of our samity (BTMSKS) of the month May 2023 to August 2023 | FHTC/10 | 04/10/2023 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.2 | 0 | 0 | 0
7195 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | payment for laboratory staff of the month April 2023 | FHTC/10 | 12/10/2023 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.45 | 0 | 0 | 0
7196 | BANKURA | Bankura Mechanical | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Acceptance cum Formal work order for the work of Electrical and illumination works related to instruments and laboratory requirement for prosed water testing laboratory at P.H.E Dte Kanchanpur OHR site , Bankura under Bankura Mechanical Division PHE, Dte. | 1019/BMD | 22/05/2023 | 60 | CHAKRABORTY MINING & ENGINEERING. | 8.54 | 0 | 0 | 70
7197 | BANKURA | Bankura Mechanical | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Acceptance cum Formal work order for the work of Name Electrical and illumination works related to instruments and laboratory requirement for proposed water testing laboratory at Simlapal BPHC campus, Bankura under Bankura Mechanical Division PHE, Dte. | 1020/BMD | 22/05/2023 | 60 | M/S DAS & SARKAR ENTERPRISE | 8.55 | 0 | 0 | 60
7198 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Improvement of water testing laboratory building for Bankura-II Sub District water testing Laboratory (Mallabhum Mahila Kalyan Samity) at Tilabedia OHR site of Bankura -II Block under RWS Bankura Sub- Division under Bankura Division P.H.E. Dte. ( Annexure-I) | 758/BQA | 04/04/2023 | 60 | GOUR GORAI | 12.05 | 0 | 0 | 25
7199 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Improvement of Joypur Sub District Laboratory (Hijaldiha Vivekananda Seva Samity) at Joypur OHR/Headwork Site Campus under Bankura Division PHE Dte. ( Annexure-IV) | 757/BQA | 04/04/2023 | 60 | GANGADHAR MONDAL | 17.92 | 0 | 0 | 70
7200 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | IMPROVEMENT OF INDPUR SUB-DISTRICT LABAROTARY AT JAMBEDIYA WATER SUPPLY SCHEME UNDER BANKURA DIVISION PHE DTE. UNDER JAL JEEVAN MISSION. ( Annexure-V). | 759/BQA | 04/04/2023 | 60 | SAYED PAHALOWAN | 24.03 | 0 | 0 | 97
7201 | BANKURA | Bankura Mechanical | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Acceptance cum Formal work order for the work of Electrical and illumination works related to instruments and laboratory requirement for proposed water testing laboratory at P.H.E Dte OHR site, Joypur water supply scheme, Bankura under Bankura Mechanical Division PHE, Dte. | 1018/BMD | 22/05/2023 | 60 | SUTRADHAR TRADERS | 8.55 | 0 | 0 | 80
7202 | BANKURA | Bankura Mechanical | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Acceptance cum Formal work order for the work of Electrical and illumination works related to instruments and laboratory requirement for proposed Water Testing Laboratory at PHED OHR site, Jambedia of Indpur Sub-District Laboratory under Bankura Mechanical Division PHE, Dte. | 1017/BMD | 22/05/2023 | 60 | KASHINATH DEY | 8.56 | 0 | 0 | 100
7203 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Repairing and Renovation Work of an existing damaged PHE Dte. quarter in connection with sifting of Sonamukhi Sub District Water Testing Laboratory (Formerly Sonamukhi Bikalpa Unnayan Samity) at Sonamukhi Water Supply Scheme Campus, Sonamukhi, Bankura (Door Window Painting, Rack & Table Covering by ACP Pannel, Sanitary, Plumbing, Water Supply, Electrification, Furniture Purchase Work) (Sl No.- 02) | 17/BK | 08/02/2023 | 59 | BIT ENTERPRISE | 3.72 | 0 | 0 | 10
7204 | BANKURA | Bankura Division | Infrastructure Development for Different Water Testing Laboratory regarding NABL Accreditation/Recognition under Bankura Division .PHE Dte. Related to Support Activities Under Jal Jeevan Mission. , SM/15259 | Support-WQMSP | Repairing and Renovation Work of an existing damaged PHE Dte. quarter in connection with sifting of Sonamukhi Sub District Water Testing Laboratory (Formerly Sonamukhi Bikalpa Unnayan Samity) at Sonamukhi Water Supply Scheme Campus, Sonamukhi, Bankura (Dismentling, Dam Proofing, Crack Repairing, Re-Plastering, Flooring, Inside Outside Wall Painting Work) (Sl No.- 01) | 15/BK | 07/02/2023 | 59 | BIT ENTERPRISE | 4.51 | 0 | 0 | 10
7205 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Supply, creation of Sign board at 8 (Seven) nos i.e. Patrasayer Sub District Water Testing Laboratory, Sanabandh Sub District Water Testing Laboratory, Saltora Sub District Water Testing Laboratory, Taldangra Sub District Water Testing Laboratory, Gangajalghati Sub District Water Testing Laboratory and Bishnupur Sub District Water Testing Laboratory, Onda Sub District Water Testing Laboratory and Bankura -ll sab district water testing laboratory under Bankura Division. (Sl No- 01) | 79/BK | 03/05/2023 | 31 | ABHIRUP MALLA | 0.91 | 0 | 0 | 30
7206 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Supply, creation of Sign board at 8 (Seven) nos i.e. Raipur Sub District Water Testing Laboratory, Sonamukhi Sub District Water Testing Laboratory, Simlapal Sub District Water Testing Laboratory, Hijaldiha vivekananda Seva Samity Sub District Water Testing Laboratory, Brajarajpur Tentulia Mahila & Sishu Kalyan Samity, Sarberia Sub District Water Testing Laboratory and Mukutmanipur WTP Site Sub District Water Testing Laboratory.Bankura District Water Testing Laboratory under Bankura Division. (Sl No.- 02) | 80/BK | 03/05/2023 | 31 | ABHIRUP MALLA | 0.91 | 0 | 0 | 20
7207 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Continuation Work order for providing services for operation of 10 (ten) nos Laboratory w.e.f.01.05.2023 to 31.05.2023 under Bankura Division, P.H.E.Dte. | 1526/BQA | 16/06/2023 | 90 | CLIFFORD FACILITY SERVICES PVT. LTD. | 1.1 | 0 | 0 | 80
7208 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Enhancement of monthly remuneration of laboratory personnel working under Bankura Division, P.H.E.Dte. (Arrear payment for 3 Lab from 01.01.2023 to 30.06.2023, Bankura -II,Simlapal, Sonamukhi Sub- District Laboratary). | 2464/BQA | 30/12/2022 | 182 | CLIFFORD FACILITY SERVICES PVT. LTD. | 2.83 | 0 | 0 | 85
7209 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Enhancement of monthly remuneration of laboratory personnel working under Bankura Division, P.H.E.Dte. (Arrear bill for 10 Labs from 01.01.2023 to 23.04.2023) | 2465/BQA | 30/12/2022 | 121 | CLIFFORD FACILITY SERVICES PVT. LTD. | 4.4 | 0 | 0 | 85
7210 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Supply of 1 (one) No. Diesel/ LPG/ CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, R.W.S. Bankura Sub- Division, P.H.E. Dte. W.e.f. 01.01.2024 to 30.06.2024 . | 278/BK | 29/12/2023 | 182 | CHANPA SINGHA | 0.86 | 0 | 0 | 0
7211 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Installation of annual Internet Prepaid recharge of Bankura District Laboratory, Gangajalghati & Patrasayer Sub-District Water Testing Laboratory under Bankura Division, P.H.E.Dte. | 211\A\BK | 21/09/2023 | 366 | TAPAS DEY | 0.09 | 0 | 0 | 95
7212 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | WORK ORDER FOR TAX CONSULTANT FEES FOR THE FINANCIAL YEAR 2022-23 & 2023-24 FOR THE OFFICE OF THE ASSISTANT ENGINEER ,R.W.S BANKURA SUB DIVISION P.H.E. Dte. | 44/BK | 23/02/2024 | 7 | ATANU PATRA | 0.06 | 0 | 0 | 0
7213 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Day to day Operation & Maintenance for 14(Forteen) Nos. PHED Managed Laboratories under Bankura Division, P.H.E. Dte. w.e.f. 01.09.2023 to 30.06.2024. (for 10 months) | 193/BK | 31/08/2023 | 304 | TAPAS DEY | 3.33 | 0 | 0 | 95
7214 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Day to day Operation & Maintenance for the different Laboratories under Bankura Division, P.H.E. Dte. (for 02 months) w.e.f. 01.07.2023 to 31.08.2023. (Sl No-02) | 163\BK | 30/06/2023 | 62 | TAPAS DEY | 0.51 | 0 | 0 | 97
7215 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Day to day operation & Maintenance for the different Laboratories under Bankura Division , P.H.E. Dte. (for 02 months) w.e.f. 01.07.2023 to 31.08.2023. | 164\BK | 30/06/2023 | 62 | TAPAS DEY | 0.14 | 0 | 0 | 98
7216 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Repairing & maintenance works of Bankura District laboratory and 13 (Thirteen) nos. Sub District Water Testing Laboratories under Bankura Division P.H.E. Dte. | 265\BK | 08/12/2023 | 31 | TAPAS DEY | 0.97 | 0 | 0 | 100
7217 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work Order for Shifting of different materials Like FTKs (Fe,FRC,Bacteria, pH, TDS,Turbidity & Fluoride) including Training Manuals, Data Record Sheet Book & Bags for carrying kits from Office of The Assistant Engineer ,R.W.S Bankura Sub-Division P.H.E. Dte. to Ranibandh, Indus, Bankura-I, Bankura-II, Joypur & Taldangra B.M.O.H Office under Bankura District (Sl No.-02) | 09\A\BK | 10/01/2024 | 7 | ABHIRUP MALLA | 0.1 | 0 | 0 | 100
7218 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Shifting of different materials Like FTKs (Fe, FRC, Bacteria, pH, TDS, Turbidity & Fluoride) including Training Manuals, Data Record Sheet Book & Bags for carrying kits from Office of The Assistant Engineer ,R.W.S Bankura Sub-Division P.H.E. Dte. to Raipur, Hirbandh, Saltora, Bishnupur, Indpur & Onda B.M.O.H Office under Bankura District (Sl No.-03) | 11\BK | 11/01/2024 | 7 | ABHIRUP MALLA | 0.1 | 0 | 0 | 100
7219 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Shifting of laboratory machineries from existing N.G.O laboratory to new construct PHED managed laboratory under Bankura Division P.H.E. Dte. (Phase-II) | 79\A\BK | 15/03/2024 | 7 | ABHIRUP MALLA | 0.1 | 0 | 0 | 85
7220 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Sanabandh sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. | 285\\BK | 29/12/2023 | 62 | DULAL MAJUMDER | 0.9 | 0 | 0 | 95
7221 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Providing services for operation of 02 (Two) Nos. Sub-District Water Testing Laboratories w.e.f. 01.07.2024 to 31.12.2024 (06 Months) under Bankura Division, P.H.E. Dte. | 1536/BQA | 21/06/2024 | 183 | TAPAS DEY | 7.08 | 0 | 0 | 95
7222 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Installation of annual Internet Prepaid recharge of Mukutmanipur WTP Laboratory, Sanabandh & Bankura-II Sub-District Water Testing Laboratory under Bankura Division, P.H.E.Dte. | 210/BK | 21/09/2023 | 366 | TAPAS DEY | 0.09 | 0 | 0 | 95
7223 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Installation of annual Internet Prepaid recharge of Raipur, Taldangra & Simlapal Sub-District Water Testing Laboratory under Bankura Division, P.H.E.Dte. | 211/BK | 21/09/2023 | 366 | TAPAS DEY | 0.09 | 0 | 0 | 95
7224 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Festival Bonus of 1(One) no District Laboratory & 02 (Two) nos Sub-District Laboratories i.e. Sanabandh, Sarberia, under Bankura Division, P.H.E.Dte.for the financial year 2023-24 | 236/BK | 04/10/2024 | 20 | TAPAS DEY | 0.79 | 0 | 0 | 95
7225 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Day to day Operation & Maintenance for the Assistant Engineer,R.W.S.Bankura Sub-Division office building and office premises under Bankura Division,P.H.E. Dte.(for 12 months)w.e.f. 01.05.2023 to 30.04.2024. | 73/BK | 28/04/2023 | 366 | GANESH ROY | 0.97 | 0 | 0 | 98
7226 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Installation of annual Internet Prepaid recharge of Saltora & Sarberia Sub-District Water Testing Laboratory under Bankura Division, P.H.E.Dte. | 222\A\BK | 04/10/2023 | 366 | TAPAS DEY | 0.06 | 0 | 0 | 96
7227 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Installation of annual Internet Prepaid recharge of Bishnupur, Onda & Sonamukhi Sub-District Water Testing Laboratory under Bankura Division, P.H.E.Dte. | 222/BK | 04/10/2023 | 366 | TAPAS DEY | 0.09 | 0 | 0 | 95
7228 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Festival Bonus of 04 (Four) nos. Sub-District Laboratories i.e. Saltora, Gangajalghati, Patrasayer, Bishnupur, under Bankura Division, P.H.E.Dte.for the financial year 2023-24 | 237/BK | 04/10/2024 | 20 | TAPAS DEY | 0.94 | 0 | 0 | 95
7229 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Festival Bonus of 04 (Four) nos Sub-District Laboratories i.e. Onda, Raipur, Taldangra, Indpur, under Bankura Division, P.H.E.Dte.for the financial year 2023-24 | 238/BK | 04/10/2024 | 20 | TAPAS DEY | 0.94 | 0 | 0 | 95
7230 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Shifting of different materials Like FTKs (Fe, FRC, Bacteria, pH, TDS, Turbidity & Fluoride) including Training Manuals, Data Record Sheet Book & Bags for carrying kits from Office of The Assistant Engineer , R.W.S Bankura Sub-Division P.H.E. Dte. to Sarenga, Patrasayer, Barjora, Gangajalghati & Mejia B.M.O.H Office under Bankura District (Sl No.-01) | 09\BK | 10/01/2024 | 7 | ABHIRUP MALLA | 0.1 | 0 | 0 | 100
7231 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Shifting of different materials Like FTKs (Fe, FRC, Bacteria, pH, TDS, Turbidity & Fluoride) including Training Manuals, Data Record Sheet Book & Bags for carrying kits from Office of The Assistant Engineer ,R.W.S Bankura Sub-Division P.H.E. Dte. to Kotulpur, Khatra, Simlapal, Chhatna & Sonamukhi B.M.O.H Office under Bankura District (Sl No.-04) | 11\A\BK | 11/01/2024 | 7 | ABHIRUP MALLA | 0.09 | 0 | 0 | 100
7232 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Supply of 1 (one) No. Diesel/ LPG/ CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, R.W.S. Bankura Sub- Division, P.H.E. Dte. W.e.f. 22.07.2023 to 31.12.2023. | 166\BK | 13/07/2023 | 163 | CHANPA SINGHA | 0.77 | 0 | 0 | 70
7233 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Festival Bonus of 04 (Four) nos Sub-District Laboratories i.e. Simlapal, Bankura-II, Sonamukhi & Joypur, under Bankura Division, P.H.E.Dte.for the financial year 2023-24 | 239/BK | 04/10/2024 | 20 | TAPAS DEY | 0.94 | 0 | 0 | 95
7234 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Providing services for operation of 02 (Two) Nos. Sub-District Water Testing Laboratories w.e.f. 01.04.2024 to 30.06.2024 (03 Months) under Bankura Division, P.H.E.Dte. | 911/BQA | 14/03/2024 | 92 | TAPAS DEY | 3.54 | 0 | 0 | 95
7235 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Shifting of laboratory machineries from existing N.G.O laboratory to new construct PHED managed laboratory under Bankura Division P.H.E. Dte. (Phase-I) | 78\A\BK | 15/03/2024 | 7 | ABHIRUP MALLA | 0.1 | 0 | 0 | 90
7236 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Continuation Work Order for Providing services for operation of 1(one) No.District Water Testing Laboratory & 12 ( Twelve) Nos. Sub-District Water Testing Laboratories w.e.f. 01.07.2024 to 30.09.2024(03 Months) under Bankura Division, P.H.E.Dte. | 1587/BQA | 26/06/2024 | 92 | CLIFFORD FACILITY SERVICES PVT. LTD. | 23.43 | 0 | 0 | 95
7237 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Shifting of laboratory machineries from existing N.G.O laboratory to new construct PHED managed laboratory under Bankura Division P.H.E. Dte. (Phase-II) | 78\B\BK | 15/03/2024 | 7 | ABHIRUP MALLA | 0.1 | 0 | 0 | 85
7238 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Shifting of laboratory machineries from existing N.G.O laboratory to new construct PHED managed laboratory under Bankura Division P.H.E. Dte. (Phase-I) | 79\BK | 15/03/2024 | 7 | ABHIRUP MALLA | 0.1 | 0 | 0 | 85
7239 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Payment of laboratory staff for the months December 2023 & January 2024 | FHTC/03 | 12/03/2024 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.9 | 0 | 0 | 0
7240 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | honorarium of lab personal | BP-143/2024-25 | 02/07/2024 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.9 | 0 | 0 | 0
7241 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Lab Maintenance charges & Administrative expenses | BP-144/2024-25 | 02/07/2024 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.2 | 0 | 0 | 0
7242 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Water testing laboratory of our samity (BTMSKS) for administrative expecses for the monthe december 2023 to January 2024 | FHTC/03 | 12/03/2024 | 0 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.09 | 0 | 0 | 0
7243 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Supply of 1 (one) No. Diesel/ LPG/ CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, R.W.S. Bankura Sub- Division, P.H.E. Dte. W.e.f. 01.07.2024 to 31.12.2024 . | 157\BK | 28/06/2024 | 184 | CHANPA SINGHA | 0.87 | 0 | 0 | 0
7244 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | REPARING & MAINTENANCE WORKS OF 1(One) NO. DISTRICT WATER TESTING LABORATORY AND 13(Thirteen)NOs. SUB DISTRICT WATER TESTING LABORATORIES w.e.f. 01.04.2024 to 31.03.2025 UNDER BANKURA DIVISION P.H.E. Dte. | 1499/BQA | 18/06/2024 | 45 | TAPAS DEY | 4.82 | 0 | 0 | 95
7245 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Continuation work order for day to day Operation & Maintenance for 14 (Forteen)Nos. PHED Managed Laboratories under Bankura Division P.H.E.Dte. w.e.f 01.10.2024 to 31.12.2024 | 228/A/BK | 30/09/2024 | 92 | TAPAS DEY | 0.81 | 0 | 0 | 98
7246 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for day to day Operation & Maintenance for 02 (Two)Nos. New PHED Managed Laboratories under Bankura Division P.H.E.Dte. w.e.f 01.07.2024 to 30.09.2024 | 156/BK | 28/06/2024 | 92 | TAPAS DEY | 0.23 | 0 | 0 | 96
7247 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Continuation work order for Day to day Operation & Maintenance for 14(Forteen) Nos. PHED Managed Laboratories under Bankura Division, P.H.E. Dte. w.e.f. 01.07.2024 to 30.09.2024. (for 03 months) | 154/BK | 28/06/2024 | 92 | TAPAS DEY | 0.81 | 0 | 0 | 98
7248 | BANKURA | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/17128 | Support-WQMSP | Work order for Electrification works at Taldangra Sub-District Water Testing Laboratory, Heating and Office room under Taldangra Block under Bankura R.W.S Sub-Division under Bankura Division P.H.E Dte.(Sl. no. 04) | 278/BK | 27/12/2024 | 30 | TAPAS DEY | 0.73 | 0 | 0 | 98
7249 | BANKURA | Bankura Division | Infrastructure development for Taldangra Sub-District water Testing Laboratory regarding NABL accreditation under Bankura Division, PHE Dte. related to support activities under JJM , SM/17416 | Support-WQMSP | WORKS FOR EXTENSION OF TALDANGRA SUB - DISTRICT LABORATORY UNDER BANKURA RWS SUB-DIVISION AT TALDANGRA BLOCK CAMPASS 2021 - 22 | 761/BQA | 04/04/2023 | 453 | UTTAM KUMAR SINHAMAHAPATRA | 16.79 | 0 | 0 | 98
Total | [9 empty] | 7003993.1 | 1334.33 | 0.02