## List of issued work order (Rs.
List of issued work order (Rs. in Lakh)
Sl No. | District | Division | Scheme | Scheme Category | Work Name | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Sail investigation work for identification of sub sail profile for proposed intake WTP & OHR site Marbel Lake its adjoining mouzas area w/s scheme (Tender No. 359/PD of 2020-21) | 58/844322 | 08/06/2021 | 0 | MOYTEC | 1.35 | 0 | 0 | 0
2 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Construction of 30 Cu.m/hr capacity WTP , installation of MS structural intake jetty, supplying and laying 150 mm dia MS ERW raw water pipe line from source to WTP , construction of pump house , boundary wall, drain, inside WTP PCC road etc. for Marble Lake Water Supply Scheme. (Tender No-42/SE/PMU of 20-21) | BP-2022-23-62 | 24/05/2022 | 0 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 23.1 | 0 | 0 | 0
3 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Laying in new alignment of different dia DI and HDPE pipe line for clear water rising main and distribution system & construction of RCC elevated reservoir capacity 100 cum (Torch type) staging height 20 metre at Bhuinghora mouza for marble Lake & adjoining area W/S Scheme of Purulia Sadar Sub- Division (Tender No- 10/2020-21 of SE/PMU/WBPWSP) | BP-2021-22-324 | 22/03/2022 | 0 | ANUP KUMAR SAHA | 89.2 | 0 | 0 | 0
4 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Construction of 30 Cu.m/hr capacity WTP , installation of MS structural intake jetty , supplying and laying 150 mm dia MS ERW raw water pipe line from source to WTP , construction of pump house , boundary wall, drain, inside WTP PCC road etc. for Marble Lake Water Supply Scheme. (Tender No.42/SE/PMU of 2020-21) | BP-2021-22-253 | 25/02/2022 | 0 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 58.72 | 0 | 0 | 0
5 | PURULIA | Purulia Mechanical | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | SUPPLY DELIVERY AND INSTALLATION OF ELECTRO MECHANICAL EQUIPMENTS SUBMERSIBLE PUMP MOTOR SETS FOR RAW WATER PUMP HOUSE , CENTRIFUGAL PUMP MOTOR SETS FOR CLEAR WATER PUMP HOUSE AT MARBLE LAKE PIPED WATER SUPPLY SCHEME (TR.NO 179 OF 21-22) | C022228319640 | 09/02/2022 | 0 | COMBINE ENTERPRISE | 37.42 | 0 | 0 | 0
6 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Supply delivery & installation of submersible pumping machinery for Marble lake W/S scheme of Baghmundi block (Tender No- 372/2021-22 of EE/PMD) | BP-2022-23-23 | 07/04/2022 | 0 | COMBINE ENTERPRISES | 1.82 | 0 | 0 | 0
7 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Laying in new alignment of different dia DI and HDPE pipe line for clear water rising main and distribution system and Construction of R.C.C. Elevated Reservoir, Capcaity 100 cum (Torch Type), Staging height 20 metre at Bhuinghora mouza for Marble Lake & its adjoing area W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division,P.H.E. Dte. | 1416/PD | 29/12/2020 | 12 | ANUP KUMAR SAHA | 178.29 | 58.68 | 32.91 | 0
8 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Construction of 30 Cu.m/hr capacity WTP , installation of MS structural intake jetty , supplying and laying 150 mm dia MS ERW raw water pipe line from source to WTP , construction of pump house , boundary wall, drain, inside WTP PCC road etc. for Marble Lake Water Supply Scheme | 353/PD | 25/02/2021 | 270 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 205.74 | 46.76 | 37.76 | 100
9 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Construction of RCC Back Wash Reservoir of capacity 57.00 Cum at AT WTP Campus site of Marbel Lake W/S Scheme at Ajodhya Hill W/S Scheme of Purulia Sadar Sub-Division, Under Purulia Division, PHE Dte. | 640/PSD | 21/09/2021 | 45 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 4.82 | 0 | 0 | 85
10 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Construction of Fencing on The Entry of Marble Lake under Marble Lake W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | 507/PSD | 12/08/2022 | 25 | ANUP KUMAR SAHA | 1 | 0 | 0 | 100
11 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Laying Remaining Portion of distribution pipe Line due to shifting of OHR Location Of Marble lake & Its Adjoing area W/S Scheme At Ajodhya Hill Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 514/PSD | 12/08/2022 | 45 | ANUP KUMAR SAHA | 4.62 | 0 | 0 | 100
12 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Extension Of Distribution Line Near marble Lake road to Dulgubera and Laying of GI Pipe over Hatinada Khal Of Marble lake & Its Adjoing area W/S Scheme At Ajodhya Hill Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 509/PSD | 12/08/2022 | 45 | ANUP KUMAR SAHA | 4.75 | 0 | 0 | 100
13 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Sinking of 200 mm dia average 180 mtr deep Reverse Rotary/DTH Rigbored tubewell and necessary VES test at Bhuinghora OHR campurs as Additional Source of water for Marble Lake W/S Scheme to mitigate water crisis in draught like situation under Purulia Sadar Sub-Division, PHE Dte.(TubeWell No-1) | 1633/PD | 28/10/2022 | 30 | ANUP KUMAR SAHA | 4.25 | 0 | 0 | 75
14 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Sinking of 200 mm dia average 180 mtr deep Reverse Rotary/DTH Rigbored tubewell and necessary VES test at Bhuinghora OHR campurs as Additional Source of water for Marble Lake W/S Scheme to mitigate water crisis in draught like situation under Purulia Sadar Sub-Division, PHE Dte.(TubeWell No-2) | 1634/PD | 28/10/2022 | 30 | ANUP KUMAR SAHA | 4.25 | 0 | 0 | 100
15 | PURULIA | Purulia Mechanical | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Supply delivery and installation of electro mechanical equipments submersible pump motor sets of Raw water pump house , centrifugal pump motor sets for Clear water pump house at Marble Lake piped water supply scheme , Block : Baghmundi under Purulia Mechanical Division PHE Dte. Dist : Purulia | 471/PMD | 28/07/2021 | 150 | COMBINE ENTERPRISES | 43.7 | 0 | 0 | 100
16 | PURULIA | Purulia Mechanical | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Supply delivery and installation of Voltage stabilizer ,valves, external illumination arrangement with allied works at Marble lake PWSS Under Purulia Mechanical Division PHE Dte Dist-Purulia. | 307/PMD | 16/03/2023 | 30 | COMBINE ENTERPRISES | 13.17 | 0 | 0 | 60
17 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Allied Work of Construction of roof, slab, plaster etc. of New Constructed Ajodhya Camp Office under Marble Lake & Its Adjoing Area W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. | 4675/PSD | 27/07/2023 | 15 | BOSE CONSTRUCTION | 0.88 | 0 | 0 | 100
18 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Construction of Parapet Wall of New Constructed Ajodhya Camp Office under Marble Lake & Its Adjoing Area W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. | 4676/PSD | 27/07/2023 | 15 | BOSE CONSTRUCTION | 0.95 | 0 | 0 | 100
19 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Material Requisition To Resource Division | 47/PD | 15/01/2021 | 0 | Resource Division | 51.57 | 0 | 0 | 0
20 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Laying of Loop Line for the distribution System at different command area of Patuara, Ramjibanpur, Bhomorbera,Lawadih etc of Satra under Marble Lake W/S Scheme Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1500/PD | 27/08/2024 | 735 | SUBODH PRAMANIK | 27.42 | 0 | 0 | 80
21 | PURULIA | Purulia Mechanical | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Supply and installation of PLC panel, Level transmitter with other allied work at Marble Lake water supply scheme under Purulia Mechanical Division PHE Dte. | 1577/PMD | 14/11/2024 | 90 | SUBRATA DUTTA | 14.57 | 0 | 0 | 0
22 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Construction of boundary wall for OHR campus at Bhuinghora mouza of Marbel Lake W/S Scheme at Ajodhya Hill under Purulia Division, PHE Dte. | 1280/PD | 07/12/2020 | 30 | SHAYED NADEEM AHAMAD | 9.05 | 8.32 | 100 | 0
23 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Construction of Office Cum Godown at Ist Floor of Ajodhya Camp Office under Marble Lake & Its Adjoing Area W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. | 538/PD | 01/04/2022 | 100 | BOSE CONSTRUCTION | 20.61 | 0 | 0 | 98
24 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Continuation work order for O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte. [w.e.f 21.02.23 to 20.05.23] | 245/PD | 20/02/2023 | 90 | ANUP KUMAR SAHA | 1.68 | 0 | 0 | 100
25 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Continuation work order for O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte. [w.e.f 29.08.23 to 26.11.23] | 1169/PD | 28/08/2023 | 90 | ANUP KUMAR SAHA | 1.68 | 0 | 0 | 100
26 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Continuation work order for O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte. [w.e.f 21.05.23 to 28.08.23] | 678/PD | 17/05/2023 | 90 | ANUP KUMAR SAHA | 1.68 | 0 | 0 | 100
27 | PURULIA | Purulia Mechanical | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Arrangement of Pandel & other Miscellaneous works for infield training at Pump operator & valve operator of different water supply scheme under Purulia Mechanical Division, PHE Dte. | 23/PMSD(Drilling) | 16/02/2024 | 15 | AMIT PATHAK | 0.54 | 0 | 0 | 100
28 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Allied works for construction of office cum Godown at Ajodhya under Marble Lake W/S Scheme Purulia Division, PHE Dte. (JJM) | 1516/PD | 27/08/2024 | 45 | BOSE CONSTRUCTION | 11.59 | 0 | 0 | 100
29 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Laying HDPE distribution pipeline to cover the left out habitation of Ajodhya, Bagandih & Chatni mouza at Ajodhya Under Marble Lake W/S Scheme under Purulia Division, PHE Dte. | 1510/PD | 27/08/2024 | 45 | TUMPA GORAIN | 23.18 | 0 | 0 | 100
30 | PURULIA | Purulia Mechanical | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Arrangement of refreshment for infield training of pump operator & valve operator of different water supply scheme under Purulia Mechanical Division, PHE Dte. | 24/PMSD(Drilling) | 16/02/2024 | 15 | AMIT PATHAK | 0.43 | 0 | 0 | 100
31 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Construction of shed and other works at Manbhum Paridarshan Abas Campus under Marble Lake W/S Scheme Purulia Division, PHE Dte. | 1499/PD | 27/08/2024 | 45 | MAHARSHI BANERJEE | 5.61 | 0 | 0 | 100
32 | PURULIA | Purulia Division | Piped Water Supply Scheme from Marble Lake to adjoining areas. , SM/07764 | New | Construction of main drain at Baghmundi WTP Site under Piped Water Supply Scheme from Marble Lake under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 892/PD | 07/05/2024 | 45 | ROY CONSTRUCTION | 2.32 | 0 | 0 | 100
33 | PURULIA | Purulia Mechanical | Augmentation of Beldi Water Supply Scheme , SM/09218 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Beldi Water Supply scheme Block Arsha under PMD PHE Dte. District Purulia. | 165/PMD | 07/03/2022 | 30 | DEBJYOTI BASU | 20.5 | 0 | 0 | 100
34 | PURULIA | Purulia Division | Augmentation of Beldi Water Supply Scheme , SM/09218 | Augmentation | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Tumba-Jhalda, Gouradag & Jhariadih) Part-B | 1241/PD | 01/12/2020 | 45 | SUSANTA KR DUTTA | 42.97 | 0 | 0 | 0
35 | PURULIA | Purulia Division | Augmentation of Beldi Water Supply Scheme , SM/09218 | Augmentation | Repairing and Renovation of Beldi Pump house(OHR Site and Riversite) and repairing of bounday wall under Purulia Sadar Sub Division under Purulia Division ,PHE Dte. | 168/PSD | 18/04/2022 | 30 | ASHOKE ADHIKARY | 4.83 | 0 | 0 | 100
36 | PURULIA | Purulia Division | Augmentation of Beldi Water Supply Scheme , SM/09218 | Augmentation | Construction of 5.0 x 3.0 mtr size Switch Room cum Chlorine Room approach road, plinth protection, surface drain etc. complete at Gouradag Riversite for Beldi W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | 90/PSD | 14/03/2022 | 45 | KANCHAN MAHATO | 4.53 | 0 | 0 | 85
37 | PURULIA | Purulia Mechanical | Augmentation of Beldi Water Supply Scheme , SM/09218 | Augmentation | Supply delivery and installation of centrifugal pumping machineries, voltage stabilizer, Flowmeter with necessary substitutes and allied works at BELDI w/s scheme under PMD, PHE Dte. in the District of Purulia.. | 201/PMD | 28/02/2023 | 60 | TAPAN KUMAR DEY | 34.55 | 0 | 0 | 60
38 | PURULIA | Purulia Mechanical | Augmentation of Beldi Water Supply Scheme , SM/09218 | Augmentation | Rectification of different feeders of Beldi W/S scheme(Low lift) for Augmentation of Beldi W/S Scheme under PMD, PHE Dte. in the District of Purulia. | 421/PMD | 11/03/2024 | 30 | TAPAN KUMAR DEY | 5.21 | 0 | 0 | 30
39 | PURULIA | Purulia Division | Augmentation of Beldi Water Supply Scheme , SM/09218 | Augmentation | Construction of WBSEDCL Room and Repairing of old Rising Main Pipeline for Augmentation of Sirkabad W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. (Under Beldi Water Supply Scheme) | 314/PD | 01/03/2024 | 243 | KABERI DUTTA | 2.53 | 0 | 0 | 100
40 | PURULIA | Purulia Division | Augmentation of Beldi Water Supply Scheme , SM/09218 | Augmentation | Bill payment for TDS Certificate 26Q for the Q.E June,2023 to September,2023. | BP-2024-25-18 | 22/04/2024 | 0 | NIGAM CONSULTANCY SERVICE | 0.35 | 0 | 0 | 0
41 | PURULIA | Purulia Division | Augmentation of Beldi Water Supply Scheme , SM/09218 | Augmentation | Indian Railways Miscellaneous collection | BP-2023-24-758 | 11/01/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 0.01 | 0 | 0 | 0
42 | PURULIA | Purulia Division | Augmentation of Beldi Water Supply Scheme , SM/09218 | Augmentation | Xerox bill paid for Raghunathpur Sub Division. | BP-2023-24-797 | 06/02/2024 | 0 | DUTTA XEROX CENTRE | 0.06 | 0 | 0 | 0
43 | PURULIA | Purulia Division | Augmentation of Beldi Water Supply Scheme , SM/09218 | Augmentation | Construction of 5.0 x 3.0 mtr size Guard Room, plinth protection,surface drain etc.complete at Sirkabad Riversite for Sirkabad W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte.(Under Beldi Water Supply Scheme) | 313/PD | 01/03/2024 | 212 | MAHATO CONSTRUCTION | 5.5 | 0 | 0 | 100
44 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10224 | School | FHTC Connetion for School Hura W/s Scheme. |  | 18/07/2022 | 0 | MS D.PALIT AND CO. | 225.03 | 0 | 0 | 0
45 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10224 | School | Water supply Tap Connection Arrangement for 35 nos School upto 200 Students within Hura Block (Part-C) and 15 nos School upto 200 Students within Raghunathpur-II Block (Part-B) of Purulia District under Purulia Division, PHE Dte. (Tender No. 23/2022-23 of SE/PMU/WBPWSP(P) ) | BP-2022-23-235 | 05/09/2022 | 0 | BALAJI UDDYOG | 77.99 | 0 | 0 | 0
46 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10224 | School | ESTIMATE FOR WATER SUPPLY ARRANGEMENT OF CHITORMA JUNIOR HIGH SCHOOL, PABRA PRY SCHOOL & DAMANPUR PRY SCHOOL IN RAGHUNATHPUR-II BLOCK OF THE DISTRICT PURULIA UNDER PURULIA DIVISION, PHE. DTE. FOR (ESTIMATE FOR MODEL -1 , UPTO 200 STUDENTS). SL NO.03 | 27/PR | 31/01/2022 | 180 | PRATIK SAHA | 3.16 | 0 | 0 | 0
47 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10224 | School | Water supply Tap Connection Arrangement for 45 nos School upto 200 Students, 7 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Hura Block (Part-A) of Purulia District under Purulia Division, PHE Dte | 567/PD | 08/04/2022 | 45 | MS D.PALIT AND CO. | 227.54 | 0 | 0 | 100
48 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10224 | School | Providing Functional Household Tap Connection (FHTC) at different AWC, School and other allied works of Raghunathpur Water Supply Scheme (Zone-VIII) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 170/RNP | 07/04/2022 | 30 | KHITISH CHANDRA PATHAK | 1.88 | 0 | 0 | 0
49 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10224 | School | Water supply Tap Connection Arrangement for 49 nos School upto 200 Students within Hura Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | 678/PD | 25/04/2022 | 45 | EQUIPMENTS AND SPARES AGENCIES | 206.57 | 0 | 0 | 100
50 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10224 | School | Water supply Tap Connection Arrangement for 38 nos School upto 200 Students, within Purulia-II Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | 414/PD | 16/03/2022 | 45 | ANUP KUMAR SAHA | 159.38 | 0 | 0 | 100
51 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10224 | School | Water supply Tap Connection Arrangement for 35 nos School upto 200 Students within Hura Block (Part-C) and 15 nos School upto 200 Students within Raghunathpur-II Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | 699/PD | 28/04/2022 | 45 | BALAJI UDDYOG | 210.78 | 0 | 0 | 100
52 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10224 | School | Water supply Tap Connection Arrangement for 45 nos School upto 200 Students, 3 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Raghunathpur-II Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | 700/PD | 28/04/2022 | 45 | BALAJI UDDYOG | 211.01 | 0 | 0 | 100
53 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 203 nos. under Hura & Raghunathpur-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10224 | School | FHTC Connetion for School Hura W/s Scheme. |  | 18/07/2022 | 0 | MS D.PALIT AND CO. | 225.03 | 0 | 0 | 0
54 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Nutundih GP, Raghunathpur-II Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 681/PMD | 28/09/2022 | 15 | KHITISH CH. PATHAK | 25.33 | 0 | 0 | 0
55 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Borrah GP, Raghunathpur-II Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 679/PMD | 28/09/2022 | 15 | NUPUR CHANDRA HALDER | 15.87 | 0 | 0 | 0
56 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Mangalda Moutore GP, Raghunathpur-II Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 680/PMD | 28/09/2022 | 15 | KHITISH CH. PATHAK | 38 | 0 | 0 | 0
57 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Raghunathpur-II Block (Part-H) of Purulia District under Purulia Division, PHE Dte. (Tender No- 19/2022-23 of EE/PD) | BP-2022-23-431 | 25/11/2022 | 0 | JYOTY SOLAR POWER | 65.07 | 0 | 0 | 0
58 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | ESTIMATE FOR WATER SUPPLY ARRANGEMENT OF NARENDRAPUR PRY SCHOOL, CHANGURI PRY.NARIRA PRY IN RAGHUNATHPUR-II BLOCK OF THE DISTRICT PURULIA UNDER PURULIA DIVISION, PHE. DTE. FOR (ESTIMATE FOR MODEL -1 , UPTO 200 STUDENTS). SL NO.09 | 33/PR | 31/01/2022 | 180 | ANUDIP SAHA | 3.18 | 0 | 0 | 0
59 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Water supply Tap Connection Arrangement for 19 nos AWC within Raghunathpur-II Block of Purulia District under Purulia Division, PHE Dte.(Phase-II) [Part-B(4 Nos.), Part-D & F] | 822/PD | 17/05/2022 | 45 | WRISHI ENTERPRISE | 86.06 | 0 | 0 | 35
60 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Joradih GP and Chelyama GP, Raghunathpur-II Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 709/PMD | 17/10/2022 | 30 | ANUP KR. SAHA | 69.67 | 0 | 0 | 0
61 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Execution of the yield test at Serendi, Tunturi- Suisa GP in Bagmundi Block within the district of Purulia under code SM10250 under PMD, PHE, Dte. | 21/PMSD(Drilling) | 31/01/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0 | 0
62 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Raghunathpur-II Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | 499/PD | 29/03/2022 | 45 | JYOTY SOLAR POWER | 71.04 | 0 | 0 | 0
63 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Nildih GP, Raghunathpur-II Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 682/PMD | 28/09/2022 | 15 | RABINDRA NATH KHAN | 28.52 | 0 | 0 | 0
64 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 3 nos AWC within Raghunathpur-II Block (Part-E) of Purulia District under Purulia Division, PHE Dte." | 1734/PD | 22/11/2022 | 45 | MADHU SUDAN RAKSHIT | 14.08 | 0 | 0 | 0
65 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Mangalda Moutore GP, Raghunathpur-II Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.220/EE/PMD of 2022-23) | BP-2022-23-508 | 22/12/2022 | 0 | KHITISH CHANDRA PATHAK | 6.56 | 0 | 0 | 0
66 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Neturia GP, Raghunathpur II Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.226/EE/PMD of 2022-23) | BP-2022-23-472 | 16/12/2022 | 0 | KHITISH CHANDRA PATHAK | 18.29 | 0 | 0 | 0
67 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Paradih GP and Chelyama GP, Raghunathpur II Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.218/EE/PMD of 2022-23) | BP-2022-23-463 | 08/12/2022 | 0 | ANUP KUMAR SAHA | 42.76 | 0 | 0 | 0
68 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Borrah GP, Raghunathpur-II Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.222/EE/PMD of 2022-23) | BP-2022-23-528 | 09/01/2023 | 0 | NUPUR CHANDRA HALDER | 11.59 | 0 | 0 | 0
69 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Nildih GP, Raghunathpur-II Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.219/EE/PMD of 2022-23) | BP-2022-23-452 | 02/12/2022 | 0 | RABINDRANATH KHAN | 17.88 | 0 | 0 | 0
70 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Mangalda Moutora GP, Raghunathpur II Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.220/EE/PMD of 2022-23) | BP-2022-23-471 | 16/12/2022 | 0 | KHITISH CHANDRA PATHAK | 28.45 | 0 | 0 | 0
71 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Raghunathpur-II Block of Purulia District under Purulia Division, PHE Dte.(Phase-I) [Part-A(12 Nos.) & Part-B(8 Nos.)] | 823/PD | 17/05/2022 | 45 | NATIONAL CONSTRUCTION | 90.59 | 0 | 0 | 60
72 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within RAGHUNATHPUR-II Block (Part-C),12 nos Awc Within RAGHUNATHPUR block (Part-G) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | 1871/PD | 13/12/2022 | 45 | RABINDRANATH KHAN | 66.19 | 0 | 0 | 50
73 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Water supply Tap Connection Arrangement for 4 nos AWC within RAGHUNATHPUR-II Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | 1870/PD | 13/12/2022 | 45 | M/S ACHARJEE CONSTRUCTION | 32.75 | 0 | 0 | 50
74 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos)under Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10250 | Anganwadi | Construction of Rigbored Tube well (200mmx 165mm) by DTH method in different sourceless AWC at Raghunathpur-ll Block where adjacent road is narrow and critical under Purulia Mechanical Division PHE. Dte. in the District of Purulia | 70/PMD | 31/01/2023 | 20 | GOENKA ENTERPRISE | 41.02 | 0 | 0 | 15
75 | PURULIA | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme , SM/15936 | Augmentation | Construction of RCC Clear Water Reservoir (CWR) of capacity 15m3 including ventury etc. complete at Eklabya Model School Campus, Susunia Manbazar II Block of Manbazar II Block(part) W/S Scheme under Purulia Division, PHE Dte. | 1632/PD | 03/11/2022 | 100 | ROY CONSTRUCTION | 4.81 | 0 | 0 | 0
76 | PURULIA | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme , SM/15936 | Augmentation | Guarding arrangement through Registered firm organized by Ex-Military person for WTP site of surface water supply scheme for Manbazar-II Block (Part) under Purulia Sadar Sub-Division, PHE Dte. (w.e.f. 01.04.2022 to 30.04.2022) | 531/2/PD | 30/03/2022 | 30 | FRONTLINE EX-SERVICEMEN BUREAU | 1.4 | 0 | 0 | 0
77 | PURULIA | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme , SM/15936 | Augmentation | 1. Identification of parallel distribution pipeline & loop pipeline including preparation of drawing & other allied works to cater the water supply problem in household tap connections at manbazar-II block under Purulia Division, PHE Dte. | 355/PD | 14/03/2023 | 30 | M/S. DESTINY CONSTRUCTION | 9.54 | 0 | 0 | 25
78 | PURULIA | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme , SM/15936 | Augmentation | Material Requisition To Resource Division | 528/PD | 11/04/2023 | 0 | Resource Division | 644.45 | 0 | 0 | 0
79 | PURULIA | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme , SM/15936 | Augmentation | Regarding laying of water supply pipe line along road side and road crossing on Boro-Jamtoria Road in respect of Augumentation of Manbazar-II water supply scheme JJM in District of Purulia. | BP-2023-24-664 | 10/11/2023 | 0 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 6.02 | 0 | 0 | 0
80 | PURULIA | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme , SM/15936 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Goverment Office,Health Centre, ICDS Centre,SSK,MSK,Primary School ,High school at different habitation under command area Zone-III & Zone-IV of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-I, Part-II) | 511/PSD | 12/08/2022 | 45 | SADHAN GORAIN | 2.43 | 0 | 0 | 100
81 | PURULIA | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme , SM/15936 | Augmentation | Laying of Dedicated distribution pipe line For Paisagora under command area Zone-II under Jal Jeevan Mission (JJM and JAL SAPNA) of Manbazar II Block (part) Water Supply Scheme ofManbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | 1840/PD | 12/12/2022 | 45 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 32.63 | 0 | 0 | 100
82 | PURULIA | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme , SM/15936 | Augmentation | Conducting reconnaissance of feasible check dam site fo empounding reservoir site over rivers, recommending pinpoint site, conducting contour, longitudinal and traverse level survey on waterways and ponds with all geo reference, submission of report to E-I-C for preparation hydro graphic survey map of intake site at mukutmanipur dam & contour map of proposed WTP site of southern sector at Manbazar - II Block under Purulia Division, PHE Dte. | 364/PD | 14/03/2023 | 30 | LEMNISCATE | 11.16 | 0 | 0 | 100
83 | PURULIA | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme , SM/15936 | Augmentation | Laying of Loop Pipe Line for distribution System under command area Zone-II at different habitation For Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeevan Mission (JJM and JAL SAPNA) of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte .(From Zone-II OHR to Dhabakata village,Jaragora village Via Boro Mor) | 502/PD | 31/03/2023 | 45 | PRIYATOSH MUKHERJEE | 94.15 | 0 | 0 | 100
84 | PURULIA | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme , SM/15936 | Augmentation | Laying of Loop Pipe Line for distribution System under command area Zone-II at different habitation For Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeevan Mission (JJM and JAL SAPNA) of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte .(Part-II- FromZ-II OHR to Dangardi,Boro PS to Joypur-Chotokadam-Dhadangar Mudipara, Dharampur Namopara, Goialapara Via Rampu Mahato Para) | 503/PD | 31/03/2023 | 45 | MS D.PALIT AND CO. | 85.65 | 0 | 0 | 100
85 | PURULIA | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme , SM/15936 | Augmentation | Laying of Loop Pipe Line for distribution System under command area Zone-I at different habitation For Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeevan Mission (JJM and JAL SAPNA) of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte .-FromManikdih mor to Dhanda village Via Tilaboni Mor,)Punda,Govindpur, Tilaboni, Toparbad.) | 537/PD | 12/04/2023 | 45 | MOONLIGHT HOUSE | 29.2 | 0 | 0 | 100
86 | PURULIA | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme , SM/15936 | Augmentation | Laying of Loop Pipe Line for distribution System under command area Zone-I at different habitation For Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeevan Mission (JJM and JAL SAPNA) of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte - i)FromBasantapur mor to Jugiadih village ii) Panra Morto Uppar pannra & Choto Pannra),Olgara, Kumari,) | 538/PD | 12/04/2023 | 45 | RAKSHIT ENTERPRISE | 25.94 | 0 | 0 | 100
87 | PURULIA | Purulia Division | Augmentation of Manbazar-II Block(Part) Water Supply Scheme , SM/15936 | Augmentation | Shifting and laying of HDPE distribution main pipeline from Burudi more to Dharampur village end due to widening of PWD road at Manbazar-2 block under Manbazar-II Water Supply Scheme Under Purulia Division ,PHE Dte | 671/PD | 17/05/2023 | 60 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 41.18 | 0 | 0 | 100
88 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Supply, Delivery, Storage, Installation and Commissioning of Secondery Gaseous Chlorination Arrangement at Zone -I, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | 2386/W-181/JICA/PMU/2022 | 10/08/2023 | 184 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 26.42 | 0 | 0 | 0
89 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Supply, Delivery, Storage, Installation and Commissioning of Secondary Gaseous Chlorination Arrangement at Zone -VI, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | 2391/W-181/JICA/PMU/2022 | 10/08/2023 | 360 | COMBINE ENTERPRISE | 26.46 | 0 | 0 | 0
90 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Material Requisition To Resource Division | 2147/W-181/JICA/PMU/2013 | 26/07/2023 | 0 | Resource Division | 91.65 | 0 | 0 | 0
91 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Material Requisition To Resource Division | 2068/W-34/JICA/PMU/2013 | 24/07/2023 | 0 | Resource Division | 2368.36 | 0 | 0 | 0
92 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Supply, Delivery, Storage, Installation and Commissioning of Secondary Gaseous Chlorination Arrangement at Zone -VIII, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | 2393/W-181/JICA/PMU/2022 | 10/08/2023 | 520 | TAPAN KUMAR DEY | 26.44 | 0 | 0 | 0
93 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Supply, Delivery, Storage, Installation and Commissioning of Secondery Gaseous Chlorination Arrangement at Zone -II, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | 2387/W-181/JICA/PMU/2022 | 10/08/2023 | 532 | TAPAN KUMAR DEY | 26.44 | 0 | 0 | 84
94 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Providing Mechanical/ Electrical Works with all Ancillaries and Auxiliaries for High Lift Pumping Machinery, Gaseous Chlorination, Illumination arrangement at Intermediate Booster Pumping Station - II of Left-Out Mouzas of Barabazar Piped Water Supply Scheme under PMU, WBPWSP (P) PHE Dte. in the District of Purulia. | 2401/W-181/JICA/PMU/2022 | 11/08/2023 | 537 | RABINDRA NATH KHAN | 102.5 | 0 | 0 | 40
95 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Soil investigation for determining the safe bearing capacity and other relevant parameters of soil in 8 nos different OHR site & 2 nos CWR site of surface Water Based Piped water Supply Scheme for left out mouzas of Barabazar Block,Purulia under JICA Assisted WBPWSP(P), PHE DTE | 2523/W-181/JICA/PMU/2022 | 22/08/2023 | 116 | MABCO CONSULTANT | 7.24 | 0 | 0 | 100
96 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Material Requisition To Resource Division | 1001/W-181/JIC/PMU/2022 | 30/04/2024 | 0 | Resource Division | 194.9 | 0 | 0 | 0
97 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Material Requisition To Resource Division | 594/W-181/JICA/PMU/2022 | 06/03/2024 | 0 | Resource Division | 38.92 | 0 | 0 | 0
98 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Conducting route survey & investigation of command area map along the road fixing up alignment including showing existing distribution and Rising Main net works,all structures and features at Barabazar Leftout portion under PMU, WBPWSP (Purulia), PHE Dte. | 1300/W-181/JICA/PMU/2013 | 12/07/2022 | 15 | INDRANIL DUTTA & ASSOCIATES | 4.62 | 0 | 0 | 100
99 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Construction of Over Head Reservoir of Capacity 100 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-II water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | 2347/W-181/JICA/PMU/2022 | 09/08/2023 | 990 | M/S S & P CONSTRUCTION | 218.93 | 0 | 0 | 82
100 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Laying of Rising Main cum Transmission Main for The Piped Water Supply Scheme for Left-Out Mouzas of Barabazar Block, Dist. Purulia under West Bengal Project Management Unit, Purulia, PHE Dte. | 2348/W-181/JICA/PMU/2022 | 09/08/2023 | 1020 | M/S S & P CONSTRUCTION | 247.24 | 0 | 0 | 86
101 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Supply, Delivery, Storage, Installation and Commissioning of Secondary Gaseous Chlorination Arrangement at Zone -VII, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | 2392/W-181/JICA/PMU/2022 | 10/08/2023 | 1075 | ANUP KUMAR SAHA | 26.46 | 0 | 0 | 0
102 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Construction of Over Head Reservoir of Capacity 250 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-I water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | 2351/W-181/JICA/PMU/2022 | 09/08/2023 | 990 | SANTANU BANERJEE | 459.23 | 0 | 0 | 80
103 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Construction of Over Head Reservoir of Capacity 150 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-IV water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | 2349/W-181/JICA/PMU/2022 | 09/08/2023 | 1080 | PARTHA PRATIM CHHATAIT | 217.07 | 0 | 0 | 40
104 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Supply, Delivery, Storage, Installation and Commissioning of Secondary Gaseous Chlorination Arrangement at Zone -V, OHR Under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | 2390/W-181/JICA/PMU/2022 | 10/08/2023 | 694 | M/S SAJAHAN CHOWDHURY | 26.44 | 0 | 0 | 0
105 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Providing Mechanical / Electrical Works with all Ancillaries and Auxiliaries for High Lift Pumping Machinery, Substation, Gaseous Chlorination, illumination arrangement at Intermediate Booster Pumping Station - I of Left-Out Mouzas of Barabazar Piped Water Supply Scheme under PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | 2394/W-181/JICA/PMU/2022 | 10/08/2023 | 1357 | EASTERN INDIA SALES & SERVICE | 334.6 | 0 | 0 | 0
106 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Construction of Over Head Reservoir of Capacity 300 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-VI water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | 2354/W-181/JICA/PMU/2022 | 09/08/2023 | 810 | PRINCE INDUSTRIES ( INDIA) | 429.21 | 0 | 0 | 75
107 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Providing Yard Lighting and other related works at OHRs for Left-Out Mouzas of Barabazar Piped Water Supply Scheme under PMU, WBPWSP (P) PHE Dte. in the District of Purulia. | 2402/W-181/JICA/PMU/2022 | 11/08/2023 | 915 | PROGRESSIVE ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 30.85 | 0 | 0 | 0
108 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Supply, Delivery, Storage, Installation and Commissioning of Secondary Gaseous Chlorination Arrangement at Zone -IV, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | 2389/W-181/JICA/PMU/2022 | 10/08/2023 | 521 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT. LTD. | 26.46 | 0 | 0 | 0
109 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Construction of Over Head Reservoir of Capacity 250 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-VII water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | 2353/W-181/JICA/PMU/2022 | 09/08/2023 | 810 | S.DUTTA | 464.97 | 0 | 0 | 50
110 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Construction of Over Head Reservoir of Capacity 300 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-III water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | 2405/W-181/JICA/PMU/2022 | 11/08/2023 | 810 | DEBAKI RANJAN SARKAR | 524.57 | 0 | 0 | 30
111 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Construction of 600 cum capacity CWR, 75 cum capacity CWR, 1 no of Sub-station Building, 2 nos of Pump Houses & Boundary Wall of CWRs of water supply scheme of left-out mouzas of Barabazr under West Bengal Project Management Unit, Purulia, PHE Dte. | 2350/W-181/JICA/PMU/2022 | 09/08/2023 | 900 | SAMAN KUMAR MAHATO | 184.49 | 0 | 0 | 40
112 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Supply, Delivery, Storage, Installation and Commissioning of Secondery Gaseous Chlorination Arrangement at Zone -III, OHR under Left-Out Mouzas of Barabazar Piped Water Supply Scheme, PMU, WBPWSP (P), PHE Dte. in the District of Purulia. | 2388/W-181/JICA/PMU/2022 | 10/08/2023 | 530 | SUBRATA DUTTA | 26.46 | 0 | 0 | 0
113 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Construction of Over Head Reservoir of Capacity 400 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-VIII water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | 2406/W-181/JICA/PMU/2022 | 11/08/2023 | 1080 | ANUP KUMAR SAHA | 658.94 | 0 | 0 | 75
114 | PURULIA | PMU - WBDWSIP - EE-II | Left out Mouzas of Barabazar pipe water supply scheme , SM/18319 | New | Construction of Over Head Reservoir of Capacity 300 cum; Stg. Ht. 20mtr., laying of distribution system, Construction of secondary chlorination room and providing FHTC connection under Zone-V water supply scheme of left-out Mouzas of Barabazar surface based Water Supply Scheme under Project Management Unit, West Bengal Piped Water Supply Project (Purulia), PHE Dte. | 2352/W-181/JICA/PMU/2022 | 09/08/2023 | 810 | NIBHAS SINHA | 465.39 | 0 | 0 | 82
115 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Supply delivery and installation of Gaseous Chlorination System, MCC, all electro mechanical equipments at OHR No.-4 under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE Dte. Dist.- Purulia. | 1256/PMD | 17/11/2023 | 90 | RABINDRA NATH KHAN | 21.67 | 0 | 0 | 50
116 | PURULIA | Purulia Division | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Repairing and Renovation of Over Head Reservoir Capcaity 374cum at (ESR) at Lakhanpur W.T.P. under Raghunathpur Area (EAP) W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1720/PD | 04/12/2023 | 483 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 13.36 | 0 | 0 | 0
117 | PURULIA | Purulia Division | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Repairing and renovation of existing structure (i.e. Clarifier Tank, CWR, Pump House, Switch Room etc.) at Lakhanpur WTP under Raghunathpur Area (EAP) W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1719/PD | 04/12/2023 | 453 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 28.94 | 0 | 0 | 0
118 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Repairing of Raw water Intke pump house panel at Lakshmanpur WTP under Raghunathpur water supply project under PMD PHE DTE . | 998/PMD | 21/06/2024 | 90 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 26.2 | 0 | 0 | 0
119 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Replacement of existing one number old VT pump with new one at intake of Lakshmanpur WTP of Raghunathpur W/S Project with allied works, under PMD, PHE, Dte. | 951/PMD | 19/06/2024 | 90 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 20.75 | 0 | 0 | 0
120 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Repairing of Clear water pump house Panel at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD PHE Dte. | 999/PMD | 21/06/2024 | 90 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 57.19 | 0 | 0 | 0
121 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Replacement of existing old Recirculation Sump Pump motor set at Lakshmanpur WTP of Raghunathpur W/S project with allied works, under PMD, PHE, Dte. | 950/PMD | 19/06/2024 | 90 | SAIBAL SARKAR | 22.94 | 0 | 0 | 0
122 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Street light illumination arrangement at Lakshmanpur WTP MiddleSide of Recirculation System under Raghunathpur Water Supply Project underPurulia Mechanical Division, PHE. Dte. | 1545/PMD | 11/11/2024 | 60 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 1 | 0 | 0 | 0
123 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Street light illumination arrangement at Lakshmanpur WTP West Side of Recirculation System under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE. Dte. | 1441/PMD | 01/10/2024 | 30 | MD. ASLAM | 0.99 | 0 | 0 | 0
124 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Repairing and rectification of Gaseous Chlorination system at OHR no. 5,6 & 7 of Raghunathpur Water Supply Project under P.M.D., P.H.E. Dte. | 1182/PMD | 03/11/2023 | 15 | EASTERN INDIA SALES AND SERVICE | 15.26 | 0 | 0 | 100
125 | PURULIA | Purulia Division | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Laying pipe line across railway track area near mouza Shaldiha at Sutaboi under Keliathole Palashkola W/S Scheme within Kashipur Block within Raghunathpur Sub-Division under Purulia Division PHE Dte. | 1532/PD | 16/10/2023 | 30 | SADHAN GORAIN | 52.43 | 0 | 0 | 100
126 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Supply delivery and installation of Gaseous Chlorination System, MCC, all electro mechanical equipments at OHR No.-2 under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE Dte. Dist.- Purulia. | 1254/PMD | 17/11/2023 | 90 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 21.66 | 0 | 0 | 100
127 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Supply delivery and installation of Gaseous Chlorination System, MCC, all electro mechanical equipments at OHR No.-1 under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE Dte. Dist.- Purulia. | 1253/PMD | 17/11/2023 | 90 | TAPAN KUMAR DEY | 21.67 | 0 | 0 | 100
128 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Supply delivery and installation of Gaseous Chlorination System, MCC, all electro mechanical equipments at OHR No.-3 under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE Dte. Dist.- Purulia. | 1255/PMD | 17/11/2023 | 90 | SAIBAL SARKAR | 21.67 | 0 | 0 | 70
129 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Supply of Safety items of Gaseous Chlorination system at Lakshmanpur WTP and OHR no 5 ,6 ,7 under Raghunathpur W/S project under PMD, PHE, Dte | 955/PMD | 19/06/2024 | 90 | TUSHAR GHOSH | 9.75 | 0 | 0 | 100
130 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Replacement of 14 Ring Current Collector at Lakshmanpur WTP Clariflocculator under Raghunathpur water supply project under Purulia Mechanical Division , P.H.E. Dte. | 420/PMD | 11/03/2024 | 296 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 1.48 | 0 | 0 | 100
131 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Supply, delivery & fitting of Fire Extinguisher with refilling of Fire Extinguisher at different sections of Raghunathpur Water Supply Project under Purulia Mechanical Division PHE, Dte. | 434/PMD | 11/03/2024 | 30 | M/S R.K. ENTERPRISE | 2.16 | 0 | 0 | 10
132 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Repairing of Chemical house panel at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD PHE Dte. | 948/PMD | 19/06/2024 | 90 | M/S UJJAL DIESEL SERVICE | 5.66 | 0 | 0 | 100
133 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Repairing of Filter house Panel at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD PHE DTE. | 949/PMD | 19/06/2024 | 90 | MOUSUMI BENERJEE | 10.45 | 0 | 0 | 100
134 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Street light illumination arrangement at Lakshmanpur WTP East side of Recirculation System under Raghunathpur Water Supply Project underPurulia Mechanical Division, PHE. Dte. | 1227/PMD | 13/08/2024 | 20 | M/S R.K. ENTERPRISE | 0.98 | 0 | 0 | 100
135 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Supply & fixing of display board for depicting details of Pump and others at Pump House/Other location of Raghunathpur and other blocks in the Dist-Purulia under Purulia Mechanical Division, PHE Dte. | 1260/PMD | 22/08/2024 | 131 | SUJIT MUKHERJEE | 0.85 | 0 | 0 | 100
136 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | WBSEDCL for Sohardi Mouza, Babugram, P.O-Sanka, Raghunathpur Water Supply Scheme | BP-24-25-28 | 11/06/2024 | 0 | WBSEDCL PURULIA | 2.32 | 0 | 0 | 0
137 | PURULIA | Purulia Division | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Repairing and renovation of existing structure (i.e. Administrative building, Cholrine House, Filter House, Chemical House ) at Lakhanpur WTP under Raghunathpur Area (EAP) W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1718/PD | 04/12/2023 | 409 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 33.25 | 0 | 0 | 100
138 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Defixing the existing idle unit and supply delivery and installation of Electro-Magnetic Flow Meter with cable and remote display unit at different site of WTP. Intake OHR inlet and Outlet pipeline at Forest premises at Garpanchakot, WBSEDCL office premises under Raghunathpur water supply project under PMD. PHE. Dte. | 953/PMD | 19/06/2024 | 408 | EASTERN INDIA SALES AND SERVICE | 83.58 | 0 | 0 | 65
139 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Supply, delivery, laying and connection of cable for high lift pump house power connection and other works under Raghunathpur water supply project under PMD, PHE, Dte. | 1700/PMD | 06/12/2024 | 90 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 68.36 | 0 | 0 | 100
140 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Additional work related to Defixing the existing old unit and installation of new Electro Magnetic Flow meter with cable and remote display unit at different site under Raghunathpur w/s project under PMD, PHE Dte. | 529/PMD | 28/03/2025 | 60 | EASTERN INDIA SALES AND SERVICE | 5.48 | 0 | 0 | 0
141 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Modification of existing filter bed control system with allied works at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD, PHE, Dte. | 568/PMD | 07/04/2025 | 120 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 101.61 | 0 | 0 | 0
142 | PURULIA | Purulia Mechanical | Special Repair & Renovation of W.T.P. at Lakhanpur under Raghunathpur Water Supply Scheme. , SM/18915 | Augmentation | Repairing of internal and External illuminations arrangements at existing Pump house-2 nos, PDB room Transformer room-2 nos , DG room, VCB room-2nos, AVR room, chlorine room, filter house(first floor and ground floor), chemical house (first floor and ground floor), Administrative building and Nine nos of OHR with supply luminaires and under Raghunathpur water supply project under PMD, PHE, Dte. | 952/PMD | 19/06/2024 | 227 | SUBRATA DUTTA | 28.81 | 0 | 0 | 100
143 | PURULIA | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06940 | Retrofitting | Retrofitting of Beldi W/s Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under Jal Sapna Programme (Habitation Covered Beldi, Bhursha, Kumirkuli, Domepara, Goaladih Jatratar) Part-A (Tender No. 8/SE/PMU of 2020-21) | 387/844341 | 08/03/2021 | 0 | BOSE CONSTRUCTION | 31.34 | 0 | 0 | 0
144 | PURULIA | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06940 | Retrofitting | Retrofitting of Beldi water supply scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional House Hold Tap connection (FHTC) under JAL SWAPNA Program (Habitation covered Beldi, Bursha Kalimati, Dome Para, Goaladih ...) Part-A. (Tender No.08/SE/PMU of 2020-21) | 158/8443209 | 17/09/2021 | 0 | BOSE CONSTRUCTION | 10.57 | 0 | 0 | 0
145 | PURULIA | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06940 | Retrofitting | Retrofitting of Beldi W/s Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under Jal Sapna Programme (Habitation Covered Tumba Jhalda, Gouradag & Jharidih) Part-B (Tender No. 191/EE/PD of 2020-21) | 378/84432 | 01/03/2021 | 0 | SUSANTA KR DUTTA | 28.44 | 0 | 0 | 0
146 | PURULIA | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06940 | Retrofitting | Repairing & restoration of the damaged elevated watch reservoir ...under Beldi water supply scheme. (Tender No.08/EE/PD of 2022-23) (Ad-interim) | 127/8443195 | 28/09/2022 | 0 | KOUSHIK CHATTERJEE | 5.5 | 0 | 0 | 0
147 | PURULIA | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06940 | Retrofitting | Additional pipe line of 20mm HDPE (OD) for the work of FHTC of Beldi W/s Scheme at Arsha Block Providing of FHTC under Jal Swapna Programe. (Habitation Name: Tumba Jhalda Goradag) (Tender No.191/EE/PD of 2020-21) | 301/8443105/2 | 18/02/2022 | 0 | SUSANTA KR DUTTA | 2.88 | 0 | 0 | 0
148 | PURULIA | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06940 | Retrofitting | Additional estimate for retrofitting of Beldi Water supply scheme for FHTC in connection with Jal Swapna Project at Arsha Block. (Tender No.324/EE/PD of 2021-22) | 342/8443126/2 | 22/03/2022 | 0 | BOSE CONSTRUCTION | 2.83 | 0 | 0 | 0
149 | PURULIA | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06940 | Retrofitting | Extension of distribution pipeline Providing FHTC under Jal Sapna Programme of Beldi W/S Scheme under Purulia Division PHE Dte. (Habitation Name:-Tumba Jhalda, Gouradag, Jhariadih) (Tender No.878/EE/PD of 2021-22) | 342/8443126/1 | 22/03/2022 | 0 | BOSE CONSTRUCTION | 5.26 | 0 | 0 | 0
150 | PURULIA | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06940 | Retrofitting | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Tumba-Jhalda, Gouradag & Jhariadih) Part-B (Tender No.191/EE/PD of 2020-21) | 301/8443105/1 | 18/02/2022 | 0 | SUSANTA KR DUTTA | 1.97 | 0 | 0 | 0
151 | PURULIA | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06940 | Retrofitting | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Beldi, Bhursa, Kumirkuli, Domepara, Goaladih & Jatratanr) Part-A | 1410/PD | 29/12/2020 | 45 | BOSE CONSTRUCTION | 43.92 | 0 | 0 | 0
152 | PURULIA | Purulia Division | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06940 | Retrofitting | Retrofitting of Beldi Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Tumba-Jhalda, Gouradag & Jhariadih) Part-B | 1241/PD | 01/12/2020 | 45 | SUSANTA KR DUTTA | 42.97 | 7.3 | 100 | 0
153 | PURULIA | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06941 | Retrofitting | Retrofitting of Kudagara W/s Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under Jal Sapna Programme (Habitation Covered Kudagar & Bamundiha) Part-A (Tender No. 12/SE/PMU of 2020-21) | 419/8443127 | 18/03/2021 | 0 | GOUTAM CHAKRABORTY | 28.55 | 0 | 0 | 0
154 | PURULIA | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06941 | Retrofitting | Retrofitting of Kudagara W/s Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional house hold tap connection (FHTC) under Jal Swapna Programme under Purulia Division PHE Dte. (Habitation covered: Gourangdi, Manpur, Kanchanpur & Juradi) Part-B. (Tender No. 195/EE/PD of 2020-21) | 437/8443179 | 27/03/2021 | 0 | HIRAK KUMAR SAO | 11.08 | 0 | 0 | 0
155 | PURULIA | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06941 | Retrofitting | FHTC water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gourangdi, Manpur, Kanchanpur & Juradi Mouza of Kudagara Piped W/s Scheme (Phase-2) (Tender No.422/EE/PD of 2020-21) | 142/844349/1 | 08/09/2021 | 0 | HIRAK KUMAR SAO | 3.03 | 0 | 0 | 0
156 | PURULIA | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06941 | Retrofitting | Retrofitting of Khudagara W/s Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA program (Habitation covered: Gourangdi, Manpur, Kanchanpur & Juradi) Part-B (Tender No.195/EE/PD of 2020-21) | 142/844349/2 | 08/09/2021 | 0 | HIRAK KUMAR SAO | 1.83 | 0 | 0 | 0
157 | PURULIA | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06941 | Retrofitting | FHTC water tap connection ineach house hold from existing distribution system within scheme jurisdiction in Kudagara & Bamundiha Mouza of Khudagar Piped Water Supply Scheme with in Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Phase-2) (Tender No. 408/SE/PMU of 2020-21) | 137/84433/2 | 01/09/2021 | 0 | M/S CHAKRABORTY CONSTRUCTION | 4.28 | 0 | 0 | 0
158 | PURULIA | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06941 | Retrofitting | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Gourangdih, Manpur, Kanchanpur & Juradi) Part-B | 1242/PD | 01/12/2020 | 45 | HIRAK KUMAR SAO | 16.01 | 0 | 0 | 0
159 | PURULIA | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06941 | Retrofitting | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Kudagara & Bamandia) Part-A | 1411/PD | 29/12/2020 | 45 | GOUTAM CHAKRABORTY | 47.17 | 10.6 | 100 | 0
160 | PURULIA | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06941 | Retrofitting | New sinking of 4 (Four) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line with all allied works at Puncha river site of Puncha W/S Scheme under Purulia Division, PHE Dte. | 150/PD | 24/01/2022 | 45 | KOUSHIK CHATTERJEE | 25.5 | 0 | 0 | 100
161 | PURULIA | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06941 | Retrofitting | Emergent Repairing of 100 mm dia Collecting line damaged due to flash flood in connection with Jal Jeevan Mission (JJM) under Kudagara W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 185/PD | 07/02/2023 | 15 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 3.7 | 0 | 0 | 100
162 | PURULIA | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06941 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-K) | 23/PSD | 13/01/2021 | 45 | SIDDHARTHA SANKAR SARKAR | 3.63 | 0 | 0 | 100
163 | PURULIA | Purulia Division | Retrofitting of Kudagara Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06941 | Retrofitting | Emergency piling work along with sand filling at collecting line treanches for protection work against flash flood Khudagara W/S Scheme under Purulia Division, PHE Dte. | 1790/PD | 08/12/2023 | 60 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 39.43 | 0 | 0 | 100
164 | PURULIA | Purulia Division | Retrofitting of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07836 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-B (Mouza- Ghatkul, Gobindapur Alis , Amaidi, Hariraidi ALIS, Birbaldi, Kalipathar, Kharbana, Kulbana, Malancha, Shalchura, Taltly under Gunyarae G.P). (590 Nos.) | 63/PD | 15/01/2021 | 45 | KHITISH CHANDRA PATHAK | 29.98 | 28 | 71.58 | 100
165 | PURULIA | Purulia Division | Retrofitting of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07836 | Retrofitting | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-D) (Tender No. 264/EE/PD of 2020-21) | BP-2021-22-43 | 19/07/2021 | 0 | DEBAKI RANJAN SARKAR | 27.12 | 0 | 0 | 0
166 | PURULIA | Purulia Division | Retrofitting of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07836 | Retrofitting | Construction of Boundary wall, RCC Pillar gate, Barbed wire, and other allied work at Bathanbari Head Work Site under Bathanbari W/s Schemeunder Raghunathpur Sub-Division PHE Dte. (Total length of Boundary Wall 42.00 mtr.) (Tender No.235/EE/PD of 2020-21) | BP-2021-22-65 | 12/08/2021 | 0 | KHITISH CHANDRA PATHAK | 2.76 | 0 | 0 | 0
167 | PURULIA | Purulia Division | Retrofitting of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07836 | Retrofitting | Repairing of Pressure filtre,Plumbing work of toilet,Clearing of OHR Campus and other allied works under Bathanbari W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 113/RNP | 08/02/2021 | 15 | KHITISH CHANDRA PATHAK | 1.47 | 0 | 0 | 90
168 | PURULIA | Purulia Division | Retrofitting of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07836 | Retrofitting | Additional work for FHTC Bathanbari Water supply Scheme [Ad- Interim payment] [Tender No- 935/2021-22 of EE/PD) | BP-2021-22-298 | 09/03/2022 | 0 | KHITISH CHANDRA PATHAK | 5 | 0 | 0 | 0
169 | PURULIA | Purulia Division | Retrofitting of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07836 | Retrofitting | Additional work for functional Household Tap Connection (FHTC) including other allied works of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No.935/EE/PD of 2021-22) | BP-2021-22-300 | 09/03/2022 | 0 | KHITISH CHANDRA PATHAK | 33.31 | 0 | 0 | 0
170 | PURULIA | Purulia Division | Retrofitting of Paharpur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07840 | Retrofitting | Laying of distribution pipe line ( 90 & 75 mm dia HDPE pipe ) for Kargali and Jamua villege of Raghunathpur-II Development Block under Raghunathpur Sub-Divn, P.H.E. Dte. (In connection with Paray Samadhan) | 743/PD | 06/07/2021 | 30 | KHITISH CHANDRA PATHAK | 11.96 | 0 | 0 | 80
171 | PURULIA | Purulia Division | Retrofitting of Paharpur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07840 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Paharpur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (176 Nos.) | 62/PD | 15/01/2021 | 45 | SHYAMAL KUMAR DEY | 9.88 | 8.13 | 100 | 0
172 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07566 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni W/s Scheme at Hura Block. (Zone-I) (1591 Nos) (Tender No. 345/EE/PD of 2020-21) | BP-2021-22-40 | 19/07/2021 | 0 | KOUSHIK CHATTERJEE | 4.69 | 0 | 0 | 0
173 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07566 | Retrofitting | Changing of HDPE Pipe line due to damaged pipe near Rangadih Pry. School near Srishtidhar Mahato House & Kharpara main line to Ranjit Mahato house under kalaboni W/S Scheme (Zone-III) (Part- II) (Tender No. 386/20-21 of EE/PD) | BP-2021-22-45 | 19/07/2021 | 0 | BASANTA KUMAR SINGHADEO | 4.04 | 0 | 0 | 0
174 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07566 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Zone -II (1182 Nos.) (Tender No.384/EE/PD of 2020-21) | BP-2021-22-102 | 13/09/2021 | 0 | BASANTA KUMAR SINGHADEO | 34.04 | 0 | 0 | 0
175 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07566 | Retrofitting | Changing of HDPE Pipe line due to damaged pipe near Rangadih Pry. School near Srishtidhar Mahato House & Kharpara main line to Ranjit Mahato house under kalaboni W/S Scheme (Zone-III) (Part- I) (Tender No. 387/20-21 of EE/PD) | BP-2021-22-46 | 19/07/2021 | 0 | BASANTA KUMAR SINGHADEO | 4.32 | 0 | 0 | 0
176 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07566 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni W/S Scheme at Hura Block of Raghunathpur Sub- Division PHE Dte. at Zone- III (970 Nos.) (Tender No:- 336/EE/PD of 2020-21) | BP-2021-22-89 | 23/08/2021 | 0 | PRIYATOSH MUKHERJEE | 27.81 | 0 | 0 | 0
177 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07566 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni W/S Scheme at Hura Block of Raghunathpur Sub- Division PHE Dte. at Zone- IV (1016 Nos.) (Tender No:- 313/EE/PD of 2020-21) | BP-2021-22-90 | 23/08/2021 | 0 | RABIN CHANDRA CHAIL | 9.69 | 0 | 0 | 0
178 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07566 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni W/s Scheme at Hura Block of Raghunathpur Sub-Division under Purulia Division PHE Dte. at Zone-IV (1016 Nos.) (Tender No. 313/EE/PD of 2020-21) | 10/844326/1 | 12/04/2021 | 0 | RABIN CHANDRA CHAIL | 7.95 | 0 | 0 | 0
179 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07566 | Retrofitting | Temporary water supply arrangement through extension of Distribution Main by supplying & laying 63mm dia HDPE pipe line from Deshra More to Deshra Village (loop line) and to Bathandih Bero Bandh with allied works at Zone-III (Deshra OHR) under Kalabani W/s Scheme (Zone-III) of Raghunathpur Sub-Division PHE Dte. under Purulia Division PHE Dte. (Tender No. 388/EE/PD of 2020-21) | BP-2021-22-124 | 11/10/2021 | 0 | BASANTA KUMAR SINGHADEO | 2.96 | 0 | 0 | 0
180 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07566 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone- I) (120 Nos.) (Tender No.898/EE/PD of 2021-22) | BP-2021-22-268 | 28/02/2022 | 0 | CHAIL CONSTRUCTION | 6.2 | 0 | 0 | 0
181 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07566 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Zone - I (1591 Nos.) (Tender No.345/EE/PD of 2020-21) | BP-2021-22-244 | 16/02/2022 | 0 | KOUSHIK CHATTERJEE | 4.73 | 0 | 0 | 0
182 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07566 | Retrofitting | Functional household Tap connection (FHTC) in connection with other allied works of Kalaboni W/S Scheme at Hura Block of Raghunathpur (Zone-II) (Tender No- 905/2021-22 of EE/PD) | BP-2021-22-318 | 22/03/2022 | 0 | RAHIBUDDIN MONDAL | 12.46 | 0 | 0 | 0
183 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07566 | Retrofitting | Additional work for FHTC including other allied works of Kalabani W/s Scheme. (Tender No.887/EE/PD of 2021-22) | BP-2021-22-257 | 25/02/2022 | 0 | BASANTA KUMAR SINGHADEO | 7.91 | 0 | 0 | 0
184 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07566 | Retrofitting | Additional work for Functional Household tap Connection (FHTC) including other allied works of kalaboni W/S Scheme at Hura block of Raghunathpur Sub- Division Zone-III (Tender No- 942/2021-22 of EE/PD) | BP-2021-22-316 | 22/03/2022 | 0 | PRIYATOSH MUKHERJEE | 8.11 | 0 | 0 | 0
185 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07566 | Retrofitting | Additional work for functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-IV) (Tender No.856/EE/PD of 2021-22) | BP-2021-22-233 | 03/02/2022 | 0 | RABIN CHANDRA CHAIL | 3.76 | 0 | 0 | 0
186 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07566 | Retrofitting | Supplying, laying and aligning of HDPE pipe line and othar allied works at Kalabani Water Supply Scheme (Zone-II) of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 1404/PD | 01/09/2022 | 45 | NANIGOPAL DEY | 19.42 | 0 | 0 | 0
187 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07566 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Zone -IV(1016 Nos.) | 164/PD | 01/02/2021 | 45 | RABIN CHANDRA CHAIL | 45.51 | 22.73 | 100 | 0
188 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07566 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Kalaboni Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Zone -II (1182 Nos.) | 162/PD | 01/02/2021 | 45 | BASANTA KUMAR SINGHADEO | 52.62 | 19.16 | 36.02 | 0
189 | PURULIA | Purulia Division | Retrofitting of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07566 | Retrofitting | Bypass arrangement with allied works in between of over flow line to distribution main Kolaboni Zone-I OHR site under Kolaboni W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 468/RNP | 26/09/2024 | 20 | RABIN CHANDRA CHAIL | 0.95 | 0 | 0 | 100
190 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Tap Connection of different existing PWSS (Jhalda Municipality W/S Scheme block-Jhalda-I) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 360/2021-22 of EE/PD) | BP-2022-23-105 | 16/07/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.97 | 0 | 0 | 0
191 | PURULIA | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | SUPPLY DELIVERY & INSTT OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF JHALDA W/S SCHEME UNDER PMD PHE DTE.(TR.NO 343 OF 2021-22) | C042211566405 | 08/04/2022 | 0 | ANUP KR. SAHA | 12.25 | 0 | 0 | 0
192 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Preparation of DPR (consultancy work) in connection with Functional household Connection of different existing PWSS Jhalda Aug. W/S Scheme (Rural Part) Block- Jhalda-II) to be Augmentation/ Rejuvenation (Tender No- 540/2021-22 of EE/PD) | BP-2021-22-322 | 22/03/2022 | 0 | M/S TECH VISION | 4.69 | 0 | 0 | 0
193 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, part- I) of Jhalda-II Block under Purulia Sadar Sub- Division, PHE Dte. (Part-I Begunkodar Habitation G.P. Begunkodar) (Tender No- 34/2022-23 of SE/PMU/WBPWSP(P) ) | BP-2022-23-112 | 16/07/2022 | 0 | M/S S & P CONSTRUCTION | 49.46 | 0 | 0 | 0
194 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, Part-II) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-II-Chatambari Habitation, GP- Begunkodar) (Tender No.947/EE/PD of 2021-22) | BP-2022-23-26 | 07/04/2022 | 0 | BHAGABANDAS KUMAR | 18.69 | 0 | 0 | 0
195 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, Part-I) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-I-Begunkodar Habitation GP- Begunkodar) (Tender No.34/SE/PMU of 2022-23) | BP-2022-23-408 | 20/10/2022 | 0 | M/S S & P CONSTRUCTION | 35.71 | 0 | 0 | 0
196 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, Part-III) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-III-Jaharhatu,Nischantapur Habitation, GP- Bamnia-Beladh) (Tender No- 149/2022-23 of EE/PD) | BP-2022-23-405 | 20/10/2022 | 0 | ZAKIR HOSSIN MONDAL | 67.77 | 0 | 0 | 0
197 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Laying of DI distribution pipe line for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) in Mouza-Jaharhatu, Habitation-Gurrabera under command area (Zone-IB) of Augementation of Jhalda Water Supply Scheme (Rural Part) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 254/PD | 10/02/2022 | 30 | KANAILAL PAL | 10.08 | 0 | 0 | 0
198 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, Part-I) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-I-Begunkodar Habitation GP- Begunkodar) | 827/PD | 17/05/2022 | 45 | M/S S & P CONSTRUCTION | 153.83 | 0 | 0 | 85
199 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Supplying delivery fitting& fixing of 30 nos of Sign board (ACP Sheet)at different solar tubewell site within Jhalda-2 Block in Purulia District under Purulia Division, PHE Dte. | 255/PD | 31/03/2023 | 5 | R.K ENTERPRISE | 0.63 | 0 | 0 | 70
200 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Supplying delivery fitting& fixing of 20 nos of Sign board (ACP Sheet)at different solar tubewell site within Jhalda-2 Block in Purulia District under Purulia Division, PHE Dte. | 254/PSD | 31/03/2023 | 5 | R.K ENTERPRISE | 0.42 | 0 | 0 | 0
201 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Emergent Dismantling of R.C.C. Elevator Reservoir, Capacity 681 Cum (Intze Type), Staging height 20 meter at Jhalda Municipality OHR site including By pass arrangement for direct supply due to Dismantling of Jhalda OHR with allied works of Jhalda W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 632(1-2)/PD | 24/11/2021 | 60 | ANUP KUMAR SAHA | 24.06 | 0 | 0 | 0
202 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, Part-II) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-II-Chatambari Habitation, GP- Begunkodar) | 68/PD | 17/01/2022 | 45 | BHAGABANDAS KUMAR | 35.23 | 0 | 0 | 85
203 | PURULIA | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Jhalda Water Supply scheme Block Jhalda under PMD PHE Dte. District Purulia. | 113/PMD | 28/02/2022 | 30 | ANUP KUMAR SAHA | 20.47 | 0 | 0 | 100
204 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Jhalda Water Supply Scheme (Zone-II, Part-III) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-III-Jaharhatu,Nischantapur Habitation, GP- Bamnia-Beladh) | 408/PD | 15/03/2022 | 60 | ZAKIR HOSSIN MONDAL | 90.73 | 0 | 0 | 98
205 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Augementation of Jhalda Water Supply Scheme (Rural Part) (Zone-II, Part-IV) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Habitation-Supurdih and Brindabanpur, Gp-Begunkodar) | 649/PD | 22/04/2022 | 45 | BHAGABANDAS KUMAR | 21.02 | 0 | 0 | 100
206 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Repairing, renovation & restoration of Store room including at Masina Pump House site of Jhalda W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | 92/PSD | 14/03/2022 | 30 | CHATTERJEE CONSTRUCTION | 3.58 | 0 | 0 | 95
207 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Withdrawing & relaying of AC pipe line from Birsamor to Sramik Kalyan Kendra, Namopara to Kumarkuli Road and installation of sluice valve and Repairing of valve chamber at Jhalda under Jhalda Municipality W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. | 512/PSD | 12/08/2022 | 30 | SK MANIR | 2 | 0 | 0 | 0
208 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Laying of parallel distribution pipeline for providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area of Jhalda Water Supply Scheme (Zone-II, Part-I) of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-I-Begunkodar Habitation GP- Begunkodar) | 1810/PD | 06/12/2022 | 274 | M/S S & P CONSTRUCTION | 28.57 | 0 | 0 | 80
209 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Supplying delivery fitting& fixing of 30 nos of Sign board (ACP Sheet)at different solar tubewell site within Jhalda-1 Block in Purulia District under Purulia Division, PHE Dte. | 252/PSD | 31/03/2023 | 5 | R.K ENTERPRISE | 0.65 | 0 | 0 | 100
210 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Route Survey & Drawing Preparation for uncovered areas under Jhalda-II Block under Purulia Division, PHE Dte. | 525/PD | 10/04/2023 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 3.21 | 0 | 0 | 100
211 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Laying of distribution pipeline for providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation under Zone-1A command area of Jhalda W/S Scheme of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Phase-II, Zone-1A, Part-I, GP-Begunkodar, Habitation-Murguma, Narayanpur Alias Lakhipur) | 536/PD | 12/04/2023 | 45 | BOSE CONSTRUCTION | 14.61 | 0 | 0 | 100
212 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Material Requisition To Resource Division | 1564/PD | 16/12/2021 | 0 | Resource Division | 70.09 | 0 | 0 | 0
213 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Material Requisition To Resource Division | 393/PD | 11/03/2022 | 0 | Resource Division | 3.18 | 0 | 0 | 0
214 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Material Requisition To Resource Division | 240/PD | 20/02/2023 | 0 | Resource Division | 83.68 | 0 | 0 | 0
215 | PURULIA | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Material Requisition To Resource Division | 618/PMD | 01/06/2023 | 0 | Resource Division | 1.55 | 0 | 0 | 0
216 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Regarding laying of water supply pipe line along road side and road crossing on Begunkodar-Arsha Road in respect of Augumentation of Jhalda (Rural Part) water supply scheme JJM in the District of Purulia. | BP-2022-23-511 | 22/12/2022 | 0 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 12.93 | 0 | 0 | 0
217 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Making Xerox copy of original DPR, Drawing, Mouza Map etc. | 27/2023-149 | 30/05/2023 | 0 | SB CONSTRUCTION | 0.37 | 0 | 0 | 0
218 | PURULIA | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Supply, delivery and installation of centrifugal pumping machineries, MCC panel, Flowmeter With necessary substitutes and allied works at WTP area of Jhalda Augmentation w/s project under PMD, PHE Dte. in the District of Purulia | 45/PMD | 19/01/2023 | 60 | SUNRISE ENGINEERING CORPORATION | 49.44 | 0 | 0 | 60
219 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Supplying delivery fitting& fixing of 20 nos of Sign board (ACP Sheet)at different solar tubewell site within Jhalda-1 Block in Purulia District under Purulia Division, PHE Dte. | 253/PSD | 31/03/2023 | 5 | R.K ENTERPRISE | 0.43 | 0 | 0 | 100
220 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Repairing , renovation & Construction Damaged (portion) of Boundary Wall of Masina Pump House Campus Of Jhalda W/S Scheme Under Purulia Division ,PHE DTE... | 934/PD | 19/07/2023 | 30 | CHATTERJEE CONSTRUCTION | 9.37 | 0 | 0 | 80
221 | PURULIA | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Providing external illumination arrangement at WTP area of Jhalda Aug WTP under PMD, PHE Dte. in the District of Purulia. | 1206/PMD | 03/11/2023 | 60 | ANUP KUMAR SAHA | 2.74 | 0 | 0 | 100
222 | PURULIA | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | New Connection for Augmentation at Begunkodar O.H.R near H.S School, Po begunkadar Ps Kotshila. | BILL/00849/2023 | 01/03/2024 | 0 | WBSEDCL PURULIA | 0.41 | 0 | 0 | 0
223 | PURULIA | Purulia Division | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Providing Functional Household Tap Connection (FHTC) in Goverment Office,Health Centre, ICDS Centre,SSK,MSK, Primary School ,High school at Jhalda Municipalty Under Jhalda Municipalty Water Supply Scheme of Jhalda-I Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-I) | 516/PSD | 12/08/2022 | 323 | SEKH IRFAN | 0.92 | 0 | 0 | 100
224 | PURULIA | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Supply delivery and installation of centrifugal pumping machineries, MCC panel and with necessary substitutes and allied works at the intake of the Jhalda Augmentation w/s project under PMD, PHE Dte. in the District of Purulia | 44/PMD | 19/01/2023 | 714 | ANUP KR. SAHA | 43.88 | 0 | 0 | 70
225 | PURULIA | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at OHR site for Augmentation of Jhalda Water Supply scheme Block Jhalda under PMD PHE Dte. District Purulia. | 83/PMD | 01/02/2023 | 670 | ANUP KR. SAHA | 21.57 | 0 | 0 | 100
226 | PURULIA | Purulia Mechanical | Rejuvenation of Jhalda (Rural Part) Water Supply Scheme to accommodate FHTC , SM/09577 | Augmentation | Replacement of essential item on the intake Burge of Jhalda Augmentation W/S Scheme under P.M.D., P.H.E.Dte | 1173/PMD | 03/11/2023 | 425 | ANUP KUMAR SAHA | 6.21 | 0 | 0 | 50
227 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Construction of switch room cum chlorine room at Zone-II OHR site of Sutaboi W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (Tender No- 857/21-22 of EE/PD) | BP-2022-23-144 | 20/07/2022 | 0 | M/S SAYAK BHATTACHARYA | 4.19 | 0 | 0 | 0
228 | PURULIA | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | NEW SERVICE CONNECTION FOR OHR SITE AT SUTABOI WATER SUPPLY SCHEME UNDER PMD PHE DTE. | BP-2022-23-32 | 08/09/2022 | 0 | WBSEDCL PURULIA | 0.28 | 0 | 0 | 0
229 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Sinking of 08 (Eight) No. 200 mm dia river bed tube well horizontal at Darkeswar river (Sutaboi Ghat) along with laying of 100 mm dia GI collecting line with all allied works under Sutaboi Aug. Water Supply Scheme under Raghunathpur Sub- Division, PHE dte.(Tender No- 952/2021-22 of EE/PD) | BP-2022-23-99 | 16/07/2022 | 0 | ASHOK KUMAR CHATTERJEE | 19.18 | 0 | 0 | 0
230 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Additional work of providing FHTC and other allied works of Sutaboi W/S Scheme at Kashipur under Raghunathpur Sub- Division, PHE Dte. (Tender No:- 54/EE/PD of 2022-23) | BP-2022-23-123 | 19/07/2022 | 0 | SANTANU BANERJEE | 24.43 | 0 | 0 | 0
231 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Re sinking of 02 (Two) No. 200 mm dia river bed tube well horizontal at Darkeswar river (Sutaboi ghat) alongwith laying of 100 mm dia GI collecting line with all allied works under Sutaboi Water Supply Scheme under Raghunathpur Sub- Division, PHE dte. (TW No. 2& 6) (Tender No- 956/2021-22 of EE/PD) | BP-2022-23-104 | 16/07/2022 | 0 | ASHOK KUMAR CHATTERJEE | 4.8 | 0 | 0 | 0
232 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Construction of switch room cum chlorine room at Zone-I OHR site of Sutaboi W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (Tender No- 966/2021-22 of EE/PD) | BP-2022-23-125 | 19/07/2022 | 0 | ASHOK KUMAR CHATTERJEE | 4.22 | 0 | 0 | 0
233 | PURULIA | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | NEW SERVICE CONNECTION AT OHR 2 SITE OF SUTABAI WATER SUPPLY SCHEME UNDER PMD PHE DTE. | BP-2022-23-33 | 08/09/2022 | 0 | WBSEDCL PURULIA | 0.28 | 0 | 0 | 0
234 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Construction of switch room cum chlorine room at Head work site of Sutaboi W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (Tender No- 967/2021-22 of EE/PD) | BP-2022-23-126 | 19/07/2022 | 0 | ASHOK KUMAR CHATTERJEE | 4.23 | 0 | 0 | 0
235 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir at Zone-I & II of Capcaity 350Cum & 150 Cum and other allied works under Sutaboi W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 153/PD | 25/01/2022 | 70 | ASHOK KUMAR CHATTERJEE | 10.24 | 0 | 0 | 0
236 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Construction of RCC Clear water reservoir (CWR) of capacity 100 Cum with other allied works at Sutaboi river site under Sutaboi w/s Scheme under Raghunathpur Sub-Division, PHE Dte | 387/PD | 11/03/2022 | 100 | ASHOK KUMAR CHATTERJEE | 13.89 | 0 | 0 | 0
237 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Laying Distribution pipe line including functional Household Tap Connection (FHTC) and other allied works of Kashipur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-B) | 260/PD | 11/02/2022 | 60 | MUNNA AGROTECH ENTERPRISE | 88.48 | 0 | 0 | 100
238 | PURULIA | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sutabai Water Supply scheme (OHR no 2 Site ) Block Kashipur under PMD PHE Dte. District Purulia. | 310/PMD | 11/05/2022 | 30 | COMBINE ENTERPRISE | 20.48 | 0 | 0 | 96
239 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Additional work by providing functional Household Tap Connection (FHTC) and other allied works of Sutaboi Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 790/PD | 05/05/2022 | 45 | SANTANU BANERJEE | 24.47 | 0 | 0 | 0
240 | PURULIA | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sutabai Water Supply scheme (OHR no 1 Site) Block Kashipur under PMD PHE Dte. District Purulia. | 309/PMD | 11/05/2022 | 30 | ANUP KR. SAHA | 20.47 | 0 | 0 | 96
241 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Sinking of 8 (Eight) nos. 200 mm dia river bed tubewell (Horizontal) at darekeswar river ( Sutaboi Ghat) alongwith laying of 100 mm dia G.I. collecting line with all allied works under Sutaboi Aug. W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | 151/PD | 24/01/2022 | 30 | ASHOK KUMAR CHATTERJEE | 41.88 | 0 | 0 | 0
242 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Construction of Pump House at Head work site of Sutaboi W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 204/PD | 01/02/2022 | 120 | SUJIT CHAKRABORTY | 5.06 | 0 | 0 | 100
243 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Resinking of 2(Two) nos. 200 mm dia river bed tubewell (Horizontal) at darekeswar river ( Sutaboi Ghat) alongwith laying of 100 mm dia G.I. collecting line with all allied works under Sutaboi W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (TW NO-2 & 6) | 144/PD | 24/01/2022 | 30 | ASHOK KUMAR CHATTERJEE | 11.43 | 0 | 0 | 0
244 | PURULIA | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Supply delivery and installation submersible pumping machineries at new deep tube well, MCC panel and laying of cable line, with others allied works for augmentation of Sutaboi water supply scheme under Purulia Mechanical Division, PHE Dte. in the District of Purulia | 324/PMD | 22/03/2023 | 60 | COMBINE ENTERPRISES | 71.28 | 0 | 0 | 100
245 | PURULIA | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Yard lighting arrangement with others allied works at OHR-1 for Augmentation of sutaboi w/s scheme under PMD, PHE Dte. in the District of Purulia. | 392/PMD | 06/04/2023 | 60 | MOUSUMI BENERJEE | 5.88 | 0 | 0 | 100
246 | PURULIA | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Riverbed illumination arrangement with others allied works for Augmentation of Sutaboi w/s scheme under PMD, PHE Dte. in the District of Purulia. | 393/PMD | 06/04/2023 | 60 | MAHIPAL MAJHI | 5.95 | 0 | 0 | 100
247 | PURULIA | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Internal lighting arrangement at Sutaboi pump house, Chlorination room at OHR site 1&2 with others allied works for Augmentation of Sutaboi w/s scheme under PMD, PHE, Dte | 391/PMD | 06/04/2023 | 60 | S. PATHAK & CO. | 2.74 | 0 | 0 | 100
248 | PURULIA | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Yard lighting arrangement with others allied works at OHR-2 under sutaboi w/s scheme under PMD, PHE Dte. in the District of Purulia. | 869/PMD | 21/07/2023 | 60 | M/S UJJAL DIESEL SERVICE | 5.81 | 0 | 0 | 100
249 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Material Requisition To Resource Division | 964/PD | 21/06/2022 | 0 | Resource Division | 33.36 | 0 | 0 | 0
250 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Xerox bill office purpose. | BP-2023-24-301 | 14/07/2023 | 0 | DUTTA XEROX CENTRE | 0.45 | 0 | 0 | 0
251 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Indian railway Miscellaneous collection. | BP-2022-23-555 | 18/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 5.4 | 0 | 0 | 0
252 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/7171 bill paid for the month of May,22 to June,22. | BP-2023-24-335 | 02/08/2023 | 0 | NIRUPAMA DEY | 0.68 | 0 | 0 | 0
253 | PURULIA | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Yard lighting arrangement with others allied work at Joypur water supply scheme (OHR site) for Augmentation of Joypur PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | 418/PMD | 11/03/2024 | 60 | ASHOKE ADHIKARY | 8.07 | 0 | 0 | 0
254 | PURULIA | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Supply, delivery and installation of Centrifugal Pump set with other allied work at River site of Augmentation of Sutaboi water supply scheme under Purulia Mechanical Division PHE Dte. | 1473/PMD | 21/10/2024 | 120 | COMBINE ENTERPRISES | 5.61 | 0 | 0 | 0
255 | PURULIA | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Supply, Delivery and installation of 150KVA oil cooled voltage stabilizer and supply cable and making cable trench with allied works for Augmentation of Sutaboi w/s scheme under PMD, PHE Dte. in the District of Purulia. | 353/PMD | 27/03/2023 | 60 | SWAPAN ENTERPRISE | 18.17 | 0 | 0 | 100
256 | PURULIA | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Supply delivery & installation of flow meter and with others allied works for Augmentation Sutaboi w/s scheme under Purulia Mechanical Division, PHE, Dte. in the Purulia District. (w.e.f 01.11.23 to 31.12.23) | 390/PMD | 06/04/2023 | 60 | S. PATHAK & CO. | 4.85 | 0 | 0 | 100
257 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Continuation work Order for the work of "Hiring of Ambassador Car / Bolero for the Assistant Engineer, Raghunathpur Sub-Divn, PHE Dte. (w.e.f. 01/01/2023 to 31/12/2023)" | 699/PD | 20/12/2022 | 365 | NIRUPAMA DEY | 1.86 | 0 | 0 | 100
258 | PURULIA | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Supply and installation of Booster pumping machinery for gaseous chlorination system at OHR-I site of Sutaboi W/S scheme under PMD P.H.E Dte. | 218/PMD | 20/02/2024 | 15 | S. PATHAK & CO. | 0.96 | 0 | 0 | 100
259 | PURULIA | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Supply, delivery and installation of MCC panel at Sutaboi Water Supply Scheme under Purulia Mechanical Division P.H.E Dte. | 193/PMD | 16/02/2024 | 15 | SUJIT MUKHERJEE | 0.64 | 0 | 0 | 100
260 | PURULIA | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Supply, delivery and installation of Centrifugal pumping machinery with other allied work at River site of Augmentation of Sutaboi water supply scheme under Purulia Mechanical Division PHE Dte. | 965/PMD | 20/06/2024 | 469 | NUPUR CHANDRA HALDER | 20.18 | 0 | 0 | 20
261 | PURULIA | Purulia Division | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Sutaboi Water Supply Scheme under zone-I & zone-ii at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 1403/PD | 01/09/2022 | 1034 | ASHOK KUMAR CHATTERJEE | 85.35 | 0 | 0 | 70
262 | PURULIA | Purulia Mechanical | Augmentation of Sutabai Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09579 | Augmentation | Supply, Delivery, Storage, Installation and Commissioning of Chlorination Arrangement at Head work site of Augmentation of Sutaboi water supply scheme under Purulia Mechanical Division, P.H.E. Dte. | 440/PMD | 11/03/2024 | 570 | M/S D.G.B.ENTERPRISE | 25 | 0 | 0 | 97
263 | PURULIA | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Arrah Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | 114/PMD | 28/02/2022 | 30 | TAPAN KUMAR DEY | 20.47 | 0 | 0 | 100
264 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Supplying & laying different dia HDPE pipe line from Arra OHR to Lower Beniasole under Arra W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Tender No.927/EE/PD of 2021-22) | BP-2022-23-416 | 07/11/2022 | 0 | RABIN CHANDRA CHAIL | 3.94 | 0 | 0 | 0
265 | PURULIA | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | SUPPLY DELIVERY AND INSTALLATION OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF ARRAH WATER SUPPLY SCHEME UNDER KASHIPUR BLOCK (TR.NO 373 OF 2021-22) | C042228557261 | 13/04/2022 | 0 | TAPAN KUMAR DEY | 8.76 | 0 | 0 | 0
266 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Argumentation of Arrah Water Supply Scheme (Zone-II & III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Manpura, Tupardi, Narayangarh alias Karka. (Tender No.932/EE/PD of 2021-22) | BP-2021-22-378 | 28/03/2022 | 0 | SUBHAS CHANDRA MAHATO | 2.98 | 0 | 0 | 0
267 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Supplying & Laying different dia HDPE pipe line from Arra OHR to lower Beniasole under Arra W/S Scheme (Tender No- 927/2021-22 of EE/PD) | BP-2021-22-371 | 29/03/2022 | 0 | RABIN CHANDRA CHAIL | 37.14 | 0 | 0 | 0
268 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 700 cum at Arrah under Arrah W/S Scheme(Zone-I) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 329/PD | 28/02/2022 | 60 | RABIN CHANDRA CHAIL | 7.41 | 0 | 0 | 0
269 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Sinking of 1(one) No. 200 mm dia DTH rigbored tubewell and necessary 65 mm dia collecting line at Narayanpur river side under Arrah W/S Scheme under Raghunathpur Sub Division,P.H.E Dte. | 83/PD | 17/01/2023 | 30 | SUBHAS CHANDRA MAHATO | 2.21 | 0 | 0 | 0
270 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Arrah Water Supply Scheme at Raghunathpur -I Block under Purulia Division, PHE Dte.(Mouza-Arrah , Habitation-Arrah,Barabagan) | 180/PD | 02/02/2021 | 45 | SADHAN GORAIN | 131.09 | 0 | 0 | 100
271 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Supplying & laying different dia HDPE pipe line for extension of distribution line in different lines of Uppar Beniasole, Mission Para and Panchudanga under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 579/RNP | 27/09/2021 | 45 | MS GORAIN CONCERN | 4.84 | 0 | 0 | 0
272 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Supplying & laying different dia HDPE pipe line from Arra OHR to Gosaidanga under Arra W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 64/PD | 17/01/2022 | 45 | RABIN CHANDRA CHAIL | 25.25 | 0 | 0 | 95
273 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 50m3 including ventury etc. complete at Arrah Zone-I OHR Campus,under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 65/PD | 17/01/2022 | 100 | RABIN CHANDRA CHAIL | 6.81 | 0 | 0 | 95
274 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Argumentation of Arrah Water Supply Scheme (Zone-I) at Raghunathpur-I Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Arrah. | 154/PD | 25/01/2022 | 45 | MS GORAIN CONCERN | 14.02 | 0 | 0 | 100
275 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Argumentation of Arrah Water Supply Scheme (Zone-II & III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Manpura, Tupardi, Narayangarh alias Karka. | 155/PD | 25/01/2022 | 45 | SUBHAS CHANDRA MAHATO | 7.15 | 0 | 0 | 65
276 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Construction of Guard Room cum store at Pump House Campus under Arrah W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 328/PD | 28/02/2022 | 100 | SUBHAS CHANDRA MAHATO | 6.23 | 0 | 0 | 100
277 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Laying of Distribution pipe line ( 90 mm dia HDPE pipe ) from Arrah Pump House to Narayangarh of Kashipur Development Block under Arrah W/S Scheme of Raghunathpur Sub-Divn, P.H.E. Dte. | 356/RNP | 01/06/2022 | 30 | SUBHAS CHANDRA MAHATO | 1.33 | 0 | 0 | 0
278 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Construction of Switch Room Cum Chlorin Room at OHR Site (Zone-I) of Arrah W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1878/PD | 14/12/2022 | 45 | CHAIL CONSTRUCTION | 5.04 | 0 | 0 | 100
279 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Construction of Switch Room Cum Chlorin Room at OHR Site (Zone-II) of Arrah W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1879/PD | 14/12/2022 | 90 | SANDIP KUMAR DUBEY | 5.04 | 0 | 0 | 100
280 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 120 cum at Gagnabad under Arrah W/S Scheme(Zone-III) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1881/PD | 14/12/2022 | 30 | TUMPA GORAIN | 4.19 | 0 | 0 | 100
281 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 100 cum at Manpura under Arrah W/S Scheme(Zone-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1818/PD | 06/12/2022 | 30 | SANDIP KUMAR DUBEY | 4.46 | 0 | 0 | 100
282 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Laying of distribution pipe line ( 75 mm dia HDPE pipe ) towards Narayangarh Bauri Para under Arrah W/S Scheme of Raghunathpur Sub-Division, P.H.E. Dte. | 711/RNP | 23/12/2022 | 20 | SUBHAS CHANDRA MAHATO | 0.97 | 0 | 0 | 0
283 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Construction of Switch Room Cum Chlorin Room at OHR Site (Zone-III) of Arrah W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1880/PD | 14/12/2022 | 30 | CHANCHAL MISHRA | 5.04 | 0 | 0 | 100
284 | PURULIA | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Supply & installation of Centrifugal pumping machinery with MCC panel, Flow meter and other allied works for Augmentation at Arrah w/s scheme under PMD, PHE Dte. in the District of Purulia. | 200/PMD | 28/02/2023 | 60 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 71.89 | 0 | 0 | 100
285 | PURULIA | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Supply & installation of Submersible pumping machineries for Direct pumping with other allied works for Augmentation at arrah w/s (zone-l) scheme under PMD, PHE, Dte. in the District of Puurlia | 89/PMD | 02/02/2023 | 60 | SAMAN KUMAR MAHATO | 14.03 | 0 | 0 | 100
286 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Making interconnection between existing Rising main to CWR , CWR to distribution line towards Beniasole & Gosaindanga for direct pumping under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 993/PD | 26/07/2023 | 60 | RABIN CHANDRA CHAIL | 2.74 | 0 | 0 | 100
287 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Supplying laying fitting fixing of HDPE pipe from Raherdihi to Mohan Gora Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 992/PD | 26/07/2023 | 60 | BISWAJIT MAJI | 10.19 | 0 | 0 | 100
288 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Sinking of 2 (Two) nos. 200 mm dia river bed tubewell (Horizontal) at Darakeswar river (Narayangarh Ghat) alongwith laying of 100 mm dia G.I. collecting line with all allied works under Arrah W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | 994/PD | 26/07/2023 | 45 | CHAIL CONSTRUCTION | 12.17 | 0 | 0 | 100
289 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Emergency Hiring of Diesel Pump for pumping out water from sand pit of Intake Well (No.-1) at Narayangarh under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 90/CAMP/RNP | 26/04/2023 | 7 | RABIN CHANDRA CHAIL | 0.93 | 0 | 0 | 100
290 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Emergency Hiring of Diesel Pump for pumping out water from sand pit of Intake Well (No.-2) at Narayangarh under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 91/CAMP/RNP | 26/04/2023 | 7 | RABIN CHANDRA CHAIL | 0.93 | 0 | 0 | 100
291 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Supplying & laying different dia HDPE pipe line from Arra OHR to Lower Beniasole under Arra W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 53/PD | 13/01/2022 | 45 | RABIN CHANDRA CHAIL | 63.62 | 0 | 0 | 100
292 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Material Requisition To Resource Division | 961/PD | 20/06/2022 | 0 | Resource Division | 37.97 | 0 | 0 | 0
293 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Material Requisition To Resource Division | 800/PD | 16/06/2023 | 0 | Resource Division | 17.7 | 0 | 0 | 0
294 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Supplying & laying different dia HDPE pipe line from Arra OHR to Lower Beniasole under Arra W/S Scheme of Raghunathpur Sub- Division, PHE Dte. (Tender No- 927/2021-22 of EE/PD) | BP-2022-23-81 | 01/07/2022 | 0 | RABIN CHANDRA CHAIL | 22.53 | 0 | 0 | 0
295 | PURULIA | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | New connection for OHR 1 at Augmentation of Arrha Water Supply Scheme | BP-22-23-83 | 24/02/2023 | 0 | WBSEDCL PURULIA | 1.16 | 0 | 0 | 0
296 | PURULIA | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Arrah OHR-2 for Augmentation of Arrah Water Supply scheme Block Raghunathpur-I under Purulia Mechanical Division PHE. Dte. District Purulia | 215/PMD | 28/02/2023 | 30 | TAPAN KUMAR DEY | 21.61 | 0 | 0 | 80
297 | PURULIA | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Arrah OHR-1for Augmentation of Arrah Water Supply scheme Block Raghunathpur-I under Purulia Mechanical Division PHE. Dte. District Purulia | 214/PMD | 28/02/2023 | 30 | COMBINE ENTERPRISES | 21.62 | 0 | 0 | 100
298 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Laying of HDPE pipe (PE-100, PN-10) for collecting line of riverbed Intake Well (for 1 & 2) at Narayangarh under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 995/PD | 26/07/2023 | 60 | RABIN CHANDRA CHAIL | 6.21 | 0 | 0 | 100
299 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Laying of distribution pipe line ( 90 mm & 75 mm dia HDPE pipe ) towards Narayangarh Mahato Para & Majhee Para in connection with FHTC under Arrah W/S Scheme of Raghunathpur Sub-Divn, P.H.E. Dte. | 996/PD | 26/07/2023 | 60 | TUMPA GORAIN | 3.61 | 0 | 0 | 100
300 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Supplying laying fitting fixing of HDPE pipe & FHTC Connection Near Amlatora more to Amlatora last matha & to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1362/PD | 13/09/2023 | 45 | IKBAL CONSTRUCTION | 8.95 | 0 | 0 | 50
301 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Continuation work Order for the work of "Hiring of Ambassador Car / Bolero for the Assistant Engineer, Raghunathpur Sub-Divn, PHE Dte. (w.e.f. 01/01/2023 to 31/12/2023)" | 699/PD | 20/12/2022 | 365 | NIRUPAMA DEY | 1.86 | 0 | 0 | 100
302 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Providing Functional Household Tap Connection (FHTC) including other allied works of Arrah Water Supply Scheme (Zone - I) at Raghunathpur - I Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1801/PD | 08/12/2023 | 60 | CHAIL CONSTRUCTION | 7.03 | 0 | 0 | 100
303 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Providing House Hold Tap Connection (FHTC) at Narayangarh Majhipara and repairing and renovation of Pump House Campus under ARRAH W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 89/PD | 15/01/2024 | 60 | SUBHAS CHANDRA MAHATO | 5.26 | 0 | 0 | 100
304 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Laying of distribution pipe line (90 mm dia HDPE pipe) From Milon Sporting Club to K. Mangal Rao House under Arrah W/S Scheme (Zone-I) of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | 22/RNP | 15/01/2024 | 7 | RABIN CHANDRA CHAIL | 0.96 | 0 | 0 | 100
305 | PURULIA | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Supply, Delivery and installation of submersible pumping machineries into the intake well with allied cable line and other allied works for augmentation of Arrah w/s scheme under PMD, PHE Dte. in the District of Purulia. | 992/PMD | 21/06/2024 | 60 | M/S R.K. ENTERPRISE | 4.6 | 0 | 0 | 100
306 | PURULIA | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Supply delivery and installation of 50 KVA voltage stabilizer at Arrah OHR site(Z-I) for Augmentation of Arrah water supply scheme under PMD PHE Dte. in the district of purulia. | 375/PMD | 04/03/2024 | 60 | BISHWANATH NANDI | 7.09 | 0 | 0 | 100
307 | PURULIA | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | New connection for OHR 2(Manpura) under Augmentation of Arrha Water Supply Scheme under PMD PHE Dte. | BP-23-24-271 | 22/01/2024 | 0 | WBSEDCL PURULIA | 0.31 | 0 | 0 | 0
308 | PURULIA | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Supply delivery and installation of Internal lighting and external lighting for Arrah w/s scheme(Zone-1and Zone-II) under PMD, PHE Dte. in the District of Purulia | 819/PMD | 14/07/2023 | 262 | M/S A.D. CONCERN | 5.9 | 0 | 0 | 100
309 | PURULIA | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Supply, delivery and fitting fixing of ST pole and laying of cable line for lighting arrangement at(Z-I, Z-II and pump house) with other allied works under Arrah Water Supply Scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | 1202/PMD | 03/11/2023 | 395 | TAPAN KUMAR DEY | 6.6 | 0 | 0 | 70
310 | PURULIA | Purulia Division | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Construction of 2 Nos. 3 mtr dia Intake well at Darakeshwar river alongwith laying of 100 mm dia G.I. collecting line with all allied works under Arrah W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | 1927/PD | 22/12/2022 | 314 | RABIN CHANDRA CHAIL | 19.19 | 0 | 0 | 100
311 | PURULIA | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Supply & installation of submersible pumping machinery at newly constructed River Bed Tubewell for Augmentation of Arrah w/s scheme under PMD, PHE Dte. in the District of Purulia. | 199/PMD | 28/02/2023 | 954 | JAL PRAVAHIKA PVT. LTD | 22.65 | 0 | 0 | 75
312 | PURULIA | Purulia Mechanical | Augmentation of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block under Purulia Division, PHE Dte. , SM/09580 | Augmentation | Augmentation of existing old LBSF unit by the new one VCB (one incoming two outgoing) at Arrah W/S scheme under PMD, PHE Dte. in the District of Purulia. | 800/PMD | 12/07/2023 | 782 | COMBINE ENTERPRISES | 29.23 | 0 | 0 | 81
313 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Laying of 250mm dia DI (K9) pipe rising main from riverside pump house site to OHR site under Puncha W/s Scheme (T/N-940/21-22) |  | 05/07/2022 | 0 | SWAPAN MANDAL | 11.08 | 0 | 0 | 0
314 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Laying of distribution pipe line From Bahadurpur CWR to Laulara Mouza under Command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part -A) (Tender No- 33/2022-23 of SE/PMU) | BP-2022-23-387 | 19/10/2022 | 0 | SWAPAN MANDAL | 16.59 | 0 | 0 | 0
315 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | New sinking of 4 nos 200 mm dia riverbed tube wells horizontal of kansai along with laying of 100mm dia GI connecting line with all allied works of Puncha W/S Scheme. (Tender No- 01/2022-23 of EE/PD) | BP-2022-23-49 | 19/05/2022 | 0 | KOUSHIK CHATTERJEE | 9.58 | 0 | 0 | 0
316 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line through OHR under command area of augmentation of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No-20/SE/PMU of 21-22) | BP-2022-23-52 | 17/05/2022 | 0 | JAYANTA KUMAR MONDAL | 105.31 | 0 | 0 | 0
317 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line through CWR under command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Mouza Name:-Dhadki, Amalakanali) (Tender No- 985/2021-22 of EE/PD) | BP-2022-23-382 | 19/10/2022 | 0 | SWAPAN MANDAL | 30.29 | 0 | 0 | 0
318 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Regarding laying of water supply pipe line aling road side and road croosing on Hura-Puncha Road from 19.00 Kmp to 21.00 Kmp in respect of Augmentation of Purulia water supply scheme (Dhadki more towards Puncha Girls High School) | BP-2022-23-430 | 24/11/2022 | 0 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 32.27 | 0 | 0 | 0
319 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Laying of distribution pipe line From Bahadurpur CWR to Laulara Mouza under Command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part-B) (Tender No- 141/2022-23 of EE/PD) | BP-2022-23-388 | 19/10/2022 | 0 | SWAPAN MANDAL | 56.04 | 0 | 0 | 0
320 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Construction of R.C.C. Elevated Reservoir, Capacity 250 cum (Intze Type With Solid Raft), Staging height 20 metre for Distribution System under Puncha W/S Scheme under Purulia Division, PHE Dte. (Tender No- 27/2022-23 of EE/PD) | BP-2022-23-406 | 20/10/2022 | 0 | JAYANTA KUMAR MONDAL | 29.19 | 0 | 0 | 0
321 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line through CWR under command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Mouza Name:-Pandui) | 235/PD | 09/02/2022 | 60 | SUNRISE ENGINEERING CORPORATION | 52.23 | 0 | 0 | 0
322 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | New sinking of 4 (Four) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line with all allied works at Puncha river site of Puncha W/S Scheme under Purulia Division, PHE Dte. | 150/PD | 24/01/2022 | 45 | KOUSHIK CHATTERJEE | 25.5 | 0 | 0 | 100
323 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Laying of balance distribution pipeline including other allied works for Puncha W/S scheme under Purulia Sadar Sub Division under Purulia Division ,PHE. Dte. | 505/PSD | 12/08/2022 | 30 | JAYANTA KUMAR MONDAL | 4.31 | 0 | 0 | 100
324 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Laying of 180mm HDPE pipe with other allied works at Puncha Mouza to provide FHTC for Puncha W/S scheme under Purulia Sadar sub Division under Purulia Division ,PHE. Dte | 503/PSD | 12/08/2022 | 30 | JAYANTA KUMAR MONDAL | 4.48 | 0 | 0 | 100
325 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Construction of Boundary wall at Bahadurpur OHR Site under Puncha W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | 1722/PD | 22/11/2022 | 60 | RAHIBUDDIN MONDAL | 22.83 | 0 | 0 | 25
326 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Material Requisition To Resource Division | 398/PD | 11/03/2022 | 0 | Resource Division | 30.45 | 0 | 0 | 0
327 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Material Requisition To Resource Division | 164/PD | 27/01/2022 | 0 | Resource Division | 316.76 | 0 | 0 | 0
328 | PURULIA | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Material Requisition To Resource Division | 615/PMD | 01/06/2023 | 0 | Resource Division | 1.55 | 0 | 0 | 0
329 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line through OHR under command area of augmentation of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Tender No- 20/2021-22 of SE/PMU/WBPWSP(P) | BP-2021-22-335 | 23/03/2022 | 0 | JAYANTA KUMAR MONDAL | 116.68 | 0 | 0 | 0
330 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Construction of RCC clear water Reservoir (CWR) of capacity 100 cum at Puncha OHR site of Puncha W/S Scheme under Purulia Sadar Sub- Division, PHE Dte. (Tender No- 23/2022-23 of EE/PD) | BP-2022-23-116 | 16/07/2022 | 0 | SOUVIK MANDAL | 7.03 | 0 | 0 | 0
331 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Laying of distribution pipe line from Bahadurpur CWR to Laulara mouza under command area of Puncha W/S Scheme (Tender No- 33/2022-23 of SE/PMU/WBPWSP(P) ) | BP-2022-23-132 | 19/07/2022 | 0 | SWAPAN MANDAL | 85.91 | 0 | 0 | 0
332 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Construction of RCC clear water Reservoir (CWR) of capacity 100 cum at Puncha river site pump house of Puncha W/S Scheme under Purulia Sadar Sub- Division, PHE Dte. (Tender No- 29/2022-23 of EE/PD) | BP-2022-23-121 | 16/07/2022 | 0 | KM ENTERPRISES | 7.01 | 0 | 0 | 0
333 | PURULIA | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | New Connection for Augmentation of Puncha W/S Scheme | BP-2023-24-155 | 14/09/2023 | 0 | WBSEDCL PURULIA | 2.8 | 0 | 0 | 0
334 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Laying of 250 mm dia Di K9 pipe as rising main from riverside pump house site to OHR site under Puncha W/s Scheme of Purulia Sadar Sub- Division, under Purulia Division PHE Dte. (Tender No- 940/2021-22 of EE/PD) | BP-2022-23-75 | 01/07/2022 | 0 | SWAPAN MANDAL | 11.08 | 0 | 0 | 0
335 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Office purpose computer bill payment. | BP-2023-24-300 | 14/07/2023 | 0 | SRI KRISHNA COMPUTER | 0.95 | 0 | 0 | 0
336 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line through CWR under command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Mouza Name:-Dhadki, Amalakanali) | 236/PS | 09/02/2022 | 1217 | SWAPAN MANDAL | 65.64 | 0 | 0 | 90
337 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation & Supplying & laying of HDPE pipe through CWR for Distribution System of Puncha W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Tatari) | 1631/PD | 03/11/2022 | 1169 | SOUVIK MANDAL | 53.02 | 0 | 0 | 80
338 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Laying of parallel line under command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Laulara Mouza) | 180/PD | 07/02/2023 | 45 | MS D.PALIT AND CO. | 25.24 | 0 | 0 | 100
339 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Puncha OHR Site (Bahadurpur) for Augmentation of Puncha W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | 662/PD | 17/05/2023 | 100 | ASHOKE ADHIKARY | 14.24 | 0 | 0 | 60
340 | PURULIA | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Providing and installation of HOT Crane, Electro magnetic Flow meter and other allied woks for Augmentation of Puncha Water Supply Scheme (River Site) under purilia Mechanical Division, P.H.E. Dte. in the District of Purulia. | 1196/PMD | 03/11/2023 | 180 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 10.26 | 0 | 0 | 80
341 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Construction of R.C.C. Elevated Reservoir, Capacity 250 cum (Intze Type With Solid Raft), Staging height 20 metre for Distribution System under Puncha W/S Scheme under Purulia Division, PHE Dte. | 537/PD | 01/04/2022 | 270 | JAYANTA KUMAR MONDAL | 66.71 | 0 | 0 | 100
342 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Laying of parallel distribution pipeline for providing FHTC at Tatari Mouza of Puncha Water Supply Scheme ounder Purulia Division, PHE Dte | 356/PD | 14/03/2023 | 30 | SOUVIK MANDAL | 3.67 | 0 | 0 | 100
343 | PURULIA | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Supply delivery and installation of Internal lighting and external lighting for Augmentation of Puncha w/s scheme(River Site) under PMD, PHE Dte. in the District of Purulia. | 868/PMD | 21/07/2023 | 60 | SOUVIK MANDAL | 2.83 | 0 | 0 | 100
344 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Laying of gap portion of Distribution pipeline at bridge portion Between Bahadurpur to puncha Mouzas for puncha W/S Scheme under purulia sadar Sub-Division under purulia division. PHE.Dte. | 890/PD | 04/07/2023 | 30 | J.S. CONSTRUCTION | 10.39 | 0 | 0 | 100
345 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Work of Vendoring service service relating to E-return for Income-Tax and GST and allied service of Purulia Division, PHE Dte. (w.e.f 01.10.2023 to 30.09.2024) | BP-2024-25-356 | 11/09/2024 | 0 | NIGAM CONSULTANCY SERVICES | 0.77 | 0 | 0 | 0
346 | PURULIA | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | New Connection for Augmentation of Puncha. | BP-23-24-247 | 28/12/2023 | 0 | WBSEDCL PURULIA | 11.46 | 0 | 0 | 0
347 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Laying of distribution pipe line From Bahadurpur CWR to Laulara Mouza under Command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part-B) | 643/PD | 22/04/2022 | 1047 | SWAPAN MANDAL | 79.55 | 0 | 0 | 100
348 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line through CWR under command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Mouza Name:-Laulara) | 935/PD | 16/06/2022 | 45 | MS D.PALIT AND CO. | 112.05 | 0 | 0 | 85
349 | PURULIA | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Supply & installation of submersible pumping machinery at with MCC panel newly constructed River Bed Tubewell for Augmentation of Puncha w/s scheme under PMD, PHE Dte. in the District of Purulia. | 259/PMD | 06/03/2023 | 1062 | ANUP KR. SAHA | 36.41 | 0 | 0 | 66
350 | PURULIA | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Supply delivery and installation of Internal lighting and external lighting for Puncha w/s scheme(OHR Site) under PMD, PHE Dte. in the District of Purulia. | 257/PMD | 06/03/2023 | 894 | SWAPAN MANDAL | 3.01 | 0 | 0 | 90
351 | PURULIA | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Supply, Delivery and installation 125kva voltage stabilizer for Augmentation of Puncha(River Site) w/s scheme for under PMD, PHE Dte. in the District of Purulia. | 260/PMD | 06/03/2023 | 907 | SEN BROTHERS | 13.61 | 0 | 0 | 100
352 | PURULIA | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Supply, Delivery and installation 60kva voltage stabilizer for Augmentation of Puncha w/s scheme(OHR Site) for under PMD, PHE Dte. in the District of Purulia. | 258/PMD | 06/03/2023 | 894 | SWAPAN MANDAL | 7.71 | 0 | 0 | 60
353 | PURULIA | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Puncha w/s scheme(OHR Site) under PMD, PHE Dte. in the District of Purulia. | 516/PMD | 05/05/2023 | 981 | EASTERN INDIA SALES AND SERVICE | 65.68 | 0 | 0 | 36
354 | PURULIA | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Puncha w/s scheme(River Site) under PMD, PHE Dte. in the District of Purulia. | 517/PMD | 05/05/2023 | 644 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 50.41 | 0 | 0 | 80
355 | PURULIA | Purulia Division | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Laying of distribution pipe line From Bahadurpur CWR to Laulara Mouza under Command area of Puncha Water Supply Scheme of Puncha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part -A) | 805/PD | 10/05/2022 | 1164 | SWAPAN MANDAL | 107.71 | 0 | 0 | 100
356 | PURULIA | Purulia Mechanical | Augmentation of Puncha PWSS for providing Functional Household Tap Connection (FHTC) , SM/10048 | Augmentation | Supply, delivery and installation of Open well Submersible pumping machinery with others electro-mechanical work at Puncha River site for Augmentation of Puncha PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | 40/PMD | 10/01/2025 | 325 | S. PATHAK & CO. | 9.44 | 0 | 0 | 100
357 | PURULIA | Purulia Division | Providing FHTC under Arsha Water Supply Scheme , SM/10544 | Augmentation | Supply and Delivery of DI Fittings And Valve For Arsha and its Adjoing Mouza W/S Scheme of Purulia Sadar Sub-Division Under Purulia Division Phe Dte. | 1756/PD | 22/11/2022 | 15 | AMAL KUMAR MUKHERJEE | 2.65 | 0 | 0 | 100
358 | PURULIA | Purulia Division | Providing FHTC under Arsha Water Supply Scheme , SM/10544 | Augmentation | Painting, fixing of water level indicator, brickwork at ground floor and other allied works related to Over Head Reservoir of 100 Cum Capacity at fasko mouza under Arsha water supply scheme(Zone-II) of Purulia Division, P.H.E. Dte. | 1233/PD | 03/07/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 9.42 | 0 | 0 | 0
359 | PURULIA | Purulia Division | Providing FHTC under Arsha Water Supply Scheme , SM/10544 | Augmentation | Construction of Guard Room with sanitary and plumbing arrangement with approach road, plinth protection, surface drain etc. complete at Arsha Zone-III for Augmentation of Arsha W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | 2178/PD | 13/12/2024 | 90 | SADHAN GORAIN | 5.27 | 0 | 0 | 0
360 | PURULIA | Purulia Division | Providing FHTC under Arsha Water Supply Scheme , SM/10544 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under Zone-1 command area of Arsha & its Adjoing Mouza Water Supply Scheme of Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Zone-1, GP-Arsha,Village-Rangamati, Habitation-Rangamati- 624 nos,Pattarn-136Nos, Santaldih-25 nos, Asharamdih-68 nos) | 1745/PD | 22/11/2022 | 45 | TUMPA GORAIN | 62.69 | 0 | 0 | 100
361 | PURULIA | Purulia Division | Providing FHTC under Arsha Water Supply Scheme , SM/10544 | Augmentation | Extension of distribution pipeline at gap portion & other allied works including providing FHTC in connection with Jal Jeevan Mission at different habitation at Arsha & its Adjoing Mouza(Zone-3, GP-Arsha,Village-Tumba) Water Supply Scheme under Purulia Division, PHE Dte. | 108/PD | 20/01/2023 | 30 | MOONLIGHT HOUSE | 24.38 | 0 | 0 | 100
362 | PURULIA | Purulia Division | Providing FHTC under Arsha Water Supply Scheme , SM/10544 | Augmentation | Supplying & laying of Parallel line and Branch line of HDPE pipe for Distribution System of Arsha W/S Scheme(Zone-1) under Purulia Division PHE Dte. (Mouza Name-Rangamati)(Village Name-Asaramdih) | 1350/PD | 13/09/2023 | 30 | TUMPA GORAIN | 12.98 | 0 | 0 | 100
363 | PURULIA | Purulia Division | Providing FHTC under Arsha Water Supply Scheme , SM/10544 | Augmentation | Construction of RCC elevated reservoir of capacity 100 cum & staging height 20 mtr. for Arsha W/S Scheme at (Zone-II) under Purulia Division, PHE Dte. | 802/PD | 05/05/2022 | 240 | ANUP KUMAR SAHA | 30.47 | 0 | 0 | 75
364 | PURULIA | Purulia Division | Providing FHTC under Arsha Water Supply Scheme , SM/10544 | Augmentation | Construction of Boundary wall at Arsha Zone-2 OHR Site and Making Bypass Arrangement at OHR Site under Arsha W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 95/PD | 15/01/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 25.58 | 0 | 0 | 100
365 | PURULIA | Purulia Division | Providing FHTC under Arsha Water Supply Scheme , SM/10544 | Augmentation | Laying Gap portion DI Rising Main & Distribution for zone-II and Laying in new alignment of Distribution Pipeline due to Construction village Road at Zone III with Construction protection wall for Rising Main pipeline of Arsha & Its Adjoining Mouza W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1488/PD | 12/10/2023 | 30 | SADHAN GORAIN | 20.19 | 0 | 0 | 80
366 | PURULIA | Purulia Division | Providing FHTC under Arsha Water Supply Scheme , SM/10544 | Augmentation | Supplying & Laying of Distribution pipeline and Providing FHTC at Arsha W/S Scheme (Zone-3) under Purulia Division PHE Dte. (Mouza Covered-Arsha,Khedadih,Tumba) | 1370/PD | 25/07/2024 | 447 | SADHAN GORAIN | 39.24 | 0 | 0 | 45
367 | PURULIA | Purulia Division | Providing FHTC under Arsha Water Supply Scheme , SM/10544 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and Laying of distribution Pipeline of Arsha (Zone-III) W/S Scheme of Purulia SadarSub_Division under Purulia Division PHE Dte. [Tumba Village] | 1141/PD | 18/06/2024 | 45 | MOONLIGHT HOUSE | 6.65 | 0 | 0 | 0
368 | PURULIA | Purulia Division | Providing FHTC under Arsha Water Supply Scheme , SM/10544 | Augmentation | Laying of distribution pipeline at gap portion & other allied works including providing FHTC in connection with Jal Jeevan Mission at different habitation at Arsha & its Adjoing Mouza(Zone-2, GP-Arsha,Village-Fasko) Water Supply Scheme under Purulia Division, PHE Dte | 106/PD | 20/01/2023 | 741 | KANTILAL SAO | 33.89 | 0 | 0 | 100
369 | PURULIA | Purulia Division | Providing FHTC under Arsha Water Supply Scheme , SM/10544 | Augmentation | Laying of Distribution pipeline of Arsha W/S Scheme (Zone-1) under Purulia Division PHE Dte.(Mouza Covered Rangamati,Pattanr,Asaramdih) | 1369/PD | 25/07/2024 | 270 | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 24.74 | 0 | 0 | 100
370 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. , SM/10278 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within NETURIA Block (Part-C-II) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | 1864/PD | 13/12/2022 | 45 | KHITISH CHANDRA PATHAK | 51.93 | 0 | 0 | 0
371 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. , SM/10278 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Neturia Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | 608/PD | 19/04/2022 | 45 | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 15.77 | 0 | 0 | 0
372 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. , SM/10278 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Neturia Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | 607/PD | 19/04/2022 | 45 | MD AAMIR KHAN | 47.36 | 0 | 0 | 100
373 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. , SM/10278 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Neturia Block (Part-G) of Purulia District under Purulia Division, PHE Dte. (Phase-IV) | 1118/PD | 25/07/2022 | 45 | JYOTY SOLAR POWER | 54.44 | 0 | 0 | 100
374 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. , SM/10278 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within NETURIA Block (Part-C-I) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | 1863/PD | 13/12/2022 | 45 | SUNRISE ENGINEERING CORPORATION | 52.05 | 0 | 0 | 100
375 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. , SM/10278 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within NETURIA Block (Part-F) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | 1865/PD | 13/12/2022 | 45 | BASHUDEV DUTTA | 94.34 | 0 | 0 | 100
376 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. , SM/10278 | Anganwadi | Water supply Tap Connection Arrangement for 21 nos AWC within Neturia Block of Purulia District under Purulia Division, PHE Dte.(Phase-I) (Part-A and B) | 819/PD | 17/05/2022 | 45 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 95.03 | 0 | 0 | 100
377 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. , SM/10278 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Neturia Block (Part-E) of Purulia District under Purulia Division, PHE Dte. (Phase-II) | 1228/PD | 22/08/2022 | 45 | WATER TECH | 90.73 | 0 | 0 | 100
378 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Neturia Block In Purulia District under Purulia Division, PHE.Dte. , SM/10278 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Neturia Block (Part-D)of Purulia District under Purulia Division, PHE Dte. (Phase-I) | 1117/PD | 25/07/2022 | 45 | WATER TECH | 90.73 | 0 | 0 | 100
379 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | 1153/PD | 01/08/2022 | 45 | JYOTY SOLAR POWER | 158.35 | 0 | 0 | 0
380 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-H) of Purulia District under Purulia Division, PHE Dte. (Tender No- 65/2022-23 of SE/PMU/WBPWSP(P) ) | BP-2022-23-404 | 20/10/2022 | 0 | JYOTY SOLAR POWER | 88.84 | 0 | 0 | 0
381 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Kashipur Block (Part-M) of Purulia District under Purulia Division, PHE Dte. | 145/PD | 03/02/2023 | 45 | S N POLYMERS PVT LTD | 206.54 | 0 | 0 | 100
382 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Kashipur Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | 754/PD | 02/05/2022 | 45 | AMITAVA CHAKRABORTY | 71.14 | 0 | 0 | 0
383 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10277 | Anganwadi | Providing Functional Household Tap Connection (FHTC) at different AWC, School and other allied works of Keliathole -Palashkola Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 348/RNP | 01/06/2022 | 20 | SUBHAS CHANDRA MAHATO | 1.48 | 0 | 0 | 100
384 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Kashipur Block (Part-A) of Purulia District under Purulia Division, PHE Dte.(Phase-I) | 1129/PD | 25/07/2022 | 45 | RAJ KUMAR MONDAL | 94.93 | 0 | 0 | 0
385 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Kashipur Block (Part-K) of Purulia District under Purulia Division, PHE Dte. | 1159/PD | 01/08/2022 | 45 | PRINCE INDUSTRIES ( INDIA) | 197.96 | 0 | 0 | 0
386 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | 1151/PD | 01/08/2022 | 45 | WATER TECH | 158.37 | 0 | 0 | 100
387 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Kashipur Block (Part-E) of Purulia District under Purulia Division, PHE Dte.(Phase-III) | 1131/PD | 25/07/2022 | 45 | SINGHA ENTERPRISE | 94.88 | 0 | 0 | 100
388 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Kashipur Block (Part-P) of Purulia District under Purulia Division, PHE Dte.(Phase-IV) | 1132/PD | 25/07/2022 | 45 | PRINCE INDUSTRIES ( INDIA) | 95.01 | 0 | 0 | 0
389 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Kashipur Block (Part-L) of Purulia District under Purulia Division, PHE Dte. | 1201/PD | 12/08/2022 | 45 | MS D.PALIT AND CO. | 197.96 | 0 | 0 | 0
390 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | 22/PD | 05/01/2023 | 45 | WATER TECH | 165.38 | 0 | 0 | 100
391 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Kashipur Block (Part-F) of Purulia District under Purulia Division, PHE Dte. | 753/PD | 02/05/2022 | 45 | RABIN CHANDRA CHAIL | 70.52 | 0 | 0 | 0
392 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10277 | Anganwadi | Making Xerox copy of original DPR, Drawing, Mouza Map etc. | 27/2023-149 | 30/05/2023 | 0 | SB CONSTRUCTION | 0.37 | 0 | 0 | 0
393 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Kashipur Block (Part-B) of Purulia District under Purulia Division, PHE Dte.(Phase-II) | 1130/PD | 25/07/2022 | 45 | A ONE CONSTRUCTION | 94.93 | 0 | 0 | 0
394 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Kashipur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10277 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | 146/PD | 03/02/2023 | 45 | BALAJI UDDYOG | 164.99 | 0 | 0 | 100
395 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Digha G.P of Neturia Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1047/BMD | 23/08/2022 | 30 | SUMIT KUMAR CHAKRABORTY | 48.32 | 0 | 0 | 0
396 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depths. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Sarbori G.P of Neturia Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1053/BMD | 23/08/2022 | 40 | SINGHA ENTERPRISE | 61.13 | 0 | 0 | 0
397 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different sourceless AWC at Guniara G.P in Neturia Block in the Distric of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1048/BMD | 23/08/2022 | 25 | SUMIT KUMAR CHAKRABORTY | 35.44 | 0 | 0 | 0
398 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Janardandih G.P of Neturia Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1049/BMD | 23/08/2022 | 20 | ANUP KUMAR SAHA | 32.44 | 0 | 0 | 0
399 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Bhamunia, Saltora, Rayesba G.P of Neturia Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1050/BMD | 23/08/2022 | 30 | ANUP KUMAR SAHA | 48.66 | 0 | 0 | 0
400 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Rayesbandh G.P of Neturia Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1051/BMD | 23/08/2022 | 40 | CHAKRABORTY MAINING & ENGINEERING. | 72.84 | 0 | 0 | 0
401 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Saltore G.P of Neturia Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1052/BMD | 23/08/2022 | 40 | PRINCE INDUSTRIES (INDIA) | 67.13 | 0 | 0 | 0
402 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Jhalda-I Block (Part-H) of Purulia District under Purulia Division, PHE Dte. (Tender No- 28/2022-23 of EE/PD) | BP-2022-23-400 | 20/10/2022 | 0 | NATIONAL CONSTRUCTION | 12.09 | 0 | 0 | 0
403 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Acceptance cum Work Order for, ¿Water supply Tap Connection Arrangement for 20 nos AWC within HUra Block (Part-E) of Purulia District under Purulia Division, PHE Dte.(Phase-II)" | 1706/PD | 22/11/2022 | 45 | SHWET BARANI | 95.6 | 0 | 0 | 35
404 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Jhalda-I Block ) of Purulia District under Purulia Division, PHE Dte. | 42/PD | 09/01/2023 | 45 | DEBANJAN SEAL | 1.66 | 0 | 0 | 0
405 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 58 nos AWC within Nituria Block ) of Purulia District under Purulia Division, PHE Dte. | 36/PD | 09/01/2023 | 45 | ASHOK KUMAR CHATTERJEE | 32.2 | 0 | 0 | 0
406 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Jhalda-I Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | 473/PD | 24/03/2022 | 45 | NATIONAL CONSTRUCTION | 47.04 | 0 | 0 | 100
407 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Jhalda-I Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | 462/PD | 24/03/2022 | 45 | WRISHI ENTERPRISE | 47.04 | 0 | 0 | 100
408 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Acceptance cum Work Order For "Water supply Tap Connection Arrangement for 3 nos AWC within Jhalda-I Block (Part-I) of Purulia District under Purulia Division, PHE Dte." | 1727/PD | 22/11/2022 | 45 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 24.79 | 0 | 0 | 100
409 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within JHALDA-1 Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | 1858/PD | 13/12/2022 | 45 | PRINCE INDUSTRIES ( INDIA) | 99.23 | 0 | 0 | 0
410 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within JHALDA-1 Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | 1859/PD | 13/12/2022 | 45 | M/S. BIMALENDU BOSE | 99.22 | 0 | 0 | 100
411 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Jhalda-I Block (Part-D) of Purulia District under Purulia Division, PHE Dte. (SL-4) | 269/PD | 24/02/2023 | 45 | SINGHA ENTERPRISE | 165.14 | 0 | 0 | 100
412 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Jhalda-I Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | 1050/PD | 08/07/2022 | 45 | PRASENJIT BASAK | 157.97 | 0 | 0 | 100
413 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 45 nos School upto 200 Students, 5 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within JHALDA -I BLOCK (Part-A) of Purulia District under Purulia Division, PHE Dte. | 799/PD | 05/05/2022 | 1215 | S AND P ENTERPRISE | 219.6 | 0 | 0 | 100
414 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(114 nos) under Jhalda-I, Neturia & Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10286 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Jhalda-I Block (Part-E) & 9 nos AWC within Jhalda-I Block (Part-F) of Purulia District under Purulia Division, PHE Dte. (Phase-I) (Sl. No. 11) | 268/PD | 24/02/2023 | 838 | MOTI RAHAMAN | 147.74 | 0 | 0 | 100
415 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 196 nos. under Manbazar I & Neturia Block In Purulia District under Purulia Division, PHE.Dte. , SM/10229 | School | Water supply Tap Connection Arrangement for 40 nos School upto 200 Students, within Manbazar-I Block (Part-B) of Purulia District under Purulia Division, PHE Dte. (Tender No.17/SE/PMU of 2022-23) | BP-2022-23-328 | 29/09/2022 | 0 | EQUIPMENTS AND SPARES AGENCIES | 75.73 | 0 | 0 | 0
416 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 196 nos. under Manbazar I & Neturia Block In Purulia District under Purulia Division, PHE.Dte. , SM/10229 | School | Water supply Tap Connection Arrangement for 49 nos School upto 200 Students, 4 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Neturia Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | 566/PD | 08/04/2022 | 45 | MS D.PALIT AND CO. | 232.21 | 0 | 0 | 100
417 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 196 nos. under Manbazar I & Neturia Block In Purulia District under Purulia Division, PHE.Dte. , SM/10229 | School | Water supply Tap Connection Arrangement for 46 nos School upto 200 Students, 7 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Manbazar-I Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | 676/PD | 25/04/2022 | 45 | EQUIPMENTS AND SPARES AGENCIES | 232.07 | 0 | 0 | 100
418 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 196 nos. under Manbazar I & Neturia Block In Purulia District under Purulia Division, PHE.Dte. , SM/10229 | School | Water supply Tap Connection Arrangement for 40 nos School upto 200 Students, within Manbazar-I Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | 674/PD | 25/04/2022 | 45 | EQUIPMENTS AND SPARES AGENCIES | 168.51 | 0 | 0 | 100
419 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 196 nos. under Manbazar I & Neturia Block In Purulia District under Purulia Division, PHE.Dte. , SM/10229 | School | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewellssinked at various Schools & AWCs of . Puncha&Manbazar-I Blocks under Purulia Division ,PHE,Dte. | 1738/PD | 04/12/2023 | 30 | ESSAR CONSTRUCTION | 12.6 | 0 | 0 | 70
420 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 196 nos. under Manbazar I & Neturia Block In Purulia District under Purulia Division, PHE.Dte. , SM/10229 | School | Water supply Tap Connection Arrangement for 30 nos School upto 200 Students, within Manbazar-I Block (Part-C) and 16 nos School upto 200 Students, within Neturia Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | 677/PD | 25/04/2022 | 45 | BINGAS ELECTRICAL ELECTRONICS AND SOLAR SYSTEM | 193.98 | 0 | 0 | 100
421 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Continuation work order for Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Saltore- Hijuli W/S Scheme block- Neturia) to be augmented/ Retrofitting under Purulia Division, PHE Dte. (Tender No- 973/2021-22 of EE/PD) | BP-2022-23-137 | 19/07/2022 | 0 | M/S TECH VISION | 0.41 | 0 | 0 | 0
422 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Saltore- Hijuli W/S Scheme block- Neturia) to be augmented/ Retrofitting under Purulia Division, PHE Dte. (Tender No- 543/2021-22 of EE/PD) | BP-2022-23-138 | 19/07/2022 | 0 | M/S TECH VISION | 4.08 | 0 | 0 | 0
423 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Construction of RCC Clear water reservoir (CWR) of capacity 100 Cum with other allied works at Damodar river site under Saltora-Hijli W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | 865/PD | 23/05/2022 | 100 | BALAJI UDDYOG | 13.87 | 0 | 0 | 0
424 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | New Sinking of 200 mm dia 8 (Eight) Nos river bed vertical tubewell alongwith necessary 100 mm dia GI collecting line from River bed Tubewell to common manifold chamber at river bank (Damodar River) under Saltora-Hijli W/S Scheme under Raghunathpur Sub Division, PHE Dte. | 855/PD | 23/05/2022 | 30 | ASHOK KUMAR CHATTERJEE | 41.13 | 0 | 0 | 35
425 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Repairing & renovation of of CWR, Office Bldg., Pump Houses and Boundary Wall at Saltora -Hijli W/S Scheme under Purulia Division, PHE Dte. | 867/PD | 23/05/2022 | 60 | M/S ADITYA KUMAR | 6.94 | 0 | 0 | 50
426 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Distribution System with FHTC work (285 Nos.) of Saltore-Hijuli Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-I | 1009/PD | 29/06/2022 | 45 | PARTHA PRATIM CHHATAIT | 110.11 | 0 | 0 | 0
427 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Laying of Clear Water Rising Main under Saltore-Hijuli W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 856/PD | 23/05/2022 | 60 | BASANTA KUMAR SINGHADEO | 51.02 | 0 | 0 | 25
428 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Additional work for Restoration work by construction of RCC Retaining wall for protection work of dedicated transformer at Saltore-Hijuli CWR site of Saltore-Hijuli W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Handed over to PRI Bodies ) | 273/6/RNP | 19/05/2022 | 15 | BASANTA KUMAR SINGHADEO | 0.88 | 0 | 0 | 0
429 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Saltore-Hijuli OHR Campus under Saltore-Hijuli W/S Scheme under Raghunathpur Sub-Division, P.H.E. Dte. (Total length of Boundary Wall 40.00 mtr.) | 332/RNP | 01/06/2022 | 21 | AMIT PATHAK | 3.65 | 0 | 0 | 100
430 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Construction of Switch Room-Cum-Chlorine Room at OHR Site under Saltore-Hijuli W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 331/RNP | 01/06/2022 | 90 | DEBANJAN SEAL | 4.46 | 0 | 0 | 100
431 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. at Saltore-Hijuli W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | 343/RNP | 01/06/2022 | 30 | G.TECH INDIA | 1.4 | 0 | 0 | 75
432 | PURULIA | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Supply delivery and fitting fixing of the luminaries external and internal lighting with others allied works at SALTORE HIJULI w/s scheme under PMD, PHE Dte. in the District of Purulia. | 135/PMD | 20/02/2023 | 60 | BISHWANATH NANDI | 7.64 | 0 | 0 | 0
433 | PURULIA | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Supply, Delivery and installation of 8 nos. River bed submersible pumps motor sets with other allied works for SALTORE HIJULI w/s scheme under PMD, PHE Dte. in the District of Purulia. | 527/PMD | 05/05/2023 | 60 | INDRAJIT MITRA | 23.5 | 0 | 0 | 8
434 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Additional work for Construction of Switch Room Cum Chlorine Room at OHR Site of Saltore-Hijuli W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Part -I) | 399/RNP | 05/09/2023 | 15 | DEBANJAN SEAL | 0.94 | 0 | 0 | 100
435 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Additional work for Construction of Switch Room Cum Chlorin Room at OHR Site of Saltore-Hijuli W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Part - II) | 397/RNP | 05/09/2023 | 15 | DEBANJAN SEAL | 0.97 | 0 | 0 | 100
436 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Construction of Switch Room-Cum-Chlorine Room at River Site under Saltore-Hijuli W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 330/RNP | 01/06/2022 | 90 | SUBRATA SINGHADEO | 4.48 | 0 | 0 | 95
437 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Material Requisition To Resource Division | 958/PD | 20/06/2022 | 0 | Resource Division | 158.64 | 0 | 0 | 0
438 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Material Requisition To Resource Division | 979/PD | 22/06/2022 | 0 | Resource Division | 118.82 | 0 | 0 | 0
439 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Material Requisition To Resource Division | 426/PD | 21/03/2023 | 0 | Resource Division | 37.42 | 0 | 0 | 0
440 | PURULIA | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | ENHANCEMENT OF CONTRACTUAL DEMAND FOR AUGMENTATION OF SALTORE HIJULI WATER SUPPLY SCHEME | BP-22-23-85 | 28/02/2023 | 0 | WBSEDCL PURULIA | 4.68 | 0 | 0 | 0
441 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Distribution System with FHTC work and construction of Boundary wall at OHR Site of Saltore-Hijuli Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-II | 1891/PD | 15/12/2022 | 60 | BALAJI UDDYOG | 204.07 | 0 | 0 | 35
442 | PURULIA | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Supply, Delivery and installation of CWR Submersible pumping machineries, MCC Panels, flow meter with others allied works for Augmentation at SALTORE HIJULI ( ZONE-3) w/s scheme under PMD, PHE Dte. in the District of Purulia. | 132/PMD | 20/02/2023 | 60 | M/S D. PALIT & CO. | 27.01 | 0 | 0 | 35
443 | PURULIA | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Saltore Hijuli Water Supply scheme Block Neturia under PMD PHE Dte. District Purulia. | 446/PMD | 20/04/2023 | 30 | T.N.BANERJEE | 21.56 | 0 | 0 | 50
444 | PURULIA | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Supply, delivery and Installation of Submersible pumping machineries for newly constructed tube wells and other allied works for Augmentation of Saltore hijuli W/S scheme under PMD Dte. in the District Purulia. | 976/PMD | 20/06/2024 | 60 | BISHWANATH NANDI | 8.76 | 0 | 0 | 70
445 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Construction of RCC Over Head Reservoir (Intze type with solid raft ) of capacity 200 cum and staging height 20 mtr. with including supply of all labour & materials for Saltora -Hijli W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | 793/PD | 05/05/2022 | 270 | ASHOK KUMAR CHATTERJEE | 64.5 | 0 | 0 | 100
446 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Construction of Pump House (10 X 7 mtr) at Head Work site under Saltore-Hijuli W/S Scheme of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | 864/PD | 23/05/2022 | 100 | M/S SAYAK BHATTACHARYA | 15.23 | 0 | 0 | 100
447 | PURULIA | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Supply and delivery of Free chlorine test kit at different Pumping water supply scheme under Purulia Mechanical Division, PHE Dte .in the District Purulia | 46/PMSD(W/S) | 08/02/2024 | 15 | M/S R.K. ENTERPRISE | 0.94 | 0 | 0 | 100
448 | PURULIA | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Quotation for removal of one 63 KVA DTR along with one span HT & one span LT line at the premises of Saltore Hijuli PHE | BP-23-24-222 | 05/12/2023 | 0 | WBSEDCL PURULIA | 0.09 | 0 | 0 | 0
449 | PURULIA | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | New service connection at Saltore Hijuli OHR site | BP-24-25-15 | 24/05/2024 | 0 | WBSEDCL SALTORE CCC | 0.11 | 0 | 0 | 0
450 | PURULIA | Purulia Division | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Distribution System with FHTC work and construction of approach road at Pump House of Saltore-Hijuli Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-III | 1892/PD | 15/12/2022 | 865 | PRAVAT SARKAR | 99.55 | 0 | 0 | 88
451 | PURULIA | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Supply, Delivery and installation of Centrifugal pumping machineries, MCC Panels, flow meter, HOT crane with others allied works for Augmentation at SALTORE HIJULI (ZONE-1 and 2) w/s scheme under PMD, PHE Dte. in the District of Purulia . | 134/PMD | 20/02/2023 | 60 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 70.46 | 0 | 0 | 100
452 | PURULIA | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Supply and installation of automatically controlled diaphragm type Chlorinator dosing pump with Piping & structural works in connection with Disinfection arrangement System for zone-III & Miscellaneous works at Pump House under Saltore-Hijuli W/S Scheme, Purulia Mechanical Division, P.H.E Dte. | 1574/PMD | 14/11/2024 | 107 | BISHWANATH NANDI | 4.42 | 0 | 0 | 100
453 | PURULIA | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Testing commissioning of Gaseous chlorination system and extension of solution line upto OLD CWR for Augmentation at Saltore Hijuli (Zone-1 & 2) under PMD, PHE Dte in the district of Purulia. (2ND Call) | 353/PMSD(W/S) | 04/09/2024 | 392 | BISHWANATH NANDI | 0.81 | 0 | 0 | 100
454 | PURULIA | Purulia Mechanical | Augmentation of Saltore-Hijuli Water Supply Scheme , SM/10721 | Augmentation | Supply, delivery and fitting fixing of Mainswitch and cable for Pumphouse and internal and external illumination of OHR site for Augmentation at Saltore Hijuli(Zone-1 & 2) w/s supply scheme under PMD,PHE Dte .in the District of Purulia. | 376/PMD | 04/03/2024 | 60 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 10.49 | 0 | 0 | 100
455 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Nutandi (J.L. No.- 61) and replacement/ extention of distribution pipe line under augmentation of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 871/PD | 23/05/2022 | 45 | AJAY MONDAL | 35.11 | 0 | 0 | 50
456 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | New sinking of 2 (Two) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line with all allied works at Deolghata river site of Joypur W/S Scheme under Purulia Division, PHE Dte. (Phase-II) | 846/PD | 23/05/2022 | 30 | AMAL KUMAR MUKHERJEE | 13.15 | 0 | 0 | 0
457 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Construction of RCC Clear Water Reservoir (CWR) of Capacity 100 Cum with other allied works at Deolghata Pump House campus of Joypur W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | 850/PD | 23/05/2022 | 100 | SK ABBAS | 10.71 | 0 | 0 | 0
458 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Barbenda (J.L. No.- 63) and replacement/ extention of distribution pipe line under augmentation of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1039/A/PD | 07/07/2022 | 60 | PREMNATH MITRA | 80.51 | 0 | 0 | 32
459 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Supply & delivery DI Specials for Newly Laying of Rising Main (DI-K9) Pipe line from Deolghata River Site Pump House to 200 Cum Capacity CWR at Rahardaga OHR Site under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte. PHE Dte | 423/PD | 21/03/2023 | 45 | BOSE CONSTRUCTION | 43.97 | 0 | 0 | 60
460 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Withdrawing of 150 mm dia. DI Pipe (distribution main) & newly laying in new trench and through culvert under Railway track near Ranibandh Rail Crossing of Joypur Water Supply Scheme at Joypur Block under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | 247/PSD | 31/03/2023 | 10 | APEX TRADERS | 0.71 | 0 | 0 | 0
461 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | New sinking of 2 (Two) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line with all allied works at Deolghata river site of Joypur W/S Scheme under Purulia Division, PHE Dte. (Phase-I) | 845/PD | 23/05/2022 | 30 | AMAL KUMAR MUKHERJEE | 13.15 | 0 | 0 | 0
462 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Continuation work for Soil Investigation work for proposed 1000 M3 capacity Over Head Reservoir of Joypur W/S Scheme under Purulia Division P.H.E Dte. | 112/A/PD | 20/01/2023 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 0 | 0
463 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Installation of a Big-Dia D.T.H. Tube Well (200mm x 165mm) considering 300mt. Depth at Joypur OHR Campus to combat the Draught like situation in Joypur Block area of the District Purulia under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 816/PD | 26/06/2023 | 45 | SADHAN GORAIN | 5.01 | 0 | 0 | 95
464 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Supply & delivery DI Specials for Newly Laying of Distribution Main (DI-K7) Pipe line from OHR Site to Joypur Ranibandh Rail Crossing & Towards Raghbore More under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte. PHE Dte | 817/PD | 26/06/2023 | 45 | PRIYATOSH MUKHERJEE | 4.11 | 0 | 0 | 98
465 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Installation of a Big-Dia D.T.H. Tube Well (200mm x 165mm) considering 250mtr. Depth at Joypur OHR Campus to combat the Draught like situation in Joypur Block area of the District Purulia under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1352/PD | 13/09/2023 | 45 | SADHAN GORAIN | 4.18 | 0 | 0 | 100
466 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Material Requisition To Resource Division | 970/PD | 21/06/2022 | 0 | Resource Division | 372.24 | 0 | 0 | 0
467 | PURULIA | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Material Requisition To Resource Division | 613/PMD | 01/06/2023 | 0 | Resource Division | 1.55 | 0 | 0 | 0
468 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Joypur W/S Scheme, Block- Joypur) ) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 535/2021-22 of EE/PD) | BP-2022-23-119 | 16/07/2022 | 0 | RADIANT | 8.59 | 0 | 0 | 0
469 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Indian Railways Miscellaneous collection. | BP-2022-23-5179 | 02/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 45.74 | 0 | 0 | 0
470 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Indian Railways Miscellaneous collection. | BP-2022-23-5176 | 02/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 5.34 | 0 | 0 | 0
471 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Indian Railways Miscellaneous collection. | BP-2022-23-5175 | 02/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 6.27 | 0 | 0 | 0
472 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Rahardaga (Jl-64) & Mouza-Mirdi (Jl-102) and replacement/ extention of distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 842/PD | 23/05/2022 | 45 | PRIYATOSH MUKHERJEE | 71.27 | 0 | 0 | 70
473 | PURULIA | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Joypur OHR for Augmentation of Joypur Water supply scheme block Joypur under PMD PHE Dte. district Purulia | 212/PMD | 28/02/2023 | 30 | ANUP KR. SAHA | 21.6 | 0 | 0 | 93
474 | PURULIA | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Arrangement of internal lighting with other allied works for augmentation of Joypur (River side & OHR side) water supply scheme under PMD, PHE Dte. In the district of Purulia. | 242/PMD | 03/03/2023 | 60 | MD. ASLAM | 1.21 | 0 | 0 | 60
475 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Construction of Over Head Reservoir (OHR) of 1000 Cum Capacity, Staging Height 20 mtr. at existing OHR Campus (Rahardaga Mouza ) of Joypur W/S Scheme under Purulia Sadar Sub-Division of Purulia Division, P.H.E. Dte. | 148/PD | 03/02/2023 | 270 | SADHAN GORAIN | 229.29 | 0 | 0 | 92
476 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Newly Laying of Rising Main (DI-K9) Pipe line from Deolghata River Site Pump House to 200 Cum Capacity CWR at Rahardaga OHR Site under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte. PHE Dte | 424/PD | 21/03/2023 | 45 | BOSE CONSTRUCTION | 88.75 | 0 | 0 | 100
477 | PURULIA | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Yard lighting arrangement with others allied work at Joypur water Supply Scheme (River Site) for Augmentation of Joypur PWSS under Purulia Mechanical Division, P.H.E. Dte. in the District of Purulia. | 1193/PMD | 03/11/2023 | 60 | S. PATHAK & CO. | 10.83 | 0 | 0 | 56
478 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Left Out Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Rahardaga (Jl-64) & Mouza-Mirdi (Jl-102) and extension of Parallal distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 90/PD | 15/01/2024 | 60 | PRIYATOSH MUKHERJEE | 61.3 | 0 | 0 | 75
479 | PURULIA | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Yard lighting arrangement with others allied work at Joypur water supply scheme (OHR site) for Augmentation of Joypur PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | 418/PMD | 11/03/2024 | 60 | ASHOKE ADHIKARY | 8.07 | 0 | 0 | 0
480 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Construction of Staff Toilet at Riversite Pump house under Joypur PWSS Scheme under Purulia Division, PHE Dte. | 886/PD | 07/05/2024 | 60 | PURNA CHANDRA TEWARI | 4.1 | 0 | 0 | 0
481 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Construction of pump house for accommodating centrifugal pump for pumping of water including panel room & chlorination room at Joypur OHR site of Joypur W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | 847/PD | 23/05/2022 | 90 | KM ENTERPRISES | 16.44 | 0 | 0 | 100
482 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Repairing, renovation & restoration of Pump house & store cum Guard room at Deolghata Pump house campus of Joypur W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | 848/PD | 23/05/2022 | 60 | SEKH IRFAN | 5.38 | 0 | 0 | 100
483 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Chitahi (Jl-105) & Mouza-Ghaghri (Jl-106) and replacement/ extention of distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 843/PD | 23/05/2022 | 45 | MOONLIGHT HOUSE | 14.06 | 0 | 0 | 100
484 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Tunta (Jl-104) and replacement/ extention of distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 1754/PD | 22/11/2022 | 45 | M/S KHAN ENTERPRISE | 23.24 | 0 | 0 | 100
485 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Repairing, renovation of Boundary Wall at Joypur OHR site of Joypur W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | 1838/PD | 12/12/2022 | 30 | TRINITY CONSTRUCTION | 18.79 | 0 | 0 | 100
486 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Continuation work for Soil Investigation work for proposed 350 cubic meter capacity Over Head Reservoir of Bandwan W/S Scheme under Purulia Division P.H.E Dte. | 231/PD | 17/02/2023 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 0 | 100
487 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Continuation work for Soil Investigation work for proposed 200 cubic meter capacity Over Head Reservour of Darda W/S Scheme under Purulia Division P.H.E dte. | 232/PD | 17/02/2023 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 0 | 100
488 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Continuation work for Soil Investigation work for proposed 600 cubic meter capacity Over Head Reservour of ManbazaR -I W/S Scheme under Purulia Division P.H.E dte. | 233/PD | 17/02/2023 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 0 | 100
489 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Continuation work for Soil Investigation work for proposed 100 cubic meter capacity Over Head Reservour of Arsha W/S Scheme under Purulia Division P.H.E dte. | 236/PD | 17/02/2023 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 0 | 100
490 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Shyampur Mouza) | 279/PD | 27/02/2023 | 30 | S. R. ENTERPRISE | 10.39 | 0 | 0 | 60
491 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Continuation work for Soil Investigation work for proposed 250 cubic meter capacity Over Head Reservour of Puncha W/S Scheme under Purulia Division P.H.E dte. | 234/PD | 17/02/2023 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 0 | 100
492 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Emergent Dismantling of R.C.C. Elevated Reservoir, Capcaity 350 Cum (Intze Type), Staging height 20 metre at Joypur OHR Site of Joypur W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 553/PD | 13/04/2023 | 90 | TAPAN CHANDRA | 10.38 | 0 | 0 | 100
493 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Construction of Chlorine cum Switch Room & Guard Room with sanitary and plumbing arrangement with approach road, plinth protection, surface drain, Land development etc. complete at Joypur OHR Site, of Joypur W/S Scheme under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte. | 659/PD | 17/05/2023 | 100 | KM ENTERPRISES | 10.91 | 0 | 0 | 100
494 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Construction of Undercut Pump house including panel room & chlorination room at Deulghata Pump House of Joypur W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | 1796/PD | 08/12/2023 | 90 | M/S CONTRACTORS SYNDICATE | 23.01 | 0 | 0 | 100
495 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Continuation work for Soil Investigation work for proposed 750 cubic meter capacity Over Head Reservour of Kotshila W/S Scheme under Purulia Division P.H.E dte. | 235/PD | 17/02/2023 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 0 | 100
496 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Laying DI Rising Main in new alignment from Pump house to OHR and making Inter Connection Arrangement with Distribution System for Joypur W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1062/PD | 07/06/2024 | 60 | BHAGABAN DAS KUMAR | 2.55 | 0 | 0 | 100
497 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Extension of PVC pipe line in distribution system for Stand Post at different School & ICDS Centre of Joypur Block to supply drinking water of command area of Joypur Water Supply Scheme under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | 1394/PD | 01/09/2022 | 45 | AMAL KUMAR MUKHERJEE | 6.32 | 0 | 0 | 100
498 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Laying of Pipeline from Banahata Mouza to Kachahatu Mouza for Providing FHTC at Joypur Water Supply Scheme under Purulia Division, PHE Dte. | 529/PD | 16/03/2024 | 60 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 84.88 | 0 | 0 | 100
499 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and) at Gurrabera habitation of Mouza-Ritudih (JL-62) under command area of Joypur Water Supply Scheme of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 890/PD | 07/05/2024 | 45 | BHAGABAN DAS KUMAR | 3.24 | 0 | 0 | 100
500 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Construction of Staff Toilet at Sirkabad OHR Site under Joypur PWSS Scheme under Purulia Division, PHE Dte. | 885/PD | 07/05/2024 | 147 | INDRAJIT SARKAR | 4.09 | 0 | 0 | 100
501 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Providing Left Out & Parallal distribution pipe line including Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Chitahi (JL-105) & Mouza- Ghaghri (JL-106) under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1093/PD | 07/06/2024 | 60 | MOONLIGHT HOUSE | 4.13 | 0 | 0 | 100
502 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | New sinking of 2(Two ) nos. 200 mm dia river bed tubewell (Horizontal) at Kansabati river alongwith laying of 100 mm dia G.I. collecting line with other allied works of Joypur W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division PHE Dte. | 1503/PD | 27/08/2024 | 30 | BOSE CONSTRUCTION | 18.14 | 0 | 0 | 100
503 | PURULIA | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | New Connection for Augmentation of Joypur (River Side) W/S Scheme | BP-2023-24-150 | 14/09/2023 | 0 | WBSEDCL PURULIA | 7.5 | 0 | 0 | 0
504 | PURULIA | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | New Connection For Augmentation of Joypur | BP-2023-24-149 | 14/09/2023 | 0 | WBSEDCL PURULIA | 4.45 | 0 | 0 | 0
505 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Ritudih (JL-62) & Mouza- Joypur (JL-66) and replacement/ extention of distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 936/PD | 16/06/2022 | 930 | M/S. S. CHOUDHURY | 201.33 | 0 | 0 | 100
506 | PURULIA | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmwter and other allied works for augmentation of Joypur(Riverside) water supply scheme under PMD, PHE Dte. In the district of Purulia. | 244/PMD | 03/03/2023 | 790 | COMBINE ENTERPRISES | 58.94 | 0 | 0 | 35
507 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Providing (Left Out) Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Bhaddi (J.L. No.- 65) & Mouza- Litiadih (J.L. No.-99) and replacement/ extention of distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 378/PD | 16/03/2023 | 1022 | AMAL KUMAR MUKHERJEE | 8.93 | 0 | 0 | 50
508 | PURULIA | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well with allied cable line and other allied works for augmentation of Joypur(riverside) w/s scheme under PMD, PHE Dte. in the District of Purulia. | 243/PMD | 03/03/2023 | 367 | ANUP KR. SAHA | 70.91 | 0 | 0 | 66
509 | PURULIA | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmeter and other allied works for augmentation of Joypur (OHR side) water supply scheme under PMD, PHE Dte. in the District of Purulia. | 421/PMD | 13/04/2023 | 60 | MERCURY ENGINEERING COMPANY | 36.21 | 0 | 0 | 30
510 | PURULIA | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Supply delivery and installation of 150 KVA voltage stabilizer for Augmentation of Joypur(River Side) water supply scheme under PMD PHE Dte. In the district of Purulia. | 801/PMD | 12/07/2023 | 664 | M/S P.P.ELECTRICALS | 15.63 | 0 | 0 | 96
511 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Laying of Collecting line from Riverbed Manifold to Pump house and Laying of Distribution pipeline from Existing OHR to Main Road and other allied works complete under Kotshila W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. (Under Joypur W/S Scheme) | 293/PD | 28/02/2024 | 484 | ASHOKE ADHIKARY | 12.9 | 0 | 0 | 80
512 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Left Out Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Rahardaga (Jl-64) & Mouza-Mirdi (Jl-102) and extention of Parallal distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 491/PD | 16/03/2024 | 360 | UMA CONSTRUCTION | 74.86 | 0 | 0 | 100
513 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Baliagora (J.L. No.- 96), Mouza- Mukundapur (J.L. No.-97), Mouza-Kamukhap (J.L. No.- 98) & Mouza- Amdih(J.L. No.-100) and replacement/ extention of distribution pipe line under augmentation of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 873/PD | 23/05/2022 | 954 | M/S. S. CHOUDHURY | 72.66 | 0 | 0 | 55
514 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Shyampur (Jl-101) & Mouza-Dhabani (Jl-103) and replacement/ extention of distribution pipe line under command area of Joypur Water Supply Scheme of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 841/PD | 23/05/2022 | 887 | SUNNY ELECTRIC CO | 56.74 | 0 | 0 | 100
515 | PURULIA | Purulia Division | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Construction of RCC Clear Water Reservoir (CWR) of Capacity 200 Cum with other allied work at OHR campus of Joypur W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | 1837/PD | 12/12/2022 | 361 | KM ENTERPRISES | 33.08 | 0 | 0 | 100
516 | PURULIA | Purulia Mechanical | Augmentation of Joypur PWSS for Proving Functional Household Tap Connection (FHTC) , SM/10722 | Augmentation | Supply delivery and installation of 100 KVA voltage stabilizer for Augmentation of Joypur(OHR Side) water supply scheme under PMD PHE Dte. In the district of Purulia. | 245/PMD | 03/03/2023 | 60 | ANUP KR. SAHA | 10.76 | 0 | 0 | 96
517 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10249 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Chharrah G.P of Purulia-II Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1129/BMD | 12/09/2022 | 15 | ABHIJIT MUKHERJEE | 42.52 | 0 | 0 | 0
518 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10249 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Ghongha G.P of Purulia-II Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1130/BMD | 12/09/2022 | 25 | SUMIT KUMAR CHAKRABORTY | 70.88 | 0 | 0 | 0
519 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10249 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Hutmura & Raghabpur G.P of Purulia-II Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1131/BMD | 12/09/2022 | 15 | CHAKRABORTY MAINING & ENGINEERING. | 35.89 | 0 | 0 | 0
520 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10249 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Belma & Bhangra G.P of Purulia-II Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1128/BMD | 12/09/2022 | 15 | ABHIJIT MUKHERJEE | 42.52 | 0 | 0 | 0
521 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10249 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Aga yesa Narrah G.P of Purulia-II Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1197/BMD | 22/09/2022 | 15 | PREMNATH MITRA | 35.83 | 0 | 0 | 0
522 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10249 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method sourceless AWC at Purulia-II Block where adjacent road is narrow and critical under Purulia Mechanical Division PHE Dte. in the District of Purulia | 529/PMD | 05/05/2023 | 30 | NUPUR CHANDRA HALDER | 31.54 | 0 | 0 | 0
523 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10249 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Purulia-II Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | 739/PD | 02/05/2022 | 45 | INDRAJIT SARKAR | 13.6 | 0 | 0 | 100
524 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10249 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Purulia-II Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | 740/PD | 02/05/2022 | 45 | BHUTNATH MISHRA | 13.53 | 0 | 0 | 100
525 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10249 | Anganwadi | Installation of Big-Dia D.T.H. Tube Well (200mm x 165mm) by Robotic DTH Rigs for drilling upto 1200 ft or small form factor trolly mounted rig with trolly mounted compressor suitable for narrow 68 inch wide roads considering 200mt Depth in diferent AWC of different Blocks (PHASE-1) of the District Purulia under Purulia RWS Sub Division,PHE Dte. under Purulia Division, PHE Dte. | 48/PD | 09/01/2023 | 45 | S N POLYMERS PVT LTD | 96.17 | 0 | 0 | 0
526 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10249 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Purulia-II Block ) of Purulia District under Purulia Division, PHE Dte. | 37/PD | 09/01/2023 | 45 | TAPAN CHANDRA | 6.4 | 0 | 0 | 0
527 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10249 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Purulia-II Block (Part-E) of Purulia District under Purulia Division, PHE Dte. | 766/PD | 02/05/2022 | 45 | SOUHARDYA BUSINESS LINE | 40.73 | 0 | 0 | 100
528 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10249 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within PURULIA-II Block (Part-J,L,M,N,N,O) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | 1869/PD | 13/12/2022 | 45 | IKBAL CONSTRUCTION | 28.24 | 0 | 0 | 100
529 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10249 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Purulia-II Block (Part-B) of Purulia District under Purulia Division, PHE Dte. (Phase-I) | 1702/PD | 22/11/2022 | 45 | KOUSHIK CHATTERJEE | 91.59 | 0 | 0 | 100
530 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10249 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Golamara G.P of Purulia-II Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1198/BMD | 22/09/2022 | 15 | AMITAVA CHAKRABORTY | 35.4 | 0 | 0 | 100
531 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10249 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Pindra G.P of Purulia-II Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1199/BMD | 22/09/2022 | 15 | AMITAVA CHAKRABORTY | 32.22 | 0 | 0 | 90
532 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(97 nos) under Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10249 | Anganwadi | Supply and Delivery of fuel(Diesel) and lubricants to Departmental Rig KLR and supporting vehicle WB 67 6943 in connection of Purulia JJM Program at BMSD(D) under PHE Dte. |  | 30/05/2024 | 0 | LALJI RAJA & SONS AGENCIES | 1.69 | 0 | 0 | 0
533 | PURULIA | Purulia Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06942 | Retrofitting | Retrofitting of Baram water supply scheme at Arsha Block of Purulia Sadar-Sub Division for providing functional house hold Tap connection (FHTC) under Jal Sapna program (Habitation covered Baram, Thakushima, Bridhistarh, Jharatar) Part-A. (Tender No. 9/SE/PMU of 2020-21) | 369/8443218 | 25/02/2021 | 0 | KOUSHIK CHATTERJEE | 28.91 | 0 | 0 | 0
534 | PURULIA | Purulia Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06942 | Retrofitting | Retrofitting of Boram W/s Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under Jal Sapna Programme (Habitation Covered Mankiyari, Torang, Matkumpiri, Raipur, Jibandity) Part-B. (Tender No. 160/EE/PD of 2020-21) | 386/844340 | 08/03/2021 | 0 | SOUMITRA CHAKRABORTY | 20.9 | 0 | 0 | 0
535 | PURULIA | Purulia Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06942 | Retrofitting | Extention of distribution pipeline for providing FHTC under Jal Sapna Programme of Baram W/S Scheme under Purulia Division PHE Dte. (Habitation Name:-Mankiary,Gundligora,Matkampiri, Torang) (Tender No.875/EE/PD of 2021-22) | 133/8443221/2 | 29/09/2022 | 0 | SOUMITRA CHAKRABORTY | 0.44 | 0 | 0 | 0
536 | PURULIA | Purulia Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06942 | Retrofitting | Extention of distribution pipeline for providing FHTC under Jal Sapna Programme of Baram W/S Scheme under Purulia Division PHE Dte. (Habitation Name:-Baram,Thakurshima,Briddhitanr,Jaratanr) (Tender No.874/EE/PD of 2021-22) | 133/8443221/1 | 29/09/2022 | 0 | SOUMITRA CHAKRABORTY | 1.2 | 0 | 0 | 0
537 | PURULIA | Purulia Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06942 | Retrofitting | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Mankiyari, Torang, Matkompiri, Raipur, Jibandih & Gundligora) Part-B (Tender No.160/EE/PD of 2020-21) | 278/844393/2 | 14/01/2022 | 0 | SOUMITRA CHAKRABORTY | 5.64 | 0 | 0 | 0
538 | PURULIA | Purulia Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06942 | Retrofitting | Laying of additional pipeline of 20mm HDPE (OD) for the work of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Mankiyari, Torang, Matkompiri, Raipur, Jibandih & Gundligora) Part-B (Tender No.721/EE/PD of 2020-21) | 278/844393/1 | 14/01/2022 | 0 | SOUMITRA CHAKRABORTY | 2.62 | 0 | 0 | 0
539 | PURULIA | Purulia Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06942 | Retrofitting | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Baram, Thakurshima, Briddhitanr & Joratanr) Part-A | 1409/PD | 29/12/2020 | 45 | KOUSHIK CHATTERJEE | 48.17 | 8.62 | 100 | 0
540 | PURULIA | Purulia Division | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06942 | Retrofitting | Searching report of land & Retainer Service by Regional Advocate(s) for direct purchase of land for public purpose by Dept. through Zilla Parisad from Intending owners WTP for surface based piped water supply scheme for Purulia District under Division PHE Dte. | 9/2024-25 | 09/04/2024 | 0 | RANJEET CHATTERJEE | 1.97 | 0 | 0 | 0
541 | PURULIA | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS , SM/14460 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. Of Dubra Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-B] | 100/PD | 20/01/2023 | 90 | MANATOSH SINGH | 79.67 | 0 | 0 | 55
542 | PURULIA | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS , SM/14460 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dubra Water Supply Scheme, Block- Para ) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 1749/PD | 22/11/2022 | 30 | M/S. DESTINY CONSTRUCTION | 3.48 | 0 | 0 | 100
543 | PURULIA | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS , SM/14460 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. Of Dubra Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-E] | 103/PD | 20/01/2023 | 30 | M/S SAYAK BHATTACHARYA | 13.69 | 0 | 0 | 100
544 | PURULIA | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS , SM/14460 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. Of Dubra Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-C] | 101/PD | 20/01/2023 | 30 | SOUMITRA CHAKRABORTY | 98.6 | 0 | 0 | 100
545 | PURULIA | Purulia Mechanical | Augmentation of Dubra Pipe Water Supply Scheme PWSS , SM/14460 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Dubra (Pump house site) Water Supply scheme Block Para under PMD PHE Dte. District Purulia | 445/PMD | 20/04/2023 | 30 | DEY ENTERPRISE,MALDAH | 21.63 | 0 | 0 | 70
546 | PURULIA | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS , SM/14460 | Augmentation | Laying of Distribution System is a rest portion of Part-E including providing House Hold Tap Connection (FHTC) and other allied works for Aug. Of Dubra Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 882/PD | 03/07/2023 | 45 | SABYASACHI MISHRA | 11.94 | 0 | 0 | 100
547 | PURULIA | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS , SM/14460 | Augmentation | Restoration of Road after laying of drinking water pipe line under Jal Jeevan Mission for Kashipur W/S Schema along Hura-Kashipur-Adra-Raghunathpur Road under Purulia Division, P.WD in the district of Purulia in the year 2023-24. | BP-2023-24-386 | 18/08/2023 | 0 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 60.8 | 0 | 0 | 0
548 | PURULIA | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS , SM/14460 | Augmentation | Restoration of Road after laying of drinking water pipe line under Jal Jeevan Mission for Dubra W/S Schema on Raghunathpur Chandankairy-Chas Road CH-13.963 KM to CH-15.178 Km under Purulia Division, P.W.D in the district of Purulia in the year 2023-2024. | BP-2023-24-387 | 18/08/2023 | 0 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 95.57 | 0 | 0 | 0
549 | PURULIA | Purulia Mechanical | Augmentation of Dubra Pipe Water Supply Scheme PWSS , SM/14460 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, HOT, Flowmeter and other allied works for augmentation of Dubra water supply scheme under PMD, PHE Dte. In the district of Purulia. | 296/PMD | 16/03/2023 | 60 | TAPAN KUMAR DEY | 42.49 | 0 | 0 | 40
550 | PURULIA | Purulia Mechanical | Augmentation of Dubra Pipe Water Supply Scheme PWSS , SM/14460 | Augmentation | Supply delivery and installation of 50 KVA voltage stabilizer for Augmentation of Dubra water supply scheme under PMD PHE Dte. In the district of Purulia. (2 nd Call) | 1172/PMD | 03/11/2023 | 60 | SWAPAN ENTERPRISE | 7.21 | 0 | 0 | 75
551 | PURULIA | Purulia Mechanical | Augmentation of Dubra Pipe Water Supply Scheme PWSS , SM/14460 | Augmentation | Internal and external illumination with other allied works for augmentation of Dubra water supply scheme under PMD, PHE Dte. In the district of Purulia. (2 nd Call) | 1174/PMD | 03/11/2023 | 60 | PINTU DEY | 5.37 | 0 | 0 | 25
552 | PURULIA | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS , SM/14460 | Augmentation | Supply, delivery fitting & fixing of 1 No. Scheme Description Sign board (6' X 3') under Dubra W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. Location:- Head Work Site | 25/RNP | 15/01/2024 | 7 | M/S SAYAK BHATTACHARYA | 0.17 | 0 | 0 | 0
553 | PURULIA | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS , SM/14460 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. Of Dubra Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-D] | 102/PD | 20/01/2023 | 45 | SUBRATA SINGHADEO | 39.27 | 0 | 0 | 100
554 | PURULIA | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS , SM/14460 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Dubra Mouza, JL No.-79, Plot No.499 at OHR site under Dubra W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 544/PD | 12/04/2023 | 629 | ASHOK KUMAR CHATTERJEE | 14.79 | 0 | 0 | 100
555 | PURULIA | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS , SM/14460 | Augmentation | Construction of RCC Clear water reservoir (CWR) of capacity 100 Cum, Pump house for accommodating centrifugal pump and making inter-connection by CIDF & M.S Pipe for pumping of water including Panel room & Chlorination room and Sinking of 2 (Two) Nos. 200 mm dia DTH rigbored tubewell with other allied works at Dubra OHR campus of Dubra W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1542/PD | 16/10/2023 | 777 | MANATOSH SINGH | 47.18 | 0 | 0 | 60
556 | PURULIA | Purulia Division | Augmentation of Dubra Pipe Water Supply Scheme PWSS , SM/14460 | Augmentation | Laying of Distribution System including supply of materials including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Dubra Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-A] | 99/PD | 20/01/2023 | 1076 | NANIGOPAL DEY | 97.25 | 0 | 0 | 40
557 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Extension service connection from existing distribution main to Telkupi Baruni ghat, Kastogora Pry. School, Dandahit Pry. School, Madhukunda Prathamik Vidyalaya & Bagalgora Pry. School under Balitora Improvement Water Supply Scheme (Tender No- 01/2020-21 of EE/PD) |  | 03/03/2022 | 0 | KOUSHIK CHATTERJEE | 1.81 | 0 | 0 | 0
558 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | FHTC water tap connection in Schhol and health centre from existing distribution system with other allied works within scheme Jurisdiction of Lagda Piped W/s Scheme. (Tender No.825/EE/PD of 2021-22) | BP-2021-22-279 | 03/03/2022 | 0 | M/S CHAKRABORTY CONSTRUCTION | 1.68 | 0 | 0 | 0
559 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Estimate for water supply arrangement at Mukundapur Prymary School Model-I (Upto 200 students) under Joypur Block. (Tender No.1017/EE/PD of 2021-22) | BP-2022-23-19 | 07/04/2022 | 0 | AMAL KUMAR MUKHERJEE | 0.96 | 0 | 0 | 0
560 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Extension of PVC & G.I pipe line in distribution system for Stand Post at different School & Offices of Purulia-II Block area to drinking water supply under Bongabari W/s Scheme. (Tender No.879/EE/PD of 2021-22) | BP-2021-22-280 | 03/03/2022 | 0 | SOUVIK MANDAL | 2.65 | 0 | 0 | 0
561 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Providing Functional Household Tap Connection (FHTC) at different AWC School and other allied works of Santuri Water Supply Scheme at Santuri Block of Raghunathpur Sub- Division under Purulia Division, PHE Dte. (Tender No- 392/2022-23 of EE/PD) | BP-2022-23-273 | 23/09/2022 | 0 | MS MITRA SENGUPTA ENTERPRISES | 1.1 | 0 | 0 | 0
562 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Extension of service connection from existing Distribution Main to Telkupi Baruni Ghat, Kastogora Pry. School, Dandahit Pry. School, Madhukunda Prathamik Vidyalaya and Bagalgoria Pry. School under Balitora improvement W/s Scheme. (Tender No.1/EE/PD of 2020-21) | BP-2021-22-278 | 03/03/2022 | 0 | KOUSHIK CHATTERJEE | 1.81 | 0 | 0 | 0
563 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | MODEL ESTIMATE FOR SKILLING OF MANPOWER TO GENERATE EMPLOYMENT OPPURTUNITIES AND TO SUPPORT IMPLEMENTATION OF JAL SWAPNA (For 5 nos Blocks Neturia,Para,Bagmundi,Raghunathpur-I,Puncha) | 15/(S-6)/PR | 05/02/2021 | 7 | KOUSHIK CHATTERJEE | 0.7 | 0 | 0 | 100
564 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 39 nos AWC within Raghunathpur -I Block ) of Purulia District under Purulia Division, PHE Dte. | 38_/PD | 09/01/2023 | 45 | DILIP MISHRA | 21.67 | 0 | 0 | 0
565 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Barabazar Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | 469/PD | 24/03/2022 | 45 | KOUSHIK CHATTERJEE | 23.43 | 0 | 0 | 60
566 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Manbazar-I Block (Part-K) of Purulia District under Purulia Division, PHE Dte. | 598/PD | 19/04/2022 | 45 | ZAKIR HOSSIN MONDAL | 15.63 | 0 | 0 | 100
567 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Kashipur Block (Part-E) of Purulia District under Purulia Division, PHE Dte.(Phase-III) | 1131/PD | 25/07/2022 | 45 | SINGHA ENTERPRISE | 94.88 | 0 | 0 | 100
568 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Barabazar Block (Part-F)of Purulia District under Purulia Division, PHE Dte. | 1855/PD | 13/12/2022 | 45 | SANTANU BANERJEE | 74.42 | 0 | 0 | 100
569 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | 1151_/PD | 01/08/2022 | 45 | WATER TECH | 158.37 | 0 | 0 | 100
570 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | SKILLING OF MANPOWER TO GENERATE EMPLOYMENT OPPURTUNITIES AND TO SUPPORT IMPLEMENTATION OF JAL SWAPNA (For 5 nos Blocks Manbazar-I, Jhalda-I, Jhalda-II, Manbazar-II, Joypur) | 15/(S-5)/PR | 05/02/2021 | 7 | KOUSHIK CHATTERJEE | 3.49 | 0 | 0 | 100
571 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | 22_/PD | 05/01/2023 | 45 | WATER TECH | 165.38 | 0 | 0 | 100
572 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Estimate for water supply arrangement of Manbazar Girls Pry School, Manbazar Rajakpara Pry School & Manbazar Bauripara Pry School in Manbazar-I Block of the District Purulia under Purulia Division, PHE Dte. for [Estimate for Model 1 upto 200 students) (Tender No- 1018/2021-22 of EE/PD) | BP-2022-23-77 | 01/07/2022 | 0 | KANAILAL PAL | 1.16 | 0 | 0 | 0
573 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Model estimate for skilling of manpower to generate employment opportunities and to support implementation of Jal Swapna [ for 5 nos Blocks Kashipur, Raghunathpur-II, Hura, arsha, Santuri] (Tender No 789/2021-22 of EE/PD) | BP-2022-23-842 | 31/03/2023 | 0 | MANATOSH SINGH | 3.48 | 0 | 0 | 0
574 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Estimate for water supply arrangement of Bartoric High School in Neturia Block in the District Purulia under Purulia District, PHE Dte. (Tender No- 1028/2021-22 of EE/PD) | BP-2022-23-66 | 01/07/2022 | 0 | INDRAJIT SARKAR | 1.59 | 0 | 0 | 0
575 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Withdrawing & lowering of 1M- II hand pump assembly for measurement of water level at different block of District Purulia (w.e.f. 01/09/2021 to 31/08/2022) [Name of block Hura, Kashipur, Neturia, Para, Raghunathpur-I, Raghunathpur-II, Santuri, Manbazar-I, Puncha, Purulia-II] (Tender No. 764/EE/PD of 2021-22) | BP-2022-23-78 | 01/07/2022 | 0 | ANUDIP SAHA | 0.66 | 0 | 0 | 0
576 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Model estimate for skilling of manpower to generate employment opportunities and to support implementation of Jal Swapna [ for 5 nos Blocks Neturia, Para, Baghmundi, Raghunathpur-I, Puncha] (Tender No 330/2021-22 of EE/PD) | BP-2022-23-792 | 24/03/2023 | 0 | KOUSHIK CHATTERJEE | 3.48 | 0 | 0 | 0
577 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Model estimate for skilling of manpower to generate employment opportunities and to support implementation of Jal Swapna [For 5 nos block Purulia I, Balarampur, Bundwan, Purulia-II, Barabazar] (Tender No- 788/2021-22 of EE/PD) | BP-2023-24-52 | 19/04/2023 | 0 | MANATOSH SINGH | 0.68 | 0 | 0 | 0
578 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at various ICDS centre and schools and supply of drinking water through water tanker to various places from nearby headwork sites of different W/S Scheme to mitigate draught like situation under Bandwan Block of Purulia Sadar Sub- Division, PHE Dte. (Tender No- 56/2022-23 of EE/PD) | BP-2022-23-96 | 07/07/2022 | 0 | BOSE CONSTRUCTION | 1.57 | 0 | 0 | 0
579 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Raghunathpur-I Block (Part-B) & 6 nos AWC within Raghunathpur Block (Part-D-II) of Purulia District under Purulia Division, PHE Dte. | 353/PD | 14/03/2023 | 45 | PREMNATH MITRA | 148.86 | 0 | 0 | 49
580 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Barabazar Block (Part-R) of Purulia District under Purulia Division, PHE Dte. | 1156/PD | 01/08/2022 | 45 | MANASH GHOSH | 197.96 | 0 | 0 | 100
581 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 1 nos AWC within Barabazar Block (Part-S), of Purulia District under Purulia Division, PHE Dte. | 1728/PD | 22/11/2022 | 45 | PRATIK SAHA | 8.27 | 0 | 0 | 100
582 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Work of Vendoring service service relating to E-return for Income-Tax and GST and allied service of Purulia Division, PHE Dte. (w.e.f 01.10.2023 to 30.09.2024) | BP-2024-25-356 | 11/09/2024 | 0 | NIGAM CONSULTANCY SERVICES | 0.77 | 0 | 0 | 0
583 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Supply of stationery materials for office use | BP-2024-25-531 | 20/11/2024 | 0 | KETIKA CONSUMERS CO-OPERATIVE STORES LTD | 2.49 | 0 | 0 | 0
584 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Regarding the expenses on the gram Sabha meeting for Har Ghar Jaal certification in Janardandi GP under Neturia Block on 01.03.2024. | BP-2024-25-395 | 19/09/2024 | 0 | KOUSHIK CHATTERJEE | 0.56 | 0 | 0 | 0
585 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Bill Payment for supply repairing & installation of computer related components for office purpose. | BP-2024-25-515 | 06/10/2024 | 0 | SRI KRISHNA COMPUTER | 1.2 | 0 | 0 | 0
586 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Reimbursement of the amount spent during the training program of pump operator & valve operator as per JJM guidelines on 31/01/2023 | BP-2024-25-396 | 19/09/2024 | 0 | BOSE CONSTRUCTION | 0.57 | 0 | 0 | 0
587 | PURULIA | Purulia Division | Extension of Pipeline to Anganwadi Centres (AWCS) located within command area of PWS Schemes within Purulia District under Purulia Division, PHE Dte. , SM/08718 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Jhalda-II Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | 729/PD | 02/05/2022 | 45 | MOONLIGHT HOUSE | 23.57 | 0 | 0 | 100
588 | PURULIA | Purulia Division | Retrofitting of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07838 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte at (Mouza:-Kalapathar, ,Kendtanr, Kultore , Kumardih, ushjuri Sonathol). (1309 Nos.) (Tender No. 373/EE/PD of 2020-21) (Ad-interim) | 89/8443101 | 15/07/2021 | 0 | KHAN ENTERPRISE | 7.11 | 0 | 0 | 0
589 | PURULIA | Purulia Division | Retrofitting of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07838 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Sonathali W/S Scheme at Kashipur Block of Raghunathpur Sub- Division PHE Dte. at Mouza- Kalapathar, Kendtanr, kultore, kumardih, Ushjuri Sonathol (1309) Nos. (Tender No:- 373/EE/PD of 2020-21) |  | 09/08/2021 | 0 | KHAN ENTERPRISE | 14.38 | 0 | 0 | 0
590 | PURULIA | Purulia Division | Retrofitting of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07838 | Retrofitting | Functional House Hold Connection (FHTC) including other allied works of Sonatholi Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division PHE Dte. (Mouza- Kashipur, Kendtanr, Kultore, Kumardih, Ushjuri Sonatholi) (1309 nos.) (Tender No. 373/EE/PD of 2020-21) |  | 22/03/2021 | 0 | KHAN ENTERPRISE | 28.02 | 0 | 0 | 0
591 | PURULIA | Purulia Division | Retrofitting of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07838 | Retrofitting | Additional work for functional Household Tap Connection (FHTC) including other allied works of augmentation of Sonathali Water Supply Scheme at Kashipur Block. (Tender No.17/SE/PMU of 2021-22) | BP-2022-23-46 | 02/05/2022 | 0 | S AND P CONSTRUCTION | 16.37 | 0 | 0 | 0
592 | PURULIA | Purulia Division | Retrofitting of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07838 | Retrofitting | Construction of Boundary wall, RCC pillar, barbed wire & other allied works under Sonathali W/S Scheme (Tender No-930/2021-22 of EE/PD) | BP-2022-23-57 | 20/05/2022 | 0 | TOTAL INFRA | 3.35 | 0 | 0 | 0
593 | PURULIA | Purulia Division | Retrofitting of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07838 | Retrofitting | Construction of G.I. Shed at 1st Floor of Raghunathpur Sub-Divisional office buiding under Aug. of Sonathol W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1747/PD | 22/11/2022 | 45 | MANATOSH SINGH | 4.3 | 0 | 0 | 0
594 | PURULIA | Purulia Division | Retrofitting of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07838 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte at (Muza:-Kalapathar, ,Kendtanr, Kultore , Kumardih, ushjuri Sonathol). (1309 Nos.) | 213/PD | 08/02/2021 | 45 | KHAN ENTERPRISE | 70.34 | 60.28 | 100 | 0
595 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Baltora , Habitation - Mathorgoria (30 Nos.),Baltora (82 Nos.) | 24/RNP | 11/01/2021 | 15 | KANAILAL PAL | 4.78 | 0 | 0 | 100
596 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Dhanasdi, Habitation - Dhanasdi (84 Nos.), Mouza-Ektira, Habitation - Ektira (28 Nos.) | 29/RNP | 11/01/2021 | 15 | KABERI DUTTA | 4.78 | 0 | 0 | 100
597 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional house hold tap connection (FHTC) including other allied works of under Balotora W/s Scheme of Santuri Block of mouza Monpur (112 Nos). (Tender No. 286/EE/PD of 2020-21) | 17/844362/1 | 21/04/2021 | 0 | CHAIL CONSTRUCTION | 4.44 | 0 | 0 | 0
598 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | FHTC including other allied works of Balitora water supply scheme at Santuri Block at Mouza-Balitora, Habitation (108 Nos) (Tender No. 288/EE/PD of 2020-21) (Ad-interim) | 70/844369 | 18/06/2021 | 0 | NANIGOPAL DEY | 1.86 | 0 | 0 | 0
599 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional house hold tap connection (FHTC) including other allied works of Balitora W/s Scheme at Santuri Block (Tender No. 363/PD of 2020-21) | 59/844323 | 08/06/2021 | 0 | SUPRIYA MAHANTI MISHRA | 4.76 | 0 | 0 | 0
600 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block at Mouza- Balitora, Habitation- Balitora (108 Nos.) (Tender No:- 288/EE/PD of 2020-21) | BP-2021-22-50 | 20/07/2021 | 0 | NANIGOPAL DEY | 2.18 | 0 | 0 | 0
601 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora W/S Scheme at Santuri Block of Raghunathpur Sub- Division PHE Dte. at Mouza- Dandahit, Habitation- Dandahit (108 Nos.) (Tender No:- 414/EE/PD of 2020-21) | BP-2021-22-86 | 23/08/2021 | 0 | ASHOK KUMAR CHATTERJEE | 4.79 | 0 | 0 | 0
602 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. at Mouza- Bakuliashota, Habitation-Bakulia (16 Nos.), Mouza- Santuri, Habitation- Uppardih (46 Nos.) Mouza- Ektira, Habitation- Berakural-(1), Ektira (48 Nos.) Mouza-Kastagora Habitation- Chapabera Chak-(1) (Tender No.342/EE/PD of 2020-21) | BP-2021-22-131 | 11/10/2021 | 0 | MS MITRA SENGUPTA ENTERPRISES | 4.63 | 0 | 0 | 0
603 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. at Mouza- Bakuliashota, Habitation-Bakulia (112 Nos.) (Tender No.276/EE/PD of 2020-21) | BP-2021-22-132 | 11/10/2021 | 0 | DEB SHANKAR LAYEK | 4.54 | 0 | 0 | 0
604 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora W/S Scheme at Santuri Block of Raghunathpur Sub- Division PHE Dte. at Mouza- Deuli, Habitation- Deuli (70 Nos.) Mouza- Sunuri, Habitaion- Sunuri (42 Nos.) (Tender No:- 348/EE/PD of 2020-21) | BP-2021-22-95 | 23/08/2021 | 0 | SK ABBAS | 3.61 | 0 | 0 | 0
605 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza- Madhukunda Alias Mokura, Habitation- Madhukunda Alias Mokura (86 Nos.) Mouza-Saspur, Habitation-Saspur (26 Nos.) (Tender No.302/EE/PD of 2020-21) | BP-2021-22-87 | 23/08/2021 | 0 | SUBRATA SINGHADEO | 4.53 | 0 | 0 | 0
606 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/s Scheme at Santuri Block within Raghunathpur Sub-Division under Purulia Division PHE Dte. Mouza- Santuri, Habitation-Santuri (112 Nos.) (Tender No. 295/EE/PD of 2020-21) | 11/844325/2 | 12/04/2021 | 0 | M/S SAYAK BHATTACHARYA | 4.66 | 0 | 0 | 0
607 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora W/s Scheme at Santuri Block of Raghunathpur Sub-Division at Mouza- Baltora, Habitation- Baltora (51 Nos), Mouza- Santuri, Habitation- Santuri (61 Nos), (Tender No:- 299/EE/PD of 2020-21) | BP-2021-22-118 | 11/10/2021 | 0 | SUBRATA SINGHADEO | 3.55 | 0 | 0 | 0
608 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at (Balitora, Habitation- Balitora). (112 Nos.) (Tender No.305/EE/PD of 2020-21) | BP-2021-22-67 | 12/08/2021 | 0 | TUMPA GORAIN | 4.52 | 0 | 0 | 0
609 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza-Dandahit, Habitation- Dandahit). (112 Nos.) (Tender No.279/EE/PD of 2021-22) | BP-2021-22-68 | 12/08/2021 | 0 | SIKHA ENTERPRISES | 4.77 | 0 | 0 | 0
610 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional house hold tap connection (FHTC) including other allied works of under Balotora W/s Scheme of Santuri Block of mouza Monpur (88 Nos). (Tender No. 281/EE/PD of 2020-21) | 17/844362/2 | 21/04/2021 | 0 | SUDHANSHU OJHA | 4.4 | 0 | 0 | 0
611 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora W/s Scheme at Santuri Block of Raghunathpur Sub-Division at Mouza- Kashatagora, Habitation- Kashatagora (112 Nos) (Tender No:- 271/EE/PD of 2020-21) | BP-2021-22-116 | 11/10/2021 | 0 | KHITISH CHANDRA PATHAK | 4.43 | 0 | 0 | 0
612 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block at Mouza- Jagannathdi, Habitation-Jagannathdi (09 Nos.), Mouza- Kshatagora Habitation - Kshatagora (11 nos), Mouza- Manpur, Habitation- Manpur (46 Nos.), Siyal Danga (39) (Tender No:- 283/EE/PD of 2020-21) | BP-2021-22-51 | 20/07/2021 | 0 | SANDIP KUMAR DUBEY | 4.68 | 0 | 0 | 0
613 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Balitora, Habitation- Mathorgoria (30 Nos.) (82 Nos.) (Tender No.337/EE/PD of 2020-21) | BP-2021-22-66 | 12/08/2021 | 0 | KANAILAL PAL | 4.5 | 0 | 0 | 0
614 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora W/S Scheme at Santuri Block of Raghunathpur Sub- Division PHE Dte. at Mouza- Madhukunda Alias Mokura, Habitation- Madhukunda Alias Mokura (112) Nos. (Tender No:- 362/EE/PD of 2020-21) | BP-2021-22-82 | 23/08/2021 | 0 | SUBHAS CHANDRA MAHATO | 4.58 | 0 | 0 | 0
615 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | DZSGZDG |  | 30/11/2021 | 0 | KABERI DUTTA | 1 | 0 | 0 | 0
616 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional house hold tap connection (FHTC) including other allied works of Balitora W/s Scheme of Santuri Block. (Tender No. 303/EE/PD of 2020-21) | 11/844325/1 | 12/04/2021 | 0 | ROY CONSTRUCTION | 4.54 | 0 | 0 | 0
617 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/s Scheme at Santuri Block within Raghunathpur Sub-Division under Purulia Division PHE Dte. Mouza- Santuri, Habitation-Upardih- (63 Nos.) (49 Nos.) (Tender No. 296/EE/PD of 2020-21) | 11/844325/3 | 12/04/2021 | 0 | UTTAM KUMAR DUTTA | 4.77 | 0 | 0 | 0
618 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora W/S Scheme at Santuri Block of Raghunathpur Sub- Division PHE Dte. at Mouza- Sunuri, Habitation- Kapasdanga (35) Sunuri (77) Nos. (Tender No:- 318/EE/PD of 2020-21) | BP-2021-22-84 | 23/08/2021 | 0 | KAMAKHYA ENTERPRISE | 4.58 | 0 | 0 | 0
619 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza- Sashpur, Habitation-Sashpur (112 Nos.) (Tender No.293/EE/PD of 2020-21) | BP-2021-22-174 | 22/11/2021 | 0 | PRATIK SAHA | 4.48 | 0 | 0 | 0
620 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Baltora, Habitation -Balitora (51 Nos.), Mouza- Shunuri, Habitation - Sunuri (61 Nos.) | 25/RNP | 11/01/2021 | 15 | SUBRATA SINGHADEO | 4.73 | 0 | 0 | 100
621 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Probable estimate for sifting of ground HDPE & DI pipe line including supplying & DI pipe of Distribution line with allied works from Kapasdanga Village end to Mokra Pry. School through Jagannathdih & Saluni Village under Zone-II of Balitora W/s Scheme. (Tender No.937/EE/PD of 2021-22) | BP-2021-22-363 | 28/03/2022 | 0 | KHITISH CHANDRA PATHAK | 16.39 | 0 | 0 | 0
622 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Jagannathdi , Habitation - Jagannathdi (9 Nos.), Mouza - Kshatagora , Habitation - Kshatagora (11 Nos.), Mouza -Manpur , Habitation -Manpur (46 Nos.),Siyal Danga(39). (Tender No.812/EE/PD of 2021-22) | BP-2021-22-225 | 03/02/2022 | 0 | AMIT PATHAK | 1.6 | 0 | 0 | 0
623 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Manpur, Habitation - Manpur (112 Nos.) (Tender No.-824/EE/PD of 2021-22) | BP-2021-22-226 | 03/02/2022 | 0 | CHAIL CONSTRUCTION | 1.36 | 0 | 0 | 0
624 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Balitora , Habitation -Salani (36 Nos.), Balitora (72 Nos.) | 17/RNP | 11/01/2021 | 15 | MADHU SUDAN RAKSHIT | 4.62 | 0 | 0 | 0
625 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Dandahit , Habitation - Dandahit (108 Nos.) | 18/RNP | 11/01/2021 | 15 | ASHOK KUMAR CHATTERJEE | 4.83 | 0 | 0 | 0
626 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Jagannathdi , Habitation - Jagannathdi (9 Nos.), Mouza - Kshatagora , Habitation - Kshatagora (11 Nos.), Mouza -Manpur , Habitation -Manpur (46 Nos.),Siyal Danga(39). | 19/RNP | 11/01/2021 | 15 | SANDIP KUMAR DUBEY | 4.81 | 0 | 0 | 0
627 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Bakuliashota, Habitation -Bakulia (16 Nos.), Mouza- Shunuri, Habitation - Uppardi (46 Nos.), Mouza- Ektira, Habitation -Berakural-(1),Ektira (48 Nos.), Mouza- Kashtagora Habitation -Chapabera Chak-(1) | 20/RNP | 11/01/2021 | 15 | MS MITRA SENGUPTA ENTERPRISES | 4.78 | 0 | 0 | 0
628 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Sunuri, Habitation -Uppardi -(63Nos)Sunuri(49Nos.) | 38/RNP | 11/01/2021 | 15 | UTTAM KUMAR DUTTA | 4.78 | 0 | 0 | 0
629 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Bakuliasota , Habitation - Bakulia (112 Nos.) | 21/RNP | 11/01/2021 | 15 | DEB SHANKAR LAYEK | 4.78 | 0 | 0 | 0
630 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Supplying & laying different dia HDPE pipe line at Shunuri village of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Part-II) | 529/RNP | 27/08/2021 | 30 | RAHIBUDDIN MONDAL | 4.84 | 0 | 0 | 100
631 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Supplying & laying different dia HDPE pipe line at Shunuri village of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Part-I) | 530/RNP | 27/08/2021 | 30 | SABIR ALI KHAN | 4.84 | 0 | 0 | 100
632 | PURULIA | Purulia Division | Retrofitting of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07564 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Santuri Water Supply Scheme, Block- Santuri ) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 1750/PD | 22/11/2022 | 30 | M/S. DESTINY CONSTRUCTION | 2.3 | 0 | 0 | 100
633 | PURULIA | Purulia Mechanical | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Supply, Delivery and installation of two nos. submersible pumping machineries in newly constructed river bed tube well, voltage stabilizer with allied cable line and other allied works for augmentation of Satra w/s scheme under PMD, PHE Dte. in the District of Purulia. | 521/PMD | 05/08/2022 | 30 | NUPUR CHANDRA HALDER | 22.86 | 0 | 0 | 92
634 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-A) | 10/PSD | 13/01/2021 | 45 | GYANRANJAN SEN | 4.66 | 0 | 0 | 65
635 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Construction of RCC Clear Water Reservoir (CWR) of capacity 100 cum with other allied works at Satra boosting pump house campus of Satra W/S Scheme under Purulia Sadar Sub- Division, PHE Dte. (Tender No. 862/EE/PD of 2021-22) | BP-2022-23-130 | 19/07/2022 | 0 | SUBODH PRAMANIK | 11.52 | 0 | 0 | 0
636 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Laying of UPVC pipe as distribution main (loop line) from Misirdih More near Canel to Jhunjka village including PWD Road Crossing (Tamna-Arsha Road) by Jack pushing for drinking water supply through FHTC to meet up the water crisis at Jhunjka Village of Satra W/s Scheme under JJM. (Tender No.871/EE/PD of 2021-22) | BP-2021-22-293 | 09/03/2022 | 0 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 18.23 | 0 | 0 | 0
637 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Additional work for Extension of water supply pipe line towards Pitchkapahali, Garamthana, Lalbandh, Kishor Bharati Public School Adjacent to Patuara village from existing Satra W/s Scheme to meet up the water crisis under Jal Swapna Program. (Tender No.976/EE/PD of 2021-22) | BP-2022-23-33 | 20/04/2022 | 0 | SUBODH PRAMANIK | 12.45 | 0 | 0 | 0
638 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | providing Functional household tap Connection FHTC in connection with Jal Jeevan Mission (JJM & Jalswapna) at Ramjibanpur Jhunjka, Layardih of Hensla G.P. under command area of Satra W/S Scheme at Arsha block under Purulia Sadar Sub- Division (Tender No- 277/2020-21 of EE/PD) | BP-2021-22-312 | 22/03/2022 | 0 | KANTILAL SAO | 20.32 | 0 | 0 | 0
639 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Laying of UPVC pipe as distribution main from Misirdih More to East-West along the Tamna-Arsha Road for drinking water supply through FHTC to meet up the water crisis at Satra W/s Scheme under Jal Swapna Program. (Tender No.06/EE/PD of 2022-23) | BP-2022-23-55 | 19/05/2022 | 0 | DEBASISH CHAKRABORTY | 4.41 | 0 | 0 | 0
640 | PURULIA | Purulia Mechanical | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | SUPPLY DELIVERY & INSTT OF TWO NOS SUBMERSIBLE PUMP MOTOR SETS IN NEW CONSTRUCTED RIVERBED TUBE WELL AND LAYING OF DEPARTMENTALLY SUPPLIED CABLE LINE WITH OTHER ALLIED WORKS FOR SATRA W/S SCHEME UNDER PMD PHE DTE.(TR.NO 326/21-22) | C052221499438 | 11/05/2022 | 0 | NUPUR CHANDRA HALDER | 2.4 | 0 | 0 | 0
641 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | providing Functional household tap Connection FHTC (leftout household) in connection with Jal Jeevan Mission (JJM & Jalswapna) at Misirdih village of Chatu Hansa G.P. under command area of Satra W/S Scheme at Arsha block under Purulia Sadar Sub- Division (Tender No- 877/2021-22 of EE/PD) | BP-2021-22-305 | 14/03/2022 | 0 | BHAGABANDAS KUMAR | 6.11 | 0 | 0 | 0
642 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Providing Functional Household Tap Connection (FHTC)(leftout household) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.866/2021-22 of EE/PD) | BP-2022-23-336 | 29/09/2022 | 0 | SUBODH PRAMANIK | 8.57 | 0 | 0 | 0
643 | PURULIA | Purulia Mechanical | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, augmentation of MCC panel, Flow meter and other allied works for augmentation of Satra (River side) water supply scheme under PMD, PHE Dte. In the district of Purulia. | 129/PMD | 20/02/2023 | 60 | NUPUR CHANDRA HALDER | 36.75 | 0 | 0 | 51
644 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Laying of UPVC Pipe line from Satra OHR site towards Satra Village & Extension of PVC pipe line in distribution system for Stand Post at different School & ICDS Centre of Arsha Block to supply drinking water of command area of Satra Water Supply Scheme under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | 546/PD | 12/04/2023 | 30 | SUBODH PRAMANIK | 7.41 | 0 | 0 | 0
645 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Repairing and renovation of the Over Head reservoir (OHR) of 350 m3 Capacity, Staging Height 20 mtr. at Satra W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | 1578/PD | 17/12/2021 | 90 | SUBODH PRAMANIK | 10.25 | 0 | 0 | 90
646 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Providing Functional Household Tap Connection (FHTC)(leftout household) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1583/PD | 17/12/2021 | 45 | SUBODH PRAMANIK | 10.76 | 0 | 0 | 100
647 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Laying of 150 mm dia DI pipe line for clear water rising main from Medical hall at Misirdih to Boosting pump house at Satra Water Supply Scheme of Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1575/PD | 17/12/2021 | 90 | ANUDIP SAHA | 9.62 | 0 | 0 | 55
648 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Repairing & restoration of different works viz. Valve Chamber with replace of valve at OHR campus, Road cutting & restoration by concreting & Moorum spreading including M.S. Pipe placing as casing at different place of Satra W/S Scheme under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | 772/PD | 13/12/2021 | 30 | M/S SAWDESH ENTERPRISE | 3.52 | 0 | 0 | 95
649 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Laying of UPVC pipe as distribution main (loop line) from Satra Junior High School to Satra Uppar Para for drinking water supply through FHTC to meet up the water crisis at Satra W/S Scheme under Jalswapna Programme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1582/PD | 17/12/2021 | 90 | SUBODH PRAMANIK | 9.87 | 0 | 0 | 65
650 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Functional House hold Tap Connection (FHTC) & pipe line laying of different dia. Pipe in connection of Jal Jeevan Mission (JJM & Jal Swapna) Programme at Satra Village Uppar Para and adjacent area of Arsha Block to drinking water supply under augmentation at Satra Water Supply Scheme of Purulia Sadar Sub-Division, PHE Dte. | 1396/PD | 01/09/2022 | 45 | SUBODH PRAMANIK | 18.74 | 0 | 0 | 100
651 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Additional work for Grouting on inside & outside of cell wall for repairing and renovation of the Over Head reservoir (OHR) of 350 m3 Capacity, Staging Height 20 mtr. of Satra W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | 1639/PD | 03/11/2022 | 45 | M/S SAWDESH ENTERPRISE | 3.41 | 0 | 0 | 100
652 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Repairing, renovation & restoration of Pump house and Meter room including roof treatment & Boundary wall at satra river site & Boosting pump station of Satra W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | 1930/PD | 22/12/2022 | 60 | SUBODH PRAMANIK | 12.92 | 0 | 0 | 100
653 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Repairing of 200 mm dia Vertical and Horizontal Tubewell & 100 mm dia G.I. collecting line upto M.S. Manifold with allied works due to flash flood of Satra W/S Scheme of Purulia Sadar Sub-Division, Under Purulia Division, PHE Dte. | 287/PD | 27/02/2023 | 30 | M/S SAWDESH ENTERPRISE | 2.69 | 0 | 0 | 0
654 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Material Requisition To Resource Division | 1504/PD | 13/12/2021 | 0 | Resource Division | 58.03 | 0 | 0 | 0
655 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Material Requisition To Resource Division | 392/PD | 11/03/2022 | 0 | Resource Division | 1.28 | 0 | 0 | 0
656 | PURULIA | Purulia Mechanical | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Material Requisition To Resource Division | 620/PMD | 01/06/2023 | 0 | Resource Division | 1.55 | 0 | 0 | 0
657 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-A) (Tender No- 287/2020-21 of EE/PD) | BP-2022-23-219 | 24/08/2022 | 0 | GYANRANJAN SEN | 0.7 | 0 | 0 | 0
658 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | New sinking of 02 (Two) No. 200 mm dia river bed tube well (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI collecting line with all allied works at Satra river site of Satra Water Supply Scheme under Purulia Division, PHE Dte. Phase-1 (Tender No- 870/2021-22 of EE/PD) | BP-2022-23-92 | 07/07/2022 | 0 | SUBODH PRAMANIK | 17.23 | 0 | 0 | 0
659 | PURULIA | Purulia Mechanical | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Satra Water Supply scheme Block Arsha under PMD PHE Dte. District Purulia. | 163/PMD | 07/03/2022 | 30 | DEY ENTERPRISE | 20.5 | 0 | 0 | 85
660 | PURULIA | Purulia Mechanical | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Supply, Delivery and installation of submersible pumping machineries for river bed tube well with allied cable line and other allied works for Satra w/s scheme under PMD, PHE Dte. in the District of Purulia. | 1699/PMD | 06/12/2024 | 30 | NUPUR CHANDRA HALDER | 3.31 | 0 | 0 | 0
661 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-F) | 17/PSD | 13/01/2021 | 45 | RAKSHIT ENTERPRISE | 4.48 | 0 | 0 | 100
662 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Providing Functional Household Tap Connection (FHTC)(leftout household) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Misirdih village of Chatu Hansa G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1592/PD | 17/12/2021 | 45 | BHAGABANDAS KUMAR | 7.17 | 0 | 0 | 100
663 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Laying of UPVC pipe as distribution main from Misirdih more to East-West along the Tamna-Arsha road for drinking water supply through FHTC to meet up the water crisis at Satra W/S Scheme under Jalswapna Programme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1580/PD | 17/12/2021 | 90 | DEBASISH CHAKRABORTY | 6.73 | 0 | 0 | 100
664 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Construction of pump house for accommodating centrifugal pump for pumping of water from Satra Boosting Pump House site CWR to distribution zone of Satra water supply scheme under Purulia Sadar Sub-Division of Purulia Division, P.H.E. Dte. Purulia. | 1816/PD | 06/12/2022 | 30 | M/S SAWDESH ENTERPRISE | 16.77 | 0 | 0 | 100
665 | PURULIA | Purulia Division | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Repairing of damage pipe line including House Connection arrangement for the works related to JICA Assisted West Bengal Pipped Water Supply Project(Purulia) of Satra Water Supply Scheme under Arsha Block. | 1365/PD | 25/07/2024 | 60 | SUBODH PRAMANIK | 5.46 | 0 | 0 | 100
666 | PURULIA | Purulia Mechanical | Augmentation of Satra Water Supply Scheme , SM/09038 | Augmentation | Supply delivery and installation of Centrifugal pumping machineries, floor mounted MCC panel, HOT Crane, Flow meter and other allied works at Satra high Lift (Boosting Station) for Augmentation of Satra Water Supply Scheme under PMD, PHE Dte. in the District of Purulia. | 1190/PMD | 03/11/2023 | 90 | NUPUR CHANDRA HALDER | 43.54 | 0 | 0 | 85
667 | PURULIA | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/08584 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA)for Zone-I, II & Zone-V in different villages of Kumari, Boro-Jaragora, Dighi & Ankro-barakadam G.P. under command area of Manbazar-II Block (Part) Water Supply Scheme at Manbazar-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 243/PD | 10/02/2021 | 75 | ANUP KUMAR SAHA | 285.06 | 152.55 | 53.52 | 92
668 | PURULIA | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/08584 | Retrofitting | Shifting of distribution pipe line including making temporary diversion alone Boro-Jamtara road for construction of house pipe culvert by PW (Road) protectorate of Zone II Manbazar II Block (Part) water supply scheme (Tender No- 20/2021-22 of EE/PD) | BP-2022-23-13 | 07/04/2022 | 0 | PINAKI RANJAN MUKHERJEE | 1.23 | 0 | 0 | 0
669 | PURULIA | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/08584 | Retrofitting | Balance work for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area Zone I, Zone II & Zone V of Manbazar II Block (Part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub- Division, PHE Dte. (Part-I) (Tender No- 162/2022-23 of EE/PD) | BP-2022-23-347 | 30/09/2022 | 0 | ANUP KUMAR SAHA | 28.06 | 0 | 0 | 0
670 | PURULIA | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/08584 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) for Zone- I, Zone- II & Zone- V in different village of Kumari, Boro Jaragora GP, Dighi GP & Ankro Barakadam GP under command area of Manbazar II block (part) water supply scheme of Manabazar II Block under Purulia Sadar Sub- Division, PHE Dte. under Purulia Division, PHE Dte. (Tender No- 34/2021-22 of SE/PMU/WBPWSP) | BP-2022-23-67 | 01/07/2022 | 0 | ANUP KUMAR SAHA | 23.34 | 0 | 0 | 0
671 | PURULIA | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/08584 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Goverment Office ,Health Centre, ICDS Centre,SSK,MSK,Primary School ,High school at different habitation under command area Zone-I, Zone-II & Zone-V of Manbazar II Block (part) Water Supply Scheme ofManbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-I, Part-I) | 510/PSD | 12/08/2022 | 45 | ANUP KUMAR SAHA | 4.8 | 0 | 0 | 70
672 | PURULIA | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/08584 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA)for Zone-III & Zone-IV in different villages of Ankro-barakadam & Boro-Jaragora G.P. under command area of Manbazar-II Block (Part) Water Supply Scheme at Manbazar-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 244/PD | 10/02/2021 | 60 | SADHAN GORAIN | 132.5 | 37.58 | 30.49 | 100
673 | PURULIA | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/08584 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-E : MANBAZAR (Part), BARKURI, BARTOR, BANDUR BERIYA & SHALPARA VILLAGE] | 836/PD | 19/05/2022 | 45 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 43.61 | 0 | 0 | 100
674 | PURULIA | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/08584 | Retrofitting | New Sinking of 1 (One) Nos 200 mm dia river bed vertical tubewell (T/W No.- 1) alongwith necessary 100 mm dia GI collecting line from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Chinakuri ghat under Parbeliya W/S Scheme under Raghunathpur Sub Division, PHE Dte. | 357/RNP | 01/06/2022 | 20 | ASHOK KUMAR CHATTERJEE | 1.76 | 0 | 0 | 100
675 | PURULIA | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/08584 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area Zone-III,Habitation-Ankro,GP- Ankro- Barakadam of Manbazar II Block (part) Water Supply Scheme ofManbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-II, Part-II) (Habitation-Ankro,GP- Ankro- Barakadam ) | 517/PSD | 12/08/2022 | 40 | SADHAN GORAIN | 3.51 | 0 | 0 | 100
676 | PURULIA | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/08584 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Goverment Office,Health Centre, ICDS Centre,SSK,MSK,Primary School ,High school at different habitation under command area Zone-III & Zone-IV of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-I, Part-II) | 511/PSD | 12/08/2022 | 45 | SADHAN GORAIN | 2.43 | 0 | 0 | 100
677 | PURULIA | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/08584 | Retrofitting | Continuation work for Soil Investigation work for proposed WTP at Manbazar-II Block within within Purulia Sadar Sub-Division of Purulia Division P.H.E Dte. | 110/A/PD | 20/01/2023 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 0 | 100
678 | PURULIA | Purulia Division | Retrofitting of Manbazar-II(Part) Water Supply Scheme at Manbazar-II Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/08584 | Retrofitting | Laying of Loop Pipe Line for distribution System under command area Zone-I at different habitation For Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeevan Mission (JJM and JAL SAPNA) of Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte .-FromManikdih mor to Dhanda village Via Tilaboni Mor,)Punda,Govindpur, Tilaboni, Toparbad.) | 537/PD | 12/04/2023 | 45 | MOONLIGHT HOUSE | 29.2 | 0 | 0 | 100
679 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. , SM/10225 | School | Water supply Tap Connection Arrangement for 47 nos School upto 200 Students, 6 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within PARA BLOCK (Part-A) of Purulia District under Purulia Division, PHE Dte. | 434/PD | 21/03/2022 | 45 | PRINCE INDUSTRIES ( INDIA) | 232.18 | 0 | 0 | 0
680 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. , SM/10225 | School | Water supply Tap Connection Arrangement for 30 nos School upto 200 Students, within RAGHUNATHPUR-I Block (Part-B) and 10 nos School upto 200 Students, within PARA BLOCK (Part-C) of Purulia District under Purulia Division, PHE Dte. (Tender No.39/SE/PMU of 2021-22) | BP-2022-23-357 | 30/09/2022 | 0 | ABHIJIT MUKHERJEE | 37.53 | 0 | 0 | 0
681 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. , SM/10225 | School | Water supply Tap Connection Arrangement for 30 nos School upto 200 Students, within RAGHUNATHPUR-I Block (Part-B) and 10 nos School upto 200 Students, within PARA BLOCK (Part-C) of Purulia District under Purulia Division, PHE Dte. | 454/PD | 23/03/2022 | 45 | ABHIJIT MUKHERJEE | 168.37 | 0 | 0 | 100
682 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. , SM/10225 | School | Making Xerox copy of original DPR, Drawing, Mouza Map etc. | 27/2023-149 | 30/05/2023 | 0 | SB CONSTRUCTION | 0.37 | 0 | 0 | 0
683 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. , SM/10225 | School | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewellssinked at various Schools & AWCs of . Raghunathpur-I & Raghunathpur-II Blocks under Purulia Division ,PHE,Dte. | 1740/PD | 04/12/2023 | 30 | TUSHAR KANTI GORAI | 7.5 | 0 | 0 | 0
684 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. , SM/10225 | School | Water supply Tap Connection Arrangement for 45 nos School upto 200 Students, within PARA BLOCK (Part-B) of Purulia District under Purulia Division, PHE Dte. | 453/PD | 23/03/2022 | 45 | GOENKA ENTERPRISE | 189.42 | 0 | 0 | 100
685 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. , SM/10225 | School | Hiring of Euro-4 Diesel can of Ambassador Bharat stage-IV/TATA Indigo e.c.s Bharat Stage-IV/Swift tour Bharat stage -II/BS-III purchased on or after 01.05.2005 with Diesel/LPG/CNG Engine ( Maxi Cab, non-Airconditioned) for site visit of JJM work of 20 Nos. Blocks within Purulia District under RWS purulia Sub Division under Purulia Division PHE Dte. (Part-B) | 430-A/PR | 01/08/2023 | 195 | ANUP KUMAR SAHA | 0.96 | 0 | 0 | 0
686 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. , SM/10225 | School | Hiring of Euro-4 Diesel can of Ambassador Bharat stage-IV/TATA Indigo e.c.s Bharat Stage-IV/Swift tour Bharat stage -II/BS-III purchased on or after 01.05.2005 with Diesel/LPG/CNG Engine ( Maxi Cab, non-Airconditioned) for site visit of JJM work of 20 Nos. Blocks within Purulia District under RWS purulia Sub Division under Purulia Division PHE Dte. (Part-A) | 430/PR | 01/08/2023 | 195 | BOSE CONSTRUCTION | 0.96 | 0 | 0 | 95
687 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 187 nos. under Para & Raghunathpur-I Block In Purulia District under Purulia Division, PHE.Dte. , SM/10225 | School | Continuation work order for Hiring of Euro-4 Diesel can of Ambassador Bharat stage-IV/TATA Indigo e.c.s Bharat Stage-IV/Swift tour Bharat stage -II/BS-III purchased on or after 01.05.2005 with Diesel/LPG/CNG Engine ( Maxi Cab, non-Air conditioned) for site visit of JJM work of 20 Nos. Blocks within Purulia District under RWS purulia Sub Division under Purulia Division PHE Dte. (Part-B) | 56/A/PR | 09/02/2024 | 195 | ANUP KUMAR SAHA | 0.96 | 0 | 0 | 0
688 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Additional work for temporary water supply arrangement through construction of semi Permanent Check Dam along with wing wall by boulder pitching and other allied works at Para W/s Scheme. (Tender No.823/EE/PD of 2019-20) |  | 03/08/2022 | 0 | NANIGOPAL DEY | 4.08 | 0 | 0 | 0
689 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Distribution System with FHTC work (4328 Nos.) of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-II (Tender No.48/22-23/SE/PMU/WBPWSP(P) | BP-2022-23-320 | 29/09/2022 | 0 | NIBHAS SINHA | 120.95 | 0 | 0 | 0
690 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Distribution System with FHTC work (2374 Nos.) of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-I. (Tender No- 79/2022-23 of SE/PMU/WBPWSP(P) ) | BP-2022-23-411 | 28/10/2022 | 0 | MIDNAPUR PIPE CONCERN | 16.62 | 0 | 0 | 0
691 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Installation of 3000 mm dia X 1800 mm 2 Nos. Pressure Shell and Pressure Type Iron Elimination Plant for WTP at Para W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 792/PD | 05/05/2022 | 45 | ANUP KUMAR SAHA | 66.12 | 0 | 0 | 0
692 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Blower Room at Para Water supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 328/RNP | 01/06/2022 | 90 | DEBDAT GANGULY | 4.04 | 0 | 0 | 0
693 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Repairing of Pump House Cum Chlorine Room With Sanitary and Water Supply Arrangement at Tube Well Headwork Site under Para W/S Scheme of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | 329/RNP | 01/06/2022 | 21 | SABYASACHI MISHRA | 1.15 | 0 | 0 | 85
694 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. at Para W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | 339/RNP | 01/06/2022 | 30 | MOYTEC | 1.4 | 0 | 0 | 100
695 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Construction of RCC Clear water reservoir (CWR) of capacity 180 cum / 200 Cum with other allied works at Para Pump House site under Para W/S Scheme within Raghunathpur Sub-Division under Purulia Divisioin, PHE Dte. | 866/PD | 23/05/2022 | 100 | ADITYA HAZRA | 25.24 | 0 | 0 | 100
696 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Distribution System with FHTC work (4328 Nos.) of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-II | 1010/PD | 29/06/2022 | 45 | NIBHAS SINHA | 444.92 | 0 | 0 | 95
697 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Construction of 2 Nos. 3 mtr dia Intake well at Harai river alongwith laying of 100 mm dia G.I. collecting line with all allied works under Para W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | 1926/PD | 22/12/2022 | 90 | M/S KARUNAMOYEE CONSTRUCTION | 14.83 | 0 | 0 | 100
698 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Work for Parrllel Distribution system with FHTC work (4328 Nos.) of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division PHE Dte. Part-II | 997/PD | 26/07/2023 | 60 | NIBHAS SINHA | 95.82 | 0 | 0 | 100
699 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Material Requisition To Resource Division | 959/PD | 20/06/2022 | 0 | Resource Division | 19.57 | 0 | 0 | 0
700 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Material Requisition To Resource Division | 981/PD | 22/06/2022 | 0 | Resource Division | 176.36 | 0 | 0 | 0
701 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Temporary water supply arrangement through construction of semi Permanent Check Dam along with wing wall by boulder pitching and other allied works at Para W/s Scheme. (Tender No.823/EE/PD of 2019-20) | BP-2022-23-171 | 11/08/2022 | 0 | NANIGOPAL DEY | 1.28 | 0 | 0 | 0
702 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Para W/S Scheme, Block- Para) ) to be augmentated/ retrofitting under Purulia Division, PHE Dte. (Tender No- 537/2021-22 of EE/PD) | BP-2022-23-117 | 16/07/2022 | 0 | RADIANT | 6.26 | 0 | 0 | 0
703 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Refreshment bill paid for office meeting to Circuit House. | BP-2023-24-352 | 07/08/2023 | 0 | SHREEMA SWEETS | 0.22 | 0 | 0 | 0
704 | PURULIA | Purulia Mechanical | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | New Connection for Augmentation of para W/S | BP-23-24-151 | 14/09/2023 | 0 | WBSEDCL PURULIA | 7.5 | 0 | 0 | 0
705 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Additional work for temporary water supply arrangement through construction of semi Permanent Check Dam along with wing wall by boulder pitching and other allied works at Para W/s Scheme. (Tender No.233/EE/PD of 2022-23) | BP-2022-23-171 | 11/08/2022 | 0 | NANIGOPAL DEY | 4.08 | 0 | 0 | 0
706 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Repairing of pump house cum chlorine room with sanitary and water supply arrangement at T/W head work site under Para W/s Scheme of Raghunathpur Sub- Division, PHE Dte. [Tender No 215/2022-23 of EE/PD] | BP-2022-23-685 | 01/03/2023 | 0 | SABYASACHI MISHRA | 0.82 | 0 | 0 | 0
707 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Car bill for office purpose against vehicle reg. no.WB-55A/4524 & paid for the month of June to Aug,2022. | BP-2023-24-57 | 04/05/2023 | 0 | ANUP KUMAR SAHA | 1.17 | 0 | 0 | 0
708 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Bill of the IEC programes done in 10 blocks during ARANYA SAPTAHA. | BP-2023-24-414 | 25/08/2023 | 0 | M/S SAYAK BHATTACHARYA | 0.97 | 0 | 0 | 0
709 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Car bill paid for office purpose against Reg. No.WB-55A/7171 paid for the month of Nov & Dec,23. | BP-2023-24-53 | 28/04/2023 | 0 | NIRUPAMA DEY | 0.68 | 0 | 0 | 0
710 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Supply, delivery fitting & fixing of 2 Nos. Scheme Description Sign boards (6' X 3') under Para W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. Location :- (Hariharpur) & Head Work site (Hariharpur Basti) | 23/RNP | 15/01/2024 | 7 | M/S SAYAK BHATTACHARYA | 0.34 | 0 | 0 | 0
711 | PURULIA | Purulia Mechanical | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Supply and installation of PLC panel, Level transmitter, Solar light(OHR Site) with other allied work at para water supply scheme under Purulia Mechanical Division PHE Dte. | 1698/PMD | 06/12/2024 | 90 | KAMAKHYA ENTERPRISE | 15.46 | 0 | 0 | 0
712 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Distribution System with FHTC work (2374 Nos.) of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-I | 1253/PD | 30/08/2022 | 45 | MIDNAPUR PIPE CONCERN | 109.03 | 0 | 0 | 92
713 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Construction of R.C.C. Elevated Reservoir, Capcaity 650 cum, Staging height 20 metre including Bypass arrangement & other allied works for Augmentation of Para W/S Scheme of Raghunathpur Sub-Division under Purulia Division PHE Dte. | 1888/PD | 15/12/2022 | 270 | NIBHAS SINHA | 151.46 | 0 | 0 | 100
714 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Laying of Clear Water Rising Main at Hariharpur area from intake to OHR under Para W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 84/PD | 17/01/2023 | 90 | TAPAN CHANDRA | 38.38 | 0 | 0 | 25
715 | PURULIA | Purulia Mechanical | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Supply delivery and installation of 150 KVA voltage stabilizer for Augmentation of Para water supply scheme under PMD PHE Dte. In the district of Purulia. | 205/PMD | 28/02/2023 | 60 | M/S D. PALIT & CO. | 15.06 | 0 | 0 | 100
716 | PURULIA | Purulia Mechanical | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Para (Pump house site) Water Supply scheme Block Para under PMD PHE Dte. District Purulia | 444/PMD | 20/04/2023 | 30 | MS SAJAHAN CHOWDHURY | 21.63 | 0 | 0 | 100
717 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Construction of Pump House (8 mtr X 7.5 mtr) at Head Work Site under Para W/S Scheme of Raghunathpur Construction Sub-Divn under Purulia Division, P.H.E. Dte. | 832/PD | 26/06/2023 | 90 | GANGULY ENTERPRISES | 23.07 | 0 | 0 | 100
718 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Sinking of 4 (Four) Nos. 200 mm dia DTH rigbored tubewell with other allied works at Dubra OHR campus of Para W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 43/PD | 09/01/2024 | 45 | MANATOSH SINGH | 16.73 | 0 | 0 | 100
719 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Laying distribution System with FHTC work (540Nos.), restoration of concrete road and with allied works of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-II. | 1865/PD | 21/12/2023 | 60 | NIBHAS SINHA | 43.26 | 0 | 0 | 100
720 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Bypass arrangement of Old rising main pipe line (Old OHR site ) to new rising main pipe line and new rising main pipe line to new OHR Inlet and distribution pipe line connection with all allied works of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1520/PD | 27/08/2024 | 45 | TAPAN CHANDRA | 6.63 | 0 | 0 | 100
721 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Restoration of concrete check dam with Ancillary structure as and when needed at Harirampur Intake Site of Para W/S Scheme under Raghunathpur Sub-Division, Under Purulia Division, PHE Dte. | 331/PD | 01/03/2024 | 45 | SAMAN KUMAR MAHATO | 39.52 | 0 | 0 | 100
722 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Connecting line with manifold at two nos Intake to Iron Elevation Plant of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 908/PD | 07/05/2024 | 60 | M/S KARUNAMOYEE CONSTRUCTION | 8.8 | 0 | 0 | 100
723 | PURULIA | Purulia Mechanical | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Supply, Delivery and laying of 185 sq mm XLPE cable at para water supply scheme under PMD PHE Dte. | 1450/PMD | 01/10/2024 | 30 | SUMIT KUMAR CHAKRABORTY | 4.24 | 0 | 0 | 100
724 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Repairing of DI Rising Main & Sinking of 4(Four ) Nos. 200 mm dia DTH rigboredtubewell with 1 H.P. Submersible Pumping Machinary with allied works at Anara Girls' High School, Para S.N. High School, Dubra High School & Anara S.E. Railway Colony High School for Augmentation of Para W/S Scheme of Raghunathpur Sub-Division under Purulia Division PHE Dte | 1098/PD | 07/06/2024 | 60 | M/S SAYAK BHATTACHARYA | 22.57 | 0 | 0 | 100
725 | PURULIA | Purulia Mechanical | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Supply and Delivery and installation intake well cover & allied work at para water supply scheme under PMD PHE Dte. | 1691/PMD | 06/12/2024 | 30 | PINTU DEY | 2.04 | 0 | 0 | 100
726 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Construction of Blower room and Other Allied Works at Para Head work Site of Para Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 2331/PD | 31/12/2024 | 122 | RANI SATI CONSTRUCTION | 4.99 | 0 | 0 | 0
727 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Construction of sump at Pump House of Para head work site under Aug. of Para W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 428/RNP | 12/08/2025 | 7 | GANGULY ENTERPRISES | 0.49 | 0 | 0 | 0
728 | PURULIA | Purulia Mechanical | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, backwash pumping machineries, MCC panel, H.O.T., Flowmwter and other allied works for augmentation of Para water supply scheme under PMD, PHE Dte. In the district of Purulia. | 203/PMD | 28/02/2023 | 60 | RABINDRA NATH KHAN | 76.22 | 0 | 0 | 100
729 | PURULIA | Purulia Mechanical | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Supply, Delivery and installation of submersible pumping machineries into the intake well with allied cable line and other allied works for augmentation of Para w/s scheme under PMD, PHE Dte. in the District of Purulia. | 204/PMD | 28/02/2023 | 60 | PINTU DEY | 10.13 | 0 | 0 | 100
730 | PURULIA | Purulia Mechanical | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Internal and external illumination with other allied works for augmentation of Para water supply scheme under PMD, PHE Dte. In the district of Purulia | 388/PMD | 06/04/2023 | 802 | M/S KARUNAMOYEE CONSTRUCTION | 5.33 | 0 | 0 | 40
731 | PURULIA | Purulia Division | Augmentation of Para W/S Scheme for Providing Functional Household Tap Connection (FHTC) , SM/10718 | Augmentation | Supply, delivery fitting & fixing of 52 Nos. Land Demarcation Sign boards (0.9 m X 0.6 m) under Jal Jeevan Mission at dufferent Location under different W/S Scheme in Hura & Para Block within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 2303/PD | 31/12/2024 | 60 | AMIT PATHAK | 4.75 | 0 | 0 | 100
732 | PURULIA | Purulia Division | Surface water based water supply scheme for Augmentation of BUNDWAN PWSS , SM/15040 | Augmentation | Laying of parallel distribution pipeline to provide FHTC at Supudih Mouza of Bandwan Water Supply Scheme under Purulia Division, PHE Dte . | 285/PD | 27/02/2023 | 45 | BANERJEE CONSTRUCTION | 11.66 | 0 | 0 | 100
733 | PURULIA | Purulia Mechanical | Surface water based water supply scheme for Augmentation of BUNDWAN PWSS , SM/15040 | Augmentation | Arrangement for high pressure testing of SubStation equipment for 250 KVA Sub - Station at Bundwan w/s Scheme under Purulia Mechanical Division,PHE,Dte. | 1016/PMD | 25/06/2024 | 30 | M S ENTERPRISE | 1.19 | 0 | 0 | 100
734 | PURULIA | Purulia Mechanical | Surface water based water supply scheme for Augmentation of BUNDWAN PWSS , SM/15040 | Augmentation | Different Electro-Mechanical works at Sub-Station at Bundwan under Augmentation of Bundwan Water Supply Scheme under Purulia Mechanical Division, PHE, Dte. | 954/PMD | 19/06/2024 | 90 | M S ENTERPRISE | 30.22 | 0 | 0 | 100
735 | PURULIA | Purulia Division | Surface water based water supply scheme for Augmentation of BUNDWAN PWSS , SM/15040 | Augmentation | Survey, Investigation, Planning, Designing (aesthetically), Construction and Commissioning of a Conventional WATER TREATMENT PLANT and rising main of capacity 712 KLD as per BIS/CPHEEO Manual consisting of all Civil, Mechanical and Electrical works (excluding supply and installation of Chlorination arrangements, SCADA, Clear Water Pumps and allied works) including necessary hydraulic testing, structural testing equipment testing, trial run for a period of 3 months, etc. complete as directed by Engineer-in-charge (turn-key job). Cost includes submission of detailed design with drawing (both soft and hard copies) showing all necessary arrangements, structural & hydraulic detail etc. for Augmentation of Bandwan W/S Scheme for source augmentation | 1340/PD | 08/09/2023 | 182 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 260.9 | 0 | 0 | 85
736 | PURULIA | Purulia Division | Surface water based water supply scheme for Augmentation of BUNDWAN PWSS , SM/15040 | Augmentation | Repairing of Baffle Floculator ,Tube Settlor and Construction of Platform of Preasure Filter and Construction of Boundary wall and Repairing of Old Staff Room and other allied works under Hutmura & Bandwan W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | 1364/PD | 25/07/2024 | 240 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 91.07 | 0 | 0 | 50
737 | PURULIA | Purulia Division | Surface water based water supply scheme for Augmentation of BUNDWAN PWSS , SM/15040 | Augmentation | Laying of Distribution Pipeline From Rightgora OHR to Rithugora Village More to Connect DI Pipeline under JJM Work under Bandwan Water Supply Scheme under Purulia Dividion ,PHE Dte | 1048/PD | 17/06/2025 | 45 | BOSE CONSTRUCTION | 4.4 | 0 | 0 | 100
738 | PURULIA | Purulia Division | Surface water based water supply scheme for Augmentation of BUNDWAN PWSS , SM/15040 | Augmentation | Construction of WBSEDCL Room of Bandwan W/S Scheme and and Other allied works under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | 333/PD | 01/03/2024 | 90 | ROY CONSTRUCTION | 6.15 | 0 | 0 | 100
739 | PURULIA | Purulia Division | Surface water based water supply scheme for Augmentation of Bagmundi PWSS , SM/15041 | Augmentation | Route Survey & Drawing Preparation for uncovered areas under BAGHMUNDI Block under Purulia Division, PHE Dte. | 524/PD | 10/04/2023 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 4.16 | 0 | 0 | 100
740 | PURULIA | Purulia Division | Surface water based water supply scheme for Augmentation of Bagmundi PWSS , SM/15041 | Augmentation | Repairing and Renovation of Pump house cum switch room including other allied works at WTP site in connection with Jal Jeevan Mission (JJM) for Augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 1333/PD | 08/09/2023 | 30 | S PATHAK AND CO | 2.89 | 0 | 0 | 100
741 | PURULIA | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Bagmundi PWSS , SM/15041 | Augmentation | Supply, Delivery and installation 60kva voltage stabilizer for Augmentation of Bagmundi w/s scheme for under PMD, PHE Dte. in the District of Purulia. (2 nd Call) | 1205/PMD | 03/11/2023 | 120 | BISHWANATH NANDI | 7.74 | 0 | 0 | 100
742 | PURULIA | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Bagmundi PWSS , SM/15041 | Augmentation | Supply & delivery of electric cable at Bagmundi water supply scheme for Augmentation of Bagmundi PWSS under Purulia Mechanical Division, P.H.E. Dte. | 385/PMSD(W/S) | 17/10/2023 | 15 | SEN BROTHERS | 0.92 | 0 | 0 | 100
743 | PURULIA | Purulia Division | Surface water based water supply scheme for Augmentation of Bagmundi PWSS , SM/15041 | Augmentation | Construction of pathway at OHR Site of Bugmundi W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 332/PD | 01/03/2024 | 45 | ROY CONSTRUCTION | 2.21 | 0 | 0 | 100
744 | PURULIA | Purulia Division | Surface water based water supply scheme for Augmentation of Bagmundi PWSS , SM/15041 | Augmentation | Survey, Investigation, Planning, Designing (aesthetically), Construction and Commissioning of a Conventional WATER TREATMENT PLANT and rising main of capacity 421 KLD as per BIS/CPHEEO Manual consisting of all Civil, Mechanical and Electrical works (excluding supply and installation of Chlorination arrangements, SCADA, Clear Water Pumps and allied works) including necessary hydraulic testing, structural testing equipment testing, trial run for a period of 3 months, etc. complete as directed by Engineer-in-charge (turn-key job). Cost includes submission of detailed design with drawing (both soft and hard copies) showing all necessary arrangements, structural & hydraulic detail etc. for Augmentation of Bagmundi W/S Scheme for source augmentation | 1338/PD | 08/09/2023 | 182 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 227.9 | 0 | 0 | 5
745 | PURULIA | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Bagmundi PWSS , SM/15041 | Augmentation | Supply & fitting fixing of Main switch, valve and other electro-mechanical accessories at WTP site for Augmentation of Bagmundi water supply scheme under Purulia Mechanical Division PHE Dte. | 975/PMD | 20/06/2024 | 60 | SUBRATA DUTTA | 3.98 | 0 | 0 | 100
746 | PURULIA | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Bagmundi PWSS , SM/15041 | Augmentation | Supply, delivery and installation of Centrifugal pumping machinery, Voltage stabilizer with other allied work for direct pumping at OHR site of Augmentation of Bagmundi water supply scheme under Purulia Mechanical Division, PHE Dte. | 1173/PMD | 31/07/2024 | 478 | PINTU DEY | 29.04 | 0 | 0 | 25
747 | PURULIA | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Bathanbari Water Supply scheme Block Neturia under PMD PHE Dte. District Purulia. | 160/PMD | 07/03/2022 | 30 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 20.5 | 0 | 0 | 100
748 | PURULIA | Purulia Division | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Additional work for functional Household Tap Connection (FHTC) including other allied works of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No-935/2021-22 of EE/PD) | BP-2022-23-65 | 24/05/2022 | 0 | KHITISH CHANDRA PATHAK | 4.04 | 0 | 0 | 0
749 | PURULIA | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | SUPPLY DELIVERY & INSTT OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF BATHANBARI WATER SUPPLY SCHEME UNDER PMD PHE DTE.(TR.NO 347 OF 2021-22) | C042211590242 | 08/04/2022 | 0 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 12.27 | 0 | 0 | 0
750 | PURULIA | Purulia Division | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Repairing & renovation of RCC elevated reservoir of capacity 33000 Galon and other allied works under Bathanbari W/ S Scheme under Raghunathpur Sub- Division, PHE dte.(Tender No- 936/2021-22 of EE/PD) | BP-2022-23-103 | 16/07/2022 | 0 | KHITISH CHANDRA PATHAK | 9.76 | 0 | 0 | 0
751 | PURULIA | Purulia Division | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Additional work for functional Household Tap Connection (FHTC) including other allied works of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No.935/EE/PD of 2021-22) | BP-2021-22-300 | 09/03/2022 | 0 | KHITISH CHANDRA PATHAK | 33.31 | 0 | 0 | 0
752 | PURULIA | Purulia Division | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Construction of swtich room cum chlorine Room at OHR site of Bathanbari W/S Scheme within Raghunathpur Sub- Division (Tender No- 828/2021-22 of EE/PD) | BP-2022-23-54 | 19/05/2022 | 0 | KHITISH CHANDRA PATHAK | 4.18 | 0 | 0 | 0
753 | PURULIA | Purulia Division | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Bathanbari Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-A (Mouza- Bathanbari,Bhurkundabari under Gunyarae G.P). (1029 Nos.) | 155/PD | 01/02/2021 | 45 | DEBAKI RANJAN SARKAR | 52.24 | 0 | 0 | 0
754 | PURULIA | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Supply Delivery and installation of Submersible pumping machinery, MCC Panel, Voltage stabilizer, flow meter, ilumination arrangement with allied works for augmentation of Bathanbari PWSS under PMD PHE Dte. | 518/PMD | 05/08/2022 | 60 | COMBINE ENTERPRISES | 46.66 | 0 | 0 | 82
755 | PURULIA | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Supply delivery and installation of fabricated M.S. structure barge with others allied works at Augmentation of Bathanbari w/s scheme under PMD, PHE Dte. in the District of Purulia. | 192/PMSD (W/S) | 22/06/2022 | 21 | COMBINE ENTERPRISES | 4.27 | 0 | 0 | 80
756 | PURULIA | Purulia Division | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Supply of Tender register, HR (Materials) & contractor ledger (Including Printing & Binding complete set). | BP-2023-24-532 | 07/10/2023 | 0 | SOMA PRINTING HOUSE | 0.1 | 0 | 0 | 0
757 | PURULIA | Purulia Division | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Additional work by providing Functional Household Tap Connection (FHTC) and other allied works of Bathanbari W/S Scheme of Neturia Block Raghunathpur Sub- Division, PHE Dte. (Tender No-348/2022-23 of EE/PD) | BP-2022-23-192 | 11/08/2022 | 0 | KHITISH CHANDRA PATHAK | 4.06 | 0 | 0 | 0
758 | PURULIA | Purulia Division | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/4524 bill paid for the month of Sep,22 to June,22. | BP-2023-24-334 | 02/08/2023 | 0 | ANUP KUMAR SAHA | 2.33 | 0 | 0 | 0
759 | PURULIA | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Supply delivery and installation of 1kg/hr gaseous chlorination system of Aug. of Bathanbari water supply scheme.(Tr.no 347 of 2021-22) | C112206903482 | 10/11/2022 | 0 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 3.84 | 0 | 0 | 0
760 | PURULIA | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Supply delivery and installation of 1 kg/hr gaseous chlorination system at Baram High lift for augmentation of Baram Water supply scheme under PMD PHE Dte. District Purulia. | 439/PMD | 11/03/2024 | 60 | PINTU DEY | 25.09 | 0 | 0 | 50
761 | PURULIA | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Execution of the yield test at Joradih GP in Raghunathpur-II Block within the district of Purulia under code SM10250 under PMD, PHE, Dte. | 26/PMSD (Drilling) | 02/02/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0 | 0
762 | PURULIA | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Execution of the yield test at Udyeshpur GP in Para Block within the district of Purulia under code SM10285 under PMD, PHE, Dte. | 24/PMSD (Drilling) | 01/02/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0 | 0
763 | PURULIA | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Execution of the yield test at Dubra, Para GP in Para Block within the district of Purulia under code SM10285 under PMD, PHE, Dte. | 19/PMSD (Drilling) | 31/01/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0 | 0
764 | PURULIA | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Execution of the yield test at Lagda, Dimdiha, Sonaijuri GP in Purulia-I Block within the district of Purulia under code SM10285 under PMD, PHE, Dte. | 23/PMSD (Drilling) | 01/02/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0 | 0
765 | PURULIA | Purulia Division | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Continuation work Order for the work of "Hiring of Ambassador Car / Bolero for the Assistant Engineer, Raghunathpur Sub-Divn, PHE Dte. (w.e.f. 01/01/2023 to 31/12/2023)" | 699/PD | 20/12/2022 | 365 | NIRUPAMA DEY | 1.86 | 0 | 0 | 100
766 | PURULIA | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Supply & delivery of submersible pumping machinery at Bathanbari w/s scheme under PMD, PHE Dte. | 1234/PMD | 08/11/2023 | 15 | COMBINE ENTERPRISES | 0.68 | 0 | 0 | 100
767 | PURULIA | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Supply and delivery of submersible pump motor sets at Bathanbari W/S scheme under PMD P.H.E Dte. in the District of Purulia. | 197/PMD | 16/02/2024 | 15 | PINTU DEY | 0.6 | 0 | 0 | 100
768 | PURULIA | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Supply and delivery of submersible pump motor sets at Bathanbari w/s scheme under PMD, PHE Dte. in the District of Purulia. | 343/PMD | 28/02/2024 | 15 | S PATHAK AND CO | 0.6 | 0 | 0 | 100
769 | PURULIA | Purulia Mechanical | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Supply delivery and installation of Hose pipes and other works at Bathanbari w/s scheme under Purulia Mechanical Division, PHE Dte. in the district Purulia. | 436/PMD | 11/03/2024 | 60 | ANUP KUMAR SAHA | 15.88 | 0 | 0 | 50
770 | PURULIA | Purulia Division | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Xerox copy of original DPR, drawings, mouza map etc for office purpose | BP-2024-25-319 | 20/08/2024 | 0 | DUTTA XEROX CENTRE | 1.45 | 0 | 0 | 0
771 | PURULIA | Purulia Division | Augmentation of Bathanbari W/S Scheme , SM/09211 | Augmentation | Hiring charges of broadband at Assistant Engineer, Purulia Sadar Sub- Division, PHE Office | BP-2024-25-334 | 27/08/2024 | 0 | PURULIA CABLE & BRODBAND PARISEVA | 0.13 | 0 | 0 | 0
772 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. , SM/10227 | School | Water supply Tap Connection Arrangement for 50 nos School upto 200 Students within Kashipur Block (Part -B) and 5 nos School for 200 Students within Saturi Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | 795/PD | 05/05/2022 | 45 | SINGHA ENTERPRISE | 231.61 | 0 | 0 | 0
773 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. , SM/10227 | School | Water supply Tap Connection Arrangement for Sourceless 4 nos School upto 200 Students , 1 nos School for 501-800 Students within PURULIA-I Block ,9 nos School upto 200 Students , 1 nos School for 201-500 Students, 3 nos School for 501-800 Students, , 1 nos School for above 800 Students within PURULIA-II Block, 3 nos School upto 200 Students within NETURIA Block,11 nos School upto 200 Students within KASHIPUR Block, 1 nos School upto 200 Students within RAGHUNTHPUR-I Block, 3 nos School upto 200 Students within RAGHUNTHPUR-II, 2 nos School for 501-800 Students within SANTURI of Purulia District under Purulia Division, PHE Dte. | 555/PD | 06/04/2022 | 45 | JYOTY SOLAR POWER | 164.92 | 0 | 0 | 0
774 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. , SM/10227 | School | Water supply Tap Connection Arrangement for 50 nos School upto 200 Students, 3 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Saturi Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | 796/PD | 05/05/2022 | 45 | PRINCE INDUSTRIES ( INDIA) | 232.09 | 0 | 0 | 0
775 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. , SM/10227 | School | WATER SUPPLY ARRANGEMENT OF KHARAI, PRY. SCHOOL, GHORCHOR PRY. SCHOOL & KOLLOLI PRY. SCHOOL IN KASHIPUR BLOCK OF THE DISTRICT PURULIA UNDER PURULIA DIVISION, PHE. DTE. FOR (ESTIMATE FOR MODEL -1 UPTO 200 STUDENTS). (Tender No- 1025/21-22 of EE/PD) | BP-2022-23-243 | 05/09/2022 | 0 | SUDHANSHU OJHA | 2.9 | 0 | 0 | 0
776 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. , SM/10227 | School | Water supply tap connection arrangement for 4 nos school upto 200 students, 1 nos school for 501-800 students within Purulia-I block, 9 nos School upto 200 Students 1 nos school school for 201-500 students, 3nos school for 501-800 students, 1 nos school for above 800 students within PURULIA-II Block, 3 nos School upto 200 Students within NETURIA Block,11 nos School upto 200 Students within KASHIPUR Block, 1 nos School upto 200 Students within RAGHUNTHPUR-I Block, 3 nos School upto 200 Students within RAGHUNTHPUR-II, 2 nos School for 501-800 Students within SANTURI of Purulia District under Purulia Division, PHE Dte. (Tender No.01/SE/PMU of 2022-23) | BP-2022-23-374 | 19/10/2022 | 0 | JYOTY SOLAR POWER | 16.72 | 0 | 0 | 0
777 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. , SM/10227 | School | ESTIMATE FOR WATER SUPPLY ARRANGEMENT OF KHARAI, PRY. SCHOOL, GHORCHOR PRY. SCHOOL & KOLLOLI PRY. SCHOOL IN KASHIPUR BLOCK OF THE DISTRICT PURULIA UNDER PURULIA DIVISION, PHE. DTE. FOR (ESTIMATE FOR MODEL -1 UPTO 200 STUDENTS). SL NO.04 | 28/PR | 31/01/2022 | 180 | SUDHANSHU OJHA | 3.49 | 0 | 0 | 0
778 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. , SM/10227 | School | ESTIMATE FOR WATER SUPPLY ARRANGEMENT OF RAMJANGAL PR. SCHOOL,MASHILA PR. SCHOOL & MANPURA PR. SCHOOL IN KASHIPUR BLOCK OF THE DISTRICT PURULIA UNDER PURULIA DIVISION, PHE. DTE. FOR (ESTIMATE FOR MODEL -1 UPTO 200 STUDENTS). SL NO.11 | 35/PR | 31/01/2022 | 180 | M/S KARUNAMOYEE CONSTRUCTION | 3.22 | 0 | 0 | 0
779 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. , SM/10227 | School | Daily Operation & Mtc. of Rising Main & all Distribution System, sluice valve, street stand post etc. under Sutabai W/S Scheme under Raghnathpur Sub-Division, P.H.E. Dte. (w.e.f.01.09.2021 to 31.08.2022) | 1082/PD | 31/08/2021 | 365 | ASHOK KUMAR CHATTERJEE | 7.33 | 0 | 0 | 0
780 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. , SM/10227 | School | Water supply Tap Connection Arrangement for 50 nos School upto 200 Students, 3 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Snturi BLOCK (Part-A) of Purulia District under Purulia Division, PHE Dte. (Tender No.30/SE/PMU of 2022-23) | BP-2022-23-267 | 20/09/2022 | 0 | PRINCE INDUSTRIES ( INDIA) | 232.09 | 0 | 0 | 0
781 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. , SM/10227 | School | Water supply Tap Connection Arrangement for Sourceless 4 nos School upto 200 Students , 1 nos School for 501-800 Students within PURULIA-I Block ,9 nos School upto 200 Students , 1 nos School for 201-500 Students, 3 nos School for 501-800 Students, , 1 nos School for above 800 Students within PURULIA-II Block, 3 nos School upto 200 Students within NETURIA Block,11 nos School upto 200 Students within KASHIPUR Block, 1 nos School upto 200 Students within RAGHUNTHPUR-I Block, 3 nos School upto 200 Students within RAGHUNTHPUR-II, 2 nos School for 501-800 Students within SANTURI of Purulia District under Purulia Division, PHE Dte. (Tender No 01/2022-23 of SE/PMU) | BP-2022-23-223 | 29/08/2022 | 0 | JYOTY SOLAR POWER | 146.67 | 0 | 0 | 0
782 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. , SM/10227 | School | Water supply Tap Connection Arrangement for 50 nos School upto 200 Students within Kashipur Block (Part -B) and 5 nos School for 200 Students within Saturi Block (Part-B) of Purulia District under Purulia Division, PHE Dte. (Tender No.) (Tender No.27/22-23 of SE/PMU) | BP-2022-23-228 | 29/08/2022 | 0 | SINGHA ENTERPRISE | 231.61 | 0 | 0 | 0
783 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. , SM/10227 | School | Water supply Tap Connection Arrangement for 36nos school for 201-500 students, 2 no. school for 501-800 students and 2no school avove 800 students within Kashipur Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | 1219/PD | 17/08/2022 | 45 | PRAVAT SARKAR | 202.09 | 0 | 0 | 0
784 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 208 nos. under Kashipur & Santuri Block in Purulia District in Purulia Disision. , SM/10227 | School | Water supply Tap Connection Arrangement for 50 nos school upto 200 students within Kashipur Block (Part - C) of Purulia District under Purulia Division, PHE Dte. | 1251/PD | 30/08/2022 | 45 | PARTHA PRATIM CHHATAIT | 211.38 | 0 | 0 | 100
785 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch Type With solid raft) of capacity 200 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Value & FHTC for period of thirty six (36) month at Zone- XII of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector ) under Purulia Divn. PHE Dte. (SL-8) | 1431/PD | 29/09/2023 | 270 | MD AAMIR KHAN | 552.37 | 0 | 0 | 0
786 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Material Requisition To Resource Division | 1128/PD | 17/08/2023 | 0 | Resource Division | 8279.54 | 0 | 0 | 0
787 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Construction and commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty-six (36) months at Zone-X & XI of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL - 7) | 1369/PD | 14/09/2023 | 995 | ANUP KUMAR SAHA | 854.21 | 0 | 0 | 70
788 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Construction and commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty-six (36) months at Zone-V & VI of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL - 4) | 1367/PD | 14/09/2023 | 675 | ANUP KUMAR SAHA | 647.66 | 0 | 0 | 0
789 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch Type With solid raft) of capacity 150 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Opearation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Value & FHTC for period of thirty six (36) month at Zone- XV of Bandwan Block under Purulia Piped Water Supply Scheme (southern Sector ) under Purulia Divn. PHE Dte. (SL-11) | 1419/PD | 29/09/2023 | 405 | MS D.PALIT AND CO. | 400.45 | 0 | 0 | 10
790 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty-six (36) months at Zone-II of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL-2) | 1421/PD | 29/09/2023 | 540 | MS D.PALIT AND CO. | 478.83 | 0 | 0 | 75
791 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Construction and Commissioning of RCC Over Head Reservoir including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the peroid of thirty six (36) month at Zone- VII & VIII of Bandwan Block under Purulia Piped Water Supply Scheme (southern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL No. 3) | 1430/PD | 29/09/2023 | 1080 | ANUP KUMAR SAHA | 649.84 | 0 | 0 | 55
792 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-VI) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | 902/PD | 07/05/2024 | 60 | AEROSPATIAL SOLUTION PRIVATE LIMITED | 94.42 | 0 | 0 | 0
793 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-X) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | 1073/PD | 07/06/2024 | 60 | SAIKAT RAY | 95.21 | 0 | 0 | 0
794 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | 1053/PMD | 28/06/2024 | 365 | DAS ENTERPRISE | 50.63 | 0 | 0 | 0
795 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | 1054/PMD | 28/06/2024 | 365 | M/S S.G.ENTERPRISE | 31.65 | 0 | 0 | 0
796 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | 1055/PMD | 28/06/2024 | 365 | ANUP KUMAR SAHA | 50.65 | 0 | 0 | 0
797 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Supply Delivery and Installation of Disinfection arrangement and Illumination arrangement for OHR sites, at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | 516/PMD | 15/03/2024 | 365 | GOENKA ENTERPRISE | 258.09 | 0 | 0 | 0
798 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Supply Delivery and Installation of Disinfection arrangement and Illumination arrangement for OHR sites, at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | 517/PMD | 15/03/2024 | 365 | SINHA ELECTRICALS | 206.55 | 0 | 0 | 0
799 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | 480/PMD | 14/03/2024 | 365 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 69.58 | 0 | 0 | 0
800 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | 479/PMD | 14/03/2024 | 365 | SUBRATA DUTTA | 69.61 | 0 | 0 | 0
801 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | 482/PMD | 14/03/2024 | 365 | M/S D.G.B.ENTERPRISE | 39.77 | 0 | 0 | 0
802 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Supply Delivery and Installation of Disinfection arrangement and Illumination arrangement for OHR sites, at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | 515/PMD | 15/03/2024 | 365 | COMBINE ENTERPRISES | 154.79 | 0 | 0 | 0
803 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | 481/PMD | 14/03/2024 | 365 | RABINDRA NATH KHAN | 109.36 | 0 | 0 | 0
804 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | 1056/PMD | 28/06/2024 | 365 | RABINDRA NATH KHAN | 25.32 | 0 | 0 | 0
805 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-V) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte.(Ajodhya Hill Araea) | 1071/PD | 07/06/2024 | 60 | SHREYA ENTERPRISES | 94.55 | 0 | 0 | 0
806 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Balarampur (Zone-I) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | 901/PD | 07/05/2024 | 60 | M/S ANMOL ENGICON | 96.02 | 0 | 0 | 0
807 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-IX) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte.(Ajodhya Hill Area) | 1072/PD | 07/06/2024 | 60 | SAROJ KUMAR SINGH | 96.58 | 0 | 0 | 0
808 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-II, Zone-VIII under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1095/PD | 07/06/2024 | 60 | SUBRATA MAHAPATRA | 25.01 | 0 | 0 | 0
809 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | 1680/PMD | 05/12/2024 | 365 | SUBRATA DUTTA | 3.88 | 0 | 0 | 0
810 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Balarampur (Zone-II) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | 900/PD | 07/05/2024 | 60 | STABILITY INFRASTRUCTURE PVT. LTD. | 96.08 | 0 | 0 | 0
811 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | 1682/PMD | 05/12/2024 | 365 | RABINDRA NATH KHAN | 6.1 | 0 | 0 | 0
812 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | 1683/PMD | 05/12/2024 | 365 | PINTU DEY | 2.22 | 0 | 0 | 0
813 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Supply Delivery and Installation of Disinfection Arrangement and Illumination arrangement for OHR sites, at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte.(2nd Call) | 1740/PMD | 16/12/2024 | 365 | R.N.S. TRADING | 470.76 | 0 | 0 | 0
814 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-II,Zone-II under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | 353/PD | 04/03/2024 | 60 | PRIYATOSH MUKHERJEE | 20.95 | 0 | 0 | 100
815 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Material Requisition To Resource Division | 1979/PD | 18/11/2024 | 0 | Resource Division | 8491.44 | 0 | 0 | 0
816 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Material Requisition To Resource Division | 2254/PD | 19/12/2024 | 0 | Resource Division | 5956.59 | 0 | 0 | 0
817 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Construction and commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty-six (36) months at Zone-III & IV of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL - 3) | 1371/PD | 14/09/2023 | 945 | ANUP KUMAR SAHA | 671.47 | 0 | 0 | 40
818 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty-six (36) months at Zone-XVI of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (SL - 12) | 1368/PD | 14/09/2023 | 995 | ANUP KUMAR SAHA | 449.89 | 0 | 0 | 70
819 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty-six (36) months at Zone-XIII of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Division, PHE Dte. (2nd Call)(SL - 4) | 1370/PD | 14/09/2023 | 1083 | SAMAN KUMAR MAHATO | 184.53 | 0 | 0 | 40
820 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-XIV of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (3rd Call) | 146/PD | 29/01/2024 | 3240 | ANUP KUMAR SAHA | 247.75 | 0 | 0 | 10
821 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-II) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. (Ajodhya Hill Area) | 1065/PD | 07/06/2024 | 360 | VIVEKANANDA CONSTRUCTION | 94.95 | 0 | 0 | 35
822 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-II, Zone-VII under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1367/PD | 25/07/2024 | 30 | KOUSHIK CHATTERJEE | 20.13 | 0 | 0 | 0
823 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Construction of New Boundary wall and other allied works at Manbazar Riversite (Harekishtapur) under Purulia W/S Scheme (Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1077/PD | 07/06/2024 | 60 | CHANDAN CHATTERJEE | 31.23 | 0 | 0 | 0
824 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | 1681/PMD | 05/12/2024 | 365 | S. PATHAK & CO. | 3.88 | 0 | 0 | 0
825 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Hiring of One no. inspection vehicle for Office of the Driller-in-Charge, PMSD (Drilling) under Purulia Mechanical Division PHE Dte. (w.e.f 01/11/24 to 30/04/25) | 473/PMSD(Drilling) | 24/09/2024 | 181 | NUPUR CHANDRA HALDER | 0.86 | 0 | 0 | 0
826 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE - II , SM/18641 | New | Continuation Work Order for "Hiring of One no. inspection vehicle for Office of the Driller-in-Charge, PMSD (Drilling) under Purulia Mechanical Division PHE Dte. (w.e.f 01/05/25 to 28/10/25)" | 76/PMSD(Drilling) | 28/04/2025 | 181 | NUPUR CHANDRA HALDER | 0.86 | 0 | 0 | 0
827 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Sirkabad) | 313/PD | 25/02/2022 | 45 | DEBAKI RANJAN SARKAR | 190.82 | 0 | 0 | 95
828 | PURULIA | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sirkabad Water Supply scheme Block Arsha under PMD PHE Dte. District Purulia. | 167/PMD | 07/03/2022 | 30 | MAHADEV ENTERPRISE | 20.89 | 0 | 0 | 100
829 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System for Augmentation of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte (Mouza-Lachmanpur) (Tender No.915/EE/PD of 2021-22) | BP-2021-22-352 | 28/03/2022 | 0 | HIRAK KUMAR SAO | 17.27 | 0 | 0 | 0
830 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System for Augmentation of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte (Mouza-Lachmanpur) (Tender No.915/EE/PD of 2021-22) | BP-2022-23-407 | 20/10/2022 | 0 | HIRAK KUMAR SAO | 20.64 | 0 | 0 | 0
831 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Sirkabad) (Tender No- 24/SE/PMU of 2021-22) | BP-2021-22-379 | 29/03/2022 | 0 | DEBAKI RANJAN SARKAR | 53.62 | 0 | 0 | 0
832 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Continuation work order for Preparation of DPR (consultancy work) in connection with Functional household Tap Connection of different existing PWSS (Sirkabad W/S Scheme & Puncha W/S Scheme Block- Puncha) to be Augmentation/ Rejuvenation (Tender No- 850/2021-22 of EE/PD) | BP-2021-22-323 | 22/03/2022 | 0 | MRS. R DUTTA & COMPANY | 3.45 | 0 | 0 | 0
833 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System for Augmentation of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Upar jambad) (Tender No.903/EE/PD of 2021-22) | BP-2022-23-17 | 07/04/2022 | 0 | ALOK KUMAR CHAKRABORTY | 18.18 | 0 | 0 | 0
834 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) and supplying & laying of HDPE Pipe for distribution system of Sirkabad Water Supply Scheme of Purulia Sadar Sub- Division, PHE Dte. (Mouza- Upar Jambad) (Tender No- 903/2021-22 of EE/PD) | BP-2022-23-157 | 26/07/2022 | 0 | ALOK KUMAR CHAKRABORTY | 31.29 | 0 | 0 | 0
835 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Aharrah) (Tender No.917/EE/PD of 2021-22) | BP-2021-22-373 | 27/03/2022 | 0 | KANTILAL SAO | 31.64 | 0 | 0 | 0
836 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System for Augmentation of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Upar jambad) | 99/PD | 18/01/2022 | 70 | ALOK KUMAR CHAKRABORTY | 63.49 | 0 | 0 | 85
837 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | New sinking of 2 (Two) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line with all allied works at Sirkabad river site of Sirkabad W/S Scheme under Purulia Division, PHE Dte. | 525/PD | 30/03/2022 | 30 | HIRAK KUMAR SAO | 12.95 | 0 | 0 | 0
838 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Supplying & laying of HDPE pipe for Distribution System for augumentation of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Covered-(Sirkabad Mouza) | 1398/PD | 01/09/2022 | 45 | DEBAKI RANJAN SARKAR | 22.15 | 0 | 0 | 0
839 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Laying of Collecting line from Bandu Riverbed to Sirkabad Pump House of Sirkabad W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 357/PD | 14/03/2023 | 30 | HIRAK KUMAR SAO | 9 | 0 | 0 | 0
840 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System for Augmentation of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte (Mouza-Lachmanpur) | 100/PD | 18/01/2022 | 45 | HIRAK KUMAR SAO | 39.45 | 0 | 0 | 98
841 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Bhelaidih) | 101/PD | 18/01/2022 | 30 | SK MANIR | 13.92 | 0 | 0 | 90
842 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Gandhabazar) | 102/PD | 18/01/2022 | 60 | HIRAK KUMAR SAO | 45.46 | 0 | 0 | 60
843 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | New sinking of 1 (one) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line with all allied works at Sirkabad river site of Sirkabad W/S Scheme under Purulia Division, PHE Dte. | 330/PD | 28/02/2022 | 45 | HIRAK KUMAR SAO | 6.82 | 0 | 0 | 60
844 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Installation of Street light , Laying of Cable trench, and other electrification works at Sirkabad OHR Site Purulia Division, PHE Dte. | 4677/PSD | 27/07/2023 | 15 | CHATTERJEE CONSTRUCTION | 0.96 | 0 | 0 | 100
845 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Laying of underground Cable trench from Sirkabad lab to OHR and Installation of Street light and other allied works at Sirkabad OHR Site Purulia Division, PHE Dte. | 4678/PSD | 27/07/2023 | 15 | CHATTERJEE CONSTRUCTION | 0.85 | 0 | 0 | 100
846 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Material Requisition To Resource Division | 1506/PD | 13/12/2021 | 0 | Resource Division | 65.38 | 0 | 0 | 0
847 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Material Requisition To Resource Division | 397/PD | 11/03/2022 | 0 | Resource Division | 0.76 | 0 | 0 | 0
848 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/7171 bill paid for the month of May,22 to June,22. | BP-2023-24-335 | 02/08/2023 | 0 | NIRUPAMA DEY | 0.68 | 0 | 0 | 0
849 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Continuation work order for the work of vendering service relating to E-return for Income Tax and GST and allied service of Purulia Division, PHE Dte. (w.e.f. 01/10/2022 to 30/09/2023) | BP-2023-24-116 | 22/05/2023 | 0 | NIGAM CONSULTANCY SERVICE | 0.67 | 0 | 0 | 0
850 | PURULIA | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Supply, Delivery and installation of Submersible Pump of river bed tube well, Flowmeter & Water level transmiter with others allied works at Sirkabad w/s scheme under PMD, PHE Dte. in the District of Purulia. | 1572/PMD | 14/11/2024 | 90 | M/S D. PALIT & CO. | 22.94 | 0 | 0 | 0
851 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and supplying & laying of HDPE pipe for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza-Aharrah) | 103/PD | 18/01/2022 | 60 | KANTILAL SAO | 71.76 | 0 | 0 | 100
852 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Sirkabad W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Covered-Bhelaidih,Gandhabazar,Aharrah)) | 1399/PD | 01/09/2022 | 60 | HIRAK KUMAR SAO | 44.91 | 0 | 0 | 100
853 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Construction of Boundary wall at Sirkabad OHR Site under Sirkabad W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 243/PD | 20/02/2023 | 45 | DILIP KUMAR MAHATO | 26.71 | 0 | 0 | 100
854 | PURULIA | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Supply delivery and installation of voltage stabilizer at Sirkabad W/S under PMD PHE dte in the District of Purulia. | 265/PMD | 06/03/2023 | 60 | GOUTAM CHAKRABORTY | 12.75 | 0 | 0 | 75
855 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | New sinking of 07 (Seven) nos. 200 mm dia river bed tubewell (Horizontal) at Kansai river alongwith laying of 100 mm dia G.I. collecting line with all allied works at Sirkabad W/S Scheme under Purulia Division, PHE Dte. | 360/PD | 14/03/2023 | 45 | HIRAK KUMAR SAO | 80.83 | 0 | 0 | 100
856 | PURULIA | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Supply, delivery and installation of Submersible Pump motor and other related works at Sirkabad w/s scheme under Purulia Mechanical Division P.H.E. Dte. | 956/PMD | 19/06/2024 | 90 | RABINDRA NATH KHAN | 3.88 | 0 | 0 | 70
857 | PURULIA | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Yard lighting arrangement with others allied work at Sirkabad water supply scheme (Pump house & OHR site) for Augmentation of Sirkabad PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | 991/PMD | 21/06/2024 | 178 | ASISH KR. SEN | 11.2 | 0 | 0 | 80
858 | PURULIA | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | NEW CONNECTION FOR AUGMENTATION OF SIRKABAD | BP-23-24-249 | 04/01/2024 | 0 | WBSEDCL PURULIA | 7.42 | 0 | 0 | 0
859 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Repairing and renovation of the damaged eleveted water reservoir at Sirkabad OHR Site under Sirkabad W/S Scheme Purulia Sadar Sub Division under Purulia Division , P.H.E. Dte. | 362/PD | 14/03/2023 | 510 | SEKH IRFAN | 10.84 | 0 | 0 | 80
860 | PURULIA | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Supply, Delivery and laying of Cable of river bed tube well with other allied works at Sirkabad w/s scheme under PMD, PHE Dte. in the District of Purulia. | 1438/PMD | 01/10/2024 | 30 | M/S S.G.ENTERPRISE | 2.91 | 0 | 0 | 50
861 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Laying of parallel line & Branch line under command area of Sirkabad Water Supply Scheme of Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Aharrah Mouza) | 286/PD | 27/02/2023 | 500 | KANTILAL SAO | 8.44 | 0 | 0 | 100
862 | PURULIA | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Supply delivery and installation of Centrifugal pumping machineries with necessary substitutes and allied works at Augmentation of SIRKABAD W/S scheme under PMD, PHE Dte. in the District of Purulia. | 263/PMD | 06/03/2023 | 60 | RABINDRA NATH KHAN | 56.33 | 0 | 0 | 70
863 | PURULIA | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Supply and lowering of submersible pump motor sets at newly constructed River Bed Tubewell with supply of necessary substitute at Sirkabad water supply scheme under PMD, PHE Dte. in the District of Purulia | 410/PMD | 10/04/2023 | 632 | M/S S.G.ENTERPRISE | 26.76 | 0 | 0 | 40
864 | PURULIA | Purulia Mechanical | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Supply delivery and installation of Flowmeter at Sirkabad water supply scheme under , PMD, PHE;Dte | 440/PMD | 19/04/2023 | 623 | BISHWANATH NANDI | 4.67 | 0 | 0 | 80
865 | PURULIA | Purulia Division | Augmentatio of Sirkabad PWSS for providing Functional Household Tap Connection (FHTC) , SM/09578 | Augmentation | Repairing of Pump house, Chlorine room, Toilet & Construction of Boundary wall and Other allied works at Sirkabad Riversite Site under Sirkabad W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | 840/PD | 26/06/2023 | 455 | SK ABBAS | 15.07 | 0 | 0 | 100
866 | PURULIA | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Distribution system of Lachhyara Piped Water Supply Scheme of Raghunathpur Sub- Division under Purulia Division, PHE Dte (Tender No- 965/2021-22 of EE/PD) | BP-2022-23-143 | 21/07/2022 | 0 | ASHOK KUMAR CHATTERJEE | 25.34 | 0 | 0 | 0
867 | PURULIA | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Repairing & renovation of existing pump house cum store room & boundary wall of Lachhyara Piped Water Supply Scheme (Tender No- 968/2021-22 of EE/PD) | BP-2022-23-12 | 07/04/2022 | 0 | ASHOK KUMAR CHATTERJEE | 1.12 | 0 | 0 | 0
868 | PURULIA | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Rig Board Tubewell by DTH Method of Lachhiyara piped W/s Scheme. (Tender No.958/EE/PD of 2021-22) | BP-2021-22-362 | 28/03/2022 | 0 | ASHOK KUMAR CHATTERJEE | 16.91 | 0 | 0 | 0
869 | PURULIA | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Distribution System of Lachhyara Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Tender No.965/EE/PD of 2021-22) | BP-2022-23-9 | 05/04/2022 | 0 | ASHOK KUMAR CHATTERJEE | 23.96 | 0 | 0 | 0
870 | PURULIA | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Rig Bored Tubewell by DTH Method of Lachhyara Piped Water Supply Scheme | 34/PD | 05/01/2022 | 45 | ASHOK KUMAR CHATTERJEE | 19.43 | 0 | 0 | 100
871 | PURULIA | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dubra W/S Scheme, Block ¿ Para, & Lachhiyara W/S Schem, Block ¿ Raghunathpur - II) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 357/G/PD | 25/02/2021 | 30 | STEELCONC AND ASSOCIATES | 4.78 | 0 | 0 | 65
872 | PURULIA | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Material Requisition To Resource Division | 391/PD | 11/03/2022 | 0 | Resource Division | 22.76 | 0 | 0 | 0
873 | PURULIA | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Material Requisition To Resource Division | 980/PD | 22/06/2022 | 0 | Resource Division | 45.39 | 0 | 0 | 0
874 | PURULIA | Purulia Mechanical | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Lachayara Water Supply scheme Block Neturia under PMD PHE Dte. District Purulia. | 189/PMD | 14/03/2022 | 1022 | M/S ESTERN INDIA SALES AND SERVICE | 20.62 | 0 | 0 | 80
875 | PURULIA | Purulia Mechanical | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Supply, delivery and installation of Centrifugal pumping machineries, MCC panel with others allied works for Augmentation of Lachiyara w/s scheme under PMD, PHE, Dte. in the District of Purulia. | 91/PMD | 03/02/2023 | 60 | MAHADEV ENTERPRISE | 51.57 | 0 | 0 | 35
876 | PURULIA | Purulia Mechanical | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Supply, Delivery and installation of 60KVA oil cooled voltage stabilizer and allied works for Augmentation of Lachiyara w/s scheme under PMD, PHE, Dte. in the District of Purulia. | 92/PMD | 03/02/2023 | 60 | EMCON | 6.79 | 0 | 0 | 75
877 | PURULIA | Purulia Mechanical | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Supply delivery and installation submersible pumping machineries at new deep tube well and laying of cable line, with others allied works for Augmentation of Lachiyara w/s scheme under PMD, PHE, Dte. in the District of Purulia. | 90/PMD | 03/02/2023 | 708 | KOUSHIK CHATTERJEE | 32.79 | 0 | 0 | 50
878 | PURULIA | Purulia Mechanical | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Supply,delivery and installation of Submersible pumping machineries and Al. Armoured cables for Augmentation of Lachhiyar W/S scheme under PMD Dte .in the District Purulia. | 997/PMD | 21/06/2024 | 60 | M/S UJJAL DIESEL SERVICE | 2.83 | 0 | 0 | 74
879 | PURULIA | Purulia Mechanical | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Supply and installation of 30KVA oil cooled voltage stabilizer(at OLD Pump house) and Double tank dosing system Miscellaneous works at under Lachhiyara W/S Scheme, Purulia Mechanical Division, P.H.E Dte. | 1571/PMD | 14/11/2024 | 60 | TAPAN KUMAR DEY | 6.97 | 0 | 0 | 0
880 | PURULIA | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Construction of Switch Room Cum Chlorine Room of Lachhyara Pipe Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 54/PD | 13/01/2022 | 100 | ASHOK KUMAR CHATTERJEE | 4.89 | 0 | 0 | 100
881 | PURULIA | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Construction of Pump house for accommodating centrifugal pump for pumping of water including Panel room & Chlorination room at Lachhiyara OHR Site of Lachhiyara W/S Scheme under Raghunathpur Sub-Division, Purulia Division, PHE Dte. | 1746/PD | 22/11/2022 | 90 | TOTAL INFRA | 19.83 | 0 | 0 | 100
882 | PURULIA | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Construction of RCC Clear water reservoir (CWR) of capacity 100 Cum with other allied works at Lachhiyara OHR campus of Lachhiyara W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1752/PD | 22/11/2022 | 30 | ASHOK KUMAR CHATTERJEE | 18.32 | 0 | 0 | 100
883 | PURULIA | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Detail Cost Estimate for Over Head Reservoir of capacity 100 cum of Lachhyara Piped Water Supply Scheme of Raghunathpur Sub-Diviasion under Purulia Division, PHE Dte. | 1933/PD | 22/12/2022 | 270 | KM ENTERPRISES | 60.72 | 0 | 0 | 100
884 | PURULIA | Purulia Mechanical | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Yard lighting arrangement with others allied works for Augmentation of Lachiyara w/s scheme under PMD, PHE Dte. in the District of Purulia. (2 nd Call) | 1176/PMD | 03/11/2023 | 60 | MOUSUMI BENERJEE | 5.02 | 0 | 0 | 76
885 | PURULIA | Purulia Mechanical | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Quotation for new connection | BP-23-24-223 | 05/12/2023 | 0 | WBSEDCL PURULIA | 1.87 | 0 | 0 | 0
886 | PURULIA | Purulia Division | Augmentation of Lachhyara Piped Water Supply Scheme , SM/09212 | Augmentation | Distribution System of Lachhyara Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 55/PD | 13/01/2022 | 1234 | ASHOK KUMAR CHATTERJEE | 85.67 | 0 | 0 | 82
887 | PURULIA | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | LOAD ENHANCEMENT APPLICATION FOR CHITMU WATER SUPPLY SCHEME UNDER PMD PHE DTE. | BP-2022-23-39 | 08/09/2022 | 0 | WBSEDCL PURULIA | 1.7 | 0 | 0 | 0
888 | PURULIA | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of augmentation of Chitmu Water Supply Scheme of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Sl no. 1) | BP-2021-22-366 | 29/03/2022 | 0 | MS D.PALIT AND CO. | 19.51 | 0 | 0 | 0
889 | PURULIA | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works at Chitmu W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. (Tender No.873/EE/PD of 2021-22) | BP-2022-23-272 | 21/09/2022 | 0 | BHAGABANDAS KUMAR | 7.79 | 0 | 0 | 0
890 | PURULIA | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of augmentation of Chitmu Water Supply Scheme of Jhalda-I Block under Purulia Sadar Sub- Division, PHE Dte. (Tender No-22/2021-22 of SE/PMU/WBPWSP(P) ) | BP-2022-23-100 | 16/07/2022 | 0 | MS D.PALIT AND CO. | 22.49 | 0 | 0 | 0
891 | PURULIA | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Chitmu W/S Scheme Blalarampur W/s Scheme (Zone-I) Block Jhalda-II & Balarampur) to be Augmented / Rejuvenation under Purulia Division P.H.E. Dte. (Tender No.358/EE/PD of 2021-22) | BP-2021-22-372 | 29/03/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 1.39 | 0 | 0 | 0
892 | PURULIA | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method for Chitmu W/S Schemes under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 20/PMD | 19/01/2022 | 45 | M/S D. PALIT & CO. | 30.6 | 0 | 0 | 0
893 | PURULIA | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Supply delivery and installation of pumping machineries with Allied works at Chitmu w/s scheme under PMD, PHE Dte. in the District of Purulia. | 306/PMD | 06/05/2022 | 30 | RABINDRA NATH KHAN | 35.6 | 0 | 0 | 85
894 | PURULIA | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Repairing of damaged pipe line & Stand post at different location and construction of new stand post at primary school & ICDS center of Chitmu village to supply drinking water under Chitmu Water Supply Scheme of Purulia Sadar Sub-Division, PHE Dte. | 282/PD | 27/02/2023 | 20 | BHAGABANDAS KUMAR | 1.23 | 0 | 0 | 0
895 | PURULIA | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft ) of capacity 100 cum and staging height 20 mtr. with including supply of all labour & materials for Chitmu W/S Scheme under Purulia Sadar Sub-Division, Purulia Division P.H.E Dte. | 1550/PD | 15/12/2021 | 270 | KOUSHIK CHATTERJEE | 43.13 | 0 | 0 | 100
896 | PURULIA | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Additional work for laying 63 mm dia(OD) for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Chitmu mouza under Chitmu Water Supply Scheme of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 439/PSD | 24/06/2022 | 15 | MS D.PALIT AND CO. | 3.31 | 0 | 0 | 95
897 | PURULIA | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Continuation work for Soil Investigation work for proposed 100 M3 capacity Over Head Reservoir of Chitmu W/S Scheme under Purulia Division P.H.E Dte. | 111/PD | 20/01/2023 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 0 | 0
898 | PURULIA | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Material Requisition To Resource Division | 1505/PD | 13/12/2021 | 0 | Resource Division | 10.96 | 0 | 0 | 0
899 | PURULIA | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Material Requisition To Resource Division | 388/PD | 11/03/2022 | 0 | Resource Division | 7.56 | 0 | 0 | 0
900 | PURULIA | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Material Requisition To Resource Division | 616/PMD | 01/06/2023 | 0 | Resource Division | 0.34 | 0 | 0 | 0
901 | PURULIA | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Indian Railways Miscellaneous collection. | BP-2022-23-5174 | 02/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 7.37 | 0 | 0 | 0
902 | PURULIA | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Construction of pump house for accommodating centrifugal pump for pumping of water including panel room & chlorination room from Chitmu Pump House to distribution area through distribution main of Chitmu W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | 1551/PD | 15/12/2021 | 90 | BHAGABANDAS KUMAR | 16.63 | 0 | 0 | 100
903 | PURULIA | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works at Chitmu W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | 1549/PD | 15/12/2021 | 90 | BHAGABANDAS KUMAR | 10.72 | 0 | 0 | 100
904 | PURULIA | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Construction of Boundary wall with other allied works at OHR site of Chitmu W/S Scheme under Purulia Sadar Sub-Division of Purulia Division PHE Dte. | 410/PD | 21/03/2023 | 45 | SAZID HOSSEN ANSARI | 16.07 | 0 | 0 | 100
905 | PURULIA | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Supply delivery and installation of Flowmeter & 50KVA voltage stabilizer and with others allied works at Chitmu water supply scheme under , PMD, PHE;Dte.in the District of Purulia. | 387/PMD | 06/04/2023 | 60 | M/S UJJAL DIESEL SERVICE | 7.49 | 0 | 0 | 100
906 | PURULIA | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Supply, delivery and installation of Centrifugal pumping machineries,, with all ancillaries & auxiliaries including allied works at CWR side pump house at Chitmu Water Supply Scheme,under Purulia Mechanical Division, PHE, Dte. | 394/PMD | 06/04/2023 | 60 | M S ENTERPRISE | 33.26 | 0 | 0 | 100
907 | PURULIA | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Supply delivery and installation of 2 MT capacity HOT Crane with other allied works for Augmentation of Chitmu Water Supply Scheme under PMD, PHE Dte. in the District of Purulia. | 1194/PMD | 03/11/2023 | 60 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 8.27 | 0 | 0 | 100
908 | PURULIA | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Supply, delivery and installation of lighting arrangement at pump house with other allied works for Augmentation of Chitmu w/s scheme under PMD, PHE Dte. in the District of Purulia. | 1150/PMD | 17/10/2023 | 30 | M/S UJJAL DIESEL SERVICE | 4.75 | 0 | 0 | 100
909 | PURULIA | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Supply, delivery and fitting-fixing of ST pole and laying of cable line for Illumination arrangement at pumphouse site with other allied works under Chitmu w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | 377/PMD | 04/03/2024 | 212 | M/S UJJAL DIESEL SERVICE | 5.56 | 0 | 0 | 100
910 | PURULIA | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Supply, delivery and fitting-fixing of MS pipe, valves and dismantling joint at Chitmu W/S scheme under P.M.D. P.H.E Dte. | 72/PMSD(W/S) | 23/02/2024 | 15 | M S ENTERPRISE | 0.94 | 0 | 0 | 100
911 | PURULIA | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Full deposit scheme for Chitmu water pump under Jhalda CCC | BP-2023-24-147 | 15/09/2023 | 0 | WBSEDCL PURULIA | 2.45 | 0 | 0 | 0
912 | PURULIA | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Sinking of 200mmX165mm tubewell with installation of submersible pumping machinery, Cable and other works for Augmentation of Chitmu w/s scheme under PMD, PHE Dte. in the District of Purulia. | 1537/PMD | 11/11/2024 | 60 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 8.74 | 0 | 0 | 40
913 | PURULIA | Purulia Division | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of augmentation of Chitmu Water Supply Scheme of Jhalda-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Sl no. 1) | 284/PD | 17/02/2022 | 774 | MS D.PALIT AND CO. | 140.81 | 0 | 0 | 100
914 | PURULIA | Purulia Mechanical | Augmentation of Chitmu PWSS for providing Functional Household Tap Connection (FHTC) , SM/09216 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Chitmu Water Supply scheme Block Jhalda-II under PMD PHE Dte. District Purulia. | 168/PMD | 07/03/2022 | 30 | CINZANO | 20.5 | 0 | 0 | 100
915 | PURULIA | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Supply delivery and installation of Submersible pumping machineries with all ancillaries & auxiliaries for augmentation of Ajodhya w/s scheme under PMD, PHE Dte. in the District of Purulia. | 520/PMD | 05/08/2022 | 30 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 31.83 | 0 | 0 | 100
916 | PURULIA | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Supply, delivery and installation of Centrifugal pumping machineries,with all ancillaries & auxiliaries including allied works for augmentation of Ajodhya Water Supply Scheme,under Purulia Mechanical Division, PHE, Dte. | 527/PMD | 05/08/2022 | 30 | SWAPAN ENTERPRISE | 9.45 | 0 | 0 | 100
917 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Tap Connection of different existing PWSS (Baghmundi W/S Scheme & Ajodhya W/S Scheme block-Baghmundi) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 361/2021-22 of EE/PD) | BP-2022-23-107 | 16/07/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 2.18 | 0 | 0 | 0
918 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Ajodhya Water Supply Scheme of Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part-I) (Tender No- 921/2021-22 of EE/PD) (Ad- Interim Payment) | BP-2022-23-21 | 07/04/2022 | 0 | TUMPA GORAIN | 5.36 | 0 | 0 | 0
919 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Ajodhya Water Supply Scheme of Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part-I) (Tender No- 921/2021-22 of EE/PD) | BP-2022-23-22 | 07/04/2022 | 0 | TUMPA GORAIN | 2.18 | 0 | 0 | 0
920 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 cum with other allied works at Ajodhya W/s Scheme. (Tender No.859/SE/PMU of 2021-22) | BP-2021-22-346 | 28/03/2022 | 0 | TUMPA GORAIN | 9.64 | 0 | 0 | 0
921 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Supplying and Laying and extention of distribution pipe line for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area of Ajodhya Water Supply Scheme of Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-II) (Tender No- 176/2022-23 of EE/PD) | BP-2022-23-415 | 28/10/2022 | 0 | SADHAN GORAIN | 67.17 | 0 | 0 | 0
922 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Laying of Collecting main Line From TubeWell to Main Rising Main of Ajodhya W/S Scheme At Ajodhya Hill Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 508/PSD | 12/08/2022 | 40 | TUMPA GORAIN | 4.85 | 0 | 0 | 0
923 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | O & M of Marble Lake and Its Adjoining Area W/S Scheme (Except Electro Mechanical component) Of rising main & all distribution system, sluice valve, street stand post etc. under Purulia Division, P.H.E. Dte [For the period of 90 days] | 1753/PD | 22/11/2022 | 90 | ANUP KUMAR SAHA | 1.68 | 0 | 0 | 0
924 | PURULIA | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Ajodhya Water Supply scheme Block Baghmundi under PMD PHE Dte. District Purulia. | 320/PMD | 17/05/2022 | 30 | ALPHA ENTERPRISES | 20.5 | 0 | 0 | 100
925 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Laying of PVC Line For CRPF Camp& Ajodhya Girls Hostel & Shifting of GI Line For Construction New CWR at OHR Campus of Ajodhya W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. | 515/PSD | 12/08/2022 | 45 | TUMPA GORAIN | 1.68 | 0 | 0 | 100
926 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Construction of Tank plateform, parapet wall, repairing & renovation gr floor staff room and sanitary Plumbing work of Ajodhya Bunglow under Ajodhya W/S Scheme of Purulia Sadar Sub-Division, PHE Dte. under JJM & Jal Sapna. | 513/PSD | 12/08/2022 | 45 | TUMPA GORAIN | 2.09 | 0 | 0 | 85
927 | PURULIA | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Electrification and Rectification of lighting arrangement at pump house with other allied works for Augmentation at Ajodhya w/s scheme under PMD, PHE Dte. in the District of Purulia . | 76/PMD | 01/02/2023 | 60 | BISHWANATH NANDI | 5.77 | 0 | 0 | 100
928 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Pushing of 600mm dia RCC pre cast pipe and 100 mm dia GI . water carrier pipe by hydraulic jacking method across Sirkabad-Ajodhya- Baghmundi PWD Road for laying Distribution Main for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) Near Ajodhya OHR site, Bagandi mor and Matakamdi PWD branch Road Junction for Ajodhya W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | 290/PD | 27/02/2023 | 45 | MS GORAIN CONCERN | 19.12 | 0 | 0 | 100
929 | PURULIA | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method for Ajodhya W/S Schemes under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 107/PMD | 28/02/2022 | 30 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 20.4 | 0 | 0 | 100
930 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Supplying hoisting & placing of PVC tank (10000 ltr 2 nos) over MS structural OHR and other allied work at Ajodhya OHR site of Ajodhya W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | 870/PD | 30/06/2023 | 30 | SARKAR ENTERPRISE | 2.43 | 0 | 0 | 100
931 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Construction of tank platform, parapet wall, repairing & renovation Ground floor staff and sanitary plumbing work of Ajodhya Bunglow under Ajodhya W/S Scheme of Purulia Sadar Sub- Division, PHE Dte. under JJM & Jalswapna [Tender No 550/2022-2023 of EE/PD] | BP-2022-23-834 | 27/03/2023 | 0 | TUMPA GORAIN | 1.63 | 0 | 0 | 0
932 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/7171 bill paid for the month of May,22 to June,22. | BP-2023-24-335 | 02/08/2023 | 0 | NIRUPAMA DEY | 0.68 | 0 | 0 | 0
933 | PURULIA | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Supply delivery and installation of submersible pumping machinery for Direct Pumping with Flow meter for Augmentation of Ajodhya w/s scheme under PMD, PHE Dte. in the District of Purulia | 903/PMD | 04/08/2023 | 30 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 7.54 | 0 | 0 | 90
934 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Laying of dedicated distribution line for providing FHTC at kotalmara habitation, bursabera habitation & chhatni habitation under Augmentation of Ajodhya water supply scheme under Purulia Division, PHE Dte. | 1712/PD | 04/12/2023 | 60 | TUMPA GORAIN | 31.22 | 0 | 0 | 100
935 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | New Construction of Boundary wall & Repairing of DI Rising Main at Ajodhya Pump House Site under Purulia Sadar Sub-Division under Purulia Division,PHE Dte. | 97/PD | 15/01/2024 | 426 | BOSE CONSTRUCTION | 15.05 | 0 | 0 | 40
936 | PURULIA | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Supply, delivery and installation of Open well Submersible pumping machinery, MCC Panel with others electro-mechanical work at Manbazar Baludih for Augmentation of Manbazar PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | 970/PMD | 20/06/2024 | 60 | M/S D. PALIT & CO. | 11.74 | 0 | 0 | 0
937 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Ajodhya Water Supply Scheme of Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Part-I) | 44/PD | 07/01/2022 | 45 | TUMPA GORAIN | 18.54 | 0 | 0 | 100
938 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Supplying and Layingand extention of distribution pipe line for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area of Ajodhya Water Supply Scheme of Baghmundi Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-II) | 43/PD | 07/01/2022 | 60 | SADHAN GORAIN | 92.36 | 0 | 0 | 100
939 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Providing FHTC at Kalafulia village under Ajodhya water supply scheme under Purulia Division, PHE Dte. | 4856/PSD | 29/09/2023 | 10 | MOUSUMI BANERJEE | 1 | 0 | 0 | 100
940 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Extention of distribution line for providing FHTC at Sitakunda to Bagandih&Kuchlirakha habitation under Ajodhya water supply scheme under Purulia Division, PHE Dte. | 1829/PD | 12/12/2023 | 60 | TUMPA GORAIN | 11.01 | 0 | 0 | 100
941 | PURULIA | Purulia Division | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Laying of distribution pipeline from Gobria to Puniasashan & providing FHTC at Puniasashan & Churingsarang village & other allied works at Ajodhya water supply scheme under Purulia Division, PHE Dte. | 1803/PD | 08/12/2023 | 60 | ANUDIP SAHA | 12.87 | 0 | 0 | 100
942 | PURULIA | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Construction of Big Dia R.B.T.W (200 mm × 165 mm) at Ajodhya Hill top of Bagmundi block in Purulia district under Purulia Mechanical Division PHE, Dte. | 437/PMD | 11/03/2024 | 30 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 14.57 | 0 | 0 | 90
943 | PURULIA | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Construction of Rig Bore tubewell (200mm x 165 mm) by DTH method at Ajodhya for Ajodhya PWSS under Purulia Mechanical Division, P.H.Engineering Dte. in the District of Purulia. | 1692/PMD | 06/12/2024 | 30 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 2.94 | 0 | 0 | 90
944 | PURULIA | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Supply, delivery and installation of Voltage stabilizer with other allied work at low lift P/H no. 3 & 4 of Augmentation of Ajodhya water supply scheme under Purulia Mechanical Division PHE Dte. | 1540/PMD | 11/11/2024 | 176 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 5.42 | 0 | 0 | 80
945 | PURULIA | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Supply, delivery and installation of Submersible pumping machinery with other allied work at Newly sunk T/W of Augmentation of Ajodhya water supply scheme under Purulia Mechanical Division PHE Dte. | 1437/PMD | 01/10/2024 | 214 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 11.87 | 0 | 0 | 90
946 | PURULIA | Purulia Mechanical | Augmentation of Ajodhya PWSS for providing Functional Household Tap Connection (FHTC , SM/09217 | Augmentation | Indoor & outdoor illumination arrangement with others electro-mechanical work at Ajodhya water supply scheme (Low lift) for Augmentation of Ajodhya PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | 1224/PMD | 13/08/2024 | 264 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 6.95 | 0 | 0 | 30
947 | PURULIA | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Supplying & laying different dia HDPE pipe line from Barrah Shiv Mandir to Borkha Village under Rangamati Village. (Tender No.1005/EE/PD of 2021-22) | BP-2021-22-375 | 29/03/2022 | 0 | MANATOSH SINGH | 14.39 | 0 | 0 | 0
948 | PURULIA | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. (Tender No.906/EE/PD of 2021-22) | BP-2021-22-297 | 09/03/2022 | 0 | SANTANU BANERJEE | 2.49 | 0 | 0 | 0
949 | PURULIA | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. (Tender No.906/EE/PD of 2021-22) (Ad-interim) | BP-2021-22-275 | 03/03/2022 | 0 | SANTANU BANERJEE | 16 | 0 | 0 | 0
950 | PURULIA | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well with allied cable line and other allied works for augmentation of Rangamati w/s scheme under PMD, PHE Dte. in the District of Purulia. | 262/PMD | 06/03/2023 | 60 | NUPUR CHANDRA HALDER | 8.54 | 0 | 0 | 0
951 | PURULIA | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Laying of distribution pipe line ( 110 mm & 90 mm dia HDPE pipe ) from Bankati Siv Mandir to Dejuri - Shyambathan More in connection with FHTC under Rangamati W/S Scheme of Raghunathpur Sub-Divn, P.H.E. Dte. | 548/PD | 12/04/2023 | 30 | M/S. DESTINY CONSTRUCTION | 7.19 | 0 | 0 | 0
952 | PURULIA | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Construction of Guard Room cum store at OHR Campus under Rangamati W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 106/PD | 18/01/2022 | 100 | CHANCHAL MISHRA | 5.86 | 0 | 0 | 98
953 | PURULIA | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 250 cum at Barrah under Rangamati W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 107/PD | 18/01/2022 | 60 | MANATOSH SINGH | 5.27 | 0 | 0 | 90
954 | PURULIA | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | New sinking of 4 (Four) nos. 200 mm dia river bed tubewell (Horizontal) at Darakeshwar river alongwith laying of 100 mm dia G.I. collecting line with all allied works under Rangamati W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | 380/PD | 11/03/2022 | 60 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 29.49 | 0 | 0 | 100
955 | PURULIA | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Construction of Guard Room cum store at Pump House Campus under Rangamati W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 381/PD | 11/03/2022 | 100 | CHANCHAL MISHRA | 5.94 | 0 | 0 | 0
956 | PURULIA | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Rangamatia Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | 395/PMD | 16/06/2022 | 30 | MS EMMESS | 20.5 | 0 | 0 | 100
957 | PURULIA | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Material Requisition To Resource Division | 965/PD | 21/06/2022 | 0 | Resource Division | 18.28 | 0 | 0 | 0
958 | PURULIA | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Construction of Guard Room cum store at OHR Campus under Rangamati W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Tender No.889/EE/PD of 2021-22) | BP-2022-23-342 | 29/09/2022 | 0 | CHANCHAL MISHRA | 5.48 | 0 | 0 | 0
959 | PURULIA | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | NEW CONNECTION FOR AUGMENTATION OF RANGAMATI WATER SUPPLY SCHEME |  | 28/02/2023 | 0 | WBSEDCL PURULIA | 4.21 | 0 | 0 | 0
960 | PURULIA | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | New sinking of 04 (Four) No. 200 mm dia river bed tube well horizontal at Darakeswar river along with laying of 100 mm dia GI collecting with all allied works under Rangamati Water Supply Scheme under Raghunathpur Sub- division, PHE Dte. (Tender No- 11/2022-23 of EE/PD) | BP-2022-23-102 | 16/07/2022 | 0 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 8.56 | 0 | 0 | 0
961 | PURULIA | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Supplying & laying different dia HDPE pipe line from Barrah Siv Mandir to Bankati village under Rangamati W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 105/PD | 18/01/2022 | 45 | MANATOSH SINGH | 22.36 | 0 | 0 | 100
962 | PURULIA | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Supply delivery and installation of 100KVA voltage stabilizer for Augmentation of Rangamati water supply scheme under Purulia Mechanical Division PHE, Dte. in the District of Purulia | 339/PMD | 24/03/2023 | 60 | SANTU MITRA | 10.39 | 0 | 0 | 100
963 | PURULIA | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Internal external illumination with other allied works for Augmentation of Rangamati Water Supply Scheme under PMD, PHE Dte. in the District of Purulia. | 1195/PMD | 03/11/2023 | 60 | SANTU MITRA | 6.37 | 0 | 0 | 100
964 | PURULIA | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Additional work for supply delivery and laying of submersible cable with jointing kit for newly constructed river bed tube well for augmentation of Rangamati water supply scheme under PMD, PHE Dte. in the district of Purulia. | 335/PMSD(W/S) | 11/09/2023 | 15 | NUPUR CHANDRA HALDER | 0.89 | 0 | 0 | 100
965 | PURULIA | Purulia Division | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Providing Functional Household Tap Connection (FHTC) including other allied works of Rangamati Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1833/PD | 12/12/2023 | 60 | BOSE CONSTRUCTION | 4.23 | 0 | 0 | 100
966 | PURULIA | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Supply, delivery and laying of cable line at Rangamati water supply scheme under PMD, PHE Dte. | 106/PMSD(W/S) | 05/03/2024 | 7 | SANTU MITRA | 0.74 | 0 | 0 | 100
967 | PURULIA | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | New Connection for Augmentation of Rangamati water supply Scheme | BP-23-24-203 | 17/10/2023 | 0 | WBSEDCL PURULIA | 4.21 | 0 | 0 | 0
968 | PURULIA | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Supply, Delivery and installation of submersible pumping machineries into the existing CWR and in River bed Tube Well with allied cable line and other allied works for augmentation of Rangamati w/s scheme under PMD, PHE Dte. in the District of Purulia. | 1294/PMD | 30/08/2024 | 397 | M/S A.D. CONCERN | 10 | 0 | 0 | 50
969 | PURULIA | Purulia Mechanical | Augmentation of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. , SM/09582 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmwter and other allied works for augmentation of Rangamati water supply scheme under PMD, PHE Dte. In the district of Purulia. | 261/PMD | 06/03/2023 | 60 | NUPUR CHANDRA HALDER | 46.44 | 0 | 0 | 72
970 | PURULIA | Purulia Division | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | Installation of 3 (Three) nos. 1.00 H.P. capacity Solar Photovoltaic Submersible Pump set in pre-existing / new bore Tube well along with 1200 Watt peak capacity Solar photovoltaic array panels on steel structure including Supply & Delivery of approved quality materials & Geophysical investigation by electrologging with all allied works at different places within Neturia Block in Purulia District of Raghunathpur Sub-Division under Purulia Division, PHE Dte.[Phase-iii][Group-E] | 365/PD | 14/03/2023 | 45 | ASHOK KUMAR CHATTERJEE | 30.01 | 0 | 0 | 0
971 | PURULIA | Purulia Division | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | Construction of Guard Room cum store at Pump House Campus under Parbeliya W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 66/PD | 17/01/2022 | 100 | M/S SHYAMASHREE ENTERPRISE | 5.2 | 0 | 0 | 100
972 | PURULIA | Purulia Division | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | Repairing and renovation of Pump House at River Side under Parbeylia W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 712/RNP | 23/12/2022 | 15 | AMIT PATHAK | 1 | 0 | 0 | 0
973 | PURULIA | Purulia Division | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | Construction of Switch Room Cum Chlorin Room at CWR Site of Parbeliya W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 45/PD | 09/01/2023 | 100 | M/S KARUNAMOYEE CONSTRUCTION | 4.86 | 0 | 0 | 100
974 | PURULIA | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 85 KVA AT 0.4 KV TO 119/119/119/119/119 KVA RESPECTIVELY AT 0.4 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o , EX ENGG PMD PHE DTE(CONSUMER ID : 932416100) TO THEIR PREMISES AT PARBELIYA WATER SUPPLY SARBARI NETURIA DIST PURULIA UNDER REGIONAL OFFICE PURULIA | BP-22-23-86 | 28/02/2023 | 0 | WBSEDCL PURULIA | 1.98 | 0 | 0 | 0
975 | PURULIA | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | Supply, delivery & installation of MCC Panel at Parbelia w/s scheme under PMD, PHE Dte. | 354/PMD | 29/02/2024 | 300 | SUBAL SARKAR | 0.64 | 0 | 0 | 100
976 | PURULIA | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Parbeliya Water Supply scheme Block Neturia under PMD PHE Dte. District Purulia. | 321/PMD | 17/05/2022 | 30 | MS SAJAHAN CHOWDHURY | 20.49 | 0 | 0 | 100
977 | PURULIA | Purulia Division | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | New Sinking of 1 (One) Nos 200 mm dia river bed vertical tubewell (T/W No.- 1) alongwith necessary 100 mm dia GI collecting line from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Chinakuri ghat under Parbeliya W/S Scheme under Raghunathpur Sub Division, PHE Dte. | 357/RNP | 01/06/2022 | 20 | ASHOK KUMAR CHATTERJEE | 1.76 | 0 | 0 | 100
978 | PURULIA | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | Supply delivery & installation of Electromagnetic flow meter and with others allied works for Augmentation of Parbeliya w/s scheme (Low lift & High lift) under Purulia Mechanical Division, PHE, Dte. in the Purulia District. | 254/PMD | 06/03/2023 | 60 | BISHWANATH NANDI | 6.91 | 0 | 0 | 100
979 | PURULIA | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | Supply, Delivery and installation of 50KVA oil cooled voltage stabilizer and allied works for Augmentation of Parbeliya w/s scheme (Low lift) under PMD, PHE Dte. in the District of Purulia | 588/PMD | 23/05/2023 | 60 | M/S A.D. CONCERN | 5.88 | 0 | 0 | 100
980 | PURULIA | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | Internal illumination of pump house room with others allied works for Augmentation of Parbeliya w/s scheme (Low lift & High lift) under PMD, PHE Dte. in the District of Purulia. | 647/PMD | 08/06/2023 | 60 | GOLAP KR. GHOSH | 1.46 | 0 | 0 | 100
981 | PURULIA | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | External and internal illumination of OHR site,High lift and low lift site of Parbeliya water supply scheme and Flood light at Low lift site for Augmentation work under Purulia Mechanical Division ,PHE Dte .in the District Purulia. | 962/PMD | 20/06/2024 | 90 | MOON LIGHT HOUSE | 8.27 | 0 | 0 | 100
982 | PURULIA | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | Supply, delivery of Submersible pumping machineries for Parbeliya W/S scheme under PMD P.H.E Dte. in the District Purulia. | 196/PMD | 16/02/2024 | 15 | M/S A.D. CONCERN | 0.59 | 0 | 0 | 100
983 | PURULIA | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | Supply, delivery & installation of Dewatering submersible pump set at Parbelia w/s scheme under PMD, PHE Dte. | 344/PMD | 28/02/2024 | 15 | M/S R.K. ENTERPRISE | 0.55 | 0 | 0 | 100
984 | PURULIA | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | Supply delivery and installation of 500 ltr UPVC tank and pipe line for eye shower for augmentation of Parbeliya High lift water supply scheme under Purulia Mechanical Division, P.H.E Dte. in the District Purulia. | 195/PMD | 16/02/2024 | 10 | MS SAJAHAN CHOWDHURY | 0.37 | 0 | 0 | 100
985 | PURULIA | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | New power connection at Parbeliya PWSS OHR Campus(Reference M.B.NO MB/0000210/2023-2024) | BP-23-24-300 | 05/03/2024 | 0 | WBSEDCL PURULIA | 0.11 | 0 | 0 | 0
986 | PURULIA | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | Sub: Enhancement of the contract demand from 85 KVA at 0.4 KV to 119/119/119/119/119 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o-THE EXE. ENGG, PMD, P.H.E DTE., PURULIA, SITE- PHE PERBELIA W/S under Purulia Regional Office. (1) Application No.- L000005249. (2) Consumer Id.- 932416100 | BP-23-24-339 | 27/03/2024 | 0 | WBSEDCL PURULIA | 6.85 | 0 | 0 | 0
987 | PURULIA | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | Supply delivery and installation of 40 KVA voltage stabilizer for augmentation of Parbeliya High lift water supply scheme under Purulia Mechanical Division ,PHE Dte .in the District Purulia. | 1293/PMD | 30/08/2024 | 182 | AVISHEK ENTERPRISE | 5.97 | 0 | 0 | 100
988 | PURULIA | Purulia Mechanical | Augmentation of Parbeliya Water Supply Scheme at Neturia Block under Purulia Division, PHE Dte. , SM/09583 | Augmentation | Supply, Delivery and installation of submersible pumps motor sets with other allied works for Parbeliya w/s scheme (Low lift) under PMD, PHE Dte. in the District of Purulia. | 437/PMD | 19/04/2023 | 60 | KOUSHIK CHATTERJEE | 12.04 | 0 | 0 | 100
989 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of Drilling Materials for Hard Rock formation Drilling for sinking of RBTW in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. Dist: Bankura. | 950/BMD | 29/07/2022 | 30 | SUDIP ENGINEERING CO | 17.87 | 0 | 0 | 0
990 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and delivery of different types of Drilling Materials for sinking of 200mm x165mm DTH type RBTW by Departmental Rig of B.M.S.D (D) in Balarampur Block in the Distric of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 851/BMD | 05/07/2022 | 30 | M/S NABIN GOPAL SENGUPTA | 36.79 | 0 | 0 | 0
991 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of DTH drilling tools at Bankura Mechanical Division for different Rig unit in over burden range for sinking of 200mmX165mm RBTW in connection to JJM programme. in the district Purulia under PHE Dte | 852/BMD | 05/07/2022 | 30 | CHAKRABORTY MAINING & ENGINEERING. | 14.3 | 0 | 0 | 0
992 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of 4 1/2 "(114 mm approx) x 10 ' long Drill Tube for 7D Drilling Rig Machine of BMSD(D), for sinking of RBTW in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 949/BMD | 29/07/2022 | 30 | AHALYA ENGINEERING WORKS | 24.34 | 0 | 0 | 0
993 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Providing Hired skilled Labour for construction of R.B.T.WIn the district of Purulia in connection to JJM Programme by Rig unit 7D/others under B.M.D, P.H.E Dte . | 311/BMSD(D) | 13/05/2022 | 30 | SUTRADHAR TRADERS | 0.94 | 0 | 0 | 0
994 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply & Delivery of UPVC Casing and others for sinking of 200mm x 165mm DTH type RBTW by KLR Rig at B.M.S.D (D) under B.M.D. P.H.E. Dte. in connection to JJM Program. | 154/BMSD(D) | 24/03/2022 | 15 | M/S DAS & SARKAR ENTERPRISE | 4.25 | 0 | 0 | 0
995 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of 150Amh , 180Amh and 100 Amh Batteries for different Rig and respective Supporting Vehicles at B.M.S.D(D), under B.M.D, P.H.E Dte in connection to JJM Programme. | 257/BMSD(D) | 22/04/2022 | 10 | SUTRADHAR TRADERS | 0.81 | 0 | 0 | 0
996 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM Programme in Purulia District by Rig unit KLR at B.M.S.D(D) under B.M.D, P.H.E Dte . | 366/BMSD(D) | 31/05/2022 | 14 | BASUDEV DEY | 0.75 | 0 | 0 | 0
997 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Gerua G.P of Balarampur Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1383/BMD | 23/11/2022 | 15 | SINGHA ENTERPRISE | 63.66 | 0 | 0 | 0
998 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of Drilling Accessories and others for sinking of 200mmX165mm DTH type RBTW by 7D Rig at B.M.S.D(D) under B.M.D, P.H.E Dte in connection to JJM programme. | 153/BMSD(D) | 24/03/2022 | 15 | UNICON | 4.25 | 0 | 0 | 0
999 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of different fast moving spares for compressor of KLR Rig vehicle in connection to JJM programme at B.M.S.D(D) under B.M.D, P.H.E Dte | 439/BMSD(D) | 13/06/2022 | 20 | M/S SWAPAN BANERJEE | 1.66 | 0 | 0 | 0
1000 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Providing man power engagement for construction of R.B.T.W in connection to JJM Programme in Purulia District by Rig unit KLR at B.M.S.D(D) under B.M.D, P.H.E Dte . | 431/BMSD(D) | 10/06/2022 | 108 | CHAKRABORTY MAINING & ENGINEERING. | 3.39 | 0 | 0 | 0
1001 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and delivery of 4 ½¿ (114 mm approx.) x 10¿ long Drill Tube for 7D Drilling Rig Machine at BMSD (D), under B.M.D. P.H.E. Dte. in connection to JJM Program. | 152/BMSD(D) | 24/03/2022 | 10 | CHAKRABORTY MAINING & ENGINEERING. | 4.86 | 0 | 0 | 0
1002 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of DTH drilling tools (Bit) for KLR Rig in over burden range for sinking of 200mmX165mm RBTW at B.M.S.D(D) under B.M.D, P.H.E Dte in connection to JJM programme. | 178/BMSD(D) | 31/03/2022 | 10 | SUDIP ENGINEERING CO | 0.94 | 0 | 0 | 0
1003 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of DTH drilling tools (Hammer) for KLR Rig in over burden range for sinking of 200mmX165mm RBTW at B.M.S.D(D) under B.M.D, P.H.E Dte in connection to JJM programme. | 179/BMSD(D) | 31/03/2022 | 10 | SUDIP ENGINEERING CO | 0.98 | 0 | 0 | 0
1004 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Darda, Ghatbera & Gerua G.P of Balarampur Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1208/BMD | 23/09/2022 | 15 | SUNRISE ENGINEERING CORPORATION | 64.87 | 0 | 0 | 0
1005 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Ghatbera G.P of Balarampur Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1209/BMD | 23/09/2022 | 15 | M/S D. PALIT AND CO. | 93.51 | 0 | 0 | 0
1006 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Providing Hired Driver and man power engagement for construction of R.B.T.W in connection to JJM Programme in Purulia District by Rig unit 7D at B.M.S.D(D) under B.M.D, P.H.E Dte . | 435/BMSD(D) | 13/06/2022 | 108 | PRADIP KUMAR DHABAL | 2.94 | 0 | 0 | 0
1007 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Providing Hired Driver(WB37D 8040) for construction of R.B.T.WIn the district of Purulia in connection to JJM Programme by Rig unit 7D/others under B.M.D, P.H.E Dte | 310/BMSD(D) | 13/05/2022 | 30 | SUTRADHAR TRADERS | 0.82 | 0 | 0 | 0
1008 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Submission of bill in connection with work of sinking Tube well in AWC Balarampur Block. |  | 16/12/2022 | 0 | M/S SHANKAR AUTO SERVICE | 3.96 | 0 | 0 | 0
1009 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Submission of bill in connection with work of sinking Tube Well in Purulia District related to JJm work. |  | 13/10/2022 | 0 | M/S NABIN GOPAL SENGUPTA | 36.79 | 0 | 0 | 0
1010 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Submission of bill in connection with work of sinking Tube well in Purulia District related to JJM work. |  | 13/10/2022 | 0 | M/S SHANKAR AUTO SERVICE | 28.78 | 0 | 0 | 0
1011 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Submission of bill in connection with work of sinking Tube Well in Purulia District related to JJm work. |  | 13/10/2022 | 0 | CHAKRABORTY MINING AND ENGINEERING | 32.18 | 0 | 0 | 0
1012 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Submission of bill in connection with the work of rising of Tube Well under Balarampur W/s Scheme in Purulia District. |  | 27/07/2022 | 0 | LALJI RAJA AND SONS | 10.79 | 0 | 0 | 0
1013 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | FHTC Connetion for Anganwari Balarampur W/s Scheme. |  | 18/07/2022 | 0 | SADHAN GORAIN | 27 | 0 | 0 | 0
1014 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Submission of bill in connection with work of sinking Tube Well in Purulia District related to JJm work. | BP-2022-23-369 | 30/09/2022 | 0 | M/S SHANKAR AUTO SERVICE | 10.27 | 0 | 0 | 0
1015 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Balarampur Block (Part-K) of Purulia District under Purulia Division, PHE Dte. | 492/PD | 29/03/2022 | 45 | SADHAN GORAIN | 70.98 | 0 | 0 | 0
1016 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Balarampur Block (Part-L) of Purulia District under Purulia Division, PHE Dte. | 493/PD | 29/03/2022 | 45 | SADHAN GORAIN | 70.98 | 0 | 0 | 0
1017 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Balarampur Block (Part-P),2 nos Awc Within Balarampur block (Part-Q) & 2nos AWC within Balarampur Block (Part-R) of Purulia District under Purulia Division, PHE Dte. | 1854/PD | 13/12/2022 | 45 | PRATIK SAHA | 57.83 | 0 | 0 | 50
1018 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Acceptance cum Formal work order for the work of Repairing of Yard lighting at BMD office premises & Store for keeping different martials under JJM Program under Bankura Mechanical Division P.H.E. Dte. | 1652/BMSD | 28/12/2022 | 10 | M/S NABIN GOPAL SENGUPTA | 0.97 | 0 | 0 | 0
1019 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Balarampur Block (Part-O) of Purulia District under Purulia Division, PHE Dte. | 496/PD | 29/03/2022 | 45 | SEN BROTHERS | 23.44 | 0 | 0 | 0
1020 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Balarampur Block (Part-N) of Purulia District under Purulia Division, PHE Dte. | 495/PD | 29/03/2022 | 45 | BOSE CONSTRUCTION | 23.57 | 0 | 0 | 0
1021 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Installation of Big-Dia D.T.H. Tube Well (200mm x 165mm) by Robotic DTH Rigs for drilling upto 1200 ft or small form factor trolly mounted rig with trolly mounted compressor suitable for narrow 68 inch wide roads considering 200mt Depth in diferent Schools of different Blocks (PHASE-2) of the District Purulia under Purulia RWS Sub Division,PHE Dte. under Purulia Division, PHE Dte. | 1755/PD | 22/11/2022 | 45 | S N POLYMERS PVT LTD | 96.12 | 0 | 0 | 0
1022 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Balarampur Block (Part-M) of Purulia District under Purulia Division, PHE Dte. | 494/PD | 29/03/2022 | 45 | GOENKA ENTERPRISE | 47.32 | 0 | 0 | 0
1023 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Installation of Big-Dia Odex-165 (Simultaneous driving of casing pipe) 165 mm dia Tube Well considering 120mt Depth in diferent schools, AWC of different blocks of the District Purulia under Purulia RWS Sub Division,PHE Dte. under Purulia Division, PHE Dte. | 1520/PD | 16/10/2023 | 60 | S N POLYMERS PVT LTD | 94.53 | 0 | 0 | 100
1024 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Supply of Fuel & lubricant bill for AWC Balarampur Block. | BP-2022-23-848 | 31/03/2023 | 0 | M/S SHANKAR AUTO SERVICE | 5.78 | 0 | 0 | 0
1025 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Submission of bill in connection with the work of sinking of Tube well in Purulia District related to JJM work. | BP-2022-23-161 | 05/08/2022 | 0 | LALJI RAJA AND SONS | 6.89 | 0 | 0 | 0
1026 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Fuel bill in connection with work of sinking tube well in Purulia District related to JJM work | BP-2022-23-500 | 22/12/2022 | 0 | LALJI RAJA AND SONS | 3.96 | 0 | 0 | 0
1027 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | SUPPLY AND DELIVERY OF DTH DRILLING TOOLS AT BANKURA MECHACINCAL DIVISION FOR DIFFERENT RIG UNIT IN OVER BURDEN RANGE FOR SINKING OF 200MM X 165MM RBTW IN CONNECTION WITH JJM PROGRAMME IN THE DISTRICT OF PURULIA UNDER PHE DTE. [TENDER NO-166/2022-2023 OF EE/BMD] | BP-2022-23-481 | 16/12/2022 | 0 | CHAKRABORTY MINING AND ENGINEERING | 14.3 | 0 | 0 | 0
1028 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | SUPPLY AND DELIVERY OF DRILLING MATERIALS FOR HARD ROCK FORMATION DRILLING FOR SINKING OF RBTW IN THE DISTRICT OF PURULIA IN CONNECTION WITH JJM PROGRAMME UNDER BANKURA MECHACINCAL DIVISION, PHE DTE. [TENDER NO-179/2022-2023 OF EE/BMD] | BP-2022-23-482 | 16/12/2022 | 0 | SUDIP ENGINEERING CO, | 17.87 | 0 | 0 | 0
1029 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Submission of bill in connection with work of sinking Tube well in Purulia District related to JJM work. | BP-2022-23-162 | 05/08/2022 | 0 | LALJI RAJA AND SONS | 3.9 | 0 | 0 | 0
1030 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Proposal for laying of water pipeline along NH-32 in the stretches -i) from Km 114.979 to Km 119.324 (RHS), ii) from Km 111.800 to Km 116.200 (LHS), iii) from Km 111.800 to Km 112.844 (RHS) & vross NH-32 at Km 112.844, Dist- Purulia, West Bengal. | BP-2022-23-477 | 09/01/2023 | 0 | NATIONAL HIGHWAY AUTHOTITY OF INDIA (NHAI) | 5.34 | 0 | 0 | 0
1031 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | SUPPLY AND DELIVERY OF DIFFERENT TYPES OF DRILLING MATERIALS FOR SINKING OF 200MM X 165 MM DTH TYPE RBTW BY DEPARTMENTAL RIG OF B.M.S.D (D) UNDER BMD PHE DTE. IN BALARAMPUR BLOCK IN THE DISTRICT OF PURULIA IN CONNECTION WITH JJM PROGRAMME UNDER BANKURA MECHACINCAL DIVISION, PHE DTE. [TENDER NO-24/2022-2023 OF EE/BMD] | BP-2022-23-485 | 16/12/2022 | 0 | M/S NABIN GOPAL SENGUPTA | 36.79 | 0 | 0 | 0
1032 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | SUPPLY AND DELIVERY OF 4 1/2 "(114 MM APPROX) X 10 LONG DRILL TUBE FOR 7D DRILLING RIG MACHINE OF BMSD(D) FOR SINKING OF RBTW IN THE DISTRICT OF PURULIA IN CONNECTION TO JJM PROGRAM UNDER BANKURA MECHANICAL DIVISION, PHE DTE. [TENDER NO-189/2022-2023 OF EE/BMD] | BP-2022-23-486 | 22/12/2022 | 0 | AHALYA ENGINEERING WORKS | 24.34 | 0 | 0 | 0
1033 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10282 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Balarampur Block (Part_C) of Purulia District under Purulia Division, PHE Dte.(Phase-I) | 1121/PD | 25/07/2022 | 1023 | JYOTY SOLAR POWER | 90.73 | 0 | 0 | 100
1034 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Repairing of Pipeline at Sirishgora road due to damage of Pipeline near New Culvert and Bandwan Bazar under Bandwan W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No- 434/2022-23 of EE/PD) | BP-2022-23-395 | 28/10/2022 | 0 | BOSE CONSTRUCTION | 0.92 | 0 | 0 | 0
1035 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub- Division, PHE Dte. (Sirisgora Mouza) (Tender No- 998/2021-22 of EE/PD) | BP-2022-23-155 | 26/07/2022 | 0 | ANUP KUMAR SAHA | 55.85 | 0 | 0 | 0
1036 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Water supply arrangement of schools model-2 (201-500 students) at Bandwan Pry. School under Bandwan Block under RWS Purulia Sub- Division, PHE Dte. (Tender No- 1021/2021-22 of EE/PD) | BP-2022-23-148 | 25/07/2022 | 0 | KABERI DUTTA | 0.98 | 0 | 0 | 0
1037 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub- Division, PHE Dte. (Pargela Mouza) (Tender No- 1002/2021-22 of EE/PD) | BP-2022-23-156 | 26/07/2022 | 0 | BOSE CONSTRUCTION | 19.67 | 0 | 0 | 0
1038 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Laying of G.I Pipeline and other allied works at Galudih Road near Culvert under Bandwan W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No- 410/2022-23 of EE/PD) | BP-2022-23-396 | 20/10/2022 | 0 | ROY CONSTRUCTION | 1.07 | 0 | 0 | 0
1039 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Various ICDS Centre and Schools and Supply of drinking water through water tanker to various places from nearby headwork sites of different W/S Scheme to mitigate draught like situation under Bandwan Block block of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 169/PSD | 18/04/2022 | 25 | BOSE CONSTRUCTION | 1.68 | 0 | 0 | 0
1040 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Laying of distribution pipe line at Sirishgora Mouza under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | 18111/PD | 06/12/2022 | 45 | ANUP KUMAR SAHA | 13.22 | 0 | 0 | 0
1041 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Supplying delivery fitting& fixing 20 nos of Sign board (ACP Sheet)at different solar tubewell site within Bandwan Block in Purulia District under Purulia Division, PHE Dte. | 251/PSD | 31/03/2023 | 5 | R.K ENTERPRISE | 0.48 | 0 | 0 | 0
1042 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Installation of 3000 mm dia x 1800 mm Pressure shell for WTP at Bandwan W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(2 Nos) | 58/PD | 13/01/2022 | 60 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 23.8 | 0 | 0 | 100
1043 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Installation of 3000 mm dia x 1800 mm (3 & 4 nos) Pressure filter shell for WTP under Augumentation of Bandwan W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(2 Nos) | 523/PD | 30/03/2022 | 60 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 23.63 | 0 | 0 | 100
1044 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Repairing of Pipeline at Sirishgora road due to damage of Pipeline near New Culvert and Bandwan Bazar under Bandwan W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 441/PSD | 24/06/2022 | 10 | BOSE CONSTRUCTION | 1.26 | 0 | 0 | 80
1045 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Laying of G.I Pipeline and other allied works at Galudih Road near Culvert under Bandwan W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 443/PSD | 24/06/2022 | 15 | ROY CONSTRUCTION | 1.07 | 0 | 0 | 100
1046 | PURULIA | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Replacement of H.L. Centrifugal pump with allied motor as needed at 950 KLD water treatment plant, Bundwan under PMD,PHE, Dte, in the district of Purulia. | 403/PMD | 17/06/2022 | 30 | RABINDRA NATH KHAN | 9.19 | 0 | 0 | 100
1047 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Augmentation of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Rithugora Mouza)Bardih Village,Jordih Village & Kodogora Village | 1806/PD | 06/12/2022 | 45 | BOSE CONSTRUCTION | 11.49 | 0 | 0 | 25
1048 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Laying of distribution pipe line at Sirishgora Mouza under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | 1811/PD | 06/12/2022 | 45 | ANUP KUMAR SAHA | 13.22 | 0 | 0 | 100
1049 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Repairing and renovation of the damaged eleveted water reservoir at Bandwan OHR Site under Bandwan W/S Scheme Purulia Sadar Sub Division under Purulia Division , P.H.E. Dte. | 1736/PD | 22/11/2022 | 45 | SUJIT CHAKRABORTY | 6.15 | 0 | 0 | 100
1050 | PURULIA | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Supply and Delivery of different gaseous chlorine spare parts for Bandwan and other water supply schemes under PMD PHE Dte. | 125/PMD | 16/02/2023 | 30 | RABINDRA NATH KHAN | 10.82 | 0 | 0 | 100
1051 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Supplying delivery fitting& fixing 30 nos of Sign board (ACP Sheet)at different solar tubewell site within Bandwan Block in Purulia District under Purulia Division, PHE Dte. | 250/PSD | 31/03/2023 | 5 | R.K ENTERPRISE | 0.72 | 0 | 0 | 100
1052 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Construction of RCC Clear water reservoir (CWR) of capacity 250 Cum with other allied works at WTP campus of Bandwan W/S scheme under Purulia Sadar Sub-Division, PHE Dte. | 632/PD | 22/04/2022 | 100 | WRISHI ENTERPRISE | 28.1 | 0 | 0 | 0
1053 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Material Requisition To Resource Division | 390/PD | 11/03/2022 | 0 | Resource Division | 37.05 | 0 | 0 | 0
1054 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Material Requisition To Resource Division | 1015/PD | 05/07/2022 | 0 | Resource Division | 225.01 | 0 | 0 | 0
1055 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Material Requisition To Resource Division | 239/PD | 20/02/2023 | 0 | Resource Division | 228.79 | 0 | 0 | 0
1056 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub- Division, PHE Dte. (Jitan Mouza) Jitan village (Tender No- 1035/2021-22 of EE/PD) | BP-2022-23-70 | 01/07/2022 | 0 | ROY CONSTRUCTION | 7.17 | 0 | 0 | 0
1057 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Bandwan W/S Scheme & Bandwan Spot W/S Scheme block-Bandwan) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 536/2021-22 of EE/PD) | BP-2022-23-90 | 07/07/2022 | 0 | RADIANT | 1.26 | 0 | 0 | 0
1058 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Regarding laying of water supply pipe line along road side and road crossing on i) Manbazar-Bandwan-Kuilapal Road ii) Barabazar-Bandwan Road iii) Bandwan-Ashanpani Road in respect of Augmentation of bandwan water supply scheme in the District of Purulia. | BP-2022-23-662 | 23/02/2023 | 0 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 139.71 | 0 | 0 | 0
1059 | PURULIA | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 85 KVA AT 0.4 KV TO 245/245/245/245/245 KVA RESPECTIVELY AT 11 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o , EX ENGG PMD PHE DTE(CONSUMER ID : 942408200) TO THEIR PREMISES AT BUNDWAN WATER SUPPLY DIST PURULIA UNDER REGIONAL OFFICE PURULIA | BP-22-23-84 | 28/02/2023 | 0 | WBSEDCL PURULIA | 9.31 | 0 | 0 | 0
1060 | PURULIA | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | FOR NEW SERVICE CONNECTION OF AUGMENTATION OF BUNDWAN WATER SUPPLY SCHEME |  | 28/02/2023 | 0 | WBSEDCL PURULIA | 0.71 | 0 | 0 | 0
1061 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub- Division, PHE Dte. (Jitan Mouza) Bamandiha village (from node J-851 to J-864) Part- B (Tender No- 55/2022-23 of EE/PD) | BP-2022-23-88 | 07/07/2022 | 0 | CHATTERJEE CONSTRUCTION | 2.47 | 0 | 0 | 0
1062 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub- Division, PHE Dte. (Jitan Mouza) Bamandiha village [from node J-846 to J-851 Part A] (Tender No- 32/2022-23 of EE/PD) | BP-2022-23-82 | 01/07/2022 | 0 | CHATTERJEE CONSTRUCTION | 2.43 | 0 | 0 | 0
1063 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Refreshment bill paid for office meeting. | BP-2023-24-368 | 10/08/2023 | 0 | MATHUR DUTTA | 0.12 | 0 | 0 | 0
1064 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Office stationary bill payment. | BP-2023-24-150 | 30/05/2023 | 0 | KETIKA CONSUMERS CO-OP STORES LTD | 1.47 | 0 | 0 | 0
1065 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/7171 bill paid for the month of May,22 to June,22. | BP-2023-24-335 | 02/08/2023 | 0 | NIRUPAMA DEY | 0.68 | 0 | 0 | 0
1066 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Sirishgora Mouza) | 335/PD | 28/02/2022 | 90 | ANUP KUMAR SAHA | 95.06 | 0 | 0 | 85
1067 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Rithugora Mouza) | 333/PD | 28/02/2022 | 60 | BOSE CONSTRUCTION | 51.38 | 0 | 0 | 80
1068 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Jitan Mouza)Bamandiha Village(From node J-851 to J-864)(Part-B) | 150/PSD | 04/04/2022 | 25 | CHATTERJEE CONSTRUCTION | 4.59 | 0 | 0 | 100
1069 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Jitan Mouza)Jitan Village | 334/PD | 28/02/2022 | 30 | ROY CONSTRUCTION | 18.56 | 0 | 0 | 100
1070 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Jitan Mouza)Bamandiha Village(From node J-846 to J-851)(Part-A) | 98/PSD | 14/03/2022 | 25 | CHATTERJEE CONSTRUCTION | 4.56 | 0 | 0 | 100
1071 | PURULIA | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Providing internal and external illumination arrangement at existing at Intake pump house, clear water, chemical house building, substation building, OHR site Chorination room for Augmentation of Bandwan PWSS under PMD, PHE Dte. in the District of Purulia. | 547/PMD | 18/08/2022 | 30 | ASHOKE ADHIKARY | 8.91 | 0 | 0 | 90
1072 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Construction of Over Head reservoir (OHR) of capacity 350 Cum with other allied works of Bandwan W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 1890/PD | 15/12/2022 | 270 | PRAVAT SARKAR | 118.62 | 0 | 0 | 100
1073 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Chilla Mouza) | 633/PD | 22/04/2022 | 60 | BOSE CONSTRUCTION | 96.26 | 0 | 0 | 100
1074 | PURULIA | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Sinking of 200mmX165mm tubewell and other allied works at Bandwan spot water supply scheme Purulia,under PMD, PHE Dte. in the District of Purulia. | 1179/PMD | 03/11/2023 | 15 | SAIBAL SARKAR | 7.13 | 0 | 0 | 100
1075 | PURULIA | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Augmentation of existing old VCB by the new one(one incoming two outgoing) and installation of one new transformer for augmentation of Bandwan PWSS under PMD, PHE Dte. in the District of Purulia. | 537/pmd | 17/08/2022 | 60 | M/S M S ENTERPRISE | 66.56 | 0 | 0 | 100
1076 | PURULIA | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | SHIFTING OF ENERGY METER FROM EXISTING METER ROOM TO ANOTHER METER ROOM AT AUG OF BUNDWAN WATER SUPPLY SCHEME UNDER PMD PHE DTE. | C072325293658 | 14/07/2023 | 0 | WBSEDCL PURULIA | 0.26 | 0 | 0 | 0
1077 | PURULIA | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Additional Quotation for PHE Connection at Chilla. | BP-23-24-270 | 22/01/2024 | 0 | WBSEDCL PURULIA | 4.02 | 0 | 0 | 0
1078 | PURULIA | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | LOAD ENHANCEMENT FOR AUG OF BUNDWAN WS SCHEME | BP-2023-24-201 | 17/10/2023 | 0 | WBSEDCL PURULIA | 0.71 | 0 | 0 | 0
1079 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Supudih Mouza) | 937/PD | 16/06/2022 | 1294 | SANTANU BANERJEE | 120.63 | 0 | 0 | 65
1080 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Laying of Main line and Parallel line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Bandwan Mouza) | 295/PD | 27/02/2023 | 45 | DEBAKI RANJAN SARKAR | 67.69 | 0 | 0 | 30
1081 | PURULIA | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Supply delivery and installation of Flowmeter for augmentation of Bandwan PWSS under PMD, PHE Dte. in the District of Purulia. | 526/PMD | 05/08/2022 | 911 | SUBRATA DUTTA | 8.02 | 0 | 0 | 100
1082 | PURULIA | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Supply delivery and installation of centrifugal pumping machineries with necessary allied works at intake for augmentation of Bandwan w/s project under PMD, PHE Dte. in the District of Purulia. | 522/PMD | 05/08/2022 | 1214 | TAPAN KUMAR DEY | 27.3 | 0 | 0 | 65
1083 | PURULIA | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Supply delivery and installation of centrifugal pumping machineries with necessary substitutes with allied works for augmentation of Bandwan PWSS under PMD, PHE Dte. in the District of Purulia. | 523/PMD | 05/08/2022 | 60 | RABINDRA NATH KHAN | 88.94 | 0 | 0 | 65
1084 | PURULIA | Purulia Mechanical | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Bandwan Water Supply scheme (OHR site) Block Bandwan under PMD PHE Dte. District Purulia. | 394/PMD | 16/06/2022 | 1020 | S P CONSTRUCTION | 20.5 | 0 | 0 | 100
1085 | PURULIA | Purulia Division | Augmentation of Bundwan PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10198 | Augmentation | Continuation work order for Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.01.2024 to 30.06.2024). | 1887/PD | 29/12/2023 | 183 | ARUNALOY SCIENTIFIC HOUSE | 3.98 | 0 | 0 | 100
1086 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Manbazar-II Block (Part-G) of Purulia District under Purulia Division, PHE Dte. (Tender No- 204/2022-23 of EE/PD) | BP-2022-23-258 | 14/09/2022 | 0 | KOUSHIK CHATTERJEE | 13.82 | 0 | 0 | 0
1087 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10279 | Anganwadi | Water supply tap connection arrangement for 3 nos. AWC within Manbazar-II block (Part-I) of Purulia District under Purulia Division, PHE Dte. (Tender No- 206/2022-23 of EE/PD) | BP-2022-23-265 | 20/09/2022 | 0 | SOUVIK MANDAL | 17.41 | 0 | 0 | 0
1088 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Manbazar-II Block (Part-E) of Purulia District under Purulia Division, PHE Dte. | 741/PD | 02/05/2022 | 45 | SANTANU BANERJEE | 71.2 | 0 | 0 | 0
1089 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within MANBAZAR-II Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | 1862/PD | 13/12/2022 | 45 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 99.14 | 0 | 0 | 0
1090 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 62 nos AWC within Manbazar-II Block ) of Purulia District under Purulia Division, PHE Dte. | 81/PD | 17/01/2023 | 45 | RAJAT KARMAKAR | 34.46 | 0 | 0 | 0
1091 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Manbazar-II Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | 743/PD | 02/05/2022 | 45 | SOUVIK MANDAL | 23.7 | 0 | 0 | 0
1092 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 3 no AWC within Manbazar-II Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | 744/PD | 02/05/2022 | 45 | KM ENTERPRISES | 23.69 | 0 | 0 | 0
1093 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Manbazar-II Block (Part-O) & 1 no AWC within Manbazar-II Block (Part-Q)of Purulia District under Purulia Division, PHE Dte.(Phase-III) | 1714/PD | 22/11/2022 | 45 | M DHARA & BROTHERS | 82.94 | 0 | 0 | 100
1094 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Manbazar-II Block (Part-C) of Purulia District under Purulia Division, PHE Dte.(Phase-I) | 1712/PD | 22/11/2022 | 45 | ANUP KUMAR SAHA | 91.32 | 0 | 0 | 100
1095 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10279 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 6 nos AWC within Manbazar-II Block (Part-P) of Purulia District under Purulia Division, PHE Dte.(Phase-IV)" | 1715/PD | 22/11/2022 | 45 | PRIYATOSH MUKHERJEE | 50.05 | 0 | 0 | 100
1096 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Balarampur Block (Part-F), 4 nos AWC within Balarampur Block (Part-E) & 2 nos AWC within Balarampur Block (Part-G) of Purulia District under Purulia Division, PHE Dte.(Phase-IV) | 1124/PD | 25/07/2022 | 45 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 81.58 | 0 | 0 | 69
1097 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Manbazar-II Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | 742/PD | 02/05/2022 | 45 | KOUSHIK CHATTERJEE | 47.27 | 0 | 0 | 100
1098 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 22 nos AWC within Manbazar-II Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | 1160/PD | 01/08/2022 | 45 | EQUIPMENTS AND SPARES AGENCIES | 174.17 | 0 | 0 | 100
1099 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Manbazar-II Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | 1161/PD | 01/08/2022 | 45 | EQUIPMENTS AND SPARES AGENCIES | 197.92 | 0 | 0 | 100
1100 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10279 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 2 nos AWC within Manbazar-II Block (Part-K), 2 nos AWC within Manbazar-II Block (Part-L) & 1 nos AWC within Manbazar-II Block (Part-M) & & 1 nos AWC within Manbazar-II Block (Part-N)of Purulia District under Purulia Division, PHE Dte." | 1732/PD | 22/11/2022 | 45 | KM ENTERPRISES | 28.34 | 0 | 0 | 100
1101 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos)under Manbazar-II & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10279 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Manbazar-II Block (Part-D) of Purulia District under Purulia Division, PHE Dte.(Phase-II) | 1713/PD | 22/11/2022 | 783 | EQUIPMENTS AND SPARES AGENCIES | 91.76 | 0 | 0 | 85
1102 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No- 185/2022-23 of EE/PD) | BP-2022-23-372 | 19/10/2022 | 0 | SUDHANSHU OJHA | 6.8 | 0 | 0 | 0
1103 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-B) (Tender No- 404/2022-23 of EE/PD) | BP-2022-23-403 | 20/10/2022 | 0 | SUPRIYA MAHANTI MISHRA | 8.44 | 0 | 0 | 0
1104 | PURULIA | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Bongabari(Zone-III) Water Supply scheme Block Kashipur under Purulia Mechanical Division PHE. Dte. in the District of Purulia | 217/PMD | 28/02/2023 | 30 | COMBINE ENTERPRISES | 21.61 | 0 | 0 | 0
1105 | PURULIA | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Supply, Delivery and installation 75kva voltage stabilizer for Augmentation of Bongabari w/s scheme(Zone-II) for under PMD, PHE Dte. in the District of Purulia. | 239/PMD | 03/03/2023 | 60 | MOUSUMI BENERJEE | 8.01 | 0 | 0 | 15
1106 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Repairing, renovation & restoration of Pump House with Panel room including roof treatment at Namo Pindra River site of Bongabari W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | 660/PD | 17/05/2023 | 60 | SABYASACHI MISHRA | 4.19 | 0 | 0 | 0
1107 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Laying of HDPE pipe as distribution main (loop line) from Surulia Road Side Hari Mandir to Surulia Shiv Mandir in Surulia village for drinking water supply through FHTC to met up the water crisis at Uppar Surulia Village from existing Bongabari W/S scheme under Jalswapna Programme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 94/PSD | 14/03/2022 | 15 | SOUVIK MANDAL | 4.6 | 0 | 0 | 100
1108 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-B) | 645/PD | 22/04/2022 | 45 | SUPRIYA MAHANTI MISHRA | 10.98 | 0 | 0 | 80
1109 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Uppar Pindra Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 648/PD | 22/04/2022 | 45 | KABERI DUTTA | 9.84 | 0 | 0 | 100
1110 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Surulia Village Bauri Para of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1390/PD | 01/09/2022 | 45 | SOUVIK MANDAL | 23.21 | 0 | 0 | 100
1111 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Construction of Temporary Car Shed near guest house under JJM / Jalswanpa under Purulia Division, PHE Dte. | 1723/PD | 22/11/2022 | 45 | BOSE CONSTRUCTION | 4.99 | 0 | 0 | 100
1112 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Repairing and Restoration of damaged 125 mm dia pipe line at bongabari near Club to Bangabari more & Rest shed to Jack pushing point and 75 mm dia from Hatuara Firm main gate to DIET-II Campus and 100mm dia GI pipe road Crossing near Surulia more for Surulia Bauri Para of Purulia-II Block area to drinking water supply under Bongabari Water Supply Scheme of Purulia Sadar Sub-Division, PHE Dte. | 1737/PD | 22/11/2022 | 45 | SADHAN GORAIN | 5.7 | 0 | 0 | 100
1113 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Uppar Pindra Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 505/PD | 31/03/2023 | 45 | KABERI DUTTA | 2.92 | 0 | 0 | 100
1114 | PURULIA | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Material Requisition To Resource Division | 611/PMD | 01/06/2023 | 0 | Resource Division | 1.03 | 0 | 0 | 0
1115 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Hatuara Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1392/PD | 01/09/2022 | 1218 | GLAMOUROOMS UNEMPLOYED CO-OPERATIVE SOCIETY LTD. | 45 | 0 | 0 | 90
1116 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Palashkola and Gopalpur Mouza of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1724/PD | 22/11/2022 | 1136 | GLAMOUROOMS UNEMPLOYED CO-OPERATIVE SOCIETY LTD. | 54.03 | 0 | 0 | 90
1117 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village including extention of distribution pipe line (Gap Portion) of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 284/PD | 27/02/2023 | 45 | SIDDHARTHA SANKAR SARKAR | 23 | 0 | 0 | 100
1118 | PURULIA | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Bongabari w/s scheme(River Site) under PMD, PHE Dte. in the District of Purulia. | 238/PMD | 03/03/2023 | 60 | COMBINE ENTERPRISES | 77.44 | 0 | 0 | 15
1119 | PURULIA | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation at Bongabari w/s scheme(Zone-II) under PMD, PHE Dte. in the District of Purulia | 309/PMD | 16/03/2023 | 30 | TAPAN KUMAR DEY | 21.6 | 0 | 0 | 0
1120 | PURULIA | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Supply delivery and installation of Internal lighting and external lighting at Proposed Pump House for Augmentation of Bongabari w/s scheme under PMD, PHE Dte. in the District of Purulia. | 867/PMD | 21/07/2023 | 60 | KANTILAL SAO | 2.84 | 0 | 0 | 0
1121 | PURULIA | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Proposed pump house Bongabari w/s(Zone-II) scheme under PMD, PHE Dte. in the District of Purulia. | 524/PMD | 05/05/2023 | 60 | DEY ENTERPRISE, HOWRAH | 37.81 | 0 | 0 | 20
1122 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Naudiha habitation under Naudiha Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 916/PD | 07/05/2024 | 329 | KM ENTERPRISES | 40.61 | 0 | 0 | 0
1123 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Laying of 250 mm DI rising main from Mahara CWR to Hatuara OHR for augmentation of Bongabari W/S scheme at Purulia-II block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 918/PD | 07/05/2024 | 60 | TAPAN CHANDRA | 84.23 | 0 | 0 | 75
1124 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Emergency piling work along with sand filling at collecting line trenches for protection work against flash flood at Sirkabad W/S Scheme under Purulia Division,PHE Dte.(Under Bongabari W/S Scheme) | 324/PD | 01/03/2024 | 45 | SUBRATA MAHAPATRA | 34.58 | 0 | 0 | 0
1125 | PURULIA | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Supply, delivery and fitting-fixing of ST pole and laying of cable line for Illumination arrangement at Proposed pump house (Zone-II) site with other allied works under Bongabari w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia | 374/PMD | 04/03/2024 | 60 | TAPAN KUMAR DEY | 5.82 | 0 | 0 | 0
1126 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Pathardih Habitation within Mahara Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1140/PD | 18/06/2024 | 45 | ASHOKE ADHIKARY | 31.61 | 0 | 0 | 0
1127 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Birgiri Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1391/PD | 01/09/2022 | 45 | GOUTAM CHAKRABORTY | 39.1 | 0 | 0 | 100
1128 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Construction of Office Room Cum Godown Room within Purulia Sadar Sub-division campus under JJM/Jal Swapna Programme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | 1744/PD | 22/11/2022 | 180 | BOSE CONSTRUCTION | 38.36 | 0 | 0 | 100
1129 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing additional Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Birgiri Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1929/PD | 22/12/2022 | 45 | GOUTAM CHAKRABORTY | 38.42 | 0 | 0 | 100
1130 | PURULIA | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Supply & installation of submersible pumping machinery at River Bed Tubewell for Augmentation of Bongabari w/s(River site) scheme under PMD, PHE Dte. in the District of Purulia. | 250/PMD | 06/03/2023 | 60 | SEN BROTHERS | 8.99 | 0 | 0 | 90
1131 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Construction of Over Head Reservoir (OHR) of 500 Cum Capacity, Staging Height 25 mtr. at Birgiri Mouza of Bangabari W/S Scheme under Purulia Sadar Sub-Division of Purulia Division, P.H.E Dte. (SL - 2) | 354/PD | 14/03/2023 | 270 | MS CHANDI CHARAN ROY | 138.29 | 0 | 0 | 100
1132 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Namo Pindra Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 506/PD | 31/03/2023 | 45 | SUDHANSHU OJHA | 5.3 | 0 | 0 | 100
1133 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Construction of Intake well with laying of horizontal strainer including allied works at the bank of Kansai river near Samsan Ghat at Puncha under Bongabari W/S Scheme of Purulia Sadar Sub- Division, Purulia Division, PHE Dte. | 1521/PD | 16/10/2023 | 60 | SOUVIK MANDAL | 43.94 | 0 | 0 | 100
1134 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Construction of Boundary wall & Sinking of T/well at Mahara Tolapathardih(Purulia-II) under Bongabari W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 361/PD | 04/03/2024 | 60 | GANGULY ENTERPRISES | 20.05 | 0 | 0 | 100
1135 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Laying of DI pipeline and Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and other allied works of Sirkabad W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte.(Under Bongabari W/S Scheme) | 329/PD | 01/03/2024 | 60 | HIRAK KUMAR SAO | 8.04 | 0 | 0 | 100
1136 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Left out HDPE Distribution main Pipe line from Hatuara OHR site to existing distribution main of Bongabari W/S scheme under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte. | 924/PD | 07/05/2024 | 60 | GOUTAM CHAKRABORTY | 64.54 | 0 | 0 | 100
1137 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Material Requisition To Resource Division | 1103/PD | 11/06/2024 | 0 | Resource Division | 289.91 | 0 | 0 | 0
1138 | PURULIA | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Payment of WBSEDCL quotation for new power connection at Bongabari W/S Scheme (Zone-II), Mahara, under PMD, PHE Dte. | BP-24-25-112 | 23/08/2024 | 0 | WBSEDCL PURULIA | 8.05 | 0 | 0 | 0
1139 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Construction of Intake well with laying of horizontal strainer including allied works at the bank of Kansai river at Namopindra village of Bongabari W/S scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | 1524/PD | 16/10/2023 | 502 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 43.43 | 0 | 0 | 85
1140 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Repairing of DI rising main pipeline including cleaning of chokage and Construction of 200 cum capacity CWR & Pump house including panel room & chlorination room, Boundary Wall at Mahara of Bongabari W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | 922/PD | 07/05/2024 | 270 | SUBRATA MAHAPATRA | 72 | 0 | 0 | 50
1141 | PURULIA | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Supply, delivery and installation of Centrifugal pumping machinery with other allied work for direct pumping at Mahara (Zone - III) of Augmentation of Bongabari water supply scheme under Purulia Mechanical Division, PHE Dte. | 1017/PMD | 25/06/2024 | 463 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 49.03 | 0 | 0 | 25
1142 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Continuation work order for the work of Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of 2 Nos. O.H.R. at Keliyathole-Palashkola W/S Scheme within Raghunathpur Sub-Division of Purulia Division, P.H.E Dte. (500 cubic meter capacity Over Head Reservoir of Bongabari W/S Scheme within Purulia Sadar Sub-Division under Purulia Division P.H.E Dte.) | 313/PD | 02/03/2023 | 121 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 0 | 100
1143 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mahara Habitation within Mahara Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 913/PD | 07/05/2024 | 604 | SANTANU BANERJEE | 29.87 | 0 | 0 | 0
1144 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Jitdih Habitation within Mahara Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 914/PD | 07/05/2024 | 604 | MAHARSHI BANERJEE | 32.57 | 0 | 0 | 0
1145 | PURULIA | Purulia Mechanical | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Supply, Delivery and Installation of Openwell submersible pumping machinery with other allied works at Bongabari w/s scheme (Pindra) under PMD, PHE Dte. in the District of Purulia. | 1544/PMD | 11/11/2024 | 324 | M/S A.D. CONCERN | 3.09 | 0 | 0 | 30
1146 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Construction of Guard room with Toilet at Bongabari OHR campus for Bongabari W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | 457/PD | 24/03/2025 | 120 | MAHATO CONSTRUCTION | 7.22 | 0 | 0 | 0
1147 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-A) | 644/PD | 22/04/2022 | 985 | SIDDHARTHA SANKAR SARKAR | 10.99 | 0 | 0 | 100
1148 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Laying of 225 mm dia.(OD) HDPE Pipe as Rising main at Upar Pindra Village of Pindra G.P. of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | 1743PD | 22/11/2022 | 1136 | GLAMOUROOMS UNEMPLOYED CO-OPERATIVE SOCIETY LTD. | 43.16 | 0 | 0 | 100
1149 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Laying of Pipe for distribution pipe line (Gap Portion) to providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 491/PD | 31/03/2023 | 642 | SIDDHARTHA SANKAR SARKAR | 20.25 | 0 | 0 | 100
1150 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Bongabari Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-C) | 646/PD | 22/04/2022 | 45 | INDRAJIT SARKAR | 10.99 | 0 | 0 | 100
1151 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Repairing of DI Pipeline and Repairing & Construction of boundary wall at Puncha Riversite Pump house Site under Puncha W/S Scheme under,Manbazar-II Purulia Sadar Sub Division under Purulia Division, PHE Dte. | 1523/PD | 16/10/2023 | 587 | KANAILAL PAL | 24.14 | 0 | 0 | 100
1152 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Construction of Boundary wall & Sinking of T/well at Bongabari (Purulia-II) under Bongabari W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 360/PD | 04/03/2024 | 211 | M/S CONTRACTORS SYNDICATE | 29.93 | 0 | 0 | 100
1153 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | New Sinking of 3 (Three) Nos 200 mm dia river bed vertical tubewell along with necessary 100 mm dia GI collecting line from River bed Tubewell to CWR at river bank (Kansabati River) at Pindra under Bangabari W/S Scheme under Purulia Sadar Sub Division of Purulia Division, PHE Dte. | 1078/PD | 07/06/2024 | 45 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 13.94 | 0 | 0 | 100
1154 | PURULIA | Purulia Division | Augmentation of Bongabari PWSS for providing Functional Household Tap Connection (FHTC) , SM/10395 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Dubkidi Habitation under Naudiha Village of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 915/PD | 07/05/2024 | 180 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 48.75 | 0 | 0 | 100
1155 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10230 | School | Water supply Tap Connection Arrangement for 25 nos AWC within Barabazar Block (Part-Q) of Purulia District under Purulia Division, PHE Dte. | 57/PD | 10/01/2023 | 45 | ANUP KUMAR SAHA | 206.73 | 0 | 0 | 90
1156 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10230 | School | Water supply Tap Connection Arrangement for 20 nos School upto 200 Students, within JHALDA-II (Part-B) and 35 nos School upto 200 Students, within BARABAZAR BLOCK (Part-B) of Purulia District under Purulia Division, PHE Dte. | 619/PD | 20/04/2022 | 45 | S N POLYMERS PVT LTD | 231.75 | 0 | 0 | 100
1157 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10230 | School | supply Tap Connection Arrangement for 49 nos School upto 200 Students, 4 nos School for 201-500 Students and 1 no School for 501-800 Students within JHALDA-II BLOCK (Part-A) of Purulia District under Purulia Division, PHE Dte. | 617/PD | 20/04/2022 | 45 | S N POLYMERS PVT LTD | 227.71 | 0 | 0 | 100
1158 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10230 | School | Water supply Tap Connection Arrangement for 42 nos School upto 200 Students, 7 nos School for 201-500 Students and 1 no School for 501-800 Students within BARABAZAR BLOCK (Part-A) of Purulia District under Purulia Division, PHE Dte. | 618/PD | 20/04/2022 | 45 | S N POLYMERS PVT LTD | 210.94 | 0 | 0 | 100
1159 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10230 | School | Water supply arrangement of schools at bamusadhu ashram high school under barabazar block within purulia district. | 492/PD | 31/03/2023 | 45 | MRINAL KANTI GORAI | 1.5 | 0 | 0 | 70
1160 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10230 | School | Water supply Tap Connection Arrangement for 3 nos School upto 200 Students within Jhalda-II Block of Purulia Division, PHE Dte. | 837/PD | 26/06/2023 | 45 | PRINCE INDUSTRIES ( INDIA) | 16.93 | 0 | 0 | 100
1161 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10230 | School | Water supply Tap Connection Arrangement for 42 nos School upto 200 Students, 7 nos School for 201-500 Students and 1 no School for 501-800 Students within BARABAZAR BLOCK (Part-A) of Purulia District under Purulia Division, PHE Dte. (Tender No.12/SE/PMU of 2022-23) | BP-2022-23-198 | 16/08/2022 | 0 | S N POLYMERS PVT LTD | 145.54 | 0 | 0 | 0
1162 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10230 | School | Water supply Tap Connection Arrangement for 40 nos School upto 200 Students, within BARABAZAR BLOCK (Part-C) of Purulia District under Purulia Division, PHE Dte. | 798/PD | 05/05/2022 | 45 | SANTANU BANERJEE | 168.21 | 0 | 0 | 100
1163 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10230 | School | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewells sinked at various Schools & AWCs of . Barabazar & Purulia-I Blocks under Purulia Division ,PHE,Dte. | 1734/PD | 04/12/2023 | 30 | BANERJEE CONSTRUCTION | 14.87 | 0 | 0 | 100
1164 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 199 nos. under Jhalda-II & Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10230 | School | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewells sinked at various Schools & AWCs of . Jhalda-I & Jhalda-II Blocks under Purulia Division ,PHE,Dte. | 1733/PD | 04/12/2023 | 30 | AMIT CHOURASIA | 8.57 | 0 | 0 | 100
1165 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Tarabari & R.C pur G.P of Santuri Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1101/BMD | 05/09/2022 | 25 | CHAKRABORTY MAINING & ENGINEERING. | 77.7 | 0 | 0 | 0
1166 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Muradi & Balitora G.P of Santuri Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1100/BMD | 05/09/2022 | 25 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 77.89 | 0 | 0 | 0
1167 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of Tyre for Different Rig Vehicle at B.M.S.D(D) in connection to JJM Programme. | 442/BMSD(D) | 13/06/2022 | 20 | RAJIB COMPANY | 2.32 | 0 | 0 | 0
1168 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of 4 1/2 "(114 mm approx) x 10 ' long Drill Tube for Different Drilling Rig Machine of BMSD(D), Under BMD,PHE Dte. in connection to JJM programme. | 274/BMSD(D) | 29/04/2022 | 15 | CHAKRABORTY MAINING & ENGINEERING. | 4.86 | 0 | 0 | 0
1169 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Acceptance cum Formal work order for the work of Providing man power engagement for construction of R.B.T.W in connection to JJM Programme in Purulia District by Rig unit 7D at B.M.S.D(D) under B.M.D, P.H.E Dte . | 436/BMSD(D) | 13/06/2022 | 108 | PRADIP KUMAR DHABAL | 3.39 | 0 | 0 | 0
1170 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Construction of Rig bored tube-well (200mmx165mm) by DTH method at Bara Urma GP at Balarampur Block under Purulia Mechanical Division PHE Dte. (Tender No.137/EE/PMD of 2022-23) | BP-2022-23-261 | 15/09/2022 | 0 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 7.21 | 0 | 0 | 0
1171 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 38 nos School upto 200 Students within Balarampur Block (Part-B) of Purulia District under Purulia Division, PHE Dte. (Tender No.26/SE/PMU of 2022-23) | BP-2022-23-389 | 19/10/2022 | 0 | CARBON SERVICES INDIA | 2.51 | 0 | 0 | 0
1172 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 38 nos School upto 200 Students within Balarampur Block (Part-B) of Purulia District under Purulia Division, PHE Dte. (Tender No.26/SE/PMU of 2022-23 [Ad - Interim Payment] ) | BP-2022-23-322 | 29/09/2022 | 0 | CARBON SERVICES INDIA | 47.79 | 0 | 0 | 0
1173 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Submission of bill in connection with work of sinking Tube well in AWC Santuri Block. |  | 16/12/2022 | 0 | M/S SHANKAR AUTO SERVICE | 4.44 | 0 | 0 | 0
1174 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 38 nos School upto 200 Students within Balarampur Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | 800/PD | 05/05/2022 | 45 | CARBON SERVICES INDIA | 159.88 | 0 | 0 | 0
1175 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Santuri Block (Part-D) of Purulia District under Purulia Division, PHE Dte.(Phase-II) | 1119/PD | 25/07/2022 | 45 | MS CHANDI CHARAN ROY | 53.71 | 0 | 0 | 0
1176 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method at Bara Urma GP, Balarampur Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 452/PMD | 04/07/2022 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 38.16 | 0 | 0 | 0
1177 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery and installation of Double vane hydraulic pump for repairing Rig vehicle 7D in connection to JJM Programme at B.M.S.D(D) under Bankura Mechanical Division PHE Dte | 935/BMSD(D) | 30/11/2022 | 10 | CHAKRABORTY MINING & ENGINEERING. | 1.31 | 0 | 0 | 0
1178 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Acceptance cum Formal work order for the work of Yield testing of different Departmentally drilling site in Darda GP of Balarampur Block and Saturi GP of Saturi Block of Purulia District in Connection to JJM programme under Bankura Mechanical Division, P.H.E. Dte. | 933/BMSD(D) | 30/11/2022 | 10 | UNITED TRADERS | 1.93 | 0 | 0 | 0
1179 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Acceptance cum Formal work order for the work of Yield testing of different Departmentally drilling site in Balarampur and Saturi Block of Purulia District in Connection to JJM programme under Bankura Mechanical Division, P.H.E. Dte. | 934/BMSD(D) | 30/11/2022 | 15 | M/S SWAPAN BANERJEE | 2.89 | 0 | 0 | 0
1180 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 55 nos AWC within Saturi Block ) of Purulia District under Purulia Division, PHE Dte. | 32/PD | 09/01/2023 | 45 | SUMIT KUMAR CHAKRABORTY | 30.55 | 0 | 0 | 0
1181 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Construction of Rigbored Tube well (200mmx 165mm) by DTH method in different sourceless AWC at Balarampur Block where adjacent road is narrow and critical under Purulia Mechanical Division PHE. Dte. in the District of Purulia | 72/PMD | 31/01/2023 | 30 | KOUSHIK CHATTERJEE | 88.32 | 0 | 0 | 0
1182 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 55 nos AWC within Balarampur & Addl. Block ) of Purulia District under Purulia Division, PHE Dte. | 28/PD | 09/01/2023 | 45 | NATIONAL CONSTRUCTION | 30.54 | 0 | 0 | 0
1183 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Fuel Bill in connection with work of sinking Tube Well in Purulia District related to JJM work | BP-2022-23-490 | 22/12/2022 | 0 | M/S SHANKAR AUTO SERVICE | 4.44 | 0 | 0 | 0
1184 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Construction of Rig board tube well (200mmX165mm) by DTH method at Boro Urma GP is Balarampur block under Purulia Mechanical Division PHE Dte. (T/N 137/EE/PMD of 2022-23) | BP-2022-23-218 | 24/08/2022 | 0 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 30.91 | 0 | 0 | 0
1185 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Balarampur Block (Part-B) & 8 nos AWC within Balarampur Block (Part-E) of Purulia District under Purulia Division, PHE Dte.(Phase-III) | 1123/PD | 25/07/2022 | 45 | NATIONAL CONSTRUCTION | 90.59 | 0 | 0 | 70
1186 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within SANTURI Block (Part-C) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | 1872/PD | 13/12/2022 | 45 | THE BUSINESS ENGINEERS INDIA | 56.73 | 0 | 0 | 100
1187 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Santuri Block (Part-B) of Purulia District under Purulia Division, PHE Dte. (Without Tubewell) (SL - 1) | 144/PD | 03/02/2023 | 45 | BILTU DAS | 117.72 | 0 | 0 | 100
1188 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Acceptance cum Formal work order for the work of Providing hired driver and skilled operator for construction of R.B.T.W in connection to JJM by Rig unit KLR at B.M.S.D(D) under Bankura Mechanical Division PHE Dte | 966/BMSD(D) | 09/12/2022 | 19 | CHAKRABORTY MINING & ENGINEERING. | 0.91 | 0 | 0 | 100
1189 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewellssinked at various Schools & AWCs of . Santuri & Neturia Blocks under Purulia Division ,PHE,Dte. | 1739/PD | 04/12/2023 | 30 | SUMIT KUMAR MITRA | 9.38 | 0 | 0 | 0
1190 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Balarampur Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | 491/PD | 29/03/2022 | 45 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 70.7 | 0 | 0 | 75
1191 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Santuri Block (Part-E) of Purulia District under Purulia Division, PHE Dte.(Phase-III) | 1120/PD | 25/07/2022 | 1000 | MOLLA ENTERPRISE | 54.41 | 0 | 0 | 100
1192 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Santuri, Balarampur Block In Purulia District under Purulia Division, PHE Dte. , SM/10251 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Santuri Block (Part-A) & 2 Nos. AWC within Santuri Block (Part-F) of Purulia District under Purulia Division, PHE Dte.(Phase-I) | 1227/PD | 22/08/2022 | 437 | MD AAMIR KHAN | 63.5 | 0 | 0 | 70
1193 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Water supply tap connection arrangement for 6 nos. AWC within Joypur block (Part-E) of Purulia District under Purulia Division, PHE Dte. (Tender No- 39/2022-23 of EE/PD) | BP-2022-23-237 | 05/09/2022 | 0 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 12.85 | 0 | 0 | 0
1194 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Joypur Block (Part-B) of Purulia District under Purulia Division, PHE Dte. . (Tender No- 88/2022-23 of EE/PD) | BP-2022-23-402 | 21/10/2022 | 0 | PARAMESWAR CHOWDHURY | 15.18 | 0 | 0 | 0
1195 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Joypur Block (Part-J) of Purulia District under Purulia Division, PHE Dte. (Tender No- 311/2022-23 of EE/PD) | BP-2022-23-414 | 28/10/2022 | 0 | SUMIT KUMAR CHAKRABORTY | 7.57 | 0 | 0 | 0
1196 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Joypur Block (Part-N) of Purulia District under Purulia Division, PHE Dte.(Phase-I) (Tender no- 655/2022-23 of EE/PD) | BP-2022-23-433 | 25/11/2022 | 0 | SANTANU BANERJEE | 32.57 | 0 | 0 | 0
1197 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 1 no AWC within Joypur Block (Part-K) of Purulia District under Purulia Division, PHE Dte. | 721/PD | 02/05/2022 | 45 | RAKSHIT ENTERPRISE | 7.86 | 0 | 0 | 100
1198 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Construction of Rigbored Tubewell (200mm X 165mm) by DTH method in different source less AWC at BAHARA GP and NADIHA GP, PARA Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. | 753/PMD | 07/11/2022 | 25 | PREMNATH MITRA | 63.46 | 0 | 0 | 0
1199 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 19 nos AWC within (Joypur Block ) of Purulia District under Purulia Division, PHE Dte. | 39/PD | 09/01/2023 | 45 | SK ABBAS | 10.55 | 0 | 0 | 0
1200 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Joypur Block (Part-E) of Purulia District under Purulia Division, PHE Dte. | 416/PD | 16/03/2022 | 45 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 47.13 | 0 | 0 | 0
1201 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 1 no AWC within Joypur Block (Part-M) of Purulia District under Purulia Division, PHE Dte. | 722/PD | 02/05/2022 | 45 | PRATIK SAHA | 7.85 | 0 | 0 | 0
1202 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Joypur Block (Part-F) of Purulia District under Purulia Division, PHE Dte. | 728/PD | 02/05/2022 | 45 | MUNNA AGROTECH ENTERPRISE | 47.35 | 0 | 0 | 100
1203 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Joypur Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | 726/PD | 02/05/2022 | 45 | WRISHI ENTERPRISE | 23.6 | 0 | 0 | 0
1204 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Joypur Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | 724/PD | 02/05/2022 | 45 | SUMIT CHAKRABORTY | 15.71 | 0 | 0 | 100
1205 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 1 no AWC within Joypur Block (Part-L) of Purulia District under Purulia Division, PHE Dte. | 723/PD | 02/05/2022 | 45 | GOPAL ACHARJEE | 7.88 | 0 | 0 | 0
1206 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Joypur Block (Part-N) of Purulia District under Purulia Division, PHE Dte.(Phase-I) | 1229/PD | 22/08/2022 | 45 | SANTANU BANERJEE | 94.93 | 0 | 0 | 0
1207 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Joypur Block (Part-A) of Purulia District under Purulia Division, PHE Dte.(Phase-II) | 1033/PD | 25/07/2022 | 45 | MEGA SOLAR ENERGY | 94.93 | 0 | 0 | 0
1208 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 3 nos AWC within Joypur Block (Part-O), 1 nos AWC within Joypur Block (Part-P) of Purulia District under Purulia Division, PHE Dte." | 1729/PD | 22/11/2022 | 45 | SOUMITRA CHAKRABORTY | 33.06 | 0 | 0 | 100
1209 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Joypur Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | 727/PD | 02/05/2022 | 45 | NATIONAL CONSTRUCTION | 23.6 | 0 | 0 | 0
1210 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Joypur Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | 983/PD | 22/06/2022 | 45 | MEGA SOLAR ENERGY | 158.22 | 0 | 0 | 0
1211 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Refreshment bill paid for office meeting. | BP-2023-24-368 | 10/08/2023 | 0 | MATHUR DUTTA | 0.12 | 0 | 0 | 0
1212 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Bill of the IEC programes done in 10 blocks during ARANYA SAPTAHA. | BP-2023-24-414 | 25/08/2023 | 0 | M/S SAYAK BHATTACHARYA | 0.97 | 0 | 0 | 0
1213 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Bill paid for submission of TDS certificate 24Q for the A.Y:2023-2024. | BP-2023-24-371 | 10/08/2023 | 0 | NIGAM CONSULTANCY SERVICE | 0.35 | 0 | 0 | 0
1214 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewellssinked at various Schools & AWCs of . Joypur & Balarampur blocks under Purulia Division ,PHE,Dte. | 1732/PD | 04/12/2023 | 30 | VIVEKANANDA CONSTRUCTION | 12.4 | 0 | 0 | 0
1215 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Joypur Block (Part-D) of Purulia District under Purulia Division, PHE Dte. | 1052/PD | 08/07/2022 | 45 | SINGHA ENTERPRISE | 158.13 | 0 | 0 | 100
1216 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Joypur and Para In Purulia District under Purulia Division, PHE.Dte. , SM/10255 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Joypur Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | 415/PD | 16/03/2022 | 45 | PARAMESWAR CHOWDHURY | 46.89 | 0 | 0 | 100
1217 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 357/E/PD | 25/02/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 42.7 | 0 | 0 | 100
1218 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Repairing and renovation of Panel Room at office of the Assistant Engineer, Raghunathpur Sub-Division, PHE Dte. at S.D. Hospital Campus under Raghunathpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 94/RNP | 10/03/2023 | 15 | BISWAJIT MAJI | 0.91 | 0 | 0 | 0
1219 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone IV B under PMD PHE Dte. District Purulia. | 861/PMD | 20/07/2023 | 30 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 21.6 | 0 | 0 | 75
1220 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Continuation work order for the work of Survey & Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 1025/PD | 06/01/2023 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5 | 0 | 0 | 100
1221 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 1008/PD | 29/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
1222 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 942/PD | 19/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
1223 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Continuation work order for the work of Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 1087/A/PD | 16/01/2023 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.15 | 0 | 0 | 100
1224 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 931/A/PD | 13/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
1225 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 1002/PD | 23/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
1226 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Supplying & laying of different dia HDPE pipe line with other allied works from Tilabani OHR Campus to Bathandih village through Rabon More at Tilabani villlage under Kalabani G.P. under Kalabani W/S Scheme (Zone-IV) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 665/PD | 17/05/2023 | 30 | SADHAN GORAIN | 12.88 | 0 | 0 | 100
1227 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Material Requisition To Resource Division | 78/PD | 17/01/2023 | 0 | Resource Division | 0.55 | 0 | 0 | 0
1228 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Construction of Pump House (10 X 7 mtr) at Boosting Station under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | 276/PD | 27/02/2023 | 1040 | BASANTA KUMAR SINGHADEO | 18.56 | 0 | 0 | 40
1229 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Laying of Distribution System including pipe carrying structure all complete including cost of materials including providing Functional Household Tap Connection (FHTC) and other allied works for Aug. Work of Raghunathpur Water Supply Scheme (German Assisted)(Zone-IV A) within Raghunathpur Sub Division under Purulia Division, PHE Dte. (SL-5) | 584/PD | 20/04/2023 | 60 | M/S RAJ KUMAR KHAN | 267.81 | 0 | 0 | 80
1230 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Construction of Guard Room with toilet block at Zone-IV A under Raghunathpur W/S Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 2103/PD | 05/12/2024 | 90 | PRAKASH DESHMUKH | 6.41 | 0 | 0 | 0
1231 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Construction of RCC Over Head Reservoir (Torch types with solid raft) capacity 150 Cum and other allied works of Raghunathpur Water Supply Scheme (Zone-I B) of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 92/PD | 20/01/2023 | 270 | BOSE CONSTRUCTION | 72.84 | 0 | 0 | 85
1232 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Repairing and renovation of Gar Panchakot Inspection Bunglow (Ground Floor) with allied works at Lakhanpur WTP under Raghunathpur Area (EAP) W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 46/PD | 09/01/2023 | 60 | CREATIVE WATER AND PROCESS TECHNOLOGIES PRIVATE LIMITED | 4.39 | 0 | 0 | 100
1233 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Repairing works at 8 Nos Bridge of Rising Pipe line works under Raghunathpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 2327/PD | 31/12/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 13.81 | 0 | 0 | 0
1234 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Construction of Guard Room with toilet block at Zone-IV B under Raghunathpur W/S Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 2104/PD | 05/12/2024 | 90 | SAANVI CONSTRUCTION | 6.41 | 0 | 0 | 0
1235 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site-Babugram, Zone-VI (T/W-III), under Raghunathpur water supply project, PHE Dte. | 563/PMD | 07/04/2025 | 20 | SANTU MITRA | 0.94 | 0 | 0 | 0
1236 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Addition of column pipe including supply along with other works at OHR site-IA/II , Gobag (T/W no- 1,2,3 & 4 ) under Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 633/PMD | 24/04/2025 | 15 | ANUP KUMAR SAHA | 0.75 | 0 | 0 | 0
1237 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Supply, delivery & Installation of Submersible Pumping Machinery along with allied works, at OHR site- Babugram, Zone-VI (T/W-IV), under Raghunathpur water supply project, PHE Dte. | 621/PMD | 22/04/2025 | 20 | ANUP KUMAR SAHA | 0.94 | 0 | 0 | 0
1238 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site-Babugram, Zone-VI (T/W-II), under Raghunathpur water supply project, PHE Dte. | 562/PMD | 07/04/2025 | 20 | S. PATHAK & CO. | 0.96 | 0 | 0 | 0
1239 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Supply, delivery & installation of earthing arrangement and other works at OHR site- Babugram (Zone-VI) of Raghunathpur water supply project under Purulia Mechanical Division,PHE Dte. | 561/PMD | 07/04/2025 | 20 | ANUP KUMAR SAHA | 0.96 | 0 | 0 | 0
1240 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Construction of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 cum and staging height 20 mtr and laying of Distribution System including pipe carrying structure all complete including providing House Hold Tap Connection (FHTC) and other allied works for Aug. work of Raghunathpur Water Supply Scheme (German Assisted) (Zone-IV B) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (SL - 6) | 270/PD | 24/02/2023 | 645 | MITHU BUILDERS | 211.47 | 0 | 0 | 75
1241 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Laying of Distribution Pipeline from Zone IV B OHR site to Ekunja More and other allied works for Aug. of Raghunathpur Water Supply Scheme (Zone - IV B) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 104/PD | 15/01/2024 | 60 | MITHU BUILDERS | 27.51 | 0 | 0 | 100
1242 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Laying of GI pipe line from Raghunathpur office campus CWR to SD Hospital CWR and other allied works under Raghunathpur W/S Scheme (Zone-IV) (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 180/RNP | 04/04/2024 | 7 | SOMNATH SINGH | 0.96 | 0 | 0 | 100
1243 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Salata (Z-IB) (Tube well-III), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 1108/PMD | 11/07/2024 | 82 | ANUP KUMAR SAHA | 0.81 | 0 | 0 | 90
1244 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV A & IV B , SM/14024 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site -Salata (I-B) (Tube Well -IV) of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 1257/PMD | 22/08/2024 | 40 | ANUP KUMAR SAHA | 0.81 | 0 | 0 | 95
1245 | PURULIA | Purulia Division | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss , SM/15039 | Augmentation | Construction of appron & other work inconnection with 100 cum CWR at Ramchandrapur WTP (Zone-II) under Ramchandrapur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 398/RNP | 05/09/2023 | 15 | MADHU SUDAN RAKSHIT | 0.92 | 0 | 0 | 100
1246 | PURULIA | Purulia Division | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss , SM/15039 | Augmentation | Survey, Investigation, Planning, Designing (aesthetically), Construction and Commissioning of a Conventional WATER TREATMENT PLANT and rising main of capacity 1521 KLD as per BIS/CPHEEO Manual consisting of all Civil, Mechanical and Electrical works (excluding supply and installation of Chlorination arrangements, SCADA, Clear Water Pumps and allied works) including necessary hydraulic testing, structural testing equipment testing, trial run for a period of 3 months, etc. complete as directed by Engineer-in-charge (turn-key job). Cost includes submission of detailed design with drawing (both soft and hard copies) showing all necessary arrangements, structural & hydraulic detail etc. for Augmentation of Ramchandrrapur W/S Scheme for source augmentation. | 1090/PD | 10/08/2023 | 839 | ANUP KUMAR SAHA | 213.35 | 0 | 0 | 70
1247 | PURULIA | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss , SM/15039 | Augmentation | Providing indoor and outdoor lighting, making double tank system and other allied works at OHR site at Rangadanga under Augmentation of Ramchandrapur Water supply scheme under Purulia Mechanical Division PHE Dte. | 1552/PMD | 11/11/2024 | 60 | SEN BROTHERS | 5.73 | 0 | 0 | 0
1248 | PURULIA | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss , SM/15039 | Augmentation | Supply delivery and installation of Voltage stabilizer at New Pump house for Augmentation of Ramchandrapur water supply scheme under PMD PHE Dte. in the district of Purulia. | 1553/PMD | 11/11/2024 | 90 | KOUSHIK CHATTERJEE | 5.99 | 0 | 0 | 0
1249 | PURULIA | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss , SM/15039 | Augmentation | Supply, Delivery, Storage, Installation and Commissioning of Pre Chlorination Arrangement at WTP and High Lift site under Augmentation of Ramchandrapur water supply scheme under Purulia Mechanical Division, P.H.E. Dte. | 1575/PMD | 14/11/2024 | 90 | PREMNATH MITRA | 24.94 | 0 | 0 | 0
1250 | PURULIA | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss , SM/15039 | Augmentation | Supply and delivery of Submersible pumping machineries at Augmentation of Ramchandrapur Water Supply Scheme, under Purulia Mechanical Division, PHE. Dte. | 969/PMD | 20/06/2024 | 30 | COMBINE ENTERPRISES | 1.69 | 0 | 0 | 0
1251 | PURULIA | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss , SM/15039 | Augmentation | Supply, Delivery, Storage, Installation and Commissioning of Chlorination Arrangement at New pump house under Augmentation of Ramchandrapur water supply scheme under Purulia Mechanical Division, P.H.E. Dte. | 964/PMD | 20/06/2024 | 90 | S S ENTERPRISE | 25.29 | 0 | 0 | 80
1252 | PURULIA | Purulia Division | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss , SM/15039 | Augmentation | Laying pipe line across railway track near Mouza-Kotaldih for supply of water under Ramchandrapur W/S Scheme (Zone-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1530/PD | 16/10/2023 | 30 | NIBHAS SINHA | 34.55 | 0 | 0 | 100
1253 | PURULIA | Purulia Division | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss , SM/15039 | Augmentation | Laying pipe line across railway track near Mouza-Mijhardih for supply of water under Ramchandrapur W/S Scheme (Zone-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1531/PD | 16/10/2023 | 30 | NIBHAS SINHA | 34.09 | 0 | 0 | 100
1254 | PURULIA | Purulia Division | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss , SM/15039 | Augmentation | Supplying , fitting and fixing Cast Iron heavy type spiral stiar case at Ramchandrapur under Ramchandrapur W/S Scheme of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 1195/PD | 26/06/2024 | 60 | MADHU SUDAN RAKSHIT | 2.7 | 0 | 0 | 100
1255 | PURULIA | Purulia Division | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss , SM/15039 | Augmentation | Supply and installtion of Pressure Shell / Pressure filter (Size- 3000 mm dia X 1800 mm) and laying of HDPE distribution pipe line at Bathanbari under Ramchandrapur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte.(SM Code-SM/15039) | 1358/PD | 25/07/2024 | 30 | M/S SAYAK BHATTACHARYA | 48.06 | 0 | 0 | 65
1256 | PURULIA | Purulia Mechanical | Surface water based water supply scheme for Augmentation of Ramchandrapur Pwss , SM/15039 | Augmentation | Supply delivery and installation of Submersible pump, MS pipe, specials including allied works in connection with direct pumping under Augmentation of Ramchandrapur Water supply scheme under Purulia Mechanical Division, PHE Dte. in the District Purulia. | 1549/PMD | 11/11/2024 | 60 | EASTERN INDIA SALES AND SERVICE | 2.58 | 0 | 0 | 100
1257 | PURULIA | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Ramchandrapur Water Supply scheme Block Santuri under PMD PHE Dte. District Purulia. | 161/PMD | 07/03/2022 | 30 | MERCURY ENGINEERING COMPANY | 20.5 | 0 | 0 | 100
1258 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Supplying laying different dia HDPE and DI pipe including Functional Household Connection (FHTC) for Distribution system (Zone-I) of Augmentation of Ramchandrapur W/s Scheme. (Tender No.23/SE/PMU of 2021-22) | BP-2021-22-385 | 29/03/2022 | 0 | ANUP KUMAR SAHA | 42.77 | 0 | 0 | 0
1259 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Construction of Guard room near intake pathway under Ramchandrapur W/ S Scheme under Raghunathpur Sub- Division, PHE Dte.(Tender No- 569/2021-22 of EE/PD) | BP-2022-23-101 | 16/07/2022 | 0 | MADHU SUDAN RAKSHIT | 4.21 | 0 | 0 | 0
1260 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Ramchandrapur W/S Scheme Block - Santuri) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. (Tender No.538/EE/PD of 2021-22) | BP-2021-22-274 | 03/03/2022 | 0 | RADIANT | 4.26 | 0 | 0 | 0
1261 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Functional Household Tap Connection (FHTC including other allied works of Ramchandrapur Water Supply Scheme (Zone - III) at Santuri Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. at Mouza - Murulia (Jl No. 15) | 147/PD | 24/01/2022 | 45 | BASANTA KUMAR SINGHADEO | 68.57 | 0 | 0 | 95
1262 | PURULIA | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Internal and External illumination work for Augmentation Ramchandrapur Water supply scheme at Existing WTP and Intake pump house , Block: santuri , Under Purulia Mechanical Division PHE Dte Dist-Purulia. | 525/PMD | 05/08/2022 | 30 | MOON LIGHT HOUSE | 9.48 | 0 | 0 | 55
1263 | PURULIA | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Supply, delivery and installation of automatically controlled Chlorinator having flow rate of 100 LPH and maximum pressure of 10 kg/cm2. at Augmentation of Ramchandrapur water supply scheme OHR/pump house block Santuri, under Purulia Mechanical Division PHE, Dte. district-Purulia. | 94/PMD | 03/02/2023 | 30 | GOLAP KR. GHOSH | 1.92 | 0 | 0 | 0
1264 | PURULIA | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Supply delivery and installation of Centrifugal pump motor sets MCC, Flowmeter to supply Zone I & II OHR with allied works at New pump house of Augmentation of Ramchandrapur water supply scheme Block: Santuri, Under Purulia Mechanical Division PHE, Dte. in the District of Purulia. | 93/PMD | 03/02/2023 | 60 | MAHADEV ENTERPRISE | 36.04 | 0 | 0 | 20
1265 | PURULIA | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Supply, delivery and installation of voltage stabilizer at WTP site and allied works for Augmentation of Ramchandrapur water supply scheme District- Purulia, under Purulia Mechanical Division PHE, Dte. Dist- Purulia. | 95/PMD | 03/02/2023 | 60 | MOON LIGHT HOUSE | 6.31 | 0 | 0 | 40
1266 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir of capacity 150 Cum including other allied works at OHR site of Ramchandrapur W/S Scheme of Raghunathpur Sub-Division under Purulia Division PHE Dte. | 733/RNP | 06/12/2021 | 60 | MADHU SUDAN RAKSHIT | 4.59 | 0 | 0 | 25
1267 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works at Ramchandrapur W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | 148/PD | 24/01/2022 | 90 | MADHU SUDAN RAKSHIT | 10.63 | 0 | 0 | 100
1268 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. at Ramchandrapur W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | 340/RNP | 01/06/2022 | 30 | VOYAGER | 1.4 | 0 | 0 | 80
1269 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Repairing and renovation of existing Boundary Wall at Ramchandrapur WTP under Ramchandrapur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1924/PD | 22/12/2022 | 30 | MOONLIGHT HOUSE | 4.15 | 0 | 0 | 100
1270 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Construction of pump house for accommodating centrifugal pump for pumping of water including panel room & chlorination room of Ramchandrapur W/S Scheme under Raghunathpur Sub-Division, Purulia Division, PHE Dte. | 524/PD | 30/03/2022 | 100 | MADHU SUDAN RAKSHIT | 16.75 | 0 | 0 | 100
1271 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Material Requisition To Resource Division | 394 | 11/03/2022 | 0 | Resource Division | 29.79 | 0 | 0 | 0
1272 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Material Requisition To Resource Division | 976/PD | 22/06/2022 | 0 | Resource Division | 144.33 | 0 | 0 | 0
1273 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Demand notice for renewal of 150mm dia M.S carrier pipe with 600mm dia MS casing pipe under Rly Track at Km. N305/25-27 in between Muradih-Madhukunda station by PHED/Purulia for Ramchandrapur W/s Scheme. (Letter No.Engg./TE/1/C dt.24/08/2022) | BP-2022-23-509 | 22/12/2022 | 0 | F.A &C A.O/S.E RAILWAY GURDEN | 3.34 | 0 | 0 | 0
1274 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Indian Railway miscellaneous collection. | BP-2023-24-302 | 14/07/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
1275 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Supplying laying different dia HDPE and DI pipe including Functional Household Tap Connection (FHTC) for distribution system (Zone-I) augmentation of Ramchandrapur W/S Scheme under Raghunathpur Sub-Division, PHE Dte. Sl no- 1 (Tender No- 23/2021-22 of SE/PMU/WBPWSP(P) ) | BP-2022-23-93 | 07/07/2022 | 0 | ANUP KUMAR SAHA | 87.04 | 0 | 0 | 0
1276 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Indian Railway miscellaneous collection. | BP-2023-24-303 | 14/07/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
1277 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Construction of RCC Clear water reservoir (CWR) of capacity 100 Cum, Pump house for accommodating centrifugal pump and making inter-connection by CIDF & M.S Pipe for pumping of water including Panel room & Chlorination room, Boundary wall and Sinking of 3 (Three) Nos. 200 mm dia DTH rigbored tubewell with other allied works at Santuri OHR campus of Santuri W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1541/PD | 16/10/2023 | 474 | CHATTERJEE CONSTRUCTION | 67.71 | 0 | 0 | 45
1278 | PURULIA | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Internal Illumination and Yard lighting arrangement at newly Constructed Pump House under under Augmentation of Ramchandrapur Water Supply Scheme, Block: Santuri, under Purulia Mechanical Division, PHE, Dte. in the District of Purulia. | 372/PMD | 04/03/2024 | 60 | SEN BROTHERS | 11.66 | 0 | 0 | 0
1279 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Supplying, laying different dia HDPE pipe including Functional House Hold Tap Connection (FHTC) for Distribution System (Zone-III) of augmentation of Ramchandrapur W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 621/PD | 20/04/2022 | 45 | ASHOK KUMAR CHATTERJEE | 195.98 | 0 | 0 | 100
1280 | PURULIA | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Supply delivery and installation of Centrifugal pump motor sets, MCC, with allied works at WTP site for Augmentation of Ramchandrapur water supply scheme Block: Santuri, Under Purulia Mechanical Division PHE Dte. Dist-Purulia | 133/PMD | 20/02/2023 | 60 | DEBJYOTI BASU | 34.04 | 0 | 0 | 100
1281 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Supplying, laying different dia HDPE pipe including Functional House Hold Tap Connection (FHTC) for Distribution System including Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 400 cum and staging height 20 mtr. (Zone-II) of Ramchandrapur W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1198/PD | 12/08/2022 | 270 | NIBHAS SINHA | 316.96 | 0 | 0 | 100
1282 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Rangadanga High School , OHR Campus under Ramchandrapur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 175 mtr.) | 1832/PD | 12/12/2023 | 30 | NIBHAS SINHA | 17.72 | 0 | 0 | 100
1283 | PURULIA | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Providing And Installation of H.O.T. Crane at newly constructed Pump House and old pump house under Augmentation of Ramchandrapur Water Supply Scheme, Block: Santuri, under Purulia Mechanical Division, PHE, Dte. in the District of Purulia. | 371/PMD | 04/03/2024 | 60 | EASTERN INDIA SALES AND SERVICE | 16.98 | 0 | 0 | 100
1284 | PURULIA | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Quotation for new connection at Rangadanga OHR site under Ramchandrapur water supply scheme. | BP-24-25-11 | 10/05/2024 | 0 | SANTURI CCC | 2.88 | 0 | 0 | 0
1285 | PURULIA | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Quotation money payment for new connection near baranti Dam | BP-2024-25-32 | 21/06/2024 | 0 | SANTURI CCC | 6.19 | 0 | 0 | 0
1286 | PURULIA | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Quotation for New Connection at New Pump House at Ramchandrapur | BP-24-25-14 | 24/05/2024 | 0 | SANTURI CCC | 1.29 | 0 | 0 | 0
1287 | PURULIA | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Bill for Load Enhancement for Aug of Ramchandrapur W/S Scheme. | BP-23-24-226 | 05/12/2023 | 0 | WBSEDCL PURULIA | 1.41 | 0 | 0 | 0
1288 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Laying of 200 mm dia DI pipe for Rising Main including allied works of Ramchandrapur W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 791/PD | 05/05/2022 | 1123 | ASHOK KUMAR CHATTERJEE | 12.83 | 0 | 0 | 50
1289 | PURULIA | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Supply delivery and installation of VT pump motor , MCC Panel and other electromechanical equipment's for Raw water intake pump house at Augmentation of Ramchandrapur PWSS, Block: Santuri, Under Purulia Mechanical Division PHE Dte Dist- Purulia. | 46/PMD | 19/01/2023 | 803 | EASTERN INDIA SALES AND SERVICE | 65.49 | 0 | 0 | 100
1290 | PURULIA | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Supply, delivery and installation of Vertical multistage centrifugal pump motor sets , Panel , Flow meter and all electro mechanical equipments at Augmentation of Ramchandrapur water supply scheme for direct pumping Block- Santuri, under Purulia Mechanical Division PHE Dte. Dist- Purulia. | 96/PMD | 03/02/2023 | 788 | EASTERN INDIA SALES AND SERVICE | 51.14 | 0 | 0 | 100
1291 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Ramchandrapur CWR,Pump House Campus (Zone -II ) under Ramchandrapur W/S Scheme under Raghunathpur Sub-Division, P.H.E. Dte. (Total length of Boundary Wall 217.00 mtr.) | 1923/PD | 22/12/2022 | 889 | MADHU SUDAN RAKSHIT | 21.27 | 0 | 0 | 80
1292 | PURULIA | Purulia Mechanical | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Providing And Installation of 2 M.T. capacity manually operated curved monorail for Low Lift Pump House and High Lift Pump House under Augmentation of Sonathali Water Supply Scheme, Block: Kashipur, under Purulia Mechanical Division, PHE, Dte. in the District of Purulia. | 379/PMD | 04/03/2024 | 348 | S. PATHAK & CO. | 10.22 | 0 | 0 | 100
1293 | PURULIA | Purulia Division | Augmentation of Ground Water Supply Scheme for Ramchandrapur to Accommodate FHTC in Santuri Block, District-Purulia , SM/10045 | Augmentation | Continuation Work order for Operation & Maintenance and water testing in the laboratory of Santuri Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.05.2024 to 31.06.2024) | 266/A/PR | 26/04/2024 | 61 | UTSAV AGENCY | 0.43 | 0 | 0 | 100
1294 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA , SM/16530 | Solarisation | Installation of Ongrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Purulia I Block under PMD, PHE, Dte. District Purulia. | 895/PMD | 01/08/2023 | 60 | ANUP KR. SAHA | 6.42 | 0 | 0 | 83
1295 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA , SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Hura Block under PMD, PHE, Dte. District Purulia. | 907/PMD | 07/08/2023 | 60 | SEN BROTHERS | 6.42 | 0 | 0 | 90
1296 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA , SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Purulia II Block under PMD, PHE, Dte. District Purulia. | 908/PMD | 07/08/2023 | 60 | SAIBAL SARKAR | 6.42 | 0 | 0 | 50
1297 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA , SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Balarampur Block under PMD, PHE, Dte. District Purulia. | 909/PMD | 07/08/2023 | 60 | THE BUSINESS ENGINEERS INDIA | 3.21 | 0 | 0 | 90
1298 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA , SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Bundwan Block under PMD, PHE, Dte. District Purulia. | 911/PMD | 07/08/2023 | 60 | THE BUSINESS ENGINEERS INDIA | 3.21 | 0 | 0 | 50
1299 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA , SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Bagmundi Block under PMD, PHE, Dte. District Purulia. | 906/PMD | 07/08/2023 | 60 | COMBINE ENTERPRISES | 6.42 | 0 | 0 | 80
1300 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA , SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Puncha Block under PMD, PHE, Dte. District Purulia. (2 nd Call) | 1200/PMD | 03/11/2023 | 60 | P. T. ENTERPRISE | 3.16 | 0 | 0 | 90
1301 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA , SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Para Block under PMD, PHE, Dte. District Purulia. (2 nd Call) | 1177/PMD | 03/11/2023 | 90 | S. PATHAK & CO. | 6.3 | 0 | 0 | 85
1302 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA , SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Manbazar I Block under PMD, PHE, Dte. District Purulia. (3rd Call) | 484/PMD | 14/03/2024 | 60 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 3.21 | 0 | 0 | 0
1303 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA , SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Jhalda II Block under PMD, PHE, Dte. District Purulia.(2nd Call) | 1638/PMD | 29/11/2024 | 60 | THE BUSINESS ENGINEERS INDIA | 6.41 | 0 | 0 | 0
1304 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA , SM/16530 | Solarisation | Installation of display Board as per deptt. spec for all sanction solar scheme at different block (Manbazar- I, kashipur Bagmundi, Arsha etc) under Purulia Mechanical Division, PHE Dte. | 189/PMSD(Drilling) | 15/12/2023 | 20 | PINTU DEY | 0.97 | 0 | 0 | 100
1305 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA , SM/16530 | Solarisation | Installation of display board as per deptt spec for all sanction solar scheme at different block (Hura,Jhalda II, Purulia I, & II etc) under Purulia Mechanical Division, PHE Dte | 188/PMSD(Drilling) | 15/12/2023 | 20 | PINTU DEY | 0.97 | 0 | 0 | 100
1306 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA , SM/16530 | Solarisation | Installation of Ongrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Arsha Block under PMD, PHE, Dte. District Purulia. | 894/PMD | 01/08/2023 | 551 | SHWET BARANI | 12.84 | 0 | 0 | 80
1307 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA , SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Barabazar Block under PMD, PHE, Dte. District Purulia. | 910/PMD | 07/08/2023 | 60 | NUPUR CHANDRA HALDER | 3.21 | 0 | 0 | 85
1308 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA , SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Kashipur Block under PMD, PHE, Dte. District Purulia. | 913/PMD | 07/08/2023 | 60 | A.K INDUSTRIES | 19.25 | 0 | 0 | 70
1309 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA , SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Joypur Block under PMD, PHE, Dte. District Purulia. | 912/PMD | 07/08/2023 | 60 | NUPUR CHANDRA HALDER | 3.21 | 0 | 0 | 85
1310 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA , SM/16530 | Solarisation | Installation of OnGrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Neturia Block under PMD, PHE, Dte. District Purulia. | 914/PMD | 07/08/2023 | 60 | A.K INDUSTRIES | 19.25 | 0 | 0 | 100
1311 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PWSS AT DIFFERENT BLOCKS UNDER PMD PHE DTE. DISTRICT PURULIA , SM/16530 | Solarisation | Installation of Ongrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at different water supply schemes of Santuri Block under PMD, PHE, Dte. District Purulia. | 919/PMD | 07/08/2023 | 60 | MS ELECTRO ENTERPRISES | 9.63 | 0 | 0 | 85
1312 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | Rectification of internal & external lighting arrangement at conference hall & allied premises of awareness generation cum water sample collection centre at Mouza-ghat Block - Manbazar-2 under Purulia Mechanical Division under PHE Dte. | 581/PMD | 19/05/2023 | 30 | PREMNATH MITRA | 11.92 | 0 | 0 | 70
1313 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Manbazar Water Supply scheme Block Manbazar-I under PMD PHE Dte. District Purulia. (2nd Call) | 1203/PMD | 03/11/2023 | 90 | PRINCE INDUSTRIES (INDIA) | 21.5 | 0 | 0 | 0
1314 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | Supply delivery and installation of gaseous chlorination system,MCC,all electro mechanical equipments at OHR( Zone-4) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | 559/PMD | 16/05/2023 | 60 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 21.65 | 0 | 0 | 100
1315 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | Replacement of Rupture & multiple jointed LT Cable line from clear water pump house to Intake pump house at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | 554/PMD | 16/05/2023 | 60 | ANUP KR. SAHA | 42.18 | 0 | 0 | 100
1316 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | Supply delivery and installation of gaseous chlorination system, MCC, all electro mechanical equipment's at OHR( Zone-5) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | 560/PMD | 16/05/2023 | 60 | H K DAS AND CO | 21.65 | 0 | 0 | 100
1317 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | Augmentation of existing gaseous chlorination system at Manbazar-2(Part) w/s Scheme under Purulia mechanical Division, PHE, Dte. in the purulia district. | 561/PMD | 16/05/2023 | 60 | ASHOKE ADHIKARY | 15.5 | 0 | 0 | 100
1318 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | New service connection for Kutni OHR campus for Aug of Manbazar -II (part II) W/S scheme |  | 22/06/2023 | 0 | WBSEDCL PURULIA | 0.29 | 0 | 0 | 0
1319 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | NEW SERVICE CONNECTION FOR DANGORDI FOR AUG OF MANBAZAR -II(PART) WATER SUPPLY SCHEME | BP-2023-2024-71 | 14/07/2023 | 0 | WBSEDCL PURULIA | 0.29 | 0 | 0 | 0
1320 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | NEW SERVICE CONNECTION FOR KUTNI UNDER AUG OF MANBAZAR-II(PART) WATER SUPPLY SCHEME | BP-2023-2024-74 | 14/07/2023 | 0 | WBSEDCL PURULIA | 0.29 | 0 | 0 | 0
1321 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | New service connection for khariduara OHR campus for Aug of Manbazar (part-II) W/S scheme | BP-2023-2024-73 | 14/07/2023 | 0 | WBSEDCL PURULIA | 0.29 | 0 | 0 | 0
1322 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | NEW SERVICE CONNECTION FOR HENSLA UNDER AUGMENTATION OF MANBAZAR-II (PART) WATER SUPPLY SCHEME | BP-2023-2024-72 | 14/07/2023 | 0 | WBSEDCL PURULIA | 0.29 | 0 | 0 | 0
1323 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | Providing and Installation of Electro-Mechanical Equipment¿s at Intake, Clear water Pump House and 5 nos. OHRs in Manbazar-II (Part) water supply scheme under Purulia Mechanical Division, PHE, Dte., District Purulia. | 1569/PMD | 14/11/2024 | 90 | EASTERN INDIA SALES AND SERVICE | 80.69 | 0 | 0 | 0
1324 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | Supply delivery and installation of gaseous chlorination system, MCC, all electro mechanical equipment's at OHR( Zone-3) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | 558/PMD | 16/05/2023 | 60 | GOENKA ENTERPRISE | 21.65 | 0 | 0 | 100
1325 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | Installation of One no submersible pumping machinery at intake pump house with supply and installation of Scada compatible MCC panel at Manbazar-II (part) w/s scheme under PMD, PHE, Dte. in the district of purulia | 582/PMD | 19/05/2023 | 60 | TAPAN KUMAR DEY | 26.38 | 0 | 0 | 60
1326 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | Replacement of old centrifugal pump motor sets by the new pump motor set with supply and installation of Scada compatible MCC panel at clear water pump house at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | 553/PMD | 16/05/2023 | 60 | RABINDRA NATH KHAN | 110.31 | 0 | 0 | 100
1327 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | Augmentation of existing old VCB by the new one(one incoming two outgoing) and installation of one new transformer at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | 555/PMD | 16/05/2023 | 60 | TAPAN KUMAR DEY | 61.95 | 0 | 0 | 95
1328 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | Supply delivery and installation of gaseous chlorination system,MCC,all electro mechanical equipments at OHR( Zone-1) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | 556/PMD | 16/05/2023 | 60 | SWAPAN ENTERPRISE | 21.65 | 0 | 0 | 10
1329 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | Supply delivery and installation of gaseous chlorination system,MCC,all electro mechanical equipments at OHR( Zone-2) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | 557/PMD | 16/05/2023 | 60 | NUPUR CHANDRA HALDER | 21.66 | 0 | 0 | 65
1330 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | Arrangement for high pressure testing of Sub -Station equipment for 500 KVA Sub - Station at Manbazar - II Water Supply Scheme under Purulia Mechanical Division, PHE,Dte. | 971/PMD | 20/06/2024 | 30 | TAPAN KUMAR DEY | 1.19 | 0 | 0 | 100
1331 | PURULIA | Purulia Mechanical | AUGMENTATION OF ELECTROMECHANICAL COMPONENTS AT MANBAZAR -II (PART)WATER SUPPLY SCHEME UNDER PURULIA MECHANICAL DIVISION , PHE DTE. , SM/16414 | Augmentation | Making fencing boundry at Transformer Yard of Manbazar - II Water Supply Scheme under Purulia Mechanical Division, PHE, Dte. | 1702/PMD | 06/12/2024 | 360 | TAPAN KUMAR DEY | 1.53 | 0 | 0 | 100
1332 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B , SM/18306 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone VI B under PMD PHE Dte. District Purulia. | 803/PMD | 12/07/2023 | 30 | MERCURY ENGINEERING COMPANY | 21.6 | 0 | 0 | 0
1333 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B , SM/18306 | Augmentation | Material Requisition To Resource Division | 74/PD | 17/01/2023 | 0 | Resource Division | 1.75 | 0 | 0 | 0
1334 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B , SM/18306 | Augmentation | Laying of Distribution pipe line including providing functional House Hold Tap Connection (FHTC), and other allied works of Raghunathpur Water Supply Scheme (Zone-VIA) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(SL-8) | 1041/PD | 04/08/2023 | 606 | DEBAKI RANJAN SARKAR | 310.01 | 0 | 0 | 60
1335 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B , SM/18306 | Augmentation | Laying of Distribution pipe line including providing functional House Hold Tap Connection (FHTC), construction of 250 Cum OHR and other allied works of Raghunathpur Water Supply Scheme (Zone-VIB) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(SL-9) | 1021/PD | 01/08/2023 | 270 | SWAPAN MANDAL | 280.53 | 0 | 0 | 35
1336 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B , SM/18306 | Augmentation | Construction of Switch Room Cum Chlorin Room at Zone-VI B (Babugram) OHR Site of Raghunathpur W/S Scheme (German Project) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1729/PD | 04/12/2023 | 100 | SAANVI CONSTRUCTION | 4.81 | 0 | 0 | 100
1337 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B , SM/18306 | Augmentation | Quotation for new service connection at Zone-VI OHR(Babugram) site under Raghunathpur Aug. water supply scheme. | BP-24-25-75 | 02/08/2024 | 0 | WBSEDCL PURULIA | 6.21 | 0 | 0 | 0
1338 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B , SM/18306 | Augmentation | Repairing & Renovation of Existing Rising Main and other allied works for Aug.work of Raghunathpur Water Supply Scheme (German Assisted) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (SL No.4) | 1578/PD | 30/10/2023 | 823 | ANUP KUMAR SAHA | 300.79 | 0 | 0 | 65
1339 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B , SM/18306 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir capacity 278 cum and other allied works under Raghunathpur W/S Scheme (Zone-VI-A) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 2321/PD | 31/12/2024 | 516 | CHAIL CONSTRUCTION | 11.41 | 0 | 0 | 0
1340 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B , SM/18306 | Augmentation | Repairing of DI Rising Main, construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(One) no tubewell at OHR Sites of (Zone - VI B) of Raghunathpur Water Supply Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 180 m) | 1362/PD | 25/07/2024 | 525 | BASANTA KUMAR SINGHADEO | 24.88 | 0 | 0 | 0
1341 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B , SM/18306 | Augmentation | Supply, delivery & Installation of Submersible Pumping Machinery along with allied works, at OHR site- Babugram, Zone-VI (T/W-I), under Raghunathpur water supply project, PHE Dte. | 517/PMD | 28/03/2025 | 20 | SUJIT MUKHERJEE | 0.99 | 0 | 0 | 0
1342 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VI A & VI B , SM/18306 | Augmentation | Addition of column pipe including supply along with allied works at OHR site-VII B, Ketlapur under Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 634/PMD | 24/04/2025 | 15 | ANUP KUMAR SAHA | 0.49 | 0 | 0 | 0
1343 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month at Zone- XVI of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector ) under Purulia Divn. PHE Dte.(SL-12) | 1104/PD | 14/08/2023 | 270 | ANUP KUMAR SAHA | 449.89 | 0 | 0 | 0
1344 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six(36) month at Zone- II of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector ) under Purulia Divn. PHE Dte.(SL-2) | 1095/PD | 14/08/2023 | 270 | MS D.PALIT AND CO. | 478.83 | 0 | 0 | 0
1345 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month at Zone- XV of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector ) under Purulia Divn. PHE Dte.(SL-11) | 1108/PD | 16/08/2023 | 270 | MS D.PALIT AND CO. | 400.45 | 0 | 0 | 0
1346 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approved drawing (No:PCI/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month at Zone- XIII of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (2nd Call)(SL-4) | 1092/PD | 14/08/2023 | 270 | SAMAN KUMAR MAHATO | 184.53 | 0 | 0 | 0
1347 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-I of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-8) | 1574/PD | 30/10/2023 | 270 | BOSE CONSTRUCTION | 181.34 | 0 | 0 | 0
1348 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Laying of Distribution pipeline From Balarampur OHR site CWR to Petrol Pump near Bihari bandh at Balarampur Zone-2 under Purulia W/S Scheme under Purulia Division PHE Dte. | 2202/PD | 13/12/2024 | 60 | SADHAN GORAIN | 93.97 | 0 | 0 | 0
1349 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Balarampur (Zone-VII) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | 2164/PD | 13/12/2024 | 60 | AEROSPATIAL SOLUTION PRIVATE LIMITED | 85.04 | 0 | 0 | 0
1350 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-VII) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | 903/PD | 07/05/2024 | 60 | CHATTERJEE CONSTRUCTION | 95.89 | 0 | 0 | 0
1351 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-VIII) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | 904/PD | 07/05/2024 | 60 | M/S SB CONSTRUCTION | 95.99 | 0 | 0 | 0
1352 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Purulia-I (Zone-V) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | 919/PD | 07/05/2024 | 60 | M/S SB CONSTRUCTION | 61 | 0 | 0 | 50
1353 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Boundary wall & Sinking of T/well at Bandwan,Zone-X under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 2191/PD | 13/12/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 22.55 | 0 | 0 | 0
1354 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-III) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | 2206/PD | 13/12/2024 | 60 | AEROSPATIAL SOLUTION PRIVATE LIMITED | 87.13 | 0 | 0 | 0
1355 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-II,Zone-III under Purulia W/S Scheme (Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 2095/PD | 05/12/2024 | 60 | M D CONSTRUCTION | 25.74 | 0 | 0 | 0
1356 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-I,Zone-II under Purulia W/S Scheme (Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 2097/PD | 05/12/2024 | 60 | CHINMOY SEN | 26.6 | 0 | 0 | 0
1357 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Balarampur (Zone-III) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | 2167/PD | 13/12/2024 | 60 | AEROSPATIAL SOLUTION PRIVATE LIMITED | 84.97 | 0 | 0 | 0
1358 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Laying of Distribution pipeline From Balarampur Bihari Bandh to Rail Phatak (bagmundiRoad ) at Balarampur Zone-2 under Purulia W/S Scheme under Purulia Division PHE Dte. | 2201/PD | 13/12/2024 | 60 | SADHAN GORAIN | 83.98 | 0 | 0 | 0
1359 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Boundary wall & Sinking of T/well at Bandwan,Zone-XI under Purulia W/S Scheme (Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 2098/PD | 05/12/2024 | 60 | INDRAJIT SARKAR | 19.27 | 0 | 0 | 0
1360 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-II,Zone-V under Purulia W/S Scheme(Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 2099/PD | 05/12/2024 | 60 | BANERJEE CONSTRUCTION | 23.55 | 0 | 0 | 0
1361 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Left out laying of Distribution Pipe Line for distribution System at Chatambari Mouza under command area of Jhalda Rural W/S Scheme Under Purulia W/S Scheme (Southern Sector) of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1507/PD | 27/08/2024 | 45 | BHAGABAN DAS KUMAR | 2.73 | 0 | 0 | 100
1362 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution pipe line and providing FHTC including other allied work & Operation & Maintenance of Distribution, pipe line (Dt/HDPE),including Sluce Valve & FHTC for the period of thirty six (36) month at zone-Ix of Bandwan Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (Sl No.6) | 1099/PD | 14/08/2023 | 540 | JAL PRAVAHIKA PVT. LTD. | 492.94 | 0 | 0 | 40
1363 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-II & III of Manbazar-II Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (SL No.2) | 1584/PD | 30/10/2023 | 790 | DEBAKI RANJAN SARKAR | 667.42 | 0 | 0 | 50
1364 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-V & VI of Manbazar-II Block under Purulia Piped Water Supply Scheme (Southern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL No.10) | 1579/PD | 30/10/2023 | 945 | ANUP KUMAR SAHA | 982.47 | 0 | 0 | 40
1365 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Boundary wall & Sinking of T/well at Bandwan,Zone-III under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 44/PD | 10/01/2025 | 45 | SUDHANSHU OJHA | 19.2 | 0 | 0 | 0
1366 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-I,Zone-I under Purulia W/S Scheme(Southern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 2094/PD | 05/12/2024 | 60 | ARATI MAHATO | 22.53 | 0 | 0 | 0
1367 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-XI Bandwan Block within Southern Sector under Purulia Division, PHE Dte. | 503/PD | 25/03/2025 | 150 | JYOGOMAYA ENTERPRISE | 16.7 | 0 | 0 | 0
1368 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-XV) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | 111/PD | 21/01/2025 | 60 | AEROSPATIAL SOLUTION PRIVATE LIMITED | 85.32 | 0 | 0 | 0
1369 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-X Bandwan Block within Southern Sector under Purulia Division, PHE Dte. | 502/PD | 25/03/2025 | 150 | JYOGOMAYA ENTERPRISE | 16.7 | 0 | 0 | 0
1370 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Baghmundi (Zone - XIII & XIV) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | 1089/PD | 17/06/2025 | 120 | PURNIMA ELECTRICS AND DECORATORS | 28.82 | 0 | 0 | 0
1371 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Balarampur (Zone - IX&X) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | 1093/PD | 17/06/2025 | 120 | PARADISE ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 28.84 | 0 | 0 | 0
1372 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-IV Bandwan Block within Southern Sector under Purulia Division, PHE Dte. | 483/PD | 25/03/2025 | 150 | ROY CONSTRUCTION | 15.71 | 0 | 0 | 0
1373 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-XII Bandwan Block within Southern Sector under Purulia Division, PHE Dte. | 490/PD | 25/03/2025 | 150 | MOONLIGHT HOUSE | 16.2 | 0 | 0 | 0
1374 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-I) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | 2199/PD | 13/12/2024 | 60 | INFINITE INFRATECH EPC | 85.98 | 0 | 0 | 0
1375 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Balarampur (Zone - VII & VIII) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | 1090/PD | 17/06/2025 | 120 | M/S SB CONSTRUCTION | 28.5 | 0 | 0 | 0
1376 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Manbazar-II (Zone - II & V) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | 1094/PD | 17/06/2025 | 120 | PRAKASH DESHMUKH | 28.73 | 0 | 0 | 0
1377 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Baghmundi (Zone - VI, VII & VIII) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | 1097/PD | 17/06/2025 | 120 | SUJIT SAHANA | 49.71 | 0 | 0 | 0
1378 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Manbazar-II (Zone - II, IV & VI) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | 1100/PD | 17/06/2025 | 120 | SAHADEV HALDER | 50.09 | 0 | 0 | 0
1379 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Manbazar-II (Zone - VII & VIII) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | 1095/PD | 17/06/2025 | 120 | MAA SARADA CONSTRUCTION | 28.82 | 0 | 0 | 0
1380 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Baghmundi (Zone-IV) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | 2208/PD | 13/12/2024 | 60 | AKHANDAMRIT METALS PRIVATE LIMITED | 68.26 | 0 | 0 | 0
1381 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Ajodhya Hill of Baghmundi Block (Zone-XIII) under Purulia W/S Scheme (southern sector) of Purulia Division, PHE Dte. | 2207/PD | 13/12/2024 | 60 | ELITE ENGINEERING AND CONSTRUCTION | 96.42 | 0 | 0 | 0
1382 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Baghmundi (Zone - II, III & V) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | 1096/PD | 17/06/2025 | 120 | SOUHARDYA BUSINESS LINE | 49.99 | 0 | 0 | 0
1383 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-I Manbazar-II Block within Southern Sector under Purulia Division, PHE Dte. | 495/PD | 25/03/2025 | 150 | SINGHA ENTERPRISE | 16.53 | 0 | 0 | 0
1384 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-II Bandwan Block within Southern Sector Purulia District under Purulia Division, PHE Dte. | 476/PD | 25/03/2025 | 150 | GANGULY ENTERPRISES | 15.52 | 0 | 0 | 0
1385 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-III Bandwan Block within Southern Sector under Purulia Division, PHE Dte. | 480/PD | 25/03/2025 | 150 | AMITAVA KUNDU | 16.52 | 0 | 0 | 0
1386 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Bandwan (Zone - VII, XIII & XIV) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | 1088/PD | 17/06/2025 | 120 | BLUEDOT CONSTRUCTION | 43.22 | 0 | 0 | 0
1387 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-III Manbazar-II Block within Southern Sector under Purulia Division, PHE Dte. | 497/PD | 25/03/2025 | 150 | CHANCHAL MISHRA | 16.61 | 0 | 0 | 0
1388 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-IX Bandwan Block within Southern Sector under Purulia Division, PHE Dte. | 501/PD | 25/03/2025 | 150 | SANJAY KUMAR NARSARIA | 16.69 | 0 | 0 | 0
1389 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Baghmundi (Zone - IX, XI & XII) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | 1098/PD | 17/06/2025 | 120 | SOUMYAJIT SAHANA | 49.71 | 0 | 0 | 0
1390 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Baghmundi (Zone - I, IV & X) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | 1427/PD | 05/08/2025 | 120 | M/S BHABATARAN MEHTA | 42.84 | 0 | 0 | 0
1391 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Balarampur (Zone - I, II & VI) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | 1099/PD | 17/06/2025 | 120 | M/S. SAJEDA ENTERPRISE | 50.11 | 0 | 0 | 0
1392 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Baghmundi (Zone - XV& XVI) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | 1092/PD | 17/06/2025 | 120 | BABA LOKNATH WORKS CONTRACTOR | 28.73 | 0 | 0 | 0
1393 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Zone-VIII Bandwan Block within Southern Sector under Purulia Division, PHE Dte. | 1521/PD | 19/08/2025 | 120 | KOUSHIK CHATTERJEE | 16.63 | 0 | 0 | 0
1394 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Scada Room and Chlorine Room at Bandwan (Zone - XV & XVI) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | 1529/PD | 19/08/2025 | 120 | ROY CONSTRUCTION | 28.49 | 0 | 0 | 0
1395 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Repairing of existing AC/UPVC distribution pipeline due to widening of PWD Road ,Laying of Rising main Pipeline for Jica Projects on Emergency basis and Relevant other allied works at Manbazar-1 under Purulia W/S Scheme under Purulia Division,PHEDte | 2203/PD | 13/12/2024 | 60 | MACHINO TECHNO | 10.39 | 0 | 0 | 100
1396 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE III , SM/18653 | New | Construction of Boundary wall & Sinking of T/well at Purulia-II,Zone-II under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1504/PD | 27/08/2024 | 45 | RANJIB GHATAK | 21.02 | 0 | 0 | 100
1397 | PURULIA | Purulia Division | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07563 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Arrah Water Supply Scheme at Raghunathpur -I Block under Purulia Division, PHE Dte.(Mouza-Arrah , Habitation-Gosaidanga,Jhariardi , Kamalasthan) (Tender No. 37/SE/PMU of 2020-21) | BP-2021-22-247 | 16/02/2022 | 0 | PREMNATH MITRA | 29.4 | 0 | 0 | 0
1398 | PURULIA | Purulia Division | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07563 | Retrofitting | Additional works for functional house hold tap connection (FHTC) including other allied works of Augmentation Arrah W/s Scheme (Zone-II) of Kashipur Block. (Tender No. 853/EE/PD of 2021-22) | BP-2021-22-264 | 28/02/2022 | 0 | SHYAMAL KUMAR DEY | 4.53 | 0 | 0 | 0
1399 | PURULIA | Purulia Division | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07563 | Retrofitting | Additional work for functional Household Tap Connection (FHTC) including other allied works of Aug. Arrah Water Supply Scheme of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-II) Gagnabad (Part-B) (Tender No.856/EE/PD of 2021-22) | BP-2021-22-265 | 28/02/2022 | 0 | M/S KARUNAMOYEE CONSTRUCTION | 3.73 | 0 | 0 | 0
1400 | PURULIA | Purulia Division | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07563 | Retrofitting | Supply & laying different dia HDPE pipe line Adra DHR to Gosaidanga under Arrah W/s Scheme. (Tender No.919/EE/PD of 2021-22) | BP-2021-22-342 | 25/03/2022 | 0 | RABIN CHANDRA CHAIL | 21.59 | 0 | 0 | 0
1401 | PURULIA | Purulia Division | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07563 | Retrofitting | Supplying & Laying different dia HDPE pipe line from Arra OHR to lower Beniasole under Arra W/S Scheme (Tender No- 927/2021-22 of EE/PD) | BP-2021-22-371 | 29/03/2022 | 0 | RABIN CHANDRA CHAIL | 37.14 | 0 | 0 | 0
1402 | PURULIA | Purulia Division | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07563 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Arrah Water Supply Scheme at Raghunathpur -I Block under Purulia Division, PHE Dte.(Mouza-Arrah , Habitation-Arrah,Barabagan) | 180/PD | 02/02/2021 | 45 | SADHAN GORAIN | 131.09 | 30.21 | 100 | 100
1403 | PURULIA | Purulia Division | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07563 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Arrah Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte.(Mouza-Gagnabad , Habitation-Bauripara, Gagnabaid ,Kalu Para ,Pakhirdanga Mouza-Ghorakata(P)Habitation-Ghorakata , Mouza-Jhariatdi (P),Habitation-Jhriadihi,Mouza-Manpura , Habitation-Ganpandi,Manpura, Mouza-Narayangar Alias Karka, Habitation-Kanka,Narayan Nagar.) | 1407/PD | 29/12/2020 | 45 | M/S KARUNAMOYEE CONSTRUCTION | 55.9 | 55.82 | 100 | 0
1404 | PURULIA | Purulia Division | Retrofitting of Arrah Water Supply Scheme at Raghunathpur-I & Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07563 | Retrofitting | Laying of HDPE pipe (PE-100, PN-10) for collecting line of riverbed Intake Well (for 1 & 2) at Narayangarh under Arrah W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 995/PD | 26/07/2023 | 60 | RABIN CHANDRA CHAIL | 6.21 | 0 | 0 | 100
1405 | PURULIA | Purulia Division | Retrofitting of Parbeliya Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07841 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Parbeliya Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-B ( Mouza- Parbeliya City , Parbelia under Bhamuria & Saltore G.P). (1364Nos.) (Tender No. 402/EE/PD of 2021-22) | BP-2021-22-243 | 16/02/2022 | 0 | ASHOK KUMAR CHATTERJEE | 49.23 | 0 | 0 | 0
1406 | PURULIA | Purulia Division | Retrofitting of Parbeliya Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07841 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Parbeliya Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-A (Mouza-Gosaindih, Parbeliya, Gopaldhawh, Parbeliya City under Bhamuria & Saltore G.P) (493 nos.) (Tender No.324/EE/PD of 2020-21) | BP-2021-22-227 | 03/02/2022 | 0 | TAPAN CHANDRA | 22.48 | 0 | 0 | 0
1407 | PURULIA | Purulia Division | Retrofitting of Parbeliya Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07841 | Retrofitting | Supplying fitting and fixing cast iron heavy type spiral stair case at Parbeliya under Parbeliya W/S Scheme of Raghunathpur Sub- Division, PHE Dte. (Tender No- 544/2022-23 of EE/PD) | BP-2022-23-394 | 20/10/2022 | 0 | SUBHAS CHANDRA MAHATO | 1.43 | 0 | 0 | 0
1408 | PURULIA | Purulia Division | Retrofitting of Parbeliya Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07841 | Retrofitting | Supplying , fitting and fixing Cast Iron heavy type spiral stair case at Parbeliya under Parbeliya W/S Scheme of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 492/RNP | 02/08/2022 | 10 | SUBHAS CHANDRA MAHATO | 1.58 | 0 | 0 | 95
1409 | PURULIA | Purulia Division | Retrofitting of Sutabai Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07565 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Sutabai W/s Scheme at Kashipur Block within Raghunathpur Sub-Division under Purulia Division PHE Dte. (3331 Nos.) (Tender No. 35/SE/PMU of 2020-21) | BP-2021-22-39 | 19/07/2021 | 0 | SANTANU BANERJEE | 66.81 | 0 | 0 | 0
1410 | PURULIA | Purulia Division | Retrofitting of Sutabai Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07565 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Sutaboi Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (3331 Nos.) | 242/PD | 10/02/2021 | 60 | SANTANU BANERJEE | 154.04 | 87.21 | 50 | 0
1411 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Providing FHTC in connection with JJM & JAL SAPNA at different habitation and extension of distribution pipeline under command area of augmentation of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Part-A : Water Supply through OHR at Baligara & Baghudi Mouza) | 183/PD | 31/01/2022 | 45 | GOUTAM CHAKRABORTY | 112.43 | 0 | 0 | 39
1412 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Providing FHTC in connection with JJM & JAL SAPNA at different habitation and extension of distribution pipeline under command area of Augmantation of Lagda W/S Scheme. (Part-A W/S through OHR at Baligara @ Baghudi Mouza) (Tender No.16/SE/PMU of 2021-22) | BP-2022-23-45 | 02/05/2022 | 0 | GOUTAM CHAKRABORTY | 16.95 | 0 | 0 | 0
1413 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Providing FHTC in connection with JJM and JAL SWAPNA at different habitation and extension of distribution pipe line under command area of Augmentation of Lagda Water Supply Scheme of Purulia Sadar Sub- Division, PHE Dte. [Part-B water supply through direct pumping at Lagda mouza] (Tender No- 21/2021-22 of SE/PMU/WBPWSP(P) ) | BP-2022-23-145 | 22/07/2022 | 0 | SADHAN GORAIN | 94.59 | 0 | 0 | 0
1414 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Providing FHTC in connection with JJM & JAL SAPNA at different habitation and extension of distribution pipeline under command area of augmentation of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Part-A : Water Supply through OHR at Baligara & Baghudi Mouza) (Tender No.16/SE/PMU of 2021-22) (Ad-interim) | BP-2022-23-37 | 28/04/2022 | 0 | GOUTAM CHAKRABORTY | 50 | 0 | 0 | 0
1415 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Continuation work for Preparation of DPR (consultancy work) in connection with the Functional Household Tap Connection of different existing PWSS (Lagda W/S Scheme & Barabazar W/S Scheme block-Purulia-I, Barabazar) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 848/2021-22 of EE/PD) | BP-2022-23-110 | 16/07/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 1.91 | 0 | 0 | 0
1416 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Tap Connection of different existing PWSS (Lagda W/S Scheme & Barabazar W/S Scheme block-Purulia-I, Barabazar) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 357/2021-22 of EE/PD) | BP-2022-23-109 | 16/07/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 1.05 | 0 | 0 | 0
1417 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | New sinking of 2 (Two) nos 200 mm dia river bed tubewell (Horizontal) at Kasabati river alongwith laying of 100 mm dia G.I. collecting line with other allied works of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 1586/PD | 17/12/2021 | 30 | MANATOSH SINGH | 11.25 | 0 | 0 | 55
1418 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Laying of different dia distribution pipeline (Additional length) in connection with JJM and JAL SAPNA at different habitation under command area of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Part-A : Water Supply through OHR at Baligara & Baghudi Mouza) | 1400/PD | 01/09/2022 | 45 | GOUTAM CHAKRABORTY | 12.14 | 0 | 0 | 100
1419 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Laying of distribution pipeline including placement of sluice valves at different places for providing 47 nos. Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at BALIGARA village under command area of Augmentation of LAGDA Water Supply Scheme of Purulia-I Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1817/PD | 06/12/2022 | 90 | M/S CHAKRABORTY CONSTRUCTION | 14.17 | 0 | 0 | 95
1420 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Laying of 150 mm dia DI Rising Main in connection with Jal Jeevan Mission (JJM) for Augmentation of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 175/PD | 07/02/2023 | 30 | M/S CHAKRABORTY CONSTRUCTION | 21.28 | 0 | 0 | 100
1421 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Repairing of DI rising main pipeline & renovation of R.C.C. Elevated Reservoir of capacity 135 Cum (Intze Type), at headwork site of Lagda W/S Scheme including repairing of Pump house cum switch room (Unit-I&II) including other allied works in connection with Jal Jeevan Mission (JJM) for Augmentation of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 280/PD | 27/02/2023 | 30 | M/S CHAKRABORTY CONSTRUCTION | 10.29 | 0 | 0 | 100
1422 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Repairing of existing 200mm and 150 mm DI rising main pipeline and Providing Functinal household tap connection (FHTC) at Baligara Village and Laying of HDPE pipe and MS Casing Pipe and other allied works under Lagda W/S Scheme under Purulia Division, PHE Dte | 1351/PD | 13/09/2023 | 30 | GOUTAM CHAKRABORTY | 14.54 | 0 | 0 | 100
1423 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Material Requisition To Resource Division | 1507/PD | 13/12/2021 | 0 | Resource Division | 51.27 | 0 | 0 | 0
1424 | PURULIA | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Material Requisition To Resource Division | 610/PMD | 01/06/2023 | 0 | Resource Division | 0.86 | 0 | 0 | 0
1425 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/4524 bill paid for the month of Sep,22 to June,22. | BP-2023-24-334 | 02/08/2023 | 0 | ANUP KUMAR SAHA | 2.33 | 0 | 0 | 0
1426 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Indian Railways Miscellaneous collection. | BP-2022-23-5171 | 02/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 5.23 | 0 | 0 | 0
1427 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Indian Railways Miscellaneous collection. | BP-2022-23-5177 | 02/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 6.09 | 0 | 0 | 0
1428 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/7171 bill paid for the month of May,22 to June,22. | BP-2023-24-335 | 02/08/2023 | 0 | NIRUPAMA DEY | 0.68 | 0 | 0 | 0
1429 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Bank guarantee of Proposed Way Leave permission of Water pipe line Crossing for application ID No SER ADA-2022 WL 38, SER ADA-2022 WL 42. SER ADA 2022 WL 43, SER- ADA 2022 WL-55. SER-ADA-2022-WL-56. SER-ADA-2022 WL-60, SER ADA 2022 WL-61. |  | 08/02/2023 | 0 | F.A & C.A.O /S.E.RLY /GARDEN REACH-43 | 5 | 0 | 0 | 0
1430 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Kotshila Mouza) (Under Lagda W/S Scheme) | 514/PD | 16/03/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 9.13 | 0 | 0 | 0
1431 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Construction of pathway at Ajodhya Pump House under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. Length : 115.00 Mtr. Width : 2.40 Mtr.(Under Lagda W/S Scheme) | 495/PD | 16/03/2024 | 30 | TUMPA GORAIN | 4.13 | 0 | 0 | 0
1432 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Barudi Mouza) (Under Lagda W/S Scheme) | 512/PD | 16/03/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 11.24 | 0 | 0 | 0
1433 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Chayadih Mouza) (Under Lagda W/S Scheme) | 516/PD | 16/03/2024 | 60 | SABYASACHI MISHRA | 7.82 | 0 | 0 | 70
1434 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Providing FHTC in connection with JJM & JAL SAPNA at different habitation and extension of distribution pipeline under command area of augmentation of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Part-B : Water Supply through direct pumping at Lagda Mouza) | 217/PD | 08/02/2022 | 45 | SADHAN GORAIN | 237.24 | 0 | 0 | 100
1435 | PURULIA | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Lagda Water Supply scheme Block Purulia-I under PMD PHE Dte. District Purulia. | 164/PMD | 07/03/2022 | 30 | ASHUTOSH DAS AND CO. | 20.5 | 0 | 0 | 90
1436 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works in connection with Jal Jeevan Mission (JJM) and JAL SAPNA for Augmentation of Lagda W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 1721/PD | 22/11/2022 | 100 | SWASTIK ENTERPRISE | 16.82 | 0 | 0 | 65
1437 | PURULIA | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Supply delivery and installation of voltage stabilizer at OHR site of Lagda W/S under PMD PHE dte in the District of Purulia. | 210/PMD | 28/02/2023 | 672 | TUSHAR GHOSH | 7.07 | 0 | 0 | 90
1438 | PURULIA | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Supply delivery and installation of voltage stabilizer at Augmentation of Lagda W/S under PMD PHE dte in the District of Purulia. | 308/PMD | 16/03/2023 | 30 | GOUTAM CHAKRABORTY | 11.85 | 0 | 0 | 70
1439 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Lagda river site for Augmentation of Lagda W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | 573/PD | 19/04/2023 | 90 | SWASTIK ENTERPRISE | 14.23 | 0 | 0 | 80
1440 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Construction of meter room, panel room,undercut pump house & surface drain with other allied works at Lagda OHR Site for Augmentation of Lagda W/S Scheme under Purulia sader Sub-Division, under Purulia Division, PHE Dte. | 554/PD | 13/04/2023 | 45 | CHITTARANJAN MAJHI | 13.87 | 0 | 0 | 100
1441 | PURULIA | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Providing internal and external illumination arrangement at existing at OHR site of Lagda W/S under PMD, PHE Dte. in the District of Purulia. | 650/PMD | 08/06/2023 | 60 | TUSHAR GHOSH | 6.13 | 0 | 0 | 90
1442 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Supply & delivery DI Specials for Newly Laying of Rising Main (DI-K9) Pipe line LagdaRiversite Pump House to 100 Cum Capacity CWR at Lagda OHR Site under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte. PHE Dte. | 1706/PD | 04/12/2023 | 30 | M/S CHAKRABORTY CONSTRUCTION | 1.46 | 0 | 0 | 100
1443 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Puncha OHR Site (Bahadurpur) for Augmentation of Lagda W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | 662_PD | 17/05/2023 | 534 | ASHOKE ADHIKARY | 14.24 | 0 | 0 | 60
1444 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Making bypass arrangement & other allied works at lagda OHR site of Lagda W/S Scheme under Purulia Division, PHE Dte. | 1378/PD | 25/07/2024 | 60 | M/S CHAKRABORTY CONSTRUCTION | 4.32 | 0 | 0 | 100
1445 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Supplying & laying Parallel HDPE pipe and Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and other allied works of Puncha W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte.( under Lagda Water Supply Scheme ) | 346/PD | 04/03/2024 | 186 | JAYANTA KUMAR MONDAL | 21.97 | 0 | 0 | 100
1446 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Cleaning & Fencing at Ajodhya Pump House Site under Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(Under Lagda W/S Scheme) | 497/PD | 16/03/2024 | 45 | SARKAR ENTERPRISE | 1.08 | 0 | 0 | 100
1447 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and Laying of Branch distribution Pipeline of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Goaladih Mouza] (Under Lagda W/S Scheme) | 513/PD | 16/03/2024 | 60 | SOUMITRA CHAKRABORTY | 4.43 | 0 | 0 | 100
1448 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Uparbatri Mouza) (Under Lagda W/S Scheme) | 515/PD | 16/03/2024 | 60 | SOUVIK MANDAL | 5.55 | 0 | 0 | 100
1449 | PURULIA | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | New connection for Augmentation OHR site of Lagda W/S | BP-23-24-301 | 05/03/2024 | 0 | WBSEDCL PURULIA | 7.04 | 0 | 0 | 0
1450 | PURULIA | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | New connection for Augmentation of River site of Lagda W/S, block- Purulia | BP-23-24-298 | 05/03/2024 | 0 | WBSEDCL PURULIA | 7.63 | 0 | 0 | 0
1451 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Supply of stationery materials for office use | BP-2024-25-531 | 20/11/2024 | 0 | KETIKA CONSUMERS CO-OPERATIVE STORES LTD | 2.49 | 0 | 0 | 0
1452 | PURULIA | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Supply and lowering of submersible pump motor sets at at newly constructed River Bed Tube well with supply of necessary substitutes at Lagda w/s scheme under PMD, PHE Dte. in the District of Purulia. | 130/PMD | 20/02/2023 | 1046 | SANTANU BANERJEE | 26.09 | 0 | 0 | 40
1453 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum at Puncha OHR site of Lagda W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | 527_PD | 30/03/2022 | 100 | SOUVIK MANDAL | 10.83 | 0 | 0 | 0
1454 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Repairing of DI rising main pipeline & repairing of FHTC & construction of pathway including other allied works of existing godown, store room, pump room & buildings at Purulia Sadar Sub-Division under Augmentation of Lagda Water supply scheme of Purulia Division, PHE Dte. | 1082/PD | 07/06/2024 | 60 | SIKHA ENTERPRISE | 43.73 | 0 | 0 | 100
1455 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Continuation of work for Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Southern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte. w.e.f. 14/09/2025 to 15/03/2025 | 515/PSD | 11/09/2025 | 183 | MALAY BANDYOPADHYAY | 0.9 | 0 | 0 | 0
1456 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Continuation work for Hiring of Euro-4 Diesel car (BS-IV) on daily rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Northern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte. (w.e.f 14/09/2025 to 15/03/2025) | 523/PSD | 11/09/2025 | 183 | SHIVA ENTERPRISES | 0.9 | 0 | 0 | 0
1457 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | New sinking of 3 (Three) nos 200 mm dia river bed tubewell (Horizontal) at Kasabati river alongwith laying of 100 mm dia G.I. collecting line with other allied works of Lagda W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte. | 1585/PD | 17/12/2021 | 30 | KOUSHIK CHATTERJEE | 17.14 | 0 | 0 | 55
1458 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum at Puncha river site pump house of Lagda W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | 526/PD | 30/03/2022 | 200 | KM ENTERPRISES | 10.81 | 0 | 0 | 100
1459 | PURULIA | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Supply delivery and installation of centrifugal pumping machineries, Flowmeter with necessary substitutes and allied electrical panel at Lagda w/s scheme under PMD, PHE Dte. in the District of Purulia. | 131/PMD | 20/02/2023 | 701 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 69.89 | 0 | 0 | 70
1460 | PURULIA | Purulia Division | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Interconnection of new & old DI rising main with new pump house & other allied works for direct supply & pathway of Lagda Water Supply Scheme under Purulia Division, PHE Dte. | 2123/PD | 05/12/2024 | 45 | M/S CHAKRABORTY CONSTRUCTION | 9.77 | 0 | 0 | 100
1461 | PURULIA | Purulia Mechanical | Augmentation of Lagda PWSS for providing Functional Household Tap Connection (FHTC) , SM/09036 | Augmentation | Supply, delivery and installation of Submersible Pump motor and other related works for Augmentation work of Lagda w/s scheme (OHR Site) under Purulia Mechanical Division P.H.E. Dte. | 373/PMD | 04/03/2024 | 515 | GOUTAM CHAKRABORTY | 4.73 | 0 | 0 | 50
1462 | PURULIA | Purulia Division | Water Supply Arrangement to 119 nos. sourceless schools located outside of the command area of existing PWS Schemes under Purulia Division, PHE Dte. , SM/10257 | School | Water supply Tap Connection Arrangement for 22 nos AWC within Barabazar Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | 1199/PD | 12/08/2022 | 45 | MS D.PALIT AND CO. | 174.05 | 0 | 0 | 85
1463 | PURULIA | Purulia Division | Water Supply Arrangement to 119 nos. sourceless schools located outside of the command area of existing PWS Schemes under Purulia Division, PHE Dte. , SM/10257 | School | Installation of Big-Dia D.T.H. Tube Well (200mm x 165mm) by Robotic DTH Rigs for drilling upto 1200 ft or small form factor trolly mounted rig with trolly mounted compressor suitable for narrow 68 inch wide roads considering 200mt Depth in diferent school of different Blocks (PHASE-1) of the District Purulia under Purulia RWS Sub Division,PHE Dte. under Purulia Division, PHE Dte. | 112/PD | 20/01/2023 | 45 | MS D.PALIT AND CO. | 96.12 | 0 | 0 | 100
1464 | PURULIA | Purulia Division | Water Supply Arrangement to 119 nos. sourceless schools located outside of the command area of existing PWS Schemes under Purulia Division, PHE Dte. , SM/10257 | School | Installation of Big-Dia Odex-165 (Simultaneous driving of casing pipe) 165 mm dia Tube Well considering 120mt Depth in diferent school of different blocks of the District Purulia JJM under Purulia RWS Sub-Division,PHEDte. under Purulia Division, PHE Dte. | 540/PD | 18/03/2024 | 60 | S N POLYMERS PVT LTD | 92.73 | 0 | 0 | 0
1465 | PURULIA | Purulia Division | Water Supply Arrangement to 119 nos. sourceless schools located outside of the command area of existing PWS Schemes under Purulia Division, PHE Dte. , SM/10257 | School | Water supply Tap Connection Arrangement for 47 nos School upto 200 Students, 4 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Joypur Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | 675/PD | 25/04/2022 | 45 | EQUIPMENTS AND SPARES AGENCIES | 223.53 | 0 | 0 | 100
1466 | PURULIA | Purulia Division | Water Supply Arrangement to 119 nos. sourceless schools located outside of the command area of existing PWS Schemes under Purulia Division, PHE Dte. , SM/10257 | School | Water supply Tap Connection Arrangement for 20 nos AWC within Barabazar Block (Part-D) of Purulia District under Purulia Division, PHE Dte. | 1154/PD | 01/08/2022 | 45 | GOENKA ENTERPRISE | 158.27 | 0 | 0 | 100
1467 | PURULIA | Purulia Division | Water Supply Arrangement to 119 nos. sourceless schools located outside of the command area of existing PWS Schemes under Purulia Division, PHE Dte. , SM/10257 | School | Water supply Tap Connection Arrangement for 6 nos AWC within Jhalda-II Block (Part-F) of Purulia District under Purulia Division, PHE Dte. | 417/PD | 16/03/2022 | 45 | SINGHA ENTERPRISE | 47.29 | 0 | 0 | 100
1468 | PURULIA | Purulia Division | Water Supply Arrangement to 119 nos. sourceless schools located outside of the command area of existing PWS Schemes under Purulia Division, PHE Dte. , SM/10257 | School | Providing necessary water supply arrangement within school with connection from new Big-Dia D.T.H. Tube Well (200mm x 165mm) considering 200mt Dept and GI pipe of adequate dia and PVC pipes (medium duty confirming to the ASTMD-1785) and length where necessary 6 nos. alloy Iron with brass spindle bib cock/ stop cock at toilet and kitchen, gunmetal wheel valves, supplying submersible pumping machinery 1.0 HP of Crompton/ KSB or other renowned make conforming to latest BIS codes with all necessary electrical connections supplying PVC water storage tank of approved quality of total capacity of 2000 ltr capacity.(4nos. 500ltrs tank) ( To be installed at roof top of school building ) all complete. Block:-Santuri, Site:-i) Talberia Primary School(Santuri GP), ii) Gumra Pry School ( Tarabari G.P), iii) Lapahari pry School (Tarabari G.P) Block:-Jhalda-II, Site:- i) Rigid HIgh School (Rigid G.P) | 526/PD | 16/03/2024 | 60 | SINGHA ENTERPRISE | 20.78 | 0 | 0 | 100
1469 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Bandwan Block (Part-K) of Purulia District under Purulia Division, PHE Dte. (Tender No.60/EE/PD of 2022-23) | BP-2022-23-436 | 28/11/2022 | 0 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 12.93 | 0 | 0 | 0
1470 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Bandwan Block (Part-L) of Purulia District under Purulia Division, PHE Dte. (Tender No.61/EE/PD of 2022-23) | BP-2022-23-435 | 28/11/2022 | 0 | HARI NARAYAN YADAV CONSTRUCTION CO | 8.89 | 0 | 0 | 0
1471 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Bandwan Block (Part-D) of Purulia District under Purulia Division, PHE Dte. (Tender No.70/SE/PMU of 2022-23) | BP-2022-23-337 | 29/09/2022 | 0 | J.S. CONSTRUCTION | 28.62 | 0 | 0 | 0
1472 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Bandwan Block (Part-L) of Purulia District under Purulia Division, PHE Dte. | 752/PD | 02/05/2022 | 45 | HARI NARAYAN YADAV CONSTRUCTION CO | 23.72 | 0 | 0 | 0
1473 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 9 no AWC within Bandwan Block (Part-F) of Purulia District under Purulia Division, PHE Dte. | 745/PD | 02/05/2022 | 45 | BOSE CONSTRUCTION | 70.87 | 0 | 0 | 0
1474 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 26 nos AWC within Bandwan Block ) of Purulia District under Purulia Division, PHE Dte. | 33/PD | 09/01/2023 | 45 | ROY CONSTRUCTION | 14.05 | 0 | 0 | 0
1475 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Bandwan Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | 748/PD | 02/05/2022 | 45 | JYOTY SOLAR POWER | 47.51 | 0 | 0 | 0
1476 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Bandwan Block (Part-E) of Purulia District under Purulia Division, PHE Dte. (SL - 4) | 1158/PD | 01/08/2022 | 45 | M/S. BIMALENDU BOSE | 158.35 | 0 | 0 | 100
1477 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Bandwan Block (Part-D) of Purulia District under Purulia Division, PHE Dte. | 1157/PD | 01/08/2022 | 45 | J.S. CONSTRUCTION | 158.35 | 0 | 0 | 100
1478 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Bandwan Block (Part-M) & 2 nos AWC within Bandwan Block (Part-N) of Purulia District under Purulia Division, PHE Dte.(Phase-I) | 1709/PD | 22/11/2022 | 45 | GOUTAM CHAKRABORTY | 66.41 | 0 | 0 | 0
1479 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Bandwan Block (Part-A) of Purulia District under Purulia Division, PHE Dte.(Phase-II) | 1710/PD | 22/11/2022 | 45 | PRINCE INDUSTRIES ( INDIA) | 91.77 | 0 | 0 | 0
1480 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Bandwan Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | 750/PD | 02/05/2022 | 45 | MEGA SOLAR ENERGY | 47.47 | 0 | 0 | 0
1481 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Bandwan Block (Part-K) of Purulia District under Purulia Division, PHE Dte. | 751/PD | 02/05/2022 | 45 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 23.73 | 0 | 0 | 0
1482 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply tap connection arrangement for 09 nos. AWC within Bandwan block (Part-F) of Purulia District under Purulia Division, PHE Dte. [Tender No 213/2022-2023 of EE/PD] | BP-2022-23-533 | 11/01/2023 | 0 | BOSE CONSTRUCTION | 25.99 | 0 | 0 | 0
1483 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Supply and delivery of 200 mm dia UPVC pipe for Purulia-I Block and other Blocks at Drilling Store/Site under Purulia Mechanical Division, P.H.E Dte. (Tender No.262/EE/PMD of 2022-23) | BP-2022-23-512 | 22/12/2022 | 0 | COMBINE ENTERPRISES | 16.67 | 0 | 0 | 0
1484 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Supply of Fuel & lubricant bill for AWC Bandwan Block. | BP-2022-23-850 | 31/03/2023 | 0 | M/S SHANKAR AUTO SERVICE | 8.26 | 0 | 0 | 0
1485 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Bandwan Block (Part-E) of Purulia District under Purulia Division, PHE Dte. (SL - 4) (Tender No.69/EE/PD of 2022-23) | BP-2022-23-331 | 29/09/2022 | 0 | M/S. BIMALENDU BOSE | 38.12 | 0 | 0 | 0
1486 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply tap connection arrangement for 11 nos. AWC within Bandwan block (Part-C) of Purulia District under Purulia division, PHE Dte. (Phase-III) [Tender No 837/2022-2023 of EE/PD] | BP-2022-23-532 | 11/01/2023 | 0 | BOSE CONSTRUCTION | 34.13 | 0 | 0 | 0
1487 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Bandwan Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | 749/PD | 02/05/2022 | 45 | SOUMITRA CHAKRABORTY | 47.47 | 0 | 0 | 100
1488 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Bandwan Block (Part-C) of Purulia District under Purulia Division, PHE Dte.(Phase-III) | 1711/PD | 22/11/2022 | 45 | BOSE CONSTRUCTION | 91 | 0 | 0 | 100
1489 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Bandwan Block In Purulia District under Purulia Division, PHE.Dte. , SM/10283 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Bandwan Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | 1250/PD | 30/08/2022 | 945 | PREMNATH MITRA | 197.98 | 0 | 0 | 100
1490 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Manguria Lalpur GP, Hura Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 705/PMD | 17/10/2022 | 7 | SAIBAL SARKAR | 6.33 | 0 | 0 | 0
1491 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Construction of Rig board tube well (200mmX165mm) by DTH method at Keshargarh GP is Hura block under Purulia Mechanical Division PHE Dte. (T/N 138/EE/PMD of 2022-23) |  | 13/08/2022 | 0 | MS D.PALIT AND CO. | 38.15 | 0 | 0 | 0
1492 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Construction of Rig bored tube-well (200mmx165mm) by DTH method at Ludhurka GP at Hura Block under Purulia Mechanical Division PHE Dte. (Tender No.142/EE/PMD of 2022-23) | BP-2022-23-260 | 15/09/2022 | 0 | RABINDRANATH KHAN | 10.46 | 0 | 0 | 0
1493 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method at Keshargarh GP, Hura Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 453/PMD | 04/07/2022 | 15 | M/S D. PALIT & CO. | 38.15 | 0 | 0 | 0
1494 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method at Ladhurka GP, Hura Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 455/PMD | 04/07/2022 | 7 | RABINDRA NATH KHAN | 12.72 | 0 | 0 | 0
1495 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Hura Block ) of Purulia District under Purulia Division, PHE Dte. | 29/PD | 09/01/2023 | 45 | CHANDAN CHATTERJEE | 6.66 | 0 | 0 | 0
1496 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Execution of the yield test at Jabrrah, Manguria - Lalpur , Lakhanpur , Daldali GP in Hura Block within the district of Purulia under code SM10275 under PMD, PHE, Dte. | 20/PMSD(Drilling) | 31/01/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0 | 0
1497 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Execution of the yield test at different GP in Hura Block within the district of Purulia under code SM10275 under PMD, PHE, Dte. | 25/PMSD(Drilling) | 01/02/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0 | 0
1498 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Construction of Rigbored Tube well (200mmx 165mm) by DTH method in different sourceless AWC at Hura Block where adjacent road is narrow and critical under Purulia Mechanical Division PHE. Dte. in the District of Purulia | 69/PMD | 31/01/2023 | 20 | KHITISH CH. PATHAK | 50.46 | 0 | 0 | 0
1499 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Washing and developing of tube well for AWC programme at Hura and other block under PMD, PHE, Dte.(2nd call) | 416/PMD | 12/04/2023 | 15 | SUMIT KR. CHAKRABORTY | 3.58 | 0 | 0 | 0
1500 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Supply & Delivery of 12 Volt Battery for Truck engine,supporting vehicle & 18D/AR Rig unit under Purulia Mechanical Division ,PHE Dte. | 108/PMSD(DRILLING) | 21/04/2022 | 7 | M/S UJJAL DIESEL SERVICE | 0.65 | 0 | 0 | 0
1501 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Repairing, general maintenance and all other allied works of rig mounted Truck AUT 5202 under PMD, PHE Dte. | 55/PMSD (Drilling) | 16/03/2022 | 15 | M/S UJJAL DIESEL SERVICE | 1.88 | 0 | 0 | 0
1502 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Water supply Tap Connection Arrangement for 9 no AWC within Hura Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | 763/PD | 02/05/2022 | 45 | BISWESWAR CONSTRUCTION | 40.63 | 0 | 0 | 100
1503 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Execution of Yield Test of R.B.T. Well at different sites under PMD,PHE, Dte. | 216/PMSD (Drilling) | 05/08/2022 | 3 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 4.55 | 0 | 0 | 0
1504 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Lakhanpur GP, Hura Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 708/PMD | 17/10/2022 | 15 | SWAPAN MANDAL | 15.87 | 0 | 0 | 0
1505 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Jabarrah GP Hura Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 707/PMD | 17/10/2022 | 25 | SUMIT KR. CHAKRABORTY | 41.18 | 0 | 0 | 0
1506 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within HURA Block (Part-B-I) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | 1856/PD | 13/12/2022 | 45 | HI-LIGHT ELECTRONICS | 51.01 | 0 | 0 | 100
1507 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 12 nos AWC within Hura Block (Part-A), 2 nos AWC within Hura Block (Part-C) & 1 no AWC within Hura Block (Part-D)of Purulia District under Purulia Division, PHE Dte.(Phase-I)" | 1735/PD | 22/11/2022 | 45 | KRISHNA CONSTRUCTION AND ORDER SUPPLIER | 70.95 | 0 | 0 | 100
1508 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Hura GP, Hura Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 706/PMD | 17/10/2022 | 30 | M/S D. PALIT & CO. | 72.86 | 0 | 0 | 0
1509 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Daldali GP and Rakhera-Bishpuria GP, Hura Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 678/PMD | 28/09/2022 | 25 | KOUSHIK CHATTERJEE | 57.04 | 0 | 0 | 0
1510 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within HURA Block (Part-B-II) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | 1857/PD | 13/12/2022 | 45 | MADHU SUDAN RAKSHIT | 51.93 | 0 | 0 | 100
1511 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Construction of Rig board tube well (200mmX165mm) by DTH method at Keshargarh GP in Hura block under Purulia Mechanical Division PHE Dte. (Tender No 138/EE/PMD of 2022-23) | BP-2022-23-206 | 24/08/2022 | 0 | MS D.PALIT AND CO. | 38.15 | 0 | 0 | 0
1512 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Jabarrah GP Hura Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.214/EE/PMD of 2022-23) | BP-2022-23-455 | 02/12/2022 | 0 | SUMIT KUMAR CHAKRABORTY | 33.76 | 0 | 0 | 0
1513 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Hura GP Hura Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.215/EE/PMD of 2022-23) | BP-2022-23-454 | 02/12/2022 | 0 | MS D.PALIT AND CO. | 46.16 | 0 | 0 | 0
1514 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Lakhanpur GP, Hura Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.225/EE/PMD of 2022-23) | BP-2022-23-453 | 02/12/2022 | 0 | SWAPAN MANDAL | 10.1 | 0 | 0 | 0
1515 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Construction of rigbored tubewell (200 mm x 165 mm) by DTH method in different sourceless AWC at Manguria-Lalpur GP, Hura Block under PMD, PHE Dte. in the District of Purulia [Tender No 216/2022-2023 of EE/PMD] | BP-2022-23-498 | 22/12/2022 | 0 | SAIBAL SARKAR | 5.46 | 0 | 0 | 0
1516 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Daldali and R - Bispuria GP, Hura Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.217/EE/PMD of 2022-23) | BP-2022-23-451 | 02/12/2022 | 0 | KOUSHIK CHATTERJEE | 37.5 | 0 | 0 | 0
1517 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Execution of the yield test at different GPs in Hura within the district of Purulia under PMD, PHE, Dte. | 128/PMSD(W/S) | 27/03/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0 | 0
1518 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewells sinked at various Schools & AWCs of . Hura & Purulia-II Blocks under Purulia Division ,PHE,Dte. | 1735/PD | 04/12/2023 | 30 | CHATTERJEE CONSTRUCTION | 10.62 | 0 | 0 | 0
1519 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Bandwan Water Supply Scheme of Bandwan Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Jitan Mouza)Bamandiha Village(From node J-851 to J-864)(Part-B) | 150/PSD | 04/04/2022 | 25 | CHATTERJEE CONSTRUCTION | 4.59 | 0 | 0 | 100
1520 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Hura Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | 764/PD | 02/05/2022 | 45 | BISWESWAR CONSTRUCTION | 27.08 | 0 | 0 | 100
1521 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | 146/PD | 03/02/2023 | 45 | BALAJI UDDYOG | 164.99 | 0 | 0 | 100
1522 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Hura Block In Purulia District under Purulia Division, PHE.Dte. , SM/10275 | Anganwadi | Water supply Tap Connection Arrangement for 9 no AWC within Hura Block (Part-F) of Purulia District under Purulia Division, PHE Dte. | 762/PD | 02/05/2022 | 45 | NANIGOPAL DEY | 40.4 | 0 | 0 | 100
1523 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Continuation work order for Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Kotshila W/S Scheme block-Jhalda-II ) to be augmentation/ Rejuvenation under Purulia Division, PHE Dte. (Tender No- 971/2021-22 of EE/PD) | BP-2022-23-139 | 19/07/2022 | 0 | HORIZEN | 1.99 | 0 | 0 | 0
1524 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Chitarpur) (Tender No.506/2022-23 of EE/PD) | BP-2022-23-312 | 26/09/2022 | 0 | NANIGOPAL DEY | 8.78 | 0 | 0 | 0
1525 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | New Sinking of 02 (Two) No. 200 mm dia river bed tube wells (horizontal) at river bed of Kansai along with laying of 100 mm dia GI collecting line other allied works of Kotshila Water Supply Scheme under Purulia Division, PHE dte.(Tender No- 126/2022-23 of EE/PD) | BP-2022-23-128 | 19/07/2022 | 0 | KOUSHIK CHATTERJEE | 5.39 | 0 | 0 | 0
1526 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Barudi) (Tender No- 282/2022-23 of EE/PD) | BP-2022-23-377 | 19/10/2022 | 0 | ANUP KUMAR SAHA | 32.08 | 0 | 0 | 0
1527 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name- Kotshila) (Tender No- 281/2022-23 of EE/PD) | BP-2022-23-376 | 19/10/2022 | 0 | ANUP KUMAR SAHA | 50.47 | 0 | 0 | 0
1528 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | New Sinking of 03 (Three) No. 200 mm dia river bed tube wells (horizontal) at river bed of Kansai along with laying of 100 mm dia GI collecting line with construction of 01 nos common manifold chamber at kotshila river site of Kotshila Water Supply Scheme under Purulia Division, PHE dte.(Tender No- 124/2022-23 of EE/PD) | BP-2022-23-129 | 19/07/2022 | 0 | BOSE CONSTRUCTION | 8.56 | 0 | 0 | 0
1529 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Kotshila W/S Scheme block-Jhalda-II ) to be augmentation/ Rejuvenation under Purulia Division, PHE Dte. (Tender No- 544/2021-22 of EE/PD) | BP-2022-23-140 | 19/07/2022 | 0 | HORIZEN | 7.98 | 0 | 0 | 0
1530 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE Pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Chayadih) | 872/PD | 23/05/2022 | 60 | APURBA PATRA | 46.84 | 0 | 0 | 70
1531 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Laying of 250 mm and 150 mm dia DI (K9) pipe as rising main from riverside pump house site to OHR site under Kotshila Water Supply Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 849/PD | 23/05/2022 | 60 | GLOBAL CONSTRUCTION | 75.85 | 0 | 0 | 0
1532 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Kachahatu) Zone-II | 1079/PD | 12/07/2022 | 45 | PRAVAT SARKAR | 111.73 | 0 | 0 | 65
1533 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Panroma) Zone-ii | 1054/PD | 08/07/2022 | 45 | M/S. MSS RISING ENTERPRISE | 36.04 | 0 | 0 | 65
1534 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Jiudaru) | 1043/A/PD | 07/07/2022 | 60 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 64.02 | 0 | 0 | 35
1535 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE Pipe line for Distribution System under augmentation of augumentation Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Hetbatari) | 1226/PD | 22/08/2022 | 30 | SARKAR ENTERPRISE | 15.98 | 0 | 0 | 25
1536 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE Pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Nowahatu) | 1056/PD | 08/07/2022 | 45 | MOLLA ENTERPRISE | 23.78 | 0 | 0 | 0
1537 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Ghatketia) | 1057/PD | 08/07/2022 | 30 | ROY CONSTRUCTION | 9.1 | 0 | 0 | 0
1538 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Construction of Transformer base for Installing Transformer and Cable Trench for HT & LT Line at Kotshila Pump House Campus under Kotshila W/S Scheme under Purulia Sadar Sub-Division under Purulia Division,PHE DTE . | 1807/PD | 06/12/2022 | 45 | SAIBAL SARKAR | 15.18 | 0 | 0 | 0
1539 | PURULIA | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supply, delivery and installation 12kg/cm2 chlorine machine with others works for Augmentation of Kotshila w/s scheme under Purulia Mechanical Division, PHE, Dte. in purulia district. | 77/PMD | 01/02/2023 | 30 | R K ENTERPRISES | 3.6 | 0 | 0 | 91
1540 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division underPurulia Division, PHE Dte (Goaladih Mouza) | 179/PD | 07/02/2023 | 30 | SB CONSTRUCTION | 6.47 | 0 | 0 | 90
1541 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | New sinking of 3 (Three) nos 200 mm dia river bed tubewell (Horizontal) at Kangshabati river alongwith laying of 100 mm dia G.I. collecting line with Construction of 1 nos Common Manifold Chamber at Kotshila river site of Kotshila W/S Scheme under Purulia Division, PHE Dte. | 862/PD | 23/05/2022 | 30 | BOSE CONSTRUCTION | 23.05 | 0 | 0 | 100
1542 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | New sinking of 2 (Two) nos 200 mm dia river bed tubewell (Horizontal) at Kangshabati river alongwith laying of 100 mm dia G.I. collecting line with other allied works of Kotshila W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte. | 861/PD | 23/05/2022 | 30 | KOUSHIK CHATTERJEE | 11.39 | 0 | 0 | 100
1543 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Laying of 300mm dia distribution main & Laying of 90mm dia Parallel line at Murulahar Mouza of Kotshila Water Supply Scheme under Purulia Division, PHE Dte | 294/PD | 27/02/2023 | 45 | KM ENTERPRISES | 52.23 | 0 | 0 | 100
1544 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Laying of 280mm dia distribution main & Laying of 90mm dia Parallel line at Murulahar Mouza of Kotshila Water Supply Scheme under Purulia Division, PHE Dte | 293/PD | 27/02/2023 | 45 | GOUTAM CHAKRABORTY | 81.35 | 0 | 0 | 100
1545 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Laying of Pipeline from Kachahatu Riversite Pump House to Banahata Mouza for Providing FHTC at Kotshila Water Supply Scheme under Purulia Division, PHE Dte. | 177/PD | 07/02/2023 | 45 | SUBODH PRAMANIK | 88.16 | 0 | 0 | 100
1546 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Laying of Collecting line from Kanshabati Riverbed to Manifold Chamber for implementaion of JJM project of Kotshila W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 359/PD | 14/03/2023 | 30 | BOSE CONSTRUCTION | 7.65 | 0 | 0 | 100
1547 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Laying of Collecting line from Kanshabati Riverbed to Kachahatu Pump house for implementation of JJM Project of Kotshila W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 358/PD | 14/03/2023 | 30 | KOUSHIK CHATTERJEE | 3.1 | 0 | 0 | 100
1548 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Material Requisition To Resource Division | 969/PD | 21/06/2022 | 0 | Resource Division | 369.8 | 0 | 0 | 0
1549 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Material Requisition To Resource Division | 968/PD | 21/06/2022 | 0 | Resource Division | 177.02 | 0 | 0 | 0
1550 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Car bill paid for office purpose for the month of Jan & Feb,23 against Vehicle Reg. No. WB/55A/7171. |  | 30/11/2022 | 0 | NIRUPAMA DEY | 0.63 | 0 | 0 | 0
1551 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Indian Railways Miscellaneous collection. | BP-2022-23-5172 | 02/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 37.72 | 0 | 0 | 0
1552 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Indian Railways Miscellaneous collection. | BP-2022-23-5173 | 02/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 8.79 | 0 | 0 | 0
1553 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Bill paid for Way leave Facility Charge of Rail Bhumi Crossing Seva (IR-RBCS) under South Eastern Railway, Ranchi Divison against Application ID:SER-RNC-2022-WL-8, 9, 10 dt.22/11/2022. | BP-2022-23-459 | 05/12/2022 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 33.83 | 0 | 0 | 0
1554 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Restoration of only Hard Shoulder of Purulia Ranchi Road under PWD Purulia Division from Rakbore more to Adardih Bridge after laying of Drinking water pipeline of Kotshila W/S Scheme under Jal-Jeban Mission of PHE Dte, Purulia in the District of Purulia during the year 2022-2023. | BP-2023-24-209 | 08/06/2023 | 0 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 23.61 | 0 | 0 | 0
1555 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Car bill for office purpose against vehicle reg. no.WB-55A/7171 & paid for the month of Jan,23 & Feb,23. | BP-2023-24-58 | 04/05/2023 | 0 | NIRUPAMA DEY | 0.63 | 0 | 0 | 0
1556 | PURULIA | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | DEPOSITION OF THE EARNEST MONEY FOR THE PORPOSED ENHANCEMENT OF THE LOAD AT KOTHSILA WATER SUPPLY SCHEME | 780/PMD | 23/11/2022 | 0 | WBSEDCL PURULIA | 0.05 | 0 | 0 | 0
1557 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/4524 bill paid for the month of Sep,22 to June,22. | BP-2023-24-334 | 02/08/2023 | 0 | ANUP KUMAR SAHA | 2.33 | 0 | 0 | 0
1558 | PURULIA | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 125 KVA AT 0.4 KV TO 281/281/281/281/281 KVA RESPECTIVELY AT 11 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o EX ENGG PMD PHE DTE. (CONSUMER ID : 942406300) TO THEIR PREMISES AT KOTSHILA WATER SUPPLY SCHEME (AUGMENTATION) |  | 28/02/2023 | 0 | WBSEDCL PURULIA | 10.37 | 0 | 0 | 0
1559 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Construction of RCC Clear water reservoir (CWR) of capacity 150 Cum with other allied works at Kotshila pumphouse under Purulia Sadar Sub-Division, PHE Dte. | 860/PD | 23/05/2022 | 90 | BOSE CONSTRUCTION | 17.45 | 0 | 0 | 65
1560 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Chaitandih) | 874/PD | 23/05/2022 | 30 | PRATIK SAHA | 23.33 | 0 | 0 | 75
1561 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Chiruhatu) | 876/PD | 23/05/2022 | 45 | GOUTAM CHAKRABORTY | 46.54 | 0 | 0 | 85
1562 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of augumentation Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Barudi) | 1041/PD | 07/07/2022 | 970 | ANUP KUMAR SAHA | 82.11 | 0 | 0 | 85
1563 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Timangda) | 1039/PD | 07/07/2022 | 45 | MANATOSH SINGH | 44.34 | 0 | 0 | 80
1564 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name- Kotshila) | 1044/PD | 07/07/2022 | 970 | ANUP KUMAR SAHA | 74.83 | 0 | 0 | 85
1565 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE Pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Uparbatri) | 938/PD | 16/06/2022 | 1110 | SWAPAN MANDAL | 116.02 | 0 | 0 | 80
1566 | PURULIA | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supply, delivery and installation of Centrifugal pumping machineries, MCC Panel with others allied works for Augmentation of KOTSHILA w/s scheme under PMD, PHE Dte. in the District of Purulia. | 43/PMD | 19/01/2023 | 60 | TAPAN KUMAR DEY | 78.43 | 0 | 0 | 65
1567 | PURULIA | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supply, delivery and installation of 400KVA 11/.433 KV substation with 11 KV 800A VCB Panel with others allied works for Augmentation of Kotshila w/s scheme under PMD, PHE Dte. in the District of Purulia | 42/PMD | 19/01/2023 | 60 | CHAKRABORTY ENTERPRISE | 48.1 | 0 | 0 | 60
1568 | PURULIA | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supply delivery and installation submersible pumping machineries & 3 core 10 Sq. mm Al Ar. cable line , with others allied works for Augmentation of Kotshila W/S scheme under PMD, PHE Dte. in the District of Purulia | 154/PMD | 24/02/2023 | 60 | M/S S.G.ENTERPRISE | 31.8 | 0 | 0 | 75
1569 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Banahatu) Zone-ii | 1055/PD | 08/07/2022 | 1362 | SUBODH PRAMANIK | 58.54 | 0 | 0 | 90
1570 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Murulahar ) | 1043/PD | 07/07/2022 | 60 | PARTHA PRATIM CHHATAIT | 91.56 | 0 | 0 | 70
1571 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE Pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Tiraldih or Goaladih) | 1058/PD | 08/07/2022 | 60 | SOUMITRA CHAKRABORTY | 56.18 | 0 | 0 | 100
1572 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Chitarpur) | 1059/PD | 08/07/2022 | 60 | NANIGOPAL DEY | 33.35 | 0 | 0 | 90
1573 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Hanslata) Zone-ii | 1053/PD | 08/07/2022 | 45 | BABA LOKENATH LABOUR CONSTRUCTION CO-OP SOCIETY LTD. | 21.95 | 0 | 0 | 100
1574 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Construction of Over Head Reservoir (OHR) of 750 Cum Capacity, Staging Height 20 mtr. at BDO office Campus at Kotshila under Purulia Sadar Sub-Division of Purulia Division, P.H.E. Dte. | 1887/PD | 15/12/2022 | 270 | ANUP KUMAR SAHA | 161.06 | 0 | 0 | 100
1575 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Chitarpur Mouza) | 181/PD | 07/02/2023 | 30 | NANIGOPAL DEY | 2.71 | 0 | 0 | 90
1576 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Construction of Boundary wall at Kachahatu Pump House Site under Kotshila W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | 110/PD | 20/01/2023 | 30 | KANAILAL PAL | 14.97 | 0 | 0 | 100
1577 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Laying of Parallel Distribution Pipeline at Banahatu Mouza of Kotshila Water Supply Scheme under Purulia Division, PHE Dte | 292/PD | 27/02/2023 | 45 | M/S SAWDESH ENTERPRISE | 28.73 | 0 | 0 | 100
1578 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Shyampur Mouza) | 279/PD | 27/02/2023 | 30 | S. R. ENTERPRISE | 10.39 | 0 | 0 | 60
1579 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Construction of Chlorine cum Switch Room & Guard Room with sanitary and plumbing arrangment with approach road, plinth protection, surface drain etc. complete at Kotshila OHR Site for Augmentation of Kotshila W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | 369/PD | 14/03/2023 | 100 | SABYASACHI MISHRA | 8.18 | 0 | 0 | 70
1580 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Laying of Main Line & Parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Jiudaru Mouza) | 345/pd | 13/03/2023 | 90 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 79.96 | 0 | 0 | 100
1581 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | 13 Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Chiruhatu Mouza) | 361/PD | 14/03/2023 | 45 | M/S CHAKRABORTY CONSTRUCTION | 9.62 | 0 | 0 | 100
1582 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Laying of Pipeline from Jiudaru Mouza to Murulahar Mouza for Providing FHTC at Kotshila Water Supply Scheme under Purulia Division, PHE Dte. | 699/PD | 22/05/2023 | 90 | RAJAT KARMAKAR | 30.33 | 0 | 0 | 10
1583 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Laying of parallel line under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (Adardih Mouza) | 818/PD | 26/06/2023 | 45 | SUSANTA KR DUTTA | 10.03 | 0 | 0 | 100
1584 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Laying of Pipeline from Kachahatu Mouza to Jiudaru Mouza & Murulahar Mouza for Providing FHTC at Kotshila Water Supply Scheme under Purulia Division, PHE Dte. | 700/PD | 22/05/2023 | 90 | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 84.69 | 0 | 0 | 100
1585 | PURULIA | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supply and delivery of essential Electromechanical items for Augmentation of Kotshila w/s Scheme in PMD store under Purulia Mechanical Division PHE, Dte | 1178/PMD | 03/11/2023 | 60 | SAIBAL SARKAR | 5.15 | 0 | 0 | 100
1586 | PURULIA | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Bill for earnest money for the proposed Enhancement of the load at your premises at Kotshila W/S Scheme. | BP-23-24-219 | 05/12/2023 | 0 | WBSEDCL PURULIA | 0.05 | 0 | 0 | 0
1587 | PURULIA | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Enhancement of the contract demand from 125KVA at 0.4 KV to 281/281//281//281//281 KVA respectively at 11 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE Kotshila Water Supply, (Consumer ID -942406300) | BP-24-25-1 | 19/04/2024 | 0 | WBSEDCL PURULIA | 10.24 | 0 | 0 | 0
1588 | PURULIA | Purulia Mechanical | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | SHIFTING OF ENERGY METER FROM EXISTING METER ROOM TO ANOTHER ROOM AT KOTHSILA WS SCHEME | BP-23-24-269 | 22/01/2024 | 0 | WBSEDCL PURULIA | 0.28 | 0 | 0 | 0
1589 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Office stationary bill supply & bill paid for the Bill No.765,770,785,848,850,839,840,841,842,849,845,847,837,838 & 836. | BP-2024-25-261 | 24/07/2024 | 0 | KETIKA CONSUMERS CO-OP STORES LTD | 4.31 | 0 | 0 | 0
1590 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Adardih) | 875/PD | 23/05/2022 | 1001 | SUSANTA KR DUTTA | 40.45 | 0 | 0 | 90
1591 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System under augmentation of Kotshila W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. (Mouza Name-Shyampur) | 1042/PD | 07/07/2022 | 945 | S. R. ENTERPRISE | 64.93 | 0 | 0 | 92
1592 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Repairing of DI Rising main (K-9) including laying of Parallel line at Jiudaru Mouza under Kotshila Water Supply Scheme in Connection with Jal-Jeevan Mission Works at Purulia Division ,PHE Dte . | 937/PD | 19/07/2023 | 30 | ANUP KUMAR SAHA | 95.31 | 0 | 0 | 80
1593 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Withdrawing & Relaying of DI(K-9) rising main pipeline including cleaning of chokage & laying of parallel pipeline at Kotshila water supply scheme under Purulia Division ,PHE Dte. | 939/PD | 19/07/2023 | 30 | ANUP KUMAR SAHA | 87.21 | 0 | 0 | 70
1594 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Construction of Pump house for accommodating centrifugal pump for pumping of water including Panel room & Chlorination room from Kotshila Pump House to distribution area through distribution main of Kotshila W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | 859/PD | 23/05/2022 | 100 | CHOUDHURY STONE CRUSHING | 16.65 | 0 | 0 | 50
1595 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Repairing of DI Pipeline Rising main (K-9) including laying of Parallel line at Barudi Mouza for Providing FHTC under Kotshila Water Supply Scheme in Connection with Jal-Jeevan Mission Works at Purulia Division ,PHE Dte . | 938/PD | 19/07/2023 | 30 | ANUP KUMAR SAHA | 78.98 | 0 | 0 | 100
1596 | PURULIA | Purulia Division | Augmentation of Kotshila Water Supply Scheme. , SM/10723 | Augmentation | Laying of Parallel line at Jiudaru Mouza and Branch Line and Gap portion of Hanslata Mouza under command area of Kotshila Water Supply Scheme of Kotshila Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | 868/PD | 30/06/2023 | 30 | RAJAT KARMAKAR | 11.46 | 0 | 0 | 100
1597 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. , SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Manbazar-I Block (Part-G) of Purulia District under Purulia Division, PHE Dte. (Tender No- 706/2022-23 of EE/PD) | BP-2022-23-434 | 25/11/2022 | 0 | THE BUSINESS ENGINEERS INDIA | 36.92 | 0 | 0 | 0
1598 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. , SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Manbazar-I Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | 595/PD | 19/04/2022 | 45 | MEGA SOLAR ENERGY | 47.31 | 0 | 0 | 0
1599 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. , SM/10252 | Anganwadi | Acceptance cum Work Order for, ¿Water supply Tap Connection Arrangement for 11 nos AWC within Manbazar-I Block (Part-A) of Purulia District under Purulia Division, PHE Dte.(Phase-I)" | 1716/PD | 22/11/2022 | 45 | DIGITEK | 91.23 | 0 | 0 | 91
1600 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. , SM/10252 | Anganwadi | Acceptance cum Work Order for, ¿Water supply Tap Connection Arrangement for 11 nos AWC within Manbazar-I Block (Part-B) of Purulia District under Purulia Division, PHE Dte.(Phase-II)" | 1717/PD | 22/11/2022 | 45 | BILTU DAS | 91.09 | 0 | 0 | 0
1601 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. , SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 29 nos AWC within Manbazar-I Block of Purulia District under Purulia Division, PHE Dte. | 80/PD | 17/01/2023 | 45 | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 16.11 | 0 | 0 | 0
1602 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. , SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Manbazar-I Block (Part-D) of Purulia District under Purulia Division, PHE Dte. | 1047/PD | 08/07/2022 | 45 | AMITAVA CHAKRABORTY | 157.91 | 0 | 0 | 61
1603 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. , SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Manbazar-I Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | 1249/PD | 30/08/2022 | 45 | M DHARA & BROTHERS | 197.78 | 0 | 0 | 90
1604 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. , SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Manbazar-I Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | 596/PD | 19/04/2022 | 45 | GLAMOUROOMS UNEMPLOYED CO-OPERATIVE SOCIETY LTD. | 23.64 | 0 | 0 | 60
1605 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. , SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Manbazar-I Block (Part-L) of Purulia District under Purulia Division, PHE Dte. | 599/PD | 19/04/2022 | 45 | GOUTAM CHAKRABORTY | 15.78 | 0 | 0 | 0
1606 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. , SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 1 no AWC within Manbazar-I Block (Part-M) of Purulia District under Purulia Division, PHE Dte. | 600/PD | 19/04/2022 | 45 | DEBSHANKAR LAYEK | 7.82 | 0 | 0 | 0
1607 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. , SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Manbazar-I Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | 597/PD | 19/04/2022 | 45 | RAJAT KARMAKAR | 23.66 | 0 | 0 | 0
1608 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. , SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Manbazar-I Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | 594/PD | 19/04/2022 | 45 | THE BUSINESS ENGINEERS INDIA | 47.2 | 0 | 0 | 0
1609 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. , SM/10252 | Anganwadi | Making Xerox copy of original DPR, Drawing, Mouza Map etc. | 27/2023-149 | 30/05/2023 | 0 | SB CONSTRUCTION | 0.37 | 0 | 0 | 0
1610 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. , SM/10252 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 9 nos AWC within Manbazar-I Block (Part-N) of Purulia District under Purulia Division, PHE Dte.(Phase-IV)" | 1719/PD | 22/11/2022 | 45 | NANIGOPAL DEY | 75.02 | 0 | 0 | 95
1611 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. , SM/10252 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 6 nos AWC within Manbazar-I Block (Part-O) & 1 no AWC within Manbazar-I Block (Part-P) of Purulia District under Purulia Division, PHE Dte.(Phase-V)" | 1720/PD | 22/11/2022 | 45 | MANATOSH SINGH | 58.28 | 0 | 0 | 40
1612 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. , SM/10252 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within MANBAZAR-1 Block (Part-F) of Purulia District under Purulia Division, PHE Dte. | 1861/PD | 13/12/2022 | 45 | NANIGOPAL DEY | 99.13 | 0 | 0 | 86
1613 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 116 nos. under Manbazar-I Block In Purulia District under Purulia Division, PHE. Dte. , SM/10252 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 11 nos AWC within Manbazar-I Block (Part-E) of Purulia District under Purulia Division, PHE Dte.(Phase-III)" | 1718/PD | 22/11/2022 | 45 | SINGHA ENTERPRISE | 91.63 | 0 | 0 | 100
1614 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Execution of Electrical resistivity survey for searching ground water availability by experienced qualified geologist or applied geophysistat Anara, Bhowridih, Dubra, Bahara, Gram panchayats in PARA block and other areas for RBTW source creation in AWC withinPurulia district under PMD, PHE, Dte. | 217/PMSD (Drilling) | 05/08/2022 | 3 | NUPUR CHANDRA HALDER | 4.93 | 0 | 0 | 0
1615 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Dubra GP, Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 712/PMD | 17/10/2022 | 30 | TAPAN KUMAR DEY | 66.5 | 0 | 0 | 0
1616 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Udayespur GP, Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 713/PMD | 17/10/2022 | 25 | JYOTY SOLAR POWER | 44.32 | 0 | 0 | 0
1617 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Jabara Jhapra-I GP and Jabara Jhapra -II GP Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 724/PMD | 19/10/2022 | 30 | SANTANU BANERJEE | 72.8 | 0 | 0 | 0
1618 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Para GP and Anara GP, Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 710/PMD | 17/10/2022 | 30 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 69.68 | 0 | 0 | 0
1619 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Para Block (Part-B) of Purulia District under Purulia Division, PHE Dte.(Without Tubewell) | 1152/PD | 01/08/2022 | 45 | PRADIP KUMAR DHABAL | 113.31 | 0 | 0 | 80
1620 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Water supply Tap Connection Arrangement for 5 nos AWC within Para Block (Part-J), 3 nos AWC within Para Block (Part-K) & 3 nos AWC within Para Block (Part-L) of Purulia District under Purulia Division, PHE Dte. (Phase-I) | 1701/PD | 22/11/2022 | 45 | MS D.PALIT AND CO. | 91.69 | 0 | 0 | 0
1621 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Water supply Tap Connection Arrangement for 37 nos AWC within PARA Block ) of Purulia District under Purulia Division, PHE Dte. | 34/PD | 09/01/2023 | 45 | SUBHAS CHANDRA MAHATO | 20.47 | 0 | 0 | 0
1622 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Bhowridih GP, Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 711/PMD | 17/10/2022 | 25 | PRINCE INDUSTRIES (INDIA) | 50.71 | 0 | 0 | 0
1623 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200 X 165) mm by DTH method in different source less AWC at Deoli GP, Para Block under Purulia Mechanical Division, P.H.E Dte. in the District of Purulia | 751/PMD | 07/11/2022 | 7 | M/S KARUNAMOYEE CONSTRUCTION | 3.17 | 0 | 0 | 0
1624 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Washing and developing of tube well for AWC programme at Para and other block under PMD, PHE, Dte.(2nd call) | 415/PMD | 12/04/2023 | 15 | SUMIT KR. CHAKRABORTY | 4.92 | 0 | 0 | 100
1625 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Dubra GP, Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.232/EE/PMD of 2022-23) | BP-2022-23-516 | 02/01/2023 | 0 | TAPAN KR. DEY | 49.6 | 0 | 0 | 0
1626 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Jabara Jhapra-I GP and Jabara Jhapra -II GP Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.231/EE/PMD of 2022-23) | BP-2022-23-505 | 22/12/2022 | 0 | SANTANU BANERJEE | 49.96 | 0 | 0 | 0
1627 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Udayespur GP, Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.230/EE/PMD of 2022-23) | BP-2022-23-530 | 09/01/2023 | 0 | JYOTY SOLAR POWER | 22.58 | 0 | 0 | 0
1628 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Execution of Electrical resistivity survey for searching ground water availability by experienced qualified geologist or applied geophysistat Anara, Bhowridih, Dubra, Bahara, Gram panchayats in PARA block and other areas for RBTW source creation in AWC withinPurulia district under PMD, PHE, Dte. (Tender No.202/EE/PMD of 2022-23) | BP-2022-23-457 | 02/12/2022 | 0 | NUPUR CHANDRA HALDER | 4.93 | 0 | 0 | 0
1629 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Jabara Jhapra-I GP and Jabara Jhapra -II GP Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.231/EE/PMD of 2022-23) | BP-2022-23-507 | 22/12/2022 | 0 | SANTANU BANERJEE | 10.19 | 0 | 0 | 0
1630 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Para GP and Anara GP, Para Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.233/EE/PMD of 2022-23) | BP-2022-23-473 | 16/12/2022 | 0 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 68.79 | 0 | 0 | 0
1631 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Water supply Tap Connection Arrangement for 21 nos AWC within Para Block of Purulia District under Purulia Division, PHE Dte. (Phase-V) (Part-G, H and I) | 824/PD | 17/05/2022 | 45 | M DHARA & BROTHERS | 95.18 | 0 | 0 | 60
1632 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Para Block of Purulia District under Purulia Division, PHE Dte.(Phase-III) (Part-A, C & P) | 820/PD | 17/05/2022 | 45 | JYOTY SOLAR POWER | 90.72 | 0 | 0 | 100
1633 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within PARA Block (Part-D)& 5 nos Awc Within PARA block (Part-C-II) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | 1866/PD | 13/12/2022 | 45 | S.S CONSTRUCTION | 80.37 | 0 | 0 | 100
1634 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Para Block of Purulia District under Purulia Division, PHE Dte.(Phase-I) (Part-E) | 821/PD | 17/05/2022 | 1020 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 90.51 | 0 | 0 | 100
1635 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Para Block (Part-F) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | 1867/PD | 13/12/2022 | 45 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 94.41 | 0 | 0 | 100
1636 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Para Block In Purulia District under Purulia Division, PHE.Dte. , SM/10254 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Para Block (Part-M), 2 nos AWC within Para Block (Part-N) & 6 nos AWC within Para Block (Part-O) of Purulia District under Purulia Division, PHE Dte. | 1725/PD | 22/11/2022 | 45 | M/S KARUNAMOYEE CONSTRUCTION | 82.6 | 0 | 0 | 0
1637 | PURULIA | Purulia Mechanical | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Baram Water Supply scheme Block Arsha under PMD PHE Dte. District Purulia. | 112/PMD | 28/02/2022 | 30 | A G ENTERPRISE | 20.48 | 0 | 0 | 99
1638 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Installation of new staircase spiral for OHR & other allied works at Baram W/S Scheme (Tender No-365/EE/PD of 2021-22) | BP-2022-23-48 | 17/05/2022 | 0 | SOUMITRA CHAKRABORTY | 3.06 | 0 | 0 | 0
1639 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Repairing of 1 no. horizontal tube well with changing of collecting line and other allied works at Torang river side of Baram W/S Scheme under Purulia Sadar Sub- Division, PHE Dte. (Tender No- 239/2022-23 of EE/PD) | BP-2022-23-158 | 27/07/2022 | 0 | SOUMITRA CHAKRABORTY | 2.17 | 0 | 0 | 0
1640 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Extention of distribution pipeline for providing FHTC under Jal Sapna Programme of Baram W/S Scheme under Purulia Division PHE Dte. (Habitation Name:-Mankiary,Gundligora,Matkampiri, Torang) (Tender No.875/EE/PD of 2021-22) | BP-2022-23-59 | 20/05/2022 | 0 | SOUMITRA CHAKRABORTY | 5.88 | 0 | 0 | 0
1641 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Extention of distribution pipeline for providing FHTC under Jal Sapna Programme of Baram W/S Scheme under Purulia Division PHE Dte. (Habitation Name:-Baram,Thakurshima,Briddhitanr,Jaratanr) (Tender No.874/EE/PD of 2021-22) | BP-2022-23-58 | 20/05/2022 | 0 | SOUMITRA CHAKRABORTY | 19.28 | 0 | 0 | 0
1642 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Retrofitting of Baram Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for Providing Functional Household Tap Connection (FHTC) under JAL SAPNA programme under Purulia Division, PHE Dte. (Habitation covered Mankiyari, Torang, Matkompiri, Raipur, Jibandih & Gundligora) Part-B | 1240/PD | 01/12/2020 | 45 | SOUMITRA CHAKRABORTY | 29.89 | 0 | 0 | 0
1643 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Supply and delivery of ferric alum at different water supply scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 382/PD | 11/03/2022 | 10 | ROY CONSTRUCTION | 5.71 | 0 | 0 | 20
1644 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Repairing and Renovation of Baram Pump house and Torang Pump House ,riverside) under Purulia Sadar Sub Division under Purulia Division ,PHE .DTE | 167/PSD | 18/04/2022 | 30 | AKUL SUTRADHAR | 4.85 | 0 | 0 | 0
1645 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Construction of 5.0 x 3.0 mtr size Guard Room , approach road, plinth protection, surface drain etc. complete at Mankiyari OHR site for Baram W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | 166/PSD | 18/04/2022 | 30 | SOUMITRA CHAKRABORTY | 4.71 | 0 | 0 | 75
1646 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Repairing 1 no Horizontal Tubewell at Kansai River at Torang Riverside and other allied works Baram W/S Scheme under Purulia Sadar Sub Division under Purulia Division , PHE Dte.(T/W no-3) | 1808/Pd | 06/12/2022 | 30 | SOUMITRA CHAKRABORTY | 1.73 | 0 | 0 | 100
1647 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Supply delivery fitting & fixing of sign board (ACP Sheet) at 10nos site within Purulia District under RWS Purulia Sub-Division PHE Dte.( Part-C) SL NO. 07 | 97/PR | 28/02/2023 | 30 | MRINAL KANTI GORAI | 0.65 | 0 | 0 | 100
1648 | PURULIA | Purulia Mechanical | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Supply delivery and installation of 100 KVA voltage stabilizer for Augmentation of Baram(River Side) water supply scheme under PMD PHE Dte. In the district of Purulia. | 237/PMD | 03/03/2023 | 60 | S. PATHAK & CO. | 10.86 | 0 | 0 | 65
1649 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Extension of PVC pipe line in distribution system from Deolghata Pump House to River site Smashan Ghat ( Burning Ghat) with construction of a Stand post for met up the drinking water crisis under Joypur Water Supply Scheme of Purulia Sadar Sub-Division, PHE Dte. | 4681/PSD | 27/07/2023 | 10 | APEX TRADERS | 0.29 | 0 | 0 | 100
1650 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Withdrawing of 150 mm dia.G.I. damaged Collecting line & newly laying of 160 mm dia HDPE Pipe line as Collecting line and 40 mm dia G.I. Guard Pilling at river bed of Kansai near Deolghata of Joypur Water Supply Scheme at Joypur Block under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | 4674/PSD | 27/07/2023 | 10 | APEX TRADERS | 0.78 | 0 | 0 | 100
1651 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2022 to 30.06.2023) | 308-PR | 29/06/2022 | 365 | COMPUTER MEDIA | 2.73 | 0 | 0 | 100
1652 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2022 to 30.06.2023) | 309_PR | 29/06/2022 | 365 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
1653 | PURULIA | Purulia Mechanical | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Material Requisition To Resource Division | 619/PMD | 01/06/2023 | 0 | Resource Division | 1.55 | 0 | 0 | 0
1654 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Bill paid for due to awareness program in the ocation of Independence Day organised by DPMU. | BP-2023-24-715 | 13/12/2023 | 0 | ANUDIP SAHA | 0.54 | 0 | 0 | 0
1655 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Bill payment to Sri Krishna Computer against bill no.010/2023-24 to 017/2023-24 | BP-2023-24-629 | 17/10/2023 | 0 | SRI KRISHNA COMPUTER | 0.63 | 0 | 0 | 0
1656 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Construction of 5.0 x 3.0 mtr size Guard Room, plinth protection, surface drain etc.complete at Sirkabad OHR Site for Sirkabad W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | 35/PD | 08/01/2024 | 100 | KABERI DUTTA | 5.05 | 0 | 0 | 0
1657 | PURULIA | Purulia Mechanical | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Supply delivery and installation of 1 kg/hr gaseous chlorination system at Baram High lift for augmentation of Baram Water supply scheme under PMD PHE Dte. District Purulia. | 439/PMD | 11/03/2024 | 60 | PINTU DEY | 25.09 | 0 | 0 | 50
1658 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | New sinking of 01 (One) nos. 200 mm dia river bed tubewell (Horizontal) at Kansai river alongwith laying of 100 mm dia G.I. collecting line with all allied works at Baram W/S Scheme under Purulia Division, PHE Dte. (Part-B) | 1739/PD | 22/11/2022 | 30 | SOUMITRA CHAKRABORTY | 8.91 | 0 | 0 | 100
1659 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | New sinking of 02 (Two) nos. 200 mm dia river bed tubewell (Horizontal) at Kansai river alongwith laying of 100 mm dia G.I. collecting line with all allied works at Baram W/S Scheme under Purulia Division, PHE Dte. (Part-A) | 1738/PD | 22/11/2022 | 30 | SOUMITRA CHAKRABORTY | 18.35 | 0 | 0 | 100
1660 | PURULIA | Purulia Mechanical | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well with allied cable line and other allied works for augmentation of Baram(River Side) w/s scheme under PMD, PHE Dte. in the District of Purulia. | 236/PMD | 03/03/2023 | 60 | SUMIT KR. CHAKRABORTY | 11.33 | 0 | 0 | 20
1661 | PURULIA | Purulia Division | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Computer service & spare parts supply bill paid. | BP-2023-24-750 | 05/01/2024 | 0 | SRI KRISHNA COMPUTER | 0.65 | 0 | 0 | 0
1662 | PURULIA | Purulia Mechanical | Augmentation of Baram Water Supply Scheme , SM/09213 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmeter and other allied works for augmentation of Baram(River Side) water supply scheme under PMD, PHE Dte. In the district of Purulia. | 522/PMD | 05/05/2023 | 607 | P K ENGINEERING | 39.21 | 0 | 0 | 100
1663 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII , SM/14023 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 357/E/PD | 25/02/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 42.7 | 0 | 0 | 100
1664 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII , SM/14023 | Augmentation | Repairing of DI rising main and repairing, renovation of Boundary wall (Total lenght =148 mtr) at Raghunathpur W/S Scheme (Zone-VIII) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 545/PD | 12/04/2023 | 30 | M/S SAYAK BHATTACHARYA | 10.93 | 0 | 0 | 0
1665 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII , SM/14023 | Augmentation | Continuation work order for the work of Survey & Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 1025/PD | 06/01/2023 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5 | 0 | 0 | 100
1666 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII , SM/14023 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 1008/PD | 29/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
1667 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII , SM/14023 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 942/PD | 19/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
1668 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII , SM/14023 | Augmentation | Continuation work order for the work of Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 1087/A/PD | 16/01/2023 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.15 | 0 | 0 | 100
1669 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII , SM/14023 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 931/A/PD | 13/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
1670 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII , SM/14023 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 1002/PD | 23/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
1671 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII , SM/14023 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Raghunathpur Pipe Water Supply scheme for Zone-VIII under Purulia Mechanical Division PHE. Dte. District Purulia | 218/PMD | 28/02/2023 | 30 | JAL PRAVAHIKA PVT. LTD | 21.57 | 0 | 0 | 100
1672 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII , SM/14023 | Augmentation | Repairing of DI Rising Main and new Construction of Boundary wall, RCC Pillar, Barbed wire at Raghunathpur W/S Scheme (Zone-VIII) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 867/PD | 30/06/2023 | 30 | M/S SAYAK BHATTACHARYA | 4.25 | 0 | 0 | 100
1673 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII , SM/14023 | Augmentation | Material Requisition To Resource Division | 72/PD | 17/01/2023 | 0 | Resource Division | 1.38 | 0 | 0 | 0
1674 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII , SM/14023 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Seleta Mouza, JL No.-41, Plot No.237 at Boosting Pump Station site under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 543/PD | 12/04/2023 | 60 | SUBRATA SINGHADEO | 33.43 | 0 | 0 | 42
1675 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII , SM/14023 | Augmentation | Repairing of DI Rising Main, construction of RCC Clear water reservoir (CWR) of capacity 150 Cum, New Boundary wall (Lenth=62 mtr) and 01 No. Sinking of RBT Tubewell (200X165 mm dia) and other allied works at Zone-VIII OHR campus of Raghunathpur W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 897/PD | 07/05/2024 | 718 | SANDIP KUMAR DUBEY | 36.14 | 0 | 0 | 60
1676 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII , SM/14023 | Augmentation | Construction of 4 Nos. Sluice Valve Chamber at Setpalash & Cheliyama Bagdipara under Raghunathpur W/S Scheme (German Assisted) Zone-VIII of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 174/RNP | 27/03/2024 | 7 | JOY GURU ENTERPRISE | 0.92 | 0 | 0 | 100
1677 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII , SM/14023 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC), and other allied works of Raghunathpur Water Supply Scheme (Zone-VIII) at Raghunathpur-II Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. (SL - 10) | 432/PD | 22/03/2023 | 1016 | PREMNATH MITRA | 414.3 | 0 | 0 | 45
1678 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII , SM/14023 | Augmentation | Laying of different dia HDPE pipe in distribution pipe line , replacing existing CI Pipes and allied works of Raghunathpur Water Supply Scheme( Zone -VIII) at Raghunathpur-II Block of Raghunathpur Sub division under Purulia Division,PHE DTE. | 1596/PD | 30/08/2024 | 579 | PREMNATH MITRA | 94.69 | 0 | 0 | 0
1679 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VIII , SM/14023 | Augmentation | Continuation work order for the work of "Day to day hiring and operation charges of 1 (one) number 10/15 KVA Generator set Engaging one number expert operator for the office of the Assistant Engineer, Raghunathpur Sub-Division under Purulia Division, PHE Dte. under Raghunathpur W/S Scheme (German Project) (w.e.f. 04.04.2025 to 03.06.2025)" | 166/RNP | 02/04/2025 | 61 | MANATOSH SINGH | 0.87 | 0 | 0 | 0
1680 | PURULIA | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS , SM/14459 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-VI] | 97/PD | 20/01/2023 | 30 | DEBANJAN SEAL | 4.95 | 0 | 0 | 85
1681 | PURULIA | Purulia Mechanical | Augmentation of Santuri Pipe Water Supply Scheme PWSS , SM/14459 | Augmentation | Supply, Delivery and installation of 30KVA oil cooled voltage stabilizer and allied works for Augmentation of Santuri w/s scheme under PMD, PHE Dte. in the District of Purulia. | 298/PMD | 16/03/2023 | 60 | BISHWANATH NANDI | 4.13 | 0 | 0 | 80
1682 | PURULIA | Purulia Mechanical | Augmentation of Santuri Pipe Water Supply Scheme PWSS , SM/14459 | Augmentation | Yard lighting arrangement with others allied works for Augmentation of Santuri w/s scheme under PMD, PHE Dte. in the District of Purulia. | 299/PMD | 16/03/2023 | 60 | S. PATHAK & CO. | 5.02 | 0 | 0 | 20
1683 | PURULIA | Purulia Mechanical | Augmentation of Santuri Pipe Water Supply Scheme PWSS , SM/14459 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Santuri Water Supply scheme Block Santuri under PMD PHE Dte. District Purulia. | 447/PMD | 20/04/2023 | 30 | DAS ENTERPRISE | 21.57 | 0 | 0 | 25
1684 | PURULIA | Purulia Mechanical | Augmentation of Santuri Pipe Water Supply Scheme PWSS , SM/14459 | Augmentation | New Connection for Augmentation of Santuri | BP-2023-24-148 | 14/09/2023 | 0 | WBSEDCL PURULIA | 4.95 | 0 | 0 | 0
1685 | PURULIA | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS , SM/14459 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-II] | 94/PD | 20/01/2023 | 30 | MS MITRA SENGUPTA ENTERPRISES | 8.37 | 0 | 0 | 45
1686 | PURULIA | Purulia Mechanical | Augmentation of Santuri Pipe Water Supply Scheme PWSS , SM/14459 | Augmentation | Supply, Delivery and installation of Centrifugal pumping machineries, MCC panel with others allied works for Augmentation of Santuri w/s scheme under PMD, PHE Dte. in the District of Purulia. | 297/PMD | 16/03/2023 | 60 | GOENKA ENTERPRISE | 33.83 | 0 | 0 | 20
1687 | PURULIA | Purulia Mechanical | Augmentation of Santuri Pipe Water Supply Scheme PWSS , SM/14459 | Augmentation | Supply, delivery and installation of Submersible pumping machineries ,Al. Armoured cables and laying of Al. armoured cables for Augmentation of Santuri W/S scheme under PMD Dte .in the District Purulia. | 996/PMD | 21/06/2024 | 60 | SEN BROTHERS | 4.25 | 0 | 0 | 70
1688 | PURULIA | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS , SM/14459 | Augmentation | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - I of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part - D, Mouza - PORADIHA, BELJHUPA, KALAID] | 1054/PD | 08/08/2023 | 90 | CHATTERJEE CONSTRUCTION | 64.43 | 0 | 0 | 63
1689 | PURULIA | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS , SM/14459 | Augmentation | Construction of RCC Over Head Reservoir (OHR) Capacity 100 cum and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 98/PD | 20/01/2023 | 270 | CHATTERJEE CONSTRUCTION | 56.67 | 0 | 0 | 100
1690 | PURULIA | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS , SM/14459 | Augmentation | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - I of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part - B, Mouza - Dumdumi] | 1055/PD | 08/08/2023 | 90 | M/S SAYAK BHATTACHARYA | 73.52 | 0 | 0 | 100
1691 | PURULIA | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS , SM/14459 | Augmentation | Construction of Switch Room Cum Chlorin Room at Santuri OHR Site of Santuri W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 933/PD | 19/07/2023 | 100 | PURNA CHANDRA TEWARI | 4.21 | 0 | 0 | 100
1692 | PURULIA | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS , SM/14459 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-I] | 93/PD | 20/01/2023 | 802 | KHITISH CHANDRA PATHAK | 59.34 | 0 | 0 | 80
1693 | PURULIA | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS , SM/14459 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-III] | 95/PD | 20/01/2023 | 621 | CHANDAN CHATTERJEE | 11.22 | 0 | 0 | 95
1694 | PURULIA | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS , SM/14459 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-V] | 96/PD | 20/01/2023 | 802 | AMIT PATHAK | 10.76 | 0 | 0 | 85
1695 | PURULIA | Purulia Division | Augmentation of Santuri Pipe Water Supply Scheme PWSS , SM/14459 | Augmentation | Laying of Distribution System including providing House Hold Tap Connection (FHTC) and other allied works for Aug. of Santuri Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-IV] | 396/PD | 16/03/2023 | 45 | M/S ACHARJEE CONSTRUCTION | 19.01 | 0 | 0 | 62
1696 | PURULIA | Purulia Mechanical | SOLARISATION OF WBSEDCL ENERGISED PUMPING INSTALLATION IN G.W.BASED CHITMU PWSS, BLOCK -JHALDA II UNDER PMD,PHE Dte.,DISTRICT- PURULIA , SM/14169 | Solarisation | Installation of Ongrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping installation at Chitmu water supply schemes of Jhalda II Block under PMD, PHE, Dte. District Purulia. | 915/PMD | 07/08/2023 | 60 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 6.26 | 0 | 0 | 90
1697 | PURULIA | Purulia Division | MINI PIPED WATER SUPPLY SCHEME FOR BAMANDIHA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER MANBAZAR-I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/14251 | New | Survey in connection with the Mini Water Supply Scheme having house hold less than 100 under Manbazar-I & Manbazar-II Block [18 + 19 =37 nos Habitations] under Jal Sapna/ JJM Programme under Purulia Division P.H.E. Dte. (Part-III) | 159/PSD | 24/02/2023 | 21 | M/S R. DUTTA & CO. | 4.69 | 0 | 0 | 0
1698 | PURULIA | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07839 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Maguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-B Mouza-Daldali, Bhagabandh under Daldali G.P.(1139 Nos.) | 157/PD | 01/02/2021 | 45 | GOUTAM CHAKRABORTY | 56.95 | 34.58 | 89.33 | 85
1699 | PURULIA | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07839 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Maguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-C (Mouza-Maguria-Lalpur under Maguria-Lalpurr G.P). 1218 Nos.) (Tender No.307/EE/PD OF 2020-21) | BP-2021-22-106 | 14/09/2021 | 0 | SWAPAN MANDAL | 46.14 | 0 | 0 | 0
1700 | PURULIA | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07839 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur W/s Scheme at Hura Block of Raghunathpur Sub-DivisionPHE Dte. (Tender No. 409/EE/PD of 2020-21) | BP-2021-22-98 | 23/08/2021 | 0 | ALOK KUMAR CHAKRABORTY | 28.51 | 0 | 0 | 0
1701 | PURULIA | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07839 | Retrofitting | Artificial recharging of existing river bed tubewells along with all others related items of works to combat extreme drought like situation under Manguria-Lalpur W/s Scheme of Raghunathpur Sub-Division PHE Dte. under Purulia Division PHE Dte. (Tender No. 376/EE/PD of 2021-22) | BP-2021-22-125 | 11/10/2021 | 0 | ALOK KUMAR CHAKRABORTY | 4.78 | 0 | 0 | 0
1702 | PURULIA | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07839 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur W/s Scheme at Hura Block of Raghunathpur Sub-Division under Purulia Division PHE Dte. at Part-B Mouza- Daldali, Bhagabandh under Daldali G.P (1139 Nos.) (Tender No. 309/EE/PD of 2020-21) | 9/844324/2 | 12/04/2021 | 0 | GOUTAM CHAKRABORTY | 13.28 | 0 | 0 | 0
1703 | PURULIA | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07839 | Retrofitting | Additional work for functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) Mouza-Daldali, Bhagabandh under Daldali (1139 Nos.) Part-II. (Tender No.826/EE/PD of 2021-22) | BP-2021-22-231 | 03/02/2022 | 0 | GOUTAM CHAKRABORTY | 4.8 | 0 | 0 | 0
1704 | PURULIA | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07839 | Retrofitting | Additional work for functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) Mouza-Daldali, Bhagabandh under Daldali G.P Part-III. (Tender No.827/EE/PD of 2021-22) | BP-2021-22-228 | 03/02/2022 | 0 | GOUTAM CHAKRABORTY | 4.82 | 0 | 0 | 0
1705 | PURULIA | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07839 | Retrofitting | Distribution Main by supplying & laying of different dia HDPE pipe line and Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No.959/EE/PD of 2021-22) | BP-2021-22-292 | 09/03/2022 | 0 | PREMNATH MITRA | 53.06 | 0 | 0 | 0
1706 | PURULIA | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07839 | Retrofitting | Additional work for functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) Mouza-Daldali, Bhagabandh under Daldali G.P Part-IV. (Tender No.830/EE/PD of 2021-22) | BP-2021-22-229 | 03/02/2022 | 0 | GOUTAM CHAKRABORTY | 4.15 | 0 | 0 | 0
1707 | PURULIA | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07839 | Retrofitting | Additional work for functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) Mouza-Daldali, Bhagabandh under Daldali (1139 Nos.) Part-I. (Tender No.833/EE/PD of 2021-22) | BP-2021-22-230 | 03/02/2022 | 0 | GOUTAM CHAKRABORTY | 4.77 | 0 | 0 | 0
1708 | PURULIA | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07839 | Retrofitting | Additional work for functional Household Tap Connection (FHTC) and other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-A) (Chatumadar G.P.) | 1353/PD | 13/09/2023 | 45 | ALOK KUMAR CHAKRABORTY | 2.02 | 0 | 0 | 100
1709 | PURULIA | Purulia Division | Retrofitting of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07839 | Retrofitting | Repairing and renovation op pipe line at Lalpur & Hijuli village under Lalpur-Manguria Water supply Scheme. (Tender No.533/EE/PD of 2022-23) | 181/844340 | 06/12/2022 | 0 | ALOK KUMAR CHAKRABORTY | 0.86 | 0 | 0 | 0
1710 | PURULIA | Purulia Division | MINI PIPED WATER SUPPLY SCHEME FOR ANKDUAR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER JAIPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/16091 | New | Survey in connection with the Mini Water Supply Scheme having house hold less than 100 under Jaipur Block [21 nos Habitations] under Jal Sapna/ JJM Programme under Purulia Division P.H.E. Dte. | 161/PSD | 24/02/2023 | 21 | INDRANIL DUTTA & ASSOCIATES | 2.97 | 0 | 0 | 0
1711 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Sidpur mouza (Jl. No.154) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No- 1007/2021-22 of EE/PD) | BP-2021-22-347 | 28/03/2022 | 0 | M/S KARUNAMOYEE CONSTRUCTION | 27.68 | 0 | 0 | 0
1712 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Supply and delivery of 6mm N.B. gun Metal Ferrule for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation of Hutmura Mouza (JL No 139) & Phulberia mouza (JL No 140) under Hutmura Water Supply Scheme of Purulia II Block under Purulia Division, PHE Dte. (Tender No- 445/2022-23 of EE/PD) | BP-2022-23-310 | 26/09/2022 | 0 | M/S KARUNAMOYEE CONSTRUCTION | 4.76 | 0 | 0 | 0
1713 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation of Korcha mouza (JL No- 151) and replacement/extension of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub- Division, PHE Dte. (Tender No- 13/2022-23 of EE/PD) | BP-2022-23-136 | 19/07/2022 | 0 | SHYAMAL KUMAR DEY | 17.28 | 0 | 0 | 0
1714 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Kandhurka alias Bhabanipur mouza (Jl. No.155) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.920/EE/PD of 2021-22) | BP-2021-22-368 | 29/03/2022 | 0 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 10.34 | 0 | 0 | 0
1715 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Repairing renovation & restoration of Store cum Guard room at Hutmura WTP campus of Hutmura W/s Scheme. (Tender No.893/EE/PD of 2021-22) | BP-2021-22-392 | 30/03/2022 | 0 | TAPAN CHANDRA | 1.82 | 0 | 0 | 0
1716 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Preparation of DPR (consultancy work) in connection with Functional household Tap Connection of different existing PWSS (Hutmura W/S Scheme Block- Purulia-II) to be Augmentation/ Rejuvenation (Tender No- 540/2021-22 of EE/PD) | BP-2021-22-303 | 21/03/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 3.97 | 0 | 0 | 0
1717 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Providing FHTC in connection with JJM and JAL SWAPNA at different habitation of Hutmura Mouza JL No 139 & Phulberia Mouza JL No 140 under Hutmura Water Supply Scheme of Purulia II Block under Purulia Sadar Sub- Division, PHE Dte. (Tender No- 05/2022-23 of EE/PD) | BP-2022-23-308 | 26/09/2022 | 0 | M/S KARUNAMOYEE CONSTRUCTION | 37.94 | 0 | 0 | 0
1718 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Repairing, renovation & restoration of pump house & Chlorine cum Alum dozing room at Hutmura WTP campus of Hutmura W/s Scheme. (Tender No.831/EE/PD of 2021-22) | BP-2022-23-41 | 02/05/2022 | 0 | TARASANKAR DEY | 2.44 | 0 | 0 | 0
1719 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Preparation of DPR (consultancy work) in connection with Functional household Tap Connection of different existing PWSS (Hutmura W/S Scheme Block- Purulia-II) to be Augmentation/ Rejuvenation (Tender No- 849/2021-22 of EE/PD) | BP-2021-22-302 | 21/03/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 1.07 | 0 | 0 | 0
1720 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Kandhurka alias Bhabanipur mouza (Jl. No.155) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.920/EE/PD of 2021-22) | BP-2022-23-277 | 22/09/2022 | 0 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 12.26 | 0 | 0 | 0
1721 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Repairing renovation & restoration of switch cum meter room including roof treatment at Hutmura Dam site of Hutmura W/S Scheme under Purulia Sadar Sub- Division (Tender No- 837/2021-22 of EE/PD) | BP-2021-22-319 | 22/03/2022 | 0 | INDRAJIT SARKAR | 2.27 | 0 | 0 | 0
1722 | PURULIA | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Enhancement of contract demand load for Augmentation of Hutmura Water Supply Scheme |  | 03/11/2022 | 0 | WBSEDCL PURULIA | 3.08 | 0 | 0 | 0
1723 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Karcha mouza (Jl. No.151) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 422/PD | 17/03/2022 | 45 | SHYAMAL KUMAR DEY | 31.94 | 0 | 0 | 75
1724 | PURULIA | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Augmentation of floating walkway lowering and anchoring of existing repaired floating barge with required ms work by necessary supply of materials and other allied works at Hutmura(Low Lift) W/S scheme under PMD PHE Dte in the district of Purulia. | 124/PMD | 15/02/2023 | 60 | ASHOKE ADHIKARY | 7.85 | 0 | 0 | 0
1725 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Construction of 5.0 x 3.0 mtr size Switch Room cum Chlorine Room approach road, plinth protection, surface drain etc. complete for Hutmura W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | 741/PSD | 13/12/2021 | 60 | KABERI DUTTA | 4.57 | 0 | 0 | 0
1726 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Repairing and renovation of the Over Head reservoir (OHR) of 30000 gallon Capacity, Staging Height 20 mtr. at Hutmura WTP campus under Hutmura W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | 1544/PD | 15/12/2021 | 60 | M/S KARUNAMOYEE CONSTRUCTION | 7.26 | 0 | 0 | 85
1727 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Laying of 200 mm dia DI (K9) pipe as rising main from intake site to WTP under Hutmura Water Supply Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 1594/PD | 17/12/2021 | 30 | SHYAMAL KUMAR DEY | 5.7 | 0 | 0 | 0
1728 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Extension of pipe line in distribution system for Stand Post at different School & ICDS Centre of Purulia-II Block to supply drinking water of command area including road crossing of pipe line and replacement of Sluice Valve on delivery pipe line at OHR Campus and distribution main at field of Hutmura Water Supply Scheme under Purulia Sadar Sub-Division of Purulia Division, PHE Dte. | 504/PSD | 12/08/2022 | 40 | M/S KARUNAMOYEE CONSTRUCTION | 4.14 | 0 | 0 | 100
1729 | PURULIA | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Hutmura Water Supply scheme Block Purulia-II under PMD PHE Dte. District Purulia. | 397/PMD | 16/06/2022 | 30 | SUBRATA DUTTA | 20.51 | 0 | 0 | 100
1730 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works at Hutmura W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | 1545/PD | 15/12/2021 | 60 | SHYAMAL KUMAR DEY | 10.73 | 0 | 0 | 0
1731 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Repairing, renovation and changing of filter media of filter bed including cleaning the tube settler to enhancement the filteration rate of water to meet up water crisis at Hutmura WTP of Hutmura W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | 745/PSD | 13/12/2021 | 20 | SHYAMAL KUMAR DEY | 2.22 | 0 | 0 | 85
1732 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Material Requisition To Resource Division | 1628/PD | 31/12/2021 | 0 | Resource Division | 26.12 | 0 | 0 | 0
1733 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Material Requisition To Resource Division | 389/PD | 11/03/2022 | 0 | Resource Division | 0.72 | 0 | 0 | 0
1734 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Extension/ replacement of distribution pipe line in different habitation of Hutmura Mouza (Jl No. 139) & Phulberia mouza (JL No 140) for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under augmentation of Hutmura Water Supply Scheme of Purulia II Block under Purulia Sadar Sub- Division under Purulia Division, PHE Dte. (Tender No- 27/2021-22 of SE/PMU/WBPWSP) | BP-2022-23-76 | 01/07/2022 | 0 | PREMNATH MITRA | 53.19 | 0 | 0 | 0
1735 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Laying of 200 mm dia DI k9 pipe as rising main from intake site to WTP under Hutmura W/S Scheme of Purulia Sadar Sub- Division, under Purulia Division, PHE Dte (Tender No- 868/2021-22 of EE/PD) | BP-2022-23-73 | 01/07/2022 | 0 | SHYAMAL KUMAR DEY | 1.04 | 0 | 0 | 0
1736 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Construction of RCC clear water Reservoir (CWR) of capacity 100 cum with other allied works at Hutmura W/S Scheme under Purulia Sadar Sub- Division, PHE Dte. (Tender No. 867/EE/PD of 2021-22) | BP-2022-23-97 | 07/07/2022 | 0 | SHYAMAL KUMAR DEY | 8.46 | 0 | 0 | 0
1737 | PURULIA | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Supply and installation of PLC panel, Level transmitter, Solar light(OHR Site) with other allied work at Hutmura water supply scheme under Purulia Mechanical Division PHE Dte. | 1695/PMD | 06/12/2024 | 90 | SUBRATA DUTTA | 9.99 | 0 | 0 | 0
1738 | PURULIA | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Supply delivery and installation of 50 KVA voltage stabilizer for Augmentation of Hutmura(low lift site) water supply scheme under PMD PHE Dte. In the district of Purulia. | 1448/PMD | 01/10/2024 | 90 | ASHOKE ADHIKARY | 7.37 | 0 | 0 | 0
1739 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Kandhurka alias Bhabanipur mouza (Jl. No.155) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 96/PD | 18/01/2022 | 45 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 26.3 | 0 | 0 | 100
1740 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Hutmura mouza (Jl. No.139) & Phulberia mouza (Jl. No.140) under Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 97/PD | 18/01/2022 | 60 | M/S KARUNAMOYEE CONSTRUCTION | 72.9 | 0 | 0 | 100
1741 | PURULIA | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Repairing, overhauling thorough repairing of floating walkway with required MS work by necessary supply of materials and other allied works at Hutmura (Low Lift) w/s scheme under PMD PHE Dte. in the district of Purulia. | 78/PMSD (W/S) | 08/03/2022 | 7 | SUBRATA DUTTA | 4.6 | 0 | 0 | 80
1742 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Additional Pipe laying of 50 mm dia (OD) for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Kandhurka alias Bhabanipur mouza (Jl. No.155) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 440/PSD | 24/06/2022 | 15 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 2.48 | 0 | 0 | 90
1743 | PURULIA | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Supply delivery and installation of centrifugal pumping machineries, MCC panel, flowmeter and other allied works at Hutmura(OHR site) water supply scheme under PMD, PHE Dte. In the district of Purulia. | 241/PMD | 03/03/2023 | 60 | SUBRATA DUTTA | 50.17 | 0 | 0 | 100
1744 | PURULIA | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Supply, Delivery and installation of submersible pumping machineries with flexible hose pipe, MCC panel, flowmeter with other allied works for augmentation of Hutmura(Intake side) w/s scheme under PMD, PHE Dte. in the District of Purulia. | 240/PMD | 03/03/2023 | 60 | KHITISH CH. PATHAK | 18.86 | 0 | 0 | 100
1745 | PURULIA | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Internal and external illumination with other allied works for augmentation of Hutmura W/S scheme(both intake & OHR site) water supply scheme under PMD, PHE Dte. In the district of Purulia. | 525/PMD | 05/05/2023 | 60 | ASISH KR. SEN | 5.12 | 0 | 0 | 100
1746 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Sidpur mouza (Jl. No.154) and replacement/ extention of distribution pipe line under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 98/PD | 18/01/2022 | 70 | M/S KARUNAMOYEE CONSTRUCTION | 82.79 | 0 | 0 | 100
1747 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Construction of 5.0 x 3.0 mtr size Meter Room including approach road, plinth protection, surface drain etc. complete for Hutmura W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | 656/PD | 17/05/2023 | 100 | SUDHANSHU OJHA | 4.92 | 0 | 0 | 100
1748 | PURULIA | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Supply, fixing of PVC pipe,cable,valve etc and other allied works at Hutmura (low lift) Site water supply scheme under Purulia Mechanical Division, PHE, Dte. | 1305/PMD | 03/09/2024 | 20 | KHITISH CH. PATHAK | 3.39 | 0 | 0 | 100
1749 | PURULIA | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | New connection for Hutmura high lift Water supply scheme | BP-23-24-282 | 16/02/2024 | 0 | WBSEDCL PURULIA | 7.07 | 0 | 0 | 0
1750 | PURULIA | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Continuation Work Order for "Hiring of One no. inspection vehicle for Office of the Driller-In-Charge, PMSD (Drilling) under Purulia Mechanical Division P.H.E Dte." (W.e.f- 01.05.2024 to 31.10.2024) | 49/PMSD(Drilling) | 12/03/2024 | 184 | NUPUR CHANDRA HALDER | 0.9 | 0 | 0 | 100
1751 | PURULIA | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Supply, delivery and installation of Open well Submersuble pumping machinery for direct pumping with others electro-mechanical work at Hutmura W/S (OHR Site) under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | 993/PMD | 21/06/2024 | 406 | SUBRATA DUTTA | 15.59 | 0 | 0 | 55
1752 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Extention / replacement of distribution pipe line in different habitation of Hutmura mouza (Jl. No.139) & Phulberia mouza (Jl. No.140) for providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) under augmentation of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 358/PD | 04/03/2022 | 1183 | PREMNATH MITRA | 121.12 | 0 | 0 | 100
1753 | PURULIA | Purulia Division | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Karcha mouza (Jl. No.151) of Hutmura Water Supply Scheme of Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1629/PD | 03/11/2022 | 698 | SHYAMAL KUMAR DEY | 9.56 | 0 | 0 | 100
1754 | PURULIA | Purulia Mechanical | Augmentation of Hutmura PWSS for providing Functional Household Tap Connection (FHTC) , SM/09037 | Augmentation | Supply delivery and installation of 50 KVA voltage stabilizer for Augmentation of Hutmura(OHR site) water supply scheme under PMD PHE Dte. In the district of Purulia. | 395/PMD | 06/04/2023 | 60 | MOON LIGHT HOUSE | 7.36 | 0 | 0 | 100
1755 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Additional work for functional House Hold Tap Connection FHTC including other allied works of Kalaboni Water Supply Scheme of Hura Block Zone- I (Tender No- 982/2021-22 of EE/PD) | BP-2021-22-330 | 23/03/2022 | 0 | NANIGOPAL DEY | 7.35 | 0 | 0 | 0
1756 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-III) (250 Nos.) (Tender No.987/EE/PD of 2021-22) | BP-2022-23-64 | 24/05/2022 | 0 | M/S ACHARJEE CONSTRUCTION | 1.67 | 0 | 0 | 0
1757 | PURULIA | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | NEW SERVICE CONNECTION FOR DESHRA OHR SITE UNDER KALABANI WATER SUPPLY SCHEME UNDER PMD PHE DTE. | BP-2022-23-36 | 08/09/2022 | 0 | WBSEDCL PURULIA | 0.29 | 0 | 0 | 0
1758 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-III) (250 Nos.) (Tender No.978/EE/PD of 2021-22) | BP-2022-23-1 | 05/04/2022 | 0 | M/S ACHARJEE CONSTRUCTION | 10.69 | 0 | 0 | 0
1759 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Additional work by Functional Household Tap Connection (FHTC) including other allied works of Kalaboni Water Supply Scheme of Hura Block of Raghunathpur Sub- Division under Purulia Division, PHE Dte. Zone-II (250) nos. (Tender No- 216/2022-23 of EE/PD) | BP-2022-23-159 | 27/07/2022 | 0 | RAHIBUDDIN MONDAL | 3.3 | 0 | 0 | 0
1760 | PURULIA | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | NEW SERVICE CONNECTION AT PHE LADHURKA OHR SITE UNDER KALABANI WATER SUPPLY SCHEME UNDER PMD PHE DTE. | BP-2022-23-35 | 08/09/2022 | 0 | WBSEDCL PURULIA | 0.48 | 0 | 0 | 0
1761 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Functional household Tap connection (FHTC) in connection with other allied works of Kalaboni W/S Scheme at Hura Block of Raghunathpur (Zone-II) (Tender No- 905/2021-22 of EE/PD) | BP-2021-22-318 | 22/03/2022 | 0 | RAHIBUDDIN MONDAL | 12.46 | 0 | 0 | 0
1762 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Construction of Guard Room cum Chlorine Room at Kalabani Zone-I OHR Campus under Kalabani W/S Scheme (Zone-I) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Tender No.928/EE/PD of 2021-22) | BP-2022-23-253 | 15/09/2022 | 0 | RABIN CHANDRA CHAIL | 5.14 | 0 | 0 | 0
1763 | PURULIA | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | NEW SERVICE CONNECTION FOR KALABANI WATER SUPPLY SCHEME | BP-22-23-34 | 08/09/2022 | 0 | WBSEDCL PURULIA | 0.48 | 0 | 0 | 0
1764 | PURULIA | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | NEW SERVICE CONNECTION FOR TILABANI OHR SITE UNDER KALABANI WATER SUPPLY SCHEME UNDER PMD PHE DTE. | BP-2022-23-37 | 08/09/2022 | 0 | WBSEDCL PURULIA | 0.48 | 0 | 0 | 0
1765 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Construction of guard room along with sanitary & plumbing arrangement at OHR campus (Zone-III) at Deshra of kalaboni (Improvement) W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (Tender No- 886/2021-22 of EE/PD) | BP-2022-23-127 | 19/07/2022 | 0 | BASANTA KUMAR SINGHADEO | 5.04 | 0 | 0 | 0
1766 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Additional work for functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-I) | 1515/PD | 13/12/2021 | 30 | NANIGOPAL DEY | 7.36 | 0 | 0 | 0
1767 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Additional work for functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-II) | 1516/PD | 13/12/2021 | 30 | BASANTA KUMAR SINGHADEO | 7.91 | 0 | 0 | 0
1768 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Additional work for functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-III) | 1517/PD | 13/12/2021 | 30 | PRIYATOSH MUKHERJEE | 8.38 | 0 | 0 | 0
1769 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Construction of Guard Room cum Chlorine Room at Tilabani Zone-IV OHR Campus under Kalabani W/S Scheme (Zone-IV) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1522/PD | 13/12/2021 | 100 | SADHAN GORAIN | 5.95 | 0 | 0 | 0
1770 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 150 cum and Boundary Wall at Deshra OHR Site under Kalabani W/S Scheme (Zone-III) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1525/PD | 13/12/2021 | 60 | BASANTA KUMAR SINGHADEO | 4.87 | 0 | 0 | 0
1771 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone- I) (120 Nos.) | 1528/PD | 13/12/2021 | 30 | CHAIL CONSTRUCTION | 7.56 | 0 | 0 | 0
1772 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-III) (250 Nos.) | 1519/PD | 13/12/2021 | 30 | M/S ACHARJEE CONSTRUCTION | 12.43 | 0 | 0 | 0
1773 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Construction of Guard Room cum Chlorine Room at Deshra Zone-III OHR Campus under Kalabani W/S Scheme (Zone-III) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1520/PD | 13/12/2021 | 100 | BASANTA KUMAR SINGHADEO | 5.89 | 0 | 0 | 0
1774 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 200 cum and Boundary Wall at Kalabani OHR Site under Kalabani W/S Scheme (Zone-I) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1523/PD | 13/12/2021 | 60 | RABIN CHANDRA CHAIL | 4.97 | 0 | 0 | 95
1775 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Construction of Guard Room cum Chlorine Room at Kalabani Zone-I OHR Campus under Kalabani W/S Scheme (Zone-I) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1521/PD | 13/12/2021 | 100 | RABIN CHANDRA CHAIL | 5.92 | 0 | 0 | 96
1776 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 150 cum and Boundary Wall at Ladhurka OHR Site under Kalabani W/S Scheme (Zone-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1524/PD | 13/12/2021 | 60 | NANIGOPAL DEY | 4.8 | 0 | 0 | 95
1777 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Repairing and renovation of WTP campus under Kalabani W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 761/RNP | 15/12/2021 | 45 | SADHAN GORAIN | 4.46 | 0 | 0 | 0
1778 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 200 cum and Boundary Wall at Tilabani zone- IV under Kalabani W/S Scheme (Zone-IV) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1526/PD | 13/12/2021 | 60 | SADHAN GORAIN | 5 | 0 | 0 | 0
1779 | PURULIA | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kalabani Water Supply scheme (OHR no 2 site) Block Hura under PMD PHE Dte. District Purulia. | 322/PMD | 17/05/2022 | 30 | AHALYA ENGINEERING WORKS | 20.57 | 0 | 0 | 98
1780 | PURULIA | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kalabani Water Supply scheme (OHR no 3 site) Block Hura under PMD PHE Dte. District Purulia. | 323/PMD | 17/05/2022 | 30 | S.P. ENTERPRISE | 20.48 | 0 | 0 | 100
1781 | PURULIA | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kalabani Water Supply scheme (OHR no 4 site) Block Hura under PMD PHE Dte. District Purulia. | 324/PMD | 17/05/2022 | 30 | CREATIVE WATER AND PROCESS TECHNOLOGY PVT LTD. | 20.51 | 0 | 0 | 100
1782 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Restoration, repairing & laying of HDPE Pipe line and other allied works under Kalaboni W/S Scheme(Zone-III) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 496/RNP | 02/08/2022 | 20 | SUBRATA SINGHADEO | 4.76 | 0 | 0 | 95
1783 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Supplying & laying of HDPE of pipeline for Tentuldih Village and Interconnection work of overflow line with distribution line at Kalaboni Zone-I OHR site under Kalaboni W/S Scheme under FHTC work (Jal Swapna Project) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1405/PD | 01/09/2022 | 45 | CHAIL CONSTRUCTION | 8.91 | 0 | 0 | 96
1784 | PURULIA | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Supply delivery and installation of submersible pump-motor set instead of existing submersible pump-motor set at Kalabani w/s scheme under Purulia Mechanical Division , PHE, Dte. in the district of Purulia. | 592/PMD | 24/05/2023 | 30 | SUBRATA DUTTA | 9.05 | 0 | 0 | 100
1785 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Sinking of 1(one) No. 200 mm dia DTH rigbored tubewell and dismantling and renovation of boundary wall at (Zone-IV ) under Kolaboni W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1355/PD | 13/09/2023 | 30 | SADHAN GORAIN | 4.34 | 0 | 0 | 100
1786 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Sinking of 1(one) No. 200 mm dia DTH rigbored tubewell and dismantling and renovation of boundary wall at (Zone-I ) under Kolaboni W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1356/PD | 13/09/2023 | 30 | CHAIL CONSTRUCTION | 3.19 | 0 | 0 | 100
1787 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Repairing & renovation of RCC elevated Reservoir capacity 150 cum and boundary wall at Deshra OHR site under kalaboni W/S Scheme (zone-III of Raghunathpur Sub- Division under Purulia Division, PHE Dte. (Tender No-888/2021-22 of EE/PD) | BP-2022-23-79 | 01/07/2022 | 0 | BASANTA KUMAR SINGHADEO | 4.14 | 0 | 0 | 0
1788 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Kalabani Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Zone-II) (250 Nos.) | 1518/PD | 13/12/2021 | 30 | RAHIBUDDIN MONDAL | 12.36 | 0 | 0 | 0
1789 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Restoration work by construction of RCC Retaining wall for Protection work at Kalabani Intake site of Kalabani W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1527/PD | 13/12/2021 | 60 | SADHAN GORAIN | 5.68 | 0 | 0 | 0
1790 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Supply, delivery fitting & fixing of 5 Nos. Scheme Description Sign boards (6' X 3') under Kalaboni W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. Location:- Zone-I (Kalaboni), Zone-II (Ladhurka), Zone-III(Deshra), Zone-IV(Tilaboni) & WTP Campus. | 24/RNP | 15/01/2024 | 7 | M/S SAYAK BHATTACHARYA | 0.86 | 0 | 0 | 0
1791 | PURULIA | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Supply, delivery and installation of lighting arrangement at Ladhurka OHR site (Zone-II) with other allied works under Kalabani w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | 643/PMD | 08/06/2023 | 30 | KOUSHIK CHATTERJEE | 2.46 | 0 | 0 | 100
1792 | PURULIA | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Supply, delivery and installation of lighting arrangement at Kalabani OHR site (Zone-I) with other allied works under Kalabani w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | 641/PMD | 08/06/2023 | 30 | MD. ASLAM | 2.56 | 0 | 0 | 100
1793 | PURULIA | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Supply, delivery and installation of lighting arrangement at Deshra OHR site (Zone-III) with other allied works under Kalabani w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | 642/PMD | 08/06/2023 | 30 | MD. ASLAM | 2.45 | 0 | 0 | 100
1794 | PURULIA | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Supply, delivery and installation of lighting arrangement at Tialabani OHR site (Zone-IV) with other allied works under Kalabani w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | 640/PMD | 08/06/2023 | 30 | MOON LIGHT HOUSE | 2.5 | 0 | 0 | 100
1795 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Supplying laying fitting fixing of HDPE pipe from Manguria-Lalpur OHR site Zone -II main distribution pipe line to Kusmagora Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Kalabani W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 991/PD | 26/07/2023 | 60 | ALOK KUMAR CHAKRABORTY | 14.14 | 0 | 0 | 100
1796 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Supplying laying fitting fixing of HDPE pipe from Manguria-Lalpur OHR site Zone -I main distribution pipe line to Jabjobi Gora Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Kalabani W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1359/PD | 13/09/2023 | 45 | M/S SAYAK BHATTACHARYA | 18.72 | 0 | 0 | 100
1797 | PURULIA | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Sinking of 200mmX165mm tubewell and other allied works for Kalabani water supply scheme Purulia,under PMD, PHE Dte. in the District of Purulia. | 1201/PMD | 03/11/2023 | 15 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 7.12 | 0 | 0 | 100
1798 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Supplying laying fitting fixing of HDPE pipe line from Kolaboni Zone -I OHR site to Hirgram & Hir Rangadihi Village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Kolaboni W/S Scheme of Raghunathpur Sub- Division under Purulia Division, PHE Dte. | 1533/PD | 16/10/2023 | 45 | CHAIL CONSTRUCTION | 18.17 | 0 | 0 | 100
1799 | PURULIA | Purulia Division | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Gravel Paking around Intake, Construction of Guard Wall , Chain link fencing , Digging of earth at Kolaboni Intake site under Kaloboni W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 87/PD | 15/01/2024 | 60 | SADHAN GORAIN | 11.17 | 0 | 0 | 100
1800 | PURULIA | Purulia Mechanical | Augmentation of Kalabani W/S Scheme at Hura Block under Purulia Division, PHE Dte. , SM/09581 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kalabani Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | 111/PMD | 28/02/2022 | 1038 | ORIENTAL ENGINEERING CO. | 20.43 | 0 | 0 | 100
1801 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Laying Distribution pipe line including functional Household Tap Connection (FHTC) and other allied works of Kashipur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-B) (Tender No.963/EE/PD of 2021-22) | BP-2022-23-7 | 05/04/2022 | 0 | MUNNA AGROTECH ENTERPRISE | 62.99 | 0 | 0 | 0
1802 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Sinking of 4 nos 200 mm dia river bed tube well (Horizon) of Darekeswar river (Baikara Ghat) along with laying of 100mm dia GI collecting line with all allied works under Kashipur W/S Scheme (Tender No- 1008/EE/PD of 2021-22) | BP-2022-23-56 | 20/05/2022 | 0 | RABIN CHANDRA CHAIL | 9.27 | 0 | 0 | 0
1803 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Kashipur W/S Scheme, Block - Kashipur) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. (Tender No.727/EE/PD of 2021-22) | BP-2021-22-266 | 28/02/2022 | 0 | STEELCONC AND ASSOCIATES | 4.78 | 0 | 0 | 0
1804 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Laying Distribution pipe line including functional Household Tap Connection (FHTC) and other allied works of Kashipur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-A) (Tender No.37/SE/PMU of 2022-23) | BP-2022-23-360 | 30/09/2022 | 0 | SANTANU BANERJEE | 207.93 | 0 | 0 | 0
1805 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Kashipur W/S Scheme, Block - Kashipur) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. (Tender No.727/EE/PD of 2021-22) |  | 23/02/2022 | 0 | STEELCONC AND ASSOCIATES | 4.78 | 0 | 0 | 0
1806 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Kashipur W/S Scheme, Block Kashipur) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. (Tender No.836/EE/PD of 2021-22) | BP-2021-22-333 | 23/03/2022 | 0 | STEELCONC AND ASSOCIATES | 1.97 | 0 | 0 | 0
1807 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Laying Distribution pipe line including functional Household Tap Connection (FHTC) and other allied works of Kashipur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-B) | 260/PD | 11/02/2022 | 60 | MUNNA AGROTECH ENTERPRISE | 88.48 | 0 | 0 | 100
1808 | PURULIA | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Supply delivery and fitting fixing of the luminaries external and internal lighting with others allied for Augmentation at KASHIPUR w/s scheme under PMD, PHE Dte. in the District of Purulia. | 40/PMD | 19/01/2023 | 60 | PINTU DEY | 7.98 | 0 | 0 | 0
1809 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Sinking of 4 (Four) nos. 200 mm dia river bed tubewell (Horizontal) at darekeswar river (Baikara Ghat) alongwith laying of 100 mm dia G.I. collecting line with all allied works under Kashipur W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | 237/PD | 09/02/2022 | 30 | RABIN CHANDRA CHAIL | 26.74 | 0 | 0 | 100
1810 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Construction of Pump House at Head work site under Kashipur W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | 261/PD | 11/02/2022 | 100 | RABIN CHANDRA CHAIL | 15.35 | 0 | 0 | 85
1811 | PURULIA | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Supply, Delivery and installation of 4 nos. submersible pumps motor sets with other allied works for augmentation of Kashipur w/s scheme under PMD, PHE Dte. in the District of Purulia. | 519/PMD | 05/08/2022 | 30 | DEY ENTERPRISE, HOWRAH | 10.24 | 0 | 0 | 80
1812 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. at Kashipur W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | 344/RNP | 01/06/2022 | 30 | GLORY ENGINEERS SYNDICATE | 1.4 | 0 | 0 | 100
1813 | PURULIA | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Supply delivery and installation of 125 KVA voltage stabilizer for Augmentation of KASHIPUR water supply scheme under PMD PHE Dte. In the district of Purulia. | 75/PMD | 01/02/2023 | 60 | PINTU DEY | 11.26 | 0 | 0 | 100
1814 | PURULIA | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Supply delivery and fitting of 3 Ton capacity triple spur gear type chain pulley Block Mono rail with others allied works for Augmentation at KASHIPUR w/s scheme under PMD, PHE Dte. in the District of Purulia. | 41/PMD | 19/01/2023 | 60 | RABINDRA NATH KHAN | 9.64 | 0 | 0 | 0
1815 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Route Survey & Drawing Preparation for uncovered areas under Kashipur Block under Purulia Division, PHE Dte. | 526/PD | 10/04/2023 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 4.95 | 0 | 0 | 100
1816 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Material Requisition To Resource Division | 399/PD | 11/03/2022 | 0 | Resource Division | 17.15 | 0 | 0 | 0
1817 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Material Requisition To Resource Division | 962/PD | 21/06/2022 | 0 | Resource Division | 18.67 | 0 | 0 | 0
1818 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Material Requisition To Resource Division | 975/PD | 22/06/2022 | 0 | Resource Division | 3.52 | 0 | 0 | 0
1819 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Restoration of Road after laying of drinking water pipe line under Jal Jeevan Mission for Argumentation of Kashipur W/S Scheme on Hura Kaaluput Adra Raghunathpur Road (From Ch.16.00 Km to Ch.16.346 Km) under Purulia Division PWD in the District of Purulia during the year 2023-2024. | BP-2023-24-312 | 26/07/2023 | 0 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 11.08 | 0 | 0 | 0
1820 | PURULIA | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 60 KVA AT 0.4 KV TO 105/105/105/105/105 KVA RESPECTIVELY AT 0.4 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o , EX ENGG PMD PHE DTE(CONSUMER ID : 950023805) TO THEIR PREMISES AT KASHIPUR WATER SUPPLY KASHIPUR DIST PURULIA UNDER REGIONAL OFFICE PURULIA | BP-22-23-87 | 28/02/2023 | 0 | WBSEDCL PURULIA | 3.71 | 0 | 0 | 0
1821 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Construction of RCC elevated reservoir of capacity 250 cum Other allied works under Kashipur W/S Scheme under Raghunathpur Sub-Division, P.H.E. Dte. | 652/PD | 22/04/2022 | 270 | NANIGOPAL DEY | 62.33 | 0 | 0 | 100
1822 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Repairing and Renovation of R.C.C. Old and New Elevated Reservoir including Pump House and other allied works under Kashipur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1928/PD | 22/12/2022 | 90 | SUDHANSHU OJHA | 11.58 | 0 | 0 | 75
1823 | PURULIA | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Supply delivery & installation of flow meter and with others allied works for Augmentation at KASHIPUR w/s scheme under Purulia Mechanical Division, PHE, Dte. in the Purulia District. | 123/PMD | 15/02/2023 | 60 | SANTU MITRA | 3.92 | 0 | 0 | 30
1824 | PURULIA | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Supply delivery and installation of Centrifugal pumping machineries, MCC Panel with others allied works for Augmentation of KASHIPUR Water supply Scheme under PMD, PHE Dte. in the District of Purulia | 39/PMD | 19/01/2023 | 60 | WEST BENGAL ENGINEERING CO | 67.56 | 0 | 0 | 43
1825 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Laying of distribution pipe line & Restoration work by cleaning and chowkage clearance of distribution Main & including providing House Hold Tap Connection (FHTC) two no (Adivasi Hostel) and other allied works at Daldali village under Kashipur Piped water supply scheme of Raghunathpur Sub Division uneder Purulia Division, PHE Dte. | 907/PD | 07/05/2024 | 60 | CHANCHAL MISHRA | 2.61 | 0 | 0 | 100
1826 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Construction of Meter Room at Pump House Site (Kaduri) of Rangamati W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Under Kashipur Water Supply Scheme) | 347/PD | 04/03/2024 | 90 | SUBHAS CHANDRA MAHATO | 2.03 | 0 | 0 | 100
1827 | PURULIA | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Supply, delivery & installation of submersible pumping machinery at River Bed Tubewell and changing cable line, clamping and other allied works at Kashipur w/s scheme under PMD, PHE Dte. in the District of Purulia. | 1230/PMD | 13/08/2024 | 20 | PINTU DEY | 1.62 | 0 | 0 | 100
1828 | PURULIA | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Cable laying from river bed site to pump house at kashipur water supply scheme of augumentation and other allied works under PMD, PHE Dte in the district of purulia. | 963/PMD | 20/06/2024 | 30 | PINTU DEY | 1.71 | 0 | 0 | 100
1829 | PURULIA | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Enhancement of the contract demand from 60 KVA at 0.4 KV to 105/105//105/105/105 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE Kashipur Water Supply, (Consumer ID -950023805) | BP-23-24-311 | 21/03/2024 | 0 | WBSEDCL KASHIPUR CCC | 4.47 | 0 | 0 | 0
1830 | PURULIA | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Supply, Delivery and installation of 4 nos. submersible pumps motor sets with other allied works for Augmentation work of Kashipur w/s scheme under PMD, PHE Dte. in the District of Purulia. | 1546/PMD | 11/11/2024 | 460 | PINTU DEY | 12.16 | 0 | 0 | 45
1831 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Allied works for Laying pipe line , mending good of tap connection due to damage of road during construction of drainage system in connection with Jal jiban mission within Augmentation of Kashipur w/s Scheme under Raghunathpur Sub Division PHE Dte . | 580/PD | 07/04/2025 | 45 | MAHARSHI BANERJEE | 28.69 | 0 | 0 | 80
1832 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Laying Distribution pipe line including functional Household Tap Connection (FHTC) and other allied works of Kashipur Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-A) | 881/PD | 23/05/2022 | 979 | SANTANU BANERJEE | 356.15 | 0 | 0 | 90
1833 | PURULIA | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kashipur Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | 430/PMD | 23/06/2022 | 30 | PREMNATH MITRA | 20.49 | 0 | 0 | 100
1834 | PURULIA | Purulia Mechanical | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Supply and installation of PLC panel, Level transmitter, Solar light(OHR Site) with other allied work at Kashipur water supply scheme under Purulia Mechanical Division PHE Dte. | 1696/PMD | 06/12/2024 | 360 | PINTU DEY | 13.57 | 0 | 0 | 100
1835 | PURULIA | Purulia Division | Augmentation of Kashipur Piped Water Supply Scheme , SM/10047 | Augmentation | Supply fitting fixing MS Specials 200 mm dia in sluice valve chamber at Kashipur under Kashipur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1517/PD | 27/08/2024 | 45 | CHAIL CONSTRUCTION | 1.44 | 0 | 0 | 95
1836 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. , SM/10281 | Anganwadi | Water supply Tap Connection Arrangement for 37nos School upto 200 Students, within Arsha Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | 442/PD | 22/03/2022 | 45 | MEGA SOLAR ENERGY | 155.9 | 0 | 0 | 0
1837 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. , SM/10281 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Arsha G.P of Arsha Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1124/BMD | 12/09/2022 | 22 | M/S D. PALIT AND CO. | 64.49 | 0 | 0 | 0
1838 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. , SM/10281 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Sirkabad G.P of Arsha Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1127/BMD | 12/09/2022 | 15 | M DHARA AND BROTHERS | 36.98 | 0 | 0 | 0
1839 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. , SM/10281 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Puara G.P of Arsha Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1137/BMD | 13/09/2022 | 15 | M DHARA AND BROTHERS | 40.06 | 0 | 0 | 0
1840 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. , SM/10281 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Beldih, Hensla & Mankiyesari G.P of Arsha Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1125/BMD | 12/09/2022 | 20 | M DHARA AND BROTHERS | 43.69 | 0 | 0 | 0
1841 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. , SM/10281 | Anganwadi | Acceptance cum Formal work order for the work of Construction of 200 mm X 165 mm x 200 Mtr depth. Rig Bored Tube wells (D.T.H drilling) in different source less AWC at Chatuhansa & Hetgugui G.P of Arsha Block in the District of Purulia in connection to JJM Program under Bankura Mechanical Division PHE Dte. | 1126/BMD | 12/09/2022 | 20 | M/S D. PALIT AND CO. | 58.04 | 0 | 0 | 0
1842 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. , SM/10281 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 20 nos AWC within Arsha Block (Part-D) of Purulia District under Purulia Division, PHE Dte." | 1733/PD | 22/11/2022 | 45 | M/S. BADAL GHOSH | 94.63 | 0 | 0 | 0
1843 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. , SM/10281 | Anganwadi | Water supply Tap Connection Arrangement for 24 nos AWC within Arsha Block ) of Purulia District under Purulia Division, PHE Dte. | 82/PD | 17/01/2023 | 45 | THE BUSINESS ENGINEERS INDIA | 13.34 | 0 | 0 | 0
1844 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. , SM/10281 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 12 nos AWC within Arsha Block (Part-B) of Purulia District under Purulia Division, PHE Dte." | 1730/PD | 22/11/2022 | 45 | CHATTERJEE CONSTRUCTION | 56.76 | 0 | 0 | 0
1845 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. , SM/10281 | Anganwadi | Acceptance cum Work Order for "Water supply Tap Connection Arrangement for 12 nos AWC within Arsha Block (Part-A) & 1 nos AWC within Arsha Block (Part-E)of Purulia District under Purulia Division, PHE Dte." | 1731/PD | 22/11/2022 | 45 | SEN BROTHERS | 61.5 | 0 | 0 | 100
1846 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. , SM/10281 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Kashipur Block (Part-M) of Purulia District under Purulia Division, PHE Dte. | 145_/PD | 03/02/2023 | 45 | S N POLYMERS PVT LTD | 206.54 | 0 | 0 | 100
1847 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. , SM/10281 | Anganwadi | Water supply Tap Connection Arrangement for 13 nos AWC within Arsha Block of Purulia District under Purulia Division, PHE Dte.(Phase-II) (Part-C, H & I) | 818/PD | 17/05/2022 | 45 | MEGA SOLAR ENERGY | 58.91 | 0 | 0 | 100
1848 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. , SM/10281 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Arsha Block (Part-F),9 nos Awc Within Arsha block (Part-G) & 2nos AWC within Arsha Block (Part-J) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | 1852/PD | 13/12/2022 | 45 | KAMAKHYA ENTERPRISE | 94.65 | 0 | 0 | 100
1849 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. , SM/10281 | Anganwadi | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewellssinked at various Schools & AWCs of . Arsha & Bagmundi blocks under Purulia Division ,PHE,Dte. | 1731/PD | 04/12/2023 | 30 | VIVEKANANDA CONSTRUCTION | 12 | 0 | 0 | 100
1850 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC 108 nos. under Arsha Block In Purulia District under Purulia Division, PHE.Dte. , SM/10281 | Anganwadi | Water supply Tap Connection Arrangement for 13 nos AWC within Arsha Block of Purulia District under Purulia Division, PHE Dte.(Phase-III) (Part-A, B & C) | 826/PD | 17/05/2022 | 45 | KAMAKHYA ENTERPRISE | 81.25 | 0 | 0 | 100
1851 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. , SM/10274 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Raghunathpur-I Block (Part-H) of Purulia District under Purulia Division, PHE Dte. (Tender No.222/EE/PD of 2022-23) | BP-2022-23-278 | 22/09/2022 | 0 | M/S ACHARJEE CONSTRUCTION | 12.86 | 0 | 0 | 0
1852 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. , SM/10274 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Raghunathpur-I Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | 736/PD | 02/05/2022 | 45 | M/S ACHARJEE CONSTRUCTION | 47.43 | 0 | 0 | 0
1853 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. , SM/10274 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Raghunathpur-I Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | 737/PD | 02/05/2022 | 45 | NANIGOPAL DEY | 23.44 | 0 | 0 | 0
1854 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. , SM/10274 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Raghunathpur-I Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | 735/PD | 02/05/2022 | 45 | KHITISH CHANDRA PATHAK | 47.09 | 0 | 0 | 0
1855 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. , SM/10274 | Anganwadi | Water supply Tap Connection Arrangement for 1 no AWC within Raghunathpur-I Block (Part-L) of Purulia District under Purulia Division, PHE Dte. | 738/PD | 02/05/2022 | 45 | SUBHAS CHANDRA MAHATO | 8.29 | 0 | 0 | 0
1856 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. , SM/10274 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Raghunathpur-I Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | 1048/PD | 08/07/2022 | 45 | PRINCE INDUSTRIES ( INDIA) | 197.94 | 0 | 0 | 0
1857 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. , SM/10274 | Anganwadi | Installation of Big-Dia D.T.H. Tube Well (200mm x 165mm) by Robotic DTH Rigs for drilling upto 1200 ft or small form factor trolly mounted rig with trolly mounted compressor suitable for narrow 68 inch wide roads considering 200mt Depth in diferent AWC of different Blocks (PHASE-2) of the District Purulia under Purulia RWS Sub Division,PHE Dte. under Purulia Division, PHE Dte. | 49/PD | 09/01/2023 | 45 | ANUP KUMAR SAHA | 96.1 | 0 | 0 | 100
1858 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. , SM/10274 | Anganwadi | Making Xerox copy of original DPR, Drawing, Mouza Map etc. | 27/2023-149 | 30/05/2023 | 0 | SB CONSTRUCTION | 0.37 | 0 | 0 | 0
1859 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. , SM/10274 | Anganwadi | car hire bill for office purpose against Reg. No.WB55A/7171 bill paid for the month of May,22 to June,22. | BP-2023-24-335 | 02/08/2023 | 0 | NIRUPAMA DEY | 0.68 | 0 | 0 | 0
1860 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. , SM/10274 | Anganwadi | Water supply tap connection arrangement for 25 nos AWC within Raghunathpur-I Block (Part-C) of Purulia District under Purulia Division PHE Dte. (Tender No.50/SE/PMU of 2022-23) | BP-2022-23-447 | 02/12/2022 | 0 | PRINCE INDUSTRIES ( INDIA) | 197.74 | 0 | 0 | 0
1861 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. , SM/10274 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Raghunathpur-I Block (Part-F) of Purulia District under Purulia Division, PHE Dte. | 734/PD | 02/05/2022 | 45 | BASANTA KUMAR SINGHADEO | 70.85 | 0 | 0 | 55
1862 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. , SM/10274 | Anganwadi | Water supply Tap Connection Arrangement for 9nos AWC within Raghunathpur-I Block (Part-E), 2nos AWC within Raghunathpur-I Block (Part-J) & 2nos AWC within Raghunathpur-I Block (Part-K) of Purulia District under Purulia Division, PHE Dte. (Phase-III) (SL-10) | 211/PD | 13/02/2023 | 45 | PRAVAT SARKAR | 107.27 | 0 | 0 | 100
1863 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(102 nos) under Raghunathpur-I Block In Purulia District under Purulia Division, PHE Dte. , SM/10274 | Anganwadi | Water supply Tap Connection Arrangement for 12nos AWC within Raghunathpur-I Block (Part-A) & 6 nos AWC within Raghunathpur-I Block (Part-D-I ) of Purulia District under Purulia Division, PHE Dte. (Phase-I) | 147/PD | 03/02/2023 | 45 | SANTANU BANERJEE | 148.82 | 0 | 0 | 100
1864 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTHmethod in different source less AWC at Serengdi GP and Birgram GP Bagmundi Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 717/PMD | 17/10/2022 | 30 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 69.68 | 0 | 0 | 0
1865 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Matha GP, Bagmundi Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 714/PMD | 17/10/2022 | 15 | GOENKA ENTERPRISE | 31.7 | 0 | 0 | 0
1866 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Bagmundi GP, Bagmundi Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. | 715/PMD | 17/10/2022 | 15 | RABINDRA NATH KHAN | 28.52 | 0 | 0 | 0
1867 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Supply and delivery of 200mm dia UPVC pipe for Baghmundi Block at Drilling Store/Site under Purulia Mechancial Division,P.H.E Dte. | 756/PMD | 07/11/2022 | 30 | NUPUR CHANDRA HALDER | 10.27 | 0 | 0 | 0
1868 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works at Bagmundi WTP site of Bagmundi W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 1931/PD | 22/12/2022 | 90 | ROY CONSTRUCTION | 17.88 | 0 | 0 | 0
1869 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Execution of the yield test at Matha & Bagmundi GP in Bagmundi Block within the district of Purulia under code SM10276 under PMD, PHE, Dte. | 31/PMSD(Drilling) | 03/02/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0 | 0
1870 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 33 nos AWC within Jhalda-II Block ) of Purulia District under Purulia Division, PHE Dte. | 41/PD | 09/01/2023 | 45 | IKBAL CONSTRUCTION | 18.31 | 0 | 0 | 0
1871 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Bagmundi Block where adjacent road is narrow and critical under Purulia Mechanical Division PHE, Dte. In the District of Purulia | 68/PMD | 31/01/2023 | 20 | S N POLYMERS (P) LIMITED | 50.44 | 0 | 0 | 0
1872 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 104 nos AWC within Kashipur & Addl. Block ) of Purulia District under Purulia Division, PHE Dte. | 30/PD | 09/01/2023 | 45 | MADHU SUDAN RAKSHIT | 57.8 | 0 | 0 | 0
1873 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 5 nos AWC within Bagmundi Block ) of Purulia District under Purulia Division, PHE Dte. | 43/PD | 09/01/2023 | 45 | ANUDIP SAHA | 2.78 | 0 | 0 | 0
1874 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Installation of Big-Dia Odex-165 (Simultaneous driving of casing pipe) 165 mm dia Tube Well considering 120mt Depth in diferent schools, AWC of different blocks of the District Purulia under Purulia RWS Sub Division,PHE Dte. under Purulia Division, PHE Dte. | 836/PD | 26/06/2023 | 60 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 94.03 | 0 | 0 | 0
1875 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Kashipur Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | 754/PD | 02/05/2022 | 45 | AMITAVA CHAKRABORTY | 71.14 | 0 | 0 | 0
1876 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Kashipur Block (Part-A) of Purulia District under Purulia Division, PHE Dte.(Phase-I) | 1129/PD | 25/07/2022 | 45 | RAJ KUMAR MONDAL | 94.93 | 0 | 0 | 0
1877 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Jhalda-II Block (Part-C), 2 nos AWC within Jhalda-II Block (Part-D) & 6 nos AWC within Jhalda-II Block (Part-B) of Purulia District under Purulia Division, PHE Dte.(Phase-II) | 1128/PD | 25/07/2022 | 45 | PRINCE INDUSTRIES ( INDIA) | 87.09 | 0 | 0 | 0
1878 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 36nos school for 201-500 students, 2 no. school for 501-800 students and 2no school avove 800 students within Kashipur Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | 1219/PD | 17/08/2022 | 45 | PRAVAT SARKAR | 202.09 | 0 | 0 | 0
1879 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Kashipur Block (Part-B) of Purulia District under Purulia Division, PHE Dte.(Phase-II) | 1130/PD | 25/07/2022 | 45 | A ONE CONSTRUCTION | 94.93 | 0 | 0 | 0
1880 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Kashipur Block (Part-L) of Purulia District under Purulia Division, PHE Dte. | 1201/PD | 12/08/2022 | 45 | MS D.PALIT AND CO. | 197.96 | 0 | 0 | 0
1881 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Sindri GP, Bagmundi Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 718/PMD | 17/10/2022 | 15 | SUMIT KR. CHAKRABORTY | 38.02 | 0 | 0 | 0
1882 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Acceptance cum Work Order For Water supply Tap Connection Arrangement for 2 nos AWC within Kashipur Block (Part-N), 1 nos AWC within Kashipur Block (Part-O) of Purulia District under Purulia Division, PHE Dte. | 1726/PD | 22/11/2022 | 45 | SUBODH PRAMANIK | 24.68 | 0 | 0 | 0
1883 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Construction of Rig bore tube well (200mm X 165mm) by DTH method in different source less AWC at Burda-Kalimati G.P, Baghmundi Block under Purulia Mechanical Division, P.H.E Dte. in the District of Purulia. | 752/PMD | 07/11/2022 | 25 | CHAKRABORTY MINING AND ENGINEERING | 50.66 | 0 | 0 | 0
1884 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Tanturi-Suisa GP, Bagmundi Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. | 716/PMD | 17/10/2022 | 15 | NUPUR CHANDRA HALDER | 12.7 | 0 | 0 | 0
1885 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | 22/PD | 05/01/2023 | 45 | WATER TECH | 165.38 | 0 | 0 | 100
1886 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Jhalda-II Block (Part-E) of Purulia District under Purulia Division, PHE Dte. | 418/PD | 16/03/2022 | 45 | PRINCE INDUSTRIES ( INDIA) | 71.01 | 0 | 0 | 0
1887 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Bagmundi GP, Bagmundi Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.228/EE/PMD of 2022-23) | BP-2022-23-488 | 22/12/2022 | 0 | RABINDRANATH KHAN | 15.23 | 0 | 0 | 0
1888 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Matha GP, Bagmundi Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.229/EE/PMD of 2022-23) | BP-2022-23-531 | 09/01/2023 | 0 | GOENKA ENTERPRISE | 18.36 | 0 | 0 | 0
1889 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Tanturi-Suisa GP, Bagmundi Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.227/EE/PMD of 2022-23) | BP-2022-23-489 | 22/12/2022 | 0 | NUPUR CHANDRA HALDER | 8.69 | 0 | 0 | 0
1890 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Supply and delivery of 200mm dia UPVC pipe for Baghmundi Block at Drilling Store/Site under Purulia Mechancial Division, P.H.E Dte. (Tender No.263/EE/PD of 2022-23) | BP-2022-23-529 | 09/01/2023 | 0 | NUPUR CHANDRA HALDER | 10.25 | 0 | 0 | 0
1891 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Sindri GP Bagmundi Block under Purulia Mechanical Division PHE Dte. in the District of Purulia. (Tender No.221/EE/PMD of 2022-23) | BP-2022-23-456 | 02/12/2022 | 0 | SUMIT KUMAR CHAKRABORTY | 28.21 | 0 | 0 | 0
1892 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Bagmundi GP, Bagmundi Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.228/EE/PD of 2022-23) | BP-2022-23-487 | 22/12/2022 | 0 | RABINDRANATH KHAN | 4 | 0 | 0 | 0
1893 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different source less AWC at Serengdi GP and Birgram GP Bagmundi Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. (Tender No.236/EE/PMD of 2022-23) | BP-2022-23-474 | 16/12/2022 | 0 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 68.49 | 0 | 0 | 0
1894 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Kashipur Block (Part-D) of Purulia District under Purulia Division, PHE Dte. | 1155/PD | 01/08/2022 | 45 | BINGAS ELECTRICAL ELECTRONICS AND SOLAR SYSTEM | 158.22 | 0 | 0 | 80
1895 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within JHALDA -II Block (Part-G)&2 nos Awc Within JHALDA-II block (Part-I) of Purulia District under Purulia Division, PHE Dte. | 1860/PD | 13/12/2022 | 45 | HARI NARAYAN YADAV CONSTRUCTION CO | 41.31 | 0 | 0 | 100
1896 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(109 nos) under Jhalda-II, Barabazar, Bagmundi, Kashipur, Raghunathpur-II Block In Purulia District under Purulia Division, PHE Dte. , SM/10276 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Bagmundi Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | 497/PD | 29/03/2022 | 45 | SUNRISE ENGINEERING CORPORATION | 71.04 | 0 | 0 | 100
1897 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Acceptance cum Formal work order for the work of Providing Hired Driver and man power engagement for construction of R.B.T.W in connection to JJM Programme in Purulia District by Rig unit KLR at B.M.S.D(D) under B.M.D, P.H.E Dte . | 433/BMSD(D) | 13/06/2022 | 108 | CHAKRABORTY MAINING & ENGINEERING. | 2.37 | 0 | 0 | 0
1898 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of DTH Hammer for different Rig unit for sinking of 200mmX165mm RBTW in over burden range at B.M.S.D(D) under B.M.D, P.H.E Dte in connection to JJM programme. | 170/BMSD(D) | 29/03/2022 | 10 | SUDIP ENGINEERING CO | 0.98 | 0 | 0 | 0
1899 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Puncha Block (Part-E) of Purulia District under Purulia Division, PHE Dte. (Tender No.133/EE/PD of 2022-23) | BP-2022-23-325 | 29/09/2022 | 0 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 18.21 | 0 | 0 | 0
1900 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Puncha Block (Part-I) of Purulia District under Purulia Division, PHE Dte. (Tender No. 334/2022-23 of EE/PD)) | BP-2022-23-236 | 05/09/2022 | 0 | M/S ACHARJEE CONSTRUCTION | 6.2 | 0 | 0 | 0
1901 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Puncha Block (Part-F) of Purulia District under Purulia Division, PHE Dte. (Tender No- 103/2022-23 of EE/PD) | BP-2022-23-432 | 25/11/2022 | 0 | JYOTY SOLAR POWER | 25.18 | 0 | 0 | 0
1902 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Puncha Block (Part-H) of Purulia District under Purulia Division, PHE Dte. (Tender No- 156/2022-23 of EE/PD) | BP-2022-23-268 | 20/09/2022 | 0 | SWAPAN MANDAL | 17.44 | 0 | 0 | 0
1903 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Balarampur Block (Part-A) & 9 nos AWC within Balarampur Block (Part-D) of Purulia District under Purulia Division, PHE Dte.(Phase-II) | 1122/PD | 25/07/2022 | 45 | WRISHI ENTERPRISE | 95.12 | 0 | 0 | 60
1904 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of different fast moving spares fpr compressor of KLR Rig vehicle in connection to JJM programme at B.M.S.D(D) under B.M.D, P.H.E Dte | 439/BMSD(D) | 13/06/2022 | 20 | M/S SWAPAN BANERJEE | 1.66 | 0 | 0 | 0
1905 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Acceptance cum Formal work order for the work of Supply and Delivery of Tyre for Different Rig Vehicle at B.M.S.D(D) in connection to JJM Programme. | 442/BMSD(D) | 13/06/2022 | 20 | RAJIB COMPANY | 2.32 | 0 | 0 | 0
1906 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Acceptance cum Formal work order for the work of Providing Hired Driver and man power engagement for construction of R.B.T.W in connection to JJM Programme in Purulia District by Rig unit 7D at B.M.S.D(D) under B.M.D, P.H.E Dte . | 435/BMSD(D) | 13/06/2022 | 108 | PRADIP KUMAR DHABAL | 2.94 | 0 | 0 | 0
1907 | PURULIA | Bankura Mechanical | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Acceptance cum Formal work order for the work of Providing Manpower engagement for construction of R.B.T.W. in connection to JJM programme in Purulia district by Rig Unit 7D at BMSD(D)) under BMD, P.H.E.Dte | 436/BMSD(D) | 13/06/2022 | 108 | PRADIP KUMAR DHABAL | 3.39 | 0 | 0 | 0
1908 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Puncha Block (Part-A) of Purulia District under Purulia Division, PHE Dte. (Phase-I) | 1703/PD | 22/11/2022 | 45 | SWAPAN MANDAL | 91.55 | 0 | 0 | 0
1909 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 15 nos AWC within Puncha Block ) of Purulia District under Purulia Division, PHE Dte. | 31/PD | 09/01/2023 | 45 | S. S. ENTERPRISE | 8.34 | 0 | 0 | 0
1910 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Puncha Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | 604/PD | 19/04/2022 | 45 | SWAPAN MANDAL | 23.62 | 0 | 0 | 0
1911 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 1 no AWC within Puncha Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | 606/PD | 19/04/2022 | 45 | M/S A.D.CONCERN | 7.88 | 0 | 0 | 0
1912 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Puncha Block (Part-F) of Purulia District under Purulia Division, PHE Dte. | 602/PD | 19/04/2022 | 45 | JYOTY SOLAR POWER | 47.36 | 0 | 0 | 0
1913 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Puncha Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | 605/PD | 19/04/2022 | 45 | M/S ACHARJEE CONSTRUCTION | 15.77 | 0 | 0 | 0
1914 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 20nos AWC within Puncha Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | 1051/PD | 08/07/2022 | 45 | B.K. ENTERPRI SE | 158.35 | 0 | 0 | 100
1915 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Puncha Block (Part-D) of Purulia District under Purulia Division, PHE Dte. (Phase-II) | 1704/PD | 22/11/2022 | 45 | RABIN CHANDRA CHAIL | 91.55 | 0 | 0 | 100
1916 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Supply of Fuel & lubricant bill for AWC Puncha Block. | BP-2022-23-849 | 31/03/2023 | 0 | M/S SHANKAR AUTO SERVICE | 4.74 | 0 | 0 | 0
1917 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Puncha Block (Part-F) of Purulia District under Purulia Division, PHE Dte. (Tender No. 103/22-23 of EE/PD) | BP-2022-23-222 | 29/08/2022 | 0 | JYOTY SOLAR POWER | 14.8 | 0 | 0 | 0
1918 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Balarampur Block (Part-H)of Purulia District under Purulia Division, PHE Dte.(Phase-V) | 1125/PD | 25/07/2022 | 45 | BALAJI UDDYOG | 90.51 | 0 | 0 | 70
1919 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Balarampur Block (Part-I)of Purulia District under Purulia Division, PHE Dte.(Phase-VI) | 1126/PD | 25/07/2022 | 45 | BALAJI UDDYOG | 90.51 | 0 | 0 | 40
1920 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Puncha Block (Part-E) of Purulia District under Purulia Division, PHE Dte. | 601/PD | 19/04/2022 | 45 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 70.71 | 0 | 0 | 100
1921 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Puncha Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | 603/PD | 19/04/2022 | 45 | RABINDRANATH KHAN | 23.45 | 0 | 0 | 100
1922 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Puncha Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | 1200/PD | 12/08/2022 | 45 | BALAJI UDDYOG | 197.48 | 0 | 0 | 100
1923 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Puncha Block (Part-K) & 2 nos AWC within Puncha Block (Part-L) of Purulia District under Purulia Division, PHE Dte. (Phase-III) | 1705/PD | 22/11/2022 | 45 | MUNNA AGROTECH ENTERPRISE | 91.67 | 0 | 0 | 100
1924 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(113 nos)under Puncha & Balarampur Block In Purulia District under Purulia Division, PHE.Dte. , SM/10280 | Anganwadi | Work of Vendoring service service relating to E-return for Income-Tax and GST and allied service of Purulia Division, PHE Dte. (w.e.f 01.10.2023 to 30.09.2024) | BP-2024-25-356 | 11/09/2024 | 0 | NIGAM CONSULTANCY SERVICES | 0.77 | 0 | 0 | 0
1925 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Preparation of DPR (Consultancy Work) in connection with the Functional House Hold Connection of different existing PWSS (Palashkola-Keliyathol W/s Scheme, Block Kashipur) to be Augmented/Retrofitting. (Tender No.835/EE/PD of 2021-22) | BP-2022-23-232 | 05/09/2022 | 0 | STEELCONC AND ASSOCIATES | 2.32 | 0 | 0 | 0
1926 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Laying Distribution pipe line and other allied works of Keliathole and Palaskola Water Supply Scheme (Zone-I) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No.68/SE/PMU of 2022-23) | BP-2022-23-397 | 20/10/2022 | 0 | MADHU SUDAN RAKSHIT | 44.2 | 0 | 0 | 0
1927 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Construction of Switch Room-Cum-Chlorine Room at Head Work Site of Keliathole-Palashkola W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 338/RNP | 01/06/2022 | 45 | CHANCHAL MISHRA | 4.23 | 0 | 0 | 0
1928 | PURULIA | Purulia Mechanical | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Supply & installation of submersible pumping machinery at River Bed Tubewell at Palashkhola Keliyathol w/s scheme under PMD, PHE Dte. in the District of Purulia. | 267/PMD | 06/03/2023 | 60 | SAIBAL SARKAR | 47.89 | 0 | 0 | 50
1929 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Providing Functional Household Tap Connection (FHTC) and other allied works of Keliathole Palashkola Water Supply Scheme(Zone-III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 142/RNP | 06/04/2023 | 7 | AMIT PATHAK | 0.93 | 0 | 0 | 0
1930 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Continuation work order for the work of Guarding arrangement through Registered firm organized by Ex-Military person for Guarding of all Govt. properties laying at Keliyathol Elevated Reservoir site under Palaskola-Kelyathol W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (w.e.f. 01.09.2022 to 30.10.2022) | 1360/PD | 31/08/2022 | 60 | MANBHUM SECURITY SERVICE | 1.46 | 0 | 0 | 0
1931 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Palashkola-Keliyathole W/S Scheme, Block - Kashipur) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 357/D/PD | 25/02/2021 | 30 | STEELCONC AND ASSOCIATES | 7.72 | 0 | 0 | 100
1932 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Providing Functional Household Tap Connection (FHTC) at different AWC, School and other allied works of Keliathole -Palashkola Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 348/RNP | 01/06/2022 | 20 | SUBHAS CHANDRA MAHATO | 1.48 | 0 | 0 | 100
1933 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Augmentation by providing functional Household Tap Connection (FHTC) and other allied works of Keliathole Palaskola Water Supply Scheme (Zone-III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-J/II) ( i. Mouza- Gosaindih Alias Birsinghabari, Hab.- Suridih, ii. Mouza- Jibanpur, Hab.- Jibanpur) | 336/RNP | 01/06/2022 | 45 | AMIT PATHAK | 4.55 | 0 | 0 | 100
1934 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Augmentation by providing functional Household Tap Connection (FHTC) and other allied works of Keliathole Palaskola Water Supply Scheme (Zone-II) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-F/I) (Mouza- Keliathole, Hab- Keliathole) | 333/RNP | 01/06/2022 | 45 | NANIGOPAL DEY | 4.58 | 0 | 0 | 100
1935 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Augmentation by providing functional Household Tap Connection (FHTC) and other allied works of Keliathole Palaskola Water Supply Scheme (Zone-II) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-F/II) (Mouza- Keliathole, Hab.- Keliathole) | 334/RNP | 01/06/2022 | 45 | NANIGOPAL DEY | 4.46 | 0 | 0 | 100
1936 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Augmentation by providing functional Household Tap Connection (FHTC) and other allied works of Keliathole Palaskola Water Supply Scheme (Zone-III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-J/I) ( i. Mouza- Gosaindih Alias Birsinghabari, Hab.- Suridih, ii. Mouza- Jibanpur, Hab.- Jibanpur) | 335/RNP | 01/06/2022 | 45 | SUBHAS CHANDRA MAHATO | 4.55 | 0 | 0 | 100
1937 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of 2 Nos. O.H.R. at Keliyathole-Palashkola W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | 465/RNP | 14/07/2022 | 30 | M.K.KAYAL & ASSOCIATES | 2.79 | 0 | 0 | 100
1938 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Repairing and Renovation of Elevated Reservoir at Keliathole Zone and Palashkola Zone including Head work site and other allied works under Keliathole Palashkola W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1925/PD | 22/12/2022 | 90 | SUBHAS CHANDRA MAHATO | 13.16 | 0 | 0 | 100
1939 | PURULIA | Purulia Mechanical | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Palashkhola Keliyathol Water Supply scheme Block Kashipur under Purulia Mechanical Division PHE. Dte. District Purulia | 216/PMD | 28/02/2023 | 30 | COMBINE ENTERPRISES | 21.61 | 0 | 0 | 100
1940 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Material Requisition To Resource Division | 314/PD | 03/03/2023 | 0 | Resource Division | 528.8 | 0 | 0 | 0
1941 | PURULIA | Purulia Mechanical | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Enhancement of contractual demand from 90 KVA at 0.4 KV to their premises at PALASHKHOLA WATER SUPPLY, Dist- Purulia under Regional Office Purulia. |  | 20/07/2023 | 0 | WBSEDCL PURULIA | 6.55 | 0 | 0 | 0
1942 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Restoration of Road after laying of drinking water pipe line under Jal Jeevan Mission for Argumentation of Keliathole-Palashkola W/S Scheme on Hura Kashipur Adra Raghunathpur Road (From Ch.22.163 Km to Ch.22.825 Km) under Purulia Division PWD in the District of Purulia during the year 2023-2024. | BP-2023-24-313 | 26/07/2023 | 0 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 41.92 | 0 | 0 | 0
1943 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Augmentation by providing functional Household Tap Connection (FHTC) and other allied works of Keliathole Palaskola Water Supply Scheme (Zone-III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-L) | 1421/PD | 08/09/2022 | 45 | M/S NANDY ENTERPRISE | 108.08 | 0 | 0 | 90
1944 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Construction of RCC elevated reservoir of capacity 150 cum under Keliathole Palaskola W/S Scheme (Zone-I) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 1401/PD | 01/09/2022 | 270 | SANTANU BANERJEE | 67.83 | 0 | 0 | 90
1945 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Construction of RCC elevated reservoir of capacity 250 cum under Keliathole Palaskola W/S Scheme (Zone-III) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 1402/PD | 01/09/2022 | 270 | RABIN CHANDRA CHAIL | 78.62 | 0 | 0 | 100
1946 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Providing functional Household Tap Connection (FHTC) including Other allied works under Keliathole Palaskola W/S Scheme (Zone-I & III) under Raghunathpur Sub-Division, P.H.E. | 1893/PD | 15/12/2022 | 60 | BASANTA KUMAR SINGHADEO | 129.67 | 0 | 0 | 90
1947 | PURULIA | Purulia Mechanical | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Rectification of Internal lighting and external lighting for Palashkhola Keliyathol w/s scheme under PMD, PHE Dte. in the District of Purulia. | 518/PMD | 05/05/2023 | 60 | RAKSHIT ENTERPRISE | 9.24 | 0 | 0 | 100
1948 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Rudra Mouza, JL No.-10, Plot No.68 at OHR site under Keliyathole-Palashkola W/S Scheme (Zone-I) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 701/PD | 22/05/2023 | 60 | MAHARSHI BANERJEE | 14.33 | 0 | 0 | 70
1949 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Supplying laying fitting fixing of HDPE pipe from Manguria-Lalpur OHR site Zone -I main distribution pipe line to Dolang Kocha Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Manguria-Lalpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1358/PD | 13/09/2023 | 45 | CHANDAN CHATTERJEE | 16.26 | 0 | 0 | 100
1950 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Construction of Office Cum Godown at PHE Campus Under Keliathole Palashkola w/s Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 93/PD | 15/01/2024 | 90 | KM ENTERPRISES | 25.62 | 0 | 0 | 100
1951 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Supplying laying fitting fixing of HDPE pipe line from Chatanigoramore to Kharhbon & Rangadihi Village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Kolaboni Under Kalyathol & Palaskhola W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1505/PD | 27/08/2024 | 45 | CHAIL CONSTRUCTION | 29.59 | 0 | 0 | 100
1952 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | New Sinking of 2 (Two) Nos 200 mm dia river bed vertical tubewell (T/W No.- 4 & 5) along with necessary 100 mm dia GI collecting line from Riverbed Tubewell to common manifold chamber at river bank (Damodar River) at Chinakurighat of Parbeliya W/S Scheme under Keliyathol-Palashkola W/S Scheme of Raghunathpur Sub-Division under Purulia Division , PHE Dte. | 1244/PD | 04/07/2024 | 45 | M/S KARUNAMOYEE CONSTRUCTION | 4.38 | 0 | 0 | 100
1953 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Bypass arrangement with allied works in between of over flow line to distribution main Kolaboni Zone-III OHR site & supplying laying fitting fixing Parallel pipe line at Rangadihi Village & Kharpara village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Kolaboni W/S at Kalyathol & Palaskhola Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte.(Zone -III) | 1354/PD | 25/07/2024 | 90 | SUBRATA SINGHADEO | 22.28 | 0 | 0 | 100
1954 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Supplying laying fitting fixing of HDPE pipe line from Kolaboni Zone -I OHR site to Chatanigora , & Pinrrah Village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Kolaboni Under Kalyathol & Palaskhola W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1506/PD | 27/08/2024 | 45 | CHAIL CONSTRUCTION | 45.72 | 0 | 0 | 100
1955 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Repering & Renovation of connecting line at Kasai River of Maguria Lalpur & including providing House Hold Tap Connection (FHTC) of two no school (Amliatora Pry School -1no, Daldali Girls High School-2nos) and other allied works under Maguria Lalpur W/S at Kalyathol & Palaskhola Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1359/PD | 25/07/2024 | 60 | ALOK KUMAR CHAKRABORTY | 2.54 | 0 | 0 | 100
1956 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Emergent Supply and delivery of sluice valve, MJ collar and all types of CIDF/DI specials for repairing and maintenance of pipe line under Kalyathol & Palaskhola Piped Water Supply Scheme Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-B] | 56/PD | 09/01/2024 | 20 | SSPR VALVE MANUFACTURING PVT LTD | 8.58 | 0 | 0 | 95
1957 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Sinking of 1(One) nostubewell, laying DI pipe , filling and surface dressing at OHR Site of Zone - I of Kashipur Block under Keliathol-Palashkola W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 1355/PD | 25/07/2024 | 30 | MAHARSHI BANERJEE | 6.26 | 0 | 0 | 80
1958 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Supplying laying fitting fixing of different dia pipe line & FHTC connection repairing (Damage of Old different dia pipe line & FHTC connection due to widening of road & Drain of PWD Roads from Doldoli more to Mourandih more &Karandih village ) in connection with Jal Jeevan Mission (JJM) under Maguria Lalpur Under Kalyathol & Palaskhola W/S Scheme of Raghunathpur Sub-Division uneder Purulia Division, PHE Dte. | 1519/PD | 27/08/2024 | 45 | ALOK KUMAR CHAKRABORTY | 16.16 | 0 | 0 | 100
1959 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Laying of Distribution System of pipe line at Kakdiha village is a rest portion of Part-E including providing House Hold Tap Connection (FHTC) and other allied works for Aug. Kalyathol & Palaskhola Piped Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 898/PD | 07/05/2024 | 45 | SABYASACHI MISHRA | 14.23 | 0 | 0 | 100
1960 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Laying of Distribution line and Road Crossing and Construction of Sluice valve Chamber and other allied works for Kashipur under Kalyathol & Palaskhola W/S Scheme in connection with FHTC connection under Jal Jeevan Mission (JJM) Programme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1707/PD | 05/09/2024 | 45 | MAHARSHI BANERJEE | 33.25 | 0 | 0 | 80
1961 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Emergent Supply and delivery of sluice valve, MJ collar and all types of CIDF/DI specials for repairing and maintenance of pipe line under Kalyathol & Palaskhola Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. [Part-A] | 55/PD | 09/01/2024 | 20 | SSPR VALVE MANUFACTURING PVT LTD | 8.13 | 0 | 0 | 95
1962 | PURULIA | Purulia Mechanical | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Enhancement of the contract demand from 90 KVA at 0.4 KV to 180/180/180/180/180 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE Palashkhola Water Supply, (Consumer ID -942406300) | BP-23-24-340 | 21/03/2024 | 0 | WBSEDCL PURULIA | 16.57 | 0 | 0 | 0
1963 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Sl ii) Restoration of Road after laying of drinking water pipe line under Jal Jeevan Mission for Kashipur WS Scheme along Hura-Kashipur-Adra-Raghunathpur Road under Purulia Division PWD in the district of Purulia in Year 2023-2024. Estimate Amount: Rs.1,21,59,280/- | BP-2024-25-408 | 22/09/2024 | 0 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 57.29 | 0 | 0 | 0
1964 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Laying Distribution pipe line and other allied works of Keliathole and Palaskola Water Supply Scheme (Zone-I) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 1162/PD | 01/08/2022 | 974 | MADHU SUDAN RAKSHIT | 121.14 | 0 | 0 | 90
1965 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Additional estimate for laying of distribution system, mending good damage of road and other allied works under Keliathole Palashkola w/s Scheme (Zone-III) within Raghunathpur Sub Division Under Purulia Division ,PHE Dte. | 521/PD | 16/03/2024 | 503 | PREMNATH MITRA | 87.58 | 0 | 0 | 0
1966 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Laying Distribution system ,Functional House hold tap Connection including other allied work under Keliathole Palashkola W/S Scheme (Zone-III) within Raghunathpur Sub-Division under Purulia Division PHE Dte | 2177/PD | 13/12/2024 | 60 | SUBRATA SINGHADEO | 1.69 | 0 | 0 | 0
1967 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Laying Distribution System, installation of Valve, Construction of Valve Chamber and other allied works at Gap Portion under Keliathole Palashkola w/s Scheme (Zone-I) within Raghunathpur Sub-Division Under Purulia Division, PHE Dte | 2184/PD | 13/12/2024 | 336 | MADHU SUDAN RAKSHIT | 19.21 | 0 | 0 | 90
1968 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Laying Distribution pipe line including providing functional Household Tap Connection (FHTC), Laying Clear water Rising main ,Sinking of 6 (Six) nos. 200 mm dia river bed tubewell (Horizontal) at darekeswar river (Baikara Ghat) alongwith laying of 100 mm dia G.I. collecting line , and other allied works of Keliathole and Palaskola Water Supply Scheme (Zone-II) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 1252/PD | 30/08/2022 | 945 | PRINCE INDUSTRIES ( INDIA) | 188.52 | 0 | 0 | 70
1969 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Laying Distribution pipe line and other allied works of Keliathole and Palaskola Water Supply Scheme (Zone-III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (SL-5) | 1443/PD | 14/09/2022 | 1052 | PREMNATH MITRA | 265.46 | 0 | 0 | 95
1970 | PURULIA | Purulia Mechanical | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Supply, Delivery and installation 200 kva voltage stabilizer for Augmentation of Palashkhola Keliyathol w/s scheme for under PMD, PHE Dte. in the District of Purulia. | 519/PMD | 05/05/2023 | 60 | ALPHA ENTERPRISES | 26.97 | 0 | 0 | 100
1971 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Laying distribution pipe line and other allied work under Keliathole Palashkola Water Supply Scheme (Zone-III) at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 673/PD | 17/05/2023 | 807 | PREMNATH MITRA | 70.11 | 0 | 0 | 100
1972 | PURULIA | Purulia Mechanical | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Supply & installation of Horizontal Multistage Centrifugal pumping machinery with other allied works for Augmentation at Palashkhola Keliyathol w/s scheme under PMD, PHE Dte. in the District of Purulia. | 646/PMD | 08/06/2023 | 662 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 77.49 | 0 | 0 | 100
1973 | PURULIA | Purulia Division | Augmentation of Kalyathol & Palaskhola Piped Water Supply Scheme , SM/11453 | Augmentation | Supply, delivery fitting & fixing of 33Nos. Land Demarcation Sign boards (0.9 m X 0.6 m) under Jal Jeevan Mission at dufferent Location under different W/S Scheme in Kashipur Block within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 2308/PD | 31/12/2024 | 60 | BISWAJIT MAJI | 3.01 | 0 | 0 | 100
1974 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A , SM/14025 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 357/E/PD | 25/02/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 42.7 | 0 | 0 | 100
1975 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A , SM/14025 | Augmentation | Repairing and renovation of Gar Panchakot Inspection Bunglow (1st Floor & outside) with allied works at Lakhanpur WTP under Raghunathpur Area (EAP) W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 278/PD | 27/02/2023 | 30 | CREATIVE WATER AND PROCESS TECHNOLOGIES PRIVATE LIMITED | 3.09 | 0 | 0 | 0
1976 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A , SM/14025 | Augmentation | Continuation work order for the work of Survey & Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 1025/PD | 06/01/2023 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5 | 0 | 0 | 100
1977 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A , SM/14025 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 1008/PD | 29/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
1978 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A , SM/14025 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 942/PD | 19/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
1979 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A , SM/14025 | Augmentation | Continuation work order for the work of Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 1087/A/PD | 16/01/2023 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.15 | 0 | 0 | 100
1980 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A , SM/14025 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 931/A/PD | 13/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
1981 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A , SM/14025 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 1002/PD | 23/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
1982 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A , SM/14025 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Nanduka Mouza, JL No.-63, Plot No.-476 under Raghunathpur-II Block at OHR site under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte | 698/PD | 22/05/2023 | 60 | AMIT PATHAK | 14.25 | 0 | 0 | 100
1983 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A , SM/14025 | Augmentation | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-V-A) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Name of Mouzas-Simra ,Pabra , Nabagram, Muchkunda , Muldi , pratappur , Dhanuktor , Manipur) | 2204/PD | 13/12/2024 | 60 | SANTANU BANERJEE | 96.18 | 0 | 0 | 0
1984 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A , SM/14025 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Khajura Mouza, JL No.-164, Plot No.-565 under Raghunathpur-I Block at OHR site under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 766/PD | 08/06/2023 | 60 | MAA TARA CONSTRUCTION | 11.42 | 0 | 0 | 100
1985 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A , SM/14025 | Augmentation | Construction of Switch Room Cum Chlorin Room at Zone-V-B (Nanduka) OHR Site of Raghunathpur W/S Scheme (German Project) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1728/PD | 04/12/2023 | 100 | MANIK MAHATO | 4.86 | 0 | 0 | 100
1986 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A , SM/14025 | Augmentation | Material Requisition To Resource Division | 1104/PD | 11/06/2024 | 0 | Resource Division | 25.08 | 0 | 0 | 0
1987 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V A , SM/14025 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC), and other allied works of Raghunathpur Water Supply Scheme (Zone-VA) at Raghunathpur-II Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. (SL - 7) | 461/PD | 27/03/2023 | 733 | SANTANU BANERJEE | 341.55 | 0 | 0 | 75
1988 | PURULIA | Purulia Division | MINI PIPED WATER SUPPLY SCHEME FOR BAMNI VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER ARSHA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/16570 | New | Survey in connection with the Mini Water Supply Scheme having house hold within 20 under Arsha, Baghmundi, Balarampur, Barabazar, Bundwan, Jaipur & Jhalda-I Block [3+14+5+22+10+6+18=78 nos Habitations] under Jal Sapna/ JJM Programme under Purulia Division P.H.E. Dte. | 112/A/PSD | 10/02/2023 | 21 | M/S R. DUTTA & CO. | 3.07 | 0 | 0 | 0
1989 | PURULIA | Purulia Division | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) , SM/18528 | New | Details survey of WTP site as well as intake site to ascertion depth and area basin at Shiulibari Mouza, Nituria Block under Northern Zone W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 549/PD | 12/04/2023 | 30 | ROY CHOWDHURY ASSOCIATES | 5.39 | 0 | 0 | 100
1990 | PURULIA | Purulia Division | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) , SM/18528 | New | Material Requisition To Resource Division | 1904/PD | 21/10/2024 | 0 | Resource Division | 66.57 | 0 | 0 | 0
1991 | PURULIA | Purulia Division | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) , SM/18528 | New | Electric quotation along with M.B No1200/PMD for payment of shifting of 11KV PHE feeder & 11 KV Rampur feeder from Northern Sector WTP Campus for payment from your end. | BP-2023-24-889 | 18/03/2024 | 0 | WBSEDCL | 45.82 | 0 | 0 | 0
1992 | PURULIA | Purulia Division | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) , SM/18528 | New | Construction and Commissioning of RCC Over Head Reservoir ( Torch type with solid raft ) of capacity 150 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied works & Operation & Maintenance of Distribution , Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six month (36) for Zone-II of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-2) | 1560/PD | 18/10/2023 | 1171 | RAJ BROTHERS | 264.65 | 0 | 0 | 22
1993 | PURULIA | Purulia Mechanical | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) , SM/18528 | New | Hiring of maxi cab (non air conditioned) Bharat Stage-III Diesel/LPG/CNG driver engine including driver for official use of the Assistant Engineer, Purulia Mechanical Sub-Division (W/S) PHE, Dte. (01/10/24 to 31/03/25) | 399/PMSD(W/S) | 23/09/2024 | 182 | PINTU DEY | 0.86 | 0 | 0 | 0
1994 | PURULIA | Purulia Division | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I) , SM/18528 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone - V & VI of Hura Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 270 m). | 63/PD | 10/01/2024 | 415 | SUBHAS CHANDRA MAHATO | 37.7 | 0 | 0 | 100
1995 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part - A , Mouza - Dhenksila, Ledasan] | 1062/PD | 08/08/2023 | 60 | BOSE CONSTRUCTION | 83.17 | 0 | 0 | 0
1996 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 200 CUM and staging height 20 mtr as per approved drawing (No:PCI/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month at Zone- VIII of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call)(SL-6) | 1098/PD | 14/08/2023 | 270 | PRAVAT SARKAR | 406.17 | 0 | 0 | 0
1997 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -C , Mouza - Saoradi & Kushtor] | 1079/PD | 10/08/2023 | 45 | BASANTA PARAMANIK | 28.33 | 0 | 0 | 0
1998 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing (No:PCI/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month at Zone- IV of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call)(SL-5) | 1093/PD | 14/08/2023 | 270 | MS D.PALIT AND CO. | 373.13 | 0 | 0 | 0
1999 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six(36) month at Zone- VII of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector ) under Purulia Divn. PHE Dte.(SL-16) | 1094/PD | 14/08/2023 | 270 | KOUSHIK CHATTERJEE | 274.47 | 0 | 0 | 0
2000 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of boundary wall at Zone IV H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | 1144/PD | 17/08/2023 | 30 | DILIP MISHRA | 17.51 | 0 | 0 | 0
2001 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 500 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for Zone-VI of Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-12) | 1575/PD | 30/10/2023 | 270 | SADHAN GORAIN | 704.66 | 0 | 0 | 0
2002 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Raibanbh Mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | 1646/PD | 08/11/2023 | 60 | ROY CONSTRUCTION | 19.01 | 0 | 0 | 0
2003 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Belguma mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | 1645/PD | 08/11/2023 | 60 | S.R ENTERPRISE | 58.5 | 0 | 0 | 0
2004 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for Zone-IV of Raghunathpur-I Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-1) | 1564/PD | 26/10/2023 | 270 | PARTHA PRATIM CHHATAIT | 393.93 | 0 | 0 | 0
2005 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe Line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector) at Purulia-I Block (Zone-VI) For Buridi Mouza under Purulia Division. PHE Dte. | 1638/PD | 08/11/2023 | 45 | TAPAS KUMBHAKAR | 46.5 | 0 | 0 | 0
2006 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 300 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012)with allied works for Zone- V of Santuri Block under Purulia Piped Water Supply Scheme (Northern Zone ) under Purulia Divn. PHE Dte. | 692/PD | 22/05/2023 | 210 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 81.57 | 0 | 0 | 0
2007 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - VII of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -D, Mouza - Kendthol & Kharbar] | 1070/PD | 08/08/2023 | 60 | ASHOKE ADHIKARY | 28.6 | 0 | 0 | 45
2008 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - VI of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -E, Mouza - Amlagarya, Shaltora & Rambhatdi] | 1061/PD | 08/08/2023 | 878 | SUBRATA SINGHADEO | 76.77 | 0 | 0 | 30
2009 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -F , Mouza - Amdiha, Bidhakata] | 1064/PD | 08/08/2023 | 482 | CHANDAN CHATTERJEE | 37.59 | 0 | 0 | 60
2010 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providingFunctional Household Tap Connection (FHTC), including other allied work for Zone - VII of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -E, Mouza - Palash Pahari & Benrya] | 1071/PD | 08/08/2023 | 60 | M/S KHAN ENTERPRISE | 42.09 | 0 | 0 | 70
2011 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -C, Mouza - Jiyataal, Chhayrabari, Ambari] | 1052/PD | 08/08/2023 | 60 | M/S. BADAL GHOSH | 93.96 | 0 | 0 | 60
2012 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providingFunctional Household Tap Connection (FHTC) including other allied work for Zone VII of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -C, Mouza-kulal &gothbathanj] | 1069/PD | 08/08/2023 | 60 | SK ABBAS | 31.68 | 0 | 0 | 45
2013 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - VI of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -B , Mouza - Salberya] | 1058/PD | 08/08/2023 | 443 | SUBHAS CHANDRA MAHATO | 42.72 | 0 | 0 | 48
2014 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - VI of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -D, Mouza - Benagaria(5%), Ghutgarya, Latulbad & Dulalgora] | 1060/PD | 08/08/2023 | 60 | PRATIK SAHA | 93.7 | 0 | 0 | 70
2015 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -E , Mouza - Lapahari, Nuhichabad, Moraldi] | 1051/PD | 08/08/2023 | 60 | SUMIT KUMAR CHAKRABORTY | 58.97 | 0 | 0 | 60
2016 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -B , Mouza - Brindabanpur] | 1078/PD | 10/08/2023 | 60 | M/S MONDAL ENTERPRISE | 74.83 | 0 | 0 | 60
2017 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -G , Mouza - Kankarkiari, Malibana, Dubrajpur] | 1065/PD | 08/08/2023 | 1123 | MADHU SUDAN RAKSHIT | 59.37 | 0 | 0 | 65
2018 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -D , Mouza - Tarabari, Gumra] | 1050/PD | 08/08/2023 | 602 | KHITISH CHANDRA PATHAK | 96.93 | 0 | 0 | 60
2019 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -G , Mouza - Muktipur] | 1083/PD | 10/08/2023 | 60 | CHATTERJEE CONSTRUCTION | 94.06 | 0 | 0 | 75
2020 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including submission of complete detailed drawing of distribution system, rising main etc. after execution of work and other allied work for Zone - I of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division , PHE Dte. [Part - C, Mouza - Pachandapur, Beliapur & Kalikapur] | 1084/PD | 10/08/2023 | 60 | RANJIB GHATAK | 91.79 | 0 | 0 | 60
2021 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - VII of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -F, Mouza - Goalberya &Matidundra] | 1072/PD | 08/08/2023 | 60 | TAPAN CHANDRA | 49.95 | 0 | 0 | 48
2022 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - V of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -B , Mouza - Benagaria] | 1063/PD | 08/08/2023 | 60 | KABERI DUTTA | 32.36 | 0 | 0 | 76
2023 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -D , Mouza - Kinaidih & Majharadih] | 1080/PD | 10/08/2023 | 529 | THE BUSINESS ENGINEERS INDIA | 25.17 | 0 | 0 | 65
2024 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -A , Mouza - Kandberya & Authumajhirdi] | 1077/PD | 10/08/2023 | 60 | M/S KALYANI ENTERPRISE | 95.29 | 0 | 0 | 60
2025 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-VIII of Purulia-I block for Amandih mouza under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division ,PHE Dte. | 1495/PD | 12/10/2023 | 45 | SUSANTA KR DUTTA | 60.42 | 0 | 0 | 0
2026 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Zone ) at Purulia I Block (Zone-V) for Hulka & Kultanr alias nadiyara Under Purulia Divn PHE DTE. | 1493/PD | 12/10/2023 | 45 | KABERI DUTTA | 11.47 | 0 | 0 | 0
2027 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -F , Mouza - Jibanpur Alias Ramjibanpur, Barhanti & Talberya] | 1540/PD | 16/10/2023 | 443 | M/S SB CONSTRUCTION | 65.75 | 0 | 0 | 55
2028 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month for Zone-XI of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-8) | 1426/PD | 29/09/2023 | 703 | SUJIT SAHANA | 361.35 | 0 | 0 | 15
2029 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenances of Distributions , Pipe Lines (DI/HDPE), including Slice Valves & FHTCs for the period of thirty six (36) month Zone - X , XI & XIV of Hura Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-2) | 1415/PD | 29/09/2023 | 360 | LUKE ENGICON | 1374.87 | 0 | 0 | 30
2030 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-V of Purulia-I block for Mahalitora Mouza under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division, PHE Dte. | 1491/PD | 12/10/2023 | 45 | SOUVIK MANDAL | 33.54 | 0 | 0 | 0
2031 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - II of Neturia Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -D, Mouza - Narayanpur & Nadiha (20%) ] | 1634/PD | 08/11/2023 | 45 | BABA LOKNATH ENTERPRISE | 59.46 | 0 | 0 | 60
2032 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -B, Mouza - Kalipahari, Hansdima] | 1536/PD | 16/10/2023 | 533 | KHITISH CHANDRA PATHAK | 77.29 | 0 | 0 | 60
2033 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providingFunctional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -D, Mouza - Pirargoriya & Lediam] | 1538/PD | 16/10/2023 | 60 | GHOSH AND ROY ENTERPRISE | 52.38 | 0 | 0 | 55
2034 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Zone ) at Purulia I Block (Zone-VIII) for Dimdiha Mouza Under Purulia Divn PHE DTE. | 1526/PD | 16/10/2023 | 45 | BHAGABANDAS KUMAR | 31.72 | 0 | 0 | 0
2035 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -A, Mouza - Marbedya, Ghoramurga] | 1535/PD | 16/10/2023 | 868 | AMIT PATHAK | 64.16 | 0 | 0 | 55
2036 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for Zone-III of Raghunathpur-I Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-15) | 1567/PD | 26/10/2023 | 888 | KM ENTERPRISES | 243.33 | 0 | 0 | 65
2037 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir ( Torch type with solid raft ) of capacity 250 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied works & Operation & Maintenance of Distribution , Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six month (36) for Zone-II of Raghunathpur - I Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-14) | 1559/PD | 18/10/2023 | 1076 | ASHOKE KUMAR CHATTERJEE | 413.23 | 0 | 0 | 5
2038 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - II of Neturia Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -B, Mouza - Nadiha (80%)] | 1633/PD | 08/11/2023 | 60 | MOLLA ENTERPRISE | 67.12 | 0 | 0 | 60
2039 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector)at Purulia-I Block(Zone-VI) For Khojda Mouza under Purulia Division. PHE Dte. | 1636/PD | 08/11/2023 | 45 | SOUVIK MANDAL | 51.27 | 0 | 0 | 0
2040 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Zone )at Purulia I Block (Zone-IV) for Chakra, Kultanr alias Nadiyara Under Purulia Divn. PHE DTE. | 1528/PD | 16/10/2023 | 45 | SOUHARDYA BUSINESS LINE | 34.94 | 0 | 0 | 0
2041 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -C, Mouza - Chhota Pathar, Kashikunri, Baghadabar & Kushunda] | 1537/PD | 16/10/2023 | 60 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 84.9 | 0 | 0 | 60
2042 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector)at Purulia-I Block(Zone-VI) For Bamra Mouza under Purulia Division. PHE Dte. | 1640/PD | 08/11/2023 | 60 | CHATTERJEE CONSTRUCTION | 15.46 | 0 | 0 | 0
2043 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Simulia Mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | 1641/PD | 08/11/2023 | 60 | RAJAT KARMAKAR | 43.25 | 0 | 0 | 0
2044 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector)at Purulia-I Block(Zone-VI) For Kanali Mouza under Purulia Division. PHE Dte. | 1637/PD | 08/11/2023 | 45 | MANATOSH SINGH | 50.19 | 0 | 0 | 0
2045 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Chakda Mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | 1643/PD | 08/11/2023 | 60 | MS D.PALIT AND CO. | 88.91 | 0 | 0 | 0
2046 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-V of Purulia-I block for Dhadhka mouza under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division ,PHE Dte. | 1497/PD | 12/10/2023 | 45 | KOUSHIK CHATTERJEE | 22.91 | 0 | 0 | 0
2047 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Kalipur Mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | 1642/PD | 08/11/2023 | 60 | DEBANJAN SEAL | 22.77 | 0 | 0 | 0
2048 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir including Laying Distribution Pipe lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six (36) months for Zone- XIV & XV of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector ) under Purulia Divn. PHE Dte. (2nd Call) (SL-1) | 1598/PD | 31/10/2023 | 793 | MRITYUNJOY MUKHERJEE & CO | 831.47 | 0 | 0 | 1
2049 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) nos tubewellat BPS Site (Mouza- PurbaBero, JL No-195, Plot No-1839) of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 330 mtr.) | 83/PD | 15/01/2024 | 60 | SABYASACHI MISHRA | 38.55 | 0 | 0 | 0
2050 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line including FHTC and other allied work for Zone-I of Neturia Block at Mouza-Pochhara under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHEDte.(Part-B) | 92/PD | 15/01/2024 | 807 | BISWAJIT MAJI | 22.45 | 0 | 0 | 60
2051 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone - XV & XVI of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 290 m) | 81/PD | 15/01/2024 | 60 | SUMIT KUMAR CHAKRABORTY | 39.78 | 0 | 0 | 50
2052 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line including other allied work for Zone-I of Neturia Block under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte.(Part-D) | 94/PD | 15/01/2024 | 60 | KANJILAL AND CO. | 12.5 | 0 | 0 | 0
2053 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- V & VI of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 280 m) | 70/PD | 10/01/2024 | 60 | HUSSAIN CONSTRUCTION | 38.75 | 0 | 0 | 0
2054 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone - VII & VIII of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 280 m) | 80/PD | 15/01/2024 | 60 | KRISHNA CONSTRUCTION AND ORDER SUPPLIER | 38.78 | 0 | 0 | 50
2055 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-VII of Purulia-I block for Golbera mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | 239/PD | 15/02/2024 | 60 | MARAUTI CONSTRUCTION AND CO | 83.25 | 0 | 0 | 0
2056 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-VI of Purulia-I block for Shibdi Mouza under Purulia Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (Sl No. 30) | 1030/PD | 04/06/2024 | 60 | MS D.PALIT AND CO. | 120.66 | 0 | 0 | 0
2057 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Neturia (Zone-I) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 923/PD | 07/05/2024 | 60 | M/S SB CONSTRUCTION | 63.99 | 0 | 0 | 0
2058 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 600 CUM and staging height 20 mtr as per approved drawing (No:PCI/OHR/3/2012) with allied works for Zone- I of Purulia-1 Block under Purulia Piped Water Supply Scheme (Northern Zone ) under Purulia Divn. PHE Dte. (Sl No. 01) | 1026/PD | 04/06/2024 | 270 | SADHAN GORAIN | 141.19 | 0 | 0 | 0
2059 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-VIII of Purulia-I block for Rudra mouza (Part B) under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division, PHE Dte. | 1060/PD | 07/06/2024 | 60 | SOUMITRA CHAKRABORTY | 77.87 | 0 | 0 | 0
2060 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) and Laying Distribution Pipe Lines with allied works for Zone-II of Neturia Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte.[ Part - A, Mouza- Puapur ] (Sl No. 06) | 1029/PD | 04/06/2024 | 270 | KHITISH CHANDRA PATHAK | 157.44 | 0 | 0 | 0
2061 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) and providing Functional Household Tap Connection (Mouza - Bhul) with allied works for Purulia Piped Water Supply Scheme (Northern Zone) under Purulia Divn. PHE Dte. (Sl No. 01) | 1027/PD | 04/06/2024 | 270 | M DHARA & BROTHERS | 131.3 | 0 | 0 | 0
2062 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -F , Mouza - Lalgarh] | 1082/PD | 10/08/2023 | 60 | M/S SAYAK BHATTACHARYA | 71.84 | 0 | 0 | 100
2063 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - III of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -E , Mouza - Kotaldih] | 1081/PD | 10/08/2023 | 45 | HAFIJUR RAHAMAN MIDYA | 39.96 | 0 | 0 | 90
2064 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - II of Neturia Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -E, Mouza - Ranipur Colliery & Deiliya] | 1635/PD | 08/11/2023 | 30 | M/S SAYAK BHATTACHARYA | 89.86 | 0 | 0 | 100
2065 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- XI & XII of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 280 m) | 72/PD | 10/01/2024 | 60 | SAMAN KUMAR MAHATO | 38.79 | 0 | 0 | 100
2066 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying distribution system including providing FHTC(Lalpur Paharpur , Domsota) and other allied works for Zone-I of Neturia Block under Purulia Piped Water Supply Scheme (Northern Zone ) under Purulia Divn. PHE Dte. (Part-A) | 99/PD | 15/01/2024 | 60 | M/S SAYAK BHATTACHARYA | 51.94 | 0 | 0 | 100
2067 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- III & IV of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 300 m) | 69/PD | 10/01/2024 | 416 | CHANCHAL MISHRA | 40.76 | 0 | 0 | 95
2068 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- XI & XII of Hura Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division,P.H.E. Dte.(Total Length of Boundary Wall: 280m) | 66/PD | 10/01/2024 | 268 | M/S KALYANI ENTERPRISE | 38.8 | 0 | 0 | 100
2069 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- I & II of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 290 m) | 68/PD | 10/01/2024 | 60 | AMIT PATHAK | 39.72 | 0 | 0 | 65
2070 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone - I & II of Hura Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 280 m) | 192/PD | 02/02/2024 | 60 | TOTAL INFRA | 38.57 | 0 | 0 | 100
2071 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone - XVII & XVIII of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 280 m) | 82/PD | 15/01/2024 | 60 | SANJAY KUMAR NARSARIA | 38.72 | 0 | 0 | 100
2072 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall & Sinking of T/well at Jhalda-II,Zone-VII under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | 334/PD | 01/03/2024 | 60 | VIVEKANANDA CONSTRUCTION | 22.85 | 0 | 0 | 100
2073 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI rising main including bypass arrangement & other allied works & construction of boundary wall at Baghmundi WTP Site in Purulia Water Supply Scheme (Northern Sector) under Purulia Division, PHE Dte. | 895/PD | 07/05/2024 | 60 | ROY CONSTRUCTION | 36.11 | 0 | 0 | 100
2074 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Sinking of 1(One) nos tube well, Withdrawing and relaying of DI Pipe, Earth filling and surface dressing Near Northern Sector Head work site under Purulia Piped w/s Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 912/PD | 07/05/2024 | 30 | CHATTERJEE CONSTRUCTION | 7.82 | 0 | 0 | 85
2075 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Sinking of 1(One) no 200 mm dia DTH rigbored tubewell at OHR Sites of Zone - II ( Fusrabad) of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 1501/PD | 27/08/2024 | 30 | BISWAJIT MAJI | 5.49 | 0 | 0 | 100
2076 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Sinking of 1(One) nos tubewell at OHR Site of Zone - V of Raghunathpur-II Block under Northen Sector Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 1521/PD | 27/08/2024 | 30 | CHAIL CONSTRUCTION | 5.08 | 0 | 0 | 100
2077 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Material Requisition To Resource Division | 2255/PD | 19/12/2024 | 0 | Resource Division | 157.32 | 0 | 0 | 0
2078 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB050611202404020185125751XX DT.06-11-2024. | BP-2024-25-527 | 14/11/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
2079 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB052611202406351574709356XX DT.26-11-2024. | BP-2024-25-532 | 02/12/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
2080 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB051111202412201575410323XX DT.11-11-2024. | BP-2024-25-529 | 14/11/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
2081 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Restoration of Road after laying of drinking after pipe line under JAL Jeevan Mission for W/S Scheme along Raghunathpur Chalunia Road, in the District of Purulia under Purulia Division PWD Dte. during the year 2024-2025. (Memo No.924/PWD dt.19.06.2024) (Norther Sector) | BP-2024-25-340 | 28/08/2024 | 0 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 47.28 | 0 | 0 | 0
2082 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Restoration of Road after laying of drinking after pipe line under JAL Jeevan Mission for W/S Scheme along Raghunathpur Chalunia Road, in the District of Purulia under Purulia Division PWD Dte. during the year 2024-2025. (Memo No.1536/PWD dt.27.09.2024) (Norther Sector) | BP-2024-25-530 | 14/11/2024 | 0 | EXECUTIVE ENGINEER, PURULIA DIVISION PWD DTE. | 47.28 | 0 | 0 | 0
2083 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB051111202412211573995764XX DT.11-11-2024. | BP-2024-25-528 | 14/11/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
2084 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Additional work of Laying Distribution Pipe line at Zone-III of Purulia-II Block under Purulia Piped Water Supply Scheme (Northen Sector) under Purulia Division, PHE Dte. | 1058/PD | 17/06/2025 | 45 | SWAPAN MANDAL | 0 | 0 | 0 | 0
2085 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) with allied works for Zone- IV of Santuri Block under Purulia Piped Water Supply Scheme ( Northern Zone ) under Purulia Divn. PHE Dte. | 693/PD | 22/05/2023 | 1045 | M/S. BADAL GHOSH | 87.8 | 0 | 0 | 65
2086 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012), Laying of Distribution pipeline, providing FHTC including other allied works for Zone- II of Santuri Block under Purulia Piped Water Supply Scheme (Northern Zone ) under Purulia Divn. PHE Dte. [Part - A Mouza- MURULIA (3.5%)] | 694/PD | 22/05/2023 | 872 | MAHARSHI BANERJEE | 95.06 | 0 | 0 | 90
2087 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - VI of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -C, Mouza - Bhagabandh, Kherad] | 1059/PD | 08/08/2023 | 518 | SINGHA ENTERPRISE | 51.36 | 0 | 0 | 0
2088 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone- VII of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -B , Mouza - Gorsika] | 1068/PD | 08/08/2023 | 545 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 71.26 | 0 | 0 | 50
2089 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 200 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012), Laying of Distribution Pipe Line with allied works for Zone- VII of Santuri Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. [Part - A Mouza-Gorsika] | 1138/PD | 17/08/2023 | 1088 | AMIT PATHAK | 94.37 | 0 | 0 | 20
2090 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenances of Distributions , Pipe Lines (DI/HDPE), including Slice Valves & FHTCs for the period of thirty six month for Purulia Piped Water Supply Scheme (Northern Sector) at Puncha Block(Zone - VII & VIII) under Purulia Divn. PHE Dte. (SL-3) | 1416/PD | 29/09/2023 | 636 | JAYANTA KUMAR MONDAL | 888.48 | 0 | 0 | 38
2091 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six months (36) for Zone-III & IV of Raghunathpur - II Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-21) | 1428/PD | 29/09/2023 | 812 | NIBHAS SINHA | 863.77 | 0 | 0 | 12
2092 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied Works & Operation & Maintenance of Distribution , Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six month (36) for Zone- V of Raghunathpur - II block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-22) | 1422/PD | 29/09/2023 | 915 | RABIN CHANDRA CHAIL | 207.13 | 0 | 0 | 20
2093 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenances of Distributions , Pipe Lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six (36) months for Purulia Piped Water Supply Scheme (Northern Sector) at Manbazar-I Block(Zone - I to IV) under Purulia Divn. PHE Dte. (SL-4) | 1417/PD | 29/09/2023 | 780 | SHYAM KUMAR | 1479.87 | 0 | 0 | 50
2094 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied Works & Operation & Maintenance of Distribution , Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six month (36) for Zone- I of Raghunathpur - II block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-19) | 1424/PD | 29/09/2023 | 1095 | TUMPA GORAIN | 117.63 | 0 | 0 | 15
2095 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-V of Purulia-I block for Hulka & kultanr Alias nadiyara under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division ,PHE Dte. | 1492/PD | 12/10/2023 | 452 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 41.55 | 0 | 0 | 0
2096 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing ( No: PCI-I/OHR/3/2012)with allied works for Purulia Water Supply Scheme.(Location:-Block-Purulia-1 , Zone-VIII) for Northern Zone | 1494/PD | 12/10/2023 | 539 | KM ENTERPRISES | 81.93 | 0 | 0 | 45
2097 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for Purulia Piped Water Supply Scheme (Northern Sector) at Puncha Block (zone-IV & V) under Purulia Divn. PHE Dte. (2nd Call) (SL No. 11) | 1573/PD | 30/10/2023 | 270 | JAYANTA KUMAR MONDAL | 1398.36 | 0 | 0 | 42
2098 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-XVI of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-6) | 1577/PD | 30/10/2023 | 884 | PREMNATH MITRA | 498.9 | 0 | 0 | 0
2099 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-IV of Chakra, Kultanr alias Nadiyara,Palkiri,Baroyadi of Purulia-I block under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division ,PHE Dte. | 1527/PD | 16/10/2023 | 867 | M/S SAWDESH ENTERPRISE | 63.56 | 0 | 0 | 60
2100 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 400 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-VII of Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-13) | 1576/PD | 30/10/2023 | 270 | SADHAN GORAIN | 692.19 | 0 | 0 | 25
2101 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Kotloi Mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | 1644/PD | 08/11/2023 | 425 | SUBODH PRAMANIK | 40.95 | 0 | 0 | 0
2102 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir(s) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for different Zones in Joypur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL No.1) | 1594/PD | 31/10/2023 | 725 | PRITI EPC PRIVATE LIMITED | 5517.66 | 0 | 0 | 10
2103 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-VI & VII of Raghunathpur-I Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL No.7) | 1583/PD | 30/10/2023 | 1083 | DEBAKI RANJAN SARKAR | 973.78 | 0 | 0 | 32
2104 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part - E, Mouza - Nimtikuri & Manjuri] | 1539/PD | 16/10/2023 | 747 | MAA TARA CONSTRUCTION | 47.96 | 0 | 0 | 0
2105 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 300 CUM and staging height 20 mtr as per approved drawing ( No: PCI-I/OHR/3/2012)Including soil testing with other allied works for Zone-III of Santuri Block under Purulia Piped Water Supply Scheme(Northern) under Puru;ia Divn. PHE Dte. | 1282/PD | 31/08/2023 | 815 | CHATTERJEE CONSTRUCTION | 81.76 | 0 | 0 | 10
2106 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for Zone-I of Raghunathpur-I Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-13) | 1566/PD | 26/10/2023 | 270 | KOUSHIK CHATTERJEE | 144.2 | 0 | 0 | 0
2107 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe Line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector) at Purulia-I block(Zone-II) for Satar Mouza under Purulia Division. PHE Dte. | 1632/PD | 08/11/2023 | 749 | HIRAK KUMAR SAO | 70.4 | 0 | 0 | 60
2108 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) AT Zone-VIII of Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-12) | 1565/PD | 26/10/2023 | 540 | BBC ENTERPRISE | 535.9 | 0 | 0 | 45
2109 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity of 200 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied work & Operation & Maintenance of Distribution, Pipe line(DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) months for Zone-XIII of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (Sl No. 10) | 1433/PD | 29/09/2023 | 1002 | MADHU SUDAN RAKSHIT | 296.95 | 0 | 0 | 25
2110 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-VIII of Purulia-I block for Dimdiha Mouza under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division, PHE Dte. | 1525/PD | 16/10/2023 | 808 | GOUTAM CHAKRABORTY | 112.33 | 0 | 0 | 0
2111 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector)at Purulia-I Block(Zone-VI) For Gondhudi Mouza under Purulia Division. PHE Dte. | 1639/PD | 08/11/2023 | 785 | M/S CHAKRABORTY CONSTRUCTION | 49.52 | 0 | 0 | 0
2112 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) for Zone-III & IV of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL No.2) | 1582/PD | 30/10/2023 | 1083 | DEBAKI RANJAN SARKAR | 787.54 | 0 | 0 | 10
2113 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-IX of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-4) | 1581/PD | 30/10/2023 | 601 | J.S. CONSTRUCTION | 458.06 | 0 | 0 | 20
2114 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenances of Distributions , Pipe Lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six (36) months for Purulia Piped Water Supply Scheme (Northern Sector) at Puncha Block(Zone - I , II & III) under Purulia Divn. PHE Dte. (SL-1) | 1432/PD | 29/09/2023 | 641 | HANNAN BUILDERS PRIVATE LIMITED | 1240.82 | 0 | 0 | 30
2115 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 200 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-III of Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-7) | 1592/PD | 31/10/2023 | 640 | SWAPAN MANDAL | 295.01 | 0 | 0 | 70
2116 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity of 350 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line(DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) months for Zone-I of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (Sl No. 1) | 1593/PD | 31/10/2023 | 942 | SANTANU BANERJEE | 574.33 | 0 | 0 | 70
2117 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity of 400 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line(DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) months for Zone-II of Raghunathpur-II Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (Sl No. 20) | 1599/PD | 31/10/2023 | 1082 | DEBAKI RANJAN SARKAR | 404.59 | 0 | 0 | 0
2118 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone-VII & VIII of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL No.5) | 1591/PD | 31/10/2023 | 944 | SANTANU BANERJEE | 769.41 | 0 | 0 | 40
2119 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir ( Torch type with solid raft ) of capacity 200 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied works & Operation & Maintenance of Distribution , Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six month (36) for Zone-II of Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-7) | 1557/PD | 18/10/2023 | 541 | RANJIB GHATAK | 277.73 | 0 | 0 | 75
2120 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Continuation work for Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/ TATA indigo eCS Bharat Stage-IV/ Swift tour Bharat stage-IV or as similar model for the official uses under Purulia Sadar Sub-Division, PHE Dte. | 4783/PSD | 24/08/2023 | 184 | BOSE CONSTRUCTION | 0.88 | 0 | 0 | 0
2121 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir(s) including Laying Distribution Pipe Line(s) and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six months (36) at Zone- IX to XV of Purulia-II Block under Purulia Piped Water Supply Scheme ( Northern Sector) under Purulia Divn. PHE Dte.(2nd Call) | 41/PD | 08/01/2024 | 1080 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3673.24 | 0 | 0 | 15
2122 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir(s) including Laying Distribution Pipe Line(s) and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six months (36) at Zone- I,II,III,IV,V,VI,VII,VIII,IX,XII,XIII of Hura Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte.(2nd Call) | 1761/PD | 07/12/2023 | 1082 | S & P ENTERPRISE | 5304.39 | 0 | 0 | 55
2123 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Hiring of Euro-4 Diesel car (BS-IV) on daily rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of 13 nos Blocks under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte (Northen Zone) | 4769/PSD | 21/08/2023 | 184 | ANUP KUMAR SAHA | 0.9 | 0 | 0 | 0
2124 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and Commissioning of RCC Over Head Reservoir(s) including Laying Distribution Pipe Line(s) and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe Line (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six month (36) at Zone- I to XVIII of Para Block under Purulia Piped Water Supply Scheme ( Northern Sector) under Purulia Divn. PHE Dte. | 1821/PD | 12/12/2023 | 720 | M/S ANAND SINGH | 7701.69 | 0 | 0 | 40
2125 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- XIII & XIV of Hura Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 260m) | 67/PD | 10/01/2024 | 357 | S.S CONSTRUCTION | 36.76 | 0 | 0 | 65
2126 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) with allied works for Zone-I of Neturia Block under Purulia Piped Water Supply Scheme (Northern Zone) under Purulia Divn. PHE Dte. | 91/PD | 15/01/2024 | 272 | SIMA ENTERPRISE | 70.28 | 0 | 0 | 85
2127 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) nos tubewellat BPS Site (Mouza- GamarKunri, JL No-167, Plot No-756) of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 380 mtr.) | 85/PD | 15/01/2024 | 807 | CHAIL CONSTRUCTION | 43.63 | 0 | 0 | 0
2128 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat BPS Site (Mouza- Tara, JL No-182, Plot No-1587) of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 400 mtr.) | 84/PD | 15/01/2024 | 60 | NANIGOPAL DEY | 45.63 | 0 | 0 | 10
2129 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-XI) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 2339/PD | 31/12/2024 | 60 | JULI ENTERPRISE | 30.06 | 0 | 0 | 0
2130 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of distribution pipe line and other allied work for Zone-III of Santuri Block under Surface water based water supply scheme for Purulia district (Northern Sector) Under Purulia Division PHE. DTE. Part-B Mouza- Brindabanpur | 2015/PD | 22/11/2024 | 60 | M/S MONDAL ENTERPRISE | 17.47 | 0 | 0 | 0
2131 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-XI) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 2310/PD | 31/12/2024 | 335 | VIVEKANANDA CONSTRUCTION | 33.11 | 0 | 0 | 0
2132 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Northern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte.(Northern Sector) | 130B/PSD | 14/03/2024 | 183 | SHIVA ENTERPRISES | 0.9 | 0 | 0 | 0
2133 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-X) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 2324/PD | 31/12/2024 | 60 | M/S CONTRACTORS SYNDICATE | 34.06 | 0 | 0 | 0
2134 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-VII) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 2323/PD | 31/12/2024 | 60 | SEKH ABBAS | 34.09 | 0 | 0 | 0
2135 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Extension part of Construction of Boundary wall and earth filling in low land by carried earth at Bhuiyadi OHR site (Zone-III) at Kashipur Block under surface water based piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 55 mtr.) | 2342/PD | 31/12/2024 | 60 | M/S SAYAK BHATTACHARYA | 48.64 | 0 | 0 | 0
2136 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of distributuion pipe line and other allied work for Zone-I of Santuri Block under Surface Water Based Water Supply Scheme for Purulia District (Northern Sector) under Purulia Division PHE. DTE. Part-C (Mouza- Pachandapur, Beliapur & Kalikapur ) | 2014/PD | 22/11/2024 | 30 | RANJIB GHATAK | 3.49 | 0 | 0 | 100
2137 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-III) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 2298/PD | 31/12/2024 | 60 | PRATIK SAHA | 34.03 | 0 | 0 | 0
2138 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Continuation work for Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/ TATA indigo eCS Bharat Stage-IV/ Swift tour Bharat stage-IV or as similar model for the official uses under Purulia Sadar Sub-Division, PHE Dte.(01/03/2024 to 31/08/2024) | 101/PSD | 27/02/2024 | 182 | BOSE CONSTRUCTION | 0.88 | 0 | 0 | 0
2139 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Continuation work order for Hiring of Euro-4 Diesel can of Ambassador Bharat stage-IV/TATA Indigo e.c.s Bharat Stage-IV/Swift tour Bharat stage =-IV or as similar model for the Assistant Engineer to look after the ongoing works under RWS Purulia Sub-Division PHE Dte (For12 months ) (w.e.f. 01/09/2022 to 31/08/2023). | 415/A/PR | 30/08/2022 | 365 | ANUP KUMAR SAHA | 1.76 | 0 | 0 | 100
2140 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Continuation of work for Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Southern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte.(Northern Sector) w.e.f. 13/09/2024 to 14/03/2025 | 431/PSD | 11/09/2024 | 183 | MALAY BANDYOPADHYAY | 0.9 | 0 | 0 | 0
2141 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of Balance portion parallal HDPE pipeline and other allied work under Purulia Piped water supply Scheme (Northern Sector ), Kashipur Block Zone -I within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 458/PD | 24/03/2025 | 252 | PRINCE INDUSTRIES ( INDIA) | 70.43 | 0 | 0 | 50
2142 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-XVI) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 2332/PD | 31/12/2024 | 60 | UTTAM KUMAR PARAMANIK | 29.89 | 0 | 0 | 0
2143 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-XVII) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 2333/PD | 31/12/2024 | 60 | SUMIT KUMAR MITRA | 32.38 | 0 | 0 | 0
2144 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-IX)under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 2318/PD | 31/12/2024 | 478 | SAPAN KUMAR PARAMANIK | 34 | 0 | 0 | 0
2145 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Continuation work order for Hiring of Euro-4 Diesel can of Ambassador Bharat stage-IV/TATA Indigo e.c.s Bharat Stage-IV/Swift tour Bharat stage -II/BS-III purchased on or after 01.05.2005 with Diesel/LPG/CNG Engine ( Maxi Cab, non-Air conditioned) for site visit of JJM work of 20 Nos. Blocks within Purulia District under RWS purulia Sub Division under Purulia Division PHE Dte. (Part-A) | 213/A/PR | 27/03/2024 | 180 | BOSE CONSTRUCTION | 0.88 | 0 | 0 | 0
2146 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-XIII) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 2312/PD | 31/12/2024 | 60 | SUBHAS CHANDRA MAHATO | 31.96 | 0 | 0 | 0
2147 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-II,Zone-VI under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 2192/PD | 13/12/2024 | 384 | BISWAJIT MAJI | 22.64 | 0 | 0 | 0
2148 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Continuation work for Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Northern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte. (Northern Sector) (w.e.f 13/09/2024 to 14/03/2025) | 432/PSD | 11/09/2024 | 183 | SHIVA ENTERPRISES | 0.9 | 0 | 0 | 0
2149 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of 13 nos Blocks under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte. (w.e.f. 01/10/2023 to 31/03/2024) | 4857/PSD | 29/09/2023 | 183 | KOUSHIK CHATTERJEE | 0.9 | 0 | 0 | 0
2150 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Continuation work for Hiring of Euro-4 Diesel car (BS-IV) on daily rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of 13 nos Blocks under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte.(w.e.f. 01/03/2024 to 30/08/2024)=184 days | 102/PSD | 27/02/2024 | 184 | ANUP KUMAR SAHA | 0.9 | 0 | 0 | 0
2151 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall & Sinking of T/well at Manbazar-II,Zone-I under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | 1862/PD | 30/09/2024 | 425 | BANERJEE CONSTRUCTION | 14.37 | 0 | 0 | 20
2152 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Hiring of Ambassador Car / Bolero for JJM related works for the Assistant Engineer, Raghunathpur Sub-Division under Purulia Division, PHE Dte. (w.e.f. 01.09.2024 to 31.08.2025) | 1653/PD | 30/08/2024 | 365 | CHANDRA SHEKHAR KUNDU | 1.76 | 0 | 0 | 0
2153 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-IX) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 2301/PD | 31/12/2024 | 60 | S S ENTERPRISE | 34.25 | 0 | 0 | 0
2154 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-XIV) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 2306/PD | 31/12/2024 | 60 | MAHATO CONSTRUCTION | 29.14 | 0 | 0 | 0
2155 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Maguria Mouza under Purulia Piped Water Supply Scheme (Northern Zone) under Purulia Divn. PHE Dte. (Sl No. 20) | 1031/PD | 04/06/2024 | 424 | ANUP KUMAR SAHA | 148.36 | 0 | 0 | 0
2156 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and other allied work for Zone-II of Purulia-I block for Bhul Mouza under Purulia Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (Sl No. 02) | 1028/PD | 04/06/2024 | 269 | SOUMITRA CHAKRABORTY | 113.07 | 0 | 0 | 50
2157 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at PURULIA-I (Zone-VII) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 2313/PD | 31/12/2024 | 213 | TARA MAA SHAKTI CONSTRUCTION | 37.61 | 0 | 0 | 90
2158 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-IV) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 85/PD | 16/01/2025 | 319 | M/S KHAN ENTERPRISE | 31.36 | 0 | 0 | 95
2159 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-II) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 2348/PD | 31/12/2024 | 420 | SANTOSH KUMAR | 29.24 | 0 | 0 | 60
2160 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Southern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte.(Northern Sector) | 130A/PSD | 14/03/2024 | 183 | MALAY BANDYOPADHYAY | 0.9 | 0 | 0 | 0
2161 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-I) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 2334/PD | 31/12/2024 | 366 | BHAGABAN DAS KUMAR | 30.63 | 0 | 0 | 90
2162 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I, II of Hura Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 715/PD | 24/04/2025 | 120 | JULI ENTERPRISE | 33.35 | 0 | 0 | 0
2163 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I, II & III of Para Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 719/PD | 24/04/2025 | 120 | TARA MAA SHAKTI CONSTRUCTION | 50.06 | 0 | 0 | 0
2164 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-XIII) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 2305/PD | 31/12/2024 | 60 | BISWAJIT SINGH | 29.87 | 0 | 0 | 0
2165 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line work for zone-l of Neturia Block at Mouza - Pochhara under Purulia water supply scheme (Northern Sector ) under Purulia Division Phe. Dte | 439/PD | 24/03/2025 | 373 | BISWAJIT MAJI | 16 | 0 | 0 | 65
2166 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-VI, VII & VIII of Purulia-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 712/PD | 24/04/2025 | 120 | AMITAVA KUNDU | 49.74 | 0 | 0 | 0
2167 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-V) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 2338/PD | 31/12/2024 | 420 | PAMPA DAS AND COMPANY | 30.46 | 0 | 0 | 0
2168 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Chlorine room of size 4.00 mtr X 4.00 mtr X 3.50 mtr (Ht) at Head works site of Baram under Purulia W/S Scheme under Purulia Sadar Sub-Division Under Purulia Division , PHE Dte. | 110/PD | 21/01/2025 | 90 | AKUL SUTRADHAR | 3.86 | 0 | 0 | 0
2169 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-XI, & XIII of Kashipur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 686/PD | 24/04/2025 | 360 | MADHU SUDAN RAKSHIT | 33.04 | 0 | 0 | 0
2170 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-IV & V of JoypurBlock Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte | 680/PD | 24/04/2025 | 120 | M D CONSTRUCTION | 33.33 | 0 | 0 | 0
2171 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-VIII, IX & X of Kashipur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 693/PD | 24/04/2025 | 120 | SANTANU BANERJEE | 49.72 | 0 | 0 | 0
2172 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-IV & V of Puncha Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 697/PD | 24/04/2025 | 120 | M/S CONTRACTORS SYNDICATE | 33.19 | 0 | 0 | 0
2173 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone- X of Hura Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 718/PD | 24/04/2025 | 120 | BISHAL ENTERPRISE | 16.68 | 0 | 0 | 0
2174 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Continuation work for Hiring of Euro-4 Diesel car (BS-IV) on daily rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Northern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte. (Northern Sector) (w.e.f 15/03/2025 to 13/09/2025) | 131A/PSSD | 13/03/2025 | 183 | SHIVA ENTERPRISES | 0.9 | 0 | 0 | 0
2175 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Continuation work for Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/ TATA indigo eCS Bharat Stage-IV/Swift tour Bharat stage-IV or as similar model for the official uses under Purulia Sadar Sub-Division, PHE Dte(w.e.f.01.09.2024 to 28.02.2025). | 397A/PSD | 29/08/2024 | 183 | BOSE CONSTRUCTION | 0.88 | 0 | 0 | 100
2176 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-I (Zone-V) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 2322/PD | 31/12/2024 | 60 | AMIT CHOURASIA | 31.62 | 0 | 0 | 0
2177 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone- XVI of Jhalda-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 694/PD | 24/04/2025 | 120 | PROBODH CHANDRA MAJHI | 16.69 | 0 | 0 | 0
2178 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Supplying fitting and fixing M.S. gate of Jail type and 600 mm (+/- 30 mm) diametre R.B.T (Reinforced Barbed Tape) Concertina fencing work of Zone - IV of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 340/RNP | 20/06/2025 | 7 | CHINMOY SEN | 0.86 | 0 | 0 | 98
2179 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Continuation of work for Hiring of Euro-4 Diesel car (BS-IV) on daly rate basis having contract carriage permit for plying within West Bengal from Regional Transport Authority for the site visit of JJM work of Southern Sector of Purulia Water Supply Scheme under Office of the Assistant Engineer, Purulia Sadar Sub-Division, PHE Dte. (Northern Sector) w.e.f. 15/03/2025 to 13/09/2025 | 131/PSSD | 13/03/2025 | 183 | MALAY BANDYOPADHYAY | 0.9 | 0 | 0 | 0
2180 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-VI of Kashipur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 691/PD | 24/04/2025 | 342 | PRINCE INDUSTRIES ( INDIA) | 16.7 | 0 | 0 | 0
2181 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-XV & XVI of Para Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 695/PD | 24/04/2025 | 120 | BISHAL ENTERPRISE | 33.38 | 0 | 0 | 0
2182 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of DI pipe along with interconnection arrangement at OHR site & Construction of Boundary wall & pathway & Sinking of Tubewell at Jhalda-II (Zone-XII) under Purulia W/S Scheme (Northern sector) of Purulia Division, PHE Dte. | 2340/PD | 31/12/2024 | 60 | DEBANJAN SEAL | 29.19 | 0 | 0 | 0
2183 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector)at Purulia-I Block (Zone-II) For Tentlo Mouza under Purulia Division. PHE Dte. | 2011/PD | 21/11/2024 | 252 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 64.02 | 0 | 0 | 0
2184 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Jack pushing between Sanka & Rukni Rly. Station in Adra-BJE Section for The surface based piped water supply scheme For the District Purulia (Northern Sector) under Raghunathpur Sub Division under Purulia Division, PHE Dte. | 570/PD | 07/04/2025 | 359 | RABIN CHANDRA CHAIL | 38.68 | 0 | 0 | 0
2185 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Continuation work for Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/ TATA indigo eCS Bharat Stage-IV/Swift tour Bharat stage-IV or as similar model for the official uses under Purulia Sadar Sub-Division, PHE Dte (w.e.f.01.03.2025 to 31.08.2025) | 96/PSD | 27/02/2025 | 181 | BOSE CONSTRUCTION | 0.88 | 0 | 0 | 0
2186 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-VII & VIII of Hura Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte | 690/PD | 24/04/2025 | 120 | SATYA NARAYAN BELTHARIA | 33.04 | 0 | 0 | 0
2187 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-IV & V of Purulia-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte | 684/PD | 24/04/2025 | 120 | GANGULY ENTERPRISES | 33.21 | 0 | 0 | 0
2188 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-VIII & IX of Jhalda-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 685/PD | 24/04/2025 | 120 | SEKH ABBAS | 33.39 | 0 | 0 | 0
2189 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-XII & XIII of Purulia-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte | 687/PD | 24/04/2025 | 240 | BASANTA PARAMANIK | 33.34 | 0 | 0 | 0
2190 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall & Sinking of T/well at Purulia-II,Zone-IV under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 337/PD | 11/03/2025 | 60 | SAZID HOSSEN ANSARI | 24.7 | 0 | 0 | 0
2191 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-VII & VIII of Puncha Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 699/PD | 24/04/2025 | 120 | SANJAY KUMAR NARSARIA | 33.38 | 0 | 0 | 0
2192 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-VI, VII of Joypur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 707/PD | 24/04/2025 | 120 | SANTOSH KUMAR | 33.33 | 0 | 0 | 0
2193 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-VIII of Purulia-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 708/PD | 24/04/2025 | 120 | SUDHANSHU OJHA | 16.6 | 0 | 0 | 0
2194 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone- IV of Kashipur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 701/PD | 24/04/2025 | 120 | CHINMOY SEN | 16.58 | 0 | 0 | 0
2195 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-XIV & XV of Kashipur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 702/PD | 24/04/2025 | 120 | CHANDAN CHATTERJEE | 33.16 | 0 | 0 | 0
2196 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall & Sinking of T/well at Purulia-II,Zone-VIII under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 336/PD | 10/03/2025 | 60 | SAZID HOSSEN ANSARI | 24.78 | 0 | 0 | 0
2197 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I & III of Joypur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 677/PD | 24/04/2025 | 120 | SAMAN KUMAR MAHATO | 33.33 | 0 | 0 | 0
2198 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I of Jhalda-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte | 679/PD | 24/04/2025 | 120 | BHAGABAN DAS KUMAR | 16.55 | 0 | 0 | 0
2199 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-IX & X of JoypurBlock Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte | 681/PD | 24/04/2025 | 120 | SAMAN KUMAR MAHATO | 33.33 | 0 | 0 | 0
2200 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-V of Santuri Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 700/PD | 24/04/2025 | 120 | MAA TARA CONSTRUCTION | 16.7 | 0 | 0 | 0
2201 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I, II & III of Purulia-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 709/PD | 24/04/2025 | 120 | SINGHA ENTERPRISE | 50.03 | 0 | 0 | 0
2202 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone- XI of Purulia-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 713/PD | 24/04/2025 | 120 | CHANCHAL MISHRA | 16.66 | 0 | 0 | 0
2203 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Left out HDPE pipe line and pushing of 600mm dia MS pre cast pipe and 100 mm dia GI water carrier pipe by hydraulic jacking method across Purulia Ranchi NH Road for laying distribution line in connection with Jal Jeevan Mission at for Zone-III of Purulia -I block for Belkuri mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division, PHE Dte. | 444/PD | 24/03/2025 | 283 | GOUTAM CHAKRABORTY | 64.98 | 0 | 0 | 75
2204 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I, of Purulia-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 710/PD | 24/04/2025 | 120 | DEBSHANKAR LAYEK | 16.62 | 0 | 0 | 0
2205 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-II, III & IV of Raghunathpur-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 724/PD | 24/04/2025 | 120 | KRISHNA CONSTRUCTION AND ORDER SUPPLIER | 50.1 | 0 | 0 | 0
2206 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Allied work of laying Distribution pipe line and other allied works for Zone-III of Santuri Block Purulia pipe Water Supply Scheme (Northern Sector ) under Purulia Division PHE Dte Part-C ( Mouza- Brindabanpur, Vill.- Asharikand ) | 1117/PD | 23/06/2025 | 45 | M/S MONDAL ENTERPRISE | 55.57 | 0 | 0 | 0
2207 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Kashipur (Zone - VII & XII) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1082/PD | 17/06/2025 | 360 | MADHU SUDAN RAKSHIT | 28.7 | 0 | 0 | 0
2208 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Neturia (Zone - I) Of Purulia Pipe Water Supply Scheme (Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1067/PD | 17/06/2025 | 120 | SAANVI CONSTRUCTION | 14.4 | 0 | 0 | 0
2209 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-VII of Raghunathpur-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 714/PD | 24/04/2025 | 120 | CHANCHAL MISHRA | 16.65 | 0 | 0 | 0
2210 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Para (Zone - X&XI) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1077/PD | 17/06/2025 | 120 | AMRIT CONSTRUCTION | 28.63 | 0 | 0 | 0
2211 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Jhalda-II (Zone - II, III & VI) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1083/PD | 17/06/2025 | 120 | MAHATO CONSTRUCTION | 43.05 | 0 | 0 | 0
2212 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-IV, V & VI of Hura Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 716/PD | 24/04/2025 | 120 | TOTAL INFRA | 50.08 | 0 | 0 | 0
2213 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-XII, XIII & XIV of Para Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 721/PD | 24/04/2025 | 362 | M/S S & P CONSTRUCTION | 50.09 | 0 | 0 | 0
2214 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-IV, V & VI of Raghunathpur-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte | 723/PD | 24/04/2025 | 342 | PRINCE INDUSTRIES ( INDIA) | 50.11 | 0 | 0 | 0
2215 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Laying of Left-out Distribution HDPE Pipe line and other allied work for Zone - III of Raghunathpur - I Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHEDte. | 1055/PD | 17/06/2025 | 288 | KM ENTERPRISES | 48.34 | 0 | 0 | 100
2216 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-XI of Joypur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 706/PD | 24/04/2025 | 120 | B.M ENTERPRISE | 16.66 | 0 | 0 | 0
2217 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Additional work of Laying Distribution Pipe line at Zone-III of Purulia-II Block under Purulia Piped Water Supply Scheme (Northen Sector) under Purulia Division, PHE Dte. | 1058/PD | 17/06/2025 | 198 | SWAPAN MANDAL | 23.25 | 0 | 0 | 80
2218 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-V & VI of Jhalda-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte | 678/PD | 24/04/2025 | 120 | AIM CONSTRUCTION | 33.38 | 0 | 0 | 0
2219 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Purulia-II (Zone - II & III) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1072/PD | 17/06/2025 | 120 | SUBHAS CHANDRA MAHATO | 28.7 | 0 | 0 | 0
2220 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Hura (Zone - III & IX) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1073/PD | 17/06/2025 | 120 | MOHOR CONSTRUCTION | 28.69 | 0 | 0 | 0
2221 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Hura (Zone - XIII & XIV) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1075/PD | 17/06/2025 | 120 | MS D.PALIT AND CO. | 28.8 | 0 | 0 | 0
2222 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Pushing of 600mm dia RCC pre cast pipe and 200 mm dia MS water carrier pipe by hydraulic jacking method across Pirargaria Road for laying Distribution Main for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) and Installation of 2(two) nos of Tubewell through DTH process at OHR site of Zone-III of Purulia-II Block Purulia piped W/S Scheme( Northern Sector) under Purulia Division, PHE Dte. | 929/PD | 27/05/2025 | 219 | SOUVIK MANDAL | 13.1 | 0 | 0 | 60
2223 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Raghunathpur-I (Zone - I & III) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 999/PD | 11/06/2025 | 120 | DILIP MISHRA | 28.4 | 0 | 0 | 0
2224 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Santuri (Zone - I, VI & VII) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1084/PD | 17/06/2025 | 120 | CHATTERJEE CONSTRUCTION | 43.27 | 0 | 0 | 0
2225 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall at OHR(200 cum)site of ZONE III at Dhunari Mouza of Purulia 2 Block under Purulia piped water supply scheme( Northern Sector) under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | 1056/PD | 17/06/2025 | 372 | BISWAJIT MAJI | 16.97 | 0 | 0 | 0
2226 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Jhalda-I (Zone - IV & VII) Of Purulia Pipe Water Supply Scheme (Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1069/PD | 17/06/2025 | 120 | MANTAJ ANSARI | 28.8 | 0 | 0 | 0
2227 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Para (Zone - V & VI) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1076/PD | 17/06/2025 | 120 | M/S CONTRACTORS SYNDICATE | 28.66 | 0 | 0 | 0
2228 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-XII, XIII & XIV of Jhalda-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 689/PD | 24/04/2025 | 120 | SUMANTA GHOSH | 49.86 | 0 | 0 | 0
2229 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-V & VII of Jhalda-II Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 698/PD | 24/04/2025 | 120 | SUMANTA GHOSH | 33.24 | 0 | 0 | 0
2230 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Joypur (Zone - II & VIII) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1071/PD | 17/06/2025 | 120 | SAZID HOSSEN ANSARI | 28.82 | 0 | 0 | 0
2231 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-XVI of Kashipur Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 717/PD | 24/04/2025 | 120 | JOGMAYA CONSTRUCTION | 16.54 | 0 | 0 | 0
2232 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Continuation Order for the Work of Jack pushing between Sanka &Rukni Rly. Station in Adra-BJE Section for The surface based piped water supply scheme For the District Purulia (Northern Sector) under Raghunathpur Sub Division under Purulia Division, PHE Dte. | 1208/PD | 08/07/2025 | 327 | RABIN CHANDRA CHAIL | 38.68 | 0 | 0 | 0
2233 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Purulia-I (Zone - VI & VII) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1384/PD | 29/07/2025 | 120 | ZAKIR HOSSIN MONDAL | 28.83 | 0 | 0 | 0
2234 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Jhalda-I (Zone - X & XI) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1388/PD | 29/07/2025 | 120 | SEKH IRFAN | 28.69 | 0 | 0 | 0
2235 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-IX of Para Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1523/PD | 19/08/2025 | 120 | AMIT PATHAK | 16.61 | 0 | 0 | 0
2236 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I, II & III of JoypurBlock Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1524/PD | 19/08/2025 | 120 | MAHATO CONSTRUCTION | 49.86 | 0 | 0 | 0
2237 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-II of Raghunathpur-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1525/PD | 19/08/2025 | 120 | DILIP MISHRA | 16.33 | 0 | 0 | 0
2238 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I, & III of Manbazar-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1526/PD | 19/08/2025 | 120 | SAZID HOSSEN ANSARI | 33.38 | 0 | 0 | 0
2239 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I, III of Puncha Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. (Group-B) | 1527/PD | 19/08/2025 | 120 | BABA LOKNATH ENTERPRISE | 32.99 | 0 | 0 | 0
2240 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Manbazar-I (Zone - II & IV) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1078/PD | 17/06/2025 | 120 | M/S MECHANICAL AND CIVIL | 28.8 | 0 | 0 | 0
2241 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Jhalda-I (Zone - XV & XVII) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1580/PD | 20/08/2025 | 120 | MAHATO CONSTRUCTION | 28.7 | 0 | 0 | 0
2242 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Zone-I, II & III of Jhalda-I Block Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1522/PD | 19/08/2025 | 120 | PRATIMA CONSTRUCTION | 50.06 | 0 | 0 | 0
2243 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Jhalda-II (Zone - VIII & XIV ) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1070/PD | 17/06/2025 | 120 | BIJOY KUMAR PATRA | 28.81 | 0 | 0 | 0
2244 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Puncha (Zone - II) Of Purulia Pipe Water Supply Scheme (Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1068/PD | 17/06/2025 | 120 | M/S SAMARESH SARKAR | 13.81 | 0 | 0 | 0
2245 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Purulia-II (Zone - IX & X) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1390/PD | 29/07/2025 | 120 | PRASENJIT CHOUDHURY | 28.56 | 0 | 0 | 0
2246 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Scada Room and Chlorine Room at Purulia-I (Zone - IV & V) Of Purulia Pipe Water Supply Scheme(Northern Sector) within Purulia District under Purulia Division, PHE Dte. | 1389/PD | 29/07/2025 | 120 | DALIM ENTERPRISE | 28.27 | 0 | 0 | 0
2247 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Repairing and Renovation of Boundary wall including other allied works at Kanchanpur boosting site in connection with Jal Jeevan Mission (JJM) at Kudagara under Purulia W/S Scheme (Northern Sector) of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 1332/PD | 08/09/2023 | 30 | MITRA CONSTRUCTION | 2.56 | 0 | 0 | 100
2248 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- IX & X of Hura Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 300m) | 65/PD | 10/01/2024 | 360 | WATER TECH | 40.82 | 0 | 0 | 100
2249 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone- IX & X of Para Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total Length of Boundary Wall: 290 m) | 71/PD | 10/01/2024 | 444 | SUJIT CHAKRABORTY | 39.58 | 0 | 0 | 100
2250 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-III) , SM/18654 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 2(Two) nos tubewellat OHR Sites of Zone - III & IV of Hura Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total Length of Boundary Wall: 260 m) | 193/PD | 02/02/2024 | 420 | JULI ENTERPRISE | 36.69 | 0 | 0 | 100
2251 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10223 | School | Water supply tap connection arrangement for 38 nos. school upto 200 students within Purulia-II block (Part-B) of Purulia District under Purulia Division, PHE Dte. (Tender No- 33/2021-22 of SE/PMU/WBPWSP(P) ) | BP-2022-23-113 | 16/07/2022 | 0 | ANUP KUMAR SAHA | 65.04 | 0 | 0 | 0
2252 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10223 | School | Water supply tap connection arrangement for 38 nos. school upto 200 students within Manbazar-II block (Part-B) of Purulia District under Purulia Division, PHE Dte. (Tender No- 15/2022-23 of SE/PMU/WBPWSP(P) ) | BP-2022-23-114 | 16/07/2022 | 0 | KOUSHIK CHATTERJEE | 66.37 | 0 | 0 | 0
2253 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10223 | School | Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/TATA Indigo e.c.s Bharat Stage-IV/Swift tour Bharat stage =-IV or as similar model for Surveying the work of AWC in 10 Nos. Blocks within Purulia District under RWS Purulia Sub Division under Purulia Division PHE Dte | 258-B/PR | 03/05/2023 | 20 | ANUP KUMAR SAHA | 0.29 | 0 | 0 | 0
2254 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10223 | School | Water supply Tap Connection Arrangement for 47 nos School upto 200 Students, 5 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Manbazar-II Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | 578/PD | 12/04/2022 | 45 | PREMNATH MITRA | 228 | 0 | 0 | 100
2255 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10223 | School | Water supply Tap Connection Arrangement for 9 nos AWC within Bagmundi Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | 497/PD | 29/03/2022 | 45 | SUNRISE ENGINEERING CORPORATION | 71.04 | 0 | 0 | 100
2256 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10223 | School | Water supply Tap Connection Arrangement for 38 nos School upto 200 Students, within Manbazar-II Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | 673/PD | 25/04/2022 | 45 | KOUSHIK CHATTERJEE | 159.88 | 0 | 0 | 100
2257 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10223 | School | Water supply Tap Connection Arrangement for 46 nos School upto 200 Students, 5 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Purulia-II Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | 402/PD | 11/03/2022 | 45 | EQUIPMENTS AND SPARES AGENCIES | 223.56 | 0 | 0 | 100
2258 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10223 | School | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewells sinked at various Schools & AWCs of . Bundwan & Manbazar-II Blocks under Purulia Division ,PHE,Dte. | 1736/PD | 04/12/2023 | 30 | PRAKASH DESHMUKH | 9.8 | 0 | 0 | 100
2259 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10223 | School | Xerox bill paid for Division office | BP-2024-25-29 | 26/04/2024 | 0 | DUTTA XEROX CENTRE | 1.07 | 0 | 0 | 0
2260 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10223 | School | Car bill for office purpose against vehicle reg. no.WB55-B6555 period form July,22 to Jan,23. | BP-2024-25-30 | 26/04/2024 | 0 | ANUP KUMAR SAHA | 2.77 | 0 | 0 | 0
2261 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 183 nos. under Manbazar II & Purulia-II Block In Purulia District under Purulia Division, PHE.Dte. , SM/10223 | School | Car bill for office purpose against vehicle reg. no.WB55-B6555 period form July,22 to Jan,23. | BP-2024-25-28 | 26/04/2024 | 0 | BOSE CONSTRUCTION | 1.73 | 0 | 0 | 0
2262 | PURULIA | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. , SM/06826 | Augmentation | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari W/s Scheme under Jal Swapna Programme. (Tender No. 14/SE/PMU of 2020-21) | 448/8443187 | 30/03/2021 | 0 | SWAPAN MANDAL | 26.54 | 0 | 0 | 0
2263 | PURULIA | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. , SM/06826 | Augmentation | Re-Sinking of No-1 Tube-well 200mm 200mm dia river bed tube-well at riverbed of Kansai at Pindra site of Bongabari W/s Scheme. (Tender No. 868/EE/PD of 2019-20) | 95/8443116 | 19/07/2021 | 0 | SANTANU BANERJEE | 0.45 | 0 | 0 | 0
2264 | PURULIA | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. , SM/06826 | Augmentation | Laying of HDPE pipe & distribution main (loop line) from Surulia Roads side Hari Mandir to Surulia Shiv Mandir in Surulia village for deinking water supply through FHTC to metup the water crisis at upar Surulia village from existing Bongabari W/s Scheme under Jaal Swapna Programme. (Tender No.1031/EE/PD of 2021-22) | 368/8443191 | 31/03/2022 | 0 | SOUVIK MANDAL | 4.29 | 0 | 0 | 0
2265 | PURULIA | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. , SM/06826 | Augmentation | Arrangement of drinking water supply through FHTC to meet up the acute crisis by extending distribution like to Surulia village from existing Bongabari W/s Scheme under Jalswapna Programe. (Tender No.567/EE/PD of 2021-22) | 264/8443156/1 | 20/12/2021 | 0 | SWAPAN MANDAL | 4.27 | 0 | 0 | 0
2266 | PURULIA | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. , SM/06826 | Augmentation | Arrangement of drinking water supply through FHTC to meet up the acute crisis by extending distribution like to Surulia village from existing Bongabari W/s Scheme under Jalswapna Programe. (Tender No.14/EE/PD of 2020-21) | 264/8443156/2 | 20/12/2021 | 0 | SWAPAN MANDAL | 13.72 | 0 | 0 | 0
2267 | PURULIA | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. , SM/06826 | Augmentation | Construction of Guard Room & boundarry wall near Guest House Campus and with drawing and relaying of CI pipes under Purulia Division, PHE Dte. | 184/PD | 07/02/2023 | 100 | MANATOSH SINGH | 4.19 | 0 | 0 | 0
2268 | PURULIA | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. , SM/06826 | Augmentation | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari W/S Scheme under Jalswapna Programme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1412/PD | 29/12/2020 | 45 | SWAPAN MANDAL | 68.85 | 6.6 | 94.34 | 100
2269 | PURULIA | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. , SM/06826 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Uppar Pindra Village of Pindra G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 648/PD | 22/04/2022 | 45 | KABERI DUTTA | 9.84 | 0 | 0 | 100
2270 | PURULIA | Purulia Division | Arrangement for drinking water supply through FHTC to meet up the acute crisis by extending distribution line to Surulia Village from existing Bongabari WSS under Jalswapna Programme. , SM/06826 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Surulia Village Bauri Para of Raghabpur G.P. under command area of Bongabari Water Supply Scheme at Purulia-II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1390/PD | 01/09/2022 | 45 | SOUVIK MANDAL | 23.21 | 0 | 0 | 100
2271 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-C) (Tender No. 339/EE/PD of 2020-21) | BP-2021-22-42 | 19/07/2021 | 0 | ANUDIP SAHA | 2.62 | 0 | 0 | 0
2272 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-D) (Tender No. 264/EE/PD of 2020-21) |  | 12/04/2021 | 0 | M/S S & P CONSTRUCTION | 2.66 | 0 | 0 | 0
2273 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SWAPNA) at Patuara, Hinduhir & Dharmerbera (Bhamarbera) village of Chatu Hansa G.P. under command area of Satra W/S Scheme at Arsha Block under Purulia Sadar Sub- Division, PHE Dte. (Tender No:- 263/EE/PD of 2020-21) |  | 09/08/2021 | 0 | SUBODH PRAMANIK | 31.87 | 0 | 0 | 0
2274 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SAPNA) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(Part-A) (Tender No.287/EE/PD of 2020-21) | BP-2021-22-83 | 16/08/2021 | 0 | GYANRANJAN SEN | 3.01 | 0 | 0 | 0
2275 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SWAPNA) at Satra village of Hensia G.P. under command area of Satra W/S Scheme at Arsha Block (Part- H) (Tender No:- 21/EE/PD of 2021-22) | BP-2021-22-53 | 20/07/2021 | 0 | PRATIK SAHA | 2.8 | 0 | 0 | 0
2276 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-J) (Tender No.269/EE/PD of 2020-21) | BP-2021-22-135 | 11/10/2021 | 0 | M/S ACHARJEE CONSTRUCTION | 3.43 | 0 | 0 | 0
2277 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Prviding Functional HouseholdTapConnection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-B) (Tender No. 338/EE/PD of 2020-21) | BP-2021-22-117 | 11/10/2021 | 0 | SIDDHARTHA SANKAR SARKAR | 3.85 | 0 | 0 | 0
2278 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-E) (Tender No. 417/EE/PD of 2020-21) | BP-2021-22-41 | 19/07/2021 | 0 | INDRAJIT SARKAR | 2.91 | 0 | 0 | 0
2279 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SAPNA) at Harnama & Nimdiha village of Beldih G.P under command area of Satra W/s Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.304/EE/PD of 2020-21) | BP-2021-22-91 | 23/08/2021 | 0 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 9.31 | 0 | 0 | 0
2280 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Prviding Functional HouseholdTapConnection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-G) (Tender No. 284/EE/PD of 2020-21) | BP-2021-22-122 | 11/10/2021 | 0 | TUSHAR KANTI GORAI | 3.69 | 0 | 0 | 0
2281 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-K) (Tender No.352/EE/PD of 2020-21) | BP-2021-22-119 | 11/10/2021 | 0 | SIDDHARTHA SANKAR SARKAR | 3.16 | 0 | 0 | 0
2282 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SAPNA) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(Part-I) (Tender No.350/EE/PD of 2020-21) | BP-2021-22-97 | 23/08/2021 | 0 | S.K IRFAN | 2.94 | 0 | 0 | 0
2283 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SWAPNA) at Misirdih village of Chatu Hansa G.P. under command area of Satra W/S Scheme at Arsha Block (Tender No:- 328/EE/PD of 2020-21) | BP-2021-22-52 | 20/07/2021 | 0 | BHAGABANDAS KUMAR | 10.04 | 0 | 0 | 0
2284 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & JAL SAPNA) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(Part-F) (Tender No.317/EE/PD of 2020-21) | BP-2021-22-81 | 23/08/2021 | 0 | RAKSHIT ENTERPRISE | 2.57 | 0 | 0 | 0
2285 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Prviding Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL Sapna) at Satra village of Hensla G.P under command area of Satra W/s Scheme at Arsha Block. (Part-D) (Tender No. 264/EE/PD of 2020-21) | BP-2021-22-44 | 19/07/2021 | 0 | M/S. S.P CONSTRUCTION | 2.66 | 0 | 0 | 0
2286 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Laying op UPVC pipe as distribution main (Loop Line) from Satra Junior High School to Satra uppar para for drinking water supply through FHTC meet up the water crisis at Satra W/s Scheme. (Tender No.864/EE/PD of 2021-2022) | BP-2021-22-239 | 16/02/2022 | 0 | SUBODH PRAMANIK | 7.31 | 0 | 0 | 0
2287 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-C) (Tender No.339/EE/PD of 2020-21) | BP-2021-22-245 | 16/02/2022 | 0 | ANUDIP SAHA | 0.92 | 0 | 0 | 0
2288 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-H) (Tender No.21/EE/PD of 2021-22) | BP-2021-22-256 | 25/02/2022 | 0 | PRATIK SAHA | 1.66 | 0 | 0 | 0
2289 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | New Sinking of 2 (Two) Nos 200 mm dia river bed vertical tubewell (T/W No.- 1 & 2 ) alongwith necessary 100 mm dia GI collecting line in connection with FHTC from River bed Tubewell to common manifold chamber at river bank (Kansai River) at Satra under Satra W/S Scheme under Purulia Sadar Sub Division of Purulia Division, PHE Dte. (Tender No.863/EE/PD of 2021-22) | BP-2021-22-235 | 03/02/2022 | 0 | SUBODH PRAMANIK | 9.7 | 0 | 0 | 0
2290 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Harnama and Nimdih village of Beldih G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.304/EE/PD of 2020-21) | BP-2021-22-262 | 28/02/2022 | 0 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 0.23 | 0 | 0 | 0
2291 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Patuara, Hinduhir & Dharmerbera (Bhamarbera) village of Chatu Hansa G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.263/EE/PD of 2020-21) | BP-2021-22-259 | 28/02/2022 | 0 | SUBODH PRAMANIK | 7.97 | 0 | 0 | 0
2292 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Misirdih village of Chatu Hansa G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Tender No.328/EE/PD of 2020-21) | BP-2021-22-255 | 28/02/2022 | 0 | BHAGABANDAS KUMAR | 4.89 | 0 | 0 | 0
2293 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-D) (Tender No.264/EE/PD of 2020-21) | BP-2021-22-254 | 25/02/2022 | 0 | M/S. S.P CONSTRUCTION | 0.96 | 0 | 0 | 0
2294 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Laying of UPVC pipe as distribution main (loop line) from Misirdih More near Canel to Jhunjka village including PWD Road Crossing (Tamna-Arsha Road) by Jack pushing for drinking water supply through FHTC to meet up the water crisis at Jhunjka Village of Satra W/s Scheme under JJM. (Tender No.871/EE/PD of 2021-22) | BP-2021-22-293 | 09/03/2022 | 0 | ANGEL LABOUR CONTRACT & CONSTRUCTION CO OPERATIVE SOCIETY LTD | 18.23 | 0 | 0 | 0
2295 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-E) (Tender No.417/EE/PD of 2020-21) | BP-2021-22-242 | 16/02/2022 | 0 | INDRAJIT SARKAR | 1.05 | 0 | 0 | 0
2296 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-I). (Tender No.350/EE/PD of 2020-21) | BP-2021-22-260 | 28/02/2022 | 0 | S.K IRFAN | 0.64 | 0 | 0 | 0
2297 | PURULIA | Purulia Division | Retrofitting of Satra Water Supply Scheme at Arsha Block of Purulia Sadar Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07567 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at Satra village of Hensla G.P. under command area of Satra Water Supply Scheme at Arsha Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Part-J) | 21/PSD | 13/01/2021 | 45 | M/S ACHARJEE CONSTRUCTION | 4.5 | 0 | 0 | 100
2298 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Balitora , Habitation - Balitora (112 Nos.) | 23/RNP | 11/01/2021 | 15 | TUMPA GORAIN | 4.78 | 0 | 0 | 100
2299 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | New Sinking of 2 (Two) Nos 200 mm dia river bed vertical tubewell (T/W No.- 5 & 6) alongwith necessary 100 mm dia GI collecting line in connection with FHTC from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Balitora under Balitora W/S Scheme under Raghunathpur Sub Division, under Purulia Division PHE Dte. PHE Dte. (Tender No.404/EE/PD of 2020-21) | BP-2021-22-252 | 25/02/2022 | 0 | ASHOK KUMAR CHATTERJEE | 19.66 | 0 | 0 | 0
2300 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Balitora , Habitation - Balitora (112 Nos.) (Tender No- 804/EE/PD of 2021-22) | BP-2021-22-338 | 25/03/2022 | 0 | TUMPA GORAIN | 2.14 | 0 | 0 | 0
2301 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Additional work for Functional Household Tap Connection FHTC including other allied works of Balitora Water supply Scheme at Santuri Block part- II [Tender No- 907/2021-22 of EE/PD) | BP-2021-22-276 | 03/03/2022 | 0 | RAHIBUDDIN MONDAL | 0.93 | 0 | 0 | 0
2302 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Supplying & laying different dia HDPE pipe line of distribution linewith allied works from Mokra village more to Jadudi village under (zone-II) of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Tender No.995/EE/PD of 2021-22) | BP-2022-23-295 | 23/09/2022 | 0 | SANDIP KUMAR DUBEY | 1.79 | 0 | 0 | 0
2303 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Shifting of under ground HDPE & DI pipe line including supplying & laying HDPE & DI pipe of distribution line with allied works from Manpur Pry. School to Ektira Village end under Zone-III of Balitora W/S Scheme of Raghunathpur Sub-Division, PHE Dte. (Tender No. 923/EE/PD of 2021-22) | BP-2022-23-111 | 16/07/2022 | 0 | BASANTA KUMAR SINGHADEO | 7.33 | 0 | 0 | 0
2304 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Balitora Water Supply Scheme of Santuri Block of Raghunathpur Sub- Division under Purulia Division, PHE Dte. at mouza- Balitora, Habitation- Balitora (108) nos. (Tender No- 288/20-21 of EE/PD) | BP-2022-23-152 | 26/07/2022 | 0 | NANIGOPAL DEY | 0.36 | 0 | 0 | 0
2305 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Potable estimate for Shifting of under ground HDPE & DI pipe line including supplying & laying HDPE & DI pipe of distribution line with allied works from Kapasdanga village end to Mokra Pry. School through Jagannathdih & Saluni village under Zone-II of Balitora W/S Scheme of Raghunathpur Sub-Division, PHE Dte. (Tender No. 937/EE/PD of 2021-22) | BP-2022-23-153 | 26/07/2022 | 0 | KHITISH CHANDRA PATHAK | 5.49 | 0 | 0 | 0
2306 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | FHTC including other allied works of Baltora W/S Scheme at Santuri block (Tender No- 262/2020-21 of EE/PD) | BP-2022-23-47 | 17/05/2022 | 0 | MADHU SUDAN RAKSHIT | 4.62 | 0 | 0 | 0
2307 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Supplying & laying different dia HDPE pipe line of distribution linewith allied works from Dandahit Bauro para to Danesdih village & end of Batka village to Syaldanga village &Kastagora village (zone-II1) site under (zone-III) of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (T/N-948/21-22) |  | 05/07/2022 | 0 | M/S. S.P CONSTRUCTION | 10.16 | 0 | 0 | 0
2308 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Additional works for Functional Household Tap Connection (FHTC) including other allied works of Balitora W/s Scheme at Santuri Block Raghunathpur Sub_Division under Purulia Division PHE Dte. Mouza- Dandahit, Hab-Dandahit (112 Nos) (Tender No.823/EE/PD of 2021-22) | BP-2021-22-317 | 22/03/2022 | 0 | SIKHA ENTERPRISES | 2.01 | 0 | 0 | 0
2309 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Additional work for Functional House Hold Connection (FHTC) in connection with other allied works of Baltora W/s Scheme at Santuri Block (Mouza- Sunuri, Habitation-Sunuri) [Part-I] (Tender No.908/EE/PD of 2021-22) | BP-2021-22-263 | 28/02/2022 | 0 | RAHIBUDDIN MONDAL | 3.75 | 0 | 0 | 0
2310 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Supplying and laying different dia HDPE pipe line of Distribution line with allied works from Makra village more to Jadudih village under (Zone-II) Balitora W/s Scheme. (Tender No.995/EE/PD of 2021-22) | BP-2021-22-384 | 28/03/2022 | 0 | SANDIP KUMAR DUBEY | 5.73 | 0 | 0 | 0
2311 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block at Mouza- Dandahit Habitation-Batka, Dandahit (Tender No- 855/2021-22 of EE/PD) | BP-2021-22-327 | 22/03/2022 | 0 | ROY CONSTRUCTION | 0.54 | 0 | 0 | 0
2312 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Deuli, Hab-Deuli, Mouza-Suburi, Hab-Santuri. (Tender No- 803/EE/PD of 2021-22) | BP-2021-22-321 | 22/03/2022 | 0 | SK ABBAS | 4.28 | 0 | 0 | 0
2313 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Deuli, Habitation - Deuli (70 Nos.), Mouza-Sunuri, Habitation - Sunuri (42 Nos.) (Tender No.348/EE/PD of 2020-21) | BP-2022-23-25 | 07/04/2022 | 0 | SK ABBAS | 1.01 | 0 | 0 | 0
2314 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Providing FHTC supplying & laying different dia HDPE pipe line under zone-I of Balitora W/S Scheme (Tender No- 934/2021-22 of EE/PD) | BP-2022-23-20 | 07/04/2022 | 0 | GLAMOUROOMS UNEMPLOYED CO-OPERATIVE SOCIETY LTD. | 9.81 | 0 | 0 | 0
2315 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Shifting of underground HDPE & DIpipe line including supplying & laying HDPE & DI pipe of Distribution line with allied works from Manpur Pry. School to Ektira Village end under Zone-III of Balitora W/s Scheme. (Tender No.923/EE/PD of 2021-22) | BP-2021-22-349 | 28/03/2022 | 0 | BASANTA KUMAR SINGHADEO | 14 | 0 | 0 | 0
2316 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza - Balitora , Habitation - Balitora (112 Nos.) (Tender No.804/EE/PD of 2021-22) | BP-2022-23-311 | 26/09/2022 | 0 | TUMPA GORAIN | 0.97 | 0 | 0 | 0
2317 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block of Raghunathpur Sub- Division, PHE Dte. at Mouza- Balitora, Habitation- Begergoria (24) Balitora (88) Nos. (Tender No:- 281/EE/PD of 2020-21) | BP-2022-23-147 | 25/07/2022 | 0 | SUDHANSHU OJHA | 0.26 | 0 | 0 | 0
2318 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Probable estimate for sifting of ground HDPE & DI pipe line including supplying & DI pipe of Distribution line with allied works from Kapasdanga Village end to Mokra Pry. School through Jagannathdih & Saluni Village under Zone-II of Balitora W/s Scheme. (Tender No.937/EE/PD of 2021-22) | BP-2021-22-363 | 28/03/2022 | 0 | KHITISH CHANDRA PATHAK | 16.39 | 0 | 0 | 0
2319 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Balitora W/S Scheme at Santuri Block of Raghunathpur Sub- Division PHE Dte. at Mouza- Balitora, Habitation- Bagergoria (24) Nos. Balitora (88) Nos. (Tender No:- 802/EE/PD of 2021-22) | BP-2022-23-146 | 25/07/2022 | 0 | SUDHANSHU OJHA | 1.29 | 0 | 0 | 0
2320 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Repairing and Renovation of 3 (three) Nos. Over Head Reservoir (Capcaity 180cum at Bakulia, 70 cum near Mokra and 120 cum at Barsal) and other allied works under Balitora W/S scheme (Zone-I, II & III) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 42/PD | 07/01/2022 | 60 | SANTANU BANERJEE | 13.21 | 0 | 0 | 0
2321 | PURULIA | Purulia Mechanical | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Supply delivery and installation of 125 KVA voltage stabilizer for Augmentation of Balitora water supply scheme under PMD PHE Dte. In the district of Purulia. | 232/PMD | 03/03/2023 | 60 | ASHOKE ADHIKARY | 12.85 | 0 | 0 | 80
2322 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Supplying & laying different dia HDPE pipe line of distribution linewith allied works from Dandahit Bauro para to Danesdih village & end of Batka village to Syaldanga village &Kastagora village (zone-II1) site under (zone-III) of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 40/PD | 07/01/2022 | 30 | M/S. S.P CONSTRUCTION | 10.77 | 0 | 0 | 100
2323 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Supplying & laying different dia HDPE pipe line of distribution linewith allied works from Mokra village more to Jadudi village under (zone-II) of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 37/PD | 07/01/2022 | 30 | SANDIP KUMAR DUBEY | 7.54 | 0 | 0 | 100
2324 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Baltora Water Supply Scheme at Santuri Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. at Mouza -Bakuliashota, Habitation -Bakulia (16 Nos.), Mouza- Shunuri, Habitation - Uppardi (46 Nos.), Mouza- Ektira, Habitation -Berakural-(1),Ektira (48 Nos.), Mouza- Kashtagora Habitation -Chapabera Chak-(1) | 729/RNP | 06/12/2021 | 20 | MS MITRA SENGUPTA ENTERPRISES | 1.09 | 0 | 0 | 100
2325 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Functional House Hold Tap Connection (FHTC) at Deuli and supplying & laying different dia HDPE pipe line of distribution line with allied works at Sunuri & Upardih village (Zone-1) of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 346/RNP | 01/06/2022 | 20 | AMIT PATHAK | 3.87 | 0 | 0 | 100
2326 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Supplying & laying different dia HDPE pipe line of distribution line with allied works from Dandahit Bauri Para to Danesdih Village & end of Batka Village to Siyaldanga Village & Kastagora Village (Zone-III) of Balitora W/S Scheme under Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 488/RNP | 28/07/2022 | 20 | M/S. S.P CONSTRUCTION | 4.81 | 0 | 0 | 100
2327 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Chowkage clearence of Distribution line at Deuli village and shifting of DI, GI, MS Pipe from Manbazar Pump house site to Balitora Zone-I OHR campus under Balitora W/S Scheme (Zone-I) Raghunathpur Sub-Divn, P.H.E. Dte. | 396/RNP | 05/09/2023 | 15 | M/S SAYAK BHATTACHARYA | 0.96 | 0 | 0 | 100
2328 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Repairing and renovation of existing structure excluding OHR under Balitora W/S Scheme (Zone-I, II & III) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 41/PD | 07/01/2022 | 60 | SANTANU BANERJEE | 14.26 | 0 | 0 | 100
2329 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Material Requisition To Resource Division | 957/PD | 20/06/2022 | 0 | Resource Division | 26.31 | 0 | 0 | 0
2330 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Material Requisition To Resource Division | 977/PD | 22/06/2022 | 0 | Resource Division | 143.77 | 0 | 0 | 0
2331 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Supplying and laying different dia HDPE pipe line of distribution line with allied works from Dandahit Bauro Para to Danesdih village & end of Batka village to Syaldanga village & kastagora village (Zone-III) site under (Zone-III) of Balitora W/S Scheme of Raghunathpur Sub- Division under Purulia Division PHE Dte. (Tender No- 948/2021-22 of EE/PD) | BP-2022-23-80 | 01/07/2022 | 0 | M/S. S.P CONSTRUCTION | 10.16 | 0 | 0 | 0
2332 | PURULIA | Purulia Mechanical | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Enhancement of contractual demand from 71 KVA to 0.4 KV to 120/120/120/120/120 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o The Ex.Engg PMD PHE Dte.(Consumer ID : 950006038) to their premises at Balitora Water Supply Scheme |  | 28/02/2023 | 0 | WBSEDCL PURULIA | 6.74 | 0 | 0 | 0
2333 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/4524 bill paid for the month of Sep,22 to June,22. | BP-2023-24-334 | 02/08/2023 | 0 | ANUP KUMAR SAHA | 2.33 | 0 | 0 | 0
2334 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Shifting of Rising Main of underground DI pipe line including supplying & laying of DI pipe from Jagannathdih more to boundary wall of Barshal OHR (Zone-III) of Balitora W/S Scheme of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 1839/PD | 12/12/2022 | 45 | M/S SAYAK BHATTACHARYA | 23.27 | 0 | 0 | 30
2335 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Providing FHTC & Supplying & laying different dia HDPE pipe line of distribution linewith allied works from OHR (zone-1) site to Mathorgoria village More & Balitora bauripara end to bramhan para of Balitora village under zone-I of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Mouza- Balitora, Habitation :-Balitora) | 36/PD | 07/01/2022 | 60 | GLAMOUROOMS UNEMPLOYED CO-OPERATIVE SOCIETY LTD. | 37.4 | 0 | 0 | 100
2336 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | New Sinking of 4 (Four) Nos 200 mm dia river bed vertical tubewell alongwith necessary 100 mm dia GI collecting line in connection with FHTC from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Balitora under Balitora W/S Scheme under Raghunathpur Sub Division, PHE Dte. | 467/PD | 28/03/2023 | 45 | KHITISH CHANDRA PATHAK | 15.93 | 0 | 0 | 100
2337 | PURULIA | Purulia Mechanical | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, MCC panel Flowmeter and other allied works for augmentation of Balitora water supply scheme under PMD, PHE Dte. in the district of Purulia. | 438/PMD | 19/04/2023 | 60 | PREMNATH MITRA | 46.28 | 0 | 0 | 90
2338 | PURULIA | Purulia Mechanical | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well with allied cable line and other allied works for augmentation of Balitora w/s scheme under PMD, PHE Dte. in the District of Purulia. | 648/PMD | 08/06/2023 | 60 | PREMNATH MITRA | 12.15 | 0 | 0 | 91
2339 | PURULIA | Purulia Mechanical | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Payment for New Service Connection charge at Manpur , JL - 31 , Plot - 479 under Purulia Mechanical Division P.H.E. Dte. to WBSEDCL , Purulia , Santuri CCC . | BP-24-25-42 | 02/07/2024 | 0 | SANTURI CCC | 3.6 | 0 | 0 | 0
2340 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Miscellaneous collection for Indian Railways against invoice ID No.WL00000000038190 dt.02-03-2024. | BP-2023-24-867 | 08/03/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
2341 | PURULIA | Purulia Mechanical | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Payment of new Electric service connection charge to WBSEDCL ,Santuri CCC at Santuri Mouja ( O.H.R. No.2 under Balitora W.S.Scheme ) ,application no.- 2004753984 , Ref. Id.- 204318171 , Contact Demand - 1330 watt . | BP-24-25-41 | 02/07/2024 | 0 | SANTURI CCC | 0.05 | 0 | 0 | 0
2342 | PURULIA | Purulia Mechanical | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Payment for New Electric connection charge at Madhukunda O.H.R. Site , Mouja : Madhukunda under Augmentation of Balitora Water Supply to Santuri CCC of WBSEDCL . | BP-24-25-26 | 11/06/2024 | 0 | SANTURI CCC | 0.94 | 0 | 0 | 0
2343 | PURULIA | Purulia Mechanical | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Enhancement of the contract demand from 71 KVA at 0.4 KV to 120/120/120/120/120 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE Balitora Water Supply | BP-23-24-310 | 21/03/2024 | 0 | WBSEDCL PURULIA | 11.11 | 0 | 0 | 0
2344 | PURULIA | Purulia Division | Augmentation of Balitora & its adjoining mouzas water supply scheme , SM/09214 | Augmentation | Probable estimate for shifting of under ground HDPE & DI pipe line including supplying & laying HDPE & DI pipe of Distribution line with allied works from Kapashdanga Village end to Mokra Pry. School through Jagannathdih & Saluni Village under Zone-II of Balitora W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 38/PD | 07/01/2022 | 1180 | KHITISH CHANDRA PATHAK | 34.11 | 0 | 0 | 75
2345 | PURULIA | Purulia Division | Extension of piped water supply (PWS) to source less schools located within the command area of PWSSs with in Purulia District as per the list of School Education Department. (30 Nos.) , SM/09028 | School | Providing necessary water supply arrangement within school with connection from exist collapsed Big-Dia D.T.H. Tube Well (200mm x 165mm) considering 200mt Dept and GI pipe of adequate dia and PVC pipes (medium duty confirming to the ASTMD-1785) and length where necessary 6 nos. alloy Iron with brass spindle bib cock/ stop cock at toilet and kitchen, gunmetal wheel valves, supplying submersible pumping machinery 1.0 HP of Crompton/ KSB or other renowned make conforming to latest BIS codes with all necessary electrical connections supplying PVC water storage tank of approved quality of total capacity of 1500ltr capacity.(3nos. 500ltrs tank) ( To be installed at roof top of school building ) all complete. | 289/PD | 27/02/2023 | 45 | PRINCE INDUSTRIES ( INDIA) | 6.53 | 0 | 0 | 0
2346 | PURULIA | Purulia Division | Extension of piped water supply (PWS) to source less schools located within the command area of PWSSs with in Purulia District as per the list of School Education Department. (30 Nos.) , SM/09028 | School | Water supply Tap Connection Arrangement for 2 nos AWC within Joypur Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | 725/PD | 02/05/2022 | 45 | HUSSAIN CONSTRUCTION | 15.68 | 0 | 0 | 100
2347 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. , SM/10284 | Anganwadi | Water supply Tap Connection Water supply Tap Connection Arrangement for 12 nos AWC within Bagmundi Block (Part-B), 08 nos AWC within Bagmundi Block (Part-E-1) & 04 nos AWC within Bagmundi Block (Part-F-1) of Purulia District under Purulia Division, PHE Dte. (Phase-I) (Without Tubewell) (SL-13) | 212/PD | 13/02/2023 | 45 | MANASH GHOSH | 113.58 | 0 | 0 | 0
2348 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. , SM/10284 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Baghmundi Block (Part-C) of Purulia District under Purulia Division, PHE Dte. (Without Tubewell) (SL-2) | 300/PD | 28/02/2023 | 45 | MIDNAPUR PIPE CONCERN | 117.72 | 0 | 0 | 65
2349 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. , SM/10284 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Bagmundi Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | 498/PD | 29/03/2022 | 45 | KANTILAL SAO | 15.78 | 0 | 0 | 0
2350 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. , SM/10284 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Baghmundi Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | 1853/PD | 13/12/2022 | 45 | KM ENTERPRISES | 49.52 | 0 | 0 | 75
2351 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. , SM/10284 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Jhalda-II Block & Baghmundi Block (Part-A)of Purulia District under Purulia Division, PHE Dte.(Phase-I) | 1127/PD | 25/07/2022 | 45 | SINGHA ENTERPRISE | 94.88 | 0 | 0 | 100
2352 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. , SM/10284 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos. AWC within Jhalda-I, Arsha & Bandwan Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | 1050_PD | 08/07/2022 | 45 | PRASENJIT BASAK | 157.97 | 0 | 0 | 100
2353 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. , SM/10284 | Anganwadi | Water supply Tap Connection Arrangement for 12 nos AWC within Bagmundi Block (Part-A), 08 nos AWC within Bagmundi Block (Part-E-2) & 04 nos AWC within Bagmundi Block (Part-F-2) of Purulia District under Purulia Division, PHE Dte. (Phase-II) (Without Tubewell) (SL. No. 12) | 462/PD | 27/03/2023 | 800 | ZEOLITE FRESH INDIA | 113.57 | 0 | 0 | 60
2354 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. , SM/10284 | Anganwadi | Water supply Tap Connection Arrangement for 18 nos AWC within Bagmundi Block (Part-D), 02 nos AWC within Bagmundi Block (Part-E-3) & 04 nos AWC within Bagmundi Block (Part-F-3) of Purulia District under Purulia Division, PHE Dte. (Phase-III) (Without Tubewell) (SL. No. 14) | 301/PD | 28/02/2023 | 720 | ARINDAM MAJUMDAR | 113.55 | 0 | 0 | 100
2355 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 NOS) under Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. , SM/10284 | Anganwadi | Installation of 02 (Two) nos. 1.00 H.P. capacity Solar Photovoltaic Submersible Pump set in pre-existing / new bore Tube well along with 1200 Watt peak capacity Solar photovoltaic array panels on steel structure including Supply & Delivery of approved quality materials & Geophysical investigation by electrologging with all allied works at Majhidi and sahebbon Village within Ajodhya WSS in Purulia District of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1876/PD | 01/10/2024 | 45 | ROY CONSTRUCTION | 22.83 | 0 | 0 | 0
2356 | PURULIA | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Supplying & laying of HDPE pipe line for Distribution System of Sindri-Chasmore W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte. (Chirka Mouza) (Part-A) (Tender No- 315/2022-23 of EE/PD) | BP-2022-23-383 | 19/10/2022 | 0 | ZEST INFRACON | 45.52 | 0 | 0 | 0
2357 | PURULIA | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection Jal Jeevan Mission (JJM) and Jal Sapna at Chirka village of Garaphushara G.P. under command area of Sindri-Chasmore W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte. (Chirka Mouza) (Part-B) | 171/PSD | 18/04/2022 | 25 | SK ABBAS | 4.85 | 0 | 0 | 0
2358 | PURULIA | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Supply delivery and installation of centrifugal pumping machineries, flowmeter with necessary substitutes and allied electrical panel at existing pump house at Augmentation of Sindri chasmore w/s scheme under PMD, PHE Dte. in the District of Purulia. | 207/PMD | 28/02/2023 | 60 | RABINDRA NATH KHAN | 66.49 | 0 | 0 | 60
2359 | PURULIA | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Sindrichasmore Water Supply scheme Block Purulia-II under Purulia Mechanical Division PHE. Dte. District Purulia | 213/PMD | 28/02/2023 | 30 | TAPAN KUMAR DEY | 21.61 | 0 | 0 | 60
2360 | PURULIA | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Supply delivery and installation of centrifugal pumping machineries, Voltage Stabilizer with necessary substitutes and allied electrical panel at for Proposed CWR at intake side of Sindrichasmore w/s scheme under PMD, PHE Dte. in the District of Purulia. | 206/PMD | 28/02/2023 | 60 | RABINDRA NATH KHAN | 31.34 | 0 | 0 | 15
2361 | PURULIA | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/4524 bill paid for the month of Sep,22 to June,22. | BP-2023-24-334 | 02/08/2023 | 0 | ANUP KUMAR SAHA | 2.33 | 0 | 0 | 0
2362 | PURULIA | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Repairing & renovation of 100 cum capacity CWR & Pump house, Boundary Wall (OHR Site and River Site) & Tranformar room, Meter room with Guard room at Sindri-Chasmore river site Pump house campus of Sindri-Chsmore W/S Scheme of Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | 42/PD | 09/01/2024 | 631 | M/S SB CONSTRUCTION | 21.36 | 0 | 0 | 90
2363 | PURULIA | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Rectification of different feeders of Beldi W/S scheme(Low lift) for Augmentation of Beldi W/S Scheme under PMD, PHE Dte. in the District of Purulia. | 421/PMD | 11/03/2024 | 30 | TAPAN KUMAR DEY | 5.21 | 0 | 0 | 30
2364 | PURULIA | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Supply and laying of cables for taking power & Misc. works for Pump house of Sindrichasmore w/s scheme under PMD, PHE Dte. in the District Purulia. | 1451/PMD | 01/10/2024 | 30 | RABINDRA NATH KHAN | 6.21 | 0 | 0 | 0
2365 | PURULIA | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Supply of valves, pipes and miscellaneous works for new proposed CWR & existing P.H of Sindrichasmore w/s scheme under PMD, PHE Dte. in the district Purulia. | 995/PMD | 21/06/2024 | 60 | RABINDRA NATH KHAN | 1.61 | 0 | 0 | 0
2366 | PURULIA | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Internal and external illumination with other allied works for augmentation of existing pump house & new CWR pump house of Sindrichasmore water supply scheme under Purulia Mechanical Division , PHE Dte .in the District Purulia | 972/PMD | 20/06/2024 | 226 | COMBINE ENTERPRISES | 18.83 | 0 | 0 | 20
2367 | PURULIA | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Supplying & laying of HDPE pipe line for Distribution System of Sindri-Chasmore W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte. (Chirka Mouza) (Part-A) | 629/PD | 22/04/2022 | 45 | ZEST INFRACON | 68.48 | 0 | 0 | 100
2368 | PURULIA | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Repairing and renovation of the Over Head reservoir (OHR) of 250 m3 Capacity, Staging Height 20 mtr. of Sindri-Chasmore W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | 1477/PD | 20/09/2022 | 90 | SADHAN GORAIN | 11.8 | 0 | 0 | 100
2369 | PURULIA | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Repairing of DI rising main pipeline including cleaning of chokage & Construction of 100 Cum capacity RCC clear water reservoir (CWR) and Construction of Meter Room, Panel Room, undercut pump house with other allied works at river site campus and providing 456 nos functional household tap connection at chirka mouza in connection with Jal Jeevan Mission (JJM) for Augmentation of Sindri-ChasmoreW/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 655/PD | 17/05/2023 | 60 | SB CONSTRUCTION | 59.68 | 0 | 0 | 100
2370 | PURULIA | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Providing internal and external illumination arrangement at proposed CWR of Sindrichasmore W/S under PMD, PHE Dte. in the District of Purulia. | 649/PMD | 08/06/2023 | 60 | MAHIPAL MAJHI | 6.13 | 0 | 0 | 5
2371 | PURULIA | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Construction of RCC common manifold camber and Laying of 250 mm dia DI rising main from manifold chamber to CWR at river site of Sindri- chas more W/S scheme in connection of Jal Jeevan Mission (JJM) under Sindri-chas more W/S scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1529/PD | 16/10/2023 | 45 | SADHAN GORAIN | 11.86 | 0 | 0 | 100
2372 | PURULIA | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Pushing of 600mm dia MS pipe and 100 mm dia MS water carrier pipe by hydraulic jacking method across Purulia to Jhalda Road for laying Distribution Main for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission at 04 (Four) different location Near Chas more for Sindri Chasmore W/S Scheme under Purulia Sadar Sub-Division, Purulia Division, PHE Dte. | 1830/PD | 12/12/2023 | 60 | MS GORAIN CONCERN | 41.39 | 0 | 0 | 45
2373 | PURULIA | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Repairing of DI rising main pipeline including cleaning of chokage & Construction of Boundary wall, pathway and landfilling with other allied works at river site of Sindri Chasmore W/S Scheme of Purulia Sadar Sub-Divn. under Purulia Division, PHE Dte. | 1831/PD | 12/12/2023 | 60 | M/S SB CONSTRUCTION | 18.02 | 0 | 0 | 70
2374 | PURULIA | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Supply, delivery & installation of Glow Sign board & Lighting conductor under Sindri Chas more Water Supply Scheme under Purulia Mechanical Division P.H.E Dte.in the district of Purulia. | 350/PMSD(W/S) | 04/09/2024 | 15 | PINTU DEY | 0.48 | 0 | 0 | 100
2375 | PURULIA | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Laying of 250 mm dia MS Pipe and Road Crossing and Construction of PCC Approach Road at OHR site for Sindri-Chas W/S Scheme in connection with FHTC connection under Jal Jeevan Mission (JJM) Programme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 509/PD | 16/03/2024 | 60 | SADHAN GORAIN | 22.84 | 0 | 0 | 100
2376 | PURULIA | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Supply and installation of 2 M.T capacity single girder H.O.T crane with gantry girder and square rail for Sindrichasmore w/s scheme new CWR Pump house under PMD, PHE Dte. in the District of Purulia. | 968/PMD | 20/06/2024 | 60 | RABINDRA NATH KHAN | 8.09 | 0 | 0 | 100
2377 | PURULIA | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Enhancement of the contract demand from 80 KVA at 0.4 KV to 105/105//105//105//105 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE SINDRI CHASMORE Water Supply, (Consumer ID -942413800) | BP-23-24-308 | 19/03/2024 | 0 | WBSEDCL PURULIA | 1.44 | 0 | 0 | 0
2378 | PURULIA | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Supply and installation of Indoor type Vacuum Circuit breaker and allied works for Sindrichasmore w/s scheme under PMD, PHE Dte. in the District of Purulia. | 1542/PMD | 11/11/2024 | 385 | RABINDRA NATH KHAN | 12.07 | 0 | 0 | 100
2379 | PURULIA | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Supply and lowering of submersible pump motor sets at at newly constructed River Bed Tubewell with supply of necessary substitutes at Augmentation of Sindri chasmore w/s scheme under PMD, PHE Dte. in the District of Purulia. | 208/PMD | 28/02/2023 | 704 | RABINDRA NATH KHAN | 17.88 | 0 | 0 | 85
2380 | PURULIA | Purulia Mechanical | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Supply and installation of automatically controlled diaphragm type Chlorinator dosing pump with Piping & structural works in connection with Disinfection arrangement System & Miscellaneous works at Pump House under Sindrichasmore W/S Scheme, Purulia Mechanical Division, P.H.E Dte. | 1543/PMD | 11/11/2024 | 60 | MAHIPAL MAJHI | 3.63 | 0 | 0 | 100
2381 | PURULIA | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Laying of MS pipe distribution line at Garafusro under command area of Sindri Chasmore W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1509/PD | 27/08/2024 | 158 | SADHAN GORAIN | 32.27 | 0 | 0 | 100
2382 | PURULIA | Purulia Division | Augmentation of Sindhri Chasmore PWSS for providing Functional Household Tap Connection (FHTC) , SM/10347 | Augmentation | Laying of Left out Loop Pipe Line for distribution System at Sindri and Garafusro Mouza under command area of Sindri Chasmore W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | 1085/PD | 07/06/2024 | 60 | SADHAN GORAIN | 24.37 | 0 | 0 | 100
2383 | PURULIA | Purulia Mechanical | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Manguria lalpur Water Supply scheme Block Hura under PMD PHE Dte. District Purulia. | 166/PMD | 07/03/2022 | 30 | JAL PRAVAHIKA PVT. LTD | 20.5 | 0 | 0 | 100
2384 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Distribution Main by supplying & laying of different dia HDPE pipe line and Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No.959/EE/PD of 2021-22) | BP-2021-22-292 | 09/03/2022 | 0 | PREMNATH MITRA | 53.06 | 0 | 0 | 0
2385 | PURULIA | Purulia Mechanical | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | SUPPLY DELIVERY & INSTALLATION OF 1KG/HR GASEOUS CHLORINATION SYSTEM OF AUGMENTATION OF MANGURIA LALPUR W/S SCHEME, HURA BLOCK UNDER PMD PHE DTE.(TR.NO 371 OF 2021-22) | C042211603113 | 08/04/2022 | 0 | JAL PRAVAHIKA PVT. LTD | 8.78 | 0 | 0 | 0
2386 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Additional work for Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B)(Daldali G.P.)(220 Nos.) (Tender No.22/EE/PD of 2022-23) | BP-2022-23-51 | 17/05/2022 | 0 | M/S CHAKRABORTY CONSTRUCTION | 4.54 | 0 | 0 | 0
2387 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-A) (Chatumadar G.P.)(300 Nos) (Tender No..902/EE/PD OF 2021-22) | BP-2022-23-238 | 05/09/2022 | 0 | ALOK KUMAR CHAKRABORTY | 6.2 | 0 | 0 | 0
2388 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Maguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-A( Mouza-Amlatara,Chatumadar,Kajali,Karamadi under Chatumadar G.P). (987 Nos.) (Tender No.409/EE/PD of 2020-2021) | BP-2021-22-240 | 16/02/2022 | 0 | ALOK KUMAR CHAKRABORTY | 2.61 | 0 | 0 | 0
2389 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B)(Daldali G.P.)(220 Nos.) (Tender No.946/EE/PD of 2021-22) | BP-2022-23-31 | 08/04/2022 | 0 | M/S CHAKRABORTY CONSTRUCTION | 8.65 | 0 | 0 | 0
2390 | PURULIA | Purulia Mechanical | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 110 KVA AT 0.4 KV TO 160/160/160/160/160 KVA RESPECTIVELY AT 0.4 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o , THE EX ENGG PMD PHE DTE(CONSUMER ID : 950009505) TO THEIR PREMISES AT MANGURIA LALPUR WATER SUPPLY DIST PURULIA UNDER REGIONAL OFFICE PURULIA |  | 03/11/2022 | 0 | WBSEDCL PURULIA | 9.17 | 0 | 0 | 0
2391 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Additional Functional Household Tap Connection (FHTC) in connection with other allied works of Manguria-Lalpur W/s Scheme. (Tender No.901/EE/PD of 2021-22) | BP-2021-22-258 | 25/02/2022 | 0 | ALOK KUMAR CHAKRABORTY | 5.92 | 0 | 0 | 0
2392 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Maguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-C (Mouza-Maguria-Lalpur under Maguria-Lalpurr G.P). 1218 Nos.) (Tender No.307/EE/PD of 2020-21) | BP-2021-22-326 | 22/03/2022 | 0 | SWAPAN MANDAL | 8.16 | 0 | 0 | 0
2393 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Additional work for FHTC including other allied works of Manguria-lalpur W/S Scheme at Hura Block (Part- C) [Tender No- 939/2021-22 of EE/PD] | BP-2022-23-63 | 24/05/2022 | 0 | SWAPAN MANDAL | 18.23 | 0 | 0 | 0
2394 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Distribution Main by supplying & laying of different dia HDPE pipe line and Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 1554/PD | 15/12/2021 | 60 | PREMNATH MITRA | 78.3 | 0 | 0 | 85
2395 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-A)(Chatumadar G.P.)(300 Nos) | 161/PD | 25/01/2022 | 45 | ALOK KUMAR CHAKRABORTY | 13.88 | 0 | 0 | 65
2396 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B)(Daldali G.P.)(220 Nos.) | 162/PD | 25/01/2022 | 45 | M/S CHAKRABORTY CONSTRUCTION | 9.95 | 0 | 0 | 35
2397 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Additional work of Functional Household Tap Connection (FHTC) including other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) (Daldali G.P.) (220 Nos.) | 144/RNP | 31/03/2022 | 14 | M/S CHAKRABORTY CONSTRUCTION | 4.55 | 0 | 0 | 0
2398 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 300 cum at Manguria OHR under Manguria-Lalpur W/S Scheme (Zone-I) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 158/PD | 25/01/2022 | 60 | KANAILAL PAL | 7.43 | 0 | 0 | 95
2399 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Construction of Switch Room-Cum-Chlorine Room at Amrakocha Pump House Site under Manguria-Lalpur W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 85/RNP | 28/02/2022 | 90 | M/S SAYAK BHATTACHARYA | 4.39 | 0 | 0 | 90
2400 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 200 cum at Amlatora OHR under Manguria-Lalpur W/S Scheme (Zone-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 653/PD | 22/04/2022 | 30 | KANAILAL PAL | 4.69 | 0 | 0 | 90
2401 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Supplying and laying of HDPE pipe line from existing CWR to Karandih through Amrakotcha village under Manguria-Lalpur W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1815/PD | 06/12/2022 | 45 | ALOK KUMAR CHAKRABORTY | 14.41 | 0 | 0 | 100
2402 | PURULIA | Purulia Mechanical | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Supply delivery and installation of 150 KVA voltage stabilizer for Augmentation of Manguria Lalpur water supply scheme under PMD PHE Dte. In the district of Purulia | 82/PMD | 01/02/2023 | 60 | SWAPAN ENTERPRISE | 13.25 | 0 | 0 | 100
2403 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Allied works for repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 200 cum at Amlatora OHR under Manguria-Lalpur W/S Scheme (Zone-II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 183/PD | 07/02/2023 | 30 | KANAILAL PAL | 2.64 | 0 | 0 | 100
2404 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Making Two nos Bypass arrangement with allied works in between of over flow line to distribution main at Maguria Lalpur Zone-I & II OHR site under Maguria Lalpur water supply scheme of Raghunathpur Sub Division uneder Purulia Division, PHE Dte. | 880/PD | 03/07/2023 | 30 | ALOK KUMAR CHAKRABORTY | 4.2 | 0 | 0 | 100
2405 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Supplying laying fitting fixing of HDPE pipe Near Doldoli Bridge to Doldoli Bastri to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Manguria-Lalpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 990/PD | 26/07/2023 | 60 | CHANCHAL MISHRA | 5.79 | 0 | 0 | 100
2406 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | New sinking of 5(Five) nos. 200 mm dia river bed tubewell (Horizontal) at Kansabati river ( Amrakocha Ghat) alongwith laying of 100 mm dia G.I. collecting line with all allied works under Manguria-Lalpur W/S Scheme under Raghunathpur Sub-Division, PHE Dte. | 650/PD | 22/04/2022 | 45 | NANIGOPAL DEY | 18.95 | 0 | 0 | 0
2407 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Additional work for functional Household Tap Connection (FHTC) and other allied works of Manguria-Lalpur Water Supply Scheme at Hura Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-A) (Chatumadar G.P.) | 1353/PD | 13/09/2023 | 45 | ALOK KUMAR CHAKRABORTY | 2.02 | 0 | 0 | 100
2408 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Supplying laying fitting fixing of HDPE pipe from Manguria-Lalpur OHR site Zone -II main distribution pipe line to Chatumather Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) under Manguria-Lalpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1357/PD | 13/09/2023 | 45 | PRAMIT CHATTERJEE | 18.04 | 0 | 0 | 100
2409 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Material Requisition To Resource Division | 960/PD | 20/06/2022 | 0 | Resource Division | 39.43 | 0 | 0 | 0
2410 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | New sinking of 05 (Five) Nos. 200 mm dia river bed tube well (Horizontal) at Kansabati river (Amrakocha Ghat) along with laying of 100 mm dia GI collecting line with all allied works under Manguria-lalpur W/S Scheme under Raghunathpur Sub- Division, PHE Dte. (Tender No- 53/2022-23 of EE/PD) | BP-2022-23-72 | 01/07/2022 | 0 | NANIGOPAL DEY | 10.12 | 0 | 0 | 0
2411 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Car bill for hair charges for office purpose against vehicle reg. no.WB55A/7171 for the period form March,23 to April,23. | BP-2023-24-231 | 14/06/2023 | 0 | NIRUPAMA DEY | 0.71 | 0 | 0 | 0
2412 | PURULIA | Purulia Division | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Clearing of chokage and making HDPE loop line for Kalali , Amlatora, Chatumadar, & Hijuli under under Manguria-Lalpur W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1814/PD | 01/12/2022 | 180 | ALOK KUMAR CHAKRABORTY | 8.16 | 0 | 0 | 100
2413 | PURULIA | Purulia Mechanical | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well and existing one no tube well with allied cable line and other allied works for augmentation of Manguria Lalpur w/s scheme under PMD, PHE Dte. in the District of Purulia. | 80/PMD | 01/02/2023 | 60 | RAJIB COMPANY | 24.65 | 0 | 0 | 100
2414 | PURULIA | Purulia Mechanical | Augmentation of Manguria-Lalpur W/S Scheme , SM/09943 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, Flowmeter, MCC Panel and other allied works for augmentation of Manguria Lalpur water supply scheme under PMD, PHE Dte. In the district of Purulia. | 81/PMD | 01/02/2023 | 60 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 49.6 | 0 | 0 | 100
2415 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Supply and delivery of 200 mm dia UPVC pipe for Purulia-I Block and other Blocks at Drilling Store/Site under Purulia Mechanical Division, P.H.E Dte. | 754/PMD | 07/11/2022 | 30 | COMBINE ENTERPRISES | 16.67 | 0 | 0 | 0
2416 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Providing skilled labor for operation of big dia & small dia DTH drilling with departmental rig unit 26D/AR under Purulia Mechanical Division PHE Dte. (Tender No.19/EE/PMD of 2022-23) | BP-2022-23-256 | 15/09/2022 | 0 | NUPUR CHANDRA HALDER | 0.81 | 0 | 0 | 0
2417 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Construction of Rig bore tube well at different AWC under JJM Programme (Fuel & Lubricant bill) | BP-2022-23-392 | 19/10/2022 | 0 | M/S SHANKAR AUTO SERVICE | 14.86 | 0 | 0 | 0
2418 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Construction of Rig board tube well (200mmX165mm) by DTH method at Durku GP is Purulia-I block under Purulia Mechanical Division PHE Dte. (T/N 136/EE/PMD of 2022-23) |  | 13/08/2022 | 0 | ANUP KUMAR SAHA | 43.17 | 0 | 0 | 0
2419 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Submission of 01(One) Hand Receipt for fuel bill in respect of construction of Rig Board Tube Well at different AWC Programme. |  | 25/09/2022 | 0 | M/S SHANKAR AUTO SERVICE | 14.86 | 0 | 0 | 0
2420 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Providing hire boar skilled & experienced drivers for driving Departmental Rig Mounted tracks & supporting vehicle of Rig mounted tracks & operating vehicle rig unit 26D/AR & 13D/AR & other vehicle under Purulia Mechanical Division PHE Dte. (Tender No.118/EE/PMD of 2019-20) | BP-2022-23-264 | 16/09/2022 | 0 | SANTU MITRA | 0.88 | 0 | 0 | 0
2421 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Execution of electrical restor query for ground water availability by experience qualified geologist..... Nadiha Udaypur GP in Para Block & other Area for RBTW source erection in AWC with in Purulia Mechanical Division PHE Dte. (Tender No.169/EE/PMD of 2022-23) | BP-2022-23-255 | 15/09/2022 | 0 | NUPUR CHANDRA HALDER | 4.93 | 0 | 0 | 0
2422 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method at Durku GP, Purulia -I Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 454/PMD | 04/07/2022 | 15 | ANUP KR. SAHA | 34.97 | 0 | 0 | 0
2423 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Construction of Rigbored Tubewell (200mm X 165mm) by DTH method in different source less AWC at Ajodhya GP, Baghmundi Block under Purulia Mechanical Division,P.H.E Dte. in the District of Purulia. | 784/PMD | 24/11/2022 | 15 | M DHARA & BROTHERS | 37.83 | 0 | 0 | 0
2424 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Execution of the yield test at Dubra, Anara GP in Para Block within the district of Purulia under code SM10285 under PMD, PHE, Dte. | 32/PMSD(Drilling) | 03/02/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0 | 0
2425 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Construction of Rigbored Tube well (200mmx 165mm) by DTH method in different sourceless AWC at Para Block where adjacent road is narrow and critical under Purulia Mechanical Division PHE. Dte. in the District of Purulia | 73/PMD | 31/01/2023 | 30 | SUMIT KR. CHAKRABORTY | 75.71 | 0 | 0 | 0
2426 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Construction of Rigbored Tubewell (200mmx165mm) by DTH method in different sourceless AWC at Lagda GP , Purulia -I Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 28/PMD | 17/01/2023 | 10 | KHITISH CH. PATHAK | 15.86 | 0 | 0 | 0
2427 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Execution of the yield test at Anara GP in Para Block within the district of Purulia under code SM10285 under PMD, PHE, Dte. | 27/PMSD(Drilling) | 02/02/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0 | 0
2428 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Construction of Rigbored Tube well (200mmx 165mm) by DTH method in different sourceless AWC at Purulia-l Block where adjacent road is narrow and critical under Purulia Mechanical Division PHE. Dte. in the District of Purulia | 71/PMD | 31/01/2023 | 20 | RABINDRA NATH KHAN | 37.84 | 0 | 0 | 0
2429 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 7 nos AWC within Purulia-I Block ) of Purulia District under Purulia Division, PHE Dte. | 40/PD | 09/01/2023 | 45 | S. S. ENTERPRISE | 3.89 | 0 | 0 | 0
2430 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Name of Work: Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Manara GP, Purulia-I Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. | 383/PMD | 06/04/2023 | 10 | GOUTAM CHAKRABORTY | 12.69 | 0 | 0 | 0
2431 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Purulia-I Block (Part-E) of Purulia District under Purulia Division, PHE Dte. | 756/PD | 02/05/2022 | 45 | SK ABBAS | 26.93 | 0 | 0 | 100
2432 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 3 no AWC within Purulia-I Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | 760/PD | 02/05/2022 | 45 | M/S CHAKRABORTY CONSTRUCTION | 13.54 | 0 | 0 | 0
2433 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 3 no AWC within Purulia-I Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | 761/PD | 02/05/2022 | 45 | ASHOKE ADHIKARY | 13.52 | 0 | 0 | 100
2434 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 10 nos AWC within PURULIA-I Block (Part-K,L,M,N,N,O,P,Q,R) from newly sinked tubewell by mechanical division of Purulia District under Purulia Division, PHE Dte. | 1868/PD | 13/12/2022 | 45 | MAHARSHI BANERJEE | 47.3 | 0 | 0 | 80
2435 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Construction of Rigbored Tubewell (200x165mm) by DTH method in different sourceless AWC at Bhandarpuara GP , Purulia -I Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 27/PMD | 17/01/2023 | 20 | M/S D. PALIT & CO. | 44.35 | 0 | 0 | 0
2436 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Durku GP, Purulia-I Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 384/PMD | 06/04/2023 | 10 | SEN BROTHERS | 12.68 | 0 | 0 | 100
2437 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method in different sourceless AWC at Sonaijuri GP, Purulia-I Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia. | 385/PMD | 06/04/2023 | 10 | S. PATHAK & CO. | 6.34 | 0 | 0 | 100
2438 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Washing and developing of tube well for AWC programme at Purulia-I ,Purulia-II and other block under PMD, PHE, Dte.(2nd call) | 413/PMD | 12/04/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 3.58 | 0 | 0 | 100
2439 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Providing skilled labour for operation of big dia & small dia DTH drilling with departmental rig unit 26D/AR under Purulia Mechanical Division PHE Dte. (Tender No.19/EE/PMD of 2022-23) | BP-2022-23-215 | 24/08/2022 | 0 | NUPUR CHANDRA HALDER | 0.13 | 0 | 0 | 0
2440 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Construction of Rig board tube well (200mmX165mm) by DTH method at Durku GP in Purulia-I block under Purulia Mechanical Division PHE Dte. (Tender No 136/EE/PMD of 2022-23) | BP-2022-23-212 | 24/08/2022 | 0 | ANUP KUMAR SAHA | 34.96 | 0 | 0 | 0
2441 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Supply and delivery of Cummins filter & some other items at store under PMD, PHE Dte. (Tender No- 08/2022-23 of EE/PMD) | BP-2022-23-221 | 24/08/2022 | 0 | MAHIPAL MAJHI | 1.29 | 0 | 0 | 0
2442 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Repairing and regular maintenance of 2 nos water tanker (WB89-2339 & WB89-2305) and all other allied works under Purulia Mechanical Division, PHE Dte. (Tender No- 40/2022-23 of EE/PMD) | BP-2022-23-216 | 24/08/2022 | 0 | PINTU DEY | 0.59 | 0 | 0 | 0
2443 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Yield test of Purulia-I, Purulia-II, Joypur, Jhalda-I, Jhalda-II and other blocks in the District of Purulia under PMD, PHE Dte. (Tender No- 25/2022-23 of EE/PMD) | BP-2022-23-217 | 24/08/2022 | 0 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 2.18 | 0 | 0 | 0
2444 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Maintenance and minor repairing of vehicle No WAW-1992 (Swaraj Mazda) VWS-849 and minor modification work of ATR-711 under Purulia Mechanical Division, PHE Dte. (Tender No- 129/2022-23 of EE/PMD) | BP-2022-23-214 | 24/08/2022 | 0 | NUPUR CHANDRA HALDER | 0.78 | 0 | 0 | 0
2445 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Supply and delivery of drilling adaptor, Rod lifter, Rod guide bush at store under PMD, PHE Dte. (Tender No- 22/2022-23 of EE/PMD) | BP-2022-23-213 | 24/08/2022 | 0 | UJJAL DIESEL SERVICE | 3.25 | 0 | 0 | 0
2446 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Purulia-I Block of Purulia District under Purulia Division, PHE Dte.(Phase-I) (Part-D, G & K) | 825/PD | 17/05/2022 | 45 | MEGA SOLAR ENERGY | 90.64 | 0 | 0 | 100
2447 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Purulia-I Block (Part-D) of Purulia District under Purulia Division, PHE Dte. | 755/PD | 02/05/2022 | 45 | FIDERE MARINE SERVICES PVT LTD | 40.81 | 0 | 0 | 100
2448 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Purulia-I Block (Part-F) of Purulia District under Purulia Division, PHE Dte. | 757/PD | 02/05/2022 | 45 | SUBODH PRAMANIK | 26.88 | 0 | 0 | 100
2449 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Purulia-I Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | 759/PD | 02/05/2022 | 45 | THE BUSINESS ENGINEERS INDIA | 27.18 | 0 | 0 | 100
2450 | PURULIA | Purulia Mechanical | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Construction of Rigbored Tubewell (200x165mm) by DTH method in different sourceless AWC at Dimdiha GP , Purulia -I Block under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 29/PMD | 17/01/2023 | 20 | SOUMITRA CHAKRABOTY | 25.35 | 0 | 0 | 100
2451 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Repairing of Boundary walls, Supplying and fitting of Mark -II Hand Pump along with concrete platform at the low yield Big Dia DTH Tubewell or Construction of concrete cover at the dry big dia DTH Tubewell ssinked at various Schools & AWCs of . Kashipur & Para Blocks under Purulia Division ,PHE,Dte. | 1737/PD | 04/12/2023 | 30 | SANJAY KUMAR NARSARIA | 14.03 | 0 | 0 | 65
2452 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Purulia-I, Para, Bandwan Block In Purulia District under Purulia Division, PHE Dte. , SM/10285 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Bandwan Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | 1250/PD | 30/08/2022 | 945 | PREMNATH MITRA | 197.98 | 0 | 0 | 100
2453 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Supplying and laying 250 mm dia MS pipe line and crossing Manbazar-Bandwan Road at khariduara OHR site of Zone-I of Manbazar II Block (Part) W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. (Tender No- 577/2022-23 of EE/PD) | BP-2022-23-422 | 11/11/2022 | 0 | RAKSHIT ENTERPRISE | 4.34 | 0 | 0 | 0
2454 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | New sinking of 200 mm dia river bed tubewell (Horizontal) at Kasabati river alongwith laying of 100 mm dia G.I. collecting line with other allied works for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 1060/PD | 08/07/2022 | 30 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 28.64 | 0 | 0 | 0
2455 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Construction of R.C.C. Elevated Reservoir, Capcaity 600 cum (Intze Type), Staging height 20 metre including Bypass arrangement & other allied works for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 1897/PD | 15/12/2022 | 270 | DEBAKI RANJAN SARKAR | 148.87 | 0 | 0 | 72
2456 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Reconditioning of filter Bed by Changing of Filter Media of WTP and Inside & Outside Painting Of WTP Structures & Intake Bridge at Mouza Ghat of Manbazar II Block (part) W/S Scheme of Purulia Sadar Sub-Division under Purulia Sadar Sub-Division, PHE Dte. | 871/PD | 30/06/2023 | 30 | ANUP KUMAR SAHA | 25.51 | 0 | 0 | 80
2457 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works of Manbazar W/S Scheme (Zone-I) of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 858/PD | 23/05/2022 | 100 | ROY CONSTRUCTION | 13.86 | 0 | 0 | 98
2458 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area Zone-I, Zone-II & Zone-V of Habitation- Manbazar II Block (part) Water Supply Scheme of Manbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-II, Part-I),(1. GP-Kumari, Habitation-Toparbad,Tilaboni,Susunia,Rangametya, Manikdi, Kumari, Kuchlifela, Dhanda, Boch ,Khariduara Alis Balarampur, 2) Dighi GP-Tamakhun, Jhariadi.) | 1393/PD | 01/09/2022 | 45 | ANUP KUMAR SAHA | 11.23 | 0 | 0 | 100
2459 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Supplying and laying 250 mm dia MS pipe line and crossing Manbazar-Bandwan Road at khariduara OHR site of Zone-I of Manbazar II Block (Part) W/S Scheme under Purulia Sadar Sub-Division, PHE Dte. | 438/PSD | 24/06/2022 | 10 | RAKSHIT ENTERPRISE | 4.39 | 0 | 0 | 100
2460 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Laying of distribution pipeline at different School & ICDS center for providing 21 nos Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Augmentation of Manbazar W/S Scheme of Manbazar-I Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 535/PD | 12/04/2023 | 60 | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 4.4 | 0 | 0 | 91
2461 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Material Requisition To Resource Division | 1016/PD | 05/07/2022 | 0 | Resource Division | 132.89 | 0 | 0 | 0
2462 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Material Requisition To Resource Division | 968/PD | 21/06/2022 | 0 | Resource Division | 120.16 | 0 | 0 | 0
2463 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Material Requisition To Resource Division | 241/PD | 20/02/2023 | 0 | Resource Division | 217.33 | 0 | 0 | 0
2464 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Material Requisition To Resource Division | 988/PD | 23/06/2022 | 0 | Resource Division | 0.47 | 0 | 0 | 0
2465 | PURULIA | Purulia Mechanical | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Material Requisition To Resource Division | 612/PMD | 01/06/2023 | 0 | Resource Division | 3.1 | 0 | 0 | 0
2466 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Manbazar W/S Scheme, Block- Manbazar-I) ) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 539/2021-22 of EE/PD) | BP-2022-23-118 | 16/07/2022 | 0 | RADIANT | 6.62 | 0 | 0 | 0
2467 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Regarding laying of water supply pipe line along PWD Land on (i) Manbazar_Bansa Road at ch.0.00 Kmp to 0.765 Km & Damda-Chakoltore-Dradi-Kenda-Manbazar Road at ch. 45.526 to 46.00 Kmp (ii) Indkuri-Manbazar Road at ch.0.00 Km to 0.850 Km, (iii) Sindri-Manbazar Road at ch. 17.00 Kmp to 17.80 Km, (iV) Manbazar-Bandwan-Kuilapal Road at ch. 0.00 kmp to 0.636 Km in respect of Augumentation of Manbazar Water suplly Scheme under JJM. | BP-2022-23-464 | 09/12/2022 | 0 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 146.74 | 0 | 0 | 0
2468 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-C : CHARKI, RAMNAGAR, KHALPARA, KENBEDYA, KASATORA (Part), MANBAZAR (Part) VILLAGE] (2nd Call) | 1049/PD | 08/07/2022 | 45 | EQUIPMENTS AND SPARES AGENCIES | 128.82 | 0 | 0 | 90
2469 | PURULIA | Purulia Mechanical | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Supply delivery and installation of Internal lighting and external lighting for Manbazar w/s scheme under PMD, PHE Dte. in the District of Purulia. | 251PMD | 06/03/2023 | 60 | MOON LIGHT HOUSE | 12.08 | 0 | 0 | 80
2470 | PURULIA | Purulia Mechanical | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Supply & installation of submersible pumping machinery at newly constructed River Bed Tubewell at Manbazar w/s(zone-1) scheme under PMD, PHE Dte. in the District of Purulia. | 252/PMD | 06/03/2023 | 60 | SANTANU BANERJEE | 48.12 | 0 | 0 | 57
2471 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Shifting and laying of DI rising main and HDPE distribution main pipeline from manbazar Bus stand to warehouse along manbazar- Bandwan road due to widening of PWD road at Manbazar-1 block under Manbazar-I Water Supply Scheme Under Purulia Division ,PHE Dte. | 667/PD | 17/05/2023 | 60 | ROY CONSTRUCTION | 15.28 | 0 | 0 | 75
2472 | PURULIA | Purulia Mechanical | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Supply, delivery and installation of Open well Submersible pumping machinery, MCC Panel with others electro-mechanical work at Manbazar Baludih for Augmentation of Manbazar PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | 970/PMD | 20/06/2024 | 60 | M/S D. PALIT & CO. | 11.74 | 0 | 0 | 0
2473 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-E : MANBAZAR (Part), BARKURI, BARTOR, BANDUR BERIYA & SHALPARA VILLAGE] | 836/PD | 19/05/2022 | 45 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 43.61 | 0 | 0 | 100
2474 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Balaance Work for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area Zone-III, & Zone-IV of Manbazar II Block (part) Water Supply Scheme ofManbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-II) | 1478/PD | 20/09/2022 | 45 | SADHAN GORAIN | 21.29 | 0 | 0 | 100
2475 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Repairing and Renovation of Pump house cum switch room including other allied works at Boludi OHR site in connection with Jal Jeevan Mission (JJM) for Augmentation of Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 377/PD | 15/03/2023 | 45 | ROY CONSTRUCTION | 2.19 | 0 | 0 | 100
2476 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Inter connection of 200 mm dia DI pipe with newly constructed CWR including Repairing and Renovation of Guard Room cum Store Room, Boundary wall with sanitary, plumbing & electrification work with other allied works at Boludi OHR site in connection with Jal Jeevan Mission (JJM) for Augmentation of Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 376/PD | 15/03/2023 | 45 | ROY CONSTRUCTION | 6.54 | 0 | 0 | 100
2477 | PURULIA | Purulia Mechanical | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Quotation for new connection | BP-23-24-220 | 05/12/2023 | 0 | WBSEDCL PURULIA | 7.5 | 0 | 0 | 0
2478 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-D : KASATORA (Part), MANBAZAR (Part) VILLAGE] | 835/PD | 19/05/2022 | 243 | NANIGOPAL DEY | 43.62 | 0 | 0 | 90
2479 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-A : MADHUPUR, BOLUDI & JHARBAGDA (Part) VILLAGE] | 1444/PD | 14/09/2022 | 742 | MACHINO TECHNO | 122.46 | 0 | 0 | 65
2480 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-I) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-B : MANBAZAR (Part), PATHARMOHORA VILLAGE] | 1445/PD | 14/09/2022 | 742 | MACHINO TECHNO | 123.8 | 0 | 0 | 64
2481 | PURULIA | Purulia Mechanical | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Supply, Delivery and installation 175kva voltage stabilizer for Augmentation of Manbazar w/s(Zone-1) scheme for under PMD, PHE Dte. in the District of Purulia. | 253/PMD | 06/03/2023 | 703 | SANTU MITRA | 18.25 | 0 | 0 | 59
2482 | PURULIA | Purulia Mechanical | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Manbazar w/s scheme under PMD, PHE Dte. in the District of Purulia. | 246/PMD | 03/03/2023 | 788 | NUPUR CHANDRA HALDER | 69.09 | 0 | 0 | 65
2483 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Manbazar (Harekristapur) river site for Augmentation of Manbazar W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | 542/PD | 12/04/2023 | 100 | BASANTA PARAMANIK | 14.05 | 0 | 0 | 70
2484 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line for Augmentation of (Zone-II) Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 869/PD | 23/05/2022 | 618 | ZAKIR HOSSIN MONDAL | 86.39 | 0 | 0 | 100
2485 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works of Manbazar W/S Scheme (Zone-II) of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 857/PD | 23/05/2022 | 496 | BABA LOKNATH LABOUR CONTRACT CO-OPERATIVE SOCEITY LTD. | 14.06 | 0 | 0 | 100
2486 | PURULIA | Purulia Division | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Repairing and Renovation of high & low lift pump house including other allied works at Harekristapur river site in connection with Jal Jeevan Mission (JJM) for Augmentation of Manbazar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 658/PD | 17/05/2023 | 45 | INDRAJIT SARKAR | 4.4 | 0 | 0 | 97
2487 | PURULIA | Purulia Mechanical | Augmentation of Manbazar PWSS for Providing Functional Household Tap Connection (FHTC) , SM/10719 | Augmentation | Augmentation of internal and external illumination arrangement at existing at Intake pump house, clear water, chemical house buiding, substation building,OHR site Chorination room at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. (2 nd Call) | 1171/PMD | 03/11/2023 | 456 | RABINDRA NATH KHAN | 34.4 | 0 | 0 | 35
2488 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Barabazar Block (Part-K) of Purulia District under Purulia Division, PHE Dte. | 468/PD | 24/03/2022 | 45 | MANATOSH SINGH | 23.56 | 0 | 0 | 0
2489 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Barabazar Block ) of Purulia District under Purulia Division, PHE Dte. | 44/PD | 09/01/2023 | 45 | THE BUSINESS ENGINEERS INDIA | 6.11 | 0 | 0 | 0
2490 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Barabazar Block (Part-Q) of Purulia District under Purulia Division, PHE Dte. | 57/PD | 10/01/2023 | 45 | ANUP KUMAR SAHA | 206.73 | 0 | 0 | 90
2491 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Barabazar Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | 470/PD | 24/03/2022 | 45 | PRAVAT SARKAR | 46.61 | 0 | 0 | 0
2492 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 3 nos AWC within Barabazar Block (Part-J) of Purulia District under Purulia Division, PHE Dte. | 469/PD | 24/03/2022 | 45 | KOUSHIK CHATTERJEE | 23.43 | 0 | 0 | 60
2493 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 1 no AWC within Barabazar Block (Part-N) of Purulia District under Purulia Division, PHE Dte. | 464/PD | 24/03/2022 | 45 | SAIBAL SARKAR | 7.87 | 0 | 0 | 0
2494 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 1 no AWC within Barabazar Block (Part-P) of Purulia District under Purulia Division, PHE Dte. | 463/PD | 24/03/2022 | 45 | ROY CONSTRUCTION | 7.66 | 0 | 0 | 0
2495 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Barabazar Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | 472/PD | 24/03/2022 | 45 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 47.13 | 0 | 0 | 0
2496 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Barabazar Block (Part-H) of Purulia District under Purulia Division, PHE Dte. | 471/PD | 24/03/2022 | 45 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 47.14 | 0 | 0 | 0
2497 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Barabazar Block (Part-M) of Purulia District under Purulia Division, PHE Dte. | 466/PD | 24/03/2022 | 45 | PRAVAT SARKAR | 15.54 | 0 | 0 | 0
2498 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 2 nos AWC within Barabazar Block (Part-L) of Purulia District under Purulia Division, PHE Dte. | 467/PD | 24/03/2022 | 45 | M/S ACHARJEE CONSTRUCTION | 15.77 | 0 | 0 | 100
2499 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 9 nos AWC within Barabazar Block (Part-F)of Purulia District under Purulia Division, PHE Dte. | 1855/PD | 13/12/2022 | 45 | SANTANU BANERJEE | 74.42 | 0 | 0 | 100
2500 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Barabazar Block (Part-A) of Purulia District under Purulia Division, PHE Dte.(Phase-I) | 1707/PD | 22/11/2022 | 45 | JYOTY SOLAR POWER | 91.77 | 0 | 0 | 0
2501 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 11 nos AWC within Barabazar Block (Part-B) of Purulia District under Purulia Division, PHE Dte.(Phase-II) | 1708/PD | 22/11/2022 | 45 | ABHIJIT MUKHERJEE | 91.69 | 0 | 0 | 100
2502 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Barabazar Block (Part-E) of Purulia District under Purulia Division, PHE Dte. | 982/PD | 22/06/2022 | 45 | ABHIJIT MUKHERJEE | 158.27 | 0 | 0 | 100
2503 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 6 nos AWC within Barabazar Block (Part-H) of Purulia District under Purulia Division, PHE Dte. (Tender No- 37/2022-23 of EE/PD) | BP-2022-23-230 | 29/08/2022 | 0 | ENVIRON ENERGY SERVICES PRIVATE LIMITED | 12.95 | 0 | 0 | 0
2504 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Withdrawing and relaying of DI pipes and Construction of shed for mobile laboratory vehicle & office vehicle at RWS Purulia sub Division office campus in connection with JJM under Purulia Division , PHE Dte. | 1799/PD | 08/12/2023 | 60 | KOUSHIK CHATTERJEE | 5 | 0 | 0 | 83
2505 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 25 nos AWC within Barabazar Block (Part-R) of Purulia District under Purulia Division, PHE Dte. | 1156/PD | 01/08/2022 | 45 | MANASH GHOSH | 197.96 | 0 | 0 | 100
2506 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 20 nos AWC within Barabazar Block (Part-D) of Purulia District under Purulia Division, PHE Dte. | 1154/PD | 01/08/2022 | 45 | GOENKA ENTERPRISE | 158.27 | 0 | 0 | 100
2507 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 1 nos AWC within Barabazar Block (Part-S), of Purulia District under Purulia Division, PHE Dte. | 1728/PD | 22/11/2022 | 45 | PRATIK SAHA | 8.27 | 0 | 0 | 100
2508 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to AWC(116 nos) under Barabazar Block In Purulia District under Purulia Division, PHE.Dte. , SM/10253 | Anganwadi | Water supply Tap Connection Arrangement for 1 no AWC within Barabazar Block (Part-O) of Purulia District under Purulia Division, PHE Dte. | 465/PD | 24/03/2022 | 45 | S PATHAK AND CO | 7.81 | 0 | 0 | 0
2509 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A , SM/14022 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 357/E/PD | 25/02/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 42.7 | 0 | 0 | 100
2510 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A , SM/14022 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC) and other allied works for Aug. Work of Raghunathpur Water Supply Scheme (German Assisted)(Zone-VII A) within Raghunathpur Sub Division under Purulia Division, PHE Dte. | 529/PD | 11/04/2023 | 60 | AQUEDUCT PLASTICS PVT LTD | 447.81 | 0 | 0 | 8
2511 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A , SM/14022 | Augmentation | Continuation work order for the work of Survey & Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 1025/PD | 06/01/2023 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5 | 0 | 0 | 100
2512 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A , SM/14022 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 1008/PD | 29/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
2513 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A , SM/14022 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 942/PD | 19/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
2514 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A , SM/14022 | Augmentation | Continuation work order for the work of Design work for Preparation of D.P.R. (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 1087/A/PD | 16/01/2023 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.15 | 0 | 0 | 100
2515 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A , SM/14022 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 931/A/PD | 13/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
2516 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A , SM/14022 | Augmentation | Continuation work order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS Raghunathpur W/S Project, (German Assisted) to be Augmented / Retrofitting under Purulia Division P.H.E. Dte. | 1002/PD | 23/12/2022 | 5 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.85 | 0 | 0 | 100
2517 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A , SM/14022 | Augmentation | Hiring of Ambassador Car / Bolero for the Assistant Engineer, Raghunathpur Sub-Divn, PHE Dte. (w.e.f. 01/06/2023 to 31/10/2023) | 220/RNP | 30/05/2023 | 153 | CHANDRA SHEKHAR KUNDU | 0.74 | 0 | 0 | 100
2518 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A , SM/14022 | Augmentation | Material Requisition To Resource Division | 79/PD | 17/01/2023 | 0 | Resource Division | 0.15 | 0 | 0 | 0
2519 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A , SM/14022 | Augmentation | Continuous work order for the work of Hiring of Ambassador Car / Bolero for the Assistant Engineer, Raghunathpur Sub-Divn, PHE Dte. (w.e.f. 01/11/2023 to 31/03/2024) | 466/RNP | 10/10/2023 | 152 | CHANDRA SHEKHAR KUNDU | 0.74 | 0 | 0 | 60
2520 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A , SM/14022 | Augmentation | Continuation Work Order for the Work of Hiring of Ambassador Car / Bolero for the Assistant Engineer, Raghunathpur Sub-Divn, PHE Dte. (w.e.f. 01/04/2024 to 31/08/2024) | 139/RNP | 12/03/2024 | 153 | CHANDRA SHEKHAR KUNDU | 0.74 | 0 | 0 | 0
2521 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII A , SM/14022 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir capacity 331 cum and other allied works under Raghunathpur W/S Scheme (Zone-VII-A) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 2325/PD | 31/12/2024 | 381 | NANIGOPAL DEY | 13.17 | 0 | 0 | 0
2522 | PURULIA | Purulia Division | Surface water based water supply scheme for AUGMENTATION OF Hutmura PWSS , SM/15336 | Augmentation | Repairing, renovation of Boundary Wall at WTP & OHR site of Hutmura W/S Scheme Under Purulia Sadar Sub-Division, Purulia Division, P.H.E. Dte. | 936/PD | 19/07/2023 | 30 | M/S. DESTINY CONSTRUCTION | 9.67 | 0 | 0 | 100
2523 | PURULIA | Purulia Mechanical | Surface water based water supply scheme for AUGMENTATION OF Hutmura PWSS , SM/15336 | Augmentation | Priming arrangement for two nos centrifugal pump and two back wash pump and other allied works at Hutmura (OHR) Site water supply scheme under Purulia Mechanical Division, PHE, Dte. | 994/PMD | 21/06/2024 | 60 | SUBRATA DUTTA | 1.06 | 0 | 0 | 100
2524 | PURULIA | Purulia Division | Surface water based water supply scheme for AUGMENTATION OF Hutmura PWSS , SM/15336 | Augmentation | Survey, Investigation, Planning, Designing (aesthetically), Construction and Commissioning of a Conventional WATER TREATMENT PLANT and rising main of capacity 650 KLD as per BIS/CPHEEO Manual consisting of all Civil, Mechanical and Electrical works (excluding supply and installation of Chlorination arrangements, SCADA, Clear Water Pumps and allied works) including necessary hydraulic testing, structural testing equipment testing, trial run for a period of 3 months, etc. complete as directed by Engineer-in-charge (turn-key job). Cost includes submission of detailed design with drawing (both soft and hard copies) showing all necessary arrangements, structural & hydraulic detail etc. for Augmentation of Hutumura W/S Scheme for source augmentation | 1339/PD | 08/09/2023 | 730 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 248.15 | 0 | 0 | 40
2525 | PURULIA | Purulia Division | Surface water based water supply scheme for AUGMENTATION OF Hutmura PWSS , SM/15336 | Augmentation | Repairing of Baffle Floculator ,Tube Settlor and Construction of Platform of Preasure Filter and Construction of Boundary wall and Repairing of Old Staff Room and other allied works under Hutmura & Bandwan W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte . | 1364/PD | 25/07/2024 | 240 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 91.07 | 0 | 0 | 50
2526 | PURULIA | Purulia Mechanical | Surface water based water supply scheme for AUGMENTATION OF Hutmura PWSS , SM/15336 | Augmentation | Supply, Delivery and installation of submersible pumping machineries, flowmeter, backwash pump, chlorination system, external lighting arrangement with other allied works in connection with new WTP for augmentation of Hutmura(Intake side & new CWR Zone ) w/s scheme under PMD, PHE Dte. in the District of Purulia. | 1694/PMD | 06/12/2024 | 90 | DEY ENTERPRISE, HOWRAH | 55.15 | 0 | 0 | 0
2527 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B , SM/16379 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone VII B under PMD PHE Dte. District Purulia. | 450/PMD | 20/04/2023 | 30 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 21.59 | 0 | 0 | 65
2528 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B , SM/16379 | Augmentation | Material Requisition To Resource Division | 76/PD | 17/01/2023 | 0 | Resource Division | 65.11 | 0 | 0 | 0
2529 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B , SM/16379 | Augmentation | Laying Distribution System including providing Functional Household Tap Connection (FHTC) and other allied works for Aug. Work of Raghunathpur Water Supply Scheme (German Assisted)(Zone-VII B) within Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) | 530/PD | 11/04/2023 | 60 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 280.39 | 0 | 0 | 48
2530 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B , SM/16379 | Augmentation | Yard lighting and internal illumination arrangement at Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B under Purulia Mechanical Division, PHE. Dte. | 1443/PMD | 01/10/2024 | 60 | M/S A.D. CONCERN | 3.87 | 0 | 0 | 0
2531 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B , SM/16379 | Augmentation | For new connection of Augmentation of Raghunathpur zone VII B | BP-23-24-278 | 01/02/2024 | 0 | WBSEDCL PURULIA | 0.26 | 0 | 0 | 0
2532 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B , SM/16379 | Augmentation | Laying of Distribution System including providing Functional Household Tap Connection (FHTC), Construction of 350 cum OHR and staging height of 20 mtr. and other other allied works for Aug. Work of Raghunathpur Water Supply Scheme (German Assisted)(Zone - VII B) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-A | 583/PD | 20/04/2023 | 270 | PRAVAT SARKAR | 321.22 | 0 | 0 | 78
2533 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B , SM/16379 | Augmentation | Laying Distribution System of pipe line from Borsolia culvert to Sagarka more & Danduya Village including providing House Hold Tap Connection (FHTC)other allied works for Aug. work of Raghunathpur Water Supply Scheme (German Assisted) (Zone -VII B) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. Part-A | 1708/PD | 05/09/2024 | 483 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 51.67 | 0 | 0 | 80
2534 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B , SM/16379 | Augmentation | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-VII-B) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-B) | 1875/PD | 01/10/2024 | 45 | EFFLUENT & WATER TRETMENT ENGINEERS PVT LTD | 21.26 | 0 | 0 | 0
2535 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B , SM/16379 | Augmentation | Supply, delivery & Installation of Submersible Pumping Machinery and other works, at OHR site- Ketlapur, Zone-VII B (T/W-IV) under Raghunathpur water supply project, PHE Dte. | 620/PMD | 22/04/2025 | 20 | ANUP KUMAR SAHA | 0.88 | 0 | 0 | 0
2536 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B , SM/16379 | Augmentation | Supply, delivery and laying of cable and other works, at OHR site Ketlapur of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 857/PMD | 03/06/2024 | 10 | ANUP KUMAR SAHA | 0.64 | 0 | 0 | 95
2537 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 196 nos. under Puncha & Joypur Block in Purulia District in Purulia Disision. , SM/10228 | School | Water supply Tap Connection Arrangement for 40 nos School upto 200 Students within Puncha Block (Part -C) of Purulia District under Purulia Division, PHE Dte. | 577/PD | 12/04/2022 | 45 | B.K. ENTERPRI SE | 168.51 | 0 | 0 | 0
2538 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 196 nos. under Puncha & Joypur Block in Purulia District in Purulia Disision. , SM/10228 | School | FHTC Connetion for School Puncha W/s Scheme. |  | 18/07/2022 | 0 | B.K. ENTERPRI SE | 115 | 0 | 0 | 0
2539 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 196 nos. under Puncha & Joypur Block in Purulia District in Purulia Disision. , SM/10228 | School | Water supply Tap Connection Arrangement for 23 nos School upto 200 Students within Joypur Block (Part -B) and 25 nos School upto 200 Students within Puncha Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | 580/PD | 12/04/2022 | 45 | B.K. ENTERPRI SE | 202.23 | 0 | 0 | 0
2540 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 196 nos. under Puncha & Joypur Block in Purulia District in Purulia Disision. , SM/10228 | School | Water supply Tap Connection Arrangement for Sourceless 3 nos School upto 200 Students , 1 nos School for 201-500 Students within BALARAMPUR Block ,4 nos School upto 200 Students within BANDWAN Block, 8 nos School upto 200 Students,2 no School above 800 within BARABAZAR Block,16 nos School upto 200 Students within MANBAZAR-I Block, 2 nos School upto 200 Students within MANBAZAR-II Block, 1 nos School upto 200 Students, 2 nos School for 501-800 Students within PUNCHA Block , of Purulia District under Purulia Division, PHE Dte. | 671/PD | 25/04/2022 | 45 | ANUP KUMAR SAHA | 163.9 | 0 | 0 | 0
2541 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 196 nos. under Puncha & Joypur Block in Purulia District in Purulia Disision. , SM/10228 | School | Water supply Tap Connection Arrangement for 47 nos School upto 200 Students, 6 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Puncha Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | 581/PD | 12/04/2022 | 45 | M DHARA & BROTHERS | 231.81 | 0 | 0 | 100
2542 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 196 nos. under Puncha & Joypur Block in Purulia District in Purulia Disision. , SM/10228 | School | Water supply Tap Connection Arrangement for 47 nos School upto 200 Students, 4 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Joypur Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | 675/PD | 25/04/2022 | 45 | EQUIPMENTS AND SPARES AGENCIES | 223.53 | 0 | 0 | 100
2543 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 196 nos. under Puncha & Joypur Block in Purulia District in Purulia Disision. , SM/10228 | School | Water supply Tap Connection Arrangement for 2 nos AWC within Joypur Block (Part-I) of Purulia District under Purulia Division, PHE Dte. | 725/PD | 02/05/2022 | 45 | HUSSAIN CONSTRUCTION | 15.68 | 0 | 0 | 100
2544 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB , SM/18250 | Augmentation | Material Requisition To Resource Division | 77/PD | 17/01/2023 | 0 | Resource Division | 4.22 | 0 | 0 | 0
2545 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB , SM/18250 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone II B under PMD PHE Dte. District Purulia. | 802/PMD | 12/07/2023 | 30 | A G ENTERPRISE | 21.84 | 0 | 0 | 85
2546 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB , SM/18250 | Augmentation | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur W/S (Zone-VI-B) at Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB at Raghunathpur-II Block of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1382/PD | 25/07/2024 | 90 | SOUVIK MANDAL | 92.92 | 0 | 0 | 0
2547 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB , SM/18250 | Augmentation | Construction of Substation Building at Boosting station (Seleta mouza) under Raghunathpur water supply scheme and Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1402/PD | 25/07/2024 | 526 | SUBRATA SINGHADEO | 40.98 | 0 | 0 | 75
2548 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB , SM/18250 | Augmentation | Construction of Guard Room with toilet block at Zone-IIA under Raghunathpur W/S Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 2100/PD | 05/12/2024 | 60 | PURNA CHANDRA TEWARI | 6.42 | 0 | 0 | 0
2549 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB , SM/18250 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, hi-lifting boundary wall and other allied works under Raghunathpur W/S Scheme (Zone-II-A) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 2190/PD | 13/12/2024 | 90 | DILIP MISHRA | 12.66 | 0 | 0 | 0
2550 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB , SM/18250 | Augmentation | Construction of Guard Room with toilet block at Zone-IIB under Raghunathpur W/S Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 2101/PD | 05/12/2024 | 60 | CHANCHAL MISHRA | 6.43 | 0 | 0 | 0
2551 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB , SM/18250 | Augmentation | Construction of 1 No. Secondary Pannel cum meter Room at Lakhanpur W.T.P. near Intake Bridge under Raghunathpur W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 883/PD | 03/07/2023 | 30 | CHANDAN CHATTERJEE | 6.78 | 0 | 0 | 100
2552 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB , SM/18250 | Augmentation | Construction of Switch Room Cum Chlorin Room at Zone-II-B (Khajura) OHR Site of Raghunathpur W/S Scheme (German Project) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1730/PD | 04/12/2023 | 180 | MAA TARA CONSTRUCTION | 4.86 | 0 | 0 | 100
2553 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB , SM/18250 | Augmentation | NEW CONNECTION FOR AUGMENTATION OF RAGHUNATHPUR ZONE IIB | BP-23-24-248 | 04/01/2024 | 0 | WBSEDCL PURULIA | 2.87 | 0 | 0 | 0
2554 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB , SM/18250 | Augmentation | Construction of Rcc Over Head Reservoir (Torch type with solid raft)of capacity 150 cum and staging heght 20 mtr and laying of Distribution System including pipe carrying structure all complete including providing House Hold Tap Connection (FHTC)and other alliedworks for Aug. work of Raghunathpur Watersupply scheme (German Assisted) (Zone-II B) within Raghunathpur Sub-Division under Purulia Division,PHE Dte.(SL-4) | 1337/PD | 08/09/2023 | 755 | MANIRUL ISLAM SK | 261.26 | 0 | 0 | 63
2555 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB , SM/18250 | Augmentation | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-II B) at Raghunathpur-I Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 2299/PD | 31/12/2024 | 181 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 78.64 | 0 | 0 | 0
2556 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB , SM/18250 | Augmentation | Addition of column pipe including supply along with allied works, at OHR site-II B, Khajura under Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 635/PMD | 24/04/2025 | 15 | ANUP KUMAR SAHA | 0.37 | 0 | 0 | 0
2557 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB , SM/18250 | Augmentation | Laying of Distribution System including pipe carrying structure all complete including providing House Hold Tap Connection (FHTC), and other allied works for Aug.work of Raghunathpur Water Supply Scheme (German Assisted) (Zone-IIA)within Raghunathpur Sub Division under Purulia Division, PHE Dte.(SL-3) | 1020/PD | 01/08/2023 | 669 | ANUP KUMAR SAHA | 401.92 | 0 | 0 | 100
2558 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB , SM/18250 | Augmentation | Earthing arrangement and other works, at OHR site Uporkhajura of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 899/PMD | 10/06/2024 | 15 | ANUP KUMAR SAHA | 0.5 | 0 | 0 | 90
2559 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IIA & IIB , SM/18250 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Uporkhajura (Tube well-II), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 1027/PMD | 25/06/2024 | 15 | ANUP KUMAR SAHA | 0.81 | 0 | 0 | 95
2560 | PURULIA | Purulia Mechanical | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I) , SM/18333 | New | Hiring of maxi cab (non air conditioned) Bharat Stage-III Diesel/LPG/CNG driver engine including driver for official use of the Executive Engineer, Purulia Mechanical Division PHE, Dte. (01/10/24 to 31/03/25) | 400/PMSD(W/S) | 23/09/2024 | 182 | TAPAN KUMAR DEY | 0.86 | 0 | 0 | 0
2561 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I) , SM/18333 | New | Continuation work order for Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/ TATA indigo eCS Bharat Stage-IV/ Swift tour Bharat stage-IV or as similar model for the official uses under Purulia Division, PHE Dte. (w.e.f.01.09.2023 to 31.08.2024.) | 477/A/PR | 31/08/2023 | 366 | ANUP KUMAR SAHA | 1.76 | 0 | 0 | 0
2562 | PURULIA | Purulia Division | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I) , SM/18333 | New | Construction of Scada Room and Chlorine Room at Balarampur (Zone - III, IV & V) Of Purulia Pipe Water Supply Scheme(Southern Sector) within Purulia District under Purulia Division, PHE Dte. | 1086/PD | 17/06/2025 | 120 | RANI SATI CONSTRUCTION | 43.06 | 0 | 0 | 0
2563 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction and Commissioning of RCC Over Head Reservoirs (Torch type with solid raft) of capacity 300 CUM andstaging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) month at Zone-I of Purulia-2 block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-5) | 1427/PD | 29/09/2023 | 270 | HANNAN BUILDERS PRIVATE LIMITED | 441.37 | 0 | 0 | 0
2564 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction and Commissioning of RCC Over Head Reservoir ( Torch type with solid raft ) of capacity 500 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe Line and providing FHTC including other allied works & Operation & Maintenance of Distribution , Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six month (36) for Zone-V Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-9) | 1558/PD | 18/10/2023 | 270 | M/S TARUN KUMAR PATRA | 869.94 | 0 | 0 | 0
2565 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Kalipur mouza (Zone-I) Under Purulia Divn PHE DTE. | 1568/PD | 26/10/2023 | 45 | PRADIPTA CHOUDHURY | 1.3 | 0 | 0 | 0
2566 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line including FHTC and other allied work for Zone-III of Purulia-I block for Simulbera mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | 1713/PD | 04/12/2023 | 60 | THE STAR & CO. | 41.68 | 0 | 0 | 0
2567 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -H , Mouza - Nabaghanadi alias Patharbad&Khayerbasia Chak] | 1727/PD | 04/12/2023 | 60 | IKBAL CONSTRUCTION | 19.32 | 0 | 0 | 0
2568 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - VIII of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 145 mtr.) | 1774/PD | 08/12/2023 | 60 | IKBAL CONSTRUCTION | 19.41 | 0 | 0 | 0
2569 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Dulmi mouza under Purulia Water Supply Scheme ( Northern Sector) Under Purulia Division , PHE Dte. | 1699/PD | 30/11/2023 | 60 | SUNNY ELECTRIC CO | 72.3 | 0 | 0 | 0
2570 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Material Requisition To Resource Division | 1127/PD | 17/08/2023 | 0 | Resource Division | 19846.99 | 0 | 0 | 0
2571 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of boundary wall at Zone VI H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | 1146/PD | 17/08/2023 | 30 | HUSSAIN CONSTRUCTION | 21.51 | 0 | 0 | 70
2572 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch Type With solid raft) of capacity 150 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Value & FHTC for period of thirty six (36) month at Zone- VII of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector ) under Purulia Divn. PHE Dte. (SL-16) | 1418/PD | 29/09/2023 | 540 | KOUSHIK CHATTERJEE | 274.47 | 0 | 0 | 70
2573 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 250 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty-six (36) months at Zone-IV of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Division, PHE Dte. (2nd Call)(SL-5) | 1420/PD | 29/09/2023 | 675 | MS D.PALIT AND CO. | 373.13 | 0 | 0 | 50
2574 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction and Commissioning of RCC Over Head Reservoirs (Torch type with solid raft) of capacity 200 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) months for Zone-XII of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (SL-9) | 1425/PD | 29/09/2023 | 703 | SUJIT SAHANA | 274.06 | 0 | 0 | 22
2575 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012), Laying of Distribution Pipe line & providing Functional Household Tap Connection (FHTC) including other allied works, for Zone- I of Santuri Block under Purulia Piped Water Supply Scheme (Northern Zone ) under Purulia Divn. PHE Dte. [Part - A, Mouza - Mohanpur] | 697/PD | 22/05/2023 | 680 | KHITISH CHANDRA PATHAK | 93.94 | 0 | 0 | 40
2576 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Maguria mouza (Zone-I) Under Purulia Divn PHE DTE. | 1515/PD | 16/10/2023 | 45 | SOUVIK MANDAL | 45.44 | 0 | 0 | 0
2577 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line including providing FHTC and other allied work for Zone-III of Purulia-I block for Kukurgarya mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | 1715/PD | 04/12/2023 | 724 | HIRAK KUMAR SAO | 72.48 | 0 | 0 | 65
2578 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) with allied works for purulia water supply scheme.(Location:-Block-Purulia -I, Zone-III) for Northern Zone. | 1717/PD | 04/12/2023 | 270 | M/S RAJ KUMAR KHAN | 96.67 | 0 | 0 | 30
2579 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Raibandh Mouza (Zone-I) Under Purulia Divn PHE DTE. | 1561/PD | 18/10/2023 | 45 | CHATTERJEE CONSTRUCTION | 12.16 | 0 | 0 | 0
2580 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Dulmi Mouza (Zone-I) Under Purulia Divn PHE DTE. | 1604/PD | 01/11/2023 | 45 | CHANCHAL MISHRA | 8.03 | 0 | 0 | 0
2581 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Simulia mouza (Zone-I) Under Purulia Divn PHE DTE. | 1600/PD | 31/10/2023 | 45 | KRISHNA CONSTRUCTION AND ORDER SUPPLIER | 31.76 | 0 | 0 | 0
2582 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line including providing FHTC and other allied work for Zone-III of Purulia-I block for Ghagharjuri mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | 1716/PD | 04/12/2023 | 100 | BALAJI UDDYOG | 93.8 | 0 | 0 | 0
2583 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Chakda mouza (Zone-I) Under Purulia Divn PHE DTE. | 1562/PD | 18/10/2023 | 45 | M DHARA & BROTHERS | 38.95 | 0 | 0 | 0
2584 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - VI of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | 1788/PD | 08/12/2023 | 60 | SOUVIK MANDAL | 20.95 | 0 | 0 | 80
2585 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012) including providing FHTC including other allied work allied works for purulia water supply scheme.(Northern Sector ) at Purulia -I Block (Zone-IV) for Hulka Mouza under Purulia Division PHE Dte. | 1794/PD | 08/12/2023 | 480 | SUBRATA MAHAPATRA | 82.06 | 0 | 0 | 65
2586 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line and other allied work for Zone-VIII of Purulia-I block for Rudra mouza (part) under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division ,PHE Dte. | 1826/PD | 12/12/2023 | 60 | BARI ENTERPRISE | 29.81 | 0 | 0 | 0
2587 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 200 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012)with allied works for purulia water supply scheme.(Location:-Block-Purulia-1, Zone-VI) for Northern Zone | 1792/PD | 08/12/2023 | 270 | SADHAN GORAIN | 74.45 | 0 | 0 | 0
2588 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line including providing FHTC and other allied work for Zone-III of Purulia-I block for Ketuabera mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | 1714/PD | 04/12/2023 | 60 | M/S SB CONSTRUCTION | 47.7 | 0 | 0 | 0
2589 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - IV of Santuri Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -G , Mouza - Talberya (20%)] | 1726/PD | 04/12/2023 | 60 | VINCI CONSTRUCTION | 12.23 | 0 | 0 | 60
2590 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC), including other allied work for Zone - II of Neturia Block under Purulia Pipe Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. [Part -C, Mouza - Gopalpur, Mahukura] | 1807/PD | 08/12/2023 | 45 | S. S. ENTERPRISE | 30.88 | 0 | 0 | 64
2591 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - XI of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 188 mtr.) | 1777/PD | 08/12/2023 | 60 | BHUTNATH MISHRA | 23.66 | 0 | 0 | 100
2592 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - I of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | 1783/PD | 08/12/2023 | 756 | SUBRATA SINGHADEO | 20.81 | 0 | 0 | 65
2593 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Belguma mouza (Zone-I) Under Purulia Divn PHE DTE. | 1514/PD | 16/10/2023 | 45 | SEKH ABBAS | 28.09 | 0 | 0 | 0
2594 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Golbera mouza (Zone-VII) Under Purulia Divn PHE DTE | 1795/PD | 08/12/2023 | 45 | SEKH ABBAS | 19.55 | 0 | 0 | 0
2595 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Zone )at Purulia I Block (Zone-V) for Mahalitora mouza Under Purulia Divn PHE DTE. | 1867/PD | 21/12/2023 | 60 | BHAGABANDAS KUMAR | 15.2 | 0 | 0 | 0
2596 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Zone )at Purulia I Block (Zone-VIII) for Rudra mouza Under Purulia Divn PHE DTE. | 1827/PD | 12/12/2023 | 60 | SUSANTA KR DUTTA | 24.58 | 0 | 0 | 0
2597 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012)with allied works for purulia water supply scheme.(Location:-Block-Purulia-1 , Zone-V ) for Northern Zone. | 1828/PD | 12/12/2023 | 270 | M/S SB CONSTRUCTION | 70.03 | 0 | 0 | 60
2598 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line and other allied work for Zone-I of Purulia-I block for Maguria Mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division, PHE Dte. | 51/PD | 09/01/2024 | 60 | ANUP KUMAR SAHA | 148.36 | 0 | 0 | 0
2599 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Manbazar I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 471/PMD | 14/03/2024 | 365 | SUNRISE ENGINEERING CORPORATION | 19.89 | 0 | 0 | 0
2600 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Joypur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 496/PMD | 15/03/2024 | 365 | DEY ENTERPRISE, HOWRAH | 474.14 | 0 | 0 | 0
2601 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Hura Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 493/PMD | 15/03/2024 | 365 | A G ENTERPRISE | 413.21 | 0 | 0 | 0
2602 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Manbazar I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 498/PMD | 15/03/2024 | 365 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 103.28 | 0 | 0 | 0
2603 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Purulia I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 502/PMD | 15/03/2024 | 365 | AHALYA ENGINEERING WORKS | 206.45 | 0 | 0 | 0
2604 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Jhalda I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 1669/PMD | 05/12/2024 | 365 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 3.32 | 0 | 0 | 0
2605 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Jhalda II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 1670/PMD | 05/12/2024 | 365 | SEN BROTHERS | 2.77 | 0 | 0 | 0
2606 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Raghunathpur I Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | 1050/PMD | 28/06/2024 | 365 | BISHWANATH NANDI | 22.86 | 0 | 0 | 0
2607 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Santuri Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | 1052/PMD | 28/06/2024 | 365 | NUPUR CHANDRA HALDER | 22.16 | 0 | 0 | 0
2608 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Jhalda I Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | 1018/PMD | 25/06/2024 | 365 | TAPAN KUMAR DEY | 53.82 | 0 | 0 | 0
2609 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Jhalda II Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | 1019/PMD | 25/06/2024 | 365 | JAL PRAVAHIKA PVT. LTD | 41.16 | 0 | 0 | 0
2610 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Kashipur Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | 1021/PMD | 25/06/2024 | 365 | DEBJYOTI BASU | 53.82 | 0 | 0 | 0
2611 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Manbazar I Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | 1022/PMD | 25/06/2024 | 365 | SANTU MITRA | 12.66 | 0 | 0 | 0
2612 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Para Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | 1024/PMD | 25/06/2024 | 365 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 56.98 | 0 | 0 | 0
2613 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Jhalda-I ,Zone-XV under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 503/PD | 16/03/2024 | 60 | MANTAJ ANSARI | 25.17 | 0 | 0 | 0
2614 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Joypur Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | 1020/PMD | 25/06/2024 | 365 | A G ENTERPRISE | 34.82 | 0 | 0 | 0
2615 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Purulia II Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | 1049/PMD | 28/06/2024 | 365 | SAIBAL SARKAR | 47.49 | 0 | 0 | 0
2616 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Purulia II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 945/PMD | 19/06/2024 | 365 | ASHOKE ADHIKARY | 39.78 | 0 | 0 | 0
2617 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Neturia Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | 1023/PMD | 25/06/2024 | 365 | SEN BROTHERS | 6.33 | 0 | 0 | 0
2618 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Jhalda I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 941/PMD | 19/06/2024 | 365 | WEST BENGAL ENGINEERING CO | 568.2 | 0 | 0 | 0
2619 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Purulia-II ,Zone-I under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | 356/PD | 04/03/2024 | 60 | CHOUDHURY STONE CRUSHING | 25.14 | 0 | 0 | 85
2620 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Santuri Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 506/PMD | 15/03/2024 | 365 | PREMNATH MITRA | 206.89 | 0 | 0 | 0
2621 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Jhalda I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 467/PMD | 14/03/2024 | 365 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 59.66 | 0 | 0 | 0
2622 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Joypur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 469/PMD | 14/03/2024 | 365 | SEN BROTHERS | 19.88 | 0 | 0 | 0
2623 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Jhalda-I,Zone-XIV under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division,PHE Dte. | 348/PD | 04/03/2024 | 60 | UTTAM KUMAR DUTTA | 19.44 | 0 | 0 | 0
2624 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Hura Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 466/PMD | 14/03/2024 | 365 | DEBJYOTI BASU | 59.65 | 0 | 0 | 0
2625 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Kashipur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 470/PMD | 14/03/2024 | 365 | NUPUR CHANDRA HALDER | 69.62 | 0 | 0 | 0
2626 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Puncha Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 474/PMD | 14/03/2024 | 365 | SANTU MITRA | 9.94 | 0 | 0 | 0
2627 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Raghunathpur II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 477/PMD | 14/03/2024 | 365 | PINTU DEY | 19.89 | 0 | 0 | 0
2628 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Jhalda II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 495/PMD | 15/03/2024 | 365 | EASTERN INDIA SALES AND SERVICE | 413.27 | 0 | 0 | 0
2629 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Neturia Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 499/PMD | 15/03/2024 | 365 | JAL PRAVAHIKA PVT. LTD | 51.65 | 0 | 0 | 0
2630 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Puncha Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 501/PMD | 15/03/2024 | 365 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 309.93 | 0 | 0 | 0
2631 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Disinfection Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Jhalda II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 468/PMD | 14/03/2024 | 365 | DAS ENTERPRISE | 49.68 | 0 | 0 | 0
2632 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Neturia Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 472/PMD | 14/03/2024 | 365 | M/S A.D. CONCERN | 9.94 | 0 | 0 | 0
2633 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Raghunathpur I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 476/PMD | 14/03/2024 | 365 | M/S D. PALIT & CO. | 19.89 | 0 | 0 | 0
2634 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Para Block at PWSS SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 473/PMD | 14/03/2024 | 365 | SAIBAL SARKAR | 39.78 | 0 | 0 | 0
2635 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Purulia I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 475/PMD | 14/03/2024 | 365 | JAL PRAVAHIKA PVT. LTD | 39.76 | 0 | 0 | 0
2636 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Raghunathpur I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 504/PMD | 15/03/2024 | 365 | TAPAN KUMAR DEY | 257.9 | 0 | 0 | 0
2637 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Raghunathpur II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 505/PMD | 15/03/2024 | 365 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 154.78 | 0 | 0 | 0
2638 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Jhalda-II,Zone-III under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 349/PD | 04/03/2024 | 60 | SUMIT KUMAR MITRA | 19.31 | 0 | 0 | 60
2639 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Purulia-II ,Zone-VI under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | 359/PD | 04/03/2024 | 60 | SAZID HOSSEN ANSARI | 25.1 | 0 | 0 | 0
2640 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Santuri Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 478/PMD | 14/03/2024 | 365 | COMBINE ENTERPRISES | 29.84 | 0 | 0 | 0
2641 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Puncha ,Zone-II under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(Under Northern Sector W/S Scheme) | 502/PD | 16/03/2024 | 60 | SUMIT KUMAR MITRA | 23.95 | 0 | 0 | 0
2642 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector ) at Purulia-I Block(Zone-VII) For Kalidasdi Mouza under Purulia Division. PHE Dte. | 492/PD | 16/03/2024 | 60 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 34.47 | 0 | 0 | 0
2643 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block(Zone-II) For Bhalumara Mouza under Purulia Division. PHE Dte. | 490/PD | 16/03/2024 | 165 | RAHIBUDDIN MONDAL | 23.46 | 0 | 0 | 50
2644 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Jhalda-I ,Zone-II under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. (Under Northern Sector W/S Scheme) | 498/PD | 16/03/2024 | 60 | SEKH ABBAS | 25.08 | 0 | 0 | 0
2645 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block(Zone-VII) For Shyamdasdi Alias shyampur Mouza under Purulia Division. PHE Dte. | 530/PD | 16/03/2024 | 60 | M/S ACHARJEE CONSTRUCTION | 33.22 | 0 | 0 | 0
2646 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement and Illumination arrangement for OHR sites, at Para Block at PWSS SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 943/PMD | 19/06/2024 | 365 | ORIENTAL ENGINEERING CO. | 723.12 | 0 | 0 | 0
2647 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Puncha Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | 1025/PMD | 25/06/2024 | 365 | SUBRATA DUTTA | 22.15 | 0 | 0 | 0
2648 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Purulia II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 1676/PMD | 05/12/2024 | 365 | ASHOKE ADHIKARY | 2.22 | 0 | 0 | 0
2649 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Raghunathpur II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 1678/PPMD | 05/12/2024 | 365 | PINTU DEY | 1.11 | 0 | 0 | 0
2650 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement and Illumination arrangement for OHR sites, at Purulia II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 944/PMD | 19/06/2024 | 365 | MAHADEV ENTERPRISE | 561.07 | 0 | 0 | 0
2651 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line and Providing FHTC including other allied work for Nadiyara mouza ( Zone-V Part-B) Northern Zone at Purulia-I Block under Purulia Water Supply Scheme Under Purulia Division ,PHE Dte. | 1136/PD | 18/06/2024 | 60 | NANIGOPAL DEY | 74.58 | 0 | 0 | 0
2652 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Purulia I Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | 1048/PMD | 28/06/2024 | 365 | ASHOKE ADHIKARY | 25.32 | 0 | 0 | 0
2653 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Raghunathpur II Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | 1051/PMD | 28/06/2024 | 365 | S. PATHAK & CO. | 15.82 | 0 | 0 | 0
2654 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Para and Neturia Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 1674/PMD | 05/12/2024 | 365 | M/S A.D. CONCERN | 2.77 | 0 | 0 | 0
2655 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Purulia I and Puncha Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 1675/PMD | 05/12/2024 | 365 | SANTU MITRA | 2.77 | 0 | 0 | 0
2656 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Raghunathpur I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 1677/PMD | 05/12/2024 | 365 | M/S D. PALIT & CO. | 1.11 | 0 | 0 | 0
2657 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Santuri Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 1679/PMD | 05/12/2024 | 365 | COMBINE ENTERPRISES | 1.66 | 0 | 0 | 0
2658 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Joypur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 1671/PMD | 05/12/2024 | 365 | SEN BROTHERS | 1.11 | 0 | 0 | 0
2659 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Internal illumination and outdoor lighting arrangement and other allied works for Augmentation of Balitora Water Supply Scheme under Purulia Mechanical Division. PHE. Dte. | 1292/PMD | 30/08/2024 | 60 | PREMNATH MITRA | 7.83 | 0 | 0 | 2
2660 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Hura Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 1668/PMD | 05/12/2024 | 365 | NUPUR CHANDRA HALDER | 3.31 | 0 | 0 | 0
2661 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery & Installation of Disinfection Arrangement and Illumination arrangement for OHR sites, at Kashipur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 942/PMD | 19/06/2024 | 365 | CONCORD ENGINEERING | 516.53 | 0 | 0 | 0
2662 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Kashipur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 1672/PMD | 05/12/2024 | 365 | NUPUR CHANDRA HALDER | 3.88 | 0 | 0 | 0
2663 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of boundary wall at Zone VII H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | 1147/PD | 17/08/2023 | 30 | GANGULY ENTERPRISES | 16.72 | 0 | 0 | 100
2664 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of boundary wall at Zone V H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | 1145/PD | 17/08/2023 | 30 | SUMIT KUMAR MITRA | 15.1 | 0 | 0 | 100
2665 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of boundary wall at Zone III H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | 1143/PD | 17/08/2023 | 30 | BABA LOKNATH ENTERPRISE | 18.56 | 0 | 0 | 100
2666 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of boundary wall at Zone II H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | 1142/PD | 17/08/2023 | 30 | SANTOSH KUMAR | 15.35 | 0 | 0 | 100
2667 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewell at Zone - V of Raghunathpur-II Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 165 mtr.) | 1725/PD | 04/12/2023 | 60 | KRISHNA CONSTRUCTION AND ORDER SUPPLIER | 21.47 | 0 | 0 | 100
2668 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewell at Zone - I of Raghunathpur-II Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 145 mtr.) | 1721/PD | 04/12/2023 | 60 | S.PATHAK & CO. | 19.47 | 0 | 0 | 100
2669 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewell at Zone - IV of Raghunathpur-II Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 115 mtr.) | 1724/PD | 04/12/2023 | 60 | MOUSUMI BANERJEE | 16.44 | 0 | 0 | 75
2670 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - II of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 170 mtr.) | 1768/PD | 08/12/2023 | 60 | CHAIL CONSTRUCTION | 21.95 | 0 | 0 | 100
2671 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - I of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 165 mtr.) | 1767/PD | 08/12/2023 | 456 | PRINCE INDUSTRIES ( INDIA) | 21.48 | 0 | 0 | 100
2672 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - III of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 170 mtr.) | 1769/PD | 08/12/2023 | 60 | M/S SAYAK BHATTACHARYA | 21.97 | 0 | 0 | 100
2673 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - XII of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 165 mtr.) | 1778/PD | 08/12/2023 | 60 | M/S KHAN ENTERPRISE | 21.46 | 0 | 0 | 60
2674 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - II of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | 1784/PD | 08/12/2023 | 60 | BISWAJIT MAJI | 20.94 | 0 | 0 | 100
2675 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - V of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 188 mtr.) | 1771/PD | 08/12/2023 | 60 | SUBHAS CHANDRA MAHATO | 22.82 | 0 | 0 | 98
2676 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - VII of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 188 mtr.) | 1773/PD | 08/12/2023 | 60 | NANIGOPAL DEY | 23.75 | 0 | 0 | 10
2677 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - IV of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 125 mtr.) | 1770/PD | 08/12/2023 | 60 | CHINMOY SEN | 17.39 | 0 | 0 | 70
2678 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - X of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 160 mtr.) | 1776/PD | 08/12/2023 | 60 | CHANCHAL MISHRA | 20.96 | 0 | 0 | 97
2679 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - XIV of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 65 mtr.) | 1780/PD | 08/12/2023 | 60 | PURNA CHANDRA TEWARI | 11.43 | 0 | 0 | 98
2680 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying of Collecting line from Kanshabati Riverbed to Harekishtapur Riversite Pump House under Manbazar W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 1798/PD | 08/12/2023 | 60 | RAJAT KARMAKAR | 24.44 | 0 | 0 | 100
2681 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - III of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | 1785/PD | 08/12/2023 | 353 | KM ENTERPRISES | 20.98 | 0 | 0 | 100
2682 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Fencing work with concrete pillars for 15 Nos vested land for Northern & Southern Sector water supply scheme Under Purulia W/S Scheme (Northern Sector) under Purulia Division, PHE Dte. | 1513/PD | 27/08/2024 | 45 | CHATTERJEE CONSTRUCTION | 5.9 | 0 | 0 | 100
2683 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Making arrangement of interconnection at distribution pipeline with newly laid distribution pipeline & installation of sluice valves on pipeline at jiudaru mouza under Kotshila W/S at Purulia Water Supply scheme (Northern Sector) under Purulia Division,PHEDte. | 1377/PD | 25/07/2024 | 60 | GOUTAM CHAKRABORTY | 12.21 | 0 | 0 | 100
2684 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Jhalda-II,Zone-VI under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | 351/PD | 04/03/2024 | 60 | JAHANGIR ANSARI | 19.45 | 0 | 0 | 100
2685 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Jhalda-II,Zone-VIII under Purulia W/S Scheme under Purulia Sadar Sub Division-under Purulia Division, PHE Dte. | 350/PD | 04/03/2024 | 60 | BHAGABANDAS KUMAR | 22.86 | 0 | 0 | 100
2686 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Jhalda-I,Zone-VIII under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte.(Under Northern Sector W/S Scheme) | 499/PD | 16/03/2024 | 60 | BANERJEE CONSTRUCTION | 20.41 | 0 | 0 | 100
2687 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Sinking of 3 nos New 200 mm dia horizontal tube-well and laying of 100mm dia GI pipe collecting main from RBT to common manifold at river side of Satra Head Works site of Purulia water supply scheme (Northern Sector) under Purulia Division, P.H.E. Dte. | 1064/PD | 07/06/2024 | 45 | SUBODH PRAMANIK | 32.54 | 0 | 0 | 100
2688 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | New sinking of 2(Two) nos 200mm dia riverbed tube wells (Horizontal) at river bed of Kansai along with laying of 100 mm dia GI connecting line of Puncha W/S at Purulia Water Supply Scheme (Northern Sector) under Purulia Division, PHE Dte. | 1376/PD | 25/07/2024 | 30 | SOUVIK MANDAL | 7.56 | 0 | 0 | 100
2689 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Material Requisition To Resource Division | 1980/PD | 18/11/2024 | 0 | Resource Division | 9544.07 | 0 | 0 | 0
2690 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Material Requisition To Resource Division | 2253/PD | 19/12/2024 | 0 | Resource Division | 8838.63 | 0 | 0 | 0
2691 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Material Requisition To Resource Division | 1342/PD | 24/07/2024 | 0 | Resource Division | 1191.18 | 0 | 0 | 0
2692 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB050912202411333713585370XX DT.09-12-2024. | BP-2024-25-535 | 13/12/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
2693 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB051612202401322652788750XX DT.16-12-2024. | BP-2024-25-539 | 19/12/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
2694 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB052410202411410689904167XX DT.24-10-2024. | BP-2024-25-520 | 29/10/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 5.93 | 0 | 0 | 0
2695 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB052410202411113832563388047XX DT.24-10-2024. | BP-2024-25-521 | 29/10/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 5.04 | 0 | 0 | 0
2696 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Indian Railways Miscellaneous collection against Merchant Reference no.WL0703IB051612202401360237000585XX DT.16-12-2024. | BP-2024-25-538 | 19/12/2024 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 1.06 | 0 | 0 | 0
2697 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of boundary wall at Zone I H/W (OHR) site of Neturia block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | 1139/PD | 17/08/2023 | 684 | ASHOK KUMAR CHATTERJEE | 15.52 | 0 | 0 | 100
2698 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of boundary wall at Zone II H/W (OHR) site of Neturia block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte | 1140/PD | 17/08/2023 | 958 | ASHOK KUMAR CHATTERJEE | 15.52 | 0 | 0 | 0
2699 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 350 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty-six (36) months at Zone-IV of Purulia-2 Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Division, PHE Dte. (2nd Call)(Sl No. 8) | 1423/PD | 29/09/2023 | 540 | KHAN ENTERPRISE | 430.24 | 0 | 0 | 20
2700 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch Type With solid raft) of capacity 200 CUM and staging height 20 mtr as per approve drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Value & FHTC for period of thirty six (36) month at Zone- VIII of Manbazar-II Block under Purulia Piped Water Supply Scheme (Northern Sector ) under Purulia Divn. PHE Dte. (2nd Call) (SL No. 6) | 1429/PD | 29/09/2023 | 672 | PRAVAT SARKAR | 406.17 | 0 | 0 | 30
2701 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 200 CUM and staging height 20 mtr as per approved drawing ( No:PC-I/OHR/3/2012) including Laying Distribution Pipe line and providing FHTC including other allied works & Operation & Maintenance of Distribution, Pipe line (DI/HDPE), including Sluice Valve & FHTC for the period of thirty six (36) months for Zone- I of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector ) under Purulia Divn. PHE Dte. (2nd Call) (SL No. 1) | 1596/PD | 31/10/2023 | 880 | PRINCE INDUSTRIES ( INDIA) | 405.49 | 0 | 0 | 8
2702 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction and commissioning of RCC Over Head Reservoirs including Laying Distribution Pipe lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions, Pipe lines (DI/HDPE), including Sluice Valves & FHTCs for the period of thirty six (36) months for Zone- V & VI of Kashipur Block under Purulia Piped Water Supply Scheme (Northern Sector ) under Purulia Divn. PHE Dte. (2nd Call) (SL N.3) | 1595/PD | 31/10/2023 | 880 | PRINCE INDUSTRIES ( INDIA) | 1031.22 | 0 | 0 | 12
2703 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 400 CUM and staging height 20 mtr as per approved drawing (No: PC-I/OHR/3/2012) including Laying Distribution Pipe Lines and providing FHTCs including other allied works & Operation & Maintenance of Distributions , Pipe Line (DI/HDPE), including Sluice Valves & FHTC for the period of thirty six month (36) at Zone-V of Raghunathpur-I Block under Purulia Piped Water Supply Scheme (Northern Sector) under Purulia Divn. PHE Dte. (2nd Call) (SL-2) | 1597/PD | 31/10/2023 | 880 | PRINCE INDUSTRIES ( INDIA) | 536.56 | 0 | 0 | 5
2704 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line and providing FHTC including other allied works for Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block(Zone-VII) For Rudra Mouza under Purulia Division. PHE Dte. | 1700/PD | 30/11/2023 | 610 | M/S CHAKRABORTY CONSTRUCTION | 59.01 | 0 | 0 | 0
2705 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Providing FHTC including other allied work of Purulia Piped Water Supply Scheme (Northern Sector )at Purulia-I Block for Kotloi Mouza (Zone-I) Under Purulia Divn PHE DTE. | 1603/PD | 01/11/2023 | 410 | SUBODH PRAMANIK | 37.61 | 0 | 0 | 0
2706 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - XVI of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 165 mtr.) | 1782/PD | 08/12/2023 | 540 | PARTHASARATHI SAHABABU | 20.67 | 0 | 0 | 50
2707 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - IV of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | 1786/PD | 08/12/2023 | 755 | SUBRATA SINGHADEO | 20.83 | 0 | 0 | 0
2708 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - VII of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | 1789/PD | 08/12/2023 | 471 | DEBAKI RANJAN SARKAR | 21.19 | 0 | 0 | 65
2709 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - XIII of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 160 mtr.) | 1779/PD | 08/12/2023 | 796 | MADHU SUDAN RAKSHIT | 20.95 | 0 | 0 | 0
2710 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - XV of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 205 mtr.) | 1781/PD | 08/12/2023 | 469 | CHANDAN CHATTERJEE | 25.44 | 0 | 0 | 100
2711 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line and other allied work for Zone-V of Purulia-I block for Nadiyara Mouza under Purulia Water Supply Scheme (Northern Zone) Under Purulia Division ,PHE Dte. | 1825/PD | 12/12/2023 | 750 | PROGRESSIVE ENGINEERS CO OPERATIVE SOCIETY LIMITED | 53.85 | 0 | 0 | 1
2712 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Purulia-II ,Zone-XI under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte.. | 358/PD | 04/03/2024 | 420 | SINGHA ENTERPRISE | 21.01 | 0 | 0 | 0
2713 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line and providing Functional Household Tap Connection (FHTC) including other allied work at gap portion of Tiyashi for Zone-IV of Santuri Block under Purulia Pipe water supply scheme (Northern section) under Purulia Dvision PHED te [ Part-A Mouza- Tiyashi, Marbedya, Ghoramurga]. | 2121/PD | 05/12/2024 | 392 | AMIT PATHAK | 44.28 | 0 | 0 | 0
2714 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Chlorine room of size 4.00 mtr X 4.00 mtr X 3.50 mtr (Ht) at Head works site of Satra under Purulia W/S Scheme under Purulia Sadar Sub-Division Under Purulia Division , PHE Dte. | 109/PD | 21/01/2025 | 376 | AKUL SUTRADHAR | 3.92 | 0 | 0 | 60
2715 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | New Sinking of 2 (Two) Nos 200 mm dia river bed vertical tube well along with necessary 100 mm dia GI collecting line from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Maheshnadi Under Purulia W/S Scheme (Northern Sector) under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 2114/PD | 05/12/2024 | 150 | ASHOKE KUMAR CHATTERJEE | 19.19 | 0 | 0 | 0
2716 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Providing Left Out &Parallal distribution pipe line including Functional Household Tap Connection (FHTC) and Distribution main in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation of Mouza-Ritudih (JL-62) & Mouza- Joypur (JL-66) Mouza-Baliagora (J.L. No.- 96), Mouza- Mukundapur (J.L. No.-97), Mouza-Kamukhap (J.L. No.- 98) & Mouza- Amdih(J.L. No.-100) under command area of Purulia Water Supply Scheme (Northern Sector) of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1246/PD | 04/07/2024 | 271 | S.S. CONSTRUCTION | 95.44 | 0 | 0 | 0
2717 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Puncha ,Zone-III under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | 354/PD | 04/03/2024 | 572 | KANJILAL AND CO. | 29.22 | 0 | 0 | 30
2718 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Purulia-I ,Zone-VIII under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division,PHE Dte. | 355/PD | 04/03/2024 | 515 | KM ENTERPRISES | 21.04 | 0 | 0 | 45
2719 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Puncha,Zone-IV under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | 500/PD | 16/03/2024 | 480 | SOUMITRA KUMAR DAS | 28.26 | 0 | 0 | 55
2720 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying a dedicated pipe Line for Jaratanr, briddhitanr for the distribution System and repairing work at Gungligora of BORAM Under Purulia W/S scheme (Northern Sector) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 2111/PD | 05/12/2024 | 479 | SOUMITRA CHAKRABORTY | 11.94 | 0 | 0 | 50
2721 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Manbazar I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | 1673/PMD | 05/12/2024 | 365 | S. PATHAK & CO. | 1.11 | 0 | 0 | 0
2722 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying of Balance Pipeline under Command area of Purulia -1 (Northern Sector) under Jal Jeevan Mission Project under Purulia Division, PHE Dte (Bhul Mouza) | 2112/PD | 05/12/2024 | 60 | SOUMITRA CHAKRABORTY | 38.35 | 0 | 0 | 70
2723 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Making arrangement for support structure for completion of Jack Pushing work under railway line for laying of distribution pipeline & other allied works at lagda Under Purulia W/S Scheme (Northern Sector) under Purulia Division, PHE Dte. | 2125/PD | 05/12/2024 | 60 | SADHAN GORAIN | 11.12 | 0 | 0 | 100
2724 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply delivery and installation of 40 KVA voltage stabilizer for augmentation of Parbeliya High lift water supply scheme under Purulia Mechanical Division ,PHE Dte .in the District Purulia. | 1293/PMD | 30/08/2024 | 182 | AVISHEK ENTERPRISE | 5.97 | 0 | 0 | 100
2725 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Purulia-II,Zone-VII under Purulia W/S Scheme under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 2187/PD | 13/12/2024 | 60 | JOGMAYA CONSTRUCTION | 20.09 | 0 | 0 | 0
2726 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line and other allied work under Balitora Zone-1 at Balitora under Purulia W/S Scheme (Northern Sector) under Raghunathpur Sub-Division under Purulia Division ,PHE Dte. | 2129/PD | 05/12/2024 | 177 | KHITISH CHANDRA PATHAK | 27.97 | 0 | 0 | 75
2727 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Providing Left Out &Parallal distribution pipe line in connection with Jal Jeevan Mission (JJM and) at different habitation of Mouza-Ritudih (JL-62) & Mouza- Joypur (JL-66) under command area of Purulia Water Supply Scheme (Northern Sector) of Joypur Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte | 1245/PD | 04/07/2024 | 271 | M/S. S. CHOUDHURY | 66.92 | 0 | 0 | 0
2728 | PURULIA | Purulia Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Hura Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | 1253/PMD | 22/08/2024 | 365 | KAMAKHYA ENTERPRISE | 45.76 | 0 | 0 | 0
2729 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying of Balance portion parallal HDPE pipeline and other allied work under Purulia Piped water supply Scheme (Northern Sector), Kashipur Block Zone XIII within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 488/PD | 25/03/2025 | 120 | MADHU SUDAN RAKSHIT | 59.38 | 0 | 0 | 95
2730 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying of Balance portion parallal HDPE pipeline and other allied work under Purulia Piped water supply Scheme (Northern Sector), Kashipur Block Zone VI within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 493/PD | 25/03/2025 | 251 | PRINCE INDUSTRIES ( INDIA) | 89.76 | 0 | 0 | 50
2731 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying of Balance portion parallal HDPE pipeline and other allied work under Purulia Piped water supply Scheme (Northern Sector ), Kashipur Block Zone XI & XII within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 477/PD | 25/03/2025 | 120 | SUJIT SAHANA | 29.95 | 0 | 0 | 0
2732 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of boundary wall at Zone I H/W (OHR) site of Santuri block and sinking of 1 (one) no. Tubewell under surface Based Piped W/S Scheme Purulia Piped W/S Scheme (Northern Sector) under Raghunathpur Sub Division under Purulia Division PHE Dte. | 1141/PD | 17/08/2023 | 30 | MAA TARA CONSTRUCTION | 18.03 | 0 | 0 | 100
2733 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewell at Zone - II of Raghunathpur-II Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 132 mtr.) | 1722/PD | 04/12/2023 | 542 | SAIBAL SARKAR | 18.17 | 0 | 0 | 65
2734 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewell at Zone - III of Raghunathpur-II Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 115 mtr.) | 1723/PD | 04/12/2023 | 575 | CHANCHAL MISHRA | 16.47 | 0 | 0 | 100
2735 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 CUM and staging height 20 mtr as per approved drawing (No:PC-I/OHR/3/2012)with allied works for purulia water supply scheme.(Location:-Block-Purulia-1 , Zone-VII ) for Northern Zone | 1791/PD | 08/12/2023 | 612 | SAHADEV HALDER | 70.08 | 0 | 0 | 65
2736 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - V of Raghunathpur-I Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte.(Total length of Boundary Wall 160 mtr.) | 1787/PD | 08/12/2023 | 755 | PRINCE INDUSTRIES ( INDIA) | 20.98 | 0 | 0 | 90
2737 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall, RCC Pillar, gate, Barbed wire & Sinking of 1(one) no tubewellat OHR Site of Zone - VI of Kashipur Block under Surface Water Based Piped Water Supply Scheme for Purulia District (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. (Total length of Boundary Wall 137 mtr.) | 1772/PD | 08/12/2023 | 456 | PRINCE INDUSTRIES ( INDIA) | 18.68 | 0 | 0 | 100
2738 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying Distribution Pipe line and other allied work for Zone-III of Purulia-I block for Belkundi mouza under Purulia Water Supply Scheme (Northern Sector) Under Purulia Division ,PHE Dte. | 1824/PD | 12/12/2023 | 567 | GOUTAM CHAKRABORTY | 86.92 | 0 | 0 | 75
2739 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | New Sinking of 2 (Two) Nos 200 mm dia river bed vertical tube well along with necessary 110 mm dia HDPE collecting line from River bed Tube well to common manifold chamber at river bank (Damodar River) at Bhamuria Under Purulia W/S Scheme (Northern Sector) under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 2124/PD | 05/12/2024 | 45 | KHITISH CHANDRA PATHAK | 12.46 | 0 | 0 | 100
2740 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Road Crossing of Distribution Main by jack pushing at PWD Road & supplying laying fitting fixing of HDPE pipe line from Kolaboni Zone -I V OHR site to Panjunia Village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection') in connection with Jal Jeevan Mission (JJM) & with all allied works at Kolaboni under Keliyathol-Palashkola W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1655/PD | 30/08/2024 | 90 | MS GORAIN CONCERN | 50.19 | 0 | 0 | 100
2741 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Laying pipe line across railway track near Mouza-Gangpur for supply of water under Ramchandrapur (Zone-I) Under Purulia W/S scheme (Northern Sector) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 2119/PD | 05/12/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 34.39 | 0 | 0 | 100
2742 | PURULIA | Purulia Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) (PHASE-II) , SM/18731 | New | Construction of Boundary wall & Sinking of T/well at Jhalda-II,Zone-IV under Purulia W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | 352/PD | 04/03/2024 | 60 | AMITAVA KUNDU | 19.47 | 0 | 0 | 100
2743 | PURULIA | Purulia Division | Retrofitting of Rangamati Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06939 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Rangamati Water Supply Scheme at Kashipur Block under Purulia Division, PHE Dte. | 1408/PD | 29/12/2020 | 45 | SANTANU BANERJEE | 77.87 | 25.89 | 100 | 100
2744 | PURULIA | Purulia Division | Retrofitting of Rangamati Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06939 | Retrofitting | Providing Functional house hold tap connection (FHTC) in communication with Jal Dhara/ Jal Swapna under Rangamati W/s Scheme. (Tender No. 11/SE/PMU of 2020-21) | 424/8443137 | 22/03/2021 | 0 | SANTANU BANERJEE | 51.65 | 0 | 0 | 0
2745 | PURULIA | Purulia Division | Retrofitting of Rangamati Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06939 | Retrofitting | Supplying & laying different dia HDPE pipe line from Barrah Siramdih to Bonkhali village under Rangamati. (Tender No.1005/EE/PD of 20210-22) | 121/8443142 | 23/09/2022 | 0 | MANATOSH SINGH | 3.52 | 0 | 0 | 0
2746 | PURULIA | Purulia Division | Retrofitting of Rangamati Water Supply Scheme at Kashipur Block of Raghunathpur Sub-Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/06939 | Retrofitting | Retrofitting of Rangamati Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme under Purulia Division, PHE Dte. | 104/PD | 18/01/2022 | 30 | SANTANU BANERJEE | 18.64 | 0 | 0 | 0
2747 | PURULIA | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07837 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-C (Mouza- Bhamuria, Habitation-Sarkardih Tola under Bhamuria G.P). (655 Nos.) | 61/PD | 15/01/2021 | 45 | LEO CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 32.49 | 0 | 0 | 100
2748 | PURULIA | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07837 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-A (Mouza-Alkusha, Asanbani, Baruipara under Bhamuria G.P). (586 Nos.) | 57/PD | 15/01/2021 | 45 | ANUP KUMAR SAHA | 29.11 | 0 | 0 | 100
2749 | PURULIA | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07837 | Retrofitting | Functional Household Tap Connection (FHTC) including other allied works of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. Part-D (Mouza-Bonra under Bhamuria GP ).( 889 Nos.) (Tender No.333/EE/PD of 2020-21) | BP-2021-22-365 | 28/03/2022 | 0 | BABA LOKENATH LABOUR CONSTRUCTION CO-OP SOCIETY LTD. | 40.33 | 0 | 0 | 0
2750 | PURULIA | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07837 | Retrofitting | Rejuvenation work for supplying & laying of HDPE piped distribution main with all allied works from old OHR site at Bhamuria & adjacent habitation under Bhamuria W/S Scheme (Tender No- 547/2021-22 of EE/PD) | BP-2021-22-334 | 23/03/2022 | 0 | ANUP KUMAR SAHA | 10.5 | 0 | 0 | 0
2751 | PURULIA | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07837 | Retrofitting | New Sinking of 1(one) No 200 mm dia river bed vertical tube well (T/W No. 2) along with necessary 100 mm dia GI collecting line from riverbed tube well to manifold chamber at river bank (Damodar River) at Manikeswar ghat at Hirakund under Bhamuria Improvement W/S Scheme under Raghunathpur Sub-Division, PHE Dte. (Tube well No - 2) | 404/PD | 15/01/2021 | 30 | ANUP KUMAR SAHA | 7.38 | 0 | 0 | 0
2752 | PURULIA | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07837 | Retrofitting | Additional work by providing Functional Household Tap Connection (FHTC) and other allied works of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part -A) | 459/RNP | 12/07/2022 | 20 | ANUP KUMAR SAHA | 4.79 | 0 | 0 | 100
2753 | PURULIA | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07837 | Retrofitting | Additional work by providing Functional Household Tap Connection (FHTC) and other allied works of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part -B) | 460/RNP | 12/07/2022 | 20 | ANUP KUMAR SAHA | 4.85 | 0 | 0 | 100
2754 | PURULIA | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07837 | Retrofitting | Additional work by providing Functional Household Tap Connection (FHTC) including Interconnection between Over flow and Distribution Main and other allied works of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part -C) | 461/RNP | 12/07/2022 | 20 | ANUP KUMAR SAHA | 4.21 | 0 | 0 | 100
2755 | PURULIA | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07837 | Retrofitting | Sinking of 2 (Two) No 200 mm dia river bed vertical tubewell (T/W No.3 & 4) alongwith necessary 100 mm dia GI collecting line to common manifold chamber Cleaning of chowkage of distribution line and other allied work under Bhamuria W/S Scheme under Raghunathpur Sub Division, PHE Dte. | 674/PD | 17/05/2023 | 45 | ANUP KUMAR SAHA | 11.84 | 0 | 0 | 100
2756 | PURULIA | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07837 | Retrofitting | Re-sinking of 01 (One) No. 200 mm dia river bed vertical tube well T/W no- 4 along with necessary 100 mm dia GI collecting under Bhamuria W/S Scheme (Tender No- 110/2022-23 of EE/PD) | BP-2022-23-95 | 07/07/2022 | 0 | ANUP KUMAR SAHA | 4.38 | 0 | 0 | 0
2757 | PURULIA | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07837 | Retrofitting | New sinking of 02 (Two) No. 200 mm dia river bed vertical tube well T/W no- 3&4 along with necessary 100 mm dia GI collecting line 250 mm dia clear water rising main in connection with FHTC from river bed tube well to common manifold chamber at river bank (Damodar river) of Manikeswar Ghat at Hirakund under Bhamuria Water Supply Scheme under Raghunathpur Sub- Division, PHE dte.(Tender No- 24/2020-21 of EE/PD) | BP-2022-23-94 | 07/07/2022 | 0 | ANUP KUMAR SAHA | 16.61 | 0 | 0 | 0
2758 | PURULIA | Purulia Division | Retrofitting of Bhamuria Water Supply Scheme at Neturia Block of Raghunathpur Sub Division for providing Functional Household Tap Connection (FHTC) under JAL SWAPNA Programme , SM/07837 | Retrofitting | New sinking of 01 (One) No. 200 mm dia river bed vertical tube well T/W no- 2 along with necessary 100 mm dia GI collecting line from river bed tube well to manifold chamber at river bank (Damodar river) of Manikeswar Ghat under Bhamuria Water Supply Scheme (Tender No- 14/2020-21 of EE/PD) | BP-2022-23-68 | 01/07/2022 | 0 | ANUP KUMAR SAHA | 7.14 | 0 | 0 | 0
2759 | PURULIA | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Barabazar Water Supply scheme Block Barabazar under PMD PHE Dte. District Purulia. | 108/PMD | 28/02/2022 | 30 | M/S M S ENTERPRISE | 20.48 | 0 | 0 | 100
2760 | PURULIA | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method for Barabazar and other Schemes under Purulia Mechanical Division PHE.Dte. in the District of Purulia | 19/PMD | 19/01/2022 | 30 | RABINDRA NATH KHAN | 13.59 | 0 | 0 | 79
2761 | PURULIA | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | CONSTRUCTION OF RIG BORE TUBE WELL (200 x165) MM DIA BY DTH METHOD FOR BARABAZAR AND OTHER SCHEMES UNDER PMD PHE DTE.(TR.NO 60 OF 2022-23) | C072218251845 | 18/07/2022 | 0 | RABINDRA NATH KHAN | 8.16 | 0 | 0 | 0
2762 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Construction of RCC Clear Water Reservoir (CWR) of capacity 100 cum with other allied works at Barabazar W/s Scheme. (Tender No.1013/EE/PD of 2021-22) | BP-2021-22-345 | 28/03/2022 | 0 | KOUSHIK CHATTERJEE | 7.9 | 0 | 0 | 0
2763 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Lagda W/S Scheme & Barabazar W/s Scheme, Block Purulia-I, Barabazar) to be Augmentation / Rejuvenation under Purulia Division P.H.E. Dte. (SL No.07) (Tender No.357/EE/PD of 2021-22) | BP-2021-22-369 | 30/03/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 3.55 | 0 | 0 | 0
2764 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Repairing ,renovation & Construction Damaged (Portion) of Boundary Wall of Brabazar OHR Side Campus Of Barabazar W/S Scheme Under Purulia Division ,PHE DTE.. | 1553/PD | 15/12/2021 | 45 | DEBASISH CHAKRABORTY | 10.02 | 0 | 0 | 55
2765 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Guarding arrangement through Registered firm organized by Ex-Military person at Barabazar OHR site of Barabazar W/S Scheme under Purulia Division, PHE Dte. (w.e.f. 01.04.2022 to 30.04.2022) | 530/4/PD | 30/03/2022 | 30 | FRONTLINE EX-SERVICEMEN BUREAU | 0.58 | 0 | 0 | 0
2766 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Construction of R.C.C. Elevated Reservoir, Capcaity 250 cum (Intze Type With Solid Raft), Staging height 20 metre for Distribution System under Rejuvanation of Barabazar W/S Scheme under Purulia Division, PHE Dte. | 378/PD | 11/03/2022 | 270 | PRAVAT SARKAR | 70.29 | 0 | 0 | 93
2767 | PURULIA | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Supply delivery and installation of Submersible pumping machinery with all ancillaries & auxiliaries works for Augmentation of Barabazar Water Supply Scheme under PMD PHE Dte. in the District of Purulia. | 766/PMD | 14/11/2022 | 7 | MOUSUMI BENERJEE | 3.24 | 0 | 0 | 90
2768 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Material Requisition To Resource Division | 1509/PD | 13/12/2021 | 0 | Resource Division | 6.46 | 0 | 0 | 0
2769 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Material Requisition To Resource Division | 242/PD | 20/02/2023 | 0 | Resource Division | 6.4 | 0 | 0 | 0
2770 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line under command area of Barabazar Water Supply Scheme of Barabazar Block under Purulia Sadar Sub- Division, PHE Dte. Part-II (Tender No- 1012/2021-22 of EE/PD) | BP-2022-23-122 | 16/07/2022 | 0 | PRAVAT SARKAR | 27.6 | 0 | 0 | 0
2771 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Regarding laying of water supply pipe line along road side and road crossing on i) Balrampur-Barabazar-Sindri Road from 16.780 Km to 18.90 Km and Barabazar-Bandwan Road from 0.00 Km to 0.76 Km in respect of Augmentation of Barabazar water supply scheme in the District of Purulia. | BP-2022-23-663 | 23/02/2023 | 0 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 48.28 | 0 | 0 | 0
2772 | PURULIA | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | New Connection for Augmentation of Barabazar W/S Scheme. | BP-23-24-154 | 14/09/2023 | 0 | WBSEDCL PURULIA | 3.74 | 0 | 0 | 0
2773 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | car hire bill for office purpose against Reg. No.WB55A/4524 bill paid for the month of Sep,22 to June,22. | BP-2023-24-334 | 02/08/2023 | 0 | ANUP KUMAR SAHA | 2.33 | 0 | 0 | 0
2774 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Barabazar Water Supply Scheme of Barabazar Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-II) | 379/PD | 11/03/2022 | 60 | PRAVAT SARKAR | 91.16 | 0 | 0 | 80
2775 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Repairing of Guard Room at Barabazar OHR Site under Barabazar W/S Scheme under Purulia Sadar Sub Division under Purulia Division, PHE Dte. | 1804/PD | 08/12/2023 | 30 | CHATTERJEE CONSTRUCTION | 1.88 | 0 | 0 | 0
2776 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Repairing of Boundary wall & DI Rising Main at Barabazar River Site under Barabazar W/S Scheme under Purulia Sadar Sub-Division under Purulia Division,PHE Dte. | 96/PD | 15/01/2024 | 60 | CHATTERJEE CONSTRUCTION | 14.67 | 0 | 0 | 0
2777 | PURULIA | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Supply, Delivery and Installation & Commissioning of Chlorination Arrangement at Barabazar OHR for Augmentation of Barabazar water supply scheme under Purulia Mechanical Division, P.H.E. Dte. | 1090/PMD | 08/07/2024 | 60 | MOUSUMI BENERJEE | 10.14 | 0 | 0 | 70
2778 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under command area of Barabazar Water Supply Scheme of Barabazar Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PART-I) | 312/PD | 25/02/2022 | 45 | KOUSHIK CHATTERJEE | 152.12 | 0 | 0 | 100
2779 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area Zone-III,Habitation-Ankro,GP- Ankro- Barakadam of Manbazar II Block (part) Water Supply Scheme ofManbazar II Block under Purulia Sadar Sub-Division under Purulia Division, PHE Dte (PHASE-II, Part-II) (Habitation-Ankro,GP- Ankro- Barakadam ) | 517/PSD | 12/08/2022 | 40 | SADHAN GORAIN | 3.51 | 0 | 0 | 100
2780 | PURULIA | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Supply delivery and installation of 75 KVA voltage stabilizer for Augmentation of Barabazar water supply scheme under PMD PHE Dte. In the district of Purulia | 235/PMD | 03/03/2023 | 60 | MOUSUMI BENERJEE | 7.6 | 0 | 0 | 35
2781 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Making Interconnection and Bypass arrangemet of Rising Main and Distribution Pipeline For Newly Constructed OHR at Barabazar OHR Site of Aug. Barabazar W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 493/PD | 31/03/2023 | 45 | KOUSHIK CHATTERJEE | 8.09 | 0 | 0 | 100
2782 | PURULIA | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmeter and other allied works for augmentation of Barabazar water supply scheme under PMD, PHE Dte. In the district of Purulia | 521/PMD | 05/05/2023 | 60 | GOENKA ENTERPRISE | 36.99 | 0 | 0 | 100
2783 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Sinking of 02 Nos 200 mm dia rig bored tubewell by DTH method of drilling (200 mm X 165 mm) at augmentation of Barabazar Water Supply Scheme (River Site) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1709/PD | 04/12/2023 | 45 | CHATTERJEE CONSTRUCTION | 9.26 | 0 | 0 | 100
2784 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Sinking of 02 Nos 200 mm dia rig bored tubewell by DTH method of drilling (200 mm X 165 mm) at augmentation of Barabazar Water Supply Scheme (River Site) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1802/PD | 08/12/2023 | 30 | KOUSHIK CHATTERJEE | 9.26 | 0 | 0 | 100
2785 | PURULIA | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Supply and laying of 1.1 KV grade 3.5 core 95 sq. mm XLPE insulated Al. armoured cable for Augmentation at Barabazar W/S Scheme under PMD, PHE Dte. in the District of Purulia | 499/PMSD(W/S) | 21/12/2023 | 15 | MOUSUMI BENERJEE | 0.62 | 0 | 0 | 100
2786 | PURULIA | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Supply and fitting fixing of loop box for outdoor lighting for Augmentation at Barabazar Water Supply Scheme under PMD, PHE Dte.in the district of Purulia. (2ND Call) | 349/PMSD(W/S) | 04/09/2024 | 10 | AVISHEK ENTERPRISE | 0.17 | 0 | 0 | 100
2787 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Supply of stationery materials for office use | BP-2024-25-531 | 20/11/2024 | 0 | KETIKA CONSUMERS CO-OPERATIVE STORES LTD | 2.49 | 0 | 0 | 0
2788 | PURULIA | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Supply,delivery and Installation of Level Transmitter ,Submersible pumping machineries and other allied works for Augmentation of Barabazar W/S scheme under PMD Dte .in the District Purulia | 1693/PMD | 06/12/2024 | 111 | MOUSUMI BENERJEE | 7.51 | 0 | 0 | 50
2789 | PURULIA | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Supply, Delivery and installation of submersible pumping machineries in newly constructed tube well with allied cable line and other allied works for augmentation of Barabazar w/s scheme under PMD, PHE Dte. in the District of Purulia. | 234/PMD | 03/03/2023 | 700 | MOUSUMI BENERJEE | 9.65 | 0 | 0 | 70
2790 | PURULIA | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Internal and external illumination with other allied works for augmentation of Barabazar water supply scheme under PMD, PHE Dte. In the district of Purulia. | 233/PMD | 03/03/2023 | 795 | AVISHEK ENTERPRISE | 4.86 | 0 | 0 | 100
2791 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Construction of WBSEDCL Meter Room & Guard Room with sanitary and plumbing arrangment at Barabazar River Site for Augmentation of Barabazar W/S Scheme under Purulia Sadar Sub-Division, of Purulia Division, PHE Dte.. | 663/PD | 17/05/2023 | 500 | CHATTERJEE CONSTRUCTION | 7.69 | 0 | 0 | 100
2792 | PURULIA | Purulia Division | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | Sinking of 01 Nos 200 mm dia rig bored tubewell by DTH method of drilling (200 mm X 165 mm) at augmentation of Barabazar Water Supply Scheme (OHR Site) under Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 2200/PD | 13/12/2024 | 30 | CHATTERJEE CONSTRUCTION | 4.61 | 0 | 0 | 100
2793 | PURULIA | Purulia Mechanical | Augmentation of Barabazar PWSS for providing Functional Household Tap Connection (FHTC) , SM/09209 | Augmentation | External illumination of OHR site barabazar water supply scheme for Augmentation work under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | 419/PMD | 11/03/2024 | 570 | BISHWANATH NANDI | 7.55 | 0 | 0 | 100
2794 | PURULIA | Purulia Division | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Additional work for functional Household Tap Connection (FHTC) including other allied works of augmentation of SonathaliWater Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Tender No. 17/SE/PMU of 2021-22) | BP-2021-22-267 | 28/02/2022 | 0 | M/S S & P CONSTRUCTION | 35.45 | 0 | 0 | 0
2795 | PURULIA | Purulia Division | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Construction of Boundary wall, RCC pillar, barbed wire & other allied works under Sonathali W/S Scheme (Tender No-930/2021-22 of EE/PD) | BP-2022-23-57 | 20/05/2022 | 0 | TOTAL INFRA | 3.35 | 0 | 0 | 0
2796 | PURULIA | Purulia Mechanical | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | SUPPLY DELIVERY & INSTT. OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF SNATHOL W/S SCHEME KASHIPUR BLOCK UNDER PMD PHE DTE.(TR.NO 342 OF 2021-22) | C032262583160 | 28/03/2022 | 0 | R.N.S. TRADING | 13.71 | 0 | 0 | 0
2797 | PURULIA | Purulia Division | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Additional work for functional Household Tap Connection (FHTC) including other allied works of augmentation of Sonathali Water Supply Scheme at Kashipur Block. (Tender No.17/SE/PMU of 2021-22) | BP-2022-23-46 | 02/05/2022 | 0 | S AND P CONSTRUCTION | 16.37 | 0 | 0 | 0
2798 | PURULIA | Purulia Division | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Sinking of 08 (Eight) No. 200 mm dia river bed tube well horizontal at Darkeswar river (Kalapathar Ghat) along with laying of 100 mm dia GI collecting line with all allied works under Sonatholi Water Supply Scheme under Raghunathpur Sub- Division, PHE dte.(Tender No- 02/2022-23 of EE/PD) | BP-2022-23-115 | 16/07/2022 | 0 | KOUSHIK CHATTERJEE | 18.97 | 0 | 0 | 0
2799 | PURULIA | Purulia Division | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Construction of Switch Room-Cum-Chlorine Room at OHR Site of Sonathali W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 725/RNP | 06/12/2021 | 90 | MADHU SUDAN RAKSHIT | 4.21 | 0 | 0 | 0
2800 | PURULIA | Purulia Mechanical | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Supply delivery and installation of Submersible pump motor ,cable line,Kiosk , MCC allied electro mechanical equipments at Augmentation of sonatholi Water supply scheme Block: kashipur, Under Purulia Mechanical Division PHE Dte. Dist-Purulia. | 78/PMD | 01/02/2023 | 60 | SUMIT KR. CHAKRABORTY | 25.34 | 0 | 0 | 20
2801 | PURULIA | Purulia Division | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir of Capcaity 60000 Galon and other allied works under Sonathali W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 30/PD | 07/01/2022 | 60 | MADHU SUDAN RAKSHIT | 10.25 | 0 | 0 | 0
2802 | PURULIA | Purulia Division | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Construction of Pump House at Head work site of Sonathali W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 29/PD | 07/01/2022 | 45 | SUBHAS CHANDRA MAHATO | 5.03 | 0 | 0 | 100
2803 | PURULIA | Purulia Mechanical | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sonathol Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | 109/PMD | 28/02/2022 | 30 | R.N.S. TRADING | 20.48 | 0 | 0 | 100
2804 | PURULIA | Purulia Division | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Additional work for functional Household Tap Connection (FHTC) including other allied works of augmentation of Sonathali Water Supply Scheme at Kashipur Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 209/PD | 01/02/2022 | 45 | M/S S & P CONSTRUCTION | 158.98 | 0 | 0 | 65
2805 | PURULIA | Purulia Division | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Additional work by Providing functional Household Tap Connection (FHTC) at different AWC ,School and other allied works of Madandih & Sonathali W/S Scheme of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 789/PD | 05/05/2022 | 45 | MADHU SUDAN RAKSHIT | 6.23 | 0 | 0 | 100
2806 | PURULIA | Purulia Division | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Additional work for Construction of Pump House building at Head work Site of Sonathali W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 494/RNP | 02/08/2022 | 45 | SUBHAS CHANDRA MAHATO | 4.45 | 0 | 0 | 100
2807 | PURULIA | Purulia Division | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Construction of G.I. Shed at 1st Floor of Raghunathpur Sub-Divisional office buiding under Aug. of Sonathol W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1747/PD | 22/11/2022 | 45 | MANATOSH SINGH | 4.3 | 0 | 0 | 0
2808 | PURULIA | Purulia Division | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Construction of Pump House Building at OHR Site of Sonathali W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Related to JJM & Jal swapna programme) | 1748/PD | 22/11/2022 | 90 | MADHU SUDAN RAKSHIT | 10.31 | 0 | 0 | 0
2809 | PURULIA | Purulia Division | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Laying PVC Pipe ,Mending good damage of road, Eath work in filling of Para & Sonathali W/S Scheme of Raghunathpur Sub Division under Purulia Division, PHE Dte. | 675/PD | 17/05/2023 | 60 | ZEST INFRACON | 15.56 | 0 | 0 | 100
2810 | PURULIA | Purulia Division | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Material Requisition To Resource Division | 963/PD | 21/06/2022 | 0 | Resource Division | 33.65 | 0 | 0 | 0
2811 | PURULIA | Purulia Division | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Material Requisition To Resource Division | 441/PD | 23/03/2023 | 0 | Resource Division | 32.08 | 0 | 0 | 0
2812 | PURULIA | Purulia Division | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Construction of G.I shed at 1st floor of Raghunathpur Sub- Divisional office building under Aug. of Sonathali W/S Scheme within Raghunathpur Sub- Division, PHE Dte. [Tender No 941/2022-23 of EE/PD] | BP-2023-24-85 | 16/05/2023 | 0 | MANATOSH SINGH | 4.17 | 0 | 0 | 0
2813 | PURULIA | Purulia Mechanical | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Supply delivery and installation of Horizontal split casing centrifugal pump motor, MCC , Flow meter and All electro mechanical equipments , with allied works for Augmentation Sonathali low lift Water supply scheme Block: Kashipur, Under Purulia Mechanical Division PHE Dte Dist-Purulia. | 79/PMD | 01/02/2023 | 60 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 37.16 | 0 | 0 | 50
2814 | PURULIA | Purulia Mechanical | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Internal and external illumination arrangement at Augmentation Sonathali low lift and High lift Water supply scheme Block: Kashipur, Under Purulia Mechanical Division PHE Dte Dist-Purulia. | 312/PMD | 16/03/2023 | 30 | NUPUR CHANDRA HALDER | 5.13 | 0 | 0 | 45
2815 | PURULIA | Purulia Mechanical | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Supply delivery and installation of Vertical multistage centrifugal pump motor sets ,Pannel , Flow meter and all electro mechanical equipment's at Augmentation of Sonathali High Lift Water supply scheme for direct pumping Block :Kashipur, Under Purulia Mechanical Division PHE Dte Dist-Purulia. | 100/PMD | 09/02/2023 | 60 | R.N.S. TRADING | 45.25 | 0 | 0 | 68
2816 | PURULIA | Purulia Division | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Construction of Switch Room-Cum-Chlorine Room at Head Work Site of Sonathali W/S Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 724/RNP | 06/12/2021 | 90 | MADHU SUDAN RAKSHIT | 4.21 | 0 | 0 | 0
2817 | PURULIA | Purulia Mechanical | Augmentation of Sonathali W/S Scheme , SM/09210 | Augmentation | Providing And Installation of 2 M.T. capacity manually operated curved monorail for Low Lift Pump House and High Lift Pump House under Augmentation of Sonathali Water Supply Scheme, Block: Kashipur, under Purulia Mechanical Division, PHE, Dte. in the District of Purulia. | 379/PMD | 04/03/2024 | 348 | S. PATHAK & CO. | 10.22 | 0 | 0 | 100
2818 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Baghmundi W/S Scheme Ajodhya W/s Scheme, Block Baghmundi) to be Augmentation / Rejuvenation under Purulia Division P.H.E. Dte. (Tender No.361/EE/PD of 2021-22) | BP-2021-22-370 | 30/03/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 2.34 | 0 | 0 | 0
2819 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub_ Division under Purulia Division PHE Dte. (Part-B: Water supply through direct pumping) (Tender No.18/SE/PMU of 2021-22) | BP-2021-22-344 | 28/03/2022 | 0 | KOUSHIK CHATTERJEE | 34.28 | 0 | 0 | 0
2820 | PURULIA | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | SUPPLY DELIVERY & INSTTALATION OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF BAHGMUNDI W/S SCHEME , BAGHMUNDI BLOCK UNDER PMD PHE DTE.(TR.NO 344 OF 2021-22) | C042249065860 | 29/04/2022 | 0 | COMBINE ENTERPRISE | 3.54 | 0 | 0 | 0
2821 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub Division under Purulia Division PHE Dte. (Part-A : Water supply through OHR) |  | 12/10/2022 | 0 | NIBHAS SINHA | 39.62 | 0 | 0 | 0
2822 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub Division under Purulia Division PHE Dte. (Part-A : Water supply through OHR) (Tender No.19/SE/PMU of 2021-22) | BP-2022-23-4 | 05/04/2022 | 0 | NIBHAS SINHA | 44.89 | 0 | 0 | 0
2823 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub Division under Purulia Division PHE Dte. (Part-B : Water supply through OHR) (Tender No- 19/2021-22 of SE/PMU/WBPWSP(P) ) | BP-2022-23-393 | 19/10/2022 | 0 | NIBHAS SINHA | 39.62 | 0 | 0 | 0
2824 | PURULIA | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | SUPPLY DELIVERY AND INSTALLATION OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF BAGHMUNDI WATER SUPPLY SCHEME UNDER PMD PHE DTE.(TR.NO 344 OF 2021-22) | C042211560768 | 08/04/2022 | 0 | COMBINE ENTERPRISE | 12.25 | 0 | 0 | 0
2825 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub_ Division under Purulia Division PHE Dte. (Part-B : Water supply through direct pumping) | 182/PD | 31/01/2022 | 45 | KOUSHIK CHATTERJEE | 146.44 | 0 | 0 | 65
2826 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Laying of 150 mm dia DI Rising Main in connection with Jal Jeevan Mission (JJM) for Augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 425/PD | 21/03/2023 | 45 | KOUSHIK CHATTERJEE | 20.22 | 0 | 0 | 55
2827 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Supplying delivery fitting& fixing 20 Nos of Sign board (ACP Sheet)at different solar tubewell site within Bagmundi Block in Purulia District under Purulia Division, PHE Dte. | 249/PSD | 31/03/2023 | 5 | R.K ENTERPRISE | 0.46 | 0 | 0 | 0
2828 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Repairing and Renovation of Boundary wall including other allied works at WTP site in connection with Jal Jeevan Mission (JJM) for Augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 941/PD | 19/07/2023 | 30 | ROY CONSTRUCTION | 6.72 | 0 | 0 | 32
2829 | PURULIA | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Baghmundi Water Supply scheme Block Baghmundi under PMD PHE Dte. District Purulia. | 110/PMD | 28/02/2022 | 30 | COMBINE ENTERPRISE | 20.48 | 0 | 0 | 100
2830 | PURULIA | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Supply delivery and installation of external lighting and other allied works for Baghmundi (High Lift) water supply scheme under PMD PHE Dte. in the District of Purulia. | 755/PMD | 07/11/2022 | 30 | SUBRATA DUTTA | 4.01 | 0 | 0 | 100
2831 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Supplying delivery fitting& fixing 30 Nos of Sign board (ACP Sheet)at different solar tubewell site within Bagmundi Block in Purulia District under Purulia Division, PHE Dte. | 248/PSD | 31/03/2023 | 5 | R.K ENTERPRISE | 0.68 | 0 | 0 | 100
2832 | PURULIA | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Augmentation of Barge and floating walkway with required MS work by necessary supply of materials and other allied works for Augmentation of Bagmundi W/S scheme under PMD PHE Dte in the district of Purulia. | 520/PMD | 05/05/2023 | 60 | ASHOKE ADHIKARY | 19.46 | 0 | 0 | 21
2833 | PURULIA | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Bagmundi w/s scheme(Intake Site) under PMD, PHE Dte. in the District of Purulia. | 562/PMD | 16/05/2023 | 60 | H K DAS AND CO | 16.75 | 0 | 0 | 100
2834 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Repairing & Restoration work including supplying & laying of HDPE Piped Distribution Main with other allied work under Baghmundi W/S Scheme under Purulia Sadar Sub-Divn, P.H.E. Dte. | 4682/PSD | 27/07/2023 | 15 | SB CONSTRUCTION | 0.96 | 0 | 0 | 100
2835 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Material Requisition To Resource Division | 1508/PD | 13/12/2021 | 0 | Resource Division | 82.12 | 0 | 0 | 0
2836 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Material Requisition To Resource Division | 395/PD | 11/03/2022 | 0 | Resource Division | 4.32 | 0 | 0 | 0
2837 | PURULIA | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Load Enhancement for Augmentation of Baghmundi | BP-2023-24-152 | 14/09/2023 | 0 | WBSEDCL PURULIA | 3.86 | 0 | 0 | 0
2838 | PURULIA | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | New Connection for Augmentation of Baghmundi | BP-2023-24-153 | 14/09/2023 | 0 | WBSEDCL PURULIA | 6.08 | 0 | 0 | 0
2839 | PURULIA | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Bagmundi w/s scheme(CWR Site) under PMD, PHE Dte. in the District of Purulia. | 230/PMD | 03/03/2023 | 60 | SUBRATA DUTTA | 40.32 | 0 | 0 | 75
2840 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Shifting of distribution pipeline and existing 95 Nos FHTC due to widening & strengthening work of PWDte along Gobondapur to Ajodhya More under Baghmundi water supply scheme at Purulia Division, PHE Dte. | 1711/PD | 04/12/2023 | 60 | NIBHAS SINHA | 13 | 0 | 0 | 0
2841 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir of capacity 185 Cum (Intze Type) including other allied works at OHR site of Baghmundi W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 1531/PD | 13/12/2021 | 180 | MANATOSH SINGH | 6.22 | 0 | 0 | 100
2842 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 Cum with other allied works of Baghmundi W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 421/PD | 17/03/2022 | 100 | ANIL GORAI | 13.72 | 0 | 0 | 100
2843 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Baghmundi WTP site for Augmentation of Baghmundi W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | 504/PD | 31/03/2023 | 90 | ROY CONSTRUCTION | 13.76 | 0 | 0 | 100
2844 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Baghmundi OHR site for Augmentation of Baghmundi W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | 539/PD | 12/04/2023 | 100 | TOTAL INFRA | 13.85 | 0 | 0 | 100
2845 | PURULIA | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Supply delivery and installation of Internal lighting and external lighting for Bagmundi w/s scheme( WTP and OHR Site) under PMD, PHE Dte. in the District of Purulia. | 866/PMD | 21/07/2023 | 60 | ASHOKE ADHIKARY | 3.05 | 0 | 0 | 100
2846 | PURULIA | Purulia Division | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Supplying & laying of HDPE pipe and laying of DI pipe line for Distribution System of augmentation of Baghmundi W/S Scheme of Purulia Sadar Sub Division under Purulia Division PHE Dte. (Part-A : Water supply through OHR) | 208/PD | 01/02/2022 | 45 | NIBHAS SINHA | 148.62 | 0 | 0 | 100
2847 | PURULIA | Purulia Mechanical | Augmentation of Baghmundi PWSS for providing Functional Household Tap Connection (FHTC) , SM/09215 | Augmentation | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Bagmundi w/s scheme(OHR Site) under PMD, PHE Dte. in the District of Purulia. | 229/PMD | 03/03/2023 | 60 | PINTU DEY | 22.94 | 0 | 0 | 70
2848 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-E : SAPUA MOUZA] (Tender No- 90/2022-23 of EE/PD) | BP-2022-23-373 | 19/10/2022 | 0 | SOUMITRA CHAKRABORTY | 17.32 | 0 | 0 | 0
2849 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-J : BANSHGARH (Part) MOUZA] (Tender No- 29/2021-22 of SE/PMU/WBPWSP(P) ) | BP-2022-23-410 | 28/10/2022 | 0 | SADHAN GORAIN | 11.91 | 0 | 0 | 0
2850 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-K : BANSHGARH(Part) MOUZA] (Tender No.983/EE/PD of 2021-22) | BP-2022-23-44 | 02/05/2022 | 0 | BOSE CONSTRUCTION | 23.66 | 0 | 0 | 0
2851 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-B : BERMA(Part) MOUZA] (Tender No- 168/2022-23 of EE/PD) | BP-2022-23-409 | 28/10/2022 | 0 | MS GORAIN CONCERN | 35.37 | 0 | 0 | 0
2852 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at different habitation and extension of distribution pipe line for augmentation of Balarampur (Zone-II) Water Supply Scheme of Purulia Sadar Sub- Division under Purulia Division, PHE Dte. [Part- G Rangadih (Part) Mouza] (Tender No- 979/2021-22 of EE/PD) | BP-2022-23-437 | 30/11/2022 | 0 | SIKHA ENTERPRISES | 10.34 | 0 | 0 | 0
2853 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-I : BALARAMPUR(Part) MOUZA] | 230/PD | 09/02/2022 | 45 | TUMPA GORAIN | 18.71 | 0 | 0 | 100
2854 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-K : BANSHGARH(Part) MOUZA] | 229/PD | 09/02/2022 | 45 | BOSE CONSTRUCTION | 53.83 | 0 | 0 | 65
2855 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-M : TENTLOW(Part) MOUZA] | 228/PD | 09/02/2022 | 30 | ANUDIP SAHA | 9.57 | 0 | 0 | 100
2856 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under augmentation of Balarampur W/S Scheme (Zone-I) of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-B : Water Supply through Direct pumping at Chhota Urma (Part), Namsol (Part) & Amruhansa Mouza] (2nd Call) | 877/PD | 23/05/2022 | 45 | ANUP KUMAR SAHA | 156.85 | 0 | 0 | 0
2857 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Laying of parallel distribution pipeline for providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation under command area of Balarampur (Zone-II) Water Supply Scheme of Balarampur Block under Purulia Sadar Sub-Division,PHE Dte ( Mouza- SAPUA) | 1841/PD | 12/12/2022 | 45 | SOUMITRA CHAKRABORTY | 39.68 | 0 | 0 | 25
2858 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Laying of DI & MS distribution pipeline including installation of sluice valve due to widening & strengthening of Balarampur NH-32 of Balarampur W/S Scheme [Zone-II] of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 363/PD | 14/03/2023 | 30 | KOUSHIK CHATTERJEE | 7.39 | 0 | 0 | 0
2859 | PURULIA | Purulia Mechanical | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Balarampur OHR side zone-2 for Augmentation of Balarampur Water Supply scheme Block Balarampur under PMD PHE Dte. District Purulia. | 443/PMD | 20/04/2023 | 30 | ASHUTOSH DAS AND CO. | 21.56 | 0 | 0 | 0
2860 | PURULIA | Purulia Mechanical | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Internal and external illumination with other allied works for augmentation of Balarampur OHR site(Z-1 & Z-2) water supply scheme under PMD, PHE Dte. In the district of Purulia. | 1197/PMD | 03/11/2023 | 60 | MOON LIGHT HOUSE | 8.85 | 0 | 0 | 0
2861 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-C : BERMA(Part) MOUZA] | 233/PD | 09/02/2022 | 45 | SOUMITRA CHAKRABORTY | 21.93 | 0 | 0 | 100
2862 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-G : RANGADIH(Part) MOUZA] | 231/PD | 09/02/2022 | 45 | SIKHA ENTERPRISES | 11.76 | 0 | 0 | 100
2863 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Construction of Boundary wall with other allied works at Balarampur Zone-I OHR site under Augmentation of Balarampur W/S Scheme under Purulia Sadar Sub_ Division, PHE Dte. | 1812/PD | 06/12/2022 | 45 | SHYAMAL KUMAR DEY | 15.1 | 0 | 0 | 91
2864 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Material Requisition To Resource Division | 396/PD | 11/03/2022 | 0 | Resource Division | 24.46 | 0 | 0 | 0
2865 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Material Requisition To Resource Division | 989/PD | 23/06/2022 | 0 | Resource Division | 127.38 | 0 | 0 | 0
2866 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Continuation work for Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Chitmu W/S Scheme & Balarampur W/S Scheme (Zone-I), block-Jhalda-II & Balarampur) to be augmentation/ Rejuvenation under Purulia Division, PHE Dte. (Tender No- 844/2021-22 of EE/PD) | BP-2022-23-106 | 16/07/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 2.37 | 0 | 0 | 0
2867 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Indian Railways Miscellaneous collection. | BP-2022-23-5178 | 02/01/2023 | 0 | SOUTH EASTERN RAILWAY, RANCHI DIVISION | 6.34 | 0 | 0 | 0
2868 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Balarampur W/S Scheme (Zone-II) Block- Balarampur ) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 541/2021-22 of EE/PD) | BP-2022-23-89 | 07/07/2022 | 0 | HORIZEN | 8.39 | 0 | 0 | 0
2869 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Regarding laying of water supply pipe line along road side and road crossing on i) Balarampur-Bagmundi Road and ii) Jhalda-Bagmundi Road in respect of Augumentation of Balarampur water supply scheme in the District of Purulia. | BP-2022-23-510 | 22/12/2022 | 0 | EXECUTIVE ENGINEER PURULIA HIGHWAY DIVISION PWD (ROADS) DIRECTORATE | 45.73 | 0 | 0 | 0
2870 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Tap Connection of different existing PWSS (Chitmu W/S Scheme & Balarampur W/S Scheme Zone-I block-Jhalda II & Balarampur) to be augmentation/ rejuvenation under Purulia Division, PHE Dte. (Tender No- 358/2021-22 of EE/PD) | BP-2022-23-108 | 16/07/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 2.79 | 0 | 0 | 0
2871 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SAPNA) at different habitation and extention of distribution pipe line under augmentation of Balarampur W/S Scheme (Zone-I) of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-A : Water Supply through OHR at Baraurma, Berada, Chhota Urma (Part), & Namsol (Part) Mouza] | 314/PD | 25/02/2022 | 45 | SANTANU BANERJEE | 261.89 | 0 | 0 | 92
2872 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-D : BERMA(Part) MOUZA] | 232/PD | 09/02/2022 | 45 | MANATOSH SINGH | 32.6 | 0 | 0 | 70
2873 | PURULIA | Purulia Mechanical | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Supply delivery and installation of headwork site centrifugal pumping machineries, Flowmeter, MCC Panel and other allied works for augmentation of Balarampur WTP under PMD, PHE Dte. in the district of Purulia. | 197/PMD | 24/02/2023 | 60 | ORIENTAL ENGINEERING CO. | 147.95 | 0 | 0 | 55
2874 | PURULIA | Purulia Mechanical | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Supply delivery and installation of centrifugal pumping machineries, floor mounted MCC panel, Voltage stabilizer, Flowmeter and other allied works for augmentation of Balarampur OHR site(Zone-1) water supply scheme under PMD, PHE Dte. In the district of Purulia. | 1198/PMD | 03/11/2023 | 120 | COMBINE ENTERPRISES | 33.66 | 0 | 0 | 55
2875 | PURULIA | Purulia Mechanical | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Supply delivery and installation of centrifugal pumping machineries, floor mounted MCC panel, Voltage stabilizer, Flowmeter and other allied works for augmentation of Balarampur OHR site(Zone-2) water supply scheme under PMD, PHE Dte. In the district of Purulia. | 1199/PMD | 03/11/2023 | 120 | COMBINE ENTERPRISES | 34.58 | 0 | 0 | 60
2876 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Construction of Guard Room with sanitary and plumbing arrangment with approach road, plinth protection, surface drain etc. complete at Balarampur Zone-I for Augmentation of Balarampur W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | 323/PD | 01/03/2024 | 90 | PURNA CHANDRA TEWARI | 5.29 | 0 | 0 | 60
2877 | PURULIA | Purulia Mechanical | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Supply delivery and installation of MS pipe, specials including supply and laying of different size cables including allied works at WTP site under Augmentation of Balarampur Water supply scheme under Purulia Mechanical Division, PHE Dte. in the District Purulia. | 1548/PMD | 11/11/2024 | 60 | ORIENTAL ENGINEERING CO. | 15.53 | 0 | 0 | 0
2878 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Laying of Parallel distribution Pipeline at Barabazar Road and Balarampur Town at Balarampur Zone-2 to Providing FHTC under Balarampur Water Supply Scheme in Connection with Jal-Jeevan Mission Works at Purulia Division ,PHEDte. | 315/PD | 01/03/2024 | 60 | SADHAN GORAIN | 95.14 | 0 | 0 | 20
2879 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection(FHTC) in Connection with jal jeevan mission(JJM and Jal Jeevan) and Laying of parallel line under command area of Balarampur Water Supply Scheme of Balarampur Block under Purulia Division, PHE Dte (Kadamdih Mouza) | 511/PD | 16/03/2024 | 60 | DEBASISH CHAKRABORTY | 11.92 | 0 | 0 | 0
2880 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Construction of 6.0 x 3.50 mtr size Panel room with other allied works for Augmentation of Balarampur W/S Scheme at Balarampur WTP site of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 1813/PD | 06/12/2022 | 45 | SABYASACHI MISHRA | 4.09 | 0 | 0 | 100
2881 | PURULIA | Purulia Mechanical | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Supply delivery and installation of centrifugal pumping machineries, flowmeter, MCC panel and other allied works at intake side pump house for augmentation of Balarampur water supply scheme under PMD, PHE Dte. in the district of Purulia. | 47/PMD | 19/01/2023 | 60 | COMBINE ENTERPRISES | 74.71 | 0 | 0 | 100
2882 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | PCC Road restoration work due to dismantling the road for providing functional househole tap connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at Balarampur (Part) mouza for Agumentation of Balarampur (Zone -II) W/S Scheme of Purulia Sadar Sub-Division under Purulia Division, PHE Dte. | 291/PD | 27/02/2023 | 15 | TUMPA GORAIN | 1.88 | 0 | 0 | 100
2883 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Repairing and Renovation of Boundary wall & centry room including other allied works at WTP site in connection with Jal Jeevan Mission (JJM) for Augmentation of Balarampur W/S Scheme of Purulia Sadar Sub-Division under Purulia Division PHE Dte. | 324/PD | 09/03/2023 | 30 | ANADI MAHATO | 3.27 | 0 | 0 | 100
2884 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 100 m3 at River site including repairing of boundary wall at OHR site & shifting of 150mm dia DI distribution pipeline for Ramnagar W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 397/PD | 16/03/2023 | 100 | SWASTIK ENTERPRISE | 24.75 | 0 | 0 | 100
2885 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Balarampur_Zone-I OHR site for Augmentation of Balarampur W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | 540/PD | 12/04/2023 | 100 | SHYAMAL KUMAR DEY | 14.21 | 0 | 0 | 81
2886 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Construction of meter room, panel room, undercut pump house & surface drain with other allied works at Balarampur_Zone-II (Berma) OHR site for Augmentation of Balarampur W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | 541/PD | 12/04/2023 | 100 | SADHAN GORAIN | 14.25 | 0 | 0 | 65
2887 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir of capacity 800 Cum (Intze Type) including bypass arrangement & other allied works in connection with Jal Jeevan Mission (JJM) for Augmentation of Zone-II of Balarampur W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 819/PD | 26/06/2023 | 90 | SADHAN GORAIN | 18.27 | 0 | 0 | 100
2888 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Repairing and Renovation of High lift pump house & Sub station building including other allied works at WTP site in connection with Jal Jeevan Mission (JJM) for Augmentation of Balarampur W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 940/PD | 19/07/2023 | 30 | SAIBAL SARKAR | 5.95 | 0 | 0 | 70
2889 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir of capacity 180 Cum (Intze Type) including bypass arrangement & other allied works in connection with Jal Jeevan Mission (JJM) for Augmentation of Zone-I of Balarampur W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 661/PD | 17/05/2023 | 60 | SHYAMAL KUMAR DEY | 9.17 | 0 | 0 | 100
2890 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Construction of Guard Room with sanitary and plumbing arrangment with approach road, plinth protection, surface drain etc. complete at Balarampur Zone-II OHR Site for Augmentation of Balarampur W/S Scheme under Purulia Sadar Sub-Division, under Purulia Division, PHE Dte. | 328/PD | 02/03/2024 | 90 | MOHOR CONSTRUCTION | 5.29 | 0 | 0 | 100
2891 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line of Balarampur (Zone-II) W/S Scheme of Purulia SadarSub_Division under Purulia Division PHE Dte. [Tentlow Mouza] | 891/PD | 07/05/2024 | 45 | SIKHA ENTERPRISES | 12.4 | 0 | 0 | 100
2892 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Office Computer purpose bill payment. | BP-2024-25-58 | 14/05/2024 | 0 | SRI KRISHNA COMPUTER | 0.5 | 0 | 0 | 0
2893 | PURULIA | Purulia Mechanical | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | New Connection for Augmentation of Balarampur. | BP-23-24-246 | 28/12/2023 | 0 | WBSEDCL PURULIA | 6.55 | 0 | 0 | 0
2894 | PURULIA | Purulia Mechanical | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | New Connection for Augmentation of Balarampur. | BP-23-24-245 | 28/12/2023 | 0 | WBSEDCL PURULIA | 4.7 | 0 | 0 | 0
2895 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-B : BERMA(Part) MOUZA] | 234/PD | 09/02/2022 | 603 | MS GORAIN CONCERN | 70.99 | 0 | 0 | 65
2896 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-F : RANGADIH(Part) MOUZA] | 357/PD | 04/03/2022 | 1444 | SADHAN GORAIN | 136.58 | 0 | 0 | 70
2897 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-J : BANSHGARH (Part) MOUZA] | 367/PD | 04/03/2022 | 1462 | SADHAN GORAIN | 129.15 | 0 | 0 | 70
2898 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-H : BALARAMPUR(Part) MOUZA] | 366/PD | 04/03/2022 | 1436 | SADHAN GORAIN | 107.69 | 0 | 0 | 70
2899 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and JAL SAPNA at different habitation and extention of distribution pipe line for Augmentation of Balarampur (Zone-II) W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. [Part-A : DIRECT PUMPING AT BELA, SUNIDIH & RANGADIH MOUZA] | 365/PD | 04/03/2022 | 1279 | SADHAN GORAIN | 281.46 | 0 | 0 | 82
2900 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Construction of Chlorine cum Switch Room & Guard Room with sanitary and plumbing arrangment with other allied works at Zone-II OHR Site in connection with Jal Jeevan Mission (JJM) for Augmentation of Balarampur W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 657/PD | 17/05/2023 | 472 | SADHAN GORAIN | 7.96 | 0 | 0 | 100
2901 | PURULIA | Purulia Division | Augmentation of Balarampur PWSS for providing Functional Household Tap Connection (FHTC) , SM/10046 | Augmentation | Repairing and Renovation of Boundary wall including withdrawing and relaying pipeline and other allied works at Zone-II OHR site in connection with Jal Jeevan Mission (JJM) for Augmentation of Balarampur W/S Scheme of Purulia Sadar Sub_Division under Purulia Division PHE Dte. | 881/PD | 03/07/2023 | 427 | MS GORAIN CONCERN | 8.19 | 0 | 0 | 100
2902 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools(182 nos) under Balarampur & Purulia-I Block In Purulia District under Purulia Division, PHE.Dte. , SM/10222 | School | FHTC Connetion for School Purulia-I W/s Scheme. |  | 18/07/2022 | 0 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 61 | 0 | 0 | 0
2903 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools(182 nos) under Balarampur & Purulia-I Block In Purulia District under Purulia Division, PHE.Dte. , SM/10222 | School | Water supply Tap Connection Arrangement for 38 nos School upto 200 Students, 5 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Purulia-1 Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | 435/PD | 21/03/2022 | 45 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 190.01 | 0 | 0 | 100
2904 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools(182 nos) under Balarampur & Purulia-I Block In Purulia District under Purulia Division, PHE.Dte. , SM/10222 | School | Hiring of Euro-4 Diesel car of Ambassador Bharat stage-IV/TATA Indigo e.c.s Bharat Stage-IV/Swift tour Bharat stage =-IV or as similar model for Surveying the work of AWC in 10 Nos. Blocks within Purulia District under RWS Purulia Sub Division under Purulia Division PHE Dte | 258/A/PR | 03/05/2023 | 20 | ANUP KUMAR SAHA | 0.29 | 0 | 0 | 0
2905 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools(182 nos) under Balarampur & Purulia-I Block In Purulia District under Purulia Division, PHE.Dte. , SM/10222 | School | Water supply Tap Connection Arrangement for 54 nos School upto 200 Students, within Purulia-I Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | 565/PD | 08/04/2022 | 45 | MS D.PALIT AND CO. | 227.74 | 0 | 0 | 100
2906 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools(182 nos) under Balarampur & Purulia-I Block In Purulia District under Purulia Division, PHE.Dte. , SM/10222 | School | Water supply Tap Connection Arrangement for 40 nos School upto 200 Students, 3 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Balarampur Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | 925/PD | 07/06/2022 | 45 | ANUP KUMAR SAHA | 188.97 | 0 | 0 | 100
2907 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools(182 nos) under Balarampur & Purulia-I Block In Purulia District under Purulia Division, PHE.Dte. , SM/10222 | School | Water supply Tap Connection Arrangement for 6 nos AWC within Purulia-I Block (Part-G) of Purulia District under Purulia Division, PHE Dte. | 758/PD | 02/05/2022 | 45 | SOUHARDYA BUSINESS LINE | 27.15 | 0 | 0 | 100
2908 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 186 nos. under Bandwan & Arsha Block in Purulia District in Purulia Disision. , SM/10226 | School | FHTC Connetion for School Bundwan W/s Scheme. |  | 18/07/2022 | 0 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 60 | 0 | 0 | 0
2909 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 186 nos. under Bandwan & Arsha Block in Purulia District in Purulia Disision. , SM/10226 | School | Hiring of Euro-4 Diesel can of Ambassador Bharat stage-IV/TATA Indigo e.c.s Bharat Stage-IV/Swift tour Bharat stage -II/BS-III purchased on or after 01.05.2005 with Diesel/LPG/CNG Engine ( Maxi Cab, non-Airconditioned) for site visit of JJM work of 20 Nos. Blocks within Purulia District under RWS purulia Sub Division under Purulia Division PHE Dte. (Part-C) | 430-B/PR | 01/08/2023 | 195 | SUMIT KUMAR CHAKRABORTY | 0.96 | 0 | 0 | 0
2910 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 186 nos. under Bandwan & Arsha Block in Purulia District in Purulia Disision. , SM/10226 | School | Water supply Tap Connection Arrangement for 47 nos School upto 200 Students, 4 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Arsha Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | 672/PD | 25/04/2022 | 45 | ANUP KUMAR SAHA | 218.38 | 0 | 0 | 0
2911 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 186 nos. under Bandwan & Arsha Block in Purulia District in Purulia Disision. , SM/10226 | School | Water supply Tap Connection Arrangement for 20 nos. AWC within Jhalda-I, Arsha & Bandwan Block (Part-C) of Purulia District under Purulia Division, PHE Dte. | 1050_PD | 08/07/2022 | 45 | PRASENJIT BASAK | 157.97 | 0 | 0 | 100
2912 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 186 nos. under Bandwan & Arsha Block in Purulia District in Purulia Disision. , SM/10226 | School | Water supply Tap Connection Arrangement for 43 nos School upto 200 Students, within Bandwan Block (Part-B) of Purulia District under Purulia Division, PHE Dte. | 771/PD | 02/05/2022 | 1187 | PREMNATH MITRA | 181.33 | 0 | 0 | 100
2913 | PURULIA | Purulia Division | Water supply tap connection arrangement to Schools 186 nos. under Bandwan & Arsha Block in Purulia District in Purulia Disision. , SM/10226 | School | Water supply Tap Connection Arrangement for 47 nos School upto 200 Students, 5 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within Bandwan Block (Part-A) of Purulia District under Purulia Division, PHE Dte. | 436/PD | 21/03/2022 | 1054 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 227.94 | 0 | 0 | 100
2914 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Sarbari W/S Scheme block- Neturia) to be augmented/ Retrofitting under Purulia Division, PHE Dte. (Tender No- 542/2021-22 of EE/PD) | BP-2022-23-134 | 19/07/2022 | 0 | HORIZEN | 4.09 | 0 | 0 | 0
2915 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Continuation work order for Preparation of DPR (consultancy work) in connection with the Functional Household Connection of different existing PWSS (Sarbari W/S Scheme block- Neturia) to be augmented/ Retrofitting under Purulia Division, PHE Dte. (Tender No- 972/2021-22 of EE/PD) | BP-2022-23-141 | 19/07/2022 | 0 | HORIZEN | 2.35 | 0 | 0 | 0
2916 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Repairing and renovation of low-lift Pump House at River Side including drain under Sarbari W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 97/RNP | 13/03/2023 | 15 | AMIT PATHAK | 0.97 | 0 | 0 | 0
2917 | PURULIA | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Supply delivery and fitting fixing of the luminaries external and internal lighting with others allied works for Rejuvenation at SARBARI (Phase-2) w/s scheme under PMD, PHE Dte. in the District of Purulia.. | 645/PMD | 08/06/2023 | 30 | SANTU MITRA | 4.4 | 0 | 0 | 50
2918 | PURULIA | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Supply, Delivery and installation of Centrifugal pumping machineries, MCC Panels with others allied works for rejuvenation at SARBARI PHASE-2 w/s scheme under PMD, PHE Dte. in the District of Purulia. (2 nd Call) | 1175/PMD | 03/11/2023 | 120 | R.N.S. TRADING | 41.91 | 0 | 0 | 0
2919 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | New Sinking of 2 (Two) nos. 200 mm dia river bed vertical tubewell alongwith necessary 100 mm dia GI collecting line from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Chinakuri ghat under Sarbari W/S Scheme under Raghunathpur Sub Division, PHE Dte. [Part-B] | 854/PD | 23/05/2022 | 30 | KHITISH CHANDRA PATHAK | 7.79 | 0 | 0 | 95
2920 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | New Sinking of 2 (Two) nos. 200 mm dia river bed vertical tubewell alongwith necessary 100 mm dia GI collecting line from River bed Tubewell to common manifold chamber at river bank (Damodar River) at Chinakuri ghat under Sarbari W/S Scheme under Raghunathpur Sub Division, PHE Dte. [Part-A] | 853/PD | 23/05/2022 | 30 | KHITISH CHANDRA PATHAK | 7.79 | 0 | 0 | 90
2921 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Construction of Pump House (10 X 7 mtr) at Head Work site under Sarbari W/S Scheme of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | 863/PD | 23/05/2022 | 100 | M/S SHYAMASHREE ENTERPRISE | 15.57 | 0 | 0 | 100
2922 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. at Sarbari W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | 341/RNP | 01/06/2022 | 30 | K.S.GROUP | 1.4 | 0 | 0 | 100
2923 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Construction of Pump House (9 mtr X 4 mtr) at Boosting Station (Phase-II) under Sarbari W/S Scheme of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | 47/PD | 09/01/2023 | 100 | AMIT PATHAK | 10.66 | 0 | 0 | 100
2924 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Laying of HDPE pipe (PE-100, PN-10) for collecting line of riverbed Tubewell (for 3 & 4) under Sarbari W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1354/PD | 13/09/2023 | 30 | KHITISH CHANDRA PATHAK | 5.56 | 0 | 0 | 100
2925 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Material Requisition To Resource Division | 978/PD | 22/06/2022 | 0 | Resource Division | 239.56 | 0 | 0 | 0
2926 | PURULIA | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Material Requisition To Resource Division | 617/PMD | 01/06/2023 | 0 | Resource Division | 3.1 | 0 | 0 | 0
2927 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Making Xerox copy of original DPR, Drawing, Mouza Map etc. | 27/2023-149 | 30/05/2023 | 0 | SB CONSTRUCTION | 0.37 | 0 | 0 | 0
2928 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | New sinking of 02 (Two) No. 200 mm dia river bed vertical tube well T/W no- 3&4 along with necessary 100 mm dia GI collecting line in connection with FHTC from river bed tube well to common manifold chamber at river bank (Damodar river) at Chinakuri Ghat under Sarbari Water Supply Scheme under Raghunathpur Sub- Division, PHE dte.(Tender No- 744/2021-22 of EE/PD) | BP-2022-23-131 | 19/07/2022 | 0 | ASHOK KUMAR CHATTERJEE | 5.05 | 0 | 0 | 0
2929 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Laying of DI(k-9) pipe and other allied works for rising main under Sarbari W/S Scheem within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 844/PD | 23/05/2022 | 45 | KHITISH CHANDRA PATHAK | 30.86 | 0 | 0 | 80
2930 | PURULIA | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Supply, delivery & installation of Lighting conductor under Sarbori Water Supply Scheme under Purulia Mechanical Division P.H.E Dte.in the district of Purulia. | 351/PMSD(W/S) | 04/09/2024 | 15 | BISWAJIT MAJI | 0.61 | 0 | 0 | 0
2931 | PURULIA | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Supply and installation of valves, pipes & Misc. works for Pump house of Sarbori w/s scheme under PMD, PHE Dte. in the District Purulia. | 1452/PMD | 01/10/2024 | 30 | R.N.S. TRADING | 1.73 | 0 | 0 | 0
2932 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Supplying, laying different dia HDPE pipe including Functional House Hold Tap Connection (FHTC) for Distribution System (Zone-II) of Sarbari W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. (Mouza-Neturia, Pathardiha, Kuthibari, Nawada) | 868/PD | 23/05/2022 | 60 | KHITISH CHANDRA PATHAK | 72.9 | 0 | 0 | 75
2933 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 400 cum and staging height 20 mtr. with including supply of all labour & materials for Sarbari W/S Scheme within Raghunathpur Sub-Division of Purulia Division P.H.E Dte. | 1889/PD | 15/12/2022 | 270 | MD AAMIR KHAN | 131.92 | 0 | 0 | 100
2934 | PURULIA | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Supply, delivery and installation of Centrifugal pumping machineries, MCC Panel, Flowmeter with others allied works for Augmentation at SARBARI PHASE-1 w/s scheme under PMD, PHE, Dte. in the District of Purulia | 97/PMD | 03/02/2023 | 60 | GOENKA ENTERPRISE | 49.77 | 0 | 0 | 100
2935 | PURULIA | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sarbari Water Supply scheme Neturia Block under PMD PHE Dte. District Purulia. | 84/PMD | 01/02/2023 | 60 | GHOSE ENGINEERING SYNDICATE | 21.61 | 0 | 0 | 100
2936 | PURULIA | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Supply delivery and fitting fixing of the luminaries external and internal lighting with others allied works for Augmentation at SARBARI (Phase-1) w/s scheme under PMD, PHE Dte. in the District of Purulia. | 644/PMD | 08/06/2023 | 30 | AVISHEK ENTERPRISE | 6.27 | 0 | 0 | 100
2937 | PURULIA | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Supply and installation of 2 MT Capacity single girder H.O.T Crane with gantry girder and square rail for Sarbori Phase-2 Water Supply Scheme. | 1192/PMD | 03/11/2023 | 60 | P K ENGINEERING | 11.49 | 0 | 0 | 100
2938 | PURULIA | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Supply and installation of 2 MT Capacity single girder H.O.T Crane with gantry girder and square rail for Sarbori Phase-1 Water Supply Scheme. | 1191/PMD | 03/11/2023 | 60 | SEN BROTHERS | 9.71 | 0 | 0 | 100
2939 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Supply fitting fixing D.I Specials for 200 MM dia D.I Rising Main under Sarbari W/S Scheme under Raghunathpur Sub-Division under Purulia Division P.H.E Dte. | 524/PD | 16/03/2024 | 45 | KHITISH CHANDRA PATHAK | 4.75 | 0 | 0 | 100
2940 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Road Crossing of rising main by jack pushing at Panchyet Road under Sarbari W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 507/PD | 16/03/2024 | 60 | KHITISH CHANDRA PATHAK | 9.36 | 0 | 0 | 100
2941 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Laying of different dia HDPE Pipe line and Road crossing for additional work at Sarbori distribution line (Zone-II) under Sarbari W/S Scheme of Raghunathpur Sub-Division under Purulia Division PHE Dte. | 525/PD | 16/03/2024 | 60 | KHITISH CHANDRA PATHAK | 15.1 | 0 | 0 | 100
2942 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Construction of Toilet, Repairing of Guard Room & Remaining work of Pump House (Phase-II) at Sarbari under Sarbari W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 910/PD | 07/05/2024 | 60 | AMIT PATHAK | 7.1 | 0 | 0 | 100
2943 | PURULIA | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | QUATATION FOR SHIFTING OF TRANSFORMER | BP-23-24-238 | 13/12/2023 | 0 | WBSEDCL PURULIA | 2.36 | 0 | 0 | 0
2944 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Withdrawing & Laying of 2 Nos 100 mm dia GI Collecting line (1 & 2) at River bed of Damodar with fitting fixing of 40 mm dia GI guard pilling work under Sarbari W/S Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 607/RNP | 30/12/2024 | 152 | KHITISH CHANDRA PATHAK | 0.92 | 0 | 0 | 100
2945 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Supplying, laying different dia HDPE and DI pipe including Functional House Hold Tap Connection (FHTC) for Distribution System (Zone-I) of Sarbari W/S Scheme under Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 984/PD | 22/06/2022 | 1120 | JAYANTA KUMAR MONDAL | 356.05 | 0 | 0 | 85
2946 | PURULIA | Purulia Mechanical | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Supply, delivery and installation of 4 nos. submersible pumps motor sets at newly constructed riverbed tubewell with other allied works for Augmentation at SARBARI PHASE-1 w/s scheme under PMD, PHE Dte. in the District of Purulia. | 98/PMD | 03/02/2023 | 698 | AVISHEK ENTERPRISE | 12.13 | 0 | 0 | 100
2947 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Crossing of PWD Road and laying of additional HDPE pipe line(75mm & 63mm) with allied work (Zone-I) under Sarbari W/S Scheme within Raghunathpur Sub-Division under Purulia Division,PHEDte. | 1080/PD | 07/06/2024 | 404 | JAYANTA KUMAR MONDAL | 33.85 | 0 | 0 | 85
2948 | PURULIA | Purulia Division | Sarbari Piped Water Supply Scheme to Accommodate FHTC , SM/10720 | Augmentation | Withdrawing and new laying of necessary M.S. carrier pipe and all allied works at Ramkanali Ranipur village Railway Track at Erekusum village and new sinking of 2(two) no. 200 mm dia. River bed vertical at River Damodar with supplying and laying 100 mm dia GI collecting line from Riverbed Tubewell to CWR through common manifold chamber at river bank and execution of additional works for construction of (10.0 mtr x 7.0) mtr pump house drain, plinth protection under Saltora-Hijuli Under Sarbari W/S Scheme under Raghunathpur Sub Division, PHE Dte. | 1523/PD | 27/08/2024 | 147 | M/S SAYAK BHATTACHARYA | 43.79 | 0 | 0 | 100
2949 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 170 nos. under Jhalda I & Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. , SM/10256 | School | Water supply Tap Connection Arrangement for Sourceless 4 nos School upto 200 Students within ARSHA Block ,16 nos School upto 200 Students, 1 nos School for 201-500 Students within BAGHMUNDI Block, 10 nos School upto 200 Students within JHALDA-I Block,1 nos School upto 200 Students,1 no School above 800 Students within JHALDA-II Block, 8 nos School upto 200 Students within JOYPUR Block , of Purulia District under Purulia Division, PHE Dte. (Tender No- 24/2022-23 of SE/PMU/WBPWSP(P) ) | BP-2022-23-412 | 28/10/2022 | 0 | NATIONAL CONSTRUCTION | 32.91 | 0 | 0 | 0
2950 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 170 nos. under Jhalda I & Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. , SM/10256 | School | Water supply Tap Connection Arrangement for 40 nos School upto 200 Students, within JHALDA-I BLOCK (Part-B) of Purulia District under Purulia Division, PHE Dte. | 703/PD | 29/04/2022 | 45 | WRISHI ENTERPRISE | 168.1 | 0 | 0 | 100
2951 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 170 nos. under Jhalda I & Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. , SM/10256 | School | Water supply Tap Connection Arrangement for 40 nos School upto 200 Students, 4 nos School for 201-500 Students, 1 no School for 501-800 Students and 1 no School above 800 Students within BAGMUNDI BLOCK (Part-A) of Purulia District under Purulia Division, PHE Dte. | 620/PD | 20/04/2022 | 45 | S N POLYMERS PVT LTD | 194.08 | 0 | 0 | 100
2952 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 170 nos. under Jhalda I & Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. , SM/10256 | School | Water supply Tap Connection Arrangement for 32 nos School upto 200 Students, within BAGMUNDI BLOCK (Part-B) of Purulia District under Purulia Division, PHE Dte. | 939/PD | 16/06/2022 | 45 | SUMIT KUMAR CHAKRABORTY | 134.63 | 0 | 0 | 0
2953 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 170 nos. under Jhalda I & Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. , SM/10256 | School | Water supply Tap Connection Arrangement for 32 nos School upto 200 Students, within BAGMUNDI BLOCK (Part-B) of Purulia District under Purulia Division, PHE Dte. (Tender No- 41/2022-23 of SE/PMU) | BP-2022-23-166 | 05/08/2022 | 0 | SUMIT KUMAR CHAKRABORTY | 76.04 | 0 | 0 | 0
2954 | PURULIA | Purulia Division | Water supply Tap Connection Arrangement to Schools 170 nos. under Jhalda I & Baghmundi Block In Purulia District under Purulia Division, PHE.Dte. , SM/10256 | School | Water supply Tap Connection Arrangement for Sourceless 4 nos School upto 200 Students within ARSHA Block ,16 nos School upto 200 Students, 1 nos School for 201-500 Students within BAGHMUNDI Block, 10 nos School upto 200 Students within JHALDA-I Block,1 nos School upto 200 Students,1 no School above 800 Students within JHALDA-II Block, 8 nos School upto 200 Students within JOYPUR Block , of Purulia District under Purulia Division, PHE Dte. | 704/PD | 29/04/2022 | 45 | NATIONAL CONSTRUCTION | 172.42 | 0 | 0 | 100
2955 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone 1A/II under PMD PHE Dte. District Purulia. | 860/PMD | 20/07/2023 | 30 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 21.6 | 0 | 0 | 75
2956 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | Route Survey & Drawing Preparation for uncovered areas under Raghunathpur-II Block under Purulia Division, PHE Dte. | 527/PD | 10/04/2023 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 4.95 | 0 | 0 | 100
2957 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | Material Requisition To Resource Division | 75/PD | 17/01/2023 | 0 | Resource Division | 14.94 | 0 | 0 | 0
2958 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC), Construction of 250 Cum OHR and other allied works of Raghunathpur Water Supply Scheme (Zone-I A/II) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 472/PD | 28/03/2023 | 1096 | ASHOK KUMAR CHATTERJEE | 360.46 | 0 | 0 | 30
2959 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | Laying of distribution pipe line ( 90 mm,75mm & 63 mm dia HDPE pipe ) towards Garhpanchkot Prakriti Kendra under Raghunathpur W/S Scheme of Raghunathpur Sub-Divn, P.H.E. Dte. | 418/PD | 21/03/2023 | 45 | CHANDAN CHATTERJEE | 10.97 | 0 | 0 | 0
2960 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | Construction of RCC clear water reservoir (CWR) of capacity 500 Cum with other allied works at Boosting Station under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 275/PD | 27/02/2023 | 90 | BOSE CONSTRUCTION | 56.66 | 0 | 0 | 70
2961 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Ketlapur Mouza, JL No.-82, Plot No.-2790 under Para Block at OHR site under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 767/PD | 08/06/2023 | 60 | PARTHA SARATHI SAHABABU | 10.96 | 0 | 0 | 100
2962 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | Construction of Guard Room at WTP Campus under Raghunathpur Pipe Water Supply Scheme within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 664/PD | 17/05/2023 | 100 | BISWAJIT MAJI | 6.34 | 0 | 0 | 100
2963 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | Supply & delivery of spreading and levelling Filter media at Rapid Gravity sand filter beds after removal of existing not functioning filter media at Laxmanpur WTP under Purulia Division,P.H.E.Dte. | 317/PD | 01/03/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 15.86 | 0 | 0 | 100
2964 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | Sinking of 1(One) Nos. 200 mm dia DTH rigbored tubewell with other allied works at Boosting Pump Station (Seleta Mouza) of Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 518/PD | 16/03/2024 | 45 | SUBRATA SINGHADEO | 3.87 | 0 | 0 | 100
2965 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | For new connection at Gobag near uposasthya kendra under augmentation of Raghunathpur zone 1A/1 & zone 1A/II | BP-23-24-277 | 01/02/2024 | 0 | WBSEDCL PURULIA | 2.81 | 0 | 0 | 0
2966 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | Road Crossing of rising main by jack pushing at Raghunathpur-Barakar Road (near Bundla Brize) under Raghunathpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 2328/PD | 31/12/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 17.14 | 0 | 0 | 0
2967 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | Repairing and Renovation of R.C.C. Elevated Reservoir, Capcaity 243.5 cum at Jharukhamar under Raghunathpur W/S Scheme (Zone-IA) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 2300/PD | 31/12/2024 | 90 | ASHOKE KUMAR CHATTERJEE | 5.76 | 0 | 0 | 0
2968 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | Supply, delivery & Installation of Submersible Pumping Machinery and other works, at OHR site- Ketlapur, Zone-VII B (T/W-III) under Raghunathpur water supply project, PHE Dte. | 619/PMD | 22/04/2025 | 20 | ANUP KUMAR SAHA | 0.88 | 0 | 0 | 0
2969 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC), and other allied works of Raghunathpur Water Supply Scheme (Zone-I A/I) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 471/PD | 28/03/2023 | 826 | ASHOK KUMAR CHATTERJEE | 261.64 | 0 | 0 | 80
2970 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | Continuation work for Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30.04.2024) | 635/PR | 28/12/2023 | 122 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
2971 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site - I (Tube Well -Il), of Gobag of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 1010/PMD | 24/06/2024 | 15 | ANUP KUMAR SAHA | 0.81 | 0 | 0 | 95
2972 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | Continuation work order for Operation & Maintenance and water testing in the laboratory of Raghunathpur Sub District laboratory of Bacteriologist under RWS purulia Sub-Division PHE Dte.(w.e.f.01.01.2024 to 30 /04/2024) | 645/PR | 29/12/2023 | 122 | UTSAV AGENCY | 0.87 | 0 | 0 | 100
2973 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone 1A/1& Zone -1A/II , SM/14669 | Augmentation | Supply, delivery and laying of cable and other works, at OHR site Gobag of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 858/PMD | 03/06/2024 | 10 | ANUP KUMAR SAHA | 0.94 | 0 | 0 | 95
2974 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B , SM/14670 | Augmentation | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone V B under PMD PHE Dte. District Purulia. | 862/PMD | 20/07/2023 | 30 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 21.6 | 0 | 0 | 75
2975 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B , SM/14670 | Augmentation | Material Requisition To Resource Division | 73/PD | 17/01/2023 | 0 | Resource Division | 113.38 | 0 | 0 | 0
2976 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B , SM/14670 | Augmentation | Laying Distribution pipe line and other alliedworks of Raghunathpur Water Supply Scheme(Zone-I B) of Raghunathpur Sub Division under Purulia Division, PHE Dte. [Part-I] | 173/PD | 07/02/2023 | 1096 | MADHU SUDAN RAKSHIT | 83.87 | 0 | 0 | 75
2977 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B , SM/14670 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC) and other allied works of Raghunathpur WaterSupply Scheme (Zone-I B) of Raghunathpur Sub Division under Purulia Division, PHE Dte. [Part-II | 174/PD | 07/02/2023 | 1209 | RABIN CHANDRA CHAIL | 77.59 | 0 | 0 | 30
2978 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B , SM/14670 | Augmentation | Land development by earth filling with carried earth , Concrete road & Sinking of 1 (one) No. 200 mm dia DTH rigbored tubewell with other allied works of Raghunathpur Water Supply Scheme (German Assisted) (Zone -V B) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 905/PD | 07/05/2024 | 60 | AMIT PATHAK | 16.66 | 0 | 0 | 100
2979 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B , SM/14670 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Nanduka-V(B) of Raghunathpur water supply project under Purulia Mechanical Division,PHE Dte. | 367/PMD. | 01/03/2024 | 10 | ASHOKE ADHIKARY | 0.98 | 0 | 0 | 80
2980 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B , SM/14670 | Augmentation | Supply, delivery & installation of kiosk box comprising of motor startering arrangement (DOL), at OHR site V(B) (T/W-1) of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 445/PMD | 11/03/2024 | 10 | TAPAN KUMAR DEY | 1 | 0 | 0 | 60
2981 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B , SM/14670 | Augmentation | Supply, delivery & laying of cable and other works at OHR site- V(B) of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 443/PMD | 11/03/2024 | 10 | TAPAN KUMAR DEY | 0.84 | 0 | 0 | 60
2982 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B , SM/14670 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site-V (Tube well-II), Nanduka under Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 1028/PMD | 25/06/2024 | 15 | S. PATHAK & CO. | 0.95 | 0 | 0 | 90
2983 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B , SM/14670 | Augmentation | Sinking of 1 (one) No. 200 mm dia DTH rigbored tubewell of Raghunathpur Water Supply Scheme (German Assisted) (Zone -V B)(Nanduka) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1502/PD | 27/08/2024 | 30 | AMIT PATHAK | 5.07 | 0 | 0 | 100
2984 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B , SM/14670 | Augmentation | Supply, delivery & installation of earthing arrangement and other works at OHR site-V, Nanduka of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 1041/PMD | 26/06/2024 | 15 | S. PATHAK & CO. | 0.71 | 0 | 0 | 70
2985 | PURULIA | Purulia Mechanical | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B , SM/14670 | Augmentation | NEW CONNECTION FOR AUGMENTATION OF RAGHUNATHPUR ZONE VB | BP-23-24-250 | 04/01/2024 | 0 | WBSEDCL PURULIA | 1.18 | 0 | 0 | 0
2986 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B , SM/14670 | Augmentation | Laying Distribution pipe line including providing Functional Household Tap Connection (FHTC) and other allied works of Raghunathpur Water Supply Scheme (Zone-VB) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Part-B) | 302/PD | 28/02/2023 | 977 | M/S KARUNAMOYEE CONSTRUCTION | 149.48 | 0 | 0 | 100
2987 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B , SM/14670 | Augmentation | Construction of Boundary wall, RCC Pillar, gate, Barbed wire at Gobag Mouza, JL No.-58, Plot No.-620 under Neturia Block at OHR site under Raghunathpur W/S Scheme (German Project) of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 768/PD | 08/06/2023 | 663 | ASHOK KUMAR CHATTERJEE | 17.28 | 0 | 0 | 65
2988 | PURULIA | Purulia Division | Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone V B , SM/14670 | Augmentation | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-V-B) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Part-B) | 1498/PD | 27/08/2024 | 431 | M/S KARUNAMOYEE CONSTRUCTION | 30.19 | 0 | 0 | 100
2989 | PURULIA | Purulia Division | MINI PIPED WATER SUPPLY SCHEME FOR MADHUPUR VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER BAGMUNDI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME , SM/15380 | New | Survey in connection with the Mini Water Supply Scheme having house hold less than 100 under Baghmundi Block [37 nos Habitations] under Jal Sapna/ JJM Programme under Purulia Division P.H.E. Dte. | 100/A/PSD | 08/02/2023 | 21 | INDRANIL DUTTA & ASSOCIATES | 4.83 | 0 | 0 | 60
2990 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Supply and Installation of 4KG/HR Gaseous Chlorination system and Chlorine leak absorption system at Lakshmanpur WTP under Augmentation of Raghunarhpur W/S project with allied works, under PMD, PHE, Dte. | 1126PMD | 11/10/2023 | 120 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 80.55 | 0 | 0 | 0
2991 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Supply delivery and installation of electro mechanical equipments, HSC pump motor sets, MCC, HOT, Valves, Flowmeter ,400 KVA electrical substation, Gaseous chlorination system at Clear water Boosting pump house Under Augmentation of Raghunathpur water supply project Under Purulia Mechanical Division PHE Dte Dist-Purulia. | 1147/PMD | 16/10/2023 | 120 | MAHADEV ENTERPRISE | 331.9 | 0 | 0 | 0
2992 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Material Requisition To Resource Division | 71/PD | 17/01/2023 | 0 | Resource Division | 1429.07 | 0 | 0 | 0
2993 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Material Requisition To Resource Division | 1759/PD | 07/12/2023 | 0 | Resource Division | 40.12 | 0 | 0 | 0
2994 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Supply delivery and installation of electro mechanical equipment's, HSC pump motor sets, MCC, HOT, Valves, Flowmeter at Proposed Clear water pump house in Lakshmanpur WTP Under Augmentation of Raghunathpur water supply project Bolck : Neturia, Under Purulia Mechanical Division PHE Dte Dist-Purulia. | 458/PMD | 14/03/2024 | 120 | NEW ALIGNMENT | 192.41 | 0 | 0 | 0
2995 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Sinking of 1No. 200 mm dia DTH Rigbored TW with allied works at office campus under Aug. of Raghunathpur W/S Scheme (Zone-IB) within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 2120/PD | 05/12/2024 | 60 | MANATOSH SINGH | 4.21 | 0 | 0 | 0
2996 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Providing Mechanical / Electrical Works with all accessories for High Lift Pumping Machinary at Booster Pumping Station - Zone VIII, Augmentation of Raghunathpur Water Supply Project under PMD PHE Dte. in the District of Purulia. | 1570/PMD | 14/11/2024 | 180 | COMBINE ENTERPRISES | 47.9 | 0 | 0 | 0
2997 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Laying balance Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-VII-A) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Name of Mouzas-Madhutati or Mautor ,Baldi , Dhanara) | 2182/PD | 13/12/2024 | 60 | CHATTERJEE CONSTRUCTION | 90.91 | 0 | 0 | 0
2998 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Continuation Work Order for "Hiring charges of 1(one) no. Car.(Diesel driven) along with driver for use of the Office of the Assistant Engineer(H.Q) for augmentation of different water supply scheme in Raghunathpur Block, under Purulia Mechanical Division P.H.E Dte." With effect from :01.04.2024 to 30.09.2024 | 525/PMD | 18/03/2024 | 183 | PINTU DEY | 0.89 | 0 | 0 | 55
2999 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Uporkhajura (Tube well-III), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 1115/PMD | 12/07/2024 | 15 | ANUP KUMAR SAHA | 0.81 | 0 | 0 | 0
3000 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Repering& renovation of 4 (Four) Nos I.E Plant under Raghunathpur W/S Scheme of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1086/PD | 07/06/2024 | 60 | SADHAN GORAIN | 22.12 | 0 | 0 | 70
3001 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Supply, delivery, installation and commissioning of chlorine leak absorption System at different OHR sites of Raghunathpur Water Supply Project under PMD PHE Dte. | 1576/PMD | 14/11/2024 | 90 | TAPAN KUMAR DEY | 90.02 | 0 | 0 | 0
3002 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Hiring charges of 1(one) no. Car.(Diesel driven) along with driver for use of the Office of the Assistant Engineer(H.Q) for augmentation of different water supply scheme in Raghunathpur Block, under Purulia Mechanical Division P.H.E Dte. | 1086/PMD | 29/09/2023 | 183 | PINTU DEY | 0.89 | 0 | 0 | 84
3003 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Supply and installation of A.C Machine at Ground floor of Shimul Annex Building at Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 446/PMD | 11/03/2024 | 10 | S PATHAK AND CO | 0.79 | 0 | 0 | 99
3004 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Supply and installation of A.C Machine at first floor of Shimul Annex Building at Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 385/PMD | 04/03/2024 | 10 | S PATHAK AND CO | 0.79 | 0 | 0 | 99
3005 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Salata (Z-IB) (Tube well-I), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 906/PMD | 10/06/2024 | 15 | M/S A.D. CONCERN | 0.95 | 0 | 0 | 80
3006 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Supply and installation of 1 Ton A.C machine at Lakshmanpur Bungalow of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 1116/PMD | 12/07/2024 | 15 | TAPAN KUMAR DEY | 0.62 | 0 | 0 | 100
3007 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- VB (Tube Wel-V), Nanduka of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 1324/PMD | 04/09/2024 | 15 | PINTU DEY | 0.96 | 0 | 0 | 90
3008 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- VB (Tube well-3), Nanduka of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 1259/PMD | 22/08/2024 | 15 | M/S UJJAL DIESEL SERVICE | 0.96 | 0 | 0 | 90
3009 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- VB (Tube Wel-IV), Nanduka of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 1323/PMD | 04/09/2024 | 103 | M/S A.D. CONCERN | 0.96 | 0 | 0 | 90
3010 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Laying of HDPE Pipe (PE-100, PN-10) for collecting line of riverbed tubewell (for 1, 2, 3 & 4) under Raghunathpur W/S Scheme of Raghunathpur Sub-Division, under Purulia Division, PHE Dte. | 1075/PD | 07/06/2024 | 60 | KHITISH CHANDRA PATHAK | 6.9 | 0 | 0 | 100
3011 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Salata (Z-IB) (Tube well-II), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | 1009/PMD | 24/06/2024 | 15 | SUJIT MUKHERJEE | 0.95 | 0 | 0 | 80
3012 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Supply, fitting, fixing Swajal Gram Village signboard and thorough repairing and Renovation of R.C.C. Elevated Reservoir (Intze Type with solid raft) of Capcaity 1049.84 cum and staging height 25 mtralongwith high lifting of boundary wall and construction of approach road with all allied works and laying of HDPE pipe at Soudagar Para , Goraipara, Bandanga Village and Supply of Chair, Table and Almirah for Seating arrangement of contractual Junior Engineers at the office of the Assistant Engineer, Raghunathpur Sub-Division under Raghunathpur W/S Scheme(German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1096/PD | 07/06/2024 | 90 | M/S SAYAK BHATTACHARYA | 45.37 | 0 | 0 | 100
3013 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Material Requisition To Resource Division | 1712/PD | 06/09/2024 | 0 | Resource Division | 408.72 | 0 | 0 | 0
3014 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Quotation for new connection | BP-23-24-281 | 16/02/2024 | 0 | WBSEDCL PURULIA | 1.63 | 0 | 0 | 0
3015 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Supply of Diesel & Mobil for vehicle WB56V-4010 for the month of March-2024 under PMD, PHE Dte. | BP-24-25-80 | 02/08/2024 | 0 | M/S SANKAR AUTO SERVICE | 0.22 | 0 | 0 | 0
3016 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | New Connection for Augmentation of Raghunathpur ZOne- I B (Nanduara) | BP-24-25-27 | 11/06/2024 | 0 | WBSEDCL PURULIA | 0.25 | 0 | 0 | 0
3017 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Bulk power supply at 11 KV, Purulia for a contractual demand of 400/400/400/400/400 KVA respectively for next consecutive five years, Mouza-Salata, Block-Raghunathpur -I , Purulia | BP-23-24-299 | 05/03/2024 | 0 | WBSEDCL PURULIA | 38.16 | 0 | 0 | 0
3018 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Quotation for new connection | BP-23-24-221 | 05/12/2023 | 0 | WBSEDCL PURULIA | 0.05 | 0 | 0 | 0
3019 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Quotation for new connection | BP-23-24-280 | 16/02/2024 | 0 | WBSEDCL PURULIA | 0.61 | 0 | 0 | 0
3020 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | New Connection for Augmentation of Raghunathpur ZOne-I B (Sohardi Mouza Babugram, Sanka) |  | 08/02/2024 | 0 | WBSEDCL PURULIA | 2.32 | 0 | 0 | 0
3021 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Payment to WBSEDCL , Chelyama CCC for new connection at Vill. + P.O. - Chelyama , Rghunathpur , application no,- 2004770178 , reference Id.- 204327440 . | BP-24-25-76 | 02/08/2024 | 0 | WBSEDCL PURULIA | 5.36 | 0 | 0 | 0
3022 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Payment of New Electric Connection charge at Salata mouza ,Babugram site , Zone - IV B Raghunathpur - 1 under Augmentation of Raghunathpur W.S. Project and payment to WBSEDCL Raghunathpur CCC . Referance Id - 204346008 | BP-24-25-48 | 16/07/2024 | 0 | ASSISTANT ENGINEER & IN CHARGE, RAGHUNATHPUR 132 KV SUB STATION (WBSETCL) | 3.11 | 0 | 0 | 0
3023 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Replacement of existing two number old VT pumps with new pumps at intake pump house of Lakshmanpur WTP for Augmentation of Raghunarhpur W/S project with allied works, under PMD, PHE, Dte. | 1127/PMD | 11/10/2023 | 599 | COMBINE ENTERPRISES | 31.33 | 0 | 0 | 91
3024 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Installation of Ongrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping machinery at Existing 8 nos OHR and Proposed 6nos OHR site under Augmentation of Raghunathpur water supply project under PMD, PHE, Dte. District Purulia. | 1125/PMD | 11/10/2023 | 538 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 44.79 | 0 | 0 | 50
3025 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Construction of Pump House (13 X 8.5 mtr) at Laxmanpur WTP site to accommodate electromechanical equipment as well as safety device under Raghunathpur W/S Scheme of Raghunathpur Sub-Divn under Purulia Division, P.H.E. Dte. | 1353/PD | 25/07/2024 | 358 | BOSE CONSTRUCTION | 31.86 | 0 | 0 | 25
3026 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Laying Distribution System of Parallel pipe line and changing existlng CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte.(Name of Mouzas- Rangamati , Gobranda , Charanbandh , Muldi , Bagmanni , Nanduka) | 43/PD | 10/01/2025 | 60 | KHITISH CHANDRA PATHAK | 96.11 | 0 | 0 | 0
3027 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Laying of 250 mm D.I. pipe line for Raw water rising main with manifold at Ramchandrapur under Raghunathpur Piped Water Supply Scheme of Raghunathpur Sub-Division under Purulia Division, P.H.E. Dte. | 2329/PD | 31/12/2024 | 60 | ANUP KUMAR SAHA CIVIL CONTRACTORS PRIVATE LIMITED | 1.82 | 0 | 0 | 0
3028 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Laying balance Distribution System of Parallel pipe line and changing existing CI main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-VII-A) at Raghunathpur-II Block of Raghunathpur Sub Division under Purulia Division, PHE Dte. (Name of Mouzas-(Khantra, KhairaChak , Ruknibera, Gobindapur, Paranpur, Toldi) | 2183/PD | 13/12/2024 | 460 | NANIGOPAL DEY | 96.2 | 0 | 0 | 0
3029 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Supply of DI Specials & road crossing for Distribution line ZONE-IB of Raghunathpur W/S Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 1363/PD | 25/07/2024 | 745 | MADHU SUDAN RAKSHIT | 7.01 | 0 | 0 | 0
3030 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Continuation Work Order for"Hiring charges of 1(one) no. Car.(Diesel driven) along with driver for use of the Office of the Assistant Engineer(H.Q) for augmentation of different water supply scheme in Raghunathpur Block, under Purulia Mechanical Division P.H.E Dte." With effect from :01.10.2024 to 31.03.2025 | 1375/PMD | 19/09/2024 | 182 | PINTU DEY | 0.89 | 0 | 0 | 0
3031 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Construction of Guard Room with toilet block at Zone-III under Raghunathpur W/S Scheme (German Assisted) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 2102/PD | 05/12/2024 | 180 | SUBHAJIT KUNDU | 6.41 | 0 | 0 | 0
3032 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Yard lighting and internal illumination arrangement at Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV - B under Purulia Mechanical Division, PHE. Dte. | 1447/PMD | 01/10/2024 | 151 | BISHWANATH NANDI | 13.34 | 0 | 0 | 65
3033 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Special repairing works of HDPE pipe line from River side to Karandih Village , Kajuli Village ,Kajuli more to D.ED Collage road , Daldali Majhidih Village & Guard pilling Manifold to CWR Pipe line with all allied works of Retrofitting works in connection with Jal Jeevan Mission (JJM) at Maguria Lalpur under Raghunathpur W/S Scheme (Zone-IB) of Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 438/PD | 24/03/2025 | 120 | ALOK KUMAR CHAKRABORTY | 31.69 | 0 | 0 | 75
3034 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Maintenance work for Construction of Soak pit, Leach pit & Drain at Inspection Bunglow at Lakkhanpur WTP under Raghunathpur W/S Scheme(German Assisted) Zone-IB within Raghunathpur Sub-Division under Purulia Division, PHE Dte. | 572/PD | 07/04/2025 | 60 | CHANDAN CHATTERJEE | 5.63 | 0 | 0 | 0
3035 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Modification of existing filter bed control system with allied works at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD, PHE, Dte. | 568/PMD | 07/04/2025 | 120 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 101.61 | 0 | 0 | 0
3036 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Yard lighting arrangement at different OHR site and other works under Augmentation of Raghunathpur Pipe Water Supply Project under PMD, PHE. Dte. | 569/PMD | 07/04/2025 | 269 | BISHWANATH NANDI | 24.28 | 0 | 0 | 80
3037 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Laying Distribution System of Parallel pipeline and changing existing Cl main & branch pipe line including other allied works of Raghunathpur Water Supply Scheme (Zone-I-B) at Raghunathpur-II Block of Raghunathpur Sub-Division under Purulia Division PHE Dte. | 373/PD | 13/03/2025 | 240 | DEBAKI RANJAN SARKAR | 128.19 | 0 | 0 | 0
3038 | PURULIA | Purulia Division | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Laying of 140 mm dia HDPE pipe line From OHR to Misson Para at Arrah under Raghunathpur Water Supply Scheme (German Assisted) (Zone-IB) of Raghunathpur Sub Division Under Purulia Division PHE Dte | 1520/PD | 19/08/2025 | 285 | RABIN CHANDRA CHAIL | 21.16 | 0 | 0 | 0
3039 | PURULIA | Purulia Mechanical | Augmentation of ZOne-I B of Raghunathpur Piped Water Supply Scheme Project , SM/18779 | Augmentation | Strengthen the existing monorail at Chlorination Building of Lakshmanpur WTP and other allied works under Raghunathpur Water Supply Project under under Purulia Mechanical Division P.H.E. Dte. | 424/PMD | 11/03/2024 | 386 | RABINDRA NATH KHAN | 7.76 | 0 | 0 | 100
3040 | PURULIA | Resource | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purulia District. , SM/09027 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purulia District. | 4730/RS | 19/08/2022 | 365 | KULTIKARI MOTHER TERESA SOCIAL WELFARE SOCIETY | 430.46 | 0 | 0 | 100
3041 | PURULIA | Purulia Division | NABL accreditation of Purulia District water testing laboratory under Purulia Division, PHE Dte as per ISO/IEC 17025:2017 related to Support Activities Under Jal Jeevan Mission , SM/08682 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Bagmundi Sub-District Water Testing Laboratory under Purulia Division, PHE Dte. SL NO.01 | 334/PR | 18/08/2021 | 90 | UTSAV AGENCY | 4.82 | 0 | 0 | 0
3042 | PURULIA | Purulia Division | NABL accreditation of Purulia District water testing laboratory under Purulia Division, PHE Dte as per ISO/IEC 17025:2017 related to Support Activities Under Jal Jeevan Mission , SM/08682 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Sirkabad Sub-District Water Testing Laboratory under Purulia Division, PHE Dte. SL NO.12 | 345/PR | 18/08/2021 | 90 | UTSAV AGENCY | 4.82 | 0 | 0 | 0
3043 | PURULIA | Purulia Division | NABL accreditation of Purulia District water testing laboratory under Purulia Division, PHE Dte as per ISO/IEC 17025:2017 related to Support Activities Under Jal Jeevan Mission , SM/08682 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Barabazar Sub-District Water Testing Laboratory under Purulia Division, PHE Dte. SL NO.03 | 336/PR | 18/08/2021 | 90 | UTSAV AGENCY | 4.82 | 0 | 0 | 0
3044 | PURULIA | Purulia Division | NABL accreditation of Purulia District water testing laboratory under Purulia Division, PHE Dte as per ISO/IEC 17025:2017 related to Support Activities Under Jal Jeevan Mission , SM/08682 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Santuri Sub-District Water Testing Laboratory under Purulia Division, PHE Dte. SL NO.11 | 344/PR | 18/08/2021 | 90 | UTSAV AGENCY | 4.82 | 0 | 0 | 0
3045 | PURULIA | Purulia Division | NABL accreditation of Purulia District water testing laboratory under Purulia Division, PHE Dte as per ISO/IEC 17025:2017 related to Support Activities Under Jal Jeevan Mission , SM/08682 | Support-WQMSP | Repairing & Renovation of District laboratory for NABL Accrediation of Purulia District laboratory (Part-B) SL NO.03 | 251/PR | 10/05/2022 | 30 | TARA SANKAR CONSTRUCTION | 2.8 | 0 | 0 | 0
3046 | PURULIA | Purulia Division | NABL accreditation of Purulia District water testing laboratory under Purulia Division, PHE Dte as per ISO/IEC 17025:2017 related to Support Activities Under Jal Jeevan Mission , SM/08682 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Sister Nivedita Oldage Home NGO Laboratory under Purulia Division, PHE Dte. | 96/PD | 11/03/2022 | 90 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.85 | 0 | 0 | 0
3047 | PURULIA | Purulia Division | NABL accreditation of Purulia District water testing laboratory under Purulia Division, PHE Dte as per ISO/IEC 17025:2017 related to Support Activities Under Jal Jeevan Mission , SM/08682 | Support-WQMSP | Procurement of consumables & reagents for 3 nos On-site Mobile Analysis System (3 nos OMAS Kit) for testing public drinking water sources. SL NO.04 | 271/PR | 20/05/2022 | 90 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.72 | 0 | 0 | 0
3048 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory(NGO) including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for District Agragami Mohila O-Sisu Mangal Samiti NGO Laboratory under Purulia Division, PHE Dte. | 94/PR | 11/03/2022 | 90 | DAS AND SON | 4.77 | 0 | 0 | 0
3049 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 9 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2022 to 30.06.2023) SL NO.02 | 309/PR | 29/06/2022 | 365 | COMPUTER MEDIA | 2.97 | 0 | 0 | 100
3050 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus,Ranchi Road under Purulia Division, PHE Dte (w.e.f.01.07.2022 to 31.12.2022). SL NO.05 | 312/PR | 29/06/2022 | 183 | ARUNALOY SCIENTIFIC HOUSE | 3.86 | 0 | 0 | 0
3051 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Annual Maintenance contract for Computers Printers, UPS, Internet recharge and other related peripherals for 8 nos Laboratory of RWS Purulia Sub-Division, under Purulia Division PHE Dte (w.e.f. 01.07.2022 to 30.06.2023) SL NO.01 | 308/PR | 29/06/2022 | 365 | COMPUTER MEDIA | 2.73 | 0 | 0 | 0
3052 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Operation and Maintenance and water testing in Jhalda Aug WTP Sub-Disrict Laboratory under Purulia Division, PHE Dte. (For 01 ( One) Year) (w.e.f. 01.07.2021 to 30.06.2022) | 723/PD | 30/06/2021 | 365 | ANUP KUMAR SAHA | 5.24 | 0 | 0 | 0
3053 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Day to establishment works of RWS Purulia Sub-Division Office & maintaning of files, letters issued & despatched register, service book of officials & all others ancilliary works by deployment of 02 (Two) nos. of personnel having proficiency with computer & office assistant having experience in Government works on monthly basis for the office of the Assistant Engineer, RWS Purulia Sub-Division, P.H.E. Dte. (1st Year) (Period from 01.01.2022 to 31.12.2022) (For 12 Months) | 613/PD | 27/12/2021 | 365 | COMPUTER MEDIA | 4.48 | 0 | 0 | 0
3054 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Jhalda-I Sub District Laboratory under under RWS Purulia Sub Division PHE Dte.(w.e.f.01.05.2022 to 31.08.2022). SL NO.02 | 244/PR | 29/04/2022 | 4 | KOUSHIK CHATTERJEE | 2.09 | 0 | 0 | 0
3055 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Joypur Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.05 | 300/PR | 23/06/2022 | 365 | TUSHAR KANTI GORAI | 3.66 | 0 | 0 | 100
3056 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Baghmundi Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.01 | 296/PR | 23/06/2022 | 12 | BOSE CONSTRUCTION | 3.66 | 0 | 0 | 100
3057 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory Of Raghunathpur Sub-District Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.06 | 301/PR | 23/06/2022 | 365 | MANATOSH SINGH | 4.76 | 0 | 0 | 100
3058 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 31.12.2022). SL NO.04 | 311/PR | 29/06/2022 | 183 | ARUNALOY SCIENTIFIC HOUSE | 2.77 | 0 | 0 | 0
3059 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Kashipur Sub District Laboratory under under RWS Purulia Sub Division PHE Dte.(w.e.f.01.09.2022 to 30.06.2023). | 1356/PD | 31/08/2022 | 303 | ANUDIP SAHA | 4.72 | 0 | 0 | 100
3060 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Continuation order for the work of "Supply of Laboratory reagent/media/consumables required for routi ne water testing of different laboratories under Purulia Division, PHE Dte. ( For 3 months)" | 1895/PD | 15/12/2022 | 15 | ARUNALOY SCIENTIFIC HOUSE | 33.8 | 0 | 0 | 100
3061 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Continuation work for Day to establishment works of RWS Purulia Sub-Division Office & maintaning of files, letters issued & despatched register, service book of officials & all others ancilliary works by deployment of 02 (Two) nos. of personnel having proficiency with computer & office assistant having experience in Government works on monthly basis for the office of the Assistant Engineer, RWS Purulia Sub-Division, P.H.E. Dte. (1st Year) (Period from 01.01.2023 to 31.03.2023) | 650/PR | 30/12/2022 | 90 | COMPUTER MEDIA | 1.1 | 0 | 0 | 100
3062 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Supply delivery fitting & fixing of sign board (ACP Sheet) at 11 nos site within Purulia District under RWS Purulia Sub-Division PHE Dte.( Part-A) SL NO.05 | 95/PR | 28/02/2023 | 30 | SIKHA ENTERPRISES | 0.71 | 0 | 0 | 100
3063 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Supply & fitting & fixing Glowsine board at Division office of Purulia Division PHE Dte. (Sirkabad SDL, Bagmundi SDL,Santuri SDL,Dubra SDL ,Joypur SDL) Sl NO.02 | 92/PR | 28/02/2023 | 30 | DEBANJAN SEAL | 0.83 | 0 | 0 | 100
3064 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Supply & fitting & fixing Glowsine board at Division office of Purulia Division PHE Dte. (Bandwan WTP SDL, Balarampur WTP SDL,Jhalda WTP SDL ,Raghunathpur WTPSDL,Chemliyama SDL.) (SL NO.01) | 91/PR | 28/02/2023 | 30 | ANUDIP SAHA | 0.83 | 0 | 0 | 100
3065 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Supply delivery fitting & fixing of sign board (ACP Sheet) at 11 nos site within Purulia District under RWS Purulia Sub-Division PHE Dte.( Part-B) SL NO. 6 | 96/PR | 28/02/2023 | 30 | INDRAJIT SARKAR | 0.71 | 0 | 0 | 100
3066 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Supply & Installation of Sign Board for Place identification of 7nos of Laboratory Sites within Purulia District under RWS Purulia Sub-Division,Under Purulia Division PHE Dte (Part-D) SL NO. 13 | 103/PR | 28/02/2023 | 30 | ANUDIP SAHA | 0.92 | 0 | 0 | 100
3067 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Supply & fitting & fixing Glowsine board at Division office of Purulia Division PHE Dte. (Barabazar SDL, Raghunathpur SDL, Kashipur SDL ,Hura SDL) SL NO.03 | 93/PR | 28/02/2023 | 30 | SUDHANSHU OJHA | 0.66 | 0 | 0 | 100
3068 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Supply & Installation of Sign Board for Place identification of 7nos of Laboratory Sites within Purulia District under RWS Purulia Sub-Division,Under Purulia Division PHE Dte (Part-C) | 102/PR | 28/02/2023 | 30 | DEBANJAN SEAL | 0.92 | 0 | 0 | 100
3069 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Requisition for Salary component of laboratory, Laboratory Maintenance charges of 17 laboratory, Festival Bonus of Laboratory personnel and sample collection charges for sampling assistants (2000 rupees per month). |  | 10/01/2023 | 0 | EXECUTIVE ENGINEER, PURULIA DIVISION PH, DTE | 92.8 | 0 | 0 | 0
3070 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Kashipur Sub- District Laboratory under RWS Purulia Sub- Division, PHE Dte. (w.e.f. 01.08.2021 to 30.06.2022) ]Tender No 792/2022-2023 of EE/PD] | BP-2022-23-846 | 31/03/2023 | 0 | ANUDIP SAHA | 2.58 | 0 | 0 | 0
3071 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Operation & maintenance & water testing in the laboratory of Balarampur WTP Sub District Laboratory under RWS Purulia Sub-Division PHE Dte. (w.e.f. 01.07.2022 to 31.12.2022) [Tender No- 409/2022-23 of EE/PD] | BP-2023-24-51 | 19/04/2023 | 0 | SADHAN GORAIN | 2.59 | 0 | 0 | 0
3072 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | conduct a social awareness programmes Le SWACH SUJAL SHAKTI SAMMAN, WORLD WATER DAY, WORLD HEALTH DAY, SCHOOL AWARNESS PROGRAMMES, SAVE WATER PROGRAMMES, WORLD ENVIRONMENT DAY, VILLAGERS AWARNESS PROGRAMME as per the guidelines of JAL JEEVAN MISSION. We will be organising the programmes at several blocks. | BP-2023-24-370 | 10/08/2023 | 0 | M/S SAYAK BHATTACHARYA | 0.66 | 0 | 0 | 0
3073 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Bill paid for Laboratory testing. | BP-2023-24-306 | 18/07/2023 | 0 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.04 | 0 | 0 | 0
3074 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Bill paid for Calibration of equipment's for Laboratory purpose. | BP-2023-24-71 | 05/05/2023 | 0 | MEASURE & PRECISION ENGINEER | 0.35 | 0 | 0 | 0
3075 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Bill paid for RWS Purulia Sub-Division Laboratory Air conditioner repair MB-No.2200/PD, Page No.24 to 25 | BP-2023-24-365 | 09/08/2023 | 0 | BABA AMARNATH TRADERS | 0.1 | 0 | 0 | 0
3076 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Office stationary bill paid to NGO. | BP-2023-24-435 | 05/09/2023 | 0 | KETIKA CONSUMERS CO-OP STORES LTD | 0.34 | 0 | 0 | 0
3077 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Laboratory payment. | BP-2022-23-625 | 15/02/2023 | 0 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.04 | 0 | 0 | 0
3078 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Bonus bill paid for NGO Laboratory staffs against PFMS Vr No. BP-2022-23-574 to BP-2022-23-588; BP-2022-23-590 to BP-2022-23-600; BP-2022-23-602 to BP-2022-23-614 & BP-2022-23-618 & BP-2022-23-620 to BP-2022-23-624. | BP-2022-23-634 | 22/02/2023 | 0 | LABORATORY STAFFS | 2.21 | 0 | 0 | 0
3079 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory af Barabazar Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.02 | 297/PR | 23/06/2022 | 365 | BOSE CONSTRUCTION | 3.66 | 0 | 0 | 93
3080 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory of Santuri Sub-District Water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.07 | 302/PR | 23/06/2022 | 365 | ARUNALOY SCIENTIFIC HOUSE | 3.66 | 0 | 0 | 100
3081 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory of Sirkabad Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.08 | 303/PR | 23/06/2022 | 365 | BOSE CONSTRUCTION | 4.76 | 0 | 0 | 100
3082 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Hura Sub District Laboratory under under RWS Purulia Sub Division PHE Dte.(w.e.f.01.09.2022 to 30.06.2023). | 1354/PD | 31/08/2022 | 303 | SUPRIYA MAHANTI MISHRA | 4.81 | 0 | 0 | 100
3083 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Necessary Maintenance work of water testing in the laboratory at Hura WTP, Barabazar & Joypur Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.08.2023 to 31.07.2024). | 378/A/PR | 27/07/2023 | 366 | KABERI DUTTA | 0.96 | 0 | 0 | 100
3084 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Necessary Maintenance work of water testing in the laboratory at Manbazar-II Sub-District , Dist Lab & others water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.08.2023 to 31.07.2024). | 379/PR | 27/07/2023 | 366 | COMPUTER MEDIA | 0.96 | 0 | 0 | 100
3085 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Necessary Maintenance work of water testing in the laboratory at Jhalda-I, Sirkabad & Baghmundi Sub-District water testing Laboratory under RWS Purulia Sub-Division PHE Dte.(w.e.f.01.08.2023 to 31.07.2024). | 378/B/PR | 27/07/2023 | 366 | COMPUTER MEDIA | 0.96 | 0 | 0 | 100
3086 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Necessary Maintenance work of water testing in the laboratory at Santuri, Dubra & Cheliyama Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.08.2023 to 31.07.2024). | 379/A/PR | 27/07/2023 | 366 | COMPUTER MEDIA | 0.96 | 0 | 0 | 100
3087 | PURULIA | Purulia Division | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/14143 | Support-WQMSP | Necessary Maintenance work of water testing in the laboratory at Rghunathpur WTP,Kashipur & Raghunathpur Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.08.2023 to 31.07.2024). | 378/C/PR | 27/07/2023 | 366 | COMPUTER MEDIA | 0.96 | 0 | 0 | 100
3088 | PURULIA | Purulia Division | Infrastructure development of 4 nos. old NGO lab converted to PHED Sub District Lab and 4 Nos. Sub-District water testing lab located at Tribal Zone of Purulia District under Purulia Division, PHE Dte. in connection with NABL Recognition. , SM/17197 | Support-WQMSP | Renovation and Maintenance work of Balarampur Water Treatment Plant labrotary. | 906/PD | 07/05/2024 | 60 | SAW CONSTRUCTION | 2.99 | 0 | 0 | 0
3089 | PURULIA | Purulia Division | Infrastructure development of 4 nos. old NGO lab converted to PHED Sub District Lab and 4 Nos. Sub-District water testing lab located at Tribal Zone of Purulia District under Purulia Division, PHE Dte. in connection with NABL Recognition. , SM/17197 | Support-WQMSP | Renovation and Repairing including Electrical and Sanitary Plumbing works of Joypur Sub Distict Laboratoty for NABL Accreditation, Part-B | 835/PD | 26/06/2023 | 60 | M/S KHAN ENTERPRISE | 6.22 | 0 | 0 | 100
3090 | PURULIA | Purulia Division | Infrastructure development of 4 nos. old NGO lab converted to PHED Sub District Lab and 4 Nos. Sub-District water testing lab located at Tribal Zone of Purulia District under Purulia Division, PHE Dte. in connection with NABL Recognition. , SM/17197 | Support-WQMSP | Construction & Extension of additional building of Sirkabad sub district lab under Purulia R.W.S Subdivision under Purulia Division P.H.E. Dte. | 1899/PD | 04/10/2024 | 60 | KABERI DUTTA | 3.26 | 0 | 0 | 0
3091 | PURULIA | Purulia Division | Infrastructure development of 4 nos. old NGO lab converted to PHED Sub District Lab and 4 Nos. Sub-District water testing lab located at Tribal Zone of Purulia District under Purulia Division, PHE Dte. in connection with NABL Recognition. , SM/17197 | Support-WQMSP | Construction and extension of additional building of Shirkabad sub dist lab.Under Purulia R.W.S Sub-Division ubder Purulia Division P.H.E Dte. | 1898/PD | 04/10/2024 | 60 | KABERI DUTTA | 3.8 | 0 | 0 | 0
3092 | PURULIA | Purulia Division | Procurement of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance Programme related to Jal Jeevan Mission , SM/17411 | Support-WQMSP | Procurement of 1 no. of Mobile Laboratory Van (MLV) complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with OMAS instruments, devices, consumables, reagents, smart phone with preloaded water quality app synchronized with PHED water quality dashboard and safety gear for resource personnel for water quality testing in remote areas including external designing and painting for IEC propaganda complete with IEC audio visual aids as directed by EIC under Public Health Engineering Department, Govt. of West Bengal. | 1180/PD | 31/08/2023 | 579 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 75.86 | 0 | 0 | 80
3093 | PURULIA | Purulia Mechanical | Procurement of Computer and Peripherals for the office use in Purulia Mechanical Division and Sub-Division PHE Dte. and Office of the Assistant Chief Engineer Northern Zone PHE Dte. , SM/18738 | Support-MIS | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR OFFICE USE IN PURULIA MECHANICAL DIVISION AND SUB DIVISION P.H.E DTE. | BP-2024-25-35 | 02/07/2024 | 0 | IONET | 2.49 | 0 | 0 | 0
3094 | PURULIA | Purulia Mechanical | Procurement of Computer and Peripherals for the office use in Purulia Mechanical Division and Sub-Division PHE Dte. and Office of the Assistant Chief Engineer Northern Zone PHE Dte. , SM/18738 | Support-MIS | Procurement of computer and peripherals for office use in Purulia Mechanical Division & Sub-Division PHE Dte. | BP-2024-25-19 | 06/06/2024 | 0 | IONET | 13.06 | 0 | 0 | 0
3095 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory af Barabazar Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.02 | 297/PR | 23/06/2022 | 365 | BOSE CONSTRUCTION | 3.66 | 0 | 0 | 93
3096 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory of Sirkabad Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.08 | 303/PR | 23/06/2022 | 365 | BOSE CONSTRUCTION | 4.76 | 0 | 0 | 100
3097 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Hura Sub District Laboratory under under RWS Purulia Sub Division PHE Dte.(w.e.f.01.09.2022 to 30.06.2023). | 1354/PD | 31/08/2022 | 303 | SUPRIYA MAHANTI MISHRA | 4.81 | 0 | 0 | 100
3098 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory af Raghunathpur Sub-District Laboratory under RWS purulia Sub-Division PHE Dte. (w.e.f.01.10.2023 to 31.08.2024). | 1349/PD | 13/09/2023 | 336 | MANATOSH SINGH | 6.59 | 0 | 0 | 85
3099 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Bundwan block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June ) | 95/A/PR | 01/03/2024 | 92 | GOPAL CHANDRA MAHATO | 0.97 | 0 | 0 | 0
3100 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Puncha block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | 97/A/PR | 01/03/2024 | 92 | SRIBASH HAZRA | 0.97 | 0 | 0 | 0
3101 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Neturia block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months April to June) | 86/A/PR | 01/03/2024 | 92 | DIPAK MANDAL | 0.96 | 0 | 0 | 30
3102 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Joypur block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | 107/A/PR | 01/03/2024 | 92 | BIJAY GORAIN | 0.92 | 0 | 0 | 40
3103 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Santuri block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | 87/A/PR | 01/03/2024 | 92 | CHANDAN MONDAL | 0.77 | 0 | 0 | 30
3104 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Manbazar-I block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | 96/A/PR | 01/03/2024 | 92 | UTTAM KUMAR MAHATO | 0.97 | 0 | 0 | 42
3105 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Barabazar block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | 98/A/PR | 01/03/2024 | 92 | TAPAN MAHATO | 0.97 | 0 | 0 | 30
3106 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Balarampur block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | 99/A/PR | 01/03/2024 | 92 | BABLU MAHATO | 0.97 | 0 | 0 | 30
3107 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Jhalda-II block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to june) | 88/A/PR | 01/03/2024 | 92 | PRADIP MAHATO | 0.97 | 0 | 0 | 30
3108 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Para block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | 103/A/PR | 01/03/2024 | 92 | ROHIT BANERJEE | 0.97 | 0 | 0 | 30
3109 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Arsha block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | 90/A/PR | 01/03/2024 | 92 | SHAMBHU SEKHAR MAJHI | 0.97 | 0 | 0 | 30
3110 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Raghunathpur-I block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June ) | 101/A/PR | 01/03/2024 | 92 | NISHAN KUMAR DAS | 0.89 | 0 | 0 | 30
3111 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Raghunathpur-II block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | 104/A/PR | 01/03/2024 | 92 | SANGRAM MUKHERJEE | 0.87 | 0 | 0 | 30
3112 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Kashipur block of Purulia District under Purulia Division P. H.E. Dte.( For 1month, April) | 100/A/PR | 01/03/2024 | 31 | PANKAJ MANDAL | 0.76 | 0 | 0 | 74
3113 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Jhalda-I block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | 89/A/PR | 01/03/2024 | 92 | UMESH KUMAR MAHATO | 0.97 | 0 | 0 | 15
3114 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Manbazar-II block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | 92/A/PR | 01/01/2024 | 91 | HEMANTA MAHATA | 0.97 | 0 | 0 | 0
3115 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Baghmundi block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | 91/A/PR | 01/03/2024 | 92 | NIBARAN KUMAR | 0.97 | 0 | 0 | 30
3116 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Water sample collection charges by engagement of agency at Hura block of Purulia District under Purulia Division P. H.E. Dte. ( For 3 months, April to June) | 106/A/PR | 01/03/2024 | 92 | MILAN MAHATO | 0.97 | 0 | 0 | 52
3117 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Cheliyama Sub-District Laboratory under RWS Purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.03 | 298/PR | 23/06/2022 | 12 | ARUNALOY SCIENTIFIC HOUSE | 3.66 | 0 | 0 | 100
3118 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Dubra Sub-District Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.07.2022 to 30.06.2023). SL NO.04 | 299/PR | 07/06/2022 | 365 | ARUNALOY SCIENTIFIC HOUSE | 3.66 | 0 | 0 | 100
3119 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory af Balarampur WTP Sub-District Laboratory under RWS purulia Sub-Division PHE Dte.(w.e.f.01.02.2023 to 31.12.2023). | 171/PD | 07/02/2023 | 334 | SADHAN GORAIN | 7 | 0 | 0 | 100
3120 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory af Bundwan WTP Sub District Laboratory under RWS purulia Sub-Division, PHE Dte.(w.e.f.01.02.2023 to 31.12.2023). | 187/PD | 07/02/2023 | 334 | ARUNALOY SCIENTIFIC HOUSE | 7 | 0 | 0 | 100
3121 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Daily operation & Maintenance and water testing in the laboratory activities of Purulia District Water testing Laboratory at PHE Office Campus,Ranchi Road under Purulia Division, PHE Dte. [For 11 (Eleven) months]. | 244/PD | 20/02/2023 | 334 | ARUNALOY SCIENTIFIC HOUSE | 9.82 | 0 | 0 | 100
3122 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Supply & Installation of Sign Board for Place identification of 7nos of Laboratory Sites within Purulia District under RWS Purulia Sub-Division,Under Purulia Division PHE Dte (Part-A) | 100/PR | 28/02/2023 | 30 | COMPUTER MEDIA | 0.92 | 0 | 0 | 100
3123 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Supply & Installation of Sign Board for Place identification of 7nos of Laboratory Sites within Purulia District under RWS Purulia Sub-Division,Under Purulia Division PHE Dte (Part-B) | 101/PR | 28/02/2023 | 30 | COMPUTER MEDIA | 0.92 | 0 | 0 | 100
3124 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory af Jhalda WTP Sub-Dist Laboratory under RWS purulia Sub-Division PHE Dte (w.e.f.01.02.2023 to 31.12.2023). | 172/PD | 07/02/2023 | 334 | ANUP KUMAR SAHA | 7 | 0 | 0 | 100
3125 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Supply & fitting & fixing Glowsine board at Division office of Purulia Division PHE Dte. (2 nos Purulia District laboratory &Jhalda-II SDL,Manbazar -II SDL) SL NO.04 | 94/PR | 28/02/2023 | 30 | COMPUTER MEDIA | 0.66 | 0 | 0 | 100
3126 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Cheliyama Sub-District Laboratory under RWS purulia Sub-Division PHE Dte. (w.e.f.01.07.2023 to 30.06.2024). | 858/PD | 30/06/2023 | 365 | ARUNALOY SCIENTIFIC HOUSE | 5.27 | 0 | 0 | 100
3127 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Jhalda-I Sub District Laboratory under under RWS Purulia Sub Division PHE Dte. (w.e.f.01.07.2023 to 30.06.2024). | 860/PD | 30/06/2023 | 365 | KOUSHIK CHATTERJEE | 8.28 | 0 | 0 | 80
3128 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Kashipur Sub District Laboratory under under RWS Purulia Sub Division PHE Dte. (w.e.f.01.07.2023 to 30.06.2024). | 862/PD | 30/06/2023 | 365 | ANUDIP SAHA | 8.29 | 0 | 0 | 100
3129 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Joypur Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte. . (w.e.f.01.07.2023 to 30.06.2024). | 861/Pd | 30/06/2023 | 365 | TUSHAR KANTI GORAI | 5.26 | 0 | 0 | 53
3130 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Dubra Sub-District Laboratory under RWS purulia Sub-Division PHE Dte. . (w.e.f.01.07.2023 to 30.06.2024). | 859/PD | 30/06/2023 | 365 | ARUNALOY SCIENTIFIC HOUSE | 5.27 | 0 | 0 | 65
3131 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Santuri Sub-District Water testing Laboratory under RWS purulia Sub-Division PHE Dte. (w.e.f.01.07.2023 to 30.06.2024). | 865/PD | 30/06/2023 | 365 | ARUNALOY SCIENTIFIC HOUSE | 5.27 | 0 | 0 | 60
3132 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Sirkabad Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte. (w.e.f.01.07.2023 to 30.06.2024). | 866/PD | 30/06/2023 | 365 | SK ABBAS | 6.97 | 0 | 0 | 100
3133 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS Purulia Sub-Division PHE Dte.(w.e.f.01.09.2023 to 31.12.2023) | 476/A/23 | 31/08/2023 | 122 | COMPUTER MEDIA | 0.87 | 0 | 0 | 100
3134 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Continuation order for the work of "Supply of Laboratory reagent/media/consumables required for routine water testing of different laboratories under Purulia Division, PHE Dte. ( For 2 months)" | 1697/PD | 29/11/2023 | 15 | ARUNALOY SCIENTIFIC HOUSE | 18.27 | 0 | 0 | 100
3135 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Civil & Electrical Part related to NABL Recognition of Baghmundi Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | 1837/PD | 12/12/2023 | 120 | VIVEKANANDA CONSTRUCTION | 5.9 | 0 | 0 | 100
3136 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Civil & Electrical Part related to NABL Recognition of Manbaazar-II Sub-District Laboratory as per ISO/IEC 17025:2017 Related to Support Activities Under Jal Jeevan Mission. | 1838/PD | 12/12/2023 | 60 | SATWICK ENTERPRISE | 1.69 | 0 | 0 | 100
3137 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Supply delivery fitting & fixing of sign board (ACP Sheet) at 12 nos site within Purulia District under RWS Purulia Sub-Division PHE Dte.( Part-E) | 99/PR | 28/02/2023 | 30 | COMPUTER MEDIA | 0.77 | 0 | 0 | 100
3138 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Monthly Remunaration bill paid for F.Y:2022-23 for 47 nos. staffs per head Rs.5300/-. |  | 25/04/2024 | 0 | LABORATORY STAFFS | 2.49 | 0 | 0 | 0
3139 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Bonus bill paid for F.Y:2022-23 for 47 nos. staffs per head Rs.5300/-. | BP2024-25-38/39 | 04/05/2024 | 0 | LABORATORY STAFFS | 2.49 | 0 | 0 | 0
3140 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Honorarium payment for School & AWC Centre of water test, | BP-2024-25-124 | 30/05/2024 | 0 | LABORATORY STAFFS | 0.3 | 0 | 0 | 0
3141 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Ad-hoc Bonus 2023-24 bill payment for the Laboratory 52 nos. @ Rs.6000/- staffs. | BP-2024-25-522 | 29/10/2024 | 0 | LABORATORY STAFFS | 3.12 | 0 | 0 | 0
3142 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Raghunathpur W.T.P. Sub District laboratory under RWS purulia Sub-Division PHE Dte. (w.e.f.01.07.2023 to 30.06.2024). | 864/PD | 30/06/2023 | 365 | ANUP KUMAR SAHA | 8.21 | 0 | 0 | 100
3143 | PURULIA | Purulia Division | Operational Charges of PHED Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19090 | Support-WQMSP | Operation & Maintenance and water testing in the laboratory at Barabazar Sub-District water testing Laboratory under RWS purulia Sub-Division PHE Dte. (w.e.f.01.07.2023 to 30.06.2024). | 857/PD | 30/06/2023 | 365 | BOSE CONSTRUCTION | 5.26 | 0 | 0 | 100
Total | [9 empty] | 236401.01 | 709.02 | 0.3